## sub
Submittal Report - All
PROJECT: | Seattle Center Arena
MANAGER: | Kurt Amundsen
PREPARED BY: | Chris Minter
DATE: | 2021-10-07
ID | Spec Section | Subject | Status | Discipline | From | Received | Last Action | Contract | Forwarded To | Review Due Back | Due Back From | Current Reviewer | Due Date | Response Date | Total Days | Keywords | Related Items | Related Project Items | Review Days | Expected Date | Closed Date
|  | Loading Dock Seals and Shelters - O&M Manuals | Pending |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-10-07 12:19 | Pending Receipt - For Review | [7 empty] | 1 |  | Record Copies; Transfers; Submittals |  | -1
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
|  | Pending Receipt | For Review | 2021-10-07 12:19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) |  | Submittal Number: 11 13 16-6.0 From: CHRISTIAN ALBERS Final Due Date: 10/21/21 Subject: LOADING DOCK SEALS AND SHELTERS - O&M MANUALS Description: SEE ATTACHED LOADING DOCK SEALS AND SHELTERS - O&M MANUALS. Spec Section: 11 13 16 - LOADING DOCK SEALS AND SHELTERS Status: OPEN | Info Exchange
|  | Stationary Loading Dock Equipment - O&M Manuals - Dock Levelers + Dock Locks | Pending |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-10-07 12:34 | Pending Receipt - For Review | [7 empty] | 1 |  | Record Copies; Transfers; Submittals |  | -1
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
|  | Pending Receipt | For Review | 2021-10-07 12:34 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) |  | Submittal Number: 11 13 19-12.0 From: CHRISTIAN ALBERS Final Due Date: 10/21/21 Subject: STATIONARY LOADING DOCK EQUIPMENT - O&M MANUALS - DOCK LEVELERS + DOCK LOCKS Description: SEE ATTACHED STATIONARY LOADING DOCK EQUIPMENT - O&M MANUALS - DOCK LEVELERS + DOCK LOCKS. Spec Section: 11 13 19 - STATIONARY LOADING DOCK EQUIPMENT Status: OPEN | Info Exchange
01 33 00-002-00 | 01 33 00 - SUBMITTAL PROCEDURES | 01 33 00-002-00 Submittal Schedule - 1.20.20 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-21 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-04 | 2020-01-28 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-01-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04001 | Received | For Review | 2020-01-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Josh Dobken (Populous); Populous SCA_CCA | 2020-02-04 | Submittal Number: 01 33 00-2.0 From: GREG GOEBEL Final Due Date: 02/03/20 Subject: SUBMITTAL SCHEDULE - 1.20.20 Description: Spec Section: 01 33 00 - SUBMITTAL PROCEDURES Status: OPEN | Info Exchange
| 05583 | Forwarded | For Review | 2020-01-21 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-01-28 | Submittal Number: 01 33 00-2.0 From: GREG GOEBEL Final Due Date: 02/03/20 Subject: SUBMITTAL SCHEDULE - 1.20.20 Description: Spec Section: 01 33 00 - SUBMITTAL PROCEDURES Status: OPEN | Info Exchange
| 05702 | Responded and Closed | No Action Taken or Required | 2020-01-28 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Greg Goebel (Mortenson Construction) |  | Received for record | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-21 |  | Open Submittal Schedule - 1.20.20.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-21 |  | Open Submittal Schedule - 1.20.20.xlsx
01 33 00-003-00 | 01 33 00 - SUBMITTAL PROCEDURES | 01 33 00-003-00 Submittal Schedule - 3.23.20 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-29 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-13 | 2020-04-28 | -1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05611 | Received | For Review | 2020-04-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-13 | Submittal Number: 01 33 00-3.0 From: GREG GOEBEL Final Due Date: 05/06/20 Subject: SUBMITTAL SCHEDULE - 3.23.20 Description: PDF & EXCEL REPORT OF PROCORE SUBMITTAL REGISTRAR. ALSO, INCLUDING LEJEUNE STRUCTURAL STEEL SUBMITTAL SCHEDULE TO COMPLETION. Spec Section: 01 33 00 - SUBMITTAL PROCEDURES Status: OPEN | Info Exchange
| 07603 | Forwarded | For Review | 2020-04-28 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-05-05 | Submittal Number: 01 33 00-3.0 From: GREG GOEBEL Final Due Date: 05/06/20 Subject: SUBMITTAL SCHEDULE - 3.23.20 Description: PDF & EXCEL REPORT OF PROCORE SUBMITTAL REGISTRAR. ALSO, INCLUDING LEJEUNE STRUCTURAL STEEL SUBMITTAL SCHEDULE TO COMPLETION. Spec Section: 01 33 00 - SUBMITTAL PROCEDURES Status: OPEN | Info Exchange
| 07606 | Responded and Closed | No Action Taken or Required | 2020-04-28 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Greg Goebel (M.A. Mortenson Company) |  | Received for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-28 |  | Open Submittal Schedule - 3.23.20.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-28 |  | Open Submittal Schedule - 3.23.20.xlsx
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-28 |  | 03.17 Structural Steel Submittal Log.pdf
01 50 00-008-00 | 01 50 00 - TEMPORARY FACILITIES AND CONTROLS | 01 50 00-008-00 Temporary Access Road | Closed | Architectural | Domingo Sampayo (Mortenson Construction) | 2019-05-13 | Responded and Closed - No Action Taken or Required |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-05-27 | 2019-05-22 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-05-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01313 | Received | For Review | 2019-05-13 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-27 |  | Email
| 02290 | Forwarded | For Review | 2019-05-13 | SCA_CCA@populous.com | Tom Usher (Populous); Josh Dobken (Populous) | 2019-05-20 |  | Info Exchange
| 01365 | Review Response | No Action Taken or Required | 2019-05-22 | Josh Dobken (Populous) | SCA_CCA@populous.com |  | Received for record only | Info Exchange
| 02352 | Responded and Closed | No Action Taken or Required | 2019-05-22 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (No Action Taken or Required) from: Josh Dobken (Populous) Remarks: Received for record only | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-05-13 |  | 01 50 00-008-00 Temporary Access Road.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-13 |  | 01 50 00-008-00 Temporary Access Road.pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2019-05-22 02:00 |  | 01 50 00-008-00 Temporary Access Road_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-12 02:00 |  | 01 50 00-008-00 Temporary Access Road.pdf
01 56 39-001-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-001-00 Temp Tree Protection Plan | Closed | Landscape | Josh Broussard (Mortenson Construction) | 2019-02-27 | Responded and Closed - Revise and Resubmit | [5 empty] | 2019-03-13 | 2019-02-28 | 2 |  | Record Copies; Submittals |  | -1 |  | 2019-02-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 00973 | Received | For Review | 2019-02-27 | Josh Broussard (Mortenson Construction) | SCA_CCA@populous.com | 2019-03-13 |  | Email
| 01809 | Responded and Closed | Revise and Resubmit | 2019-02-28 | SCA_CCA@populous.com | Brent Leiter (Mortenson Construction); Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction); Josh Broussard (Mortenson Construction) |  | Please review our specification section 01 33 00 outlining proper format and resubmit. Some divisions will have further requirements for submission per their related specification sections. Josh Dobken on 2/28/2019 at 5:39 PM CST | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Josh Broussard (Mortenson Construction) | 1 | 2019-02-26 |  | 01 56 39-001-0 Temp Tree Protection Plan.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-02-26 |  | 01 56 39-001-0 Temp Tree Protection Plan.pdf
01 56 39-001-01 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-001-01 Temp Tree Protection Plan Rev 1 | Closed | Landscape | Josh Broussard (Mortenson Construction) | 2019-03-01 | Responded and Closed - Revise and Resubmit |  | Rhys Van Bemmel (Swift Company, LLC), Gareth Loveridge (Swift and Company) |  |  |  | 2019-03-15 | 2019-03-13 | 13 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-03-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01000 | Received | For Review | 2019-03-01 | Josh Broussard (Mortenson Construction) | SCA_CCA@populous.com | 2019-03-15 |  | Email
| 01820 | Forwarded | For Review | 2019-03-04 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift Company, LLC); Gareth Loveridge (Swift and Company) | 2019-03-11 | Gareth / Rhys - Please find attached submittal outlining tree protection plan. The original needed to be revised and resubmitted (it did not include a transmittal with their stamp). See note from Mortenson below: This revision includes proper reviewer stamp page and Mortenson review stamp. See attached tree protection plan as derived from the contract documents and reference standards. Note that protection installation will commence on or before March 4th in order to prepare for demolition activities. | Info Exchange
| 01045 | Review Response | Revise and Resubmit | 2019-03-13 | Rhys Van Bemmel (Swift Company, LLC) | SCA_CCA@populous.com |  | See attached for submittal 01 53 39-001-1 response. | Info Exchange
| 01894 | Responded and Closed | Revise and Resubmit | 2019-03-13 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Josh Broussard (Mortenson Construction) |  | Response (Revise and Resubmit) from: Rhys Van Bemmel (Swift Company, LLC) Remarks: See attached for submittal 01 53 39-001-1 response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Josh Broussard (Mortenson Construction) | 1 | 2019-03-01 |  | 01 56 39-001-1 Temp Tree Protection Plan Rev 1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-01 |  | 01 56 39-001-1 Temp Tree Protection Plan Rev 1.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-03-13 |  | 01 56 39-001-1 Temp Tree Protection Plan Rev 1-SWIFT- POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-03-01 |  | 01 56 39-001-1 Temp Tree Protection Plan Rev 1.pdf
01 56 39-001-02 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-001-02 Temp Tree Protection Plan Rev 2 | Closed | Landscape | Josh Broussard (Mortenson Construction) | 2019-03-18 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-04-01 | 2019-03-20 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-03-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01059 | Received | For Review | 2019-03-18 | Josh Broussard (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-01 |  | Email
| 01920 | Forwarded | For Review | 2019-03-18 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-03-25 | See attached tree protection plan updated per the Rev 1 review comments. | Info Exchange
| 01070 | Review Response | Approved as Noted | 2019-03-20 | Gareth Loveridge (Swift and Company Landscape Arch) | SCA_CCA@populous.com |  | Attached is the response to the revised submittal. See the note for the work outside of the sound wall. | Info Exchange
| 01934 | Responded and Closed | Approved as Noted | 2019-03-20 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Josh Broussard (Mortenson Construction) |  | Response (Approved as Noted) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: Attached is the response to the revised submittal. See the note for the work outside of the sound wall. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Josh Broussard (Mortenson Construction) | 1 | 2019-03-18 |  | 01 56 39-001-2 Temp Tree Protection Plan Rev 2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-18 |  | 01 56 39-001-2 Temp Tree Protection Plan Rev 2.pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2019-03-20 |  | 01 56 39-001-2 Temp Tree Protection Plan Rev 2-SWIFT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-03-18 |  | 01 56 39-001-2 Temp Tree Protection Plan Rev 2.pdf
01 56 39-001-03 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-001-03 Temp Tree Protection Plan | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-04-18 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-05-02 | 2019-04-30 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-04-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01196 | Received | For Review | 2019-04-18 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-02 |  | Email
| 02111 | Forwarded | For Review | 2019-04-18 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-04-25 |  | Info Exchange
| 01246 | Review Response | Approved as Noted | 2019-04-30 | Rhys Van Bemmel (Swift and Company Landscape Arch) | SCA_CCA@populous.com |  | Attached is Swift's response | Email
| 02202 | Responded and Closed | Approved as Noted | 2019-04-30 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is Swift's response | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-18 |  | 01 56 39-001-03 Temp Tree Protection Plan.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-18 |  | 01 56 39-001-03 Temp Tree Protection Plan.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-04-30 |  | 01 56 39-001-03 Temp Tree Protection Plan-SWIFT-2019-04-30.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 01 56 39-001-03 Temp Tree Protection Plan-SWIFT-2019-04-30_POP.pdf
01 56 39-002-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-002-00 Qualifications of Project Arborist | Closed | Landscape | Josh Broussard (Mortenson Construction) | 2019-02-27 | Responded and Closed - Revise and Resubmit | [5 empty] | 2019-03-13 | 2019-02-28 | 2 |  | Record Copies; Submittals |  | -1 |  | 2019-02-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 00981 | Received | For Review | 2019-02-27 | Josh Broussard (Mortenson Construction) | SCA_CCA@populous.com | 2019-03-13 |  | Email
| 01810 | Responded and Closed | Revise and Resubmit | 2019-02-28 | SCA_CCA@populous.com | Brent Leiter (Mortenson Construction); Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction); Josh Broussard (Mortenson Construction) |  | Please review our specification section 01 33 00 outlining proper format and resubmit. Some divisions will have further requirements for submission per their related specification sections. Josh Dobken on 2/28/2019 at 5:42 PM CST | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Josh Broussard (Mortenson Construction) | 1 | 2019-02-27 |  | 01 56 39-002-0 Qualifications of Project Arborist.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-02-27 |  | 01 56 39-002-0 Qualifications of Project Arborist.pdf
01 56 39-002-01 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-002-01 Qualifications of Project Arborist Rev 1 | Closed | Landscape | Josh Broussard (Mortenson Construction) | 2019-03-01 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-03-15 | 2019-03-11 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-03-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01001 | Received | For Review | 2019-03-01 | Josh Broussard (Mortenson Construction) | SCA_CCA@populous.com | 2019-03-15 |  | Email
| 01821 | Forwarded | For Review | 2019-03-04 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift Company, LLC); Gareth Loveridge (Swift and Company) | 2019-03-11 | Gareth/ Rhys See attached submittal for Project Arborist qualifications. Original submittal was sent back as a revise and resubmit (Mortenson didn't include a stamp or transmittal sheet). | Info Exchange
| 01876 | Responded and Closed | Approved | 2019-03-11 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Josh Broussard (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Josh Broussard (Mortenson Construction) | 1 | 2019-03-01 |  | 01 56 39-002-1 Qualifications of Project Arborist Rev 1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-01 |  | 01 56 39-002-1 Qualifications of Project Arborist Rev 1.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-03-11 02:00 |  | 01 56 39-002-1 Qualifications of Project Arborist Rev 1-SWIFT POP.pdf
01 56 39-003-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-003-00 Arborist Photo Documentation & Appraisal | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-03-11 | Responded and Closed - Revise and Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-03-25 | 2019-03-13 | 3 |  | Record Copies; Transfers; Submittals | 01 56 39-003-01 - 01 56 39-003-01 Arborist Photo Documentation & Appraisal | 2 |  | 2019-03-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01039 | Received | For Review | 2019-03-11 | Domingo Sampayo (Mortenson Construction) | Josh Dobken (Populous) | 2019-03-25 |  | Info Exchange
| 01887 | Forwarded | For Review | 2019-03-12 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift Company, LLC); Gareth Loveridge (Swift and Company) | 2019-03-19 | Please find attached Submittal - I'm putting this one through to you and will add Mortenson's stamp page as soon as they get that to us. | Info Exchange
| 01890 | Forwarded | For Review | 2019-03-13 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift Company, LLC); Gareth Loveridge (Swift and Company) | 2019-03-20 | Attached is 01 56 39-003-0 with Mortenson's stamp page. Please review this pdf. | Info Exchange
| 01046 | Review Response | Revise and Resubmit | 2019-03-13 | Rhys Van Bemmel (Swift Company, LLC) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal 01 56 39-003-0 response from Swift. | Info Exchange
| 01895 | Responded and Closed | Revise and Resubmit | 2019-03-13 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Revise and Resubmit) from: Rhys Van Bemmel (Swift Company, LLC) Remarks: Please see the attached submittal 01 56 39-003-0 response from Swift. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-03-12 |  | 01 56 39-003-0 Arborist Photo Documentation & Appraisal.pdf
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-03-12 |  | Transmittal.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-03-12 |  | 01 56 39-003-0 Arborist Photo Documentation & Appraisal.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-03-12 |  | Transmittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-03-12 |  | 01 56 39-003-0 Arborist Photo Documentation & Appraisal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-03-12 |  | Transmittal.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-03-13 |  | 01 56 39-3 Rev 0 Arborist Photo Doc Appraisal - SWIFT POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-03-12 |  | 01 56 39-003-0 Arborist Photo Documentation & Appraisal.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-03-12 |  | Transmittal.pdf
01 56 39-003-01 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-003-01 Arborist Photo Documentation & Appraisal | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-03-29 | Responded and Closed - Approved as Noted/Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-04-15 | 2019-04-15 | 18 |  | Record Copies; Transfers; Submittals | 01 56 39-003-00 - 01 56 39-003-00 Arborist Photo Documentation & Appraisal | 18 | 2019-03-27 | 2019-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01110 | Received | For Review | 2019-03-29 | Domingo Sampayo (Mortenson Construction) | Josh Dobken (Populous) | 2019-04-15 | Revised submittal includes photo documentation and data in tree table of 27 additional trees: sweetgums (26) and tree #9354 in the north courtyard. | Info Exchange
| 01976 | Forwarded | For Review | 2019-03-29 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-04-05 | Revised submittal includes photo documentation and data in tree table of 27 additional trees: sweetgums (26) and tree #9354 in the north courtyard. | Info Exchange
| 01177 | Review Response | Approved as Noted/Resubmit | 2019-04-15 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | Please find the attached submittal response for submittal 01 56 393 Revision 1. | Info Exchange
| 02084 | Responded and Closed | Approved as Noted/Resubmit | 2019-04-15 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Please find the attached submittal response for submittal 01 56 393 Revision 1. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-03-29 |  | 01 56 39-3 Rev1 Arborist Photo Doc & Appraisal (2).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-03-29 |  | 01 56 39-3 Rev1 Arborist Photo Doc & Appraisal (2).pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-04-15 |  | 01 56 39-3 Rev1 Arborist Photo Doc & Appraisal-SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-04-15 |  | 01 56 39-3 Rev1 Arborist Photo Doc & Appraisal-SWIFT_POP.pdf
01 56 39-003-02 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-003-02 Arborist Photo Doc & Appraisal | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-04-23 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-05-13 | 2019-05-09 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2019-05-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01207 | Received | For Review | 2019-04-23 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-13 |  | Email
| 02141 | Forwarded | For Review | 2019-04-23 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-04-30 |  | Info Exchange
| 02261 | Forwarded | For Review | 2019-05-08 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-05-13 | Please find updated submittal attachment for corrected information. | Info Exchange
| 01296 | Review Response | Approved as Noted | 2019-05-09 | Rhys Van Bemmel (Swift and Company Landscape Arch) | SCA_CCA@populous.com |  |  | Info Exchange
| 02270 | Responded and Closed | Approved as Noted | 2019-05-09 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-18 |  | 01 56 39-001-03 Temp Tree Protection Plan.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-18 |  | 01 56 39-001-03 Temp Tree Protection Plan.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-18 |  | 01 56 39-001-03 Temp Tree Protection Plan.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-05-08 |  | 01 56 39-003-02 Arborist Photo Doc & Appraisal - SWIFT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-09 |  | 01 56 39-003-02 Arborist Photo Doc & Appraisal - SWIFT_POP.pdf
01 56 39-004-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-004-00 Compliance Report - 03182019 | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-03-18 | Responded and Closed - No Action Taken or Required |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-04-02 | 2019-03-22 | 5 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2019-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01063 | Received | For Review | 2019-03-18 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-02 |  | Email
| 01925 | Forwarded | For Review | 2019-03-19 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-03-26 |  | Info Exchange
| 01082 | Review Response | No Action Taken or Required | 2019-03-22 | Gareth Loveridge (Swift and Company Landscape Arch) | SCA_CCA@populous.com |  | Attached is the review of the tree protection compliance report. | Info Exchange
| 01946 | Responded and Closed | No Action Taken or Required | 2019-03-22 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (No Action Taken or Required) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: Attached is the review of the tree protection compliance report. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-03-19 |  | 01 56 39-004-0 Compliance Report - 03182019.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-19 |  | 01 56 39-004-0 Compliance Report - 03182019.pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2019-03-22 |  | 01 56 39-004-0 Compliance Report - 03182019-SWIFT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-03-19 |  | 01 56 39-004-0 Compliance Report - 03182019.pdf
01 56 39-005-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-005-00 Temporary Tree Protection Labels | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-03-20 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-04-03 | 2019-03-20 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-03-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01068 | Received | For Review | 2019-03-20 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-03 |  | Email
| 01930 | Forwarded | For Review | 2019-03-20 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-03-27 | Tree labels including tree tag numbers located on the trees. Note that the tree labels will be adjusted per tree name and value. They will be printed on 11x17 on fluorescent yellow or green paper per specs. | Info Exchange
| 01933 | Responded and Closed | Approved as Noted | 2019-03-20 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Attached is the approved submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-03-20 |  | 01 56 39-005-0 Temporary Tree Protection Labels.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-20 |  | 01 56 39-005-0 Temporary Tree Protection Labels.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-03-20 |  | 01 56 39-005-0 Temporary Tree Protection Labels-SWIFT_POP.pdf
01 56 39-006-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-006-00 Arborist Compliance Report - 03292019 | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-04-01 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-04-15 | 2019-04-15 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01115 | Received | For Review | 2019-04-01 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-15 |  | Email
| 01985 | Forwarded | For Review | 2019-04-01 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-04-08 | Arborist compliance report summarizing activities related to tree protection and work within critical root zones from 3/18/19 to 3/29/19. | Info Exchange
| 01178 | Review Response | Approved as Noted | 2019-04-15 | Rhys Van Bemmel (Swift and Company Landscape Arch) | SCA_CCA@populous.com |  | Please find the attached response to submittal 01 56 39-6. | Info Exchange
| 02085 | Responded and Closed | Approved as Noted | 2019-04-15 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Please find the attached response to submittal 01 56 39-6. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-01 |  | 01 56 39-006-0 Arborist Compliance Report.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-01 |  | 01 56 39-006-0 Arborist Compliance Report.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-04-15 |  | 01 56 39-006-0 Arborist Compliance Report-SWIFT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-15 |  | 01 56 39-006-0 Arborist Compliance Report-SWIFT_POP.pdf
01 56 39-007-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-007-0 Arborist Compliance Report - 04122019 | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-04-15 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-04-29 | 2019-04-15 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01174 | Received | For Review | 2019-04-15 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-29 |  | Email
| 02078 | Forwarded | For Review | 2019-04-15 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-04-22 |  | Info Exchange
| 01179 | Review Response | Approved as Noted | 2019-04-15 | Rhys Van Bemmel (Swift and Company Landscape Arch) | SCA_CCA@populous.com |  | Please find the attached response to submittal 01 56 39-7. | Info Exchange
| 02086 | Responded and Closed | Approved as Noted | 2019-04-15 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Please find the attached response to submittal 01 56 39-7. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-15 |  | 01 56 39-007-0 Arborist Compliance Report - 04122019.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-15 |  | 01 56 39-007-0 Arborist Compliance Report - 04122019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-04-15 |  | 01 56 39-007-0 Arborist Compliance Report - 04122019-SWIFT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-15 |  | 01 56 39-007-0 Arborist Compliance Report - 04122019-SWIFT_POP.pdf
01 56 39-008-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-008-00 Arborist Compliance Report - 04262019 | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-04-29 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-05-13 | 2019-05-10 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01233 | Received | For Review | 2019-04-29 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-13 |  | Email
| 02180 | Forwarded | For Review | 2019-04-29 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-05-06 |  | Info Exchange
| 01311 | Review Response | Approved as Noted | 2019-05-10 | Rhys Van Bemmel (Swift and Company Landscape Arch) | SCA_CCA@populous.com |  | Attached is Swift’s response to submittal 01 56 39-008-00 Arborist Compliance Report. | Info Exchange
| 02287 | Responded and Closed | Approved as Noted | 2019-05-10 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is Swift’s response to submittal 01 56 39-008-00 Arborist Compliance Report. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-29 |  | 01 56 39-008-00 Arborist Compliance Report - 04262019.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-29 |  | 01 56 39-008-00 Arborist Compliance Report - 04262019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-05-10 |  | 01 56 39-008-00 Arborist Compliance Report - 04262019 - SWIFT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-10 |  | 01 56 39-008-00 Arborist Compliance Report - 04262019 - SWIFT_POP.pdf
01 56 39-009-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-009-00 Arborist Comp Report - 05102019 | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-05-14 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-05-28 | 2019-05-29 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-05-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01321 | Received | For Review | 2019-05-14 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-28 |  | Email
| 02306 | Forwarded | For Review | 2019-05-14 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-05-21 |  | Info Exchange
| 01390 | Review Response | Approved as Noted | 2019-05-29 | Rhys Van Bemmel (Swift and Company Landscape Arch) | SCA_CCA@populous.com |  |  | Info Exchange
| 02390 | Responded and Closed | Approved as Noted | 2019-05-29 | SCA_CCA@populous.com | Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-05-14 |  | 01 56 39-009-00 Arborist Comp Report - 05102019.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-14 |  | 01 56 39-009-00 Arborist Comp Report - 05102019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-05-29 |  | 01 56 39-009-00 Arborist Comp Report - 05102019-SWIFT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-29 |  | 01 56 39-009-00 Arborist Comp Report - 05102019-SWIFT_POP.pdf
01 56 39-010-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-010-00: Arborist Compliance Report - 05242019 | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-05-28 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-06-11 | 2019-06-11 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-06-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01419 | Received | For Review | 2019-05-28 | Domingo Sampayo (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-11 |  | Info Exchange
| 02421 | Forwarded | For Review | 2019-06-03 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-06-10 |  | Info Exchange
| 01491 | Review Response | Approved as Noted | 2019-06-11 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | Swift’s response is to this submittal is attached. | Info Exchange
| 02508 | Responded and Closed | Approved as Noted | 2019-06-11 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Swift’s response is to this submittal is attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-06-03 |  | 01 56 39-10 Arborist Compliance Report - 05242019.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-03 |  | 01 56 39-10 Arborist Compliance Report - 05242019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-06-11 |  | 01 56 39-10 Arborist Compliance Report - 05242019 - Swift.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-11 |  | 01 56 39-10 Arborist Compliance Report - 05242019 - Swift_POP.pdf
01 56 39-011-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-011-00: Watering Schedule for Temp Watering | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-06-04 | Responded and Closed - Approved as Noted/Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-06-18 | 2019-06-12 | 9 |  | Record Copies; Transfers; Submittals | 01 56 39-011-01 - 01 56 39-011-01 Watering Schedule for Temp Watering | 9 |  | 2019-06-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01435 | Received | For Review | 2019-06-04 | Domingo Sampayo (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-18 | 1. Watering to start in early June. 2. Day of the week to conduct the watering will be determined on site with arborist. | Info Exchange
| 02438 | Forwarded | For Review | 2019-06-04 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-06-11 | 1. Watering to start in early June. 2. Day of the week to conduct the watering will be determined on site with arborist. | Info Exchange
| 01502 | Review Response | Approved as Noted/Resubmit | 2019-06-12 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | Attached is Swift’s response to submittal 01 56 39-011-00. | Info Exchange
| 02520 | Responded and Closed | Approved as Noted/Resubmit | 2019-06-12 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is Swift’s response to submittal 01 56 39-011-00. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-06-04 |  | 01 56 39-011-00 Watering Schedule for Temp Watering.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-04 |  | 01 56 39-011-00 Watering Schedule for Temp Watering.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-06-12 |  | 01 56 39-011-00 Watering Schedule for Temp Watering - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-12 |  | 01 56 39-011-00 Watering Schedule for Temp Watering - SWIFT_POP.pdf
01 56 39-011-01 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-011-01 Watering Schedule for Temp Watering | Closed | Landscape | Domingo Sampayo (Mortenson Construction) | 2019-06-17 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-07-01 | 2019-06-27 | 11 |  | Record Copies; Transfers; Submittals | 01 56 39-011-00 - 01 56 39-011-00: Watering Schedule for Temp Watering | 9 | 2019-06-26 | 2019-06-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01562 | Received | For Review | 2019-06-17 | Domingo Sampayo (Mortenson Construction) | Shaina Burris (Populous) | 2019-07-01 |  | Email
| 02590 | Forwarded | For Review | 2019-06-19 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-06-26 |  | Info Exchange
| 01635 | Review Response | Approved | 2019-06-27 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Attached is our response to submittal 01 56 39-011-01. | Info Exchange
| 02700 | Responded and Closed | Approved | 2019-06-27 | Shaina Burris (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is our response to submittal 01 56 39-011-01. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-06-19 |  | 01 56 39-011-01 Watering Schedule for Temp Watering.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-06-19 |  | 01 56 39-011-01 Watering Schedule for Temp Watering.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-06-27 |  | 01 56 39-011-01 Watering Schedule for Temp Watering - SWIFT.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2019-06-27 |  | 01 56 39-011-01 Watering Schedule for Temp Watering - SWIFT_POP.pdf
01 56 39-012-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-012-00 Arborist Compliance Report - 06072019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-06-18 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-07-02 | 2019-06-27 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-06-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01553 | Received | For Review | 2019-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-02 | Submittal Number: 01 56 39-12.0 From: TYLER BUNTON Final Due Date: 07/09/19 Subject: ARBORIST COMPLIANCE REPORT - 06072019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 02581 | Forwarded | For Review | 2019-06-18 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-06-25 | Submittal Number: 01 56 39-12.0 From: TYLER BUNTON Final Due Date: 07/09/19 Subject: ARBORIST COMPLIANCE REPORT - 06072019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 01636 | Review Response | Approved as Noted | 2019-06-27 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached is Swift response to submittal 01 56 39-012-00. | Email
| 02701 | Responded and Closed | Approved as Noted | 2019-06-27 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is Swift response to submittal 01 56 39-012-00. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-18 |  | Arborist Compliance Report - 06072019.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-18 |  | Arborist Compliance Report - 06072019(1).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-18 |  | Compliance Report_Seattle Center Arena_06.07.2019.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-18 |  | Compliance Report_Seattle Center Arena_06.07.2019(1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-06-18 |  | 01 56 39-012-00 Arborist Compliance Report - 06072019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-06-27 |  | 01 56 39-012-00 Arborist Compliance Report - 06072019 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | 01 56 39-012-00 Arborist Compliance Report - 06072019 - SWIFT_POP.pdf
01 56 39-013-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | Wood Chip Mulch & Coir Mat | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-06-28 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-07-15 | 2019-07-08 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01652 | Received | For Review | 2019-06-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-15 | Submittal Number: 01 56 39-13.0 From: DOMINGO SAMPAYO Final Due Date: 07/08/19 Subject: WOOD CHIP MULCH & COIR MAT Description: WOOD CHIP AND COIR MAT PRODUCT DATA AND SAMPLES TO BE PROVIDED PER 01 56 39 -2 TEMPORARY TREE AND PLANT PROTECTION (1.4. F & G) Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 02720 | Forwarded | For Review | 2019-06-28 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-07-08 | Submittal Number: 01 56 39-13.0 From: DOMINGO SAMPAYO Final Due Date: 07/08/19 Subject: WOOD CHIP MULCH & COIR MAT Description: WOOD CHIP AND COIR MAT PRODUCT DATA AND SAMPLES TO BE PROVIDED PER 01 56 39 -2 TEMPORARY TREE AND PLANT PROTECTION (1.4. F & G) Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 01697 | Review Response | Approved as Noted | 2019-07-08 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | Attached is Swift’s response to submittal 01 56 39-13 Wood Chip Mulch and Coir Mat. | Info Exchange
| 02781 | Responded and Closed | Approved as Noted | 2019-07-08 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is Swift’s response to submittal 01 56 39-13 Wood Chip Mulch and Coir Mat. POP Comments - Please note that final approval requires physical samples | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | 01 56 39-13 Wood Chip Mulch & Coir Mat.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | 01 56 39-13 Wood Chip Mulch & Coir Mat(1).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | Wood Chip Mulch & Coir Mat.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | Wood Chip Mulch & Coir Mat(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | 01 56 39-13 Wood Chip Mulch & Coir Mat.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | 01 56 39-13 Wood Chip Mulch & Coir Mat(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | Wood Chip Mulch & Coir Mat.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | Wood Chip Mulch & Coir Mat(1).pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-07-08 |  | 01 56 39-13 Wood Chip Mulch Coir Mat - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-08 |  | 01 56 39-13 Wood Chip Mulch Coir Mat - SWIFT _POP.pdf
01 56 39-014-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-014-00 Arborist Compliance Report - 06212019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-06-26 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-07-09 | 2019-06-27 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-06-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01625 | Received | For Review | 2019-06-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-09 | Submittal Number: 01 56 39-14.0 From: DOMINGO SAMPAYO Final Due Date: 07/05/19 Subject: ARBORIST COMPLIANCE REPORT - 06212019 Description: ARBORIST COMPLIANCE REPORT - 06212019 Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 02684 | Forwarded | For Review | 2019-06-26 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) |  | Submittal Number: 01 56 39-14.0 From: DOMINGO SAMPAYO Final Due Date: 07/05/19 Subject: ARBORIST COMPLIANCE REPORT - 06212019 Description: ARBORIST COMPLIANCE REPORT - 06212019 Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 01637 | Review Response | Approved as Noted | 2019-06-27 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Attached is Swift’s response to submittal 01 56 39-14. | Email
| 02702 | Responded and Closed | Approved as Noted | 2019-06-27 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is Swift’s response to submittal 01 56 39-14. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-25 |  | 01 56 39-14 Arborist Compliance Report - 06212019.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-25 |  | 01 56 39-14 Arborist Compliance Report - 06212019(1).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-25 |  | Compliance Report_Seattle Center Arena_06.21.2019.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-25 |  | Compliance Report_Seattle Center Arena_06.21.2019(1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-06-26 |  | 01 56 39-14 Arborist Compliance Report - 06212019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-06-26 |  | 01 56 39-14 Arborist Compliance Report - 06212019.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | 01 56 39-14 Arborist Compliance Report - 06212019 - SWIFT_POP.pdf
01 56 39-015-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-015-00 Arborist Compliance Report - 07052019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-10 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-07-24 | 2019-07-24 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-07-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01724 | Received | For Review | 2019-07-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-24 | Submittal Number: 01 56 39-15.0 From: DOMINGO SAMPAYO Final Due Date: 07/23/19 Subject: ARBORIST COMPLIANCE REPORT - 07052019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 02825 | Forwarded | For Review | 2019-07-10 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-07-17 | Submittal Number: 01 56 39-15.0 From: DOMINGO SAMPAYO Final Due Date: 07/23/19 Subject: ARBORIST COMPLIANCE REPORT - 07052019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 01860 | Review Response | Approved as Noted | 2019-07-24 | Gareth Loveridge (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | See attached report. Contractor is required to follow tree protection requirements - there is a significant risk to long term tree health if non-compliant action continues. | Email
| 02994 | Responded and Closed | Approved as Noted | 2019-07-24 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: See attached report. Contractor is required to follow tree protection requirements - there is a significant risk to long term tree health if non-compliant action continues. 1. ANY EXPOSED ROOTS ARE OUT OF COMPLIANCE. 2. SDOT APPROVAL REQUIRED PRIOR TO EXCAVATION IN THE CRZ. 3. EXCAVATION IN CRZ / ROOT ZONE WITHOUT PROJECT ARBORIST IS NOT IN COMPLIANCE WITH SPECIFICATIONS. 4. TEARING ROOTS OF PROTECTED TREES CREATES SIGNIFICNAT RISK TO LONG TERM TREE HEALTH. 5. COMPLIANCE WITH TREE PROTECTION REQUIREMENTS IS EXPECTED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-09 |  | Arborist Compliance Report - 07052019.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-10 |  | 01 56 39-015-00 Arborist Compliance Report - 07052019.pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2019-07-24 02:00 |  | 01 56 39-015-00 Arborist Compliance Report - 07052019-SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-24 02:00 |  | 01 56 39-015-00 Arborist Compliance Report - 07052019-SWIFT_POP.pdf
01 56 39-016-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-016-00 Arborist Compliance Report - 07192019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-22 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-08-05 | 2019-08-02 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-08-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01826 | Received | For Review | 2019-07-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-05 | Submittal Number: 01 56 39-16.0 From: TYLER BUNTON Final Due Date: 07/26/19 Subject: ARBORIST COMPLIANCE REPORT - 07192019 Description: ARBORIST COMPLIANCE REPORT - 07192019 Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 02950 | Forwarded | For Review | 2019-07-22 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-07-29 | Submittal Number: 01 56 39-16.0 From: TYLER BUNTON Final Due Date: 07/26/19 Subject: ARBORIST COMPLIANCE REPORT - 07192019 Description: ARBORIST COMPLIANCE REPORT - 07192019 Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03107 | Responded and Closed | Approved as Noted | 2019-08-02 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached markup of submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-19 |  | 01 56 39-16 Arborist Compliance Report - 07192019.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-19 |  | 01 56 39-16 Arborist Compliance Report - 07192019.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-02 |  | 01 56 39-16 Arborist Compliance Report - 07192019 - SWIFT - POP.pdf
01 56 39-017-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-017-00 Arborist Compliance Report - 08022019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-12 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-08-26 | 2019-08-27 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-08-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02032 | Received | For Review | 2019-08-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-26 | Submittal Number: 01 56 39-17.0 From: DOMINGO SAMPAYO Final Due Date: 08/16/19 Subject: ARBORIST COMPLIANCE REPORT - 08022019 Description: ARBORIST COMPLIANCE REPORT - 08022019 Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03195 | Forwarded | For Review | 2019-08-12 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-08-19 | Submittal Number: 01 56 39-17.0 From: DOMINGO SAMPAYO Final Due Date: 08/16/19 Subject: ARBORIST COMPLIANCE REPORT - 08022019 Description: ARBORIST COMPLIANCE REPORT - 08022019 Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 02214 | Review Response | Approved as Noted | 2019-08-27 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 03421 | Responded and Closed | Approved as Noted | 2019-08-27 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-10 |  | 01 56 39-17 Arborist Compliance Report - 08022019.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-10 |  | 01 56 39-17 Arborist Compliance Report - 08022019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-08-27 02:00 |  | 01 56 39-17 Arborist Compliance Report - 08022019 - SWIFT2.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-27 02:00 |  | 01 56 39-17 Arborist Compliance Report - 08022019 - SWIFT_POP.pdf
01 56 39-018-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-018-00 Arborist Compliance Report - 08162019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-20 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-09-03 | 2019-08-26 | 7 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02132 | Received | For Review | 2019-08-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-03 | Submittal Number: 01 56 39-18.0 From: DOMINGO SAMPAYO Final Due Date: 09/02/19 Subject: ARBORIST COMPLIANCE REPORT - 08162019 Description: ARBORIST COMPLIANCE REPORT - 08162019 Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03309 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-08-26 | Submittal Number: 01 56 39-18.0 From: DOMINGO SAMPAYO Final Due Date: 09/02/19 Subject: ARBORIST COMPLIANCE REPORT - 08162019 Description: ARBORIST COMPLIANCE REPORT - 08162019 Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 02200 | Review Response | Approved as Noted | 2019-08-26 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 03405 | Responded and Closed | Approved as Noted | 2019-08-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | Arborist Compliance Report - 08162019.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-19 |  | 01 56 39-018-00 Arborist Compliance Report - 08162019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-08-26 02:00 |  | 01 56 39-018-00 Arborist Compliance Report - 08162019 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-26 02:00 |  | 01 56 39-018-00 Arborist Compliance Report - 08162019 - SWIFT_POP.pdf
01 56 39-019-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-019-00 Arborist Compliance Report - 08302019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-04 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-09-18 | 2019-09-11 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-09-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02299 | Received | For Review | 2019-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-18 | Submittal Number: 01 56 39-19.0 From: TYLER BUNTON Final Due Date: 09/13/19 Subject: ARBORIST COMPLIANCE REPORT - 08302019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03523 | Forwarded | For Review | 2019-09-04 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-09-11 | Submittal Number: 01 56 39-19.0 From: TYLER BUNTON Final Due Date: 09/13/19 Subject: ARBORIST COMPLIANCE REPORT - 08302019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 02377 | Review Response | Approved as Noted | 2019-09-11 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 03620 | Responded and Closed | Approved as Noted | 2019-09-11 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-04 |  | Compliance Report_Seattle Center Arena_08.30.2019.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-04 |  | 01 56 39-019-00 Compliance Report_Seattle Center Arena_08.30.2019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-09-11 02:00 |  | 01 56 39-019-00 Compliance Report_Seattle Center Arena_08.30.2019 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-11 02:00 |  | 01 56 39-019-00 Compliance Report_Seattle Center Arena_08.30.2019 - SWIFT_POP.pdf
01 56 39-020-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-020-00 Arborist Compliance Report - 09132019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-17 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-10-01 | 2019-09-30 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-09-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02422 | Received | For Review | 2019-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-10-01 | Submittal Number: 01 56 39-20.0 From: DOMINGO SAMPAYO Final Due Date: 09/30/19 Subject: ARBORIST COMPLIANCE REPORT - 09132019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03679 | Forwarded | For Review | 2019-09-17 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-09-24 | Submittal Number: 01 56 39-20.0 From: DOMINGO SAMPAYO Final Due Date: 09/30/19 Subject: ARBORIST COMPLIANCE REPORT - 09132019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 02586 | Review Response | Approved as Noted | 2019-09-30 | Gareth Loveridge (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached is our response to the Arborist report from 9/16. Of particular concern are the additional branch prunes that were completed without approval of SDOT. | Info Exchange
| 03876 | Responded and Closed | Approved as Noted | 2019-09-30 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Josh Broussard (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: Attached is our response to the Arborist report from 9/16. Of particular concern are the additional branch prunes that were completed without approval of SDOT. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-16 |  | Arborist Compliance Report - 09132019.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-17 |  | 01 56 39-020-00 Arborist Compliance Report - 09132019.pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2019-09-30 |  | 01 56 39-020-00 Arborist Compliance Report - 09132019 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-30 |  | 01 56 39-020-00 Arborist Compliance Report - 09132019 - SWIFT_POP.pdf
01 56 39-021-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-021-00 Arborist Compliance Report - 09272019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-04 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-10-18 | 2019-10-15 | 12 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-10-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02650 | Received | For Review | 2019-10-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2019-10-18 | Submittal Number: 01 56 39-21.0 From: DOMINGO SAMPAYO Final Due Date: 10/14/19 Subject: ARBORIST COMPLIANCE REPORT - 09272019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03964 | Forwarded | For Review | 2019-10-03 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-10-10 | Submittal Number: 01 56 39-21.0 From: DOMINGO SAMPAYO Final Due Date: 10/14/19 Subject: ARBORIST COMPLIANCE REPORT - 09272019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 02783 | Review Response | Approved as Noted | 2019-10-15 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | Attached is Swift’s response the arborist report. | Info Exchange
| 04127 | Responded and Closed | Approved as Noted | 2019-10-15 | Josh Dobken (Populous) | Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is Swift’s response the arborist report. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-03 02:00 |  | 01 56 39-21 Arborist Compliance Report - 09272019.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-10-03 02:00 |  | 01 56 39-21 Arborist Compliance Report - 09272019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-10-15 02:00 |  | 01 56 39-21 Arborist Compliance Report - 09272019 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-15 02:00 |  | 01 56 39-21 Arborist Compliance Report - 09272019 - SWIFT_POP.pdf
01 56 39-023-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-023-00 Arborist Compliance Report - 10112019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-15 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-10-29 | 2019-10-16 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-10-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02769 | Received | For Review | 2019-10-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2019-10-29 | Submittal Number: 01 56 39-23.0 From: DOMINGO SAMPAYO Final Due Date: 10/16/19 Subject: ARBORIST COMPLIANCE REPORT - 10112019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04111 | Forwarded | For Review | 2019-10-15 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-10-22 | Submittal Number: 01 56 39-23.0 From: DOMINGO SAMPAYO Final Due Date: 10/16/19 Subject: ARBORIST COMPLIANCE REPORT - 10112019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 02804 | Review Response | Approved as Noted | 2019-10-16 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached is Swift’s response the most recent arborist report submittal. | Info Exchange
| 04156 | Responded and Closed | Approved as Noted | 2019-10-16 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is Swift’s response the most recent arborist report submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-14 |  | Arborist Compliance Report - 10112019.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-15 |  | 01 56 39-023-00 Arborist Compliance Report - 10112019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-10-16 02:00 |  | 01 56 39-023-00 Arborist Compliance Report - 10112019 SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-16 02:00 |  | 01 56 39-023-00 Arborist Compliance Report - 10112019 SWIFT_POP.pdf
01 56 39-024-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-024-00 Arborist Compliance Report - 10252019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-28 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-11-11 | 2019-11-12 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-11-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02933 | Received | For Review | 2019-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2019-11-11 | Submittal Number: 01 56 39-24.0 From: DOMINGO SAMPAYO Final Due Date: 10/30/19 Subject: ARBORIST COMPLIANCE REPORT - 10252019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04304 | Forwarded | For Review | 2019-10-28 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-11-04 | Submittal Number: 01 56 39-24.0 From: DOMINGO SAMPAYO Final Due Date: 10/30/19 Subject: ARBORIST COMPLIANCE REPORT - 10252019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03177 | Review Response | Approved as Noted | 2019-11-12 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached is our submittal response for the most recent arborist compliance report. | Info Exchange
| 04598 | Responded and Closed | Approved as Noted | 2019-11-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is our submittal response for the most recent arborist compliance report. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-25 |  | Arborist Compliance Report - 10252019.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-25 |  | 01 56 39-024-00 Arborist Compliance Report - 10252019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-11-12 02:00 |  | 01 56 39-024-00 Arborist Compliance Report - 10252019 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-12 02:00 |  | 01 56 39-024-00 Arborist Compliance Report - 10252019 - SWIFT_POP.pdf
01 56 39-025-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-025-00 Tree Protection Plan (Updated Revision) | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-29 | Responded and Closed - Revise and Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-11-12 | 2019-11-06 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-11-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02950 | Received | For Review | 2019-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2019-11-12 | Submittal Number: 01 56 39-25.0 From: DOMINGO SAMPAYO Final Due Date: 11/19/19 Subject: TREE PROTECTION PLAN (UPDATED REVISION) Description: REVISED TREE PROTECTION PLAN Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04327 | Forwarded | For Review | 2019-10-29 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-11-05 | Submittal Number: 01 56 39-25.0 From: DOMINGO SAMPAYO Final Due Date: 11/19/19 Subject: TREE PROTECTION PLAN (UPDATED REVISION) Description: REVISED TREE PROTECTION PLAN Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03103 | Review Response | Revise and Resubmit | 2019-11-06 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached is our submittal response for 01 56 39-025-00 Tree Protection Plan. We would like this to be resubmitted with the air spading at the switchgear location added. We would also like clarification on why the steel plates are being removed from the SW gate area. | Info Exchange
| 04503 | Responded and Closed | Revise and Resubmit | 2019-11-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is our submittal response for 01 56 39-025-00 Tree Protection Plan. We would like this to be resubmitted with the air spading at the switchgear location added. We would also like clarification on why the steel plates are being removed from the SW gate area. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-28 |  | Tree Protection Plan (Updated Revision).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-28 |  | 01 56 39-025-00 Tree Protection Plan (Updated Revision).pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-11-06 02:00 |  | 01 56 39-025-00 Tree Protection Plan (Updated Revision) - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-06 02:00 |  | 01 56 39-025-00 Tree Protection Plan (Updated Revision) - SWIFT_POP.pdf
01 56 39-025-01 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-025-01 Tree Protection Plan (Updated Revision) | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-12 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-11-26 | 2019-11-26 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-11-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03159 | Received | For Review | 2019-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2019-11-26 | Submittal Number: 01 56 39-25.1 From: DOMINGO SAMPAYO Final Due Date: 11/25/19 Subject: TREE PROTECTION PLAN (UPDATED REVISION) Description: RE-SUBMITTAL OF REVISED TREE PROTECTION PLAN PER SWIF NOTES. Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04578 | Forwarded | For Review | 2019-11-11 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-11-18 | Submittal Number: 01 56 39-25.1 From: DOMINGO SAMPAYO Final Due Date: 11/25/19 Subject: TREE PROTECTION PLAN (UPDATED REVISION) Description: RE-SUBMITTAL OF REVISED TREE PROTECTION PLAN PER SWIF NOTES. Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03391 | Review Response | Approved | 2019-11-26 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | Submittal response is attached. | Info Exchange
| 04857 | Responded and Closed | Approved | 2019-11-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Submittal response is attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-11 |  | 01 56 39-25 Rev1 Tree Protection Plan (Updated).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-11 |  | 01 56 39-25 Rev1 Tree Protection Plan (Updated).pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-11-26 02:00 |  | 01 56 39-25 Rev1 Tree Protection Plan (Updated)-SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-26 02:00 |  | 01 56 39-25 Rev1 Tree Protection Plan (Updated)-SWIFT_POP.pdf
01 56 39-025-02 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-025-02 Tree Protection Plan (01/08/2021 - Updated Revision) | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-20 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-03 | 2021-01-20 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10800 | Received | For Review | 2021-01-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-02-03 | Submittal Number: 01 56 39-25.2 From: DOMINGO SAMPAYO Final Due Date: 01/25/21 Subject: TREE PROTECTION PLAN (01/08/2021 - UPDATED REVISION) Description: RE-SUBMITTAL OF REVISED TREE PROTECTION PLAN PER SWIF NOTES. Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 14047 | Forwarded | For Review | 2021-01-20 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-01-27 | Submittal Number: 01 56 39-25.2 From: DOMINGO SAMPAYO Final Due Date: 01/25/21 Subject: TREE PROTECTION PLAN (01/08/2021 - UPDATED REVISION) Description: RE-SUBMITTAL OF REVISED TREE PROTECTION PLAN PER SWIF NOTES. Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 10804 | Review Response | Approved as Noted | 2021-01-20 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 14053 | Responded and Closed | Approved as Noted | 2021-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-19 |  | L2-010 TREE AND PLANT PROTECTION PLAN.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-19 |  | L2-010 TREE AND PLANT PROTECTION PLAN.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-01-20 02:00 |  | 01 56 39-25 R2 Tree Protection Plan - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-20 02:00 |  | 01 56 39-25 R2 Tree Protection Plan - SWIFT_POP.pdf
01 56 39-026-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-026-00 Photo Documentation & Updated Condition Ratings and Appraisal Values | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-29 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-11-12 | 2019-11-06 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-11-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02951 | Received | For Review | 2019-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2019-11-12 | Submittal Number: 01 56 39-26.0 From: DOMINGO SAMPAYO Final Due Date: 11/26/19 Subject: PHOTO DOCUMENTATION & UPDATED CONDITION RATINGS AND APPRAISAL VALUES Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04328 | Forwarded | For Review | 2019-10-29 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-11-05 | Submittal Number: 01 56 39-26.0 From: DOMINGO SAMPAYO Final Due Date: 11/26/19 Subject: PHOTO DOCUMENTATION & UPDATED CONDITION RATINGS AND APPRAISAL VALUES Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03102 | Review Response | Approved | 2019-11-06 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 04502 | Responded and Closed | Approved | 2019-11-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-28 |  | Photo Doc & Updated Condition Ratings Appraisal Values.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-28 |  | 01 56 39-026-00 Photo Documentation & Updated Condition.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-10-27 02:00 |  | 01 56 39-026-00 Photo Documentation & Updated Condition.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-06 02:00 |  | 01 56 39-026-00 Photo Documentation & Updated Condition - SWIFT_POP.pdf
01 56 39-027-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-027-00 Mycorrhizae Fungal Inoculant and Cambistat Product Labels | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-29 | Responded and Closed - Revise and Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-11-12 | 2019-11-12 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-11-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02952 | Received | For Review | 2019-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2019-11-12 | Submittal Number: 01 56 39-27.0 From: DOMINGO SAMPAYO Final Due Date: 11/19/19 Subject: MYCORRHIZAE FUNGAL INOCULANT AND CAMBISTAT PRODUCT LABELS Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04329 | Forwarded | For Review | 2019-10-29 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-11-05 | Submittal Number: 01 56 39-27.0 From: DOMINGO SAMPAYO Final Due Date: 11/19/19 Subject: MYCORRHIZAE FUNGAL INOCULANT AND CAMBISTAT PRODUCT LABELS Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03179 | Review Response | Revise and Resubmit | 2019-11-12 | Gareth Loveridge (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | 1. FUNGICIDE REQUIRES CLARIFICATION FOR SUBSTITUTION. 2. CAMBISTAT APPROVED AS DIRECTED BY SDOT AND SEATTLE CENTER. | Info Exchange
| 04601 | Responded and Closed | Revise and Resubmit | 2019-11-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: 1. FUNGICIDE REQUIRES CLARIFICATION FOR SUBSTITUTION. 2. CAMBISTAT APPROVED AS DIRECTED BY SDOT AND SEATTLE CENTER. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-28 |  | Mycorrhizae Fungal Inoculant and Cambistat Product.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-28 |  | 01 56 39-027-00 Mycorrhizae Fungal Inoculant and Cambistat Product Labels.pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2019-11-12 02:00 |  | 01 56 39-027-00 Mycorrhizae Fungal Inoculant and Cambistat Product Labels - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-12 02:00 |  | 01 56 39-027-00 Mycorrhizae Fungal Inoculant and Cambistat Product Labels - SWIFT_POP.pdf
01 56 39-027-01 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-027-01 Mycorrhizae Fungal Inoculant and Cambistat Product Labels | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-12-09 08:00 | 2019-12-12 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2019-12-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03314 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2019-12-09 08:00 | Submittal Number: 01 56 39-27.1 From: DOMINGO SAMPAYO Final Due Date: 12/09/19 Subject: MYCORRHIZAE FUNGAL INOCULANT AND CAMBISTAT PRODUCT LABELS Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04768 | Forwarded | For Review | 2019-11-21 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-11-27 | Submittal Number: 01 56 39-27.1 From: DOMINGO SAMPAYO Final Due Date: 12/09/19 Subject: MYCORRHIZAE FUNGAL INOCULANT AND CAMBISTAT PRODUCT LABELS Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03452 | Review Response | Rejected | 2019-12-03 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached is Swift’s response to submittal 01 56 39-027-01 Mycorrhizae Fungal Inoculant and Cambistat Product Labels. We are rejecting this submittal. The spec calls for a liquid applied product, this is a dry pellet product that is meant to broadcast and incorporated into planting soils. | Info Exchange
| 04927 | Responded and Closed | Rejected | 2019-12-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is Swift’s response to submittal 01 56 39-027-01 Mycorrhizae Fungal Inoculant and Cambistat Product Labels. We are rejecting this submittal. The spec calls for a liquid applied product, this is a dry pellet product that is meant to broadcast and incorporated into planting soils. | Info Exchange
| 05099 | Reopened | Additional Information | 2019-12-12 14:20 | Josh Dobken (Populous) |  |  | Reopened to send a revised response to the submittal. Now included in the submittal is an email correspondence between the Arborist and Swift.
| 03614 | Review Response | Approved | 2019-12-12 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached is the revised submittal response which includes the email correspondence between Mortenson, Tree Solutions, and Swift. | Info Exchange
| 05100 | Responded and Closed | Approved | 2019-12-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Reopened (Additional Information) by: Josh Dobken Remarks: Reopened to send a revised response to the submittal. Now included in the submittal is an email correspondence between the Arborist and Swift. Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is the revised submittal response which includes the email correspondence between Mortenson, Tree Solutions, and Swift. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-21 |  | 01 56 39-27 R1 Mycorrhizae Fungal Inoculant and Cambistat.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-21 |  | 01 56 39-27 R1 Mycorrhizae Fungal Inoculant and Cambistat.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-12-03 02:00 |  | 01 56 39-27 R1 Mycorrhizae Fungal Inoculant and Cambistat SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-03 02:00 |  | 01 56 39-27 R1 Mycorrhizae Fungal Inoculant and Cambistat SWIFT_POP.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-12-12 02:00 |  | 01 56 39-27 R1 Mycorrhizae Fungal Inoculant and Cambistat SWIFT_POP - SWIFT r1.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-12 02:00 |  | 01 56 39-27 R1 Mycorrhizae Fungal Inoculant and Cambistat SWIFT_POP - SWIFT r1_POP.pdf
01 56 39-028-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-028-00 Arborist Compliance Report - 11082019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-11 | Responded and Closed - Approved as Noted/Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-11-25 | 2019-11-18 | 8 |  | Record Copies; Transfers; Submittals | 01 56 39-028-00-01 - 01 56 39-028-00 Arborist Compliance Report - 11082019 | 11 |  | 2019-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03146 | Received | For Review | 2019-11-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2019-11-25 | Submittal Number: 01 56 39-28.0 From: DOMINGO SAMPAYO Final Due Date: 11/13/19 Subject: ARBORIST COMPLIANCE REPORT - 11082019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04566 | Forwarded | For Review | 2019-11-08 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-11-15 | Submittal Number: 01 56 39-28.0 From: DOMINGO SAMPAYO Final Due Date: 11/13/19 Subject: ARBORIST COMPLIANCE REPORT - 11082019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03243 | Review Response | Approved as Noted/Resubmit | 2019-11-18 | Gareth Loveridge (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | SWIFT: ADVANCED NOTIFICATION TO OWNER'S REPRESENTATIVE AND PROJECT ARBORIST PRIOR TO MOVEMENT OR ACCESS INTO TREE PRTECTION AREA IS REQUIRED. FAILURE TO PROVIDE NOTICE IS NON-COMPLIANT. 015639 - 3.3.D.6 "Notify the Owner’s Representative and Project Arborist 24 hours in advance of the need to move a tree protection fence" | Info Exchange
| 04685 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-18 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: SWIFT: ADVANCED NOTIFICATION TO OWNER'S REPRESENTATIVE AND PROJECT ARBORIST PRIOR TO MOVEMENT OR ACCESS INTO TREE PRTECTION AREA IS REQUIRED. FAILURE TO PROVIDE NOTICE IS NON-COMPLIANT. 015639 - 3.3.D.6 "Notify the Owner’s Representative and Project Arborist 24 hours in advance of the need to move a tree protection fence" Mortenson, please provide documentation indicating a minimum of 24-hour advance notice for moving a tree protection fence. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-08 |  | 01 56 39-28 Arborist Compliance Report - 11082019.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-08 |  | 01 56 39-28 Arborist Compliance Report - 11082019.pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2019-11-18 02:00 |  | 01 56 39-28 Arborist Compliance Report - 11082019-SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-18 02:00 |  | 01 56 39-28 Arborist Compliance Report - 11082019-SWIFT_POP.pdf
01 56 39-028-00-01 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-028-00 Arborist Compliance Report - 11082019 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 01 56 39-028-00 - 01 56 39-028-00 Arborist Compliance Report - 11082019 | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-18 02:00 |  | 01 56 39-28 Arborist Compliance Report - 11082019-SWIFT_POP.pdf
01 56 39-029-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-029-00 Arborist Compliance Report - 11222019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-25 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-12-11 | 2019-12-02 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03371 | Received | For Review | 2019-11-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2019-12-11 | Submittal Number: 01 56 39-29.0 From: DOMINGO SAMPAYO Final Due Date: 11/27/19 Subject: ARBORIST COMPLIANCE REPORT - 11222019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04827 | Forwarded | For Review | 2019-11-26 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-12-03 | Submittal Number: 01 56 39-29.0 From: DOMINGO SAMPAYO Final Due Date: 11/27/19 Subject: ARBORIST COMPLIANCE REPORT - 11222019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03435 | Review Response | Approved | 2019-12-02 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | Attached is our response to the arborist report. | Info Exchange
| 04907 | Responded and Closed | Approved | 2019-12-02 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is our response to the arborist report. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-25 02:00 |  | 01 56 39-29 Arborist Compliance Report - 11222019.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-25 02:00 |  | 01 56 39-29 Arborist Compliance Report - 11222019.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2019-12-02 02:00 |  | 01 56 39-29 Arborist Compliance Report - 11222019 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-02 02:00 |  | 01 56 39-29 Arborist Compliance Report - 11222019 - SWIFT_POP.pdf
01 56 39-030-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-030-00: Arborist Compliance Report - 12062019 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-10 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-01-02 | 2019-12-17 | 8 | General | Record Copies; Transfers; Submittals |  | 7 |  | 2019-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03578 | Received | For Review | 2019-12-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2020-01-02 | Submittal Number: 01 56 39-30.0 From: DOMINGO SAMPAYO Final Due Date: 12/11/19 Subject: ARBORIST COMPLIANCE REPORT - 12062019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 05058 | Forwarded | For Review | 2019-12-10 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-12-17 | Submittal Number: 01 56 39-30.0 From: DOMINGO SAMPAYO Final Due Date: 12/11/19 Subject: ARBORIST COMPLIANCE REPORT - 12062019 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03659 | Review Response | Approved as Noted | 2019-12-16 | Gareth Loveridge (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | Attached is the submittal response. | Info Exchange
| 05179 | Responded and Closed | Approved as Noted | 2019-12-17 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: Attached is the submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-09 02:00 |  | 01 56 39-30 Arborist Compliance Report - 12062019.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 01 56 39-30 Arborist Compliance Report - 12062019.pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2019-12-17 02:00 |  | 01 56 39-30 Arborist Compliance Report - 12062019 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-17 02:00 |  | 01 56 39-30 Arborist Compliance Report - 12062019 - SWIFT_POP.pdf
01 56 39-031-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-031-00 Arborist Compliance Report - 01032020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-14 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-01-28 | 2020-01-20 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03915 | Received | For Review | 2020-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2020-01-28 | Submittal Number: 01 56 39-31.0 From: DOMINGO SAMPAYO Final Due Date: 01/17/20 Subject: ARBORIST COMPLIANCE REPORT - 01032020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 05475 | Forwarded | For Review | 2020-01-14 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-01-21 | Submittal Number: 01 56 39-31.0 From: DOMINGO SAMPAYO Final Due Date: 01/17/20 Subject: ARBORIST COMPLIANCE REPORT - 01032020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03989 | Review Response | Approved as Noted | 2020-01-20 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | See attached for Swift's response to the arborist compliance report. Outstanding items are addressed in report received 1/17. | Info Exchange
| 05568 | Responded and Closed | Approved as Noted | 2020-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See attached for Swift's response to the arborist compliance report. Outstanding items are addressed in report received 1/17. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-14 |  | 01 56 39-31 Arborist Compliance Report - 01032020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-14 |  | 01 56 39-31 Arborist Compliance Report - 01032020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-01-20 02:00 |  | 01 56 39-31 Arborist Compliance Report - 01032020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-20 02:00 |  | 01 56 39-31 Arborist Compliance Report - 01032020 - SWIFT_POP.pdf
01 56 39-032-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-032-00 Arborist Compliance Report - 01172020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-17 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-01-31 | 2020-01-20 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03977 | Received | For Review | 2020-01-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2020-01-31 | Submittal Number: 01 56 39-32.0 From: DOMINGO SAMPAYO Final Due Date: 01/22/20 Subject: ARBORIST COMPLIANCE REPORT - 01172020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 05549 | Forwarded | For Review | 2020-01-17 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-01-24 | Submittal Number: 01 56 39-32.0 From: DOMINGO SAMPAYO Final Due Date: 01/22/20 Subject: ARBORIST COMPLIANCE REPORT - 01172020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 03990 | Review Response | Approved as Noted | 2020-01-20 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | See attached for Swift response to 1/17 arborist report. Outstanding items and those not photo-documented from this and previous report to be reviewed at 1/24 site walk. | Info Exchange
| 05569 | Responded and Closed | Approved as Noted | 2020-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See attached for Swift response to 1/17 arborist report. Outstanding items and those not photo-documented from this and previous report to be reviewed at 1/24 site walk. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-17 |  | 01 56 39-32 Arborist Compliance Report - 01172020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-17 |  | 01 56 39-32 Arborist Compliance Report - 01172020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-01-20 02:00 |  | 01 56 39-32 Arborist Compliance Report - 01172020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-20 02:00 |  | 01 56 39-32 Arborist Compliance Report - 01172020 - SWIFT_POP.pdf
01 56 39-033-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-033-00 Arborist Compliance Report - 01312020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-02-20 | 2020-02-11 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04238 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2020-02-20 | Submittal Number: 01 56 39-33.0 From: DOMINGO SAMPAYO Final Due Date: 02/17/20 Subject: ARBORIST COMPLIANCE REPORT - 01312020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 05867 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-02-13 | Submittal Number: 01 56 39-33.0 From: DOMINGO SAMPAYO Final Due Date: 02/17/20 Subject: ARBORIST COMPLIANCE REPORT - 01312020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04322 | Review Response | Approved as Noted | 2020-02-11 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | See attached. | Info Exchange
| 05977 | Responded and Closed | Approved as Noted | 2020-02-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 01 56 39-33 Arborist Compliance Report - 01312020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | 01 56 39-33 Arborist Compliance Report - 01312020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-02-11 02:00 |  | 01 56 39-33 Arborist Compliance Report - 01312020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-11 02:00 |  | 01 56 39-33 Arborist Compliance Report - 01312020 - SWIFT_POP.pdf
01 56 39-034-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-034-00 Arborist Compliance Report - 02142020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-21 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-03-06 | 2020-03-02 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04437 | Received | For Review | 2020-02-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-03-06 | Submittal Number: 01 56 39-34.0 From: DOMINGO SAMPAYO Final Due Date: 03/02/20 Subject: ARBORIST COMPLIANCE REPORT - 02142020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 06125 | Forwarded | For Review | 2020-02-21 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-02-28 | Submittal Number: 01 56 39-34.0 From: DOMINGO SAMPAYO Final Due Date: 03/02/20 Subject: ARBORIST COMPLIANCE REPORT - 02142020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04579 | Review Response | Approved as Noted | 2020-03-02 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached is Swift’s most recent arborist compliance report response. Generally responsiveness has improved and out of compliance items have been reduced. However we remain concerned about the frequency of fence panels being shifted, removed, or left unsecured. | Info Exchange
| 06315 | Responded and Closed | Approved as Noted | 2020-03-02 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is Swift’s most recent arborist compliance report response. Generally responsiveness has improved and out of compliance items have been reduced. However we remain concerned about the frequency of fence panels being shifted, removed, or left unsecured. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-20 |  | 01 56 39-34 Arborist Compliance Report - 02142020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-20 |  | 01 56 39-34 Arborist Compliance Report - 02142020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-03-02 02:00 |  | 01 56 39-34 Arborist Compliance Report - 02142020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-02 02:00 |  | 01 56 39-34 Arborist Compliance Report - 02142020 - SWIFT_POP.pdf
01 56 39-035-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-035-00 Arborist Compliance Report - 03022020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-03-17 | 2020-03-18 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04593 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 01 56 39-35.0 From: DOMINGO SAMPAYO Final Due Date: 03/16/20 Subject: ARBORIST COMPLIANCE REPORT - 03022020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 06331 | Forwarded | For Review | 2020-03-03 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-03-10 | Submittal Number: 01 56 39-35.0 From: DOMINGO SAMPAYO Final Due Date: 03/16/20 Subject: ARBORIST COMPLIANCE REPORT - 03022020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 04917 | Review Response | Approved as Noted | 2020-03-18 | Gareth Loveridge (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached are the Swift comments on the report. Some arborist report recommendations are taking more than 1 week to resolve with respect to tree protection fencing. This is not acceptable practice by the contractor. | Info Exchange
| 06712 | Responded and Closed | Approved as Noted | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: Attached are the Swift comments on the report. Some arborist report recommendations are taking more than 1 week to resolve with respect to tree protection fencing. This is not acceptable practice by the contractor. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 01 56 39-35 Arborist Compliance Report - 03022020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 01 56 39-35 Arborist Compliance Report - 03022020.pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2020-03-18 02:00 |  | 01 56 39-35 Arborist Compliance Report - 03022020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-18 02:00 |  | 01 56 39-35 Arborist Compliance Report - 03022020 - SWIFT_POP.pdf
01 56 39-036-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-036-00 Arborist Compliance Report - 03132020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-03-30 | 2020-03-26 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04864 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 01 56 39-36.0 From: DOMINGO SAMPAYO Final Due Date: 03/30/20 Subject: ARBORIST COMPLIANCE REPORT - 03132020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 06644 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-03-23 | Submittal Number: 01 56 39-36.0 From: DOMINGO SAMPAYO Final Due Date: 03/30/20 Subject: ARBORIST COMPLIANCE REPORT - 03132020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 05063 | Review Response | Approved as Noted | 2020-03-26 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached is our response to the most recent arborist report. All looks good with the exception of the tree protection box at tree L7639 which was noted in the report as open on the 3/6 tree walk and closed on the 3/13 tree walk, but was observed as open at the 3/20 tree walk. We need to make sure it's secured. | Info Exchange
| 06886 | Responded and Closed | Approved as Noted | 2020-03-26 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is our response to the most recent arborist report. All looks good with the exception of the tree protection box at tree L7639 which was noted in the report as open on the 3/6 tree walk and closed on the 3/13 tree walk, but was observed as open at the 3/20 tree walk. We need to make sure it's secured. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 01 56 39-35 Arborist Compliance Report - 03022020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 01 56 39-35 Arborist Compliance Report - 03022020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-03-26 02:00 |  | 01 56 39-36 Arborist Compliance Report - 03022020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-26 02:00 |  | 01 56 39-36 Arborist Compliance Report - 03022020 - SWIFT_POP.pdf
01 56 39-037-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-037-00 Arborist Compliance Report - 03272020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-31 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-04-14 | 2020-04-16 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-04-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05121 | Received | For Review | 2020-03-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-04-14 | Submittal Number: 01 56 39-37.0 From: DOMINGO SAMPAYO Final Due Date: 04/14/20 Subject: ARBORIST COMPLIANCE REPORT - 03272020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 06952 | Forwarded | For Review | 2020-03-30 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-04-06 | Submittal Number: 01 56 39-37.0 From: DOMINGO SAMPAYO Final Due Date: 04/14/20 Subject: ARBORIST COMPLIANCE REPORT - 03272020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 06953 | Forwarded | For Review | 2020-03-30 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-04-06 | Submittal Number: 01 56 39-37.0 From: DOMINGO SAMPAYO Final Due Date: 04/14/20 Subject: ARBORIST COMPLIANCE REPORT - 03272020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 05396 | Review Response | Approved | 2020-04-15 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Submittal is attached. | Email
| 07328 | Responded and Closed | Approved | 2020-04-16 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Submittal is attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-30 |  | 01 56 39-37 Arborist Compliance Report - 03272020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-30 |  | 01 56 39-37 Arborist Compliance Report - 03272020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-30 |  | 01 56 39-37 Arborist Compliance Report - 03272020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-04-16 02:00 |  | 01 56 39-37 Arborist Compliance Report - 03272020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-16 02:00 |  | 01 56 39-37 Arborist Compliance Report - 03272020 - SWIFT_POP.pdf
01 56 39-038-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-038-00 Arborist Compliance Report - 04102020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-16 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-04-30 | 2020-04-17 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-04-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05385 | Received | For Review | 2020-04-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-04-30 | Submittal Number: 01 56 39-38.0 From: DOMINGO SAMPAYO Final Due Date: 04/27/20 Subject: ARBORIST COMPLIANCE REPORT - 04102020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 07311 | Forwarded | For Review | 2020-04-16 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-04-23 | Submittal Number: 01 56 39-38.0 From: DOMINGO SAMPAYO Final Due Date: 04/27/20 Subject: ARBORIST COMPLIANCE REPORT - 04102020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 07352 | Responded and Closed | Approved as Noted | 2020-04-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-15 |  | 01 56 39-38 Arborist Compliance Report - 04102020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-15 |  | 01 56 39-38 Arborist Compliance Report - 04102020.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-17 02:00 |  | 01 56 39-38 Arborist Compliance Report - 04102020 - SWIFT_POP.pdf
01 56 39-039-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-039-00 Arborist Compliance Report - 04242020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-15 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-06-01 07:00 | 2020-05-28 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-05-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05882 | Received | For Review | 2020-05-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-06-01 07:00 | Submittal Number: 01 56 39-39.0 From: DOMINGO SAMPAYO Final Due Date: 05/11/20 Subject: ARBORIST COMPLIANCE REPORT - 04242020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 07981 | Forwarded | For Review | 2020-05-15 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-05-22 | Submittal Number: 01 56 39-39.0 From: DOMINGO SAMPAYO Final Due Date: 05/11/20 Subject: ARBORIST COMPLIANCE REPORT - 04242020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 06085 | Review Response | Approved | 2020-05-28 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 08237 | Responded and Closed | Approved | 2020-05-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-15 |  | 01 56 39-39 Arborist Compliance Report - 04242020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-15 |  | 01 56 39-39 Arborist Compliance Report - 04242020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-05-28 02:00 |  | 01 56 39-39 Arborist Compliance Report - 04242020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-28 02:00 |  | 01 56 39-39 Arborist Compliance Report - 04242020 - SWIFT_POP.pdf
01 56 39-040-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-040-00 Arborist Compliance Report - 05082020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-05-26 07:00 | 2020-05-28 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-05-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05775 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 01 56 39-40.0 From: DOMINGO SAMPAYO Final Due Date: 05/22/20 Subject: ARBORIST COMPLIANCE REPORT - 05082020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 07832 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-05-18 | Submittal Number: 01 56 39-40.0 From: DOMINGO SAMPAYO Final Due Date: 05/22/20 Subject: ARBORIST COMPLIANCE REPORT - 05082020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 06086 | Review Response | Approved | 2020-05-28 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 08238 | Responded and Closed | Approved | 2020-05-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 01 56 39-40 Arborist Compliance Report - 05082020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 01 56 39-40 Arborist Compliance Report - 05082020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-05-28 02:00 |  | 01 56 39-40 Arborist Compliance Report - 05082020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-28 02:00 |  | 01 56 39-40 Arborist Compliance Report - 05082020 - SWIFT_POP.pdf
01 56 39-041-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-041-00 Arborist Compliance Report - 05222020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-26 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-06-09 | 2020-05-28 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-05-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06008 | Received | For Review | 2020-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-06-09 | Submittal Number: 01 56 39-41.0 From: DOMINGO SAMPAYO Final Due Date: 06/05/20 Subject: ARBORIST COMPLIANCE REPORT - 05222020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 08149 | Forwarded | For Review | 2020-05-26 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-06-02 | Submittal Number: 01 56 39-41.0 From: DOMINGO SAMPAYO Final Due Date: 06/05/20 Subject: ARBORIST COMPLIANCE REPORT - 05222020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 06087 | Review Response | Approved | 2020-05-28 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 08239 | Responded and Closed | Approved | 2020-05-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-22 |  | 01 56 39-41 Arborist Compliance Report - 05222020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-22 |  | 01 56 39-41 Arborist Compliance Report - 05222020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-05-28 02:00 |  | 01 56 39-41 Arborist Compliance Report - 05222020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-28 02:00 |  | 01 56 39-41 Arborist Compliance Report - 05222020 - SWIFT_POP.pdf
01 56 39-042-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-042-00 Arborist Compliance Report - 06052020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-08 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-06-22 | 2020-06-25 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06255 | Received | For Review | 2020-06-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-06-22 | Submittal Number: 01 56 39-42.0 From: DOMINGO SAMPAYO Final Due Date: 06/22/20 Subject: ARBORIST COMPLIANCE REPORT - 06052020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 08439 | Forwarded | For Review | 2020-06-08 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-06-15 | Submittal Number: 01 56 39-42.0 From: DOMINGO SAMPAYO Final Due Date: 06/22/20 Subject: ARBORIST COMPLIANCE REPORT - 06052020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 06618 | Review Response | Approved | 2020-06-25 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | See attached response | Info Exchange
| 08921 | Responded and Closed | Approved | 2020-06-25 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See attached response | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 01 56 39-42 Arborist Compliance Report - 06052020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 01 56 39-42 Arborist Compliance Report - 06052020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-06-25 02:00 |  | 01 56 39-42 Arborist Compliance Report - 06052020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-25 02:00 |  | 01 56 39-42 Arborist Compliance Report - 06052020 - SWIFT_pop.pdf
01 56 39-043-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-043-00 Arborist Compliance Report - 06192020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-29 | Responded and Closed - Approved as Noted/Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-07-14 07:00 | 2020-07-14 | 16 |  | Record Copies; Transfers; Submittals | 01 56 39-043-00-01 - 01 56 39-043-00 Arborist Compliance Report - 06192020 | 15 |  | 2020-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06649 | Received | For Review | 2020-06-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-07-14 07:00 | Submittal Number: 01 56 39-43.0 From: DOMINGO SAMPAYO Final Due Date: 07/06/20 Subject: ARBORIST COMPLIANCE REPORT - 06192020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 08955 | Forwarded | For Review | 2020-06-29 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-07-06 | Submittal Number: 01 56 39-43.0 From: DOMINGO SAMPAYO Final Due Date: 07/06/20 Subject: ARBORIST COMPLIANCE REPORT - 06192020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 06949 | Review Response | Approved as Noted/Resubmit | 2020-07-13 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | See pdf for Swift's response. This submittal is marked as approved as noted - resubmit. I wasn't a part of the emails regarding removal of the CDF and would like a copy of them or summary. Planting fill needs to be used to backfill the area once ready, NOT gravel. Thanks, Rhys | Info Exchange
| 09309 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See pdf for Swift's response. This submittal is marked as approved as noted - resubmit. I wasn't a part of the emails regarding removal of the CDF and would like a copy of them or summary. Planting fill needs to be used to backfill the area once ready, NOT gravel. Thanks, Rhys | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-26 |  | 01 56 39-42 Arborist Compliance Report - 06192020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-29 |  | 01 56 39-43 Arborist Compliance Report - 06192020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-06-28 02:00 |  | 01 56 39-43 Arborist Compliance Report - 06192020.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-14 02:00 |  | 01 56 39-43 Arborist Compliance Report - 06192020 - SWIFT_pop.pdf
01 56 39-043-00-01 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-043-00 Arborist Compliance Report - 06192020 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 01 56 39-043-00 - 01 56 39-043-00 Arborist Compliance Report - 06192020 | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-14 02:00 |  | 01 56 39-43 Arborist Compliance Report - 06192020 - SWIFT_pop.pdf
01 56 39-044-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-044-00 Arborist Compliance Report - 07032020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-07-20 | 2020-07-13 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06780 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 01 56 39-44.0 From: DOMINGO SAMPAYO Final Due Date: 07/17/20 Subject: ARBORIST COMPLIANCE REPORT - 07032020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 09115 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-07-13 | Submittal Number: 01 56 39-44.0 From: DOMINGO SAMPAYO Final Due Date: 07/17/20 Subject: ARBORIST COMPLIANCE REPORT - 07032020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 06940 | Review Response | Approved | 2020-07-13 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached is Swift’s response to the most recent arborist report. | Info Exchange
| 09298 | Responded and Closed | Approved | 2020-07-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Attached is Swift’s response to the most recent arborist report. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 01 56 39-44 Arborist Compliance Report - 07032020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 01 56 39-44 Arborist Compliance Report - 07032020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-07-13 02:00 |  | 01 56 39-44 Arborist Compliance Report - 07032020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-05 02:00 |  | 01 56 39-44 Arborist Compliance Report - 07032020.pdf
01 56 39-045-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-045-00 Arborist Compliance Report - 07172020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-08-06 | 2020-07-27 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-07-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07111 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 01 56 39-45.0 From: DOMINGO SAMPAYO Final Due Date: 08/07/20 Subject: ARBORIST COMPLIANCE REPORT - 07172020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 09500 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-07-30 | Submittal Number: 01 56 39-45.0 From: DOMINGO SAMPAYO Final Due Date: 08/07/20 Subject: ARBORIST COMPLIANCE REPORT - 07172020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 07167 | Review Response | Approved | 2020-07-23 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 09563 | Responded and Closed | Approved | 2020-07-27 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 01 56 39-45 Arborist Compliance Report - 07172020.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | Capture.JPG
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | 01 56 39-45 Arborist Compliance Report - 07172020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | Capture.JPG
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-07-22 02:00 |  | 01 56 39-45 Arborist Compliance Report - 07172020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-07-22 02:00 |  | Capture.JPG
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-27 02:00 |  | 01 56 39-45 Arborist Compliance Report - 07172020 - SWIFT_pop.pdf
01 56 39-046-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-046-00 Arborist Compliance Report - 07312020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-03 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-08-17 | 2020-08-18 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-08-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07306 | Received | For Review | 2020-08-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-17 | Submittal Number: 01 56 39-46.0 From: DOMINGO SAMPAYO Final Due Date: 08/21/20 Subject: ARBORIST COMPLIANCE REPORT - 07312020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 09746 | Forwarded | For Review | 2020-08-03 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-08-10 | Submittal Number: 01 56 39-46.0 From: DOMINGO SAMPAYO Final Due Date: 08/21/20 Subject: ARBORIST COMPLIANCE REPORT - 07312020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 07599 | Review Response | Approved | 2020-08-18 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 10117 | Responded and Closed | Approved | 2020-08-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-31 |  | 01 56 39-46 Arborist Compliance Report - 07312020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-31 |  | 01 56 39-46 Arborist Compliance Report - 07312020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-07-30 02:00 |  | 01 56 39-46 Arborist Compliance Report - 07312020.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-18 02:00 |  | 01 56 39-46 Arborist Compliance Report - 07312020 - SWIFT_pop.pdf
01 56 39-047-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-047-00 Arborist Compliance Report - 08142020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-09-09 | 2020-08-26 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07758 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-09-09 | Submittal Number: 01 56 39-47.0 From: DOMINGO SAMPAYO Final Due Date: 08/31/20 Subject: ARBORIST COMPLIANCE REPORT - 08142020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 10329 | Forwarded | For Review | 2020-08-26 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-09-02 | Submittal Number: 01 56 39-47.0 From: DOMINGO SAMPAYO Final Due Date: 08/31/20 Subject: ARBORIST COMPLIANCE REPORT - 08142020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 07764 | Review Response | Approved as Noted | 2020-08-26 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 10336 | Responded and Closed | Approved as Noted | 2020-08-26 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 01 56 39-47 Arborist Compliance Report - 08142020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-26 |  | 01 56 39-47 Arborist Compliance Report - 08142020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-08-26 02:00 |  | 01 56 39-47 Arborist Compliance Report - 08142020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-26 02:00 |  | 01 56 39-47 Arborist Compliance Report - 08142020 - SWIFT-pop.pdf
01 56 39-048-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-048-00 Arborist Compliance Report - 08282020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-31 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-09-15 07:00 | 2020-09-02 | 3 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07842 | Received | For Review | 2020-08-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-09-15 07:00 | Submittal Number: 01 56 39-48.0 From: DOMINGO SAMPAYO Final Due Date: 09/14/20 Subject: ARBORIST COMPLIANCE REPORT - 08282020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 10425 | Forwarded | For Review | 2020-08-29 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-09-07 | Submittal Number: 01 56 39-48.0 From: DOMINGO SAMPAYO Final Due Date: 09/14/20 Subject: ARBORIST COMPLIANCE REPORT - 08282020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 07893 | Review Response | Approved | 2020-09-01 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous); Shaina Burris (Populous) |  |  | Info Exchange
| 10495 | Responded and Closed | Approved | 2020-09-02 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-28 |  | 01 56 39-48 Arborist Compliance Report - 08282020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-28 |  | 01 56 39-48 Arborist Compliance Report - 08282020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-08-28 |  | 01 56 39-48 Arborist Compliance Report - 08282020.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-02 |  | 01 56 39-48 Arborist Compliance Report - 08282020 - SWIFT_POP.pdf
01 56 39-049-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-049-00 Arborist Compliance Report - 09112020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-14 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-09-28 | 2020-09-22 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-09-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08067 | Received | For Review | 2020-09-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-09-28 | Submittal Number: 01 56 39-49.0 From: DOMINGO SAMPAYO Final Due Date: 09/28/20 Subject: ARBORIST COMPLIANCE REPORT - 09112020 Description: ***IRRIGATION SUBCONTRACTOR WILL BE INSPECTING THE IRRIGATION SYSTEM ON MONDAY, 09/14/2020 TO MAKE SURE IT IS WORKING AS REQUIRED. **WE HAVE COMMUNICATED TO THE RESPONSIBLE TRADE THAT THE BURLAP NEEDS TO BE WETTED TO THE FULL EXTEND AND NEEDED. Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 10733 | Forwarded | For Review | 2020-09-14 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-09-21 | Submittal Number: 01 56 39-49.0 From: DOMINGO SAMPAYO Final Due Date: 09/28/20 Subject: ARBORIST COMPLIANCE REPORT - 09112020 Description: ***IRRIGATION SUBCONTRACTOR WILL BE INSPECTING THE IRRIGATION SYSTEM ON MONDAY, 09/14/2020 TO MAKE SURE IT IS WORKING AS REQUIRED. **WE HAVE COMMUNICATED TO THE RESPONSIBLE TRADE THAT THE BURLAP NEEDS TO BE WETTED TO THE FULL EXTEND AND NEEDED. Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 08261 | Review Response | Approved as Noted | 2020-09-22 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 10965 | Responded and Closed | Approved as Noted | 2020-09-22 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-11 |  | 01 56 39-49 Arborist Compliance Report - 09112020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-11 |  | 01 56 39-49 Arborist Compliance Report - 09112020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-09-22 02:00 |  | 01 56 39-49 Arborist Compliance Report - 09112020 - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-22 02:00 |  | 01 56 39-49 Arborist Compliance Report - 09112020 - SWIFT_pop.pdf
01 56 39-050-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-050-00 Arborist Compliance Report - 09252020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-10-09 | 2020-09-30 | 6 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-09-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08352 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-09 | Submittal Number: 01 56 39-50.0 From: DOMINGO SAMPAYO Final Due Date: 10/12/20 Subject: ARBORIST COMPLIANCE REPORT - 09252020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 11065 | Forwarded | For Review | 2020-09-25 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-10-02 | Submittal Number: 01 56 39-50.0 From: DOMINGO SAMPAYO Final Due Date: 10/12/20 Subject: ARBORIST COMPLIANCE REPORT - 09252020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 08439 | Review Response | Approved as Noted | 2020-09-29 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 11181 | Responded and Closed | Approved as Noted | 2020-09-30 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 01 56 39-50 Arborist Compliance Report - 09252020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 01 56 39-50 Arborist Compliance Report - 09252020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-09-24 02:00 |  | 01 56 39-50 Arborist Compliance Report - 09252020.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-30 02:00 |  | 01 56 39-50 Arborist Compliance Report - 09252020 - SWIFT_POP.pdf
01 56 39-051-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-051-00 Arborist Compliance Report - 10082020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-09 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-10-23 | 2020-10-22 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08691 | Received | For Review | 2020-10-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-23 | Submittal Number: 01 56 39-51.0 From: DOMINGO SAMPAYO Final Due Date: 10/26/20 Subject: ARBORIST COMPLIANCE REPORT - 10082020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 11476 | Forwarded | For Review | 2020-10-09 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-10-16 | Submittal Number: 01 56 39-51.0 From: DOMINGO SAMPAYO Final Due Date: 10/26/20 Subject: ARBORIST COMPLIANCE REPORT - 10082020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 08932 | Review Response | Approved as Noted | 2020-10-21 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  |  | Info Exchange
| 11802 | Responded and Closed | Approved as Noted | 2020-10-22 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-08 02:00 |  | 01 56 39-51 Arborist Compliance Report - 10082020.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-08 02:00 |  | 01 56 39-51 Arborist Compliance Report - 10082020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-10-08 |  | 01 56 39-51 Arborist Compliance Report - 10082020.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-22 |  | 01 56 39-51 Arborist Compliance Report - 10082020 SWIFT_POP.pdf
01 56 39-053-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-053-00 Arborist Compliance Report - 10232020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-26 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-11-09 | 2020-10-30 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-10-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08990 | Received | For Review | 2020-10-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-11-09 | Submittal Number: 01 56 39-53.0 From: DOMINGO SAMPAYO Final Due Date: 11/09/20 Subject: ARBORIST COMPLIANCE REPORT - 10232020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 11862 | Forwarded | For Review | 2020-10-26 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-11-02 | Submittal Number: 01 56 39-53.0 From: DOMINGO SAMPAYO Final Due Date: 11/09/20 Subject: ARBORIST COMPLIANCE REPORT - 10232020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 09120 | Review Response | Approved as Noted | 2020-10-27 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 12034 | Responded and Closed | Approved as Noted | 2020-10-30 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-23 |  | 01 56 39-53 Arborist Compliance Report - 10232020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-23 |  | 01 56 39-53 Arborist Compliance Report - 10232020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-10-22 02:00 |  | 01 56 39-53 Arborist Compliance Report - 10232020.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-30 02:00 |  | 01 56 39-53 Arborist Compliance Report - 10232020 - SWIFT_pop.pdf
01 56 39-054-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-054-00 Arborist Compliance Report - 11062020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-09 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-11-23 | 2020-11-13 | 5 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-11-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09301 | Received | For Review | 2020-11-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-11-23 | Submittal Number: 01 56 39-54.0 From: DOMINGO SAMPAYO Final Due Date: 11/23/20 Subject: ARBORIST COMPLIANCE REPORT - 11062020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 12273 | Forwarded | For Review | 2020-11-09 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-11-16 | Submittal Number: 01 56 39-54.0 From: DOMINGO SAMPAYO Final Due Date: 11/23/20 Subject: ARBORIST COMPLIANCE REPORT - 11062020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 09423 | Review Response | Approved as Noted | 2020-11-12 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 12425 | Responded and Closed | Approved as Noted | 2020-11-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 01 56 39-54 Arborist Compliance Report - 11062020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 01 56 39-54 Arborist Compliance Report - 11062020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-11-05 02:00 |  | 01 56 39-54 Arborist Compliance Report - 11062020.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-13 02:00 |  | 01 56 39-54 Arborist Compliance Report - 11062020 - SWIFT_pop.pdf
01 56 39-055-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-055-00 Arborist Compliance Report - 11202020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - No Action Taken or Required |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-12-21 | 2020-12-08 | 2 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-12-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09925 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-21 | Submittal Number: 01 56 39-55.0 From: DOMINGO SAMPAYO Final Due Date: 12/07/20 Subject: ARBORIST COMPLIANCE REPORT - 11202020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 13004 | Forwarded | For Review | 2020-12-04 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-12-11 | Submittal Number: 01 56 39-55.0 From: DOMINGO SAMPAYO Final Due Date: 12/07/20 Subject: ARBORIST COMPLIANCE REPORT - 11202020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 13120 | Responded and Closed | No Action Taken or Required | 2020-12-08 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Submittal 01 56 39-056 has been reviewed and approved as noted on 12/7, superseding this submittal. Received for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-04 |  | 01 56 39-55 Arborist Compliance Report - 11202020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-04 |  | 01 56 39-55 Arborist Compliance Report - 11202020.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-08 02:00 |  | 01 56 39-55 Arborist Compliance Report - 11202020_POP.pdf
01 56 39-056-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-056-00 Arborist Compliance Report - 12042020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-12-21 | 2020-12-07 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-12-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09941 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-21 | Submittal Number: 01 56 39-56.0 From: DOMINGO SAMPAYO Final Due Date: 12/21/20 Subject: 01 56 39-55 REVISION 0: ARBORIST COMPLIANCE REPORT - 12042020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 13020 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-12-14 | Submittal Number: 01 56 39-56.0 From: DOMINGO SAMPAYO Final Due Date: 12/21/20 Subject: 01 56 39-55 REVISION 0: ARBORIST COMPLIANCE REPORT - 12042020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 09994 | Review Response | Approved as Noted | 2020-12-07 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 13078 | Responded and Closed | Approved as Noted | 2020-12-07 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 01 56 39-56 Arborist Compliance Report - 12042020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-07 |  | 01 56 39-56 Arborist Compliance Report - 12042020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-12-06 02:00 |  | 01 56 39-56 Arborist Compliance Report - 12042020.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-07 02:00 |  | 01 56 39-56 Arborist Compliance Report - 12042020 - SWIFT_pop.pdf
01 56 39-057-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-057-00 Arborist Compliance Report - 12182020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-18 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-01-13 | 2021-01-06 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-01-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10259 | Received | For Review | 2020-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2021-01-13 | Submittal Number: 01 56 39-57.0 From: DOMINGO SAMPAYO Final Due Date: 01/01/21 Subject: ARBORIST COMPLIANCE REPORT - 12182020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 13414 | Forwarded | For Review | 2020-12-18 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-12-25 | Submittal Number: 01 56 39-57.0 From: DOMINGO SAMPAYO Final Due Date: 01/01/21 Subject: ARBORIST COMPLIANCE REPORT - 12182020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 10489 | Review Response | Approved as Noted | 2021-01-06 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  |  | Info Exchange
| 13691 | Responded and Closed | Approved as Noted | 2021-01-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-18 02:00 |  | 01 56 39-57 Arborist Compliance Report - 12182020.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-12-18 02:00 |  | 01 56 39-57 Arborist Compliance Report - 12182020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-12-18 02:00 |  | 01 56 39-57 Arborist Compliance Report - 12182020.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-06 02:00 |  | 01 56 39-57 Arborist Compliance Report - 12182020 - SWIFT_pop.pdf
01 56 39-058-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-058-00 Arborist Compliance Report - 12312020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-19 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-02 | 2021-01-19 | 1 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-01-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10758 | Received | For Review | 2021-01-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-02 | Submittal Number: 01 56 39-58.0 From: DOMINGO SAMPAYO Final Due Date: 01/14/21 Subject: ARBORIST COMPLIANCE REPORT - 12312020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 13990 | Forwarded | For Review | 2021-01-15 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-01-22 | Submittal Number: 01 56 39-58.0 From: DOMINGO SAMPAYO Final Due Date: 01/14/21 Subject: ARBORIST COMPLIANCE REPORT - 12312020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 10795 | Review Response | Approved as Noted | 2021-01-17 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 14043 | Responded and Closed | Approved as Noted | 2021-01-19 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-15 |  | 01 56 39-58 Arborist Compliance Report - 12312020.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-15 |  | 01 56 39-58 Arborist Compliance Report - 12312020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-01-14 02:00 |  | 01 56 39-58 Arborist Compliance Report - 12312020.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-19 02:00 |  | 01 56 39-58 Arborist Compliance Report - 12312020 - SWIFT_pop.pdf
01 56 39-059-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-059-00 Arborist Compliance Report - 01292020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-01 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-15 | 2021-02-09 | 9 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11054 | Received | For Review | 2021-02-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-02-15 | Submittal Number: 01 56 39-59.0 From: DOMINGO SAMPAYO Final Due Date: 02/15/21 Subject: ARBORIST COMPLIANCE REPORT - 01292020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 14353 | Forwarded | For Review | 2021-01-29 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-05 | Submittal Number: 01 56 39-59.0 From: DOMINGO SAMPAYO Final Due Date: 02/15/21 Subject: ARBORIST COMPLIANCE REPORT - 01292020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 11281 | Review Response | Approved as Noted | 2021-02-03 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | See comments in pdf. | Info Exchange
| 14625 | Responded and Closed | Approved as Noted | 2021-02-09 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-29 |  | 01 56 39-59 Arborist Compliance Report - 01292020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-29 |  | 01 56 39-59 Arborist Compliance Report - 01292020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-01-29 |  | 01 56 39-59 Arborist Compliance Report - 01292020.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-09 |  | 01 56 39-59 Arborist Compliance Report - 01292020 - SWIFT_POP.pdf
01 56 39-060-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-060-00 Arborist Compliance Report - 01152021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - No Action Taken or Required |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-22 | 2021-02-15 | 8 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11247 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-02-22 | Submittal Number: 01 56 39-60.0 From: DOMINGO SAMPAYO Final Due Date: 01/29/21 Subject: ARBORIST COMPLIANCE REPORT - 01152021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 14561 | Forwarded | For Review | 2021-02-08 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-15 | Submittal Number: 01 56 39-60.0 From: DOMINGO SAMPAYO Final Due Date: 01/29/21 Subject: ARBORIST COMPLIANCE REPORT - 01152021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 11443 | Review Response | No Action Taken or Required | 2021-02-10 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | As discussed this one was sent out of order and is superseded by the 2021-01-29 arborist report | Info Exchange
| 14824 | Responded and Closed | No Action Taken or Required | 2021-02-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: As discussed this one was sent out of order and is superseded by the 2021-01-29 arborist report | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-05 |  | 01 56 39-60 Arborist Compliance Report - 01152021.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-05 |  | 01 56 39-60 Arborist Compliance Report - 01152021.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-02-04 02:00 |  | 01 56 39-60 Arborist Compliance Report - 01152021.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-15 02:00 |  | 01 56 39-60 Arborist Compliance Report - 01152021 - SWIFT_POP.pdf
01 56 39-061-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-061-00 Arborist Compliance Report - 02122020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-26 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-12 | 2021-03-02 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11686 | Received | For Review | 2021-02-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-03-12 | Submittal Number: 01 56 39-61.0 From: DOMINGO SAMPAYO Final Due Date: 02/26/21 Subject: ARBORIST COMPLIANCE REPORT - 02122020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 15143 | Forwarded | For Review | 2021-03-01 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-08 | Submittal Number: 01 56 39-61.0 From: DOMINGO SAMPAYO Final Due Date: 02/26/21 Subject: ARBORIST COMPLIANCE REPORT - 02122020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 11736 | Review Response | Approved as Noted | 2021-03-01 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | See comments on attached pdf. MAM ensure Seattle Center is notified prior to any work within N Courtyard trees. | Info Exchange
| 15208 | Responded and Closed | Approved as Noted | 2021-03-02 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See comments on attached pdf. MAM ensure Seattle Center is notified prior to any work within N Courtyard trees. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-26 02:00 |  | 01 56 39-61 Arborist Compliance Report - 02122020.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-01 02:00 |  | 01 56 39-61 Arborist Compliance Report - 02122020_mam.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-01 |  | 01 56 39-61 Arborist Compliance Report - 02122020_mam.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-26 |  | 01 56 39-61 Arborist Compliance Report - 02122020.pdf
01 56 39-062-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-062-00 Arborist Compliance Report - 02262020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - No Action Taken or Required |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-29 | 2021-03-22 | 8 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11983 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-03-29 | Submittal Number: 01 56 39-62.0 From: DOMINGO SAMPAYO Final Due Date: 03/26/21 Subject: ARBORIST COMPLIANCE REPORT - 02262020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 15523 | Forwarded | For Review | 2021-03-15 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-22 | Submittal Number: 01 56 39-62.0 From: DOMINGO SAMPAYO Final Due Date: 03/26/21 Subject: ARBORIST COMPLIANCE REPORT - 02262020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 12149 | Review Response | No Action Taken or Required | 2021-03-16 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Submitted late, refer to following report for comments. | Info Exchange
| 15720 | Responded and Closed | No Action Taken or Required | 2021-03-22 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Submitted late, refer to following report for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-12 |  | 01 56 39-62 Arborist Compliance Report - 02262020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-12 |  | 01 56 39-62 Arborist Compliance Report - 02262020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-11 02:00 |  | 01 56 39-62 Arborist Compliance Report - 02262020.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-22 02:00 |  | 01 56 39-62 Arborist Compliance Report - 02262020 - SWIFT_POP.pdf
01 56 39-063-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-063-00 Arborist Compliance Report - 03122020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-12 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-26 | 2021-03-22 | 11 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11984 | Received | For Review | 2021-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-03-26 | Submittal Number: 01 56 39-63.0 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: ARBORIST COMPLIANCE REPORT - 03122020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 15524 | Forwarded | For Review | 2021-03-15 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-22 | Submittal Number: 01 56 39-63.0 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: ARBORIST COMPLIANCE REPORT - 03122020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 12150 | Review Response | Approved as Noted | 2021-03-16 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | See notes in attached pdf. | Info Exchange
| 15722 | Responded and Closed | Approved as Noted | 2021-03-22 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See notes in attached pdf. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-12 |  | 01 56 39-63 Arborist Compliance Report - 03122020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-12 |  | 01 56 39-63 Arborist Compliance Report - 03122020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-11 02:00 |  | 01 56 39-63 Arborist Compliance Report - 03122020.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-22 02:00 |  | 01 56 39-63 Arborist Compliance Report - 03122020 - SWIFT_POP.pdf
01 56 39-064-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-064-00 Arborist Compliance Report - 03262020 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - No Action Taken or Required |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-04-23 | 2021-04-26 | 18 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12501 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-23 | Submittal Number: 01 56 39-64.0 From: DOMINGO SAMPAYO Final Due Date: 04/09/21 Subject: ARBORIST COMPLIANCE REPORT - 03262020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 16189 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-04-15 | Submittal Number: 01 56 39-64.0 From: DOMINGO SAMPAYO Final Due Date: 04/09/21 Subject: ARBORIST COMPLIANCE REPORT - 03262020 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 12792 | Review Response | No Action Taken or Required | 2021-04-26 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 16532 | Responded and Closed | No Action Taken or Required | 2021-04-26 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 01 56 39-64 Arborist Compliance Report - 03262020.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 01 56 39-64 Arborist Compliance Report - 03262020.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-04-07 02:00 |  | 01 56 39-64 Arborist Compliance Report - 03262020.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-26 02:00 |  | 01 56 39-64 Arborist Compliance Report - 03262020 - SWIFT_POP.pdf
01 56 39-065-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-065-00 Arborist Compliance Report - 04092021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-12 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-04-26 | 2021-04-26 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12530 | Received | For Review | 2021-04-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-26 | Submittal Number: 01 56 39-65.0 From: DOMINGO SAMPAYO Final Due Date: 04/26/21 Subject: ARBORIST COMPLIANCE REPORT - 04092021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 16232 | Forwarded | For Review | 2021-04-12 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-04-19 | Submittal Number: 01 56 39-65.0 From: DOMINGO SAMPAYO Final Due Date: 04/26/21 Subject: ARBORIST COMPLIANCE REPORT - 04092021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 12793 | Review Response | Approved as Noted | 2021-04-26 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 16533 | Responded and Closed | Approved as Noted | 2021-04-26 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-12 |  | 01 56 39-65 Arborist Compliance Report - 04092021.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-12 |  | 01 56 39-65 Arborist Compliance Report - 04092021.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-04-11 02:00 |  | 01 56 39-65 Arborist Compliance Report - 04092021.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-26 02:00 |  | 01 56 39-65 Arborist Compliance Report - 04092021 - SWIFT_POP.pdf
01 56 39-066-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-066-00 Arborist Compliance Report - 04262021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-27 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-05-11 | 2021-05-06 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12806 | Received | For Review | 2021-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-05-11 | Submittal Number: 01 56 39-66.0 From: DOMINGO SAMPAYO Final Due Date: 05/11/21 Subject: ARBORIST COMPLIANCE REPORT - 04262021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 16553 | Forwarded | For Review | 2021-04-27 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-05-04 | Submittal Number: 01 56 39-66.0 From: DOMINGO SAMPAYO Final Due Date: 05/11/21 Subject: ARBORIST COMPLIANCE REPORT - 04262021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 12973 | Review Response | Approved as Noted | 2021-05-06 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 16792 | Responded and Closed | Approved as Noted | 2021-05-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-27 |  | 01 56 39-66 Arborist Compliance Report - 04262021.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-27 |  | 01 56 39-66 Arborist Compliance Report - 04262021.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-04-26 02:00 |  | 01 56 39-66 Arborist Compliance Report - 04262021.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-05-06 02:00 |  | 01 56 39-66 Arborist Compliance Report - 04262021 - SWIFT_POP.pdf
01 56 39-067-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-067-00 Arborist Compliance Report - 05102021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-12 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-05-26 | 2021-06-01 | 21 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-06-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13063 | Received | For Review | 2021-05-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-26 | Submittal Number: 01 56 39-67.0 From: CHRISTIAN GENEROSA Final Due Date: 05/25/21 Subject: ARBORIST COMPLIANCE REPORT - 05102021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 16899 | Forwarded | For Review | 2021-05-12 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-05-19 | Submittal Number: 01 56 39-67.0 From: CHRISTIAN GENEROSA Final Due Date: 05/25/21 Subject: ARBORIST COMPLIANCE REPORT - 05102021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 13342 | Review Response | Approved as Noted | 2021-05-27 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | See remarks in attached pdf. A number management issues have been highlighted related to work within CRZ. | Info Exchange
| 17263 | Responded and Closed | Approved as Noted | 2021-06-01 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See remarks in attached pdf. A number management issues have been highlighted related to work within CRZ. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | 2021-05-11 015639-0067-00 Arborist Compliance Report-05102021_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-11 |  | 2021-05-11 015639-0067-00 Arborist Compliance Report-05102021_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-10 02:00 |  | 2021-05-11 015639-0067-00 Arborist Compliance Report-05102021_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-01 02:00 |  | 015639-0067-00 Arborist Compliance Report-05102021_MAM - SWIFT-POP.pdf
01 56 39-068-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-068-00 Arborist Compliance Report - 05242021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-01 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-06-15 | 2021-06-15 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13311 | Received | For Review | 2021-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-15 | Submittal Number: 01 56 39-68.0 From: CHRISTIAN GENEROSA Final Due Date: 06/08/21 Subject: ARBORIST COMPLIANCE REPORT - 05242021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 17225 | Forwarded | For Review | 2021-06-01 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-08 | Submittal Number: 01 56 39-68.0 From: CHRISTIAN GENEROSA Final Due Date: 06/08/21 Subject: ARBORIST COMPLIANCE REPORT - 05242021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 13534 | Review Response | Approved | 2021-06-15 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 17513 | Responded and Closed | Approved | 2021-06-15 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-28 |  | 01 56 39-68 Arborist Compliance Report - 05242021.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-28 |  | 01 56 39-68 Arborist Compliance Report - 05242021.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-27 02:00 |  | 01 56 39-68 Arborist Compliance Report - 05242021.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-15 02:00 |  | 01 56 39-68 Arborist Compliance Report - 05242021 - SWIFT_POP.pdf
01 56 39-069-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-069-00 Arborist Compliance Report - 06072021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-08 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-06-22 | 2021-06-15 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13460 | Received | For Review | 2021-06-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-06-22 | Submittal Number: 01 56 39-69.0 From: DOMINGO SAMPAYO Final Due Date: 06/22/21 Subject: ARBORIST COMPLIANCE REPORT - 06072021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 17402 | Forwarded | For Review | 2021-06-08 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-15 | Submittal Number: 01 56 39-69.0 From: DOMINGO SAMPAYO Final Due Date: 06/22/21 Subject: ARBORIST COMPLIANCE REPORT - 06072021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 13535 | Review Response | Approved as Noted | 2021-06-15 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | See comments in attached pdf for items for follow up. | Info Exchange
| 17514 | Responded and Closed | Approved as Noted | 2021-06-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See comments in attached pdf for items for follow up. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-08 |  | 01 56 39-69 Arborist Compliance Report - 06072021.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-08 |  | 01 56 39-69 Arborist Compliance Report - 06072021.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-06-07 02:00 |  | 01 56 39-69 Arborist Compliance Report - 06072021.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-15 02:00 |  | 01 56 39-69 Arborist Compliance Report - 06072021 - SWIFT_POP.pdf
01 56 39-070-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-070-00 Arborist Compliance Report - 06182021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-21 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-07-06 07:00 | 2021-07-08 | 18 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13569 | Received | For Review | 2021-06-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-06 07:00 | Submittal Number: 01 56 39-70.0 From: DOMINGO SAMPAYO Final Due Date: 07/05/21 Subject: ARBORIST COMPLIANCE REPORT - 06182021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 17572 | Forwarded | For Review | 2021-06-18 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-25 | Submittal Number: 01 56 39-70.0 From: DOMINGO SAMPAYO Final Due Date: 07/05/21 Subject: ARBORIST COMPLIANCE REPORT - 06182021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 13854 | Review Response | Approved | 2021-07-06 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | Refer to report 071 for current comments. | Info Exchange
| 17932 | Responded and Closed | Approved | 2021-07-08 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Refer to report 071 for current comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-18 |  | 01 56 39-70 Arborist Compliance Report - 06182021.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-18 |  | 01 56 39-70 Arborist Compliance Report - 06182021.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-06-17 02:00 |  | 01 56 39-70 Arborist Compliance Report - 06182021.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-08 02:00 |  | 01 56 39-70 Arborist Compliance Report - 06182021 - SWIFT_POP.pdf
01 56 39-071-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-071-00 Arborist Compliance Report -07022021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-06 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-07-20 | 2021-07-08 | 3 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13801 | Received | For Review | 2021-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-20 | Submittal Number: 01 56 39-71.0 From: JAMIE ELROD Final Due Date: 07/20/21 Subject: ARBORIST COMPLIANCE REPORT -07022021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 17873 | Forwarded | For Review | 2021-07-06 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-07-13 | Submittal Number: 01 56 39-71.0 From: JAMIE ELROD Final Due Date: 07/20/21 Subject: ARBORIST COMPLIANCE REPORT -07022021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 13863 | Review Response | Approved as Noted | 2021-07-06 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | 1. A significant number of areas have had protection fencing removed. Fencing must be reinstalled at all areas of protection immediately following work. 2. Arborist must be notified of work occurring within tree protection areas. 3. Due to impacts within unsecured tree protection fencing areas, contractor to provide evaluation of soils requiring decompaction. 4. Contractor please confirm all irrigation is currently operational. Continue to hand water as required for trees without irrigation. 5. Materials must not be stored within tree protection areas. All materials stored within tree protection areas must be removed. | Info Exchange
| 17940 | Responded and Closed | Approved as Noted | 2021-07-08 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: 1. A significant number of areas have had protection fencing removed. Fencing must be reinstalled at all areas of protection immediately following work. 2. Arborist must be notified of work occurring within tree protection areas. 3. Due to impacts within unsecured tree protection fencing areas, contractor to provide evaluation of soils requiring decompaction. 4. Contractor please confirm all irrigation is currently operational. Continue to hand water as required for trees without irrigation. 5. Materials must not be stored within tree protection areas. All materials stored within tree protection areas must be removed. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-06 |  | 01 56 39-71 Arborist Compliance Report 07-02-2021.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-06 |  | 01 56 39-71 Arborist Compliance Report 07-02-2021.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-07-08 02:00 |  | 01 56 39-71 Arborist Compliance Report 07-02-2021 - SWIFT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-08 02:00 |  | 01 56 39-71 Arborist Compliance Report 07-02-2021 - SWIFT_POP.pdf
01 56 39-072-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-072-00 Arborist Compliance Report -07162021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-19 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-08-02 07:00 | 2021-08-02 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-08-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13991 | Received | For Review | 2021-07-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-08-02 07:00 | Submittal Number: 01 56 39-72.0 From: JAMIE ELROD Final Due Date: 07/30/21 Subject: ARBORIST COMPLIANCE REPORT -07162021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 18096 | Forwarded | For Review | 2021-07-16 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-07-23 | Submittal Number: 01 56 39-72.0 From: JAMIE ELROD Final Due Date: 07/30/21 Subject: ARBORIST COMPLIANCE REPORT -07162021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 14184 | Review Response | Approved as Noted | 2021-07-30 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | See notes within pdf. Follow up required for fill materials used at Thomas street back fill. Required fill is type-17 with rounded rock as noted in attached email. Also note open protection fencing remains uncorrected at SE corner as of 7/27. Roots do not have burlap and were unwetted. | Info Exchange
| 18337 | Responded and Closed | Approved as Noted | 2021-08-02 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See notes within pdf. Follow up required for fill materials used at Thomas street back fill. Required fill is type-17 with rounded rock as noted in attached email. Also note open protection fencing remains uncorrected at SE corner as of 7/27. Roots do not have burlap and were unwetted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-16 |  | 01 56 39-72 Arborist Compliance Report 07-16-2021.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-16 |  | 01 56 39-72 Arborist Compliance Report 07-16-2021.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-07-15 02:00 |  | 01 56 39-72 Arborist Compliance Report 07-16-2021.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-02 02:00 |  | 01 56 39-72 Arborist Compliance Report 07-16-2021 - SWIFT_POP.pdf
01 56 39-073-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-073-00 Arborist Compliance Report -07302021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-02 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-08-16 | 2021-08-26 | 25 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14189 | Received | For Review | 2021-08-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-08-16 | Submittal Number: 01 56 39-73.0 From: JAMIE ELROD Final Due Date: 08/16/21 Subject: ARBORIST COMPLIANCE REPORT -07302021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 18343 | Forwarded | For Review | 2021-08-02 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-09 | Submittal Number: 01 56 39-73.0 From: JAMIE ELROD Final Due Date: 08/16/21 Subject: ARBORIST COMPLIANCE REPORT -07302021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 14496 | Review Response | Approved as Noted | 2021-08-25 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 18691 | Responded and Closed | Approved as Noted | 2021-08-26 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa; Colin.Saiz@mortenson.com |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-02 |  | 01 56 39-73 Arborist Compliance Report.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-02 |  | 01 56 39-73 Arborist Compliance Report.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-08-01 02:00 |  | 01 56 39-73 Arborist Compliance Report.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-26 02:00 |  | 01 56 39-73 Arborist Compliance Report - SWIFT_pop.pdf
01 56 39-074-00 | 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION | 01 56 39-074-00 Arborist Compliance Report -08132021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-16 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-08-30 | 2021-08-26 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14384 | Received | For Review | 2021-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-08-30 | Submittal Number: 01 56 39-74.0 From: JAMIE ELROD Final Due Date: 08/30/21 Subject: ARBORIST COMPLIANCE REPORT -08132021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 18560 | Forwarded | For Review | 2021-08-16 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-23 | Submittal Number: 01 56 39-74.0 From: JAMIE ELROD Final Due Date: 08/30/21 Subject: ARBORIST COMPLIANCE REPORT -08132021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 14497 | Review Response | Approved as Noted | 2021-08-26 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | See comments in attached PDF. | Info Exchange
| 18692 | Responded and Closed | Approved as Noted | 2021-08-26 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa; Colin.Saiz@mortenson.com |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See comments in attached PDF. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-16 |  | 01 56 39-0074-00 Arborist Compliance Report 08-16-2021.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-16 |  | 01 56 39-0074-00 Arborist Compliance Report 08-16-2021.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-08-15 02:00 |  | 01 56 39-0074-00 Arborist Compliance Report 08-16-2021.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-26 02:00 |  | 01 56 39-0074-00 Arborist Compliance Report 08-16-2021 - SWIFT_pop.pdf
01 56 39-075-00 |  | 01 56 39-075-00 Arborist Compliance Report -08272021 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-01 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Shawn Stankewich (Swift and Company Landscape Arch) |  |  |  | 2021-09-15 | 2021-09-22 | 22 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-09-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14556 | Received | For Review | 2021-09-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-15 | Submittal Number: 01 56 39-75.0 From: JAMIE ELROD Final Due Date: 09/15/21 Subject: ARBORIST COMPLIANCE REPORT -08272021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 18768 | Forwarded | For Review | 2021-09-02 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-09-09 | Submittal Number: 01 56 39-75.0 From: JAMIE ELROD Final Due Date: 09/15/21 Subject: ARBORIST COMPLIANCE REPORT -08272021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 18934 | Forwarded | For Review | 2021-09-21 | Populous SCA_CCA | Shawn Stankewich (Swift and Company Landscape Arch) | 2021-09-15 | Submittal Number: 01 56 39-75.0 From: JAMIE ELROD Final Due Date: 09/15/21 Subject: ARBORIST COMPLIANCE REPORT -08272021 Description: Spec Section: 01 56 39 - TEMPORARY TREE AND PLANT PROTECTION Status: OPEN | Info Exchange
| 14689 | Review Response | Approved as Noted | 2021-09-22 | Shawn Stankewich (Swift and Company Landscape Arch) | Populous SCA_CCA |  | Please see response attached. Thanks! | Info Exchange
| 18943 | Responded and Closed | Approved as Noted | 2021-09-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Shawn Stankewich (Swift and Company Landscape Arch) Remarks: Please see response attached. Thanks! | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-01 02:00 |  | 01 56 39-0075-00 Arborist Compliance Report 08-27-2021.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-09-01 02:00 |  | 01 56 39-0075-00 Arborist Compliance Report 08-27-2021.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-09-01 02:00 |  | 01 56 39-0075-00 Arborist Compliance Report 08-27-2021.pdf
| Review Response |  | Shawn Stankewich (Swift and Company Landscape Arch) | 1 | 2021-09-01 |  | 01 56 39-0075-00 Arborist Compliance Report 08-27-2021.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-22 |  | 01 56 39-0075-00 Arborist Compliance Report 08-27-2021_SWIFT_POP.pdf
01 77 00-010-00 | 01 77 00 - CLOSEOUT PROCEDURES | 01 77 00-010-00 Millwork / Countertop Draft Warranties | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-25 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-08 | 2021-09-10 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-09-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14467 | Received | For Review | 2021-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-09-08 | Submittal Number: 01 77 00-10.0 From: MIKE SOLFELT Final Due Date: 09/08/21 Subject: MILLWORK / COUNTERTOP DRAFT WARRANTIES Description: Spec Section: 01 77 00 - CLOSEOUT PROCEDURES Status: OPEN | Info Exchange
| 18661 | Forwarded | For Review | 2021-08-25 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-01 | Submittal Number: 01 77 00-10.0 From: MIKE SOLFELT Final Due Date: 09/08/21 Subject: MILLWORK / COUNTERTOP DRAFT WARRANTIES Description: Spec Section: 01 77 00 - CLOSEOUT PROCEDURES Status: OPEN | Info Exchange
| 18854 | Responded and Closed | Approved as Noted | 2021-09-10 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | UPDATE SUBSTANTIAL COMPLETION DATES, SUBMIT IN THE FINAL O&M MANUALS PER CLOSEOUT PROCEDURES | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-25 |  | 01 77 00-10 Millwork and Countertop Draft Warranties.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-25 |  | 01 77 00-10 Millwork and Countertop Draft Warranties.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-09-10 |  | 01 77 00-10 Millwork and Countertop Draft Warranties_POP.pdf
02 41 19-001-00 | 02 41 19 - SELECTIVE DEMOLITION | 02 41 19-001-00 Selective Demo Schedule | Closed | Architectural | Joe Korchemniy (Mortenson Construction) | 2019-03-07 | Responded and Closed - Approved as Noted/Resubmit |  | Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-03-21 | 2019-03-14 | 8 |  | Record Copies; Transfers; Submittals | 02 41 19-001-00-01 - 02 41 19-001-00 Selective Demo Schedule | 7 |  | 2019-03-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01027 | Received | For Review | 2019-03-07 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-03-21 |  | Email
| 01870 | Forwarded | For Review | 2019-03-08 | SCA_CCA@populous.com | Tom Usher (Populous); Chris Minter; Josh Dobken (Populous) | 2019-03-15 |  | Info Exchange
| 01899 | Responded and Closed | Approved as Noted | 2019-03-14 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Approved as noted. | Info Exchange
| 01903 | Reopened | Additional Information | 2019-03-14 18:17 | Josh Dobken (Populous) |  |  | Revising to "Approved as Noted - Resubmit" - per Tom Usher's request.
| 01904 | Responded and Closed | Approved as Noted/Resubmit | 2019-03-14 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Reopened (Additional Information) by: Josh Dobken Remarks: Revising to "Approved as Noted - Resubmit" - per Tom Usher's request. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-08 |  | 02 41 19-001-0 Selective Demo Schedule.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-08 |  | 02 41 19-001-0 Selective Demo Schedule.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-03-14 |  | 02 41 19-001-0 Selective Demo Schedule_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-03-14 |  | 02 41 19-001-0 Selective Demo Schedule_POP.pdf
02 41 19-001-00-01 | 02 41 19 - SELECTIVE DEMOLITION | 02 41 19-001-00 Selective Demo Schedule | Expected - Overdue |  | Joe Korchemniy (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 02 41 19-001-00 - 02 41 19-001-00 Selective Demo Schedule | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-14 |  | 02 41 19-001-0 Selective Demo Schedule_POP.pdf
02 41 19-002-00 | 02 41 19 - SELECTIVE DEMOLITION | 02 41 19-002-00 Proposed Protection Measures | Closed | Architectural | Joe Korchemniy (Mortenson Construction) | 2019-03-13 | Responded and Closed - No Action Taken or Required |  | Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-03-27 | 2019-03-14 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-03-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01043 | Received | For Review | 2019-03-13 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-03-27 |  | Email
| 01892 | Forwarded | For Review | 2019-03-13 | SCA_CCA@populous.com | Tom Usher (Populous); Chris Minter; Josh Dobken (Populous) |  |  | Info Exchange
| 01906 | Responded and Closed | No Action Taken or Required | 2019-03-14 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-13 |  | 02 41 19-002-0 Proposed Protection Measures.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-13 |  | 02 41 19-002-0 Proposed Protection Measures.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-03-14 |  | 02 41 19-002-0 Proposed Protection Measures_POP.pdf
02 41 19-003-00 | 02 41 19 - SELECTIVE DEMOLITION | 02 41 19-003-00 Engineering Survey | Closed | Architectural | Joe Korchemniy (Mortenson Construction) | 2019-03-13 | Responded and Closed - No Action Taken or Required | [5 empty] | 2019-03-27 | 2019-03-14 | 2 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2019-03-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01044 | Received | For Review | 2019-03-13 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-03-27 |  | Email
| 01905 | Responded and Closed | No Action Taken or Required | 2019-03-14 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-13 |  | 02 41 19-3 Engineering survey (1).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-03-14 |  | 02 41 19-003-0 Engineering survey (1)_POP.pdf
02 41 19-003-01 | 02 41 19 - SELECTIVE DEMOLITION | 02 41 19-003-01: Engineering Survey (2) | Closed | Architectural | Joe Korchemniy (Mortenson Construction) | 2019-04-30 | Responded and Closed - No Action Taken or Required |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-05-14 | 2019-05-03 | 4 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2019-05-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01238 | Received | For Review | 2019-04-30 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) | 2019-05-14 | Demo plans (Which include engineering survey) for IFP (Art gallery), Pavilion (Includes below skatepark structure), Pavilion Restrooms, Blue Spruce, and West Court. | Info Exchange
| 02188 | Forwarded | For Review | 2019-04-29 | Josh Dobken (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-05-06 | Demo plans (Which include engineering survey) for IFP (Art gallery), Pavilion (Includes below skatepark structure), Pavilion Restrooms, Blue Spruce, and West Court. | Info Exchange
| 01258 | Review Response | No Action Taken or Required | 2019-05-03 | Josh Dobken (Populous) | Josh Dobken (Populous) |  | See attached | Info Exchange
| 02220 | Responded and Closed | No Action Taken or Required | 2019-05-03 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Response (No Action Taken or Required) from: Josh Dobken (Populous) Remarks: See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-29 |  | Submittal #02 41 19-3.1 Engineering Survey (2).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-04-29 |  | Submittal #02 41 19-3.1 Engineering Survey (2).pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2019-05-03 |  | Submittal #02 41 19-3.1 Engineering Survey (2)_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-04-29 |  | Submittal #02 41 19-3.1 Engineering Survey (2).pdf
02 41 19-004-00 | 02 41 19 - SELECTIVE DEMOLITION | 02 41 19-004-00 Hydro-Demo Extents for Y-Column and Buttress Foundations | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-06 | Responded and Closed - Revise and Resubmit |  | Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Brian MacRae (Thornton Tomasetti), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-20 | 2019-08-22 | 17 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-08-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01997 | Received | For Review | 2019-08-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-08-20 | Submittal Number: 02 41 19-4.0 From: JOE KORCHEMNIY Final Due Date: 08/20/19 Subject: HYDRO-DEMO EXTENTS FOR Y-COLUMN AND BUTTRESS FOUNDATIONS Description: SEE ATTACHED DRAWINGS WITH MARK UPS AND NOTES RELATED TO DEMOLITION EXTENTS OF Y-COLUMN AND BUTTRESS FOOTINGS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 03150 | Forwarded | For Review | 2019-08-08 | Shaina Burris (Populous) | Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-08-15 | Submittal Number: 02 41 19-4.0 From: JOE KORCHEMNIY Final Due Date: 08/20/19 Subject: HYDRO-DEMO EXTENTS FOR Y-COLUMN AND BUTTRESS FOUNDATIONS Description: SEE ATTACHED DRAWINGS WITH MARK UPS AND NOTES RELATED TO DEMOLITION EXTENTS OF Y-COLUMN AND BUTTRESS FOOTINGS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 03261 | Forwarded | For Review | 2019-08-15 | Josh Dobken (Populous) | Brian MacRae (Thornton Tomasetti) | 2019-08-20 | Submittal Number: 02 41 19-4.0 From: JOE KORCHEMNIY Final Due Date: 08/20/19 Subject: HYDRO-DEMO EXTENTS FOR Y-COLUMN AND BUTTRESS FOUNDATIONS Description: SEE ATTACHED DRAWINGS WITH MARK UPS AND NOTES RELATED TO DEMOLITION EXTENTS OF Y-COLUMN AND BUTTRESS FOOTINGS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Email
| 03365 | Forwarded | For Review | 2019-08-21 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Mich... | 2019-08-20 | Submittal Number: 02 41 19-4.0 From: JOE KORCHEMNIY Final Due Date: 08/20/19 Subject: HYDRO-DEMO EXTENTS FOR Y-COLUMN AND BUTTRESS FOUNDATIONS Description: SEE ATTACHED DRAWINGS WITH MARK UPS AND NOTES RELATED TO DEMOLITION EXTENTS OF Y-COLUMN AND BUTTRESS FOOTINGS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 02169 | Review Response | Revise and Resubmit | 2019-08-21 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | As discussed in phone call on 8/20/2019, we are requesting for Populous to verify the T/Slab elevation at the location of each Chevron. My further hand calculations generally agree with Tom’s sketches he attached earlier (see attached email), +/-1”. Please let us know what the elevations you determined are prior to returning the submittal to Mortenson. | Info Exchange
| 03374 | Responded and Closed | Revise and Resubmit | 2019-08-22 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Franz Kogler (Thornton Tomasetti) Remarks: As discussed in phone call on 8/20/2019, we are requesting for Populous to verify the T/Slab elevation at the location of each Chevron. My further hand calculations generally agree with Tom’s sketches he attached earlier (see attached email), +/-1”. Please let us know what the elevations you determined are prior to returning the submittal to Mortenson. POP/jhd - see attached bootleg architectural slab plans with dimensions indicating T.O. slab. Drawings to be issued in CCD on 8/23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-06 |  | Submittal #02 41 19-4.0 Hydro-Demo Extents.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-06 |  | Submittal #02 41 19-4.0 Hydro-Demo Extents.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-08-05 02:00 |  | Submittal #02 41 19-4.0 Hydro-Demo Extents.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-08-05 02:00 |  | Submittal #02 41 19-4.0 Hydro-Demo Extents.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-08-21 02:00 |  | Submittal #02 41 19-4.0 Hydro-Demo Extents_TTResponse.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-08-21 02:00 |  | chevron study.msg
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-22 02:00 |  | Submittal #02 41 19-4.0 Hydro-Demo Extents_TT_POP.pdf
02 41 19-004-01 | 02 41 19 - SELECTIVE DEMOLITION | 02 41 19-004-01 Hydro-Demo Extents for Y-Column and Buttress Foundations | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-26 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-09 | 2019-08-29 | 4 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-08-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02189 | Received | For Review | 2019-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-09-09 | Submittal Number: 02 41 19-4.1 From: JOE KORCHEMNIY Final Due Date: 08/30/19 Subject: HYDRO-DEMO EXTENTS FOR Y-COLUMN AND BUTTRESS FOUNDATIONS Description: SEE ATTACHED PLAN VIEW WITH CUT ELEVATIONS CALLED OUT FOR Y-COLUMNS AND CHEVRONS. LENGTH CALLED OUT IS MINIMUM REBAR THAT WILL BE EXPOSED AND CUT. AS NOTED, OUR INTENT TO IS TO PROVIDE AS MUCH ADDITIONAL REBAR AS POSSIBLE USING HYDRO DEMO TECHNIQUES. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 03391 | Forwarded | For Review | 2019-08-26 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-02 | Submittal Number: 02 41 19-4.1 From: JOE KORCHEMNIY Final Due Date: 08/30/19 Subject: HYDRO-DEMO EXTENTS FOR Y-COLUMN AND BUTTRESS FOUNDATIONS Description: SEE ATTACHED PLAN VIEW WITH CUT ELEVATIONS CALLED OUT FOR Y-COLUMNS AND CHEVRONS. LENGTH CALLED OUT IS MINIMUM REBAR THAT WILL BE EXPOSED AND CUT. AS NOTED, OUR INTENT TO IS TO PROVIDE AS MUCH ADDITIONAL REBAR AS POSSIBLE USING HYDRO DEMO TECHNIQUES. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 02242 | Review Response | Approved as Noted | 2019-08-28 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please see attached TT's response to 02 41 19-004-01. Samar | Info Exchange
| 03460 | Forwarded | For Review | 2019-08-29 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-09-05 | Submittal Number: 02 41 19-4.1 From: JOE KORCHEMNIY Final Due Date: 08/30/19 Subject: HYDRO-DEMO EXTENTS FOR Y-COLUMN AND BUTTRESS FOUNDATIONS Description: SEE ATTACHED PLAN VIEW WITH CUT ELEVATIONS CALLED OUT FOR Y-COLUMNS AND CHEVRONS. LENGTH CALLED OUT IS MINIMUM REBAR THAT WILL BE EXPOSED AND CUT. AS NOTED, OUR INTENT TO IS TO PROVIDE AS MUCH ADDITIONAL REBAR AS POSSIBLE USING HYDRO DEMO TECHNIQUES. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Email
| 03483 | Responded and Closed | Approved as Noted | 2019-08-29 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: Please see attached response to 02 41 19-004-01. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-26 |  | Submittal #02 41 19-4.1 Hydro-Demo Extents.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-26 |  | Submittal #02 41 19-4.1 Hydro-Demo Extents.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-08-25 02:00 |  | Submittal #02 41 19-4.1 Hydro-Demo Extents.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-08-25 02:00 |  | Submittal #02 41 19-4.1 Hydro-Demo Extents.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-29 02:00 |  | Submittal #02 41 19-4.1 Hydro-Demo Extents_TT_POP.pdf
02 41 19-005-00 | 02 41 19 - SELECTIVE DEMOLITION | 02 41 19-005-00 Hydro-Demo Extents for South Buttress | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-18 | Responded and Closed - Revise and Resubmit |  | Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Todd Spangler (Populous), Greg Briggs (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-10-02 | 2019-10-07 | 20 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2019-10-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02444 | Received | For Review | 2019-09-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-10-02 | Submittal Number: 02 41 19-5.0 From: JOE KORCHEMNIY Final Due Date: 10/02/19 Subject: HYDRO-DEMO EXTENTS FOR SOUTH BUTTRESS Description: DRAWING S3-42 MARKED UP TO CONFIRM HYDRO-DEMO EXTENTS FOR THE SOUTH BUTTRESS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 03705 | Forwarded | For Review | 2019-09-17 | Shaina Burris (Populous) | Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-09-24 | Submittal Number: 02 41 19-5.0 From: JOE KORCHEMNIY Final Due Date: 10/02/19 Subject: HYDRO-DEMO EXTENTS FOR SOUTH BUTTRESS Description: DRAWING S3-42 MARKED UP TO CONFIRM HYDRO-DEMO EXTENTS FOR THE SOUTH BUTTRESS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 03707 | Forwarded | For Review | 2019-09-17 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2019-09-24 | Submittal Number: 02 41 19-5.0 From: JOE KORCHEMNIY Final Due Date: 10/02/19 Subject: HYDRO-DEMO EXTENTS FOR SOUTH BUTTRESS Description: DRAWING S3-42 MARKED UP TO CONFIRM HYDRO-DEMO EXTENTS FOR THE SOUTH BUTTRESS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 03871 | Forwarded | For Review | 2019-09-30 | Todd Spangler (Populous) | Greg Briggs (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2019-10-01 | Submittal Number: 02 41 19-5.0 From: JOE KORCHEMNIY Final Due Date: 10/02/19 Subject: HYDRO-DEMO EXTENTS FOR SOUTH BUTTRESS Description: DRAWING S3-42 MARKED UP TO CONFIRM HYDRO-DEMO EXTENTS FOR THE SOUTH BUTTRESS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 03885 | Forwarded | For Review | 2019-09-30 | Josh Dobken (Populous) | Andy Tatkowski (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) | 2019-10-02 | Submittal Number: 02 41 19-5.0 From: JOE KORCHEMNIY Final Due Date: 10/02/19 Subject: HYDRO-DEMO EXTENTS FOR SOUTH BUTTRESS Description: DRAWING S3-42 MARKED UP TO CONFIRM HYDRO-DEMO EXTENTS FOR THE SOUTH BUTTRESS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 02661 | Review Response | Revise and Resubmit | 2019-10-03 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached submittal. Populous, please verify architectural acceptability. | Info Exchange
| 03975 | Forwarded | For Review | 2019-10-03 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2019-10-02 | Submittal Number: 02 41 19-5.0 From: JOE KORCHEMNIY Final Due Date: 10/02/19 Subject: HYDRO-DEMO EXTENTS FOR SOUTH BUTTRESS Description: DRAWING S3-42 MARKED UP TO CONFIRM HYDRO-DEMO EXTENTS FOR THE SOUTH BUTTRESS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 04006 | Responded and Closed | Revise and Resubmit | 2019-10-07 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Submittal #02 41 19-5.0 Hydro-Demo Extents for South Buttress.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-17 |  | Submittal #02 41 19-5.0 Hydro-Demo Extents for South Buttress.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-16 02:00 |  | Submittal #02 41 19-5.0 Hydro-Demo Extents for South Buttress.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-09-17 |  | Submittal #02 41 19-5.0 Hydro-Demo Extents for South Buttress.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-17 |  | Submittal #02 41 19-5.0 Hydro-Demo Extents for South Buttress.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-10-04 02:00 |  | Submittal #02 41 19-5.0 Hydro-Demo Extents for South Buttress_TT.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-16 02:00 |  | Submittal #02 41 19-5.0 Hydro-Demo Extents for South Buttress.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-07 |  | Submittal #02 41 19-5.0 Hydro-Demo Extents for South Buttress_TT_POP.pdf
02 41 19-005-01 | 02 41 19 - SELECTIVE DEMOLITION | 02 41 19-005-01 Hydro-Demo Extents for South Buttress | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-11 | Responded and Closed - Approved as Noted |  | Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Greg Briggs (Thornton Tomasetti), Todd Spangler (Populous), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-25 | 2019-10-16 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2019-10-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02729 | Received | For Review | 2019-10-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-10-25 | Submittal Number: 02 41 19-5.1 From: JOE KORCHEMNIY Final Due Date: 10/21/19 Subject: HYDRO-DEMO EXTENTS FOR SOUTH BUTTRESS Description: UPDATED SOUTH BUTTRESS EXTENTS SHOP DRAWING PER TT COMMENTS AND DISCUSSIONS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 04065 | Forwarded | For Review | 2019-10-11 | Shaina Burris (Populous) | Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-10-18 | Submittal Number: 02 41 19-5.1 From: JOE KORCHEMNIY Final Due Date: 10/21/19 Subject: HYDRO-DEMO EXTENTS FOR SOUTH BUTTRESS Description: UPDATED SOUTH BUTTRESS EXTENTS SHOP DRAWING PER TT COMMENTS AND DISCUSSIONS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 04119 | Forwarded | For Review | 2019-10-15 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Todd Spangler (Populous); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland... | 2019-10-22 | Submittal Number: 02 41 19-5.1 From: JOE KORCHEMNIY Final Due Date: 10/21/19 Subject: HYDRO-DEMO EXTENTS FOR SOUTH BUTTRESS Description: UPDATED SOUTH BUTTRESS EXTENTS SHOP DRAWING PER TT COMMENTS AND DISCUSSIONS. Spec Section: 02 41 19 - SELECTIVE DEMOLITION Status: OPEN | Info Exchange
| 02806 | Review Response | Approved as Noted | 2019-10-16 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | Populous, please note that TT used the PDF that Todd Spangler had already marked for Populous' review. Let us know if this is not acceptable. | Info Exchange
| 04158 | Responded and Closed | Approved as Noted | 2019-10-16 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-10 |  | Submittal #02 41 19-5.1 Hydro-Demo Extents for South Buttress.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-10 |  | Submittal #02 41 19-5.1 Hydro-Demo Extents for South Buttress.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-10-09 02:00 |  | Submittal #02 41 19-5.1 Hydro-Demo Extents for South Buttress.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-10-09 02:00 |  | Submittal #02 41 19-5.1 Hydro-Demo Extents for South Buttress.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-16 02:00 |  | Submittal #02 41 19-5.1 Hydro-Demo Extents for South Buttress_POP_TT.pdf
03 10 00-008-00 | 03 10 00 - CONCRETE FORMWORK | 03 10 00-008-00 Y-Column and Chevron Extension Formwork Shops and Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2019-12-05 08:00 | 2019-11-25 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-11-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03267 | Received | For Review | 2019-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers | 2019-12-05 08:00 | Submittal Number: 03 10 00-8.0 From: CHRISTIAN ALBERS Final Due Date: 12/03/19 Subject: Y-COLUMN AND CHEVRON EXTENSION FORMWORK SHOPS AND PRODUCT DATA Description: Spec Section: 03 10 00 - CONCRETE FORMWORK Status: OPEN | Info Exchange
| 04714 | Forwarded | For Review | 2019-11-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-26 | Submittal Number: 03 10 00-8.0 From: CHRISTIAN ALBERS Final Due Date: 12/03/19 Subject: Y-COLUMN AND CHEVRON EXTENSION FORMWORK SHOPS AND PRODUCT DATA Description: Spec Section: 03 10 00 - CONCRETE FORMWORK Status: OPEN | Info Exchange
| 03300 | Review Response | Approved as Noted | 2019-11-20 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Note that contents of submittal receive 2 separate actions from TT: · Formwork Drawings & Calculations (pg 2-37): Exceptions Noted · Construction Joints (pg 38): Approved as Noted Populous to review formwork type and tie pattern for architectural acceptability. | Info Exchange
| 04750 | Forwarded | For Review | 2019-11-20 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2019-11-27 | Submittal Number: 03 10 00-8.0 From: CHRISTIAN ALBERS Final Due Date: 12/03/19 Subject: Y-COLUMN AND CHEVRON EXTENSION FORMWORK SHOPS AND PRODUCT DATA Description: Spec Section: 03 10 00 - CONCRETE FORMWORK Status: OPEN | Info Exchange
| 04814 | Responded and Closed | Approved as Noted | 2019-11-25 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-19 |  | 03 10 00 - 08 Y-Column and Chevron Extension Formwork Shops & Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-19 |  | 03 10 00 - 08 Y-Column and Chevron Extension Formwork Shops & Product Data.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-11-18 02:00 |  | 03 10 00 - 08 Y-Column and Chevron Extension Formwork Shops & Product Data.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-18 02:00 |  | 03 10 00 - 08 Y-Column and Chevron Extension Formwork Shops & Product Data.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-11-25 |  | 03 10 00 - 08 Y-Column and Chevron Extension Formwork Shops_TT_POP.pdf
03 10 00-009-00 | 03 10 00 - CONCRETE FORMWORK | 03 10 00-009-00 South Buttress Mat Foundation Formwork Shops and Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-03 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-17 | 2019-12-04 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-12-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03438 | Received | For Review | 2019-12-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers | 2019-12-17 | Submittal Number: 03 10 00-9.0 From: CHRISTIAN ALBERS Final Due Date: 12/16/19 Subject: SOUTH BUTTRESS MAT FOUNDATION FORMWORK SHOPS AND PRODUCT DATA Description: Spec Section: 03 10 00 - CONCRETE FORMWORK Status: OPEN | Info Exchange
| 04910 | Forwarded | For Review | 2019-12-03 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-10 | Submittal Number: 03 10 00-9.0 From: CHRISTIAN ALBERS Final Due Date: 12/16/19 Subject: SOUTH BUTTRESS MAT FOUNDATION FORMWORK SHOPS AND PRODUCT DATA Description: Spec Section: 03 10 00 - CONCRETE FORMWORK Status: OPEN | Info Exchange
| 03500 | Review Response | No Action Taken or Required | 2019-12-03 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04963 | Responded and Closed | No Action Taken or Required | 2019-12-04 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-02 |  | 03 10 00 - 09 South Buttress Mat Foundation Formwork Shops and Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-02 |  | 03 10 00 - 09 South Buttress Mat Foundation Formwork Shops and Product Data.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-12-02 |  | 03 10 00 - 09 South Buttress Mat Foundation Formwork Shops and Product Data.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-12-04 |  | 03 10 00 - 09 South Buttress Mat Foundation_MAM_TT_POP.pdf
03 10 00-010-00 | 03 10 00 - CONCRETE FORMWORK | 03 10 00-010-00 Y-Column and Chevron Pile Cap Formwork Shops and Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-03 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-17 | 2019-12-05 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-12-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03449 | Received | For Review | 2019-12-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers | 2019-12-17 | Submittal Number: 03 10 00-10.0 From: CHRISTIAN ALBERS Final Due Date: 12/17/19 Subject: Y-COLUMN AND CHEVRON PILE CAP FORMWORK SHOPS AND PRODUCT DATA Description: Spec Section: 03 10 00 - CONCRETE FORMWORK Status: OPEN | Info Exchange
| 04924 | Forwarded | For Review | 2019-12-03 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-10 | Submittal Number: 03 10 00-10.0 From: CHRISTIAN ALBERS Final Due Date: 12/17/19 Subject: Y-COLUMN AND CHEVRON PILE CAP FORMWORK SHOPS AND PRODUCT DATA Description: Spec Section: 03 10 00 - CONCRETE FORMWORK Status: OPEN | Info Exchange
| 03513 | Review Response | Rejected | 2019-12-04 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Formwork Shops to be signed and sealed per Spec 031000 1.6.A.2.a. | Info Exchange
| 04980 | Responded and Closed | Rejected | 2019-12-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers |  | Response (Rejected) from: Matt Ross (Thornton Tomasetti) Remarks: Formwork Shops to be signed and sealed per Spec 031000 1.6.A.2.a. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-03 |  | 03 10 00 - 10 Y-Column and Chevron Pile Cap Formwork Shops and Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-03 |  | 03 10 00 - 10 Y-Column and Chevron Pile Cap Formwork Shops and Product Data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-02 02:00 |  | 03 10 00 - 10 Y-Column and Chevron Pile Cap Formwork Shops and Product Data.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-05 02:00 |  | 03 10 00 - 10 Y-Column and Chevron Pile Cap Formwork Shops and Product Data_TT_POP.pdf
03 10 00-010-01 | 03 10 00 - CONCRETE FORMWORK | 03 10 00-010-01 Y-Column and Chevron Pile Cap Formwork Shops and Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-02 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-16 | 2020-01-08 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03747 | Received | For Review | 2020-01-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers | 2020-01-16 | Submittal Number: 03 10 00-10.1 From: CHRISTIAN ALBERS Final Due Date: 01/06/20 Subject: Y-COLUMN AND CHEVRON PILE CAP FORMWORK SHOPS AND PRODUCT DATA Description: Spec Section: 03 10 00 - CONCRETE FORMWORK Status: OPEN | Info Exchange
| 05281 | Forwarded | For Review | 2020-01-02 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-09 | Submittal Number: 03 10 00-10.1 From: CHRISTIAN ALBERS Final Due Date: 01/06/20 Subject: Y-COLUMN AND CHEVRON PILE CAP FORMWORK SHOPS AND PRODUCT DATA Description: Spec Section: 03 10 00 - CONCRETE FORMWORK Status: OPEN | Info Exchange
| 03848 | Review Response | Approved | 2020-01-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05395 | Responded and Closed | Approved | 2020-01-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-30 |  | 03 10 00 - 10 Y-Column and Chevron Pile Cap Formwork Shops and Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-30 |  | 03 10 00 - 10 Y-Column and Chevron Pile Cap Formwork Shops and Product Data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-29 02:00 |  | 03 10 00 - 10 Y-Column and Chevron Pile Cap Formwork Shops and Product Data.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-08 02:00 |  | 03 10 00 - 10 Y-Column and Chevron Pile Cap Formwork Shops and Product Data_TT Review_POP.pdf
03 10 00-011-00 | 03 10 00 - CONCRETE FORMWORK | 03 10 00-011-00 Ice Slab Edge Formwork | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-03 08:00 | 2020-12-02 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09484 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 03 10 00-11.0 From: CHRISTIAN ALBERS Final Due Date: 11/30/20 Subject: ICE SLAB EDGE FORMWORK Description: SEE ATTACHED ICE SLAB EDGE FORMWORK SHOPS, PLEASE APPROVE THE RADIUS. Spec Section: 03 10 00 - CONCRETE FORMWORK Status: OPEN | Info Exchange
| 12502 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-24 | Submittal Number: 03 10 00-11.0 From: CHRISTIAN ALBERS Final Due Date: 11/30/20 Subject: ICE SLAB EDGE FORMWORK Description: SEE ATTACHED ICE SLAB EDGE FORMWORK SHOPS, PLEASE APPROVE THE RADIUS. Spec Section: 03 10 00 - CONCRETE FORMWORK Status: OPEN | Info Exchange
| 09847 | Review Response | Approved | 2020-12-02 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. Note Contractor to provide analysis per submittal notes. | Info Exchange
| 12930 | Responded and Closed | Approved | 2020-12-02 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 03 10 00 - 0011 - Ice Edge Formwork Shops.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 03 10 00 - 0011 - Ice Edge Formwork Shops.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-16 |  | 03 10 00 - 0011 - Ice Edge Formwork Shops.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-16 |  | 03 10 00 - 0011 - Ice Edge Formwork Shops.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-17 |  | Transmittal_Submittal - 03 10 00-011-00 (Forwarded).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-02 |  | 03 10 00 - 0011 - Ice Edge Formwork Shops_TT.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-02 |  | 03 10 00 - 0011 - Ice Edge Formwork Shops_TT-POP.pdf
03 20 00-001-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-001-00 South Parcel Detention Vault SD | Closed | Structural | Brooke Burcham (Mortenson Construction) | 2019-05-08 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Todd Spangler (Populous) |  |  |  | 2019-05-22 | 2019-05-23 | 16 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-05-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01284 | Received | For Review | 2019-05-08 | Brooke Burcham (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-22 |  | Email
| 02252 | Forwarded | For Review | 2019-05-08 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-15 |  | Info Exchange
| 01361 | Review Response | Approved as Noted | 2019-05-21 | Brian MacRae (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02346 | Forwarded | For Review | 2019-05-21 | SCA_CCA@populous.com | Todd Spangler (Populous) |  |  | Info Exchange
| 02373 | Responded and Closed | Approved as Noted | 2019-05-23 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction) |  | Response (Approved as Noted) from: Brian MacRae (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-05-08 |  | 03 20 00-001-00 South Parcel Detention Vault SD.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-08 |  | 03 20 00-001-00 South Parcel Detention Vault SD.pdf
| Review Response |  | Brian MacRae (Thornton Tomasetti) | 1 | 2019-05-08 |  | 03 20 00-001-00 South Parcel Detention Vault SD.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-08 |  | 03 20 00-001-00 South Parcel Detention Vault SD.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-23 02:00 |  | 03 20 00-001-00 South Parcel Detention Vault SD_TT_POP.pdf
03 20 00-002-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-002-00 Rebar Accessories Product Data | Closed | Structural | Brooke Burcham (Mortenson Construction) | 2019-05-09 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary |  |  |  | 2019-05-23 | 2019-05-28 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2019-05-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01298 | Received | For Review | 2019-05-09 | Brooke Burcham (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-23 |  | Email
| 02272 | Forwarded | For Review | 2019-05-09 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-16 |  | Info Exchange
| 01388 | Review Response | Approved | 2019-05-28 | Matt Ross (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02388 | Responded and Closed | Approved | 2019-05-28 | SCA_CCA@populous.com | Brooke Burcham (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-05-09 |  | 03 20 00-002-0 Rebar Accessories Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-09 |  | 03 20 00-002-0 Rebar Accessories Product Data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-05-09 |  | 03 20 00-002-0 Rebar Accessories Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-28 |  | 03 20 00-002-0 Rebar Accessories Product Data_TT review_POP.pdf
03 20 00-007-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-007-00 STABOX Product Data | Closed | Structural | Brooke Burcham (Mortenson Construction) | 2019-05-10 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary |  |  |  | 2019-05-24 | 2019-05-28 | 19 |  | Record Copies; Transfers; Submittals | 03 20 00-007-01 - 03 20 00-007-01 CONCRETE REINFORCEMENT - STABOX Product Data | 19 |  | 2019-05-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01303 | Received | For Review | 2019-05-10 | Brooke Burcham (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-24 |  | Email
| 02280 | Forwarded | For Review | 2019-05-10 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-17 |  | Info Exchange
| 01387 | Review Response | Approved as Noted | 2019-05-28 | Matt Ross (Thornton Tomasetti) | SCA_CCA@populous.com |  | Only approved at locations where #4 bars are used to dowel between slab and walls/columns. Please note there are numerous locations where #5 and #6 bars are being used. All bar dimensions shown on drawings are to be met and to overrule any dimensions shown in product data provided. | Info Exchange
| 02386 | Responded and Closed | Approved as Noted | 2019-05-28 | SCA_CCA@populous.com | Brooke Burcham (Mortenson Construction) |  | Only approved at locations where #4 bars are used to dowel between slab and walls/columns. Please note there are numerous locations where #5 and #6 bars are being used. All bar dimensions shown on drawings are to be met and to overrule any dimensions shown in product data provided. Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-05-10 |  | 03 20 00-007-00 STABOX Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-10 |  | 03 20 00-007-00 STABOX Product Data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-05-10 |  | 03 20 00-007-00 STABOX Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-28 |  | 03 20 00-007-00 STABOX Product Data_TT review_POP.pdf
03 20 00-007-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-007-01 CONCRETE REINFORCEMENT - STABOX Product Data | Closed | Structural | Brooke Burcham (Mortenson Construction) | 2019-06-06 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-06-20 | 2019-06-13 | 8 |  | Record Copies; Transfers; Submittals | 03 20 00-007-00 - 03 20 00-007-00 STABOX Product Data, 03 20 00-007-02 - 03 20 00-007-02 CONCRETE REINFORCEMENT - STABOX Product Data REV 2 | 8 |  | 2019-06-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01456 | Received | For Review | 2019-06-06 | Brooke Burcham (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-20 | Product Data for slab to vertical connections that utilize #4, #5, and #6 rebar. | Info Exchange
| 02462 | Forwarded | For Review | 2019-06-05 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-06-12 | Product Data for slab to vertical connections that utilize #4, #5, and #6 rebar. | Info Exchange
| 01514 | Review Response | Rejected | 2019-06-12 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Please provide engineering tables for #5 and #6 rebar. | Info Exchange
| 02534 | Responded and Closed | Rejected | 2019-06-13 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction) |  | Response (Rejected) from: Matt Ross (Thornton Tomasetti) Remarks: Please provide engineering tables for #5 and #6 rebar. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-06-05 |  | 032000-0007-1 Resubmittal STABOX Product Data.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-05 |  | 032000-0007-1 Resubmittal STABOX Product Data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-13 |  | 032000-0007-1 Resubmittal STABOX Product Data_TT REVIEW.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-13 |  | 032000-0007-1 Resubmittal STABOX Product Data_TT REVIEW_POP.pdf
03 20 00-007-02 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-007-02 CONCRETE REINFORCEMENT - STABOX Product Data REV 2 | Closed | Structural | Brooke Burcham (Mortenson Construction) | 2019-06-20 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti) |  |  |  | 2019-07-04 | 2019-06-21 | 2 |  | Record Copies; Transfers; Submittals | 03 20 00-007-01 - 03 20 00-007-01 CONCRETE REINFORCEMENT - STABOX Product Data | 2 | 2019-06-27 | 2019-06-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01581 | Received | For Review | 2019-06-20 | Brooke Burcham (Mortenson Construction) | Shaina Burris (Populous) | 2019-07-04 |  | Email
| 02620 | Forwarded | For Review | 2019-06-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fra... | 2019-06-27 |  | Info Exchange
| 02621 | Forwarded | For Review | 2019-06-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-06-27 |  | Info Exchange
| 01592 | Review Response | Approved | 2019-06-21 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 02633 | Responded and Closed | Approved | 2019-06-21 | Shaina Burris (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-06-20 |  | 03 20 00-007-02 CONCRETE REINFORCEMENT - STABOX Product Data REV 2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-06-20 |  | 03 20 00-007-02 CONCRETE REINFORCEMENT - STABOX Product Data REV 2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-06-20 |  | 03 20 00-007-02 CONCRETE REINFORCEMENT - STABOX Product Data REV 2.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-20 |  | 03 20 00-007-02 CONCRETE REINFORCEMENT - STABOX Product Data REV 2.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2019-06-21 |  | 03 20 00-007-02 CONCRETE REINFORCEMENT - STABOX Product Data REV 2_TT REVIEW_POP.pdf
03 20 00-009-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-009-00: Concrete Reinforcement - North Tunnel Cap | Closed | Structural | Brooke Burcham (Mortenson Construction) | 2019-05-28 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-06-11 | 2019-06-05 | 9 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-06-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01421 | Received | For Review | 2019-05-28 | Brooke Burcham (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-11 |  | Info Exchange
| 02423 | Forwarded | For Review | 2019-06-03 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-06-10 |  | Info Exchange
| 01454 | Review Response | Approved as Noted | 2019-06-05 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  | Please find attached TT's review of 03 20 00-009-00 | Info Exchange
| 02460 | Responded and Closed | Approved as Noted | 2019-06-05 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction) |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: Please find attached TT's review of 03 20 00-009-00 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-06-03 |  | 03 20 00-009-00 North Tunnel Cap.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-03 |  | 03 20 00-009-00 North Tunnel Cap.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-06-03 |  | 03 20 00-009-00 North Tunnel Cap.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-05 |  | 03 20 00-009-00 North Tunnel Cap_TT_POP.pdf
03 20 00-012-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-012-00: Foundation Shop Drawings - Area D | Closed | Structural | Tyler Kren (Mortenson Construction) | 2019-06-07 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2019-06-21 | 2019-06-25 | 19 |  | Record Copies; Transfers; Submittals | 03 20 00-012-00-01 - 03 20 00-012-00: Foundation Shop Drawings - Area D | 19 |  | 2019-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01473 | Received | For Review | 2019-06-07 | Tyler Kren (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-21 | Rebar Shop Drawings in Area D. | Info Exchange
| 02480 | Forwarded | For Review | 2019-06-07 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-06-14 | Rebar Shop Drawings in Area D. | Info Exchange
| 01606 | Review Response | Revise and Resubmit | 2019-06-24 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached reviewed drawings and SSK-0014. | Info Exchange
| 02654 | Forwarded | For Review | 2019-06-24 | Josh Dobken (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2019-06-21 | Rebar Shop Drawings in Area D. | Email
| 01624 | Review Response | Revise and Resubmit | 2019-06-25 | Josh Dobken (Populous) | Josh Dobken (Populous) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: See attached reviewed drawings and SSK-0014, to be issued in next CCD. POP - Please revise and resubmit highlighted items for approval. | Info Exchange
| 02682 | Responded and Closed | Revise and Resubmit | 2019-06-25 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Tyler Kren (Mortenson Construction) |  | Response (Revise and Resubmit) from: Josh Dobken (Populous) Remarks: Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: See attached reviewed drawings and SSK-0014, to be issued in next CCD. POP - Please revise and resubmit highlighted items for approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Tyler Kren (Mortenson Construction) | 1 | 2019-06-07 |  | 032000-0012-0 Foundation Shop Drawings-Area D.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-07 |  | 032000-0012-0 Foundation Shop Drawings-Area D.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-07 |  | 032000-0012-0 Foundation Shop Drawings-Area D.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-07 |  | 032000-0012-0 Foundation Shop Drawings-Area D.pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2019-06-25 |  | 03 20 00-012-00 Foundation Shop Drawings-Area D_TT REVIEWED_POP.pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2019-06-25 |  | SSK-0014 DTL 9_S7-10.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-07 |  | 032000-0012-0 Foundation Shop Drawings-Area D.pdf
03 20 00-012-00-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-012-00: Foundation Shop Drawings - Area D | Expected - Overdue |  | Tyler Kren (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 20 00-012-00 - 03 20 00-012-00: Foundation Shop Drawings - Area D | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | Tyler Kren (Mortenson Construction) | 1 | 2019-06-07 |  | 032000-0012-0 Foundation Shop Drawings-Area D.pdf
03 20 00-014-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-014-00 Sectors D,C, and A Foundation Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-01 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-15 | 2019-08-21 | 21 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-08-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01941 | Received | For Review | 2019-08-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-08-15 | Submittal Number: 03 20 00-14.0 From: RAELENE ROSSART Final Due Date: 08/15/19 Subject: SECTORS D,C, AND A FOUNDATION DRAWINGS Description: REVISED FOUNDATION DRAWINGS FOR SECTORS D,C, AND A WITH LETTER OF TRANSMITTAL #10. (9 DRAWINGS SUBMITTED) Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03087 | Forwarded | For Review | 2019-08-01 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-08 | Submittal Number: 03 20 00-14.0 From: RAELENE ROSSART Final Due Date: 08/15/19 Subject: SECTORS D,C, AND A FOUNDATION DRAWINGS Description: REVISED FOUNDATION DRAWINGS FOR SECTORS D,C, AND A WITH LETTER OF TRANSMITTAL #10. (9 DRAWINGS SUBMITTED) Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02097 | Review Response | Approved as Noted | 2019-08-13 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 03368 | Responded and Closed | Approved as Noted | 2019-08-21 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Approved as noted. See attached submittal. JHD - 2019 08 21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-01 |  | 032000-0014-0 Area D, C, A- Foundations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-01 |  | 032000-0014-0 Area D, C, A- Foundations.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-08-01 |  | 032000-0014-0 Area D, C, A- Foundations.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-21 02:00 |  | 032000-0014-0 Area D, C, A- Foundations_TT REVIEW_POP.pdf
03 20 00-015-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-015-00 Switchgear Vault | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-01 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-15 | 2019-08-13 | 13 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-08-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01955 | Received | For Review | 2019-08-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-08-15 | Submittal Number: 03 20 00-15.0 From: RAELENE ROSSART Final Due Date: 08/28/19 Subject: SWITCHGEAR VAULT Description: SWITCHGEAR VAULT DRAWING WITH LETTER OF TRANSMITTAL Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03100 | Forwarded | For Review | 2019-08-01 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-08 | Submittal Number: 03 20 00-15.0 From: RAELENE ROSSART Final Due Date: 08/28/19 Subject: SWITCHGEAR VAULT Description: SWITCHGEAR VAULT DRAWING WITH LETTER OF TRANSMITTAL Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02048 | Review Response | Approved as Noted | 2019-08-12 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Populous team, Please see attached TT's review of 03 20 00-015-00. Highlighted comments are for arch to confirm. Thanks, Samar | Info Exchange
| 03218 | Responded and Closed | Approved as Noted | 2019-08-13 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached review of 03 20 00-015-00. Thanks, | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-01 |  | 032000-0015-0 Switchgear Vault.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-01 |  | 03 20 00-015-00 Switchgear Vault.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-08-01 |  | 03 20 00-015-00 Switchgear Vault.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-13 |  | 03 20 00-015-00 Switchgear Vault_TT_POP.pdf
03 20 00-017-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-017-00 Rebar Terminator Caps Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-15 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-29 | 2019-08-20 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02077 | Received | For Review | 2019-08-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-08-29 | Submittal Number: 03 20 00-17.0 From: MIKE SOLFELT Final Due Date: 08/29/19 Subject: REBAR TERMINATOR CAPS PRODUCT DATA Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03250 | Forwarded | For Review | 2019-08-15 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-22 | Submittal Number: 03 20 00-17.0 From: MIKE SOLFELT Final Due Date: 08/29/19 Subject: REBAR TERMINATOR CAPS PRODUCT DATA Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02150 | Review Response | Approved | 2019-08-20 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 03330 | Responded and Closed | Approved | 2019-08-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved) from: Samar Kenkre (Thornton Tomasetti) Remarks: See attached approved submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-15 |  | 032000-0017-0 Terminator Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-15 |  | 032000-0017-0 Terminator Product Data.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-08-14 02:00 |  | 032000-0017-0 Terminator Product Data.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-20 02:00 |  | 032000-0017-0 Terminator Product Data_TT_POP.pdf
03 20 00-018-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-018-00 Rebar Coupler Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-16 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-30 | 2019-08-20 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02098 | Received | For Review | 2019-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-08-30 | Submittal Number: 03 20 00-18.0 From: MIKE SOLFELT Final Due Date: 09/13/19 Subject: REBAR COUPLER PRODUCT DATA Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03274 | Forwarded | For Review | 2019-08-16 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-23 | Submittal Number: 03 20 00-18.0 From: MIKE SOLFELT Final Due Date: 09/13/19 Subject: REBAR COUPLER PRODUCT DATA Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02149 | Review Response | Approved | 2019-08-20 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please see attached TT's review of 03 20 00-018-00. | Info Exchange
| 03329 | Responded and Closed | Approved | 2019-08-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved) from: Samar Kenkre (Thornton Tomasetti) Remarks: Please see attached TT's review of 03 20 00-018-00. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-16 |  | 032000-0018-0 Rebar Coupler Product Data v1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-16 |  | 032000-0018-0 Rebar Coupler Product Data v1.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-08-15 02:00 |  | 032000-0018-0 Rebar Coupler Product Data v1.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-20 02:00 |  | 032000-0018-0 Rebar Coupler Product Data v1_TT_POP.pdf
03 20 00-019-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-019-00 Shotcrete Wall Reinforcing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-20 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-09-03 | 2019-08-29 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-08-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02131 | Received | For Review | 2019-08-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-09-03 | Submittal Number: 03 20 00-19.0 From: MIKE SOLFELT Final Due Date: 09/02/19 Subject: SHOTCRETE WALL REINFORCING Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03308 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-26 | Submittal Number: 03 20 00-19.0 From: MIKE SOLFELT Final Due Date: 09/02/19 Subject: SHOTCRETE WALL REINFORCING Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02246 | Review Response | Approved as Noted | 2019-08-28 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 03466 | Responded and Closed | Approved as Noted | 2019-08-29 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 032000-0019-0 Shotcrete Wall Reinforcing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-19 |  | 032000-0019-0 Shotcrete Wall Reinforcing.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-08-18 02:00 |  | 032000-0019-0 Shotcrete Wall Reinforcing.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-29 02:00 |  | 032000-0019-0 Shotcrete Wall Reinforcing_TT_POP.pdf
03 20 00-020-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-020-00 Formsaver Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-26 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-09-10 07:00 | 2019-09-05 | 11 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-09-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02191 | Received | For Review | 2019-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC); Mike Solfelt | 2019-09-10 07:00 | Submittal Number: 03 20 00-20.0 From: MIKE SOLFELT Final Due Date: 09/09/19 Subject: FORMSAVER PRODUCT DATA Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03394 | Forwarded | For Review | 2019-08-26 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-02 | Submittal Number: 03 20 00-20.0 From: MIKE SOLFELT Final Due Date: 09/09/19 Subject: FORMSAVER PRODUCT DATA Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02314 | Review Response | No Action Taken or Required | 2019-09-04 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions | Info Exchange
| 03545 | Responded and Closed | Approved | 2019-09-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-26 |  | 032000-0020-00 Formsaver Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-26 |  | 032000-020-00 Formsaver Product Data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-08-25 02:00 |  | 032000-020-00 Formsaver Product Data.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-05 02:00 |  | 032000-020-00 Formsaver Product Data_TT_POP.pdf
03 20 00-021-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-021-00 Area B Foundations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-26 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-09-10 07:00 | 2019-09-05 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-09-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02192 | Received | For Review | 2019-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-09-10 07:00 | Submittal Number: 03 20 00-21.0 From: MIKE SOLFELT Final Due Date: 09/09/19 Subject: AREA B FOUNDATIONS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03395 | Forwarded | For Review | 2019-08-26 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-02 | Submittal Number: 03 20 00-21.0 From: MIKE SOLFELT Final Due Date: 09/09/19 Subject: AREA B FOUNDATIONS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02310 | Review Response | Approved as Noted | 2019-09-05 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 03541 | Responded and Closed | Approved as Noted | 2019-09-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-26 |  | 032000-0021-0 Area B Foundations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-26 |  | 032000-021-0 Area B Foundations.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-08-25 02:00 |  | 032000-021-0 Area B Foundations.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-05 02:00 |  | 032000-021-0 Area B Foundations_TT REVIEW_POP.pdf
03 20 00-022-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-022-00 Loading Dock Foundations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-13 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-09-27 | 2019-09-26 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-09-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02396 | Received | For Review | 2019-09-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-09-27 | Submittal Number: 03 20 00-22.0 From: MIKE SOLFELT Final Due Date: 09/26/19 Subject: LOADING DOCK FOUNDATIONS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03645 | Forwarded | For Review | 2019-09-12 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-19 | Submittal Number: 03 20 00-22.0 From: MIKE SOLFELT Final Due Date: 09/26/19 Subject: LOADING DOCK FOUNDATIONS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02532 | Review Response | Approved as Noted | 2019-09-26 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 03817 | Responded and Closed | Approved as Noted | 2019-09-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-12 |  | 032000-0022-0 Loading Dock Foundations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-12 |  | 032000-0022-0 Loading Dock Foundations.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-11 02:00 |  | 032000-0022-0 Loading Dock Foundations.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-26 02:00 |  | 032000-0022-0 Loading Dock Foundations_TT REVIEW_POP.pdf
03 20 00-024-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-024-00 South Buttress Mat Foundation | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-03 | 2019-10-02 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-10-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02454 | Received | For Review | 2019-09-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-10-03 | Submittal Number: 03 20 00-24.0 From: MIKE SOLFELT Final Due Date: 10/02/19 Subject: SOUTH BUTTRESS MAT FOUNDATION Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03724 | Forwarded | For Review | 2019-09-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-09-26 | Submittal Number: 03 20 00-24.0 From: MIKE SOLFELT Final Due Date: 10/02/19 Subject: SOUTH BUTTRESS MAT FOUNDATION Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02571 | Review Response | Revise and Resubmit | 2019-09-26 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached submittal. | Info Exchange
| 02629 | Review Response | Approved as Noted | 2019-10-02 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | See submittal and corresponding SSK attached. | Info Exchange
| 03928 | Responded and Closed | Approved as Noted | 2019-10-02 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See submittal and corresponding SSK attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-18 |  | 032000-0024-0 South Buttress Pad Footing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-18 |  | 032000-0024-0 South Buttress Pad Footing.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-09-18 |  | 032000-0024-0 South Buttress Pad Footing.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-10-02 02:00 |  | SSK-0076 South Buttress Pile Cap Reinforcing.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-10-02 02:00 |  | 032000-0024-0 South Buttress Pad Footing_TT_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-17 02:00 |  | 032000-0024-0 South Buttress Pad Footing.pdf
03 20 00-025-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-025-00 Shotcrete Wall Reinforcing Areas B and A | Closed | Structural, Geotechnical/Foundations | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-02 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), David Winter (Hart Crowser), Brice Exley (Hart Crowser), Joseph Harmon (Hart Crowser) |  |  |  | 2019-10-16 | 2019-11-06 | 36 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-11-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02635 | Received | For Review | 2019-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-10-16 | Submittal Number: 03 20 00-25.0 From: MIKE SOLFELT Final Due Date: 10/15/19 Subject: SHOTCRETE WALL REINFORCING AREAS B AND A Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03941 | Forwarded | For Review | 2019-10-02 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-09 | Submittal Number: 03 20 00-25.0 From: MIKE SOLFELT Final Due Date: 10/15/19 Subject: SHOTCRETE WALL REINFORCING AREAS B AND A Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02805 | Review Response | Approved as Noted | 2019-10-16 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 04157 | Forwarded | For Review | 2019-10-16 | Josh Dobken (Populous) | David Winter (Hart Crowser); Brice Exley (Hart Crowser); Joseph Harmon (Hart Crowser) | 2019-10-16 | Submittal Number: 03 20 00-25.0 From: MIKE SOLFELT Final Due Date: 10/15/19 Subject: SHOTCRETE WALL REINFORCING AREAS B AND A Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Email
| 04480 | Responded and Closed | Approved as Noted | 2019-11-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-01 |  | 032000-0025-0 Shotcrete Wall Reinforcing Areas B and A.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-01 |  | 032000-0025-0 Shotcrete Wall Reinforcing Areas B and A.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-09-30 02:00 |  | 032000-0025-0 Shotcrete Wall Reinforcing Areas B and A.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-30 02:00 |  | 032000-0025-0 Shotcrete Wall Reinforcing Areas B and A.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-06 02:00 |  | 032000-0025-0 Shotcrete Wall Reinforcing Areas B and A_TT_POP.pdf
03 20 00-026-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-026-00 Garage Foundations and Shear Walls | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-04 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-18 | 2019-10-21 | 18 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-10-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02675 | Received | For Review | 2019-10-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-10-18 | Submittal Number: 03 20 00-26.0 From: MIKE SOLFELT Final Due Date: 10/18/19 Subject: GARAGE FOUNDATIONS AND SHEAR WALLS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03993 | Forwarded | For Review | 2019-10-04 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth K... | 2019-10-11 | Submittal Number: 03 20 00-26.0 From: MIKE SOLFELT Final Due Date: 10/18/19 Subject: GARAGE FOUNDATIONS AND SHEAR WALLS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02862 | Review Response | Approved as Noted | 2019-10-18 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 04221 | Responded and Closed | Approved as Noted | 2019-10-21 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-04 02:00 |  | 032000-0026-0 Garage Foundations and Shear Walls.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-10-04 02:00 |  | 032000-0026-0 Garage Foundations and Shear Walls.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-10-04 02:00 |  | 032000-0026-0 Garage Foundations and Shear Walls.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-21 02:00 |  | 032000-0026-0 Garage Foundations and Shear Walls_TT_POP.pdf
03 20 00-027-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-027-00 Headed Stud Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-10 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-24 | 2019-10-10 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-10-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02718 | Received | For Review | 2019-10-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-10-24 | Submittal Number: 03 20 00-27.0 From: JOE KORCHEMNIY Final Due Date: 10/21/19 Subject: HEADED STUD PRODUCT DATA Description: SEE ATTACHMENT FOR WELDED HEADED STUDS THAT WILL BE INSTALLED ON SOLDIER PILES. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04053 | Forwarded | For Review | 2019-10-10 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-17 | Submittal Number: 03 20 00-27.0 From: JOE KORCHEMNIY Final Due Date: 10/21/19 Subject: HEADED STUD PRODUCT DATA Description: SEE ATTACHMENT FOR WELDED HEADED STUDS THAT WILL BE INSTALLED ON SOLDIER PILES. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02721 | Review Response | Approved | 2019-10-10 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 04056 | Responded and Closed | Approved | 2019-10-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-10 |  | Submittal #03 20 00-27.0 Headed Stud Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-10 |  | Submittal #03 20 00-27.0 Headed Stud Product Data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-09 02:00 |  | Submittal #03 20 00-27.0 Headed Stud Product Data.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-10 02:00 |  | Submittal #03 20 00-27.0 Headed Stud Product Data_TT REVIEW_POP.pdf
03 20 00-028-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-028-00 Headed Stud Welding Procedure | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-16 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-30 | 2019-10-16 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-10-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02791 | Received | For Review | 2019-10-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-10-30 | Submittal Number: 03 20 00-28.0 From: JOE KORCHEMNIY Final Due Date: 10/29/19 Subject: HEADED STUD WELDING PROCEDURE Description: SEE ATTACHMENT FOR HEADED STUD WELDING PROCEDURE FOR RECORD. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04136 | Forwarded | For Review | 2019-10-16 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-23 | Submittal Number: 03 20 00-28.0 From: JOE KORCHEMNIY Final Due Date: 10/29/19 Subject: HEADED STUD WELDING PROCEDURE Description: SEE ATTACHMENT FOR HEADED STUD WELDING PROCEDURE FOR RECORD. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 02794 | Review Response | No Action Taken or Required | 2019-10-16 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Received for record only. | Info Exchange
| 04144 | Responded and Closed | No Action Taken or Required | 2019-10-16 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Received for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-15 |  | Submittal #03 20 00-28.0 Headed Stud Welding Procedure.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-15 |  | Submittal #03 20 00-28.0 Headed Stud Welding Procedure.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-15 |  | Submittal #03 20 00-28.0 Headed Stud Welding Procedure.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-16 |  | Submittal #03 20 00-28.0 Headed Stud Welding Procedure_POP.pdf
03 20 00-029-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-029-00 Tower Crane Foundation Reinforcement | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-24 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-11-07 | 2019-11-06 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-11-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02911 | Received | For Review | 2019-10-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-11-07 | Submittal Number: 03 20 00-29.0 From: CHRISTIAN ALBERS Final Due Date: 11/07/19 Subject: TOWER CRANE FOUNDATION REINFORCEMENT Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04281 | Forwarded | For Review | 2019-10-24 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-31 | Submittal Number: 03 20 00-29.0 From: CHRISTIAN ALBERS Final Due Date: 11/07/19 Subject: TOWER CRANE FOUNDATION REINFORCEMENT Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03100 | Review Response | Approved as Noted | 2019-11-06 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04500 | Responded and Closed | Approved as Noted | 2019-11-06 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-24 |  | 03 20 00 - 0029 - 00 Tower Crane Foundation Reinforcement.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-24 |  | 03 20 00 - 0029 - 00 Tower Crane Foundation Reinforcement.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-10-23 02:00 |  | 03 20 00 - 0029 - 00 Tower Crane Foundation Reinforcement.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-11-06 02:00 |  | 03 20 00 - 0029 - 00 Tower Crane Foundation Reinforcement_TT_POP.pdf
03 20 00-030-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-030-00 Y-Column / Chevron Extensions Area D | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-29 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill |  |  |  | 2019-11-12 | 2019-11-06 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-11-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02953 | Received | For Review | 2019-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-11-12 | Submittal Number: 03 20 00-30.0 From: MIKE SOLFELT Final Due Date: 11/06/19 Subject: Y-COLUMN / CHEVRON EXTENSIONS AREA D Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04330 | Forwarded | For Review | 2019-10-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-05 | Submittal Number: 03 20 00-30.0 From: MIKE SOLFELT Final Due Date: 11/06/19 Subject: Y-COLUMN / CHEVRON EXTENSIONS AREA D Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03104 | Review Response | Approved as Noted | 2019-11-06 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | It appears that the column labels were switched between Y1A and Y1B. The same seems to have occurred at Y2A and Y2B. Please verify column location and corresponding floor level attachment locations. Additionally, TT is aware of potential alternate foundation designs at the Y-Column and Chevron extensions. Coordinate embed rebar as required. | Info Exchange
| 04506 | Responded and Closed | Approved as Noted | 2019-11-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: It appears that the column labels were switched between Y1A and Y1B. The same seems to have occurred at Y2A and Y2B. Please verify column location and corresponding floor level attachment locations. Additionally, TT is aware of potential alternate foundation designs at the Y-Column and Chevron extensions. Coordinate embed rebar as required. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-28 |  | 032000-0030-0 Area D Y-Column and Chevron Extensions.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-28 |  | 032000-0030-0 Area D Y-Column and Chevron Extensions.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-10-27 02:00 |  | 032000-0030-0 Area D Y-Column and Chevron Extensions.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-06 02:00 |  | 032000-0030-0 Area D Y-Column and Chevron Extensions_TT_POP.pdf
03 20 00-031-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-031-00 Y-Column / Chevron Extension Area C | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-30 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill |  |  |  | 2019-11-13 | 2019-11-06 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-11-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02977 | Received | For Review | 2019-10-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-11-13 | Submittal Number: 03 20 00-31.0 From: MIKE SOLFELT Final Due Date: 11/12/19 Subject: Y-COLUMN / CHEVRON EXTENSION AREA C Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04358 | Forwarded | For Review | 2019-10-30 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-06 | Submittal Number: 03 20 00-31.0 From: MIKE SOLFELT Final Due Date: 11/12/19 Subject: Y-COLUMN / CHEVRON EXTENSION AREA C Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03105 | Review Response | Approved as Noted | 2019-11-06 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT is aware of potential alternate foundation designs at the Y-Column and Chevron extensions. Coordinate rebar dowels as required. | Info Exchange
| 04507 | Responded and Closed | Approved as Noted | 2019-11-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: TT is aware of potential alternate foundation designs at the Y-Column and Chevron extensions. Coordinate rebar dowels as required. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-30 |  | 032000-0031-0 Y Column and Chevron Extensions Area C.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-30 |  | 032000-0031-0 Y Column and Chevron Extensions Area C.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-10-29 02:00 |  | 032000-0031-0 Y Column and Chevron Extensions Area C.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-06 02:00 |  | 032000-0031-0 Y Column and Chevron Extensions Area C_TT_POP.pdf
03 20 00-032-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-032-00 Y Column / Chevron Extension Area A and B | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-12 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-11-26 | 2019-11-22 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-11-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03161 | Received | For Review | 2019-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-11-26 | Submittal Number: 03 20 00-32.0 From: MIKE SOLFELT Final Due Date: 12/09/19 Subject: Y COLUMN / CHEVRON EXTENSION AREA A AND B Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04581 | Forwarded | For Review | 2019-11-12 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-19 | Submittal Number: 03 20 00-32.0 From: MIKE SOLFELT Final Due Date: 12/09/19 Subject: Y COLUMN / CHEVRON EXTENSION AREA A AND B Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03342 | Review Response | Approved as Noted | 2019-11-22 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Approved as Noted Per correspondence with MS, Mortenson confirms rebar w/formsaver couplers matching slab reinforcement (see detail 1/S7-31) will be provided in separate submittal for review and approval. Comment also applies to Quad C & D submittals. | Info Exchange
| 04796 | Responded and Closed | Approved as Noted | 2019-11-22 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: Approved as Noted Per correspondence with MS, Mortenson confirms rebar w/formsaver couplers matching slab reinforcement (see detail 1/S7-31) will be provided in separate submittal for review and approval. Comment also applies to Quad C & D submittals. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-11 |  | 032000-0032-0 Y Column and Chevron Extension.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-11 |  | 032000-0032-0 Y Column and Chevron Extension.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-11-10 02:00 |  | 032000-0032-0 Y Column and Chevron Extension.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-22 02:00 |  | 032000-0032-0 Y Column and Chevron Extension_TT_POP.pdf
03 20 00-034-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-034-00 Y Column / Chevron Pile Cap | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-03 | 2019-11-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03255 | Received | For Review | 2019-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-12-03 | Submittal Number: 03 20 00-34.0 From: MIKE SOLFELT Final Due Date: 11/22/19 Subject: Y COLUMN / CHEVRON PILE CAP Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04697 | Forwarded | For Review | 2019-11-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-26 | Submittal Number: 03 20 00-34.0 From: MIKE SOLFELT Final Due Date: 11/22/19 Subject: Y COLUMN / CHEVRON PILE CAP Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03281 | Review Response | Approved as Noted | 2019-11-20 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 04731 | Responded and Closed | Approved as Noted | 2019-11-20 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | See attached review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-19 |  | 032000-0034-0 Y Column and Chevron Pile Caps.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-19 |  | 032000-0034-0 Y Column and Chevron Pile Caps.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-19 |  | 032000-0034-0 Y Column and Chevron Pile Caps.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-11-20 |  | 032000-0034-0 Y Column and Chevron Pile Caps_TT_POP.pdf
03 20 00-035-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-035-00 Chevron Knuckles | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-12-05 08:00 | 2019-12-17 | 29 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2019-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03256 | Received | For Review | 2019-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-12-05 08:00 | Submittal Number: 03 20 00-35.0 From: MIKE SOLFELT Final Due Date: 12/03/19 Subject: CHEVRON KNUCKLES Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04698 | Forwarded | For Review | 2019-11-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-26 | Submittal Number: 03 20 00-35.0 From: MIKE SOLFELT Final Due Date: 12/03/19 Subject: CHEVRON KNUCKLES Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03608 | Review Response | Approved as Noted | 2019-12-11 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Populous to review concrete extents & Upper Concourse tie-in at T/Slab for architectural acceptability. | Info Exchange
| 05089 | Forwarded | For Review | 2019-12-12 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2019-12-05 | Submittal Number: 03 20 00-35.0 From: MIKE SOLFELT Final Due Date: 12/03/19 Subject: CHEVRON KNUCKLES Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05173 | Responded and Closed | Approved as Noted | 2019-12-17 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | See attached review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-19 |  | 032000-0035-0 Chevron Knuckles.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-19 |  | 032000-0035-0 Chevron Knuckles.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-11-18 02:00 |  | 032000-0035-0 Chevron Knuckles.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-12 02:00 |  | 032000-0035-0 Chevron Knuckles_TT_v2.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-12-17 |  | 032000-0035-0 Chevron Knuckles_TT_POP.pdf
03 20 00-036-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-036-00: NE Snorkel | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-10 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-02 | 2020-01-03 | 25 | General | Record Copies; Transfers; Submittals |  | 24 |  | 2020-01-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03579 | Received | For Review | 2019-12-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2020-01-02 | Submittal Number: 03 20 00-36.0 From: MIKE SOLFELT Final Due Date: 12/23/19 Subject: NE SNORKEL Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05059 | Forwarded | For Review | 2019-12-10 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth K... | 2019-12-17 | Submittal Number: 03 20 00-36.0 From: MIKE SOLFELT Final Due Date: 12/23/19 Subject: NE SNORKEL Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03778 | Review Response | Approved as Noted | 2020-01-02 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 05316 | Responded and Closed | Approved as Noted | 2020-01-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-09 02:00 |  | 032000-0036-0 NE Snorkel.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 032000-0036-0 NE Snorkel.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-09 02:00 |  | 032000-0036-0 NE Snorkel.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-03 02:00 |  | 032000-0036-0 NE Snorkel_TT REVIEW_POP.pdf
03 20 00-037-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-037-00 South Buttress Shear Wall | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-13 | 2020-01-07 | 20 | General | Record Copies; Transfers; Submittals |  | 16 |  | 2020-01-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03699 | Received | For Review | 2019-12-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2020-01-13 | Submittal Number: 03 20 00-37.0 From: MIKE SOLFELT Final Due Date: 01/06/20 Subject: SOUTH BUTTRESS SHEAR WALL Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05222 | Forwarded | For Review | 2019-12-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-26 | Submittal Number: 03 20 00-37.0 From: MIKE SOLFELT Final Due Date: 01/06/20 Subject: SOUTH BUTTRESS SHEAR WALL Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 03822 | Review Response | Approved as Noted | 2020-01-03 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See markups on attached submittal. | Info Exchange
| 05366 | Responded and Closed | Approved as Noted | 2020-01-07 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-19 |  | 032000-0037-0 South Buttress Shear Wall.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-19 |  | 032000-0037-0 South Buttress Shear Wall.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-12-19 |  | 032000-0037-0 South Buttress Shear Wall.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-07 |  | 032000-0037-0 South Buttress Shear Wall_TT_POP.pdf
03 20 00-038-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-038-00 Shotcrete Wall Reinforcing Area E and F | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-17 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-31 | 2020-01-31 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-01-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03947 | Received | For Review | 2020-01-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2020-01-31 | Submittal Number: 03 20 00-38.0 From: MIKE SOLFELT Final Due Date: 01/30/20 Subject: SHOTCRETE WALL REINFORCING AREA E AND F Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05514 | Forwarded | For Review | 2020-01-16 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-23 | Submittal Number: 03 20 00-38.0 From: MIKE SOLFELT Final Due Date: 01/30/20 Subject: SHOTCRETE WALL REINFORCING AREA E AND F Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04157 | Review Response | Approved as Noted | 2020-01-30 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05763 | Responded and Closed | Approved as Noted | 2020-01-31 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | See attached review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-16 |  | 032000-0038-0 Shotcrete Walls E and F.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-16 |  | 032000-0038-0 Shotcrete Walls E and F.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-01-16 |  | 032000-0038-0 Shotcrete Walls E and F.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-31 |  | 032000-0038-0 Shotcrete Walls E and F_TT_POP.pdf
03 20 00-039-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-039-00 Manhoist Footing and Wall Reinforcing Modifications | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-27 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-10 | 2020-02-11 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04081 | Received | For Review | 2020-01-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2020-02-10 | Submittal Number: 03 20 00-39.0 From: MIKE SOLFELT Final Due Date: 02/10/20 Subject: MANHOIST FOOTING AND WALL REINFORCING MODIFICATIONS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05674 | Forwarded | For Review | 2020-01-27 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-03 | Submittal Number: 03 20 00-39.0 From: MIKE SOLFELT Final Due Date: 02/10/20 Subject: MANHOIST FOOTING AND WALL REINFORCING MODIFICATIONS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04312 | Review Response | Approved as Noted | 2020-02-10 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05964 | Responded and Closed | Approved as Noted | 2020-02-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-27 |  | 032000-0039-0 Manhoist Footing and Wall - Copy.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-27 |  | 032000-0039-0 Manhoist Footing and Wall - Copy.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-27 |  | 032000-0039-0 Manhoist Footing and Wall - Copy.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-11 |  | 032000-0039-0 Manhoist Footing and Wall_TT_POP.pdf
03 20 00-040-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-040-00 Y-Column Upsizing Requirements | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-31 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-14 | 2020-02-11 | 12 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04158 | Received | For Review | 2020-01-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2020-02-14 | Submittal Number: 03 20 00-40.0 From: MIKE SOLFELT Final Due Date: 02/13/20 Subject: Y-COLUMN UPSIZING REQUIREMENTS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05764 | Forwarded | For Review | 2020-01-31 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-07 | Submittal Number: 03 20 00-40.0 From: MIKE SOLFELT Final Due Date: 02/13/20 Subject: Y-COLUMN UPSIZING REQUIREMENTS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04314 | Review Response | Approved as Noted | 2020-02-06 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05965 | Responded and Closed | Approved as Noted | 2020-02-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-30 |  | 032000-0040-0 Y-Column Upsizing Requirements.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-30 |  | 032000-0040-0 Y-Column Upsizing Requirements.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-01-30 |  | 032000-0040-0 Y-Column Upsizing Requirements.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-11 |  | 032000-0040-0 Y-Column Upsizing Requirements_TT_POP.pdf
03 20 00-041-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-041-00 Existing Reinforcement Repair Procedure | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-11 | 6 |  | Record Copies; Transfers; Submittals | 03 20 00-041-01 - 03 20 00-041-00 Existing Reinforcement Repair Procedure | 2 |  | 2020-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04237 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2020-02-20 | Submittal Number: 03 20 00-41.0 From: JOE KORCHEMNIY Final Due Date: 03/13/20 Subject: EXISTING REINFORCEMENT REPAIR PROCEDURE Description: SEE ATTACHED EXISTING REINFORCEMENT REPAIR PROCEDURE ATTACHED "FOR RECORD" ONLY. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05866 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 03 20 00-41.0 From: JOE KORCHEMNIY Final Due Date: 03/13/20 Subject: EXISTING REINFORCEMENT REPAIR PROCEDURE Description: SEE ATTACHED EXISTING REINFORCEMENT REPAIR PROCEDURE ATTACHED "FOR RECORD" ONLY. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04316 | Review Response | Approved as Noted/Resubmit | 2020-02-07 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT Response: Exceptions Noted | Info Exchange
| 05967 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | Submittal #03 20 00-41.0 Existing Reinforcement Repair Procedure.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | Submittal #03 20 00-41.0 Existing Reinforcement Repair Procedure.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-02-06 |  | Submittal #03 20 00-41.0 Existing Reinforcement Repair Procedure.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-11 |  | Submittal #03 20 00-41.0 Existing Reinforcement Repair Procedure_TT_POP.pdf
03 20 00-041-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-041-00 Existing Reinforcement Repair Procedure | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 20 00-041-00 - 03 20 00-041-00 Existing Reinforcement Repair Procedure | -1 | 2020-02-25
03 20 00-042-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-042-00 Y-Column Upsizing Requirements - Y1-5, Y16 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-13 | 8 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-02-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04251 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2020-02-20 | Submittal Number: 03 20 00-42.0 From: MIKE SOLFELT Final Due Date: 02/20/20 Subject: Y-COLUMN UPSIZING REQUIREMENTS - Y1-5, Y16 Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05883 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 03 20 00-42.0 From: MIKE SOLFELT Final Due Date: 02/20/20 Subject: Y-COLUMN UPSIZING REQUIREMENTS - Y1-5, Y16 Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04343 | Review Response | Approved as Noted | 2020-02-11 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06006 | Responded and Closed | Approved as Noted | 2020-02-13 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 032000-0042-0 Y-Column Upsizing Requireme.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | 032000-0042-0 Y-Column Upsizing Requireme.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-02-06 |  | 032000-0042-0 Y-Column Upsizing Requireme.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-13 |  | 032000-0042-0 Y-Column Upsizing Requirements_TT_POP.pdf
03 20 00-043-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-043-00 Existing Reinforcement Realignment Work Plan & Locations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-11 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-02-25 | 2020-02-13 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-02-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04320 | Received | For Review | 2020-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Josh Dobken (Populous); Populous SCA_CCA; Sean McNeill (Thornton Tomasetti) | 2020-02-25 | Submittal Number: 03 20 00-43.0 From: GREG GOEBEL Final Due Date: 02/25/20 Subject: EXISTING REINFORCEMENT REALIGNMENT WORK PLAN & LOCATIONS Description: WORK PLAN ASSOCIATED WITH PROCORE OBSERVATION #322 AND THE REALIGNMENT OF THE EXISTING REINFORCEMENT BENT DURING FOOTING DEMOLITION. LOCATIONS DETAILED IN ATTACHED PLAN VIEW MAP AS A PART OF THE WORK PLAN. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05970 | Forwarded | For Review | 2020-02-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-18 | Submittal Number: 03 20 00-43.0 From: GREG GOEBEL Final Due Date: 02/25/20 Subject: EXISTING REINFORCEMENT REALIGNMENT WORK PLAN & LOCATIONS Description: WORK PLAN ASSOCIATED WITH PROCORE OBSERVATION #322 AND THE REALIGNMENT OF THE EXISTING REINFORCEMENT BENT DURING FOOTING DEMOLITION. LOCATIONS DETAILED IN ATTACHED PLAN VIEW MAP AS A PART OF THE WORK PLAN. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04344 | Review Response | Approved | 2020-02-12 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | No Exceptions | Info Exchange
| 06007 | Responded and Closed | Approved | 2020-02-13 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FORE REVIEW AND RESPONSE. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-11 |  | 03 20 00-043-00 Existing Reinforcement Realignment Work Plan & Locations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-11 |  | 03 20 00-043-00 Existing Reinforcement Realignment Work Plan & Locations.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-02-11 |  | 03 20 00-043-00 Existing Reinforcement Realignment Work Plan & Locations.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-13 |  | 03 20 00-043-00 Existing Reinforcement Realignment Work Plan & Locations_TT_POP.pdf
03 20 00-044-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-044-00 SOMD Reinforcing Area D | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-05 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-19 | 2020-03-23 | 19 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04670 | Received | For Review | 2020-03-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-03-19 | Submittal Number: 03 20 00-44.0 From: MIKE SOLFELT Final Due Date: 03/19/20 Subject: SOMD REINFORCING AREA D Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 06425 | Forwarded | For Review | 2020-03-05 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-12 | Submittal Number: 03 20 00-44.0 From: MIKE SOLFELT Final Due Date: 03/19/20 Subject: SOMD REINFORCING AREA D Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04973 | Review Response | Approved as Noted | 2020-03-20 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Coordinate slab area and reinforcement with latest drawings. | Info Exchange
| 06781 | Responded and Closed | Approved as Noted | 2020-03-23 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Coordinate slab area and reinforcement with latest drawings. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-05 |  | 032000-0044-0 SOMD Area D.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-05 |  | 032000-0044-0 SOMD Area D.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-05 |  | 032000-0044-0 SOMD Area D.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-23 |  | 032000-0044-0 SOMD Area D_TT_POP.pdf
03 20 00-044-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-044-01 SOMD Resubmittal - Area D and Area C | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-22 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-06 | 2020-05-04 | 13 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05501 | Received | For Review | 2020-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-05-06 | Submittal Number: 03 20 00-44.1 From: MIKE SOLFELT Final Due Date: 05/06/20 Subject: SOMD RESUBMITTAL - AREA D AND AREA C Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 07459 | Forwarded | For Review | 2020-04-22 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-29 | Submittal Number: 03 20 00-44.1 From: MIKE SOLFELT Final Due Date: 05/06/20 Subject: SOMD RESUBMITTAL - AREA D AND AREA C Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05697 | Review Response | Approved as Noted | 2020-05-01 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07713 | Responded and Closed | Approved as Noted | 2020-05-04 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 032000-0044-1 SOMD Area D and C Resubmittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 032000-0044-1 SOMD Area D and C Resubmittal.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-22 |  | 032000-0044-1 SOMD Area D and C Resubmittal.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-04 |  | 032000-0044-1 SOMD Area D and C Resubmittal_TT_POP.pdf
03 20 00-045-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-045-00 SOMD Area C | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-10 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-24 | 2020-03-23 | 14 |  | Record Copies; Transfers; Submittals | 03 20 00-045-01 - 03 20 00-045-00 SOMD Area C | 12 |  | 2020-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04708 | Received | For Review | 2020-03-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-03-24 | Submittal Number: 03 20 00-45.0 From: MIKE SOLFELT Final Due Date: 03/23/20 Subject: SOMD AREA C Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 06474 | Forwarded | For Review | 2020-03-09 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-16 | Submittal Number: 03 20 00-45.0 From: MIKE SOLFELT Final Due Date: 03/23/20 Subject: SOMD AREA C Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 04972 | Review Response | Revise and Resubmit | 2020-03-20 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please resubmit Mech Mezz and Upper Concourse sheets with clarification of bend types not listed in schedules. All other sheets are approved as noted. Please coordinate slab area with latest drawings. Note: Populous to confirm a few dimensions. | Info Exchange
| 06780 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-23 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Please resubmit Mech Mezz and Upper Concourse sheets with clarification of bend types not listed in schedules. All other sheets are approved as noted. Please coordinate slab area with latest drawings. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-09 |  | 032000-0045-0 SOMD Area C.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-09 |  | 032000-0045-0 SOMD Area C.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-09 |  | 032000-0045-0 SOMD Area C.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-23 |  | 032000-0045-0 SOMD Area C_TT_POP.pdf
03 20 00-045-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-045-00 SOMD Area C | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 20 00-045-00 - 03 20 00-045-00 SOMD Area C | -1 | 2020-04-06
03 20 00-046-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-046-00 NW Snorkel Reinforcing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-30 | 2020-04-13 | 29 |  | Record Copies; Transfers; Submittals | 03 20 00-046-01 - 03 20 00-046-00 NW Snorkel Reinforcing | 29 |  | 2020-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04861 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 03 20 00-46.0 From: MIKE SOLFELT Final Due Date: 03/30/20 Subject: NW SNORKEL REINFORCING Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 06640 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-23 | Submittal Number: 03 20 00-46.0 From: MIKE SOLFELT Final Due Date: 03/30/20 Subject: NW SNORKEL REINFORCING Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05175 | Review Response | Revise and Resubmit | 2020-04-01 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07016 | Responded and Closed | Revise and Resubmit | 2020-04-01 | Josh Dobken (Populous) | Mike Steele (CAA ICON / Strategy Advisory); Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: It appears sheet is missing for upper concourse level. (Sheet R-NW-2 is duplicated). Please resubmit with complete information. | Info Exchange
| 07170 | Sent | For Information Only | 2020-04-09 | Josh Dobken (Populous) | Mike Solfelt (M.A. Mortenson Company) |  | Responded and Closed (Revise and Resubmit) to: Mike Steele (CAA ICON / Strategy Advisory); Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: It appears sheet is missing for upper concourse level. (Sheet R-NW-2 is duplicated). Please resubmit with complete information. | Info Exchange
| 07243 | Reopened | Additional Information | 2020-04-13 19:02 | Josh Dobken (Populous) |  |  | Revised comments from TT received 4/13
| 05327 | Review Response | Revise and Resubmit | 2020-04-13 | Raymond Chou (Thornton Tomasetti) | Josh Dobken (Populous) |  | Our R&R stamp that we only need to see the upper portion of the wall which is missing. This would likely impact sheets NW-3 and NW-4. | Email
| 07245 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Reopened (Additional Information) by: Josh Dobken Remarks: Revised comments from TT received 4/13. See comments in attached submittal. Resubmit per revised comments from TT and Populous. Response (Revise and Resubmit) from: Raymond Chou (Thornton Tomasetti) Remarks: Our R&R stamp that we only need to see the upper portion of the wall which is missing. This would likely impact sheets NW-3 and NW-4. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 032000-0046-0 NW Snorkel Reinforcing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 032000-0046-0 NW Snorkel Reinforcing.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-15 02:00 |  | 032000-0046-0 NW Snorkel Reinforcing.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-01 02:00 |  | 032000-0046-0 NW Snorkel Reinforcing_TT Reviewed_pop.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-04-01 02:00 |  | 032000-0046-0 NW Snorkel Reinforcing_TT Reviewed_pop.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2020-04-13 02:00 |  | 032000-0046-0 NW Snorkel Reinforcing_TT Reviewed Updated.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-13 02:00 |  | 032000-0046-0 NW Snorkel Reinforcing_TT Reviewed Updated_pop.pdf
03 20 00-046-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-046-00 NW Snorkel Reinforcing | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 20 00-046-00 - 03 20 00-046-00 NW Snorkel Reinforcing | -1 | 2020-04-15
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-01 02:00 |  | 032000-0046-0 NW Snorkel Reinforcing_TT Reviewed_pop.pdf
03 20 00-047-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-047-00 SW Snorkel Footing Reinforcement | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-08 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-22 | 2020-04-26 | 19 |  | Record Copies; Transfers; Submittals | 03 20 00-047-00-01 - 03 20 00-047-00 SW Snorkel Footing Reinforcement | 16 |  | 2020-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05257 | Received | For Review | 2020-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-04-22 | Submittal Number: 03 20 00-47.0 From: MIKE SOLFELT Final Due Date: 04/22/20 Subject: SW SNORKEL FOOTING REINFORCEMENT Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 07149 | Forwarded | For Review | 2020-04-08 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-15 | Submittal Number: 03 20 00-47.0 From: MIKE SOLFELT Final Due Date: 04/22/20 Subject: SW SNORKEL FOOTING REINFORCEMENT Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05547 | Review Response | Revise and Resubmit | 2020-04-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | SW Snorkel areas noted pending redesign per West Temp Ramp changes to be issued. | Info Exchange
| 07524 | Responded and Closed | Revise and Resubmit | 2020-04-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | SW Snorkel areas noted pending redesign per West Temp Ramp changes to be issued. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-08 |  | 032000-0047-0 SW Snorkel Footing Reinforcing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-08 |  | 032000-0047-0 SW Snorkel Footing Reinforcing.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-08 |  | 032000-0047-0 SW Snorkel Footing Reinforcing.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-26 |  | 032000-0047-0 SW Snorkel Footing Reinforcing_TT_POP.pdf
03 20 00-047-00-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-047-00 SW Snorkel Footing Reinforcement | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 20 00-047-00 - 03 20 00-047-00 SW Snorkel Footing Reinforcement | -1 | 2020-05-11
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-26 |  | 032000-0047-0 SW Snorkel Footing Reinforcing_TT_POP.pdf
03 20 00-048-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-048-00 SE Snorkel Reinforcing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-16 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-30 | 2020-04-30 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-04-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05390 | Received | For Review | 2020-04-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-04-30 | Submittal Number: 03 20 00-48.0 From: MIKE SOLFELT Final Due Date: 04/30/20 Subject: SE SNORKEL REINFORCING Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 07316 | Forwarded | For Review | 2020-04-16 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-23 | Submittal Number: 03 20 00-48.0 From: MIKE SOLFELT Final Due Date: 04/30/20 Subject: SE SNORKEL REINFORCING Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05655 | Review Response | Approved as Noted | 2020-04-29 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07658 | Responded and Closed | Approved as Noted | 2020-04-30 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-16 |  | 032000-0048-SE Snorkel Reinforcing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-16 |  | 032000-0048-SE Snorkel Reinforcing.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-15 02:00 |  | 032000-0048-SE Snorkel Reinforcing.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-30 02:00 |  | 032000-0048-SE Snorkel Reinforcing_TT REVIEW_POP.pdf
03 20 00-049-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-049-00 SE Snorkel Detention Vault | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-24 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-05-08 | 2020-05-06 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05538 | Received | For Review | 2020-04-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-05-08 | Submittal Number: 03 20 00-49.0 From: MIKE SOLFELT Final Due Date: 05/08/20 Subject: SE SNORKEL DETENTION VAULT Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 07511 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-01 | Submittal Number: 03 20 00-49.0 From: MIKE SOLFELT Final Due Date: 05/08/20 Subject: SE SNORKEL DETENTION VAULT Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 07517 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-05-01 | Submittal Number: 03 20 00-49.0 From: MIKE SOLFELT Final Due Date: 05/08/20 Subject: SE SNORKEL DETENTION VAULT Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 05716 | Review Response | Approved as Noted | 2020-05-04 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached submittal review. - J. Grant, DCI Engineers | Info Exchange
| 05755 | Review Response | Approved as Noted | 2020-05-06 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07815 | Forwarded | For Review | 2020-05-06 | Josh Dobken (Populous) | Jarrett Grant (DCI Engineers) | 2020-05-08 | Submittal Number: 03 20 00-49.0 From: MIKE SOLFELT Final Due Date: 05/08/20 Subject: SE SNORKEL DETENTION VAULT Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 07816 | Responded and Closed | Approved as Noted | 2020-05-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached submittal review. - J. Grant, DCI Engineers Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | 032000-0049- SE Snorkel Detention Vault.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-24 |  | 032000-0049- SE Snorkel Detention Vault.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-24 |  | 032000-0049- SE Snorkel Detention Vault.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-04-24 |  | 032000-0049- SE Snorkel Detention Vault.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-23 02:00 |  | 032000-0049- SE Snorkel Detention Vault.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-04-23 02:00 |  | 032000-0049- SE Snorkel Detention Vault.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-06 02:00 |  | 032000-0049- SE Snorkel Detention Vault_TT REVIEW&DCI_POP.pdf
03 20 00-050-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-050-00 SOMD Area E | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-20 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-04 07:00 | 2020-06-09 | 21 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05952 | Received | For Review | 2020-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-06-04 07:00 | Submittal Number: 03 20 00-50.0 From: MIKE SOLFELT Final Due Date: 06/03/20 Subject: SOMD AREA E Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 08082 | Forwarded | For Review | 2020-05-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-27 | Submittal Number: 03 20 00-50.0 From: MIKE SOLFELT Final Due Date: 06/03/20 Subject: SOMD AREA E Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 06292 | Review Response | Approved as Noted | 2020-06-03 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08489 | Responded and Closed | Approved as Noted | 2020-06-09 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-20 |  | 032000-0050- Sector E SOMD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-20 |  | 032000-0050- Sector E SOMD.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-05-20 |  | 032000-0050- Sector E SOMD.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-09 |  | 032000-0050- Sector E SOMD_TT_POP.pdf
03 20 00-051-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-051-00 Area A SOMD | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-24 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-09 07:00 | 2020-07-14 | 21 |  | Record Copies; Transfers; Submittals | 03 20 00-051-00-01 - 03 20 00-051-00 Area A SOMD | 17 |  | 2020-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06577 | Received | For Review | 2020-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-09 07:00 | Submittal Number: 03 20 00-51.0 From: DEVON WALTERS Final Due Date: 07/07/20 Subject: AREA A SOMD Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 08857 | Forwarded | For Review | 2020-06-23 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-30 | Submittal Number: 03 20 00-51.0 From: DEVON WALTERS Final Due Date: 07/07/20 Subject: AREA A SOMD Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 06959 | Review Response | Approved as Noted | 2020-07-09 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Arch to review a few dimensions as noted. | Info Exchange
| 09326 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-23 |  | 032000-0051- Area A SOMD.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-23 |  | 032000-0051- Area A SOMD.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-23 |  | 032000-0051- Area A SOMD.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-14 |  | 032000-0051- Area A SOMD_TT_POP.pdf
03 20 00-051-00-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-051-00 Area A SOMD | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 20 00-051-00 - 03 20 00-051-00 Area A SOMD | -1 | 2020-07-28
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-14 |  | 032000-0051- Area A SOMD_TT_POP.pdf
03 20 00-052-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-052-00 Area D SOG | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-25 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-10 07:00 | 2020-07-14 | 20 |  | Record Copies; Transfers; Submittals | 03 20 00-052-00-01 - 03 20 00-052-00 Area D SOG | 21 |  | 2020-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06586 | Received | For Review | 2020-06-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-10 07:00 | Submittal Number: 03 20 00-52.0 From: DEVON WALTERS Final Due Date: 07/08/20 Subject: AREA D SOG Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 08875 | Forwarded | For Review | 2020-06-24 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-01 | Submittal Number: 03 20 00-52.0 From: DEVON WALTERS Final Due Date: 07/08/20 Subject: AREA D SOG Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 06958 | Review Response | Revise and Resubmit | 2020-07-14 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Hydrotherapy Pit details to be formally submitted to TT for approval. | Info Exchange
| 09325 | Responded and Closed | Revise and Resubmit | 2020-07-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-24 |  | 032000-0052- Area D SOG.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-24 |  | 032000-0052- Area D SOG.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-24 |  | 032000-0052- Area D SOG.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-14 |  | 032000-0052- Area D SOG_TT_POP.pdf
03 20 00-052-00-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-052-00 Area D SOG | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 20 00-052-00 - 03 20 00-052-00 Area D SOG | -1 | 2020-07-28
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-14 |  | 032000-0052- Area D SOG_TT_POP.pdf
03 20 00-053-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-053-00 SOMD Area B and F | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-21 | 2020-07-23 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-07-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06795 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 03 20 00-53.0 From: MIKE SOLFELT Final Due Date: 07/20/20 Subject: SOMD AREA B AND F Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09130 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-13 | Submittal Number: 03 20 00-53.0 From: MIKE SOLFELT Final Due Date: 07/20/20 Subject: SOMD AREA B AND F Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 07091 | Review Response | Approved as Noted | 2020-07-21 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See comments on submittal. Populous, please review T/wall and T/Slab elevations shown on this submittal. Additionally, see question on page 10 of submittal regarding extents of a wall. | Info Exchange
| 09512 | Responded and Closed | Approved as Noted | 2020-07-23 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 032000-0053 SOMD Area B and F.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 032000-0053 SOMD Area B and F.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-07-06 |  | 032000-0053 SOMD Area B and F.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-23 |  | 032000-0053 SOMD Area B and F_TT_POP.pdf
03 20 00-054-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-054-00 SW Snorkel Foundations Redesign | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-21 | 2020-07-21 | 15 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06796 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 03 20 00-54.0 From: MIKE SOLFELT Final Due Date: 07/20/20 Subject: SW SNORKEL FOUNDATIONS REDESIGN Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09131 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-13 | Submittal Number: 03 20 00-54.0 From: MIKE SOLFELT Final Due Date: 07/20/20 Subject: SW SNORKEL FOUNDATIONS REDESIGN Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 07063 | Review Response | Approved as Noted | 2020-07-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09453 | Responded and Closed | Approved as Noted | 2020-07-21 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | SEE ATTACHED FOR REVIEW AND RESPONSE. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 032000-0054 SW Snorkel Foundations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 032000-0054 SW Snorkel Foundations.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-06 |  | 032000-0054 SW Snorkel Foundations.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-21 |  | 032000-0054 SW Snorkel Foundations_TT_POP.pdf
03 20 00-055-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-055-00 Tunnel Rebar Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-03 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-17 | 2020-08-24 | 22 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07305 | Received | For Review | 2020-08-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-17 | Submittal Number: 03 20 00-55.0 From: TYRONE THORNTON Final Due Date: 08/17/20 Subject: TUNNEL REBAR SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09744 | Forwarded | For Review | 2020-08-03 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-10 | Submittal Number: 03 20 00-55.0 From: TYRONE THORNTON Final Due Date: 08/17/20 Subject: TUNNEL REBAR SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 07671 | Review Response | Approved as Noted | 2020-08-18 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 10216 | Responded and Closed | No Action Taken or Required | 2020-08-24 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Voided per Mortenson's request. The submittal indicated in the subject was intended to be submitted to MJA and not Populous. The submittal has been updated in Procore, but you’ll need to update your system. -POP 8/21/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-03 |  | 03 20 00-TunnelRebarShopDrawings_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-03 |  | 03 20 00-55.0 TunnelRebarShopDrawings_MAM Review.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-08-03 |  | 03 20 00-55.0 TunnelRebarShopDrawings_MAM Review.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-08-03 |  | 03 20 00-TunnelRebarShopDrawings_MAM Review.pdf
03 20 00-055-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-055-01 Tunnel Rebar SD | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-15 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-29 | 2020-09-16 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-09-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08089 | Received | For Review | 2020-09-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2020-09-29 | Submittal Number: 03 20 00-55.0 From: TYRONE THORNTON Final Due Date: 08/3/20 Subject: TUNNEL REBAR SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 10757 | Forwarded | For Review | 2020-09-14 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-21 | Submittal Number: 03 20 00-55.0 From: TYRONE THORNTON Final Due Date: 08/3/20 Subject: TUNNEL REBAR SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 08151 | Review Response | Approved as Noted | 2020-09-15 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 10824 | Responded and Closed | Approved as Noted | 2020-09-16 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-14 |  | 03 20 00-055-1 Tunnel Rebar Shop Drawings_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-14 |  | 03 20 00-055-1 Tunnel Rebar Shop Drawings_MAM Review.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-09-14 |  | 03 20 00-055-1 Tunnel Rebar Shop Drawings_MAM Review.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-09-16 |  | 03 20 00-055-1 Tunnel Rebar Shop Drawings_MAM Review_TT Review-POP.pdf
03 20 00-058-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-058-00 South Parcel - Cast In-Place Concrete Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-04 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-21 | 2020-09-15 | 12 |  | Record Copies; Transfers; Submittals | 03 20 00-058-01 - 03 20 00-058-00 South Parcel - Cast In-Place Concrete Mix Design | 7 |  | 2020-09-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07967 | Received | For Review | 2020-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-21 | Submittal Number: 03 20 00-58.0 From: TYRONE THORNTON Final Due Date: 09/18/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE MIX DESIGN Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 10592 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-15 | Submittal Number: 03 20 00-58.0 From: TYRONE THORNTON Final Due Date: 09/18/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE MIX DESIGN Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 08127 | Review Response | Revise and Resubmit | 2020-09-14 | Andy Tatkowski (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached. ART ¦ TT ¦ 9/14/2020 | Info Exchange
| 10797 | Responded and Closed | Revise and Resubmit | 2020-09-15 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Andy Tatkowski (Thornton Tomasetti) Remarks: See attached. ART ¦ TT ¦ 9/14/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-04 |  | 032000-58_Tunnel Final Liner Mix Design_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-04 |  | 032000-58_Tunnel Final Liner Mix Design_MAM Review.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-09-14 02:00 |  | 032000-58_Tunnel Final Liner Mix Design_MAM Review_TT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-15 02:00 |  | 032000-58_Tunnel Final Liner Mix Design_MAM Review_TT_POP.pdf
03 20 00-058-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-058-00 South Parcel - Cast In-Place Concrete Mix Design | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 20 00-058-00 - 03 20 00-058-00 South Parcel - Cast In-Place Concrete Mix Design | -1 | 2020-09-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-15 02:00 |  | 032000-58_Tunnel Final Liner Mix Design_MAM Review_TT_POP.pdf
03 20 00-059-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-059-00 SW Snorkel Walls - CCD Revisions | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-04 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-18 | 2020-08-17 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-08-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07330 | Received | For Review | 2020-08-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-18 | Submittal Number: 03 20 00-59.0 From: MIKE SOLFELT Final Due Date: 08/17/20 Subject: SW SNORKEL WALLS - CCD REVISIONS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09775 | Forwarded | For Review | 2020-08-03 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-10 | Submittal Number: 03 20 00-59.0 From: MIKE SOLFELT Final Due Date: 08/17/20 Subject: SW SNORKEL WALLS - CCD REVISIONS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 07577 | Review Response | Approved as Noted | 2020-08-12 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 10084 | Responded and Closed | Approved as Noted | 2020-08-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | SEE ATTACHED FOR REVIEW AND RESPONSE. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-03 |  | 032000-0059 SW Snorkel Walls - CCD60 Revisions.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-03 |  | 032000-0059 SW Snorkel Walls - CCD60 Revisions.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-03 |  | 032000-0059 SW Snorkel Walls - CCD60 Revisions.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-17 |  | 032000-0059 SW Snorkel Walls - CCD60 Revisions_TT_POP.pdf
03 20 00-060-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-060-00 SOG Reinforcing Balance | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-14 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-28 | 2020-09-02 | 20 |  | Record Copies; Transfers; Submittals | 03 20 00-060-00-01 - 03 20 00-060-00 SOG Reinforcing Balance | 15 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07569 | Received | For Review | 2020-08-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-08-28 | Submittal Number: 03 20 00-60.0 From: MIKE SOLFELT Final Due Date: 08/28/20 Subject: SOG REINFORCING BALANCE Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 10075 | Forwarded | For Review | 2020-08-17 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-24 | Submittal Number: 03 20 00-60.0 From: MIKE SOLFELT Final Due Date: 08/28/20 Subject: SOG REINFORCING BALANCE Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 07894 | Review Response | Approved as Noted | 2020-08-31 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 10501 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-02 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-14 |  | 032000-0060 SOG Balance.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-14 |  | 032000-0060 SOG Balance.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-14 |  | 032000-0060 SOG Balance.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-02 |  | 032000-0060 SOG Balance_TT_POP.pdf
03 20 00-060-00-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-060-00 SOG Reinforcing Balance | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 20 00-060-00 - 03 20 00-060-00 SOG Reinforcing Balance | -1 | 2020-09-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-02 |  | 032000-0060 SOG Balance_TT_POP.pdf
03 20 00-062-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-062-00 South Parcel - North Portal Slab & Lid Concrete Reinforcing Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-16 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-30 | 2020-11-03 | 19 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-11-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08819 | Received | For Review | 2020-10-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-10-30 | Submittal Number: 03 20 00-62.0 From: TYRONE THORNTON Final Due Date: 10/29/20 Subject: SOUTH PARCEL - NORTH PORTAL SLAB & LID CONCRETE REINFORCING SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 11652 | Forwarded | For Review | 2020-10-15 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-22 | Submittal Number: 03 20 00-62.0 From: TYRONE THORNTON Final Due Date: 10/29/20 Subject: SOUTH PARCEL - NORTH PORTAL SLAB & LID CONCRETE REINFORCING SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09186 | Review Response | Approved as Noted | 2020-10-27 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 12133 | Responded and Closed | Approved as Noted | 2020-11-03 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-15 |  | 03 20 00- Rebar Shop Drawings-North Portal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-15 |  | 03 20 00-062-0 Rebar Shop Drawings-North Portal_MAM Review.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-10-15 |  | 03 20 00-062-0 Rebar Shop Drawings-North Portal_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-03 |  | 03 20 00-062-0 Rebar Shop Drawings-North Portal_MAM Review_TTReview-POP.pdf
03 20 00-063-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-063-00 Area 6 Landscape Reinforcing Shops | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-19 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-11-02 | 2020-11-16 | 29 |  | Record Copies; Transfers; Submittals |  | 32 |  | 2020-11-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08834 | Received | For Review | 2020-10-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-11-02 | Submittal Number: 03 20 00-63.0 From: CHRISTIAN ALBERS Final Due Date: 10/30/20 Subject: AREA 6 LANDSCAPE REINFORCING SHOPS Description: PLEASE REVIEW AREA 6 LANDSCAPE REINFORCING SHOP DRAWINGS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 11672 | Forwarded | For Review | 2020-10-16 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-23 | Submittal Number: 03 20 00-63.0 From: CHRISTIAN ALBERS Final Due Date: 10/30/20 Subject: AREA 6 LANDSCAPE REINFORCING SHOPS Description: PLEASE REVIEW AREA 6 LANDSCAPE REINFORCING SHOP DRAWINGS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 12077 | Forwarded | For Review | 2020-11-02 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-11-02 | Submittal Number: 03 20 00-63.0 From: CHRISTIAN ALBERS Final Due Date: 10/30/20 Subject: AREA 6 LANDSCAPE REINFORCING SHOPS Description: PLEASE REVIEW AREA 6 LANDSCAPE REINFORCING SHOP DRAWINGS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09326 | Review Response | Approved as Noted | 2020-11-09 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | See attached for comments on this submittal. | Email
| 09440 | Review Response | Approved as Noted | 2020-11-16 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | REVIEW FOR DESIGN INTENT AND CONFORMANCE WITH CONSTRUCTION DOCUMENTS IN COORDINATION WITH TT. | Info Exchange
| 12449 | Responded and Closed | Approved as Noted | 2020-11-16 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: REVIEW FOR DESIGN INTENT AND CONFORMANCE WITH CONSTRUCTION DOCUMENTS IN COORDINATION WITH TT. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-16 |  | 032000-0063 Area 6 Reinforcing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-16 |  | 032000-0063 Area 6 Reinforcing.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-15 02:00 |  | 032000-0063 Area 6 Reinforcing.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-11-09 02:00 |  | 032000-0063 Area 6 Reinforcing - SWIFT.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-11-16 02:00 |  | 032000-0063 Area 6 Reinforcing - SWIFT_TT REVIEW -SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-16 02:00 |  | 032000-0063 Area 6 Reinforcing - SWIFT_TT REVIEW -SWIFT_pop.pdf
03 20 00-064-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-064-00 03 20 00 - Concrete Reinforcement - Decline Ramp RW3 Shop Drawings | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-22 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-05 | 2020-11-02 | 12 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-11-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08941 | Received | For Review | 2020-10-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-05 | Submittal Number: 03 20 00-64.0 From: EVAN REPPLIER Final Due Date: 11/05/20 Subject: 03 20 00 - CONCRETE REINFORCEMENT - DECLINE RAMP RW3 SHOP DRAWINGS Description: DECLINE RAMP RW3 REBAR SHOP DRAWINGS Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 11811 | Forwarded | For Review | 2020-10-22 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-29 | Submittal Number: 03 20 00-64.0 From: EVAN REPPLIER Final Due Date: 11/05/20 Subject: 03 20 00 - CONCRETE REINFORCEMENT - DECLINE RAMP RW3 SHOP DRAWINGS Description: DECLINE RAMP RW3 REBAR SHOP DRAWINGS Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09169 | Review Response | Approved as Noted | 2020-10-29 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 12103 | Responded and Closed | Approved as Noted | 2020-11-02 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 12120 | Sent | For Information Only | 2020-11-02 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-22 |  | 03 20 00 - South Decline Ramp RW3 Rebar Shop Drawings_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-22 |  | 03 20 00 - South Decline Ramp RW3 Rebar Shop Drawings_MAM Review.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-10-22 |  | 03 20 00 - South Decline Ramp RW3 Rebar Shop Drawings_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-02 |  | 03 20 00 - South Decline Ramp RW3 Rebar Shop Drawings_TT Review-POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-10-21 02:00 |  | 03 20 00 - South Decline Ramp RW3 Rebar Shop Drawings_MAM Review.pdf
03 20 00-065-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-065-00 03 20 00 - Concrete Reinforcement - Dogbone & Decline Ramp Shoring Wall Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-28 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-11 | 2020-11-13 | 17 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-11-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09062 | Received | For Review | 2020-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-11 | Submittal Number: 03 20 00-65.0 From: TYRONE THORNTON Final Due Date: 11/10/20 Subject: 03 20 00 - CONCRETE REINFORCEMENT - DOGBONE & DECLINE RAMP SHORING WALL SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 11950 | Forwarded | For Review | 2020-10-28 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-04 | Submittal Number: 03 20 00-65.0 From: TYRONE THORNTON Final Due Date: 11/10/20 Subject: 03 20 00 - CONCRETE REINFORCEMENT - DOGBONE & DECLINE RAMP SHORING WALL SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09419 | Review Response | Approved as Noted | 2020-11-06 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Approved as Noted | Info Exchange
| 12433 | Responded and Closed | Approved as Noted | 2020-11-13 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 03 20 00 - South Parcel Shoring Walls Rebar Shop Drawings_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 03 20 00-065-0 South Parcel Shoring Walls Rebar Shop Drawings_MAM Review.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-10-27 |  | 03 20 00-065-0 South Parcel Shoring Walls Rebar Shop Drawings_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-13 |  | 03 20 00 - 65 South Parcel Shoring Walls Rebar Shop Drawings_MAM Review_TT-POP.pdf
03 20 00-066-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-066-00 South Parcel - Generator Slab & Wall Rebar Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-04 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-18 | 2020-11-19 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-11-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09221 | Received | For Review | 2020-11-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-18 | Submittal Number: 03 20 00-66.0 From: TYRONE THORNTON Final Due Date: 11/17/20 Subject: SOUTH PARCEL - GENERATOR SLAB & WALL REBAR SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 12176 | Forwarded | For Review | 2020-11-04 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-11 | Submittal Number: 03 20 00-66.0 From: TYRONE THORNTON Final Due Date: 11/17/20 Subject: SOUTH PARCEL - GENERATOR SLAB & WALL REBAR SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09623 | Review Response | Approved as Noted | 2020-11-19 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Approved As Noted | Info Exchange
| 12659 | Responded and Closed | Approved as Noted | 2020-11-19 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-03 |  | Generator Slab & Wall Rebar Shop Drawings_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-03 |  | 03 20 00-066-00 Generator Slab & Wall Rebar Shop Drawings_MAM Review.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-11-03 |  | 03 20 00-066-00 Generator Slab & Wall Rebar Shop Drawings_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-19 |  | 03 20 00-066-00 Generator Slab & Wall Rebar Shop Drawings_MAM Review_TT-POP.pdf
03 20 00-066-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-066-01 South Parcel - Generator Slab & Wall Rebar Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-18 | 2021-02-10 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-02-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11176 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-02-18 | Submittal Number: 03 20 00-66.1 From: TYRONE THORNTON Final Due Date: 02/17/21 Subject: SOUTH PARCEL - GENERATOR SLAB & WALL REBAR SHOP DRAWINGS Description: REVISED SHOP DRAWINGS INCLUDE THE CONTINUATION OF THE CONCRETE BEAM INTO THE WEST SADDLEBAG OF THE SOUTH PORTAL AND REFLECTS A CHANGE IN THE THICKNESS OF THE BEAM TO ACCOMMODATE THE QUANTITY OF CONDUIT. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 14482 | Forwarded | For Review | 2021-02-03 | Tyrone Thornton (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-10 | Submittal Number: 03 20 00-66.1 From: TYRONE THORNTON Final Due Date: 02/17/21 Subject: SOUTH PARCEL - GENERATOR SLAB & WALL REBAR SHOP DRAWINGS Description: REVISED SHOP DRAWINGS INCLUDE THE CONTINUATION OF THE CONCRETE BEAM INTO THE WEST SADDLEBAG OF THE SOUTH PORTAL AND REFLECTS A CHANGE IN THE THICKNESS OF THE BEAM TO ACCOMMODATE THE QUANTITY OF CONDUIT. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 11314 | Review Response | Approved | 2021-02-04 | Sean McNeill (Thornton Tomasetti) | Tyrone Thornton (Mortenson Construction) |  |  | Info Exchange
| 14668 | Responded and Closed | Approved | 2021-02-10 | Tyrone Thornton (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-03 |  | 03 20 00 - Generator Slab Shop Drawings_Revised.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-02-03 |  | 03 20 00 - Generator Slab Shop Drawings_Revised.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-02-03 |  | 03 20 00 - Generator Slab Shop Drawings_Revised.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-02-04 |  | 03 20 00-066-01 Generator Slab Shop Drawings_Revised_TT.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-02-10 |  | 03 20 00-066-01 Generator Slab Shop Drawings_Revised_TT-POP.pdf
03 20 00-067-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-067-00 SEDA Area B Additional Footings/Columns/Deck | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-12 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-30 08:00 | 2020-11-18 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09401 | Received | For Review | 2020-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-11-30 08:00 | Submittal Number: 03 20 00-67.0 From: CHRISTIAN ALBERS Final Due Date: 11/26/20 Subject: SEDA AREA B ADDITIONAL FOOTINGS/COLUMNS/DECK Description: SEE ATTACHED REINFORCEMENT SHOP DRAWING FOR AREA B FOOTINGS/COLUMNS/DECK ADDED FOR THE SEDA PACKAGE. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 12405 | Forwarded | For Review | 2020-11-12 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-19 | Submittal Number: 03 20 00-67.0 From: CHRISTIAN ALBERS Final Due Date: 11/26/20 Subject: SEDA AREA B ADDITIONAL FOOTINGS/COLUMNS/DECK Description: SEE ATTACHED REINFORCEMENT SHOP DRAWING FOR AREA B FOOTINGS/COLUMNS/DECK ADDED FOR THE SEDA PACKAGE. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09533 | Review Response | Rejected | 2020-11-17 | Raymond Chou (Thornton Tomasetti) | Shaina Burris (Populous) |  | See notes on submittal. | Info Exchange
| 12552 | Responded and Closed | Rejected | 2020-11-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE TT'S NOTES. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-12 |  | 032000-0067 SEDA Area B Additional Footings Columns Deck.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-12 |  | 032000-0067 SEDA Area B Additional Footings Columns Deck.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2020-11-17 |  | 032000-0067 SEDA Area B Additional Footings Columns Deck_TT REVIEWED.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-18 |  | 032000-0067 SEDA Area B Additional Footings Columns Deck_TT REVIEWED-POP.pdf
03 20 00-067-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-067-01 SEDA Area B Additional Footings/Columns/Deck | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-24 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-10 | 2020-12-15 | 22 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09698 | Received | For Review | 2020-11-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-12-10 | Submittal Number: 03 20 00-67.1 From: CHRISTIAN ALBERS Final Due Date: 12/07/20 Subject: SEDA AREA B ADDITIONAL FOOTINGS/COLUMNS/DECK Description: SEE ATTACHED REINFORCEMENT SHOP DRAWING FOR AREA B FOOTINGS/COLUMNS/DECK ADDED FOR THE SEDA PACKAGE. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 12759 | Forwarded | For Review | 2020-11-23 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-30 | Submittal Number: 03 20 00-67.1 From: CHRISTIAN ALBERS Final Due Date: 12/07/20 Subject: SEDA AREA B ADDITIONAL FOOTINGS/COLUMNS/DECK Description: SEE ATTACHED REINFORCEMENT SHOP DRAWING FOR AREA B FOOTINGS/COLUMNS/DECK ADDED FOR THE SEDA PACKAGE. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09781 | Review Response | Approved as Noted | 2020-11-30 | Raymond Chou (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 13318 | Responded and Closed | Approved as Noted | 2020-12-15 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Raymond Chou (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-23 |  | 032000-0067.1 SEDA Area B Additional Footings Columns Deck.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-23 |  | 032000-0067.1 SEDA Area B Additional Footings Columns Deck.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2020-12-01 02:00 |  | 032000-0067.1 SEDA Area B Additional Footings Columns Deck_TT REVIEWED UPDATED.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-15 02:00 |  | 032000-0067.1 SEDA Area B Additional Footings Columns Deck_TT REVIEWED UPDATED_pop.pdf
03 20 00-068-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-068-00 03 20 00 - Tunnel Shotcrete Mock-Up Rebar Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-20 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-08 | 2020-12-01 | 12 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09639 | Received | For Review | 2020-11-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-12-08 | Submittal Number: 03 20 00-68.0 From: TYRONE THORNTON Final Due Date: 12/04/20 Subject: 03 20 00 - TUNNEL SHOTCRETE MOCK-UP REBAR SHOP DRAWINGS Description: SHOTCRETE MOCKUP REBAR SHOP DRAWINGS WITH LINKS Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 12682 | Forwarded | For Review | 2020-11-20 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-27 | Submittal Number: 03 20 00-68.0 From: TYRONE THORNTON Final Due Date: 12/04/20 Subject: 03 20 00 - TUNNEL SHOTCRETE MOCK-UP REBAR SHOP DRAWINGS Description: SHOTCRETE MOCKUP REBAR SHOP DRAWINGS WITH LINKS Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09784 | Review Response | Approved as Noted | 2020-11-24 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Exceptions Noted | Info Exchange
| 12865 | Responded and Closed | Approved as Noted | 2020-12-01 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Sean McNeill (Thornton Tomasetti) Remarks: Exceptions Noted | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-20 |  | 03 20 00-Tunnel Mock-Up Rebar Shops_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-20 |  | 03 20 00-Tunnel Mock-Up Rebar Shops_MAM Review.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-11-19 02:00 |  | 03 20 00-Tunnel Mock-Up Rebar Shops_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-01 02:00 |  | 03 20 00-68 Tunnel Mock-Up Rebar Shops_MAM Review_TT_POP.pdf
03 20 00-069-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-069-00 03 20 00 - North Portal & Generator Elevated Slab Forming, Shoring, & Calcs Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-07 | 2020-12-02 | 14 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09557 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-12-07 | Submittal Number: 03 20 00-69.0 From: TYRONE THORNTON Final Due Date: 12/02/20 Subject: 03 20 00 - NORTH PORTAL & GENERATOR ELEVATED SLAB FORMING, SHORING, & CALCS SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 12579 | Forwarded | For Review | 2020-11-18 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-25 | Submittal Number: 03 20 00-69.0 From: TYRONE THORNTON Final Due Date: 12/02/20 Subject: 03 20 00 - NORTH PORTAL & GENERATOR ELEVATED SLAB FORMING, SHORING, & CALCS SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09817 | Review Response | No Action Taken or Required | 2020-11-24 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Received For Record | Info Exchange
| 12899 | Responded and Closed | No Action Taken or Required | 2020-12-02 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Received For Record | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 03 20 00 - Elevated Slab Forming & Shoring Drawings_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 03 20 00 - Elevated Slab Forming & Shoring Drawings_MAM Review.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-11-18 |  | 03 20 00 - Elevated Slab Forming & Shoring Drawings_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-02 |  | 03 20 00-69 Elevated Slab Forming & Shoring Drawings_MAM Review_TT-POP.pdf
03 20 00-070-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-070-00 03 20 00 - Concrete Reinforcement - Tunnel Exit Stair Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-03 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-17 | 2020-12-23 | 21 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-12-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09867 | Received | For Review | 2020-12-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (M.A. Mortenson Company) | 2020-12-17 | Submittal Number: 03 20 00-70.0 From: TYRONE THORNTON Final Due Date: 12/16/20 Subject: 03 20 00 - CONCRETE REINFORCEMENT - TUNNEL EXIT STAIR SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 12950 | Forwarded | For Review | 2020-12-03 | Tyrone Thornton (M.A. Mortenson Company) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-10 | Submittal Number: 03 20 00-70.0 From: TYRONE THORNTON Final Due Date: 12/16/20 Subject: 03 20 00 - CONCRETE REINFORCEMENT - TUNNEL EXIT STAIR SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 10343 | Review Response | Approved as Noted | 2020-12-09 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Approved as Noted. AOR to review/provide dimensions. | Info Exchange
| 13511 | Responded and Closed | Approved as Noted | 2020-12-23 | Tyrone Thornton (M.A. Mortenson Company) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-02 |  | 03 20 00_Tunnel Exit Slab Shop Drawings_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-02 |  | 03 20 00_Tunnel Exit Slab Shop Drawings_MAM Review.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-12-02 |  | 03 20 00_Tunnel Exit Slab Shop Drawings_MAM Review.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-09 |  | 03 20 00_Tunnel Exit Slab Shop Drawings_MAM Review_TT.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-23 |  | 03 20 00-72.0 Transformer Pad Rebar Shop Drawings_TT REVIEW-POP.pdf
03 20 00-071-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-071-00 West Temp Ramp Dywidag Rods | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-03 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-17 | 2020-12-07 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-12-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09866 | Received | For Review | 2020-12-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-12-17 | Submittal Number: 03 20 00-71.0 From: CHRISTIAN ALBERS Final Due Date: 12/16/20 Subject: WEST TEMP RAMP DYWIDAG RODS Description: SEE ATTACHED SHOP DRAWINGS FOR DYWIDAG RODS FOR THE WEST TEMP RAMP CLOSURE, VERIFY ROD LENGTHS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 12948 | Forwarded | For Review | 2020-12-03 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-10 | Submittal Number: 03 20 00-71.0 From: CHRISTIAN ALBERS Final Due Date: 12/16/20 Subject: WEST TEMP RAMP DYWIDAG RODS Description: SEE ATTACHED SHOP DRAWINGS FOR DYWIDAG RODS FOR THE WEST TEMP RAMP CLOSURE, VERIFY ROD LENGTHS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 09995 | Review Response | Revise and Resubmit | 2020-12-07 | Seth Knihtila (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT Comments: Washers required on all connections, please provide details for washers. #24 bars shall be gr. 80 steel, not gr. 75. Plates specified do not conform to contract drawings, verify plates specified are in accordance with details on SS1-109. Shop drawing for detail 9 on ss1-109 (embed plate in CIP wall) not provided, please provide this detail for review. See markups for further details. Tierod lengths provided - see attachment. | Info Exchange
| 13079 | Responded and Closed | Revise and Resubmit | 2020-12-07 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Seth Knihtila (Thornton Tomasetti) Remarks: TT Comments: Washers required on all connections, please provide details for washers. #24 bars shall be gr. 80 steel, not gr. 75. Plates specified do not conform to contract drawings, verify plates specified are in accordance with details on SS1-109. Shop drawing for detail 9 on ss1-109 (embed plate in CIP wall) not provided, please provide this detail for review. See markups for further details. Tierod lengths provided - see attachment. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-02 |  | 032000-0071 West Temp Ramp Dywidag Rods.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-02 |  | 032000-0071 West Temp Ramp Dywidag Rods.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2020-12-01 02:00 |  | 032000-0071 West Temp Ramp Dywidag Rods.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-07 02:00 |  | 032000-0071 West Temp Ramp Dywidag Rods_TT R&R_pop.pdf
03 20 00-071-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-071-01 West Temp Ramp Dywidag Rods | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-14 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-06 | 2020-12-16 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10134 | Received | For Review | 2020-12-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2021-01-06 | Submittal Number: 03 20 00-71.1 From: CHRISTIAN ALBERS Final Due Date: 12/28/20 Subject: WEST TEMP RAMP DYWIDAG RODS Description: SEE ATTACHED SHOP DRAWINGS FOR DYWIDAG RODS FOR THE WEST TEMP RAMP CLOSURE, REVISION 1. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13255 | Forwarded | For Review | 2020-12-14 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-21 | Submittal Number: 03 20 00-71.1 From: CHRISTIAN ALBERS Final Due Date: 12/28/20 Subject: WEST TEMP RAMP DYWIDAG RODS Description: SEE ATTACHED SHOP DRAWINGS FOR DYWIDAG RODS FOR THE WEST TEMP RAMP CLOSURE, REVISION 1. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 10190 | Review Response | Approved as Noted | 2020-12-16 | Seth Knihtila (Thornton Tomasetti) | Shaina Burris (Populous) |  | Submittal approved as noted. Contractor to submit substitution request RFI's for use of Gr. 75 bars and omission of washer from bearing plate assembly. TT will update drawings accordingly. Contractor to update shop drawings with increase plate thickness for record. | Info Exchange
| 13328 | Responded and Closed | Approved as Noted | 2020-12-16 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Seth Knihtila (Thornton Tomasetti) Remarks: Submittal approved as noted. Contractor to submit substitution request RFI's for use of Gr. 75 bars and omission of washer from bearing plate assembly. TT will update drawings accordingly. Contractor to update shop drawings with increase plate thickness for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-14 |  | West Temp Ramp Dywidag Shops Rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-14 |  | West Temp Ramp Dywidag Shops Rev 1.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2020-12-13 02:00 |  | West Temp Ramp Dywidag Shops Rev 1.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-16 02:00 |  | West Temp Ramp Dywidag Shops Rev 1_TT Approved as Noted_pop.pdf
03 20 00-072-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-072-00 Concrete Reinforcement - Transformer Pad Rebar Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-08 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-22 | 2020-12-23 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10004 | Received | For Review | 2020-12-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (M.A. Mortenson Company) | 2020-12-22 | Submittal Number: 03 20 00-72.0 From: TYRONE THORNTON Final Due Date: 12/21/20 Subject: 03 20 00 - CONCRETE REINFORCEMENT - TRANSFORMER PAD REBAR SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13092 | Forwarded | For Review | 2020-12-08 | Tyrone Thornton (M.A. Mortenson Company) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-15 | Submittal Number: 03 20 00-72.0 From: TYRONE THORNTON Final Due Date: 12/21/20 Subject: 03 20 00 - CONCRETE REINFORCEMENT - TRANSFORMER PAD REBAR SHOP DRAWINGS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 10342 | Review Response | Approved as Noted | 2020-12-22 | Samar Kenkre (Thornton Tomasetti) | Tyrone Thornton (M.A. Mortenson Company) |  |  | Info Exchange
| 13510 | Responded and Closed | Approved as Noted | 2020-12-23 | Tyrone Thornton (M.A. Mortenson Company) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 03 20 00 - Transformer Pad Rebar Shop Drawings_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-07 |  | 03 20 00 - Transformer Pad Rebar Shop Drawings_MAM Review.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-12-07 |  | 03 20 00 - Transformer Pad Rebar Shop Drawings_MAM Review.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-07 |  | 03 20 00 - Transformer Pad Rebar Shop Drawings_MAM Review.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-07 |  | 03 20 00-72.0 Transformer Pad Rebar Shop Drawings_MAM Review.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-08 |  | Transmittal_Submittal - 03 20 00-072-00 (Forwarded).pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-22 |  | 03 20 00-72.0 Transformer Pad Rebar Shop Drawings_TT REVIEW.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-07 |  | 03 20 00-72.0 Transformer Pad Rebar Shop Drawings_MAM Review.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-23 |  | 03 20 00-72.0 Transformer Pad Rebar Shop Drawings_TT REVIEW-POP.pdf
03 20 00-073-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-073-00 NE Snorkel North Wall Footing Reinforcement | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-08 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-22 | 2021-01-08 | 32 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2021-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10012 | Received | For Review | 2020-12-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-12-22 | Submittal Number: 03 20 00-73.0 From: CHRISTIAN ALBERS Final Due Date: 12/22/20 Subject: NE SNORKEL NORTH WALL FOOTING REINFORCEMENT Description: PLEASE CONFIRM THE FOLLOWING REINFORCEMENT IS ACCEPTABLE. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13103 | Forwarded | For Review | 2020-12-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-15 | Submittal Number: 03 20 00-73.0 From: CHRISTIAN ALBERS Final Due Date: 12/22/20 Subject: NE SNORKEL NORTH WALL FOOTING REINFORCEMENT Description: PLEASE CONFIRM THE FOLLOWING REINFORCEMENT IS ACCEPTABLE. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 10564 | Review Response | Approved as Noted | 2021-01-05 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 13772 | Responded and Closed | Approved as Noted | 2021-01-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Sean McNeill (Thornton Tomasetti) Remarks: Refer to comments within submittal. | Info Exchange
| 13875 | Sent | For Information Only | 2021-01-12 | Josh Dobken (Populous) | Simran George (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Responded and Closed (Approved as Noted) to: Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) Remarks: Response (Approved as Noted) from: Sean McNeill (Thornton Tomasetti) Remarks: Refer to comments within submittal. | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-08 |  | NE Snorkel North Wall Footing Reinforcement.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-08 |  | NE Snorkel North Wall Footing Reinforcement.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-12-07 02:00 |  | NE Snorkel North Wall Footing Reinforcement.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-08 02:00 |  | 032000-0073 NE Snorkel North Wall Footing Reinforcement-2_TT_pop.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-12-07 02:00 |  | NE Snorkel North Wall Footing Reinforcement.pdf
03 20 00-074-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-074-00 SE Snorkel Upper Con North Wall Reinforcing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-05 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-19 | 2021-01-15 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-01-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10447 | Received | For Review | 2021-01-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-01-19 | Submittal Number: 03 20 00-74.0 From: CHRISTIAN ALBERS Final Due Date: 01/18/21 Subject: SE SNORKEL UPPER CON NORTH WALL REINFORCING Description: EOR PLEASE PROVIDE ANSWERS TO CLOUDED QUESTIONS AS WELL AS PROVIDE DRILL AND EPOXY DETAIL FOR SOMD AND SHOTCRETE WALL TIE IN. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13635 | Forwarded | For Review | 2021-01-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-12 | Submittal Number: 03 20 00-74.0 From: CHRISTIAN ALBERS Final Due Date: 01/18/21 Subject: SE SNORKEL UPPER CON NORTH WALL REINFORCING Description: EOR PLEASE PROVIDE ANSWERS TO CLOUDED QUESTIONS AS WELL AS PROVIDE DRILL AND EPOXY DETAIL FOR SOMD AND SHOTCRETE WALL TIE IN. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 10752 | Review Response | Approved as Noted | 2021-01-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 13984 | Responded and Closed | Approved as Noted | 2021-01-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-04 |  | 032000-0074 SE Snorkel Upper Con North Wall Reinforcing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-04 |  | 032000-0074 SE Snorkel Upper Con North Wall Reinforcing.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-03 02:00 |  | 032000-0074 SE Snorkel Upper Con North Wall Reinforcing.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-15 02:00 |  | 032000-0074 SE Snorkel Upper Con North Wall Reinforcing_TT_pop.pdf
03 20 00-075-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-075-00 SW Detention Tank Reinforcement | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-06 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-21 08:00 | 2021-01-20 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10483 | Received | For Review | 2021-01-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-01-21 08:00 | Submittal Number: 03 20 00-75.0 From: CHRISTIAN ALBERS Final Due Date: 01/19/21 Subject: SW DETENTION TANK REINFORCEMENT Description: REVIEW ATTACHED REINFORCEMENT SHOPS FOR SW DETENTION TANK. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13683 | Forwarded | For Review | 2021-01-06 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-13 | Submittal Number: 03 20 00-75.0 From: CHRISTIAN ALBERS Final Due Date: 01/19/21 Subject: SW DETENTION TANK REINFORCEMENT Description: REVIEW ATTACHED REINFORCEMENT SHOPS FOR SW DETENTION TANK. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 10799 | Review Response | Approved as Noted | 2021-01-20 | Raymond Chou (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 14046 | Responded and Closed | Approved as Noted | 2021-01-20 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-05 |  | 032000-0075 - SW Detention Tank Reinforcement.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-05 |  | 032000-0075 - SW Detention Tank Reinforcement.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2021-01-20 |  | 032000-0075 - SW Detention Tank Reinforcement_TT REVIEWED.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-01-20 |  | 032000-0075 - SW Detention Tank Reinforcement_TT_POP.pdf
03 20 00-076-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-076-00 Area 2 Site Work Reinforcement Shops | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-01-27 08:00 | 2021-02-02 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-02-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10626 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-01-27 08:00 | Submittal Number: 03 20 00-76.0 From: CHRISTIAN ALBERS Final Due Date: 01/25/21 Subject: AREA 2 SITE WORK REINFORCEMENT SHOPS Description: SEE ATTACHED SHOP DRAWINGS FOR AREA 2 SITEWORK. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13834 | Forwarded | For Review | 2021-01-12 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-19 | Submittal Number: 03 20 00-76.0 From: CHRISTIAN ALBERS Final Due Date: 01/25/21 Subject: AREA 2 SITE WORK REINFORCEMENT SHOPS Description: SEE ATTACHED SHOP DRAWINGS FOR AREA 2 SITEWORK. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13857 | Forwarded | For Review | 2021-01-12 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-01-19 | Submittal Number: 03 20 00-76.0 From: CHRISTIAN ALBERS Final Due Date: 01/25/21 Subject: AREA 2 SITE WORK REINFORCEMENT SHOPS Description: SEE ATTACHED SHOP DRAWINGS FOR AREA 2 SITEWORK. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 11061 | Review Response | Approved as Noted | 2021-01-27 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | SDK¦TT¦1/27/2021 | Info Exchange
| 10993 | Review Response | Approved as Noted | 2021-02-02 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 14455 | Responded and Closed | Approved as Noted | 2021-02-02 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: SDK¦TT¦1/27/2021 Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 03 20 00 - 0076 - Area 2 Reinforcement Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-11 |  | 03 20 00 - 0076 - Area 2 Reinforcement Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-11 |  | 03 20 00 - 0076 - Area 2 Reinforcement Submittal.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2021-01-10 02:00 |  | 03 20 00 - 0076 - Area 2 Reinforcement Submittal.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-01-10 02:00 |  | 03 20 00 - 0076 - Area 2 Reinforcement Submittal.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-02 02:00 |  | 03 20 00 - 0076 - Area 2 Reinforcement Submittal_TT Review - SWIFT_pop.pdf
03 20 00-077-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-077-00 Shotcrete Zone 10 West Temp Ramp Leaveout | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-28 | 2021-01-15 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-01-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10697 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-01-28 | Submittal Number: 03 20 00-77.0 From: CHRISTIAN ALBERS Final Due Date: 01/27/21 Subject: SHOTCRETE ZONE 10 WEST TEMP RAMP LEAVEOUT Description: THIS SUBMITTAL IS FOR THE WEST TEMP RAMP LEAVEOUT IN THE SHOTCRETE WALL, DIMENSIONS HAVE BEEN FIELD VERIFIED. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13918 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-21 | Submittal Number: 03 20 00-77.0 From: CHRISTIAN ALBERS Final Due Date: 01/27/21 Subject: SHOTCRETE ZONE 10 WEST TEMP RAMP LEAVEOUT Description: THIS SUBMITTAL IS FOR THE WEST TEMP RAMP LEAVEOUT IN THE SHOTCRETE WALL, DIMENSIONS HAVE BEEN FIELD VERIFIED. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 10753 | Review Response | Approved as Noted | 2021-01-15 | Raymond Chou (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 13986 | Responded and Closed | Approved as Noted | 2021-01-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Raymond Chou (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 032000-0077 Shotcrete Zone 10 West Temp Ramp Leaveout.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 032000-0077 Shotcrete Zone 10 West Temp Ramp Leaveout.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2021-01-15 02:00 |  | 032000-0077 Shotcrete Zone 10 West Temp Ramp Leaveout_TT REVIEWED.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-15 02:00 |  | 032000-0077 Shotcrete Zone 10 West Temp Ramp Leaveout_TT REVIEWED_pop.pdf
03 20 00-078-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-078-00 Joint Filler | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-02-08 | 2021-02-08 | 15 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10936 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-02-08 | Submittal Number: 03 20 00-78.0 From: TYRONE THORNTON Final Due Date: 02/08/21 Subject: 03 20 00 - JOINT FILLER Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 14198 | Forwarded | For Review | 2021-01-25 | Tyrone Thornton (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-01 | Submittal Number: 03 20 00-78.0 From: TYRONE THORNTON Final Due Date: 02/08/21 Subject: 03 20 00 - JOINT FILLER Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 14261 | Forwarded | For Review | 2021-01-26 | Tyrone Thornton (Mortenson Construction) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-02-02 | Submittal Number: 03 20 00-78.0 From: TYRONE THORNTON Final Due Date: 02/08/21 Subject: 03 20 00 - JOINT FILLER Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 11269 | Review Response | Approved | 2021-01-29 | Jarrett Grant (DCI Engineers) | Tyrone Thornton (Mortenson Construction) |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 14601 | Responded and Closed | Approved as Noted | 2021-02-08 | Tyrone Thornton (Mortenson Construction) | Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 03 20 00 - Joint Filler_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-01-25 |  | 03 20 00 - Joint Filler_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-01-24 02:00 |  | 03 20 00 - Joint Filler_MAM Review.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-01-24 |  | 03 20 00 - Joint Filler_MAM Review.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-01-25 |  | 03 20 00 - Joint Filler_MAM Review.pdf
03 20 00-079-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-079-00 Area 3 Site Work Reinforcement Shops | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-03 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-17 | 2021-02-19 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11152 | Received | For Review | 2021-02-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-02-17 | Submittal Number: 03 20 00-79.0 From: CHRISTIAN ALBERS Final Due Date: 02/16/21 Subject: AREA 3 SITE WORK REINFORCEMENT SHOPS Description: PLEASE REVIEW AREA 3 REINFORCING SHOP DRAWINGS AND PROVIDE NECESSARY DETAILS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 14458 | Forwarded | For Review | 2021-02-03 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-10 | Submittal Number: 03 20 00-79.0 From: CHRISTIAN ALBERS Final Due Date: 02/16/21 Subject: AREA 3 SITE WORK REINFORCEMENT SHOPS Description: PLEASE REVIEW AREA 3 REINFORCING SHOP DRAWINGS AND PROVIDE NECESSARY DETAILS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 11548 | Review Response | Approved as Noted | 2021-02-12 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Approved as Noted | Info Exchange
| 14759 | Forwarded | For Review | 2021-02-12 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-17 | Submittal Number: 03 20 00-79.0 From: CHRISTIAN ALBERS Final Due Date: 02/16/21 Subject: AREA 3 SITE WORK REINFORCEMENT SHOPS Description: PLEASE REVIEW AREA 3 REINFORCING SHOP DRAWINGS AND PROVIDE NECESSARY DETAILS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 11553 | Review Response | Approved as Noted | 2021-02-19 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 14973 | Responded and Closed | Approved as Noted | 2021-02-19 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Sean McNeill (Thornton Tomasetti) Remarks: Approved as Noted Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | 03 20 00 - 79 - Area 3 Site Work Reinforcing Shops.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-02 |  | 03 20 00 - 79 - Area 3 Site Work Reinforcing Shops.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-02-01 02:00 |  | 03 20 00 - 79 - Area 3 Site Work Reinforcing Shops.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-02 |  | 03 20 00 - 79 - Area 3 Site Work Reinforcing Shops.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-02-01 02:00 |  | 03 20 00 - 79 - Area 3 Site Work Reinforcing Shops.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-19 02:00 |  | 03 20 00 - 79 - Area 3 Site Work Reinforcing Shops_TT-SWIFT_combined POP.pdf
03 20 00-080-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-080-00 NE Snorkel SOMD Reinforcement | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-05 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-19 | 2021-02-08 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11228 | Received | For Review | 2021-02-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-19 | Submittal Number: 03 20 00-80.0 From: MIKE SOLFELT Final Due Date: 02/19/21 Subject: NE SNORKEL SOMD REINFORCEMENT Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 14533 | Forwarded | For Review | 2021-02-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-12 | Submittal Number: 03 20 00-80.0 From: MIKE SOLFELT Final Due Date: 02/19/21 Subject: NE SNORKEL SOMD REINFORCEMENT Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 11273 | Review Response | Approved as Noted | 2021-02-08 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | Arch to Review. | Info Exchange
| 14605 | Responded and Closed | Approved | 2021-02-08 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-05 |  | 0332000-0080 NE Snorkel SOMD Reinforcement.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-05 |  | 0332000-0080 NE Snorkel SOMD Reinforcement.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-05 |  | 0332000-0080 NE Snorkel SOMD Reinforcement.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-08 |  | 03 20 00-080 NE Snorkel SOMD Reinforcement_TT_POP.pdf
03 20 00-081-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-081-00 South Parcel - Reinforcement Bar Mechanical Coupler Product Data for South Headwall of the Tunnel | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-04 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-18 | 2021-03-24 | 21 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11783 | Received | For Review | 2021-03-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-18 | Submittal Number: 03 20 00-81.0 From: CHRISTIAN GENEROSA Final Due Date: 03/18/21 Subject: SOUTH PARCEL - REINFORCEMENT BAR MECHANICAL COUPLER PRODUCT DATA FOR SOUTH HEADWALL OF THE TUNNEL Description: SOUTH PARCEL - REINFORCEMENT BAR MECHANICAL COUPLER PRODUCT DATA FOR SOUTH HEADWALL OF THE TUNNEL Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 15282 | Forwarded | For Review | 2021-03-04 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-11 | Submittal Number: 03 20 00-81.0 From: CHRISTIAN GENEROSA Final Due Date: 03/18/21 Subject: SOUTH PARCEL - REINFORCEMENT BAR MECHANICAL COUPLER PRODUCT DATA FOR SOUTH HEADWALL OF THE TUNNEL Description: SOUTH PARCEL - REINFORCEMENT BAR MECHANICAL COUPLER PRODUCT DATA FOR SOUTH HEADWALL OF THE TUNNEL Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 12226 | Review Response | Approved | 2021-03-05 | Sean McNeill (Thornton Tomasetti) | Josh Dobken (Populous) |  | No Exceptions | Info Exchange
| 15816 | Responded and Closed | Approved | 2021-03-24 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Sean McNeill (Thornton Tomasetti) Remarks: No Exceptions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-03 |  | 03 20 00-0081-00 Rebar Mech Coupler PD_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-02 02:00 |  | 03 20 00-0081-00 Rebar Mech Coupler PD_MAM.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-03-02 02:00 |  | 03 20 00-0081-00 Rebar Mech Coupler PD_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-24 02:00 |  | 03 20 00-0081-00 Rebar Mech Coupler PD_MAM_TT_POP.pdf
03 20 00-082-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-082-00 Area 7 Sitework Reinforcement Shops | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-05 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-19 | 2021-03-22 | 18 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11806 | Received | For Review | 2021-03-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-03-19 | Submittal Number: 03 20 00-82.0 From: CHRISTIAN ALBERS Final Due Date: 03/18/21 Subject: AREA 7 SITEWORK REINFORCEMENT SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 15298 | Forwarded | For Review | 2021-03-04 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-11 | Submittal Number: 03 20 00-82.0 From: CHRISTIAN ALBERS Final Due Date: 03/18/21 Subject: AREA 7 SITEWORK REINFORCEMENT SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 15372 | Forwarded | For Review | 2021-03-08 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-15 | Submittal Number: 03 20 00-82.0 From: CHRISTIAN ALBERS Final Due Date: 03/18/21 Subject: AREA 7 SITEWORK REINFORCEMENT SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 12161 | Review Response | Approved as Noted | 2021-03-11 | Franz Kogler (Thornton Tomasetti) | Rhys Van Bemmel (Swift and Company Landscape Arch) |  | Returned for Newforma closeout only. Return Swift's finalized submittal to Mortenson. TT-FK ¦ 2021-03-11 | Info Exchange
| 12162 | Review Response | Approved as Noted | 2021-03-15 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  |  | Info Exchange
| 15740 | Responded and Closed | Approved as Noted | 2021-03-22 | Christian Albers (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-04 |  | 03 20 00 - 82 - Area 7 Site Work Reinforcement Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-03-04 |  | 03 20 00 - 82 - Area 7 Site Work Reinforcement Shops.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-03 02:00 |  | 03 20 00 - 82 - Area 7 Site Work Reinforcement Shops.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-03-04 |  | 03 20 00 - 82 - Area 7 Site Work Reinforcement Shops.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-03 |  | 03 20 00 - 82 - Area 7 Site Work Reinforcement Shops.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-03-22 |  | 03 20 00 - 82 - Area 7 Site Work Reinforcement Shops_TTReview - SWIFT_TT_POP.pdf
03 20 00-083-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-083-00 Garage Entry Louver Wall Reinforcing Shops | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-08 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch) |  |  |  | 2021-03-22 | 2021-03-26 | 19 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11827 | Received | For Review | 2021-03-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-03-22 | Submittal Number: 03 20 00-83.0 From: CHRISTIAN ALBERS Final Due Date: 03/19/21 Subject: GARAGE ENTRY LOUVER WALL REINFORCING SHOPS Description: PLEASE REVIEW ATTACHED GARAGE ENTRY WALLS AND LOUVER OPENING REINFORCING SHOPS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 15333 | Forwarded | For Review | 2021-03-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-15 | Submittal Number: 03 20 00-83.0 From: CHRISTIAN ALBERS Final Due Date: 03/19/21 Subject: GARAGE ENTRY LOUVER WALL REINFORCING SHOPS Description: PLEASE REVIEW ATTACHED GARAGE ENTRY WALLS AND LOUVER OPENING REINFORCING SHOPS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 12227 | Review Response | Approved as Noted | 2021-03-09 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Approved as noted, see attached comments. TT-FK ¦ 2021-03-09 | Info Exchange
| 15817 | Forwarded | For Review | 2021-03-24 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch) | 2021-03-22 | Submittal Number: 03 20 00-83.0 From: CHRISTIAN ALBERS Final Due Date: 03/19/21 Subject: GARAGE ENTRY LOUVER WALL REINFORCING SHOPS Description: PLEASE REVIEW ATTACHED GARAGE ENTRY WALLS AND LOUVER OPENING REINFORCING SHOPS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Email
| 15844 | Responded and Closed | Approved as Noted | 2021-03-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-05 |  | 03 20 00 - 83 - Garage Entry Louver Wall Reinforcing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-05 |  | 03 20 00 - 83 - Garage Entry Louver Wall Reinforcing.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-03-04 02:00 |  | 03 20 00 - 83 - Garage Entry Louver Wall Reinforcing.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-04 02:00 |  | 03 20 00 - 83 - Garage Entry Louver Wall Reinforcing.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-03-26 |  | 03 20 00 - 83 - Garage Entry Louver Wall Reinforcing_TT_POP.pdf
03 20 00-084-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-084-00 Area 5 Site Work Reinforcing Shops | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-28 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch) |  |  |  | 2021-05-12 | 2021-05-24 | 27 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-05-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12823 | Received | For Review | 2021-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-05-12 | Submittal Number: 03 20 00-84.0 From: CHRISTIAN ALBERS Final Due Date: 05/11/21 Subject: AREA 5 SITE WORK REINFORCING SHOPS Description: SEE ATTACHED FOR AREA 5 SITE WORK REINFORCING SHOP DRAWINGS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 16600 | Forwarded | For Review | 2021-04-28 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-05 | Submittal Number: 03 20 00-84.0 From: CHRISTIAN ALBERS Final Due Date: 05/11/21 Subject: AREA 5 SITE WORK REINFORCING SHOPS Description: SEE ATTACHED FOR AREA 5 SITE WORK REINFORCING SHOP DRAWINGS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 16697 | Forwarded | For Review | 2021-05-04 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch) | 2021-05-11 | Submittal Number: 03 20 00-84.0 From: CHRISTIAN ALBERS Final Due Date: 05/11/21 Subject: AREA 5 SITE WORK REINFORCING SHOPS Description: SEE ATTACHED FOR AREA 5 SITE WORK REINFORCING SHOP DRAWINGS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13194 | Review Response | Approved as Noted | 2021-05-18 | Franz Kogler (Thornton Tomasetti) | Todd Spangler (Populous); Rhys Van Bemmel (Swift and Company Landscape Arch); Tom Usher (Populous); Gareth Loveridge (Swift and Company Landscape Arch) |  | Approved as noted, with noted items to be submitted separately for review and approval. Swift to return final copy of submittal. TT-FK ¦ 2021-05-18 | Info Exchange
| 13196 | Review Response | Approved as Noted | 2021-05-19 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | See comments for corrections, items to be submitted as separate submittal, and RFI for walls/stairs at gas meter location. | Info Exchange
| 17123 | Responded and Closed | Approved as Noted | 2021-05-24 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: Approved as noted, with noted items to be submitted separately for review and approval. Swift to return final copy of submittal. TT-FK ¦ 2021-05-18 Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See comments for corrections, items to be submitted as separate submittal, and RFI for walls/stairs at gas meter location. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-27 |  | 03 20 00 - 84 - Area 5 Site Work Reinforcing Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-04-27 |  | 03 20 00 - 84 - Area 5 Site Work Reinforcing Shops.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-04-26 02:00 |  | 03 20 00 - 84 - Area 5 Site Work Reinforcing Shops.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-04-27 |  | 03 20 00 - 84 - Area 5 Site Work Reinforcing Shops.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-04-26 |  | 03 20 00 - 84 - Area 5 Site Work Reinforcing Shops.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-24 02:00 |  | 03 20 00 - 84 - Area 5 Site Work Reinforcing Shops_TTReview - SWIFT_POP.pdf
03 20 00-085-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-085-00 Area 1 Landscape Reinforcing Shops | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-12 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-26 | 2021-05-20 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-05-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13060 | Received | For Review | 2021-05-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-05-26 | Submittal Number: 03 20 00-85.0 From: CHRISTIAN ALBERS Final Due Date: 05/25/21 Subject: AREA 1 LANDSCAPE REINFORCING SHOPS Description: SEE ATTACHED AREA 1 SITEWORK REINFORCING SHOPS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 16896 | Forwarded | For Review | 2021-05-12 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogle... | 2021-05-19 | Submittal Number: 03 20 00-85.0 From: CHRISTIAN ALBERS Final Due Date: 05/25/21 Subject: AREA 1 LANDSCAPE REINFORCING SHOPS Description: SEE ATTACHED AREA 1 SITEWORK REINFORCING SHOPS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13193 | Review Response | Approved as Noted | 2021-05-19 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached submittal. Swift to return final, reviewed version of submittal. TT-FK ¦ 2021-05-19 | Info Exchange
| 13217 | Review Response | Approved as Noted | 2021-05-20 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 17107 | Responded and Closed | Approved as Noted | 2021-05-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attached submittal. Swift to return final, reviewed version of submittal. TT-FK ¦ 2021-05-19 Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | 03 20 00 - 0085 - Area 1 Reinforcement Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-11 |  | 03 20 00 - 0085 - Area 1 Reinforcement Submittal.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-05-11 |  | 03 20 00 - 0085 - Area 1 Reinforcement Submittal.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-10 02:00 |  | 03 20 00 - 0085 - Area 1 Reinforcement Submittal.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-05-20 02:00 |  | 03 20 00 - 0085 - Area 1 Reinforcement Submittal_TTReview-SWIFT_POP.pdf
03 20 00-086-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-086-00 Area 4 Landscape Reinforcing Shops | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-06-03 07:00 | 2021-06-07 | 20 |  | Record Copies; Transfers; Submittals | 03 20 00-086-00-01 - 03 20 00-086-00 Area 4 Landscape Reinforcing Shops | 16 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13168 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-06-03 07:00 | Submittal Number: 03 20 00-86.0 From: CHRISTIAN ALBERS Final Due Date: 06/01/21 Subject: AREA 4 LANDSCAPE REINFORCING SHOPS Description: SEE ATTACHED AREA 4 REINFORCING SHOPS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 17050 | Forwarded | For Review | 2021-05-19 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogle... | 2021-05-26 | Submittal Number: 03 20 00-86.0 From: CHRISTIAN ALBERS Final Due Date: 06/01/21 Subject: AREA 4 LANDSCAPE REINFORCING SHOPS Description: SEE ATTACHED AREA 4 REINFORCING SHOPS. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13448 | Review Response | Approved as Noted/Resubmit | 2021-06-03 | Michael Croly (Thornton Tomasetti) | Christian Albers (Mortenson Construction) |  | Please see the attached file for TT's response | Info Exchange
| 13449 | Review Response | Approved as Noted | 2021-06-03 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Christian Albers (Mortenson Construction) |  | See comments in pdf. Resolve revision to walls 10-3, 10-3A, 10-3B, 10-3C to be resolved in seperate RFI. Back segment required at wall 10-4A (updated detail attached). | Info Exchange
| 17386 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-07 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Michael Croly (Thornton Tomasetti) Remarks: Please see the attached file for TT's response Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See comments in pdf. Resolve revision to walls 10-3, 10-3A, 10-3B, 10-3C to be resolved in seperate RFI. Back segment required at wall 10-4A (updated detail attached). | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | 03 20 00 - 0086 - Area 4 Reinforcement Submittal.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-18 |  | 03 20 00 - 0086 - Area 4 Reinforcement Submittal.pdf
| Review Response |  | Michael Croly (Thornton Tomasetti) | 1 | 2021-05-17 02:00 |  | 03 20 00 - 0086 - Area 4 Reinforcement Submittal.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-17 02:00 |  | 03 20 00 - 0086 - Area 4 Reinforcement Submittal.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-07 02:00 |  | 03 20 00 - 0086 - Area 4 Reinforcement Submittal - SWIFT_TT_POP.pdf
03 20 00-086-00-01 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-086-00 Area 4 Landscape Reinforcing Shops | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 20 00-086-00 - 03 20 00-086-00 Area 4 Landscape Reinforcing Shops | -1 | 2021-06-21
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-07 02:00 |  | 03 20 00 - 0086 - Area 4 Reinforcement Submittal - SWIFT_TT_POP.pdf
03 20 00-087-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-087-00 Axis Lounge CIP Reinforcing Shops | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-22 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-07-07 07:00 | 2021-07-08 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13602 | Received | For Review | 2021-06-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-07-07 07:00 | Submittal Number: 03 20 00-87.0 From: CHRISTIAN ALBERS Final Due Date: 07/05/21 Subject: AXIS LOUNGE CIP REINFORCING SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 17605 | Forwarded | For Review | 2021-06-22 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-29 | Submittal Number: 03 20 00-87.0 From: CHRISTIAN ALBERS Final Due Date: 07/05/21 Subject: AXIS LOUNGE CIP REINFORCING SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13861 | Review Response | Approved as Noted | 2021-06-25 | Franz Kogler (Thornton Tomasetti) | Tom Usher (Populous); Josh Dobken (Populous) |  | See attachment for submittal comments & marks. Landscape Architect and Artist to review. TT-FK ¦ 2021-06-25 | Info Exchange
| 17712 | Forwarded | For Review | 2021-06-28 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-07-05 | Submittal Number: 03 20 00-87.0 From: CHRISTIAN ALBERS Final Due Date: 07/05/21 Subject: AXIS LOUNGE CIP REINFORCING SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13862 | Review Response | Approved as Noted | 2021-07-08 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  |  | Info Exchange
| 17942 | Responded and Closed | Approved as Noted | 2021-07-08 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attachment for submittal comments & marks. Landscape Architect and Artist to review. TT-FK ¦ 2021-06-25 Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-21 |  | 03 20 00 - 87 - Axis Lounge CIP Reinforcing Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-21 |  | 03 20 00 - 87 - Axis Lounge CIP Reinforcing Shops.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-06-20 02:00 |  | 03 20 00 - 87 - Axis Lounge CIP Reinforcing Shops.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-20 02:00 |  | 03 20 00 - 87 - Axis Lounge CIP Reinforcing Shops.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-06-20 02:00 |  | 03 20 00 - 87 - Axis Lounge CIP Reinforcing Shops.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-07-08 02:00 |  | 03 20 00 - 87 - Axis Lounge CIP Reinforcing Shops_TTReview-HD comments - SWIFT_POP.pdf
03 20 00-088-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-088-00 Site Signage Footing Reinforcing Shops | Closed | Landscape, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-23 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-07-08 07:00 | 2021-07-09 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-07-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13621 | Received | For Review | 2021-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-07-08 07:00 | Submittal Number: 03 20 00-88.0 From: CHRISTIAN ALBERS Final Due Date: 07/07/21 Subject: SITE SIGNAGE FOOTING REINFORCING SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 17637 | Forwarded | For Review | 2021-06-23 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-30 | Submittal Number: 03 20 00-88.0 From: CHRISTIAN ALBERS Final Due Date: 07/07/21 Subject: SITE SIGNAGE FOOTING REINFORCING SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 17656 | Forwarded | For Review | 2021-06-24 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-07-01 | Submittal Number: 03 20 00-88.0 From: CHRISTIAN ALBERS Final Due Date: 07/07/21 Subject: SITE SIGNAGE FOOTING REINFORCING SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13883 | Review Response | Approved as Noted | 2021-07-06 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | See attached mark up. Swift review for surface finish and layout only. Reinforcing per structural. | Info Exchange
| 13884 | Review Response | Approved as Noted | 2021-07-09 | Raymond Chou (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 17974 | Responded and Closed | Approved as Noted | 2021-07-09 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See attached mark up. Swift review for surface finish and layout only. Reinforcing per structural. Response (Approved as Noted) from: Raymond Chou (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-23 |  | 032000-0088 - Site Signage Footing Reinforcing Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-23 |  | 032000-0088 - Site Signage Footing Reinforcing Shops.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-22 02:00 |  | 032000-0088 - Site Signage Footing Reinforcing Shops.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-06-22 02:00 |  | 032000-0088 - Site Signage Footing Reinforcing Shops.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2021-07-09 02:00 |  | 032000-0088 - Site Signage Footing Reinforcing Shops_TT REVIEWED.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-07-09 02:00 |  | 032000-0088 - Site Signage Footing Reinforcing Shops - SWIFT_TT_POP.pdf
03 20 00-089-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-089-00 North Courtyard Areas 6/7 Flatwork Reinforcement Shops | Closed | Landscape, Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-01 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers), Omar Masood (DCI Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Matthew Frisby |  |  |  | 2021-07-15 07:00 | 2021-07-14 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13740 | Received | For Review | 2021-07-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-07-15 07:00 | Submittal Number: 03 20 00-89.0 From: CHRISTIAN ALBERS Final Due Date: 07/14/21 Subject: NORTH COURTYARD AREAS 6/7 FLATWORK REINFORCEMENT SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 17786 | Forwarded | For Review | 2021-06-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-07 | Submittal Number: 03 20 00-89.0 From: CHRISTIAN ALBERS Final Due Date: 07/14/21 Subject: NORTH COURTYARD AREAS 6/7 FLATWORK REINFORCEMENT SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 17793 | Forwarded | For Review | 2021-07-01 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers); Omar Masood | 2021-07-08 | Submittal Number: 03 20 00-89.0 From: CHRISTIAN ALBERS Final Due Date: 07/14/21 Subject: NORTH COURTYARD AREAS 6/7 FLATWORK REINFORCEMENT SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 17865 | Forwarded | For Review | 2021-07-06 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-07-13 | Submittal Number: 03 20 00-89.0 From: CHRISTIAN ALBERS Final Due Date: 07/14/21 Subject: NORTH COURTYARD AREAS 6/7 FLATWORK REINFORCEMENT SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13929 | Review Response | Approved as Noted | 2021-07-08 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | See attached comments. Civil Review required for paving reinforcing. | Info Exchange
| 13930 | Review Response | No Action Taken or Required | 2021-07-08 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Per Swift, no TT structural review required as all elements are off structure. | Info Exchange
| 17946 | Forwarded | For Review | 2021-07-08 | Josh Dobken (Populous) | Matthew Frisby | 2021-07-15 | Submittal Number: 03 20 00-89.0 From: CHRISTIAN ALBERS Final Due Date: 07/14/21 Subject: NORTH COURTYARD AREAS 6/7 FLATWORK REINFORCEMENT SHOPS Description: Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13931 | Review Response | Approved as Noted | 2021-07-12 | Omar Masood (DCI Engineers) | Shaina Burris (Populous) |  | DCI takes no exception to the submittal as shown. Note that this review was done after construction of the courtyard areas 6/7 were completed. - O. Masood, DCI Engineers | Info Exchange
| 18032 | Responded and Closed | Approved as Noted | 2021-07-14 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-30 |  | 032000-0089 - N. Courtyard Areas 6-7 Flatwork Reinforcement Shops.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-30 |  | 032000-0089 - N. Courtyard Areas 6-7 Flatwork Reinforcement Shops.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-30 |  | 032000-0089 - N. Courtyard Areas 6-7 Flatwork Reinforcement Shops.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-29 02:00 |  | 032000-0089 - N. Courtyard Areas 6-7 Flatwork Reinforcement Shops.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-06-29 |  | 032000-0089 - N. Courtyard Areas 6-7 Flatwork Reinforcement Shops.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-06-30 |  | 032000-0089 - N. Courtyard Areas 6-7 Flatwork Reinforcement Shops.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-29 02:00 |  | 032000-0089 - N. Courtyard Areas 6-7 Flatwork Reinforcement Shops.pdf
| Review Response |  | Omar Masood (DCI Engineers) | 1 | 2021-06-30 |  | 032000-0089 - N. Courtyard Areas 6-7 Flatwork Reinforcement Shops.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-07-08 |  | 032000-0089 - N. Courtyard Areas 6-7 Flatwork Reinforcement Shops - SWIFT.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-07-12 |  | 032000-0089 - N. Courtyard Areas 6-7 Flatwork Reinforcement Shops - DCI.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-07-14 |  | 032000-0089 - N. Courtyard Areas 6-7 Flatwork Reinforcement Shops - DCI-POP.pdf
03 20 00-090-00 | 03 20 00 - CONCRETE REINFORCEMENT | 03 20 00-090-00 Area 4 Reinforcing Resubmit SW Seatwall | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-01 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers), Omar Masood (DCI Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-07-16 07:00 | 2021-07-14 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13742 | Received | For Review | 2021-07-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-07-16 07:00 | Submittal Number: 03 20 00-90.0 From: CHRISTIAN ALBERS Final Due Date: 07/14/21 Subject: AREA 4 REINFORCING RESUBMIT SW SEATWALL Description: SEE RESUBMITTED AREA 4 SW SEATWALL, REFERENCE 03 20 00 - 86 FOR ORIGINAL SUBMITTAL. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 17788 | Forwarded | For Review | 2021-06-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-07 | Submittal Number: 03 20 00-90.0 From: CHRISTIAN ALBERS Final Due Date: 07/14/21 Subject: AREA 4 REINFORCING RESUBMIT SW SEATWALL Description: SEE RESUBMITTED AREA 4 SW SEATWALL, REFERENCE 03 20 00 - 86 FOR ORIGINAL SUBMITTAL. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 17794 | Forwarded | For Review | 2021-07-01 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers); Omar Masood | 2021-07-08 | Submittal Number: 03 20 00-90.0 From: CHRISTIAN ALBERS Final Due Date: 07/14/21 Subject: AREA 4 REINFORCING RESUBMIT SW SEATWALL Description: SEE RESUBMITTED AREA 4 SW SEATWALL, REFERENCE 03 20 00 - 86 FOR ORIGINAL SUBMITTAL. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13926 | Review Response | Approved | 2021-07-01 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Swift (Landscape) to review | Info Exchange
| 17867 | Forwarded | For Review | 2021-07-06 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-07-13 | Submittal Number: 03 20 00-90.0 From: CHRISTIAN ALBERS Final Due Date: 07/14/21 Subject: AREA 4 REINFORCING RESUBMIT SW SEATWALL Description: SEE RESUBMITTED AREA 4 SW SEATWALL, REFERENCE 03 20 00 - 86 FOR ORIGINAL SUBMITTAL. Spec Section: 03 20 00 - CONCRETE REINFORCEMENT Status: OPEN | Info Exchange
| 13927 | Review Response | Approved as Noted | 2021-07-09 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  |  | Info Exchange
| 13928 | Review Response | No Action Taken or Required | 2021-07-09 | Omar Masood (DCI Engineers) | Shaina Burris (Populous) |  | Review should be done by structural (TT) for this submittal. -O.Masood, DCI Engineers | Info Exchange
| 18031 | Responded and Closed | Approved as Noted | 2021-07-14 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-30 |  | 03 20 00 - 90 - Area 4 Reinforcing Resubmit SW Seatwall.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-30 |  | 03 20 00 - 90 - Area 4 Reinforcing Resubmit SW Seatwall.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-30 |  | 03 20 00 - 90 - Area 4 Reinforcing Resubmit SW Seatwall.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-06-30 |  | 03 20 00 - 90 - Area 4 Reinforcing Resubmit SW Seatwall.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-29 02:00 |  | 03 20 00 - 90 - Area 4 Reinforcing Resubmit SW Seatwall.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-06-29 |  | 03 20 00 - 90 - Area 4 Reinforcing Resubmit SW Seatwall.pdf
| Review Response |  | Omar Masood (DCI Engineers) | 1 | 2021-06-30 |  | 03 20 00 - 90 - Area 4 Reinforcing Resubmit SW Seatwall.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-07-01 |  | 03 20 00 - 90 - Area 4 Reinforcing Resubmit SW Seatwall_TTReview.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-07-09 |  | 03 20 00 - 90 - Area 4 Reinforcing Resubmit SW Seatwall_TTReview - SWIFT.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-07-14 |  | 03 20 00 - 90 - Area 4 Reinforcing Resubmit SW Seatwall_TTReview - SWIFT-POP.pdf
03 30 00-001-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-001-00 Shoring Foundation Mix Design | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-03-25 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti) |  |  |  | 2019-04-08 | 2019-04-05 | 12 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01092 | Received | For Review | 2019-03-25 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-08 |  | Email
| 01957 | Forwarded | For Review | 2019-03-25 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-04-01 | Concrete mix designs and product data for flowable fill, structural toes and drilled shafts. | Info Exchange
| 01128 | Review Response | Approved | 2019-04-04 | Benjamin Harmon (Thornton Tomasetti) | SCA_CCA@populous.com |  | Approved. See attached. | Info Exchange
| 02002 | Responded and Closed | Approved | 2019-04-05 | SCA_CCA@populous.com | Joe Korchemniy (Mortenson Construction) |  | Response (Approved) from: Benjamin Harmon (Thornton Tomasetti) Remarks: Approved. See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-25 |  | 03 30 00-001-0 Shoring Foundation Mix Design.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-25 |  | 03 30 00-001-0 Shoring Foundation Mix Design.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-03-25 |  | 03 30 00-001-0 Shoring Foundation Mix Design.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-05 |  | 03 30 00-001-0 Shoring Foundation Mix Design - TT review_POP.pdf
03 30 00-001-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-001-01 Shoring Foundation Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-09 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-23 | 2019-08-26 | 18 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02015 | Received | For Review | 2019-08-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ella Pilgrim; . (Seattle Arena Company, LLC) | 2019-08-23 | Submittal Number: 03 30 00-1.1 From: ELLA PILGRIM Final Due Date: 08/22/19 Subject: SHORING FOUNDATION MIX DESIGN Description: CONCRETE MIX DESIGNS AND PRODUCT DATA FOR FLOWABLE FILL, STRUCTURAL TOES AND DRILLED SHAFTS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03172 | Forwarded | For Review | 2019-08-09 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-16 | Submittal Number: 03 30 00-1.1 From: ELLA PILGRIM Final Due Date: 08/22/19 Subject: SHORING FOUNDATION MIX DESIGN Description: CONCRETE MIX DESIGNS AND PRODUCT DATA FOR FLOWABLE FILL, STRUCTURAL TOES AND DRILLED SHAFTS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02184 | Review Response | Approved | 2019-08-23 | Benjamin Harmon (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 03388 | Responded and Closed | Approved | 2019-08-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for approval. TAS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-08 |  | 03 30 00-1.1 - Shoring Foundation Mix Design.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-08 |  | 03 30 00-1.1 - Shoring Foundation Mix Design.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-08-08 |  | 03 30 00-1.1 - Shoring Foundation Mix Design.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-26 |  | 03 30 00-1.1 - Shoring Foundation Mix Design_TT_POP.pdf
03 30 00-002-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-002-00 TRS Foundation Mix Design | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-24 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-05-08 | 2019-05-02 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-05-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01214 | Received | For Review | 2019-04-24 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-08 |  | Email
| 02150 | Forwarded | For Review | 2019-04-24 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-01 |  | Info Exchange
| 01252 | Review Response | Approved | 2019-05-02 | Mark Membreno (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02212 | Responded and Closed | Approved | 2019-05-02 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-24 |  | 03 30 00-002-00 TRS Foundation Mix Design.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-24 |  | 03 30 00-002-00 TRS Foundation Mix Design.pdf
| Review Response |  | Mark Membreno (Thornton Tomasetti) | 1 | 2019-04-24 |  | 03 30 00-002-00 TRS Foundation Mix Design.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-02 |  | Submittal _03 30 00 TRS Foundation Mix Design - TT Review_POP.pdf
03 30 00-003-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-003-00 Cast-In-Place_Mix Design | Closed | Structural | Brooke Burcham (Mortenson Construction) | 2019-04-25 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous) |  |  |  | 2019-05-09 | 2019-05-16 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2019-05-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01222 | Received | For Review | 2019-04-25 | Brooke Burcham (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-09 |  | Email
| 02161 | Forwarded | For Review | 2019-04-25 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-02 |  | Info Exchange
| 01340 | Review Response | Rejected | 2019-05-16 | Matt Ross (Thornton Tomasetti) | SCA_CCA@populous.com |  | - CDF TO BE SUBMITTED IN SEPARATE SUBMITTAL. NOT TO BE REVIEWED BY TT. - SPECIFICATION PROVIDES "CONCRETE MIX DESIGN SUBMITTAL FORM" TO BE FILLE DOUT AND SUBMITTED BY CONTRACTOR. - REFER TO MASS CONCRETE IN SPEC 03 30 00 SECTION 1.6 14. FOR MASS CONCRETE SUBMITTAL REQUIREMENTS. - SEE ALL OTHER TT COMMENTS INCLUDED IN SUBMITTAL | Info Exchange
| 02326 | Forwarded | For Review | 2019-05-16 | SCA_CCA@populous.com | Todd Spangler (Populous); Tom Usher (Populous) |  |  | Info Exchange
| 02328 | Responded and Closed | Rejected | 2019-05-16 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction) |  | Response (Rejected) from: Matt Ross (Thornton Tomasetti) Remarks: - CDF TO BE SUBMITTED IN SEPARATE SUBMITTAL. NOT TO BE REVIEWED BY TT. - SPECIFICATION PROVIDES "CONCRETE MIX DESIGN SUBMITTAL FORM" TO BE FILLE DOUT AND SUBMITTED BY CONTRACTOR. - REFER TO MASS CONCRETE IN SPEC 03 30 00 SECTION 1.6 14. FOR MASS CONCRETE SUBMITTAL REQUIREMENTS. - SEE ALL OTHER TT COMMENTS INCLUDED IN SUBMITTAL | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-04-25 |  | 03 30 00-003-00 Cast-In-Place_Mix Design.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-25 |  | 03 30 00-003-00 Cast-In-Place_Mix Design.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-04-25 |  | 03 30 00-003-00 Cast-In-Place_Mix Design.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-25 |  | 03 30 00-003-00 Cast-In-Place_Mix Design.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-16 02:00 |  | 03 30 00-003-00 Cast-In-Place_Mix Design_TT REVIEW - POP.pdf
03 30 00-003-02 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-003-02 Cast-In-Place Concrete - Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-30 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-13 | 2019-08-01 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-08-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01905 | Received | For Review | 2019-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC); Mike Solfelt | 2019-08-13 | Submittal Number: 03 30 00-3.2 From: MIKE SOLFELT Final Due Date: 08/12/19 Subject: CAST-IN-PLACE CONCRETE - MIX DESIGN Description: ATTACHED ARE THE CONCRETE MIX DESIGNS FOR THE PROJECT. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03048 | Forwarded | For Review | 2019-07-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-05 | Submittal Number: 03 30 00-3.2 From: MIKE SOLFELT Final Due Date: 08/12/19 Subject: CAST-IN-PLACE CONCRETE - MIX DESIGN Description: ATTACHED ARE THE CONCRETE MIX DESIGNS FOR THE PROJECT. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 01943 | Review Response | Rejected | 2019-07-31 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please submit mix designs, product data, certificates, etc in single submittal per TT's specification. | Info Exchange
| 03090 | Responded and Closed | Rejected | 2019-08-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Please submit mix designs, product data, certificates, etc in single submittal per TT's specification. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-29 |  | 033000-0003-2 Cast-In-Place_Mix Design.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-29 |  | 033000-0003-2 Cast-In-Place_Mix Design.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-29 |  | 033000-0003-2 Cast-In-Place_Mix Design.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-07-29 |  | 033000-0003-2 Cast-In-Place_Mix Design.pdf
03 30 00-003-03 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-003-03 Cast-In-Place Concrete - Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-02 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti) |  |  |  | 2019-08-22 | 2019-08-28 | 27 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2019-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01958 | Received | For Review | 2019-08-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC); Mike Solfelt | 2019-08-22 | Submittal Number: 03 30 00-3.3 From: MIKE SOLFELT Final Due Date: 08/12/19 Subject: CAST-IN-PLACE CONCRETE - MIX DESIGN Description: ATTACHED ARE THE CONCRETE MIX DESIGNS FOR THE PROJECT. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03103 | Forwarded | For Review | 2019-08-01 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-08 | Submittal Number: 03 30 00-3.3 From: MIKE SOLFELT Final Due Date: 08/12/19 Subject: CAST-IN-PLACE CONCRETE - MIX DESIGN Description: ATTACHED ARE THE CONCRETE MIX DESIGNS FOR THE PROJECT. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02124 | Review Response | Rejected | 2019-08-19 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Hello Shaina, Please see attached TT's review of 03 3000-003.3. Thanks, Samar | Info Exchange
| 03301 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Mich... | 2019-08-16 | Submittal Number: 03 30 00-3.3 From: MIKE SOLFELT Final Due Date: 08/12/19 Subject: CAST-IN-PLACE CONCRETE - MIX DESIGN Description: ATTACHED ARE THE CONCRETE MIX DESIGNS FOR THE PROJECT. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02155 | Review Response | Revise and Resubmit | 2019-08-19 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please see attached TT's revised review of 03 30 00-003-03 . | Info Exchange
| 03335 | Responded and Closed | Revise and Resubmit | 2019-08-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Revise and Resubmit) from: Samar Kenkre (Thornton Tomasetti) Remarks: Please see attached TT's revised review of 03 30 00-003-03 . | Info Exchange
| 03440 | Reopened | Additional Information | 2019-08-28 14:09 | Josh Dobken (Populous) |  |  | Reopened for a revised submittal response from TT. See attached email.
| 03441 | Responded and Closed | Approved as Noted/Resubmit | 2019-08-28 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Reopened (Additional Information) by: Josh Dobken Remarks: Reopened for a revised submittal response from TT. See attached email. Please resubmit for record once MAM revisions are completed. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-01 |  | 033000-0003.3 Cast-In-Place_Mix Design.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-01 |  | 033000-0003.3 Cast-In-Place_Mix Design.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-08-01 |  | 033000-0003.3 Cast-In-Place_Mix Design.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-01 |  | 033000-0003.3 Cast-In-Place_Mix Design.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-07-31 02:00 |  | 033000-0003.3 Cast-In-Place_Mix Design.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-20 02:00 |  | 033000-0003.3 Cast-In-Place_Mix Design_TT_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-28 02:00 |  | 033000-0003.3 Cast-In-Place_Mix Design_TT revised_POP.pdf
03 30 00-003-04 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-003-04 Cast-In-Place Concrete - Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-30 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-09-16 07:00 | 2019-09-09 | 11 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02257 | Received | For Review | 2019-08-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-09-16 07:00 | Submittal Number: 03 30 00-3.4 From: MIKE SOLFELT Final Due Date: 09/05/19 Subject: CAST-IN-PLACE CONCRETE - MIX DESIGN Description: ATTACHED ARE THE CONCRETE MIX DESIGNS FOR THE PROJECT. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03478 | Forwarded | For Review | 2019-08-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-05 | Submittal Number: 03 30 00-3.4 From: MIKE SOLFELT Final Due Date: 09/05/19 Subject: CAST-IN-PLACE CONCRETE - MIX DESIGN Description: ATTACHED ARE THE CONCRETE MIX DESIGNS FOR THE PROJECT. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02356 | Review Response | No Action Taken or Required | 2019-09-06 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Retained for record. SDK ¦ TT ¦ 9/ 6/19 | Info Exchange
| 03594 | Responded and Closed | No Action Taken or Required | 2019-09-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (No Action Taken or Required) from: Samar Kenkre (Thornton Tomasetti) Remarks: Retained for record. SDK ¦ TT ¦ 9/ 6/19 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-29 |  | 033000-0003.4 Seattle Center Mix Design Submittal Package.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-29 |  | 033000-0003.4 Seattle Center Mix Design Submittal Package.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-08-28 02:00 |  | 033000-0003.4 Seattle Center Mix Design Submittal Package.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-09 02:00 |  | 033000-0003.4 Seattle Center Mix Design Submittal Package_TT For Record_POP.pdf
03 30 00-004-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-004-00 South Parcel Detention Vault Slab - Layout Drawing | Closed | Structural | Brooke Burcham (Mortenson Construction) | 2019-05-22 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-06-05 | 2019-05-29 | 8 |  | Record Copies; Transfers; Submittals | 03 30 00-004-01 - 03 30 00-004-01 Resub - SP Det Vault Slab - Layout Drawing | 8 |  | 2019-05-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01369 | Received | For Review | 2019-05-22 | Brooke Burcham (Mortenson Construction) | SCA_CCA@populous.com | 2019-06-05 |  | Email
| 02356 | Forwarded | For Review | 2019-05-22 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fra... | 2019-05-29 |  | Info Exchange
| 01389 | Review Response | Approved as Noted/Resubmit | 2019-05-29 | Matt Ross (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02389 | Responded and Closed | Approved as Noted/Resubmit | 2019-05-29 | SCA_CCA@populous.com | Brooke Burcham (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-05-22 |  | 03 30 00-004-00 South Parcel Detention Vault Slab - Layout Drawing.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-22 |  | 03 30 00-004-00 South Parcel Detention Vault Slab - Layout Drawing.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-05-22 |  | 03 30 00-004-00 South Parcel Detention Vault Slab - Layout Drawing.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-29 |  | 03 30 00-004-00 South Parcel Detention Vault Slab - Layout Drawing_TT_POP.pdf
03 30 00-004-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-004-01 Resub - SP Det Vault Slab - Layout Drawing | Closed | Structural | Brooke Burcham (Mortenson Construction) | 2019-06-17 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-07-01 | 2019-07-03 | 17 |  | Record Copies; Transfers; Submittals | 03 30 00-004-00 - 03 30 00-004-00 South Parcel Detention Vault Slab - Layout Drawing | 14 | 2019-06-12 | 2019-07-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01561 | Received | For Review | 2019-06-17 | Brooke Burcham (Mortenson Construction) | Shaina Burris (Populous) | 2019-07-01 |  | Email
| 02589 | Forwarded | For Review | 2019-06-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fra... | 2019-06-26 |  | Info Exchange
| 01678 | Review Response | No Action Taken or Required | 2019-07-02 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | This submittal has been maintained for record as rev0 was approved as noted. | Info Exchange
| 02752 | Responded and Closed | Not Required For Review | 2019-07-03 | Shaina Burris (Populous) | Brooke Burcham (Mortenson Construction) |  | Response (No Action Taken or Required) from: Samar Kenkre (Thornton Tomasetti) Remarks: This submittal has been maintained for record as rev0 was approved as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-06-19 |  | 03 30 00-004-01 Resub - SP Det Vault Slab - Layout Drawing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-06-19 |  | 03 30 00-004-01 Resub - SP Det Vault Slab - Layout Drawing.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-06-19 |  | 03 30 00-004-01 Resub - SP Det Vault Slab - Layout Drawing.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2019-06-19 |  | 03 30 00-004-01 Resub - SP Det Vault Slab - Layout Drawing.pdf
03 30 00-005-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-005-00: Cast-In-Place South Parcel Detention Vault - Concrete Mix Design | Closed | Structural | Brooke Burcham (Mortenson Construction) | 2019-06-07 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-06-21 | 2019-06-21 | 15 |  | Record Copies; Transfers; Submittals | 03 30 00-005-01 - 03 30 00-005-01: Cast-In-Place South Parcel Detention Vault - Concrete Mix Design | 15 |  | 2019-06-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01472 | Received | For Review | 2019-06-07 | Brooke Burcham (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-21 | Concrete Mix Design for South Parcel Detention Vault. This is for the South Parcel Detention Vault. This also includes non-shrink to be used at the south parcel detention vault. | Info Exchange
| 02479 | Forwarded | For Review | 2019-06-07 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Fra... | 2019-06-14 | Concrete Mix Design for South Parcel Detention Vault. This is for the South Parcel Detention Vault. This also includes non-shrink to be used at the south parcel detention vault. | Info Exchange
| 01594 | Review Response | Rejected | 2019-06-21 | Samar Kenkre (Thornton Tomasetti) | Todd Spangler (Populous); Josh Dobken (Populous) |  | Please see attached response to 03 30 00-005-00. We have rejected this due to missing necessary attachments that TT will need to see - admixture data, certification letters, gradation reports, etc. 6/21/2019 | Info Exchange
| 02638 | Responded and Closed | Rejected | 2019-06-21 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction) |  | Response (Rejected) from: Samar Kenkre (Thornton Tomasetti) Remarks: Please see attached response to 03 30 00-005-00. We have rejected this due to missing necessary attachments that TT will need to see - admixture data, certification letters, gradation reports, etc. 6/21/2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-06-07 |  | 03 30 00-005-00 SP Det Vault - Mix Design.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-07 |  | 03 30 00-005-00 SP Det Vault - Mix Design.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-06-07 |  | 03 30 00-005-00 SP Det Vault - Mix Design.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-21 |  | 03 30 00-005-00 SP Det Vault - Mix Design_TT_POP.pdf
03 30 00-005-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-005-01: Cast-In-Place South Parcel Detention Vault - Concrete Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-06-27 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-07-12 | 2019-06-28 | 2 |  | Record Copies; Transfers; Submittals | 03 30 00-005-00 - 03 30 00-005-00: Cast-In-Place South Parcel Detention Vault - Concrete Mix Design | 1 | 2019-07-08 | 2019-06-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01638 | Received | For Review | 2019-06-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Brooke Burcham (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-12 | Submittal Number: 03 30 00-5.1 From: BROOKE BURCHAM Final Due Date: 07/15/19 Subject: CAST-IN-PLACE SOUTH PARCEL DETENTION VAULT - CONCRETE MIX DESIGN Description: CONCRETE MIX DESIGN FOR SOUTH PARCEL DETENTION VAULT. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02703 | Forwarded | For Review | 2019-06-27 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-05 | Submittal Number: 03 30 00-5.1 From: BROOKE BURCHAM Final Due Date: 07/15/19 Subject: CAST-IN-PLACE SOUTH PARCEL DETENTION VAULT - CONCRETE MIX DESIGN Description: CONCRETE MIX DESIGN FOR SOUTH PARCEL DETENTION VAULT. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Email
| 01647 | Review Response | Approved as Noted | 2019-06-27 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 02716 | Responded and Closed | Approved as Noted | 2019-06-28 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | 033000-0005-1 SP Det Vault - Mix Design Resubmit.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | 033000-0005-1 SP Det Vault - Mix Design Resubmit(1).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | Compatibility of Ingredients 2017.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | Compatibility of Ingredients 2017(1).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | mortenson - seattle center arena - south parcel mix.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | mortenson - seattle center arena - south parcel mix(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | 033000-0005-1 SP Det Vault - Mix Design Resubmit.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | 033000-0005-1 SP Det Vault - Mix Design Resubmit(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | Compatibility of Ingredients 2017.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | Compatibility of Ingredients 2017(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | mortenson - seattle center arena - south parcel mix.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | mortenson - seattle center arena - south parcel mix(1).pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-06-27 |  | 033000-0005-1 SP Det Vault - Mix Design Resubmit.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-06-27 |  | 033000-0005-1 SP Det Vault - Mix Design Resubmit(1).pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-06-27 |  | Compatibility of Ingredients 2017.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-06-27 |  | Compatibility of Ingredients 2017(1).pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-06-27 |  | mortenson - seattle center arena - south parcel mix.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-06-27 |  | mortenson - seattle center arena - south parcel mix(1).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-28 |  | 03 30 00-005-01 SP Det Vault - Mix Design Resubmit_TT_POP.pdf
03 30 00-006-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-006-00 Concrete Finishing Product Data | Closed | Structural | Brooke Burcham (Mortenson Construction) | 2019-06-13 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2019-06-27 | 2019-06-24 | 12 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01508 | Received | For Review | 2019-06-13 | Brooke Burcham (Mortenson Construction) | SCA_CCA@populous.com | 2019-06-27 |  | Email
| 02528 | Forwarded | For Review | 2019-06-13 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fra... | 2019-06-20 |  | Info Exchange
| 01607 | Review Response | Approved as Noted | 2019-06-21 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | See attached | Info Exchange
| 02655 | Forwarded | For Review | 2019-06-24 | Populous SCA_CCA | Todd Spangler (Populous); Josh Dobken (Populous) | 2019-06-27 |  | Email
| 02664 | Responded and Closed | Approved as Noted/Resubmit | 2019-06-24 | Populous SCA_CCA | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction) |  | See attached submittal. Please revise clouded products per TT comments and resubmit. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-06-13 |  | 03 30 00-006-00 Concrete Finishing Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-13 |  | 03 30 00-006-00 Concrete Finishing Product Data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-13 |  | 03 30 00-006-00 Concrete Finishing Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-13 |  | 03 30 00-006-00 Concrete Finishing Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-06-24 |  | 03 30 00-006-00 Concrete Finishing Product Data_TT REVIEW_pop.pdf
03 30 00-006-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-006-01 Concrete Finishing Product Data & Substitution Request | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-20 | Closed - Void |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-09-03 |  | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02135 | Received | For Review | 2019-08-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-09-03 | Submittal Number: 03 30 00-6.1 From: MIKE SOLFELT Final Due Date: 09/02/19 Subject: CONCRETE FINISHING PRODUCT DATA / SUBSTITUTION REQUEST Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03313 | Forwarded | For Review | 2019-08-20 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-27 | Submittal Number: 03 30 00-6.1 From: MIKE SOLFELT Final Due Date: 09/02/19 Subject: CONCRETE FINISHING PRODUCT DATA / SUBSTITUTION REQUEST Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03321 | Closed | Void | 2019-08-20 | Josh Dobken (Populous) |  |  | This item is being voided per attached email from Mike Solfelt dated 8/20/2019.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 033000-006-01 Concrete Finishing Product Data - Substitution Request.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-08-19 |  | 033000-006-01 Concrete Finishing Product Data - Substitution Request.pdf
03 30 00-018-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-018-0 Controlled Density Fill (CDF) | Closed | Structural, Civil | Domingo Sampayo (Mortenson Construction) | 2019-04-12 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti), Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant |  |  |  | 2019-04-26 | 2019-04-30 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2019-04-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01167 | Received | For Review | 2019-04-12 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-26 |  | Email
| 02055 | Forwarded | For Review | 2019-04-12 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-04-19 |  | Info Exchange
| 02200 | Forwarded | For Review | 2019-04-30 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-26 |  | Email
| 01247 | Review Response | Approved | 2019-04-30 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  | See attached | Email
| 02203 | Responded and Closed | Approved | 2019-04-30 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-12 |  | 03 30 00-018-0 Controlled Density Fill (CDF).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-12 |  | 03 30 00-018-0 Controlled Density Fill (CDF).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-12 |  | 03 30 00-018-0 Controlled Density Fill (CDF).pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-04-30 |  | 03 30 00-018-0 Controlled Density Fill _DCI 043019.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 03 30 00-018-0 Controlled Density Fill _DCI 043019_POP.pdf
03 30 00-019-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-019-00 Bench wall across 2nd Ave (Submittal Package) | Closed | Structural | Domingo Sampayo (Mortenson Construction) | 2019-05-08 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Rhys Van Bemmel (Swift and Company Landscape Arch), Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Gareth Loveridge (Swift and Company Landscape Arch), Jarrett Grant (DCI Engineers) |  |  |  | 2019-05-22 | 2019-05-15 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-05-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01279 | Received | For Review | 2019-05-08 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-22 |  | Email
| 02245 | Forwarded | For Review | 2019-05-07 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-14 |  | Info Exchange
| 01319 | Review Response | No Action Taken or Required | 2019-05-13 | Matt Ross (Thornton Tomasetti) | SCA_CCA@populous.com |  | This should be directed at Swift and/or DCI. It appears additional information is required in order to respond but Swift/DCI can respond accordingly. | Info Exchange
| 02304 | Forwarded | For Review | 2019-05-13 | SCA_CCA@populous.com | Rhys Van Bemmel (Swift and Company Landscape Arch); Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Gareth Loveridge (Swift and Company Landscape Arch); Jarrett Grant (DCI Engineers) | 2019-05-20 | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: This should be directed at Swift and/or DCI. It appears additional information is required in order to respond but Swift/DCI can respond accordingly. | Info Exchange
| 01338 | Review Response | Not Required For Review | 2019-05-15 | Tom Usher (Populous) | Josh Dobken (Populous) |  | This work is outside the project limit line – and not in the design team scope of work. This has not been reviewed. | Info Exchange
| 02323 | Responded and Closed | Not Required For Review | 2019-05-15 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Not Required For Review) from: Tom Usher (Populous) Remarks: This work is outside the project limit line – and not in the design team scope of work. This has not been reviewed. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-05-07 |  | 03 30 00-019-00 Bench wall across 2nd Ave (Submittal Package).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-07 |  | 03 30 00-019-00 Bench wall across 2nd Ave (Submittal Package).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-05-07 |  | 03 30 00-019-00 Bench wall across 2nd Ave (Submittal Package).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-07 |  | 03 30 00-019-00 Bench wall across 2nd Ave (Submittal Package).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-15 02:00 |  | 03 30 00-019-00 Bench wall across 2nd Ave (Submittal Package)_POP.pdf
03 30 00-020-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-020-00 Alternative Shoring Foundation Mix Design | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-06-17 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-07-01 | 2019-06-27 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-06-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01537 | Received | For Review | 2019-06-17 | Joe Korchemniy (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-07-01 | Submittal Number: 03 30 00-20.0 From: JOE KORCHEMNIY Final Due Date: 06/28/19 Subject: ALTERNATIVE SHORING FOUNDATION MIX DESIGN Description: SEE ATTACHED ALTERNATIVE MIX DESIGN FOR THE SHORING FOUNDATION ELEMENTS. THIS IS INTENDED TO BE A "BACK UP" TO THE ORIGINAL MIX DESIGN. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02551 | Forwarded | For Review | 2019-06-17 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fra... | 2019-06-24 | Submittal Number: 03 30 00-20.0 From: JOE KORCHEMNIY Final Due Date: 06/28/19 Subject: ALTERNATIVE SHORING FOUNDATION MIX DESIGN Description: SEE ATTACHED ALTERNATIVE MIX DESIGN FOR THE SHORING FOUNDATION ELEMENTS. THIS IS INTENDED TO BE A "BACK UP" TO THE ORIGINAL MIX DESIGN. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 01644 | Review Response | Approved | 2019-06-27 | Benjamin Harmon (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 02709 | Responded and Closed | Approved | 2019-06-27 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Response (Approved) from: Benjamin Harmon (Thornton Tomasetti) Remarks: See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-06-17 |  | Submittal #03 30 00-20.0 Alternative Shoring Foundation Mix Design.pdf
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-06-17 |  | Submittal #03 30 00-20.0 Alternative Shoring Foundation Mix Design(1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-06-17 |  | Submittal #03 30 00-20.0 Alternative Shoring Foundation Mix Design.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-06-17 |  | Submittal #03 30 00-20.0 Alternative Shoring Foundation Mix Design.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | 03 30 00-20.0 Alternative Shoring Foundation Mix Design_TT_POP.pdf
03 30 00-021-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-021-00 Layout Drawing - TRS Tangent Pile Cap Beam | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-17 | Closed - Void |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-07-31 |  | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-07-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01798 | Received | For Review | 2019-07-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-07-31 | Submittal Number: 03 30 00-021.0 From: MIKE SOLFELT Final Due Date: 07/19/19 Subject: LAYOUT DRAWING - TRS TANGENT PILE CAP BEAM Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02923 | Forwarded | For Review | 2019-07-17 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-24 | Submittal Number: 03 30 00-021.0 From: MIKE SOLFELT Final Due Date: 07/19/19 Subject: LAYOUT DRAWING - TRS TANGENT PILE CAP BEAM Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02992 | Closed | Void | 2019-07-24 | Josh Dobken (Populous) |  |  | This is TRS related and will not be reviewed through Newforma.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-16 |  | 03 30 00 - LD 001 - TRS Tangent Pile Cap Beam.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-07-17 |  | 03 30 00-021-00 TRS Tangent Pile Cap Beam.pdf
03 30 00-022-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-022-00 Geofoam Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-17 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-07-31 | 2019-08-06 | 21 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2019-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01799 | Received | For Review | 2019-07-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-07-31 | Submittal Number: 03 30 00-022.0 From: MIKE SOLFELT Final Due Date: 07/31/19 Subject: GEOFOAM PRODUCT DATA Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02925 | Forwarded | For Review | 2019-07-17 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-24 | Submittal Number: 03 30 00-022.0 From: MIKE SOLFELT Final Due Date: 07/31/19 Subject: GEOFOAM PRODUCT DATA Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 01973 | Review Response | Approved as Noted | 2019-08-02 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 03122 | Responded and Closed | Approved as Noted | 2019-08-06 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-17 |  | 033000-0022-0 Geofoam Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-17 |  | 033000-022-0 Geofoam Product Data.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-07-17 |  | 033000-022-0 Geofoam Product Data.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2019-08-06 |  | 033000-022-0 Geofoam Product Data_TT_POP.pdf
03 30 00-024-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-024-00 Concrete Vendor Material Certificates | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-30 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-13 | 2019-08-01 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-08-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01906 | Received | For Review | 2019-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-08-13 | Submittal Number: 03 30 00-024.0 From: MIKE SOLFELT Final Due Date: 08/12/19 Subject: CONCRETE VENDOR MATERIAL CERTIFICATES Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03049 | Forwarded | For Review | 2019-07-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-05 | Submittal Number: 03 30 00-024.0 From: MIKE SOLFELT Final Due Date: 08/12/19 Subject: CONCRETE VENDOR MATERIAL CERTIFICATES Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 01944 | Review Response | Rejected | 2019-07-31 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please submit mix designs, product data, certificates, etc in single submittal per TT's specification. | Info Exchange
| 03091 | Responded and Closed | Rejected | 2019-08-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Please submit mix designs, product data, certificates, etc in single submittal per TT's specification. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-29 |  | 033000-0024-0 Vendor Material Certificates.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-29 |  | 033000-0024-0 Vendor Material Certificates.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-29 |  | 033000-0024-0 Vendor Material Certificates.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-07-29 |  | 033000-0024-0 Vendor Material Certificates.pdf
03 30 00-027-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-027-00 North Portal Secant Shaft Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-21 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-09-04 | 2019-08-26 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2019-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02165 | Received | For Review | 2019-08-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-09-04 | Submittal Number: 03 30 00-027.0 From: JOE KORCHEMNIY Final Due Date: 09/03/19 Subject: NORTH PORTAL SECANT SHAFT MIX DESIGN Description: NORTH PORTAL SECANT SHAFT MIX DESIGN. STRENGTH SHOWN AS 1000PSI, MIX DESIGNS THAT RANGE 500-1000PSI SHOWN AS 1000PSI. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03362 | Forwarded | For Review | 2019-08-21 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-28 | Submittal Number: 03 30 00-027.0 From: JOE KORCHEMNIY Final Due Date: 09/03/19 Subject: NORTH PORTAL SECANT SHAFT MIX DESIGN Description: NORTH PORTAL SECANT SHAFT MIX DESIGN. STRENGTH SHOWN AS 1000PSI, MIX DESIGNS THAT RANGE 500-1000PSI SHOWN AS 1000PSI. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02197 | Review Response | Approved | 2019-08-26 | Benjamin Harmon (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 03402 | Responded and Closed | No Action Taken or Required | 2019-08-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Benjamin Harmon (Thornton Tomasetti) Remarks: TT reviewed for information purpose only. POP/jhd - received for information only - no action taken. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-20 |  | Submittal #03 30 00-27.0 North Portal Secant Shaft Mix Design.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-20 |  | Submittal #03 30 00-27.0 North Portal Secant Shaft Mix Design.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-08-19 02:00 |  | Submittal #03 30 00-27.0 North Portal Secant Shaft Mix Design.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-26 02:00 |  | Submittal #03 30 00-27.0 North Portal Secant Shaft Mix Design_TTMK_POP.pdf
03 30 00-027-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-027-01 Alternative North Portal Secant Shaft Mix Design (CADMAN) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-09 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-09-23 | 2019-09-09 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02343 | Received | For Review | 2019-09-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-09-23 | Submittal Number: 03 30 00-027.1 From: JOE KORCHEMNIY Final Due Date: 09/20/19 Subject: ALTERNATIVE NORTH PORTAL SECANT SHAFT MIX DESIGN (CADMAN) Description: ALTERNATIVE NORTH PORTAL SECANT SHAFT MIX DESIGN FROM CADMAN. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03580 | Forwarded | For Review | 2019-09-09 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-16 | Submittal Number: 03 30 00-027.1 From: JOE KORCHEMNIY Final Due Date: 09/20/19 Subject: ALTERNATIVE NORTH PORTAL SECANT SHAFT MIX DESIGN (CADMAN) Description: ALTERNATIVE NORTH PORTAL SECANT SHAFT MIX DESIGN FROM CADMAN. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02353 | Review Response | Not Required For Review | 2019-09-09 | Meeok Kim (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT Response: Reviewed for information purpose only. MK 09/09/2019 | Info Exchange
| 03592 | Responded and Closed | No Action Taken or Required | 2019-09-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Meeok Kim (Thornton Tomasetti) Remarks: TT Response: Reviewed for information purpose only. MK 09/09/2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-09 |  | Submittal #03 30 00-27.1 Alternative North Portal Mix Design (CADMAN).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-09 |  | Submittal #03 30 00-27.1 Alternative North Portal Mix Design (CADMAN).pdf
| Review Response |  | Meeok Kim (Thornton Tomasetti) | 1 | 2019-09-08 02:00 |  | Submittal #03 30 00-27.1 Alternative North Portal Mix Design (CADMAN).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-09 02:00 |  | Submittal #03 30 00-27.1 Alternative North Portal Mix Design (CADMAN)_TT_POP.pdf
03 30 00-029-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-029-00 Tower Crane Footing Calculation Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-10 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-24 | 2019-10-11 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-10-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02723 | Received | For Review | 2019-10-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-10-24 | Submittal Number: 03 30 00-029.0 From: CHRISTIAN ALBERS Final Due Date: 10/24/19 Subject: TOWER CRANE FOOTING CALCULATION PACKAGE Description: FOR RECORD SUBMITTAL OF TOWER CRANE FOOTING CALCULATION PACKAGE. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04059 | Forwarded | For Review | 2019-10-10 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-17 | Submittal Number: 03 30 00-029.0 From: CHRISTIAN ALBERS Final Due Date: 10/24/19 Subject: TOWER CRANE FOOTING CALCULATION PACKAGE Description: FOR RECORD SUBMITTAL OF TOWER CRANE FOOTING CALCULATION PACKAGE. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02739 | Review Response | No Action Taken or Required | 2019-10-10 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  | Please see attached. We have stamped with no exceptions and will maintain for record. | Info Exchange
| 04075 | Responded and Closed | No Action Taken or Required | 2019-10-11 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Samar Kenkre (Thornton Tomasetti) Remarks: Please see attached. We have stamped with no exceptions and will maintain for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-10 |  | 033000-0029 Tower Crane Calculation Package.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-10 |  | 033000-0029 Tower Crane Calculation Package.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-10-10 |  | 033000-0029 Tower Crane Calculation Package.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-10-11 |  | 033000-0029 Tower Crane Calculation Package_TT_POP.pdf
03 30 00-030-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-030-00 Lift Drawing Submittal Area D - 1 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-15 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-29 | 2019-10-22 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-10-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02782 | Received | For Review | 2019-10-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-10-29 | Submittal Number: 03 30 00-030.0 From: MIKE SOLFELT Final Due Date: 10/29/19 Subject: LIFT DRAWING SUBMITTAL AREA D - 1 Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04101 | Forwarded | For Review | 2019-10-15 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-22 | Submittal Number: 03 30 00-030.0 From: MIKE SOLFELT Final Due Date: 10/29/19 Subject: LIFT DRAWING SUBMITTAL AREA D - 1 Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04249 | Responded and Closed | No Action Taken or Required | 2019-10-22 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Submittal not required. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-15 |  | 03 30 00 - 0030 - Lift Drawing Submittal Area D - 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-15 |  | 03 30 00 - 0030 - Lift Drawing Submittal Area D - 1.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-22 |  | 03 30 00 - 0030 - Lift Drawing Submittal Area D - 1_POP.pdf
03 30 00-032-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-032-00 Concrete Patching Product Data and Procedure | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-17 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Todd Spangler (Populous), Geoff Cheong, Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2019-10-31 | 2019-10-30 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-10-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02798 | Received | For Review | 2019-10-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-10-31 | Submittal Number: 03 30 00-032.0 From: CHRISTIAN ALBERS Final Due Date: 10/30/19 Subject: CONCRETE PATCHING PRODUCT DATA AND PROCEDURE Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04150 | Forwarded | For Review | 2019-10-16 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-23 | Submittal Number: 03 30 00-032.0 From: CHRISTIAN ALBERS Final Due Date: 10/30/19 Subject: CONCRETE PATCHING PRODUCT DATA AND PROCEDURE Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02985 | Review Response | Approved as Noted | 2019-10-30 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached | Info Exchange
| 04370 | Forwarded | For Review | 2019-10-30 | Populous SCA_CCA | Todd Spangler (Populous); Geoff Cheong; Tom Usher (Populous); Chris Minter (Populous) | 2019-10-31 | Submittal Number: 03 30 00-032.0 From: CHRISTIAN ALBERS Final Due Date: 10/30/19 Subject: CONCRETE PATCHING PRODUCT DATA AND PROCEDURE Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 02973 | Review Response | Approved as Noted | 2019-10-30 | Josh Dobken (Populous) | Populous SCA_CCA |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: See attached | Info Exchange
| 04372 | Responded and Closed | Approved as Noted | 2019-10-30 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers |  | Response (Approved as Noted) from: Josh Dobken (Populous) Remarks: See attached Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-16 |  | 03 30 00 - 032 - 0 Concrete Patching Product Data and Procedure.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-16 |  | 03 30 00 - 032 - 0 Concrete Patching Product Data and Procedure.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-10-30 02:00 |  | 03 30 00 - 032 - 0 Concrete Patching Product Data and Procedure_TT.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-15 02:00 |  | 03 30 00 - 032 - 0 Concrete Patching Product Data and Procedure.pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2019-10-30 02:00 |  | 03 30 00 - 032 - 0 Concrete Patching Product Data and Procedure_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-10-15 02:00 |  | 03 30 00 - 032 - 0 Concrete Patching Product Data and Procedure.pdf
03 30 00-033-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-033-00 Mass Concrete Submittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-29 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill |  |  |  | 2019-11-12 | 2019-11-12 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-11-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02954 | Received | For Review | 2019-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-11-12 | Submittal Number: 03 30 00-033.0 From: MIKE SOLFELT Final Due Date: 11/11/19 Subject: MASS CONCRETE SUBMITTAL Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04332 | Forwarded | For Review | 2019-10-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-05 | Submittal Number: 03 30 00-033.0 From: MIKE SOLFELT Final Due Date: 11/11/19 Subject: MASS CONCRETE SUBMITTAL Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03178 | Review Response | Approved as Noted | 2019-11-12 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | FOLLOW UP WITH ALL TEST RESULTS, AND TEMPERATURE RECORDINGS PER STRUCTURAL SPEC 03 30 00 SECTION 3.5 SDK ¦ TT ¦ 11/7/2019 | Info Exchange
| 04599 | Responded and Closed | Approved as Noted | 2019-11-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: FOLLOW UP WITH ALL TEST RESULTS, AND TEMPERATURE RECORDINGS PER STRUCTURAL SPEC 03 30 00 SECTION 3.5 SDK ¦ TT ¦ 11/7/2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-28 |  | 033000-0033-00 Mass Concrete Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-28 |  | 033000-0033-00 Mass Concrete Submittal.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-10-27 02:00 |  | 033000-0033-00 Mass Concrete Submittal.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-12 02:00 |  | 033000-0033-00 Mass Concrete Submittal_TT_POP.pdf
03 30 00-034-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-034-00 Epoxy for South Buttress Drill and Epoxy | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-14 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-11-28 | 2019-11-15 | 2 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-11-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03185 | Received | For Review | 2019-11-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-11-28 | Submittal Number: 03 30 00-034.0 From: MIKE SOLFELT Final Due Date: 12/11/19 Subject: EPOXY FOR SOUTH BUTTRESS DRILL AND EPOXY Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04615 | Forwarded | For Review | 2019-11-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-20 | Submittal Number: 03 30 00-034.0 From: MIKE SOLFELT Final Due Date: 12/11/19 Subject: EPOXY FOR SOUTH BUTTRESS DRILL AND EPOXY Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03223 | Review Response | Approved | 2019-11-15 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 04661 | Responded and Closed | Approved | 2019-11-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved) from: Samar Kenkre (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-13 |  | 033000-0034-0 Epoxy for South Buttress D&E.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-13 |  | 033000-0034-0 Epoxy for South Buttress D&E.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-11-12 02:00 |  | 033000-0034-0 Epoxy for South Buttress D&E.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-15 02:00 |  | 033000-0034-0 Epoxy for South Buttress D&E_TT_POP.pdf
03 30 00-035-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-035-00 Concrete Waterstop | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-19 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Chris Minter (Populous) |  |  |  | 2019-12-05 08:00 | 2019-12-03 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03258 | Received | For Review | 2019-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-12-05 08:00 | Submittal Number: 03 30 00-035.0 From: MIKE SOLFELT Final Due Date: 12/03/19 Subject: CONCRETE WATERSTOP Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04700 | Forwarded | For Review | 2019-11-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-26 | Submittal Number: 03 30 00-035.0 From: MIKE SOLFELT Final Due Date: 12/03/19 Subject: CONCRETE WATERSTOP Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03443 | Review Response | Approved | 2019-12-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT takes no exception to waterstop joint. Arch to review waterstop for approval as well. | Info Exchange
| 04920 | Forwarded | For Review | 2019-12-03 | Josh Dobken (Populous) | Todd Spangler (Populous); Chris Minter (Populous) | 2019-12-05 | Submittal Number: 03 30 00-035.0 From: MIKE SOLFELT Final Due Date: 12/03/19 Subject: CONCRETE WATERSTOP Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04921 | Responded and Closed | Approved | 2019-12-03 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | TT takes no exception to waterstop joint. Arch to review waterstop for approval as well. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-19 |  | 033000-0035-0 Concrete Waterstop.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-19 |  | 033000-0035-0 Concrete Waterstop.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-19 |  | 033000-0035-0 Concrete Waterstop.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-18 02:00 |  | 033000-0035-0 Concrete Waterstop.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-12-03 |  | 033000-0035-0 Concrete Waterstop_TT_POP.pdf
03 30 00-036-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-036-00 Macro Fiber SOG Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-05 08:00 | 2019-12-03 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03259 | Received | For Review | 2019-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-12-05 08:00 | Submittal Number: 03 30 00-036.0 From: MIKE SOLFELT Final Due Date: 12/03/19 Subject: MACRO FIBER SOG MIX DESIGN Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04701 | Forwarded | For Review | 2019-11-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-26 | Submittal Number: 03 30 00-036.0 From: MIKE SOLFELT Final Due Date: 12/03/19 Subject: MACRO FIBER SOG MIX DESIGN Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03446 | Review Response | Approved as Noted | 2019-12-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please verify Average Residual Stress per spec 033000 per comment. No other exceptions noted and this submittal has been retained for record. | Info Exchange
| 04918 | Responded and Closed | Approved as Noted | 2019-12-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Please verify Average Residual Stress per spec 033000 per comment. No other exceptions noted and this submittal has been retained for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-19 |  | 033000-0036-0 Macro Fiber Mix Design.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-19 |  | 033000-0036-0 Macro Fiber Mix Design.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-18 02:00 |  | 033000-0036-0 Macro Fiber Mix Design.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-03 02:00 |  | 033000-0036-0 Macro Fiber Mix Design_TT REVIEW_POP.pdf
03 30 00-037-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-037-00 Cold Weather Concrete Plan | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-20 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-06 08:00 | 2019-12-03 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03290 | Received | For Review | 2019-11-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-12-06 08:00 | Submittal Number: 03 30 00-037.0 From: MIKE SOLFELT Final Due Date: 12/04/19 Subject: COLD WEATHER CONCRETE PLAN Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04739 | Forwarded | For Review | 2019-11-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-27 | Submittal Number: 03 30 00-037.0 From: MIKE SOLFELT Final Due Date: 12/04/19 Subject: COLD WEATHER CONCRETE PLAN Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03447 | Review Response | No Action Taken or Required | 2019-12-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Retained for Record only. | Info Exchange
| 04919 | Responded and Closed | No Action Taken or Required | 2019-12-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: Retained for Record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-20 |  | 033000-0037-0 Cold Weather Concrete Plan.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-20 |  | 033000-0037-0 Cold Weather Concrete Plan.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-19 02:00 |  | 033000-0037-0 Cold Weather Concrete Plan.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-19 02:00 |  | 033000-0037-0 Cold Weather Concrete Plan.pdf
03 30 00-038-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-038-00 Y-Column / Chevron Extension Pour Breaks | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-04 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-18 | 2019-12-23 | 20 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2019-12-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03459 | Received | For Review | 2019-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-12-18 | Submittal Number: 03 30 00-038.0 From: MIKE SOLFELT Final Due Date: 12/17/19 Subject: Y-COLUMN / CHEVRON EXTENSION POUR BREAKS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04933 | Forwarded | For Review | 2019-12-03 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-10 | Submittal Number: 03 30 00-038.0 From: MIKE SOLFELT Final Due Date: 12/17/19 Subject: Y-COLUMN / CHEVRON EXTENSION POUR BREAKS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03733 | Review Response | Approved as Noted | 2019-12-20 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Ongoing coordination to accommodate existing conditions at the Extension to Existing-Structure Interface may result in revised concrete cross-sections and locations. Resubmit any revisions to EOR for review and approval. See additional comments in attached submittal. POPULOUS to review construction joints for architectural acceptability. TT-FK | Info Exchange
| 05269 | Responded and Closed | Approved as Noted | 2019-12-23 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | APPROVED AS NOTED. SEE TT'S COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-03 |  | 033000-0038-0 Y-Column & Chevro Extension Pour Breaks.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-03 |  | 033000-0038-0 Y-Column & Chevro Extension Pour Breaks.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-12-02 02:00 |  | 033000-0038-0 Y-Column & Chevro Extension Pour Breaks.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2019-12-20 02:00 |  | 033000-0038-0 Y-Column & Chevro Extension Pour Breaks_TTReview.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2019-12-23 02:00 |  | 033000-0038-0 Y-Column & Chevro Extension Pour Breaks_TTReview-POP.pdf
03 30 00-039-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-039-00 Shotcrete Strip Footing Control joints | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-03 | 2020-01-03 | 24 | General | Record Copies; Transfers; Submittals |  | 24 |  | 2020-01-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03590 | Received | For Review | 2019-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2020-01-03 | Submittal Number: 03 30 00-039.0 From: MIKE SOLFELT Final Due Date: 12/24/19 Subject: SHOTCRETE STRIP FOOTING CONTROL JOINTS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 05071 | Forwarded | For Review | 2019-12-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-18 | Submittal Number: 03 30 00-039.0 From: MIKE SOLFELT Final Due Date: 12/24/19 Subject: SHOTCRETE STRIP FOOTING CONTROL JOINTS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03780 | Review Response | Approved as Noted | 2020-01-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05318 | Responded and Closed | Approved as Noted | 2020-01-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-10 |  | 033000-0039-0 Strip Footing Control Joints.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-10 |  | 033000-0039-0 Strip Footing Control Joints.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-09 02:00 |  | 033000-0039-0 Strip Footing Control Joints.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-03 02:00 |  | 033000-0039-0 Strip Footing Control Joints_TT REVIEW_POP.pdf
03 30 00-040-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-040-00 Shotcrete Construction Joint Locations | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2020-01-03 | 2020-01-07 | 28 | General | Record Copies; Transfers; Submittals |  | 24 |  | 2020-01-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03591 | Received | For Review | 2019-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2020-01-03 | Submittal Number: 03 30 00-040.0 From: MIKE SOLFELT Final Due Date: 12/24/19 Subject: SHOTCRETE CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 05072 | Forwarded | For Review | 2019-12-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-18 | Submittal Number: 03 30 00-040.0 From: MIKE SOLFELT Final Due Date: 12/24/19 Subject: SHOTCRETE CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03781 | Review Response | Approved as Noted | 2020-01-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05319 | Forwarded | For Review | 2020-01-03 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2020-01-03 | Submittal Number: 03 30 00-040.0 From: MIKE SOLFELT Final Due Date: 12/24/19 Subject: SHOTCRETE CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 05355 | Responded and Closed | Approved as Noted | 2020-01-07 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-10 |  | 033000-0040-0 Shotcrete Construction Joints.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-10 |  | 033000-0040-0 Shotcrete Construction Joints.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-09 02:00 |  | 033000-0040-0 Shotcrete Construction Joints.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 033000-0040-0 Shotcrete Construction Joints.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-07 |  | 033000-0040-0 Shotcrete Construction Joints_TT_POP.pdf
03 30 00-041-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-041-00 Epoxy at Drill and Epoxy Application - Permanent Structure | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-02 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-16 | 2020-01-08 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03748 | Received | For Review | 2020-01-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2020-01-16 | Submittal Number: 03 30 00-041.0 From: MIKE SOLFELT Final Due Date: 01/13/20 Subject: EPOXY AT DRILL AND EPOXY APPLICATION - PERMANENT STRUCTURE Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 05282 | Forwarded | For Review | 2020-01-02 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-09 | Submittal Number: 03 30 00-041.0 From: MIKE SOLFELT Final Due Date: 01/13/20 Subject: EPOXY AT DRILL AND EPOXY APPLICATION - PERMANENT STRUCTURE Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 03846 | Review Response | Approved | 2020-01-07 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. Note that general notes specify HILTI HIT-HY 200 adhesive with HILTI HAS or HIT-Z threaded rods at all post-installed applications unless noted otherwise on drawings. | Info Exchange
| 05393 | Responded and Closed | Approved | 2020-01-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. Note that general notes specify HILTI HIT-HY 200 adhesive with HILTI HAS or HIT-Z threaded rods at all post-installed applications unless noted otherwise on drawings. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-30 |  | 033000-0041-0 Epoxy at Drill.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-30 |  | 033000-0041-0 Epoxy at Drill.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-29 02:00 |  | 033000-0041-0 Epoxy at Drill.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-08 02:00 |  | 033000-0041-0 Epoxy at Drill_TT REVIEW_POP.pdf
03 30 00-042-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-042-00 Mass Concrete at Tower Crane Foundation | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-10 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-24 | 2020-01-21 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03869 | Received | For Review | 2020-01-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2020-01-24 | Submittal Number: 03 30 00-042.0 From: MIKE SOLFELT Final Due Date: 01/24/20 Subject: MASS CONCRETE AT TOWER CRANE FOUNDATION Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 05421 | Forwarded | For Review | 2020-01-10 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-17 | Submittal Number: 03 30 00-042.0 From: MIKE SOLFELT Final Due Date: 01/24/20 Subject: MASS CONCRETE AT TOWER CRANE FOUNDATION Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 04000 | Review Response | Approved as Noted | 2020-01-21 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05582 | Responded and Closed | Approved as Noted | 2020-01-21 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-10 |  | 033000-0042-0 Mass Concrete at Tower Crane Foundation.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-10 |  | 033000-0042-0 Mass Concrete at Tower Crane Foundation.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-01-09 02:00 |  | 033000-0042-0 Mass Concrete at Tower Crane Foundation.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-21 02:00 |  | 033000-0042-0 Mass Concrete at Tower Crane Foundation_TT REVIEW_POP.pdf
03 30 00-043-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-043-00 South Buttress Shear Wall Finish Mock Up | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-21 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chris Minter (Populous) |  |  |  | 2020-02-04 | 2020-02-06 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-02-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04002 | Received | For Review | 2020-01-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers | 2020-02-04 | Submittal Number: 03 30 00-043.0 From: CHRISTIAN ALBERS Final Due Date: 01/29/20 Subject: SOUTH BUTTRESS SHEAR WALL FINISH MOCK UP Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 05584 | Forwarded | For Review | 2020-01-21 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-01-28 | Submittal Number: 03 30 00-043.0 From: CHRISTIAN ALBERS Final Due Date: 01/29/20 Subject: SOUTH BUTTRESS SHEAR WALL FINISH MOCK UP Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 05838 | Forwarded | For Review | 2020-02-05 | Josh Dobken (Populous) | Chris Minter (Populous) | 2020-02-04 | Submittal Number: 03 30 00-043.0 From: CHRISTIAN ALBERS Final Due Date: 01/29/20 Subject: SOUTH BUTTRESS SHEAR WALL FINISH MOCK UP Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Email
| 05870 | Responded and Closed | Approved as Noted | 2020-02-06 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-21 |  | 03 30 00 - 043 South Buttress Shear Wall Finish Mock Up Final.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-21 |  | 03 30 00 - 043 South Buttress Shear Wall Finish Mock Up Final.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-20 02:00 |  | 03 30 00 - 043 South Buttress Shear Wall Finish Mock Up Final.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-06 |  | 03 30 00 - 043 South Buttress Shear Wall Finish Mock Up Final_POP.pdf
03 30 00-044-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-044-00 Sika 328 Grout | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-30 | 2020-04-02 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-04-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04856 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 03 30 00-044.0 From: MIKE SOLFELT Final Due Date: 03/30/20 Subject: SIKA 328 GROUT Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 06633 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-23 | Submittal Number: 03 30 00-044.0 From: MIKE SOLFELT Final Due Date: 03/30/20 Subject: SIKA 328 GROUT Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 06997 | Forwarded | For Review | 2020-04-01 | Josh Dobken (Populous) | Matt Ross (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti) | 2020-03-30 | Submittal Number: 03 30 00-044.0 From: MIKE SOLFELT Final Due Date: 03/30/20 Subject: SIKA 328 GROUT Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 05185 | Review Response | Rejected | 2020-04-02 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Contractor shall submit clearly marked locations where this product is to be used per spec 033000 1.6.B.5. | Info Exchange
| 07039 | Responded and Closed | Rejected | 2020-04-02 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Response (Rejected) from: Matt Ross (Thornton Tomasetti) Remarks: Contractor shall submit clearly marked locations where this product is to be used per spec 033000 1.6.B.5. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 033000-0044-0 Sika 328 Grout.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 033000-0044-0 Sika 328 Grout.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-15 02:00 |  | 033000-0044-0 Sika 328 Grout.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-15 02:00 |  | 033000-0044-0 Sika 328 Grout.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-02 02:00 |  | 033000-0044-0 Sika 328 Grout_TT Reviewed_POP.pdf
03 30 00-044-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-044-01 Sika 328 Grout | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-04 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-18 | 2020-06-10 | 7 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-06-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06174 | Received | For Review | 2020-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-18 | Submittal Number: 03 30 00-044.1 From: MIKE SOLFELT Final Due Date: 06/17/20 Subject: SIKA 328 GROUT Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08348 | Forwarded | For Review | 2020-06-03 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-10 | Submittal Number: 03 30 00-044.1 From: MIKE SOLFELT Final Due Date: 06/17/20 Subject: SIKA 328 GROUT Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 06329 | Review Response | Approved as Noted | 2020-06-10 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Exceptions Noted. No need to resubmit. | Info Exchange
| 08537 | Responded and Closed | Approved as Noted | 2020-06-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-03 |  | 033000-0044-01 Sika328 Grout for Base Plates.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-03 |  | 033000-0044-01 Sika328 Grout for Base Plates.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-03 |  | 033000-0044-01 Sika328 Grout for Base Plates.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-10 |  | 033000-0044-01 Sika328 Grout for Base Plates_TT_POP.pdf
03 30 00-045-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-045-00 SSMH Concrete Base | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-13 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-04-27 | 2020-04-28 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05292 | Received | For Review | 2020-04-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-04-27 | Submittal Number: 03 30 00-045.0 From: JUAN BOLANOS Final Due Date: 04/20/20 Subject: SSMH CONCRETE BASE Description: THE PLAN IS TO USE THESE MATERIALS FOR THE CONSTRUCTION OF THE SSMHS BASE THAT WILL BE LOCATED ON 1ST AVE. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 07200 | Forwarded | For Review | 2020-04-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-20 | Submittal Number: 03 30 00-045.0 From: JUAN BOLANOS Final Due Date: 04/20/20 Subject: SSMH CONCRETE BASE Description: THE PLAN IS TO USE THESE MATERIALS FOR THE CONSTRUCTION OF THE SSMHS BASE THAT WILL BE LOCATED ON 1ST AVE. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 07319 | Forwarded | For Review | 2020-04-16 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-04-23 | Submittal Number: 03 30 00-045.0 From: JUAN BOLANOS Final Due Date: 04/20/20 Subject: SSMH CONCRETE BASE Description: THE PLAN IS TO USE THESE MATERIALS FOR THE CONSTRUCTION OF THE SSMHS BASE THAT WILL BE LOCATED ON 1ST AVE. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 05612 | Review Response | Approved as Noted | 2020-04-28 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached review. - J. Grant, DCI Engineers | Info Exchange
| 07605 | Responded and Closed | Approved as Noted | 2020-04-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached review. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-11 |  | 03 30 00-045 SSMH Concrete Base.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-11 |  | 03 30 00-045 SSMH Concrete Base.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-11 |  | 03 30 00-045 SSMH Concrete Base.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-04-10 02:00 |  | 03 30 00-045 SSMH Concrete Base.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-28 02:00 |  | 03 30 00-045 SSMH Concrete Base_DCI_POP.pdf
03 30 00-046-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-046-00 Diamond Dowels at SOG Construction Joints | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-08 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-22 | 2020-05-26 | 19 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05769 | Received | For Review | 2020-05-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-05-22 | Submittal Number: 03 30 00-046.0 From: MIKE SOLFELT Final Due Date: 05/21/20 Subject: DIAMOND DOWELS AT SOG CONSTRUCTION JOINTS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 07826 | Forwarded | For Review | 2020-05-07 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-14 | Submittal Number: 03 30 00-046.0 From: MIKE SOLFELT Final Due Date: 05/21/20 Subject: DIAMOND DOWELS AT SOG CONSTRUCTION JOINTS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 06046 | Review Response | Approved | 2020-05-26 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08190 | Responded and Closed | Approved | 2020-05-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | see attached for approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-07 |  | 033000-0045 Diamond Dowels at SOG Construction Joints.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-07 |  | 033000-0045 Diamond Dowels at SOG Construction Joints.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-07 |  | 033000-0045 Diamond Dowels at SOG Construction Joints.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-26 |  | 033000-0045 Diamond Dowels at SOG Construction Joints_TT_POP.pdf
03 30 00-047-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-047-00 SOMD Control Joints Area D and A | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-26 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2020-06-09 | 2020-05-29 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-05-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06017 | Received | For Review | 2020-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-06-09 | Submittal Number: 03 30 00-047.0 From: MIKE SOLFELT Final Due Date: 06/09/20 Subject: SOMD CONTROL JOINTS AREA D AND A Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08160 | Forwarded | For Review | 2020-05-26 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-02 | Submittal Number: 03 30 00-047.0 From: MIKE SOLFELT Final Due Date: 06/09/20 Subject: SOMD CONTROL JOINTS AREA D AND A Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08180 | Forwarded | For Review | 2020-05-26 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2020-06-02 | Submittal Number: 03 30 00-047.0 From: MIKE SOLFELT Final Due Date: 06/09/20 Subject: SOMD CONTROL JOINTS AREA D AND A Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08265 | Responded and Closed | Rejected | 2020-05-29 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | PER EMAIL DISCUSSION WITH MIKE SOLFELT, REJECTING SUBMITTAL. MORTENSON TO RESUBMIT CORRECT INFORMATION FOR THIS ITEM. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-26 |  | 033000-0047 SOMD Control Joints.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-26 |  | 033000-0047 SOMD Control Joints.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-25 02:00 |  | 033000-0047 SOMD Control Joints.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-29 02:00 |  | 033000-0047 SOMD Control Joints-POP.pdf
03 30 00-047-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-047-01 SOMD Control Joints Area D and A | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-04 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-18 | 2020-06-12 | 9 |  | Record Copies; Transfers; Submittals | 03 30 00-047-02 - 03 30 00-047-01 SOMD Control Joints Area D and A | 7 |  | 2020-06-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06175 | Received | For Review | 2020-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-06-18 | Submittal Number: 03 30 00-047.1 From: MIKE SOLFELT Final Due Date: 06/10/20 Subject: SOMD CONTROL JOINTS AREA D AND A Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08349 | Forwarded | For Review | 2020-06-03 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-10 | Submittal Number: 03 30 00-047.1 From: MIKE SOLFELT Final Due Date: 06/10/20 Subject: SOMD CONTROL JOINTS AREA D AND A Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 06338 | Review Response | Revise and Resubmit | 2020-06-09 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08601 | Responded and Closed | Revise and Resubmit | 2020-06-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Refer to notes from Populous and TT within for corrections required. Several portions of 200 Level in Quad A missing from submittal. Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-03 |  | 033000-0047.01 S0MD Control Joints.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-03 |  | 033000-0047.01 S0MD Control Joints.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-03 |  | 033000-0047.01 S0MD Control Joints.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-12 02:00 |  | 033000-0047.01 S0MD Control Joints_TT_POP.pdf
03 30 00-047-02 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-047-01 SOMD Control Joints Area D and A | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 30 00-047-01 - 03 30 00-047-01 SOMD Control Joints Area D and A | -1 | 2020-06-26
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-12 02:00 |  | 033000-0047.01 S0MD Control Joints_TT_POP.pdf
03 30 00-048-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-048-00 Procore Observation 868 Y Column 15 Lift 4 Void Corrective Action Plan | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-24 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-09 07:00 | 2020-07-01 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-07-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06575 | Received | For Review | 2020-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-07-09 07:00 | Submittal Number: 03 30 00-048.0 From: MIKE SOLFELT Final Due Date: 06/30/20 Subject: PROCORE OBSERVATION 868 Y COLUMN 15 LIFT 4 VOID CORRECTIVE ACTION PLAN Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08853 | Forwarded | For Review | 2020-06-23 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-30 | Submittal Number: 03 30 00-048.0 From: MIKE SOLFELT Final Due Date: 06/30/20 Subject: PROCORE OBSERVATION 868 Y COLUMN 15 LIFT 4 VOID CORRECTIVE ACTION PLAN Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 06723 | Review Response | Approved as Noted | 2020-06-29 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Exceptions Noted | Info Exchange
| 09046 | Responded and Closed | Approved as Noted | 2020-07-01 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-23 |  | 033000-0048 Y15 Injection Grouting.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-23 |  | 033000-0048 Y15 Injection Grouting.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-06-23 |  | 033000-0048 Y15 Injection Grouting.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-06-29 |  | 033000-0048 Y15 Injection Grouting_TT Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-07-01 |  | 033000-0048 Y15 Injection Grouting_TT Review-POP.pdf
03 30 00-049-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-049-00 SOG Sawcut & Construction Joint Locations | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-09 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-23 | 2020-06-25 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06303 | Received | For Review | 2020-06-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-23 | Submittal Number: 03 30 00-049.0 From: DEVON WALTERS Final Due Date: 06/23/20 Subject: SOG SAWCUT & CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08502 | Forwarded | For Review | 2020-06-09 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-16 | Submittal Number: 03 30 00-049.0 From: DEVON WALTERS Final Due Date: 06/23/20 Subject: SOG SAWCUT & CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 06590 | Review Response | Approved as Noted | 2020-06-24 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 08919 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-25 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | PARTS OF AREA E & F ARE MISSING. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-09 |  | 033000-0049 SOG Sawcut & Construction Joint Locations.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-09 |  | 033000-0049 SOG Sawcut & Construction Joint Locations.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-08 02:00 |  | 033000-0049 SOG Sawcut & Construction Joint Locations.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-25 |  | 033000-0049 SOG Sawcut & Construction Joint Locations_TT_POP.pdf
03 30 00-049-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-049-01 SOG Sawcut & Construction Joint Locations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-29 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-14 07:00 | 2020-07-02 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06650 | Received | For Review | 2020-06-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-07-14 07:00 | Submittal Number: 03 30 00-049.1 From: DEVON WALTERS Final Due Date: 07/13/20 Subject: SOG SAWCUT & CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08956 | Forwarded | For Review | 2020-06-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-06 | Submittal Number: 03 30 00-049.1 From: DEVON WALTERS Final Due Date: 07/13/20 Subject: SOG SAWCUT & CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09089 | Responded and Closed | Revise and Resubmit | 2020-07-02 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | TRS Blockouts have already been provided in the Rev 2 version of this submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-29 |  | 033000-0049.1 SOG Sawcut & Construction Joint Locations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-29 |  | 033000-0049.1 SOG Sawcut & Construction Joint Locations.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-02 02:00 |  | 033000-0049.1 SOG Sawcut & Construction Joint Locations_POP.pdf
03 30 00-049-02 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-049-02 SOG Sawcut & Construction Joint Locations | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-30 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-15 07:00 | 2020-07-06 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06680 | Received | For Review | 2020-06-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-07-15 07:00 | Submittal Number: 03 30 00-049.2 From: DEVON WALTERS Final Due Date: 07/13/20 Subject: SOG SAWCUT & CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08996 | Forwarded | For Review | 2020-06-30 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-07 | Submittal Number: 03 30 00-049.2 From: DEVON WALTERS Final Due Date: 07/13/20 Subject: SOG SAWCUT & CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 06800 | Review Response | Approved as Noted | 2020-07-06 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09136 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: APPROVAL AS NOTED IS ONLY FOR AREA HIGHLIGHTED IN MAGENTA. CONTRACTOR TO INCORPORATE COMMENTS PER PREVIOUS SUBMITTAL AS INDICATED BY TT. CLOUD REVISIONS IN FUTURE SUBMITTALS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-30 |  | 033000-0049.2 SOG Sawcut & Construction Joint Locations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-30 |  | 033000-0049.2 SOG Sawcut & Construction Joint Locations.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-29 02:00 |  | 033000-0049.2 SOG Sawcut & Construction Joint Locations.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-06 02:00 |  | 033000-0049.2 SOG Sawcut Construction Joint Locations_TT_POP-PARTIAL REVIEW.pdf
03 30 00-049-03 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-049-03 SOG Sawcut & Construction Joint Locations | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-08 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-22 | 2020-07-27 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-07-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06858 | Received | For Review | 2020-07-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-07-22 | Submittal Number: 03 30 00-049.3 From: MIKE SOLFELT Final Due Date: 07/22/20 Subject: SOG SAWCUT & CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09205 | Forwarded | For Review | 2020-07-08 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-15 | Submittal Number: 03 30 00-049.3 From: MIKE SOLFELT Final Due Date: 07/22/20 Subject: SOG SAWCUT & CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 07121 | Review Response | Approved as Noted | 2020-07-14 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | No clouds have been found on any of the 3 revisions. TT has only reviewed parts of this submittal that were noted to be changed since the initial review. No other changes have been reviewed as noted. | Info Exchange
| 07169 | Review Response | Approved as Noted/Resubmit | 2020-07-27 | Josh Dobken (Populous) | Josh Dobken (Populous) |  | See attached for revised sawcuts. Resubmit highlighted area in southwest corner of building with revised sawcut locations as incidated. | Info Exchange
| 09567 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-27 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: No clouds have been found on any of the 3 revisions. TT has only reviewed parts of this submittal that were noted to be changed since the initial review. No other changes have been reviewed as noted. Response (Approved as Noted/Resubmit) from: Josh Dobken (Populous) Remarks: See attached. Resubmit highlighted area in southwest corner of building with revised sawcut locations as indicated. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-08 |  | 033000-0049.3 SOG Sawcut & Construction Joint Locations v2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-08 |  | 033000-0049.3 SOG Sawcut & Construction Joint Locations v2.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-08 |  | 033000-0049.3 SOG Sawcut & Construction Joint Locations v2.pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2020-07-27 02:00 |  | 033000-0049.3 SOG Sawcut & Construction Joint Locations v2_TT_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-07 02:00 |  | 033000-0049.3 SOG Sawcut & Construction Joint Locations v2.pdf
03 30 00-049-04 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-049-04 SOG Sawcut & Construction Joint Locations | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-03 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-17 | 2020-08-20 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07319 | Received | For Review | 2020-08-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-08-17 | Submittal Number: 03 30 00-049.4 From: MIKE SOLFELT Final Due Date: 08/17/20 Subject: SOG SAWCUT & CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09758 | Forwarded | For Review | 2020-08-03 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-10 | Submittal Number: 03 30 00-049.4 From: MIKE SOLFELT Final Due Date: 08/17/20 Subject: SOG SAWCUT & CONSTRUCTION JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 07639 | Review Response | Approved as Noted | 2020-08-20 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 10178 | Responded and Closed | Approved as Noted | 2020-08-20 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-03 |  | 033000-0049.4 SOG Sawcut & Construction Joint Locations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-03 |  | 033000-0049.4 SOG Sawcut & Construction Joint Locations.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-03 |  | 033000-0049.4 SOG Sawcut & Construction Joint Locations.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-20 |  | 033000-0049.3 SOG Sawcut & Construction Joint Locations v2_TT_POP.pdf
03 30 00-050-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-050-00 Concrete Finish Mock-Up Review - 6.08.20 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-11 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-25 | 2020-06-25 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06330 | Received | For Review | 2020-06-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-25 | Submittal Number: 03 30 00-050.0 From: GREG GOEBEL Final Due Date: 06/24/20 Subject: CONCRETE FINISH MOCK-UP REVIEW - 6.08.20 Description: SEE ATTACHED NOTES AND PHOTOS FROM THE 6.08.20 CONCRETE FINISH MOCK-UP REVIEW. ALSO, INCLUDED ARE SOME MORE UP CLOSE PHOTOS FROM THE 6.01.20 REVIEW. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08539 | Forwarded | For Review | 2020-06-11 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-18 | Submittal Number: 03 30 00-050.0 From: GREG GOEBEL Final Due Date: 06/24/20 Subject: CONCRETE FINISH MOCK-UP REVIEW - 6.08.20 Description: SEE ATTACHED NOTES AND PHOTOS FROM THE 6.08.20 CONCRETE FINISH MOCK-UP REVIEW. ALSO, INCLUDED ARE SOME MORE UP CLOSE PHOTOS FROM THE 6.01.20 REVIEW. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08553 | Forwarded | For Review | 2020-06-11 | Populous SCA_CCA | Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-18 | Submittal Number: 03 30 00-050.0 From: GREG GOEBEL Final Due Date: 06/24/20 Subject: CONCRETE FINISH MOCK-UP REVIEW - 6.08.20 Description: SEE ATTACHED NOTES AND PHOTOS FROM THE 6.08.20 CONCRETE FINISH MOCK-UP REVIEW. ALSO, INCLUDED ARE SOME MORE UP CLOSE PHOTOS FROM THE 6.01.20 REVIEW. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08922 | Responded and Closed | Not Required For Review | 2020-06-25 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction); Greg Goebel (M.A. Mortenson Company) |  | Meeting notes not required for review. Mockup is approved as noted. Drawings attached were not reviewed, Mortenson to submit floor finishes per level in a separate submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-11 |  | 03 30 00-050.0 SCA Concrete Finish Mock-Up Review 6.08.20.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-11 |  | 03 30 00-050.0 SCA Concrete Finish Mock-Up Review 6.08.20.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-10 02:00 |  | 03 30 00-050.0 SCA Concrete Finish Mock-Up Review 6.08.20.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-25 02:00 |  | 03 30 00-050.0 SCA Concrete Finish Mock-Up Review 6.08.20_POP.pdf
03 30 00-051-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-051-00 Air Entrained 4k Mix | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-29 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-14 07:00 | 2020-07-01 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-07-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06656 | Received | For Review | 2020-06-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-07-14 07:00 | Submittal Number: 03 30 00-051.0 From: MIKE SOLFELT Final Due Date: 07/09/20 Subject: AIR ENTRAINED 4K MIX Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08967 | Forwarded | For Review | 2020-06-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-06 | Submittal Number: 03 30 00-051.0 From: MIKE SOLFELT Final Due Date: 07/09/20 Subject: AIR ENTRAINED 4K MIX Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 06724 | Review Response | Approved | 2020-07-01 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Provide 6ksi concrete mix design for concrete used at parking garage decks. Refer to TT comments on page 44/173 of 03 3000 003.3 and RFI 2701. SDK ¦ TT ¦ 7/1/2020 | Info Exchange
| 09047 | Responded and Closed | Approved as Noted | 2020-07-01 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-25 |  | 033000-0050 Air Entrained 4k Mix.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-25 |  | 033000-0051 Air Entrained 4k Mix.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-06-25 |  | 033000-0051 Air Entrained 4k Mix.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-07-01 |  | 033000-0051 Air Entrained 4k Mix_TT REVIEW.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-07-01 |  | 033000-0051 Air Entrained 4k Mix_TT REVIEW-POP.pdf
03 30 00-052-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-052-00 SE and SW Detention Tank Hollow Core Plank Submittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-20 | 2020-07-17 | 12 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-07-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06781 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 03 30 00-052.0 From: MIKE SOLFELT Final Due Date: 07/20/20 Subject: SE AND SW DETENTION TANK HOLLOW CORE PLANK SUBMITTAL Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09116 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-13 | Submittal Number: 03 30 00-052.0 From: MIKE SOLFELT Final Due Date: 07/20/20 Subject: SE AND SW DETENTION TANK HOLLOW CORE PLANK SUBMITTAL Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 07009 | Review Response | Approved as Noted | 2020-07-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Exceptions noted within. Do not need to resubmit. Populous to verify 1 angle as noted. | Info Exchange
| 09386 | Responded and Closed | Approved as Noted | 2020-07-17 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | SEE ATTACHED FOR REVIEW AND RESPONSE. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 033000-0052 SE and SW SNorkel Detention Tank Hollow Core Plank.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 033000-0052 SE and SW SNorkel Detention Tank Hollow Core Plank.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-06 |  | 033000-0052 SE and SW SNorkel Detention Tank Hollow Core Plank.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-17 |  | 033000-0052 SE and SW SNorkel Detention Tank Hollow Core Plank_TT_POP.pdf
03 30 00-053-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-053-00 South Buttress Mat Footing Temperature Differentials | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-13 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-27 | 2020-07-15 | 3 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06920 | Received | For Review | 2020-07-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-07-27 | Submittal Number: 03 30 00-053.0 From: MIKE SOLFELT Final Due Date: 07/27/20 Subject: SOUTH BUTTRESS MAT FOOTING TEMPERATURE DIFFERENTIALS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09262 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-20 | Submittal Number: 03 30 00-053.0 From: MIKE SOLFELT Final Due Date: 07/27/20 Subject: SOUTH BUTTRESS MAT FOOTING TEMPERATURE DIFFERENTIALS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 06986 | Review Response | No Action Taken or Required | 2020-07-13 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Received for record. | Info Exchange
| 09361 | Responded and Closed | No Action Taken or Required | 2020-07-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 033000-0053 Observation 921 Mass Concrete Differential Letter.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 033000-0053 Observation 921 Mass Concrete Differential Letter.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-07-13 |  | 033000-0053 Observation 921 Mass Concrete Differential Letter.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-15 |  | 033000-0053 Observation 921 Mass Concrete Differential Letter_TT_POP.pdf
03 30 00-054-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-054-00 6000psi Air Entrained Concrete Mix | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-15 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-29 | 2020-07-16 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-07-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06976 | Received | For Review | 2020-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-07-29 | Submittal Number: 03 30 00-054.0 From: MIKE SOLFELT Final Due Date: 07/29/20 Subject: 6000PSI AIR ENTRAINED CONCRETE MIX Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09342 | Forwarded | For Review | 2020-07-15 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-22 | Submittal Number: 03 30 00-054.0 From: MIKE SOLFELT Final Due Date: 07/29/20 Subject: 6000PSI AIR ENTRAINED CONCRETE MIX Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 06994 | Review Response | Approved | 2020-07-16 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09370 | Responded and Closed | Approved | 2020-07-16 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-15 |  | 033000-0054 6000psi Air Entrained Concrete Mix Design.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-15 |  | 033000-0054 6000psi Air Entrained Concrete Mix Design.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-07-15 |  | 033000-0054 6000psi Air Entrained Concrete Mix Design.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-16 |  | 033000-0054 6000psi Air Entrained Concrete Mix Design_TT_POP.pdf
03 30 00-055-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-055-00 Waterproofing Slab Cure Type | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-15 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Tom Usher (Populous) |  |  |  | 2020-07-29 | 2020-08-04 | 21 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06977 | Received | For Review | 2020-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-07-29 | Submittal Number: 03 30 00-055.0 From: CHRISTIAN ALBERS Final Due Date: 07/29/20 Subject: WATERPROOFING SLAB CURE TYPE Description: ALL LISTED CURE TYPES WITHIN THE 03 30 00 SPECIFICATIONS ARE NOT COMPATIBLE WITH THE APPROVED WATERPROOFING ON THE UPPER CONCOURSE SLAB. THROUGH OUR RESEARCH AND CORRESPONDENCE WITH THE MANUFACTURER, THE ATTACHED "WCE SINAK" CURE TYPE HAS BEEN DEEMED TO BE COMPATIBLE WITH THEIR PRODUCTS. PLEASE ADD THIS PRODUCT TO THE SPECS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09343 | Forwarded | For Review | 2020-07-15 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-22 | Submittal Number: 03 30 00-055.0 From: CHRISTIAN ALBERS Final Due Date: 07/29/20 Subject: WATERPROOFING SLAB CURE TYPE Description: ALL LISTED CURE TYPES WITHIN THE 03 30 00 SPECIFICATIONS ARE NOT COMPATIBLE WITH THE APPROVED WATERPROOFING ON THE UPPER CONCOURSE SLAB. THROUGH OUR RESEARCH AND CORRESPONDENCE WITH THE MANUFACTURER, THE ATTACHED "WCE SINAK" CURE TYPE HAS BEEN DEEMED TO BE COMPATIBLE WITH THEIR PRODUCTS. PLEASE ADD THIS PRODUCT TO THE SPECS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 07345 | Review Response | Approved | 2020-07-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions to Curing Compound. Populous to review waterproofing. | Info Exchange
| 09693 | Forwarded | For Review | 2020-07-30 | Todd Spangler (Populous) | Tom Usher (Populous) | 2020-07-31 | Submittal Number: 03 30 00-055.0 From: CHRISTIAN ALBERS Final Due Date: 07/29/20 Subject: WATERPROOFING SLAB CURE TYPE Description: ALL LISTED CURE TYPES WITHIN THE 03 30 00 SPECIFICATIONS ARE NOT COMPATIBLE WITH THE APPROVED WATERPROOFING ON THE UPPER CONCOURSE SLAB. THROUGH OUR RESEARCH AND CORRESPONDENCE WITH THE MANUFACTURER, THE ATTACHED "WCE SINAK" CURE TYPE HAS BEEN DEEMED TO BE COMPATIBLE WITH THEIR PRODUCTS. PLEASE ADD THIS PRODUCT TO THE SPECS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09793 | Responded and Closed | Approved as Noted | 2020-08-04 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-15 |  | 03 30 00 - 0055 Waterproofing Slab Cure Type.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-15 |  | 03 30 00 - 0055 Waterproofing Slab Cure Type.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-15 |  | 03 30 00 - 0055 Waterproofing Slab Cure Type.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-07-15 |  | 03 30 00 - 0055 Waterproofing Slab Cure Type.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-07-15 |  | 03 30 00 - 0055 Waterproofing Slab Cure Type.pdf
03 30 00-056-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-056-00 SOMD Pour Breaks Package 2 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-27 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-10 | 2020-08-17 | 22 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-08-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07146 | Received | For Review | 2020-07-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-10 | Submittal Number: 03 30 00-056.0 From: MIKE SOLFELT Final Due Date: 08/10/20 Subject: SOMD POUR BREAKS PACKAGE 2 Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09542 | Forwarded | For Review | 2020-07-27 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-03 | Submittal Number: 03 30 00-056.0 From: MIKE SOLFELT Final Due Date: 08/10/20 Subject: SOMD POUR BREAKS PACKAGE 2 Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 07483 | Review Response | Approved as Noted | 2020-08-06 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 10083 | Responded and Closed | Approved as Noted | 2020-08-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-27 |  | Submittal 033000-0056 SOMD Pour Breaks Package 2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-27 |  | Submittal 033000-0056 SOMD Pour Breaks Package 2.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-27 |  | Submittal 033000-0056 SOMD Pour Breaks Package 2.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-17 |  | Submittal 033000-0056 SOMD Pour Breaks Package 2_TT_POP.pdf
03 30 00-058-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-058-00 South Parcel - Cast In-Place Concrete Hot & Cold Weather Procedures | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-09 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-23 | 2020-10-26 | 18 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-10-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08694 | Received | For Review | 2020-10-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-23 | Submittal Number: 03 30 00-58.0 From: TYRONE THORNTON Final Due Date: 10/22/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE HOT & COLD WEATHER PROCEDURES Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11480 | Forwarded | For Review | 2020-10-09 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2020-10-16 | Submittal Number: 03 30 00-58.0 From: TYRONE THORNTON Final Due Date: 10/22/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE HOT & COLD WEATHER PROCEDURES Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08991 | Review Response | No Action Taken or Required | 2020-10-22 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no comments. Received and retained for record SDK/SEM ¦ TT ¦ 10/22/2020 | Info Exchange
| 11863 | Responded and Closed | No Action Taken or Required | 2020-10-26 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Samar Kenkre (Thornton Tomasetti) Remarks: TT has no comments. Received and retained for record SDK/SEM ¦ TT ¦ 10/22/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-08 02:00 |  | 03 30 00-58 South Parcel - CIP Concrete Hot & Cold Procedures_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-08 02:00 |  | 03 30 00-58 South Parcel - CIP Concrete Hot & Cold Procedures_MAM Review.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-10-08 02:00 |  | 03 30 00-58 South Parcel - CIP Concrete Hot & Cold Procedures_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-26 02:00 |  | 03 30 00-58 South Parcel - CIP Concrete Hot & Cold Procedures_TT For Record_pop.pdf
03 30 00-059-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-059-00 South Parcel - Cast In-Place Concrete Concrete Travel Times to Project Site | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-16 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-30 | 2020-10-30 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-10-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08822 | Received | For Review | 2020-10-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-10-30 | Submittal Number: 03 30 00-59.0 From: TYRONE THORNTON Final Due Date: 10/29/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE CONCRETE TRAVEL TIMES TO PROJECT SITE Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11656 | Forwarded | For Review | 2020-10-16 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-23 | Submittal Number: 03 30 00-59.0 From: TYRONE THORNTON Final Due Date: 10/29/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE CONCRETE TRAVEL TIMES TO PROJECT SITE Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09124 | Review Response | No Action Taken or Required | 2020-10-26 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Received and Retained for Record. SDK ¦ TT ¦ 10/26/2020 | Info Exchange
| 12037 | Responded and Closed | No Action Taken or Required | 2020-10-30 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Samar Kenkre (Thornton Tomasetti) Remarks: Received and Retained for Record. SDK ¦ TT ¦ 10/26/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-15 |  | 03 30 00 - CIP Travel Time to Project_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-15 |  | 03 30 00 - CIP Travel Time to Project_MAM Review.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-10-14 02:00 |  | 03 30 00 - CIP Travel Time to Project_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-30 02:00 |  | 03 30 00 - CIP Travel Time to Project_TT For Record_pop.pdf
03 30 00-060-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-060-00 South Parcel - Cast In-Place Concrete Concrete Joint Locations | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-04 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Chris Minter (Populous) |  |  |  | 2020-09-21 | 2020-09-18 | 15 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-09-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07966 | Received | For Review | 2020-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-21 | Submittal Number: 03 30 00-60.0 From: TYRONE THORNTON Final Due Date: 09/18/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE CONCRETE JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 10591 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-15 | Submittal Number: 03 30 00-60.0 From: TYRONE THORNTON Final Due Date: 09/18/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE CONCRETE JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 10599 | Forwarded | For Review | 2020-09-08 | Josh Dobken (Populous) | Todd Spangler (Populous); Chris Minter (Populous) | 2020-09-15 | Submittal Number: 03 30 00-60.0 From: TYRONE THORNTON Final Due Date: 09/18/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE CONCRETE JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08207 | Review Response | Revise and Resubmit | 2020-09-14 | Andy Tatkowski (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached. ART ¦ TT ¦ 9/14/2020 | Info Exchange
| 10896 | Responded and Closed | Revise and Resubmit | 2020-09-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-04 |  | 03 30 00-60 Tunnel Slab Control Joint Locations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-04 |  | 03 30 00-60 Tunnel Slab Control Joint Locations.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-03 02:00 |  | 03 30 00-60 Tunnel Slab Control Joint Locations.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-09-14 |  | 03 30 00-60 Tunnel Slab Control Joint Locations_TT.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-09-18 |  | 03 30 00-60 Tunnel Slab Control Joint Locations_TT-POP.pdf
03 30 00-060-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-060-01 South Parcel - Cast In-Place Concrete Concrete Joint Locations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-29 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-13 | 2021-05-03 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-05-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12862 | Received | For Review | 2021-04-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-05-13 | Submittal Number: 03 30 00-60.1 From: TYRONE THORNTON Final Due Date: 05/13/21 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE CONCRETE JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 16641 | Forwarded | For Review | 2021-04-29 | Tyrone Thornton (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-06 | Submittal Number: 03 30 00-60.1 From: TYRONE THORNTON Final Due Date: 05/13/21 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE CONCRETE JOINT LOCATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 12908 | Review Response | Approved | 2021-05-03 | Franz Kogler (Thornton Tomasetti) | Tyrone Thornton (Mortenson Construction) |  | Received for record. | Info Exchange
| 12905 | Review Response | No Action Taken or Required | 2021-05-03 | Franz Kogler (Thornton Tomasetti) | Tom Usher (Populous) |  | Pending response (Approved) from: Franz Kogler (Thornton Tomasetti) Remarks: Received for record. | Info Exchange
| 12906 | Review Response | No Action Taken or Required | 2021-05-03 | Franz Kogler (Thornton Tomasetti) | Tom Usher (Populous) |  | Pending response (Approved) from: Franz Kogler (Thornton Tomasetti) Remarks: Received for record. | Info Exchange
| 16691 | Responded and Closed | No Action Taken or Required | 2021-05-03 | Tyrone Thornton (Mortenson Construction) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Pending response (Approved) from: Tom Usher (Populous); Franz Kogler (Thornton Tomasetti) Remarks: Received for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-29 |  | 03 30 00-60 Rev 1 Tunnel Slab Control Joint Locations_ FPC.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-04-29 |  | 03 30 00-60 Rev 1 Tunnel Slab Control Joint Locations_ FPC.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-04-28 02:00 |  | 03 30 00-60 Rev 1 Tunnel Slab Control Joint Locations_ FPC.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-05-03 |  | 03 30 00-60 Rev 1 Tunnel Slab Control Joint Locations_ FPC_TT_POP.pdf
03 30 00-062-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-062-00 South Parcel - Cast In-Place Concrete Hazardous Material Notification | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-30 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-13 | 2020-11-18 | 20 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09126 | Received | For Review | 2020-10-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-13 | Submittal Number: 03 30 00-62.0 From: TYRONE THORNTON Final Due Date: 11/13/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE HAZARDOUS MATERIAL NOTIFICATION Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 12041 | Forwarded | For Review | 2020-10-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-06 | Submittal Number: 03 30 00-62.0 From: TYRONE THORNTON Final Due Date: 11/13/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE HAZARDOUS MATERIAL NOTIFICATION Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09532 | Review Response | No Action Taken or Required | 2020-11-04 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Received and retained for record SDK ¦ TT ¦ 11/4/2020 | Info Exchange
| 12551 | Responded and Closed | No Action Taken or Required | 2020-11-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | RECIEVED FOR RECORD | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-30 |  | 03 30 00-62 - Concrete Hazardous Material Notification_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-30 |  | 03 30 00-62 - Concrete Hazardous Material Notification_MAM Review.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-10-30 |  | 03 30 00-62 - Concrete Hazardous Material Notification_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-18 |  | 03 30 00-62 - Concrete Hazardous Material Notification_TT For Record-POP.pdf
03 30 00-063-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-063-01 South Parcel - Cast In-Place Concrete Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-22 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-05 | 2020-11-02 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-11-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08947 | Received | For Review | 2020-10-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-05 | Submittal Number: 03 30 00-63.1 From: TYRONE THORNTON Final Due Date: 11/05/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE MIX DESIGN Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11818 | Forwarded | For Review | 2020-10-22 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... |  | Submittal Number: 03 30 00-63.1 From: TYRONE THORNTON Final Due Date: 11/05/20 Subject: SOUTH PARCEL - CAST IN-PLACE CONCRETE MIX DESIGN Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09163 | Review Response | Approved | 2020-11-02 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | No Exeptions | Info Exchange
| 12089 | Responded and Closed | Approved | 2020-11-02 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 12121 | Sent | For Information Only | 2020-11-02 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company) |  | Response (Approved) from: Sean McNeill (Thornton Tomasetti) Remarks: No Exeptions Responded and Closed (Approved) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-22 |  | 03 30 00 - Decline Ramp & Tunnel SOG Mix Design_Revised 10.21.20_MAM Reviewed..pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-22 |  | 03 30 00 - Decline Ramp & Tunnel SOG Mix Design_Revised 10.21.20_MAM Reviewed..pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-10-22 |  | 03 30 00 - Decline Ramp & Tunnel SOG Mix Design_Revised 10.21.20_MAM Reviewed..pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-02 |  | 03 30 00 63.1- Decline Ramp & Tunnel SOG Mix Design_Revised 10.21.20_MAM_TT_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-10-21 02:00 |  | 03 30 00 - Decline Ramp & Tunnel SOG Mix Design_Revised 10.21.20_MAM Reviewed..pdf
03 30 00-066-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-066-00 Cast-In-Place Concrete Mix Design Aisle Steps | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-07 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-21 | 2020-10-22 | 16 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08651 | Received | For Review | 2020-10-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-10-21 | Submittal Number: 03 30 00-66.0 From: CHRISTIAN ALBERS Final Due Date: 10/21/20 Subject: CAST-IN-PLACE CONCRETE MIX DESIGN AISLE STEPS Description: PLEASE APPROVE CIP MIX DESIGN FOR AISLE STEPS ON PRECAST RAKERS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11429 | Forwarded | For Review | 2020-10-08 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2020-10-15 | Submittal Number: 03 30 00-66.0 From: CHRISTIAN ALBERS Final Due Date: 10/21/20 Subject: CAST-IN-PLACE CONCRETE MIX DESIGN AISLE STEPS Description: PLEASE APPROVE CIP MIX DESIGN FOR AISLE STEPS ON PRECAST RAKERS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08921 | Review Response | Revise and Resubmit | 2020-10-20 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Provide attachments as indicated. | Info Exchange
| 11788 | Responded and Closed | Revise and Resubmit | 2020-10-22 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Provide attachments as indicated. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-07 02:00 |  | 03 30 00 - 066 - Aisle Step Mix Design.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-07 02:00 |  | 03 30 00 - 066 - Aisle Step Mix Design.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-07 |  | 03 30 00 - 066 - Aisle Step Mix Design.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-22 |  | 03 30 00 - 066 - Aisle Step Mix Design_TT_POP.pdf
03 30 00-066-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-066-01 Cast-In-Place Concrete Mix Design Aisle Steps | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-03 08:00 | 2020-11-20 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09483 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 03 30 00-66.1 From: CHRISTIAN ALBERS Final Due Date: 11/30/20 Subject: CAST-IN-PLACE CONCRETE MIX DESIGN AISLE STEPS TEPS ON PRECAST RAKERS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN Description: PLEASE APPROVE CIP MIX DESIGN FOR AISLE S | Info Exchange
| 12501 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-24 | Submittal Number: 03 30 00-66.1 From: CHRISTIAN ALBERS Final Due Date: 11/30/20 Subject: CAST-IN-PLACE CONCRETE MIX DESIGN AISLE STEPS TEPS ON PRECAST RAKERS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN Description: PLEASE APPROVE CIP MIX DESIGN FOR AISLE S | Info Exchange
| 09650 | Review Response | Approved | 2020-11-20 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 12700 | Responded and Closed | Approved | 2020-11-20 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (M.A. Mortenson Company) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 03 30 00 - 066 - 01 - Aisle Step Mix Design REV 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 03 30 00 - 066 - 01 - Aisle Step Mix Design REV 1.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-15 02:00 |  | 03 30 00 - 066 - 01 - Aisle Step Mix Design REV 1.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-20 02:00 |  | 03 30 00 - 066 - 01 - Aisle Step Mix Design REV 1_TT REVIEW_pop.pdf
03 30 00-067-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-067-00 Aisle Step Mock Up | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-16 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Tom Usher (Populous), Chris Minter (Populous), Aaron Brown (Populous) |  |  |  | 2020-10-30 | 2020-11-03 | 19 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-11-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08818 | Received | For Review | 2020-10-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jesse Erickson (M.A. Mortenson Company) | 2020-10-30 | Submittal Number: 03 30 00-67.0 From: JESSE ERICKSON Final Due Date: 10/29/20 Subject: AISLE STEP MOCK UP Description: PLEASE REVIEW AND APPROVE ATTACHED AISLE STEP MOCK UP SUBMITTAL. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11651 | Forwarded | For Review | 2020-10-15 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-22 | Submittal Number: 03 30 00-67.0 From: JESSE ERICKSON Final Due Date: 10/29/20 Subject: AISLE STEP MOCK UP Description: PLEASE REVIEW AND APPROVE ATTACHED AISLE STEP MOCK UP SUBMITTAL. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11817 | Forwarded | For Review | 2020-10-22 | Josh Dobken (Populous) | Tom Usher (Populous); Chris Minter (Populous); Aaron Brown (Populous) | 2020-10-29 | Submittal Number: 03 30 00-67.0 From: JESSE ERICKSON Final Due Date: 10/29/20 Subject: AISLE STEP MOCK UP Description: PLEASE REVIEW AND APPROVE ATTACHED AISLE STEP MOCK UP SUBMITTAL. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 12131 | Responded and Closed | Approved as Noted | 2020-11-03 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-15 |  | 033000-0067 Aisle Step Mock Up Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-15 |  | 033000-0067 Aisle Step Mock Up Submittal.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-14 02:00 |  | 033000-0067 Aisle Step Mock Up Submittal.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-03 |  | 033000-0067 Aisle Step Mock Up Submittal POP -CLM.pdf
03 30 00-068-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-068-00 Dry Shake Hardener | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-20 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-03 | 2020-10-22 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-10-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08887 | Received | For Review | 2020-10-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-11-03 | Submittal Number: 03 30 00-68.0 From: CHRISTIAN ALBERS Final Due Date: 11/03/20 Subject: DRY SHAKE HARDENER Description: SEE ATTACHED PRODUCT DATA FOR EUCLID DIAMOND PLATE DRY SHAKE HARDENER TO BE USED ON SLABS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11743 | Forwarded | For Review | 2020-10-20 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-27 | Submittal Number: 03 30 00-68.0 From: CHRISTIAN ALBERS Final Due Date: 11/03/20 Subject: DRY SHAKE HARDENER Description: SEE ATTACHED PRODUCT DATA FOR EUCLID DIAMOND PLATE DRY SHAKE HARDENER TO BE USED ON SLABS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 08922 | Review Response | Approved | 2020-10-21 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 11789 | Responded and Closed | Approved | 2020-10-22 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-20 |  | 033000-0068 - Dry Shake Hardener.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-20 |  | 033000-0068 - Dry Shake Hardener.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-20 |  | 033000-0068 - Dry Shake Hardener.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-22 |  | 033000-0068 - Dry Shake Hardener_TT_POP.pdf
03 30 00-069-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-069-00 03 30 00 - South Parcel Decline Ramp & Dogbone CIP Wall Formwork Drawings & Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-16 | 2020-11-18 | 17 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09155 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-16 | Submittal Number: 03 30 00-69.0 From: TYRONE THORNTON Final Due Date: 11/16/20 Subject: 03 30 00 - SOUTH PARCEL DECLINE RAMP & DOGBONE CIP WALL FORMWORK DRAWINGS & CALCULATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 12079 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-09 | Submittal Number: 03 30 00-69.0 From: TYRONE THORNTON Final Due Date: 11/16/20 Subject: 03 30 00 - SOUTH PARCEL DECLINE RAMP & DOGBONE CIP WALL FORMWORK DRAWINGS & CALCULATIONS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 09530 | Review Response | No Action Taken or Required | 2020-11-06 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Received for Record | Info Exchange
| 12549 | Responded and Closed | No Action Taken or Required | 2020-11-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | Decline Ramp & Dogbone CIP Formwork Dwgs & Calcs_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | Decline Ramp & Dogbone CIP Formwork Dwgs & Calcs_MAM Review.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-11-02 |  | Decline Ramp & Dogbone CIP Formwork Dwgs & Calcs_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-18 |  | 03 30 00 - 69 Decline Ramp & Dogbone CIP Formwork Dwgs & Calcs_MAM Review_TT-POP.pdf
03 30 00-070-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-070-00 Decline Ramp SOG Dowel Bar & Joint Layout | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-05 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-01-19 | 2021-01-12 | 8 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-01-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10446 | Received | For Review | 2021-01-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-01-19 | Submittal Number: 03 30 00-70.0 From: TYRONE THORNTON Final Due Date: 01/18/21 Subject: 03 30 00 - DECLINE RAMP SOG DOWEL BAR & JOINT LAYOUT Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13634 | Forwarded | For Review | 2021-01-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-12 | Submittal Number: 03 30 00-70.0 From: TYRONE THORNTON Final Due Date: 01/18/21 Subject: 03 30 00 - DECLINE RAMP SOG DOWEL BAR & JOINT LAYOUT Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13693 | Forwarded | For Review | 2021-01-06 | Josh Dobken (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-01-13 | Submittal Number: 03 30 00-70.0 From: TYRONE THORNTON Final Due Date: 01/18/21 Subject: 03 30 00 - DECLINE RAMP SOG DOWEL BAR & JOINT LAYOUT Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 10644 | Review Response | Approved as Noted | 2021-01-08 | Jarrett Grant (DCI Engineers) | Josh Dobken (Populous) |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 13854 | Responded and Closed | Approved as Noted | 2021-01-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-04 |  | 03 30 00 -Decline Ramp SOG Dowel Bar & Joint Layout_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-04 |  | 03 30 00 -Decline Ramp SOG Dowel Bar & Joint Layout_MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-03 02:00 |  | 03 30 00 -Decline Ramp SOG Dowel Bar & Joint Layout_MAM Review.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-01-03 02:00 |  | 03 30 00 -Decline Ramp SOG Dowel Bar & Joint Layout_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-12 02:00 |  | 03 30 00 -Decline Ramp SOG Dowel Bar & Joint Layout_MAM Review_DCI_pop.pdf
03 30 00-071-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-071-00 03 30 00 - Decline Ramp SOG 1-Day Paving Mix | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-01-22 08:00 | 2021-01-20 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10494 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-01-22 08:00 | Submittal Number: 03 30 00-71.0 From: TYRONE THORNTON Final Due Date: 01/20/21 Subject: 03 30 00 - DECLINE RAMP SOG 1-DAY PAVING MIX Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13697 | Forwarded | For Review | 2021-01-06 | Tyrone Thornton (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-13 | Submittal Number: 03 30 00-71.0 From: TYRONE THORNTON Final Due Date: 01/20/21 Subject: 03 30 00 - DECLINE RAMP SOG 1-DAY PAVING MIX Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13892 | Forwarded | For Review | 2021-01-13 | Tyrone Thornton (Mortenson Construction) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-01-20 | Submittal Number: 03 30 00-71.0 From: TYRONE THORNTON Final Due Date: 01/20/21 Subject: 03 30 00 - DECLINE RAMP SOG 1-DAY PAVING MIX Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 10792 | Review Response | Approved as Noted | 2021-01-20 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | Please see attached for DCI’s review of the decline ramp paving mix submittal. - J. Grant, DCI Engineers | Info Exchange
| 14039 | Responded and Closed | Approved as Noted | 2021-01-20 | Tyrone Thornton (Mortenson Construction) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: Please see attached for DCI’s review of the decline ramp paving mix submittal. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-06 |  | 03 30 00 - Decline Ramp SOG 1-Day Paving Mix.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-01-06 |  | 03 30 00 - Decline Ramp SOG 1-Day Paving Mix.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-01-06 |  | 03 30 00 - Decline Ramp SOG 1-Day Paving Mix.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-01-20 02:00 |  | 03 30 00 - Decline Ramp SOG 1-Day Paving Mix_DCI.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-01-20 02:00 |  | 03 30 00 - Decline Ramp SOG 1-Day Paving Mix_DCI_pop.pdf
03 30 00-072-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-072-00 Geofoam Area 2 Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Closed - Void |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-01-29 08:00 |  | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-01-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10698 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-01-29 08:00 | Submittal Number: 03 30 00-72.0 From: CHRISTIAN ALBERS Final Due Date: 01/27/21 Subject: GEOFOAM AREA 2 SHOP DRAWINGS Description: REVIEW AREA 2 GEOFOAM SHOPS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13919 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-21 | Submittal Number: 03 30 00-72.0 From: CHRISTIAN ALBERS Final Due Date: 01/27/21 Subject: GEOFOAM AREA 2 SHOP DRAWINGS Description: REVIEW AREA 2 GEOFOAM SHOPS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13929 | Forwarded | For Review | 2021-01-14 | Todd Spangler (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) |  | Submittal Number: 03 30 00-72.0 From: CHRISTIAN ALBERS Final Due Date: 01/27/21 Subject: GEOFOAM AREA 2 SHOP DRAWINGS Description: REVIEW AREA 2 GEOFOAM SHOPS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 14305 | Closed | Void | 2021-01-27 | Josh Dobken (Populous) |  |  | Contractor updated submittal in revision 1 while this item was still open. Item voided per email attached.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 03 20 00 - 0072 - Geofoam Area 2 Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 03 20 00 - 0072 - Geofoam Area 2 Shop Drawings.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2021-01-13 |  | 03 20 00 - 0072 - Geofoam Area 2 Shop Drawings.pdf
03 30 00-072-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-072-01 Geofoam Area 2 Shop Drawings | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-26 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-09 | 2021-02-05 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-02-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10959 | Received | For Review | 2021-01-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-02-09 | Submittal Number: 03 30 00-72.1 From: CHRISTIAN ALBERS Final Due Date: 02/01/21 Subject: GEOFOAM AREA 2 SHOP DRAWINGS Description: REVIEW AREA 2 GEOFOAM SHOPS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 14233 | Forwarded | For Review | 2021-01-26 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-02 | Submittal Number: 03 30 00-72.1 From: CHRISTIAN ALBERS Final Due Date: 02/01/21 Subject: GEOFOAM AREA 2 SHOP DRAWINGS Description: REVIEW AREA 2 GEOFOAM SHOPS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 14456 | Forwarded | For Review | 2021-02-02 | Christian Albers (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-09 | Submittal Number: 03 30 00-72.1 From: CHRISTIAN ALBERS Final Due Date: 02/01/21 Subject: GEOFOAM AREA 2 SHOP DRAWINGS Description: REVIEW AREA 2 GEOFOAM SHOPS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11234 | Review Response | Approved as Noted | 2021-02-05 | Matt Ross (Thornton Tomasetti) | Tom Usher (Populous) |  |  | Info Exchange
| 14538 | Responded and Closed | Approved as Noted | 2021-02-05 | Christian Albers (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 03 20 00 - 0072.1 - Geofoam Area 2 Shop Drawings WITH GRIDLINES.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-01-25 |  | 03 20 00 - 0072.1 - Geofoam Area 2 Shop Drawings WITH GRIDLINES.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-01-24 02:00 |  | 03 20 00 - 0072.1 - Geofoam Area 2 Shop Drawings WITH GRIDLINES.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-25 |  | 03 20 00 - 0072.1 - Geofoam Area 2 Shop Drawings WITH GRIDLINES.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-01-25 |  | 03 20 00 - 0072.1 - Geofoam Area 2 Shop Drawings WITH GRIDLINES.pdf
03 30 00-073-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-073-00 Confoam Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-26 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-09 | 2021-02-09 | 15 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10960 | Received | For Review | 2021-01-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-02-09 | Submittal Number: 03 30 00-73.0 From: CHRISTIAN ALBERS Final Due Date: 02/08/21 Subject: CONFOAM PRODUCT DATA Description: SEE ATTACHED PRODUCT DATA FOR CONFOAM TO BE USED AS INFILL IN THE SOUTH WEST SNORKEL/WEST TEMP RAMP. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 14234 | Forwarded | For Review | 2021-01-26 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-02 | Submittal Number: 03 30 00-73.0 From: CHRISTIAN ALBERS Final Due Date: 02/08/21 Subject: CONFOAM PRODUCT DATA Description: SEE ATTACHED PRODUCT DATA FOR CONFOAM TO BE USED AS INFILL IN THE SOUTH WEST SNORKEL/WEST TEMP RAMP. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11298 | Review Response | Approved | 2021-02-04 | Seth Knihtila (Thornton Tomasetti) | Christian Albers (Mortenson Construction) |  | TT: Product data submittal approved. Mortenson to submit mix design with break history for review under separate cover | Info Exchange
| 14647 | Responded and Closed | Approved | 2021-02-09 | Christian Albers (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 03 30 00 - 73 - Confoam Proudct Data.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-01-25 |  | 03 30 00 - 73 - Confoam Proudct Data.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2021-01-25 |  | 03 30 00 - 73 - Confoam Proudct Data.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-02-09 |  | 03 30 00 - 73 - Confoam Proudct Data_TT-POP.pdf
03 30 00-074-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-074-00 Area 3 Geofoam Shop Drawings | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-02 | 2021-03-05 | 18 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-03-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11447 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-03-02 | Submittal Number: 03 30 00-74.0 From: CHRISTIAN ALBERS Final Due Date: 03/01/21 Subject: AREA 3 GEOFOAM SHOP DRAWINGS Description: SEE ATTACHED AREA 3 GEOFOAM SHOP DRAWINGS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 14829 | Forwarded | For Review | 2021-02-16 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-02-23 | Submittal Number: 03 30 00-74.0 From: CHRISTIAN ALBERS Final Due Date: 03/01/21 Subject: AREA 3 GEOFOAM SHOP DRAWINGS Description: SEE ATTACHED AREA 3 GEOFOAM SHOP DRAWINGS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 14998 | Forwarded | For Review | 2021-02-22 | Christian Albers (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-01 | Submittal Number: 03 30 00-74.0 From: CHRISTIAN ALBERS Final Due Date: 03/01/21 Subject: AREA 3 GEOFOAM SHOP DRAWINGS Description: SEE ATTACHED AREA 3 GEOFOAM SHOP DRAWINGS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11822 | Review Response | Approved as Noted | 2021-02-24 | Sean McNeill (Thornton Tomasetti) | Tom Usher (Populous) |  |  | Info Exchange
| 15194 | Forwarded | For Review | 2021-03-01 | Christian Albers (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-02 | Submittal Number: 03 30 00-74.0 From: CHRISTIAN ALBERS Final Due Date: 03/01/21 Subject: AREA 3 GEOFOAM SHOP DRAWINGS Description: SEE ATTACHED AREA 3 GEOFOAM SHOP DRAWINGS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11823 | Review Response | Approved as Noted | 2021-03-04 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Tom Usher (Populous) |  |  | Info Exchange
| 15328 | Responded and Closed | Approved as Noted | 2021-03-05 | Tom Usher (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Sean McNeill (Thornton Tomasetti) Remarks: Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 03 30 00 - 74 - Area 3 Geofoam Shop Drawings.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-02-15 |  | 03 30 00 - 74 - Area 3 Geofoam Shop Drawings.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-02-14 02:00 |  | 03 30 00 - 74 - Area 3 Geofoam Shop Drawings.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-02-15 |  | 03 30 00 - 74 - Area 3 Geofoam Shop Drawings.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-02-14 02:00 |  | 03 30 00 - 74 - Area 3 Geofoam Shop Drawings.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-02-14 |  | 03 30 00 - 74 - Area 3 Geofoam Shop Drawings.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2021-03-05 |  | 03 30 00 - 74 - Area 3 Geofoam Shop Drawings_TT-SWIFT_POP.pdf
03 30 00-075-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-075-00: South Parcel - North Pony Wall Below Whalers at Generator Slab Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-25 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-11 | 2021-02-26 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-02-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11665 | Received | For Review | 2021-02-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Generosa | 2021-03-11 | Submittal Number: 03 30 00-75.0 From: CHRISTIAN GENEROSA Final Due Date: 03/12/21 Subject: SOUTH PARCEL - NORTH PONY WALL BELOW WHALERS AT GENERATOR SLAB MIX DESIGN Description: MIX DESIGN REGARDING THE NORTH PONY WALL BELOW THE WHALERS AT THE GENERATOR SLAB. THE INTENT OF THIS MIX IS TO GAIN 5000 PSI WITHIN A 5 DAY CURE PERIOD. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 15116 | Forwarded | For Review | 2021-02-25 | Christian Generosa | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-04 | Submittal Number: 03 30 00-75.0 From: CHRISTIAN GENEROSA Final Due Date: 03/12/21 Subject: SOUTH PARCEL - NORTH PONY WALL BELOW WHALERS AT GENERATOR SLAB MIX DESIGN Description: MIX DESIGN REGARDING THE NORTH PONY WALL BELOW THE WHALERS AT THE GENERATOR SLAB. THE INTENT OF THIS MIX IS TO GAIN 5000 PSI WITHIN A 5 DAY CURE PERIOD. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11669 | Review Response | Approved | 2021-02-25 | Sean McNeill (Thornton Tomasetti) | Christian Generosa |  | No Exceptions | Info Exchange
| 15121 | Responded and Closed | Approved | 2021-02-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Sean McNeill (Thornton Tomasetti) Remarks: No Exceptions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-25 02:00 |  | 033000-75 South Parcel North Pony Wall Below Whalers at Generator Slab MD _MAM.pdf
| Forwarded |  | Christian Generosa | 1 | 2021-02-25 02:00 |  | 033000-75 South Parcel North Pony Wall Below Whalers at Generator Slab MD _MAM.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-02-25 02:00 |  | 033000-75 South Parcel North Pony Wall Below Whalers at Generator Slab MD _MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-26 02:00 |  | 033000-75 South Parcel North Pony Wall Below Whalers at Generator Slab MD _MAM_TT_POP.pdf
03 30 00-076-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-076-00 Site Wall In-Place Mock Up | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-02 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-16 | 2021-03-10 | 9 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11735 | Received | For Review | 2021-03-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Jesse Erickson (Mortenson Construction) | 2021-03-16 | Submittal Number: 03 30 00-76.0 From: JESSE ERICKSON Final Due Date: 03/15/21 Subject: SITE WALL IN-PLACE MOCK UP Description: PLEASE SEE ATTACHMENTS FOR SITE WORK IN-PLACE WALL MOCK UP. REVIEWED ON 2/23 WITH POPULOUS, SWIFT, CAAICON, AND MORTENSON. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 15207 | Forwarded | For Review | 2021-03-02 | Jesse Erickson (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-09 | Submittal Number: 03 30 00-76.0 From: JESSE ERICKSON Final Due Date: 03/15/21 Subject: SITE WALL IN-PLACE MOCK UP Description: PLEASE SEE ATTACHMENTS FOR SITE WORK IN-PLACE WALL MOCK UP. REVIEWED ON 2/23 WITH POPULOUS, SWIFT, CAAICON, AND MORTENSON. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 15221 | Forwarded | For Review | 2021-03-02 | Jesse Erickson (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-09 | Submittal Number: 03 30 00-76.0 From: JESSE ERICKSON Final Due Date: 03/15/21 Subject: SITE WALL IN-PLACE MOCK UP Description: PLEASE SEE ATTACHMENTS FOR SITE WORK IN-PLACE WALL MOCK UP. REVIEWED ON 2/23 WITH POPULOUS, SWIFT, CAAICON, AND MORTENSON. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 11930 | Review Response | Approved as Noted | 2021-03-08 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA; Jesse Erickson (Mortenson Construction) |  |  | Info Exchange
| 12030 | Review Response | Approved as Noted | 2021-03-09 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Jesse Erickson (Mortenson Construction) |  |  | Info Exchange
| 15454 | Responded and Closed | Approved as Noted | 2021-03-10 | Jesse Erickson (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Jesse Erickson (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: REFER TO COMMENTS IN SUBMITTAL | Info Exchange
| 16587 | Sent | For Information Only | 2021-04-27 | Josh Dobken (Populous) | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Jesse Erickson (Mortenson Construction) |  | Responded and Closed (Approved as Noted) to: Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Jesse Erickson (Mortenson Construction) Remarks: Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: REFER TO COMMENTS IN SUBMITTAL | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-02 |  | 03 30 00-76.0 Site Wall Map mock up.pdf
| Forwarded |  | Jesse Erickson (Mortenson Construction) | 1 | 2021-03-02 |  | 03 30 00-76.0 Site Wall Map mock up.pdf
| Forwarded |  | Jesse Erickson (Mortenson Construction) | 1 | 2021-03-02 |  | 03 30 00-76.0 Site Wall Map mock up.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-01 02:00 |  | 03 30 00-76.0 Site Wall Map mock up.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-01 02:00 |  | 03 30 00-76.0 Site Wall Map mock up.pdf
| Responded and Closed |  | Jesse Erickson (Mortenson Construction) | 1 | 2021-03-10 02:00 |  | 03 30 00-76.0 Site Wall Map mock up - SWIFT_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-03-01 02:00 |  | 03 30 00-76.0 Site Wall Map mock up.pdf
03 30 00-077-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-077-00 Ice Rink Concrete Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-19 | Closed - Void |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-02 |  | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-03-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12118 | Received | For Review | 2021-03-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-04-02 | Submittal Number: 03 30 00-77.0 From: TYRONE THORNTON Final Due Date: 04/02/21 Subject: ICE RINK CONCRETE MIX DESIGN Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 15685 | Forwarded | For Review | 2021-03-19 | Tyrone Thornton (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-26 | Submittal Number: 03 30 00-77.0 From: TYRONE THORNTON Final Due Date: 04/02/21 Subject: ICE RINK CONCRETE MIX DESIGN Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 15838 | Closed | Void | 2021-03-25 | Josh Dobken (Populous) |  |  | Voided due to adjustments in numbering. Item has been re-sent by Contractor under submittal number 13 10 62-004-00.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-19 |  | 03 30 00 - ICE RINK Concrete Mix_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-03-19 |  | 03 30 00 - ICE RINK Concrete Mix_MAM Review.pdf
03 30 00-078-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-078-00 Prorail Grout and Sealant Product Data and Detail | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-24 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Chris Minter (Populous) |  |  |  | 2021-06-08 07:00 | 2021-05-26 | 3 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13229 | Received | For Review | 2021-05-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-08 07:00 | Submittal Number: 03 30 00-78.0 From: JESSE ERICKSON Final Due Date: 06/04/21 Subject: PRORAIL GROUT AND SEALANT PRODUCT DATA AND DETAIL Description: PLEASE SEE ATTACHED PDF REGARDING PRODUCT DATA AND DETAILS IN REFERENCE TO THE SEALING AND GROUTING OF THE PRORAIL. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17116 | Forwarded | For Review | 2021-05-22 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-05-31 | Submittal Number: 03 30 00-78.0 From: JESSE ERICKSON Final Due Date: 06/04/21 Subject: PRORAIL GROUT AND SEALANT PRODUCT DATA AND DETAIL Description: PLEASE SEE ATTACHED PDF REGARDING PRODUCT DATA AND DETAILS IN REFERENCE TO THE SEALING AND GROUTING OF THE PRORAIL. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17133 | Forwarded | For Review | 2021-05-24 | Populous SCA_CCA | Chris Minter (Populous) | 2021-05-31 | Submittal Number: 03 30 00-78.0 From: JESSE ERICKSON Final Due Date: 06/04/21 Subject: PRORAIL GROUT AND SEALANT PRODUCT DATA AND DETAIL Description: PLEASE SEE ATTACHED PDF REGARDING PRODUCT DATA AND DETAILS IN REFERENCE TO THE SEALING AND GROUTING OF THE PRORAIL. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17174 | Responded and Closed | Approved as Noted | 2021-05-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 17462 | Sent | For Information Only | 2021-06-13 | Populous SCA_CCA | Josh Broussard (Mortenson Construction); Brooke Burcham (Mortenson Construction); Christian Albers (Mortenson Construction); Allie Zimmerman; Cody Stieritz |  | Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-22 |  | 03 30 00-78.0 Prorail Grout and Sealant Data and Detail.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-22 02:00 |  | 03 30 00-78.0 Prorail Grout and Sealant Data and Detail.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-22 02:00 |  | Transmittal_Submittal - 03 30 00-078-00 (Forwarded).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-26 |  | 03 30 00-78.0 Prorail Grout and Sealant Data and Detail-POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-05-22 02:00 |  | 03 30 00-78.0 Prorail Grout and Sealant Data and Detail.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-05-22 02:00 |  | Transmittal_Submittal - 03 30 00-078-00 (Forwarded).pdf
03 30 00-079-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-079-00 Geofoam Area 1 Shop Drawings | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-26 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-06-10 07:00 | 2021-06-15 | 21 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13269 | Received | For Review | 2021-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-06-10 07:00 | Submittal Number: 03 30 00-79.0 From: CHRISTIAN ALBERS Final Due Date: 06/08/21 Subject: GEOFOAM AREA 1 SHOP DRAWINGS Description: SEE ATTACHED AREA 1 GEOFOAM SHOP DRAWINGS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17170 | Forwarded | For Review | 2021-05-26 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-02 | Submittal Number: 03 30 00-79.0 From: CHRISTIAN ALBERS Final Due Date: 06/08/21 Subject: GEOFOAM AREA 1 SHOP DRAWINGS Description: SEE ATTACHED AREA 1 GEOFOAM SHOP DRAWINGS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17175 | Forwarded | For Review | 2021-05-26 | Christian Albers (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-02 | Submittal Number: 03 30 00-79.0 From: CHRISTIAN ALBERS Final Due Date: 06/08/21 Subject: GEOFOAM AREA 1 SHOP DRAWINGS Description: SEE ATTACHED AREA 1 GEOFOAM SHOP DRAWINGS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13459 | Review Response | Approved as Noted | 2021-06-08 | Sean McNeill (Thornton Tomasetti) | Christian Albers (Mortenson Construction) |  |  | Info Exchange
| 13525 | Review Response | Approved as Noted | 2021-06-11 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Christian Albers (Mortenson Construction) |  |  | Info Exchange
| 17505 | Responded and Closed | Approved as Noted | 2021-06-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | REFER TO COMMENTS WITHIN SUBMITTAL Response (Approved as Noted) from: Sean McNeill (Thornton Tomasetti) Remarks: Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-25 |  | 03 30 00 - 79 - Area 1 Geofoam Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-25 |  | 03 30 00 - 79 - Area 1 Geofoam Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-25 |  | 03 30 00 - 79 - Area 1 Geofoam Shops.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-05-25 |  | 03 30 00 - 79 - Area 1 Geofoam Shops.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-24 02:00 |  | 03 30 00 - 79 - Area 1 Geofoam Shops.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-15 02:00 |  | 03 30 00 - 79 - Area 1 Geofoam Shops - SWIFT_TT_POP.pdf
03 30 00-080-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-080-00 Geofoam Area 6 Shop Drawings | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-26 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-06-10 07:00 | 2021-06-15 | 21 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13270 | Received | For Review | 2021-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-06-10 07:00 | Submittal Number: 03 30 00-80.0 From: CHRISTIAN ALBERS Final Due Date: 06/08/21 Subject: GEOFOAM AREA 6 SHOP DRAWINGS Description: SEE ATTACHED AREA 6 GEOFOAM SHOP DRAWINGS FOR REVIEW. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17171 | Forwarded | For Review | 2021-05-26 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-02 | Submittal Number: 03 30 00-80.0 From: CHRISTIAN ALBERS Final Due Date: 06/08/21 Subject: GEOFOAM AREA 6 SHOP DRAWINGS Description: SEE ATTACHED AREA 6 GEOFOAM SHOP DRAWINGS FOR REVIEW. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17176 | Forwarded | For Review | 2021-05-26 | Christian Albers (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-02 | Submittal Number: 03 30 00-80.0 From: CHRISTIAN ALBERS Final Due Date: 06/08/21 Subject: GEOFOAM AREA 6 SHOP DRAWINGS Description: SEE ATTACHED AREA 6 GEOFOAM SHOP DRAWINGS FOR REVIEW. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13529 | Review Response | Approved | 2021-06-08 | Sean McNeill (Thornton Tomasetti) | Christian Albers (Mortenson Construction) |  |  | Info Exchange
| 13530 | Review Response | Approved as Noted | 2021-06-11 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Christian Albers (Mortenson Construction) |  |  | Info Exchange
| 17506 | Responded and Closed | Approved as Noted | 2021-06-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | REFER TO COMMENTS WITHIN SUBMITTAL. CONSTRUCTION NOTES NOT REVIEWED. Response (Approved) from: Sean McNeill (Thornton Tomasetti) Remarks: Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-25 |  | 03 30 00 - 80 - Area 6 Geofoam Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-25 |  | 03 30 00 - 80 - Area 6 Geofoam Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-25 |  | 03 30 00 - 80 - Area 6 Geofoam Shops.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-05-24 02:00 |  | 03 30 00 - 80 - Area 6 Geofoam Shops.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-24 02:00 |  | 03 30 00 - 80 - Area 6 Geofoam Shops.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-15 02:00 |  | 03 30 00 - 80 - Area 6 Geofoam Shops - SWIFT_TT_POP.pdf
03 30 00-081-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-081-00 Geofoam Area 7 Shop Drawings | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-26 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-06-10 07:00 | 2021-06-15 | 21 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13271 | Received | For Review | 2021-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-06-10 07:00 | Submittal Number: 03 30 00-81.0 From: CHRISTIAN ALBERS Final Due Date: 06/08/21 Subject: GEOFOAM AREA 7 SHOP DRAWINGS Description: SEE ATTACHED AREA 7 GEOFOAM SHOP DRAWINGS FOR REVIEW. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17172 | Forwarded | For Review | 2021-05-26 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-02 | Submittal Number: 03 30 00-81.0 From: CHRISTIAN ALBERS Final Due Date: 06/08/21 Subject: GEOFOAM AREA 7 SHOP DRAWINGS Description: SEE ATTACHED AREA 7 GEOFOAM SHOP DRAWINGS FOR REVIEW. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17177 | Forwarded | For Review | 2021-05-26 | Christian Albers (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-02 | Submittal Number: 03 30 00-81.0 From: CHRISTIAN ALBERS Final Due Date: 06/08/21 Subject: GEOFOAM AREA 7 SHOP DRAWINGS Description: SEE ATTACHED AREA 7 GEOFOAM SHOP DRAWINGS FOR REVIEW. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13539 | Review Response | Approved | 2021-06-08 | Sean McNeill (Thornton Tomasetti) | Christian Albers (Mortenson Construction) |  |  | Info Exchange
| 13541 | Review Response | Approved as Noted | 2021-06-11 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Christian Albers (Mortenson Construction) |  |  | Info Exchange
| 17507 | Responded and Closed | Approved as Noted | 2021-06-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | REFER TO COMMENTS WITHIN SUBMITTAL. CONSTRUCTION NOTES NOT REVIEWED. Pending response (Approved) from: Sean McNeill (Thornton Tomasetti) Remarks: Pending response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-25 |  | 03 30 00 - 81 - Area 7 Geofoam Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-25 |  | 03 30 00 - 81 - Area 7 Geofoam Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-25 |  | 03 30 00 - 81 - Area 7 Geofoam Shops.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-05-24 02:00 |  | 03 30 00 - 81 - Area 7 Geofoam Shops.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-24 02:00 |  | 03 30 00 - 81 - Area 7 Geofoam Shops.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-15 02:00 |  | 03 30 00 - 81 - Area 7 Geofoam Shops - SWIFT_TT_POP.pdf
03 30 00-082-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-082-00 Atrium Slab NCN Remediation | Closed | Structural, Architectural, Owner/Operator | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-28 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Mike Steele (CAA ICON / Strategy Advisory), Elliott Veazey (CAA ICON / Strategy Advisory), Mike Tihista (CAA ICON / Strategy Advisory), Byron Noll (CAA ICON / Strategy Advisory), Cody Koch (CAA ICON / Strategy Advisory), Dan Wowryk (Icon Venue Group) |  |  |  | 2021-07-16 | 2021-07-15 | 49 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13312 | Received | For Review | 2021-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-16 | Submittal Number: 03 30 00-82.0 From: JESSE ERICKSON Final Due Date: 06/10/21 Subject: ATRIUM SLAB NCN REMEDIATION Description: PLEASE SEE ATTACHED PDF IN REGARDS TO PROPOSED FIX FOR NCN'S 62 AND 63 AND GENERAL ATRIUM SLAB RAIN OUT AND DEFECTIVE SLAB AREAS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17227 | Forwarded | For Review | 2021-06-01 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-08 | Submittal Number: 03 30 00-82.0 From: JESSE ERICKSON Final Due Date: 06/10/21 Subject: ATRIUM SLAB NCN REMEDIATION Description: PLEASE SEE ATTACHED PDF IN REGARDS TO PROPOSED FIX FOR NCN'S 62 AND 63 AND GENERAL ATRIUM SLAB RAIN OUT AND DEFECTIVE SLAB AREAS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13470 | Review Response | Approved | 2021-06-04 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Refer to TT comments. Arch to review. | Info Exchange
| 17357 | Forwarded | For Review | 2021-06-07 | Josh Dobken (Populous) | Mike Steele (CAA ICON / Strategy Advisory); Elliott Veazey (CAA ICON / Strategy Advisory); Mike Tihista (CAA ICON / Strategy Advisory); Byron Noll (CAA ICON / Strategy Advisory); Cody Koch (CAA ICON / Strategy Advisory); Dan Wowryk (Icon Venue Group) | 2021-06-14 | Submittal Number: 03 30 00-82.0 From: JESSE ERICKSON Final Due Date: 06/10/21 Subject: ATRIUM SLAB NCN REMEDIATION Description: PLEASE SEE ATTACHED PDF IN REGARDS TO PROPOSED FIX FOR NCN'S 62 AND 63 AND GENERAL ATRIUM SLAB RAIN OUT AND DEFECTIVE SLAB AREAS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Email
| 18067 | Responded and Closed | Approved as Noted | 2021-07-15 | Populous SCA_CCA | Brent Leiter (Mortenson Construction); Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Greg Goebel (Mortenson Construction); Alex Brown (Mortenson Constructi... |  | REFER TO ATTACHED SUBMITTAL FOR COMMENTS REFLECTING SLAB REMEDIATION AND MOCKUP REVIEW. J. Dobken / Populous 7/15/21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-01 |  | 03 30 00-082-00 Atrium NCN remediation.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-06-01 |  | 03 30 00-082-00 Atrium NCN remediation.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-04 02:00 |  | 03 30 00-082-00 Atrium NCN remediation_TT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-15 02:00 |  | 03 30 00-082-00 Atrium NCN remediation_TT_POP.pdf
03 30 00-083-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-083-00 Epoxy Crack Injection Procedure for Crack Repair at South Parcel Saddlebags | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-01 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-15 | 2021-06-09 | 9 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13313 | Received | For Review | 2021-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-15 | Submittal Number: 03 30 00-83.0 From: MICHAEL HENNESSY Final Due Date: 06/14/21 Subject: EPOXY CRACK INJECTION PROCEDURE FOR CRACK REPAIR AT SOUTH PARCEL SADDLEBAGS Description: REPEATED CRACK REPAIR PROCEDURE AT SOUTH PARCEL SADDLEBAG DOOR ENTRIES. PROCEDURE PREVIOUSLY USED FROM SOG REFERENCE OBSERVATION #942. THIS SUBMITTAL IS FOR RECORD. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17228 | Forwarded | For Review | 2021-06-01 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-08 | Submittal Number: 03 30 00-83.0 From: MICHAEL HENNESSY Final Due Date: 06/14/21 Subject: EPOXY CRACK INJECTION PROCEDURE FOR CRACK REPAIR AT SOUTH PARCEL SADDLEBAGS Description: REPEATED CRACK REPAIR PROCEDURE AT SOUTH PARCEL SADDLEBAG DOOR ENTRIES. PROCEDURE PREVIOUSLY USED FROM SOG REFERENCE OBSERVATION #942. THIS SUBMITTAL IS FOR RECORD. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13473 | Review Response | Approved as Noted | 2021-06-04 | Michael Croly (Thornton Tomasetti) | Populous SCA_CCA |  | Please see the attached file for TTs response | Info Exchange
| 17422 | Responded and Closed | Approved as Noted | 2021-06-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 17526 | Sent | For Information Only | 2021-06-15 | Populous SCA_CCA | Brooke Burcham (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Michael Croly (Thornton Tomasetti) Remarks: Please see the attached file for TTs response Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-28 |  | 2021-05-28 03 30 00-0083-00 Epoxy Crack Injection Procedures at South Parcel Saddlebags_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-28 |  | 2021-05-28 03 30 00-0083-00 Epoxy Crack Injection Procedures at South Parcel Saddlebags_MAM.pdf
| Review Response |  | Michael Croly (Thornton Tomasetti) | 1 | 2021-05-28 |  | 2021-05-28 03 30 00-0083-00 Epoxy Crack Injection Procedures at South Parcel Saddlebags_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-04 |  | 2021-05-28 03 30 00-0083-00 Epoxy Crack Injection Procedures at South Parcel Saddlebags_MAM_TT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-09 |  | 2021-05-28 03 30 00-0083-00 Epoxy Crack Injection Procedures at South Parcel Saddlebags_MAM_TT-POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-05-27 02:00 |  | 2021-05-28 03 30 00-0083-00 Epoxy Crack Injection Procedures at South Parcel Saddlebags_MAM.pdf
03 30 00-084-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-084-00 Area 5 Geofoam Shops | Closed | Landscape, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-23 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-07-08 07:00 | 2021-07-08 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13617 | Received | For Review | 2021-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-07-08 07:00 | Submittal Number: 03 30 00-84.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: AREA 5 GEOFOAM SHOPS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17632 | Forwarded | For Review | 2021-06-23 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-30 | Submittal Number: 03 30 00-84.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: AREA 5 GEOFOAM SHOPS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17657 | Forwarded | For Review | 2021-06-24 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-07-01 | Submittal Number: 03 30 00-84.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: AREA 5 GEOFOAM SHOPS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13869 | Review Response | Approved | 2021-06-29 | Franz Kogler (Thornton Tomasetti) | Christian Albers (Mortenson Construction) |  | Swift (Landscape) to review. | Info Exchange
| 13870 | Review Response | Approved as Noted | 2021-07-08 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  |  | Info Exchange
| 17945 | Responded and Closed | Approved as Noted | 2021-07-08 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | See notes in submittal attached. Contractor to coordinate geofoam requirements adjacent and below bollard footings with bollard manufacturer. Typical at all bollards. Response (Approved) from: Franz Kogler (Thornton Tomasetti) Remarks: Swift (Landscape) to review. Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-22 |  | 03 30 00 - 84 - Area 5 Geofoam Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-22 |  | 03 30 00 - 84 - Area 5 Geofoam Shops.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-21 02:00 |  | 03 30 00 - 84 - Area 5 Geofoam Shops.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-06-21 02:00 |  | 03 30 00 - 84 - Area 5 Geofoam Shops.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-06-21 02:00 |  | 03 30 00 - 84 - Area 5 Geofoam Shops.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-07-08 02:00 |  | 03 30 00 - 84 - Area 5 Geofoam Shops -TT SWIFT POP.pdf
03 30 00-085-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-085-00 Area 4 Geofoam Shops | Closed | Landscape, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-23 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-07-08 07:00 | 2021-07-08 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13618 | Received | For Review | 2021-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-07-08 07:00 | Submittal Number: 03 30 00-85.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: AREA 4 GEOFOAM SHOPS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17633 | Forwarded | For Review | 2021-06-23 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-30 | Submittal Number: 03 30 00-85.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: AREA 4 GEOFOAM SHOPS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 17658 | Forwarded | For Review | 2021-06-24 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-07-01 | Submittal Number: 03 30 00-85.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: AREA 4 GEOFOAM SHOPS Description: Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 13867 | Review Response | Approved | 2021-07-01 | Franz Kogler (Thornton Tomasetti) | Christian Albers (Mortenson Construction) |  | Landscape (Swift) to review. | Info Exchange
| 13868 | Review Response | Approved as Noted | 2021-07-07 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | See comments in submittal. | Info Exchange
| 17944 | Responded and Closed | Approved as Noted | 2021-07-08 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Franz Kogler (Thornton Tomasetti) Remarks: Landscape (Swift) to review. Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See comments in submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-22 |  | 03 30 00 - 85 - Area 4 Geofoam Shops.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-22 |  | 03 30 00 - 85 - Area 4 Geofoam Shops.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-21 02:00 |  | 03 30 00 - 85 - Area 4 Geofoam Shops.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-06-21 02:00 |  | 03 30 00 - 85 - Area 4 Geofoam Shops.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-06-21 02:00 |  | 03 30 00 - 85 - Area 4 Geofoam Shops.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-07-08 02:00 |  | 03 30 00 - 85 - Area 4 Geofoam Shops_TTReview-SWIFT_POP.pdf
03 30 00-086-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-086-00 Euclid Chemical Company Crack Repair Material - Euco Qwikstitch | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-05 | Closed - Void |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-08-19 |  | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14229 | Received | For Review | 2021-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jesse Erickson (Mortenson Construction) | 2021-08-19 | Submittal Number: 03 30 00-86.0 From: JESSE ERICKSON Final Due Date: 08/16/21 Subject: EUCLID CHEMICAL COMPANY CRACK REPAIR MATERIAL - EUCO QWIKSTITCH Description: PER SPEC 03 30 00 - 22, D - 3; ACCEPTABLE PRODUCT LISTED AS EUCLID CHEMICAL COMPANY "EUCOPOXY INJECTION RESIN", IS NO LONGER AVAILABLE BY THE EUCLID COMPANY. A EUCLID PRODUCT REPRESENTATIVE RECOMMENDED "EUCO QWIKSTITCH" AS A COMPARABLE/SUPERIOR PRODUCT. PLEASE CONFIRM "EUCO QWIKSTITCH" IS AN ACCEPTABLE SUBSTITUTE FOR "EUCOPOXY INJECTION RESIN". PLEASE SEE ATTACHED PRODUCT DATA SHEETS FOR "EUCO QWIKSTITCH". Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 18385 | Forwarded | For Review | 2021-08-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-08-12 | Submittal Number: 03 30 00-86.0 From: JESSE ERICKSON Final Due Date: 08/16/21 Subject: EUCLID CHEMICAL COMPANY CRACK REPAIR MATERIAL - EUCO QWIKSTITCH Description: PER SPEC 03 30 00 - 22, D - 3; ACCEPTABLE PRODUCT LISTED AS EUCLID CHEMICAL COMPANY "EUCOPOXY INJECTION RESIN", IS NO LONGER AVAILABLE BY THE EUCLID COMPANY. A EUCLID PRODUCT REPRESENTATIVE RECOMMENDED "EUCO QWIKSTITCH" AS A COMPARABLE/SUPERIOR PRODUCT. PLEASE CONFIRM "EUCO QWIKSTITCH" IS AN ACCEPTABLE SUBSTITUTE FOR "EUCOPOXY INJECTION RESIN". PLEASE SEE ATTACHED PRODUCT DATA SHEETS FOR "EUCO QWIKSTITCH". Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 18431 | Closed | Void | 2021-08-09 | Josh Dobken (Populous) |  |  | Superseded by revision 1.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-02 |  | Euco_QWIKstitch.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-02 |  | SS107_Euco_QWIKstitch.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-02 |  | Euco_QWIKstitch.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-02 |  | SS107_Euco_QWIKstitch.pdf
03 30 00-086-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-086-01 Euclid Chemical Company Crack Repair Material - Euco Qwikstitch | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-06 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-08-20 | 2021-08-26 | 21 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14256 | Received | For Review | 2021-08-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jesse Erickson (Mortenson Construction) | 2021-08-20 | Submittal Number: 03 30 00-86.1 From: JESSE ERICKSON Final Due Date: 08/16/21 Subject: EUCLID CHEMICAL COMPANY CRACK REPAIR MATERIAL - EUCO QWIKSTITCH Description: PER SPEC 03 30 00 - 22, D - 3; ACCEPTABLE PRODUCT LISTED FOR CRACK REPAIR IS EUCLID CHEMICAL COMPANY "EUCOPOXY INJECTION RESIN"; THIS PRODUCT IS NO LONGER AVAILABLE BY THE EUCLID COMPANY. A EUCLID PRODUCT REPRESENTATIVE RECOMMENDED "EUCO QWIKSTITCH" AS A COMPARABLE/SUPERIOR PRODUCT. PLEASE CONFIRM "EUCO QWIKSTITCH" AS AN ACCEPTABLE SUBSTITUTE FOR "EUCOPOXY INJECTION RESIN". PLEASE SEE ATTACHED PRODUCT DATA SHEETS FOR "EUCO QWIKSTITCH". Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 18418 | Forwarded | For Review | 2021-08-09 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-08-16 | Submittal Number: 03 30 00-86.1 From: JESSE ERICKSON Final Due Date: 08/16/21 Subject: EUCLID CHEMICAL COMPANY CRACK REPAIR MATERIAL - EUCO QWIKSTITCH Description: PER SPEC 03 30 00 - 22, D - 3; ACCEPTABLE PRODUCT LISTED FOR CRACK REPAIR IS EUCLID CHEMICAL COMPANY "EUCOPOXY INJECTION RESIN"; THIS PRODUCT IS NO LONGER AVAILABLE BY THE EUCLID COMPANY. A EUCLID PRODUCT REPRESENTATIVE RECOMMENDED "EUCO QWIKSTITCH" AS A COMPARABLE/SUPERIOR PRODUCT. PLEASE CONFIRM "EUCO QWIKSTITCH" AS AN ACCEPTABLE SUBSTITUTE FOR "EUCOPOXY INJECTION RESIN". PLEASE SEE ATTACHED PRODUCT DATA SHEETS FOR "EUCO QWIKSTITCH". Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 14502 | Review Response | Approved | 2021-08-11 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Arch to approve. Contractor to comment on intended use of crack repair material (SOMD/SOG/Topping Slabs/Shotcrete/etc?) | Info Exchange
| 18697 | Responded and Closed | Approved | 2021-08-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Greg Goebel (Mortenson Construction); Jesse Erickson (Mortenson Construction) |  | Email from Jesse Erickson confirms usage of crack repair materials and has been added to submittal. Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Arch to approve. Contractor to comment on intended use of crack repair material (SOMD/SOG/Topping Slabs/Shotcrete/etc?) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-06 |  | 03 30 00 00 86 Euclid Chemical Company Crack Repair Material Euco Qwikstitch.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-06 |  | 03 30 00 00 86 Euclid Chemical Company Crack Repair Material Euco Qwikstitch.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-08-05 02:00 |  | 03 30 00 00 86 Euclid Chemical Company Crack Repair Material Euco Qwikstitch.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-08-26 02:00 |  | 03 30 00 00 86 Euclid Chemical Company Crack Repair Material Euco Qwikstitch_TT_POP.pdf
03 30 00-087-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-087-00 North Courtyard Restored Seatwall Skim Coat PD | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-05 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-08-19 | 2021-09-07 | 34 |  | Record Copies; Transfers; Submittals | 03 30 00-087-00-01 - 03 30 00-087-00 North Courtyard Restored Seatwall Skim Coat PD | 30 |  | 2021-09-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14225 | Received | For Review | 2021-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-08-19 | Submittal Number: 03 30 00-87.0 From: CHRISTIAN ALBERS Final Due Date: 08/18/21 Subject: NORTH COURTYARD RESTORED SEATWALL SKIM COAT PD Description: SEE ATTACHED PRODUCT DATA FOR SKIM COAT MATERIAL TO BE USED ON THE NORTH COURTYARD EXISTING WALL TO BE REFURBISHED. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 18381 | Forwarded | For Review | 2021-08-04 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-08-11 | Submittal Number: 03 30 00-87.0 From: CHRISTIAN ALBERS Final Due Date: 08/18/21 Subject: NORTH COURTYARD RESTORED SEATWALL SKIM COAT PD Description: SEE ATTACHED PRODUCT DATA FOR SKIM COAT MATERIAL TO BE USED ON THE NORTH COURTYARD EXISTING WALL TO BE REFURBISHED. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 18388 | Forwarded | For Review | 2021-08-05 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-12 | Submittal Number: 03 30 00-87.0 From: CHRISTIAN ALBERS Final Due Date: 08/18/21 Subject: NORTH COURTYARD RESTORED SEATWALL SKIM COAT PD Description: SEE ATTACHED PRODUCT DATA FOR SKIM COAT MATERIAL TO BE USED ON THE NORTH COURTYARD EXISTING WALL TO BE REFURBISHED. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 14586 | Review Response | Approved as Noted/Resubmit | 2021-09-02 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Product approved for application and finish as illustrated in on-site mock-up. Color is not accepted, and per site conversation and email correspondence, darker color is required. Per attached email, installation occurred prior to approval of color. | Info Exchange
| 18805 | Responded and Closed | Approved as Noted/Resubmit | 2021-09-07 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Colin.Saiz@mortenson.com |  | Response (Approved as Noted/Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Product approved for application and finish as illustrated in on-site mock-up. Color is not accepted, and per site conversation and email correspondence, darker color is required. Per attached email, installation occurred prior to approval of color. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-04 |  | 03 30 00 - 87 - North Courtyard Restored Seatwall Skim Coat PD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-04 |  | 03 30 00 - 87 - North Courtyard Restored Seatwall Skim Coat PD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-04 |  | 03 30 00 - 87 - North Courtyard Restored Seatwall Skim Coat PD.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-09-07 02:00 |  | 03 30 00 - 87 - North Courtyard Restored Seatwall Skim Coat PD - SWIFT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-07 02:00 |  | 03 30 00-87- North Courtyard Restored Seatwall Skim Coat PD - SWIFT_POP.pdf
03 30 00-087-00-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-087-00 North Courtyard Restored Seatwall Skim Coat PD | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 30 00-087-00 - 03 30 00-087-00 North Courtyard Restored Seatwall Skim Coat PD | -1 | 2021-09-21
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-07 02:00 |  | 03 30 00-87- North Courtyard Restored Seatwall Skim Coat PD - SWIFT_POP.pdf
03 30 00-088-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-088-00 Site Work/ Flat Work Concrete Patching Procedure | Closed | Structural, Landscape, Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-11 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Damon Smith (DCI Engineers), Matthew Frisby |  |  |  | 2021-08-25 | 2021-09-08 | 29 |  | Record Copies; Transfers; Submittals | 03 30 00-088-00-01 - 03 30 00-088-00 Site Work/ Flat Work Concrete Patching Procedure | 29 |  | 2021-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14316 | Received | For Review | 2021-08-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-08-25 | Submittal Number: 03 30 00-88.0 From: CHRISTIAN ALBERS Final Due Date: 09/08/21 Subject: SITE WORK/ FLAT WORK CONCRETE PATCHING PROCEDURE Description: PLEASE SEE ATTACHED PDF DETAILING LARUSSO'S PATCHING PROCEDURE ALONG WITH PRODUCT DATA FOR SITE WORK FLATWORK. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 18488 | Forwarded | For Review | 2021-08-11 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-08-18 | Submittal Number: 03 30 00-88.0 From: CHRISTIAN ALBERS Final Due Date: 09/08/21 Subject: SITE WORK/ FLAT WORK CONCRETE PATCHING PROCEDURE Description: PLEASE SEE ATTACHED PDF DETAILING LARUSSO'S PATCHING PROCEDURE ALONG WITH PRODUCT DATA FOR SITE WORK FLATWORK. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 18492 | Forwarded | For Review | 2021-08-11 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-18 | Submittal Number: 03 30 00-88.0 From: CHRISTIAN ALBERS Final Due Date: 09/08/21 Subject: SITE WORK/ FLAT WORK CONCRETE PATCHING PROCEDURE Description: PLEASE SEE ATTACHED PDF DETAILING LARUSSO'S PATCHING PROCEDURE ALONG WITH PRODUCT DATA FOR SITE WORK FLATWORK. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 14574 | Review Response | Approved as Noted | 2021-08-25 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | 1. Review for finish acceptability only. Civil/Structural review required for loading / structural review off/on structure respectively. 2. Per conversation w/ Christian Albers, provide in-place mock of up patch section for acceptance of color prior to installation in other areas. 3. Maximum patch size to confirmed on case-by-case bases. Assume any full depth slab breaks, breaks over 12" in length in any direction require full slab replacement to align with general paving joint pattern. Sawcut out damaged pavements at 90degrees per manufacturer's recommendations. Do not exceed recommended depth for patching. | Info Exchange
| 18750 | Forwarded | For Review | 2021-09-01 | Populous SCA_CCA | Damon Smith (DCI Engineers); Matthew Frisby | 2021-08-25 | Submittal Number: 03 30 00-88.0 From: CHRISTIAN ALBERS Final Due Date: 09/08/21 Subject: SITE WORK/ FLAT WORK CONCRETE PATCHING PROCEDURE Description: PLEASE SEE ATTACHED PDF DETAILING LARUSSO'S PATCHING PROCEDURE ALONG WITH PRODUCT DATA FOR SITE WORK FLATWORK. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 14575 | Review Response | Not Required For Review | 2021-09-02 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous); Shaina Burris (Populous) |  | It is our understanding that the products in this submittal pertain only to sitework concrete. If this is the case, Swift and/or DCI will need to review and stamp. | Info Exchange
| 14576 | Review Response | Rejected | 2021-09-08 | Peter Stoessel | Populous SCA_CCA |  | This product is not applicable to the strength of the concrete pavement specified in 32 13 13 | Info Exchange
| 18815 | Responded and Closed | Rejected | 2021-09-08 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Colin.Saiz@mortenson.com |  | Ardex does not meet compressive strength requirements. Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: 1. Review for finish acceptability only. Civil/Structural review required for loading / structural review off/on structure respectively. 2. Per conversation w/ Christian Albers, provide in-place mock of up patch section for acceptance of color prior to installation in other areas. 3. Maximum patch size to confirmed on case-by-case bases. Assume any full depth slab breaks, breaks over 12" in length in any direction require full slab replacement to align with general paving joint pattern. Sawcut out damaged pavements at 90degrees per manufacturer's recommendations. Do not exceed recommended depth for patching. Response (Not Required For Review) from: Matt Ross (Thornton Tomasetti) Remarks: It is our understanding that the products in this submittal pertain only to sitework concrete. If this is the case, Swift and/or DCI will need to review and stamp. Response (Rejected) from: Peter Stoessel Remarks: This product is not applicable to the strength of the concrete pavement specified in 32 13 13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-11 |  | 03-30-00-88_0_Site-Work-Flat-Work-Concrete-Patching-Procedure_attachments.zip
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-11 |  | 03-30-00-88_0_Site-Work-Flat-Work-Concrete-Patching-Procedure_attachments.zip
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-11 |  | 03-30-00-88_0_Site-Work-Flat-Work-Concrete-Patching-Procedure_attachments.zip
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-08-11 |  | 03-30-00-88_0_Site-Work-Flat-Work-Concrete-Patching-Procedure_attachments.zip
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-10 02:00 |  | 03-30-00-88_0_Site-Work-Flat-Work-Concrete-Patching-Procedure_attachments.zip
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-08-11 |  | 03-30-00-88_0_Site-Work-Flat-Work-Concrete-Patching-Procedure_attachments.zip
| Review Response |  | Peter Stoessel | 1 | 2021-09-08 02:00 |  | 03-30-00-88-Site-Work-Flat-Work-Concrete-Patching-Procedure - SWIFT-DCI Response.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-08 02:00 |  | 03-30-00-88-Site-Work-Flat-Work-Concrete-Patching-Procedure - SWIFT-DCI Response_pop.pdf
03 30 00-088-00-01 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-088-00 Site Work/ Flat Work Concrete Patching Procedure | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 30 00-088-00 - 03 30 00-088-00 Site Work/ Flat Work Concrete Patching Procedure | -1 | 2021-09-22
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-08 02:00 |  | 03-30-00-88-Site-Work-Flat-Work-Concrete-Patching-Procedure - SWIFT-DCI Response_pop.pdf
03 30 00-089-00 | 03 30 00 - CAST-IN-PLACE CONCRETE | 03 30 00-089-00 Alternate Mix Design Bollards | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-14 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-09-28 | 2021-09-21 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14646 | Received | For Review | 2021-09-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-09-28 | Submittal Number: 03 30 00-89.0 From: CHRISTIAN ALBERS Final Due Date: 09/28/21 Subject: ALTERNATE MIX DESIGN BOLLARDS Description: SEE ALTERNATE MIX DESIGN FOR BOLLARDS DUE DO TRUCK DRIVER SHORTAGE WITH PREVIOUS SUPPLIERS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 18886 | Forwarded | For Review | 2021-09-14 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-09-21 | Submittal Number: 03 30 00-89.0 From: CHRISTIAN ALBERS Final Due Date: 09/28/21 Subject: ALTERNATE MIX DESIGN BOLLARDS Description: SEE ALTERNATE MIX DESIGN FOR BOLLARDS DUE DO TRUCK DRIVER SHORTAGE WITH PREVIOUS SUPPLIERS. Spec Section: 03 30 00 - CAST-IN-PLACE CONCRETE Status: OPEN | Info Exchange
| 14679 | Review Response | Approved as Noted | 2021-09-20 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Bollard MFR to review for approval. | Info Exchange
| 18931 | Responded and Closed | Approved as Noted | 2021-09-21 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Bollard MFR to review for approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-14 |  | 03 30 00 - 89 - Alternate Mix Design Bollards.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-14 |  | 03 30 00 - 89 - Alternate Mix Design Bollards.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-09-14 |  | 03 30 00 - 89 - Alternate Mix Design Bollards.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-09-21 |  | 03 30 00 - 89 - Alternate Mix Design Bollards_TT_POP.pdf
03 37 13-001-00 | 03 37 13 - SHOTCRETE | 03 37 13-001-00 Shotcrete Submittal Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-02 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-16 | 2019-08-23 | 22 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2019-08-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01963 | Received | For Review | 2019-08-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-08-16 | Submittal Number: 03 37 13-1.0 From: MIKE SOLFELT Final Due Date: 08/16/19 Subject: SHOTCRETE SUBMITTAL PACKAGE Description: MIX DESIGNS / VENDOR CERTIFICATES / PRODUCT DATA Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 03110 | Forwarded | For Review | 2019-08-03 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-12 | Submittal Number: 03 37 13-1.0 From: MIKE SOLFELT Final Due Date: 08/16/19 Subject: SHOTCRETE SUBMITTAL PACKAGE Description: MIX DESIGNS / VENDOR CERTIFICATES / PRODUCT DATA Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 02180 | Review Response | Revise and Resubmit | 2019-08-22 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Mix designs are inconsistent and deviate from spec. Please also break out admixtures not listed in spec and submit substitution request. Attached correct mix forms with resubmittal. Missing required attachments that were checked as being submitted. Gradation reports, etc. | Info Exchange
| 03382 | Responded and Closed | Revise and Resubmit | 2019-08-23 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Mix designs are inconsistent and deviate from spec. Please also break out admixtures not listed in spec and submit substitution request. Attached correct mix forms with resubmittal. Missing required attachments that were checked as being submitted. Gradation reports, etc. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-02 |  | 033713-0001-0 Mix Designs and Vendor Certs and Product data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-02 |  | 033713-0001-0 Mix Designs and Vendor Certs and Product data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-08-01 02:00 |  | 033713-0001-0 Mix Designs and Vendor Certs and Product data.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-23 02:00 |  | 033713-0001-0 Mix Designs and Vendor Certs and Product data_TT_POP combined.pdf
03 37 13-001-01 | 03 37 13 - SHOTCRETE | 03 37 13-001-01 Shotcrete Submittal Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-09-27 | 2019-10-07 | 27 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2019-10-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02378 | Received | For Review | 2019-09-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-09-27 | Submittal Number: 03 37 13-1.1 From: MIKE SOLFELT Final Due Date: 09/25/19 Subject: SHOTCRETE SUBMITTAL PACKAGE Description: MIX DESIGNS / VENDOR CERTIFICATES / PRODUCT DATA Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 03622 | Forwarded | For Review | 2019-09-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-18 | Submittal Number: 03 37 13-1.1 From: MIKE SOLFELT Final Due Date: 09/25/19 Subject: SHOTCRETE SUBMITTAL PACKAGE Description: MIX DESIGNS / VENDOR CERTIFICATES / PRODUCT DATA Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 02685 | Review Response | Approved as Noted | 2019-10-07 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 04007 | Responded and Closed | Approved as Noted | 2019-10-07 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-11 |  | 033713-0001-01 Shotcrete Submittal Package.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-11 |  | 033713-0001-01 Shotcrete Submittal Package.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-10 02:00 |  | 033713-0001-01 Shotcrete Submittal Package.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-07 02:00 |  | 033713-0001-01 Shotcrete Submittal Package_TT REVIEW_POP.pdf
03 37 13-002-00 | 03 37 13 - SHOTCRETE | 03 37 13-002-00 Shotcrete Mock-Up | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-20 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-06 08:00 | 2019-12-05 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-12-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03274 | Received | For Review | 2019-11-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-12-06 08:00 | Submittal Number: 03 37 13-2.0 From: MIKE SOLFELT Final Due Date: 12/03/19 Subject: SHOTCRETE MOCK-UP Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 04721 | Forwarded | For Review | 2019-11-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-26 | Submittal Number: 03 37 13-2.0 From: MIKE SOLFELT Final Due Date: 12/03/19 Subject: SHOTCRETE MOCK-UP Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 03512 | Review Response | Approved as Noted | 2019-12-04 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 04978 | Responded and Closed | Approved as Noted | 2019-12-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved as Noted) from: Sean McNeill (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-19 |  | 033713-0002-0 Shotcrete Panel Mock-Up.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-19 |  | 033713-0002-0 Shotcrete Panel Mock-Up.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2019-11-18 02:00 |  | 033713-0002-0 Shotcrete Panel Mock-Up.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-05 02:00 |  | 033713-0002-0 Shotcrete Panel Mock-Up_TT Review_POP.pdf
03 37 13-003-00 | 03 37 13 - SHOTCRETE | 03 37 13-003-00 South Parcel - Wet Shotcrete Submittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Closed - Void |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-19 |  | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07381 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 03 37 13-3.0 From: TYRONE THORNTON Final Due Date: 08/18/20 Subject: SOUTH PARCEL - WET SHOTCRETE SUBMITTAL Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 09836 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-12 | Submittal Number: 03 37 13-3.0 From: TYRONE THORNTON Final Due Date: 08/18/20 Subject: SOUTH PARCEL - WET SHOTCRETE SUBMITTAL Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 10353 | Closed | Void | 2020-08-19 | Josh Dobken (Populous) |  |  | Item voided per email confirmation from Tyrone Thornton and Samar Kenkre.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-05 |  | 033713-3_Wet Shotcrete Mix Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-05 |  | 033713-3_Wet Shotcrete Mix Submittal_MAM Review.pdf
03 37 13-004-00 | 03 37 13 - SHOTCRETE | 03 37 13-004-00 South Parcel - Shotcrete Certifications | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-07 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-21 | 2020-08-21 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-08-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07434 | Received | For Review | 2020-08-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-21 | Submittal Number: 03 37 13-4.0 From: TYRONE THORNTON Final Due Date: 08/19/20 Subject: SOUTH PARCEL - SHOTCRETE CERTIFICATIONS Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 09902 | Forwarded | For Review | 2020-08-06 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-13 | Submittal Number: 03 37 13-4.0 From: TYRONE THORNTON Final Due Date: 08/19/20 Subject: SOUTH PARCEL - SHOTCRETE CERTIFICATIONS Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 07663 | Review Response | No Action Taken or Required | 2020-08-21 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | RECEIVED FOR RECORD | Info Exchange
| 10208 | Responded and Closed | No Action Taken or Required | 2020-08-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Samar Kenkre (Thornton Tomasetti) Remarks: RECEIVED FOR RECORD | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | 033713-4_Shotcrete Nozzleman Certifications_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-06 |  | 033713-4_Shotcrete Nozzleman Certifications_MAM Review.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-08-05 02:00 |  | 033713-4_Shotcrete Nozzleman Certifications_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-21 02:00 |  | 033713-4_Shotcrete Nozzleman Certifications_MAM Review_TT Received FR_pop.pdf
03 37 13-006-00 | 03 37 13 - SHOTCRETE | 03 37 13-006-00 03 37 13 Shotcrete - South Parcel Shoring Shotcrete Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-28 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-11 | 2020-11-18 | 22 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09061 | Received | For Review | 2020-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-11 | Submittal Number: 03 37 13-6.0 From: TYRONE THORNTON Final Due Date: 11/10/20 Subject: 03 37 13 SHOTCRETE - SOUTH PARCEL SHORING SHOTCRETE MIX DESIGN Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 11949 | Forwarded | For Review | 2020-10-28 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-04 | Submittal Number: 03 37 13-6.0 From: TYRONE THORNTON Final Due Date: 11/10/20 Subject: 03 37 13 SHOTCRETE - SOUTH PARCEL SHORING SHOTCRETE MIX DESIGN Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 09231 | Review Response | Approved | 2020-11-02 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | No Exceptions | Info Exchange
| 12586 | Responded and Closed | Approved | 2020-11-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Sean McNeill (Thornton Tomasetti) Remarks: No Exceptions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-28 |  | 03 37 13 - South Parcel Shoring Walls Shotcrete Mix Design_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-28 |  | 03 37 13-006-0 South Parcel Shoring Walls Shotcrete Mix Design_MAM Review.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-10-28 |  | 03 37 13-006-0 South Parcel Shoring Walls Shotcrete Mix Design_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-18 02:00 |  | 03 37 13-06 - South Parcel Shoring Walls Shotcrete Mix Design_MAM Review_TT_pop.pdf
03 37 13-007-00 | 03 37 13 - SHOTCRETE | 03 37 13-007-00 03 37 13 - Tunnel Wall Shotcrete Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-20 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-08 | 2020-11-24 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-11-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09640 | Received | For Review | 2020-11-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-08 | Submittal Number: 03 37 13-7.0 From: EVAN REPPLIER Final Due Date: 12/04/20 Subject: 03 37 13 - TUNNEL WALL SHOTCRETE MIX DESIGN Description: SEATTLE CENTER ARENA TUNNEL SHOTCRETE MIX DESIGN Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 12684 | Forwarded | For Review | 2020-11-20 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-27 | Submittal Number: 03 37 13-7.0 From: EVAN REPPLIER Final Due Date: 12/04/20 Subject: 03 37 13 - TUNNEL WALL SHOTCRETE MIX DESIGN Description: SEATTLE CENTER ARENA TUNNEL SHOTCRETE MIX DESIGN Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 09732 | Review Response | Rejected | 2020-11-24 | Sean McNeill (Thornton Tomasetti) | Populous SCA_CCA |  | Rejected. | Info Exchange
| 12799 | Responded and Closed | Rejected | 2020-11-24 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Sean McNeill (Thornton Tomasetti) Remarks: Rejected. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-20 |  | 03 37 13 - South Parcel Tunnel Wall Shotcrete Mix Design_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-20 |  | 03 37 13 - South Parcel Tunnel Wall Shotcrete Mix Design_MAM Review.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-11-19 02:00 |  | 03 37 13 - South Parcel Tunnel Wall Shotcrete Mix Design_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-24 02:00 |  | 03 37 13-07 South Parcel Tunnel Wall Shotcrete Mix Design_MAM Review_TT_POP.pdf
03 37 13-007-01 | 03 37 13 - SHOTCRETE | 03 37 13-007-01 Tunnel Wall Shotcrete Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-09 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-23 | 2020-12-15 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10062 | Received | For Review | 2020-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (M.A. Mortenson Company) | 2020-12-23 | Submittal Number: 03 37 13-7.1 From: EVAN REPPLIER Final Due Date: 12/23/20 Subject: 03 37 13 - TUNNEL WALL SHOTCRETE MIX DESIGN Description: SEATTLE CENTER ARENA TUNNEL SHOTCRETE MIX DESIGN Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 13163 | Forwarded | For Review | 2020-12-09 | Tyrone Thornton (M.A. Mortenson Company) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-16 | Submittal Number: 03 37 13-7.1 From: EVAN REPPLIER Final Due Date: 12/23/20 Subject: 03 37 13 - TUNNEL WALL SHOTCRETE MIX DESIGN Description: SEATTLE CENTER ARENA TUNNEL SHOTCRETE MIX DESIGN Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 10155 | Review Response | Approved | 2020-12-14 | Sean McNeill (Thornton Tomasetti) | Tyrone Thornton (M.A. Mortenson Company) |  | No Exceptions | Info Exchange
| 13289 | Responded and Closed | Approved | 2020-12-15 | Tyrone Thornton (M.A. Mortenson Company) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-09 |  | 03 37 13 - S.P Tunnel Wall Shotcrete Mix Design_REV1_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-09 |  | 03 37 13 - S.P Tunnel Wall Shotcrete Mix Design_REV1_MAM Review.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-12-09 |  | 03 37 13 - S.P Tunnel Wall Shotcrete Mix Design_REV1_MAM Review.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2020-12-15 |  | 03 37 13-007.1 - S.P Tunnel Wall Shotcrete Mix Design_REV1_MAM_TT_POP.pdf
03 37 13-010-00 | 03 37 13 - SHOTCRETE | 03 37 13-010-00 03 37 13 - Tunnel Shotcrete Dry Mix Smoothing Layer | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-05 | Closed - Void |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-19 |  | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10445 | Received | For Review | 2021-01-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-01-19 | Submittal Number: 03 37 13-10.0 From: TYRONE THORNTON Final Due Date: 01/18/21 Subject: 03 37 13 - TUNNEL SHOTCRETE DRY MIX SMOOTHING LAYER Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 13633 | Forwarded | For Review | 2021-01-05 | Tyrone Thornton (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-12 | Submittal Number: 03 37 13-10.0 From: TYRONE THORNTON Final Due Date: 01/18/21 Subject: 03 37 13 - TUNNEL SHOTCRETE DRY MIX SMOOTHING LAYER Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 13771 | Closed | Void | 2021-01-08 | Josh Dobken (Populous) |  |  | Closed per email from Tyrone Thornton. Email attached.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-04 |  | 03 37 13 - Tunnel Shotcrete Dry Mix Smoothing Layer.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-01-04 |  | 03 37 13 - Tunnel Shotcrete Dry Mix Smoothing Layer.pdf
03 37 13-010-01 | 03 37 13 - SHOTCRETE | 03 37 13-010-01 Tunnel Shotcrete Dry Mix Smoothing Layer | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-25 | 2021-01-14 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10591 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-01-25 | Submittal Number: 03 37 13-10.1 From: TYRONE THORNTON Final Due Date: 01/22/21 Subject: 03 37 13 - TUNNEL SHOTCRETE DRY MIX SMOOTHING LAYER Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 13795 | Forwarded | For Review | 2021-01-11 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-18 | Submittal Number: 03 37 13-10.1 From: TYRONE THORNTON Final Due Date: 01/22/21 Subject: 03 37 13 - TUNNEL SHOTCRETE DRY MIX SMOOTHING LAYER Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 10705 | Review Response | Approved | 2021-01-14 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | No Exceptions | Info Exchange
| 13930 | Responded and Closed | Approved | 2021-01-14 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | 03 37 13 - Tunnel Shotcrete Dry Mix Smoothing Layer_Rev1_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-08 |  | 03 37 13 - Tunnel Shotcrete Dry Mix Smoothing Layer_Rev1_MAM Review.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-01-08 |  | 03 37 13 - Tunnel Shotcrete Dry Mix Smoothing Layer_Rev1_MAM Review.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-01-14 |  | 03 37 13 - Tunnel Shotcrete Dry Mix Smoothing Layer_Rev1_MAM_TT_POP.pdf
03 37 13-012-00 | 03 37 13 - SHOTCRETE | 03 37 13-012-00 South Parcel - Tunnel Preconstruction Shotcrete Mock-Up | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-27 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-10 | 2021-02-09 | 14 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10997 | Received | For Review | 2021-01-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-02-10 | Submittal Number: 03 37 13-12.0 From: TYRONE THORNTON Final Due Date: 02/10/21 Subject: SOUTH PARCEL - TUNNEL PRECONSTRUCTION SHOTCRETE MOCK-UP Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 14283 | Forwarded | For Review | 2021-01-27 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-03 | Submittal Number: 03 37 13-12.0 From: TYRONE THORNTON Final Due Date: 02/10/21 Subject: SOUTH PARCEL - TUNNEL PRECONSTRUCTION SHOTCRETE MOCK-UP Description: Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 11300 | Review Response | No Action Taken or Required | 2021-01-29 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Received for Record | Info Exchange
| 14648 | Responded and Closed | No Action Taken or Required | 2021-02-09 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | RECIEVED FOR RECORD. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-27 |  | 03 37 13_Tunnel Shotcrete Mock- Up.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-27 |  | 03 37 13_Tunnel Shotcrete Mock- Up.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-01-27 |  | 03 37 13_Tunnel Shotcrete Mock- Up.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-01-27 |  | 03 37 13_Tunnel Shotcrete Mock- Up.pdf
03 37 13-013-00 | 03 37 13 - SHOTCRETE | 03 37 13-013-00 South Parcel Generator Shotcrete Wall Grout Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-17 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-31 | 2021-03-24 | 8 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12073 | Received | For Review | 2021-03-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-31 | Submittal Number: 03 37 13-13.0 From: CHRISTIAN GENEROSA Final Due Date: 03/30/21 Subject: SOUTH PARCEL GENERATOR SHOTCRETE WALL GROUT PRODUCT DATA Description: GROUT PRODUCT DATA FOR SOUTH PARCEL GENERATOR SHOTCRETE WALLS. Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 15626 | Forwarded | For Review | 2021-03-17 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-24 | Submittal Number: 03 37 13-13.0 From: CHRISTIAN GENEROSA Final Due Date: 03/30/21 Subject: SOUTH PARCEL GENERATOR SHOTCRETE WALL GROUT PRODUCT DATA Description: GROUT PRODUCT DATA FOR SOUTH PARCEL GENERATOR SHOTCRETE WALLS. Spec Section: 03 37 13 - SHOTCRETE Status: OPEN | Info Exchange
| 12231 | Review Response | Approved | 2021-03-22 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | No Exceptions | Info Exchange
| 15821 | Responded and Closed | Approved | 2021-03-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Sean McNeill (Thornton Tomasetti) Remarks: No Exceptions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-16 |  | 2021-03-16 0337-0013-00 South Parcel Generator Shotcrete Wall PD_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-16 |  | 2021-03-16 0337-0013-00 South Parcel Generator Shotcrete Wall PD_MAM.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-03-15 02:00 |  | 2021-03-16 0337-0013-00 South Parcel Generator Shotcrete Wall PD_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-24 02:00 |  | 03 37 13-013 South Parcel Generator Shotcrete Wall PD_MAM_TT_POP.pdf
03 41 00-001-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-001-00 Precast Concrete - Geometry Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-14 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti) |  |  |  | 2019-10-28 | 2019-10-28 | 15 |  | Record Copies; Transfers; Submittals | 03 41 00-001-00-01 - 03 41 00-001-00 Precast Concrete - Geometry Submittal | 14 |  | 2019-10-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02758 | Received | For Review | 2019-10-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-10-28 | Submittal Number: 03 41 00-1.0 From: NATE WEINGART Final Due Date: 10/25/19 Subject: PRECAST CONCRETE - GEOMETRY SUBMITTAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 04126 | Forwarded | For Review | 2019-10-15 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-10-22 | Submittal Number: 03 41 00-1.0 From: NATE WEINGART Final Due Date: 10/25/19 Subject: PRECAST CONCRETE - GEOMETRY SUBMITTAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 04143 | Forwarded | For Review | 2019-10-16 | Todd Spangler (Populous) | Matt Ross (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) |  | Submittal Number: 03 41 00-1.0 From: NATE WEINGART Final Due Date: 10/25/19 Subject: PRECAST CONCRETE - GEOMETRY SUBMITTAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 02857 | Review Response | Approved as Noted | 2019-10-21 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | TT does not need to review again. | Info Exchange
| 02943 | Review Response | Approved as Noted/Resubmit | 2019-10-28 | Chris Minter (Populous) | Josh Dobken (Populous) |  | Nate, Need to discuss this in our next meeting. Thanks, Chris | Info Exchange
| 04319 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-28 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-14 |  | 034100-1.0 Precast Concrete - Geometry Submittal (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-10-13 02:00 |  | 034100-1.0 Precast Concrete - Geometry Submittal (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-10-14 |  | 034100-1.0 Precast Concrete - Geometry Submittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-13 02:00 |  | 034100-1.0 Precast Concrete - Geometry Submittal (MAM Review).pdf
| Review Response |  | Chris Minter (Populous) | 1 | 2019-10-28 02:00 |  | 034100-1.0 Precast Concrete - Geometry Submittal (MAM Review)_TT Reviewed_POP.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2019-10-13 02:00 |  | 034100-1.0 Precast Concrete - Geometry Submittal (MAM Review).pdf
03 41 00-001-00-01 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-001-00 Precast Concrete - Geometry Submittal | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 41 00-001-00 - 03 41 00-001-00 Precast Concrete - Geometry Submittal | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-13 02:00 |  | 034100-1.0 Precast Concrete - Geometry Submittal (MAM Review).pdf
03 41 00-002-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-002-00 Precast Concrete Finish Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-14 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-12-02 | 2019-12-03 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2019-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03188 | Received | For Review | 2019-11-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2019-12-02 | Submittal Number: 03 41 00-2.0 From: NATE WEINGART Final Due Date: 12/02/19 Subject: PRECAST CONCRETE FINISH SAMPLES Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 04618 | Forwarded | For Review | 2019-11-14 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-21 | Submittal Number: 03 41 00-2.0 From: NATE WEINGART Final Due Date: 12/02/19 Subject: PRECAST CONCRETE FINISH SAMPLES Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 04623 | Forwarded | For Review | 2019-11-14 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-11-21 | Submittal Number: 03 41 00-2.0 From: NATE WEINGART Final Due Date: 12/02/19 Subject: PRECAST CONCRETE FINISH SAMPLES Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 03450 | Review Response | Rejected | 2019-12-03 | Chris Minter (Populous) | Shaina Burris (Populous) |  | Rejected. Populous is traveling to Spokane to work with Oldcastle to develop an approvable sample. | Info Exchange
| 04925 | Responded and Closed | Rejected | 2019-12-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Response (Rejected) from: Chris Minter (Populous) Remarks: Rejected. Populous is traveling to Spokane to work with Oldcastle to develop an approvable sample. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-13 |  | 034100-2 Precast Finish Sample Photos (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-13 |  | 034100-2 Precast Finish Sample Photos (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-13 |  | 034100-2 Precast Finish Sample Photos (MAM Review).pdf
| Review Response |  | Chris Minter (Populous) | 1 | 2019-11-12 02:00 |  | 034100-2 Precast Finish Sample Photos (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-13 02:00 |  | 034100-2 Precast Finish Sample Photos (MAM Review)_POP.pdf
03 41 00-002-01 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-002-01 Precast Concrete Finish Sample Resubmittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-01-10 | 2020-01-13 | 27 | General | Record Copies; Transfers; Submittals |  | 27 |  | 2020-01-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03683 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-01-10 | Submittal Number: 03 41 00-2.1 From: NATE WEINGART Final Due Date: 01/08/20 Subject: PRECAST CONCRETE FINISH SAMPLE RESUBMITTAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 05203 | Forwarded | For Review | 2019-12-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2019-12-25 | Submittal Number: 03 41 00-2.1 From: NATE WEINGART Final Due Date: 01/08/20 Subject: PRECAST CONCRETE FINISH SAMPLE RESUBMITTAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 05461 | Responded and Closed | No Action Taken or Required | 2020-01-13 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 034100-2.1 Precast Finish Sample Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-18 |  | 034100-2.1 Precast Finish Sample Resubmittal (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-01-13 02:00 |  | 034100-2.1 Precast Finish Sample Resubmittal (MAM Review)-POP.pdf
03 41 00-003-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-003-00: Precast Shop Drawings - Lower Bowl & East/West Upper Bowl | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-04 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Matthew Farber (Thornton Tomasetti), Chris Minter (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2019-12-18 | 2019-12-20 | 17 |  | Record Copies; Transfers; Submittals | 03 41 00-003-01 - 03 41 00-003-00: Precast Shop Drawings - Lower Bowl & East/West Upper Bowl | 16 |  | 2019-12-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03515 | Received | For Review | 2019-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-12-18 | Submittal Number: 03 41 00-3.0 From: NATE WEINGART Final Due Date: 12/18/19 Subject: PRECAST SHOP DRAWINGS - LOWER BOWL & EAST/WEST UPPER BOWL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 04982 | Forwarded | For Review | 2019-12-05 | Josh Dobken (Populous) | Todd Spangler (Populous); Matthew Farber (Thornton Tomasetti); Chris Minter (Populous); Matt Ross (Thornton Tomasetti) | 2019-12-12 | Submittal Number: 03 41 00-3.0 From: NATE WEINGART Final Due Date: 12/18/19 Subject: PRECAST SHOP DRAWINGS - LOWER BOWL & EAST/WEST UPPER BOWL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 03661 | Review Response | Approved as Noted/Resubmit | 2019-12-17 | Chris Minter (Populous) | Josh Dobken (Populous) |  |  | Info Exchange
| 05211 | Sent | For Information Only | 2019-12-18 | Josh Dobken (Populous) | Nate Weingart (Mortenson Construction) |  | Nate, See attached bootleg copy of Populous' review of this submittal. We're still waiting for TT's review and will compile and send the official copy when we have it. Thanks, Josh Response (Approved as Noted/Resubmit) from: Chris Minter (Populous) Remarks: | Info Exchange
| 03718 | Review Response | Approved as Noted | 2019-12-20 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Do not need to resubmit unless confirmation notes from TT require design changes. | Info Exchange
| 05248 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Chris Minter (Populous) Remarks: Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Do not need to resubmit unless confirmation notes from TT require design changes. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-04 02:00 |  | 034100-3.0 SDs - Lower Bowl & East West Upper Bowl (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-04 02:00 |  | 034100-3.0 SDs - Lower Bowl & East West Upper Bowl (MAM Review).pdf
| Review Response |  | Chris Minter (Populous) | 1 | 2019-12-17 02:00 |  | 034100-3.0 SDs - Lower Bowl & East West Upper Bowl (MAM Review)-POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2019-12-04 02:00 |  | 034100-3.0 SDs - Lower Bowl & East West Upper Bowl (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-04 02:00 |  | 034100-3.0 SDs - Lower Bowl & East West Upper Bowl (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-20 02:00 |  | 034100-3.0 SDs - Lower Bowl & East West Upper Bowl (MAM Review)_TT Reviewed_POP.pdf
03 41 00-003-01 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-003-00: Precast Shop Drawings - Lower Bowl & East/West Upper Bowl | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 41 00-003-00 - 03 41 00-003-00: Precast Shop Drawings - Lower Bowl & East/West Upper Bowl | -1 | 2020-01-03
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-20 02:00 |  | 034100-3.0 SDs - Lower Bowl & East West Upper Bowl (MAM Review)_TT Reviewed_POP.pdf
03 41 00-004-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-004-00 Precast Shop Drawings - Suite Level, East/West Upper Concourse, North/South Upper Bowls, Architectural Wall Panels | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-24 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous) |  |  |  | 2020-03-09 | 2020-03-09 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04472 | Received | For Review | 2020-02-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-09 | Submittal Number: 03 41 00-4.0 From: NATE WEINGART Final Due Date: 03/06/20 Subject: PRECAST SHOP DRAWINGS - SUITE LEVEL, EAST/WEST UPPER CONCOURSE, NORTH/SOUTH UPPER BOWLS, ARCHITECTURAL WALL PANELS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 06165 | Forwarded | For Review | 2020-02-24 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-02 | Submittal Number: 03 41 00-4.0 From: NATE WEINGART Final Due Date: 03/06/20 Subject: PRECAST SHOP DRAWINGS - SUITE LEVEL, EAST/WEST UPPER CONCOURSE, NORTH/SOUTH UPPER BOWLS, ARCHITECTURAL WALL PANELS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 04698 | Review Response | Approved as Noted | 2020-03-05 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06459 | Forwarded | For Review | 2020-03-09 | Todd Spangler (Populous) | Chris Minter (Populous) | 2020-03-09 | Submittal Number: 03 41 00-4.0 From: NATE WEINGART Final Due Date: 03/06/20 Subject: PRECAST SHOP DRAWINGS - SUITE LEVEL, EAST/WEST UPPER CONCOURSE, NORTH/SOUTH UPPER BOWLS, ARCHITECTURAL WALL PANELS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 06460 | Sent | For Information Only | 2020-03-09 | Todd Spangler (Populous) | Nate Weingart (M.A. Mortenson Company) |  | Nate, here is a Bootleg of structural comment. | Info Exchange
| 06480 | Responded and Closed | Approved as Noted | 2020-03-09 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Nate, I approved as noted. I do want to look closer at the noted head knockers in the 3d model to finalize. If they are updated in Revisto to show these I can make a determination tomorrow. Chris | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-24 |  | 034100-4.0 SDs - Suite, EW UC, NS Upper Bowls, Stairs (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-24 |  | 034100-4.0 SDs - Suite, EW UC, NS Upper Bowls, Stairs (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-24 |  | 034100-4.0 SDs - Suite, EW UC, NS Upper Bowls, Stairs (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-02-24 |  | 034100-4.0 SDs - Suite, EW UC, NS Upper Bowls, Stairs (MAM Review).pdf
| Sent |  | Todd Spangler (Populous) | 1 | 2020-02-24 |  | 034100-4.0 SDs - Suite, EW UC, NS Upper Bowls, Stairs (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-03-05 |  | 034100-4.0 SDs_TT Reviewed.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-03-09 |  | 034100-4.0 SDs_TT Reviewed-POP REVIEWED.pdf
03 41 00-005-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-005-00: Precast Concrete Design Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-04 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Todd Spangler (Populous), Matthew Farber (Thornton Tomasetti), Tom Usher (Populous), Chris Minter (Populous), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2020-01-02 | 2019-12-20 | 17 | General | Record Copies; Transfers; Submittals |  | 16 |  | 2019-12-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03516 | Received | For Review | 2019-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-01-02 | Submittal Number: 03 41 00-5.0 From: NATE WEINGART Final Due Date: 12/18/19 Subject: PRECAST CONCRETE DESIGN CALCULATIONS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 04983 | Forwarded | For Review | 2019-12-05 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Todd Spangler (Populous); Matthew Farber (Thornton Tomasetti); Tom Usher (Populous); Chris Minter (Populous); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz... | 2019-12-12 | Submittal Number: 03 41 00-5.0 From: NATE WEINGART Final Due Date: 12/18/19 Subject: PRECAST CONCRETE DESIGN CALCULATIONS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 03719 | Review Response | Approved as Noted | 2019-12-20 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Do not need to resubmit unless confirmation notes from TT require design changes. | Info Exchange
| 05249 | Responded and Closed | Approved as Noted | 2019-12-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Do not need to resubmit unless confirmation notes from TT require design changes. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-04 02:00 |  | 034100-5.0 Precast Concrete Design Calculations (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-04 02:00 |  | 034100-5.0 Precast Concrete Design Calculations (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-04 02:00 |  | 034100-5.0 Precast Concrete Design Calculations (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-20 02:00 |  | 034100-5.0 Precast Concrete Design Calculations (MAM Review)_TT REVIEW_POP.pdf
03 41 00-005-01 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-005-01 Precast Concrete SD & Calculation Follow-Up | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-29 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-12 | 2020-02-11 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04110 | Received | For Review | 2020-01-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-02-12 | Submittal Number: 03 41 00-5.1 From: NATE WEINGART Final Due Date: 02/12/20 Subject: PRECAST CONCRETE SD & CALCULATION FOLLOW-UP Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 05714 | Forwarded | For Review | 2020-01-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-05 | Submittal Number: 03 41 00-5.1 From: NATE WEINGART Final Due Date: 02/12/20 Subject: PRECAST CONCRETE SD & CALCULATION FOLLOW-UP Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 04321 | Review Response | Approved | 2020-02-07 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Retained for record only. | Info Exchange
| 05976 | Responded and Closed | No Action Taken or Required | 2020-02-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | Retained for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-29 |  | 034100-5.1 Precast Concrete SD & Calculation Follow-Up (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-29 |  | 034100-5.1 Precast Concrete SD & Calculation Follow-Up (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-29 |  | 034100-5.1 Precast Concrete SD & Calculation Follow-Up (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-11 |  | 034100-5.1 Precast Concrete SD & Calculation Follow-Up_MAM_POP.pdf
03 41 00-006-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-006-00 Precast Full-Size Sample Drawing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Chris Minter (Populous) |  |  |  | 2019-12-02 | 2019-11-18 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03236 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-12-02 | Submittal Number: 03 41 00-6.0 From: NATE WEINGART Final Due Date: 12/03/19 Subject: PRECAST FULL-SIZE SAMPLE DRAWING Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 04676 | Forwarded | For Review | 2019-11-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Chris Minter (Populous) | 2019-11-25 | Submittal Number: 03 41 00-6.0 From: NATE WEINGART Final Due Date: 12/03/19 Subject: PRECAST FULL-SIZE SAMPLE DRAWING Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 03246 | Review Response | Approved | 2019-11-18 | Chris Minter (Populous) | Shaina Burris (Populous) |  |  | Email
| 04687 | Responded and Closed | Approved | 2019-11-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-18 |  | 034100-6.0 Precast Full-Size Sample Drawing (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-18 |  | 034100-6.0 Precast Full-Size Sample Drawing (MAM Review).pdf
| Review Response |  | Chris Minter (Populous) | 1 | 2019-11-18 02:00 |  | 034100-6.0 Precast Full-Size Sample Drawing (MAM Review)-POP.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2019-11-17 02:00 |  | 034100-6.0 Precast Full-Size Sample Drawing (MAM Review).pdf
03 41 00-007-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-007-00 Precast Concrete Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-25 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-09 | 2019-12-03 | 9 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03345 | Received | For Review | 2019-11-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-12-09 | Submittal Number: 03 41 00-7.0 From: NATE WEINGART Final Due Date: 12/09/19 Subject: PRECAST CONCRETE MIX DESIGN Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 04799 | Forwarded | For Review | 2019-11-22 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-29 | Submittal Number: 03 41 00-7.0 From: NATE WEINGART Final Due Date: 12/09/19 Subject: PRECAST CONCRETE MIX DESIGN Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 03451 | Review Response | Revise and Resubmit | 2019-12-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Refer to TT comments in submittal | Info Exchange
| 04926 | Responded and Closed | Revise and Resubmit | 2019-12-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Refer to TT comments in submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-22 |  | 034100-7.0 Precast Concrete Mix Design (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-22 |  | 034100-7.0 Precast Concrete Mix Design (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-21 02:00 |  | 034100-7.0 Precast Concrete Mix Design (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-03 02:00 |  | 034100-7.0 Precast Concrete Mix Design (MAM Review)_TT Reviewed_POP.pdf
03 41 00-007-01 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-007-01 Precast Concrete Mix Design Resubmittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-11 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-03 | 2019-12-13 | 3 | General | Record Copies; Transfers; Submittals |  | 3 |  | 2019-12-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03592 | Received | For Review | 2019-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-01-03 | Submittal Number: 03 41 00-7.1 From: NATE WEINGART Final Due Date: 01/03/20 Subject: PRECAST CONCRETE MIX DESIGN RESUBMITTAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 05073 | Forwarded | For Review | 2019-12-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-18 | Submittal Number: 03 41 00-7.1 From: NATE WEINGART Final Due Date: 01/03/20 Subject: PRECAST CONCRETE MIX DESIGN RESUBMITTAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 03631 | Review Response | Approved | 2019-12-13 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions to submittal. | Info Exchange
| 05132 | Responded and Closed | Approved | 2019-12-13 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions to submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-10 |  | 034100-7.1 Precast Concrete Mix Design Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-10 |  | 034100-7.1 Precast Concrete Mix Design Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-09 02:00 |  | 034100-7.1 Precast Concrete Mix Design Resubmittal (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-13 02:00 |  | 034100-7.1 Precast Concrete Mix Design Resubmittal (MAM Review)_TT Reviewed_POP.pdf
03 41 00-008-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-008-00 Precast Erector Welder Certifications | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-12 | 2020-10-07 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-10-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08376 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 03 41 00-8.0 From: TYLER KREN Final Due Date: 10/12/20 Subject: PRECAST ERECTOR WELDER CERTIFICATIONS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11097 | Forwarded | For Review | 2020-09-28 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-05 | Submittal Number: 03 41 00-8.0 From: TYLER KREN Final Due Date: 10/12/20 Subject: PRECAST ERECTOR WELDER CERTIFICATIONS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 08625 | Review Response | Approved as Noted | 2020-10-06 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Certification for Brian Pitts expired 8/20/20. No other exceptions. Retained for Record. | Info Exchange
| 11403 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-07 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyler Kren (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Certification for Brian Pitts expired 8/20/20. No other exceptions. Retained for Record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-28 |  | 03 41 00 - 8 Precaster Welder Certications.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-28 |  | 03 41 00 - 8 Precaster Welder Certications.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-27 02:00 |  | 03 41 00 - 8 Precaster Welder Certications.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-07 02:00 |  | 03 41 00 - 8 Precaster Welder Certications_TT REVIEW_pop.pdf
03 41 00-008-01 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-008-01 Precast Erector Welder Certifications - October | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-16 | 2020-11-02 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-11-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09150 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (M.A. Mortenson Company) | 2020-11-16 | Submittal Number: 03 41 00-8.1 From: TYLER KREN Final Due Date: 11/16/20 Subject: PRECAST ERECTOR WELDER CERTIFICATIONS - OCTOBER Description: WELDER CERTS UPDATED FOR MONTH OF OCTOBER Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 12072 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-09 | Submittal Number: 03 41 00-8.1 From: TYLER KREN Final Due Date: 11/16/20 Subject: PRECAST ERECTOR WELDER CERTIFICATIONS - OCTOBER Description: WELDER CERTS UPDATED FOR MONTH OF OCTOBER Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 09164 | Review Response | No Action Taken or Required | 2020-11-02 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Retained for Record. | Info Exchange
| 12091 | Responded and Closed | No Action Taken or Required | 2020-11-02 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Retained for Record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | 03 41 00 - 8.1 Precaster Welder Certications - October.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | 03 41 00 - 8.1 Precaster Welder Certications - October.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-02 |  | 03 41 00 - 8.1 Precaster Welder Certications - October.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-02 |  | 03 41 00 - 8.1 Precaster Welder Certications - October.pdf
03 41 00-008-02 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-008-02 Precast Erector Welder Certifications - November | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-04 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-18 | 2020-12-09 | 6 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-12-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09894 | Received | For Review | 2020-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (M.A. Mortenson Company) | 2020-12-18 | Submittal Number: 03 41 00-8.2 From: TYLER KREN Final Due Date: 12/17/20 Subject: PRECAST ERECTOR WELDER CERTIFICATIONS - NOVEMBER Description: WELDER CERTS UPDATED FOR MONTH OF NOVEMBER Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 12978 | Forwarded | For Review | 2020-12-03 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-10 | Submittal Number: 03 41 00-8.2 From: TYLER KREN Final Due Date: 12/17/20 Subject: PRECAST ERECTOR WELDER CERTIFICATIONS - NOVEMBER Description: WELDER CERTS UPDATED FOR MONTH OF NOVEMBER Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 10073 | Review Response | No Action Taken or Required | 2020-12-09 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Recieved for Record. | Info Exchange
| 13171 | Responded and Closed | No Action Taken or Required | 2020-12-09 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyler Kren (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: Recieved for Record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-03 |  | 03 41 00 - 8.2 Precaster Welder Certications - November.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-03 |  | 03 41 00 - 8.2 Precaster Welder Certications - November.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-02 02:00 |  | 03 41 00 - 8.2 Precaster Welder Certications - November.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-02 02:00 |  | 03 41 00 - 8.2 Precaster Welder Certications - November.pdf
03 41 00-009-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-009-00 Precast Concrete - Full-Size Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-14 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chris Minter (Populous) |  |  |  | 2020-01-28 | 2020-01-15 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-01-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03906 | Received | For Review | 2020-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-01-28 | Submittal Number: 03 41 00-9.0 From: NATE WEINGART Final Due Date: 01/27/20 Subject: PRECAST CONCRETE - FULL-SIZE SAMPLE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 05465 | Forwarded | For Review | 2020-01-14 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-01-21 | Submittal Number: 03 41 00-9.0 From: NATE WEINGART Final Due Date: 01/27/20 Subject: PRECAST CONCRETE - FULL-SIZE SAMPLE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 05485 | Forwarded | For Review | 2020-01-14 | Josh Dobken (Populous) | Chris Minter (Populous) | 2020-01-21 | Submittal Number: 03 41 00-9.0 From: NATE WEINGART Final Due Date: 01/27/20 Subject: PRECAST CONCRETE - FULL-SIZE SAMPLE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 05495 | Responded and Closed | Approved as Noted | 2020-01-15 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-13 |  | 034100-9.0 Precast Concrete Full-Size Sample (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-13 |  | 034100-9.0 Precast Concrete Full-Size Sample (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-12 02:00 |  | 034100-9.0 Precast Concrete Full-Size Sample (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-01-15 02:00 |  | 034100-9.0 Precast Concrete Full-Size Sample (MAM Review)-POP.pdf
03 41 00-010-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-010-00 Precast Design Calculations - Suite Level, East/West Upper Concourse & North/South Upper Bowls, Stand-Alone Stairs | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-25 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-10 | 2020-03-09 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04485 | Received | For Review | 2020-02-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-10 | Submittal Number: 03 41 00-10.0 From: STEVE WESTMAN Final Due Date: 03/06/20 Subject: PRECAST DESIGN CALCULATIONS - SUITE LEVEL, EAST/WEST UPPER CONCOURSE & NORTH/SOUTH UPPER BOWLS, STAND-ALONE STAIRS Description: PRECAST SUBMITTAL #2 Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 06179 | Forwarded | For Review | 2020-02-25 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-03 | Submittal Number: 03 41 00-10.0 From: STEVE WESTMAN Final Due Date: 03/06/20 Subject: PRECAST DESIGN CALCULATIONS - SUITE LEVEL, EAST/WEST UPPER CONCOURSE & NORTH/SOUTH UPPER BOWLS, STAND-ALONE STAIRS Description: PRECAST SUBMITTAL #2 Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 04697 | Review Response | Approved as Noted | 2020-03-05 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06458 | Responded and Closed | Approved as Noted | 2020-03-09 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and comments. | Info Exchange
| 06537 | Sent | For Construction | 2020-03-11 | Josh Dobken (Populous) | Nate Weingart (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) Remarks: See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-24 |  | 034100-10.0 Calcs - Suite, EW UC, NS Upper Bowls, Stairs (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-24 |  | 034100-10.0 Calcs - Suite, EW UC, NS Upper Bowls, Stairs (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-24 |  | 034100-10.0 Calcs - Suite, EW UC, NS Upper Bowls, Stairs (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-09 |  | 034100-10.0 Calcs - Suite, EW UC, NS Upper Bowls, Stairs_MAM_TT_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-02-23 02:00 |  | 034100-10.0 Calcs - Suite, EW UC, NS Upper Bowls, Stairs (MAM Review).pdf
03 41 00-011-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-011-00 Precast Patching Procedure & Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-27 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-12 | 2020-03-04 | 7 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-03-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04516 | Received | For Review | 2020-02-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-12 | Submittal Number: 03 41 00-11.0 From: NATE WEINGART Final Due Date: 03/12/20 Subject: PRECAST PATCHING PROCEDURE & PRODUCT DATA Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 06218 | Forwarded | For Review | 2020-02-26 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-04 | Submittal Number: 03 41 00-11.0 From: NATE WEINGART Final Due Date: 03/12/20 Subject: PRECAST PATCHING PROCEDURE & PRODUCT DATA Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 06385 | Responded and Closed | Approved | 2020-03-04 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-26 |  | 034100-11.0 Precast Patching Procedure & Product Data (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-26 |  | 034100-11.0 Precast Patching Procedure & Product Data (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-04 |  | 034100-11.0 Precast Patching Procedure & Product Data_MAM_POP.pdf
03 41 00-012-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-012-00 Precast Concrete Stair Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-25 | 2020-03-25 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-03-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04763 | Received | For Review | 2020-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-25 | Submittal Number: 03 41 00-12.0 From: NATE WEINGART Final Due Date: 03/25/20 Subject: PRECAST CONCRETE STAIR MIX DESIGN Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 06533 | Forwarded | For Review | 2020-03-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-18 | Submittal Number: 03 41 00-12.0 From: NATE WEINGART Final Due Date: 03/25/20 Subject: PRECAST CONCRETE STAIR MIX DESIGN Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 05051 | Review Response | Approved as Noted | 2020-03-25 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06873 | Responded and Closed | Approved as Noted | 2020-03-25 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 034100-12.0 Precast Concrete Stair Mix Design (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-11 |  | 034100-12.0 Precast Concrete Stair Mix Design (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-11 |  | 034100-12.0 Precast Concrete Stair Mix Design (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-25 |  | 034100-12.0 Precast Concrete Stair Mix Design_MAM_TT_POP.pdf
03 41 00-012-01 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-012-01 Precast Stair Mix Design Resubmittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-08 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-22 | 2020-04-09 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-04-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05248 | Received | For Review | 2020-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-04-22 | Submittal Number: 03 41 00-12.1 From: NATE WEINGART Final Due Date: 04/22/20 Subject: PRECAST STAIR MIX DESIGN RESUBMITTAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 07140 | Forwarded | For Review | 2020-04-08 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-15 | Submittal Number: 03 41 00-12.1 From: NATE WEINGART Final Due Date: 04/22/20 Subject: PRECAST STAIR MIX DESIGN RESUBMITTAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 05280 | Review Response | Approved | 2020-04-08 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. | Info Exchange
| 07182 | Responded and Closed | Approved | 2020-04-09 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-07 |  | 034100-12.1 Precast Stair Mix Design Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-07 |  | 034100-12.1 Precast Stair Mix Design Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-06 02:00 |  | 034100-12.1 Precast Stair Mix Design Resubmittal (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-09 02:00 |  | 034100-12.1 Precast Stair Mix Design Resubmittal (MAM Review)_TT Reviewed_pop.pdf
03 41 00-013-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-013-00 Precast Stair Finish Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-13 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chris Minter (Populous) |  |  |  | 2020-03-27 | 2020-04-02 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-04-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04812 | Received | For Review | 2020-03-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-27 | Submittal Number: 03 41 00-13.0 From: NATE WEINGART Final Due Date: 03/26/20 Subject: PRECAST STAIR FINISH SAMPLE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 06590 | Forwarded | For Review | 2020-03-13 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-03-20 | Submittal Number: 03 41 00-13.0 From: NATE WEINGART Final Due Date: 03/26/20 Subject: PRECAST STAIR FINISH SAMPLE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 06912 | Forwarded | For Review | 2020-03-27 | Josh Dobken (Populous) | Chris Minter (Populous) | 2020-03-27 | Submittal Number: 03 41 00-13.0 From: NATE WEINGART Final Due Date: 03/26/20 Subject: PRECAST STAIR FINISH SAMPLE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 07017 | Responded and Closed | Approved as Noted | 2020-04-01 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | Per Chris Minter, Monumental Stair finish is to be acid etch. All other precast stairs to be a sandblast finish. | Info Exchange
| 07036 | Reopened | Additional Information | 2020-04-02 08:50 | Josh Dobken (Populous) |  |  | Reopened due to errors sending response with Newforma.
| 07037 | Responded and Closed | Approved as Noted | 2020-04-02 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) Remarks: Per Chris Minter, Monumental Stair finish is to be acid etch. All other precast stairs to be a sandblast finish. Reopened (Additional Information) by: Josh Dobken Remarks: Reopened due to error sending response with Newforma. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-13 |  | 034100-13.0 Precast Stair Finish Sample (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-13 |  | 034100-13.0 Precast Stair Finish Sample (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-12 02:00 |  | 034100-13.0 Precast Stair Finish Sample (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-01 02:00 |  | 034100-13.0 Precast Stair Finish Sample (MAM Review)_pop.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-01 02:00 |  | 034100-13.0 Precast Stair Finish Sample (MAM Review)_pop.pdf
03 41 00-014-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-014-00 Precast Concrete Sealant Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-17 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-31 | 2020-03-17 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04875 | Received | For Review | 2020-03-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-31 | Submittal Number: 03 41 00-14.0 From: NATE WEINGART Final Due Date: 03/31/20 Subject: PRECAST CONCRETE SEALANT PRODUCT DATA Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 06662 | Forwarded | For Review | 2020-03-17 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-24 | Submittal Number: 03 41 00-14.0 From: NATE WEINGART Final Due Date: 03/31/20 Subject: PRECAST CONCRETE SEALANT PRODUCT DATA Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 06672 | Responded and Closed | Approved | 2020-03-17 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | APPROVED. CLM. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 034100-14.0 Precast Concrete Sealant Product Data (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 034100-14.0 Precast Concrete Sealant Product Data (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-03-17 |  | 034100-14.0 Precast Concrete Sealant Product Data (MAM Review)-POP.pdf
03 41 00-015-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-015-00 Precast Structural Concrete - Sealer Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-07 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous) |  |  |  | 2020-08-21 | 2020-08-28 | 22 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07436 | Received | For Review | 2020-08-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-08-21 | Submittal Number: 03 41 00-15.0 From: NATE WEINGART Final Due Date: 08/28/20 Subject: PRECAST STRUCTURAL CONCRETE - SEALER PRODUCT DATA Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 09903 | Forwarded | For Review | 2020-08-06 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-13 | Submittal Number: 03 41 00-15.0 From: NATE WEINGART Final Due Date: 08/28/20 Subject: PRECAST STRUCTURAL CONCRETE - SEALER PRODUCT DATA Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 07664 | Review Response | Approved | 2020-08-12 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. | Info Exchange
| 10062 | Forwarded | For Review | 2020-08-17 | Todd Spangler (Populous) | Chris Minter (Populous) |  | Submittal Number: 03 41 00-15.0 From: NATE WEINGART Final Due Date: 08/28/20 Subject: PRECAST STRUCTURAL CONCRETE - SEALER PRODUCT DATA Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 10398 | Responded and Closed | Approved as Noted | 2020-08-28 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | 034100-15.0 Precast Structural Concrete - Sealer Product Data (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-06 |  | 034100-15.0 Precast Structural Concrete - Sealer Product Data (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-05 02:00 |  | 034100-15.0 Precast Structural Concrete - Sealer Product Data (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-08-06 |  | 034100-15.0 Precast Structural Concrete - Sealer Product Data (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-08-12 |  | 034100-15.0 Precast Structural Concrete - Sealer Product Data (MAM Review)_TT REVIEW.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-08-28 |  | 034100-15.0 Precast Structural Concrete - Sealer Product Data (MAM Review)_TT REVIEW-POP.pdf
03 41 00-016-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-016-00 Precast Structural Concrete - Wide Joint Fix Procedure | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Aaron Brown (Populous) |  |  |  | 2020-10-09 | 2020-10-08 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08351 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-10-09 | Submittal Number: 03 41 00-16.0 From: NATE WEINGART Final Due Date: 10/09/20 Subject: PRECAST STRUCTURAL CONCRETE - WIDE JOINT FIX PROCEDURE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11064 | Forwarded | For Review | 2020-09-25 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-02 | Submittal Number: 03 41 00-16.0 From: NATE WEINGART Final Due Date: 10/09/20 Subject: PRECAST STRUCTURAL CONCRETE - WIDE JOINT FIX PROCEDURE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11099 | Forwarded | For Review | 2020-09-28 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2020-10-05 | Submittal Number: 03 41 00-16.0 From: NATE WEINGART Final Due Date: 10/09/20 Subject: PRECAST STRUCTURAL CONCRETE - WIDE JOINT FIX PROCEDURE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11255 | Forwarded | For Review | 2020-10-02 | Josh Dobken (Populous) | Aaron Brown (Populous) | 2020-10-09 | Submittal Number: 03 41 00-16.0 From: NATE WEINGART Final Due Date: 10/09/20 Subject: PRECAST STRUCTURAL CONCRETE - WIDE JOINT FIX PROCEDURE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11440 | Responded and Closed | No Action Taken or Required | 2020-10-08 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | REVIEWED. CONTRACTOR TO MOCK-UP SOLUTION. FINAL APPROVAL IS PENDING BASED ON MOCKUP. 10.08.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 034100-16.0 Precast Structural Concrete - Wide Joint Fix Procedure (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 034100-16.0 Precast Structural Concrete - Wide Joint Fix Procedure (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-24 02:00 |  | 034100-16.0 Precast Structural Concrete - Wide Joint Fix Procedure (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-24 02:00 |  | 034100-16.0 Precast Structural Concrete - Wide Joint Fix Procedure (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-08 02:00 |  | 034100-16.0 Precast Structural Concrete - Wide Joint Fix Procedure (MAM Review)_POP.pdf
03 41 00-017-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-017-00 Precast Structural Concrete - Wide Joint Fix Procedure - Option #2 - Emseal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Chris Minter (Populous), Aaron Brown (Populous) |  |  |  | 2020-10-14 | 2020-10-08 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08451 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-10-14 | Submittal Number: 03 41 00-17.0 From: NATE WEINGART Final Due Date: 10/14/20 Subject: PRECAST STRUCTURAL CONCRETE - WIDE JOINT FIX PROCEDURE - OPTION #2 - EMSEAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11192 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-07 | Submittal Number: 03 41 00-17.0 From: NATE WEINGART Final Due Date: 10/14/20 Subject: PRECAST STRUCTURAL CONCRETE - WIDE JOINT FIX PROCEDURE - OPTION #2 - EMSEAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11256 | Forwarded | For Review | 2020-10-02 | Josh Dobken (Populous) | Todd Spangler (Populous); Chris Minter (Populous); Aaron Brown (Populous) | 2020-10-09 | Submittal Number: 03 41 00-17.0 From: NATE WEINGART Final Due Date: 10/14/20 Subject: PRECAST STRUCTURAL CONCRETE - WIDE JOINT FIX PROCEDURE - OPTION #2 - EMSEAL Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11441 | Responded and Closed | No Action Taken or Required | 2020-10-08 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | REVIEWED. CONTRACTOR TO MOCK-UP SOLUTION. FINAL APPROVAL IS PENDING BASED ON MOCKUP. 10.08 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 034100-17.0 Precast Wide Joint Fix Procedure - Option #2 - Emseal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 034100-17.0 Precast Wide Joint Fix Procedure - Option #2 - Emseal (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-29 02:00 |  | 034100-17.0 Precast Wide Joint Fix Procedure - Option #2 - Emseal (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-08 02:00 |  | 034100-17.0 Precast Wide Joint Fix Procedure - Option #2 - Emseal (MAM Review)_POP.pdf
03 41 00-018-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-018-00 Precast Structural Concrete - Vomitory Wall Finish Procedure | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-01 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Aaron Brown (Populous) |  |  |  | 2020-10-15 | 2020-10-08 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08474 | Received | For Review | 2020-10-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-10-15 | Submittal Number: 03 41 00-18.0 From: NATE WEINGART Final Due Date: 10/15/20 Subject: PRECAST STRUCTURAL CONCRETE - VOMITORY WALL FINISH PROCEDURE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11218 | Forwarded | For Review | 2020-10-01 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-08 | Submittal Number: 03 41 00-18.0 From: NATE WEINGART Final Due Date: 10/15/20 Subject: PRECAST STRUCTURAL CONCRETE - VOMITORY WALL FINISH PROCEDURE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11302 | Forwarded | For Review | 2020-10-05 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Aaron Brown (Populous) | 2020-10-12 | Submittal Number: 03 41 00-18.0 From: NATE WEINGART Final Due Date: 10/15/20 Subject: PRECAST STRUCTURAL CONCRETE - VOMITORY WALL FINISH PROCEDURE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11442 | Responded and Closed | Approved | 2020-10-08 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | No exceptions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 034100-18 Precast Structural Concrete - Vomitory Wall Finish Procedure (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-01 |  | 034100-18 Precast Structural Concrete - Vomitory Wall Finish Procedure (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-30 02:00 |  | 034100-18 Precast Structural Concrete - Vomitory Wall Finish Procedure (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-08 02:00 |  | 034100-18 Precast Structural Concrete - Vomitory Wall Finish Procedure (MAM Review)_POP.pdf
03 41 00-019-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-019-00 Precast Structural Concrete - Lifting Eye Patching Products | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-02 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Aaron Brown (Populous) |  |  |  | 2020-10-16 | 2020-10-08 | 7 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08505 | Received | For Review | 2020-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-16 | Submittal Number: 03 41 00-19.0 From: NATE WEINGART Final Due Date: 10/30/20 Subject: PRECAST STRUCTURAL CONCRETE - LIFTING EYE PATCHING PRODUCTS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11251 | Forwarded | For Review | 2020-10-01 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-08 | Submittal Number: 03 41 00-19.0 From: NATE WEINGART Final Due Date: 10/30/20 Subject: PRECAST STRUCTURAL CONCRETE - LIFTING EYE PATCHING PRODUCTS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11303 | Forwarded | For Review | 2020-10-05 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Aaron Brown (Populous) | 2020-10-12 | Submittal Number: 03 41 00-19.0 From: NATE WEINGART Final Due Date: 10/30/20 Subject: PRECAST STRUCTURAL CONCRETE - LIFTING EYE PATCHING PRODUCTS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11443 | Responded and Closed | Approved | 2020-10-08 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | No exceptions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 034100-19.0 Precast Structural Concrete - Lifting Eye Patching Products (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-01 |  | 034100-19.0 Precast Structural Concrete - Lifting Eye Patching Products (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-30 02:00 |  | 034100-19.0 Precast Structural Concrete - Lifting Eye Patching Products (MAM Review).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-08 02:00 |  | 034100-19.0 Precast Structural Concrete - Lifting Eye Patching Products (MAM Review)_pop.pdf
03 41 00-020-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-020-00 Precast Structural Concrete - Tread Patching Materials & Procedure | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-06 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Aaron Brown (Populous) |  |  |  | 2020-10-20 | 2020-10-20 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08608 | Received | For Review | 2020-10-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-10-20 | Submittal Number: 03 41 00-20.0 From: NATE WEINGART Final Due Date: 10/21/20 Subject: PRECAST STRUCTURAL CONCRETE - TREAD PATCHING MATERIALS & PROCEDURE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11378 | Forwarded | For Review | 2020-10-06 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-13 | Submittal Number: 03 41 00-20.0 From: NATE WEINGART Final Due Date: 10/21/20 Subject: PRECAST STRUCTURAL CONCRETE - TREAD PATCHING MATERIALS & PROCEDURE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11391 | Forwarded | For Review | 2020-10-06 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Aaron Brown (Populous) | 2020-10-13 | Submittal Number: 03 41 00-20.0 From: NATE WEINGART Final Due Date: 10/21/20 Subject: PRECAST STRUCTURAL CONCRETE - TREAD PATCHING MATERIALS & PROCEDURE Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11748 | Responded and Closed | No Action Taken or Required | 2020-10-20 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | Reviewed. Approval is pending based on mock-up. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-06 |  | 034100-20.0 Precast Structural Concrete - Tread Patching Materials & Procedure (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-06 |  | 034100-20.0 Precast Structural Concrete - Tread Patching Materials & Procedure (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-05 02:00 |  | 034100-20.0 Precast Structural Concrete - Tread Patching Materials & Procedure (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-20 02:00 |  | 034100-20.0 Precast Structural Concrete - Tread Patching Materials & Procedure (MAM Review)_POP.pdf
03 41 00-021-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-021-00 Precast Structural Concrete - Crack Fix Criteria, Procedure, and Materials | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-08 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Aaron Brown (Populous) |  |  |  | 2020-10-22 | 2020-10-21 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-10-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08653 | Received | For Review | 2020-10-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-10-22 | Submittal Number: 03 41 00-21.0 From: NATE WEINGART Final Due Date: 10/22/20 Subject: PRECAST STRUCTURAL CONCRETE - CRACK FIX CRITERIA, PROCEDURE, AND MATERIALS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11431 | Forwarded | For Review | 2020-10-08 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2020-10-15 | Submittal Number: 03 41 00-21.0 From: NATE WEINGART Final Due Date: 10/22/20 Subject: PRECAST STRUCTURAL CONCRETE - CRACK FIX CRITERIA, PROCEDURE, AND MATERIALS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11579 | Forwarded | For Review | 2020-10-13 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Aaron Brown (Populous) | 2020-10-20 | Submittal Number: 03 41 00-21.0 From: NATE WEINGART Final Due Date: 10/22/20 Subject: PRECAST STRUCTURAL CONCRETE - CRACK FIX CRITERIA, PROCEDURE, AND MATERIALS Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11782 | Responded and Closed | No Action Taken or Required | 2020-10-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | Reviewed. Contractor to mock-up solution. Approval is pending based on mockup. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-07 02:00 |  | 034100-21.0 Precast Structural Concrete - Crack Fix Criteria Procedure and Materials (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-07 02:00 |  | 034100-21.0 Precast Structural Concrete - Crack Fix Criteria Procedure and Materials (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-07 02:00 |  | 034100-21.0 Precast Structural Concrete - Crack Fix Criteria Procedure and Materials (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-21 02:00 |  | 034100-21.0 Precast Structural Concrete - Crack Fix Criteria Procedure and Materials (MAM Review)_pop.pdf
03 41 00-022-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-022-00 Precast Structural Concrete - Additional Tread Patching Material (Back Corner Trough) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-06 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous), Josh Dobken (Populous), Aaron Brown (Populous) |  |  |  | 2020-11-20 | 2020-11-23 | 18 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-11-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09263 | Received | For Review | 2020-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-11-20 | Submittal Number: 03 41 00-22.0 From: GREG GOEBEL Final Due Date: 11/19/20 Subject: PRECAST STRUCTURAL CONCRETE - ADDITIONAL TREAD PATCHING MATERIAL (BACK CORNER TROUGH) Description: ADDITIONAL PATCHING TO BE USED AT PRECAST PLANT SPECIFICALLY FOR THE BACK CORNER TROUGH THAT RESULTED FROM FORMWORK. ORIGINAL EUCLID SPEED CRETE RED LINE PRODUCT FOUND TO HAVE HIGHER EXPANSION PROPERTIES SPECIFICALLY DURING THE WETTER FALL MONTHS OF PATCHING. EUCLID MANUFACTURE VISITED SITE AND REVIEWED PATCHING WHICH RESULTED IN SELECTION OF THIS MATERIAL FOR THE WORK BEING COMPLETED AT THE BACK CORNER TROUGH. Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 12216 | Forwarded | For Review | 2020-11-05 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-12 | Submittal Number: 03 41 00-22.0 From: GREG GOEBEL Final Due Date: 11/19/20 Subject: PRECAST STRUCTURAL CONCRETE - ADDITIONAL TREAD PATCHING MATERIAL (BACK CORNER TROUGH) Description: ADDITIONAL PATCHING TO BE USED AT PRECAST PLANT SPECIFICALLY FOR THE BACK CORNER TROUGH THAT RESULTED FROM FORMWORK. ORIGINAL EUCLID SPEED CRETE RED LINE PRODUCT FOUND TO HAVE HIGHER EXPANSION PROPERTIES SPECIFICALLY DURING THE WETTER FALL MONTHS OF PATCHING. EUCLID MANUFACTURE VISITED SITE AND REVIEWED PATCHING WHICH RESULTED IN SELECTION OF THIS MATERIAL FOR THE WORK BEING COMPLETED AT THE BACK CORNER TROUGH. Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 12229 | Forwarded | For Review | 2020-11-06 | Populous SCA_CCA | Chris Minter (Populous); Josh Dobken (Populous); Aaron Brown (Populous) | 2020-11-13 | Submittal Number: 03 41 00-22.0 From: GREG GOEBEL Final Due Date: 11/19/20 Subject: PRECAST STRUCTURAL CONCRETE - ADDITIONAL TREAD PATCHING MATERIAL (BACK CORNER TROUGH) Description: ADDITIONAL PATCHING TO BE USED AT PRECAST PLANT SPECIFICALLY FOR THE BACK CORNER TROUGH THAT RESULTED FROM FORMWORK. ORIGINAL EUCLID SPEED CRETE RED LINE PRODUCT FOUND TO HAVE HIGHER EXPANSION PROPERTIES SPECIFICALLY DURING THE WETTER FALL MONTHS OF PATCHING. EUCLID MANUFACTURE VISITED SITE AND REVIEWED PATCHING WHICH RESULTED IN SELECTION OF THIS MATERIAL FOR THE WORK BEING COMPLETED AT THE BACK CORNER TROUGH. Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 12764 | Responded and Closed | No Action Taken or Required | 2020-11-23 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Greg Goebel (M.A. Mortenson Company) |  | Reviewed. Final approval pending mockup application. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-05 |  | 034100-022-0 Precast Structural Concrete - Additional Tread Patching Material.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-05 02:00 |  | 034100-022-0 Precast Structural Concrete - Additional Tread Patching Material.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-23 02:00 |  | 034100-022-0 Precast Structural Concrete - Additional Tread Patching Material_POP.pdf
03 41 00-023-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-023-00 Cap for Unused Wi-Fi DAS Conduit Sleeves | Closed | Technology, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Michael Mazzocchi (ME Engineers), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2021-01-27 08:00 | 2021-02-03 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2021-02-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10647 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2021-01-27 08:00 | Submittal Number: 03 41 00-23.0 From: NATE WEINGART Final Due Date: 01/27/21 Subject: CAP FOR UNUSED WI-FI DAS CONDUIT SLEEVES Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 13858 | Forwarded | For Review | 2021-01-12 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-19 | Submittal Number: 03 41 00-23.0 From: NATE WEINGART Final Due Date: 01/27/21 Subject: CAP FOR UNUSED WI-FI DAS CONDUIT SLEEVES Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 13870 | Forwarded | For Review | 2021-01-12 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Michael Mazzocchi (ME Engineers) | 2021-01-19 | Submittal Number: 03 41 00-23.0 From: NATE WEINGART Final Due Date: 01/27/21 Subject: CAP FOR UNUSED WI-FI DAS CONDUIT SLEEVES Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 14418 | Forwarded | For Review | 2021-02-01 | Josh Dobken (Populous) | Tom Usher (Populous); Chris Minter (Populous) | 2021-01-27 | Submittal Number: 03 41 00-23.0 From: NATE WEINGART Final Due Date: 01/27/21 Subject: CAP FOR UNUSED WI-FI DAS CONDUIT SLEEVES Description: Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 14471 | Responded and Closed | Approved | 2021-02-03 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 034100-23.0 Cap for Unused Wi-Fi DAS Conduit Sleeves (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 034100-23.0 Cap for Unused Wi-Fi DAS Conduit Sleeves (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-11 02:00 |  | 034100-23.0 Cap for Unused Wi-Fi DAS Conduit Sleeves (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-11 02:00 |  | 034100-23.0 Cap for Unused Wi-Fi DAS Conduit Sleeves (MAM Review).pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 034100-23.0 Cap for Unused Wi-Fi DAS Conduit Sleeves (MAM Review).pdf
03 41 00-024-00 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-024-00 1st and Thomas SW Corner Precast Detention Tank | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-27 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-02-10 | 2021-02-09 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10989 | Received | For Review | 2021-01-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-02-10 | Submittal Number: 03 41 00-24.0 From: CHRISTIAN ALBERS Final Due Date: 02/09/21 Subject: 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK Description: PLEASE REVIEW THE ATTACHED SHOP DRAWINGS AND ENGINEERING CALCULATIONS FOR THE 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK. Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 14273 | Forwarded | For Review | 2021-01-27 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-03 | Submittal Number: 03 41 00-24.0 From: CHRISTIAN ALBERS Final Due Date: 02/09/21 Subject: 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK Description: PLEASE REVIEW THE ATTACHED SHOP DRAWINGS AND ENGINEERING CALCULATIONS FOR THE 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK. Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11210 | Review Response | No Action Taken or Required | 2021-02-03 | Sean McNeill (Thornton Tomasetti) | Christian Albers (Mortenson Construction) |  | Received For Record | Info Exchange
| 11211 | Review Response | Approved | 2021-02-04 | Sean McNeill (Thornton Tomasetti) | Christian Albers (Mortenson Construction) |  |  | Info Exchange
| 14611 | Forwarded | For Review | 2021-02-08 | Christian Albers (Mortenson Construction) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-02-10 | Submittal Number: 03 41 00-24.0 From: CHRISTIAN ALBERS Final Due Date: 02/09/21 Subject: 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK Description: PLEASE REVIEW THE ATTACHED SHOP DRAWINGS AND ENGINEERING CALCULATIONS FOR THE 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK. Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 11301 | Review Response | Revise and Resubmit | 2021-02-09 | Jarrett Grant (DCI Engineers) | Christian Albers (Mortenson Construction) |  | The dimensions on the product submittal do not match the dimensions specified on sheet C302 - Southwest Detention Vault Details. See attached. - J. Grant, DCI Engineers. | Info Exchange
| 14650 | Responded and Closed | Revise and Resubmit | 2021-02-09 | Christian Albers (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-26 |  | 1st and Thomas SW Corner Precast Detention Tank.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-01-26 |  | 1st and Thomas SW Corner Precast Detention Tank.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-01-26 |  | 1st and Thomas SW Corner Precast Detention Tank.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-02-04 |  | 03 41 00-024-00 1st and Thomas SW Corner Precast Detention Tank_TT.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-01-25 02:00 |  | 1st and Thomas SW Corner Precast Detention Tank.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-01-25 |  | 1st and Thomas SW Corner Precast Detention Tank.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-02-09 |  | 03 41 00-024-00 1st and Thomas SW Corner Precast Detention Tank_TT_DCI_POP.pdf
03 41 00-024-01 | 03 41 00 - PRECAST STRUCTURAL CONCRETE | 03 41 00-024-01 1st and Thomas SW Corner Precast Detention Tank | Closed | Structural, Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-10 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-03-24 | 2021-03-22 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11901 | Received | For Review | 2021-03-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-03-24 | Submittal Number: 03 41 00-24.1 From: CHRISTIAN ALBERS Final Due Date: 03/23/21 Subject: 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK Description: PLEASE REVIEW THE ATTACHED SHOP DRAWINGS AND ENGINEERING CALCULATIONS FOR THE 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK. Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE Status: OPEN | Info Exchange
| 15421 | Forwarded | For Review | 2021-03-10 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-17 | Submittal Number: 03 41 00-24.1 From: CHRISTIAN ALBERS Final Due Date: 03/23/21 Status: OPEN Subject: 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK Description: PLEASE REVIEW THE ATTACHED SHOP DRAWINGS AND ENGINEERING CALCULATIONS FOR THE 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK. Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE | Info Exchange
| 12163 | Review Response | Approved | 2021-03-10 | Franz Kogler (Thornton Tomasetti) | Tom Usher (Populous) |  | No Exceptions, see attached. Only reviewed clouded items. | Info Exchange
| 15456 | Forwarded | For Review | 2021-03-10 | Christian Albers (Mortenson Construction) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-03-17 | Submittal Number: 03 41 00-24.1 From: CHRISTIAN ALBERS Final Due Date: 03/23/21 Status: OPEN Subject: 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK Description: PLEASE REVIEW THE ATTACHED SHOP DRAWINGS AND ENGINEERING CALCULATIONS FOR THE 1ST AND THOMAS SW CORNER PRECAST DETENTION TANK. Spec Section: 03 41 00 - PRECAST STRUCTURAL CONCRETE | Info Exchange
| 12164 | Review Response | Approved | 2021-03-11 | Jarrett Grant (DCI Engineers) | Tom Usher (Populous) |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 12159 | Review Response | Approved | 2021-03-22 | Jarrett Grant (DCI Engineers) | Tom Usher (Populous) |  |  | Info Exchange
| 15741 | Responded and Closed | Approved | 2021-03-22 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved) from: Franz Kogler (Thornton Tomasetti) Remarks: No Exceptions, see attached. Only reviewed clouded items. Response (Approved) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-09 |  | 03 41 00 - 0024.1.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-03-09 |  | 03 41 00 - 0024.1.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-03-09 |  | 03 41 00 - 0024.1.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-03-08 02:00 |  | 03 41 00 - 0024.1.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-03-08 |  | 03 41 00 - 0024.1.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-03-22 |  | 03 41 00-024-01 1st & Thomas SW Corner Precast Detention Tank_TT_DCI_POP.pdf
03 45 00-001-00 | 03 45 00 - PRECAST ARCHITECTURAL CONCRETE | 03 45 00-001-00 Shop Drawings - Architectural Precast | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-17 | 2020-03-12 | 10 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-03-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04577 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 03 45 00-1.0 From: NATE WEINGART Final Due Date: 03/13/20 Subject: SHOP DRAWINGS - ARCHITECTURAL PRECAST Description: Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 06312 | Forwarded | For Review | 2020-03-02 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-09 | Submittal Number: 03 45 00-1.0 From: NATE WEINGART Final Due Date: 03/13/20 Subject: SHOP DRAWINGS - ARCHITECTURAL PRECAST Description: Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 04699 | Review Response | Approved as Noted | 2020-03-06 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06573 | Responded and Closed | Approved as Noted | 2020-03-12 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and coments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 034500-1.0 Shop Drawings - Architectural Precast (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 034500-1.0 Shop Drawings - Architectural Precast (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-02 |  | 034500-1.0 Shop Drawings - Architectural Precast (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-11 |  | 034500-1.0 Shop Drawings - Architectural Precast_MAM_TT_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-12 |  | A5-02-5 - EXTERIOR ELEVATIONS - SW MECH INTAKE & EXHAUST.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-12 |  | A5-02-6 - EXTERIOR ELEVATIONS - NW MECH INTAKE & EXHAUST.pdf
03 45 00-001-01 | 03 45 00 - PRECAST ARCHITECTURAL CONCRETE | 03 45 00-001-01 SDs - SE Snorkel Embed Modifications | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-10 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-24 | 2021-04-01 | 23 |  | Record Copies; Transfers; Submittals | 03 45 00-001-01-01 - 03 45 00-001-01 SDs - SE Snorkel Embed Modifications | 22 |  | 2021-04-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11913 | Received | For Review | 2021-03-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-03-24 | Submittal Number: 03 45 00-1.1 From: TYLER KREN Final Due Date: 03/24/21 Subject: SDS - SE SNORKEL EMBED MODIFICATIONS Description: UPDATES TO THE EMBED CONNECTIONS ON SECTIONS OF THE SE SNORKEL. Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 15436 | Forwarded | For Review | 2021-03-10 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-17 | Submittal Number: 03 45 00-1.1 From: TYLER KREN Final Due Date: 03/24/21 Subject: SDS - SE SNORKEL EMBED MODIFICATIONS Description: UPDATES TO THE EMBED CONNECTIONS ON SECTIONS OF THE SE SNORKEL. Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 15457 | Forwarded | For Review | 2021-03-10 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-17 | Submittal Number: 03 45 00-1.1 From: TYLER KREN Final Due Date: 03/24/21 Subject: SDS - SE SNORKEL EMBED MODIFICATIONS Description: UPDATES TO THE EMBED CONNECTIONS ON SECTIONS OF THE SE SNORKEL. Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 12345 | Review Response | Approved | 2021-03-31 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Josh Dobken (Populous) |  | Contractor to officially submit signed and sealed calcs for record. Arch to review. | Info Exchange
| 15993 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Contractor to officially submit signed and sealed calcs for record. Arch to review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-10 |  | 0345001.1 SE Snorkel Embed Modifications.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-10 |  | 0345001.1 SE Snorkel Embed Modifications.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-09 02:00 |  | 0345001.1 SE Snorkel Embed Modifications.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-09 |  | 0345001.1 SE Snorkel Embed Modifications.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-04-01 |  | 03 45 00-001-01 SE Snorkel Embed Modifications_TT_POP.pdf
03 45 00-001-01-01 | 03 45 00 - PRECAST ARCHITECTURAL CONCRETE | 03 45 00-001-01 SDs - SE Snorkel Embed Modifications | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 03 45 00-001-01 - 03 45 00-001-01 SDs - SE Snorkel Embed Modifications | -1 | 2021-04-15
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 03 45 00-001-01 SE Snorkel Embed Modifications_TT_POP.pdf
03 45 00-002-00 | 03 45 00 - PRECAST ARCHITECTURAL CONCRETE | 03 45 00-002-00 Design Calculations - Architectural Precast | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-02 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-16 | 2020-03-09 | 8 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04572 | Received | For Review | 2020-03-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-16 | Submittal Number: 03 45 00-2.0 From: NATE WEINGART Final Due Date: 03/13/20 Subject: DESIGN CALCULATIONS - ARCHITECTURAL PRECAST Description: Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 06305 | Forwarded | For Review | 2020-03-02 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-09 | Submittal Number: 03 45 00-2.0 From: NATE WEINGART Final Due Date: 03/13/20 Subject: DESIGN CALCULATIONS - ARCHITECTURAL PRECAST Description: Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 04696 | Review Response | Approved | 2020-03-06 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06457 | Responded and Closed | Approved | 2020-03-09 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 034500-2.0 Design Calculations - Architectural Precast (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 034500-2.0 Design Calculations - Architectural Precast (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-02 |  | 034500-2.0 Design Calculations - Architectural Precast (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-09 |  | 034500-2.0 Design Calculations - Architectural Precast_MAM_TT_POP.pdf
03 45 00-003-00 | 03 45 00 - PRECAST ARCHITECTURAL CONCRETE | 03 45 00-003-00 Architectural Precast - Range Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-13 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-03-27 | 2020-03-25 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-03-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04813 | Received | For Review | 2020-03-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-27 | Submittal Number: 03 45 00-3.0 From: NATE WEINGART Final Due Date: 03/26/20 Subject: ARCHITECTURAL PRECAST - RANGE SAMPLES Description: Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 06591 | Forwarded | For Review | 2020-03-13 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-03-20 | Submittal Number: 03 45 00-3.0 From: NATE WEINGART Final Due Date: 03/26/20 Subject: ARCHITECTURAL PRECAST - RANGE SAMPLES Description: Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 06859 | Responded and Closed | Approved as Noted | 2020-03-25 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | Clouded samples approved. Secondary approval based on large scale panels. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-13 |  | 034500-3.0 Architectural Precast Range Samples (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-13 |  | 034500-3.0 Architectural Precast Range Samples (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-13 |  | 034500-3.0 Architectural Precast Range Samples (MAM Review).pdf
03 45 00-004-00 | 03 45 00 - PRECAST ARCHITECTURAL CONCRETE | 03 45 00-004-00 Architectural Precast - Mock-up Panel Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-08 | Responded and Closed - Not Required For Review |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-22 | 2020-04-09 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-04-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05249 | Received | For Review | 2020-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-04-22 | Submittal Number: 03 45 00-4.0 From: NATE WEINGART Final Due Date: 04/22/20 Subject: ARCHITECTURAL PRECAST - MOCK-UP PANEL DRAWINGS Description: Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 07141 | Forwarded | For Review | 2020-04-08 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-04-15 | Submittal Number: 03 45 00-4.0 From: NATE WEINGART Final Due Date: 04/22/20 Subject: ARCHITECTURAL PRECAST - MOCK-UP PANEL DRAWINGS Description: Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 07189 | Responded and Closed | Not Required For Review | 2020-04-09 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-07 |  | 034500-4.0 Architectural Precast - Mock-up Panel Drawings (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-07 |  | 034500-4.0 Architectural Precast - Mock-up Panel Drawings (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-09 |  | 034500-4.0 Architectural Precast - Mock-up Panel Drawings_MAM_POP.pdf
03 45 00-005-00 | 03 45 00 - PRECAST ARCHITECTURAL CONCRETE | 03 45 00-005-00 Architectural Precast - Informational Submittals | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-17 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-01 | 2020-06-22 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-06-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06447 | Received | For Review | 2020-06-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-07-01 | Submittal Number: 03 45 00-5.0 From: NATE WEINGART Final Due Date: 07/01/20 Subject: ARCHITECTURAL PRECAST - INFORMATIONAL SUBMITTALS Description: QUALIFICATION DATA MATERIAL CERTIFICATES MATERIAL TEST REPORTS PRECONSTRUCTION TEST REPORTS SOURCE QUALITY-CONTROL TEST REPORTS FIELD QUALITY-CONTROL (AND SPECIAL INSPECTION) TEST REPORTS Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 08693 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-24 | Submittal Number: 03 45 00-5.0 From: NATE WEINGART Final Due Date: 07/01/20 Subject: ARCHITECTURAL PRECAST - INFORMATIONAL SUBMITTALS Description: QUALIFICATION DATA MATERIAL CERTIFICATES MATERIAL TEST REPORTS PRECONSTRUCTION TEST REPORTS SOURCE QUALITY-CONTROL TEST REPORTS FIELD QUALITY-CONTROL (AND SPECIAL INSPECTION) TEST REPORTS Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 06535 | Review Response | Not Required For Review | 2020-06-17 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Received for Record. | Info Exchange
| 08793 | Responded and Closed | Approved | 2020-06-22 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 034500-5.0 Architectural Precast - Informational Submittals (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 034500-5.0 Architectural Precast - Informational Submittals (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-17 |  | 034500-5.0 Architectural Precast - Informational Submittals (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-22 |  | 034500-5.0 Architectural Precast - Informational Submittals-MAM_POP.pdf
03 45 00-006-00 | 03 45 00 - PRECAST ARCHITECTURAL CONCRETE | 03 45 00-006-00 Architectural Precast - Full-Size Mock-up | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-24 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Geoff Cheong, Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-07 | 2020-08-04 | 12 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07138 | Received | For Review | 2020-07-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-07 | Submittal Number: 03 45 00-6.0 From: NATE WEINGART Final Due Date: 08/07/20 Subject: ARCHITECTURAL PRECAST - FULL-SIZE MOCK-UP Description: Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 09533 | Forwarded | For Review | 2020-07-25 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-03 | Submittal Number: 03 45 00-6.0 From: NATE WEINGART Final Due Date: 08/07/20 Subject: ARCHITECTURAL PRECAST - FULL-SIZE MOCK-UP Description: Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 09549 | Forwarded | For Review | 2020-07-27 | Populous SCA_CCA | Todd Spangler (Populous); Geoff Cheong; Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-03 | Submittal Number: 03 45 00-6.0 From: NATE WEINGART Final Due Date: 08/07/20 Subject: ARCHITECTURAL PRECAST - FULL-SIZE MOCK-UP Description: Spec Section: 03 45 00 - PRECAST ARCHITECTURAL CONCRETE Status: OPEN | Info Exchange
| 09784 | Responded and Closed | Approved as Noted | 2020-08-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | SEE ATTACHED SITE VISIT REPORT FOR COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-24 |  | 034500-6.0 Architectural Precast - Full-Size Mock-up (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-24 |  | 034500-6.0 Architectural Precast - Full-Size Mock-up (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-23 02:00 |  | 034500-6.0 Architectural Precast - Full-Size Mock-up (MAM Review).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-04 |  | 034500-6.0 Architectural Precast - Full-Size Mock-up-MAM_POP.pdf
03 53 00-001-00 | 03 53 00 - CONCRETE TOPPING | 03 53 00-001-00 Flatwork Diamond Dowel Locations | Closed | Structural, Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-29 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers), Omar Masood (DCI Engineers) |  |  |  | 2021-07-14 07:00 | 2021-07-12 | 14 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-07-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13701 | Received | For Review | 2021-06-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-07-14 07:00 | Submittal Number: 03 53 00-1.0 From: CHRISTIAN ALBERS Final Due Date: 07/13/21 Subject: FLATWORK DIAMOND DOWEL LOCATIONS Description: Spec Section: 03 53 00 - CONCRETE TOPPING Status: OPEN | Info Exchange
| 17736 | Forwarded | For Review | 2021-06-29 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-06 | Submittal Number: 03 53 00-1.0 From: CHRISTIAN ALBERS Final Due Date: 07/13/21 Subject: FLATWORK DIAMOND DOWEL LOCATIONS Description: Spec Section: 03 53 00 - CONCRETE TOPPING Status: OPEN | Info Exchange
| 17866 | Forwarded | For Review | 2021-07-06 | Christian Albers (Mortenson Construction) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers); Omar Masood | 2021-07-13 | Submittal Number: 03 53 00-1.0 From: CHRISTIAN ALBERS Final Due Date: 07/13/21 Subject: FLATWORK DIAMOND DOWEL LOCATIONS Description: Spec Section: 03 53 00 - CONCRETE TOPPING Status: OPEN | Info Exchange
| 13889 | Review Response | Approved as Noted | 2021-07-09 | Omar Masood (DCI Engineers) | Tom Usher (Populous); Josh Dobken (Populous) |  | Courtyards 6 & 7 were already constructed before material submittal was shown to DCI for review and approval. DCI takes no exception to the submittal as shown. -O. Masood, DCI Engineers | Info Exchange
| 17983 | Responded and Closed | Approved as Noted | 2021-07-12 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Omar Masood (DCI Engineers) Remarks: Courtyards 6 & 7 were already constructed before material submittal was shown to DCI for review and approval. DCI takes no exception to the submittal as shown. -O. Masood, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-29 |  | 03 53 00 - 01 - Flatwork Diamond Dowel Locations.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-29 |  | 03 53 00 - 01 - Flatwork Diamond Dowel Locations.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-28 02:00 |  | 03 53 00 - 01 - Flatwork Diamond Dowel Locations.pdf
| Review Response |  | Omar Masood (DCI Engineers) | 1 | 2021-06-28 02:00 |  | 03 53 00 - 01 - Flatwork Diamond Dowel Locations.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-12 02:00 |  | 03 53 00 - 01 - Flatwork Diamond Dowel Locations - DCI Response_POP.pdf
04 20 00-001-00 | 04 20 00 - UNIT MASONRY | 04 20 00-001-00 UNIT MASONRY - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-01-10 | 2020-01-14 | 28 | General | Record Copies; Transfers; Submittals |  | 28 |  | 2020-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03671 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-01-10 | Submittal Number: 04 20 00-1.0 From: BROOKE BURCHAM Final Due Date: 01/03/20 Subject: UNIT MASONRY - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT INDICATED. THIS IS TO ALSO INCLUDE LEED DOCUMENTATION, QUALIFICATION DATA, CERTIFICATES, MIX DESIGN, COLD/HOT WEATHER PROCEDURES, Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 05191 | Forwarded | For Review | 2019-12-18 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-12-25 | Submittal Number: 04 20 00-1.0 From: BROOKE BURCHAM Final Due Date: 01/03/20 Subject: UNIT MASONRY - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT INDICATED. THIS IS TO ALSO INCLUDE LEED DOCUMENTATION, QUALIFICATION DATA, CERTIFICATES, MIX DESIGN, COLD/HOT WEATHER PROCEDURES, Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 05478 | Responded and Closed | Approved | 2020-01-14 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 042000-0001-0 Unit Masonry Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-18 |  | 042000-0001-0 Unit Masonry Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-01-14 |  | 042000-0001-0 Unit Masonry Product Data_POP.pdf
04 20 00-003-00 | 04 20 00 - UNIT MASONRY | 04 20 00-003-00 UNIT MASONRY - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-01-10 | 2020-01-14 | 28 | General | Record Copies; Transfers; Submittals |  | 28 |  | 2020-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03684 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2020-01-10 | Submittal Number: 04 20 00-3.0 From: BROOKE BURCHAM Final Due Date: 01/03/20 Subject: UNIT MASONRY - SAMPLES Description: SAMPLES FOR INITIAL SELECTION : - 1. DECORATIVE CMUS, IN THE FORM OF SMALL-SCALE UNITS. 2. CONCRETE FACING BRICK, IN THE FORM OF SMALL-SCALE UNITS. 3. COLORED MORTAR. 4. WEEP HOLES/VENTS. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 05204 | Forwarded | For Review | 2019-12-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-12-25 | Submittal Number: 04 20 00-3.0 From: BROOKE BURCHAM Final Due Date: 01/03/20 Subject: UNIT MASONRY - SAMPLES Description: SAMPLES FOR INITIAL SELECTION : - 1. DECORATIVE CMUS, IN THE FORM OF SMALL-SCALE UNITS. 2. CONCRETE FACING BRICK, IN THE FORM OF SMALL-SCALE UNITS. 3. COLORED MORTAR. 4. WEEP HOLES/VENTS. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 05477 | Responded and Closed | Approved | 2020-01-14 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 042000-0003-0 Unit Masonry Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-18 |  | 042000-0003-0 Unit Masonry Samples.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-01-14 |  | 042000-0003-0 Unit Masonry Samples_POP.pdf
04 20 00-004-00 | 04 20 00 - UNIT MASONRY | 04 20 00-004-00 UNIT MASONRY - Rebar Shop Drawings Area A & Area C | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-09 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-06-23 | 2020-07-01 | 23 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-07-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06282 | Received | For Review | 2020-06-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-06-23 | Submittal Number: 04 20 00-4.0 From: YE ZHANG Final Due Date: 07/20/20 Subject: UNIT MASONRY - REBAR SHOP DRAWINGS AREA A & AREA C Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08477 | Forwarded | For Review | 2020-06-09 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-16 | Submittal Number: 04 20 00-4.0 From: YE ZHANG Final Due Date: 07/20/20 Subject: UNIT MASONRY - REBAR SHOP DRAWINGS AREA A & AREA C Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08621 | Forwarded | For Review | 2020-06-15 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McN... | 2020-06-22 | Submittal Number: 04 20 00-4.0 From: YE ZHANG Final Due Date: 07/20/20 Subject: UNIT MASONRY - REBAR SHOP DRAWINGS AREA A & AREA C Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 06722 | Review Response | Approved as Noted | 2020-06-29 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 09045 | Responded and Closed | Approved as Noted | 2020-07-01 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-09 |  | 042000-4-0 - Masonry Area A and Area C Shop Drawings_06.08.20_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-09 |  | 042000-4-0 - Masonry Area A and Area C Shop Drawings_06.08.20_MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-08 02:00 |  | 042000-4-0 - Masonry Area A and Area C Shop Drawings_06.08.20_MAM Review.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-08 |  | 042000-4-0 - Masonry Area A and Area C Shop Drawings_06.08.20_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-06-29 |  | 042000-4-0 - Masonry Area A and Area C Shop Drawings_06.08.20_MAM Review_TT Reviewed.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-07-01 |  | 042000-4-0 - Masonry Area A and Area C Shop Drawings_06.08.20_MAM Review_TT Reviewed-POP.pdf
04 20 00-005-00 | 04 20 00 - UNIT MASONRY | 04 20 00-005-00 UNIT MASONRY - Shop Drawings Area D | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-16 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Raymond Chou (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-06-30 | 2020-06-19 | 4 |  | Record Copies; Transfers; Submittals | 04 20 00-005-01 - 04 20 00-005-00 UNIT MASONRY - Shop Drawings Area D | 2 |  | 2020-06-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06421 | Received | For Review | 2020-06-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-06-30 | Submittal Number: 04 20 00-5.0 From: YE ZHANG Final Due Date: 06/19/20 Subject: UNIT MASONRY - SHOP DRAWINGS AREA D Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08650 | Forwarded | For Review | 2020-06-16 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-23 | Submittal Number: 04 20 00-5.0 From: YE ZHANG Final Due Date: 06/19/20 Subject: UNIT MASONRY - SHOP DRAWINGS AREA D Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08656 | Forwarded | For Review | 2020-06-16 | Shaina Burris (Populous) | Raymond Chou (Thornton Tomasetti) | 2020-06-23 | Submittal Number: 04 20 00-5.0 From: YE ZHANG Final Due Date: 06/19/20 Subject: UNIT MASONRY - SHOP DRAWINGS AREA D Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08701 | Forwarded | For Review | 2020-06-17 | Josh Dobken (Populous) | Matt Ross (Thornton Tomasetti) | 2020-06-24 | Submittal Number: 04 20 00-5.0 From: YE ZHANG Final Due Date: 06/19/20 Subject: UNIT MASONRY - SHOP DRAWINGS AREA D Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 06525 | Review Response | Not Required For Review | 2020-06-17 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Geometry submittal not required for review by Structural Engineer. Populous to review. | Info Exchange
| 08782 | Responded and Closed | Revise and Resubmit | 2020-06-19 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (M.A. Mortenson Company) |  | Quad D walls reviewed only. Resubmit with corrections noted. Some walls missing in locker room area. Issues relating to lintel reinforcement at overhead doors to be addressed in resubmittal and through RFI 2650. Overlays in drawings were misaligned, and some elevation tags were on top of dimensions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-15 |  | 042000 - Masonry Area D Shop Drawings_05.26.20_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-15 |  | 042000 - Masonry Area D Shop Drawings_05.26.20_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-15 |  | 042000 - Masonry Area D Shop Drawings_05.26.20_MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-14 02:00 |  | 042000 - Masonry Area D Shop Drawings_05.26.20_MAM Review.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-14 02:00 |  | 042000 - Masonry Area D Shop Drawings_05.26.20_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-19 02:00 |  | 042000 - Masonry Area D Shop Drawings_05.26.20_MAM Review_pop UPDATE.pdf
04 20 00-005-01 | 04 20 00 - UNIT MASONRY | 04 20 00-005-00 UNIT MASONRY - Shop Drawings Area D | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 04 20 00-005-00 - 04 20 00-005-00 UNIT MASONRY - Shop Drawings Area D | -1 | 2020-07-03
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-19 02:00 |  | 042000 - Masonry Area D Shop Drawings_05.26.20_MAM Review_pop UPDATE.pdf
04 20 00-006-00 | 04 20 00 - UNIT MASONRY | 04 20 00-006-00 UNIT MASONRY - Rebar Shop Drawings Area B,D,E | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-02 | 2020-07-31 | 44 |  | Record Copies; Transfers; Submittals | 04 20 00-006-00-01 - 04 20 00-006-00 UNIT MASONRY - Rebar Shop Drawings Area B,D,E | 21 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06483 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 04 20 00-6.0 From: YE ZHANG Final Due Date: 07/01/20 Subject: UNIT MASONRY - REBAR SHOP DRAWINGS AREA B,D,E Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08733 | Forwarded | For Review | 2020-06-18 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-25 | Submittal Number: 04 20 00-6.0 From: YE ZHANG Final Due Date: 07/01/20 Subject: UNIT MASONRY - REBAR SHOP DRAWINGS AREA B,D,E Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 07088 | Review Response | Approved as Noted/Resubmit | 2020-07-08 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached marked up submittal RNC/SDK ¦ TT ¦ 7/8/2020 | Info Exchange
| 09718 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-31 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. CM TO COORDINATE WALL LAYOUTS AND TOP OF WALLS WITH CD'S AND SUBMITTALS 04 20 00-008, 04 20 00-012 2. SEE TT ADDITIONAL COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 |  | 04 20 00-006-0 Event Level B,D,E Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-18 |  | 04 20 00-006-0 Event Level B,D,E Shop Drawings.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-06-18 |  | 04 20 00-006-0 Event Level B,D,E Shop Drawings.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-31 |  | 04 20 00-006-0 Event Level B,D,E Shop Drawings_TT REVIEW_POP.pdf
04 20 00-006-00-01 | 04 20 00 - UNIT MASONRY | 04 20 00-006-00 UNIT MASONRY - Rebar Shop Drawings Area B,D,E | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 04 20 00-006-00 - 04 20 00-006-00 UNIT MASONRY - Rebar Shop Drawings Area B,D,E | -1 | 2020-08-14
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-31 |  | 04 20 00-006-0 Event Level B,D,E Shop Drawings_TT REVIEW_POP.pdf
04 20 00-007-00 | 04 20 00 - UNIT MASONRY | 04 20 00-007-00 UNIT MASONRY - Rebar Shop Drawings Event Level Area F | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-29 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-14 07:00 | 2020-07-31 | 33 |  | Record Copies; Transfers; Submittals | 04 20 00-007-00-01 - 04 20 00-007-00 UNIT MASONRY - Rebar Shop Drawings Event Level Area F | 16 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06644 | Received | For Review | 2020-06-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-14 07:00 | Submittal Number: 04 20 00-7.0 From: TYRONE THORNTON Final Due Date: 07/10/20 Subject: UNIT MASONRY - REBAR SHOP DRAWINGS EVENT LEVEL AREA F Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08949 | Forwarded | For Review | 2020-06-27 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... |  | Submittal Number: 04 20 00-7.0 From: TYRONE THORNTON Final Due Date: 07/10/20 Subject: UNIT MASONRY - REBAR SHOP DRAWINGS EVENT LEVEL AREA F Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 07297 | Review Response | Approved as Noted | 2020-07-12 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | See marked up submittal | Info Exchange
| 09719 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-31 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. CM TO COORDINATE WALL LAYOUTS AND TOP OF WALLS WITH CD'S AND SUBMITTALS 04 20 00-008, 04 20 00-012 2. SEE TT ADDITIONAL COMMENTS 3. RESUBMIT WITH CM REVIEW STAMP | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-27 |  | 04 20 00-7.0 S21348-TR #06 Drawings_Event Level Area F.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-27 |  | 04 20 00-7.0 S21348-TR #06 Drawings_Event Level Area F.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-06-27 |  | 04 20 00-7.0 S21348-TR #06 Drawings_Event Level Area F.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-31 |  | 04 20 00-7.0 S21348-TR #06 Drawings_Event Level Area F_TT REVIEW_POP.pdf
04 20 00-007-00-01 | 04 20 00 - UNIT MASONRY | 04 20 00-007-00 UNIT MASONRY - Rebar Shop Drawings Event Level Area F | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 04 20 00-007-00 - 04 20 00-007-00 UNIT MASONRY - Rebar Shop Drawings Event Level Area F | -1 | 2020-08-14
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-31 |  | 04 20 00-7.0 S21348-TR #06 Drawings_Event Level Area F_TT REVIEW_POP.pdf
04 20 00-008-00 | 04 20 00 - UNIT MASONRY | 04 20 00-008-00 UNIT MASONRY - Shop Drawings Event Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-29 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-14 07:00 | 2020-07-10 | 12 |  | Record Copies; Transfers; Submittals | 04 20 00-008-00-01 - 04 20 00-008-00 UNIT MASONRY - Shop Drawings Event Level | 14 |  | 2020-07-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06645 | Received | For Review | 2020-06-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-07-14 07:00 | Submittal Number: 04 20 00-8.0 From: YE ZHANG Final Due Date: 07/10/20 Subject: UNIT MASONRY - SHOP DRAWINGS EVENT LEVEL Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08950 | Forwarded | For Review | 2020-06-27 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-06 | Submittal Number: 04 20 00-8.0 From: YE ZHANG Final Due Date: 07/10/20 Subject: UNIT MASONRY - SHOP DRAWINGS EVENT LEVEL Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 09250 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-10 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (M.A. Mortenson Company) |  | COORDINATE ALL DOOR ROUGH OPENINGS WITH DOOR SCHEDULE, TYPICAL. COORDINATE MEP PENETRATIONS WITH OTHERS DOORS TO BE ALIGNED ACCORDING TO A0-01, U.N.O. COORDINATE CONSTRUCTION JOINT PER SPEC 042000 SECTION 3.10. ADDITIONAL CONSTRUCTION JOINT REQUIREMENTS SHOWN IN DETAILS 1, 2 / S6-02 RESUBMIT: UPDATE PER CURRENT PLANS AS NOTED. PROVIDE SPECIAL SHAPE DETAILS. REFER TO S6-01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-26 |  | 042000-0008-0 Unit Masonry Shop Drawings Event Level.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-26 |  | 042000-0008-0 Unit Masonry Shop Drawings Event Level.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-10 02:00 |  | 042000-0008-0 Unit Masonry Shop Drawings Event Level_POP.pdf
04 20 00-008-00-01 | 04 20 00 - UNIT MASONRY | 04 20 00-008-00 UNIT MASONRY - Shop Drawings Event Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 04 20 00-008-00 - 04 20 00-008-00 UNIT MASONRY - Shop Drawings Event Level | -1 | 2020-07-24
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-10 02:00 |  | 042000-0008-0 Unit Masonry Shop Drawings Event Level_POP.pdf
04 20 00-009-00 | 04 20 00 - UNIT MASONRY | 04 20 00-009-00 UNIT MASONRY - Rebar Shop Drawings Mechanical Mezzanine Area E & F | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-29 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-14 07:00 | 2020-07-31 | 33 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06646 | Received | For Review | 2020-06-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-14 07:00 | Submittal Number: 04 20 00-9.0 From: TYRONE THORNTON Final Due Date: 07/24/20 Subject: UNIT MASONRY - REBAR SHOP DRAWINGS MECHANICAL MEZZANINE AREA E & F Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08951 | Forwarded | For Review | 2020-06-27 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-06 | Submittal Number: 04 20 00-9.0 From: TYRONE THORNTON Final Due Date: 07/24/20 Subject: UNIT MASONRY - REBAR SHOP DRAWINGS MECHANICAL MEZZANINE AREA E & F Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 07298 | Review Response | Approved as Noted | 2020-07-15 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09720 | Responded and Closed | Approved as Noted | 2020-07-31 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. CM TO COORDINATE WALL LAYOUTS AND TOP OF WALLS WITH CD'S AND SUBMITTAL 04 20 00-11 2. SEE TT ADDITIONAL COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-27 |  | 04 20 00-9-0 S21348-TR #07 Drawings_Mech Mezz Area E_F_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-27 |  | 04 20 00-9-0 S21348-TR #07 Drawings_Mech Mezz Area E_F_MAM Reviewed.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-06-27 |  | 04 20 00-9-0 S21348-TR #07 Drawings_Mech Mezz Area E_F_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-31 |  | 04 20 00-9-0 S21348-TR #07 Drawings_Mech Mezz Area E_F_MAM Reviewed_TT REVIEW_POP.pdf
04 20 00-010-00 | 04 20 00 - UNIT MASONRY | 04 20 00-010-00 UNIT MASONRY - Rebar Shop Drawings Suite & Upper Concourse Areas E & F | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-30 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-15 07:00 | 2020-07-31 | 32 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06670 | Received | For Review | 2020-06-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-15 07:00 | Submittal Number: 04 20 00-10.0 From: TYRONE THORNTON Final Due Date: 07/13/20 Subject: TAL #04 20 00-10 REVISION 0: UNIT MASONRY - REBAR SHOP DRAWINGS SUITE & UPPER CONCOURSE ARESA E & F Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08984 | Forwarded | For Review | 2020-06-30 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-07 | Submittal Number: 04 20 00-10.0 From: TYRONE THORNTON Final Due Date: 07/13/20 Subject: TAL #04 20 00-10 REVISION 0: UNIT MASONRY - REBAR SHOP DRAWINGS SUITE & UPPER CONCOURSE ARESA E & F Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 07299 | Review Response | Approved as Noted | 2020-07-16 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09721 | Responded and Closed | Approved as Noted | 2020-07-31 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. CM TO COORDINATE WALL LAYOUTS AND TOP OF WALLS WITH CD'S AND SUBMITTAL 04 20 00-11 2. SEE TT ADDITIONAL COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-30 |  | 04 20 00-010-0 S21348-TR #08 Drawings_Suite-Upper Concourse Area E_F_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-30 |  | 04 20 00-010-0 S21348-TR #08 Drawings_Suite-Upper Concourse Area E_F_MAM Reviewed.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-06-30 |  | 04 20 00-010-0 S21348-TR #08 Drawings_Suite-Upper Concourse Area E_F_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-31 |  | 04 20 00-010-0 S21348-TR #08 Drawings_Suite-Upper Concourse Area E_F_MAM Reviewed_TT REVIEW_POP.pdf
04 20 00-011-00 | 04 20 00 - UNIT MASONRY | 04 20 00-011-00 UNIT MASONRY - Shop Drawings Mech Mezz, Main Con, Suite & Upper Con Levels | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-13 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-27 | 2020-07-31 | 19 |  | Record Copies; Transfers; Submittals | 04 20 00-011-00-01 - 04 20 00-011-00 UNIT MASONRY - Shop Drawings Mech Mezz, Main Con, Suite & Upper Con Levels | 19 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06914 | Received | For Review | 2020-07-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-07-27 | Submittal Number: 04 20 00-11.0 From: YE ZHANG Final Due Date: 08/24/20 Subject: UNIT MASONRY - SHOP DRAWINGS MECH MEZZ, MAIN CON, SUITE & UPPER CON LEVELS Description: UNIT MASONRY - SHOP DRAWINGS MECH MEZZ, MAIN CON, SUITE & UPPER CON LEVELS Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 09256 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-20 | Submittal Number: 04 20 00-11.0 From: YE ZHANG Final Due Date: 08/24/20 Subject: UNIT MASONRY - SHOP DRAWINGS MECH MEZZ, MAIN CON, SUITE & UPPER CON LEVELS Description: UNIT MASONRY - SHOP DRAWINGS MECH MEZZ, MAIN CON, SUITE & UPPER CON LEVELS Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 09723 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-31 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE NOTES FOR AREAS TO RESUBMIT | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-10 |  | 042000-0011-0 Unit Masonry Shop Drawings Mech Mezz Main Con Suite & Upper Con Levels.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-10 |  | 042000-0011-0 Unit Masonry Shop Drawings Mech Mezz Main Con Suite & Upper Con Levels.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-31 |  | 042000-0011-0 Unit Masonry Shop Drawings Mech Mezz Main Con Suite & Upper Con Levels_POP.pdf
04 20 00-011-00-01 | 04 20 00 - UNIT MASONRY | 04 20 00-011-00 UNIT MASONRY - Shop Drawings Mech Mezz, Main Con, Suite & Upper Con Levels | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 04 20 00-011-00 - 04 20 00-011-00 UNIT MASONRY - Shop Drawings Mech Mezz, Main Con, Suite & Upper Con Levels | -1 | 2020-08-14
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-31 |  | 042000-0011-0 Unit Masonry Shop Drawings Mech Mezz Main Con Suite & Upper Con Levels_POP.pdf
04 20 00-012-00 | 04 20 00 - UNIT MASONRY | 04 20 00-012-00 Event Level CMU Layout | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-22 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-05 | 2020-07-31 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07101 | Received | For Review | 2020-07-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2020-08-05 | Received from: AI Assistant Mortenson Procore Connector (Mortenson Construction) Description: Submittal Number: 04 20 00-12.0 From: YE ZHANG Final Due Date: 08/05/20 Subject: TAL #04 20 00-12 REVISION 0: UNIT MASONRY - Event Level CMU Layout Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 09489 | Forwarded | For Review | 2020-07-22 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-29 | Received from: AI Assistant Mortenson Procore Connector (Mortenson Construction) Description: Submittal Number: 04 20 00-12.0 From: YE ZHANG Final Due Date: 08/05/20 Subject: TAL #04 20 00-12 REVISION 0: UNIT MASONRY - Event Level CMU Layout Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 09724 | Responded and Closed | Approved as Noted | 2020-07-31 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. SUBMITTAL SHOULD HAVE BEEN ISSUED AS 04 20 00-008-01 2.APPEARS COMMENTS ON SUBMITTAL 04 20 00-008 HAVE BEEN COMPLETED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-22 |  | 042000-0012-0-EventLevelCMULayout-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-22 |  | 042000-0012-0-EventLevelCMULayout-MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-07-31 |  | 042000-0012-0-EventLevelCMULayout-MAM_POP.pdf
04 20 00-013-00 | 04 20 00 - UNIT MASONRY | 04 20 00-013-00 UNIT MASONRY - Shop Drawing Updates Through CCD-075 | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-06 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-20 | 2020-10-28 | 23 |  | Record Copies; Transfers; Submittals | 04 20 00-013-00-01 - 04 20 00-013-00 UNIT MASONRY - Shop Drawing Updates Through CCD-075 | 15 |  | 2020-10-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08596 | Received | For Review | 2020-10-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-10-20 | Submittal Number: 04 20 00-13.0 From: JOHN SHARP Final Due Date: 10/09/20 Subject: UNIT MASONRY - SHOP DRAWING UPDATES THROUGH CCD-075 Description: WE ARE CURRENTLY WAITING FOR MINOR REVISIONS DUE TO RFI 2650.2 THOSE REVISIONS WILL BE SUBMITTED WHEN ALL QUESTIONS ARE ANSWERED AND THE DRAWINGS ARE UPDATED. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 11360 | Forwarded | For Review | 2020-10-06 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-13 | Submittal Number: 04 20 00-13.0 From: JOHN SHARP Final Due Date: 10/09/20 Subject: UNIT MASONRY - SHOP DRAWING UPDATES THROUGH CCD-075 Description: WE ARE CURRENTLY WAITING FOR MINOR REVISIONS DUE TO RFI 2650.2 THOSE REVISIONS WILL BE SUBMITTED WHEN ALL QUESTIONS ARE ANSWERED AND THE DRAWINGS ARE UPDATED. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 11522 | Forwarded | For Review | 2020-10-12 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2020-10-19 | Submittal Number: 04 20 00-13.0 From: JOHN SHARP Final Due Date: 10/09/20 Subject: UNIT MASONRY - SHOP DRAWING UPDATES THROUGH CCD-075 Description: WE ARE CURRENTLY WAITING FOR MINOR REVISIONS DUE TO RFI 2650.2 THOSE REVISIONS WILL BE SUBMITTED WHEN ALL QUESTIONS ARE ANSWERED AND THE DRAWINGS ARE UPDATED. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08915 | Review Response | Revise and Resubmit | 2020-10-20 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Control Joint spacing to follow NCMA TEK 10-2D Table 1 Guidelines. Please revise and resubmit CJ layout for EOR review and approval. | Info Exchange
| 11979 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-28 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 12011 | Sent | For Information Only | 2020-10-29 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Ye Zhang (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-06 |  | 042000-0013-0-CMUShopUpdatesCCD075-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-06 |  | 042000-0013-0-CMUShopUpdatesCCD075-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-05 02:00 |  | 042000-0013-0-CMUShopUpdatesCCD075-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-05 |  | 042000-0013-0-CMUShopUpdatesCCD075-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-10-28 |  | 042000-0013-0-CMUShopUpdatesCCD075-MAM_TT REVIEW-POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-10-05 02:00 |  | 042000-0013-0-CMUShopUpdatesCCD075-MAM.pdf
04 20 00-013-00-01 | 04 20 00 - UNIT MASONRY | 04 20 00-013-00 UNIT MASONRY - Shop Drawing Updates Through CCD-075 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 04 20 00-013-00 - 04 20 00-013-00 UNIT MASONRY - Shop Drawing Updates Through CCD-075 | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-28 |  | 042000-0013-0-CMUShopUpdatesCCD075-MAM_TT REVIEW-POP.pdf
04 20 00-014-00 | 04 20 00 - UNIT MASONRY | 04 20 00-014-00 Masonry Rebar Areas A,B,C,D CCD 075 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-01 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-15 | 2020-10-21 | 21 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-10-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08465 | Received | For Review | 2020-10-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Bradley Pawelczyk (Mortenson Construction) | 2020-10-15 | Submittal Number: 04 20 00-14.0 From: BRADLEY PAWELCZYK Final Due Date: 10/14/20 Subject: MASONRY REBAR AREAS A,B,C,D CCD 075 Description: MASONRY REBAR CCD 075 REVISIONS Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 11206 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-07 | Submittal Number: 04 20 00-14.0 From: BRADLEY PAWELCZYK Final Due Date: 10/14/20 Subject: MASONRY REBAR AREAS A,B,C,D CCD 075 Description: MASONRY REBAR CCD 075 REVISIONS Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 08911 | Review Response | Revise and Resubmit | 2020-10-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Control Joint spacing to be revised throughout to follow NCMA TEK 10-2D Table 1. Populous to advise on TT comments in submittal. Please only resubmit Quad D for approval. | Info Exchange
| 11780 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-21 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 04 20 00-14.0 S21348-TR #09 & Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 04 20 00-14.0 S21348-TR #09 & Drawings.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-30 |  | 04 20 00-14.0 S21348-TR #09 & Drawings.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-10-21 |  | 04 20 00-14.0 S21348-TR #09 & Drawings_TT REVIEW-POP.pdf
04 20 00-014-01 | 04 20 00 - UNIT MASONRY | 04 20 00-014-01 Masonry Rebar Event Level Areas A,B Only | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-09 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-23 | 2020-12-02 | 24 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09284 | Received | For Review | 2020-11-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Bradley Pawelczyk (Mortenson Construction) | 2020-11-23 | Submittal Number: 04 20 00-14.1 From: BRADLEY PAWELCZYK Final Due Date: 10/14/20 Subject: MASONRY REBAR EVENT LEVEL AREAS A,B ONLY Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 12243 | Forwarded | For Review | 2020-11-06 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-13 | Submittal Number: 04 20 00-14.1 From: BRADLEY PAWELCZYK Final Due Date: 10/14/20 Subject: MASONRY REBAR EVENT LEVEL AREAS A,B ONLY Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 09759 | Review Response | Approved as Noted | 2020-11-20 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 12907 | Responded and Closed | Approved as Noted | 2020-12-02 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | Rebar_Event-100_A-B.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | Rebar_Event-100_A-B.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-06 |  | Rebar_Event-100_A-B.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-02 |  | 04 20 00-014-01 Rebar_Event-100_A-B_TT REVIEW-POP.pdf
04 20 00-015-00 | 04 20 00 - UNIT MASONRY | 04 20 00-015-00 Unit Masonry Mock-up Review - For Record Only | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-14 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-03 | 2020-11-02 | 20 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-11-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08897 | Received | For Review | 2020-10-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Bradley Pawelczyk (Mortenson Construction) | 2020-11-03 | Submittal Number: 04 20 00-15.0 From: BRADLEY PAWELCZYK Final Due Date: 11/10/20 Subject: UNIT MASONRY MOCK-UP REVIEW - FOR RECORD ONLY Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 11770 | Forwarded | For Review | 2020-10-21 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-28 | Submittal Number: 04 20 00-15.0 From: BRADLEY PAWELCZYK Final Due Date: 11/10/20 Subject: UNIT MASONRY MOCK-UP REVIEW - FOR RECORD ONLY Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 12094 | Responded and Closed | Approved | 2020-11-02 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-20 |  | Anchor Letter.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-20 |  | CPA Masonry Wall Mock Up.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-20 |  | Transmittal_RFI - RFI 3356 (Responded and Closed).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-20 |  | Anchor Letter.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-20 |  | CPA Masonry Wall Mock Up.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-20 |  | Transmittal_RFI - RFI 3356 (Responded and Closed).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-02 |  | CPA Masonry Wall Mock Up-POP.pdf
04 20 00-016-00 | 04 20 00 - UNIT MASONRY | 04 20 00-016-00 Masonry Rebar Level 300 EF | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-04 | 2020-11-23 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-11-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09525 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Bradley Pawelczyk (Mortenson Construction) | 2020-12-04 | Submittal Number: 04 20 00-16.0 From: BRADLEY PAWELCZYK Final Due Date: 12/01/20 Subject: MASONRY REBAR LEVEL 300 EF Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 12545 | Forwarded | For Review | 2020-11-18 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-25 | Submittal Number: 04 20 00-16.0 From: BRADLEY PAWELCZYK Final Due Date: 12/01/20 Subject: MASONRY REBAR LEVEL 300 EF Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 09686 | Review Response | Approved as Noted | 2020-11-18 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 12740 | Responded and Closed | Approved as Noted | 2020-11-23 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | Masonry Rebar Shop Drawings Area EF Main Concourse.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | Masonry Rebar Shop Drawings Area EF Main Concourse.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-11-17 |  | Masonry Rebar Shop Drawings Area EF Main Concourse.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-23 |  | 04 20 00-16.0 Masonry Rebar Shop Drawings Area EF Main Concourse_TT_POP.pdf
04 20 00-017-00 | 04 20 00 - UNIT MASONRY | 04 20 00-017-00 Masonry - Product Data - Fine Grout, Type S Mortar | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-29 08:00 | 2021-01-25 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-01-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10712 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Bradley Pawelczyk (Mortenson Construction) | 2021-01-29 08:00 | Submittal Number: 04 20 00-17.0 From: BRADLEY PAWELCZYK Final Due Date: 01/28/21 Subject: MASONRY - PRODUCT DATA - FINE GROUT, TYPE S MORTAR Description: DUE TO A SHUTDOWN AT THE PLANT THAT THEY HAVE BEEN RECEIVING THEIR MORTAR AND GROUT, THE HENSON COMPANY HAS PROVIDED NEW SUBMITTALS FOR MORTAR AND GROUT. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 13934 | Forwarded | For Review | 2021-01-14 | Bradley Pawelczyk (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-21 | Submittal Number: 04 20 00-17.0 From: BRADLEY PAWELCZYK Final Due Date: 01/28/21 Subject: MASONRY - PRODUCT DATA - FINE GROUT, TYPE S MORTAR Description: DUE TO A SHUTDOWN AT THE PLANT THAT THEY HAVE BEEN RECEIVING THEIR MORTAR AND GROUT, THE HENSON COMPANY HAS PROVIDED NEW SUBMITTALS FOR MORTAR AND GROUT. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 14206 | Responded and Closed | Approved | 2021-01-25 | Bradley Pawelczyk (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | fine grout submittal.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | Type S mortar submittal 2020.pdf
| Forwarded |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-01-14 |  | fine grout submittal.pdf
| Forwarded |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-01-14 |  | Type S mortar submittal 2020.pdf
| Responded and Closed |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-01-25 |  | fine grout submittal-POP.pdf
| Responded and Closed |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-01-25 |  | Type S mortar submittal 2020-POP.pdf
04 20 00-018-00 | 04 20 00 - UNIT MASONRY | 04 20 00-018-00 Masonry Rebar Northwest Mechanical Intake | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-11 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-25 | 2021-03-26 | 44 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11327 | Received | For Review | 2021-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Bradley Pawelczyk (Mortenson Construction) | 2021-02-25 | Submittal Number: 04 20 00-18.0 From: BRADLEY PAWELCZYK Final Due Date: 02/24/21 Subject: MASONRY REBAR NORTHWEST MECHANICAL INTAKE Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 14686 | Forwarded | For Review | 2021-02-11 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-02-18 | Submittal Number: 04 20 00-18.0 From: BRADLEY PAWELCZYK Final Due Date: 02/24/21 Subject: MASONRY REBAR NORTHWEST MECHANICAL INTAKE Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 11459 | Review Response | Approved as Noted | 2021-02-16 | Matt Ross (Thornton Tomasetti) | Chad Francis (Populous) |  | Arch to review dimensions. | Info Exchange
| 15843 | Responded and Closed | Approved as Noted | 2021-03-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 15910 | Sent | For Information Only | 2021-03-29 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-10 |  | 04 20 00-18 Masonry Rebar Northwest Snorkel.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-10 |  | 04 20 00-18 Masonry Rebar Northwest Snorkel.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-10 |  | 04 20 00-18 Masonry Rebar Northwest Snorkel.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-03-26 |  | 04 20 00-18 Masonry Rebar Northwest Snorkel_TT_POP.pdf
| Sent |  | Todd Spangler (Populous) | 1 | 2021-02-10 |  | 04 20 00-18 Masonry Rebar Northwest Snorkel.pdf
04 20 00-019-00 | 04 20 00 - UNIT MASONRY | 04 20 00-019-00 Masonry - Product Data - Self Consolidating Grout | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-17 | Review Response - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2021-03-03 | 2021-02-23 | 7 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-02-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11507 | Received | For Review | 2021-02-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Bradley Pawelczyk (Mortenson Construction) | 2021-03-03 | Submittal Number: 04 20 00-19.0 From: BRADLEY PAWELCZYK Final Due Date: 03/03/21 Subject: MASONRY - PRODUCT DATA - SELF CONSOLIDATING GROUT Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 14901 | Forwarded | For Review | 2021-02-17 | Bradley Pawelczyk (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-24 | Submittal Number: 04 20 00-19.0 From: BRADLEY PAWELCZYK Final Due Date: 03/03/21 Subject: MASONRY - PRODUCT DATA - SELF CONSOLIDATING GROUT Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15034 | Forwarded | For Review | 2021-02-23 | Bradley Pawelczyk (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti) | 2021-03-02 | Submittal Number: 04 20 00-19.0 From: BRADLEY PAWELCZYK Final Due Date: 03/03/21 Subject: MASONRY - PRODUCT DATA - SELF CONSOLIDATING GROUT Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15039 | Responded and Closed | Approved | 2021-02-23 | Bradley Pawelczyk (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 11632 | Review Response | Approved | 2021-02-24 | Sean McNeill (Thornton Tomasetti) | Bradley Pawelczyk (Mortenson Construction) |  | No Exceptions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-17 |  | 042000-19 High Strength Grout Mix - 810078A.pdf
| Forwarded |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-02-17 |  | 042000-19 High Strength Grout Mix - 810078A.pdf
| Forwarded |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-02-16 02:00 |  | 042000-19 High Strength Grout Mix - 810078A.pdf
| Responded and Closed |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-02-23 |  | 042000-19 High Strength Grout Mix - 810078A-POP.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-02-16 02:00 |  | 042000-19 High Strength Grout Mix - 810078A.pdf
04 20 00-020-00 | 04 20 00 - UNIT MASONRY | 04 20 00-020-00 UNIT MASONRY - Shop drawings - RFI 3580 Additional NE Snorkel Wall | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-23 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-09 | 2021-03-08 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11595 | Received | For Review | 2021-02-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Bradley Pawelczyk (Mortenson Construction) | 2021-03-09 | Submittal Number: 04 20 00-20.0 From: BRADLEY PAWELCZYK Final Due Date: 03/08/21 Subject: UNIT MASONRY - SHOP DRAWINGS - RFI 3580 ADDITIONAL NE SNORKEL WALL Description: SHOP DRAWINGS FOR NEW CMU WALL THAT WAS REVISED IN RFI 3580 FROM 8" CONCRETE WALL TO CMU. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15023 | Forwarded | For Review | 2021-02-22 | Bradley Pawelczyk (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-01 | Submittal Number: 04 20 00-20.0 From: BRADLEY PAWELCZYK Final Due Date: 03/08/21 Subject: UNIT MASONRY - SHOP DRAWINGS - RFI 3580 ADDITIONAL NE SNORKEL WALL Description: SHOP DRAWINGS FOR NEW CMU WALL THAT WAS REVISED IN RFI 3580 FROM 8" CONCRETE WALL TO CMU. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15349 | Responded and Closed | Approved as Noted | 2021-03-08 | Bradley Pawelczyk (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-22 |  | 042000-20 Unit Masonry RFI 3580.pdf
| Forwarded |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-02-22 |  | 042000-20 Unit Masonry RFI 3580.pdf
| Responded and Closed |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-03-08 |  | 04 20 00-20 Unit Masonry RFI 3580_POP.pdf
04 20 00-021-00 | 04 20 00 - UNIT MASONRY | 04 20 00-021-00 UNIT MASONRY - Product Data - Type S Mortar with Integral Water Repellent | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-23 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-09 | 2021-03-03 | 9 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11596 | Received | For Review | 2021-02-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Bradley Pawelczyk (Mortenson Construction) | 2021-03-09 | Submittal Number: 04 20 00-21.0 From: BRADLEY PAWELCZYK Final Due Date: 03/08/21 Subject: UNIT MASONRY - PRODUCT DATA - TYPE S MORTAR WITH INTEGRAL WATER REPELLENT Description: WATER REPELLENT CONCRETE MASONRY UNITS TO BE USED AT MECHANICAL SHAFTS IN THE GARAGE. THESE WILL REMAIN PARTIALLY EXPOSED DURING CONSTRUCTION PHASE. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15024 | Forwarded | For Review | 2021-02-22 | Bradley Pawelczyk (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-01 | Submittal Number: 04 20 00-21.0 From: BRADLEY PAWELCZYK Final Due Date: 03/08/21 Subject: UNIT MASONRY - PRODUCT DATA - TYPE S MORTAR WITH INTEGRAL WATER REPELLENT Description: WATER REPELLENT CONCRETE MASONRY UNITS TO BE USED AT MECHANICAL SHAFTS IN THE GARAGE. THESE WILL REMAIN PARTIALLY EXPOSED DURING CONSTRUCTION PHASE. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15257 | Responded and Closed | Approved | 2021-03-03 | Bradley Pawelczyk (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-22 |  | 04 20 00-21 Product Data - Type S Mortar with Integral Water Repellent.pdf
| Forwarded |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-02-22 |  | 04 20 00-21 Product Data - Type S Mortar with Integral Water Repellent.pdf
| Responded and Closed |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-03-03 |  | 04 20 00-21 Product Data - Type S Mortar with Integral Water Repellent-POP.pdf
04 20 00-022-00 | 04 20 00 - UNIT MASONRY | 04 20 00-022-00 UNIT MASONRY - Product Data - CMU with Integral Water Repellent | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-23 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-09 | 2021-03-03 | 9 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11597 | Received | For Review | 2021-02-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Bradley Pawelczyk (Mortenson Construction) | 2021-03-09 | Submittal Number: 04 20 00-22.0 From: BRADLEY PAWELCZYK Final Due Date: 03/08/21 Subject: UNIT MASONRY - PRODUCT DATA - CMU WITH INTEGRAL WATER REPELLENT Description: CONCRETE MASONRY UNITS WITH INTEGRAL WATER REPELLENT WILL BE USED AT MECHANICAL SHAFTS IN THE GARAGE. THESE AREAS WILL REMAIN PARTIALLY EXPOSED THROUGHOUT THE DURATION OF CONSTRUCTION. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15025 | Forwarded | For Review | 2021-02-22 | Bradley Pawelczyk (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-01 | Submittal Number: 04 20 00-22.0 From: BRADLEY PAWELCZYK Final Due Date: 03/08/21 Subject: UNIT MASONRY - PRODUCT DATA - CMU WITH INTEGRAL WATER REPELLENT Description: CONCRETE MASONRY UNITS WITH INTEGRAL WATER REPELLENT WILL BE USED AT MECHANICAL SHAFTS IN THE GARAGE. THESE AREAS WILL REMAIN PARTIALLY EXPOSED THROUGHOUT THE DURATION OF CONSTRUCTION. Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15258 | Responded and Closed | Approved | 2021-03-03 | Bradley Pawelczyk (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-22 |  | 04 20 00-22 Product Data - Water Repellent CMU.pdf
| Forwarded |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-02-22 |  | 04 20 00-22 Product Data - Water Repellent CMU.pdf
| Responded and Closed |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-02-22 |  | 04 20 00-22 Product Data - Water Repellent CMU.pdf
04 20 00-023-00 | 04 20 00 - UNIT MASONRY | 04 20 00-023-00 UNIT MASONRY - Product Data - Joint Sealants | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-25 | Responded and Closed - Approved |  | Tom Usher (Populous) |  |  |  | 2021-03-11 | 2021-03-04 | 8 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-03-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11683 | Received | For Review | 2021-02-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Bradley Pawelczyk (Mortenson Construction) | 2021-03-11 | Submittal Number: 04 20 00-23.0 From: BRADLEY PAWELCZYK Final Due Date: 03/11/21 Subject: UNIT MASONRY - PRODUCT DATA - JOINT SEALANTS Description: FIRST ATTACHMENT IS FOR CMU WALLS THE RECEIVE PAINT. IT’S WHITE IN COLOR. (SPEC SECTION 07 92 00.2.5.1D) THE SECOND ATTACHMENT, DOW 790 GRAY IS FOR AREAS THAT DO NOT RECEIVE PAINT. (07 92 00.2.3.D) THIRD IS THE BACKER ROD AND LETTER OF COMPATIBILITY. (SPEC SECTION 07 92 00.2.6) Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15140 | Forwarded | For Review | 2021-03-01 | Josh Dobken (Populous) | Tom Usher (Populous) | 2021-03-08 | Submittal Number: 04 20 00-23.0 From: BRADLEY PAWELCZYK Final Due Date: 03/11/21 Subject: UNIT MASONRY - PRODUCT DATA - JOINT SEALANTS Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15269 | Responded and Closed | Approved | 2021-03-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-25 02:00 |  | 04 20 00-23 Product Data - Joint Sealants Grey.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-25 02:00 |  | 04 20 00-23 Product Data - Joint Sealants White.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-25 02:00 |  | 04 20 00-24 Product Data - Backer Rod.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-25 02:00 |  | 04 20 00-23 Product Data - Joint Sealants Grey.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-04 |  | 04 20 00-23 Product Data - Joint Sealants Grey-POP.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-04 |  | 04 20 00-23 Product Data - Joint Sealants Grey-POP2.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-04 |  | 04 20 00-23 Product Data - Joint Sealants White-POP.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-04 |  | 04 20 00-24 Product Data - Backer Rod-POP.pdf
04 20 00-024-00 | 04 20 00 - UNIT MASONRY | 04 20 00-024-00 UNIT MASONRY - Product Data - Joint Sealant WHITE | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-26 | Responded and Closed - Approved |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2021-03-12 | 2021-03-04 | 7 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-03-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11684 | Received | For Review | 2021-02-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Bradley Pawelczyk (Mortenson Construction) | 2021-03-12 | Submittal Number: 04 20 00-24.0 From: BRADLEY PAWELCZYK Final Due Date: 03/12/21 Subject: UNIT MASONRY - PRODUCT DATA - JOINT SEALANT WHITE Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15141 | Forwarded | For Review | 2021-03-01 | Josh Dobken (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2021-03-08 | Submittal Number: 04 20 00-24.0 From: BRADLEY PAWELCZYK Final Due Date: 03/12/21 Subject: UNIT MASONRY - PRODUCT DATA - JOINT SEALANT WHITE Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15270 | Responded and Closed | Approved | 2021-03-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-26 02:00 |  | 04 20 00-23 Product Data - Joint Sealants White.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-26 02:00 |  | 04 20 00-23 Product Data - Joint Sealants White.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-04 |  | 04 20 00-23 Product Data - Joint Sealants White-POP.pdf
04 20 00-025-00 | 04 20 00 - UNIT MASONRY | 04 20 00-025-00 UNIT MASONRY - Product Data - Backer Rod | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-26 | Responded and Closed - Approved |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2021-03-12 | 2021-03-04 | 7 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-03-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11685 | Received | For Review | 2021-02-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Bradley Pawelczyk (Mortenson Construction) | 2021-03-12 | Submittal Number: 04 20 00-25.0 From: BRADLEY PAWELCZYK Final Due Date: 03/12/21 Subject: UNIT MASONRY - PRODUCT DATA - BACKER ROD Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15142 | Forwarded | For Review | 2021-03-01 | Josh Dobken (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2021-03-08 | Submittal Number: 04 20 00-25.0 From: BRADLEY PAWELCZYK Final Due Date: 03/12/21 Subject: UNIT MASONRY - PRODUCT DATA - BACKER ROD Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15271 | Responded and Closed | Approved | 2021-03-04 | Bradley Pawelczyk (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-26 02:00 |  | 04 20 00-24 Product Data - Backer Rod.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-01 02:00 |  | 04 20 00-25 Product Data - Backer Rod_MAM.pdf
| Responded and Closed |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-03-04 |  | 04 20 00-24 Product Data - Backer Rod-POP.pdf
04 20 00-026-00 | 04 20 00 - UNIT MASONRY | 04 20 00-026-00 Masonry Rebar RFI 3580 NE Snorkel Additional Wall | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-24 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-08 07:00 | 2021-04-01 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-04-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12183 | Received | For Review | 2021-03-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Bradley Pawelczyk (Mortenson Construction) | 2021-04-08 07:00 | Submittal Number: 04 20 00-26.0 From: BRADLEY PAWELCZYK Final Due Date: 04/06/21 Subject: MASONRY REBAR RFI 3580 NE SNORKEL ADDITIONAL WALL Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 15769 | Forwarded | For Review | 2021-03-23 | Bradley Pawelczyk (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-30 | Submittal Number: 04 20 00-26.0 From: BRADLEY PAWELCZYK Final Due Date: 04/06/21 Subject: MASONRY REBAR RFI 3580 NE SNORKEL ADDITIONAL WALL Description: Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 12344 | Review Response | Approved as Noted | 2021-03-31 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Chris Minter (Populous) |  | Redetail wall per 8/S8-12 and SSK-0312. Arch tp review. | Info Exchange
| 15992 | Responded and Closed | Approved as Noted | 2021-04-01 | Bradley Pawelczyk (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Redetail wall per 8/S8-12 and SSK-0312. Arch tp review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-23 |  | 04 20 00-26 Masonry Rebar RFI 3580 Additional Wall NE Snorkel.pdf
| Forwarded |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-03-23 |  | 04 20 00-26 Masonry Rebar RFI 3580 Additional Wall NE Snorkel.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-23 |  | 04 20 00-26 Masonry Rebar RFI 3580 Additional Wall NE Snorkel.pdf
| Responded and Closed |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-04-01 |  | 04 20 00-26 Masonry Rebar RFI 3580 Additional Wall NE Snorkel_TT_POP.pdf
04 20 00-028-00 | 04 20 00 - UNIT MASONRY | 04 20 00-028-00 UNIT MASONRY - Product Data - ThermaFiber Rain Barrier | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-05 | 1 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12371 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Bradley Pawelczyk (Mortenson Construction) | 2021-04-19 | Submittal Number: 04 20 00-28.0 From: BRADLEY PAWELCZYK Final Due Date: 04/13/21 Subject: UNIT MASONRY - PRODUCT DATA - THERMAFIBER RAIN BARRIER Description: MINERAL WOOL BOARD AT NE AND NW SNORKELS ADJACENT TO CMU WALLS Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 16027 | Forwarded | For Review | 2021-04-01 | Bradley Pawelczyk (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 04 20 00-28.0 From: BRADLEY PAWELCZYK Final Due Date: 04/13/21 Subject: UNIT MASONRY - PRODUCT DATA - THERMAFIBER RAIN BARRIER Description: MINERAL WOOL BOARD AT NE AND NW SNORKELS ADJACENT TO CMU WALLS Spec Section: 04 20 00 - UNIT MASONRY Status: OPEN | Info Exchange
| 16060 | Responded and Closed | Approved | 2021-04-05 | Bradley Pawelczyk (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 04 20 00-28 UNIT MASONRY - Product Data - ThermaFiber Rain Barrier.pdf
| Forwarded |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-04-01 |  | 04 20 00-28 UNIT MASONRY - Product Data - ThermaFiber Rain Barrier.pdf
| Responded and Closed |  | Bradley Pawelczyk (Mortenson Construction) | 1 | 2021-04-05 |  | 04 20 00-28 UNIT MASONRY - Product Data - ThermaFiber Rain Barrier-POP.pdf
05 12 00-001-00 | 05 12 00 - STEEL | 05 12 00-001-00 Shoring Pile Schedule SD | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-02-25 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2019-03-11 | 2019-02-28 | 4 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-02-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 00969 | Received | For Review | 2019-02-25 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-03-11 |  | Email
| 01770 | Forwarded | For Review | 2019-02-26 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2019-03-05 | See attachment for shoring steel schedule shop drawings. Notes in blue are from shoring subcontractor and Mortenson comments in red. As shown in attachment, multiple comments are dependent on RFI responses. An expeditious review of these shop drawings would be highly appreciated since fabrication is scheduled to begin March 4th. | Info Exchange
| 01808 | Responded and Closed | Revise and Resubmit | 2019-02-28 | SCA_CCA@populous.com | Brent Leiter (Mortenson Construction); Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction); Josh Broussard (Mortenson Construction) |  | Please review our specification section 01 33 00 outlining proper format and resubmit. Some divisions will have further requirements for submission per their related specification sections. Josh Dobken on 2/28/2019 at 5:20 PM CST | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-02-26 |  | 19.02.15 Farwest Shop DWGS with Comments.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-02-26 |  | 19.02.15 Farwest Shop DWGS with Comments.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-02-26 |  | 19.02.15 Farwest Shop DWGS with Comments.pdf
05 12 00-001-01 | 05 12 00 - STEEL | 05 12 00-001-01 Shoring Pile Schedule SD | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-02-26 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti (Boston)) |  |  |  | 2019-03-12 | 2019-03-15 | 18 |  | Record Copies; Transfers; Submittals | 05 12 00-001-02 - 05 12 00-001-02: Shoring Pile Schedule Shop Drawing (REV 2) | 12 |  | 2019-03-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 00999 | Received | For Review | 2019-02-26 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-03-12 |  | Email
| 01819 | Forwarded | For Review | 2019-03-04 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti (Boston)) | 2019-03-05 | Resending the updated revised submittal. See their note below: See attachment for shoring steel schedule shop drawings. Notes in blue are from shoring subcontractor and Mortenson comments in red. As shown in attachment, multiple comments are dependent on RFI responses. An expeditious review of these shop drawings would be highly appreciated since fabrication is scheduled to begin March 4th. | Info Exchange
| 01050 | Review Response | Approved as Noted/Resubmit | 2019-03-15 | Benjamin Harmon (Thornton Tomasetti) | SCA_CCA@populous.com |  | See attached for our comments on the tieback pocket detail. Review of the remaining sheets in the submittal depend on the closure of various RFIs. Once all relevant RFIs are accepted and closed, please resubmit this package with that information included. | Info Exchange
| 01914 | Responded and Closed | Approved as Noted/Resubmit | 2019-03-15 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Benjamin Harmon (Thornton Tomasetti) Remarks: See attached for our comments on the tieback pocket detail. Review of the remaining sheets in the submittal depend on the closure of various RFIs. Once all relevant RFIs are accepted and closed, please resubmit this package with that information included. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-01 |  | Submittal #05 12 00-001-1 Shoring Pile Schedule Shop Drawing.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-01 |  | Submittal #05 12 00-001-1 Shoring Pile Schedule Shop Drawing.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-03-01 |  | Submittal #05 12 00-001-1 Shoring Pile Schedule Shop Drawing.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-03-15 |  | Shoring Pile detail_Markup_POP.pdf
05 12 00-001-02 | 05 12 00 - STEEL | 05 12 00-001-02: Shoring Pile Schedule Shop Drawing (REV 2) | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-03-22 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti) |  |  |  |  | 2019-03-23 | 2 |  | Record Copies; Transfers; Submittals | 05 12 00-001-01 - 05 12 00-001-01 Shoring Pile Schedule SD, 05 12 00-001-03 - 05 12 00-001-02: Shoring Pile Schedule Shop Drawing (REV 2) | 2 | 2019-03-29 | 2019-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01083 | Received | For Review | 2019-03-22 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) |  | Rev 2 and 3 will include the approval for the rest of the shop drawing. | Info Exchange
| 01947 | Forwarded | For Review | 2019-03-22 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-03-22 | Rev 2 and 3 will include the approval for the rest of the shop drawing. | Email
| 01088 | Review Response | Revise and Resubmit | 2019-03-22 | Ali Helwa (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 01089 | Review Response | Revise and Resubmit | 2019-03-23 | Matthew Farber (Thornton Tomasetti) | Josh Dobken (Populous) |  | This is TT's official response. What was sent to Mortenson changed based on utilities meeting on Thursday 3/21. | Info Exchange
| 01952 | Responded and Closed | Revise and Resubmit | 2019-03-23 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction); Greg Radom (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matthew Farber (Thornton Tomasetti) Remarks: This is TT's official response. What was sent to Mortenson changed based on utilities meeting on Thursday 3/21. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-03-22 |  | Submittal #05 12 00-001-2 Shoring Pile Schedule Shop Drawing_North wall Approval 1_POP.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-03-22 |  | Submittal #05 12 00-001-2 Shoring Pile Schedule Shop Drawing_North wall Approval 1_POP.pdf
| Review Response |  | Matthew Farber (Thornton Tomasetti) | 1 | 2019-03-22 |  | Submittal #05 12 00-001-2 Shoring Pile Schedule Shop Drawing_North wall Approval 1_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-03-23 |  | Submittal #05 12 00-001-2 Shoring Pile Schedule Shop Drawing_North wall Approval 1_AFH_POP.pdf
05 12 00-001-03 | 05 12 00 - STEEL | 05 12 00-001-02: Shoring Pile Schedule Shop Drawing (REV 2) | Expected - Overdue |  | Joe Korchemniy (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 12 00-001-02 - 05 12 00-001-02: Shoring Pile Schedule Shop Drawing (REV 2) | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-23 |  | Submittal #05 12 00-001-2 Shoring Pile Schedule Shop Drawing_North wall Approval 1_AFH_POP.pdf
05 12 00-013-00 | 05 12 00 - STEEL | 05 12 00-013-00 Welder Certs. | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-15 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-03 08:00 | 2019-12-03 | 19 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2019-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03199 | Received | For Review | 2019-11-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-12-03 08:00 | Submittal Number: 05 12 00-13.0 From: JES PELKEY Final Due Date: 11/28/19 Subject: WELDER CERTS. Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04632 | Forwarded | For Review | 2019-11-14 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-21 | Submittal Number: 05 12 00-13.0 From: JES PELKEY Final Due Date: 11/28/19 Subject: WELDER CERTS. Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03442 | Review Response | No Action Taken or Required | 2019-12-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Retained for record only. | Info Exchange
| 04915 | Responded and Closed | No Action Taken or Required | 2019-12-03 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | RECEVIED FOR RECORD ONLY | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-14 |  | 05 12 00-13.0 Welder Certs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-14 |  | 05 12 00-13.0 Welder Certs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-14 |  | 05 12 00-13.0 Welder Certs-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-12-03 |  | 05 12 00-13.0 Welder Certs-MAM_POP.pdf
05 12 00-013-01 | 05 12 00 - STEEL | 05 12 00-013-01 Welder Certs. - Jan 2020 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-15 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-29 | 2020-01-15 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-01-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03922 | Received | For Review | 2020-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-01-29 | Submittal Number: 05 12 00-13.1 From: RYAN CROOKSTON Final Due Date: 01/28/20 Subject: WELDER CERTS. - JAN 2020 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05486 | Forwarded | For Review | 2020-01-15 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-22 | Submittal Number: 05 12 00-13.1 From: RYAN CROOKSTON Final Due Date: 01/28/20 Subject: WELDER CERTS. - JAN 2020 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03923 | Review Response | Approved as Noted/Resubmit | 2020-01-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Welder Certification for Dion Yirka is expired. Please resubmit valid certification for record. | Info Exchange
| 05490 | Responded and Closed | Approved as Noted/Resubmit | 2020-01-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Welder Certification for Dion Yirka is expired. Please resubmit valid certification for record. | Info Exchange
| 05994 | Sent | For Information Only | 2020-02-12 | Josh Dobken (Populous) | Ryan Crookston (Mortenson Construction) |  | Responded and Closed (Approved as Noted/Resubmit) to: Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) Remarks: Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Welder Certification for Dion Yirka is expired. Please resubmit valid certification for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-14 |  | 05 12 00-13.1 Jan 2020 WABO Certs (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-14 |  | 05 12 00-13.1 Jan 2020 WABO Certs (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-13 02:00 |  | 05 12 00-13.1 Jan 2020 WABO Certs (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-15 02:00 |  | 05 12 00-13.1 Jan 2020 WABO Certs (MAM Review)_TT REVIEW_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-01-13 02:00 |  | 05 12 00-13.1 Jan 2020 WABO Certs (MAM Review).pdf
05 12 00-013-02 | 05 12 00 - STEEL | 05 12 00-013-02 Welder Certs. - March 2020 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-10 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-24 | 2020-03-23 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04743 | Received | For Review | 2020-03-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-03-24 | Submittal Number: 05 12 00-13.2 From: RYAN CROOKSTON Final Due Date: 03/24/20 Subject: WELDER CERTS. - MARCH 2020 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06515 | Forwarded | For Review | 2020-03-10 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-17 | Submittal Number: 05 12 00-13.2 From: RYAN CROOKSTON Final Due Date: 03/24/20 Subject: WELDER CERTS. - MARCH 2020 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04971 | Review Response | No Action Taken or Required | 2020-03-19 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Retained for Record. | Info Exchange
| 06779 | Responded and Closed | No Action Taken or Required | 2020-03-23 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Retained for Record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-10 |  | 05 12 00-13.2 March 2020 Welder Certs (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-10 |  | 05 12 00-13.2 March 2020 Welder Certs (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-10 |  | 05 12 00-13.2 March 2020 Welder Certs (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-23 |  | 05 12 00-13.2 March 2020 Welder Certs MAM_POP.pdf
05 12 00-013-03 | 05 12 00 - STEEL | 05 12 00-013-03 Welder Certs. - April 2020 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-29 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-13 | 2020-05-04 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05618 | Received | For Review | 2020-04-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-05-13 | Submittal Number: 05 12 00-13.3 From: RYAN CROOKSTON Final Due Date: 05/14/20 Subject: WELDER CERTS. - APRIL 2020 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07614 | Forwarded | For Review | 2020-04-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-06 | Submittal Number: 05 12 00-13.3 From: RYAN CROOKSTON Final Due Date: 05/14/20 Subject: WELDER CERTS. - APRIL 2020 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05696 | Review Response | Approved as Noted | 2020-04-29 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Confirm all expired certifications found in submittal will be renewed within grace period as noted. Retained for record only. | Info Exchange
| 07709 | Responded and Closed | Approved as Noted | 2020-05-04 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Confirm all expired certifications found in submittal will be renewed within grace period as noted. Retained for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-28 |  | 05 12 00-13.3 April 2020 Welder Certs (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-28 |  | 05 12 00-13.3 April 2020 Welder Certs (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-28 |  | 05 12 00-13.3 April 2020 Welder Certs (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-28 |  | 05 12 00-13.3 April 2020 Welder Certs (MAM Review).pdf
05 12 00-013-04 | 05 12 00 - STEEL | 05 12 00-013-04 Welder Certs. - June 2020 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-10 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-24 | 2020-06-15 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06323 | Received | For Review | 2020-06-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-06-24 | Submittal Number: 05 12 00-13.4 From: RYAN CROOKSTON Final Due Date: 06/24/20 Subject: WELDER CERTS. - JUNE 2020 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08528 | Forwarded | For Review | 2020-06-10 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-17 | Submittal Number: 05 12 00-13.4 From: RYAN CROOKSTON Final Due Date: 06/24/20 Subject: WELDER CERTS. - JUNE 2020 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06403 | Review Response | No Action Taken or Required | 2020-06-11 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | No exceptions. Retained for Record. | Info Exchange
| 08620 | Responded and Closed | No Action Taken or Required | 2020-06-15 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: No exceptions. Retained for Record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-10 |  | 05 12 00-13.4 - June 2020 Welder Certs (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-10 |  | 05 12 00-13.4 - June 2020 Welder Certs (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-09 02:00 |  | 05 12 00-13.4 - June 2020 Welder Certs (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-09 02:00 |  | 05 12 00-13.4 - June 2020 Welder Certs (MAM Review).pdf
05 12 00-013-05 | 05 12 00 - STEEL | 05 12 00-013-05 Welder Certs. - July 2020 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-24 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-07 | 2020-07-31 | 8 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07140 | Received | For Review | 2020-07-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-07 | Submittal Number: 05 12 00-13.5 From: RYAN CROOKSTON Final Due Date: 08/07/20 Subject: WELDER CERTS. - JULY 2020 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09535 | Forwarded | For Review | 2020-07-25 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-03 | Submittal Number: 05 12 00-13.5 From: RYAN CROOKSTON Final Due Date: 08/07/20 Subject: WELDER CERTS. - JULY 2020 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07279 | Review Response | Approved as Noted | 2020-07-27 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Several of the certifications included have expired on or before July 1, 2020. Please include up to date certifications. | Info Exchange
| 09699 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-31 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Several of the certifications included have expired on or before July 1, 2020. Please include up to date certifications. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-24 |  | WABO Welder Certs. - July 2020 (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-24 |  | 05 12 00-13.5 WABO Welder Certs. - July 2020 (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-24 |  | 05 12 00-13.5 WABO Welder Certs. - July 2020 (MAM Review).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-31 |  | 05 12 00-13.5 WABO Welder Certs. - July 2020 (MAM Review)_TT_POP.pdf
05 12 00-013-06 | 05 12 00 - STEEL | 05 12 00-013-06 Welder Certs. - August 2020 (Up to 08/19/2020) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-20 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-03 | 2020-08-20 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07623 | Received | For Review | 2020-08-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-09-03 | Submittal Number: 05 12 00-13.6 From: RYAN CROOKSTON Final Due Date: 09/02/20 Subject: WELDER CERTS. - AUGUST 2020 (UP TO 08/19/2020) Description: CERTIFICATIONS UP TO 08/19/2020 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 10152 | Forwarded | For Review | 2020-08-19 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-26 | Submittal Number: 05 12 00-13.6 From: RYAN CROOKSTON Final Due Date: 09/02/20 Subject: WELDER CERTS. - AUGUST 2020 (UP TO 08/19/2020) Description: CERTIFICATIONS UP TO 08/19/2020 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07643 | Review Response | Approved as Noted | 2020-08-20 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Note: there are a few certifications that are expired. One certification expired in April as noted in submittal. | Info Exchange
| 10184 | Responded and Closed | Approved as Noted | 2020-08-20 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Note: there are a few certifications that are expired. One certification expired in April as noted in submittal. | Info Exchange
| 10701 | Sent | For Information Only | 2020-09-10 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Note: there are a few certifications that are expired. One certification expired in April as noted in submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-19 |  | 05 12 00-13 Rev6 Welder Certs. - August 2020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-19 |  | 05 12 00-13 Rev6 Welder Certs. - August 2020.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-19 |  | 05 12 00-13 Rev6 Welder Certs. - August 2020.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-20 |  | 05 12 00-13 Rev6 Welder Certs. - August 2020_TT_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-08-18 02:00 |  | 05 12 00-13 Rev6 Welder Certs. - August 2020.pdf
05 12 00-013-07 | 05 12 00 - STEEL | 05 12 00-013-07 Welder Certs. - September 2020 (Up to 09/09/2020) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-17 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-01 | 2020-09-18 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-09-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08162 | Received | For Review | 2020-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-01 | Submittal Number: 05 12 00-13.7 From: RYAN CROOKSTON Final Due Date: 09/23/20 Subject: WELDER CERTS. - SEPTEMBER 2020 (UP TO 09/09/2020) Description: CERTIFICATIONS UP TO TUESDAY, 09/09/2020 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 10836 | Forwarded | For Review | 2020-09-17 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-24 | Submittal Number: 05 12 00-13.7 From: RYAN CROOKSTON Final Due Date: 09/23/20 Subject: WELDER CERTS. - SEPTEMBER 2020 (UP TO 09/09/2020) Description: CERTIFICATIONS UP TO TUESDAY, 09/09/2020 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08184 | Review Response | Approved | 2020-09-18 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Submittal Retained for Record Only. | Info Exchange
| 10869 | Responded and Closed | Approved | 2020-09-18 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Submittal Retained for Record Only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-16 |  | 05 12 00-13 R7 Sept Welder Certs.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-16 |  | 05 12 00-13 R7 Sept Welder Certs.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-16 |  | 05 12 00-13 R7 Sept Welder Certs.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-16 |  | 05 12 00-13 R7 Sept Welder Certs.pdf
05 12 00-013-08 | 05 12 00 - STEEL | 05 12 00-013-08 Welder Certs. - October 2020 (Up to 10/14/2020) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-20 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-03 | 2020-10-22 | 3 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-10-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08870 | Received | For Review | 2020-10-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-11-03 | Submittal Number: 05 12 00-13.8 From: RYAN CROOKSTON Final Due Date: 10/29/20 Subject: WELDER CERTS. - OCTOBER 2020 (UP TO 10/14/2020) Description: CERTIFICATIONS UP TO TUESDAY, 09/09/2020 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 11728 | Forwarded | For Review | 2020-10-20 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-27 | Submittal Number: 05 12 00-13.8 From: RYAN CROOKSTON Final Due Date: 10/29/20 Subject: WELDER CERTS. - OCTOBER 2020 (UP TO 10/14/2020) Description: CERTIFICATIONS UP TO TUESDAY, 09/09/2020 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08923 | Review Response | Approved | 2020-10-20 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. Retained for Record Only. | Info Exchange
| 11790 | Responded and Closed | Approved | 2020-10-22 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | TT has no exceptions. Retained for Record Only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-19 |  | 05 12 00-13 R8 Welder Certs. - Oct 2020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-19 |  | 05 12 00-13 R8 Welder Certs. - Oct 2020.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-19 |  | 05 12 00-13 R8 Welder Certs. - Oct 2020.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-19 |  | 05 12 00-13 R8 Welder Certs. - Oct 2020.pdf
05 12 00-013-09 | 05 12 00 - STEEL | 05 12 00-013-09 Welder Certs. - November 2020 (Up to 11/13/2020) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-23 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-09 | 2020-11-23 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-11-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09657 | Received | For Review | 2020-11-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-09 | Submittal Number: 05 12 00-13.9 From: RYAN CROOKSTON Final Due Date: 11/30/20 Subject: WELDER CERTS. - NOVEMBER 2020 (UP TO 11/13/2020) Description: CERTIFICATIONS UP TO TUESDAY, 09/09/2020 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 12708 | Forwarded | For Review | 2020-11-23 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-30 | Submittal Number: 05 12 00-13.9 From: RYAN CROOKSTON Final Due Date: 11/30/20 Subject: WELDER CERTS. - NOVEMBER 2020 (UP TO 11/13/2020) Description: CERTIFICATIONS UP TO TUESDAY, 09/09/2020 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09687 | Review Response | No Action Taken or Required | 2020-11-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Received for Record Only. | Info Exchange
| 12741 | Responded and Closed | No Action Taken or Required | 2020-11-23 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Received for Record Only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-20 |  | 05 12 00-13 R9 Welder Certs. - Nov. 2020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-20 |  | 05 12 00-13 R9 Welder Certs. - Nov. 2020.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-20 |  | 05 12 00-13 R9 Welder Certs. - Nov. 2020.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-20 |  | 05 12 00-13 R9 Welder Certs. - Nov. 2020.pdf
05 12 00-014-00 | 05 12 00 - STEEL | 05 12 00-014-0 TRS - Steel Mill Order W36 Beams - MP | Closed | Structural | Ella Pilgrim | 2019-04-04 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-04-18 | 2019-04-30 | 27 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2019-04-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01126 | Received | For Review | 2019-04-04 | Ella Pilgrim | SCA_CCA@populous.com | 2019-04-18 |  | Email
| 01999 | Forwarded | For Review | 2019-04-04 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-04-11 |  | Info Exchange
| 02052 | Forwarded | For Review | 2019-04-12 | SCA_CCA@populous.com | Shawn Leary; Mark Membreno (Thornton Tomasetti) |  |  | Info Exchange
| 01243 | Review Response | No Action Taken or Required | 2019-04-29 | Mark Membreno (Thornton Tomasetti) | SCA_CCA@populous.com |  | Received for record only. | Info Exchange
| 02193 | Responded and Closed | Not Required For Review | 2019-04-30 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Ella Pilgrim |  | Response (No Action Taken or Required) from: Mark Membreno (Thornton Tomasetti) Remarks: Received for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Ella Pilgrim (Mortenson Construction) | 1 | 2019-04-04 |  | 05 12 00-014-0 TRS - Steel Mill Order W36 Beams - MP.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-04 |  | 05 12 00-014-0 TRS - Steel Mill Order W36 Beams - MP.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-04 |  | 05 12 00-014-0 TRS - Steel Mill Order W36 Beams - MP.pdf
| Review Response |  | Mark Membreno (Thornton Tomasetti) | 1 | 2019-04-04 |  | 05 12 00-014-0 TRS - Steel Mill Order W36 Beams - MP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 05 12 00-014-0 TRS - Steel Mill Order W36 Beams_TT Response 20190429_POP.pdf
05 12 00-015-00 | 05 12 00 - STEEL | 05 12 00-015-0 TRS - Above Grade Pile Mill Order - MP | Closed | Structural | Ella Pilgrim | 2019-04-12 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-04-26 | 2019-04-30 | 19 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2019-04-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01165 | Received | For Review | 2019-04-12 | Ella Pilgrim | SCA_CCA@populous.com | 2019-04-26 |  | Email
| 02053 | Forwarded | For Review | 2019-04-12 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-04-19 |  | Info Exchange
| 01244 | Review Response | No Action Taken or Required | 2019-04-29 | Mark Membreno (Thornton Tomasetti) | SCA_CCA@populous.com |  | Received for record only. Dimensions and quantities not reviewed. Contractor to coordinate with 4/22/2019 drawings. | Info Exchange
| 02196 | Responded and Closed | No Action Taken or Required | 2019-04-30 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Ella Pilgrim |  | Response (No Action Taken or Required) from: Mark Membreno (Thornton Tomasetti) Remarks: Received for record only. Dimensions and quantities not reviewed. Contractor to coordinate with 4/22/2019 drawings. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Ella Pilgrim (Mortenson Construction) | 1 | 2019-04-12 |  | 05 12 00-015-0 TRS - Above Grade Pile Mill Order - MP.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-12 |  | 05 12 00-015-0 TRS - Above Grade Pile Mill Order - MP.pdf
| Review Response |  | Mark Membreno (Thornton Tomasetti) | 1 | 2019-04-12 |  | 05 12 00-015-0 TRS - Above Grade Pile Mill Order - MP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 05 12 00-015-0 TRS - Above Grade Pile Mill Order_TT REVIEW_POP.pdf
05 12 00-020-00 | 05 12 00 - STEEL | 05 12 00-020-00 TRS - Quality Control Program | Closed | Structural | Ella Pilgrim | 2019-04-30 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-05-14 | 2019-05-08 | 9 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-05-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01241 | Received | For Review | 2019-04-30 | Ella Pilgrim | SCA_CCA@populous.com | 2019-05-14 |  | Email
| 02191 | Forwarded | For Review | 2019-04-30 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-07 |  | Info Exchange
| 01270 | Review Response | No Action Taken or Required | 2019-05-06 | Mark Membreno (Thornton Tomasetti) | SCA_CCA@populous.com |  | Received for record. | Info Exchange
| 02259 | Responded and Closed | Not Required For Review | 2019-05-08 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Ella Pilgrim |  | Submittals regarding TRS are to be sent directly to TT. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Ella Pilgrim (Mortenson Construction) | 1 | 2019-04-30 |  | 05 12 00-020-00 TRS - Quality Control Program.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 05 12 00-020-00 TRS - Quality Control Program.pdf
| Review Response |  | Mark Membreno (Thornton Tomasetti) | 1 | 2019-04-30 |  | 05 12 00-020-00 TRS - Quality Control Program.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 05 12 00-020-00 TRS - Quality Control Program.pdf
05 12 00-022-00 | 05 12 00 - STEEL | 05 12 00-022-00 TRS - Welding Procedures Specifications | Closed | Structural | Ella Pilgrim | 2019-04-30 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous) |  |  |  | 2019-05-14 | 2019-05-08 | 9 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-05-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01240 | Received | For Review | 2019-04-30 | Ella Pilgrim | SCA_CCA@populous.com | 2019-05-14 |  | Email
| 02190 | Forwarded | For Review | 2019-04-30 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-07 |  | Info Exchange
| 01277 | Review Response | No Action Taken or Required | 2019-05-06 | Mark Membreno (Thornton Tomasetti) | SCA_CCA@populous.com |  | Received for record. | Info Exchange
| 02240 | Forwarded | For Review | 2019-05-07 | SCA_CCA@populous.com | Todd Spangler (Populous); Tom Usher (Populous) |  |  | Info Exchange
| 02258 | Responded and Closed | Not Required For Review | 2019-05-08 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Ella Pilgrim |  | Submittals regarding TRS are to be sent directly to TT. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Ella Pilgrim (Mortenson Construction) | 1 | 2019-04-30 |  | 05 12 00-022-00 TRS - Welding Procedures Specifications.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 05 12 00-022-00 TRS - Welding Procedures Specifications.pdf
| Review Response |  | Mark Membreno (Thornton Tomasetti) | 1 | 2019-04-30 |  | 05 12 00-022-00 TRS - Welding Procedures Specifications.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 05 12 00-022-00 TRS - Welding Procedures Specifications.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 05 12 00-022-00 TRS - Welding Procedures Specifications.pdf
05 12 00-023-00 | 05 12 00 - STEEL | 05 12 00-023-00 TRS - Welder Certifications | Closed | Structural | Ella Pilgrim | 2019-04-30 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous) |  |  |  | 2019-05-14 | 2019-05-08 | 9 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-05-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01239 | Received | For Review | 2019-04-30 | Ella Pilgrim | SCA_CCA@populous.com | 2019-05-14 |  | Email
| 02189 | Forwarded | For Review | 2019-04-30 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-07 |  | Info Exchange
| 01276 | Review Response | No Action Taken or Required | 2019-05-06 | Mark Membreno (Thornton Tomasetti) | SCA_CCA@populous.com |  | Received for record | Info Exchange
| 02239 | Forwarded | For Review | 2019-05-07 | SCA_CCA@populous.com | Todd Spangler (Populous); Tom Usher (Populous) |  |  | Info Exchange
| 02257 | Responded and Closed | Not Required For Review | 2019-05-08 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Ella Pilgrim |  | Submittals regarding TRS are to be sent directly to TT. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Ella Pilgrim (Mortenson Construction) | 1 | 2019-04-30 |  | 05 12 00-023-00 TRS - Welder Certifications.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 05 12 00-023-00 TRS - Welder Certifications.pdf
| Review Response |  | Mark Membreno (Thornton Tomasetti) | 1 | 2019-04-30 |  | 05 12 00-023-00 TRS - Welder Certifications.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 05 12 00-023-00 TRS - Welder Certifications.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 05 12 00-023-00 TRS - Welder Certifications.pdf
05 12 00-028-00 | 05 12 00 - STEEL | 05 12 00-028-00 SPS Shop Drawings and Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-17 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-31 | 2019-10-31 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-10-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02812 | Received | For Review | 2019-10-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-10-31 | Submittal Number: 05 12 00-28.0 From: JES PELKEY Final Due Date: 10/30/19 Subject: SPS SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04161 | Forwarded | For Review | 2019-10-17 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-24 | Submittal Number: 05 12 00-28.0 From: JES PELKEY Final Due Date: 10/30/19 Subject: SPS SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02998 | Review Response | Revise and Resubmit | 2019-10-31 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04383 | Responded and Closed | Revise and Resubmit | 2019-10-31 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| 04385 | Reopened | Additional Information | 2019-10-31 11:04 | Josh Dobken (Populous) |  |  | Closed in error
| 04387 | Responded and Closed | Revise and Resubmit | 2019-10-31 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-16 |  | 05 12 00-28.0 SPS SD, PD, and Initial Calcs-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-16 |  | 05 12 00-28.0 SPS SD, PD, and Initial Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-15 02:00 |  | 05 12 00-28.0 SPS SD, PD, and Initial Calcs-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-10-31 02:00 |  | 05 12 00-28.0 SPS SD, PD, and Initial Calcs-MAM_TT Reviewed_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-10-16 |  | 05 12 00-28.0 SPS SD, PD, and Initial Calcs-MAM.pdf
05 12 00-028-01 | 05 12 00 - STEEL | 05 12 00-028-01 SPS Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-25 | 20 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04232 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-02-20 | Submittal Number: 05 12 00-28.1 From: JES PELKEY Final Due Date: 02/17/20 Subject: SPS SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05861 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 05 12 00-28.1 From: JES PELKEY Final Due Date: 02/17/20 Subject: SPS SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04493 | Review Response | Approved as Noted/Resubmit | 2020-02-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06187 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-25 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| 06228 | Sent | For Construction | 2020-02-26 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Responded and Closed (Approved as Noted/Resubmit) to: Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 05 12 00-28.1 SPS Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | 05 12 00-28.1 SPS Shop Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-06 |  | 05 12 00-28.1 SPS Shop Drawings-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-25 |  | 05 12 00-28.1 SPS Shop Drawings-MAM_TT_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-02-05 02:00 |  | 05 12 00-28.1 SPS Shop Drawings-MAM.pdf
05 12 00-028-02 | 05 12 00 - STEEL | 05 12 00-028-02 SPS Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-28 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-12 | 2020-05-12 | 15 |  | Record Copies; Transfers; Submittals | 05 12 00-028-02-01 - 05 12 00-028-02 SPS Shop Drawings | 14 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05590 | Received | For Review | 2020-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-05-12 | Submittal Number: 05 12 00-28.2 From: JES PELKEY Final Due Date: 05/12/20 Subject: SPS SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07575 | Forwarded | For Review | 2020-04-28 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-05 | Submittal Number: 05 12 00-28.2 From: JES PELKEY Final Due Date: 05/12/20 Subject: SPS SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05827 | Review Response | Revise and Resubmit | 2020-05-11 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please provided calcs for SPS to base steel connection including calcs to show connection capable of transferring a diaphragm shear of 400#/ft per partial plan notes on S8-30. | Info Exchange
| 07911 | Responded and Closed | Revise and Resubmit | 2020-05-12 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please provided calcs for SPS to base steel connection including calcs to show connection capable of transferring a diaphragm shear of 400#/ft per partial plan notes on S8-30. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-27 |  | 05 12 00-28.2 SPS SD and Calcs-Stamped-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-27 |  | 05 12 00-28.2 SPS SD and Calcs-Stamped-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-27 |  | 05 12 00-28.2 SPS SD and Calcs-Stamped-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-12 |  | 05 12 00-28.2 SPS SD and Calcs-Stamped-MAM_TT_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-12 |  | A1-46 - SLAB PLAN - BRIDGE LEVEL.pdf
05 12 00-028-02-01 | 05 12 00 - STEEL | 05 12 00-028-02 SPS Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 12 00-028-02 - 05 12 00-028-02 SPS Shop Drawings | -1 | 2020-05-26
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-12 |  | 05 12 00-28.2 SPS SD and Calcs-Stamped-MAM_TT_POP.pdf
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-12 |  | A1-46 - SLAB PLAN - BRIDGE LEVEL.pdf
05 12 00-033-00 | 05 12 00 - STEEL | 05 12 00-033-00: Seq 9701 & 9801 Area D Anchors and Embeds | Closed | Structural | Jes Pelkey (Mortenson Construction) | 2019-05-24 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-06-10 | 2019-06-10 | 18 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-06-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01420 | Received | For Review | 2019-05-24 | Jes Pelkey (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-10 | MAM Reviewed. All other embeds to be submitted shortly for the remainder of Quad D. | Info Exchange
| 02422 | Forwarded | For Review | 2019-06-03 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-06-07 | MAM Reviewed. All other embeds to be submitted shortly for the remainder of Quad D. | Info Exchange
| 01475 | Review Response | Revise and Resubmit | 2019-06-10 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached for SSK-0005. | Info Exchange
| 02483 | Forwarded | For Review | 2019-06-10 | Josh Dobken (Populous) | Todd Spangler (Populous) |  | MAM Reviewed. All other embeds to be submitted shortly for the remainder of Quad D. | Email
| 02493 | Responded and Closed | Revise and Resubmit | 2019-06-10 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: See attached for SSK-0005 in addition to submittal. POP comments in light blue. Please revise/ resubmit. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-06-03 |  | 05 12 00-33.0 Seq 9701 & 9801 Area D Anchors & Embeds-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-03 |  | 05 12 00-33.0 Seq 9701 & 9801 Area D Anchors & Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-07 |  | 05 12 00-33.0 Seq 9701 & 9801 Area D Anchors & Embeds-MAM_TT REVIEW.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-10 |  | SSK-0005 Submittal 05 12 00-033.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-03 |  | 05 12 00-33.0 Seq 9701 & 9801 Area D Anchors & Embeds-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-10 |  | SSK-0005 Submittal 05 12 00-033.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-10 |  | 05 12 00-33.0 Seq 9701 & 9801 Area D Anchors & Embeds-MAM_TT REVIEW_POP.pdf
05 12 00-033-01 | 05 12 00 - STEEL | 05 12 00-033-01 Seq 9701 & 9801 Area D Anchors & Embeds | Closed | Structural | Jes Pelkey (Mortenson Construction) | 2019-06-20 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-07-05 | 2019-07-03 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-07-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01579 | Received | For Review | 2019-06-20 | Jes Pelkey (Mortenson Construction) | Populous SCA_CCA | 2019-07-05 |  | Email
| 02617 | Forwarded | For Review | 2019-06-20 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fra... | 2019-06-27 |  | Info Exchange
| 01679 | Review Response | Approved | 2019-07-02 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has only reviewed clouded items. All other parts of this submittal are assumed to have been unchanged and have been reviewed in previous rev. | Info Exchange
| 02753 | Responded and Closed | Approved | 2019-07-03 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has only reviewed clouded items. All other parts of this submittal are assumed to have been unchanged and have been reviewed in previous rev. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-06-20 |  | 05 12 00-033-01 Seq 9701 & 9801 Area D Anchors & Embeds-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-20 |  | 05 12 00-033-01 Seq 9701 & 9801 Area D Anchors & Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-20 |  | 05 12 00-033-01 Seq 9701 & 9801 Area D Anchors & Embeds-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-07-03 |  | 05 12 00-033-01 Seq 9701 & 9801 Area D Anchors & Embeds-MAM_TT REVIEW_POP.pdf
05 12 00-037-00 | 05 12 00 - STEEL | 05 12 00-037-00 Quad B1 A Structural Steel - Seq. 601-606 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-24 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-13 | 2020-03-24 | 30 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04456 | Received | For Review | 2020-02-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-03-13 | Submittal Number: 05 12 00-37.0 From: JES PELKEY Final Due Date: 03/09/20 Subject: QUAD B1 A STRUCTURAL STEEL - SEQ. 601-606 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06149 | Forwarded | For Review | 2020-02-24 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-02 | Submittal Number: 05 12 00-37.0 From: JES PELKEY Final Due Date: 03/09/20 Subject: QUAD B1 A STRUCTURAL STEEL - SEQ. 601-606 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05025 | Review Response | Approved as Noted | 2020-03-18 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Note: Contractor Proposed West Temp Ramp changes may affect steel in this submittal. | Info Exchange
| 06842 | Responded and Closed | Approved as Noted | 2020-03-24 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-22 |  | 05 12 00-37.0 Quad B1A Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-22 |  | 05 12 00-37.0 Quad B1A Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-22 |  | 05 12 00-37.0 Quad B1A Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-24 |  | 05 12 00-37.0 Quad B1A Steel SD-MAM_TT_POP.pdf
05 12 00-037-01 | 05 12 00 - STEEL | 05 12 00-037-01 Quad B1 A Structural Steel - Revisions due to West Temp Ramp | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-19 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-06 07:00 | 2020-06-25 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06502 | Received | For Review | 2020-06-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-06 07:00 | Submittal Number: 05 12 00-37.1 From: JES PELKEY Final Due Date: 07/02/20 Subject: QUAD B1 A STRUCTURAL STEEL - REVISIONS DUE TO WEST TEMP RAMP Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08756 | Forwarded | For Review | 2020-06-18 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-25 | Submittal Number: 05 12 00-37.1 From: JES PELKEY Final Due Date: 07/02/20 Subject: QUAD B1 A STRUCTURAL STEEL - REVISIONS DUE TO WEST TEMP RAMP Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06596 | Review Response | Revise and Resubmit | 2020-06-23 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Refer to individual stamps on sheets for pieces that TT needs to review again once revised. All other pieces are approved as noted. | Info Exchange
| 08891 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-25 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 |  | 05 12 00-37.1 Quad B1A Steel SD RR for WTR-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-18 |  | 05 12 00-37.1 Quad B1A Steel SD RR for WTR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-18 |  | 05 12 00-37.1 Quad B1A Steel SD RR for WTR-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-25 |  | 05 12 00-37.1 Quad B1A Steel SD RR for WTR-MAM_TT_POP.pdf
05 12 00-037-02 | 05 12 00 - STEEL | 05 12 00-037-02 Quad B1 A Structural Steel - WTR Revisions 5 Members | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-01 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-15 | 2020-07-01 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-07-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06713 | Received | For Review | 2020-07-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company); Jes Pelkey (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-07-15 | Submittal Number: 05 12 00-37.2 From: JES PELKEY Final Due Date: 07/16/20 Subject: QUAD B1 A STRUCTURAL STEEL - WTR REVISIONS 5 MEMBERS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09024 | Forwarded | For Review | 2020-06-30 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-07 | Submittal Number: 05 12 00-37.2 From: JES PELKEY Final Due Date: 07/16/20 Subject: QUAD B1 A STRUCTURAL STEEL - WTR REVISIONS 5 MEMBERS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06725 | Review Response | Approved as Noted | 2020-07-01 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09048 | Responded and Closed | Approved as Noted | 2020-07-01 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-30 |  | 05 12 00-37 Quad B1 A Struct Steel - WTR Rev 5.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-30 |  | 05 12 00-37 Quad B1 A Struct Steel - WTR Rev 5.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-30 |  | 05 12 00-37 Quad B1 A Struct Steel - WTR Rev 5.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-07-01 |  | 05 12 00-37 Quad B1 A Struct Steel - WTR Rev 5_TT REVIEW.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-07-01 |  | 05 12 00-37 Quad B1 A Struct Steel - WTR Rev 5_TT REVIEW-POP.pdf
05 12 00-045-00 | 05 12 00 - STEEL | 05 12 00-045-00: Seq 9702 & 9802 Quad C Anchors & Embeds | Closed | Structural | Jes Pelkey (Mortenson Construction) | 2019-06-07 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Todd Spangler (Populous), Matthew Farber (Thornton Tomasetti), Josh Dobken (Populous), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-06-21 | 2019-06-19 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-06-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01467 | Received | For Review | 2019-06-07 | Jes Pelkey (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-21 | MAM Reviewed. Please confirm all clouded questions. | Info Exchange
| 02474 | Forwarded | For Review | 2019-06-07 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Todd Spangler (Populous); Matthew Farber (Thornton Tomasetti); Josh Dobken (Populous); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tom... | 2019-06-14 | MAM Reviewed. Please confirm all clouded questions. | Info Exchange
| 01513 | Review Response | Approved as Noted/Resubmit | 2019-06-13 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Anchors AAN. Please R&R all embeds per CCD-011 | Info Exchange
| 02533 | Forwarded | For Review | 2019-06-13 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2019-06-20 | MAM Reviewed. Please confirm all clouded questions. | Email
| 01564 | Review Response | Approved as Noted/Resubmit | 2019-06-19 | Josh Dobken (Populous) | Josh Dobken (Populous) |  | POP COMMENTS - Approved as noted / Resubmit Please see comments on sheet AB3 and revise and resubmit that sheet for approval. | Info Exchange
| 02593 | Responded and Closed | Approved as Noted/Resubmit | 2019-06-19 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Anchors AAN. Please R&R all embeds per CCD-011 Response (Approved as Noted/Resubmit) from: Josh Dobken (Populous) Remarks: POP COMMENTS - Approved as noted / Resubmit Please see comments on sheet AB3 and revise and resubmit that sheet for approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-06-07 |  | 05 12 00-45.0 Seq. 9702 & 9802 Quad C Anchors & Embeds-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-07 |  | 05 12 00-45.0 Seq. 9702 & 9802 Quad C Anchors & Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-07 |  | 05 12 00-45.0 Seq. 9702 & 9802 Quad C Anchors & Embeds-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-07 |  | 05 12 00-45.0 Seq. 9702 & 9802 Quad C Anchors & Embeds-MAM.pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2019-06-19 |  | 05 12 00-45.0 Seq. 9702 & 9802 Quad C Anchors & Embeds-MAM_TT REVIEW_POP REVIEW.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-07 |  | 05 12 00-45.0 Seq. 9702 & 9802 Quad C Anchors & Embeds-MAM.pdf
05 12 00-045-01 | 05 12 00 - STEEL | 05 12 00-045-01 Seq 9702 & 9802 Quad C Embeds - Revisions | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-10 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-07-24 | 2019-07-11 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-07-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01726 | Received | For Review | 2019-07-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC) | 2019-07-24 | Submittal Number: 05 12 00-45.1 From: JES PELKEY Final Due Date: 07/25/19 Subject: SEQ 9702 & 9802 QUAD C EMBEDS - REVISIONS Description: REVISE AND RESUBMIT SHEET AB3 AND EMBED SHEETS PER COMMENTS AND CCD-011 UPDATED SHEETS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02829 | Forwarded | For Review | 2019-07-10 | . (Seattle Arena Company, LLC) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-17 | Submittal Number: 05 12 00-45.1 From: JES PELKEY Final Due Date: 07/25/19 Subject: SEQ 9702 & 9802 QUAD C EMBEDS - REVISIONS Description: REVISE AND RESUBMIT SHEET AB3 AND EMBED SHEETS PER COMMENTS AND CCD-011 UPDATED SHEETS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 01749 | Review Response | Approved as Noted | 2019-07-11 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 02856 | Forwarded | For Review | 2019-07-11 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2019-07-18 | Submittal Number: 05 12 00-45.1 From: JES PELKEY Final Due Date: 07/25/19 Subject: SEQ 9702 & 9802 QUAD C EMBEDS - REVISIONS Description: REVISE AND RESUBMIT SHEET AB3 AND EMBED SHEETS PER COMMENTS AND CCD-011 UPDATED SHEETS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Email
| 02866 | Responded and Closed | Approved as Noted | 2019-07-11 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-10 |  | 05 12 00-45.1 Seq 9702 & 9802 Quad C Embeds-Revisions-MAM.pdf
| Forwarded |  | . (Seattle Arena Company, LLC) | 1 | 2019-07-10 |  | 05 12 00-45.1 Seq 9702 & 9802 Quad C Embeds-Revisions-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-10 |  | 05 12 00-45.1 Seq 9702 & 9802 Quad C Embeds-Revisions-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-07-10 |  | 05 12 00-45.1 Seq 9702 & 9802 Quad C Embeds-Revisions-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-11 |  | 05 12 00-45.1 Seq 9702 & 9802 Quad C Embeds-Revisions-MAM_TT REVIEWED_POP.pdf
05 12 00-049-00 | 05 12 00 - STEEL | 05 12 00-049-00 Seq. 9703 Area E&F Anchor Rods | Closed | Structural | Jes Pelkey (Mortenson Construction) | 2019-06-12 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2019-06-26 | 2019-06-20 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-06-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01494 | Received | For Review | 2019-06-12 | Jes Pelkey (Mortenson Construction) | SCA_CCA@populous.com | 2019-06-26 |  | Email
| 02511 | Forwarded | For Review | 2019-06-12 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fra... | 2019-06-19 |  | Info Exchange
| 01582 | Review Response | Approved as Noted | 2019-06-20 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 02619 | Forwarded | For Review | 2019-06-20 | Populous SCA_CCA | Todd Spangler (Populous); Josh Dobken (Populous) | 2019-06-26 |  | Email
| 02629 | Responded and Closed | Approved as Noted | 2019-06-20 | Populous SCA_CCA | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction) |  | Approved as noted by Populous and TT. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-06-12 |  | 05 12 00-049-00 Seq. 9703 Area E&F Anchor Rods-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-12 |  | 05 12 00-049-00 Seq. 9703 Area E&F Anchor Rods-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-12 |  | 05 12 00-049-00 Seq. 9703 Area E&F Anchor Rods-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-12 |  | 05 12 00-049-00 Seq. 9703 Area E&F Anchor Rods-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-06-20 |  | 05 12 00-049-00 Seq. 9703 Area E&F Anchor Rods-MAM_TT Review_POP.pdf
05 12 00-052-00 | 05 12 00 - STEEL | 05 12 00-052-00 Seq 9704 & 9804 Quad A Anchors & Embeds | Closed | Structural | Jes Pelkey (Mortenson Construction) | 2019-06-19 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2019-07-02 | 2019-06-25 | 7 |  | Record Copies; Transfers; Submittals | 05 12 00-052-01 - 05 12 00-052-01 Seq 9704 & 9804 Quad A Anchors & Embeds | 7 |  | 2019-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01560 | Received | For Review | 2019-06-19 | Jes Pelkey (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-07-02 | Submittal Number: 05 12 00-52.0 From: JES PELKEY Final Due Date: 07/02/19 Subject: SEQ 9704 & 9804 QUAD A ANCHORS & EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02588 | Forwarded | For Review | 2019-06-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fra... | 2019-06-26 | Submittal Number: 05 12 00-52.0 From: JES PELKEY Final Due Date: 07/02/19 Subject: SEQ 9704 & 9804 QUAD A ANCHORS & EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 01588 | Review Response | Approved as Noted | 2019-06-20 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 02628 | Forwarded | For Review | 2019-06-20 | Josh Dobken (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2019-06-27 | Submittal Number: 05 12 00-52.0 From: JES PELKEY Final Due Date: 07/02/19 Subject: SEQ 9704 & 9804 QUAD A ANCHORS & EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Email
| 01615 | Review Response | Approved as Noted/Resubmit | 2019-06-25 | Todd Spangler (Populous) | Josh Dobken (Populous) |  | Approved as noted, resubmit. | Info Exchange
| 02671 | Responded and Closed | Approved as Noted/Resubmit | 2019-06-25 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Todd Spangler (Populous) Remarks: Approved as noted, resubmit. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-06-18 |  | 05 12 00-52.0 Seq 9704 & 9804 Quad A Anchors & Embeds-MAM.pdf
| Received |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-06-18 |  | 05 12 00-52.0 Seq 9704 & 9804 Quad A Anchors & Embeds-MAM(1).pdf
| Received |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-06-18 |  | Seq 9704, 9804 Quad A Anchors and Embeds.pdf
| Received |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-06-18 |  | Seq 9704, 9804 Quad A Anchors and Embeds(1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-06-19 |  | 05 12 00-52.0 Seq 9704 & 9804 Quad A Anchors & Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-19 |  | 05 12 00-52.0 Seq 9704 & 9804 Quad A Anchors & Embeds-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-18 |  | 05 12 00-52.0 Seq 9704 & 9804 Quad A Anchors & Embeds-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-18 |  | 05 12 00-52.0 Seq 9704 & 9804 Quad A Anchors & Embeds-MAM(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-18 |  | Seq 9704, 9804 Quad A Anchors and Embeds.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-18 |  | Seq 9704, 9804 Quad A Anchors and Embeds(1).pdf
| Review Response |  | Todd Spangler (Populous) | 1 | 2019-06-25 |  | 05 12 00-52.0 Seq 9704 & 9804 Quad A Anchors & Embeds-MAM_TT REVIEW _POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-18 |  | 05 12 00-52.0 Seq 9704 & 9804 Quad A Anchors & Embeds-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-18 |  | 05 12 00-52.0 Seq 9704 & 9804 Quad A Anchors & Embeds-MAM(1).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-18 |  | Seq 9704, 9804 Quad A Anchors and Embeds.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-18 |  | Seq 9704, 9804 Quad A Anchors and Embeds(1).pdf
05 12 00-052-01 | 05 12 00 - STEEL | 05 12 00-052-01 Seq 9704 & 9804 Quad A Anchors & Embeds | Expected - Overdue | Structural | Jes Pelkey (Mortenson Construction) | [7 empty] | 2019-07-10 |  | -1 |  | Submittals | 05 12 00-052-00 - 05 12 00-052-00 Seq 9704 & 9804 Quad A Anchors & Embeds | -1 | 2019-07-09
05 12 00-054-00 | 05 12 00 - STEEL | Seq 9705 & 9805 Quad B Anchor & Embeds | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-06-27 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-07-12 | 2019-07-09 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-07-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01643 | Received | For Review | 2019-06-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-07-12 | Submittal Number: 05 12 00-54.0 From: JES PELKEY Final Due Date: 07/10/19 Subject: SEQ 9705 & 9805 QUAD B ANCHOR & EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02708 | Forwarded | For Review | 2019-06-27 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-05 | Submittal Number: 05 12 00-54.0 From: JES PELKEY Final Due Date: 07/10/19 Subject: SEQ 9705 & 9805 QUAD B ANCHOR & EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 01684 | Review Response | Approved as Noted/Resubmit | 2019-07-03 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Resubmit embed off of column at C2.C-WB2 per response to RFI 1211 and new detail to be issued in CCD-017 | Info Exchange
| 02778 | Forwarded | For Review | 2019-07-08 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2019-07-12 | Submittal Number: 05 12 00-54.0 From: JES PELKEY Final Due Date: 07/10/19 Subject: SEQ 9705 & 9805 QUAD B ANCHOR & EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Email
| 01704 | Review Response | Approved as Noted | 2019-07-09 | Todd Spangler (Populous) | Josh Dobken (Populous) |  |  | Info Exchange
| 02799 | Responded and Closed | Approved as Noted/Resubmit | 2019-07-09 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Resubmit embed off of column at C2.C-WB2 per response to RFI 1211 and new detail to be issued in CCD-017 Response (Approved as Noted) from: Todd Spangler (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-26 |  | 05 12 00-54.0 Seq 9705 & 9805 Quad B Anchor & Embeds-MAM.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-26 |  | 05 12 00-54.0 Seq 9705 & 9805 Quad B Anchor & Embeds-MAM(1).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-26 |  | Area B Anchor Bolts and Embeds.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-26 |  | Area B Anchor Bolts and Embeds(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | 05 12 00-54.0 Seq 9705 & 9805 Quad B Anchor & Embeds-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | 05 12 00-54.0 Seq 9705 & 9805 Quad B Anchor & Embeds-MAM(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | Area B Anchor Bolts and Embeds.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | Area B Anchor Bolts and Embeds(1).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-26 |  | 05 12 00-54.0 Seq 9705 & 9805 Quad B Anchor & Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-26 |  | 05 12 00-54.0 Seq 9705 & 9805 Quad B Anchor & Embeds-MAM(1).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-26 |  | Area B Anchor Bolts and Embeds.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-26 |  | Area B Anchor Bolts and Embeds(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | 05 12 00-54.0 Seq 9705 & 9805 Quad B Anchor & Embeds-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | 05 12 00-54.0 Seq 9705 & 9805 Quad B Anchor & Embeds-MAM(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | Area B Anchor Bolts and Embeds.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | Area B Anchor Bolts and Embeds(1).pdf
| Review Response |  | Todd Spangler (Populous) | 1 | 2019-07-08 |  | 05 12 00-54.0 Seq 9705 9805 Quad B Anchor Embeds-MAM_TT REVIEWED_POP REVIEW.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | 05 12 00-54.0 Seq 9705 & 9805 Quad B Anchor & Embeds-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | 05 12 00-54.0 Seq 9705 & 9805 Quad B Anchor & Embeds-MAM(1).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | Area B Anchor Bolts and Embeds.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | Area B Anchor Bolts and Embeds(1).pdf
05 12 00-054-01 | 05 12 00 - STEEL | 05 12 00-054-01 Seq 9705 & 9805 Quad B Anchor & Embeds - Embeds off of Column C2.C-WB2 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-31 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-11-14 | 2019-11-08 | 9 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-11-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02993 | Received | For Review | 2019-10-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-11-14 | Submittal Number: 05 12 00-54.1 From: JES PELKEY Final Due Date: 11/15/19 Subject: SEQ 9705 & 9805 QUAD B ANCHOR & EMBEDS - EMBEDS OFF OF COLUMN C2.C-WB2 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04377 | Forwarded | For Review | 2019-10-31 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-07 | Submittal Number: 05 12 00-54.1 From: JES PELKEY Final Due Date: 11/15/19 Subject: SEQ 9705 & 9805 QUAD B ANCHOR & EMBEDS - EMBEDS OFF OF COLUMN C2.C-WB2 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03127 | Review Response | Approved as Noted | 2019-11-06 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04538 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-08 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. Submit for record only with MAM review and stamp. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-31 |  | 05 12 00-54.1 Quad B AB and Embeds-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-31 |  | 05 12 00-54.1 Quad B AB and Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-31 |  | 05 12 00-54.1 Quad B AB and Embeds-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-11-08 |  | 05 12 00-54.1 Quad B AB and Embeds-MAM_TT_TAS.pdf
05 12 00-054-02 | 05 12 00 - STEEL | 05 12 00-054-02 Seq 9705 & 9805 Quad B Anchor & Embeds - Stamped | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-03 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2019-12-17 | 2019-12-13 | 11 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-12-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03439 | Received | For Review | 2019-12-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-17 | Submittal Number: 05 12 00-54.2 From: JES PELKEY Final Due Date: 12/17/19 Subject: SEQ 9705 & 9805 QUAD B ANCHOR & EMBEDS - STAMPED Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04911 | Forwarded | For Review | 2019-12-03 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-10 | Submittal Number: 05 12 00-54.2 From: JES PELKEY Final Due Date: 12/17/19 Subject: SEQ 9705 & 9805 QUAD B ANCHOR & EMBEDS - STAMPED Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03553 | Review Response | No Action Taken or Required | 2019-12-09 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Nothing for TT to review. | Info Exchange
| 05022 | Forwarded | For Review | 2019-12-09 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2019-12-16 | Submittal Number: 05 12 00-54.2 From: JES PELKEY Final Due Date: 12/17/19 Subject: SEQ 9705 & 9805 QUAD B ANCHOR & EMBEDS - STAMPED Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05118 | Responded and Closed | Not Required For Review | 2019-12-13 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Received for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-03 |  | 05 12 00-54.2 Quad B AB and Embeds-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-03 |  | 05 12 00-54.2 Quad B AB and Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-02 02:00 |  | 05 12 00-54.2 Quad B AB and Embeds-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-02 02:00 |  | 05 12 00-54.2 Quad B AB and Embeds-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-13 |  | 05 12 00-54.2 Quad B AB and Embeds-MAM_POP.pdf
05 12 00-056-00 | 05 12 00 - STEEL | 05 12 00-056-00 Slide Bearing Assembly Shop Drawings and Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-22 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-05 | 2019-07-23 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-07-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01839 | Received | For Review | 2019-07-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-08-05 | Submittal Number: 05 12 00-56.0 From: JES PELKEY Final Due Date: 08/05/19 Subject: SLIDE BEARING ASSEMBLY SHOP DRAWINGS AND PRODUCT DATA Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02964 | Forwarded | For Review | 2019-07-22 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-29 | Submittal Number: 05 12 00-56.0 From: JES PELKEY Final Due Date: 08/05/19 Subject: SLIDE BEARING ASSEMBLY SHOP DRAWINGS AND PRODUCT DATA Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 01849 | Review Response | Rejected | 2019-07-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | For slide bearing assembly shop drawings, please submit key plan to note location of slide bearings for review. | Info Exchange
| 02977 | Responded and Closed | Rejected | 2019-07-23 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Matt Ross (Thornton Tomasetti) Remarks: For slide bearing assembly shop drawings, please submit key plan to note location of slide bearings for review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-22 |  | 05 12 00-56.0 Slide Bearing Assembly SD and PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-22 |  | 05 12 00-56.0 Slide Bearing Assembly SD and PD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-21 02:00 |  | 05 12 00-56.0 Slide Bearing Assembly SD and PD-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-23 02:00 |  | 05 12 00-56.0 Slide Bearing Assembly SD and PD-MAM_POP.pdf
05 12 00-056-01 | 05 12 00 - STEEL | 05 12 00-056-01 Slide Bearing Assembly Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-31 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-14 | 2019-08-12 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-08-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01934 | Received | For Review | 2019-07-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-08-14 | Submittal Number: 05 12 00-56.1 From: JES PELKEY Final Due Date: 08/14/19 Subject: SLIDE BEARING ASSEMBLY PRODUCT DATA Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03080 | Forwarded | For Review | 2019-07-31 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-07 | Submittal Number: 05 12 00-56.1 From: JES PELKEY Final Due Date: 08/14/19 Subject: SLIDE BEARING ASSEMBLY PRODUCT DATA Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02036 | Review Response | Rejected | 2019-08-12 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Details 1/S4-11 and 5/S7-40 specify CON-SERV/CON-SLIDE Slide Bearing Pads type CSB. These slide bearings have bearing capacities that exceed those of the Fabreeka bearing pad contained in this submittal. | Info Exchange
| 03203 | Responded and Closed | Rejected | 2019-08-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Matt Ross (Thornton Tomasetti) Remarks: Details 1/S4-11 and 5/S7-40 specify CON-SERV/CON-SLIDE Slide Bearing Pads type CSB. These slide bearings have bearing capacities that exceed those of the Fabreeka bearing pad contained in this submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-31 |  | 05 12 00-56.1 Slide Bearing Assembly SD and PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-31 |  | 05 12 00-56.1 Slide Bearing Assembly SD and PD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-30 02:00 |  | 05 12 00-56.1 Slide Bearing Assembly SD and PD-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-12 02:00 |  | 05 12 00-56.1 Slide Bearing Assembly SD and PD-MAM_TT _POP.pdf
05 12 00-056-02 | 05 12 00 - STEEL | 05 12 00-056-02 Slide Bearing Assembly Product Data - CON-SERV/CON-SLIDE | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-10 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-24 | 2019-10-11 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-10-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02719 | Received | For Review | 2019-10-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-10-24 | Submittal Number: 05 12 00-56.2 From: JES PELKEY Final Due Date: 10/24/19 Subject: SLIDE BEARING ASSEMBLY PRODUCT DATA - CON-SERV/CON-SLIDE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04054 | Forwarded | For Review | 2019-10-10 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-17 | Submittal Number: 05 12 00-56.2 From: JES PELKEY Final Due Date: 10/24/19 Subject: SLIDE BEARING ASSEMBLY PRODUCT DATA - CON-SERV/CON-SLIDE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02740 | Review Response | Approved as Noted | 2019-10-11 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04077 | Responded and Closed | Approved as Noted | 2019-10-11 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-09 |  | 05 12 00-56.2 Slide Bearing Assembly PD and Design Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-09 |  | 05 12 00-56.2 Slide Bearing Assembly PD and Design Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-09 |  | 05 12 00-56.2 Slide Bearing Assembly PD and Design Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-10-11 |  | 05 12 00-56.2 Slide Bearing Assembly PD and Design Drawings-MAM_TT Review_POP.pdf
05 12 00-057-00 | 05 12 00 - STEEL | 05 12 00-057-00 Quad D Embeds | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-10 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-07-24 | 2019-08-07 | 29 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2019-08-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01725 | Received | For Review | 2019-07-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-24 | Submittal Number: 05 12 00-57.0 From: JES PELKEY Final Due Date: 07/24/19 Subject: QUAD D EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02826 | Forwarded | For Review | 2019-07-10 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-17 | Submittal Number: 05 12 00-57.0 From: JES PELKEY Final Due Date: 07/24/19 Subject: QUAD D EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 01989 | Review Response | Revise and Resubmit | 2019-08-07 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Refer to SSK-0037 sent with Submittal 051200-059-00 Response for revised slide bearing details as noted in submittal comments. | Info Exchange
| 03142 | Forwarded | For Review | 2019-08-07 | Todd Spangler (Populous) | Todd Spangler (Populous) |  | Submittal Number: 05 12 00-57.0 From: JES PELKEY Final Due Date: 07/24/19 Subject: QUAD D EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03143 | Responded and Closed | Revise and Resubmit | 2019-08-07 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to SSK-0037 sent with Submittal 051200-059-00 Response for revised slide bearing details as noted in submittal comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-09 |  | 05 12 00-57.0 Quad D Embeds-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-10 |  | 05 12 00-57.0 Quad D Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-10 |  | 05 12 00-57.0 Quad D Embeds-MAM.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-07-09 |  | 05 12 00-57.0 Quad D Embeds-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-07 |  | 05 12 00-57.0 Quad D Embeds-MAM_TT REVIEW - POP.pdf
05 12 00-057-01 | 05 12 00 - STEEL | 05 12 00-057-01 Quad D Embeds | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-13 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-09-27 | 2019-09-27 | 15 |  | Record Copies; Transfers; Submittals | 05 12 00-057-02 - 05 12 00-057-01 Quad D Embeds | 14 |  | 2019-09-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02405 | Received | For Review | 2019-09-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Jes Pelkey (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-27 | Submittal Number: 05 12 00-57.1 From: JES PELKEY Final Due Date: 09/27/19 Subject: QUAD D EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03659 | Forwarded | For Review | 2019-09-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-20 | Submittal Number: 05 12 00-57.1 From: JES PELKEY Final Due Date: 09/27/19 Subject: QUAD D EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02547 | Review Response | Approved as Noted/Resubmit | 2019-09-26 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Approved as Noted but Revise and Resubmit for Record. | Info Exchange
| 03836 | Responded and Closed | Approved as Noted/Resubmit | 2019-09-27 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Approved as Noted but Revise and Resubmit for Record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-13 |  | 05 12 00-57.1 Quad D Embeds-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-13 |  | 05 12 00-57.1 Quad D Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-13 |  | 05 12 00-57.1 Quad D Embeds-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-27 |  | 05 12 00-57.1 Quad D Embeds-MAM_TT REVIEW_POP.pdf
05 12 00-057-02 | 05 12 00 - STEEL | 05 12 00-057-01 Quad D Embeds | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 12 00-057-01 - 05 12 00-057-01 Quad D Embeds | -1 | 2019-10-11
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-27 |  | 05 12 00-57.1 Quad D Embeds-MAM_TT REVIEW_POP.pdf
05 12 00-058-00 | 05 12 00 - STEEL | 05 12 00-058-00 TRS - Grid Line G2 Drilled Shaft Rebar Cage SD | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-03 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), TLau@ThorntonTomasetti.com |  |  |  | 2019-07-18 | 2019-07-10 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-07-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01682 | Received | For Review | 2019-07-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ella Pilgrim; . (Seattle Arena Company, LLC) | 2019-07-18 | Submittal Number: 05 12 00-58.0 From: ELLA PILGRIM Final Due Date: 07/17/19 Subject: TRS - GRID LINE G2 DRILLED SHAFT REBAR CAGE SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02758 | Forwarded | For Review | 2019-07-03 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fra... | 2019-07-10 | Submittal Number: 05 12 00-58.0 From: ELLA PILGRIM Final Due Date: 07/17/19 Subject: TRS - GRID LINE G2 DRILLED SHAFT REBAR CAGE SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 01688 | Review Response | No Action Taken or Required | 2019-07-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | This is a TRS submittal and is to be handled by TT and Mortenson directly through Procore. | Info Exchange
| 02762 | Responded and Closed | No Action Taken or Required | 2019-07-03 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: This is a TRS submittal and is to be handled by TT and Mortenson directly through Procore. | Info Exchange
| 02763 | Reopened | Additional Information | 2019-07-03 14:13 | Kelsea Conkright (Populous) |  |  | Submittal covers both TRS and permanent structure. Previous response to submittal was under assumption that it was only related to TRS.
| 02767 | Forwarded | For Review | 2019-07-03 | Kelsea Conkright (Populous) | TLau@ThorntonTomasetti.com |  | Submittal Number: 05 12 00-58.0 From: ELLA PILGRIM Final Due Date: 07/17/19 Subject: TRS - GRID LINE G2 DRILLED SHAFT REBAR CAGE SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 01730 | Review Response | Approved as Noted | 2019-07-10 | Matt Ross (Thornton Tomasetti) | Kelsea Conkright (Populous) |  |  | Info Exchange
| 02834 | Responded and Closed | Approved as Noted | 2019-07-10 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-02 |  | 05 12 00-58.0 - TRS - Grid Line G2 Drilled Shaft Rebar Cage Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-03 |  | 05 12 00-58.0 - TRS - Grid Line G2 Drilled Shaft Rebar Cage Shop Drawings.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-03 |  | 05 12 00-58.0 - TRS - Grid Line G2 Drilled Shaft Rebar Cage Shop Drawings.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2019-07-02 |  | 05 12 00-58.0 - TRS - Grid Line G2 Drilled Shaft Rebar Cage Shop Drawings.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2019-07-02 |  | 05 12 00-58.0 - TRS - Grid Line G2 Drilled Shaft Rebar Cage Shop Drawings.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-03 |  | 05 12 00-58.0 - TRS - Grid Line G2 Drilled Shaft Rebar Cage Shop Drawings.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2019-07-10 |  | 05 12 00-58.0 - TRS - Grid Line G2 Drilled Shaft Rebar Cage Shop Drawings_TT_POP.pdf
05 12 00-059-00 | 05 12 00 - STEEL | 05 12 00-059-00 Quad C Embeds | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-16 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-07-30 | 2019-08-07 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2019-08-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01780 | Received | For Review | 2019-07-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-30 | Submittal Number: 05 12 00-59.0 From: JES PELKEY Final Due Date: 07/30/19 Subject: QUAD C EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02905 | Forwarded | For Review | 2019-07-16 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-23 | Submittal Number: 05 12 00-59.0 From: JES PELKEY Final Due Date: 07/30/19 Subject: QUAD C EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 01988 | Review Response | Revise and Resubmit | 2019-08-07 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached SSK for revised slide bearing details as noted in submittal comments. | Info Exchange
| 03140 | Forwarded | For Review | 2019-08-07 | Populous SCA_CCA | Todd Spangler (Populous) |  | Submittal Number: 05 12 00-59.0 From: JES PELKEY Final Due Date: 07/30/19 Subject: QUAD C EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03141 | Responded and Closed | Revise and Resubmit | 2019-08-07 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached SSK for revised slide bearing details as noted in submittal comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-15 |  | 05 12 00-59.0 Quad C Embeds-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-16 |  | 05 12 00-59.0 Quad C Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-16 |  | 05 12 00-59.0 Quad C Embeds-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-07-15 |  | 05 12 00-59.0 Quad C Embeds-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-07 |  | SSK-0037 Revised Slide Bearing Details.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-07 |  | 05 12 00-59.0 Quad C Embeds-MAM_TT REVIEW - POP.pdf
05 12 00-059-01 | 05 12 00 - STEEL | 05 12 00-059-01 Quad C Embeds | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-17 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-01 | 2019-10-01 | 15 |  | Record Copies; Transfers; Submittals | 05 12 00-059-02 - 05 12 00-059-02 Quad C Embeds | 10 |  | 2019-10-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02423 | Received | For Review | 2019-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; . (Seattle Arena Company, LLC) | 2019-10-01 | Submittal Number: 05 12 00-59.1 From: JES PELKEY Final Due Date: 09/30/19 Subject: QUAD C EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03680 | Forwarded | For Review | 2019-09-17 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-24 | Submittal Number: 05 12 00-59.1 From: JES PELKEY Final Due Date: 09/30/19 Subject: QUAD C EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02576 | Review Response | Approved as Noted/Resubmit | 2019-09-26 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Approved as Noted but please Revise and Resubmit for Record. | Info Exchange
| 03908 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Approved as Noted but please Revise and Resubmit for Record. See attached for review and comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-16 |  | 05 12 00-59.1 Quad C Embeds-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-16 |  | 05 12 00-59.1 Quad C Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-16 |  | 05 12 00-59.1 Quad C Embeds-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-01 |  | 05 12 00-59.1 Quad C Embeds-MAM_TT REVIEW_POP.pdf
05 12 00-059-02 | 05 12 00 - STEEL | 05 12 00-059-02 Quad C Embeds | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [7 empty] | 2019-10-15 |  | -1 |  | Submittals | 05 12 00-059-01 - 05 12 00-059-01 Quad C Embeds | -1 | 2019-10-15
05 12 00-062-00 | 05 12 00 - STEEL | 05 12 00-062-00 G2 Wet Set Columns - Populous Review | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-15 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-07-29 | 2019-08-02 | 19 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2019-08-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01764 | Received | For Review | 2019-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ella Pilgrim | 2019-07-29 | Submittal Number: 05 12 00-62.0 From: ELLA PILGRIM Final Due Date: 07/26/19 Subject: G2 WET SET COLUMNS - POPULOUS REVIEW Description: APPROVED BY TT IN SUBMITTAL 05 12 00-51 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02884 | Forwarded | For Review | 2019-07-15 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-22 | Submittal Number: 05 12 00-62.0 From: ELLA PILGRIM Final Due Date: 07/26/19 Subject: G2 WET SET COLUMNS - POPULOUS REVIEW Description: APPROVED BY TT IN SUBMITTAL 05 12 00-51 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 01962 | Review Response | Not Required For Review | 2019-08-01 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Retained for Record Only | Info Exchange
| 03108 | Responded and Closed | No Action Taken or Required | 2019-08-02 | Todd Spangler (Populous) | Ella Pilgrim; AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Retained for Record Only | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-12 |  | 05 12 00-062 G2 Wet Set Columns - Populous Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-15 |  | 05 12 00-062 G2 Wet Set Columns - Populous Review.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-15 |  | 05 12 00-062 G2 Wet Set Columns - Populous Review.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-07-12 |  | 05 12 00-062 G2 Wet Set Columns - Populous Review.pdf
05 12 00-063-00 | 05 12 00 - STEEL | 05 12 00-063-00 Quad E & F Embeds - Sequence 22, 9708 & 9813 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-25 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-08 | 2019-08-12 | 19 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-08-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01863 | Received | For Review | 2019-07-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-08-08 | Submittal Number: 05 12 00-63.0 From: BRAD KIRSCHENHEITER Final Due Date: 08/07/19 Subject: QUAD E & F EMBEDS - SEQUENCE 22, 9708 & 9813 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02996 | Forwarded | For Review | 2019-07-24 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-31 | Submittal Number: 05 12 00-63.0 From: BRAD KIRSCHENHEITER Final Due Date: 08/07/19 Subject: QUAD E & F EMBEDS - SEQUENCE 22, 9708 & 9813 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02026 | Review Response | Revise and Resubmit | 2019-08-08 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 03192 | Responded and Closed | Revise and Resubmit | 2019-08-12 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-24 |  | 05 12 00-63.0 Quad E & F Embeds - Seq. 22, 9708, & 9813-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-24 |  | 05 12 00-63.0 Quad E & F Embeds - Seq. 22, 9708, & 9813-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-24 |  | 05 12 00-63.0 Quad E & F Embeds - Seq. 22, 9708, & 9813-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-12 |  | 05 12 00-63.0 Quad E & F Embeds - Seq. 22, 9708, & 9813-MAM_TT REVIEW - POP.pdf
05 12 00-063-01 | 05 12 00 - STEEL | 05 12 00-063-01 Quad E & F Embeds - Sequence 22, 9708 & 9813 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-30 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-14 | 2019-10-11 | 12 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-10-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02601 | Received | For Review | 2019-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-10-14 | Submittal Number: 05 12 00-63.1 From: BRAD KIRSCHENHEITER Final Due Date: 10/14/19 Subject: QUAD E & F EMBEDS - SEQUENCE 22, 9708 & 9813 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03893 | Forwarded | For Review | 2019-09-30 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-07 | Submittal Number: 05 12 00-63.1 From: BRAD KIRSCHENHEITER Final Due Date: 10/14/19 Subject: QUAD E & F EMBEDS - SEQUENCE 22, 9708 & 9813 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02737 | Review Response | Approved as Noted | 2019-10-10 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 04073 | Responded and Closed | Approved as Noted | 2019-10-11 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-30 |  | 05 12 00-63.1 Quad E & F Embeds-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-30 |  | 05 12 00-63.1 Quad E & F Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-30 |  | 05 12 00-63.1 Quad E & F Embeds-MAM.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2019-10-11 |  | 05 12 00-63.1 Quad E & F Embeds-MAM_TT REVIEW_POP.pdf
05 12 00-065-00 | 05 12 00 - STEEL | 05 12 00-065-00 Sequence 23, 9709 & 9814 Quad A Embeds Approval Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-29 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-12 | 2019-08-16 | 19 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2019-08-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01895 | Received | For Review | 2019-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-12 | Submittal Number: 05 12 00-65.0 From: BRAD KIRSCHENHEITER Final Due Date: 08/13/19 Subject: SEQUENCE 23, 9709 & 9814 QUAD A EMBEDS APPROVAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03036 | Forwarded | For Review | 2019-07-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-05 | Submittal Number: 05 12 00-65.0 From: BRAD KIRSCHENHEITER Final Due Date: 08/13/19 Subject: SEQUENCE 23, 9709 & 9814 QUAD A EMBEDS APPROVAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02096 | Review Response | Revise and Resubmit | 2019-08-14 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Note: Location of Chevron Extension extents to be field verified per existing chevron leg dimensions above Upper Concourse per details on S7-53. These dimensions apply in all Quads A-D. | Info Exchange
| 03271 | Responded and Closed | Revise and Resubmit | 2019-08-16 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Note: Location of Chevron Extension extents to be field verified per existing chevron leg dimensions above Upper Concourse per details on S7-53. These dimensions apply in all Quads A-D. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-29 |  | 05 12 00-65.0 Quad A Embeds - Seq. 23, 9709 & 9814 SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-29 |  | 05 12 00-65.0 Quad A Embeds - Seq. 23, 9709 & 9814 SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-07-29 |  | 05 12 00-65.0 Quad A Embeds - Seq. 23, 9709 & 9814 SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-16 |  | 05 12 00-65.0 Quad A Embeds - Seq. 23, 9709 & 9814 SD-MAM_TT_POP.pdf
05 12 00-065-01 | 05 12 00 - STEEL | 05 12 00-065-01 Sequence 23, 9709 & 9814 Quad A Embeds Approval Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-31 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-11-15 | 2019-11-15 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-11-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03001 | Received | For Review | 2019-10-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-11-15 | Submittal Number: 05 12 00-65.1 From: BRAD KIRSCHENHEITER Final Due Date: 11/15/19 Subject: SEQUENCE 23, 9709 & 9814 QUAD A EMBEDS APPROVAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04389 | Forwarded | For Review | 2019-10-31 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-07 | Submittal Number: 05 12 00-65.1 From: BRAD KIRSCHENHEITER Final Due Date: 11/15/19 Subject: SEQUENCE 23, 9709 & 9814 QUAD A EMBEDS APPROVAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03222 | Review Response | Approved as Noted/Resubmit | 2019-11-14 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | SEE STAMPED SHEETS FOR PIECES TT WILL NEED TO REVIEW AGAIN ONCE REVISED. ALL OTHER SHEETS ARE APPROVED AS NOTED. ALL CHANGES IN FUTURE SUBMITTALS ARE TO BE CLOUDED TO NOTIFY REVIEWER WHAT HAS CHANGED. SLIDE BEARING NOTES: 1. SLIDE BEARINGS AT SUITE LEVEL TO HAVE WELDED REBAR INSTEAD OF OUTER COLUMN OF STUDS PER 5/S7-40. 2. SLIDE BEARINGS AT UPPER CONCOURSE ARE ON HOLD PENDING TT REDESIGN. | Info Exchange
| 04664 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-15 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: SEE STAMPED SHEETS FOR PIECES TT WILL NEED TO REVIEW AGAIN ONCE REVISED. ALL OTHER SHEETS ARE APPROVED AS NOTED. ALL CHANGES IN FUTURE SUBMITTALS ARE TO BE CLOUDED TO NOTIFY REVIEWER WHAT HAS CHANGED. SLIDE BEARING NOTES: 1. SLIDE BEARINGS AT SUITE LEVEL TO HAVE WELDED REBAR INSTEAD OF OUTER COLUMN OF STUDS PER 5/S7-40. 2. SLIDE BEARINGS AT UPPER CONCOURSE ARE ON HOLD PENDING TT REDESIGN. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-31 |  | 05 12 00-65.1 Quad A Embeds-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-31 |  | 05 12 00-65.1 Quad A Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-30 02:00 |  | 05 12 00-65.1 Quad A Embeds-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-11-15 02:00 |  | 05 12 00-65.1 Quad A Embeds-MAM_TT_POP.pdf
05 12 00-065-02 | 05 12 00 - STEEL | 05 12 00-065-02 Sequence 23, 9709 & 9814 Quad A Embeds Approval Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-20 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-05 | 2020-02-27 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04416 | Received | For Review | 2020-02-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-03-05 | Submittal Number: 05 12 00-65.2 From: BRAD KIRSCHENHEITER Final Due Date: 03/05/20 Subject: SEQUENCE 23, 9709 & 9814 QUAD A EMBEDS APPROVAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06102 | Forwarded | For Review | 2020-02-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-26 | Submittal Number: 05 12 00-65.2 From: BRAD KIRSCHENHEITER Final Due Date: 03/05/20 Subject: SEQUENCE 23, 9709 & 9814 QUAD A EMBEDS APPROVAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04547 | Review Response | Approved as Noted | 2020-02-27 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06257 | Responded and Closed | Approved as Noted | 2020-02-27 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review and comments. | Info Exchange
| 06355 | Sent | For Construction | 2020-03-03 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company) |  |  | Info Exchange
| 06399 | Sent | For Construction | 2020-03-04 | Josh Dobken (Populous) | Jes Pelkey (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) Remarks: See attached for review and comments. Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-19 |  | 05 12 00-65.2 Quad A Embeds-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-19 |  | 05 12 00-65.2 Quad A Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-19 |  | 05 12 00-65.2 Quad A Embeds-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-27 |  | 05 12 00-65.2 Quad A Embeds-MAM_TT_POP.pdf
| Sent |  | Todd Spangler (Populous) | 1 | 2020-02-19 |  | 05 12 00-65.2 Quad A Embeds-MAM.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-02-18 02:00 |  | 05 12 00-65.2 Quad A Embeds-MAM.pdf
05 12 00-066-00 | 05 12 00 - STEEL | 05 12 00-066-00 Quad D Structural Steel SD - Seq. 111-116 & 119-120 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-09-09 | 2019-09-10 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2019-09-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02104 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Jes Pelkey (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-09 | Submittal Number: 05 12 00-66.0 From: JES PELKEY Final Due Date: 09/02/19 Subject: QUAD D STRUCTURAL STEEL SD - SEQ. 111-116 & 119-120 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03281 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-26 | Submittal Number: 05 12 00-66.0 From: JES PELKEY Final Due Date: 09/02/19 Subject: QUAD D STRUCTURAL STEEL SD - SEQ. 111-116 & 119-120 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02313 | Review Response | Revise and Resubmit | 2019-09-04 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Revise and Resubmit column uplift base plates per TT response to RFI 1370. (2016C and 2017C). BRB gussets have not been reviewed as TT is waiting on calcs from BRB MFR. Please confirm all BRB gussets in project are being designed per "KISS" method. Coordinate framing around temporary TRS slab openings with TRS drawings. Note: coordinate openings for TRS pipe columns with TRS team. | Info Exchange
| 03544 | Forwarded | For Review | 2019-09-05 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2019-09-09 | Submittal Number: 05 12 00-66.0 From: JES PELKEY Final Due Date: 09/02/19 Subject: QUAD D STRUCTURAL STEEL SD - SEQ. 111-116 & 119-120 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02365 | Review Response | Revise and Resubmit | 2019-09-10 | Todd Spangler (Populous) | Populous SCA_CCA |  | See attached submittal comments and sketch. | Info Exchange
| 03604 | Responded and Closed | Revise and Resubmit | 2019-09-10 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal comments and sketch. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 05 12 00-66.0 Quad D Seq. 111 to 116, 119 & 120 SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-19 |  | 05 12 00-66.0 Quad D Seq. 111 to 116, 119 & 120 SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-08-18 02:00 |  | 05 12 00-66.0 Quad D Seq. 111 to 116, 119 & 120 SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-08-18 02:00 |  | 05 12 00-66.0 Quad D Seq. 111 to 116, 119 & 120 SD-MAM.pdf
| Review Response |  | Todd Spangler (Populous) | 1 | 2019-09-10 |  | 05 12 00-66.0 Quad D Seq. 111 to 116, 119 & 120 SD-MAM_TT REVIEW_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-09-10 |  | 05 12 00-66.0 Quad D Seq. 111 to 116, 119 & 120 SD-MAM_TT REVIEW_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-09-10 |  | SSK-0060 Detail 4.S4-11.pdf
05 12 00-066-01 | 05 12 00 - STEEL | 05 12 00-066-01 Quad D1 Structural Steel SD - Seq. 111-116 & 119-120 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-29 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill |  |  |  | 2019-11-12 | 2019-11-06 | 9 |  | Record Copies; Transfers; Submittals | 05 12 00-066-02 - 05 12 00-066-02 Quad D1 Structural Steel SD - Seq. 111-116 & 119-120 | 10 |  | 2019-11-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02939 | Received | For Review | 2019-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-11-12 | Submittal Number: 05 12 00-66.1 From: JES PELKEY Final Due Date: 11/11/19 Subject: QUAD D1 STRUCTURAL STEEL SD - SEQ. 111-116 & 119-120 Description: RESUBMITTAL ONLY REQUIRED FOR 2 COLUMNS Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04311 | Forwarded | For Review | 2019-10-28 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-04 | Submittal Number: 05 12 00-66.1 From: JES PELKEY Final Due Date: 11/11/19 Subject: QUAD D1 STRUCTURAL STEEL SD - SEQ. 111-116 & 119-120 Description: RESUBMITTAL ONLY REQUIRED FOR 2 COLUMNS Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03101 | Review Response | Revise and Resubmit | 2019-11-06 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has not reviewed pieces in submittal. Please resubmit with revised Corebrace calcs per TT's comments on Submittal 051200-145. Corebrace to submit connection information so TT can review connections including, but not limited to: Gusset size, thickness, unbraced length, BRB connection to gusset information, weld lengths, weld sizes. | Info Exchange
| 04501 | Responded and Closed | Revise and Resubmit | 2019-11-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: TT has not reviewed pieces in submittal. Please resubmit with revised Corebrace calcs per TT's comments on Submittal 051200-145. Corebrace to submit connection information so TT can review connections including, but not limited to: Gusset size, thickness, unbraced length, BRB connection to gusset information, weld lengths, weld sizes. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-28 |  | 05 12 00-66.1 Quad D1 Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-28 |  | 05 12 00-66.1 Quad D1 Shop Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-27 02:00 |  | 05 12 00-66.1 Quad D1 Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-06 02:00 |  | 05 12 00-66.1 Quad D1 Shop Drawings-MAM_TT REVIEW_POP.pdf
05 12 00-066-02 | 05 12 00 - STEEL | 05 12 00-066-02 Quad D1 Structural Steel SD - Seq. 111-116 & 119-120 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-09 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-23 | 2019-12-11 | 3 |  | Record Copies; Transfers; Submittals | 05 12 00-066-01 - 05 12 00-066-01 Quad D1 Structural Steel SD - Seq. 111-116 & 119-120 | 2 | 2019-11-20 | 2019-12-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03555 | Received | For Review | 2019-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-23 | Submittal Number: 05 12 00-66.2 From: JES PELKEY Final Due Date: 12/20/19 Subject: QUAD D1 STRUCTURAL STEEL SD - SEQ. 111-116 & 119-120 Description: RESUBMITTAL ONLY REQUIRED FOR 2 COLUMNS Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05048 | Forwarded | For Review | 2019-12-10 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth K... | 2019-12-17 | Submittal Number: 05 12 00-66.2 From: JES PELKEY Final Due Date: 12/20/19 Subject: QUAD D1 STRUCTURAL STEEL SD - SEQ. 111-116 & 119-120 Description: RESUBMITTAL ONLY REQUIRED FOR 2 COLUMNS Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03604 | Review Response | Approved as Noted | 2019-12-11 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 05085 | Responded and Closed | Approved as Noted | 2019-12-11 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-06 02:00 |  | 05 12 00-66.1 Quad D1 Shop Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-06 02:00 |  | 05 12 00-66.1 Quad D1 Shop Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-06 02:00 |  | 05 12 00-66.1 Quad D1 Shop Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-11 02:00 |  | 05 12 00-66.2 Quad D1 SD-MAM_TT REVIEW_POP.pdf
05 12 00-066-03 | 05 12 00 - STEEL | 05 12 00-066-03 Quad D1 Structural Steel SD - Seq. 111-116 & 119-120 - CCD41 Changes | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-11 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04227 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-20 | Submittal Number: 05 12 00-66.3 From: JES PELKEY Final Due Date: 12/20/19 Subject: QUAD D1 STRUCTURAL STEEL SD - SEQ. 111-116 & 119-120 - CCD41 CHANGES Description: RESUBMITTAL ONLY REQUIRED FOR 2 COLUMNS Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05856 | Forwarded | For Review | 2020-02-06 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 05 12 00-66.3 From: JES PELKEY Final Due Date: 12/20/19 Subject: QUAD D1 STRUCTURAL STEEL SD - SEQ. 111-116 & 119-120 - CCD41 CHANGES Description: RESUBMITTAL ONLY REQUIRED FOR 2 COLUMNS Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04317 | Review Response | Approved as Noted | 2020-02-07 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 05975 | Responded and Closed | Approved as Noted | 2020-02-11 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 05 12 00-66.3 Quad D1 SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-06 |  | 05 12 00-66.3 Quad D1 SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-06 |  | 05 12 00-66.3 Quad D1 SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-11 |  | 05 12 00-66.3 Quad D1 SD-MAM_TT_POP.pdf
05 12 00-067-00 | 05 12 00 - STEEL | 05 12 00-067-00 North Buttress - Seq. 510, 525-526 & 566 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-04 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-24 | 2019-09-25 | 22 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-09-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02288 | Received | For Review | 2019-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Jes Pelkey (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-24 | Submittal Number: 05 12 00-67.0 From: JES PELKEY Final Due Date: 09/17/19 Subject: NORTH BUTTRESS - SEQ. 510, 525-526 & 566 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03511 | Forwarded | For Review | 2019-09-04 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-11 | Submittal Number: 05 12 00-67.0 From: JES PELKEY Final Due Date: 09/17/19 Subject: NORTH BUTTRESS - SEQ. 510, 525-526 & 566 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02474 | Review Response | Approved as Noted/Resubmit | 2019-09-18 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Resubmit sheets as noted. Populous to verify dimensions as noted. | Info Exchange
| 03748 | Forwarded | For Review | 2019-09-20 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-09-24 | Submittal Number: 05 12 00-67.0 From: JES PELKEY Final Due Date: 09/17/19 Subject: NORTH BUTTRESS - SEQ. 510, 525-526 & 566 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03812 | Responded and Closed | Approved as Noted/Resubmit | 2019-09-25 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Resubmit sheets as noted. Populous to verify dimensions as noted. Only sheets indicated by TT need to be resubmitted. All other sheets are approved as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-03 |  | Sequence 510, 525, 526 Approval Package.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-03 |  | 05 12 00-67.0 Sequence 510, 525, 526 Approval Package.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-02 02:00 |  | 05 12 00-67.0 Sequence 510, 525, 526 Approval Package.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-02 02:00 |  | Sequence 510, 525, 526 Approval Package.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-25 02:00 |  | 05 12 00-67.0 Sequence 510, 525, 526 Approval Package_TT REVIEW_POP.pdf
05 12 00-067-01 | 05 12 00 - STEEL | 05 12 00-067-01 North Buttress NB1- Seq. 510, 525-526, & 566 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-10 | 2019-12-20 | 3 | General | Record Copies; Transfers; Submittals |  | 3 |  | 2019-12-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03672 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Jes Pelkey (Mortenson Construction) | 2020-01-10 | Submittal Number: 05 12 00-67.1 From: JES PELKEY Final Due Date: 01/03/20 Subject: NORTH BUTTRESS NB1- SEQ. 510, 525-526, & 566 Description: RESUBMITTAL ONLY ON THE PAGES THAT HAVE BEEN STAMPED INDIVIDUALLY AS "REVISE AND RESUBMIT". Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05192 | Forwarded | For Review | 2019-12-18 | Jes Pelkey (Mortenson Construction) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-25 | Submittal Number: 05 12 00-67.1 From: JES PELKEY Final Due Date: 01/03/20 Subject: NORTH BUTTRESS NB1- SEQ. 510, 525-526, & 566 Description: RESUBMITTAL ONLY ON THE PAGES THAT HAVE BEEN STAMPED INDIVIDUALLY AS "REVISE AND RESUBMIT". Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03722 | Review Response | Approved as Noted | 2019-12-20 | Matt Ross (Thornton Tomasetti) | Jes Pelkey (Mortenson Construction) |  |  | Info Exchange
| 05250 | Responded and Closed | Approved as Noted | 2019-12-20 | Jes Pelkey (Mortenson Construction) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 05 12 00-67.1 North Buttress NB1 SD-MAM.pdf
| Forwarded |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-12-18 |  | 05 12 00-67.1 North Buttress NB1 SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-17 02:00 |  | 05 12 00-67.1 North Buttress NB1 SD-MAM.pdf
| Responded and Closed |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-12-20 02:00 |  | 05 12 00-67.1 North Buttress NB1 SD-MAM_TT REVIEW_POP.pdf
05 12 00-068-00 | 05 12 00 - STEEL | 05 12 00-068-00 Quad D2 Structural Steel SD - Seq. 120-126 & 129-130 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-12 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2019-10-02 | 2019-10-04 | 23 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2019-10-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02388 | Received | For Review | 2019-09-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Jes Pelkey (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-10-02 | Submittal Number: 05 12 00-68.0 From: JES PELKEY Final Due Date: 09/25/19 Subject: QUAD D2 STRUCTURAL STEEL SD - SEQ. 120-126 & 129-130 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03635 | Forwarded | For Review | 2019-09-12 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-19 | Submittal Number: 05 12 00-68.0 From: JES PELKEY Final Due Date: 09/25/19 Subject: QUAD D2 STRUCTURAL STEEL SD - SEQ. 120-126 & 129-130 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02639 | Review Response | Approved as Noted/Resubmit | 2019-10-02 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | See Revise and Resubmit stamps on individual sheets for pieces TT would like to review again. Note, TT has not reviewed anything related to BRB gussets as we have not received calcs from the BRB MFR. | Info Exchange
| 03948 | Forwarded | For Review | 2019-10-02 | Josh Dobken (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2019-10-02 | Submittal Number: 05 12 00-68.0 From: JES PELKEY Final Due Date: 09/25/19 Subject: QUAD D2 STRUCTURAL STEEL SD - SEQ. 120-126 & 129-130 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03979 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-04 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for markups. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-11 |  | 05 12 00-68.0 Quad D Seq. 120-126 & 129-130 SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-11 |  | 05 12 00-68.0 Quad D Seq. 120-126 & 129-130 SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-10 02:00 |  | 05 12 00-68.0 Quad D Seq. 120-126 & 129-130 SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-10 02:00 |  | 05 12 00-68.0 Quad D Seq. 120-126 & 129-130 SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-04 |  | 05 12 00-68.0 Quad D Seq. 120-126 & 129-130 SD-MAM_TT REVIEW_POP.pdf
05 12 00-068-01 | 05 12 00 - STEEL | 05 12 00-068-01 Quad D2 Structural Steel SD - Seq. 121-126 & 129-130 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-13 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-01-27 | 2020-01-28 | 16 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-01-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03882 | Received | For Review | 2020-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-27 | Submittal Number: 05 12 00-68.1 From: JES PELKEY Final Due Date: 01/24/20 Subject: QUAD D2 STRUCTURAL STEEL SD - SEQ. 121-126 & 129-130 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05439 | Forwarded | For Review | 2020-01-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-20 | Submittal Number: 05 12 00-68.1 From: JES PELKEY Final Due Date: 01/24/20 Subject: QUAD D2 STRUCTURAL STEEL SD - SEQ. 121-126 & 129-130 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03924 | Review Response | Approved as Noted | 2020-01-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05669 | Forwarded | For Review | 2020-01-27 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-01-27 | Submittal Number: 05 12 00-68.1 From: JES PELKEY Final Due Date: 01/24/20 Subject: QUAD D2 STRUCTURAL STEEL SD - SEQ. 121-126 & 129-130 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05698 | Responded and Closed | Approved as Noted | 2020-01-28 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-10 |  | 05 12 00-68.1 Quad D2 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-10 |  | 05 12 00-68.1 Quad D2 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-09 02:00 |  | 05 12 00-68.1 Quad D2 Steel SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-09 02:00 |  | 05 12 00-68.1 Quad D2 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-28 |  | 05 12 00-68.1 Quad D2 Steel SD-MAM_TT_POP.pdf
05 12 00-070-00 | 05 12 00 - STEEL | 05 12 00-070-00 Quad D3 Structural Steel SD - Seq. 132-135, 138, 140, 145-150 & 160 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-30 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-18 | 2019-10-29 | 30 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-10-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02569 | Received | For Review | 2019-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Jes Pelkey (Mortenson Construction) | 2019-10-18 | Submittal Number: 05 12 00-70.0 From: JES PELKEY Final Due Date: 10/14/19 Subject: QUAD D3 STRUCTURAL STEEL SD - SEQ. 132-135, 138, 140, 145-150 & 160 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03857 | Forwarded | For Review | 2019-09-30 | Jes Pelkey (Mortenson Construction) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-07 | Submittal Number: 05 12 00-70.0 From: JES PELKEY Final Due Date: 10/14/19 Subject: QUAD D3 STRUCTURAL STEEL SD - SEQ. 132-135, 138, 140, 145-150 & 160 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02778 | Review Response | Approved as Noted/Resubmit | 2019-10-15 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Josh Dobken (Populous) |  | Arch to review indicated dimensions. See stamped sheets noting which pieces are to be resubmitted to design team for approval. All other pieces are approved as noted. Note: TT has not received BRB calcs and, therefore, has not reviewed any BRB connections. | Info Exchange
| 04331 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-29 | Jes Pelkey (Mortenson Construction) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. File name shortened for Newforma. See stamped sheets noting which pieces are to be resubmitted to design team for approval. All other pieces are approved as noted. Note: TT has not received BRB calcs and, therefore, has not reviewed any BRB connections. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-28 |  | 05 12 00-70.0 Quad D3 - Seq. 132-135, 138, 140, 145-150 & 160-MAM.pdf
| Forwarded |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-09-28 |  | 05 12 00-70.0 Quad D3 - Seq. 132-135, 138, 140, 145-150 & 160-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-28 |  | 05 12 00-70.0 Quad D3 - Seq. 132-135, 138, 140, 145-150 & 160-MAM.pdf
| Responded and Closed |  | Jes Pelkey (Mortenson Construction) | 1 | 2019-10-29 |  | 05 12 00-70.0 Quad D3_MAM_TT_POP.pdf
05 12 00-070-01 | 05 12 00 - STEEL | 05 12 00-070-01 Quad D3 Resubmittal - Seqs. 132 135 138 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-21 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-04 | 2020-01-27 | 7 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-01-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03994 | Received | For Review | 2020-01-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-02-04 | Submittal Number: 05 12 00-70.1 From: JES PELKEY Final Due Date: 02/03/20 Subject: QUAD D3 RESUBMITTAL - SEQS. 132 135 138 Description: BRB'S AND ELEVATOR TUBE STEEL. ELEVATOR TUBE STEEL DESIGN PENDING REDESIGN FROM TT. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05573 | Forwarded | For Review | 2020-01-21 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-28 | Submittal Number: 05 12 00-70.1 From: JES PELKEY Final Due Date: 02/03/20 Subject: QUAD D3 RESUBMITTAL - SEQS. 132 135 138 Description: BRB'S AND ELEVATOR TUBE STEEL. ELEVATOR TUBE STEEL DESIGN PENDING REDESIGN FROM TT. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04069 | Review Response | Approved as Noted | 2020-01-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05660 | Responded and Closed | Approved as Noted | 2020-01-27 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-20 |  | 05 12 00-70.1 Quad D3 Resubmittal - Seqs. 132 135 138 (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-20 |  | 05 12 00-70.1 Quad D3 Resubmittal - Seqs. 132 135 138 (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-19 02:00 |  | 05 12 00-70.1 Quad D3 Resubmittal - Seqs. 132 135 138 (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-27 02:00 |  | 05 12 00-70.1 Quad D3 Resubmittal - Seqs. 132 135 138 (MAM Review)_TT REVIEW_POP.pdf
05 12 00-074-00 | 05 12 00 - STEEL | 05 12 00-074-00 North Buttress - Seq. 131 NB1 & 136-137 NB2 and NB3 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-24 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-08 | 2019-10-09 | 16 |  | Record Copies; Transfers; Submittals |  | 14 | 2019-09-23 | 2019-10-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02515 | Received | For Review | 2019-09-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Josh Dobken (Populous) | 2019-10-08 | Submittal Number: 05 12 00-74.0 From: JES PELKEY Final Due Date: 10/07/19 Subject: NORTH BUTTRESS - SEQ. 131 NB1 & 136-137 NB2 AND NB3 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03794 | Forwarded | For Review | 2019-09-25 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2019-10-02 | Submittal Number: 05 12 00-74.0 From: JES PELKEY Final Due Date: 10/07/19 Subject: NORTH BUTTRESS - SEQ. 131 NB1 & 136-137 NB2 AND NB3 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02696 | Review Response | Approved as Noted/Resubmit | 2019-10-08 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | See stamps on sheets for which pieces TT needs to review again once revised. All other sheets are approved as noted. | Info Exchange
| 04048 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-09 | Josh Dobken (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-23 02:00 |  | 05 12 00-74.0 North Buttress - Seq. 131, 136-137-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-23 02:00 |  | 05 12 00-74.0 North Buttress - Seq. 131, 136-137-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-23 |  | 05 12 00-74.0 North Buttress - Seq. 131, 136-137-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-09 |  | 05 12 00-74.0 North Buttress - Seq. 131, 136-137-MAM_TT REVIEW_POP.pdf
05 12 00-074-01 | 05 12 00 - STEEL | 05 12 00-074-01 North Buttress NB2 - Seq. 131 & 136-137 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-04 08:00 | 2019-12-04 | 17 |  | Record Copies; Transfers; Submittals | 05 12 00-074-02 - 05 12 00-074-02 North Buttress NB2 - Seq. 131 & 136-137 | 17 |  | 2019-12-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03227 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-04 08:00 | Submittal Number: 05 12 00-74.1 From: JES PELKEY Final Due Date: 12/03/19 Subject: NORTH BUTTRESS NB2 - SEQ. 131 & 136-137 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04666 | Forwarded | For Review | 2019-11-18 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-25 | Submittal Number: 05 12 00-74.1 From: JES PELKEY Final Due Date: 12/03/19 Subject: NORTH BUTTRESS NB2 - SEQ. 131 & 136-137 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03499 | Review Response | Approved as Noted/Resubmit | 2019-12-04 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Please provide girders to review connection material as noted. | Info Exchange
| 04961 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-04 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-18 |  | 05 12 00-74.1 North Buttress NB2 SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-18 |  | 05 12 00-74.1 North Buttress NB2 SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-18 |  | 05 12 00-74.1 North Buttress NB2 SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-04 |  | 05 12 00-74.1 North Buttress NB2 SD-MAM_TT_POP.pdf
05 12 00-074-02 | 05 12 00 - STEEL | 05 12 00-074-02 North Buttress NB2 - Seq. 131 & 136-137 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-04 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-18 | 2019-12-06 | 3 |  | Record Copies; Transfers; Submittals | 05 12 00-074-01 - 05 12 00-074-01 North Buttress NB2 - Seq. 131 & 136-137 | 1 | 2019-12-18 | 2019-12-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03523 | Received | For Review | 2019-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-18 | Submittal Number: 05 12 00-74.2 From: JES PELKEY Final Due Date: 12/18/19 Subject: NORTH BUTTRESS NB2 - SEQ. 131 & 136-137 - BEAM 2995B Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04989 | Forwarded | For Review | 2019-12-05 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth K... | 2019-12-12 | Submittal Number: 05 12 00-74.2 From: JES PELKEY Final Due Date: 12/18/19 Subject: NORTH BUTTRESS NB2 - SEQ. 131 & 136-137 - BEAM 2995B Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03525 | Review Response | Approved | 2019-12-05 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04994 | Responded and Closed | Approved | 2019-12-06 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. Thanks | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-04 02:00 |  | 05 12 00-74.2 North Buttress NB2 Beam 2995B-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-04 02:00 |  | 05 12 00-74.2 North Buttress NB2 Beam 2995B-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-04 |  | 05 12 00-74.2 North Buttress NB2 Beam 2995B-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-06 |  | 05 12 00-74.2 North Buttress NB2 Beam 2995B-MAM_TT_POP.pdf
05 12 00-076-00 | 05 12 00 - STEEL | 05 12 00-076-00 North Buttress - Seq. 143a & 143b | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-25 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-10-09 | 2019-10-11 | 17 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-10-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02519 | Received | For Review | 2019-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Jes Pelkey (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-10-09 | Submittal Number: 05 12 00-76.0 From: JES PELKEY Final Due Date: 10/08/19 Subject: NORTH BUTTRESS - SEQ. 143A & 143B Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03798 | Forwarded | For Review | 2019-09-25 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2019-10-02 | Submittal Number: 05 12 00-76.0 From: JES PELKEY Final Due Date: 10/08/19 Subject: NORTH BUTTRESS - SEQ. 143A & 143B Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02713 | Review Response | Approved as Noted | 2019-10-09 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Arch to review dimensions and specific comments from TT. | Info Exchange
| 04051 | Forwarded | For Review | 2019-10-09 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-10-09 | Submittal Number: 05 12 00-76.0 From: JES PELKEY Final Due Date: 10/08/19 Subject: NORTH BUTTRESS - SEQ. 143A & 143B Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04076 | Responded and Closed | Approved as Noted | 2019-10-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-25 02:00 |  | 05 12 00-76.0 North Buttress - Seq. 143a & 143b-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-25 02:00 |  | 05 12 00-76.0 North Buttress - Seq. 143a & 143b-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-25 02:00 |  | 05 12 00-76.0 North Buttress - Seq. 143a & 143b-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-25 02:00 |  | 05 12 00-76.0 North Buttress - Seq. 143a & 143b-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-11 |  | 05 12 00-76.0 North Buttress - Seq. 143a & 143b-MAM_TT REVIEW_POP.pdf
05 12 00-076-01 | 05 12 00 - STEEL | 05 12 00-076-01 North Buttress NB3 - Seq. 143a & 143b | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-17 | 12 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04233 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-20 | Submittal Number: 05 12 00-76.1 From: JES PELKEY Final Due Date: 02/17/20 Subject: NORTH BUTTRESS NB3 - SEQ. 143A & 143B Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05862 | Forwarded | For Review | 2020-02-06 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 05 12 00-76.1 From: JES PELKEY Final Due Date: 02/17/20 Subject: NORTH BUTTRESS NB3 - SEQ. 143A & 143B Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04362 | Review Response | Approved as Noted | 2020-02-07 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06032 | Responded and Closed | Approved as Noted | 2020-02-17 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 05 12 00-76.1 North Buttress NB3-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-06 |  | 05 12 00-76.1 North Buttress NB3-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-06 |  | 05 12 00-76.1 North Buttress NB3-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-17 |  | 05 12 00-76.1 North Buttress NB3-MAM_TT_POP.pdf
05 12 00-077-00 | 05 12 00 - STEEL | 05 12 00-077-00 Quad D4 Structural Steel SD - Seq. 139, 141-142, 144 & 151-156 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-22 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Nick Theimer (ME Engineers), Chris Minter (Populous), Josh Dobken (Populous), Heidi Evans (ME Engineers) |  |  |  | 2019-11-13 | 2019-11-20 | 30 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2019-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02873 | Received | For Review | 2019-10-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-11-13 | Submittal Number: 05 12 00-77.0 From: JES PELKEY Final Due Date: 11/04/19 Subject: QUAD D4 STRUCTURAL STEEL SD - SEQ. 139, 141-142, 144 & 151-156 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04236 | Forwarded | For Review | 2019-10-22 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-29 | Submittal Number: 05 12 00-77.0 From: JES PELKEY Final Due Date: 11/04/19 Subject: QUAD D4 STRUCTURAL STEEL SD - SEQ. 139, 141-142, 144 & 151-156 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03196 | Review Response | Approved as Noted/Resubmit | 2019-11-13 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | See stamped sheets for pieces TT needs to review again once revised. All other sheets are approved as noted. Corebrace to submit revised calcs and organized connection information for TT to review BRB connections. There were a few locations where channel framing was too close to opening. Coordination with MEP required to locate web penetrations a minimum of 1 beam depth from edge of web penetration per 4&6/S5-11. | Info Exchange
| 04627 | Forwarded | For Review | 2019-11-14 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Nick Theimer (ME Engineers); Chris Minter (Populous); Josh Dobken (Populous); Heidi Evans (ME Engineers) | 2019-11-13 | Submittal Number: 05 12 00-77.0 From: JES PELKEY Final Due Date: 11/04/19 Subject: QUAD D4 STRUCTURAL STEEL SD - SEQ. 139, 141-142, 144 & 151-156 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04730 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-20 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attach for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-21 |  | 05 12 00-77.0 Quad D4 Steel SD-MAm.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-21 |  | 05 12 00-77.0 Quad D4 Steel SD-MAm.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-20 02:00 |  | 05 12 00-77.0 Quad D4 Steel SD-MAm.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-10-20 02:00 |  | 05 12 00-77.0 Quad D4 Steel SD-MAm.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-11-20 |  | 05 12 00-77.0 Quad D4 Steel SD-MAM_TT REVIEW_POP.pdf
05 12 00-077-01 | 05 12 00 - STEEL | 05 12 00-077-01 Quad D4 Resubmittal - Seq. 139 141 142 144 151-156 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-23 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-06 | 2020-01-30 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-01-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04032 | Received | For Review | 2020-01-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-02-06 | Submittal Number: 05 12 00-77.1 From: JES PELKEY Final Due Date: 02/06/20 Subject: QUAD D4 RESUBMITTAL - SEQ. 139 141 142 144 151-156 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05619 | Forwarded | For Review | 2020-01-23 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-30 | Submittal Number: 05 12 00-77.1 From: JES PELKEY Final Due Date: 02/06/20 Subject: QUAD D4 RESUBMITTAL - SEQ. 139 141 142 144 151-156 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04144 | Review Response | Revise and Resubmit | 2020-01-30 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has only reviewed pieces of submittal that have been clouded or marked to be revised in previous submittal. Please revise with updated elevator layout. Please include missing pieces that were revised as part of reframing at Press Level. For all proposed beam web penetration shifts, please submit RFI for TT to review and approve. If proposed locations are not acceptable or if TT advises to add reinforcement plates at penetrations, these members will need to be resubmit for approval. All pieces that are unstamped and are not affected by the above comments are approved as noted. | Info Exchange
| 05748 | Responded and Closed | Approved as Noted/Resubmit | 2020-01-30 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: TT has only reviewed pieces of submittal that have been clouded or marked to be revised in previous submittal. Please revise with updated elevator layout. Please include missing pieces that were revised as part of reframing at Press Level. For all proposed beam web penetration shifts, please submit RFI for TT to review and approve. If proposed locations are not acceptable or if TT advises to add reinforcement plates at penetrations, these members will need to be resubmit for approval. All pieces that are unstamped and are not affected by the above comments are approved as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-22 |  | 05 12 00-77.1 Quad D4 Resubmittal - Seq. 139 141 142 144 151-156 (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-22 |  | 05 12 00-77.1 Quad D4 Resubmittal - Seq. 139 141 142 144 151-156 (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-21 02:00 |  | 05 12 00-77.1 Quad D4 Resubmittal - Seq. 139 141 142 144 151-156 (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-30 02:00 |  | 05 12 00-77.1 Quad D4 Resubmittal - Seq. 139 141 142 144 151-156 (MAM Review)_TT REVIEW_POP.pdf
05 12 00-077-02 | 05 12 00 - STEEL | 05 12 00-077-02 Quad D4 RR and Elevator D1 Affected Members | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-20 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-05 | 2020-03-09 | 19 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04425 | Received | For Review | 2020-02-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-05 | Submittal Number: 05 12 00-77.2 From: JES PELKEY Final Due Date: 03/05/20 Subject: QUAD D4 RR AND ELEVATOR D1 AFFECTED MEMBERS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06112 | Forwarded | For Review | 2020-02-20 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-27 | Submittal Number: 05 12 00-77.2 From: JES PELKEY Final Due Date: 03/05/20 Subject: QUAD D4 RR AND ELEVATOR D1 AFFECTED MEMBERS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04638 | Review Response | Approved as Noted | 2020-03-03 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06462 | Responded and Closed | Approved as Noted | 2020-03-09 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-20 |  | 05 12 00-77.2 Quad D4 RR and D1 Elevator Changes-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-20 |  | 05 12 00-77.2 Quad D4 RR and D1 Elevator Changes-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-20 |  | 05 12 00-77.2 Quad D4 RR and D1 Elevator Changes-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-09 |  | 05 12 00-77.2 Quad D4 RR and D1 Elevator Changes-MAM_TT_POP.pdf
05 12 00-078-00 | 05 12 00 - STEEL | 05 12 00-078-00 Quad C1 Structural Steel - Seq. 511-514, 519, 527, 536-537 & 540-541 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-08 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-28 | 2019-10-29 | 22 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2019-10-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02689 | Received | For Review | 2019-10-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-10-28 | Submittal Number: 05 12 00-78.0 From: JES PELKEY Final Due Date: 10/21/19 Subject: QUAD C1 STRUCTURAL STEEL - SEQ. 511-514, 519, 527, 536-537 & 540-541 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04015 | Forwarded | For Review | 2019-10-07 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-14 | Submittal Number: 05 12 00-78.0 From: JES PELKEY Final Due Date: 10/21/19 Subject: QUAD C1 STRUCTURAL STEEL - SEQ. 511-514, 519, 527, 536-537 & 540-541 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02916 | Review Response | Approved as Noted/Resubmit | 2019-10-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Refer to stamps on sheets for pieces TT would like to review again once revised. All other sheets are approved as noted. TT has not reviewed any BRB connections as we have not received calcs from BRB MFR. Refer to RFI 1429 and design from Conserv per Submittal 051200-056.2 for changes to Slide Bearings. Finalized details to be issued pending Mortenson's approval of revised detail. | Info Exchange
| 04320 | Responded and Closed | Revise and Resubmit | 2019-10-29 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for review and comments. POP had to revise the file name so that it was shorter. It's a Newforma thing. Refer to stamps on sheets for pieces TT would like to review again once revised. All other sheets are approved as noted. TT has not reviewed any BRB connections as we have not received calcs from BRB MFR. Refer to RFI 1429 and design from Conserv per Submittal 051200-056.2 for changes to Slide Bearings. Finalized details to be issued pending Mortenson's approval of revised detail. Thanks | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-07 |  | 05 12 00-78.0 Quad C1 Steel SD- Seq. 511-514, 519, 527, 536-537 & 540-541-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-07 |  | 05 12 00-78.0 Quad C1 Steel SD- Seq. 511-514, 519, 527, 536-537 & 540-541-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-06 02:00 |  | 05 12 00-78.0 Quad C1 Steel SD- Seq. 511-514, 519, 527, 536-537 & 540-541-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-29 |  | 05 12 00-78.0 Quad C1 Steel SD_MAM_TT_POP.pdf
05 12 00-078-01 | 05 12 00 - STEEL | 05 12 00-078-01 Quad C1 Structural Steel - Seq. 511-514, 519, 527, 536-537 & 540-541 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-13 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-27 | 2020-01-14 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03886 | Received | For Review | 2020-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-27 | Submittal Number: 05 12 00-78.1 From: JES PELKEY Final Due Date: 01/27/20 Subject: QUAD C1 STRUCTURAL STEEL - SEQ. 511-514, 519, 527, 536-537 & 540-541 Description: BRB'S, SLIDE BEARING CONNECTIONS, AND ESCALATOR STEEL. ESCALATOR STEEL WILL BE RE-ISSUED IN UPCOMING CCD/RFI. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05443 | Forwarded | For Review | 2020-01-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-20 | Submittal Number: 05 12 00-78.1 From: JES PELKEY Final Due Date: 01/27/20 Subject: QUAD C1 STRUCTURAL STEEL - SEQ. 511-514, 519, 527, 536-537 & 540-541 Description: BRB'S, SLIDE BEARING CONNECTIONS, AND ESCALATOR STEEL. ESCALATOR STEEL WILL BE RE-ISSUED IN UPCOMING CCD/RFI. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03921 | Review Response | Approved as Noted | 2020-01-14 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05484 | Responded and Closed | Approved as Noted | 2020-01-14 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-13 |  | 05 12 00-78.1 Quad C1 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-13 |  | 05 12 00-78.1 Quad C1 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-12 02:00 |  | 05 12 00-78.1 Quad C1 Steel SD-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-14 02:00 |  | 05 12 00-78.1 Quad C1 Steel SD-MAM_TT REVIEW_POP.pdf
05 12 00-078-02 | 05 12 00 - STEEL | 05 12 00-078-02 Quad C1 Structural Steel - Seq. 511-514, 519, 527, 536-537 & 540-541 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-27 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-10 | 2020-02-17 | 22 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04082 | Received | For Review | 2020-01-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-02-10 | Submittal Number: 05 12 00-78.2 From: JES PELKEY Final Due Date: 02/07/20 Subject: QUAD C1 STRUCTURAL STEEL - SEQ. 511-514, 519, 527, 536-537 & 540-541 Description: BRB'S, SLIDE BEARING CONNECTIONS, AND ESCALATOR STEEL. ESCALATOR STEEL WILL BE RE-ISSUED IN UPCOMING CCD/RFI. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05675 | Forwarded | For Review | 2020-01-27 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-03 | Submittal Number: 05 12 00-78.2 From: JES PELKEY Final Due Date: 02/07/20 Subject: QUAD C1 STRUCTURAL STEEL - SEQ. 511-514, 519, 527, 536-537 & 540-541 Description: BRB'S, SLIDE BEARING CONNECTIONS, AND ESCALATOR STEEL. ESCALATOR STEEL WILL BE RE-ISSUED IN UPCOMING CCD/RFI. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04363 | Review Response | Approved as Noted/Resubmit | 2020-02-10 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please revise Main Concourse framing per escalator reframe and WTR changes per latest drawings. Populous to confirm slab edges as noted. Note: contrary to the description of this submittal, no BRBs or Slide Bearings were included in this Rev. | Info Exchange
| 06035 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-17 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-27 |  | 05 12 00-78.2 Quad C1 Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-27 |  | 05 12 00-78.2 Quad C1 Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-27 |  | 05 12 00-78.2 Quad C1 Resubmittal (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-17 |  | 05 12 00-78.2 Quad C1 Resubmittal (MAM Review)_TT_POP.pdf
05 12 00-078-03 | 05 12 00 - STEEL | 05 12 00-078-03 Quad C1 Structural Steel - Escalator Framing | Closed | Structural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-12 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC) |  |  |  | 2020-03-26 | 2020-03-17 | 6 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04792 | Received | For Review | 2020-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company); Nate Weingart (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-03-26 | Submittal Number: 05 12 00-78.3 From: JES PELKEY Final Due Date: 03/26/20 Subject: QUAD C1 STRUCTURAL STEEL - ESCALATOR FRAMING Description: BRB'S, SLIDE BEARING CONNECTIONS, AND ESCALATOR STEEL. ESCALATOR STEEL WILL BE RE-ISSUED IN UPCOMING CCD/RFI. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06568 | Forwarded | For Review | 2020-03-12 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-19 | Submittal Number: 05 12 00-78.3 From: JES PELKEY Final Due Date: 03/26/20 Subject: QUAD C1 STRUCTURAL STEEL - ESCALATOR FRAMING Description: BRB'S, SLIDE BEARING CONNECTIONS, AND ESCALATOR STEEL. ESCALATOR STEEL WILL BE RE-ISSUED IN UPCOMING CCD/RFI. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04869 | Review Response | Approved as Noted | 2020-03-13 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06653 | Forwarded | For Review | 2020-03-16 | Josh Dobken (Populous) | Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC) | 2020-03-23 | Submittal Number: 05 12 00-78.3 From: JES PELKEY Final Due Date: 03/26/20 Subject: QUAD C1 STRUCTURAL STEEL - ESCALATOR FRAMING Description: BRB'S, SLIDE BEARING CONNECTIONS, AND ESCALATOR STEEL. ESCALATOR STEEL WILL BE RE-ISSUED IN UPCOMING CCD/RFI. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04893 | Review Response | Not Required For Review | 2020-03-16 | Scott Shepler (Fortune Shepler Saling FS2EC) | Josh Dobken (Populous) |  | This item is for TT review, not FS2. | Info Exchange
| 06657 | Responded and Closed | Approved as Noted | 2020-03-17 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-12 |  | 05 12 00-78.3 Quad C1 Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-12 |  | 05 12 00-78.3 Quad C1 Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-12 |  | 05 12 00-78.3 Quad C1 Steel SD RR-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-11 02:00 |  | 05 12 00-78.3 Quad C1 Steel SD RR-MAM.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-03-11 02:00 |  | 05 12 00-78.3 Quad C1 Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-17 |  | 05 12 00-78.3 Quad C1 Steel SD RR-MAM_TT_POP.pdf
05 12 00-079-00 | 05 12 00 - STEEL | 05 12 00-079-00 Quad D5 Structural Steel - Seq. 156-158 & 199 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-28 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill |  |  |  | 2019-11-11 | 2019-11-14 | 18 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-11-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02936 | Received | For Review | 2019-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-11-11 | Submittal Number: 05 12 00-79.0 From: JES PELKEY Final Due Date: 11/11/19 Subject: QUAD D5 STRUCTURAL STEEL - SEQ. 156-158 & 199 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04308 | Forwarded | For Review | 2019-10-28 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-04 | Submittal Number: 05 12 00-79.0 From: JES PELKEY Final Due Date: 11/11/19 Subject: QUAD D5 STRUCTURAL STEEL - SEQ. 156-158 & 199 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03163 | Review Response | Approved as Noted/Resubmit | 2019-11-11 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | See stamped sheets for pieces TT requires a subsequent review of. BRB connections not reviewed. Refer to TT response to RFI 1769 for resubmittal of calcs. | Info Exchange
| 04628 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-14 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-28 |  | 05 12 00-79.0 Quad D5 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-28 |  | 05 12 00-79.0 Quad D5 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-28 |  | 05 12 00-79.0 Quad D5 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-11-14 |  | 05 12 00-79.0 Quad D5 Steel SD-MAM_TT_POP.pdf
05 12 00-079-01 | 05 12 00 - STEEL | 05 12 00-079-01 Quad D5 Structural Steel - Seq. 156-158 & 199 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-24 | 2020-02-25 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04271 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-02-24 | Submittal Number: 05 12 00-79.1 From: JES PELKEY Final Due Date: 02/21/20 Subject: QUAD D5 STRUCTURAL STEEL - SEQ. 156-158 & 199 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05912 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-17 | Submittal Number: 05 12 00-79.1 From: JES PELKEY Final Due Date: 02/21/20 Subject: QUAD D5 STRUCTURAL STEEL - SEQ. 156-158 & 199 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04492 | Review Response | Approved as Noted | 2020-02-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06186 | Responded and Closed | Approved as Noted | 2020-02-25 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-10 |  | 05 12 00-79.1 Quad D5 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 05 12 00-79.1 Quad D5 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-10 |  | 05 12 00-79.1 Quad D5 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-25 |  | 05 12 00-79.1 Quad D5 Steel SD-MAM_TT_POP.pdf
05 12 00-080-00 | 05 12 00 - STEEL | 05 12 00-080-00 Quad C2 Structural Steel - Seq. 515-518, 520-522, 524, 530, 542-543 & 546-547 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-05 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-11-26 08:00 | 2019-12-04 | 30 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2019-12-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03044 | Received | For Review | 2019-11-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-11-26 08:00 | Submittal Number: 05 12 00-80.0 From: JES PELKEY Final Due Date: 11/18/19 Subject: QUAD C2 STRUCTURAL STEEL - SEQ. 515-518, 520-522, 524, 530, 542-543 & 546-547 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04434 | Forwarded | For Review | 2019-11-05 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-12 | Submittal Number: 05 12 00-80.0 From: JES PELKEY Final Due Date: 11/18/19 Subject: QUAD C2 STRUCTURAL STEEL - SEQ. 515-518, 520-522, 524, 530, 542-543 & 546-547 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03393 | Review Response | Approved as Noted/Resubmit | 2019-11-26 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | See individual stamps on sheets for pieces TT needs to review again once revised. | Info Exchange
| 04859 | Forwarded | For Review | 2019-11-26 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-11-26 | Submittal Number: 05 12 00-80.0 From: JES PELKEY Final Due Date: 11/18/19 Subject: QUAD C2 STRUCTURAL STEEL - SEQ. 515-518, 520-522, 524, 530, 542-543 & 546-547 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04962 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-04 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-04 |  | 05 12 00-80.0 Quad C2 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-04 |  | 05 12 00-80.0 Quad C2 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-03 01:00 |  | 05 12 00-80.0 Quad C2 Steel SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-03 01:00 |  | 05 12 00-80.0 Quad C2 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-12-04 |  | 05 12 00-80.0 Quad C2 Steel SD-MAM_TT_POP.pdf
05 12 00-080-01 | 05 12 00 - STEEL | 05 12 00-080-01 Quad C2 Structural Steel - Seq. 515-518, 520-522, 530, 542-543 & 546-547 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-30 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-13 | 2020-02-17 | 19 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04140 | Received | For Review | 2020-01-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-02-13 | Submittal Number: 05 12 00-80.1 From: JES PELKEY Final Due Date: 02/13/20 Subject: QUAD C2 STRUCTURAL STEEL - SEQ. 515-518, 520-522, 530, 542-543 & 546-547 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05743 | Forwarded | For Review | 2020-01-30 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-06 | Submittal Number: 05 12 00-80.1 From: JES PELKEY Final Due Date: 02/13/20 Subject: QUAD C2 STRUCTURAL STEEL - SEQ. 515-518, 520-522, 530, 542-543 & 546-547 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04366 | Review Response | Approved as Noted | 2020-02-12 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06036 | Responded and Closed | Approved as Noted | 2020-02-17 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-30 |  | 05 12 00-80.1 Quad C2 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-30 |  | 05 12 00-80.1 Quad C2 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-30 |  | 05 12 00-80.1 Quad C2 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-17 |  | 05 12 00-80.1 Quad C2 Steel SD-MAM_TT_POP.pdf
05 12 00-081-00 | 05 12 00 - STEEL | 05 12 00-081-00 East Buttress EB - Seq. 117-118, 127-128, & 166 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-13 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-09-27 | 2019-09-25 | 13 |  | Record Copies; Transfers; Submittals | 05 12 00-081-00-01 - 05 12 00-081-00 East Buttress EB - Seq. 117-118, 127-128, & 166 | 13 |  | 2019-09-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02400 | Received | For Review | 2019-09-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Jes Pelkey (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-27 | Submittal Number: 05 12 00-81.0 From: JES PELKEY Final Due Date: 09/26/19 Subject: EAST BUTTRESS EB - SEQ. 117-118, 127-128, & 166 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03652 | Forwarded | For Review | 2019-09-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-20 | Submittal Number: 05 12 00-81.0 From: JES PELKEY Final Due Date: 09/26/19 Subject: EAST BUTTRESS EB - SEQ. 117-118, 127-128, & 166 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02528 | Review Response | Approved as Noted/Resubmit | 2019-09-25 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached for which sheets need to be resubmitted. TT waiting on Corebrace calcs to review BRB connections. | Info Exchange
| 03810 | Responded and Closed | Approved as Noted/Resubmit | 2019-09-25 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: See attached for which sheets need to be resubmitted. TT waiting on Corebrace calcs to review BRB connections. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-12 |  | 05 12 00-81.0 East Buttress EB - Seq. 117-118, 127-128, & 166-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-12 |  | 05 12 00-81.0 East Buttress EB - Seq. 117-118, 127-128, & 166-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-11 02:00 |  | 05 12 00-81.0 East Buttress EB - Seq. 117-118, 127-128, & 166-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-25 02:00 |  | 05 12 00-81.0 East Buttress EB - Seq. 117-118, 127-128, & 166-MAM_TT REVIEW_POP.pdf
05 12 00-081-00-01 | 05 12 00 - STEEL | 05 12 00-081-00 East Buttress EB - Seq. 117-118, 127-128, & 166 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 12 00-081-00 - 05 12 00-081-00 East Buttress EB - Seq. 117-118, 127-128, & 166 | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-25 02:00 |  | 05 12 00-81.0 East Buttress EB - Seq. 117-118, 127-128, & 166-MAM_TT REVIEW_POP.pdf
05 12 00-083-00 | 05 12 00 - STEEL | 05 12 00-083-00 Quad C3A Structural Steel - Seq. 523, 528-529, 531-532, 534 & 548-555 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-13 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-11-27 | 2019-12-10 | 28 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2019-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03183 | Received | For Review | 2019-11-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-11-27 | Submittal Number: 05 12 00-83.0 From: JES PELKEY Final Due Date: 11/28/19 Subject: QUAD C3A STRUCTURAL STEEL - SEQ. 523, 528-529, 531-532, 534 & 548-555 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04607 | Forwarded | For Review | 2019-11-13 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-20 | Submittal Number: 05 12 00-83.0 From: JES PELKEY Final Due Date: 11/28/19 Subject: QUAD C3A STRUCTURAL STEEL - SEQ. 523, 528-529, 531-532, 534 & 548-555 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03552 | Review Response | Approved as Noted/Resubmit | 2019-12-06 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | See stamps on sheets for pieces TT will need to review again once revised. Please submit an RFI for all missing connections. | Info Exchange
| 05021 | Forwarded | For Review | 2019-12-09 | Populous SCA_CCA | Todd Spangler (Populous) | 2019-11-27 | Submittal Number: 05 12 00-83.0 From: JES PELKEY Final Due Date: 11/28/19 Subject: QUAD C3A STRUCTURAL STEEL - SEQ. 523, 528-529, 531-532, 534 & 548-555 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05029 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-10 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comment. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-13 |  | 05 12 00-83.0 Quad C3A Shop Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-13 |  | 05 12 00-83.0 Quad C3A Shop Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-12 02:00 |  | 05 12 00-83.0 Quad C3A Shop Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-12 02:00 |  | 05 12 00-83.0 Quad C3A Shop Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-10 |  | 05 12 00-83.0 Quad C3A Shop Drawings-MAM_TT_POP.pdf
05 12 00-083-01 | 05 12 00 - STEEL | 05 12 00-083-01 Quad C3A Structural Steel - Seq. 523, 528-529, 531-532, 534 & 548-555 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-28 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-11 | 2020-02-17 | 21 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04086 | Received | For Review | 2020-01-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-11 | Submittal Number: 05 12 00-83.1 From: JES PELKEY Final Due Date: 02/10/20 Subject: QUAD C3A STRUCTURAL STEEL - SEQ. 523, 528-529, 531-532, 534 & 548-555 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05679 | Forwarded | For Review | 2020-01-28 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-04 | Submittal Number: 05 12 00-83.1 From: JES PELKEY Final Due Date: 02/10/20 Subject: QUAD C3A STRUCTURAL STEEL - SEQ. 523, 528-529, 531-532, 534 & 548-555 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04367 | Review Response | Approved as Noted/Resubmit | 2020-02-07 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Please provide HSS to W21 as noted in CCD-041. Please resubmit piece 5421G for approval. | Info Exchange
| 06037 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-17 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. Please provide HSS to W21 as noted in CCD-041. Please resubmit piece 5421G for approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-27 |  | 05 12 00-83.1 Quad C3A Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-01-27 |  | 05 12 00-83.1 Quad C3A Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-27 |  | 05 12 00-83.1 Quad C3A Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-17 |  | 05 12 00-83.1 Quad C3A Steel SD-MAM_TT_POP.pdf
05 12 00-083-02 | 05 12 00 - STEEL | 05 12 00-083-02 Quad C3A Structural Steel - 5421G | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-18 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-01 | 2020-03-23 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04912 | Received | For Review | 2020-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-01 | Submittal Number: 05 12 00-83.2 From: JES PELKEY Final Due Date: 04/01/20 Subject: QUAD C3A STRUCTURAL STEEL - 5421G Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06706 | Forwarded | For Review | 2020-03-18 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-25 | Submittal Number: 05 12 00-83.2 From: JES PELKEY Final Due Date: 04/01/20 Subject: QUAD C3A STRUCTURAL STEEL - 5421G Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04975 | Review Response | Approved | 2020-03-19 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06784 | Responded and Closed | Approved | 2020-03-23 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-18 |  | 05 12 00-83.2 Quad C3A Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-18 |  | 05 12 00-83.2 Quad C3A Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-18 |  | 05 12 00-83.2 Quad C3A Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-23 |  | 05 12 00-83.2 Quad C3A Steel SD RR-MAM_TT_POP.pdf
05 12 00-084-00 | 05 12 00 - STEEL | 05 12 00-084-00 Quad A1 Structural Steel - Seq. 211-216 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-15 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-12-09 | 2019-12-13 | 29 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2019-12-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03204 | Received | For Review | 2019-11-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-12-09 | Submittal Number: 05 12 00-84.0 From: JES PELKEY Final Due Date: 11/29/19 Subject: QUAD A1 STRUCTURAL STEEL - SEQ. 211-216 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04637 | Forwarded | For Review | 2019-11-15 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-22 | Submittal Number: 05 12 00-84.0 From: JES PELKEY Final Due Date: 11/29/19 Subject: QUAD A1 STRUCTURAL STEEL - SEQ. 211-216 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03606 | Review Response | Approved as Noted | 2019-12-11 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Elevator A2 and A3 being revised by TT. Please issue RFI for all missing connections | Info Exchange
| 05087 | Forwarded | For Review | 2019-12-11 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2019-12-09 | Submittal Number: 05 12 00-84.0 From: JES PELKEY Final Due Date: 11/29/19 Subject: QUAD A1 STRUCTURAL STEEL - SEQ. 211-216 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05111 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-13 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-14 |  | 05 12 00-84.0 Quad A1 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-14 |  | 05 12 00-84.0 Quad A1 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-13 02:00 |  | 05 12 00-84.0 Quad A1 Steel SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-13 02:00 |  | 05 12 00-84.0 Quad A1 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-12-13 |  | 05 12 00-84.0 Quad A1 Steel SD-MAM_TT_POP.pdf
05 12 00-084-01 | 05 12 00 - STEEL | 05 12 00-084-01 Quad A1 Structural Steel - Seq. 211-216 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-23 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-07 | 2020-04-28 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05506 | Received | For Review | 2020-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-05-07 | Submittal Number: 05 12 00-84.1 From: JES PELKEY Final Due Date: 05/06/20 Subject: QUAD A1 STRUCTURAL STEEL - SEQ. 211-216 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07465 | Forwarded | For Review | 2020-04-22 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-29 | Submittal Number: 05 12 00-84.1 From: JES PELKEY Final Due Date: 05/06/20 Subject: QUAD A1 STRUCTURAL STEEL - SEQ. 211-216 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05614 | Review Response | Approved as Noted | 2020-04-27 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please submit RFI for divider beam clash at Mech Mezz as noted. | Info Exchange
| 07610 | Responded and Closed | Approved as Noted | 2020-04-28 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 05 12 00-84.1 Quad A1 Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 05 12 00-84.1 Quad A1 Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-22 |  | 05 12 00-84.1 Quad A1 Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-28 |  | 05 12 00-84.1 Quad A1 Steel SD RR-MAM_TT_POP.pdf
05 12 00-085-00 | 05 12 00 - STEEL | 05 12 00-085-00 Quad C3B Structural Steel - Seq. 556-563 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-13 | 2019-12-18 | 28 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2019-12-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03301 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-13 | Submittal Number: 05 12 00-85.0 From: JES PELKEY Final Due Date: 12/05/19 Subject: QUAD C3B STRUCTURAL STEEL - SEQ. 556-563 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04755 | Forwarded | For Review | 2019-11-21 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-27 | Submittal Number: 05 12 00-85.0 From: JES PELKEY Final Due Date: 12/05/19 Subject: QUAD C3B STRUCTURAL STEEL - SEQ. 556-563 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03691 | Review Response | Approved as Noted/Resubmit | 2019-12-18 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | See individual stamps on sheets for pieces TT is required to review again once revised. All other pieces are approved as noted. | Info Exchange
| 05216 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-18 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: See individual stamps on sheets for pieces TT is required to review again once revised. All other pieces are approved as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-20 |  | 05 12 00-85.0 Quad C3B Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-20 |  | 05 12 00-85.0 Quad C3B Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-19 02:00 |  | 05 12 00-85.0 Quad C3B Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-18 02:00 |  | 05 12 00-85.0 Quad C3B Steel SD-MAM_TT REVIEW_POP.pdf
05 12 00-085-01 | 05 12 00 - STEEL | 05 12 00-085-01 Quad C3B Structural Steel - Seq. 556-563 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-28 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-11 | 2020-02-17 | 21 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04087 | Received | For Review | 2020-01-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-11 | Submittal Number: 05 12 00-85.1 From: JES PELKEY Final Due Date: 02/10/20 Subject: QUAD C3B STRUCTURAL STEEL - SEQ. 556-563 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05680 | Forwarded | For Review | 2020-01-28 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-04 | Submittal Number: 05 12 00-85.1 From: JES PELKEY Final Due Date: 02/10/20 Subject: QUAD C3B STRUCTURAL STEEL - SEQ. 556-563 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04368 | Review Response | Approved as Noted | 2020-02-07 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06046 | Responded and Closed | Approved as Noted | 2020-02-17 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-27 |  | 05 12 00-85.1 Quad C3B Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-01-27 |  | 05 12 00-85.1 Quad C3B Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-27 |  | 05 12 00-85.1 Quad C3B Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-17 |  | 05 12 00-85.1 Quad C3B Steel SD-MAM_TT_POP.pdf
05 12 00-086-00 | 05 12 00 - STEEL | 05 12 00-086-00: Quad A2 Structural Steel - Seq. 217-228 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-10 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2020-01-08 08:00 | 2020-01-09 | 31 | General | Record Copies; Transfers; Submittals |  | 30 |  | 2020-01-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03580 | Received | For Review | 2019-12-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-01-08 08:00 | Submittal Number: 05 12 00-86.0 From: JES PELKEY Final Due Date: 12/23/19 Subject: QUAD A2 STRUCTURAL STEEL - SEQ. 217-228 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05060 | Forwarded | For Review | 2019-12-10 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth K... | 2019-12-17 | Submittal Number: 05 12 00-86.0 From: JES PELKEY Final Due Date: 12/23/19 Subject: QUAD A2 STRUCTURAL STEEL - SEQ. 217-228 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03845 | Review Response | Approved as Noted/Resubmit | 2020-01-08 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 05392 | Forwarded | For Review | 2020-01-08 | Populous SCA_CCA | Todd Spangler (Populous); Josh Dobken (Populous) | 2020-01-08 | Submittal Number: 05 12 00-86.0 From: JES PELKEY Final Due Date: 12/23/19 Subject: QUAD A2 STRUCTURAL STEEL - SEQ. 217-228 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05399 | Responded and Closed | Approved as Noted/Resubmit | 2020-01-09 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. Another level of discussion is required for the steel framing supporting the historic curtain wall. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-09 02:00 |  | 05 12 00-86.0 Quad A2 Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-09 02:00 |  | 05 12 00-86.0 Quad A2 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-09 02:00 |  | 05 12 00-86.0 Quad A2 Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-09 02:00 |  | 05 12 00-86.0 Quad A2 Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-01-09 |  | 05 12 00-86.0 Quad A2 Steel SD-MAM_TT_POP.pdf
05 12 00-086-01 | 05 12 00 - STEEL | 05 12 00-086-01 Quad A2 Structural Steel - Seq. 217-228 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-28 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-12 | 2020-05-04 | 7 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05591 | Received | For Review | 2020-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-05-12 | Submittal Number: 05 12 00-86.1 From: JES PELKEY Final Due Date: 05/11/20 Subject: QUAD A2 STRUCTURAL STEEL - SEQ. 217-228 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07576 | Forwarded | For Review | 2020-04-28 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-05 | Submittal Number: 05 12 00-86.1 From: JES PELKEY Final Due Date: 05/11/20 Subject: QUAD A2 STRUCTURAL STEEL - SEQ. 217-228 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05698 | Review Response | Approved as Noted | 2020-04-30 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Note: Sheet E398 was marked as needing to be revised and resubmit in previous review and was not included in this rev. Please submit for review and approval. | Info Exchange
| 07716 | Responded and Closed | Approved as Noted | 2020-05-04 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Note: Sheet E398 was marked as needing to be revised and resubmit in previous review and was not included in this rev. Please submit for review and approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-27 |  | 05 12 00-86.1 Quad A2 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-27 |  | 05 12 00-86.1 Quad A2 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-27 |  | 05 12 00-86.1 Quad A2 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-04 |  | 05 12 00-86.1 Quad A2 Steel SD-MAM_TT_POP.pdf
05 12 00-087-00 | 05 12 00 - STEEL | 05 12 00-087-00 Quad F1 Steel SD - Seq. 711-717 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-26 | 2020-03-03 | 27 |  | Record Copies; Transfers; Submittals | 05 12 00-087-01 - 05 12 00-087-00 Quad F1 Steel SD - Seq. 711-717 | 21 |  | 2020-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04228 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) | 2020-02-26 | Submittal Number: 05 12 00-87.0 From: JES PELKEY Final Due Date: 02/17/20 Subject: QUAD F1 STEEL SD - SEQ. 711-717 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05857 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 05 12 00-87.0 From: JES PELKEY Final Due Date: 02/17/20 Subject: QUAD F1 STEEL SD - SEQ. 711-717 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04559 | Review Response | Approved as Noted | 2020-02-26 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06363 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-03 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 05 12 00-87.0 Quad F1 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | 05 12 00-87.0 Quad F1 Steel SD-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-02-06 |  | 05 12 00-87.0 Quad F1 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-03 |  | 05 12 00-87.0 Quad F1 Steel SD-MAM_TT_POP.pdf
05 12 00-087-01 | 05 12 00 - STEEL | 05 12 00-087-00 Quad F1 Steel SD - Seq. 711-717 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 12 00-087-00 - 05 12 00-087-00 Quad F1 Steel SD - Seq. 711-717 | -1 | 2020-03-17
05 12 00-088-00 | 05 12 00 - STEEL | 05 12 00-088-00 Quad C4 Structural Steel - Seq. 533, 535 & 564-565 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-02 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2020-01-22 | 2020-01-28 | 27 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-01-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03749 | Received | For Review | 2020-01-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-22 | Submittal Number: 05 12 00-88.0 From: JES PELKEY Final Due Date: 01/15/20 Subject: QUAD C4 STRUCTURAL STEEL - SEQ. 533, 535 & 564-565 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05283 | Forwarded | For Review | 2020-01-02 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-09 | Submittal Number: 05 12 00-88.0 From: JES PELKEY Final Due Date: 01/15/20 Subject: QUAD C4 STRUCTURAL STEEL - SEQ. 533, 535 & 564-565 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04018 | Review Response | Approved as Noted | 2020-01-21 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | There are elevations shown in this submittal with missing BRB connections as Corebrace had not designed at the time this submittal was issued. However, the members to which these BRBs connect to are not part of this submittal. Please resubmit pieces in associated submittals that are affected by these BRB connections. All other pieces in this submittal are approved as noted. BRBs reviewed using Corebrace Rev 3 calcs. If any BRBs require updates per Rev 4 calcs (outside of the typical weld size comments in our review), these pieces including all members and columns to which gussets are connecting. | Info Exchange
| 05604 | Forwarded | For Review | 2020-01-22 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2020-01-22 | Submittal Number: 05 12 00-88.0 From: JES PELKEY Final Due Date: 01/15/20 Subject: QUAD C4 STRUCTURAL STEEL - SEQ. 533, 535 & 564-565 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05699 | Responded and Closed | Approved as Noted | 2020-01-28 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-31 |  | 05 12 00-88.0 Quad C4 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-31 |  | 05 12 00-88.0 Quad C4 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-30 02:00 |  | 05 12 00-88.0 Quad C4 Steel SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-30 02:00 |  | 05 12 00-88.0 Quad C4 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-28 |  | 05 12 00-88.0 Quad C4 Steel SD-MAM_TT_POP.pdf
05 12 00-089-00 | 05 12 00 - STEEL | 05 12 00-089-00 Quad A3A Structural Steel - Seq. 230-232 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-27 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-13 07:00 | 2020-04-19 | 24 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-04-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05084 | Received | For Review | 2020-03-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-13 07:00 | Submittal Number: 05 12 00-89.0 From: JES PELKEY Final Due Date: 04/17/20 Subject: QUAD A3A STRUCTURAL STEEL - SEQ. 230-232 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06908 | Forwarded | For Review | 2020-03-27 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-03 | Submittal Number: 05 12 00-89.0 From: JES PELKEY Final Due Date: 04/17/20 Subject: QUAD A3A STRUCTURAL STEEL - SEQ. 230-232 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05417 | Review Response | Approved as Noted/Resubmit | 2020-04-17 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Resubmit Raker with BRB connection once completed by Corebrace. | Info Exchange
| 07358 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-19 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Resubmit Raker with BRB connection once completed by Corebrace. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-27 |  | 05 12 00-89.0 Quad A3A Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-27 |  | 05 12 00-89.0 Quad A3A Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-27 |  | 05 12 00-89.0 Quad A3A Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-19 |  | 05 12 00-89.0 Quad A3A Steel SD-MAM_TT_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-19 |  | A1-45-5 - SLAB PLAN - SPACE NEEDLE CLUB LEVEL.pdf
05 12 00-089-01 | 05 12 00 - STEEL | 05 12 00-089-01 Quad A3A Structural Steel - Corebrace Connection | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-18 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-02 07:00 | 2020-05-26 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05905 | Received | For Review | 2020-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-06-02 07:00 | Submittal Number: 05 12 00-89.1 From: JES PELKEY Final Due Date: 06/01/20 Subject: QUAD A3A STRUCTURAL STEEL - COREBRACE CONNECTION Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08010 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-25 | Submittal Number: 05 12 00-89.1 From: JES PELKEY Final Due Date: 06/01/20 Subject: QUAD A3A STRUCTURAL STEEL - COREBRACE CONNECTION Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06048 | Review Response | Approved as Noted | 2020-05-26 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08192 | Responded and Closed | Approved as Noted | 2020-05-26 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | see attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 05 12 00-89.1 Quad A3A Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 05 12 00-89.1 Quad A3A Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-18 |  | 05 12 00-89.1 Quad A3A Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-26 |  | 05 12 00-89.1 Quad A3A Steel SD RR-MAM_TT_POP.pdf
05 12 00-090-00 | 05 12 00 - STEEL | 05 12 00-090-00 Quad E1 Steel SD - Seq. 701-705 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-10 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2020-01-30 | 2020-02-04 | 26 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03857 | Received | For Review | 2020-01-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-30 | Submittal Number: 05 12 00-90.0 From: JES PELKEY Final Due Date: 01/23/20 Subject: QUAD E1 STEEL SD - SEQ. 701-705 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05406 | Forwarded | For Review | 2020-01-09 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-16 | Submittal Number: 05 12 00-90.0 From: JES PELKEY Final Due Date: 01/23/20 Subject: QUAD E1 STEEL SD - SEQ. 701-705 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04100 | Review Response | Approved as Noted/Resubmit | 2020-01-27 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Hi Shaina/Josh, Please find attached TT's review of this submittal. I have listed the sheets that need to be revised and resubmitted on the front sheet. We have also marked slab edge distances and a few elevations for Pop review. Thanks, Samar | Info Exchange
| 05695 | Forwarded | For Review | 2020-01-28 | Josh Dobken (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2020-01-30 | Submittal Number: 05 12 00-90.0 From: JES PELKEY Final Due Date: 01/23/20 Subject: QUAD E1 STEEL SD - SEQ. 701-705 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05823 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-04 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-09 |  | 05 12 00-90.0 Quad E1 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-09 |  | 05 12 00-90.0 Quad E1 Steel SD-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-01-08 02:00 |  | 05 12 00-90.0 Quad E1 Steel SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-08 02:00 |  | 05 12 00-90.0 Quad E1 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-04 |  | 05 12 00-90.0 Quad E1 Steel SD-MAM_TT_POP.pdf
05 12 00-090-01 | 05 12 00 - STEEL | 05 12 00-090-01 Quad E1 Steel SD - Seq. 701-705 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-24 | 2020-02-17 | 8 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04272 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-02-24 | Submittal Number: 05 12 00-90.1 From: JES PELKEY Final Due Date: 02/21/20 Subject: QUAD E1 STEEL SD - SEQ. 701-705 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05913 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-17 | Submittal Number: 05 12 00-90.1 From: JES PELKEY Final Due Date: 02/21/20 Subject: QUAD E1 STEEL SD - SEQ. 701-705 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04378 | Review Response | Approved as Noted/Resubmit | 2020-02-13 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06053 | Responded and Closed | Approved as Noted | 2020-02-17 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-10 |  | 05 12 00-90.1 Quad E1 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 05 12 00-90.1 Quad E1 Steel SD-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-02-10 |  | 05 12 00-90.1 Quad E1 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-17 |  | 05 12 00-90.1 Quad E1 Steel SD-MAM_TT_POP.pdf
05 12 00-090-02 | 05 12 00 - STEEL | 05 12 00-090-02 Quad E1 Steel SD - Sheet E715.7 and Elevator Revisions | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-18 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-01 | 2020-03-24 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04920 | Received | For Review | 2020-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-01 | Submittal Number: 05 12 00-90.2 From: JES PELKEY Final Due Date: 04/01/20 Subject: QUAD E1 STEEL SD - SHEET E715.7 AND ELEVATOR REVISIONS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06717 | Forwarded | For Review | 2020-03-18 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-25 | Submittal Number: 05 12 00-90.2 From: JES PELKEY Final Due Date: 04/01/20 Subject: QUAD E1 STEEL SD - SHEET E715.7 AND ELEVATOR REVISIONS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05021 | Review Response | Approved as Noted | 2020-03-24 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06838 | Responded and Closed | Approved as Noted | 2020-03-24 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | see attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-18 |  | 05 12 00-90.2 Quad E1 RR and Elevator RR-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-18 |  | 05 12 00-90.2 Quad E1 RR and Elevator RR-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-03-18 |  | 05 12 00-90.2 Quad E1 RR and Elevator RR-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-24 |  | 05 12 00-90.2 Quad E1 RR and Elevator RR-MAM_TT_POP.pdf
05 12 00-091-00 | 05 12 00 - STEEL | 05 12 00-091-00 West Buttress WB - Seq. 538-539, 544-545 & 551b | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-14 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-03 | 2020-02-03 | 21 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-02-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03907 | Received | For Review | 2020-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-02-03 | Submittal Number: 05 12 00-91.0 From: JES PELKEY Final Due Date: 01/27/20 Subject: WEST BUTTRESS WB - SEQ. 538-539, 544-545 & 551B Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05466 | Forwarded | For Review | 2020-01-14 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-21 | Submittal Number: 05 12 00-91.0 From: JES PELKEY Final Due Date: 01/27/20 Subject: WEST BUTTRESS WB - SEQ. 538-539, 544-545 & 551B Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04101 | Review Response | Approved as Noted | 2020-01-27 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05696 | Forwarded | For Review | 2020-01-28 | Josh Dobken (Populous) | Todd Spangler (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-02-03 | Submittal Number: 05 12 00-91.0 From: JES PELKEY Final Due Date: 01/27/20 Subject: WEST BUTTRESS WB - SEQ. 538-539, 544-545 & 551B Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05790 | Responded and Closed | Approved as Noted | 2020-02-03 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-13 |  | 05 12 00-91.0 West Buttress WB Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-13 |  | 05 12 00-91.0 West Buttress WB Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-12 02:00 |  | 05 12 00-91.0 West Buttress WB Steel SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-12 02:00 |  | 05 12 00-91.0 West Buttress WB Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-03 |  | 05 12 00-91.0 West Buttress WB Steel SD-MAM_TT_POP.pdf
05 12 00-092-00 | 05 12 00 - STEEL | 05 12 00-092-00 Quad A3B and A4A Structural Steel - Seq. 233, 234a-234b, 237-238 & 241 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-30 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-20 | 2020-04-20 | 22 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05097 | Received | For Review | 2020-03-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-20 | Submittal Number: 05 12 00-92.0 From: JES PELKEY Final Due Date: 03/19/20 Subject: QUAD A3B AND A4A STRUCTURAL STEEL - SEQ. 233, 234A-234B, 237-238 & 241 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06925 | Forwarded | For Review | 2020-03-30 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-06 | Submittal Number: 05 12 00-92.0 From: JES PELKEY Final Due Date: 03/19/20 Subject: QUAD A3B AND A4A STRUCTURAL STEEL - SEQ. 233, 234A-234B, 237-238 & 241 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05422 | Review Response | Approved as Noted | 2020-04-09 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07375 | Responded and Closed | Approved as Noted | 2020-04-20 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-29 |  | 05 12 00-92.0 Quad A3B and A4A Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-29 |  | 05 12 00-92.0 Quad A3B and A4A Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-29 |  | 05 12 00-92.0 Quad A3B and A4A Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-20 |  | 05 12 00-92.0 Quad A3B and A4A Steel SD-MAM_TT_POP.pdf
05 12 00-093-00 | 05 12 00 - STEEL | 05 12 00-093-00 Atrium Steel SD - Seq. 425 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-20 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-03 | 2020-08-06 | 18 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07013 | Received | For Review | 2020-07-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-08-03 | Submittal Number: 05 12 00-93.0 From: JES PELKEY Final Due Date: 08/03/20 Subject: ATRIUM STEEL SD - SEQ. 425 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09395 | Forwarded | For Review | 2020-07-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-27 | Submittal Number: 05 12 00-93.0 From: JES PELKEY Final Due Date: 08/03/20 Subject: ATRIUM STEEL SD - SEQ. 425 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07337 | Review Response | Approved as Noted | 2020-07-31 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09865 | Responded and Closed | Approved as Noted | 2020-08-06 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-20 |  | 05 12 00-93.0 Atrium Seq. 425 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-20 |  | 05 12 00-93.0 Atrium Seq. 425 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-20 |  | 05 12 00-93.0 Atrium Seq. 425 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-06 |  | 05 12 00-93.0 Atrium Seq. 425 Steel SD-MAM_TT_POP.pdf
05 12 00-094-00 | 05 12 00 - STEEL | 05 12 00-094-00 South Buttress SB - Seq. 235-236, 239-240, 242-246 & 620 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-19 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous) |  |  |  | 2020-03-10 | 2020-03-23 | 34 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04394 | Received | For Review | 2020-02-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-03-10 | Submittal Number: 05 12 00-94.0 From: JES PELKEY Final Due Date: 03/10/20 Subject: SOUTH BUTTRESS SB - SEQ. 235-236, 239-240, 242-246 & 620 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06074 | Forwarded | For Review | 2020-02-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-26 | Submittal Number: 05 12 00-94.0 From: JES PELKEY Final Due Date: 03/10/20 Subject: SOUTH BUTTRESS SB - SEQ. 235-236, 239-240, 242-246 & 620 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04882 | Review Response | Approved as Noted/Resubmit | 2020-03-12 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06764 | Forwarded | For Review | 2020-03-19 | Josh Dobken (Populous) | Chris Minter (Populous) | 2020-03-10 | Submittal Number: 05 12 00-94.0 From: JES PELKEY Final Due Date: 03/10/20 Subject: SOUTH BUTTRESS SB - SEQ. 235-236, 239-240, 242-246 & 620 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06813 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-23 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-18 |  | 05 12 00-94.0 South Buttress SB Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-18 |  | 05 12 00-94.0 South Buttress SB Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-18 |  | 05 12 00-94.0 South Buttress SB Steel SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-17 02:00 |  | 05 12 00-94.0 South Buttress SB Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-23 |  | 05 12 00-94.0 South Buttress SB Steel SD-MAM_TT_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-23 |  | A1-45-5 - SLAB PLAN - SPACE NEEDLE CLUB LEVEL.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-23 |  | A1-45-A - SLAB PLAN - UPPER CONCOURSE LEVEL - AREA A.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-23 |  | A1-45-B - SLAB PLAN - UPPER CONCOURSE LEVEL - AREA B.pdf
05 12 00-094-01 | 05 12 00 - STEEL | 05 12 00-094-01 South Buttress SB - Seq. 235-236, 239-240, 242-246 & 620 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-06 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-20 | 2020-05-12 | 7 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05734 | Received | For Review | 2020-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-05-20 | Submittal Number: 05 12 00-94.1 From: JES PELKEY Final Due Date: 05/19/20 Subject: SOUTH BUTTRESS SB - SEQ. 235-236, 239-240, 242-246 & 620 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07780 | Forwarded | For Review | 2020-05-05 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-12 | Submittal Number: 05 12 00-94.1 From: JES PELKEY Final Due Date: 05/19/20 Subject: SOUTH BUTTRESS SB - SEQ. 235-236, 239-240, 242-246 & 620 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05832 | Review Response | Approved as Noted/Resubmit | 2020-05-08 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Corebrace to provide clarity to detailing and designate "Top" and "Bottom" ends of BRB at South Buttress at Mech Level. Please resubmit column 8220C with new corebrace detail for review and approval. All other pieces are approved as noted. | Info Exchange
| 07913 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-12 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | 05 12 00-94.1 South Buttress SB Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-05 |  | 05 12 00-94.1 South Buttress SB Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-05 |  | 05 12 00-94.1 South Buttress SB Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-12 |  | 05 12 00-94.1 South Buttress SB Steel SD RR-MAM_TT_POP.pdf
05 12 00-094-02 | 05 12 00 - STEEL | 05 12 00-094-02 South Buttress SB - Seq. 235-236, 239-240, 242-246 & 620 - 1 column | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-25 | 2020-06-15 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06331 | Received | For Review | 2020-06-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-06-25 | Submittal Number: 05 12 00-94.2 From: JES PELKEY Final Due Date: 06/24/20 Subject: SOUTH BUTTRESS SB - SEQ. 235-236, 239-240, 242-246 & 620 - 1 COLUMN Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08540 | Forwarded | For Review | 2020-06-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-18 | Submittal Number: 05 12 00-94.2 From: JES PELKEY Final Due Date: 06/24/20 Subject: SOUTH BUTTRESS SB - SEQ. 235-236, 239-240, 242-246 & 620 - 1 COLUMN Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06404 | Review Response | Approved as Noted | 2020-06-11 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08623 | Responded and Closed | Approved as Noted | 2020-06-15 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | see attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-10 |  | 05 12 00-94.2 South Buttress Steel SD BRB Column-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-10 |  | 05 12 00-94.2 South Buttress Steel SD BRB Column-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-10 |  | 05 12 00-94.2 South Buttress Steel SD BRB Column-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-15 |  | 05 12 00-94.2 South Buttress Steel SD BRB Column-MAM_TT_POP.pdf
05 12 00-095-00 | 05 12 00 - STEEL | 05 12 00-095-00 Lower Bowl Rakers LBR - Seq. 801-804 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-22 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-08 07:00 | 2020-06-08 | 18 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-06-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05988 | Received | For Review | 2020-05-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-06-08 07:00 | Submittal Number: 05 12 00-95.0 From: JES PELKEY Final Due Date: 06/05/20 Subject: LOWER BOWL RAKERS LBR - SEQ. 801-804 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08125 | Forwarded | For Review | 2020-05-22 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-29 | Submittal Number: 05 12 00-95.0 From: JES PELKEY Final Due Date: 06/05/20 Subject: LOWER BOWL RAKERS LBR - SEQ. 801-804 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06261 | Review Response | Approved as Noted | 2020-06-04 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08450 | Responded and Closed | Approved as Noted | 2020-06-08 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-21 |  | 05 12 00-95.0 Lower Bowl Rakers Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-21 |  | 05 12 00-95.0 Lower Bowl Rakers Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-21 |  | 05 12 00-95.0 Lower Bowl Rakers Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-08 |  | 05 12 00-95.0 Lower Bowl Rakers Steel SD-MAM_TT_POP.pdf
05 12 00-096-00 | 05 12 00 - STEEL | 05 12 00-096-00 Quad B2 A Structural Steel - Seq. 613-616 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-12 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-26 | 2020-04-02 | 22 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-04-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04772 | Received | For Review | 2020-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-03-26 | Submittal Number: 05 12 00-96.0 From: JES PELKEY Final Due Date: 03/26/20 Subject: QUAD B2 A STRUCTURAL STEEL - SEQ. 613-616 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06547 | Forwarded | For Review | 2020-03-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-18 | Submittal Number: 05 12 00-96.0 From: JES PELKEY Final Due Date: 03/26/20 Subject: QUAD B2 A STRUCTURAL STEEL - SEQ. 613-616 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05079 | Review Response | Approved as Noted | 2020-03-26 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07018 | Responded and Closed | Approved as Noted | 2020-04-01 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. | Info Exchange
| 07044 | Reopened | Additional Information | 2020-04-02 09:30 | Josh Dobken (Populous) |  |  | Reopened due to issues sending in Newforma
| 07045 | Responded and Closed | Approved as Noted | 2020-04-02 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Responded and Closed (Approved as Noted) to: Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: See attached. Reopened (Additional Information) by: Josh Dobken Remarks: Reopened due to issues sending in Newforma | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 05 12 00-96.0 Quad B2 A Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-11 |  | 05 12 00-96.0 Quad B2 A Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-11 |  | 05 12 00-96.0 Quad B2 A Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-01 |  | 05 12 00-96.0 Quad B2 A Steel SD-MAM_TT_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-01 02:00 |  | 05 12 00-96.0 Quad B2 A Steel SD-MAM_TT_POP.pdf
05 12 00-098-00 | 05 12 00 - STEEL | 05 12 00-098-00 Quad B5 Structural Steel - Seq. 401-403 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-02 | 2020-04-06 | 19 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04961 | Received | For Review | 2020-03-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-02 | Submittal Number: 05 12 00-98.0 From: JES PELKEY Final Due Date: 02/11/20 Subject: QUAD B5 STRUCTURAL STEEL - SEQ. 401-403 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06760 | Forwarded | For Review | 2020-03-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-26 | Submittal Number: 05 12 00-98.0 From: JES PELKEY Final Due Date: 02/11/20 Subject: QUAD B5 STRUCTURAL STEEL - SEQ. 401-403 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05196 | Review Response | Approved as Noted | 2020-04-02 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07099 | Responded and Closed | Approved as Noted | 2020-04-06 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-19 |  | 05 12 00-98.0 Quad B5 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-19 |  | 05 12 00-98.0 Quad B5 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-19 |  | 05 12 00-98.0 Quad B5 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-06 |  | 05 12 00-98.0 Quad B5 Steel SD-MAM_TT_POP.pdf
05 12 00-099-00 | 05 12 00 - STEEL | 05 12 00-099-00 Quad B3 Structural Steel - Seq. 623-625 & 627-629 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-04 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-22 | 2020-05-20 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-05-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05679 | Received | For Review | 2020-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-05-22 | Submittal Number: 05 12 00-99.0 From: JES PELKEY Final Due Date: 05/18/20 Subject: QUAD B3 STRUCTURAL STEEL - SEQ. 623-625 & 627-629 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07690 | Forwarded | For Review | 2020-05-04 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-11 | Submittal Number: 05 12 00-99.0 From: JES PELKEY Final Due Date: 05/18/20 Subject: QUAD B3 STRUCTURAL STEEL - SEQ. 623-625 & 627-629 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05956 | Review Response | Approved as Noted/Resubmit | 2020-05-19 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Resubmit column for BRB connection per latest corebrace calcs. All other pieces are approved as noted. | Info Exchange
| 08088 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-20 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-03 |  | 05 12 00-99.0 Quad B3 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-03 |  | 05 12 00-99.0 Quad B3 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-03 |  | 05 12 00-99.0 Quad B3 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-20 |  | 05 12 00-99.0 Quad B3 Steel SD-MAM_TT_POP.pdf
05 12 00-099-01 | 05 12 00 - STEEL | 05 12 00-099-01 Quad B3 Structural Steel - Seq. 623-625 & 627-629 - BRB Connection | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-03 | 2020-06-23 | 5 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-06-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06529 | Received | For Review | 2020-06-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-07-03 | Submittal Number: 05 12 00-99.1 From: JES PELKEY Final Due Date: 07/03/20 Subject: QUAD B3 STRUCTURAL STEEL - SEQ. 623-625 & 627-629 - BRB CONNECTION Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08787 | Forwarded | For Review | 2020-06-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-29 | Submittal Number: 05 12 00-99.1 From: JES PELKEY Final Due Date: 07/03/20 Subject: QUAD B3 STRUCTURAL STEEL - SEQ. 623-625 & 627-629 - BRB CONNECTION Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06561 | Review Response | Approved as Noted | 2020-06-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08832 | Responded and Closed | Approved as Noted | 2020-06-23 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-19 |  | 05 12 00-99.1 Quad B3 Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-19 |  | 05 12 00-99.1 Quad B3 Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-19 |  | 05 12 00-99.1 Quad B3 Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-23 |  | 05 12 00-99.1 Quad B3 Steel SD RR-MAM_TT_POP.pdf
05 12 00-100-00 | 05 12 00 - STEEL | 05 12 00-100-00 Quad A5 and A6 Structural Steel - Seq. 404, 405a, 407-409 & 414-415 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-09 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2020-01-29 | 2020-02-17 | 40 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2020-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03850 | Received | For Review | 2020-01-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-29 | Submittal Number: 05 12 00-100.0 From: JES PELKEY Final Due Date: 01/23/20 Subject: QUAD A5 AND A6 STRUCTURAL STEEL - SEQ. 404, 405A, 407-409 & 414-415 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05398 | Forwarded | For Review | 2020-01-09 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-16 | Submittal Number: 05 12 00-100.0 From: JES PELKEY Final Due Date: 01/23/20 Subject: QUAD A5 AND A6 STRUCTURAL STEEL - SEQ. 404, 405A, 407-409 & 414-415 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04216 | Review Response | Approved as Noted/Resubmit | 2020-02-04 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05842 | Forwarded | For Review | 2020-02-05 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2020-01-29 | Submittal Number: 05 12 00-100.0 From: JES PELKEY Final Due Date: 01/23/20 Subject: QUAD A5 AND A6 STRUCTURAL STEEL - SEQ. 404, 405A, 407-409 & 414-415 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06031 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-17 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-09 |  | 05 12 00-100.0 A5 and A6 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-09 |  | 05 12 00-100.0 A5 and A6 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-08 02:00 |  | 05 12 00-100.0 A5 and A6 Steel SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-08 02:00 |  | 05 12 00-100.0 A5 and A6 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-17 |  | 05 12 00-100.0 A5 and A6 Steel SD-MAM_TT_POP.pdf
05 12 00-100-01 | 05 12 00 - STEEL | 05 12 00-100-01 Quad A5 and A6 Structural Steel - Seq. 404, 405a, 407-409 & 414-415 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-17 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-31 | 2020-04-01 | 16 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-04-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04876 | Received | For Review | 2020-03-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-03-31 | Submittal Number: 05 12 00-100.1 From: JES PELKEY Final Due Date: 03/30/20 Subject: QUAD A5 AND A6 STRUCTURAL STEEL - SEQ. 404, 405A, 407-409 & 414-415 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06663 | Forwarded | For Review | 2020-03-17 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-24 | Submittal Number: 05 12 00-100.1 From: JES PELKEY Final Due Date: 03/30/20 Subject: QUAD A5 AND A6 STRUCTURAL STEEL - SEQ. 404, 405A, 407-409 & 414-415 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05007 | Review Response | Revise and Resubmit | 2020-03-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please submit 2 kickers 8039VB AND 7635VB for approval. These were not found in the submittal. All other pieces are approved as noted. Escalator steel frame to be officially submitted to TT for approval/record. | Info Exchange
| 07003 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-01 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 05 12 00-100.1 Quad A5 and A6 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 05 12 00-100.1 Quad A5 and A6 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-16 |  | 05 12 00-100.1 Quad A5 and A6 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-01 |  | 05 12 00-100.1 Quad A5 and A6 Steel SD-MAM_TT_POP.pdf
05 12 00-100-02 | 05 12 00 - STEEL | 05 12 00-100-02 Quad A5 and A6 Structural Steel - RR 2 Braces | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-22 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-06 | 2020-04-28 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05502 | Received | For Review | 2020-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-05-06 | Submittal Number: 05 12 00-100.2 From: JES PELKEY Final Due Date: 05/06/20 Subject: QUAD A5 AND A6 STRUCTURAL STEEL - RR 2 BRACES Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07460 | Forwarded | For Review | 2020-04-22 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-29 | Submittal Number: 05 12 00-100.2 From: JES PELKEY Final Due Date: 05/06/20 Subject: QUAD A5 AND A6 STRUCTURAL STEEL - RR 2 BRACES Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05613 | Review Response | Approved as Noted | 2020-04-27 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07609 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-28 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and response. I'm concerned items are not being picked up. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 05 12 00-100.2 Quad A5-A6 - 2 Braces RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 05 12 00-100.2 Quad A5-A6 - 2 Braces RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-22 |  | 05 12 00-100.2 Quad A5-A6 - 2 Braces RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-28 |  | 05 12 00-100.2 Quad A5-A6 - 2 Braces RR-MAM_TT_POP.pdf
05 12 00-100-03 | 05 12 00 - STEEL | 05 12 00-100-03 Quad A5 and A6 Structural Steel - A6 Freight and Grating Revisions | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-02 | 2020-06-18 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06484 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-02 | Submittal Number: 05 12 00-100.3 From: JES PELKEY Final Due Date: 07/02/20 Subject: QUAD A5 AND A6 STRUCTURAL STEEL - A6 FREIGHT AND GRATING REVISIONS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08735 | Forwarded | For Review | 2020-06-18 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-25 | Submittal Number: 05 12 00-100.3 From: JES PELKEY Final Due Date: 07/02/20 Subject: QUAD A5 AND A6 STRUCTURAL STEEL - A6 FREIGHT AND GRATING REVISIONS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06499 | Review Response | Approved as Noted | 2020-06-18 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 08755 | Responded and Closed | Approved as Noted | 2020-06-18 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 |  | 05 12 00-100.3 Quad A5&A6 Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-18 |  | 05 12 00-100.3 Quad A5&A6 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-18 |  | 05 12 00-100.3 Quad A5&A6 Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-18 |  | 05 12 00-100.3 Quad A5&A6 Steel SD-MAM_TT_POP.pdf
05 12 00-101-00 | 05 12 00 - STEEL | 05 12 00-101-00 Quad B4 Structural Steel - Seq. 630-635 & 626 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-04 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-22 | 2020-05-27 | 24 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-05-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05680 | Received | For Review | 2020-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-05-22 | Submittal Number: 05 12 00-101.0 From: JES PELKEY Final Due Date: 05/25/20 Subject: QUAD B4 STRUCTURAL STEEL - SEQ. 630-635 & 626 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07691 | Forwarded | For Review | 2020-05-04 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-11 | Submittal Number: 05 12 00-101.0 From: JES PELKEY Final Due Date: 05/25/20 Subject: QUAD B4 STRUCTURAL STEEL - SEQ. 630-635 & 626 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06013 | Review Response | Approved as Noted/Resubmit | 2020-05-26 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | See individual stamps on sheets for pieces requiring a Revise and Resubmit. All other pieces are approved as noted. | Info Exchange
| 08196 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-27 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-03 |  | 05 12 00-101.0 Quad B4 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-03 |  | 05 12 00-101.0 Quad B4 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-03 |  | 05 12 00-101.0 Quad B4 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-27 |  | 05 12 00-101.0 Quad B4 Steel SD-MAM_TT_POP.pdf
05 12 00-101-01 | 05 12 00 - STEEL | 05 12 00-101-01 Quad B4 Structural Steel - 4 members | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-03 | 2020-06-23 | 5 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-06-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06530 | Received | For Review | 2020-06-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-03 | Submittal Number: 05 12 00-101.1 From: JES PELKEY Final Due Date: 07/03/20 Subject: QUAD B4 STRUCTURAL STEEL - 4 MEMBERS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08788 | Forwarded | For Review | 2020-06-20 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-29 | Submittal Number: 05 12 00-101.1 From: JES PELKEY Final Due Date: 07/03/20 Subject: QUAD B4 STRUCTURAL STEEL - 4 MEMBERS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06560 | Review Response | Approved as Noted | 2020-06-23 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 08830 | Responded and Closed | Approved as Noted | 2020-06-23 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-19 |  | 05 12 00-101.1 Quad B4 Steel SD RR-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-19 |  | 05 12 00-101.1 Quad B4 Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-19 |  | 05 12 00-101.1 Quad B4 Steel SD RR-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-23 |  | 05 12 00-101.1 Quad B4 Steel SD RR-MAM_TT_POP.pdf
05 12 00-102-00 | 05 12 00 - STEEL | 05 12 00-102-00 West Bridge Truss Steel - Seq. 299 & 900 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-21 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-11 | 2020-06-16 | 27 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-06-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05978 | Received | For Review | 2020-05-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-06-11 | Submittal Number: 05 12 00-102.0 From: JES PELKEY Final Due Date: 06/11/20 Subject: WEST BRIDGE TRUSS STEEL - SEQ. 299 & 900 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08116 | Forwarded | For Review | 2020-05-21 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-28 | Submittal Number: 05 12 00-102.0 From: JES PELKEY Final Due Date: 06/11/20 Subject: WEST BRIDGE TRUSS STEEL - SEQ. 299 & 900 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06409 | Review Response | Approved as Noted | 2020-06-11 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Coordinate truss cambering with notes on sheet S3-80. Coordinate with RFIs 2411, 2389, 2377, and 2219 and associated revs for weld lengths at truss verticals, diagonals, stiffeners, etc. TMD support steel does not match structural drawings. | Info Exchange
| 08651 | Responded and Closed | Approved as Noted | 2020-06-16 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-21 |  | 05 12 00-102.0 West Bridge Truss Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-21 |  | 05 12 00-102.0 West Bridge Truss Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-21 |  | 05 12 00-102.0 West Bridge Truss Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-16 |  | 05 12 00-102.0 West Bridge Truss Steel SD-MAM_TT_POP.pdf
05 12 00-106-00 | 05 12 00 - STEEL | 05 12 00-106-00 Quad B Embeds - Sequence 24, 9710, & 9824 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-13 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-08-27 | 2019-08-28 | 16 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02043 | Received | For Review | 2019-08-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-27 | Submittal Number: 05 12 00-106.0 From: BART BIESTERFELD Final Due Date: 08/28/19 Subject: QUAD B EMBEDS - SEQUENCE 24, 9710, & 9824 Description: PLEASE REVIEW AND RETURN BY 8/9 FOR TIMELY RELEASE TO FABRICATION Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03210 | Forwarded | For Review | 2019-08-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-20 | Submittal Number: 05 12 00-106.0 From: BART BIESTERFELD Final Due Date: 08/28/19 Subject: QUAD B EMBEDS - SEQUENCE 24, 9710, & 9824 Description: PLEASE REVIEW AND RETURN BY 8/9 FOR TIMELY RELEASE TO FABRICATION Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02201 | Review Response | Revise and Resubmit | 2019-08-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 03406 | Forwarded | For Review | 2019-08-26 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-27 | Submittal Number: 05 12 00-106.0 From: BART BIESTERFELD Final Due Date: 08/28/19 Subject: QUAD B EMBEDS - SEQUENCE 24, 9710, & 9824 Description: PLEASE REVIEW AND RETURN BY 8/9 FOR TIMELY RELEASE TO FABRICATION Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Email
| 03442 | Responded and Closed | Revise and Resubmit | 2019-08-28 | Todd Spangler (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-13 |  | 05 12 00-106.0 Quad B Embeds - Seq. 24, 9710, & 9824-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-13 |  | 05 12 00-106.0 Quad B Embeds - Seq. 24, 9710, & 9824-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-08-12 02:00 |  | 05 12 00-106.0 Quad B Embeds - Seq. 24, 9710, & 9824-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-08-12 02:00 |  | 05 12 00-106.0 Quad B Embeds - Seq. 24, 9710, & 9824-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-28 02:00 |  | 05 12 00-106.0 Quad B Embeds - Seq. 24, 9710, & 9824-MAM_TT_POP.pdf
05 12 00-106-01 | 05 12 00 - STEEL | 05 12 00-106-01 Quad B Embeds - Sequence 24, 9710, & 9824 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-20 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-05 | 2020-03-03 | 13 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04419 | Received | For Review | 2020-02-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-03-05 | Submittal Number: 05 12 00-106.1 From: BART BIESTERFELD Final Due Date: 03/05/20 Subject: QUAD B EMBEDS - SEQUENCE 24, 9710, & 9824 Description: PLEASE REVIEW AND RETURN BY 8/9 FOR TIMELY RELEASE TO FABRICATION Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06103 | Forwarded | For Review | 2020-02-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-27 | Submittal Number: 05 12 00-106.1 From: BART BIESTERFELD Final Due Date: 03/05/20 Subject: QUAD B EMBEDS - SEQUENCE 24, 9710, & 9824 Description: PLEASE REVIEW AND RETURN BY 8/9 FOR TIMELY RELEASE TO FABRICATION Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04592 | Review Response | Approved as Noted/Resubmit | 2020-03-02 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Note that there are areas pending redesign due to contractor proposed West Temp Ramp changes. All other pieces are approved as noted. | Info Exchange
| 06330 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-03 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Note that there are areas pending redesign due to contractor proposed West Temp Ramp changes. All other pieces are approved as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-19 |  | 05 12 00-106.1 Quad B Embeds-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-19 |  | 05 12 00-106.1 Quad B Embeds-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-19 |  | 05 12 00-106.1 Quad B Embeds-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-03 |  | 05 12 00-106.1 Quad B Embeds-MAM_TT_POP.pdf
05 12 00-106-02 | 05 12 00 - STEEL | 05 12 00-106-02 Quad B Embeds - Sequence 24, 9710, & 9824 - West Temp Ramp Changes | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-02 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-16 | 2020-06-16 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-06-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06147 | Received | For Review | 2020-06-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-06-16 | Submittal Number: 05 12 00-106.2 From: BART BIESTERFELD Final Due Date: 06/15/20 Subject: QUAD B EMBEDS - SEQUENCE 24, 9710, & 9824 - WEST TEMP RAMP CHANGES Description: PLEASE REVIEW AND RETURN BY 8/9 FOR TIMELY RELEASE TO FABRICATION Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08315 | Forwarded | For Review | 2020-06-02 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-09 | Submittal Number: 05 12 00-106.2 From: BART BIESTERFELD Final Due Date: 06/15/20 Subject: QUAD B EMBEDS - SEQUENCE 24, 9710, & 9824 - WEST TEMP RAMP CHANGES Description: PLEASE REVIEW AND RETURN BY 8/9 FOR TIMELY RELEASE TO FABRICATION Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06430 | Review Response | Approved as Noted | 2020-06-16 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08677 | Responded and Closed | Approved as Noted | 2020-06-16 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-01 |  | 05 12 00-106.2 Quad B Embeds SW Snorkel-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-01 |  | 05 12 00-106.2 Quad B Embeds SW Snorkel-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-01 |  | 05 12 00-106.2 Quad B Embeds SW Snorkel-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-16 |  | 05 12 00-106.2 Quad B Embeds SW Snorkel-MAM_TT_POP.pdf
05 12 00-108-00 | 05 12 00 - STEEL | 05 12 00-108-00 Sequence 9901 Quad D Connx Materials | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-28 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill |  |  |  | 2019-11-11 | 2019-10-30 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-10-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02931 | Received | For Review | 2019-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-11-11 | Submittal Number: 05 12 00-108.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/11/19 Subject: SEQUENCE 9901 QUAD D CONNX MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04302 | Forwarded | For Review | 2019-10-28 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-04 | Submittal Number: 05 12 00-108.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/11/19 Subject: SEQUENCE 9901 QUAD D CONNX MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02974 | Review Response | Approved as Noted/Resubmit | 2019-10-30 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | See stamps on sheets for which pieces TT needs to review again. | Info Exchange
| 04360 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-30 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-28 |  | 05 12 00-108.0 Quad D Connection Materials-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-28 |  | 05 12 00-108.0 Quad D Connection Materials-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-28 |  | 05 12 00-108.0 Quad D Connection Materials-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-30 |  | 05 12 00-108.0 Quad D Connection Materials-MAM_TT_POP.pdf
05 12 00-108-01 | 05 12 00 - STEEL | 05 12 00-108-01 Sequence 9901 Quad D Connx Materials R&R | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-06 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-20 | 2020-01-07 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-01-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03786 | Received | For Review | 2020-01-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-20 | Submittal Number: 05 12 00-108.1 From: BRAD KIRSCHENHEITER Final Due Date: 01/20/20 Subject: SEQUENCE 9901 QUAD D CONNX MATERIALS R&R Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05326 | Forwarded | For Review | 2020-01-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-13 | Submittal Number: 05 12 00-108.1 From: BRAD KIRSCHENHEITER Final Due Date: 01/20/20 Subject: SEQUENCE 9901 QUAD D CONNX MATERIALS R&R Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03821 | Review Response | Approved as Noted/Resubmit | 2020-01-07 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please provide missing pieces that were noted to be updated in the previous submittal. Also note added framing due to temp hoist and TRS column blockout framing. All other pieces are approved as noted. | Info Exchange
| 05365 | Responded and Closed | Revise and Resubmit | 2020-01-07 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-06 |  | 05 12 00-108.1 Quad D Connection Materials-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-06 |  | 05 12 00-108.1 Quad D Connection Materials-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-06 |  | 05 12 00-108.1 Quad D Connection Materials-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-07 |  | 05 12 00-108.1 Quad D Connection Materials-MAM_TT_POP.pdf
05 12 00-108-02 | 05 12 00 - STEEL | 05 12 00-108-02 Sequence 9901 & 9902 Quad D Connx Materials R&R | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-22 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-05 | 2020-01-27 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-01-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04007 | Received | For Review | 2020-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-02-05 | Submittal Number: 05 12 00-108.2 From: BRAD KIRSCHENHEITER Final Due Date: 02/05/20 Subject: SEQUENCE 9901 & 9902 QUAD D CONNX MATERIALS R&R Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05591 | Forwarded | For Review | 2020-01-22 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-29 | Submittal Number: 05 12 00-108.2 From: BRAD KIRSCHENHEITER Final Due Date: 02/05/20 Subject: SEQUENCE 9901 & 9902 QUAD D CONNX MATERIALS R&R Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04066 | Review Response | Approved | 2020-01-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05659 | Responded and Closed | Approved as Noted | 2020-01-27 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-21 |  | 05 12 00-108.2 Quad D Connection Materials (MAM Review2).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-21 |  | 05 12 00-108.2 Quad D Connection Materials (MAM Review2).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-21 |  | 05 12 00-108.2 Quad D Connection Materials (MAM Review2).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-27 |  | 05 12 00-108.2 Quad D Connection Materials (MAM Review2)_TT_POP.pdf
05 12 00-114-00 | 05 12 00 - STEEL | 05 12 00-114-00 Roof Strengthening Steel Quad D Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-14 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2019-08-28 | 2019-08-30 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-08-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02049 | Received | For Review | 2019-08-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC); Nate Weingart (Mortenson Construction) | 2019-08-28 | Submittal Number: 05 12 00-114.0 From: NATE WEINGART Final Due Date: 08/27/19 Subject: ROOF STRENGTHENING STEEL QUAD D SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03220 | Forwarded | For Review | 2019-08-14 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-21 | Submittal Number: 05 12 00-114.0 From: NATE WEINGART Final Due Date: 08/27/19 Subject: ROOF STRENGTHENING STEEL QUAD D SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02253 | Review Response | Revise and Resubmit | 2019-08-29 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please see attached TT's review of 05 12 00-114-00. Please note that Populous is to provide comments on sheets E5, E16, E25.1, E25.2, E27.2. | Info Exchange
| 03474 | Forwarded | For Review | 2019-08-29 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2019-08-28 | Submittal Number: 05 12 00-114.0 From: NATE WEINGART Final Due Date: 08/27/19 Subject: ROOF STRENGTHENING STEEL QUAD D SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Email
| 03496 | Responded and Closed | Revise and Resubmit | 2019-08-30 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for review and comments. TAS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-13 |  | 051200-SD-114.0 - Roof Strengthening Steel Quad D Shop Drawings (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-13 |  | 051200-SD-114.0 - Roof Strengthening Steel Quad D Shop Drawings (MAM Review).pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-08-12 02:00 |  | 051200-SD-114.0 - Roof Strengthening Steel Quad D Shop Drawings (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-08-12 02:00 |  | 051200-SD-114.0 - Roof Strengthening Steel Quad D Shop Drawings (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-30 |  | 051200-SD-114.0 - Roof Strengthening Steel Quad D Shop Drawings MAM_TT_POP.pdf
05 12 00-114-01 | 05 12 00 - STEEL | 05 12 00-114-01 Roof Strengthening Steel Quad D Shop Drawing Resubmittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-18 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-10-08 | 2019-10-07 | 20 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-10-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02447 | Received | For Review | 2019-09-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-10-08 | Submittal Number: 05 12 00-114.1 From: NATE WEINGART Final Due Date: 09/24/19 Subject: ROOF STRENGTHENING STEEL QUAD D SHOP DRAWING RESUBMITTAL Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03712 | Forwarded | For Review | 2019-09-18 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-09-25 | Submittal Number: 05 12 00-114.1 From: NATE WEINGART Final Due Date: 09/24/19 Subject: ROOF STRENGTHENING STEEL QUAD D SHOP DRAWING RESUBMITTAL Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02662 | Review Response | Revise and Resubmit | 2019-10-03 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Populous to review paint/primer notes. See stamps & comments on individual sheets. (2) Sheets Revise & Resubmit, (245) Sheets Approved or Approved As Noted. | Info Exchange
| 03976 | Forwarded | For Review | 2019-10-03 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-10-08 | Submittal Number: 05 12 00-114.1 From: NATE WEINGART Final Due Date: 09/24/19 Subject: ROOF STRENGTHENING STEEL QUAD D SHOP DRAWING RESUBMITTAL Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Email
| 04011 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-07 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED See stamps & comments on individual sheets. (2) Sheets Revise & Resubmit, (245) Sheets Approved or Approved As Noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | 051200-SD-114.1 - Roof Strength Steel Quad D Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-17 |  | 051200-SD-114.1 - Roof Strength Steel Quad D Resubmittal (MAM Review).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | 051200-SD-114.1 - Roof Strength Steel Quad D Resubmittal (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-07 |  | Transmittal_Submittal - 05 12 00-114-01 (Responded and Closed).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-07 |  | 051200-SD-114.1 - Roof Strength Steel Quad D Resubmittal (MAM Review)_TT_POP.pdf
05 12 00-114-02 | 05 12 00 - STEEL | 05 12 00-114-02 Roof Strengthening Steel Quad D Shop Drawings - Field Use | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-29 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill |  |  |  | 2019-11-12 | 2019-11-08 | 11 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-11-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02955 | Received | For Review | 2019-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-11-12 | Submittal Number: 05 12 00-114.2 From: NATE WEINGART Final Due Date: 11/08/19 Subject: ROOF STRENGTHENING STEEL QUAD D SHOP DRAWINGS - FIELD USE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04333 | Forwarded | For Review | 2019-10-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-05 | Submittal Number: 05 12 00-114.2 From: NATE WEINGART Final Due Date: 11/08/19 Subject: ROOF STRENGTHENING STEEL QUAD D SHOP DRAWINGS - FIELD USE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03126 | Review Response | Approved as Noted | 2019-11-07 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04537 | Responded and Closed | Approved as Noted | 2019-11-08 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-28 |  | 051200-SD-114.1 - Roof Strength Steel Quad D Resubmittal (Field Use).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-28 |  | 051200-SD-114.1 - Roof Strength Steel Quad D Resubmittal (Field Use).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-28 |  | 051200-SD-114.1 - Roof Strength Steel Quad D Resubmittal (Field Use).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-11-08 |  | 051200-SD-114.1 - Roof Strength Steel Quad D Resubmittal (Field Use)_TT_POP.pdf
05 12 00-115-00 | 05 12 00 - STEEL | 05 12 00-115-00 Roof Strengthening Steel Quad C Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-02 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2019-10-22 | 2019-10-22 | 21 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-10-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02636 | Received | For Review | 2019-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-10-22 | Submittal Number: 05 12 00-115.0 From: JES PELKEY Final Due Date: 10/18/19 Subject: ROOF STRENGTHENING STEEL QUAD C SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03945 | Forwarded | For Review | 2019-10-02 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-09 | Submittal Number: 05 12 00-115.0 From: JES PELKEY Final Due Date: 10/18/19 Subject: ROOF STRENGTHENING STEEL QUAD C SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02810 | Review Response | Approved as Noted | 2019-10-17 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Modifications have been made to the structural retrofit schedules after this submittal was sent to TT for review. See latest issued drawings for all changes. Markups of issued changes within this submittal have been provided as a courtesy and do not supercede contract documents. Populous to review comments on sheets PN 12 and E32.3. See attached sketch SSK-0088. | Info Exchange
| 04159 | Forwarded | For Review | 2019-10-16 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2019-10-22 | Submittal Number: 05 12 00-115.0 From: JES PELKEY Final Due Date: 10/18/19 Subject: ROOF STRENGTHENING STEEL QUAD C SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04254 | Responded and Closed | Approved as Noted | 2019-10-22 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for review & comment. TAS Modifications have been made to the structural retrofit schedules after this submittal was sent to TT for review. See latest issued drawings for all changes. Markups of issued changes within this submittal have been provided as a courtesy and do not supercede contract documents. Populous to review comments on sheets PN 12 and E32.3. See attached sketch SSK-0088. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-30 |  | 051200-SD-115.0 - Roof Strengthening Steel Quad C Shop Drawings (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-30 |  | 051200-SD-115.0 - Roof Strengthening Steel Quad C Shop Drawings (MAM Review).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-09-29 02:00 |  | 051200-SD-115.0 - Roof Strengthening Steel Quad C Shop Drawings (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-29 02:00 |  | 051200-SD-115.0 - Roof Strengthening Steel Quad C Shop Drawings (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-16 |  | SSK-0088 Detail 12.S5-75 - T14 Truss Hanger Clash.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-22 |  | 051200-SD-115.0 - Roof Strengthening Steel Quad C Shop Drawings_MAM_TT_POP.pdf
05 12 00-116-00 | 05 12 00 - STEEL | 05 12 00-116-00 Roof Strengthening Steel Quad A Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-13 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-11-27 | 2019-12-02 | 20 |  | Record Copies; Transfers; Submittals | 05 12 00-116-01 - 05 12 00-116-00 Roof Strengthening Steel Quad A Shop Drawings | 15 |  | 2019-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03182 | Received | For Review | 2019-11-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-11-27 | Submittal Number: 05 12 00-116.0 From: JES PELKEY Final Due Date: 11/27/19 Subject: ROOF STRENGTHENING STEEL QUAD A SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04605 | Forwarded | For Review | 2019-11-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-20 | Submittal Number: 05 12 00-116.0 From: JES PELKEY Final Due Date: 11/27/19 Subject: ROOF STRENGTHENING STEEL QUAD A SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03417 | Review Response | Approved as Noted/Resubmit | 2019-11-27 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | EACH INDIVIDUAL SHEET APPROVED/APPROVED AS NOTED UNLESS STAMPED AS REVISE & RESUBMIT. REVISE & RESUBMIT LIST: PIECE DRAWING 1546B, 1700P, 1607P, 1649P, 1628P POPULOUS TO REVIEW: PN14 (PG 281) | Info Exchange
| 04888 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-02 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | EACH INDIVIDUAL SHEET APPROVED/APPROVED AS NOTED UNLESS STAMPED AS REVISE & RESUBMIT. REVISE & RESUBMIT LIST: PIECE DRAWING 1546B, 1700P, 1607P, 1649P, 1628P | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-12 |  | 051200-116.0 Roof Strength Steel Quad A (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-12 |  | 051200-116.0 Roof Strength Steel Quad A (MAM Review).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-11-12 |  | 051200-116.0 Roof Strength Steel Quad A (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-12-02 |  | 051200-116.0 Roof Strength Steel Quad A_MAM_TT_POP.pdf
05 12 00-116-01 | 05 12 00 - STEEL | 05 12 00-116-00 Roof Strengthening Steel Quad A Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 12 00-116-00 - 05 12 00-116-00 Roof Strengthening Steel Quad A Shop Drawings | -1 | 2019-12-16
05 12 00-117-00 | 05 12 00 - STEEL | 05 12 00-117-00 Roof Strengthening Steel Quad B Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-04 08:00 | 2019-12-10 | 23 |  | Record Copies; Transfers; Submittals | 05 12 00-117-01 - 05 12 00-117-00 Roof Strengthening Steel Quad B Shop Drawings | 23 |  | 2019-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03228 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-12-04 08:00 | Submittal Number: 05 12 00-117.0 From: JES PELKEY Final Due Date: 12/04/19 Subject: ROOF STRENGTHENING STEEL QUAD B SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04667 | Forwarded | For Review | 2019-11-18 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-25 | Submittal Number: 05 12 00-117.0 From: JES PELKEY Final Due Date: 12/04/19 Subject: ROOF STRENGTHENING STEEL QUAD B SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03583 | Review Response | Approved as Noted/Resubmit | 2019-12-10 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | EACH INDIVIDUAL SHEET APPROVED/APPROVED AS NOTED UNLESS STAMPED AS REVISE & RESUBMIT. Pop to review: PN15 (pg 255) R&R List: 1969P | Info Exchange
| 05063 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-10 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-15 |  | 051200-117.0 Roof Strength Steel Quad B (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-15 |  | 051200-117.0 Roof Strength Steel Quad B (MAM Review).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-11-15 |  | 051200-117.0 Roof Strength Steel Quad B (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-12-10 |  | 051200-117.0 Roof Strength Steel Quad B MAM_TT_POP.pdf
05 12 00-117-01 | 05 12 00 - STEEL | 05 12 00-117-00 Roof Strengthening Steel Quad B Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 12 00-117-00 - 05 12 00-117-00 Roof Strengthening Steel Quad B Shop Drawings | -1 | 2019-12-24
05 12 00-121-00 | 05 12 00 - STEEL | 05 12 00-121-00 Sequence 9902 Quad C Connection Materials | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-30 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill |  |  |  | 2019-11-13 | 2019-11-05 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-11-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02981 | Received | For Review | 2019-10-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-11-13 | Submittal Number: 05 12 00-121.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/13/19 Subject: SEQUENCE 9902 QUAD C CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04364 | Forwarded | For Review | 2019-10-30 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-06 | Submittal Number: 05 12 00-121.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/13/19 Subject: SEQUENCE 9902 QUAD C CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03056 | Review Response | Approved as Noted/Resubmit | 2019-11-05 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous); Populous SCA_CCA |  | Arch to verify dimensions as noted. Resubmit sheets with R&R stamps on them. All other sheets are approved as noted. | Info Exchange
| 04451 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-05 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for comments and review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-30 |  | 05 12 00-121.0-Quad C Connection Materials-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-30 |  | 05 12 00-121.0-Quad C Connection Materials-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-30 |  | 05 12 00-121.0-Quad C Connection Materials-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-11-05 |  | 05 12 00-121.0-Quad C Connection Materials-MAM_TT_POP.pdf
05 12 00-121-01 | 05 12 00 - STEEL | 05 12 00-121-01 Sequence 9903 & 9904 Quad C Connection Materials | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-20 | 15 |  | Record Copies; Transfers; Submittals | 05 12 00-121-01-01 - 05 12 00-121-01 Sequence 9903 & 9904 Quad C Connection Materials | 15 |  | 2020-02-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04234 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-20 | Submittal Number: 05 12 00-121.1 From: BRAD KIRSCHENHEITER Final Due Date: 02/17/20 Subject: SEQUENCE 9903 & 9904 QUAD C CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05863 | Forwarded | For Review | 2020-02-06 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 05 12 00-121.1 From: BRAD KIRSCHENHEITER Final Due Date: 02/17/20 Subject: SEQUENCE 9903 & 9904 QUAD C CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04434 | Review Response | Approved as Noted/Resubmit | 2020-02-20 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Please provide connection material for the steel added per RFI 1824. All other pieces are approved as noted. | Info Exchange
| 06121 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review and comments. | Info Exchange
| 06227 | Sent | For Construction | 2020-02-26 | Populous SCA_CCA | Will Traylor (M.A. Mortenson Company); Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Please provide connection material for the steel added per RFI 1824. All other pieces are approved as noted. Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) Remarks: See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 05 12 00-121.1 Quad C Connex Materials-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-06 |  | 05 12 00-121.1 Quad C Connex Materials-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-06 |  | 05 12 00-121.1 Quad C Connex Materials-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-20 |  | 05 12 00-121.1 Quad C Connex Materials-MAM_TT_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2020-02-05 02:00 |  | 05 12 00-121.1 Quad C Connex Materials-MAM.pdf
05 12 00-121-01-01 | 05 12 00 - STEEL | 05 12 00-121-01 Sequence 9903 & 9904 Quad C Connection Materials | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 12 00-121-01 - 05 12 00-121-01 Sequence 9903 & 9904 Quad C Connection Materials | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-20 |  | 05 12 00-121.1 Quad C Connex Materials-MAM_TT_POP.pdf
05 12 00-122-00 | 05 12 00 - STEEL | 05 12 00-122-00 NE Snorkel Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-21 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-11-04 | 2019-11-08 | 19 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-11-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02849 | Received | For Review | 2019-10-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-11-04 | Submittal Number: 05 12 00-122.0 From: JES PELKEY Final Due Date: 11/02/19 Subject: NE SNORKEL SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04207 | Forwarded | For Review | 2019-10-21 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-28 | Submittal Number: 05 12 00-122.0 From: JES PELKEY Final Due Date: 11/02/19 Subject: NE SNORKEL SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03043 | Review Response | Approved as Noted | 2019-11-04 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04433 | Forwarded | For Review | 2019-11-04 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-11-04 | Submittal Number: 05 12 00-122.0 From: JES PELKEY Final Due Date: 11/02/19 Subject: NE SNORKEL SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04536 | Responded and Closed | Approved as Noted | 2019-11-08 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-18 |  | 05 12 00-122.0 NE Snorkel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-18 |  | 05 12 00-122.0 NE Snorkel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-17 02:00 |  | 05 12 00-122.0 NE Snorkel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-17 02:00 |  | 05 12 00-122.0 NE Snorkel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-11-08 |  | 05 12 00-122.0 NE Snorkel SD-MAM_TT_POP.pdf
05 12 00-124-00 | 05 12 00 - STEEL | 05 12 00-124-00 NW Snorkel Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-25 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-17 | 2019-12-20 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2019-12-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03355 | Received | For Review | 2019-11-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-17 | Submittal Number: 05 12 00-124.0 From: JES PELKEY Final Due Date: 12/10/19 Subject: NW SNORKEL SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04809 | Forwarded | For Review | 2019-11-25 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-02 | Submittal Number: 05 12 00-124.0 From: JES PELKEY Final Due Date: 12/10/19 Subject: NW SNORKEL SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03721 | Review Response | Approved as Noted | 2019-12-20 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Coordinate W12 strut connections to misaligned soldier piles with TT response to RFIs 1845 and 1844.1. | Info Exchange
| 05251 | Responded and Closed | Approved as Noted | 2019-12-20 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Coordinate W12 strut connections to misaligned soldier piles with TT response to RFIs 1845 and 1844.1. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-25 |  | 05 12 00-124.0 NW Snorkel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-25 |  | 05 12 00-124.0 NW Snorkel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-24 02:00 |  | 05 12 00-124.0 NW Snorkel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-20 02:00 |  | 05 12 00-124.0 NW Snorkel SD-MAM_TT REVIEW_POP.pdf
05 12 00-125-00 | 05 12 00 - STEEL | 05 12 00-125-00 SE Snorkel Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-12 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-26 | 2020-04-05 | 25 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04774 | Received | For Review | 2020-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-03-26 | Submittal Number: 05 12 00-125.0 From: JES PELKEY Final Due Date: 03/25/20 Subject: SE SNORKEL SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06549 | Forwarded | For Review | 2020-03-12 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-19 | Submittal Number: 05 12 00-125.0 From: JES PELKEY Final Due Date: 03/25/20 Subject: SE SNORKEL SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05162 | Review Response | Approved as Noted/Resubmit | 2020-03-30 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07091 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-05 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and response. Submit RFI for steel 'T' for columns on grid SA.3. Various RFI responses noted in review comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 05 12 00-125.0 SE Snorkel Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-11 |  | 05 12 00-125.0 SE Snorkel Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-11 |  | 05 12 00-125.0 SE Snorkel Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-05 |  | 05 12 00-125.0 SE Snorkel Steel SD-MAM_TT_POP.pdf
05 12 00-125-01 | 05 12 00 - STEEL | 05 12 00-125-01 SE Snorkel Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-01 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-15 | 2020-07-14 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06716 | Received | For Review | 2020-07-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company); Jes Pelkey (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-07-15 | Submittal Number: 05 12 00-125.1 From: JES PELKEY Final Due Date: 03/02/20 Subject: SE SNORKEL SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09030 | Forwarded | For Review | 2020-06-30 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-07 | Submittal Number: 05 12 00-125.1 From: JES PELKEY Final Due Date: 03/02/20 Subject: SE SNORKEL SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06951 | Review Response | Approved as Noted | 2020-07-13 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09314 | Responded and Closed | Approved as Noted | 2020-07-14 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-30 |  | 05 12 00-125 SE Snorkel Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-30 |  | 05 12 00-125 SE Snorkel Shop Drawings.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-30 |  | 05 12 00-125 SE Snorkel Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-14 |  | 05 12 00-125 SE Snorkel Shop Drawings_TT_POP.pdf
05 12 00-132-00 | 05 12 00 - STEEL | 05 12 00-132-00 Product Data - Hilti Anchors & Epoxy for Infill Truss Connection to Ring Beam | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-04 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-09-18 | 2019-09-20 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-09-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02286 | Received | For Review | 2019-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Nate Weingart (Mortenson Construction) | 2019-09-18 | Submittal Number: 05 12 00-132.0 From: NATE WEINGART Final Due Date: 09/17/19 Subject: PRODUCT DATA - HILTI ANCHORS & EPOXY FOR INFILL TRUSS CONNECTION TO RING BEAM Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| t | Forwarded | For Review | 2019-09-03 | Nate Weingart (Mortenson Construction) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-11 | Submittal Number: 05 12 00-132.0 From: NATE WEINGART Final Due Date: 09/17/19 Subject: PRODUCT DATA - HILTI ANCHORS & EPOXY FOR INFILL TRUSS CONNECTION TO RING BEAM Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Email
| 02473 | Review Response | Approved | 2019-09-18 | Matt Ross (Thornton Tomasetti) | Nate Weingart (Mortenson Construction) |  |  | Info Exchange
| 03747 | Responded and Closed | Approved | 2019-09-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Nate Weingart (Mortenson Construction) | 1 | 2019-09-03 02:00 |  | 051200-PD-001.0 Hilti Anchors & Epoxy for Infill Truss to Ring Beam (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-03 02:00 |  | 051200-PD-001.0 Hilti Anchors & Epoxy for Infill Truss to Ring Beam (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-20 02:00 |  | 051200-132.0 Hilti Anchors Epoxy for Infill Truss to Ring Beam (MAM Review)_TT_POP.pdf
05 12 00-138-00 | 05 12 00 - STEEL | 05 12 00-138-00 Roof Hanging Scaffold Design & Engineering Submittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-16 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-09-30 | 2019-10-02 | 17 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2019-10-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02407 | Received | For Review | 2019-09-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-09-30 | Submittal Number: 05 12 00-138.0 From: NATE WEINGART Final Due Date: 09/20/19 Subject: ROOF HANGING SCAFFOLD DESIGN & ENGINEERING SUBMITTAL Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03663 | Forwarded | For Review | 2019-09-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-20 | Submittal Number: 05 12 00-138.0 From: NATE WEINGART Final Due Date: 09/20/19 Subject: ROOF HANGING SCAFFOLD DESIGN & ENGINEERING SUBMITTAL Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03940 | Responded and Closed | Not Required For Review | 2019-10-02 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Submittal not required for review by permanent design team. Submittal is to be handled by TT and Mortenson directly through Procore. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-13 |  | 051200-138.0 Roof Scaffold D&E Submittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-13 |  | 051200-138.0 Roof Scaffold D&E Submittal (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-02 02:00 |  | 051200-138.0 Roof Scaffold D&E Submittal (MAM Review)_POP.pdf
05 12 00-141-00 | 05 12 00 - STEEL | 05 12 00-141-00 Main Roof Rotation Bearings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-05 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-11-19 | 2019-11-15 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-11-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03051 | Received | For Review | 2019-11-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-11-19 | Submittal Number: 05 12 00-141.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/20/19 Subject: MAIN ROOF ROTATION BEARINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04441 | Forwarded | For Review | 2019-11-05 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-12 | Submittal Number: 05 12 00-141.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/20/19 Subject: MAIN ROOF ROTATION BEARINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03221 | Review Response | Revise and Resubmit | 2019-11-15 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Please revise and resubmit per TT's comments. | Info Exchange
| 04660 | Responded and Closed | Revise and Resubmit | 2019-11-15 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Please revise and resubmit per TT's comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-05 |  | 05 12 00-141.0 Main Roof Rotation Bearings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-05 |  | 05 12 00-141.0 Main Roof Rotation Bearings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-04 02:00 |  | 05 12 00-141.0 Main Roof Rotation Bearings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-11-15 02:00 |  | 05 12 00-141.0 Main Roof Rotation Bearings-MAM-TT REVIEW_POP.pdf
05 12 00-141-01 | 05 12 00 - STEEL | 05 12 00-141-01 Main Roof Rotation Bearings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-02 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-16 | 2019-12-03 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03423 | Received | For Review | 2019-12-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-16 | Submittal Number: 05 12 00-141.1 From: BRAD KIRSCHENHEITER Final Due Date: 12/16/19 Subject: MAIN ROOF ROTATION BEARINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04894 | Forwarded | For Review | 2019-12-02 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-09 | Submittal Number: 05 12 00-141.1 From: BRAD KIRSCHENHEITER Final Due Date: 12/16/19 Subject: MAIN ROOF ROTATION BEARINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03445 | Review Response | Approved | 2019-12-03 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04917 | Responded and Closed | Approved | 2019-12-03 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-02 |  | 05 12 00-141.1 Main Roof Rotation Bearings REV1-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-02 |  | 05 12 00-141.1 Main Roof Rotation Bearings REV1-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-01 02:00 |  | 05 12 00-141.1 Main Roof Rotation Bearings REV1-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-03 02:00 |  | 05 12 00-141.1 Main Roof Rotation Bearings REV1-MAM_TT REVIEW_POP.pdf
05 12 00-145-00 | 05 12 00 - STEEL | 05 12 00-145-00 Corebrace BRB Rev 0 Submittal Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-28 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill |  |  |  | 2019-11-11 | 2019-11-05 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-11-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02937 | Received | For Review | 2019-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-11-11 | Submittal Number: 05 12 00-145.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/12/19 Subject: COREBRACE BRB REV 0 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04309 | Forwarded | For Review | 2019-10-28 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-04 | Submittal Number: 05 12 00-145.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/12/19 Subject: COREBRACE BRB REV 0 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03058 | Review Response | Rejected | 2019-11-05 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Gusset to beam and gusset to column interfaces are to be designed for resolved brace component eccentric to brace centerline, typ. Additionally, some calcs are using the UFM which is not an acceptable design method. Please use the KISS method for all brace connection design. Please revise calcs and resubmit for review. | Info Exchange
| 04454 | Responded and Closed | Rejected | 2019-11-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-28 |  | 05 12 00-145.0 Corebrace BRB Submittal Package-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-28 |  | 05 12 00-145.0 Corebrace BRB Submittal Package-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-28 |  | 05 12 00-145.0 Corebrace BRB Submittal Package-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-11-05 |  | 05 12 00-145.0 Corebrace BRB Submittal Package-MAM_TT_POP.pdf
05 12 00-145-01 | 05 12 00 - STEEL | 05 12 00-145-01 Corebrace BRB Rev 1 Submittal Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-15 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-02 | 2019-11-18 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2019-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03216 | Received | For Review | 2019-11-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-02 | Submittal Number: 05 12 00-145.1 From: BRAD KIRSCHENHEITER Final Due Date: 11/29/19 Subject: COREBRACE BRB REV 1 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04650 | Forwarded | For Review | 2019-11-15 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-22 | Submittal Number: 05 12 00-145.1 From: BRAD KIRSCHENHEITER Final Due Date: 11/29/19 Subject: COREBRACE BRB REV 1 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03247 | Review Response | Revise and Resubmit | 2019-11-18 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | See comments on page 1 of submittal. | Info Exchange
| 04689 | Responded and Closed | Revise and Resubmit | 2019-11-18 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: See comments on page 1 of submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-15 |  | 05 12 00-145.1 Corebrace BRB SD and Calcs-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-15 |  | 05 12 00-145.1 Corebrace BRB SD and Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-14 02:00 |  | 05 12 00-145.1 Corebrace BRB SD and Calcs-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-11-18 02:00 |  | 05 12 00-145.1 Corebrace BRB SD and Calcs-MAM_TT REVIEW_POP.pdf
05 12 00-145-02 | 05 12 00 - STEEL | 05 12 00-145-02 Corebrace BRB Rev 2 Submittal Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-09 08:00 | 2019-11-21 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-11-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03296 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-09 08:00 | Submittal Number: 05 12 00-145.2 From: BRAD KIRSCHENHEITER Final Due Date: 11/29/19 Subject: COREBRACE BRB REV 2 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04745 | Forwarded | For Review | 2019-11-20 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-27 | Submittal Number: 05 12 00-145.2 From: BRAD KIRSCHENHEITER Final Due Date: 11/29/19 Subject: COREBRACE BRB REV 2 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03322 | Review Response | Approved | 2019-11-21 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04777 | Responded and Closed | Approved | 2019-11-21 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-20 |  | 05 12 00-145.2 Corebrace BRB Rev 2 SD and Calcs-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-20 |  | 05 12 00-145.2 Corebrace BRB Rev 2 SD and Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-19 02:00 |  | 05 12 00-145.2 Corebrace BRB Rev 2 SD and Calcs-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-11-21 02:00 |  | 05 12 00-145.2 Corebrace BRB Rev 2 SD and Calcs-MAM_TT REVIEW_POP.pdf
05 12 00-145-03 | 05 12 00 - STEEL | 05 12 00-145-03 Corebrace BRB Rev 3 Submittal Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-27 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-11 | 2019-12-11 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-12-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03404 | Received | For Review | 2019-11-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-11 | Submittal Number: 05 12 00-145.3 From: BRAD KIRSCHENHEITER Final Due Date: 12/13/19 Subject: COREBRACE BRB REV 3 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04871 | Forwarded | For Review | 2019-11-27 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-04 | Submittal Number: 05 12 00-145.3 From: BRAD KIRSCHENHEITER Final Due Date: 12/13/19 Subject: COREBRACE BRB REV 3 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03605 | Review Response | Approved | 2019-12-11 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has only reviewed 11 clouded BRBs in green as newly designed items. Shaded items in tables are noted to have changed since rev 1 and not necessarily between rev 2 and 3. Please notify TT is any other changes have been made between rev 2 and 3 not related to those 11 BRBs | Info Exchange
| 05086 | Responded and Closed | Approved | 2019-12-11 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has only reviewed 11 clouded BRBs in green as newly designed items. Shaded items in tables are noted to have changed since rev 1 and not necessarily between rev 2 and 3. Please notify TT is any other changes have been made between rev 2 and 3 not related to those 11 BRBs | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-27 |  | 05 12 00-145.3 Corebrace BRB Rev 3 SD and Calcs-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-27 |  | 05 12 00-145.3 Corebrace BRB Rev 3 SD and Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-26 02:00 |  | 05 12 00-145.3 Corebrace BRB Rev 3 SD and Calcs-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-11 02:00 |  | 05 12 00-145.3 Corebrace BRB Rev 3 SD and Calcs-MAM_TT REVIEW_POP.pdf
05 12 00-145-04 | 05 12 00 - STEEL | 05 12 00-145-04 Corebrace BRB Rev 4 Submittal Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-17 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-31 | 2020-02-05 | 20 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-02-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03967 | Received | For Review | 2020-01-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-31 | Submittal Number: 05 12 00-145.4 From: BRAD KIRSCHENHEITER Final Due Date: 01/30/20 Subject: COREBRACE BRB REV 4 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05536 | Forwarded | For Review | 2020-01-17 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-24 | Submittal Number: 05 12 00-145.4 From: BRAD KIRSCHENHEITER Final Due Date: 01/30/20 Subject: COREBRACE BRB REV 4 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04215 | Review Response | Approved as Noted/Resubmit | 2020-02-04 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | All BRBs except those attaching to the rigging grid are approved as noted. Please resubmit rigging grid BRBs with drawings and calcs. | Info Exchange
| 05841 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: All BRBs except those attaching to the rigging grid are approved as noted. Please resubmit rigging grid BRBs with drawings and calcs. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-16 |  | 05 12 00-145.4 Corebrace BRB Rev 4 SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-16 |  | 05 12 00-145.4 Corebrace BRB Rev 4 SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-15 02:00 |  | 05 12 00-145.4 Corebrace BRB Rev 4 SD-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-05 02:00 |  | 05 12 00-145.4 Corebrace BRB Rev 4 SD-MAM_TT REVIEW_POP.pdf
05 12 00-145-05 | 05 12 00 - STEEL | 05 12 00-145-05 Corebrace BRB Rev 5 Submittal Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-07 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-21 | 2020-02-20 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-02-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04260 | Received | For Review | 2020-02-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) | 2020-02-21 | Submittal Number: 05 12 00-145.5 From: BRAD KIRSCHENHEITER Final Due Date: 02/21/20 Subject: COREBRACE BRB REV 5 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05895 | Forwarded | For Review | 2020-02-07 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-14 | Submittal Number: 05 12 00-145.5 From: BRAD KIRSCHENHEITER Final Due Date: 02/21/20 Subject: COREBRACE BRB REV 5 SUBMITTAL PACKAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04433 | Review Response | Approved as Noted | 2020-02-19 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06120 | Responded and Closed | Approved as Noted | 2020-02-20 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-07 |  | 05 12 00-145.5 Corebrace BRB Rev 5 SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-07 |  | 05 12 00-145.5 Corebrace BRB Rev 5 SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-07 |  | 05 12 00-145.5 Corebrace BRB Rev 5 SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-20 |  | 05 12 00-145.5 Corebrace BRB Rev 5 SD-MAM_TT_POP.pdf
05 12 00-145-06 | 05 12 00 - STEEL | 05 12 00-145-06 Corebrace BRB Rev 7 Submittal Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-06 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-20 | 2020-05-11 | 6 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-05-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05733 | Received | For Review | 2020-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-20 | Submittal Number: 05 12 00-145.6 From: BRAD KIRSCHENHEITER Final Due Date: 05/19/20 Subject: COREBRACE BRB REV 7 SUBMITTAL PACKAGE Description: SEE ATTACHED FOR REV 7. THIS REVISION ADJUSTS THE LENGTHS OF BRB 1917 (TWO BRACES) AND ALSO ADDS IN BRB 1983 (TWO NEW BRACES). PLEASE NOTE THAT REV 6 WAS FOR COORDINATION PURPOSES BETWEEN COREBRACE AND OUR STEEL DETAILER AND WAS NOT SUBMITTED FOR APPROVAL. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07779 | Forwarded | For Review | 2020-05-05 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-12 | Submittal Number: 05 12 00-145.6 From: BRAD KIRSCHENHEITER Final Due Date: 05/19/20 Subject: COREBRACE BRB REV 7 SUBMITTAL PACKAGE Description: SEE ATTACHED FOR REV 7. THIS REVISION ADJUSTS THE LENGTHS OF BRB 1917 (TWO BRACES) AND ALSO ADDS IN BRB 1983 (TWO NEW BRACES). PLEASE NOTE THAT REV 6 WAS FOR COORDINATION PURPOSES BETWEEN COREBRACE AND OUR STEEL DETAILER AND WAS NOT SUBMITTED FOR APPROVAL. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05772 | Review Response | Approved | 2020-05-08 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 07830 | Responded and Closed | Approved | 2020-05-11 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | 05 12 00-145.6 Corebrace BRB SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-05 |  | 05 12 00-145.6 Corebrace BRB SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-05 |  | 05 12 00-145.6 Corebrace BRB SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-11 |  | 05 12 00-145.6 Corebrace BRB SD-MAM_TT_POP.pdf
05 12 00-145-07 | 05 12 00 - STEEL | 05 12 00-145-07 Corebrace BRB Rev 8 - Updated Schedule | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-02 | 2020-05-26 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05932 | Received | For Review | 2020-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-02 | Submittal Number: 05 12 00-145.7 From: BRAD KIRSCHENHEITER Final Due Date: 06/02/20 Subject: COREBRACE BRB REV 8 - UPDATED SCHEDULE Description: SEE ATTACHED FOR REV 7. THIS REVISION ADJUSTS THE LENGTHS OF BRB 1917 (TWO BRACES) AND ALSO ADDS IN BRB 1983 (TWO NEW BRACES). PLEASE NOTE THAT REV 6 WAS FOR COORDINATION PURPOSES BETWEEN COREBRACE AND OUR STEEL DETAILER AND WAS NOT SUBMITTED FOR APPROVAL. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08051 | Forwarded | For Review | 2020-05-19 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-26 | Submittal Number: 05 12 00-145.7 From: BRAD KIRSCHENHEITER Final Due Date: 06/02/20 Subject: COREBRACE BRB REV 8 - UPDATED SCHEDULE Description: SEE ATTACHED FOR REV 7. THIS REVISION ADJUSTS THE LENGTHS OF BRB 1917 (TWO BRACES) AND ALSO ADDS IN BRB 1983 (TWO NEW BRACES). PLEASE NOTE THAT REV 6 WAS FOR COORDINATION PURPOSES BETWEEN COREBRACE AND OUR STEEL DETAILER AND WAS NOT SUBMITTED FOR APPROVAL. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06042 | Review Response | Approved as Noted | 2020-05-26 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Note to Detailer: a few BRBs have been updated that were already approved per previous calcs. TT has only reviewed portions of this submittal that have been clouded or shaded cells of BRB schedules. All other pieces are assumed to have been unchanged since previous review. | Info Exchange
| 08185 | Responded and Closed | Approved as Noted | 2020-05-26 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Note to Detailer: a few BRBs have been updated that were already approved per previous calcs. TT has only reviewed portions of this submittal that have been clouded or shaded cells of BRB schedules. All other pieces are assumed to have been unchanged since previous review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 |  | 05 12 00-145.7 Corebrace BRB Rev. 8-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-19 |  | 05 12 00-145.7 Corebrace BRB Rev. 8-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-19 |  | 05 12 00-145.7 Corebrace BRB Rev. 8-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-26 |  | 05 12 00-145.7 Corebrace BRB Rev. 8-MAM_TT_POP.pdf
05 12 00-145-08 | 05 12 00 - STEEL | 05 12 00-145-08 Corebrace BRB Rev 9 - Updated Schedule for Rigging Grid Connections | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-28 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-14 07:00 | 2020-09-02 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07797 | Received | For Review | 2020-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company) | 2020-09-14 07:00 | Submittal Number: 05 12 00-145.8 From: BRAD KIRSCHENHEITER Final Due Date: 09/10/20 Subject: COREBRACE BRB REV 9 - UPDATED SCHEDULE FOR RIGGING GRID CONNECTIONS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 10375 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-03 | Submittal Number: 05 12 00-145.8 From: BRAD KIRSCHENHEITER Final Due Date: 09/10/20 Subject: COREBRACE BRB REV 9 - UPDATED SCHEDULE FOR RIGGING GRID CONNECTIONS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07895 | Review Response | Approved | 2020-09-01 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 10496 | Responded and Closed | Approved | 2020-09-02 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR APPROVAL | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 05 12 00-145.8 Corebrace BRB Rev. 9 Rigging Grid-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-27 |  | 05 12 00-145.8 Corebrace BRB Rev. 9 Rigging Grid-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-27 |  | 05 12 00-145.8 Corebrace BRB Rev. 9 Rigging Grid-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-02 |  | 05 12 00-145.8 Corebrace BRB Rev. 9 Rigging Grid-MAM_TT_POP.pdf
05 12 00-151-00 | 05 12 00 - STEEL | 05 12 00-151-00 Welding Procedures - Roof Strengthening Steel & Garage | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-21 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-11-04 | 2019-10-30 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-10-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02860 | Received | For Review | 2019-10-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-11-04 | Submittal Number: 05 12 00-151.0 From: NATE WEINGART Final Due Date: 11/01/19 Subject: WELDING PROCEDURES - ROOF STRENGTHENING STEEL & GARAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04218 | Forwarded | For Review | 2019-10-21 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-28 | Submittal Number: 05 12 00-151.0 From: NATE WEINGART Final Due Date: 11/01/19 Subject: WELDING PROCEDURES - ROOF STRENGTHENING STEEL & GARAGE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 02978 | Review Response | Rejected | 2019-10-30 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | This submittal has not been reviewed and approved by the Owner’s Testing Agency prior to submission to TT, as required by Specification 051200 1.6.A.9. All the submitted WPSs are marked as pre-qualified. However, the welds to the existing tri-chord truss will be to base metal that is not prequalified per AWS D1.1 Clause 3 requirements. Submit WPSs and PQRs for the non-prequalified welds for EOR review and approval. | Info Exchange
| 04361 | Responded and Closed | Rejected | 2019-10-30 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | This submittal has not been reviewed and approved by the Owner’s Testing Agency prior to submission to TT, as required by Specification 051200 1.6.A.9. All the submitted WPSs are marked as pre-qualified. However, the welds to the existing tri-chord truss will be to base metal that is not prequalified per AWS D1.1 Clause 3 requirements. Submit WPSs and PQRs for the non-prequalified welds for EOR review and approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-21 |  | 051200-151.0 Welding Procedures - Roof Strength & Garage (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-21 |  | 051200-151.0 Welding Procedures - Roof Strength & Garage (MAM Review).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-10-21 |  | 051200-151.0 Welding Procedures - Roof Strength & Garage (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-30 |  | 051200-151.0 Welding Procedures - Roof Strength & Garage_MAM_TT_POP.pdf
05 12 00-154-00 | 05 12 00 - STEEL | 05 12 00-154-00 Sequence 9909 & 9910 Quad A Connection Materials | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-25 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-09 | 2019-12-04 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-12-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03361 | Received | For Review | 2019-11-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-09 | Submittal Number: 05 12 00-154.0 From: BRAD KIRSCHENHEITER Final Due Date: 12/09/19 Subject: SEQUENCE 9909 & 9910 QUAD A CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04817 | Forwarded | For Review | 2019-11-25 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-02 | Submittal Number: 05 12 00-154.0 From: BRAD KIRSCHENHEITER Final Due Date: 12/09/19 Subject: SEQUENCE 9909 & 9910 QUAD A CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03501 | Review Response | Approved as Noted/Resubmit | 2019-12-03 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | See stamps on sheets for pieces TT is required to review again once revised. Note, slide bearing assemblies at Upper Concourse Y-Columns were not reviewed by TT as these are on hold pending redesign. All other pieces are approved as noted. | Info Exchange
| 04964 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-25 |  | 05 12 00-154.0 Quad A Connection Material-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-25 |  | 05 12 00-154.0 Quad A Connection Material-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-25 |  | 05 12 00-154.0 Quad A Connection Material-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-04 |  | 05 12 00-154.0 Quad A Connection Material-MAM_TT_POP.pdf
05 12 00-154-01 | 05 12 00 - STEEL | 05 12 00-154-01 Sequence 9909 & 9910 Quad A Connection Materials | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-20 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-02-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04229 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-20 | Submittal Number: 05 12 00-154.1 From: BRAD KIRSCHENHEITER Final Due Date: 02/18/20 Subject: SEQUENCE 9909 & 9910 QUAD A CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05858 | Forwarded | For Review | 2020-02-06 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 05 12 00-154.1 From: BRAD KIRSCHENHEITER Final Due Date: 02/18/20 Subject: SEQUENCE 9909 & 9910 QUAD A CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04435 | Review Response | Approved as Noted | 2020-02-20 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06122 | Responded and Closed | Approved as Noted | 2020-02-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 05 12 00-154.1 Quad A Connection Material-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-06 |  | 05 12 00-154.1 Quad A Connection Material-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-06 |  | 05 12 00-154.1 Quad A Connection Material-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-20 |  | 05 12 00-154.1 Quad A Connection Material-MAM_TT_POP.pdf
05 12 00-155-00 | 05 12 00 - STEEL | 05 12 00-155-00 Hilti Pins & Punch Lok Product Data and Calcs | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-13 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-27 | 2020-04-01 | 20 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-04-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04797 | Received | For Review | 2020-03-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-27 | Submittal Number: 05 12 00-155.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/09/20 Subject: HILTI PINS & PUNCH LOK PRODUCT DATA AND CALCS Description: SUBMITTING HILTI PRODUCT DATA TO USE ENP-19 L15 PINS AS AN ALTERNATE TO PUDDLE WELDING THE METAL DECK. SIDELAPS TO BE CONNECTED USING THE VERCO VSC2 SYSTEM AS AN ALTERNATE TO WELDING. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06574 | Forwarded | For Review | 2020-03-12 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-19 | Submittal Number: 05 12 00-155.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/09/20 Subject: HILTI PINS & PUNCH LOK PRODUCT DATA AND CALCS Description: SUBMITTING HILTI PRODUCT DATA TO USE ENP-19 L15 PINS AS AN ALTERNATE TO PUDDLE WELDING THE METAL DECK. SIDELAPS TO BE CONNECTED USING THE VERCO VSC2 SYSTEM AS AN ALTERNATE TO WELDING. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05168 | Review Response | Approved | 2020-04-01 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 07005 | Responded and Closed | Approved | 2020-04-01 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-12 |  | 05 12 00-155.0 Hilti Pins and Punch Lok PD and Calc-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-12 |  | 05 12 00-155.0 Hilti Pins and Punch Lok PD and Calc-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-12 |  | 05 12 00-155.0 Hilti Pins and Punch Lok PD and Calc-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-01 |  | 05 12 00-155.0 Hilti Pins and Punch Lok PD and Calc-MAM_TT_POP.pdf
05 12 00-156-00 | 05 12 00 - STEEL | 05 12 00-156-00 Quad C2 Steel Shop Drawings - Sequence 524 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-13 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-11-27 | 2019-12-03 | 21 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03184 | Received | For Review | 2019-11-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-11-27 | Submittal Number: 05 12 00-156.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/28/19 Subject: QUAD C2 STEEL SHOP DRAWINGS - SEQUENCE 524 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04609 | Forwarded | For Review | 2019-11-13 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-20 | Submittal Number: 05 12 00-156.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/28/19 Subject: QUAD C2 STEEL SHOP DRAWINGS - SEQUENCE 524 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03392 | Review Response | Approved as Noted | 2019-11-26 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04858 | Forwarded | For Review | 2019-11-26 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-11-27 | Submittal Number: 05 12 00-156.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/28/19 Subject: QUAD C2 STEEL SHOP DRAWINGS - SEQUENCE 524 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04914 | Responded and Closed | Approved as Noted | 2019-12-03 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-13 |  | 05 12 00-156.0 Quad C2 - Seq. 524-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-13 |  | 05 12 00-156.0 Quad C2 - Seq. 524-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-12 02:00 |  | 05 12 00-156.0 Quad C2 - Seq. 524-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-12 02:00 |  | 05 12 00-156.0 Quad C2 - Seq. 524-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-03 |  | 05 12 00-156.0 Quad C2 - Seq. 524-MAM_TT_POP.pdf
05 12 00-158-00 | 05 12 00 - STEEL | 05 12 00-158-00 Corebrace BRB QA/QC Document | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-25 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-08 | 2020-03-30 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-03-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05032 | Received | For Review | 2020-03-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-08 | Submittal Number: 05 12 00-158.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/08/20 Subject: COREBRACE BRB QA/QC DOCUMENT Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06852 | Forwarded | For Review | 2020-03-25 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-01 | Submittal Number: 05 12 00-158.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/08/20 Subject: COREBRACE BRB QA/QC DOCUMENT Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05108 | Review Response | Not Required For Review | 2020-03-30 | Sean McNeill (Thornton Tomasetti) | Populous SCA_CCA |  | Received for Record | Info Exchange
| 06938 | Responded and Closed | Not Required For Review | 2020-03-30 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | Received for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-25 |  | 05 12 00-158.0 CoreBrace BRB QA-QC Plan-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-25 |  | 05 12 00-158.0 CoreBrace BRB QA-QC Plan-MAM.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-03-25 |  | 05 12 00-158.0 CoreBrace BRB QA-QC Plan-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-30 |  | 05 12 00-158.0 CoreBrace BRB QA-QC Plan-MAM_TT_POP.pdf
05 12 00-159-00 | 05 12 00 - STEEL | 05 12 00-159-00 Quad E2 Steel SD - Seq. 706-710 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-17 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-06 | 2020-02-28 | 43 |  | Record Copies; Transfers; Submittals |  | 25 |  | 2020-02-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03968 | Received | For Review | 2020-01-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-02-06 | Submittal Number: 05 12 00-159.0 From: JES PELKEY Final Due Date: 01/31/20 Subject: QUAD E2 STEEL SD - SEQ. 706-710 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05537 | Forwarded | For Review | 2020-01-17 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-24 | Submittal Number: 05 12 00-159.0 From: JES PELKEY Final Due Date: 01/31/20 Subject: QUAD E2 STEEL SD - SEQ. 706-710 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04380 | Review Response | Approved as Noted/Resubmit | 2020-02-10 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06283 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-28 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-17 |  | 05 12 00-159.0 Quad E2 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-17 |  | 05 12 00-159.0 Quad E2 Steel SD-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-01-17 |  | 05 12 00-159.0 Quad E2 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-28 |  | 05 12 00-159.0 Quad E2 Steel SD-MAM_TT_POP.pdf
05 12 00-159-01 | 05 12 00 - STEEL | 05 12 00-159-01 Quad E2 Steel SD - Seq. 706-710 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-19 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-02 | 2020-04-02 | 15 |  | Record Copies; Transfers; Submittals | 05 12 00-159-01-01 - 05 12 00-159-01 Quad E2 Steel SD - Seq. 706-710 | 16 |  | 2020-04-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04933 | Received | For Review | 2020-03-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-02 | Submittal Number: 05 12 00-159.1 From: JES PELKEY Final Due Date: 04/01/20 Subject: QUAD E2 STEEL SD - SEQ. 706-710 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06729 | Forwarded | For Review | 2020-03-18 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-25 | Submittal Number: 05 12 00-159.1 From: JES PELKEY Final Due Date: 04/01/20 Subject: QUAD E2 STEEL SD - SEQ. 706-710 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07027 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-02 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. resubmit for record piece revised from response to RFI 2262. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-18 |  | 05 12 00-159.1 Quad E2 Steel RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-18 |  | 05 12 00-159.1 Quad E2 Steel RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-02 |  | 05 12 00-159.1 Quad E2 Steel RR-MAM_TT_POP.pdf
05 12 00-159-01-01 | 05 12 00 - STEEL | 05 12 00-159-01 Quad E2 Steel SD - Seq. 706-710 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 12 00-159-01 - 05 12 00-159-01 Quad E2 Steel SD - Seq. 706-710 | -1 | 2020-04-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-02 |  | 05 12 00-159.1 Quad E2 Steel RR-MAM_TT_POP.pdf
05 12 00-160-00 | 05 12 00 - STEEL | 05 12 00-160-00 Quad B1 B Steel SD - Seq. 607-612 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-25 | 2020-04-02 | 23 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-04-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04768 | Received | For Review | 2020-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-03-25 | Submittal Number: 05 12 00-160.0 From: JES PELKEY Final Due Date: 04/08/20 Subject: QUAD B1 B STEEL SD - SEQ. 607-612 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06542 | Forwarded | For Review | 2020-03-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-18 | Submittal Number: 05 12 00-160.0 From: JES PELKEY Final Due Date: 04/08/20 Subject: QUAD B1 B STEEL SD - SEQ. 607-612 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05178 | Review Response | Approved as Noted | 2020-03-31 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07024 | Responded and Closed | Approved as Noted | 2020-04-02 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 05 12 00-160.0 Quad B1 B Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-11 |  | 05 12 00-160.0 Quad B1 B Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-11 |  | 05 12 00-160.0 Quad B1 B Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-02 |  | 05 12 00-160.0 Quad B1 B Steel SD-MAM_TT_POP.pdf
05 12 00-161-00 | 05 12 00 - STEEL | 05 12 00-161-00 Quad F2 Steel SD - Seq. 718-721 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-24 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-13 | 2020-03-17 | 23 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04457 | Received | For Review | 2020-02-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-03-13 | Submittal Number: 05 12 00-161.0 From: JES PELKEY Final Due Date: 03/09/20 Subject: QUAD F2 STEEL SD - SEQ. 718-721 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06150 | Forwarded | For Review | 2020-02-24 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-02 | Submittal Number: 05 12 00-161.0 From: JES PELKEY Final Due Date: 03/09/20 Subject: QUAD F2 STEEL SD - SEQ. 718-721 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04872 | Review Response | Approved as Noted/Resubmit | 2020-03-10 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06659 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-17 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-21 |  | 05 12 00-161.0 Quad F2 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-21 |  | 05 12 00-161.0 Quad F2 Steel SD-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-02-21 |  | 05 12 00-161.0 Quad F2 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-21 |  | 05 12 00-161.0 Quad F2 Steel SD-MAM.pdf
05 12 00-161-01 | 05 12 00 - STEEL | 05 12 00-161-01 Quad F2 Steel SD - Seq. 718-721 - 5 sheets | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-07 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-21 | 2020-04-13 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05236 | Received | For Review | 2020-04-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-21 | Submittal Number: 05 12 00-161.1 From: JES PELKEY Final Due Date: 04/21/20 Subject: QUAD F2 STEEL SD - SEQ. 718-721 - 5 SHEETS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07126 | Forwarded | For Review | 2020-04-07 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-14 | Submittal Number: 05 12 00-161.1 From: JES PELKEY Final Due Date: 04/21/20 Subject: QUAD F2 STEEL SD - SEQ. 718-721 - 5 SHEETS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05245 | Review Response | Approved as Noted | 2020-04-08 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07199 | Responded and Closed | Approved as Noted | 2020-04-13 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-07 |  | 05 12 00-161.1 Quad F2 Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-07 |  | 05 12 00-161.1 Quad F2 Steel SD RR-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-04-07 |  | 05 12 00-161.1 Quad F2 Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-13 |  | 05 12 00-161.1 Quad F2 Steel SD RR-MAM_TT_POP.pdf
05 12 00-162-00 | 05 12 00 - STEEL | 05 12 00-162-00 Quad EF1 Steel SD - Seq. 722-723 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-24 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous) |  |  |  | 2020-03-13 | 2020-03-23 | 29 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04458 | Received | For Review | 2020-02-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-03-13 | Submittal Number: 05 12 00-162.0 From: JES PELKEY Final Due Date: 03/09/20 Subject: QUAD EF1 STEEL SD - SEQ. 722-723 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06151 | Forwarded | For Review | 2020-02-24 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-02 | Submittal Number: 05 12 00-162.0 From: JES PELKEY Final Due Date: 03/09/20 Subject: QUAD EF1 STEEL SD - SEQ. 722-723 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04950 | Review Response | Approved as Noted/Resubmit | 2020-03-18 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06765 | Forwarded | For Review | 2020-03-19 | Josh Dobken (Populous) | Chris Minter (Populous) | 2020-03-13 | Submittal Number: 05 12 00-162.0 From: JES PELKEY Final Due Date: 03/09/20 Subject: QUAD EF1 STEEL SD - SEQ. 722-723 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06820 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-23 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-22 |  | 05 12 00-162.0 Quad EF1 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-22 |  | 05 12 00-162.0 Quad EF1 Steel SD-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-02-22 |  | 05 12 00-162.0 Quad EF1 Steel SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-21 02:00 |  | 05 12 00-162.0 Quad EF1 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-23 |  | 05 12 00-162.0 Quad EF1 Steel SD-MAM_TT_POP.pdf
05 12 00-162-01 | 05 12 00 - STEEL | 05 12 00-162-01 Quad EF1 Steel SD - Seq. 722-723 - 3 sheets | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-09 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-23 | 2020-04-20 | 12 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05270 | Received | For Review | 2020-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-23 | Submittal Number: 05 12 00-162.1 From: JES PELKEY Final Due Date: 04/22/20 Subject: QUAD EF1 STEEL SD - SEQ. 722-723 - 3 SHEETS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07163 | Forwarded | For Review | 2020-04-09 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-16 | Submittal Number: 05 12 00-162.1 From: JES PELKEY Final Due Date: 04/22/20 Subject: QUAD EF1 STEEL SD - SEQ. 722-723 - 3 SHEETS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05384 | Review Response | Approved as Noted | 2020-04-16 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07408 | Responded and Closed | Approved as Noted | 2020-04-20 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-08 |  | 05 12 00-162.1 Quad EF1 Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-08 |  | 05 12 00-162.1 Quad EF1 Steel SD RR-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-04-16 |  | 05 12 00-162.1 Quad EF1 Steel SD RR-MAM_TT.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-20 |  | 05 12 00-162.1 Quad EF1 Steel SD RR-MAM_TT_POP.pdf
05 12 00-163-00 | 05 12 00 - STEEL | 05 12 00-163-00 Quad EF2 Steel SD - Seq. 724-727 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-23 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-14 | 2020-04-19 | 28 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-04-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04976 | Received | For Review | 2020-03-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-14 | Submittal Number: 05 12 00-163.0 From: JES PELKEY Final Due Date: 04/10/20 Subject: QUAD EF2 STEEL SD - SEQ. 724-727 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06785 | Forwarded | For Review | 2020-03-23 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-30 | Submittal Number: 05 12 00-163.0 From: JES PELKEY Final Due Date: 04/10/20 Subject: QUAD EF2 STEEL SD - SEQ. 724-727 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05391 | Review Response | Approved as Noted/Resubmit | 2020-04-13 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07357 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-19 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-20 |  | 05 12 00-163.0 Quad EF2 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-20 |  | 05 12 00-163.0 Quad EF2 Steel SD-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-03-20 |  | 05 12 00-163.0 Quad EF2 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-19 |  | 05 12 00-163.0 Quad EF2 Steel SD-MAM_TT_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-19 |  | A1-45-E - SLAB PLAN - UPPER CONCOURSE LEVEL - AREA E.pdf
05 12 00-163-01 | 05 12 00 - STEEL | 05 12 00-163-01 Quad EF2 Steel SD - Seq. 724-727 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-25 | 2020-06-22 | 12 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-06-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06332 | Received | For Review | 2020-06-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-06-25 | Submittal Number: 05 12 00-163.1 From: JES PELKEY Final Due Date: 06/24/20 Subject: QUAD EF2 STEEL SD - SEQ. 724-727 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08541 | Forwarded | For Review | 2020-06-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-18 | Submittal Number: 05 12 00-163.1 From: JES PELKEY Final Due Date: 06/24/20 Subject: QUAD EF2 STEEL SD - SEQ. 724-727 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06536 | Review Response | Approved | 2020-06-18 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | GC TO COORDINATE WITH RFI 2706 RESPONSES. SDK ¦ TT ¦ 6/18/2020 | Info Exchange
| 08794 | Responded and Closed | Approved as Noted | 2020-06-22 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-10 |  | 05 12 00-163.1 Quad EF2 Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-10 |  | 05 12 00-163.1 Quad EF2 Steel SD RR-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-06-10 |  | 05 12 00-163.1 Quad EF2 Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-22 |  | 05 12 00-163.1 Quad EF2 Steel SD RR-MAM_TT_POP.pdf
05 12 00-164-00 | 05 12 00 - STEEL | 05 12 00-164-00 Quad B2 B Steel SD - Seq. 617-619 & 621-622 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-26 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-16 | 2020-04-20 | 26 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05049 | Received | For Review | 2020-03-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-16 | Submittal Number: 05 12 00-164.0 From: JES PELKEY Final Due Date: 04/29/20 Subject: QUAD B2 B STEEL SD - SEQ. 617-619 & 621-622 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06871 | Forwarded | For Review | 2020-03-25 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-01 | Submittal Number: 05 12 00-164.0 From: JES PELKEY Final Due Date: 04/29/20 Subject: QUAD B2 B STEEL SD - SEQ. 617-619 & 621-622 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05418 | Review Response | Approved as Noted | 2020-04-13 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07363 | Responded and Closed | Approved as Noted | 2020-04-20 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-25 |  | 05 12 00-164.0 Quad B2B Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-25 |  | 05 12 00-164.0 Quad B2B Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-25 |  | 05 12 00-164.0 Quad B2B Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-20 |  | 05 12 00-164.0 Quad B2B Steel SD-MAM_TT _POP.pdf
05 12 00-165-00 | 05 12 00 - STEEL | 05 12 00-165-00 Atrium Steel SD - Seq. 424 and 428 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-20 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-03 | 2020-07-31 | 12 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07014 | Received | For Review | 2020-07-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-08-03 | Submittal Number: 05 12 00-165.0 From: JES PELKEY Final Due Date: 08/03/20 Subject: ATRIUM STEEL SD - SEQ. 424 AND 428 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09396 | Forwarded | For Review | 2020-07-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-27 | Submittal Number: 05 12 00-165.0 From: JES PELKEY Final Due Date: 08/03/20 Subject: ATRIUM STEEL SD - SEQ. 424 AND 428 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07278 | Review Response | Approved as Noted | 2020-07-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09698 | Responded and Closed | Approved as Noted | 2020-07-31 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-19 |  | 05 12 00-165.0 Atrium Steel SD Seq 424 & 428-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-19 |  | 05 12 00-165.0 Atrium Steel SD Seq 424 & 428-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-19 |  | 05 12 00-165.0 Atrium Steel SD Seq 424 & 428-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-31 |  | 05 12 00-165.0 Atrium Steel SD Seq 424 & 428-MAM_TT_POP.pdf
05 12 00-166-00 | 05 12 00 - STEEL | 05 12 00-166-00 Atrium Steel SD - Seq. 423 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-15 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-29 | 2020-07-31 | 17 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06983 | Received | For Review | 2020-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-07-29 | Submittal Number: 05 12 00-166.0 From: JES PELKEY Final Due Date: 07/29/20 Subject: ATRIUM STEEL SD - SEQ. 423 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09348 | Forwarded | For Review | 2020-07-15 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-22 | Submittal Number: 05 12 00-166.0 From: JES PELKEY Final Due Date: 07/29/20 Subject: ATRIUM STEEL SD - SEQ. 423 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07277 | Review Response | Approved as Noted | 2020-07-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09697 | Responded and Closed | Approved as Noted | 2020-07-31 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-15 |  | 05 12 00-166.0 Atrium Seq 423 Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-15 |  | 05 12 00-166.0 Atrium Seq 423 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-15 |  | 05 12 00-166.0 Atrium Seq 423 Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-31 |  | 05 12 00-166.0 Atrium Seq 423 Steel SD-MAM_TT_POP.pdf
05 12 00-167-00 | 05 12 00 - STEEL | 05 12 00-167-00 Upper Concourse Embeds - Y-Columns 17, 18, and 19 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-10 | 2019-12-19 | 2 | General | Record Copies; Transfers; Submittals |  | 2 |  | 2019-12-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03673 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-10 | Submittal Number: 05 12 00-167.0 From: JES PELKEY Final Due Date: 12/20/19 Subject: UPPER CONCOURSE EMBEDS - Y-COLUMNS 17, 18, AND 19 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05193 | Forwarded | For Review | 2019-12-18 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-25 | Submittal Number: 05 12 00-167.0 From: JES PELKEY Final Due Date: 12/20/19 Subject: UPPER CONCOURSE EMBEDS - Y-COLUMNS 17, 18, AND 19 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03708 | Review Response | Approved as Noted | 2019-12-19 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05238 | Responded and Closed | Approved as Noted | 2019-12-19 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 05 12 00-167.0 UC Embeds Y-Cols. 17, 18, and 19-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-18 |  | 05 12 00-167.0 UC Embeds Y-Cols. 17, 18, and 19-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-17 02:00 |  | 05 12 00-167.0 UC Embeds Y-Cols. 17, 18, and 19-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-19 02:00 |  | 05 12 00-167.0 UC Embeds Y-Cols. 17, 18, and 19-MAM_TT Reviewed_POP.pdf
05 12 00-168-00 | 05 12 00 - STEEL | 05 12 00-168-00 Upper Concourse Embeds Y-Columns 1, 16, and 20 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-10 | 2019-12-19 | 2 | General | Record Copies; Transfers; Submittals |  | 2 |  | 2019-12-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03689 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-10 | Submittal Number: 05 12 00-168.0 From: JES PELKEY Final Due Date: 01/01/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMNS 1, 16, AND 20 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05209 | Forwarded | For Review | 2019-12-18 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-25 | Submittal Number: 05 12 00-168.0 From: JES PELKEY Final Due Date: 01/01/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMNS 1, 16, AND 20 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03709 | Review Response | Approved as Noted | 2019-12-19 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05239 | Responded and Closed | Approved as Noted | 2019-12-19 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 05 12 00-168.0 UC Embeds Y-Cols. 1, 16, 20-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-18 |  | 05 12 00-168.0 UC Embeds Y-Cols. 1, 16, 20-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-17 02:00 |  | 05 12 00-168.0 UC Embeds Y-Cols. 1, 16, 20-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-19 02:00 |  | 05 12 00-168.0 UC Embeds Y-Cols. 1, 16, 20-MAM_TT Reviewed_POP.pdf
05 12 00-169-00 | 05 12 00 - STEEL | 05 12 00-169-00 Sequence 9905 Quad E Connection Materials | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-17 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2020-02-06 | 2020-02-06 | 21 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-02-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03948 | Received | For Review | 2020-01-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-02-06 | Submittal Number: 05 12 00-169.0 From: BRAD KIRSCHENHEITER Final Due Date: 01/30/20 Subject: SEQUENCE 9905 QUAD E CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05515 | Forwarded | For Review | 2020-01-16 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-23 | Submittal Number: 05 12 00-169.0 From: BRAD KIRSCHENHEITER Final Due Date: 01/30/20 Subject: SEQUENCE 9905 QUAD E CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04214 | Review Response | Approved as Noted/Resubmit | 2020-02-04 | Andy Tatkowski (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached. All unstamped sheets are approved as noted. ART ¦ TT ¦ 2/4/2020 | Info Exchange
| 05840 | Forwarded | For Review | 2020-02-05 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2020-02-06 | Submittal Number: 05 12 00-169.0 From: BRAD KIRSCHENHEITER Final Due Date: 01/30/20 Subject: SEQUENCE 9905 QUAD E CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05854 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-06 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-16 |  | 05 12 00-169.0 Quad E Connection Materials-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-16 |  | 05 12 00-169.0 Quad E Connection Materials-MAM.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-02-04 02:00 |  | 05 12 00-169.0 Quad E Connection Materials-MAM_TT.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-15 02:00 |  | 05 12 00-169.0 Quad E Connection Materials-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-06 |  | 05 12 00-169.0 Quad E Connection Materials-MAM_TT_POP.pdf
05 12 00-169-01 | 05 12 00 - STEEL | 05 12 00-169-01 Sequence 9905 Quad E Connection Materials RR | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-27 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-10 | 2020-04-02 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-04-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05085 | Received | For Review | 2020-03-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-10 | Submittal Number: 05 12 00-169.1 From: BRAD KIRSCHENHEITER Final Due Date: 04/10/20 Subject: SEQUENCE 9905 QUAD E CONNECTION MATERIALS RR Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06909 | Forwarded | For Review | 2020-03-27 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-03 | Submittal Number: 05 12 00-169.1 From: BRAD KIRSCHENHEITER Final Due Date: 04/10/20 Subject: SEQUENCE 9905 QUAD E CONNECTION MATERIALS RR Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05176 | Review Response | Approved | 2020-04-01 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07019 | Responded and Closed | Approved | 2020-04-01 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | SEE ATTACHED. | Info Exchange
| 07046 | Reopened | Additional Information | 2020-04-02 09:34 | Josh Dobken (Populous) |  |  | Reopened due to errors sending in Newforma
| 07047 | Responded and Closed | Approved | 2020-04-02 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Samar Kenkre (Thornton Tomasetti) Remarks: Responded and Closed (Approved) to: Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) Remarks: SEE ATTACHED. Reopened (Additional Information) by: Josh Dobken Remarks: Reopened due to errors sending in Newforma | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-27 |  | 05 12 00-169.1 Quad E Connection Material RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-27 |  | 05 12 00-169.1 Quad E Connection Material RR-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-03-27 |  | 05 12 00-169.1 Quad E Connection Material RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-01 |  | 05 12 00-169.1 Quad E Connection Material RR-MAM_TT_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-01 02:00 |  | 05 12 00-169.1 Quad E Connection Material RR-MAM_TT_POP.pdf
05 12 00-171-00 | 05 12 00 - STEEL | 05 12 00-171-00 Upper Concourse Embeds Y-Columns - 2 and 3 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-20 | 2020-01-14 | 9 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03787 | Received | For Review | 2020-01-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-20 | Submittal Number: 05 12 00-171.0 From: JES PELKEY Final Due Date: 01/20/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMNS - 2 AND 3 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05327 | Forwarded | For Review | 2020-01-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-13 | Submittal Number: 05 12 00-171.0 From: JES PELKEY Final Due Date: 01/20/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMNS - 2 AND 3 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 03913 | Review Response | Approved as Noted | 2020-01-10 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05472 | Responded and Closed | Approved as Noted | 2020-01-14 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-06 |  | 05 12 00-171.0 Upper Concourse Embeds Y-Columns 2 and 3-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-06 |  | 05 12 00-171.0 Upper Concourse Embeds Y-Columns 2 and 3-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-06 |  | 05 12 00-171.0 Upper Concourse Embeds Y-Columns 2 and 3-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-14 |  | 05 12 00-171.0 Upper Concourse Embeds Y-Columns 2 and 3-MAM_TT_POP.pdf
05 12 00-172-00 | 05 12 00 - STEEL | 05 12 00-172-00 Upper Concourse Embeds Y-Columns 11, 12, 13, 14, and 15 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-17 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-31 | 2020-01-27 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-01-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03951 | Received | For Review | 2020-01-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-31 | Submittal Number: 05 12 00-172.0 From: JES PELKEY Final Due Date: 01/30/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMNS 11, 12, 13, 14, AND 15 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05521 | Forwarded | For Review | 2020-01-16 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-23 | Submittal Number: 05 12 00-172.0 From: JES PELKEY Final Due Date: 01/30/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMNS 11, 12, 13, 14, AND 15 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04065 | Review Response | Approved as Noted | 2020-01-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05658 | Responded and Closed | Approved as Noted | 2020-01-27 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-16 |  | 05 12 00-172.0 UC Embeds Y-Cols 11, 12, 13, 14, and 15-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-16 |  | 05 12 00-172.0 UC Embeds Y-Cols 11, 12, 13, 14, and 15-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-15 02:00 |  | 05 12 00-172.0 UC Embeds Y-Cols 11, 12, 13, 14, and 15-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-27 02:00 |  | 05 12 00-172.0 UC Embeds Y-Cols 11, 12, 13, 14, and 15-MAM_TT Reviewed_POP.pdf
05 12 00-173-00 | 05 12 00 - STEEL | 05 12 00-173-00 Sequence 9907 Quad F Connection Materials | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-17 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-31 | 2020-02-05 | 20 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-02-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03950 | Received | For Review | 2020-01-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-01-31 | Submittal Number: 05 12 00-173.0 From: BRAD KIRSCHENHEITER Final Due Date: 01/30/20 Subject: SEQUENCE 9907 QUAD F CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05519 | Forwarded | For Review | 2020-01-16 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-23 | Submittal Number: 05 12 00-173.0 From: BRAD KIRSCHENHEITER Final Due Date: 01/30/20 Subject: SEQUENCE 9907 QUAD F CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04213 | Review Response | Approved as Noted/Resubmit | 2020-02-05 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05839 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Samar Kenkre (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-16 |  | 05 12 00-173.0 Quad F Connection Materials-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-16 |  | 05 12 00-173.0 Quad F Connection Materials-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-01-15 02:00 |  | 05 12 00-173.0 Quad F Connection Materials-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-05 02:00 |  | 05 12 00-173.0 Quad F Connection Materials-MAM_TT_POP.pdf
05 12 00-173-01 | 05 12 00 - STEEL | 05 12 00-173-01 Sequence 9907 Quad F Connection Materials | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-20 | Closed - Reviewed |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-05 |  | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04420 | Received | For Review | 2020-02-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-03-05 | Submittal Number: 05 12 00-173.1 From: BRAD KIRSCHENHEITER Final Due Date: 03/04/20 Subject: SEQUENCE 9907 QUAD F CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06104 | Forwarded | For Review | 2020-02-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-27 | Submittal Number: 05 12 00-173.1 From: BRAD KIRSCHENHEITER Final Due Date: 03/04/20 Subject: SEQUENCE 9907 QUAD F CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04548 | Review Response | Approved as Noted | 2020-02-26 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06258 | Responded and Closed | Approved as Noted | 2020-02-27 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review and comments. | Info Exchange
| 06259 | Reopened | Additional Information | 2020-02-27 13:54 | Todd Spangler (Populous)
| 06260 | Closed | Reviewed | 2020-02-27 | Todd Spangler (Populous)
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-19 |  | 05 12 00-173.1 Quad F Connection Materials-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-19 |  | 05 12 00-173.1 Quad F Connection Materials-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-02-19 |  | 05 12 00-173.1 Quad F Connection Materials-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-19 |  | 05 12 00-173.1 Quad F Connection Materials-MAM.pdf
05 12 00-181-00 | 05 12 00 - STEEL | 05 12 00-181-00 Sequence 61G-66G Cooling Tower | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-27 | 22 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04224 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Will Traylor (Mortenson Construction); Jes Pelkey (Mortenson Construction) | 2020-02-20 | Submittal Number: 05 12 00-181.0 From: BRAD KIRSCHENHEITER Final Due Date: 02/17/20 Subject: SEQUENCE 61G-66G COOLING TOWER Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05852 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 05 12 00-181.0 From: BRAD KIRSCHENHEITER Final Due Date: 02/17/20 Subject: SEQUENCE 61G-66G COOLING TOWER Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04494 | Review Response | Approved as Noted/Resubmit | 2020-02-20 | Andy Tatkowski (Thornton Tomasetti) | Shaina Burris (Populous) |  | Individual sheets have been marked Revise and Resubmit. ART ¦ TT ¦ 2/20/2020 | Info Exchange
| 06255 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-27 | Todd Spangler (Populous) | Will Traylor (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | Sequence 61G-66G Cooling Tower SD's - MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | Sequence 61G-66G Cooling Tower SD's - MAM Review.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-02-20 |  | Sequence 61G-66G Cooling Tower SD's - MAM Review_TT.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-27 |  | X1-2 - GRID GEOMETRY PLAN - SOUTH.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-27 |  | 05 12 00-181-00 - Sequence 61G-66G Cooling Tower SD's - MAM_TT_POP.pdf
05 12 00-181-01 | 05 12 00 - STEEL | 05 12 00-181-01 Sequence 61G-66G & 69G Cooling Tower | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-06 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-20 | 2020-05-19 | 14 |  | Record Copies; Transfers; Submittals | 05 12 00-181-01-01 - 05 12 00-181-01 Sequence 61G-66G & 69G Cooling Tower | 13 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05738 | Received | For Review | 2020-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-05-20 | Submittal Number: 05 12 00-181.1 From: BRAD KIRSCHENHEITER Final Due Date: 05/20/20 Subject: SEQUENCE 61G-66G & 69G COOLING TOWER Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07784 | Forwarded | For Review | 2020-05-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-13 | Submittal Number: 05 12 00-181.1 From: BRAD KIRSCHENHEITER Final Due Date: 05/20/20 Subject: SEQUENCE 61G-66G & 69G COOLING TOWER Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05925 | Review Response | Approved as Noted | 2020-05-18 | Andy Tatkowski (Thornton Tomasetti) | Shaina Burris (Populous) |  | Note, some sheets have been marked revise and resubmit. See attached. ART ¦ TT ¦ 5/18/2020 | Info Exchange
| 08038 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-19 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | Note, some sheets have been marked revise and resubmit. See attached. ART ¦ TT ¦ 5/18/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | 05 12 00-181.1 Cooling Tower SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-05 |  | 05 12 00-181.1 Cooling Tower SD RR-MAM.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-05-18 |  | Seq 61G-66G & 69G R&R Approval Package WMT clouded_TT.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-19 |  | 05 12 00-181.1 Cooling Tower SD RR-MAM_TT_POP.pdf
05 12 00-181-01-01 | 05 12 00 - STEEL | 05 12 00-181-01 Sequence 61G-66G & 69G Cooling Tower | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 12 00-181-01 - 05 12 00-181-01 Sequence 61G-66G & 69G Cooling Tower | -1 | 2020-06-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 |  | 05 12 00-181.1 Cooling Tower SD RR-MAM_TT_POP.pdf
05 12 00-182-00 | 05 12 00 - STEEL | 05 12 00-182-00 Upper Concourse Embeds Y-Column 4 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-25 | 20 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04235 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-20 | Submittal Number: 05 12 00-182.0 From: JES PELKEY Final Due Date: 02/17/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMN 4 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05864 | Forwarded | For Review | 2020-02-06 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 05 12 00-182.0 From: JES PELKEY Final Due Date: 02/17/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMN 4 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04489 | Review Response | Approved as Noted | 2020-02-18 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06183 | Responded and Closed | Approved as Noted | 2020-02-25 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 05 12 00-182.0 UC Embeds Y-Col 4-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-06 |  | 05 12 00-182.0 UC Embeds Y-Col 4-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-06 |  | 05 12 00-182.0 UC Embeds Y-Col 4-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-25 |  | 05 12 00-182.0 UC Embeds Y-Col 4-MAM_TT_POP.pdf
05 12 00-184-00 | 05 12 00 - STEEL | 05 12 00-184-00 Steel Galvanizing Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-30 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-14 | 2020-04-13 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05098 | Received | For Review | 2020-03-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-14 | Submittal Number: 05 12 00-184.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/10/20 Subject: STEEL GALVANIZING DATA Description: HOT DIP GALVANIZING DATA AND FIELD APPLIED GALV TOUCH-UP PAINT OVER FIELD WELDS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06926 | Forwarded | For Review | 2020-03-30 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-06 | Submittal Number: 05 12 00-184.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/10/20 Subject: STEEL GALVANIZING DATA Description: HOT DIP GALVANIZING DATA AND FIELD APPLIED GALV TOUCH-UP PAINT OVER FIELD WELDS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05326 | Review Response | Approved as Noted | 2020-04-10 | Sean McNeill (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 07244 | Responded and Closed | Approved as Noted | 2020-04-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-27 |  | 05 12 00-184.0 Steel Galvanizing Data-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-27 |  | 05 12 00-184.0 Steel Galvanizing Data-MAM.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-03-27 |  | 05 12 00-184.0 Steel Galvanizing Data-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-13 |  | 05 12 00-184.0 Steel Galvanizing Data-MAM_TT_POP.pdf
05 12 00-185-00 | 05 12 00 - STEEL | 05 12 00-185-00 Cooling Tower Steel SD - Sequence 67G & 68G | Closed | Structural, Architectural, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-14 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Bryan Klote (Populous), Mark Lievens (ME Engineers) |  |  |  | 2020-05-29 07:00 | 2020-06-03 | 21 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05864 | Received | For Review | 2020-05-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-05-29 07:00 | Submittal Number: 05 12 00-185.0 From: JES PELKEY Final Due Date: 05/28/20 Subject: COOLING TOWER STEEL SD - SEQUENCE 67G & 68G Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07957 | Forwarded | For Review | 2020-05-14 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-21 | Submittal Number: 05 12 00-185.0 From: JES PELKEY Final Due Date: 05/28/20 Subject: COOLING TOWER STEEL SD - SEQUENCE 67G & 68G Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06098 | Review Response | Approved as Noted | 2020-05-27 | Andy Tatkowski (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached. ART ¦ TT ¦ 5/27/2020 | Info Exchange
| 08255 | Forwarded | For Review | 2020-05-28 | Todd Spangler (Populous) | Bryan Klote (Populous); Mark Lievens (ME Engineers) | 2020-05-29 | Guys, I did not know they included the dunnage platforms and openings in this submittal. Bryan and or Mark can you please review the platforms and railing openings required and the location of the cooling tower supports? Please and thanks. Sorry for the late notice but this is a hot submittal. | Info Exchange
| 08353 | Responded and Closed | Approved as Noted | 2020-06-03 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-14 |  | 05 12 00-185.0 Cooling Tower Steel SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-14 |  | 05 12 00-185.0 Cooling Tower Steel SD-MAM.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-05-27 |  | 05 12 00-185.0 Cooling Tower Steel SD-MAM_TT.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-05-14 |  | 05 12 00-185.0 Cooling Tower Steel SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-03 |  | 05 12 00-185.0 Cooling Tower Steel SD-MAM_TT_POP.pdf
05 12 00-186-00 | 05 12 00 - STEEL | 05 12 00-186-00 Upper Concourse Embeds Y-Columns - 7, 8, 9, and 10 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-02-25 | 2020-02-25 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04318 | Received | For Review | 2020-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company) | 2020-02-25 | Submittal Number: 05 12 00-186.0 From: JES PELKEY Final Due Date: 02/25/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMNS - 7, 8, 9, AND 10 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05968 | Forwarded | For Review | 2020-02-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-18 | Submittal Number: 05 12 00-186.0 From: JES PELKEY Final Due Date: 02/25/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMNS - 7, 8, 9, AND 10 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04491 | Review Response | Approved as Noted | 2020-02-19 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06185 | Responded and Closed | Approved as Noted | 2020-02-25 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-11 |  | 05 12 00-186.0 UC Embeds Y-Col 7, 8, 9, and 10-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-11 |  | 05 12 00-186.0 UC Embeds Y-Col 7, 8, 9, and 10-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-11 |  | 05 12 00-186.0 UC Embeds Y-Col 7, 8, 9, and 10-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-25 |  | 05 12 00-186.0 UC Embeds Y-Col 7, 8, 9, and 10-MAM_TT_POP.pdf
05 12 00-186-01 | 05 12 00 - STEEL | 05 12 00-186-01 Upper Concourse Embeds Y-Columns - 7, 8, 9, and 10 - FOR RECORD | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-06 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-20 | 2020-03-09 | 4 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04677 | Received | For Review | 2020-03-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-20 | Submittal Number: 05 12 00-186.1 From: JES PELKEY Final Due Date: 03/10/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMNS - 7, 8, 9, AND 10 - FOR RECORD Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06435 | Forwarded | For Review | 2020-03-05 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-12 | Submittal Number: 05 12 00-186.1 From: JES PELKEY Final Due Date: 03/10/20 Subject: UPPER CONCOURSE EMBEDS Y-COLUMNS - 7, 8, 9, AND 10 - FOR RECORD Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04694 | Review Response | No Action Taken or Required | 2020-03-05 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Received for Record. | Info Exchange
| 06455 | Responded and Closed | No Action Taken or Required | 2020-03-09 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Received for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-05 |  | 05 12 00-186.1 UC Embeds Y-Cols 7, 8, 9, and 10-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-05 |  | 05 12 00-186.1 UC Embeds Y-Cols 7, 8, 9, and 10-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-05 |  | 05 12 00-186.1 UC Embeds Y-Cols 7, 8, 9, and 10-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-09 |  | 05 12 00-186.1 UC Embeds Y-Cols 7, 8, 9, and 10-MAM_POP.pdf
05 12 00-187-00 | 05 12 00 - STEEL | 05 12 00-187-00 Tuned Mass Dampers | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-17 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-02 | 2020-02-27 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04356 | Received | For Review | 2020-02-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-02 | Submittal Number: 05 12 00-187.0 From: BRAD KIRSCHENHEITER Final Due Date: 02/28/20 Subject: TUNED MASS DAMPERS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06029 | Forwarded | For Review | 2020-02-17 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-24 | Submittal Number: 05 12 00-187.0 From: BRAD KIRSCHENHEITER Final Due Date: 02/28/20 Subject: TUNED MASS DAMPERS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04546 | Review Response | Approved as Noted | 2020-02-27 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06256 | Responded and Closed | Approved as Noted | 2020-02-27 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-14 |  | 05 12 00-187.0 Tuned Mass Dampers SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-14 |  | 05 12 00-187.0 Tuned Mass Dampers SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-14 |  | 05 12 00-187.0 Tuned Mass Dampers SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-27 |  | 05 12 00-187.0 Tuned Mass Dampers SD-MAM_TT_POP.pdf
05 12 00-187-01 | 05 12 00 - STEEL | 05 12 00-187-01 Tuned Mass Damper Field Use - FOR RECORD | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-28 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-11 | 2020-08-28 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07798 | Received | For Review | 2020-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company) | 2020-09-11 | Submittal Number: 05 12 00-187.1 From: BRAD KIRSCHENHEITER Final Due Date: 09/10/20 Subject: TUNED MASS DAMPER FIELD USE - FOR RECORD Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 10376 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-03 | Submittal Number: 05 12 00-187.1 From: BRAD KIRSCHENHEITER Final Due Date: 09/10/20 Subject: TUNED MASS DAMPER FIELD USE - FOR RECORD Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07819 | Review Response | Approved | 2020-08-28 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Retained for Record. | Info Exchange
| 10396 | Responded and Closed | Approved | 2020-08-28 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | Retained for Record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 05 12 00-187.1 Tuned Mass Damper Field Use Drawing-MAm.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-27 |  | 05 12 00-187.1 Tuned Mass Damper Field Use Drawing-MAm.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-27 |  | 05 12 00-187.1 Tuned Mass Damper Field Use Drawing-MAm.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-27 |  | 05 12 00-187.1 Tuned Mass Damper Field Use Drawing-MAm.pdf
05 12 00-189-00 | 05 12 00 - STEEL | 05 12 00-189-00 Sequence 137 & 526 Approval Package (RFI 1824) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-20 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-05 | 2020-02-27 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04414 | Received | For Review | 2020-02-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-05 | Submittal Number: 05 12 00-189.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/18/20 Subject: SEQUENCE 137 & 526 APPROVAL PACKAGE (RFI 1824) Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06100 | Forwarded | For Review | 2020-02-19 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-26 | Submittal Number: 05 12 00-189.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/18/20 Subject: SEQUENCE 137 & 526 APPROVAL PACKAGE (RFI 1824) Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04554 | Review Response | Approved as Noted | 2020-02-27 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06271 | Responded and Closed | Approved as Noted | 2020-02-27 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-19 |  | 05 12 00-189.0 Sequence 137 & 526 Steel SD (RFI 1824)-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-19 |  | 05 12 00-189.0 Sequence 137 & 526 Steel SD (RFI 1824)-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-19 |  | 05 12 00-189.0 Sequence 137 & 526 Steel SD (RFI 1824)-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-27 |  | 05 12 00-189.0 Sequence 137 & 526 Steel SD (RFI 1824)-MAM_TT_POP.pdf
05 12 00-190-00 | 05 12 00 - STEEL | 05 12 00-190-00 RFI#2164 Vehicle Barrier Added Embeds | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-20 | 2020-03-23 | 18 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04682 | Received | For Review | 2020-03-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-20 | Submittal Number: 05 12 00-190.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/19/20 Subject: RFI#2164 VEHICLE BARRIER ADDED EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06441 | Forwarded | For Review | 2020-03-06 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-13 | Submittal Number: 05 12 00-190.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/19/20 Subject: RFI#2164 VEHICLE BARRIER ADDED EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04974 | Review Response | Approved | 2020-03-18 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06782 | Responded and Closed | Approved as Noted | 2020-03-23 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-06 |  | 05 12 00-190.0 RFI#2164 Vehicle Barrier Added Embeds-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-06 |  | 05 12 00-190.0 RFI#2164 Vehicle Barrier Added Embeds-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-03-06 |  | 05 12 00-190.0 RFI#2164 Vehicle Barrier Added Embeds-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-23 |  | 05 12 00-190.0 RFI#2164 Vehicle Barrier Added Embeds-MAM_TT_POP.pdf
05 12 00-191-00 | 05 12 00 - STEEL | 05 12 00-191-00 Quad D Stud Layout Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-30 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-14 | 2020-04-14 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-04-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05099 | Received | For Review | 2020-03-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-14 | Submittal Number: 05 12 00-191.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/13/20 Subject: QUAD D STUD LAYOUT DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06927 | Forwarded | For Review | 2020-03-30 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-06 | Submittal Number: 05 12 00-191.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/13/20 Subject: QUAD D STUD LAYOUT DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05342 | Review Response | Approved as Noted | 2020-04-14 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Populous to review/comment on EOS location, page 5 of submittal attachment. TT-FK ¦ 2020-04-14 | Info Exchange
| 07267 | Responded and Closed | Approved as Noted | 2020-04-14 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-29 |  | 05 12 00-191.0 Quad D Stud Layout Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-29 |  | 05 12 00-191.0 Quad D Stud Layout Drawings-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-03-29 |  | 05 12 00-191.0 Quad D Stud Layout Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-14 |  | 05 12 00-191.0 Quad D Stud Layout Drawings-MAM_TT_POP.pdf
05 12 00-192-00 | 05 12 00 - STEEL | 05 12 00-192-00 DCCI Quality Submittals | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-02 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-16 | 2020-03-17 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04574 | Received | For Review | 2020-03-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company); Greg Goebel (M.A. Mortenson Company) | 2020-03-16 | Submittal Number: 05 12 00-192.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/16/20 Subject: DCCI QUALITY SUBMITTALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06307 | Forwarded | For Review | 2020-03-02 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-09 | Submittal Number: 05 12 00-192.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/16/20 Subject: DCCI QUALITY SUBMITTALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04870 | Review Response | Not Required For Review | 2020-03-16 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Received for Record | Info Exchange
| 06655 | Responded and Closed | Not Required For Review | 2020-03-17 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Received for Record. Missing MAM cover page and review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 1540.02 SS-High Strength Bolting Plan TC Rev 0.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 1540.02 QMP - Superstructure.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 1540.02 QMP - Superstructure.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 1540.02 SS-High Strength Bolting Plan TC Rev 0.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-03-02 |  | 1540.02 QMP - Superstructure.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-03-02 |  | 1540.02 SS-High Strength Bolting Plan TC Rev 0.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-17 |  | 1540.02 SS-High Strength Bolting Plan TC Rev 0_TT_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-17 |  | 1540.02 QMP - Superstructure_TT_POP.pdf
05 12 00-193-00 | 05 12 00 - STEEL | 05 12 00-193-00 RFI 1880.1 Revisions | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-20 | 2020-03-13 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-03-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04681 | Received | For Review | 2020-03-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-20 | Submittal Number: 05 12 00-193.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/19/20 Subject: RFI 1880.1 REVISIONS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06439 | Forwarded | For Review | 2020-03-05 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-12 | Submittal Number: 05 12 00-193.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/19/20 Subject: RFI 1880.1 REVISIONS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04828 | Review Response | Approved as Noted | 2020-03-13 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06605 | Responded and Closed | Approved as Noted | 2020-03-13 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-05 |  | 05 12 00-193.0 RFI#1880.1 Steel Revs-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-05 |  | 05 12 00-193.0 RFI#1880.1 Steel Revs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-04 02:00 |  | 05 12 00-193.0 RFI#1880.1 Steel Revs-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-13 02:00 |  | 05 12 00-193.0 RFI#1880.1 Steel Revs-MAM_TT REVIEW_POP.pdf
05 12 00-194-00 | 05 12 00 - STEEL | 05 12 00-194-00 DCCI Erector Welding Procedures | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-17 | 2020-03-10 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04617 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Greg Goebel (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 05 12 00-194.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/10/20 Subject: DCCI ERECTOR WELDING PROCEDURES Description: DCCI AND SUB-TIER TRADES WELDING PROCEDURES SPECIFICATIONS SUBMITTED FOR RECORD WITH OWNER'S TESTING AGENCY APPROVAL. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06356 | Forwarded | For Review | 2020-03-03 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-10 | Submittal Number: 05 12 00-194.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/10/20 Subject: DCCI ERECTOR WELDING PROCEDURES Description: DCCI AND SUB-TIER TRADES WELDING PROCEDURES SPECIFICATIONS SUBMITTED FOR RECORD WITH OWNER'S TESTING AGENCY APPROVAL. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04746 | Review Response | Approved | 2020-03-10 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | No exceptions. Copy retained for record. | Info Exchange
| 06518 | Responded and Closed | Approved | 2020-03-10 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-03 |  | DCCI Combined Welding Procedures - Submitted 03.03.2020.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-03 |  | DCCI Combined Welding Procedures - Submitted 03.03.2020.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-10 |  | DCCI Combined Welding Procedures - Submitted 03.03.2020_TT_POP.pdf
05 12 00-197-00 | 05 12 00 - STEEL | 05 12 00-197-00 Sequence 9911 & 9912 Quad B Connection Materials | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-20 | 2020-03-23 | 18 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04683 | Received | For Review | 2020-03-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-20 | Submittal Number: 05 12 00-197.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/19/20 Subject: SEQUENCE 9911 & 9912 QUAD B CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06442 | Forwarded | For Review | 2020-03-06 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-13 | Submittal Number: 05 12 00-197.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/19/20 Subject: SEQUENCE 9911 & 9912 QUAD B CONNECTION MATERIALS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04985 | Review Response | Approved as Noted | 2020-03-19 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Some areas may be affected by contractor proposed west temp ramp changes. | Info Exchange
| 06795 | Responded and Closed | Approved as Noted | 2020-03-23 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-05 |  | 05 12 00-197.0 Quad B Connection Materials-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-05 |  | 05 12 00-197.0 Quad B Connection Materials-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-05 |  | 05 12 00-197.0 Quad B Connection Materials-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-23 |  | 05 12 00-197.0 Quad B Connection Materials-MAM_TT_POP.pdf
05 12 00-197-01 | 05 12 00 - STEEL | 05 12 00-197-01 Sequence 9911 & 9912 Quad B Connection Materials - West Temp Ramp Changes | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-25 | 2020-06-17 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-06-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06333 | Received | For Review | 2020-06-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-06-25 | Submittal Number: 05 12 00-197.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/24/20 Subject: SEQUENCE 9911 & 9912 QUAD B CONNECTION MATERIALS - WEST TEMP RAMP CHANGES Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08542 | Forwarded | For Review | 2020-06-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-18 | Submittal Number: 05 12 00-197.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/24/20 Subject: SEQUENCE 9911 & 9912 QUAD B CONNECTION MATERIALS - WEST TEMP RAMP CHANGES Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06454 | Review Response | Approved as Noted | 2020-06-16 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08704 | Responded and Closed | Approved as Noted | 2020-06-17 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-10 |  | 05 12 00-197.1 Quad B Connection Material-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-10 |  | 05 12 00-197.1 Quad B Connection Material-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-10 |  | 05 12 00-197.1 Quad B Connection Material-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-17 |  | 05 12 00-197.1 Quad B Connection Material-MAM_TT_POP.pdf
05 12 00-199-00 | 05 12 00 - STEEL | 05 12 00-199-00 LeJeune & TrueNorth Steel Quality Control Program | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-02 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-16 | 2020-03-17 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04573 | Received | For Review | 2020-03-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-16 | Submittal Number: 05 12 00-199.0 From: GREG GOEBEL Final Due Date: 03/16/20 Subject: LEJEUNE & TRUENORTH STEEL QUALITY CONTROL PROGRAM Description: QUALITY CONTROL PROGRAMS SUBMITTED FOR RECORD FROM LEJEUNE, WISSCO, AND TRUE NORTH STEEL SUPPLIERS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06306 | Forwarded | For Review | 2020-03-02 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-09 | Submittal Number: 05 12 00-199.0 From: GREG GOEBEL Final Due Date: 03/16/20 Subject: LEJEUNE & TRUENORTH STEEL QUALITY CONTROL PROGRAM Description: QUALITY CONTROL PROGRAMS SUBMITTED FOR RECORD FROM LEJEUNE, WISSCO, AND TRUE NORTH STEEL SUPPLIERS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04871 | Review Response | Not Required For Review | 2020-03-16 | Sean McNeill (Thornton Tomasetti) | Populous SCA_CCA |  | Received for record | Info Exchange
| 06656 | Responded and Closed | Not Required For Review | 2020-03-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Received for record | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | LeJeune Shop Quality Manual.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | TrueNorth Steel Quality Management System 11-01-19.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-02 |  | LeJeune Shop Quality Manual.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-02 |  | TrueNorth Steel Quality Management System 11-01-19.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-03-02 |  | LeJeune Shop Quality Manual.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-03-02 |  | TrueNorth Steel Quality Management System 11-01-19.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-17 |  | TrueNorth Steel Quality Management System 11-01-19_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-17 |  | LeJeune Shop Quality Manual_TT_POP.pdf
05 12 00-200-00 | 05 12 00 - STEEL | 05 12 00-200-00 LeJeune & True North Shop Welding Procedures | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-17 | 2020-03-10 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04594 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-17 | Submittal Number: 05 12 00-200.0 From: GREG GOEBEL Final Due Date: 03/16/20 Subject: LEJEUNE & TRUE NORTH SHOP WELDING PROCEDURES Description: LEJEUNE AND TRUE NORTH WELDING PROCEDURES SUBMITTED FOR RECORD. MAYES, OWNERS TESTING AGENCY, COMMENTS ATTACHED AT BEGINNING OF SUBMITTAL WITH THEIR REQUESTS INCLUDED IN SUBMITTAL. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06332 | Forwarded | For Review | 2020-03-03 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-10 | Submittal Number: 05 12 00-200.0 From: GREG GOEBEL Final Due Date: 03/16/20 Subject: LEJEUNE & TRUE NORTH SHOP WELDING PROCEDURES Description: LEJEUNE AND TRUE NORTH WELDING PROCEDURES SUBMITTED FOR RECORD. MAYES, OWNERS TESTING AGENCY, COMMENTS ATTACHED AT BEGINNING OF SUBMITTAL WITH THEIR REQUESTS INCLUDED IN SUBMITTAL. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04748 | Review Response | Approved as Noted | 2020-03-10 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Exceptions noted. Copy retained for record. | Info Exchange
| 06520 | Responded and Closed | Approved as Noted | 2020-03-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Greg Goebel (M.A. Mortenson Company) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-03 |  | LeJeune and True North WPS Submittal - SCA_R1 2.24.20.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-03 |  | LeJeune and True North WPS Submittal - SCA_R1 2.24.20.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-03 |  | LeJeune and True North WPS Submittal - SCA_R1 2.24.20.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-10 |  | LeJeune and True North WPS Submittal - SCA_R1 2.24.20_TT_POP.pdf
05 12 00-200-01 | 05 12 00 - STEEL | 05 12 00-200-01 LeJeune & True North Shop Welding Procedures | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-26 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-09 | 2020-03-26 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05053 | Received | For Review | 2020-03-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2020-04-09 | Received from: AI Assistant Mortenson Procore Connector (Mortenson Construction) Description: Submittal Number: 05 12 00-200.1 From: GREG GOEBEL Final Due Date: 04/9/2020 Subject: LEJEUNE & TRUE NORTH SHOP WELDING PROCEDURES Description: LEJEUNE AND TRUE NORTH WELDING PROCEDURES SUBMITTED FOR RECORD. MAYES, OWNERS TESTING AGENCY, COMMENTS ATTACHED AT BEGINNING OF SUBMITTAL WITH THEIR REQUESTS INCLUDED IN SUBMITTAL. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06875 | Forwarded | For Review | 2020-03-25 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-01 | Received from: AI Assistant Mortenson Procore Connector (Mortenson Construction) Description: Submittal Number: 05 12 00-200.1 From: GREG GOEBEL Final Due Date: 04/9/2020 Subject: LEJEUNE & TRUE NORTH SHOP WELDING PROCEDURES Description: LEJEUNE AND TRUE NORTH WELDING PROCEDURES SUBMITTED FOR RECORD. MAYES, OWNERS TESTING AGENCY, COMMENTS ATTACHED AT BEGINNING OF SUBMITTAL WITH THEIR REQUESTS INCLUDED IN SUBMITTAL. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06890 | Forwarded | For Review | 2020-03-26 | Shaina Burris (Populous) | Matt Ross (Thornton Tomasetti) | 2020-04-02 | Received from: AI Assistant Mortenson Procore Connector (Mortenson Construction) Description: Submittal Number: 05 12 00-200.1 From: GREG GOEBEL Final Due Date: 04/9/2020 Subject: LEJEUNE & TRUE NORTH SHOP WELDING PROCEDURES Description: LEJEUNE AND TRUE NORTH WELDING PROCEDURES SUBMITTED FOR RECORD. MAYES, OWNERS TESTING AGENCY, COMMENTS ATTACHED AT BEGINNING OF SUBMITTAL WITH THEIR REQUESTS INCLUDED IN SUBMITTAL. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05067 | Review Response | Approved | 2020-03-26 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | No exceptions. Copy retained for record. | Info Exchange
| 06891 | Responded and Closed | Approved | 2020-03-26 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | No exceptions. Copy retained for record. | Info Exchange
| 07217 | Sent | For Information Only | 2020-04-13 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Greg Goebel (M.A. Mortenson Company) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: No exceptions. Copy retained for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-25 |  | LeJeune and True North WPS Submittal - SCA_R1 Submitted 3.19.29.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-25 |  | LeJeune and True North WPS Submittal - SCA_R1 Submitted 3.19.29.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-24 02:00 |  | LeJeune and True North WPS Submittal - SCA_R1 Submitted 3.19.29.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-24 |  | LeJeune and True North WPS Submittal - SCA_R1 Submitted 3.19.29.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-03-26 |  | 05 12 00-200-01 - LeJeune and True North WPS Submittal_TT_POP.pdf
| Sent |  | Shaina Burris (Populous) | 1 | 2020-03-24 02:00 |  | LeJeune and True North WPS Submittal - SCA_R1 Submitted 3.19.29.pdf
05 12 00-202-00 | 05 12 00 - STEEL | 05 12 00-202-00 Elevator A6 Hold Down Embeds | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-05 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-19 | 2020-03-09 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04665 | Received | For Review | 2020-03-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-19 | Submittal Number: 05 12 00-202.0 From: NATE WEINGART Final Due Date: 03/19/20 Subject: ELEVATOR A6 HOLD DOWN EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06420 | Forwarded | For Review | 2020-03-05 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-12 | Submittal Number: 05 12 00-202.0 From: NATE WEINGART Final Due Date: 03/19/20 Subject: ELEVATOR A6 HOLD DOWN EMBEDS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 04695 | Review Response | Approved | 2020-03-05 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06456 | Responded and Closed | Approved as Noted | 2020-03-09 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-05 |  | 051200-202.0 Elevator A6 Machine Hold Down Embeds (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-05 |  | 051200-202.0 Elevator A6 Machine Hold Down Embeds (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-05 |  | 051200-202.0 Elevator A6 Machine Hold Down Embeds (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-09 |  | 051200-202.0 Elevator A6 Machine Hold Down Embeds MAM_TT_POP.pdf
05 12 00-204-00 | 05 12 00 - STEEL | 05 12 00-204-00 Catwalk Handrail Splice Locks | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-30 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-14 | 2020-04-13 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05093 | Received | For Review | 2020-03-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-14 | Submittal Number: 05 12 00-204.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/10/20 Subject: CATWALK HANDRAIL SPLICE LOCKS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06921 | Forwarded | For Review | 2020-03-27 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-03 | Submittal Number: 05 12 00-204.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/10/20 Subject: CATWALK HANDRAIL SPLICE LOCKS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05328 | Review Response | Approved | 2020-04-09 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions | Info Exchange
| 07246 | Responded and Closed | Approved as Noted | 2020-04-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-27 |  | 05 12 00-204.0 Catwalk Handrail Splice Locks PD & SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-27 |  | 05 12 00-204.0 Catwalk Handrail Splice Locks PD & SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-27 |  | 05 12 00-204.0 Catwalk Handrail Splice Locks PD & SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-13 |  | 05 12 00-204.0 Catwalk Handrail Splice Locks PD & SD-MAM_TT_POP.pdf
05 12 00-205-00 | 05 12 00 - STEEL | 05 12 00-205-00 Quad C - Elevator C1-C2 Revised Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-18 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-01 | 2020-03-26 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04901 | Received | For Review | 2020-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-01 | Submittal Number: 05 12 00-205.0 From: STEPHEN PRINCE Final Due Date: 03/31/20 Subject: QUAD C - ELEVATOR C1-C2 REVISED PACKAGE Description: R&R/OFA PACKAGE HAS BEEN POSTED ON PROCORE FOR ALL STEEL AFFECTED BY RE-FRAMING CHANGES AT ELEVATOR C1,C2 (QUAD C). PLEASE NOTE THE FOLLOWING… INCORPORATES RECEIVED COORDINATION INFORMATION FOR QUAD C ELEVATORS (ELEVATORS C1 AND C2) INCORPORATES RFI 1734 (NOC 120) INCORPORATES RFI 1709 (NOC 107) INCORPORATES RFI 2156 (NOC 296) INCORPORATES BFA COMMENTS FROM 05 12 00-28.1 SPS SHOP DRAWINGS-MAM_TT_POP_02-28-2020 UPDATED E-PLANS: E267, E268, E274, E275, E288, E290, E291, E292, E317, E318, E319, E320, E325, E326, E327, E340, E341 & E342 NEW SECTION DETAIL’S: E327.1 UPDATED SHOP DRAWINGS: 4695C, 4696C, 4697C, 4698C, 4741G, 4743G, 4747G, 4750G, 4754G, 4756G, 4757G, 4846B, 4847B, 4849B, 4850B, 4853B, 4854B, 4989BP, 4990BP, 4991BP, 4992BP, 4993BP, 4995BP, 5008BP, 5009BP, 5010BP, 5011BP, 5012BP, 5013BP, 5014BP, 5018BP, 5019BP, 5022BP, 5048VB, 5054A, 5055A, 5311C, 5312C, 5314C, 5326C, 5327C, 5335C, 5336C, 5339C, 5340C, 5378G, 5379G,, 5380G, 5388G, 5391G, 5392G, 5449G, 5451G, 5527G, 5529B, 5530B, 5532B, 5534B, 5535B, 5536B, 5588B, 5594B, 5717BP, 5718BP, 5719BP, 5720BP, 5721BP, 5722BP, 5728BP, 5729BP, 5730BP, 5731BP, 5733BP, 5734BP & 5737BP NEW SHOP DRAWINGS: 5153BP, 5153BP, 5154BP, 5155BP, 5845A, 5846BP, 5847BP, 5848BP, 5849BP, 5850BP, 5851BP, 5858VB, 5859B & 5860A VOID SHOP DRAWINGS: 4699C, 4700C, 4702C, 4701C, 5100C, 5307C, 5308C, 5309C, 5329C, 5701VB Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06694 | Forwarded | For Review | 2020-03-18 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-25 | Submittal Number: 05 12 00-205.0 From: STEPHEN PRINCE Final Due Date: 03/31/20 Subject: QUAD C - ELEVATOR C1-C2 REVISED PACKAGE Description: R&R/OFA PACKAGE HAS BEEN POSTED ON PROCORE FOR ALL STEEL AFFECTED BY RE-FRAMING CHANGES AT ELEVATOR C1,C2 (QUAD C). PLEASE NOTE THE FOLLOWING… INCORPORATES RECEIVED COORDINATION INFORMATION FOR QUAD C ELEVATORS (ELEVATORS C1 AND C2) INCORPORATES RFI 1734 (NOC 120) INCORPORATES RFI 1709 (NOC 107) INCORPORATES RFI 2156 (NOC 296) INCORPORATES BFA COMMENTS FROM 05 12 00-28.1 SPS SHOP DRAWINGS-MAM_TT_POP_02-28-2020 UPDATED E-PLANS: E267, E268, E274, E275, E288, E290, E291, E292, E317, E318, E319, E320, E325, E326, E327, E340, E341 & E342 NEW SECTION DETAIL’S: E327.1 UPDATED SHOP DRAWINGS: 4695C, 4696C, 4697C, 4698C, 4741G, 4743G, 4747G, 4750G, 4754G, 4756G, 4757G, 4846B, 4847B, 4849B, 4850B, 4853B, 4854B, 4989BP, 4990BP, 4991BP, 4992BP, 4993BP, 4995BP, 5008BP, 5009BP, 5010BP, 5011BP, 5012BP, 5013BP, 5014BP, 5018BP, 5019BP, 5022BP, 5048VB, 5054A, 5055A, 5311C, 5312C, 5314C, 5326C, 5327C, 5335C, 5336C, 5339C, 5340C, 5378G, 5379G,, 5380G, 5388G, 5391G, 5392G, 5449G, 5451G, 5527G, 5529B, 5530B, 5532B, 5534B, 5535B, 5536B, 5588B, 5594B, 5717BP, 5718BP, 5719BP, 5720BP, 5721BP, 5722BP, 5728BP, 5729BP, 5730BP, 5731BP, 5733BP, 5734BP & 5737BP NEW SHOP DRAWINGS: 5153BP, 5153BP, 5154BP, 5155BP, 5845A, 5846BP, 5847BP, 5848BP, 5849BP, 5850BP, 5851BP, 5858VB, 5859B & 5860A VOID SHOP DRAWINGS: 4699C, 4700C, 4702C, 4701C, 5100C, 5307C, 5308C, 5309C, 5329C, 5701VB Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05073 | Review Response | Approved as Noted/Resubmit | 2020-03-26 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | See submittal comments for pieces to be submitted for review. | Info Exchange
| 06897 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-17 |  | 05 12 00-205.0 Quad C Elevator C1-C2 RR-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-17 |  | 05 12 00-205.0 Quad C Elevator C1-C2 RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-17 |  | 05 12 00-205.0 Quad C Elevator C1-C2 RR-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-26 |  | 05 12 00-205.0 Quad C Elevator C1-C2 RR-MAM_TT_POP.pdf
05 12 00-205-01 | 05 12 00 - STEEL | 05 12 00-205-01 Quad C - Elevator C1-C2 Revised Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-08 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-22 | 2020-04-15 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05258 | Received | For Review | 2020-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-22 | Submittal Number: 05 12 00-205.1 From: STEPHEN PRINCE Final Due Date: 04/22/20 Subject: QUAD C - ELEVATOR C1-C2 REVISED PACKAGE Description: R&R/OFA PACKAGE HAS BEEN POSTED ON PROCORE FOR ALL STEEL AFFECTED BY RE-FRAMING CHANGES AT ELEVATOR C1,C2 (QUAD C). PLEASE NOTE THE FOLLOWING… INCORPORATES RECEIVED COORDINATION INFORMATION FOR QUAD C ELEVATORS (ELEVATORS C1 AND C2) INCORPORATES RFI 1734 (NOC 120) INCORPORATES RFI 1709 (NOC 107) INCORPORATES RFI 2156 (NOC 296) INCORPORATES BFA COMMENTS FROM 05 12 00-28.1 SPS SHOP DRAWINGS-MAM_TT_POP_02-28-2020 UPDATED E-PLANS: E267, E268, E274, E275, E288, E290, E291, E292, E317, E318, E319, E320, E325, E326, E327, E340, E341 & E342 NEW SECTION DETAIL’S: E327.1 UPDATED SHOP DRAWINGS: 4695C, 4696C, 4697C, 4698C, 4741G, 4743G, 4747G, 4750G, 4754G, 4756G, 4757G, 4846B, 4847B, 4849B, 4850B, 4853B, 4854B, 4989BP, 4990BP, 4991BP, 4992BP, 4993BP, 4995BP, 5008BP, 5009BP, 5010BP, 5011BP, 5012BP, 5013BP, 5014BP, 5018BP, 5019BP, 5022BP, 5048VB, 5054A, 5055A, 5311C, 5312C, 5314C, 5326C, 5327C, 5335C, 5336C, 5339C, 5340C, 5378G, 5379G,, 5380G, 5388G, 5391G, 5392G, 5449G, 5451G, 5527G, 5529B, 5530B, 5532B, 5534B, 5535B, 5536B, 5588B, 5594B, 5717BP, 5718BP, 5719BP, 5720BP, 5721BP, 5722BP, 5728BP, 5729BP, 5730BP, 5731BP, 5733BP, 5734BP & 5737BP NEW SHOP DRAWINGS: 5153BP, 5153BP, 5154BP, 5155BP, 5845A, 5846BP, 5847BP, 5848BP, 5849BP, 5850BP, 5851BP, 5858VB, 5859B & 5860A VOID SHOP DRAWINGS: 4699C, 4700C, 4702C, 4701C, 5100C, 5307C, 5308C, 5309C, 5329C, 5701VB Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07150 | Forwarded | For Review | 2020-04-08 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-15 | Submittal Number: 05 12 00-205.1 From: STEPHEN PRINCE Final Due Date: 04/22/20 Subject: QUAD C - ELEVATOR C1-C2 REVISED PACKAGE Description: R&R/OFA PACKAGE HAS BEEN POSTED ON PROCORE FOR ALL STEEL AFFECTED BY RE-FRAMING CHANGES AT ELEVATOR C1,C2 (QUAD C). PLEASE NOTE THE FOLLOWING… INCORPORATES RECEIVED COORDINATION INFORMATION FOR QUAD C ELEVATORS (ELEVATORS C1 AND C2) INCORPORATES RFI 1734 (NOC 120) INCORPORATES RFI 1709 (NOC 107) INCORPORATES RFI 2156 (NOC 296) INCORPORATES BFA COMMENTS FROM 05 12 00-28.1 SPS SHOP DRAWINGS-MAM_TT_POP_02-28-2020 UPDATED E-PLANS: E267, E268, E274, E275, E288, E290, E291, E292, E317, E318, E319, E320, E325, E326, E327, E340, E341 & E342 NEW SECTION DETAIL’S: E327.1 UPDATED SHOP DRAWINGS: 4695C, 4696C, 4697C, 4698C, 4741G, 4743G, 4747G, 4750G, 4754G, 4756G, 4757G, 4846B, 4847B, 4849B, 4850B, 4853B, 4854B, 4989BP, 4990BP, 4991BP, 4992BP, 4993BP, 4995BP, 5008BP, 5009BP, 5010BP, 5011BP, 5012BP, 5013BP, 5014BP, 5018BP, 5019BP, 5022BP, 5048VB, 5054A, 5055A, 5311C, 5312C, 5314C, 5326C, 5327C, 5335C, 5336C, 5339C, 5340C, 5378G, 5379G,, 5380G, 5388G, 5391G, 5392G, 5449G, 5451G, 5527G, 5529B, 5530B, 5532B, 5534B, 5535B, 5536B, 5588B, 5594B, 5717BP, 5718BP, 5719BP, 5720BP, 5721BP, 5722BP, 5728BP, 5729BP, 5730BP, 5731BP, 5733BP, 5734BP & 5737BP NEW SHOP DRAWINGS: 5153BP, 5153BP, 5154BP, 5155BP, 5845A, 5846BP, 5847BP, 5848BP, 5849BP, 5850BP, 5851BP, 5858VB, 5859B & 5860A VOID SHOP DRAWINGS: 4699C, 4700C, 4702C, 4701C, 5100C, 5307C, 5308C, 5309C, 5329C, 5701VB Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05380 | Review Response | Approved as Noted | 2020-04-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07307 | Responded and Closed | Approved as Noted | 2020-04-15 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-08 |  | 05 12 00-205.1 Quad C Elevator C1-C2 RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-08 |  | 05 12 00-205.1 Quad C Elevator C1-C2 RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-08 |  | 05 12 00-205.1 Quad C Elevator C1-C2 RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-15 |  | 05 12 00-205.1 Quad C Elevator C1-C2 RR-MAM_TT_POP.pdf
05 12 00-206-00 | 05 12 00 - STEEL | 05 12 00-206-00 Quad B6 Steel Shop Drawings- Sequence 406, 410 & 411 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-26 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-09 | 2020-04-15 | 21 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05069 | Received | For Review | 2020-03-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-09 | Submittal Number: 05 12 00-206.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/10/20 Subject: QUAD B6 STEEL SHOP DRAWINGS- SEQUENCE 406, 410 & 411 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06894 | Forwarded | For Review | 2020-03-26 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-02 | Submittal Number: 05 12 00-206.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/10/20 Subject: QUAD B6 STEEL SHOP DRAWINGS- SEQUENCE 406, 410 & 411 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05244 | Review Response | Approved as Noted | 2020-04-07 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | There are several slab edge questions on piece sheets for Arch to verify. | Info Exchange
| 07306 | Responded and Closed | Approved as Noted | 2020-04-15 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-26 |  | 05 12 00-206.0 Quad B6 Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-26 |  | 05 12 00-206.0 Quad B6 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-26 |  | 05 12 00-206.0 Quad B6 Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-15 |  | 05 12 00-206.0 Quad B6 Steel SD-MAM_TT_POP.pdf
05 12 00-207-00 | 05 12 00 - STEEL | 05 12 00-207-00 Monument Stair Bearing Pad Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-07 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-21 | 2020-04-20 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05243 | Received | For Review | 2020-04-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-21 | Submittal Number: 05 12 00-207.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/21/20 Subject: MONUMENT STAIR BEARING PAD DATA Description: BEARING PAD MATERIAL AS DIRECTED IN PROJECT RFI 2348 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07135 | Forwarded | For Review | 2020-04-07 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-14 | Submittal Number: 05 12 00-207.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/21/20 Subject: MONUMENT STAIR BEARING PAD DATA Description: BEARING PAD MATERIAL AS DIRECTED IN PROJECT RFI 2348 Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05457 | Review Response | Approved | 2020-04-20 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 07407 | Responded and Closed | Approved | 2020-04-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-07 |  | 05 12 00-207.0 Monumental Stair Bearing Pad PD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-07 |  | 05 12 00-207.0 Monumental Stair Bearing Pad PD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-07 |  | 05 12 00-207.0 Monumental Stair Bearing Pad PD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-20 |  | 05 12 00-207.0 Monumental Stair Bearing Pad PD-MAM_TT_POP.pdf
05 12 00-208-00 | 05 12 00 - STEEL | 05 12 00-208-00 Sequence 72 Hydrotherapy Pit Framing Steel SD | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-09 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-23 | 2020-04-29 | 21 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-04-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05260 | Received | For Review | 2020-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-23 | Submittal Number: 05 12 00-208.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/22/20 Subject: SEQUENCE 72 HYDROTHERAPY PIT FRAMING STEEL SD Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07153 | Forwarded | For Review | 2020-04-08 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-15 | Submittal Number: 05 12 00-208.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/22/20 Subject: SEQUENCE 72 HYDROTHERAPY PIT FRAMING STEEL SD Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05490 | Review Response | Approved as Noted | 2020-04-21 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Populous to review and confirm locations of framing. | Info Exchange
| 07625 | Responded and Closed | Approved as Noted | 2020-04-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | APPROVED AS NOTED. SEE ARCHITECT'S DIMENSIONS.-CLM | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-08 |  | 05 12 00-208.0 Hydrotherapy Pit Framing SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-08 |  | 05 12 00-208.0 Hydrotherapy Pit Framing SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-08 |  | 05 12 00-208.0 Hydrotherapy Pit Framing SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-29 |  | 05 12 00-208.0 Hydrotherapy Pit Framing SD-MAM_TT REVIEW-POP-CLM.pdf
05 12 00-209-00 | 05 12 00 - STEEL | 05 12 00-209-00 Quad E/F Stud Layout Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-29 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-13 | 2020-05-14 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-05-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05637 | Received | For Review | 2020-04-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-05-13 | Submittal Number: 05 12 00-209.0 From: JES PELKEY Final Due Date: 05/13/20 Subject: QUAD E/F STUD LAYOUT DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07633 | Forwarded | For Review | 2020-04-29 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-06 | Submittal Number: 05 12 00-209.0 From: JES PELKEY Final Due Date: 05/13/20 Subject: QUAD E/F STUD LAYOUT DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05866 | Review Response | Approved as Noted | 2020-05-13 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07960 | Responded and Closed | Approved as Noted | 2020-05-14 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-29 |  | 05 12 00-209.0 Quad E and F Stud Layout SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-29 |  | 05 12 00-209.0 Quad E and F Stud Layout SD-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-04-29 |  | 05 12 00-209.0 Quad E and F Stud Layout SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-14 |  | 05 12 00-209.0 Quad E and F Stud Layout SD-MAM_TT_POP.pdf
05 12 00-210-00 | 05 12 00 - STEEL | 05 12 00-210-00 Quad A-C Stud Layout Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-28 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-12 | 2020-05-12 | 15 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05592 | Received | For Review | 2020-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-12 | Submittal Number: 05 12 00-210.0 From: JES PELKEY Final Due Date: 05/12/20 Subject: QUAD A-C STUD LAYOUT DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07577 | Forwarded | For Review | 2020-04-28 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-05 | Submittal Number: 05 12 00-210.0 From: JES PELKEY Final Due Date: 05/12/20 Subject: QUAD A-C STUD LAYOUT DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05700 | Review Response | Approved as Noted | 2020-05-04 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 07886 | Responded and Closed | Approved as Noted | 2020-05-12 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-28 |  | 05 12 00-210.0 Quad A-C Stud Layout Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-28 |  | 05 12 00-210.0 Quad A-C Stud Layout Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-28 |  | 05 12 00-210.0 Quad A-C Stud Layout Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-12 |  | 05 12 00-210.0 Quad A-C Stud Layout Drawings-MAM_TT_POP.pdf
05 12 00-211-00 | 05 12 00 - STEEL | 05 12 00-211-00 North Window Shade Support Steel - Seq. 73 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-09 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-23 | 2020-07-22 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-07-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06886 | Received | For Review | 2020-07-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-23 | Submittal Number: 05 12 00-211.0 From: JES PELKEY Final Due Date: 07/23/20 Subject: NORTH WINDOW SHADE SUPPORT STEEL - SEQ. 73 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09228 | Forwarded | For Review | 2020-07-09 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-16 | Submittal Number: 05 12 00-211.0 From: JES PELKEY Final Due Date: 07/23/20 Subject: NORTH WINDOW SHADE SUPPORT STEEL - SEQ. 73 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07089 | Review Response | Approved as Noted/Resubmit | 2020-07-21 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  | - GC to submit RFI for clash at precast. - GC to submit confirming RFI for slab leave out per comments on 1/E869 - See typical comments on 14910BP, 14926P, 14945A SDK ¦ TT ¦ 7/21/2020 | Info Exchange
| 09477 | Responded and Closed | Approved as Noted | 2020-07-22 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | - GC to submit RFI for clash at precast. - GC to submit confirming RFI for slab leave out per comments on 1/E869 - See typical comments on 14910BP, 14926P, 14945A SDK ¦ TT ¦ 7/21/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-09 |  | 05 12 00-211.0 North Window Shade Support Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-09 |  | 05 12 00-211.0 North Window Shade Support Steel SD-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-07-09 |  | 05 12 00-211.0 North Window Shade Support Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-22 |  | 05 12 00-211.0 North Window Shade Support Steel SD-MAM_TT_POP.pdf
05 12 00-212-00 | 05 12 00 - STEEL | 05 12 00-212-00 Sequence 70 & 71 Monumental Stair Framing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-07 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-21 | 2020-04-20 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05238 | Received | For Review | 2020-04-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-21 | Submittal Number: 05 12 00-212.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/21/20 Subject: SEQUENCE 70 & 71 MONUMENTAL STAIR FRAMING Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07129 | Forwarded | For Review | 2020-04-07 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-14 | Submittal Number: 05 12 00-212.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/21/20 Subject: SEQUENCE 70 & 71 MONUMENTAL STAIR FRAMING Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05456 | Review Response | Approved as Noted | 2020-04-20 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 07406 | Responded and Closed | Approved as Noted | 2020-04-20 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-07 |  | 05 12 00-212.0 Monumental Stair Framing-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-07 |  | 05 12 00-212.0 Monumental Stair Framing-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-07 |  | 05 12 00-212.0 Monumental Stair Framing-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-20 |  | 05 12 00-212.0 Monumental Stair Framing-MAM_TT_POP.pdf
05 12 00-213-00 | 05 12 00 - STEEL | 05 12 00-213-00 Quad D Catwalk & Rigging Grid Steel SD - Seq. DR1-DR4 & DRH1 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-22 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-06 | 2020-05-13 | 22 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-05-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05503 | Received | For Review | 2020-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-06 | Submittal Number: 05 12 00-213.0 From: BRAD KIRSCHENHEITER Final Due Date: 05/13/20 Subject: QUAD D CATWALK & RIGGING GRID STEEL SD - SEQ. DR1-DR4 & DRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07461 | Forwarded | For Review | 2020-04-22 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-29 | Submittal Number: 05 12 00-213.0 From: BRAD KIRSCHENHEITER Final Due Date: 05/13/20 Subject: QUAD D CATWALK & RIGGING GRID STEEL SD - SEQ. DR1-DR4 & DRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05773 | Review Response | Approved as Noted/Resubmit | 2020-05-07 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Detail BRB at Rigging Grid Truss per Corebrace calcs. Kicker missing as noted near C/35.7. Provide calculations for connection of stair railing to stair stringer. Connection calcs not included in submittal. | Info Exchange
| 07944 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 05 12 00-213.0 Quad D Catwalk and Rigging Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-22 |  | 05 12 00-213.0 Quad D Catwalk and Rigging Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-22 |  | 05 12 00-213.0 Quad D Catwalk and Rigging Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-07 |  | 05 12 00-213.0 Quad D Catwalk and Rigging Steel SD-TT REVIEW.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-13 |  | 05 12 00-213.0 Quad D Catwalk and Rigging Steel SD-TT_POP-CLM.pdf
05 12 00-213-01 | 05 12 00 - STEEL | 05 12 00-213-01 Quad D Catwalk & Rigging Grid Steel SD - Seq. DR1-DR4 & DRH1 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous) |  |  |  | 2020-06-25 | 2020-06-15 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06350 | Received | For Review | 2020-06-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-06-25 | Submittal Number: 05 12 00-213.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/25/20 Subject: QUAD D CATWALK & RIGGING GRID STEEL SD - SEQ. DR1-DR4 & DRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08565 | Forwarded | For Review | 2020-06-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-18 | Submittal Number: 05 12 00-213.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/25/20 Subject: QUAD D CATWALK & RIGGING GRID STEEL SD - SEQ. DR1-DR4 & DRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06418 | Review Response | Approved as Noted | 2020-06-12 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08640 | Forwarded | For Review | 2020-06-15 | Todd Spangler (Populous) | Chris Minter (Populous) |  | Submittal Number: 05 12 00-213.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/25/20 Subject: QUAD D CATWALK & RIGGING GRID STEEL SD - SEQ. DR1-DR4 & DRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08646 | Responded and Closed | Approved as Noted | 2020-06-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-11 |  | 05 12 00-213.1 Quad D Catwalk Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-11 |  | 05 12 00-213.1 Quad D Catwalk Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-11 |  | 05 12 00-213.1 Quad D Catwalk Steel SD RR-MAM.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-06-11 |  | 05 12 00-213.1 Quad D Catwalk Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-15 |  | 05 12 00-213.1 Quad D Catwalk Steel SD RR-MAM_TT_POP.pdf
05 12 00-215-00 | 05 12 00 - STEEL | 05 12 00-215-00 Atrium Steel SD - Seq. 421 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-24 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-09 07:00 | 2020-07-14 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06584 | Received | For Review | 2020-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-09 07:00 | Submittal Number: 05 12 00-215.0 From: BRAD KIRSCHENHEITER Final Due Date: 07/08/20 Subject: ATRIUM STEEL SD - SEQ. 421 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08867 | Forwarded | For Review | 2020-06-24 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-01 | Submittal Number: 05 12 00-215.0 From: BRAD KIRSCHENHEITER Final Due Date: 07/08/20 Subject: ATRIUM STEEL SD - SEQ. 421 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09311 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-14 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHEDF FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-24 |  | 05 12 00-215.0 Atrium Seq. 421 Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-24 |  | 05 12 00-215.0 Atrium Seq. 421 Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-14 |  | 05 12 00-215.0 Atrium Seq. 421 Steel SD-MAM_TT_POP.pdf
05 12 00-215-01 | 05 12 00 - STEEL | 05 12 00-215-01 Atrium Steel SD - Seq. 421 - drawings E1002 and E1010 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-30 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-13 | 2020-08-04 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07255 | Received | For Review | 2020-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-13 | Submittal Number: 05 12 00-215.1 From: BRAD KIRSCHENHEITER Final Due Date: 08/13/20 Subject: ATRIUM STEEL SD - SEQ. 421 - DRAWINGS E1002 AND E1010 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09667 | Forwarded | For Review | 2020-07-30 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-06 | Submittal Number: 05 12 00-215.1 From: BRAD KIRSCHENHEITER Final Due Date: 08/13/20 Subject: ATRIUM STEEL SD - SEQ. 421 - DRAWINGS E1002 AND E1010 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07338 | Review Response | Approved | 2020-07-31 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 09786 | Responded and Closed | Approved as Noted | 2020-08-04 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTAHCED FOR REVIEW AND COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-29 |  | 05 12 00-215.1 Atrium Seq. 421 SD RR-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-29 |  | 05 12 00-215.1 Atrium Seq. 421 SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-29 |  | 05 12 00-215.1 Atrium Seq. 421 SD RR-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-04 |  | 05 12 00-215.1 Atrium Seq. 421 SD RR-MAM_TT_POP.pdf
05 12 00-216-00 | 05 12 00 - STEEL | 05 12 00-216-00 Escalator A1 A2 B1 B2 Intermediate Support Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-20 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-04 | 2020-04-20 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05426 | Received | For Review | 2020-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-05-04 | Submittal Number: 05 12 00-216.0 From: NATE WEINGART Final Due Date: 05/01/20 Subject: ESCALATOR A1 A2 B1 B2 INTERMEDIATE SUPPORT DESIGN Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07364 | Forwarded | For Review | 2020-04-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-27 | Submittal Number: 05 12 00-216.0 From: NATE WEINGART Final Due Date: 05/01/20 Subject: ESCALATOR A1 A2 B1 B2 INTERMEDIATE SUPPORT DESIGN Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05455 | Review Response | Approved | 2020-04-20 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. Retained for Record. | Info Exchange
| 07405 | Responded and Closed | Approved | 2020-04-20 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-20 |  | 05 12 00-216.0 Escalator A1 A2 B1 B2 Intermediate Support Design (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-20 |  | 05 12 00-216.0 Escalator A1 A2 B1 B2 Intermediate Support Design (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-20 |  | 05 12 00-216.0 Escalator A1 A2 B1 B2 Intermediate Support Design (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-20 |  | 05 12 00-216.0 Escalator A1 A2 B1 B2 Intermediate Support Design-MAM_TT_POP.pdf
05 12 00-217-00 | 05 12 00 - STEEL | 05 12 00-217-00 Quad A Catwalk & Rigging Grid - Sequence AR1-AR4 & ARH1 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-08 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous) |  |  |  | 2020-05-22 | 2020-05-26 | 19 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05771 | Received | For Review | 2020-05-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-22 | Submittal Number: 05 12 00-217.0 From: BRAD KIRSCHENHEITER Final Due Date: 05/20/20 Subject: QUAD A CATWALK & RIGGING GRID - SEQUENCE AR1-AR4 & ARH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07828 | Forwarded | For Review | 2020-05-08 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-15 | Submittal Number: 05 12 00-217.0 From: BRAD KIRSCHENHEITER Final Due Date: 05/20/20 Subject: QUAD A CATWALK & RIGGING GRID - SEQUENCE AR1-AR4 & ARH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06036 | Review Response | Approved as Noted/Resubmit | 2020-05-15 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Refer to comments regarding BRB detailing, railing to stair stringer connection, and channels at rail posts. | Info Exchange
| 08087 | Forwarded | For Review | 2020-05-20 | Populous SCA_CCA | Chris Minter (Populous) | 2020-05-22 | Submittal Number: 05 12 00-217.0 From: BRAD KIRSCHENHEITER Final Due Date: 05/20/20 Subject: QUAD A CATWALK & RIGGING GRID - SEQUENCE AR1-AR4 & ARH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08184 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-07 |  | 05 12 00-217.0 Quad A Catwalk Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-07 |  | 05 12 00-217.0 Quad A Catwalk Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-07 |  | 05 12 00-217.0 Quad A Catwalk Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-07 |  | 05 12 00-217.0 Quad A Catwalk Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-15 |  | 05 12 00-217.0 Quad A Catwalk Steel SD-MAM_TT REVIEW.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-26 |  | 05 12 00-217.0 Quad A Catwalk Steel SD-MAM_TT REVIEW-POP.pdf
05 12 00-217-01 | 05 12 00 - STEEL | 05 12 00-217-01 Quad A Catwalk & Rigging Grid - Sequence AR1-AR4 & ARH1 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-12 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous) |  |  |  | 2020-06-26 | 2020-06-15 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06367 | Received | For Review | 2020-06-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-06-26 | Submittal Number: 05 12 00-217.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/25/20 Subject: QUAD A CATWALK & RIGGING GRID - SEQUENCE AR1-AR4 & ARH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08583 | Forwarded | For Review | 2020-06-12 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-19 | Submittal Number: 05 12 00-217.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/25/20 Subject: QUAD A CATWALK & RIGGING GRID - SEQUENCE AR1-AR4 & ARH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06417 | Review Response | Approved as Noted | 2020-06-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08641 | Forwarded | For Review | 2020-06-15 | Todd Spangler (Populous) | Chris Minter (Populous) |  | Submittal Number: 05 12 00-217.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/25/20 Subject: QUAD A CATWALK & RIGGING GRID - SEQUENCE AR1-AR4 & ARH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08645 | Responded and Closed | Approved as Noted | 2020-06-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-11 |  | 05 12 00-217.1 Quad A Catwalk Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-11 |  | 05 12 00-217.1 Quad A Catwalk Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-11 |  | 05 12 00-217.1 Quad A Catwalk Steel SD RR-MAM.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-06-11 |  | 05 12 00-217.1 Quad A Catwalk Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-15 |  | 05 12 00-217.1 Quad A Catwalk Steel SD RR-MAM_TT_POP.pdf
05 12 00-217-02 | 05 12 00 - STEEL | 05 12 00-217-02 Quad A & B Rigging Grid Catwalk - Guardrail Height Modification at Truss Stair | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-23 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-07 | 2021-06-23 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-06-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13622 | Received | For Review | 2021-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-07 | Submittal Number: 05 12 00-217.2 From: SKYLER MITCHELL Final Due Date: 07/07/21 Subject: QUAD A & B RIGGING GRID CATWALK - GUARDRAIL HEIGHT MODIFICATION AT TRUSS STAIR Description: SHOP DRAWINGS AND TEST REPORT DATA FOR GUARDRAIL HEIGHT INCREASE AT CATWALK STAIR PLATFORM, APPLICABLE AT QUAD A AND QUAD B. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 17638 | Forwarded | For Review | 2021-06-23 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-30 | Submittal Number: 05 12 00-217.2 From: SKYLER MITCHELL Final Due Date: 07/07/21 Subject: QUAD A & B RIGGING GRID CATWALK - GUARDRAIL HEIGHT MODIFICATION AT TRUSS STAIR Description: SHOP DRAWINGS AND TEST REPORT DATA FOR GUARDRAIL HEIGHT INCREASE AT CATWALK STAIR PLATFORM, APPLICABLE AT QUAD A AND QUAD B. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 13623 | Review Response | Approved | 2021-06-23 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 17642 | Responded and Closed | Approved | 2021-06-23 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-23 |  | 05 12 00-217.2 Quad A and B Rigging Grid Catwalk Guardrail Modification_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-23 |  | 05 12 00-217.2 Quad A and B Rigging Grid Catwalk Guardrail Modification_MAM Review.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-06-22 02:00 |  | 05 12 00-217.2 Quad A and B Rigging Grid Catwalk Guardrail Modification_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-23 02:00 |  | 05 12 00-217.2 Quad A and B Rigging Grid Catwalk Guardrail Modification_MAM Review_TT_POP.pdf
05 12 00-218-00 | 05 12 00 - STEEL | 05 12 00-218-00 Atrium Steel Sequence 422a, 422b, 426 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-25 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-10 07:00 | 2020-07-15 | 21 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06595 | Received | For Review | 2020-06-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-10 07:00 | Submittal Number: 05 12 00-218.0 From: BRAD KIRSCHENHEITER Final Due Date: 07/13/20 Subject: ATRIUM STEEL SEQUENCE 422A, 422B, 426 Description: UPDATED TO ADD ADDITIONAL PN SHEETS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08887 | Forwarded | For Review | 2020-06-25 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-02 | Submittal Number: 05 12 00-218.0 From: BRAD KIRSCHENHEITER Final Due Date: 07/13/20 Subject: ATRIUM STEEL SEQUENCE 422A, 422B, 426 Description: UPDATED TO ADD ADDITIONAL PN SHEETS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06952 | Review Response | Revise and Resubmit | 2020-07-09 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | See stamps on sheets for pieces that will be required to be reviewed and approved again once revised. All other sheets are approved as noted. | Info Exchange
| 09359 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-15 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-24 |  | 05 12 00-218.0 Atrium Seq 422&426 Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-24 |  | 05 12 00-218.0 Atrium Seq 422&426 Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-24 |  | 05 12 00-218.0 Atrium Seq 422&426 Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-15 |  | 05 12 00-218.0 Atrium Seq 422&426 Steel SD-MAM_TT_POP.pdf
05 12 00-218-01 | 05 12 00 - STEEL | 05 12 00-218-01 Atrium Steel Sequence 422a, 422b, 426 - E1022, 40254G, 40308P, 41502G | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-30 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-13 | 2020-08-04 | 6 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07256 | Received | For Review | 2020-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-08-13 | Submittal Number: 05 12 00-218.1 From: BRAD KIRSCHENHEITER Final Due Date: 08/13/20 Subject: ATRIUM STEEL SEQUENCE 422A, 422B, 426 - E1022, 40254G, 40308P, 41502G Description: UPDATED TO ADD ADDITIONAL PN SHEETS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09668 | Forwarded | For Review | 2020-07-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-06 | Submittal Number: 05 12 00-218.1 From: BRAD KIRSCHENHEITER Final Due Date: 08/13/20 Subject: ATRIUM STEEL SEQUENCE 422A, 422B, 426 - E1022, 40254G, 40308P, 41502G Description: UPDATED TO ADD ADDITIONAL PN SHEETS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07339 | Review Response | Approved as Noted | 2020-08-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09787 | Responded and Closed | Approved as Noted | 2020-08-04 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-29 |  | 05 12 00-218.1 Atrium Seq. 422 & 426 Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-29 |  | 05 12 00-218.1 Atrium Seq. 422 & 426 Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-29 |  | 05 12 00-218.1 Atrium Seq. 422 & 426 Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-04 |  | 05 12 00-218.1 Atrium Seq. 422 & 426 Steel SD RR-MAM_TT_POP.pdf
05 12 00-220-00 | 05 12 00 - STEEL | 05 12 00-220-00 Bressi Garage Coupler for Cable Replacement | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-27 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-11 | 2020-05-04 | 8 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05556 | Received | For Review | 2020-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-11 | Submittal Number: 05 12 00-220.0 From: JES PELKEY Final Due Date: 05/22/20 Subject: BRESSI GARAGE COUPLER FOR CABLE REPLACEMENT Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07532 | Forwarded | For Review | 2020-04-27 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-04 | Submittal Number: 05 12 00-220.0 From: JES PELKEY Final Due Date: 05/22/20 Subject: BRESSI GARAGE COUPLER FOR CABLE REPLACEMENT Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 05699 | Review Response | No Action Taken or Required | 2020-04-30 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Per previous conversations with MAM, this item is outside of TT's scope. Not reviewed - TT-FK | Info Exchange
| 07717 | Responded and Closed | Not Required For Review | 2020-05-04 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Per previous conversations with MAM, this item is outside of TT's scope. Not reviewed - TT-FK | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | 05 12 00-220.0 Bressi Garage Coupler for Cables-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-24 |  | 05 12 00-220.0 Bressi Garage Coupler for Cables-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-04-24 |  | 05 12 00-220.0 Bressi Garage Coupler for Cables-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-04 |  | 05 12 00-220.0 Bressi Garage Coupler for Cables-MAM_POP.pdf
05 12 00-220-01 | 05 12 00 - STEEL | 05 12 00-220-01 Bressi Garage Coupler for Cable Replacement | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-27 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-10 | 2020-11-04 | 9 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-11-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09026 | Received | For Review | 2020-10-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-11-10 | Submittal Number: 05 12 00-220.1 From: JES PELKEY Final Due Date: 11/10/20 Subject: BRESSI GARAGE COUPLER FOR CABLE REPLACEMENT Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 11907 | Forwarded | For Review | 2020-10-27 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-03 | Submittal Number: 05 12 00-220.1 From: JES PELKEY Final Due Date: 11/10/20 Subject: BRESSI GARAGE COUPLER FOR CABLE REPLACEMENT Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09230 | Review Response | Approved | 2020-11-02 | Sean McNeill (Thornton Tomasetti) | Populous SCA_CCA |  | No Exceptions | Info Exchange
| 12188 | Responded and Closed | Approved | 2020-11-04 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 05 12 00-220.1 Bressi Garage Coupler for Calbes Rev1-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-27 |  | 05 12 00-220.1 Bressi Garage Coupler for Calbes Rev1-MAM.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-10-27 |  | 05 12 00-220.1 Bressi Garage Coupler for Calbes Rev1-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-04 |  | 05 12 00-220.1 Bressi Garage Coupler for Calbes Rev1-MAM_TT_POP.pdf
05 12 00-222-00 | 05 12 00 - STEEL | 05 12 00-222-00 Quad C Catwalk & Rigging Grid Steel SD - Seq. CR1-CR4 & CRH1 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-01 | 2020-06-05 | 26 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-06-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05785 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-01 | Submittal Number: 05 12 00-222.0 From: BRAD KIRSCHENHEITER Final Due Date: 05/22/20 Subject: QUAD C CATWALK & RIGGING GRID STEEL SD - SEQ. CR1-CR4 & CRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07842 | Forwarded | For Review | 2020-05-11 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-18 | Submittal Number: 05 12 00-222.0 From: BRAD KIRSCHENHEITER Final Due Date: 05/22/20 Subject: QUAD C CATWALK & RIGGING GRID STEEL SD - SEQ. CR1-CR4 & CRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06234 | Review Response | Approved as Noted/Resubmit | 2020-06-01 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 08418 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 05 12 00-222.0 Quad C Catwalk and Rigging SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-11 |  | 05 12 00-222.0 Quad C Catwalk and Rigging SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-11 |  | 05 12 00-222.0 Quad C Catwalk and Rigging SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-01 |  | 05 12 00-222.0 Quad C Catwalk and Rigging SD-MAM_TT REVIEW.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-05 |  | 05 12 00-222.0 Quad C Catwalk and Rigging SD-MAM_TT REVIEW-POP.pdf
05 12 00-222-01 | 05 12 00 - STEEL | 05 12 00-222-01 Quad C Catwalk & Rigging Grid Steel SD - Seq. CR1-CR4 & CRH1 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-15 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous) |  |  |  | 2020-06-29 | 2020-06-15 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06394 | Received | For Review | 2020-06-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-06-29 | Submittal Number: 05 12 00-222.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/29/20 Subject: QUAD C CATWALK & RIGGING GRID STEEL SD - SEQ. CR1-CR4 & CRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08612 | Forwarded | For Review | 2020-06-15 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-22 | Submittal Number: 05 12 00-222.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/29/20 Subject: QUAD C CATWALK & RIGGING GRID STEEL SD - SEQ. CR1-CR4 & CRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06416 | Review Response | Approved as Noted | 2020-06-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08642 | Forwarded | For Review | 2020-06-15 | Todd Spangler (Populous) | Chris Minter (Populous) |  | Submittal Number: 05 12 00-222.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/29/20 Subject: QUAD C CATWALK & RIGGING GRID STEEL SD - SEQ. CR1-CR4 & CRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08644 | Responded and Closed | Approved | 2020-06-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | SEE ATTACHE. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-15 |  | 05 12 00-222.1 Quad C Catwalk Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-15 |  | 05 12 00-222.1 Quad C Catwalk Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-15 |  | 05 12 00-222.1 Quad C Catwalk Steel SD RR-MAM.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-06-15 |  | 05 12 00-222.1 Quad C Catwalk Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-15 |  | 05 12 00-222.1 Quad C Catwalk Steel SD RR-MAM_TT_POP.pdf
05 12 00-223-00 | 05 12 00 - STEEL | 05 12 00-223-00 Quad B Catwalk & Rigging Grid - Sequence BR1-BR6 & BRH1 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-01 | 2020-06-05 | 26 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-06-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05776 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-01 | Submittal Number: 05 12 00-223.0 From: BRAD KIRSCHENHEITER Final Due Date: 05/22/20 Subject: QUAD B CATWALK & RIGGING GRID - SEQUENCE BR1-BR6 & BRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07833 | Forwarded | For Review | 2020-05-11 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-18 | Submittal Number: 05 12 00-223.0 From: BRAD KIRSCHENHEITER Final Due Date: 05/22/20 Subject: QUAD B CATWALK & RIGGING GRID - SEQUENCE BR1-BR6 & BRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06235 | Review Response | Approved as Noted/Resubmit | 2020-06-01 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 08419 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 05 12 00-223.0 Quad B Catwalk and Rigging Grid Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-11 |  | 05 12 00-223.0 Quad B Catwalk and Rigging Grid Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-11 |  | 05 12 00-223.0 Quad B Catwalk and Rigging Grid Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-01 |  | 05 12 00-223.0 Quad B Catwalk and Rigging Grid Steel SD-MAM_TT REVIEW.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-05 |  | 05 12 00-223.0 Quad B Catwalk and Rigging Grid Steel SD-MAM_TT REVIEW-POP.pdf
05 12 00-223-01 | 05 12 00 - STEEL | 05 12 00-223-01 Quad B Catwalk & Rigging Grid - Sequence BR1-BR6 & BRH1 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-15 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-29 | 2020-06-15 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06396 | Received | For Review | 2020-06-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-06-29 | Submittal Number: 05 12 00-223.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/29/20 Subject: QUAD B CATWALK & RIGGING GRID - SEQUENCE BR1-BR6 & BRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08613 | Forwarded | For Review | 2020-06-15 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-22 | Submittal Number: 05 12 00-223.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/29/20 Subject: QUAD B CATWALK & RIGGING GRID - SEQUENCE BR1-BR6 & BRH1 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06415 | Review Response | Approved as Noted | 2020-06-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08643 | Responded and Closed | Approved as Noted | 2020-06-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-15 |  | 05 12 00-223.1 Quad B Catwalk Steel SD RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-15 |  | 05 12 00-223.1 Quad B Catwalk Steel SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-15 |  | 05 12 00-223.1 Quad B Catwalk Steel SD RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-15 |  | 05 12 00-223.1 Quad B Catwalk Steel SD RR-MAM_TT_POP.pdf
05 12 00-224-00 | 05 12 00 - STEEL | 05 12 00-224-00 Sequence 61G Cooling Tower West Pipe Chase | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-19 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-02 | 2020-06-04 | 17 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05933 | Received | For Review | 2020-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company); Whitney Thomas | 2020-06-02 | Submittal Number: 05 12 00-224.0 From: BRAD KIRSCHENHEITER Final Due Date: 06/02/20 Subject: SEQUENCE 61G COOLING TOWER WEST PIPE CHASE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08052 | Forwarded | For Review | 2020-05-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-26 | Submittal Number: 05 12 00-224.0 From: BRAD KIRSCHENHEITER Final Due Date: 06/02/20 Subject: SEQUENCE 61G COOLING TOWER WEST PIPE CHASE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06184 | Review Response | Approved as Noted | 2020-05-29 | Andy Tatkowski (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached. ART ¦ TT ¦ 5/29/2020 | Info Exchange
| 08361 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-04 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | see attached for review and comments. Resubmit layout sheet E801 to confirm changes for exiting grades for the bottom HSS locations, bent plate dimensions, and gate staggered elevation. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 |  | 05 12 00-224.0 Cooling Tower West Pipe Chase SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-19 |  | 05 12 00-224.0 Cooling Tower West Pipe Chase SD-MAM.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-05-29 |  | 05 12 00-224.0 Cooling Tower West Pipe Chase SD-MAM_TT.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-04 |  | 05 12 00-224.0 Cooling Tower West Pipe Chase SD-MAM_TT_POP.pdf
05 12 00-224-01 | 05 12 00 - STEEL | 05 12 00-224-01 Sequence 61G Cooling Tower West Pipe Chase | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-30 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-15 07:00 | 2020-07-01 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-07-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06699 | Received | For Review | 2020-06-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-07-15 07:00 | Submittal Number: 05 12 00-224.1 From: BRAD KIRSCHENHEITER Final Due Date: 07/14/20 Subject: SEQUENCE 61G COOLING TOWER WEST PIPE CHASE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09016 | Forwarded | For Review | 2020-06-30 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-07 | Submittal Number: 05 12 00-224.1 From: BRAD KIRSCHENHEITER Final Due Date: 07/14/20 Subject: SEQUENCE 61G COOLING TOWER WEST PIPE CHASE Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09036 | Responded and Closed | Approved as Noted | 2020-07-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-30 |  | 05 12 00-224.1 Sequence 61G Cooling Tower West Pipe Chase (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-30 |  | 05 12 00-224.1 Sequence 61G Cooling Tower West Pipe Chase (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-01 |  | 05 12 00-224.1 Sequence 61G Cooling Tower West Pipe Chase-MAM_POP.pdf
05 12 00-229-00 | 05 12 00 - STEEL | 05 12 00-229-00 DAHU Platform and Gates - Sequence 74 & 74H | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Bryan Klote (Populous), Todd Spangler (Populous) |  |  |  | 2020-07-06 07:00 | 2020-07-17 | 29 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06503 | Received | For Review | 2020-06-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-06 07:00 | Submittal Number: 05 12 00-229.0 From: BRAD KIRSCHENHEITER Final Due Date: 07/02/20 Subject: DAHU PLATFORM AND GATES - SEQUENCE 74 & 74H Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08757 | Forwarded | For Review | 2020-06-18 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-25 | Submittal Number: 05 12 00-229.0 From: BRAD KIRSCHENHEITER Final Due Date: 07/02/20 Subject: DAHU PLATFORM AND GATES - SEQUENCE 74 & 74H Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 06669 | Review Response | Approved as Noted | 2020-06-26 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Channels to shift to align with posts throughout. Gates and connections of posts to steel not reviewed by TT. | Info Exchange
| 08981 | Forwarded | For Review | 2020-06-29 | Populous SCA_CCA | Bryan Klote (Populous); Todd Spangler (Populous) |  | Can you review the gates? Thanks Submittal Number: 05 12 00-229.0 From: BRAD KIRSCHENHEITER Final Due Date: 07/02/20 Subject: DAHU PLATFORM AND GATES - SEQUENCE 74 & 74H Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09387 | Responded and Closed | Approved as Noted | 2020-07-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 |  | 05 12 00-229.0 DAHU Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-18 |  | 05 12 00-229.0 DAHU Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-18 |  | 05 12 00-229.0 DAHU Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-18 |  | 05 12 00-229.0 DAHU Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-17 |  | 05 12 00-229.0 DAHU Steel SD-MAM_TT_POP.pdf
05 12 00-230-00 | 05 12 00 - STEEL | 05 12 00-230-00 SW Snorkel Steel Shop Drawings - Sequence 54G | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-06 | 2020-08-04 | 13 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07104 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-06 | Submittal Number: 05 12 00-230.0m: BRAD KIRSCHENHEITER Final Due Date: 08/03/20 Subject: SW SNORKEL STEEL SHOP DRAWINGS - SEQUENCE 54G Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN Fro | Info Exchange
| 09492 | Forwarded | For Review | 2020-07-23 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-30 | Submittal Number: 05 12 00-230.0m: BRAD KIRSCHENHEITER Final Due Date: 08/03/20 Subject: SW SNORKEL STEEL SHOP DRAWINGS - SEQUENCE 54G Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN Fro | Info Exchange
| 07340 | Review Response | Revise and Resubmit | 2020-07-31 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Revise pieces as noted. All other pieces are approved as noted. | Info Exchange
| 09788 | Responded and Closed | Approved as Noted | 2020-08-04 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 05 12 00-230.0 SW Snorkel Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-23 |  | 05 12 00-230.0 SW Snorkel Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-23 |  | 05 12 00-230.0 SW Snorkel Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-04 |  | 05 12 00-230.0 SW Snorkel Steel SD-MAM_TT_POP.pdf
05 12 00-231-00 | 05 12 00 - STEEL | 05 12 00-231-00 Roof Reinforcing Steel Adjustments at BRB Connections | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-28 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-14 07:00 | 2020-09-02 | 6 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07802 | Received | For Review | 2020-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company) | 2020-09-14 07:00 | Submittal Number: 05 12 00-231.0 From: BRAD KIRSCHENHEITER Final Due Date: 09/10/20 Subject: ROOF REINFORCING STEEL ADJUSTMENTS AT BRB CONNECTIONS Description: CHANGES AT THE ROOF BRB CONNECTIONS DUE TO FIELD SURVEY OF EXISTING CONDITIONS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 10380 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-03 | Submittal Number: 05 12 00-231.0 From: BRAD KIRSCHENHEITER Final Due Date: 09/10/20 Subject: ROOF REINFORCING STEEL ADJUSTMENTS AT BRB CONNECTIONS Description: CHANGES AT THE ROOF BRB CONNECTIONS DUE TO FIELD SURVEY OF EXISTING CONDITIONS. Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07896 | Review Response | Approved as Noted | 2020-08-31 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached submittal. | Info Exchange
| 10497 | Responded and Closed | Approved as Noted | 2020-09-02 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 05 12 00-231.0 Roof Reinforcing Steel Adjustments for BRBs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-27 |  | 05 12 00-231.0 Roof Reinforcing Steel Adjustments for BRBs-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-08-27 |  | 05 12 00-231.0 Roof Reinforcing Steel Adjustments for BRBs-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-02 |  | 05 12 00-231.0 Roof Reinforcing Steel Adjustments for BRBs-MAM_TT_POP.pdf
05 12 00-232-00 | 05 12 00 - STEEL | 05 12 00-232-00 Atrium Roof Halfen Detan Rods Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-11 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-25 | 2020-08-20 | 10 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07493 | Received | For Review | 2020-08-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-25 | Submittal Number: 05 12 00-232.0 From: BRAD KIRSCHENHEITER Final Due Date: 08/24/20 Subject: ATRIUM ROOF HALFEN DETAN RODS PRODUCT DATA Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09978 | Forwarded | For Review | 2020-08-10 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-17 | Submittal Number: 05 12 00-232.0 From: BRAD KIRSCHENHEITER Final Due Date: 08/24/20 Subject: ATRIUM ROOF HALFEN DETAN RODS PRODUCT DATA Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07640 | Review Response | Approved | 2020-08-17 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 10179 | Responded and Closed | Approved | 2020-08-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-10 |  | 05 12 00-232.0 Atrium Roof Halfen Detan Rods PD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-10 |  | 05 12 00-232.0 Atrium Roof Halfen Detan Rods PD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-10 |  | 05 12 00-232.0 Atrium Roof Halfen Detan Rods PD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-20 |  | 05 12 00-232.0 Atrium Roof Halfen Detan Rods PD-MAM_TT_POP.pdf
05 12 00-234-00 | 05 12 00 - STEEL | 05 12 00-234-00 Garage Steel MEP Frames for RFI 3074 Sustainability Changes | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-28 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-14 07:00 | 2020-09-15 | 19 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-09-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07803 | Received | For Review | 2020-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-14 07:00 | Submittal Number: 05 12 00-234.0 From: BRAD KIRSCHENHEITER Final Due Date: 09/10/20 Subject: GARAGE STEEL MEP FRAMES FOR RFI 3074 SUSTAINABILITY CHANGES Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 10381 | Forwarded | For Review | 2020-08-27 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-03 | Submittal Number: 05 12 00-234.0 From: BRAD KIRSCHENHEITER Final Due Date: 09/10/20 Subject: GARAGE STEEL MEP FRAMES FOR RFI 3074 SUSTAINABILITY CHANGES Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 07939 | Review Response | Approved as Noted | 2020-09-04 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Populous to verify opening geometry & paint requirements. TT has only reviewed clouded information. Refer to past submittal reviews for full review of sheets. | Info Exchange
| 10798 | Responded and Closed | Approved as Noted | 2020-09-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 05 12 00-234.0 Garage Steel MEP Frames RFI#3074-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-27 |  | 05 12 00-234.0 Garage Steel MEP Frames RFI#3074-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-08-27 |  | 05 12 00-234.0 Garage Steel MEP Frames RFI#3074-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-15 |  | 05 12 00-234.0 Garage Steel MEP Frames RFI#3074-MAM_TT_POP.pdf
05 12 00-235-00 | 05 12 00 - STEEL | 05 12 00-235-00 South Historic Curtainwall Support Steel Shop Drawings- Sequence 78 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-15 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-29 | 2020-09-29 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08098 | Received | For Review | 2020-09-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-29 | Submittal Number: 05 12 00-235.0 From: BRAD KIRSCHENHEITER Final Due Date: 09/28/20 Subject: SOUTH HISTORIC CURTAINWALL SUPPORT STEEL SHOP DRAWINGS- SEQUENCE 78 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 10763 | Forwarded | For Review | 2020-09-14 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-21 | Submittal Number: 05 12 00-235.0 From: BRAD KIRSCHENHEITER Final Due Date: 09/28/20 Subject: SOUTH HISTORIC CURTAINWALL SUPPORT STEEL SHOP DRAWINGS- SEQUENCE 78 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08413 | Review Response | Approved as Noted | 2020-09-28 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 11151 | Responded and Closed | Approved as Noted | 2020-09-29 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-14 |  | 05 12 00-235.0 South Curtainwall Support Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-14 |  | 05 12 00-235.0 South Curtainwall Support Steel SD-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-09-14 |  | 05 12 00-235.0 South Curtainwall Support Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-29 |  | 05 12 00-235.0 South Curtainwall Support Steel SD-MAM_TT_POP.pdf
05 12 00-236-00 | 05 12 00 - STEEL | 05 12 00-236-00 SE and SW Snorkel LED Board Steel Supports Shop Drawings - Seq. 53G & 54G | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-19 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-02 | 2020-11-04 | 17 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-11-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08843 | Received | For Review | 2020-10-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-11-02 | Submittal Number: 05 12 00-236.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/13/20 Subject: SE AND SW SNORKEL LED BOARD STEEL SUPPORTS SHOP DRAWINGS - SEQ. 53G & 54G Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 11686 | Forwarded | For Review | 2020-10-19 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-26 | Submittal Number: 05 12 00-236.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/13/20 Subject: SE AND SW SNORKEL LED BOARD STEEL SUPPORTS SHOP DRAWINGS - SEQ. 53G & 54G Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09185 | Review Response | Approved as Noted | 2020-10-29 | Raymond Chou (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 12187 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-04 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. Submit for record channel closure pieces as marked up. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-16 |  | 05 12 00-236.0 SE and SW Snorkel LED Support SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-16 |  | 05 12 00-236.0 SE and SW Snorkel LED Support SD-MAM.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2020-10-29 |  | 05 12 00-236.0 SE and SW Snorkel LED Support SD-MAM_TT REVIEWED.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-04 |  | 05 12 00-236.0 SE and SW Snorkel LED Support SD-MAM_TT_POP.pdf
05 12 00-236-01 | 05 12 00 - STEEL | 05 12 00-236-01 SE and SW Snorkel LED Board Steel Supports Shop Drawings - FOR RECORD | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-10 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-24 | 2020-11-13 | 4 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-11-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09344 | Received | For Review | 2020-11-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-11-24 | Submittal Number: 05 12 00-236.1 From: BRAD KIRSCHENHEITER Final Due Date: 11/24/20 Subject: SE AND SW SNORKEL LED BOARD STEEL SUPPORTS SHOP DRAWINGS - FOR RECORD Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 12325 | Forwarded | For Review | 2020-11-10 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-17 | Submittal Number: 05 12 00-236.1 From: BRAD KIRSCHENHEITER Final Due Date: 11/24/20 Subject: SE AND SW SNORKEL LED BOARD STEEL SUPPORTS SHOP DRAWINGS - FOR RECORD Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09411 | Review Response | No Action Taken or Required | 2020-11-12 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Retained for Record only. | Info Exchange
| 12416 | Responded and Closed | Approved as Noted | 2020-11-13 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-10 |  | 05 12 00-236.1 SE and SW Snorkel LED Board Steel Channel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-10 |  | 05 12 00-236.1 SE and SW Snorkel LED Board Steel Channel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-10 |  | 05 12 00-236.1 SE and SW Snorkel LED Board Steel Channel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-13 |  | 05 12 00-236.1 SE and SW Snorkel LED Board Steel Channel SD-MAM_POP.pdf
05 12 00-237-00 | 05 12 00 - STEEL | 05 12 00-237-00 Center Roof Reinforcing Shop Drawings - Seq. 13 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-12 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-26 | 2020-10-20 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-10-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08720 | Received | For Review | 2020-10-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-26 | Submittal Number: 05 12 00-237.0 From: JES PELKEY Final Due Date: 10/23/20 Subject: CENTER ROOF REINFORCING SHOP DRAWINGS - SEQ. 13 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 11516 | Forwarded | For Review | 2020-10-12 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-19 | Submittal Number: 05 12 00-237.0 From: JES PELKEY Final Due Date: 10/23/20 Subject: CENTER ROOF REINFORCING SHOP DRAWINGS - SEQ. 13 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 08869 | Review Response | Approved as Noted | 2020-10-20 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Populous to review painting requirements on page 5 of submittal. | Info Exchange
| 11726 | Responded and Closed | Approved as Noted | 2020-10-20 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-12 |  | 05 12 00-237.0 Center Roof Reinforcing SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-12 |  | 05 12 00-237.0 Center Roof Reinforcing SD-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-10-12 |  | 05 12 00-237.0 Center Roof Reinforcing SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-20 |  | 05 12 00-237.0 Center Roof Reinforcing SD-MAM_TT_POP.pdf
05 12 00-238-00 | 05 12 00 - STEEL | 05 12 00-238-00 CCD78 Added Steel for SEDA Platform | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-05 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-19 | 2020-11-18 | 14 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09245 | Received | For Review | 2020-11-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-11-19 | Submittal Number: 05 12 00-238.0 From: JES PELKEY Final Due Date: 11/19/20 Subject: CCD78 ADDED STEEL FOR SEDA PLATFORM Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 12201 | Forwarded | For Review | 2020-11-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-12 | Submittal Number: 05 12 00-238.0 From: JES PELKEY Final Due Date: 11/19/20 Subject: CCD78 ADDED STEEL FOR SEDA PLATFORM Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09534 | Review Response | Approved as Noted | 2020-11-13 | Raymond Chou (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 12553 | Responded and Closed | Approved as Noted | 2020-11-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-05 |  | 05 12 00-238.0 CCD78 Added Steel for SEDA Platform SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-05 |  | 05 12 00-238.0 CCD78 Added Steel for SEDA Platform SD-MAM.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2020-11-13 |  | 05 12 00-238.0 CCD78 Added Steel for SEDA Platform SD-MAM_TT REVIEWED.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-18 |  | 032000-0067 SEDA Area B Additional Footings Columns Deck_TT REVIEWED-POP.pdf
05 12 00-239-00 | 05 12 00 - STEEL | 05 12 00-239-00 Crown Signage Roof Support Steel Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-12 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-26 | 2020-11-12 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-11-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09398 | Received | For Review | 2020-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-11-26 | Submittal Number: 05 12 00-239.0 From: JES PELKEY Final Due Date: 11/16/20 Subject: CROWN SIGNAGE ROOF SUPPORT STEEL SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 12401 | Forwarded | For Review | 2020-11-12 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-19 | Submittal Number: 05 12 00-239.0 From: JES PELKEY Final Due Date: 11/16/20 Subject: CROWN SIGNAGE ROOF SUPPORT STEEL SHOP DRAWINGS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 09404 | Review Response | Approved as Noted | 2020-11-12 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 12408 | Responded and Closed | Approved as Noted | 2020-11-12 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-12 |  | 05 12 00-239.0 Crown Sign Roof Support Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-12 |  | 05 12 00-239.0 Crown Sign Roof Support Steel SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-12 |  | 05 12 00-239.0 Crown Sign Roof Support Steel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-12 |  | 05 12 00-239.0 Crown Sign Roof Support Steel SD-MAM_TT_POP.pdf
05 12 00-240-00 | 05 12 00 - STEEL | 05 12 00-240-00 Sequence 96 & 96G Security Office - CCD079 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-04 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-18 | 2020-12-15 | 12 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09893 | Received | For Review | 2020-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-18 | Submittal Number: 05 12 00-240.0 From: BRAD KIRSCHENHEITER Final Due Date: 12/17/20 Subject: SEQUENCE 96 & 96G SECURITY OFFICE - CCD079 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 12977 | Forwarded | For Review | 2020-12-03 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-10 | Submittal Number: 05 12 00-240.0 From: BRAD KIRSCHENHEITER Final Due Date: 12/17/20 Subject: SEQUENCE 96 & 96G SECURITY OFFICE - CCD079 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 10162 | Review Response | Approved as Noted | 2020-12-15 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  | - TT has not reviewed erection aids and erection field bolts. - Arch to comment on galvanized finish and steel - Arch to confirm steel elevations/location in plan and locations of grating | Info Exchange
| 13298 | Responded and Closed | Approved as Noted | 2020-12-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-03 |  | 05 12 00-240.0 Seq 96 & 96G Security Office CCD079 SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-03 |  | 05 12 00-240.0 Seq 96 & 96G Security Office CCD079 SD-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-12-03 |  | 05 12 00-240.0 Seq 96 & 96G Security Office CCD079 SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-15 |  | 05 12 00-240.0 Seq 96 & 96G Security Office CCD079 SD-MAM_TT_POP.pdf
05 12 00-241-00 | 05 12 00 - STEEL | 05 12 00-241-00 CCD78 LED Pole Steel SD - Seq 100 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-03 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-17 | 2020-12-10 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09873 | Received | For Review | 2020-12-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-17 | Submittal Number: 05 12 00-241.0 From: BRAD KIRSCHENHEITER Final Due Date: 12/17/20 Subject: CCD78 LED POLE STEEL SD - SEQ 100 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 12956 | Forwarded | For Review | 2020-12-03 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-10 | Submittal Number: 05 12 00-241.0 From: BRAD KIRSCHENHEITER Final Due Date: 12/17/20 Subject: CCD78 LED POLE STEEL SD - SEQ 100 Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 10085 | Review Response | Approved as Noted | 2020-12-10 | Raymond Chou (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 13183 | Responded and Closed | Approved as Noted | 2020-12-10 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-03 |  | 05 12 00-241.0 CCD078 LED Pole SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-03 |  | 05 12 00-241.0 CCD078 LED Pole SD-MAM.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2020-12-10 |  | 05 12 00-241.0 CCD078 LED Pole SD-MAM_TT Reviewed.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-10 |  | 05 12 00-241.0 CCD078 LED Pole SD-MAM_TT_POP.pdf
05 12 00-242-00 | 05 12 00 - STEEL | 05 12 00-242-00 CCD078 LED Pole Steel Shop Drawings - McClean | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-22 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-14 | 2021-01-06 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-01-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10325 | Received | For Review | 2020-12-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-14 | Submittal Number: 05 12 00-242.0 From: JES PELKEY Final Due Date: 01/06/21 Subject: CCD078 LED POLE STEEL SHOP DRAWINGS - MCCLEAN Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 13489 | Forwarded | For Review | 2020-12-22 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-29 | Submittal Number: 05 12 00-242.0 From: JES PELKEY Final Due Date: 01/06/21 Subject: CCD078 LED POLE STEEL SHOP DRAWINGS - MCCLEAN Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 10479 | Review Response | Approved as Noted | 2021-01-05 | Raymond Chou (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 13678 | Responded and Closed | Approved | 2021-01-06 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-22 |  | 05 12 00-242.0 CCD078 LED Pole Steel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-22 |  | 05 12 00-242.0 CCD078 LED Pole Steel SD-MAM.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2021-01-05 |  | 05 12 00-242.0 CCD078 LED Pole Steel SD-MAM_TT REVIEWED.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-06 |  | 05 12 00-242.0 CCD078 LED Pole Steel SD-MAM_TT_POP.pdf
05 12 00-243-00 | 05 12 00 - STEEL | 05 12 00-243-00 Seq. 426/427 Atrium Columns - 41531C and 41798C FOR RECORD | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-09 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-23 | 2020-12-10 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10043 | Received | For Review | 2020-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Jes Pelkey (M.A. Mortenson Company) | 2020-12-23 | Submittal Number: 05 12 00-243.0 From: JES PELKEY Final Due Date: 12/22/20 Subject: SEQ. 426/427 ATRIUM COLUMNS - 41531C AND 41798C FOR RECORD Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 13141 | Forwarded | For Review | 2020-12-09 | Jes Pelkey (M.A. Mortenson Company) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-16 | Submittal Number: 05 12 00-243.0 From: JES PELKEY Final Due Date: 12/22/20 Subject: SEQ. 426/427 ATRIUM COLUMNS - 41531C AND 41798C FOR RECORD Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 10083 | Review Response | Approved as Noted | 2020-12-09 | Matt Ross (Thornton Tomasetti) | Jes Pelkey (M.A. Mortenson Company) |  |  | Info Exchange
| 13181 | Responded and Closed | Approved as Noted | 2020-12-10 | Jes Pelkey (M.A. Mortenson Company) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-08 |  | 05 12 00-243.0 Seq.426-427 Atrium Columns For Record-MAM.pdf
| Forwarded |  | Jes Pelkey (Mortenson Construction) | 1 | 2020-12-08 |  | 05 12 00-243.0 Seq.426-427 Atrium Columns For Record-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-08 |  | 05 12 00-243.0 Seq.426-427 Atrium Columns For Record-MAM.pdf
| Responded and Closed |  | Jes Pelkey (Mortenson Construction) | 1 | 2020-12-10 |  | 05 12 00-243.0 Seq.426-427 Atrium Columns For Record-MAM_TT_POP.pdf
05 12 00-244-00 | 05 12 00 - STEEL | 05 12 00-244-00 Generator Enclosure Wind Screen | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-17 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-31 | 2021-03-29 | 13 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12057 | Received | For Review | 2021-03-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-03-31 | Submittal Number: 05 12 00-244.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/30/21 Subject: GENERATOR ENCLOSURE WIND SCREEN Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 15613 | Forwarded | For Review | 2021-03-16 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-23 | Submittal Number: 05 12 00-244.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/30/21 Subject: GENERATOR ENCLOSURE WIND SCREEN Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 12278 | Review Response | Approved as Noted/Resubmit | 2021-03-26 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Approved as noted, submit product data for record as noted on submittal. TT-FK ¦ 2021-03-26 | Info Exchange
| 15902 | Responded and Closed | Approved as Noted | 2021-03-29 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-16 |  | Generator Enclosure Approval Package (Seq 102)_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-16 |  | Generator Enclosure Approval Package (Seq 102)_MAM Review.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-03-16 |  | Generator Enclosure Approval Package (Seq 102)_MAM Review.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-03-29 |  | 05 12 00-244.0 Generator Enclosure Approval Package (Seq 102)_MAM_TT_POP.pdf
05 12 00-245-00 | 05 12 00 - STEEL | 05 12 00-245-00 Catwalk Added Channels Due to Electrical Loads | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-10 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-24 | 2021-05-17 | 8 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-05-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13017 | Received | For Review | 2021-05-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-24 | Submittal Number: 05 12 00-245.0 From: JES PELKEY Final Due Date: 05/21/21 Subject: CATWALK ADDED CHANNELS DUE TO ELECTRICAL LOADS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 16845 | Forwarded | For Review | 2021-05-10 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-17 | Submittal Number: 05 12 00-245.0 From: JES PELKEY Final Due Date: 05/21/21 Subject: CATWALK ADDED CHANNELS DUE TO ELECTRICAL LOADS Description: Spec Section: 05 12 00 - STRUCTURAL STEEL Status: OPEN | Info Exchange
| 13117 | Review Response | Approved as Noted | 2021-05-12 | Raymond Chou (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 16969 | Responded and Closed | Approved as Noted | 2021-05-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 05 12 00-245.0 Catwalk Added Channels SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-10 |  | 05 12 00-245.0 Catwalk Added Channels SD-MAM.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2021-05-12 |  | 05 12 00-245.0 Catwalk Added Channels SD-MAM_TT REVIEWED.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-17 |  | 05 12 00-245.0 Catwalk Added Channels SD-MAM_TT_POP.pdf
05 12 10-001-00 | 05 12 10 - STRUCTURAL STEEL FRAMING - SEISMIC-WR-MRF | 05 12 10-001-00 Roof Strengthening Steel - Hanging Scaffold Design Initial Submittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-25 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-08 | 2019-08-01 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-08-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01886 | Received | For Review | 2019-07-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC) | 2019-08-08 | Submittal Number: 05 12 10-CA-001.0 From: NATE WEINGART Final Due Date: 08/09/19 Subject: ROOF STRENGTHENING STEEL - HANGING SCAFFOLD DESIGN INITIAL SUBMITTAL Description: Spec Section: 05 12 10 - STRUCTURAL STEEL - ADDITIONAL SEISMIC REQUIREMENTS Status: OPEN | Info Exchange
| 03024 | Forwarded | For Review | 2019-07-26 | . (Seattle Arena Company, LLC) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-02 | Submittal Number: 05 12 10-CA-001.0 From: NATE WEINGART Final Due Date: 08/09/19 Subject: ROOF STRENGTHENING STEEL - HANGING SCAFFOLD DESIGN INITIAL SUBMITTAL Description: Spec Section: 05 12 10 - STRUCTURAL STEEL - ADDITIONAL SEISMIC REQUIREMENTS Status: OPEN | Info Exchange
| 01946 | Review Response | Revise and Resubmit | 2019-08-01 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Hanging scaffolding and roof reinforcement details were discussed at client meeting on 7/31. A meeting will be set up week of 8/5 between TT, Mort, Pop and Icon to discuss this topic and next steps. Information provided is not sufficient to determine impact on roof and will be on agenda in upcoming meeting. | Info Exchange
| 03093 | Responded and Closed | Revise and Resubmit | 2019-08-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Hanging scaffolding and roof reinforcement details were discussed at client meeting on 7/31. A meeting will be set up week of 8/5 between TT, Mort, Pop and Icon to discuss this topic and next steps. Information provided is not sufficient to determine impact on roof and will be on agenda in upcoming meeting. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-25 02:00 |  | 051210-CA-001.0 Scaffold Design Initial Submittal (MAM Review).pdf
| Forwarded |  | . (Seattle Arena Company, LLC) | 1 | 2019-07-25 02:00 |  | 051210-CA-001.0 Scaffold Design Initial Submittal (MAM Review).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-07-25 |  | 051210-CA-001.0 Scaffold Design Initial Submittal (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-07-25 |  | 051210-CA-001.0 Scaffold Design Initial Submittal (MAM Review).pdf
05 12 10-001-01 | 05 12 10 - STRUCTURAL STEEL FRAMING - SEISMIC-WR-MRF | 05 12 10-001-01 Roof Strengthening Steel - Hanging Scaffold Design Initial Submittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-05 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-19 | 2019-08-15 | 11 |  | Record Copies; Transfers; Submittals | 05 12 10-001-02 - 05 12 10-001-01 Roof Strengthening Steel - Hanging Scaffold Design Initial Submittal | 8 |  | 2019-08-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01998 | Received | For Review | 2019-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-08-19 | Submittal Number: 05 12 10-CA-001.1 From: NATE WEINGART Final Due Date: 08/09/19 Subject: ROOF STRENGTHENING STEEL - HANGING SCAFFOLD DESIGN INITIAL SUBMITTAL Description: Spec Section: 05 12 10 - STRUCTURAL STEEL - ADDITIONAL SEISMIC REQUIREMENTS Status: OPEN | Info Exchange
| 03151 | Forwarded | For Review | 2019-08-08 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-15 | Submittal Number: 05 12 10-CA-001.1 From: NATE WEINGART Final Due Date: 08/09/19 Subject: ROOF STRENGTHENING STEEL - HANGING SCAFFOLD DESIGN INITIAL SUBMITTAL Description: Spec Section: 05 12 10 - STRUCTURAL STEEL - ADDITIONAL SEISMIC REQUIREMENTS Status: OPEN | Info Exchange
| 03605 | Responded and Closed | Revise and Resubmit | 2019-08-15 | Josh Dobken (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Backdating the closing of this submittal to match Procore comments dated 8/15: "API to change attachment detail based on TT comments in 8/6 design meeting." | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-05 |  | 051210-CA-001.1 Scaffold Design Initial Submittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-05 |  | 051210-CA-001.1 Scaffold Design Initial Submittal (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-04 02:00 |  | 051210-CA-001.1 Scaffold Design Initial Submittal (MAM Review).pdf
05 12 10-001-02 | 05 12 10 - STRUCTURAL STEEL FRAMING - SEISMIC-WR-MRF | 05 12 10-001-01 Roof Strengthening Steel - Hanging Scaffold Design Initial Submittal | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 12 10-001-01 - 05 12 10-001-01 Roof Strengthening Steel - Hanging Scaffold Design Initial Submittal | -1 | 2019-08-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-04 02:00 |  | 051210-CA-001.1 Scaffold Design Initial Submittal (MAM Review).pdf
05 30 00-008-00 | 05 30 00 - STEEL DECK | 05 30 00-008-00 Quad D Decking Shop Drawings | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-07 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-11-21 | 2019-11-26 | 20 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-11-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03106 | Received | For Review | 2019-11-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-11-21 | Submittal Number: 05 30 00-8.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/21/19 Subject: QUAD D DECKING SHOP DRAWINGS Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 04509 | Forwarded | For Review | 2019-11-07 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-14 | Submittal Number: 05 30 00-8.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/21/19 Subject: QUAD D DECKING SHOP DRAWINGS Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 03346 | Review Response | Approved as Noted/Resubmit | 2019-11-22 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | See stamps on sheets for which sheets TT needs to review again once revised. All other sheets are approved as noted. Arch to review indicated dimensions. | Info Exchange
| 04834 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-06 |  | 05 30 00-8.0 Quad D Decking-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-06 |  | 05 30 00-8.0 Quad D Decking-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-06 |  | 05 30 00-8.0 Quad D Decking-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-11-25 |  | 05 30 00-8.0 Quad D Decking-MAM_TT_POP.pdf
05 30 00-008-01 | 05 30 00 - STEEL DECK | 05 30 00-008-01 Quad D Decking Resubmittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-11 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04225 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-02-20 | Submittal Number: 05 30 00-8.1 From: BRAD KIRSCHENHEITER Final Due Date: 02/20/20 Subject: QUAD D DECKING RESUBMITTAL Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 05853 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 05 30 00-8.1 From: BRAD KIRSCHENHEITER Final Due Date: 02/20/20 Subject: QUAD D DECKING RESUBMITTAL Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 04310 | Review Response | Approved as Noted | 2020-02-07 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 05974 | Responded and Closed | Approved as Noted | 2020-02-11 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review and comments. Revisions around stair D1 is required per the stair submittal. MAM to coordinate revisions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 05 30 00-8.1 Quad D Decking Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | 05 30 00-8.1 Quad D Decking Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-06 |  | 05 30 00-8.1 Quad D Decking Resubmittal (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-11 |  | 05 30 00-8.1 Quad D Decking Resubmittal (MAM Review)_TT_POP.pdf
05 30 00-009-00 | 05 30 00 - STEEL DECK | 05 30 00-009-00 Quad C Metal Decking Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-25 | 2020-03-12 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-03-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04753 | Received | For Review | 2020-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-25 | Submittal Number: 05 30 00-9.0 From: NATE WEINGART Final Due Date: 03/25/20 Subject: QUAD C METAL DECKING SHOP DRAWINGS Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 06524 | Forwarded | For Review | 2020-03-10 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-17 | Submittal Number: 05 30 00-9.0 From: NATE WEINGART Final Due Date: 03/25/20 Subject: QUAD C METAL DECKING SHOP DRAWINGS Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 04791 | Review Response | Approved as Noted | 2020-03-11 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06569 | Responded and Closed | Approved as Noted | 2020-03-12 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-10 |  | 053000-9.0 Quad C Metal Decking Shop Drawings (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-10 |  | 053000-9.0 Quad C Metal Decking Shop Drawings (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-10 |  | 053000-9.0 Quad C Metal Decking Shop Drawings (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-12 |  | 053000-9.0 Quad C Metal Decking Shop Drawings_MAM_TT_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-12 |  | A1-43 - SLAB PLAN - MAIN CONCOURSE LEVEL.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-12 |  | A1-44 - SLAB PLAN - SUITE LEVEL.pdf
05 30 00-010-00 | 05 30 00 - STEEL DECK | 05 30 00-010-00 Quad A Steel Decking Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-30 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-14 | 2020-04-17 | 19 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-04-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05100 | Received | For Review | 2020-03-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-04-14 | Submittal Number: 05 30 00-10.0 From: NATE WEINGART Final Due Date: 04/10/20 Subject: QUAD A STEEL DECKING SHOP DRAWINGS Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 06928 | Forwarded | For Review | 2020-03-30 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-06 | Submittal Number: 05 30 00-10.0 From: NATE WEINGART Final Due Date: 04/10/20 Subject: QUAD A STEEL DECKING SHOP DRAWINGS Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 05381 | Review Response | Approved as Noted | 2020-04-14 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 07337 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-17 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and response. Seems like there were a lot of framing dims off. The upper concourse background is old atrium design. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-27 |  | 053000-10.0 Area A Metal Decking Shop Drawings (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-27 |  | 053000-10.0 Area A Metal Decking Shop Drawings (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-27 |  | 053000-10.0 Area A Metal Decking Shop Drawings (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-17 |  | 053000-10.0 Area A Metal Decking Shop Drawings-MAM_TT_POP.pdf
05 30 00-010-01 | 05 30 00 - STEEL DECK | 05 30 00-010-01 Quad A Steel Decking SD Resubmittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-26 07:00 | 2020-05-19 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05795 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 05 30 00-10.1 From: NATE WEINGART Final Due Date: 05/22/20 Subject: QUAD A STEEL DECKING SD RESUBMITTAL Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 07858 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-18 | Submittal Number: 05 30 00-10.1 From: NATE WEINGART Final Due Date: 05/22/20 Subject: QUAD A STEEL DECKING SD RESUBMITTAL Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 05926 | Review Response | Approved as Noted | 2020-05-19 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08048 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-19 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 053000-10.1 Quad A Steel Decking SD Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 053000-10.1 Quad A Steel Decking SD Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-11 |  | 053000-10.1 Quad A Steel Decking SD Resubmittal (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-19 |  | 053000-10.1 Quad A Steel Decking SD Resubmittal (MAM Review)_TT_POP.pdf
05 30 00-010-02 | 05 30 00 - STEEL DECK | 05 30 00-010-02 Quad A Upper Concourse Resubmittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-02 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-16 | 2020-06-15 | 14 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06134 | Received | For Review | 2020-06-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-06-16 | Submittal Number: 05 30 00-10.2 From: NATE WEINGART Final Due Date: 06/15/20 Subject: QUAD A UPPER CONCOURSE RESUBMITTAL Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 08297 | Forwarded | For Review | 2020-06-01 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-08 | Submittal Number: 05 30 00-10.2 From: NATE WEINGART Final Due Date: 06/15/20 Subject: QUAD A UPPER CONCOURSE RESUBMITTAL Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 06408 | Review Response | Approved as Noted | 2020-06-11 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08629 | Responded and Closed | Approved as Noted | 2020-06-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-01 |  | 053000-10.2 Quad A Upper Concourse Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-01 |  | 053000-10.2 Quad A Upper Concourse Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-01 |  | 053000-10.2 Quad A Upper Concourse Resubmittal (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-15 |  | 053000-10.2 Quad A Upper Concourse Resubmittal-MAM_TT_POP.pdf
05 30 00-011-00 | 05 30 00 - STEEL DECK | 05 30 00-011-00 Quad F Deck Approval Package | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-17 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-03-02 | 2020-03-03 | 16 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04383 | Received | For Review | 2020-02-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Will Traylor (M.A. Mortenson Company); Jes Pelkey (M.A. Mortenson Company) | 2020-03-02 | Submittal Number: 05 30 00-11.0 From: BRAD KIRSCHENHEITER Final Due Date: 11/19/19 Subject: QUAD F DECK APPROVAL PACKAGE Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 06056 | Responded and Closed | Rejected | 2020-02-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please review submittal procedures (01 33 00, section 1.5 D) and resubmit as a single PDF package with Mortenson stamp sheet stamped at front. | Info Exchange
| 06070 | Reopened | Additional Information | 2020-02-18 14:47 | Josh Dobken (Populous) |  |  | Reopened - Attachments required were included. Forwarding to be reviewed.
| 06071 | Forwarded | For Review | 2020-02-18 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-02-25 | Submittal Number: 05 30 00-11.0 From: WILL TRAYLOR Final Due Date: 11/19/19 Subject: QUAD F DECK APPROVAL PACKAGE Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 04620 | Review Response | Approved as Noted/Resubmit | 2020-03-02 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 06365 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-03 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | See attached for review and comments | Info Exchange
| 06673 | Sent | For Construction | 2020-03-17 | Josh Dobken (Populous) | Jes Pelkey (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted/Resubmit) to: Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) Remarks: See attached for review and comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | 053000-11 Quad F Deck SD's - Mort Reviewed.PDF
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | 12.11.19 Additional West TB Failures.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | 20.01.15- G.1 Shear Wall Reinforcing.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | 2020.01.15 M2-5.5A grilles emailed question.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | A1-01_ EVENT LEVEL - HUB DRAIN LOCATION.PDF
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | Al. Sliding Doors.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | C200_ UTILITY PLAN SEATTLE CENTER ARENA Rev.8.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | HC-RFI-064 CDW Piping Tunnel to Garage.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | HPI-013 RFI 1399 Grease duct plan.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | P2-1A-EVENT-LEVEL-PLUMBING---AREA-A-Rev.7.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | P2-1B-EVENT-LEVEL-PLUMBING---AREA-B-Rev.4.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | P2-1C-EVENT-LEVEL-PLUMBING---AREA-C-Rev.7.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | P2-1D-EVENT-LEVEL-PLUMBING---AREA-D-Rev.6.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | Parking Garage MEP Distance off of Steel.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | Quad F Vehicle Barrier Clarifications - SCA LSC RFI #141.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RE Additional West TB Failures.msg
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RE Level 300 B Additional Beam Penetrations.msg
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RE West Wall Replacement Anchors.msg
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RE_ SCA ERS North Portal Grout and Lateral Connection.msg
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 1790 - Attachment.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 1791 - Attachment.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 1794 - Attachment.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 1899 - Response.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 190 - Multiple Power Sources for Fire Pump.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 1904 - Attachment.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 191 - Grounding and Spacers in Duct Banks.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 192 - Exterior Paint on Vaults.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 221 - Lower Bowl Underseat Wifi.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 228 - Fire Alarm Identification Spec Change.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 231 - Missing Elevation and Speaker for SW Event Level Wall.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI 233 - L16 Lights on Main Concourse.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI TOS-Snorkels.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | RFI-058 Louver Coordination 11.14.19.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | SCA LSC RFI #103.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | SCA LSC RFI #105.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | SCA LSC RFI #106.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | SCA LSC RFI #108.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | SCA LSC RFI #109.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | SCA LSC RFI #135.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | SCA LSC RFI #138.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | SCA LSC RFI #161.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | 053000-11 Quad F Deck SD's - Mort Reviewed.PDF
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | 12.11.19 Additional West TB Failures.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | 20.01.15- G.1 Shear Wall Reinforcing.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | 2020.01.15 M2-5.5A grilles emailed question.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | A1-01_ EVENT LEVEL - HUB DRAIN LOCATION.PDF
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | Al. Sliding Doors.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | C200_ UTILITY PLAN SEATTLE CENTER ARENA Rev.8.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | HC-RFI-064 CDW Piping Tunnel to Garage.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | HPI-013 RFI 1399 Grease duct plan.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | P2-1A-EVENT-LEVEL-PLUMBING---AREA-A-Rev.7.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | P2-1B-EVENT-LEVEL-PLUMBING---AREA-B-Rev.4.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | P2-1C-EVENT-LEVEL-PLUMBING---AREA-C-Rev.7.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | P2-1D-EVENT-LEVEL-PLUMBING---AREA-D-Rev.6.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | Parking Garage MEP Distance off of Steel.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | Quad F Vehicle Barrier Clarifications - SCA LSC RFI #141.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RE Additional West TB Failures.msg
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RE Level 300 B Additional Beam Penetrations.msg
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RE West Wall Replacement Anchors.msg
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RE_ SCA ERS North Portal Grout and Lateral Connection.msg
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 1790 - Attachment.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 1791 - Attachment.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 1794 - Attachment.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 1899 - Response.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 190 - Multiple Power Sources for Fire Pump.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 1904 - Attachment.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 191 - Grounding and Spacers in Duct Banks.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 192 - Exterior Paint on Vaults.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 221 - Lower Bowl Underseat Wifi.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 228 - Fire Alarm Identification Spec Change.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 231 - Missing Elevation and Speaker for SW Event Level Wall.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI 233 - L16 Lights on Main Concourse.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI TOS-Snorkels.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | RFI-058 Louver Coordination 11.14.19.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | SCA LSC RFI #103.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | SCA LSC RFI #105.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | SCA LSC RFI #106.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | SCA LSC RFI #108.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | SCA LSC RFI #109.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | SCA LSC RFI #135.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | SCA LSC RFI #138.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | SCA LSC RFI #161.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | 053000-11 Quad F Deck SD's - Mort Reviewed.PDF
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-02-16 |  | 053000-11 Quad F Deck SD's - Mort Reviewed.PDF
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-03 |  | 053000-11 Quad F Deck SD's - MAM_TT_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-02-16 02:00 |  | 053000-11 Quad F Deck SD's - Mort Reviewed.PDF
05 30 00-011-01 | 05 30 00 - STEEL DECK | 05 30 00-011-01 Area F Ticket Office Roof Decking Resubmittal | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-18 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-02 07:00 | 2020-06-04 | 18 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05892 | Received | For Review | 2020-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-06-02 07:00 | Submittal Number: 05 30 00-11.1 From: NATE WEINGART Final Due Date: 05/29/20 Subject: AREA F TICKET OFFICE ROOF DECKING RESUBMITTAL Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 07992 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-25 | Submittal Number: 05 30 00-11.1 From: NATE WEINGART Final Due Date: 05/29/20 Subject: AREA F TICKET OFFICE ROOF DECKING RESUBMITTAL Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 06193 | Review Response | Approved as Noted | 2020-05-31 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08371 | Responded and Closed | Approved as Noted | 2020-06-04 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and comments. There seems to be a lot of confusion here with the correct details and dimensions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-15 |  | 053000-11.1 Area F Ticket Office Roof Decking Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-15 |  | 053000-11.1 Area F Ticket Office Roof Decking Resubmittal (MAM Review).pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-05-15 |  | 053000-11.1 Area F Ticket Office Roof Decking Resubmittal (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-04 |  | 053000-11.1 Area F Ticket Office Roof Decking Resubmittal_TT_POP.pdf
05 30 00-012-00 | 05 30 00 - STEEL DECK | 05 30 00-012-00 Area E Metal Decking Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-30 | 2020-03-24 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04863 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 05 30 00-12.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/27/20 Subject: AREA E METAL DECKING SHOP DRAWINGS Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 06643 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-23 | Submittal Number: 05 30 00-12.0 From: BRAD KIRSCHENHEITER Final Due Date: 03/27/20 Subject: AREA E METAL DECKING SHOP DRAWINGS Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 06827 | Responded and Closed | Approved as Noted | 2020-03-24 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached review and comments. Send design team RFI's for slab edge coordination and CMU wall support detail. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 053000-12.0 Area E Metal Decking Shop Drawings (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 053000-12.0 Area E Metal Decking Shop Drawings (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-24 |  | 053000-12.0 Area E Metal Decking Shop Drawings_MAM_TT_POP.pdf
05 30 00-013-0 | 05 30 00 - STEEL DECK | 05 30 00-013-0 Deck Installer Specific Detail - Field Conditions | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-16 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-30 | 2020-06-25 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06432 | Received | For Review | 2020-06-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-30 | Submittal Number: 05 30 00-13.0 From: BRAD KIRSCHENHEITER Final Due Date: 06/30/20 Subject: DECK INSTALLER SPECIFIC DETAIL - FIELD CONDITIONS Description: DETAILS FOR DECK INSTALLERS PREFERRED METHOD OF HANDLING LESS COMMON INSTALL ISSUES THAT ARE NOT COVERED IN THE DECK SUPPLIERS DRAWINGS. Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 08670 | Forwarded | For Review | 2020-06-16 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-23 | Submittal Number: 05 30 00-13.0 From: BRAD KIRSCHENHEITER Final Due Date: 06/30/20 Subject: DECK INSTALLER SPECIFIC DETAIL - FIELD CONDITIONS Description: DETAILS FOR DECK INSTALLERS PREFERRED METHOD OF HANDLING LESS COMMON INSTALL ISSUES THAT ARE NOT COVERED IN THE DECK SUPPLIERS DRAWINGS. Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 06597 | Review Response | Approved | 2020-06-24 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 08892 | Responded and Closed | Approved | 2020-06-25 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-16 |  | 05 30 00-13.0 Deck Field Conditions Details -MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-16 |  | 05 30 00-13.0 Deck Field Conditions Details -MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-16 |  | 05 30 00-13.0 Deck Field Conditions Details -MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-25 |  | 05 30 00-13.0 Deck Field Conditions Details -MAM_TT_POP.pdf
05 30 00-014-00 | 05 30 00 - STEEL DECK | 05 30 00-014-00 Area B Metal Decking Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-13 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-27 | 2020-04-28 | 16 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05293 | Received | For Review | 2020-04-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-04-27 | Submittal Number: 05 30 00-14.0 From: NATE WEINGART Final Due Date: 04/27/20 Subject: AREA B METAL DECKING SHOP DRAWINGS Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 07201 | Forwarded | For Review | 2020-04-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-20 | Submittal Number: 05 30 00-14.0 From: NATE WEINGART Final Due Date: 04/27/20 Subject: AREA B METAL DECKING SHOP DRAWINGS Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 05607 | Review Response | Approved as Noted/Resubmit | 2020-04-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Revise and Resubmit SW Snorkel areas once West Temp Ramp revisions have been finalized and issued. All other areas are approved as noted. | Info Exchange
| 07607 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-28 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-11 |  | 053000-14.0 Area B Metal Decking Shop Drawings (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-11 |  | 053000-14.0 Area B Metal Decking Shop Drawings (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-11 |  | 053000-14.0 Area B Metal Decking Shop Drawings (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-28 |  | 053000-14.0 Area B Metal Decking Shop Drawings-MAM_TT_POP.pdf
05 30 00-014-01 | 05 30 00 - STEEL DECK | 05 30 00-014-01 Area B Deck Resubmittal - SW Snorkel | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-30 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-13 | 2020-08-06 | 8 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07257 | Received | For Review | 2020-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-13 | Submittal Number: 05 30 00-14.1 From: JES PELKEY Final Due Date: 08/12/20 Subject: AREA B DECK RESUBMITTAL - SW SNORKEL Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 09669 | Forwarded | For Review | 2020-07-30 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-06 | Submittal Number: 05 30 00-14.1 From: JES PELKEY Final Due Date: 08/12/20 Subject: AREA B DECK RESUBMITTAL - SW SNORKEL Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 07358 | Review Response | Approved as Noted | 2020-08-04 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 09864 | Responded and Closed | Approved as Noted | 2020-08-06 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-29 |  | 05 30 00-14.1 Area B Metal Decking SD RR- MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-29 |  | 05 30 00-14.1 Area B Metal Decking SD RR- MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-29 |  | 05 30 00-14.1 Area B Metal Decking SD RR- MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-06 |  | 05 30 00-14.1 Area B Metal Decking SD RR- MAM_TT_POP.pdf
05 30 00-015-00 | 05 30 00 - STEEL DECK | 05 30 00-015-00 Quad A & B Atrium Decking Shop Drawing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-06 | 2020-07-31 | 9 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07105 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-06 | Submittal Number: 05 30 00-15.0 From: JES PELKEY Final Due Date: 08/05/20 Subject: QUAD A & B ATRIUM DECKING SHOP DRAWING Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 09493 | Forwarded | For Review | 2020-07-23 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-30 | Submittal Number: 05 30 00-15.0 From: JES PELKEY Final Due Date: 08/05/20 Subject: QUAD A & B ATRIUM DECKING SHOP DRAWING Description: Spec Section: 05 30 00 - STEEL DECK Status: OPEN | Info Exchange
| 07280 | Review Response | Approved | 2020-07-27 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 09700 | Responded and Closed | Approved as Noted | 2020-07-31 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 05 30 00-15.0 Atrium Decking SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-23 |  | 05 30 00-15.0 Atrium Decking SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-23 |  | 05 30 00-15.0 Atrium Decking SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-31 |  | 05 30 00-15.0 Atrium Decking SD-MAM_TT_POP.pdf
05 40 00-001-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-001-00 COLD-FORMED METAL FRAMING - Product Data, Exterior Framing Shop Drawings and Calculations | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-04 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-24 | 2020-06-30 | 27 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-06-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06176 | Received | For Review | 2020-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-06-24 | Submittal Number: 05 40 00-1.0 From: TYRONE THORNTON Final Due Date: 06/17/20 Subject: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Description: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 08350 | Forwarded | For Review | 2020-06-03 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-10 | Submittal Number: 05 40 00-1.0 From: TYRONE THORNTON Final Due Date: 06/17/20 Subject: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Description: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 06549 | Review Response | Approved as Noted | 2020-06-22 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08817 | Forwarded | For Review | 2020-06-22 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-18 | Submittal Number: 05 40 00-1.0 From: TYRONE THORNTON Final Due Date: 06/17/20 Subject: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Description: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09035 | Responded and Closed | Revise and Resubmit | 2020-06-30 | Todd Spangler (Populous) | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-03 |  | 054000-0001-0 Product Data & Shop Drawings CFMF-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-03 |  | 054000-0001-0 Product Data & Shop Drawings CFMF-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-02 02:00 |  | 054000-0001-0 Product Data & Shop Drawings CFMF-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-02 02:00 |  | 054000-0001-0 Product Data & Shop Drawings CFMF-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-30 |  | 054000-0001-0 Product Data & Shop Drawings CFMF-MAM_POP.pdf
05 40 00-001-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-001-01 COLD-FORMED METAL FRAMING - Product Data, Exterior Framing Shop Drawings and Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-06 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Kristin Long (Populous) |  |  |  | 2020-11-20 | 2020-11-23 | 18 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-11-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09270 | Received | For Review | 2020-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-11-20 | Submittal Number: 05 40 00-1.1 From: TYRONE THORNTON Final Due Date: 11/19/20 Subject: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Description: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12222 | Forwarded | For Review | 2020-11-06 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-13 | Submittal Number: 05 40 00-1.1 From: TYRONE THORNTON Final Due Date: 11/19/20 Subject: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Description: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12257 | Forwarded | For Review | 2020-11-08 | Todd Spangler (Populous) | Kristin Long (Populous) |  | Submittal Number: 05 40 00-1.1 From: TYRONE THORNTON Final Due Date: 11/19/20 Subject: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Description: COLD-FORMED METAL FRAMING - PRODUCT DATA, EXTERIOR FRAMING SHOP DRAWINGS AND CALCULATIONS Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09665 | Review Response | Approved | 2020-11-16 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | TT has only reviewed this submittal to verify previous comments were picked up. All other parts of this submittal are assumed to remain unchanged from previous review as nothing is clouded within submittal. If other parts have been changed, please resubmit this submittal with all changes from Rev 0 clearly clouded. | Info Exchange
| 12723 | Responded and Closed | Approved as Noted | 2020-11-23 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-05 |  | 054000-0001-1-CFMF-PD-EXteriorSDCalcs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-05 |  | 054000-0001-1-CFMF-PD-EXteriorSDCalcs-MAM.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-11-05 |  | 054000-0001-1-CFMF-PD-EXteriorSDCalcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-05 |  | 054000-0001-1-CFMF-PD-EXteriorSDCalcs-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-23 |  | 054000-0001-1-CFMF-PD-EXteriorSDCalcs-MAM_TT_POP.pdf
05 40 00-002-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-002-00 COLD-FORMED METAL FRAMING - LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-19 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-06 07:00 | 2020-07-06 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06521 | Received | For Review | 2020-06-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-06 07:00 | Submittal Number: 05 40 00-2.0 From: JES PELKEY Final Due Date: 07/03/20 Subject: COLD-FORMED METAL FRAMING - LEED DATA Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 08776 | Forwarded | For Review | 2020-06-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-06-26 | Submittal Number: 05 40 00-2.0 From: JES PELKEY Final Due Date: 07/03/20 Subject: COLD-FORMED METAL FRAMING - LEED DATA Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 08815 | Forwarded | For Review | 2020-06-22 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-29 | Submittal Number: 05 40 00-2.0 From: JES PELKEY Final Due Date: 07/03/20 Subject: COLD-FORMED METAL FRAMING - LEED DATA Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09128 | Responded and Closed | Approved | 2020-07-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-19 |  | SCA 05-40-00 Cold Form Metal Framing LEED Submittal_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-19 |  | SCA 05-40-00 Cold Form Metal Framing LEED Submittal_MAM Reviewed.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-18 02:00 |  | SCA 05-40-00 Cold Form Metal Framing LEED Submittal_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-06 |  | SCA 05-40-00 Cold Form Metal Framing LEED Submittal_MAM Reviewed_POP.pdf
05 40 00-004-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-004-00 SL2 Plenum Shop Drawings | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-20 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-08-03 | 2020-08-06 | 18 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07393 | Received | For Review | 2020-07-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2020-08-03 | Received from: AI Assistant Mortenson Procore Connector (Mortenson Construction) Description: Submittal Number: 05 40 00-4.0 From: YE ZHANG Final Due Date: 07/30/20 Subject: SL2 Plenum Shop Drawings Description: Spec Section: 05 40 00 - SL2 Plenum Shop Drawings Status: OPEN | Info Exchange
| 07394 | Review Response | Approved | 2020-08-05 | Bryan Klote (Populous) | Josh Dobken (Populous) |  |  | Info Exchange
| 09856 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2020-08-03 | Received from: AI Assistant Mortenson Procore Connector (Mortenson Construction) Description: Submittal Number: 05 40 00-4.0 From: YE ZHANG Final Due Date: 07/30/20 Subject: SL2 Plenum Shop Drawings Description: Spec Section: 05 40 00 - SL2 Plenum Shop Drawings Status: OPEN | Email
| 07413 | Review Response | Approved as Noted | 2020-08-06 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Refer to comments in submittal. Submittal is required to be resubmitted for approval if comments result in design changes. | Info Exchange
| 09880 | Responded and Closed | Approved as Noted | 2020-08-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company); Ye Zhang (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Refer to comments in submittal. Submittal is required to be resubmitted for approval if comments result in design changes. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-03 |  | 054000-0004-0-CFMF-SL2-PlenumShopDrawingsCalculations-MAM.pdf
| Review Response |  | Bryan Klote (Populous) | 1 | 2020-08-03 02:00 |  | 054000-0004-0-CFMF-SL2-PlenumShopDrawingsCalculations-MAM_POP.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-03 02:00 |  | 054000-0004-0-CFMF-SL2-PlenumShopDrawingsCalculations-MAM_POP.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-03 02:00 |  | 054000-0004-0-CFMF-SL2-PlenumShopDrawingsCalculations-MAM_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-06 02:00 |  | 054000-0004-0-CFMF-SL2-PlenumShopDrawingsCalculations-MAM_TT_pop.pdf
05 40 00-005-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-005-00 COLD-FORMED METAL FRAMING - Plenum SL6 Shop Drawings and Calculations | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-21 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-04 | 2020-07-31 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07055 | Received | For Review | 2020-07-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-08-04 | Submittal Number: 05 40 00-5.0 From: TYRONE THORNTON Final Due Date: 08/03/20 Subject: COLD-FORMED METAL FRAMING - PLENUM SL6 SHOP DRAWINGS AND CALCULATIONS Description: QUALIFICATION DATA : FOR TESTING AGENCY. Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09444 | Forwarded | For Review | 2020-07-21 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-28 | Submittal Number: 05 40 00-5.0 From: TYRONE THORNTON Final Due Date: 08/03/20 Subject: COLD-FORMED METAL FRAMING - PLENUM SL6 SHOP DRAWINGS AND CALCULATIONS Description: QUALIFICATION DATA : FOR TESTING AGENCY. Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 07282 | Review Response | Revise and Resubmit | 2020-07-28 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Full submittal not reviewed as MAM noted revised detail for attachment to Mech steel was going to be included in next revision. | Info Exchange
| 09702 | Responded and Closed | Revise and Resubmit | 2020-07-31 | Todd Spangler (Populous) | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Full submittal not reviewed as MAM noted revised detail for attachment to Mech steel was going to be included in next revision. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-20 |  | 054000-0005-0-CFMF-SL6-PlenumShopDrawingsCalculations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-20 |  | 054000-0005-0-CFMF-SL6-PlenumShopDrawingsCalculations-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-20 |  | 054000-0005-0-CFMF-SL6-PlenumShopDrawingsCalculations-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-31 |  | 054000-0005-0-CFMF-SL6-PlenumShopDrawingsCalculations-MAM_TT_POP.pdf
05 40 00-005-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-005-01 COLD-FORMED METAL FRAMING - Plenum SL6 Shop Drawings and Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-29 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-12 | 2020-08-05 | 8 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-08-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07237 | Received | For Review | 2020-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-08-12 | Submittal Number: 05 40 00-5.1 From: TYRONE THORNTON Final Due Date: 08/12/20 Subject: COLD-FORMED METAL FRAMING - PLENUM SL6 SHOP DRAWINGS AND CALCULATIONS Description: REV 1 Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09651 | Forwarded | For Review | 2020-07-29 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-05 | Submittal Number: 05 40 00-5.1 From: TYRONE THORNTON Final Due Date: 08/12/20 Subject: COLD-FORMED METAL FRAMING - PLENUM SL6 SHOP DRAWINGS AND CALCULATIONS Description: REV 1 Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 07386 | Review Response | Revise and Resubmit | 2020-07-31 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Resubmit missing detail for plenum connection at column locations as noted. | Info Exchange
| 09841 | Responded and Closed | Revise and Resubmit | 2020-08-05 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Resubmit missing detail for plenum connection at column locations as noted. | Info Exchange
| 09844 | Reopened | Additional Information | 2020-08-05 12:49 | Bryan Klote (Populous) |  |  | missing attachment
| 09845 | Responded and Closed | Revise and Resubmit | 2020-08-05 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Resubmit missing detail for plenum connection at column locations as noted. Reopened (Additional Information) by: Bryan Klote Remarks: missing attachment added | Info Exchange
| 09846 | Sent | For Information Only | 2020-08-05 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company); Alex Brown (M.A. Mortenson Company); Ye Zhang (M.A. Mortenson Company) |  | Responded and Closed (Revise and Resubmit) to: Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (M.A. Mortenson Company) Remarks: Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Resubmit missing detail for plenum connection at column locations as noted. Reopened (Additional Information) by: Bryan Klote Remarks: missing attachment added | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-29 |  | 054000-0005-1-CFMF-SL6PlenumShopDrawingsCalculations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-29 |  | 054000-0005-1-CFMF-SL6PlenumShopDrawingsCalculations-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-29 |  | 054000-0005-1-CFMF-SL6PlenumShopDrawingsCalculations-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-29 |  | 054000-0005-1-CFMF-SL6PlenumShopDrawingsCalculations-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-08-05 |  | 054000-0005-1-CFMF-SL6PlenumShopDrawingsCalculations-MAM_TT_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-07-28 02:00 |  | 054000-0005-1-CFMF-SL6PlenumShopDrawingsCalculations-MAM.pdf
05 40 00-005-02 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-005-02 COLD-FORMED METAL FRAMING - SL6 Transition Detail at Structural Columns | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-07 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-21 | 2020-08-14 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-08-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07438 | Received | For Review | 2020-08-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-08-21 | Submittal Number: 05 40 00-5.2 From: TYRONE THORNTON Final Due Date: 08/20/20 Subject: COLD-FORMED METAL FRAMING - SL6 TRANSITION DETAIL AT STRUCTURAL COLUMNS Description: REV 2 WITH TRANSITION DETAIL AT STRUCTURAL COLUMNS ONLY Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09905 | Forwarded | For Review | 2020-08-06 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-13 | Submittal Number: 05 40 00-5.2 From: TYRONE THORNTON Final Due Date: 08/20/20 Subject: COLD-FORMED METAL FRAMING - SL6 TRANSITION DETAIL AT STRUCTURAL COLUMNS Description: REV 2 WITH TRANSITION DETAIL AT STRUCTURAL COLUMNS ONLY Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 07554 | Review Response | Approved | 2020-08-14 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. | Info Exchange
| 10054 | Responded and Closed | Approved | 2020-08-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | 054000-0005-2-CFMF-SL6TrasitionDetail-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-06 |  | 054000-0005-2-CFMF-SL6TrasitionDetail-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-05 02:00 |  | 054000-0005-2-CFMF-SL6TrasitionDetail-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-14 02:00 |  | 054000-0005-2-CFMF-SL6TrasitionDetail-MAM_TT Reviewed_POP.pdf
05 40 00-005-03 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-005-03 COLD-FORMED METAL FRAMING - SL6 Engineering and Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-21 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-04 | 2020-08-28 | 8 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07672 | Received | For Review | 2020-08-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-09-04 | Submittal Number: 05 40 00-5.3 From: TYRONE THORNTON Final Due Date: 09/03/20 Subject: COLD-FORMED METAL FRAMING - SL6 ENGINEERING AND CALCULATIONS Description: REV 3 IS TO ADDRESS WHEN THE COLUMN ATTACHMENT DETAILS APPLY AND WHEN THEY ARE NOT NEEDED, AS WELL AS DEFINING THE CANTILEVER DISTANCE THE HORIZONTAL MEMBER IS ALLOWED TO CANTILEVER WITHOUT HAVING A VERTICAL CONNECTION TO STRUCTURE ABOVE. Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 10217 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-31 | Submittal Number: 05 40 00-5.3 From: TYRONE THORNTON Final Due Date: 09/03/20 Subject: COLD-FORMED METAL FRAMING - SL6 ENGINEERING AND CALCULATIONS Description: REV 3 IS TO ADDRESS WHEN THE COLUMN ATTACHMENT DETAILS APPLY AND WHEN THEY ARE NOT NEEDED, AS WELL AS DEFINING THE CANTILEVER DISTANCE THE HORIZONTAL MEMBER IS ALLOWED TO CANTILEVER WITHOUT HAVING A VERTICAL CONNECTION TO STRUCTURE ABOVE. Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 07820 | Review Response | Approved | 2020-08-27 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. | Info Exchange
| 10397 | Responded and Closed | Approved | 2020-08-28 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 054000-0005-3-CFMF-SL6EngineeringCalculations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-20 |  | 054000-0005-3-CFMF-SL6EngineeringCalculations-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-20 |  | 054000-0005-3-CFMF-SL6EngineeringCalculations-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-28 |  | 054000-0005-3-CFMF-SL6EngineeringCalculations-MAM_TT_POP.pdf
05 40 00-006-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-006-00 COLD-FORMED METAL FRAMING - CDX Plywood for SL6 Assembly | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-31 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-15 07:00 | 2020-09-02 | 3 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07843 | Received | For Review | 2020-08-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-09-15 07:00 | Submittal Number: 05 40 00-6.0 From: TYRONE THORNTON Final Due Date: 09/11/20 Subject: COLD-FORMED METAL FRAMING - CDX PLYWOOD FOR SL6 ASSEMBLY Description: WELDING CERTIFICATES. PRODUCT TEST REPORTS : FOR EACH LISTED PRODUCT, FOR TESTS PERFORMED BYA QUALIFIED TESTING AGENCY. 1. STEEL SHEET. 2. EXPANSION ANCHORS. 3. POWER-ACTUATED ANCHORS. 4. MECHANICAL FASTENERS. 5. VERTICAL DEFLECTION CLIPS. 6. HORIZONTAL DRIFT DEFLECTION CLIPS 7. MISCELLANEOUS STRUCTURAL CLIPS AND ACCESSORIES. Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 10426 | Forwarded | For Review | 2020-08-29 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-07 | Submittal Number: 05 40 00-6.0 From: TYRONE THORNTON Final Due Date: 09/11/20 Subject: COLD-FORMED METAL FRAMING - CDX PLYWOOD FOR SL6 ASSEMBLY Description: WELDING CERTIFICATES. PRODUCT TEST REPORTS : FOR EACH LISTED PRODUCT, FOR TESTS PERFORMED BYA QUALIFIED TESTING AGENCY. 1. STEEL SHEET. 2. EXPANSION ANCHORS. 3. POWER-ACTUATED ANCHORS. 4. MECHANICAL FASTENERS. 5. VERTICAL DEFLECTION CLIPS. 6. HORIZONTAL DRIFT DEFLECTION CLIPS 7. MISCELLANEOUS STRUCTURAL CLIPS AND ACCESSORIES. Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 10498 | Responded and Closed | Approved | 2020-09-02 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-28 |  | 054000-0006-0-CFMF-CDX Plywood for SL6-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-28 |  | 054000-0006-0-CFMF-CDX Plywood for SL6-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-02 |  | 054000-0006-0-CFMF-CDX Plywood for SL6-MAM_POP.pdf
05 40 00-007-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-007-00 COLD-FORMED METAL FRAMING - Engineering Judgment for Fire Rating of the SL-6 Assembly at the Snorkel Plenum Locations | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-29 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-12 | 2020-08-04 | 7 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07212 | Received | For Review | 2020-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-08-12 | Submittal Number: 05 40 00-7.0 From: TYRONE THORNTON Final Due Date: 08/11/20 Subject: COLD-FORMED METAL FRAMING - ENGINEERING JUDGEMENT FOR FIRE RATING OF THE SL-6 ASSEMBLY AT THE SNORKEL PLENUM LOCATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09619 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-04 | Submittal Number: 05 40 00-7.0 From: TYRONE THORNTON Final Due Date: 08/11/20 Subject: COLD-FORMED METAL FRAMING - ENGINEERING JUDGEMENT FOR FIRE RATING OF THE SL-6 ASSEMBLY AT THE SNORKEL PLENUM LOCATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09782 | Responded and Closed | No Action Taken or Required | 2020-08-04 | Todd Spangler (Populous) | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | REVIEWED FOR DESIGN INTENT. PER DIV 1 SECTION 1.7 GC/CM RESPONSIBLE TO SUBMIT TO THE AHJ. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-28 |  | 054000-0008-0-CFMF-EJ for SL6-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-28 |  | 054000-007-0-CFMF-EJ for SL6-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-04 |  | 054000-007-0-CFMF-EJ for SL6-MAM_POP.pdf
05 40 00-008-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-008-00 COLD-FORMED METAL FRAMING - Engineering Judgment for SL-2 Transition to 2hr Rated Wall | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-28 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-11 | 2020-08-04 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07174 | Received | For Review | 2020-07-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-08-11 | Submittal Number: 05 40 00-8.0 From: TYRONE THORNTON Final Due Date: 08/10/20 Subject: COLD-FORMED METAL FRAMING - ENGINEERING JUDGEMENT FOR SL-2 TRANSITION TO 2HR RATED WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09575 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-04 | Submittal Number: 05 40 00-8.0 From: TYRONE THORNTON Final Due Date: 08/10/20 Subject: COLD-FORMED METAL FRAMING - ENGINEERING JUDGEMENT FOR SL-2 TRANSITION TO 2HR RATED WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09783 | Responded and Closed | No Action Taken or Required | 2020-08-04 | Todd Spangler (Populous) | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | REVIEWED FOR DESIGN INTENT. PER DIV 1 SECTION 1.7 GC/CM RESPONSIBLE TO SUBMIT TO THE AHJ. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-27 |  | 054000-0008-0-CFMF-EJ for SL2-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-27 |  | 054000-0008-0-CFMF-EJ for SL2-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-04 |  | 054000-0008-0-CFMF-EJ for SL2-MAM_POP.pdf
05 40 00-011-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-011-00 COLD-FORMED METAL FRAMING - Shop Drawings_PCI | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-16 | 2020-11-11 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09151 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-11-16 | Submittal Number: 05 40 00-11.0 From: ALLIE ZIMMERMAN Final Due Date: 11/16/20 Subject: COLD-FORMED METAL FRAMING - SHOP DRAWINGS_PCI Description: SHOP DRAWINGS: 1. INCLUDE LAYOUT, SPACINGS, SIZES, THICKNESSES, AND TYPES OF COLD-FORMED STEEL FRAMING; FABRICATION; AND FASTENING AND ANCHORAGE DETAILS, INCLUDING MECHANICAL FASTENERS. 2. INDICATE REINFORCING CHANNELS, OPENING FRAMING, SUPPLEMENTAL FRAMING, STRAPPING, BRACING, BRIDGING, SPLICES, ACCESSORIES, CONNECTION DETAILS, AND ATTACHMENT TO ADJOINING WORK Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12073 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-09 | Submittal Number: 05 40 00-11.0 From: ALLIE ZIMMERMAN Final Due Date: 11/16/20 Subject: COLD-FORMED METAL FRAMING - SHOP DRAWINGS_PCI Description: SHOP DRAWINGS: 1. INCLUDE LAYOUT, SPACINGS, SIZES, THICKNESSES, AND TYPES OF COLD-FORMED STEEL FRAMING; FABRICATION; AND FASTENING AND ANCHORAGE DETAILS, INCLUDING MECHANICAL FASTENERS. 2. INDICATE REINFORCING CHANNELS, OPENING FRAMING, SUPPLEMENTAL FRAMING, STRAPPING, BRACING, BRIDGING, SPLICES, ACCESSORIES, CONNECTION DETAILS, AND ATTACHMENT TO ADJOINING WORK Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12076 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-09 | Submittal Number: 05 40 00-11.0 From: ALLIE ZIMMERMAN Final Due Date: 11/16/20 Subject: COLD-FORMED METAL FRAMING - SHOP DRAWINGS_PCI Description: SHOP DRAWINGS: 1. INCLUDE LAYOUT, SPACINGS, SIZES, THICKNESSES, AND TYPES OF COLD-FORMED STEEL FRAMING; FABRICATION; AND FASTENING AND ANCHORAGE DETAILS, INCLUDING MECHANICAL FASTENERS. 2. INDICATE REINFORCING CHANNELS, OPENING FRAMING, SUPPLEMENTAL FRAMING, STRAPPING, BRACING, BRIDGING, SPLICES, ACCESSORIES, CONNECTION DETAILS, AND ATTACHMENT TO ADJOINING WORK Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09372 | Review Response | Revise and Resubmit | 2020-11-10 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Structural systems in this submittal should be designed using ASCE 7-10 Chapter 13 for Non-Structural Elements assuming these are "Access Floors". Seismic Base shall be assumed to be at Main Concourse Levl (Elev +98'-0"). See typical comments regarding Seismic Design Criteria found on General Notes Sheet S0-01. Please clearly identify both gravity and lateral loads imposed at all connections to base structural elements for review and approval by EOR. | Info Exchange
| 12361 | Responded and Closed | Revise and Resubmit | 2020-11-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-02 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings_MAM Reviewed.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-11 |  | 05 40 00-011 - Cold Formed Metal Framing Shop Drawings-MAM_TT_POP.pdf
05 40 00-011-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-011-01 COLD-FORMED METAL FRAMING - Shop Drawings_PCI | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-07 | 2020-12-11 | 23 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-12-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09574 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-07 | Submittal Number: 05 40 00-11.1 From: ALLIE ZIMMERMAN Final Due Date: 12/03/20 Subject: COLD-FORMED METAL FRAMING - SHOP DRAWINGS_PCI Description: SHOP DRAWINGS: 1. INCLUDE LAYOUT, SPACINGS, SIZES, THICKNESSES, AND TYPES OF COLD-FORMED STEEL FRAMING; FABRICATION; AND FASTENING AND ANCHORAGE DETAILS, INCLUDING MECHANICAL FASTENERS. 2. INDICATE REINFORCING CHANNELS, OPENING FRAMING, SUPPLEMENTAL FRAMING, STRAPPING, BRACING, BRIDGING, SPLICES, ACCESSORIES, CONNECTION DETAILS, AND ATTACHMENT TO ADJOINING WORK Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12603 | Forwarded | For Review | 2020-11-19 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-26 | Submittal Number: 05 40 00-11.1 From: ALLIE ZIMMERMAN Final Due Date: 12/03/20 Subject: COLD-FORMED METAL FRAMING - SHOP DRAWINGS_PCI Description: SHOP DRAWINGS: 1. INCLUDE LAYOUT, SPACINGS, SIZES, THICKNESSES, AND TYPES OF COLD-FORMED STEEL FRAMING; FABRICATION; AND FASTENING AND ANCHORAGE DETAILS, INCLUDING MECHANICAL FASTENERS. 2. INDICATE REINFORCING CHANNELS, OPENING FRAMING, SUPPLEMENTAL FRAMING, STRAPPING, BRACING, BRIDGING, SPLICES, ACCESSORIES, CONNECTION DETAILS, AND ATTACHMENT TO ADJOINING WORK Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09952 | Review Response | Revise and Resubmit | 2020-12-07 | Raymond Chou (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 13205 | Responded and Closed | Revise and Resubmit | 2020-12-11 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings - REV1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-18 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings - REV1.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2020-12-07 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings - REV1_TT Reviewed.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-11 |  | 05 40 00-011-01 - Cold Formed Metal Framing Shop Drawings_TT_POP.pdf
05 40 00-011-02 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-011-02 COLD-FORMED METAL FRAMING - Shop Drawings_PCI | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-22 08:00 | 2021-02-02 | 27 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2021-02-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10514 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-01-22 08:00 | Submittal Number: 05 40 00-11.2 From: ALLIE ZIMMERMAN Final Due Date: 01/21/21 Subject: COLD-FORMED METAL FRAMING - SHOP DRAWINGS_PCI Description: SHOP DRAWINGS: 1. INCLUDE LAYOUT, SPACINGS, SIZES, THICKNESSES, AND TYPES OF COLD-FORMED STEEL FRAMING; FABRICATION; AND FASTENING AND ANCHORAGE DETAILS, INCLUDING MECHANICAL FASTENERS. 2. INDICATE REINFORCING CHANNELS, OPENING FRAMING, SUPPLEMENTAL FRAMING, STRAPPING, BRACING, BRIDGING, SPLICES, ACCESSORIES, CONNECTION DETAILS, AND ATTACHMENT TO ADJOINING WORK Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13717 | Forwarded | For Review | 2021-01-07 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-14 | Submittal Number: 05 40 00-11.2 From: ALLIE ZIMMERMAN Final Due Date: 01/21/21 Subject: COLD-FORMED METAL FRAMING - SHOP DRAWINGS_PCI Description: SHOP DRAWINGS: 1. INCLUDE LAYOUT, SPACINGS, SIZES, THICKNESSES, AND TYPES OF COLD-FORMED STEEL FRAMING; FABRICATION; AND FASTENING AND ANCHORAGE DETAILS, INCLUDING MECHANICAL FASTENERS. 2. INDICATE REINFORCING CHANNELS, OPENING FRAMING, SUPPLEMENTAL FRAMING, STRAPPING, BRACING, BRIDGING, SPLICES, ACCESSORIES, CONNECTION DETAILS, AND ATTACHMENT TO ADJOINING WORK Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11878 | Review Response | Approved | 2021-01-20 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. | Info Exchange
| 11124 | Review Response | Approved | 2021-02-02 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14435 | Responded and Closed | Approved | 2021-02-02 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-07 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings - REV2_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-07 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings - REV2_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-06 02:00 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings - REV2_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-02 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings - REV2_MAM_TT_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-07 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing Shop Drawings - REV2_MAM Reviewed.pdf
05 40 00-012-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-012-00 COLD-FORMED METAL FRAMING - Certificates & Test Reports - PCI | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-11 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-25 | 2020-11-25 | 15 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-11-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09356 | Received | For Review | 2020-11-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-11-25 | Submittal Number: 05 40 00-12.0 From: ALLIE ZIMMERMAN Final Due Date: 11/24/20 Subject: COLD-FORMED METAL FRAMING - CERTIFICATES & TEST REPORTS - PCI Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12345 | Forwarded | For Review | 2020-11-11 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-18 | Submittal Number: 05 40 00-12.0 From: ALLIE ZIMMERMAN Final Due Date: 11/24/20 Subject: COLD-FORMED METAL FRAMING - CERTIFICATES & TEST REPORTS - PCI Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09745 | Review Response | No Action Taken or Required | 2020-11-23 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Received for Record Only. | Info Exchange
| 12813 | Responded and Closed | No Action Taken or Required | 2020-11-25 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: Received for Record Only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-10 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-10 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-09 02:00 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing_MAM Reviewed.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-25 02:00 |  | PCI Material Submittal - 05 40 00 - Cold Formed Metal Framing_MAM Reviewed_pop.pdf
05 40 00-013-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-013-00 CFMF-SL6 Eng Calcs Elec Substations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-14 | 2020-10-07 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-10-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08450 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2020-10-14 | Submittal Number: 05 40 00-13.0 From: YE ZHANG Final Due Date: 9/22/20 Subject: COLD-FORMED METAL FRAMING - CFMF-SL6 Eng Calcs Elec Substations Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11191 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-07 | Submittal Number: 05 40 00-13.0 From: YE ZHANG Final Due Date: 9/22/20 Subject: COLD-FORMED METAL FRAMING - CFMF-SL6 Eng Calcs Elec Substations Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 08624 | Review Response | Approved | 2020-10-07 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 11402 | Responded and Closed | Approved | 2020-10-07 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (M.A. Mortenson Company) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 05 40 00-013-00 CFMF-SL6 Eng Calcs Elec Substations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 05 40 00-013-00 CFMF-SL6 Eng Calcs Elec Substations-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-29 02:00 |  | 05 40 00-013-00 CFMF-SL6 Eng Calcs Elec Substations-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-07 02:00 |  | 05 40 00-013-00 CFMF-SL6 Eng Calcs Elec Substations-MAM_TT REVIEW_pop.pdf
05 40 00-014-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-014-00 COLD-FORMED METAL FRAMING - SL2 Upper Levels Design at NE and SE Snorkels | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-09 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-23 | 2020-09-28 | 20 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07997 | Received | For Review | 2020-09-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-09-23 | Submittal Number: 05 40 00-14.0 From: TYRONE THORNTON Final Due Date: 09/22/20 Subject: COLD-FORMED METAL FRAMING - SL2 UPPER LEVELS DESIGN AT NE AND SE SNORKELS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 10628 | Forwarded | For Review | 2020-09-09 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-16 | Submittal Number: 05 40 00-14.0 From: TYRONE THORNTON Final Due Date: 09/22/20 Subject: COLD-FORMED METAL FRAMING - SL2 UPPER LEVELS DESIGN AT NE AND SE SNORKELS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 08332 | Review Response | Revise and Resubmit | 2020-09-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08333 | Review Response | Revise and Resubmit | 2020-09-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 11126 | Responded and Closed | Revise and Resubmit | 2020-09-28 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-08 |  | 054000-0005-14-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-08 |  | 054000-0005-14-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-08 |  | 054000-0005-14-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-08 |  | 054000-0005-14-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-09-24 |  | 054000-0005-14-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM_TT REVIEW.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-09-28 |  | 054000-0005-14-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM_TT REVIEW-POP.pdf
05 40 00-014-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-014-01 COLD-FORMED METAL FRAMING - SL2 Upper Levels Design at NE and SE Snorkels | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-09 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Chris Minter (Populous), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti) |  |  |  | 2020-10-23 | 2020-10-22 | 14 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-10-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08692 | Received | For Review | 2020-10-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-10-23 | Submittal Number: 05 40 00-14.1 From: YE ZHANG Final Due Date: 10/16/20 Subject: COLD-FORMED METAL FRAMING - SL2 UPPER LEVELS DESIGN AT NE AND SE SNORKELS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11478 | Forwarded | For Review | 2020-10-09 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Chris Minter (Populous); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) | 2020-10-16 | Submittal Number: 05 40 00-14.1 From: YE ZHANG Final Due Date: 10/16/20 Subject: COLD-FORMED METAL FRAMING - SL2 UPPER LEVELS DESIGN AT NE AND SE SNORKELS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 08925 | Review Response | Approved | 2020-10-20 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 11792 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-22 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | REVISE SE PER CCD 074 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-08 02:00 |  | 054000-0014-0-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM_FIRSTLINE RESPONSE.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-08 02:00 |  | 054000-0014-1-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-08 02:00 |  | 054000-0014-0-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM_FIRSTLINE RESPONSE.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-08 02:00 |  | 054000-0014-1-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-08 |  | 054000-0014-0-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM_FIRSTLINE RESPONSE.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-08 |  | 054000-0014-1-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-22 |  | 054000-0014-1-CFMF-SL2UpperLevelsDesignNEandSESnorkels-MAM_TT_POP.pdf
05 40 00-014-02 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-014-02 COLD-FORMED METAL FRAMING - SL2 Upper Levels Design at SE Snorkels per CCD-074 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-28 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-11 | 2020-11-02 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-11-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09060 | Received | For Review | 2020-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-11-11 | Submittal Number: 05 40 00-14.2 From: YE ZHANG Final Due Date: 10/16/20 Subject: COLD-FORMED METAL FRAMING - SL2 UPPER LEVELS DESIGN AT SE SNORKELS PER CCD-074 Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11947 | Forwarded | For Review | 2020-10-28 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-04 | Submittal Number: 05 40 00-14.2 From: YE ZHANG Final Due Date: 10/16/20 Subject: COLD-FORMED METAL FRAMING - SL2 UPPER LEVELS DESIGN AT SE SNORKELS PER CCD-074 Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12096 | Responded and Closed | Approved | 2020-11-02 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 054000-0014-2-CFMF-SL2UpperLevelsDesignSESnorkels-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 054000-0014-2-CFMF-SL2UpperLevelsDesignSESnorkels-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-02 |  | 054000-0014-2-CFMF-SL2UpperLevelsDesignSESnorkels-MAM-POP.pdf
05 40 00-015-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-015-00 COLD-FORMED METAL FRAMING - SL2 Upper Levels Design at NW and SW Snorkels | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti) |  |  |  | 2020-10-07 | 2020-10-13 | 21 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08275 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 05 40 00-15.0 From: YE ZHANG Final Due Date: 10/06/20 Subject: COLD-FORMED METAL FRAMING - SL2 UPPER LEVELS DESIGN AT NW AND SW SNORKELS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 10982 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-30 | Submittal Number: 05 40 00-15.0 From: YE ZHANG Final Due Date: 10/06/20 Subject: COLD-FORMED METAL FRAMING - SL2 UPPER LEVELS DESIGN AT NW AND SW SNORKELS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11145 | Forwarded | For Review | 2020-09-29 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) | 2020-10-06 | Submittal Number: 05 40 00-15.0 From: YE ZHANG Final Due Date: 10/06/20 Subject: COLD-FORMED METAL FRAMING - SL2 UPPER LEVELS DESIGN AT NW AND SW SNORKELS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 08763 | Review Response | Approved as Noted | 2020-10-12 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 11589 | Responded and Closed | Approved as Noted | 2020-10-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 054000-0005-15-CFMF-SL2UpperLevelsDesignNWandSWSnorkels-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 054000-0005-15-CFMF-SL2UpperLevelsDesignNWandSWSnorkels-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-22 02:00 |  | 054000-0005-15-CFMF-SL2UpperLevelsDesignNWandSWSnorkels-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-22 02:00 |  | 054000-0005-15-CFMF-SL2UpperLevelsDesignNWandSWSnorkels-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-13 02:00 |  | 054000-0005-15-CFMF-SL2UpperLevelsDesignNWandSWSnorkels-MAM_TT REVIEW_POP.pdf
05 40 00-016-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-016-00 05 40 00 Cold Formed Metal Framing - Raised Seating ADA Platform Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-09 | 2020-09-28 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-09-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08345 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-10-09 | Submittal Number: 05 40 00-16.0 From: TYRONE THORNTON Final Due Date: 10/08/20 Subject: 05 40 00 COLD FORMED METAL FRAMING - RAISED SEATING ADA PLATFORM SHOP DRAWINGS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11056 | Forwarded | For Review | 2020-09-25 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-02 | Submittal Number: 05 40 00-16.0 From: TYRONE THORNTON Final Due Date: 10/08/20 Subject: 05 40 00 COLD FORMED METAL FRAMING - RAISED SEATING ADA PLATFORM SHOP DRAWINGS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 08388 | Review Response | Approved as Noted | 2020-09-28 | Chris Minter (Populous) | Shaina Burris (Populous) |  |  | Email
| 11121 | Responded and Closed | Approved as Noted | 2020-09-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Chris Minter (Populous) Remarks: See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | SCA 05-40-00 Cold Formed Metal Framing Raised Seating Platform Engineering Shops FSI 9.24.20_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | SCA 05-40-00 Cold Formed Metal Framing Raised Seating Platform Engineering Shops FSI 9.24.20_MAM Review.pdf
| Review Response |  | Chris Minter (Populous) | 1 | 2020-09-28 02:00 |  | SCA 05-40-00 Cold Formed Metal Framing Raised Seating Platform Engineering Shops FSI 9.24.20_MAM Review-POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-23 02:00 |  | SCA 05-40-00 Cold Formed Metal Framing Raised Seating Platform Engineering Shops FSI 9.24.20_MAM Review.pdf
05 40 00-017-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-017-00 COLD-FORMED METAL FRAMING - SL6 Alternate Threaded Rod Connection Detail | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-10-12 | 2020-10-08 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08364 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 05 40 00-17.0 From: YE ZHANG Final Due Date: 10/02/20 Subject: COLD-FORMED METAL FRAMING - SL6 ALTERNATE THREADED ROD CONNECTION DETAIL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11077 | Forwarded | For Review | 2020-09-28 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-05 | Submittal Number: 05 40 00-17.0 From: YE ZHANG Final Due Date: 10/02/20 Subject: COLD-FORMED METAL FRAMING - SL6 ALTERNATE THREADED ROD CONNECTION DETAIL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11401 | Forwarded | For Review | 2020-10-07 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2020-10-12 | Submittal Number: 05 40 00-17.0 From: YE ZHANG Final Due Date: 10/02/20 Subject: COLD-FORMED METAL FRAMING - SL6 ALTERNATE THREADED ROD CONNECTION DETAIL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 08670 | Review Response | Approved | 2020-10-08 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 11452 | Responded and Closed | Approved | 2020-10-08 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 054000-0017-0-CFMF-SL6ThreadedRodDetail-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 054000-0017-0-CFMF-SL6ThreadedRodDetail-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-24 02:00 |  | 054000-0017-0-CFMF-SL6ThreadedRodDetail-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-24 |  | 054000-0017-0-CFMF-SL6ThreadedRodDetail-MAM.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-08 |  | 054000-0017-0-CFMF-SL6ThreadedRodDetail-MAM_TT_POP.pdf
05 40 00-018-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-018-00 COLD-FORMED METAL FRAMING - SL6 Alternate HSS Engineering Detail with Kicker at West Plenum | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-13 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-27 | 2020-10-14 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-10-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08755 | Received | For Review | 2020-10-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-10-27 | Submittal Number: 05 40 00-18.0 From: YE ZHANG Final Due Date: 10/16/20 Subject: COLD-FORMED METAL FRAMING - SL6 ALTERNATE HSS ENGINEERING DETAIL WITH KICKER AT WEST PLENUM Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11571 | Forwarded | For Review | 2020-10-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-20 | Submittal Number: 05 40 00-18.0 From: YE ZHANG Final Due Date: 10/16/20 Subject: COLD-FORMED METAL FRAMING - SL6 ALTERNATE HSS ENGINEERING DETAIL WITH KICKER AT WEST PLENUM Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 08774 | Review Response | Approved as Noted | 2020-10-14 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 11603 | Responded and Closed | Approved as Noted | 2020-10-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-13 |  | 054000-0018-0-CFMF-SL6EngineeringDetailwithKicker-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-13 |  | 054000-0018-0-CFMF-SL6EngineeringDetailwithKicker-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-12 02:00 |  | 054000-0018-0-CFMF-SL6EngineeringDetailwithKicker-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-14 02:00 |  | 054000-0018-0-CFMF-SL6EngineeringDetailwithKicker-MAM_TT REVIEW_POP.pdf
05 40 00-019-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-019-00 COLD-FORMED METAL FRAMING - SL6 Engineering for NE Snorkel HSS Protrusion | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-20 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-03 | 2020-10-22 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-10-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08867 | Received | For Review | 2020-10-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-11-03 | Submittal Number: 05 40 00-19.0 From: YE ZHANG Final Due Date: 11/02/20 Subject: COLD-FORMED METAL FRAMING - SL6 ENGINEERING FOR NE SNORKEL HSS PROTRUSION Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11724 | Forwarded | For Review | 2020-10-19 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-26 | Submittal Number: 05 40 00-19.0 From: YE ZHANG Final Due Date: 11/02/20 Subject: COLD-FORMED METAL FRAMING - SL6 ENGINEERING FOR NE SNORKEL HSS PROTRUSION Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 08924 | Review Response | Approved | 2020-10-21 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 11791 | Responded and Closed | Approved as Noted | 2020-10-22 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-19 |  | 054000-0005-19-CFMF-SL6EngineeringforNESnorkelHSSProtrusion-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-19 |  | 054000-0005-19-CFMF-SL6EngineeringforNESnorkelHSSProtrusion-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-19 |  | 054000-0005-19-CFMF-SL6EngineeringforNESnorkelHSSProtrusion-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-22 |  | 054000-0005-19-CFMF-SL6EngineeringforNESnorkelHSSProtrusion-MAM_TT_POP.pdf
05 40 00-020-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-020-00 COLD-FORMED METAL FRAMING - Atrium Framing Engineering and Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-03 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-17 | 2020-11-11 | 9 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09205 | Received | For Review | 2020-11-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-11-17 | Submittal Number: 05 40 00-20.0 From: YE ZHANG Final Due Date: 11/16/20 Subject: COLD-FORMED METAL FRAMING - ATRIUM FRAMING ENGINEERING AND CALCULATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12154 | Forwarded | For Review | 2020-11-03 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-10 | Submittal Number: 05 40 00-20.0 From: YE ZHANG Final Due Date: 11/16/20 Subject: COLD-FORMED METAL FRAMING - ATRIUM FRAMING ENGINEERING AND CALCULATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12228 | Forwarded | For Review | 2020-11-06 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-13 | Submittal Number: 05 40 00-20.0 From: YE ZHANG Final Due Date: 11/16/20 Subject: COLD-FORMED METAL FRAMING - ATRIUM FRAMING ENGINEERING AND CALCULATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 09369 | Review Response | Approved | 2020-11-10 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 12358 | Responded and Closed | Approved | 2020-11-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | 054000-0020-0-CFMF-AtriumEngineeringCalcs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | 054000-0020-0-CFMF-AtriumEngineeringCalcs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 054000-0020-0-CFMF-AtriumEngineeringCalcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-06 |  | 054000-0020-0-CFMF-AtriumEngineeringCalcs-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-11 |  | 054000-0020-0-CFMF-AtriumEngineeringCalcs-MAM_TT_POP.pdf
05 40 00-021-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-021-00 COLD-FORMED METAL FRAMING - Atrium LED Engineering Details and Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-25 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-11 | 2020-12-15 | 21 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09757 | Received | For Review | 2020-11-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-12-11 | Submittal Number: 05 40 00-21.0 From: YE ZHANG Final Due Date: 12/09/20 Subject: COLD-FORMED METAL FRAMING - ATRIUM LED ENGINEERING DETAILS AND CALCULATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12825 | Forwarded | For Review | 2020-11-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-07 | Submittal Number: 05 40 00-21.0 From: YE ZHANG Final Due Date: 12/09/20 Subject: COLD-FORMED METAL FRAMING - ATRIUM LED ENGINEERING DETAILS AND CALCULATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 10158 | Review Response | Approved as Noted | 2020-12-14 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 13291 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | RESUBMIT FOR RECORD. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-25 |  | 054000-0021-0-CFMF-AtriumLEDEngineeringCalcs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-25 |  | 054000-0021-0-CFMF-AtriumLEDEngineeringCalcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-25 |  | 054000-0021-0-CFMF-AtriumLEDEngineeringCalcs-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-15 |  | 054000-0021-0-CFMF-AtriumLEDEngineeringCalcs-MAM_TT_POP.pdf
05 40 00-021-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-021-01 COLD-FORMED METAL FRAMING - Atrium LED Engineering Details and Calculations (For Record) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-28 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-11 | 2021-02-08 | 12 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11022 | Received | For Review | 2021-01-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-02-11 | Submittal Number: 05 40 00-21.1 From: YE ZHANG Final Due Date: 02/10/21 Subject: COLD-FORMED METAL FRAMING - ATRIUM LED ENGINEERING DETAILS AND CALCULATIONS (FOR RECORD) Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 14318 | Forwarded | For Review | 2021-01-28 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-04 | Submittal Number: 05 40 00-21.1 From: YE ZHANG Final Due Date: 02/10/21 Subject: COLD-FORMED METAL FRAMING - ATRIUM LED ENGINEERING DETAILS AND CALCULATIONS (FOR RECORD) Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11246 | Review Response | Approved | 2021-02-02 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Recieved for Record. | Info Exchange
| 14565 | Responded and Closed | Approved as Noted | 2021-02-08 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-27 |  | 054000-0005-21-CFMF-AtriumLEDEngineeringForRecord-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-27 |  | 054000-0005-21-CFMF-AtriumLEDEngineeringForRecord-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-27 |  | 054000-0005-21-CFMF-AtriumLEDEngineeringForRecord-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-08 |  | 05 40 00-21.1 CFMF-AtriumLEDEngineeringForRecord-MAM_POP.pdf
05 40 00-021-02 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-021-02 COLD-FORMED METAL FRAMING - Atrium LED Engineering Details and Calculations | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-03 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Todd Spangler (Populous), Kuebler Perry (Populous) |  |  |  | 2021-06-17 | 2021-06-09 | 7 |  | Record Copies; Transfers; Submittals | 05 40 00-021-02-01 - 05 40 00-021-02 COLD-FORMED METAL FRAMING - Atrium LED Engineering Details and Calculations | 2 |  | 2021-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13366 | Received | For Review | 2021-06-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-06-17 | Submittal Number: 05 40 00-21.2 From: YE ZHANG Final Due Date: 06/16/21 Subject: COLD-FORMED METAL FRAMING - ATRIUM LED ENGINEERING DETAILS AND CALCULATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17295 | Forwarded | For Review | 2021-06-03 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-10 | Submittal Number: 05 40 00-21.2 From: YE ZHANG Final Due Date: 06/16/21 Subject: COLD-FORMED METAL FRAMING - ATRIUM LED ENGINEERING DETAILS AND CALCULATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13464 | Review Response | Approved | 2021-06-04 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous); Shaina Burris (Populous) |  |  | Info Exchange
| 17359 | Forwarded | For Review | 2021-06-07 | Josh Dobken (Populous) | Todd Spangler (Populous); Kuebler Perry (Populous) | 2021-06-14 | Submittal Number: 05 40 00-21.2 From: YE ZHANG Final Due Date: 06/16/21 Subject: COLD-FORMED METAL FRAMING - ATRIUM LED ENGINEERING DETAILS AND CALCULATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17409 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-09 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-03 |  | Submittal 05 40 00-21 Revision 2 COLD-FORMED METAL FRAMING - Atrium LED Engineering Details and Calculations_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-03 |  | Submittal 05 40 00-21 Revision 2 COLD-FORMED METAL FRAMING - Atrium LED Engineering Details and Calculations_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-06-03 |  | Submittal 05 40 00-21 Revision 2 COLD-FORMED METAL FRAMING - Atrium LED Engineering Details and Calculations_MAM Reviewed.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-02 02:00 |  | Submittal 05 40 00-21 Revision 2 COLD-FORMED METAL FRAMING - Atrium LED Engineering Details and Calculations_MAM Reviewed.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-06-03 |  | 05 40 00-21 Revision 2 COLD-FORMED METAL FRAMING - Atrium LED Details and Calcs_MAM Reviewed.pdf
05 40 00-021-02-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-021-02 COLD-FORMED METAL FRAMING - Atrium LED Engineering Details and Calculations | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 40 00-021-02 - 05 40 00-021-02 COLD-FORMED METAL FRAMING - Atrium LED Engineering Details and Calculations | -1 | 2021-06-23
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-03 |  | 05 40 00-21 Revision 2 COLD-FORMED METAL FRAMING - Atrium LED Details and Calcs_MAM Reviewed.pdf
05 40 00-022-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-022-00 COLD-FORMED METAL FRAMING - Vendor Comms 05.27.01 and 05.35.01 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-21 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-13 | 2020-12-30 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-12-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10289 | Received | For Review | 2020-12-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2021-01-13 | Submittal Number: 05 40 00-22.0 From: YE ZHANG Final Due Date: 01/01/21 Subject: COLD-FORMED METAL FRAMING - VENDOR COMMS 05.27.01 AND 05.35.01 Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13447 | Forwarded | For Review | 2020-12-21 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-28 | Submittal Number: 05 40 00-22.0 From: YE ZHANG Final Due Date: 01/01/21 Subject: COLD-FORMED METAL FRAMING - VENDOR COMMS 05.27.01 AND 05.35.01 Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13538 | Responded and Closed | Approved | 2020-12-30 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-21 |  | 054000-0022-0-CFMF-VendorComms-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-21 |  | 054000-0022-0-CFMF-VendorComms-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-21 |  | 054000-0022-0-CFMF-VendorComms-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-21 |  | Transmittal_Submittal - 05 40 00-022-00 (Forwarded).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-30 |  | 054000-0022-0-CFMF-VendorComms-MAM-POP.pdf
05 40 00-023-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-023-00 COLD-FORMED METAL FRAMING - Elevator Shaft Wall Boxed Beams | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-23 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-15 | 2021-01-08 | 17 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10338 | Received | For Review | 2020-12-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2021-01-15 | Submittal Number: 05 40 00-23.0 From: YE ZHANG Final Due Date: 01/05/21 Subject: COLD-FORMED METAL FRAMING - ELEVATOR SHAFT WALL BOXED BEAMS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13505 | Forwarded | For Review | 2020-12-23 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-30 | Submittal Number: 05 40 00-23.0 From: YE ZHANG Final Due Date: 01/05/21 Subject: COLD-FORMED METAL FRAMING - ELEVATOR SHAFT WALL BOXED BEAMS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 10565 | Review Response | Approved | 2021-01-06 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 13774 | Responded and Closed | Approved | 2021-01-08 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 14026 | Sent | For Information Only | 2021-01-19 | Josh Dobken (Populous) | Simran George (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Responded and Closed (Approved) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-22 |  | 054000-0023-0-CFMF-ElevatorShaftBoxedBeams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-22 |  | 054000-0023-0-CFMF-ElevatorShaftBoxedBeams-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-22 |  | 054000-0023-0-CFMF-ElevatorShaftBoxedBeams-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-01-06 |  | 054000-0023-0-CFMF-ElevatorShaftBoxedBeams-MAM_TT.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-01-08 |  | 054000-0023-0-CFMF-ElevatorShaftBoxedBeams-MAM_TT-POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-12-21 02:00 |  | 054000-0023-0-CFMF-ElevatorShaftBoxedBeams-MAM.pdf
05 40 00-024-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-024-00 COLD-FORMED METAL FRAMING - Precast By Pass Wall on Upper Concourse | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-18 | 2021-01-11 | 8 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10367 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2021-01-18 | Submittal Number: 05 40 00-24.0 From: YE ZHANG Final Due Date: 01/12/21 Subject: COLD-FORMED METAL FRAMING - PRECAST BY PASS WALL ON UPPER CONCOURSE Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13548 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-11 | Submittal Number: 05 40 00-24.0 From: YE ZHANG Final Due Date: 01/12/21 Subject: COLD-FORMED METAL FRAMING - PRECAST BY PASS WALL ON UPPER CONCOURSE Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 10585 | Review Response | Approved as Noted | 2021-01-07 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Precast engineer to review and approve loads imposed and connections to precast stadia units. | Info Exchange
| 13790 | Responded and Closed | Approved as Noted | 2021-01-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Precast engineer to review and approve loads imposed and connections to precast stadia units. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-29 |  | 054000-0024-0-CFMF-PrecastByPassWall-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-29 |  | 054000-0024-0-CFMF-PrecastByPassWall-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-29 |  | 054000-0024-0-CFMF-PrecastByPassWall-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-29 |  | 054000-0024-0-CFMF-PrecastByPassWall-MAM.pdf
05 40 00-025-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-025-00 Structural Support for SL6 Plenum for Electrical Substation 01.16.05 Buildout | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Closed - Void |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-27 08:00 |  | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-01-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10638 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-01-27 08:00 | Submittal Number: 05 40 00-25.0 From: YE ZHANG Final Due Date: 01/26/21 Subject: STRUCTURAL SUPPORT FOR SL6 PLENUM FOR ELECTRICAL SUBSTATION 01.16.05 BUILDOUT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13848 | Forwarded | For Review | 2021-01-12 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-19 | Submittal Number: 05 40 00-25.0 From: YE ZHANG Final Due Date: 01/26/21 Subject: STRUCTURAL SUPPORT FOR SL6 PLENUM FOR ELECTRICAL SUBSTATION 01.16.05 BUILDOUT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 14182 | Closed | Void | 2021-01-22 | Josh Dobken (Populous) |  |  | Closed per email attached.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 054000-0025-0-CFMF-StructuralSupportforSL6-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 054000-0025-0-CFMF-StructuralSupportforSL6-MAM.pdf
05 40 00-026-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-026-00 COLD-FORMED METAL FRAMING - L550 TR Elec Room Engineering Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-13 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-28 08:00 | 2021-02-08 | 27 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10664 | Received | For Review | 2021-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-01-28 08:00 | Submittal Number: 05 40 00-26.0 From: YE ZHANG Final Due Date: 01/26/21 Subject: COLD-FORMED METAL FRAMING - L550 TR ELEC ROOM ENGINEERING CALCULATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13885 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-20 | Submittal Number: 05 40 00-26.0 From: YE ZHANG Final Due Date: 01/26/21 Subject: COLD-FORMED METAL FRAMING - L550 TR ELEC ROOM ENGINEERING CALCULATIONS Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11261 | Review Response | Approved as Noted | 2021-01-29 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Coordinate attachments and loads imposed at Precast with Precast Engineer, TYP. | Info Exchange
| 14592 | Responded and Closed | Approved as Noted | 2021-02-08 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 054000-0026-0-CFMF-L550TRElecRoom-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 054000-0026-0-CFMF-L550TRElecRoom-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-12 |  | 054000-0026-0-CFMF-L550TRElecRoom-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-02-08 |  | 054000-0026-0-CFMF-L550TRElecRoom-MAM_TT-POP.pdf
05 40 00-027-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-027-00 COLD-FORMED METAL FRAMING - Press Bridge Corridor Soffit | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-10 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-24 | 2021-02-16 | 7 |  | Record Copies; Transfers; Submittals | 05 40 00-027-00-01 - 05 40 00-027-00 COLD-FORMED METAL FRAMING - Press Bridge Corridor Soffit | 2 |  | 2021-02-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11311 | Received | For Review | 2021-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-02-24 | Submittal Number: 05 40 00-27.0 From: YE ZHANG Final Due Date: 02/23/21 Subject: COLD-FORMED METAL FRAMING - PRESS BRIDGE CORRIDOR SOFFIT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 14662 | Forwarded | For Review | 2021-02-10 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-02-17 | Submittal Number: 05 40 00-27.0 From: YE ZHANG Final Due Date: 02/23/21 Subject: COLD-FORMED METAL FRAMING - PRESS BRIDGE CORRIDOR SOFFIT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11458 | Review Response | Revise and Resubmit | 2021-02-11 | Matt Ross (Thornton Tomasetti) | Bryan Klote (Populous) |  | Provide clarification on TT questions within submittal. All loads imposed and attachments to SPS floor to be coordinated, reviewed, and approved by SPS supplier. | Info Exchange
| 14840 | Responded and Closed | Revise and Resubmit | 2021-02-16 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE TT'S RESPONSE. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-09 |  | 054000-0027-0-CFMF-PressBridgeSoffit-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-09 |  | 054000-0027-0-CFMF-PressBridgeSoffit-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-09 |  | 054000-0027-0-CFMF-PressBridgeSoffit-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-02-16 |  | 054000-0027-0-CFMF-PressBridgeSoffit-MAM_TT-POP.pdf
05 40 00-027-00-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-027-00 COLD-FORMED METAL FRAMING - Press Bridge Corridor Soffit | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 40 00-027-00 - 05 40 00-027-00 COLD-FORMED METAL FRAMING - Press Bridge Corridor Soffit | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-16 |  | 054000-0027-0-CFMF-PressBridgeSoffit-MAM_TT-POP.pdf
05 40 00-028-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-028-00 COLD-FORMED METAL FRAMING - LED Ticker Board Support Framing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-11 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-25 | 2021-02-16 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-02-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11328 | Received | For Review | 2021-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-25 | Submittal Number: 05 40 00-28.0 From: YE ZHANG Final Due Date: 02/24/21 Subject: COLD-FORMED METAL FRAMING - LED TICKER BOARD SUPPORT FRAMING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 14687 | Forwarded | For Review | 2021-02-11 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-02-18 | Submittal Number: 05 40 00-28.0 From: YE ZHANG Final Due Date: 02/24/21 Subject: COLD-FORMED METAL FRAMING - LED TICKER BOARD SUPPORT FRAMING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11457 | Review Response | Approved as Noted | 2021-02-11 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Populous SCA_CCA |  |  | Info Exchange
| 14839 | Responded and Closed | Approved as Noted | 2021-02-16 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-10 |  | 054000-0028-0-CFMF-LEDTickerBoard-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-10 |  | 054000-0028-0-CFMF-LEDTickerBoard-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-10 |  | 054000-0028-0-CFMF-LEDTickerBoard-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-10 |  | 054000-0028-0-CFMF-LEDTickerBoard-MAM.pdf
05 40 00-029-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-029-00 CFMF - Whiskey Bar Soffit Engineering | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-23 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-03-09 | 2021-03-05 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11616 | Received | For Review | 2021-02-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ye Zhang (Mortenson Construction) | 2021-03-09 | Submittal Number: 05 40 00-29.0 From: ALLIE ZIMMERMAN Final Due Date: 03/09/21 Subject: COLD-FORMED METAL FRAMING - WHISKEY BAR SOFFIT ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 15054 | Forwarded | For Review | 2021-02-24 | Ye Zhang (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Chad F... | 2021-03-03 | Submittal Number: 05 40 00-29.0 From: ALLIE ZIMMERMAN Final Due Date: 03/09/21 Subject: COLD-FORMED METAL FRAMING - WHISKEY BAR SOFFIT ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11826 | Review Response | Revise and Resubmit | 2021-03-03 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Kuebler Perry (Populous) |  | Provide clarity and confirmations of TT's assumptions. Provide markups and/or detail references as required to clarify calcs and sketches. | Info Exchange
| 15331 | Responded and Closed | Revise and Resubmit | 2021-03-05 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (Mortenson Construction); Allie Zimmerman |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Provide clarity and confirmations of TT's assumptions. Provide markups and/or detail references as required to clarify calcs and sketches. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-23 02:00 |  | Submittal 05 40 00-29 Revision 0 COLD-FORMED METAL FRAMING - Whiskey Bar Soffit Engineering_MAM Reviewed.pdf
| Forwarded |  | Ye Zhang (Mortenson Construction) | 1 | 2021-02-23 02:00 |  | 05 40 00-029-00 CFMF - Whiskey Bar Soffit Engineering_MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-23 02:00 |  | 05 40 00-029-00 CFMF - Whiskey Bar Soffit Engineering_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-05 02:00 |  | 05 40 00-029-00 CFMF - Whiskey Bar Soffit Engineering_MAM_TT_POP.pdf
05 40 00-029-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-029-01 COLD-FORMED METAL FRAMING - Whiskey Bar Soffit Engineering | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-23 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-07 07:00 | 2021-03-31 | 9 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12181 | Received | For Review | 2021-03-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-04-07 07:00 | Submittal Number: 05 40 00-29.1 From: ALLIE ZIMMERMAN Final Due Date: 04/06/21 Subject: COLD-FORMED METAL FRAMING - WHISKEY BAR SOFFIT ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 15767 | Forwarded | For Review | 2021-03-23 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-30 | Submittal Number: 05 40 00-29.1 From: ALLIE ZIMMERMAN Final Due Date: 04/06/21 Subject: COLD-FORMED METAL FRAMING - WHISKEY BAR SOFFIT ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12337 | Review Response | Approved as Noted | 2021-03-30 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 15980 | Responded and Closed | Approved as Noted | 2021-03-31 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-23 |  | Submittal 05 40 00-29 Revision 1 COLD-FORMED METAL FRAMING - Whiskey Bar Soffit Engineering_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-23 |  | Submittal 05 40 00-29 Revision 1 COLD-FORMED METAL FRAMING - Whiskey Bar Soffit Engineering_MAM Review.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-23 |  | Submittal 05 40 00-29 Revision 1 COLD-FORMED METAL FRAMING - Whiskey Bar Soffit Engineering_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-31 |  | Submittal 05 40 00-29 Revision 1 COLD-FORMED METAL FRAMING - Whiskey Bar Soffit Engineering_MAM Review_TT REVIEW_POP.pdf
05 40 00-030-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-030-00 COLD-FORMED METAL FRAMING - NW Plenum Overhead Door | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-02 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-16 | 2021-03-08 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11737 | Received | For Review | 2021-03-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-03-16 | Submittal Number: 05 40 00-30.0 From: ALLIE ZIMMERMAN Final Due Date: 03/15/21 Subject: COLD-FORMED METAL FRAMING - NW PLENUM OVERHEAD DOOR Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 15209 | Forwarded | For Review | 2021-03-02 | Allie Zimmerman | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-09 | Submittal Number: 05 40 00-30.0 From: ALLIE ZIMMERMAN Final Due Date: 03/15/21 Subject: COLD-FORMED METAL FRAMING - NW PLENUM OVERHEAD DOOR Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 11838 | Review Response | Approved | 2021-03-03 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | TT has no exceptions. | Info Exchange
| 15346 | Responded and Closed | Approved | 2021-03-08 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-01 |  | Submittal 05 40 00-30 Revision 0 COLD-FORMED METAL FRAMING - NW Plenum Overhead Door_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-03-01 |  | Submittal 05 40 00-30 Revision 0 COLD-FORMED METAL FRAMING - NW Plenum Overhead Door_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-01 |  | Submittal 05 40 00-30 Revision 0 COLD-FORMED METAL FRAMING - NW Plenum Overhead Door_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-03-08 |  | 05 40 00-30 - CFMF - NW Plenum Overhead Door_MAM_TT_POP.pdf
05 40 00-034-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-034-00 COLD FORMED METAL FRAMING - Welding Certificates_PCI | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-25 | 2021-05-12 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13018 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-05-25 | Submittal Number: 05 40 00-34.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: COLD FORMED METAL FRAMING - WELDING CERTIFICATES_PCI Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 16846 | Forwarded | For Review | 2021-05-10 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-17 | Submittal Number: 05 40 00-34.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: COLD FORMED METAL FRAMING - WELDING CERTIFICATES_PCI Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13065 | Review Response | No Action Taken or Required | 2021-05-11 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Retained for Record Only. | Info Exchange
| 16901 | Responded and Closed | No Action Taken or Required | 2021-05-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: Retained for Record Only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | Submittal 05 40 00-34 Revision 0 COLD FORMED METAL FRAMING - Welding Certificates_PCI_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-10 |  | Submittal 05 40 00-34 Revision 0 COLD FORMED METAL FRAMING - Welding Certificates_PCI_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-09 02:00 |  | Submittal 05 40 00-34 Revision 0 COLD FORMED METAL FRAMING - Welding Certificates_PCI_MAM Reviewed.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-05-09 02:00 |  | Submittal 05 40 00-34 Revision 0 COLD FORMED METAL FRAMING - Welding Certificates_PCI_MAM Reviewed.pdf
05 40 00-035-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-035-00 COLD FORMED METAL FRAMING - Main Concourse T Bar Engineering | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-12 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-26 | 2021-03-26 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11965 | Received | For Review | 2021-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ye Zhang (Mortenson Construction) | 2021-03-26 | Submittal Number: 05 40 00-35.0 From: ALLIE ZIMMERMAN Final Due Date: 04/09/21 Subject: COLD FORMED METAL FRAMING - MAIN CONCOURSE T BAR ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 15500 | Forwarded | For Review | 2021-03-12 | Ye Zhang (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-19 | Submittal Number: 05 40 00-35.0 From: ALLIE ZIMMERMAN Final Due Date: 04/09/21 Subject: COLD FORMED METAL FRAMING - MAIN CONCOURSE T BAR ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12283 | Review Response | Approved as Noted | 2021-03-17 | Matt Ross (Thornton Tomasetti) | Kuebler Perry (Populous) |  | See comments within submittal. Clarify calcs if EOR assumptions are incorrect. Arch to review. | Info Exchange
| 12271 | Review Response | Revise and Resubmit | 2021-03-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 15872 | Responded and Closed | Revise and Resubmit | 2021-03-26 | Ye Zhang (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-12 |  | Submittal 05 40 00-35 Revision 0 COLD FORMED METAL FRAMING - Main Concourse T Bar Engineering_MAM Reviewed.pdf
| Forwarded |  | Ye Zhang (Mortenson Construction) | 1 | 2021-03-12 |  | Submittal 05 40 00-35 Revision 0 COLD FORMED METAL FRAMING - Main Concourse T Bar Engineering_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-11 02:00 |  | Submittal 05 40 00-35 Revision 0 COLD FORMED METAL FRAMING - Main Concourse T Bar Engineering_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-26 |  | Submittal 05 40 00-35 Revision 0 Reviewed_TT_POP.pdf
| Responded and Closed |  | Ye Zhang (Mortenson Construction) | 1 | 2021-03-12 |  | Submittal 05 40 00-35 Revision 0 COLD FORMED METAL FRAMING - Main Concourse T Bar Engineering_MAM Reviewed.pdf
05 40 00-035-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-035-01 COLD FORMED METAL FRAMING - Main Concourse T Bar Engineering | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-23 | 2021-04-16 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-04-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12493 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ye Zhang (Mortenson Construction) | 2021-04-23 | Submittal Number: 05 40 00-35.1 From: ALLIE ZIMMERMAN Final Due Date: 04/14/21 Subject: COLD FORMED METAL FRAMING - MAIN CONCOURSE T BAR ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 16181 | Forwarded | For Review | 2021-04-08 | Ye Zhang (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-15 | Submittal Number: 05 40 00-35.1 From: ALLIE ZIMMERMAN Final Due Date: 04/14/21 Subject: COLD FORMED METAL FRAMING - MAIN CONCOURSE T BAR ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12655 | Review Response | Approved as Noted | 2021-04-12 | Matt Ross (Thornton Tomasetti) | Kuebler Perry (Populous) |  | Arch to review. Do not need to resubmit. | Info Exchange
| 12617 | Review Response | Approved as Noted | 2021-04-16 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached shop drawings review. | Info Exchange
| 16335 | Responded and Closed | Approved as Noted | 2021-04-16 | Ye Zhang (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached shop drawings review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | Submittal 05 40 00-35 Revision 1 COLD FORMED METAL FRAMING - Main Concourse T Bar Engineering_MAM Reviewed.pdf
| Forwarded |  | Ye Zhang (Mortenson Construction) | 1 | 2021-04-08 |  | Submittal 05 40 00-35 Revision 1 COLD FORMED METAL FRAMING - Main Concourse T Bar Engineering_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-07 02:00 |  | Submittal 05 40 00-35 Revision 1 COLD FORMED METAL FRAMING - Main Concourse T Bar Engineering_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-16 |  | Submittal 05 40 00-35 Revision 1 CMFM - MC T Bar Engineering_MAM Review_TT_POP.pdf
| Responded and Closed |  | Ye Zhang (Mortenson Construction) | 1 | 2021-04-08 |  | Submittal 05 40 00-35 Revision 1 COLD FORMED METAL FRAMING - Main Concourse T Bar Engineering_MAM Reviewed.pdf
05 40 00-035-02 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-035-02 COLD FORMED METAL FRAMING - Main Concourse T Bar Engineering | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-06-02 07:00 | 2021-05-19 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13132 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ye Zhang (Mortenson Construction) | 2021-06-02 07:00 | Submittal Number: 05 40 00-35.2 From: ALLIE ZIMMERMAN Final Due Date: 05/31/21 Subject: COLD FORMED METAL FRAMING - MAIN CONCOURSE T BAR ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 16992 | Forwarded | For Review | 2021-05-18 | Ye Zhang (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-25 | Submittal Number: 05 40 00-35.2 From: ALLIE ZIMMERMAN Final Due Date: 05/31/21 Subject: COLD FORMED METAL FRAMING - MAIN CONCOURSE T BAR ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13166 | Review Response | Approved | 2021-05-18 | Matt Ross (Thornton Tomasetti) | Kuebler Perry (Populous); Chris Minter (Populous) |  | TT has no exceptions. | Info Exchange
| 17048 | Responded and Closed | Approved | 2021-05-19 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Ye Zhang (Mortenson Construction) | 1 | 2021-05-18 |  | 05 40 00-035-2 COLD FORMED METAL FRAMING - Main Concourse T Bar_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-18 |  | 05 40 00-035-2 COLD FORMED METAL FRAMING - Main Concourse T Bar_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-19 |  | 05 40 00-035-2 COLD FORMED METAL FRAMING - Main Concourse T Bar_MAM Reviewed_TT_POP.pdf
05 40 00-036-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-036-00 COLD-FORMED METAL FRAMING - RFI 3919 Slab Edge Framing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-16 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-30 | 2021-03-22 | 7 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12024 | Received | For Review | 2021-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-30 | Submittal Number: 05 40 00-36.0 From: YE ZHANG Final Due Date: 03/29/21 Subject: COLD-FORMED METAL FRAMING - RFI 3919 SLAB EDGE FRAMING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 15563 | Forwarded | For Review | 2021-03-15 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-22 | Submittal Number: 05 40 00-36.0 From: YE ZHANG Final Due Date: 03/29/21 Subject: COLD-FORMED METAL FRAMING - RFI 3919 SLAB EDGE FRAMING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12147 | Review Response | Approved | 2021-03-18 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | TT has no exceptions. | Info Exchange
| 15712 | Responded and Closed | Approved as Noted | 2021-03-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR RESPONSE. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-15 |  | 054000-0036-0-CFMF-SlabEdgeRFI3919-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-15 |  | 054000-0036-0-CFMF-SlabEdgeRFI3919-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-15 |  | 054000-0036-0-CFMF-SlabEdgeRFI3919-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-22 |  | 05 40 00-0036-CFMF-SlabEdgeRFI3919-MAM_TT_POP.pdf
05 40 00-037-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-037-00 COLD-FORMED METAL FRAMING - RFI 2546.2 Revised Upper Concourse Roof Support | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-22 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-06 07:00 | 2021-04-13 | 23 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12131 | Received | For Review | 2021-03-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-04-06 07:00 | Submittal Number: 05 40 00-37.0 From: YE ZHANG Final Due Date: 04/03/21 Subject: COLD-FORMED METAL FRAMING - RFI 2546.2 REVISED UPPER CONCOURSE ROOF SUPPORT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 15701 | Forwarded | For Review | 2021-03-22 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-29 | Submittal Number: 05 40 00-37.0 From: YE ZHANG Final Due Date: 04/03/21 Subject: COLD-FORMED METAL FRAMING - RFI 2546.2 REVISED UPPER CONCOURSE ROOF SUPPORT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12573 | Review Response | Approved as Noted | 2021-03-30 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Arch to review extents. | Info Exchange
| 16288 | Responded and Closed | Approved as Noted | 2021-04-13 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Arch to review extents. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-21 |  | 054000-0037-0-CFMF-RFI2546.2 Upper Con Roof Support-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-21 |  | 054000-0037-0-CFMF-RFI2546.2 Upper Con Roof Support-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-20 02:00 |  | 054000-0037-0-CFMF-RFI2546.2 Upper Con Roof Support-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-04-13 02:00 |  | 054000-0037-0-CFMF-RFI2546.2 Upper Con Roof Support-MAM_TT_POP.pdf
05 40 00-038-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-038-00 COLD FORMED METAL FRAMING - Main Con South LED Wall) | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-31 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-28 | 2021-04-26 | 27 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12614 | Received | For Review | 2021-03-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-28 | Submittal Number: 05 40 00-38.0 From: YE ZHANG Final Due Date: 04/14/21 Subject: COLD FORMED METAL FRAMING - Main Con South LED Wall) Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Email
| 16331 | Forwarded | For Review | 2021-04-15 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-14 | Submittal Number: 05 40 00-38.0 From: YE ZHANG Final Due Date: 04/14/21 Subject: COLD FORMED METAL FRAMING - Main Con South LED Wall) Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12769 | Review Response | Approved as Noted | 2021-04-22 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Arch to review. Revise and Resubmit if TT comments result in changes to calcs. Otherwise approved as noted. | Info Exchange
| 16507 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Arch to review. Revise and Resubmit if TT comments result in changes to calcs. Otherwise approved as noted. Revise and resubmit any details/CFMF being supported by the esc. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-15 |  | 054000-0038-0-CFMF-MainConSouthLEDWall-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-15 |  | 054000-0038-0-CFMF-MainConSouthLEDWall-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-15 |  | 054000-0038-0-CFMF-MainConSouthLEDWall-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-26 |  | 054000-0038-0-CFMF-MainConSouthLEDWall-MAM_TT_POP.pdf
05 40 00-038-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-038-01 COLD FORMED METAL FRAMING - Main Con South LED Wall | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-06-03 07:00 | 2021-05-24 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-05-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13169 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-06-03 07:00 | Submittal Number: 05 40 00-38.1 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: COLD FORMED METAL FRAMING - MAIN CON SOUTH LED WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17051 | Forwarded | For Review | 2021-05-19 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-26 | Submittal Number: 05 40 00-38.1 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: COLD FORMED METAL FRAMING - MAIN CON SOUTH LED WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13236 | Review Response | Revise and Resubmit | 2021-05-19 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | Revise SK-092A per previous Arch comments. Arch to review. | Info Exchange
| 17126 | Responded and Closed | Rejected | 2021-05-24 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Revise SK-092A per previous Arch comments. Arch to review. Previous comments where ignored. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 05 40 00-38 Revision 1 COLD FORMED METAL FRAMING - Main Con South LED Wall_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-18 |  | Submittal 05 40 00-38 Revision 1 COLD FORMED METAL FRAMING - Main Con South LED Wall_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-18 |  | Submittal 05 40 00-38 Revision 1 COLD FORMED METAL FRAMING - Main Con South LED Wall_MAM Reviewed.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-05-24 |  | 05 40 00-38-001_COLD FORMED METAL FRAMING - Main Con South LED Wall_MAM_TT_POP.pdf
05 40 00-038-02 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-038-02 COLD FORMED METAL FRAMING - Main Con South LED Wall | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-03 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Todd Spangler (Populous), Kuebler Perry (Populous) |  |  |  | 2021-06-17 | 2021-06-09 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13373 | Received | For Review | 2021-06-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-17 | Submittal Number: 05 40 00-38.2 From: ALLIE ZIMMERMAN Final Due Date: 06/16/21 Subject: COLD FORMED METAL FRAMING - MAIN CON SOUTH LED WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17301 | Forwarded | For Review | 2021-06-03 | Allie Zimmerman | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-10 | Submittal Number: 05 40 00-38.2 From: ALLIE ZIMMERMAN Final Due Date: 06/16/21 Subject: COLD FORMED METAL FRAMING - MAIN CON SOUTH LED WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13463 | Review Response | Revise and Resubmit | 2021-06-04 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | Soffit framing below Stair does not appear to be designed for seismic lateral forces. Arch to review submittal. | Info Exchange
| 17360 | Forwarded | For Review | 2021-06-07 | Josh Dobken (Populous) | Todd Spangler (Populous); Kuebler Perry (Populous) | 2021-06-14 | Submittal Number: 05 40 00-38.2 From: ALLIE ZIMMERMAN Final Due Date: 06/16/21 Subject: COLD FORMED METAL FRAMING - MAIN CON SOUTH LED WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17408 | Responded and Closed | Revise and Resubmit | 2021-06-09 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Soffit framing below Stair does not appear to be designed for seismic lateral forces. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-03 |  | Submittal 05 40 00-38 Revision 2 COLD FORMED METAL FRAMING - Main Con South LED Wall_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-06-03 |  | Submittal 05 40 00-38 Revision 2 COLD FORMED METAL FRAMING - Main Con South LED Wall_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-06-03 |  | Submittal 05 40 00-38 Revision 2 COLD FORMED METAL FRAMING - Main Con South LED Wall_MAM Reviewed.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-02 02:00 |  | Submittal 05 40 00-38 Revision 2 COLD FORMED METAL FRAMING - Main Con South LED Wall_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-06-09 |  | Submittal 05 40 00-38 Revision 2 COLD FORMED METAL FRAMING - Main Con South LED Wall_MAM_TT_POP.pdf
05 40 00-038-03 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-038-03 COLD FORMED METAL FRAMING - Main Con South LED Wall | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-28 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-13 07:00 | 2021-07-15 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13678 | Received | For Review | 2021-06-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-07-13 07:00 | Submittal Number: 05 40 00-38.3 From: ALLIE ZIMMERMAN Final Due Date: 07/12/21 Subject: COLD FORMED METAL FRAMING - MAIN CON SOUTH LED WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17713 | Forwarded | For Review | 2021-06-28 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-05 | Submittal Number: 05 40 00-38.3 From: ALLIE ZIMMERMAN Final Due Date: 07/12/21 Subject: COLD FORMED METAL FRAMING - MAIN CON SOUTH LED WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13946 | Review Response | Approved | 2021-07-15 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 18063 | Responded and Closed | Approved as Noted | 2021-07-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-28 |  | Submittal 05 40 00-38 Revision 3 COLD FORMED METAL FRAMING - Main Con South LED Wall_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-28 |  | Submittal 05 40 00-38 Revision 3 COLD FORMED METAL FRAMING - Main Con South LED Wall_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-07-15 |  | Submittal 05 40 00-38 Revision 3 CFMF - Main Con South LED Wall_MAM_TT.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-07-15 |  | Submittal 05 40 00-38 Revision 3 CFMF - Main Con South LED Wall_MAM_TT_POP.pdf
05 40 00-039-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-039-00 COLD-FORMED METAL FRAMING - Cooling Tower Screen Wall | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-23 | 2021-04-26 | 18 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12494 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-04-23 | Submittal Number: 05 40 00-39.0 From: YE ZHANG Final Due Date: 04/14/21 Subject: COLD-FORMED METAL FRAMING - COOLING TOWER SCREEN WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 16182 | Forwarded | For Review | 2021-04-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-15 | Submittal Number: 05 40 00-39.0 From: YE ZHANG Final Due Date: 04/14/21 Subject: COLD-FORMED METAL FRAMING - COOLING TOWER SCREEN WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12768 | Review Response | Approved | 2021-04-23 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached submittal TT-FK/MC ¦ 2021-04-23 | Info Exchange
| 16506 | Responded and Closed | Approved | 2021-04-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 054000-0039-0-CFMF-CoolingTowerScreenWall-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-08 |  | 054000-0039-0-CFMF-CoolingTowerScreenWall-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-04-08 |  | 054000-0039-0-CFMF-CoolingTowerScreenWall-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-04-26 |  | 054000-0039-0-CFMF-CoolingTowerScreenWall-MAM_TT_POP.pdf
05 40 00-040-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-040-00 CFMF-CL23 Support Framing Press Bridge-MAM | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-19 | 2021-04-06 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12397 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-19 | Submittal Number: 05 40 00-40.0 From: YE ZHANG Final Due Date: 04/14/21 Subject: COLD-FORMED METAL FRAMING - RFI 2546.2 REVISED UPPER CONCOURSE ROOF SUPPORT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Email
| 16068 | Forwarded | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-12 | Submittal Number: 05 40 00-40.0 From: YE ZHANG Final Due Date: 04/14/21 Subject: COLD-FORMED METAL FRAMING - RFI 2546.2 REVISED UPPER CONCOURSE ROOF SUPPORT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12423 | Review Response | Approved as Noted | 2021-04-05 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Josh Dobken (Populous); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Arch to advise if ceilings are accessible for maintenance/install/etc. If so, design for 20 psf LL or 200# localized point load over 2.5 sf area. Note CFMF span direction in typical bays differs from outer bays as shown on 3/S3-81. | Info Exchange
| 16097 | Responded and Closed | Approved as Noted | 2021-04-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Ceilings to be designed for maintenance accessibility. Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Arch to advise if ceilings are accessible for maintenance/install/etc. If so, design for 20 psf LL or 200# localized point load over 2.5 sf area. Note CFMF span direction in typical bays differs from outer bays as shown on 3/S3-81. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 05 40 00-040-0 CFMF-CL23 Support Framing Press Bridge-MAM.pdf
| Forwarded |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 05 40 00-040-0 CFMF-CL23 Support Framing Press Bridge-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-04 02:00 |  | 05 40 00-040-0 CFMF-CL23 Support Framing Press Bridge-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-04-06 02:00 |  | 054000-0040-0-CFMF-CL23SupportFramingPressBridge-MAM_TT_pop.pdf
05 40 00-041-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-041-00 COLD FORMED METAL FRAMING - Space Needle Back Bar Engineering | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-19 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-03 | 2021-05-10 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12631 | Received | For Review | 2021-04-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ye Zhang (Mortenson Construction) | 2021-05-03 | Submittal Number: 05 40 00-41.0 From: ALLIE ZIMMERMAN Final Due Date: 05/03/21 Subject: COLD FORMED METAL FRAMING - SPACE NEEDLE BACK BAR ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 16348 | Forwarded | For Review | 2021-04-19 | Ye Zhang (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-26 | Submittal Number: 05 40 00-41.0 From: ALLIE ZIMMERMAN Final Due Date: 05/03/21 Subject: COLD FORMED METAL FRAMING - SPACE NEEDLE BACK BAR ENGINEERING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13023 | Review Response | Approved as Noted/Resubmit | 2021-05-04 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Kuebler Perry (Populous) |  | Arch to review. Resubmit calcs with signature and date on seal. | Info Exchange
| 13002 | Review Response | Approved as Noted | 2021-05-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16824 | Responded and Closed | Approved as Noted | 2021-05-10 | Ye Zhang (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-18 |  | Submittal 05 40 00-41 Revision 0 COLD FORMED METAL FRAMING - Space Needle Back Bar Engineering_MAM Reviewed.pdf
| Forwarded |  | Ye Zhang (Mortenson Construction) | 1 | 2021-04-18 |  | Submittal 05 40 00-41 Revision 0 COLD FORMED METAL FRAMING - Space Needle Back Bar Engineering_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-17 02:00 |  | Submittal 05 40 00-41 Revision 0 COLD FORMED METAL FRAMING - Space Needle Back Bar Engineering_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-10 |  | Submittal 05 40 00-41 Revision 0 COLD FORMED METAL FRAMING -MAM _TT_POP.pdf
| Responded and Closed |  | Ye Zhang (Mortenson Construction) | 1 | 2021-04-18 |  | Submittal 05 40 00-41 Revision 0 COLD FORMED METAL FRAMING - Space Needle Back Bar Engineering_MAM Reviewed.pdf
05 40 00-042-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-042-00 COLD FORMED METAL FRAMING - Main Concourse Area A Monumental Stair Lid | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-16 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-30 | 2021-05-03 | 18 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-05-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12622 | Received | For Review | 2021-04-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-04-30 | Submittal Number: 05 40 00-42.0 From: ALLIE ZIMMERMAN Final Due Date: 04/30/21 Subject: COLD FORMED METAL FRAMING - MAIN CONCOURSE AREA A MONUMENTAL STAIR LID Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 16339 | Forwarded | For Review | 2021-04-16 | Allie Zimmerman | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-23 | Submittal Number: 05 40 00-42.0 From: ALLIE ZIMMERMAN Final Due Date: 04/30/21 Subject: COLD FORMED METAL FRAMING - MAIN CONCOURSE AREA A MONUMENTAL STAIR LID Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 12892 | Review Response | Approved as Noted | 2021-04-22 | Matt Ross (Thornton Tomasetti) | Chris Minter (Populous) |  | Arch to review. | Info Exchange
| 16679 | Responded and Closed | Approved | 2021-05-03 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-16 |  | Submittal 05 40 00-42 Revision 0 COLD FORMED METAL FRAMING - Main Concourse Area A Monumental Stair Lid_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-04-16 |  | Submittal 05 40 00-42 Revision 0 COLD FORMED METAL FRAMING - Main Concourse Area A Monumental Stair Lid_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-16 |  | Submittal 05 40 00-42 Revision 0 COLD FORMED METAL FRAMING - Main Concourse Area A Monumental Stair Lid_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-04-22 |  | 05 40 00-42-0 COLD FORMED METAL FRAMING_MAM Reviewed_TT.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-05-03 |  | 05 40 00-42-0 COLD FORMED METAL FRAMING_MAM Reviewed_TT-POP.pdf
05 40 00-043-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-043-00 COLD FORMED METAL FRAMING - Main Concourse Area B Monumental Stair Lid | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Review Response - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-06-02 07:00 | 2021-05-18 | 1 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13133 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-02 07:00 | Submittal Number: 05 40 00-43.0 From: ALLIE ZIMMERMAN Final Due Date: 05/25/21 Subject: COLD FORMED METAL FRAMING - MAIN CONCOURSE AREA B MONUMENTAL STAIR LID Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 16993 | Forwarded | For Review | 2021-05-18 | Allie Zimmerman | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-25 | Submittal Number: 05 40 00-43.0 From: ALLIE ZIMMERMAN Final Due Date: 05/25/21 Subject: COLD FORMED METAL FRAMING - MAIN CONCOURSE AREA B MONUMENTAL STAIR LID Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17039 | Responded and Closed | Approved | 2021-05-18 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 13238 | Review Response | Approved | 2021-05-20 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous); Allie Zimmerman |  | TT has no exceptions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 05 40 00-43 Revision 0 COLD FORMED METAL FRAMING - Main Concourse Area B Monumental Stair Lid_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 05 40 00-43 Revision 0 COLD FORMED METAL FRAMING - Main Concourse Area B Monumental Stair Lid_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 05 40 00-43 Revision 0 COLD FORMED METAL FRAMING - Main Concourse Area B Monumental Stair Lid_MAM Reviewed-POP.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-17 02:00 |  | Submittal 05 40 00-43 Revision 0 COLD FORMED METAL FRAMING - Main Concourse Area B Monumental Stair Lid_MAM Reviewed.pdf
05 40 00-044-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-044-00 COLD FORMED METAL FRAMING - RFI 4492 Plenum Framing | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-06-02 07:00 | 2021-05-24 | 7 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-05-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13134 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-02 07:00 | Submittal Number: 05 40 00-44.0 From: ALLIE ZIMMERMAN Final Due Date: 05/27/21 Subject: COLD FORMED METAL FRAMING - RFI 4492 PLENUM FRAMING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 16994 | Forwarded | For Review | 2021-05-18 | Allie Zimmerman | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-25 | Submittal Number: 05 40 00-44.0 From: ALLIE ZIMMERMAN Final Due Date: 05/27/21 Subject: COLD FORMED METAL FRAMING - RFI 4492 PLENUM FRAMING Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13235 | Review Response | Approved | 2021-05-20 | Franz Kogler (Thornton Tomasetti) | Allie Zimmerman |  | No Exceptions, see attached. | Info Exchange
| 17125 | Responded and Closed | Approved | 2021-05-24 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | No Exceptions, see attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 05 40 00-44 Revision 0 COLD FORMED METAL FRAMING - RFI 4492 Plenum Framing_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 05 40 00-44 Revision 0 COLD FORMED METAL FRAMING - RFI 4492 Plenum Framing_MAM Reviewed.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-05-18 |  | Submittal 05 40 00-44 Revision 0 COLD FORMED METAL FRAMING - RFI 4492 Plenum Framing_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-05-24 |  | 05 40 00-44 - 00_COLD FORMED METAL FRAMING - RFI 4492 Plenum Framing_TT_POP.pdf
05 40 00-045-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-045-00 COLD FORMED METAL FRAMING - Wire Connections North Upper Concourse Soffit | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-06-02 07:00 | 2021-05-27 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-05-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13135 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-02 07:00 | Submittal Number: 05 40 00-45.0 From: ALLIE ZIMMERMAN Final Due Date: 05/27/21 Subject: COLD FORMED METAL FRAMING - WIRE CONNECTIONS NORTH UPPER CONCOURSE SOFFIT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 16995 | Forwarded | For Review | 2021-05-18 | Allie Zimmerman | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-25 | Submittal Number: 05 40 00-45.0 From: ALLIE ZIMMERMAN Final Due Date: 05/27/21 Subject: COLD FORMED METAL FRAMING - WIRE CONNECTIONS NORTH UPPER CONCOURSE SOFFIT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13300 | Review Response | Approved | 2021-05-26 | Matt Ross (Thornton Tomasetti) | Allie Zimmerman |  | TT has no exceptions. Confirm soffit will be laterally braced for seismic per other detail. Arch to review. | Info Exchange
| 17204 | Responded and Closed | Approved as Noted | 2021-05-27 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 05 40 00-45 Revision 0 COLD FORMED METAL FRAMING - Wire Connections North Upper Concourse Soffit_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 05 40 00-45 Revision 0 COLD FORMED METAL FRAMING - Wire Connections North Upper Concourse Soffit_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-18 |  | Submittal 05 40 00-45 Revision 0 COLD FORMED METAL FRAMING - Wire Connections North Upper Concourse Soffit_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-05-26 |  | Submittal 05 40 00-45 Revision 0 COLD FORMED METAL FRAMING - Wire Connections North Upper Concourse Soffit_MAM Reviewed_TT.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-05-27 |  | Submittal 05 40 00-45 COLD FORMED METAL FRAMING -MAM _TT-POP.pdf
05 40 00-046-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-046-00 COLD FORMED METAL FRAMING - RFI 4555 Pole Mount TV Support | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-06-03 07:00 | 2021-05-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-05-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13170 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-06-03 07:00 | Submittal Number: 05 40 00-46.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: COLD FORMED METAL FRAMING - RFI 4555 POLE MOUNT TV SUPPORT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17052 | Forwarded | For Review | 2021-05-19 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-26 | Submittal Number: 05 40 00-46.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: COLD FORMED METAL FRAMING - RFI 4555 POLE MOUNT TV SUPPORT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13216 | Review Response | Approved | 2021-05-20 | Matt Ross (Thornton Tomasetti) | Kelsea Conkright (Populous) |  | TT has no exceptions. | Info Exchange
| 17106 | Responded and Closed | Approved | 2021-05-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 05 40 00-46 Revision 0 COLD FORMED METAL FRAMING - RFI 4555 Pole Mount TV Support_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-18 |  | Submittal 05 40 00-46 Revision 0 COLD FORMED METAL FRAMING - RFI 4555 Pole Mount TV Support_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-18 |  | Submittal 05 40 00-46 Revision 0 COLD FORMED METAL FRAMING - RFI 4555 Pole Mount TV Support_MAM Reviewed.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-20 |  | Submittal 05 40 00-46 Revision 0 COLD FORMED METAL FRAMING_TT_POP.pdf
05 40 00-047-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-047-00 COLD FORMED METAL FRAMING - NW Intake Corner | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-06-03 07:00 | 2021-05-24 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-05-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13171 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-03 07:00 | Submittal Number: 05 40 00-47.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: COLD FORMED METAL FRAMING - NW INTAKE CORNER Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17053 | Forwarded | For Review | 2021-05-19 | Allie Zimmerman | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-26 | Submittal Number: 05 40 00-47.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: COLD FORMED METAL FRAMING - NW INTAKE CORNER Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13234 | Review Response | Rejected | 2021-05-24 | Matt Ross (Thornton Tomasetti) | Allie Zimmerman |  | Calcs to be signed and sealed. | Info Exchange
| 17124 | Responded and Closed | Rejected | 2021-05-24 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Calcs to be signed and sealed. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 05 40 00-47 Revision 0 COLD FORMED METAL FRAMING - NW Intake Corner_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 05 40 00-47 Revision 0 COLD FORMED METAL FRAMING - NW Intake Corner_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-18 |  | Submittal 05 40 00-47 Revision 0 COLD FORMED METAL FRAMING - NW Intake Corner_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-05-24 |  | 05 40 00-47-00 COLD FORMED METAL FRAMING - NW Intake Corner_MAM_TT_POP.pdf
05 40 00-047-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-047-01 COLD FORMED METAL FRAMING - NW Intake Corner | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-03 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-17 | 2021-06-07 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13367 | Received | For Review | 2021-06-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-06-17 | Submittal Number: 05 40 00-47.1 From: ALLIE ZIMMERMAN Final Due Date: 06/16/21 Subject: COLD FORMED METAL FRAMING - NW INTAKE CORNER Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17296 | Forwarded | For Review | 2021-06-03 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-10 | Submittal Number: 05 40 00-47.1 From: ALLIE ZIMMERMAN Final Due Date: 06/16/21 Subject: COLD FORMED METAL FRAMING - NW INTAKE CORNER Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13422 | Review Response | Approved | 2021-06-04 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous); Shaina Burris (Populous) |  |  | Info Exchange
| 17355 | Responded and Closed | Approved as Noted | 2021-06-07 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-03 |  | Submittal 05 40 00-47 Revision 1 COLD FORMED METAL FRAMING - NW Intake Corner_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-03 |  | Submittal 05 40 00-47 Revision 1 COLD FORMED METAL FRAMING - NW Intake Corner_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-06-03 |  | Submittal 05 40 00-47 Revision 1 COLD FORMED METAL FRAMING - NW Intake Corner_MAM Reviewed.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-06-07 |  | 05 40 00-47 Revision 1 COLD FORMED METAL FRAMING - NW Intake Corner_MAM_TT_POP.pdf
05 40 00-048-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-048-00 COLD FORMED METAL FRAMING - Amazon Living Wall | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-07 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-21 | 2021-07-13 | 7 |  | Record Copies; Transfers; Submittals | 05 40 00-048-00-01 - 05 40 00-048-00 COLD FORMED METAL FRAMING - Amazon Living Wall | 3 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13821 | Received | For Review | 2021-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-07-21 | Submittal Number: 05 40 00-48.0 From: YE ZHANG Final Due Date: 07/14/21 Subject: COLD FORMED METAL FRAMING - AMAZON LIVING WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17893 | Forwarded | For Review | 2021-07-07 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-14 | Submittal Number: 05 40 00-48.0 From: YE ZHANG Final Due Date: 07/14/21 Subject: COLD FORMED METAL FRAMING - AMAZON LIVING WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13899 | Review Response | Approved as Noted/Resubmit | 2021-07-09 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Provide Missing detail and calcs for connection of headers to jambs. Rest of submittal is approved as noted. Arch to review. | Info Exchange
| 18002 | Responded and Closed | Approved as Noted/Resubmit | 2021-07-13 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-07 |  | 054000-0048-0-CFMF-AmazonLivingWall-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-07 |  | 054000-0048-0-CFMF-AmazonLivingWall-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-07-07 |  | 054000-0048-0-CFMF-AmazonLivingWall-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-07-13 |  | 054000-0048-0-CFMF-AmazonLivingWall-MAM_TT_POP.pdf
05 40 00-048-00-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-048-00 COLD FORMED METAL FRAMING - Amazon Living Wall | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 40 00-048-00 - 05 40 00-048-00 COLD FORMED METAL FRAMING - Amazon Living Wall | -1 | 2021-07-27
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-13 |  | 054000-0048-0-CFMF-AmazonLivingWall-MAM_TT_POP.pdf
05 40 00-048-01 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-048-01 COLD FORMED METAL FRAMING - Amazon Living Wall | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-16 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-30 | 2021-07-26 | 11 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13978 | Received | For Review | 2021-07-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-07-30 | Submittal Number: 05 40 00-48.1 From: YE ZHANG Final Due Date: 07/30/21 Subject: COLD FORMED METAL FRAMING - AMAZON LIVING WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 18080 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-23 | Submittal Number: 05 40 00-48.1 From: YE ZHANG Final Due Date: 07/30/21 Subject: COLD FORMED METAL FRAMING - AMAZON LIVING WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 14108 | Review Response | Approved | 2021-07-20 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Shaina Burris (Populous) |  | TT has no exceptions. | Info Exchange
| 18239 | Responded and Closed | Approved as Noted | 2021-07-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-16 |  | Submittal 05 40 00-48 Revision 1 COLD FORMED METAL FRAMING - Amazon Living Wall_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | Submittal 05 40 00-48 Revision 1 COLD FORMED METAL FRAMING - Amazon Living Wall_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-07-16 |  | Submittal 05 40 00-48 Revision 1 COLD FORMED METAL FRAMING - Amazon Living Wall_MAM Reviewed.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-07-26 |  | 05 40 00-48 Revision 1 COLD FORMED METAL FRAMING - Amazon Living Wall_MAM_TT_POP.pdf
05 40 00-049-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-049-00 COLD FORMED METAL FRAMING - Cooling Tower Conduit Clash Detail | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-09 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-23 | 2021-07-15 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13857 | Received | For Review | 2021-07-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-07-23 | Submittal Number: 05 40 00-49.0 From: YE ZHANG Final Due Date: 07/09/21 Subject: COLD FORMED METAL FRAMING - COOLING TOWER CONDUIT CLASH DETAIL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 17935 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-15 | Submittal Number: 05 40 00-49.0 From: YE ZHANG Final Due Date: 07/09/21 Subject: COLD FORMED METAL FRAMING - COOLING TOWER CONDUIT CLASH DETAIL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 13960 | Review Response | Approved | 2021-07-14 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | No exceptions, see attached. | Info Exchange
| 18062 | Responded and Closed | Approved | 2021-07-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-08 |  | 054000-0049-0-CFMF-CoolingTowerConduitClash-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-08 |  | 054000-0049-0-CFMF-CoolingTowerConduitClash-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-07-08 |  | 054000-0049-0-CFMF-CoolingTowerConduitClash-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-07-15 |  | 054000-0049-0-CFMF-CoolingTowerConduitClash-MAM_TT_POP.pdf
05 40 00-050-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-050-00 COLD FORMED METAL FRAMING - Craft Beer Bar Roof Signage Support | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-16 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-30 | 2021-07-26 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-07-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13971 | Received | For Review | 2021-07-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-07-30 | Submittal Number: 05 40 00-50.0 From: ALLIE ZIMMERMAN Final Due Date: 07/30/21 Subject: COLD FORMED METAL FRAMING - CRAFT BEER BAR ROOF SIGNAGE SUPPORT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 18073 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-23 | Submittal Number: 05 40 00-50.0 From: ALLIE ZIMMERMAN Final Due Date: 07/30/21 Subject: COLD FORMED METAL FRAMING - CRAFT BEER BAR ROOF SIGNAGE SUPPORT Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 14107 | Review Response | Approved as Noted | 2021-07-26 | Matt Ross (Thornton Tomasetti) | Geoff Cheong; Kuebler Perry (Populous); Shaina Burris (Populous) |  |  | Info Exchange
| 18238 | Responded and Closed | Approved as Noted | 2021-07-26 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-16 |  | Submittal 05 40 00-50 Revision 0 COLD FORMED METAL FRAMING - Craft Beer Bar Roof Signage Support_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | Submittal 05 40 00-50 Revision 0 COLD FORMED METAL FRAMING - Craft Beer Bar Roof Signage Support_MAM Reviewed.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-07-16 |  | Submittal 05 40 00-50 Revision 0 COLD FORMED METAL FRAMING - Craft Beer Bar Roof Signage Support_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-26 |  | Submittal 05 40 00-50 Revision 0 COLD FORMED METAL FRAMING - Craft Beer Bar Roof Signage Support_MAM Reviewed_TT_POP.pdf
05 40 00-051-00 | 05 40 00 - COLD-FORMED METAL FRAMING | 05 40 00-051-00 COLD FORMED METAL FRAMING - Upper Concourse Coors Light Die Wall | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-16 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-30 | 2021-07-20 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13992 | Received | For Review | 2021-07-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-07-30 | Submittal Number: 05 40 00-51.0 From: ALLIE ZIMMERMAN Final Due Date: 07/30/21 Subject: COLD FORMED METAL FRAMING - UPPER CONCOURSE COORS LIGHT DIE WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 18097 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-23 | Submittal Number: 05 40 00-51.0 From: ALLIE ZIMMERMAN Final Due Date: 07/30/21 Subject: COLD FORMED METAL FRAMING - UPPER CONCOURSE COORS LIGHT DIE WALL Description: Spec Section: 05 40 00 - COLD-FORMED METAL FRAMING Status: OPEN | Info Exchange
| 14033 | Review Response | Approved | 2021-07-19 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 14015 | Review Response | Approved as Noted | 2021-07-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18135 | Responded and Closed | Approved as Noted | 2021-07-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-16 |  | Submittal 05 40 00-51 Revision 0 COLD FORMED METAL FRAMING - Upper Concourse Coors Light Die Wall.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | Submittal 05 40 00-51 Revision 0 COLD FORMED METAL FRAMING - Upper Concourse Coors Light Die Wall.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-07-15 02:00 |  | Submittal 05 40 00-51 Revision 0 COLD FORMED METAL FRAMING - Upper Concourse Coors Light Die Wall.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-20 |  | Submittal 05 40 00-51 Revision CFMF - UC Coors Light Die Wall_TT_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-16 |  | Submittal 05 40 00-51 Revision 0 COLD FORMED METAL FRAMING - Upper Concourse Coors Light Die Wall.pdf
05 50 00-001-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-001-00 Shop Drawings - Top-of-CMU-Wall Supports | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-14 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-03 | 2020-08-07 | 25 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-08-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06943 | Received | For Review | 2020-07-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-03 | Submittal Number: 05 50 00-1.0 From: DOMINGO SAMPAYO Final Due Date: 07/27/20 Subject: SHOP DRAWINGS - TOP-OF-CMU-WALL SUPPORTS Description: PRODUCT DATA : FOR THE FOLLOWING: 1. NONSLIP AGGREGATES AND NONSLIP-AGGREGATE SURFACE FINISHES. 2. METAL NOSINGS AND TREADS. 3. PAINT PRODUCTS. 4. GROUT. 5. SLOTTED CHANNEL FRAMING. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09301 | Forwarded | For Review | 2020-07-14 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-21 | Submittal Number: 05 50 00-1.0 From: DOMINGO SAMPAYO Final Due Date: 07/27/20 Subject: SHOP DRAWINGS - TOP-OF-CMU-WALL SUPPORTS Description: PRODUCT DATA : FOR THE FOLLOWING: 1. NONSLIP AGGREGATES AND NONSLIP-AGGREGATE SURFACE FINISHES. 2. METAL NOSINGS AND TREADS. 3. PAINT PRODUCTS. 4. GROUT. 5. SLOTTED CHANNEL FRAMING. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 07215 | Review Response | Revise and Resubmit | 2020-07-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09938 | Responded and Closed | Revise and Resubmit | 2020-08-07 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | CM TO COORDINATE ALL CMU WALL LOCATIONS PER SUBMITTALS 04 20 00-012 AND 04 20 00-011. REFER TO A0-01 FOR TOP OF MASONRY AT STACKED WALL CONDITIONS AND WALL MODIFIERS, TYP. REFER TO A2 SERIES ARCHITECTURAL SHEETS FOR WALL TYPES. Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| 09982 | Sent | For Information Only | 2020-08-10 | Todd Spangler (Populous) | Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 05 50 00-1 Shop Drawings - Top-of-CMU-Wall Supports.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 05 50 00-1 Shop Drawings - Top-of-CMU-Wall Supports.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-12 02:00 |  | 05 50 00-1 Shop Drawings - Top-of-CMU-Wall Supports.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-07 02:00 |  | 05 50 00-1 Shop Drawings - Top-of-CMU-Wall Supports_TT REVIEW_POP.pdf
| Sent |  | Todd Spangler (Populous) | 1 | 2020-07-13 |  | 05 50 00-1 Shop Drawings - Top-of-CMU-Wall Supports.pdf
05 50 00-001-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-001-01 Shop Drawings - Top-of-CMU-Wall Supports | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-11 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-31 | 2020-08-31 | 21 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-08-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07494 | Received | For Review | 2020-08-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-31 | Submittal Number: 05 50 00-1.1 From: DOMINGO SAMPAYO Final Due Date: 08/21/20 Subject: SHOP DRAWINGS - TOP-OF-CMU-WALL SUPPORTS Description: PRODUCT DATA : FOR THE FOLLOWING: 1. NONSLIP AGGREGATES AND NONSLIP-AGGREGATE SURFACE FINISHES. 2. METAL NOSINGS AND TREADS. 3. PAINT PRODUCTS. 4. GROUT. 5. SLOTTED CHANNEL FRAMING. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09979 | Forwarded | For Review | 2020-08-10 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-17 | Submittal Number: 05 50 00-1.1 From: DOMINGO SAMPAYO Final Due Date: 08/21/20 Subject: SHOP DRAWINGS - TOP-OF-CMU-WALL SUPPORTS Description: PRODUCT DATA : FOR THE FOLLOWING: 1. NONSLIP AGGREGATES AND NONSLIP-AGGREGATE SURFACE FINISHES. 2. METAL NOSINGS AND TREADS. 3. PAINT PRODUCTS. 4. GROUT. 5. SLOTTED CHANNEL FRAMING. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 07821 | Review Response | Approved as Noted | 2020-08-28 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Refer to comments on first page of submittal. Since no changes were clouded, TT has only review parts of submittal that were commented on in the previous review as well as new erection plans. All other parts of submittal are assumed to have remained unchanged from previous review. If there are other parts of this submittal that have been revised since the original rev, this submittal is to be resubmit with clouds indicated areas that have been revised. | Info Exchange
| 10401 | Responded and Closed | Approved as Noted | 2020-08-28 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 10440 | Reopened | Additional Information | 2020-08-31 11:57 | Chris Minter (Populous) |  |  | error with attachment.
| 10441 | Responded and Closed | Approved as Noted | 2020-08-31 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See correct attachment. Approved as Noted. CLM | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-10 |  | 05 50 00-1 Rev1 SD - Top-of-CMU-Wall Supports.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-10 |  | 05 50 00-1 Rev1 SD - Top-of-CMU-Wall Supports.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-10 |  | 05 50 00-1 Rev1 SD - Top-of-CMU-Wall Supports.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-08-28 |  | 05 50 00-1 Rev1 SD - Top-of-CMU-Wall Supports_TT REVIEW.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-08-07 |  | 05 50 00-1 Shop Drawings - Top-of-CMU-Wall Supports_TT REVIEW_POP.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-08-28 |  | 05 50 00-1 Rev1 SD - Top-of-CMU-Wall Supports_TT REVIEW-POP.pdf
05 50 00-012-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-012-01 Corner Guards | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-14 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-28 | 2020-08-24 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07570 | Received | For Review | 2020-08-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-28 | Submittal Number: 05 50 00-12.1 From: CHLOE HOEPFINGER Final Due Date: 08/21/20 Subject: CORNER GUARDS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10076 | Forwarded | For Review | 2020-08-17 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-24 | Submittal Number: 05 50 00-12.1 From: CHLOE HOEPFINGER Final Due Date: 08/21/20 Subject: CORNER GUARDS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 07716 | Review Response | Approved as Noted | 2020-08-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 10265 | Responded and Closed | Approved as Noted | 2020-08-24 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-14 |  | 05 50 00-12 Rev1 Corner Guards.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-14 |  | 05 50 00-12 Rev1 Corner Guards.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-14 |  | 05 50 00-12 Rev1 Corner Guards.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-24 |  | 05 50 00-12 Rev1 Corner Guards_TT_POP.pdf
05 50 00-013-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-013-00 Pipe Bollards | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-19 | 2020-08-05 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-08-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07361 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 05 50 00-13.0 From: CHLOE HOEPFINGER Final Due Date: 08/18/20 Subject: PIPE BOLLARDS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09812 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-12 | Submittal Number: 05 50 00-13.0 From: CHLOE HOEPFINGER Final Due Date: 08/18/20 Subject: PIPE BOLLARDS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09843 | Responded and Closed | Rejected | 2020-08-05 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Submittal rejected - was not prepared for Architect review. Submittal has been sent back into Contractor's court. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-04 |  | CPA - Bollard Submittal Review 8.3.20.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-04 |  | 05 50 00-13.0 CPA - Bollard Submittal Review 8.3.20.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-05 02:00 |  | 05 50 00-13.0 CPA - Bollard Submittal Review 8.3.20_POP.pdf
05 50 00-013-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-013-01 Pipe Bollards | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-06 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-20 | 2020-08-31 | 26 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2020-08-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07391 | Received | For Review | 2020-08-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-20 | Submittal Number: 05 50 00-13.1 From: CHLOE HOEPFINGER Final Due Date: 08/18/20 Subject: PIPE BOLLARDS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09854 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-12 | Submittal Number: 05 50 00-13.1 From: CHLOE HOEPFINGER Final Due Date: 08/18/20 Subject: PIPE BOLLARDS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10459 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-31 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Approved as noted. Still missing bollards from contract documents. See attached arch sheets for locations. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-05 |  | 05 50 00-13 Rev1 Pipe Bollards.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-05 |  | 05 50 00-13 Rev1 Pipe Bollards.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-31 |  | 05 50 00-13 Rev1 Pipe Bollards_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-31 |  | A2-1G - EVENT LEVEL - AREAS G&H.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-31 |  | A2-2E - MECHANICAL MEZZANINE LEVEL - AREA E.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-31 |  | A2-3E - MAIN CONCOURSE LEVEL - AREA E.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-31 |  | A2-4E - SUITE LEVEL - AREA E.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-31 |  | A2-4F - SUITE LEVEL - AREA F.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-31 |  | A3-07-2 - ENLARGED PLANS - COOLING TOWER.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-31 |  | A8-02-25 - PLAN DETAILS - GARAGE.pdf
05 50 00-013-02 | 05 50 00 - METAL FABRICATIONS | 05 50 00-013-02 Pipe Bollards | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2020-10-12 | 2020-10-14 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-10-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08382 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 05 50 00-13.2 From: DOMINGO SAMPAYO Final Due Date: 09/28/20 Subject: PIPE BOLLARDS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11114 | Forwarded | For Review | 2020-09-28 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-05 | Submittal Number: 05 50 00-13.2 From: DOMINGO SAMPAYO Final Due Date: 09/28/20 Subject: PIPE BOLLARDS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11588 | Forwarded | For Review | 2020-10-13 | Josh Dobken (Populous) | Tom Usher (Populous); Chris Minter (Populous) | 2020-10-12 | Submittal Number: 05 50 00-13.2 From: DOMINGO SAMPAYO Final Due Date: 09/28/20 Subject: PIPE BOLLARDS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11624 | Responded and Closed | Approved as Noted | 2020-10-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Architect comments are based on information available through CCD077 to be issued 10/16/2020. See attached. Architect recommends owner review all bollards prior to installation. Refer to comments in specific areas. | Info Exchange
| 11827 | Sent | For Information Only | 2020-10-23 | Todd Spangler (Populous) | Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Architect comments are based on information available through CCD077 to be issued 10/16/2020. See attached. Architect recommends owner review all bollards prior to installation. Refer to comments in specific areas. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-28 |  | 05 50 00-13 R2 Pipe Bollards.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-28 |  | 05 50 00-13 R2 Pipe Bollards.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-27 02:00 |  | 05 50 00-13 R2 Pipe Bollards.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-14 02:00 |  | 05 50 00-13 R2 Pipe Bollards_pop.pdf
| Sent |  | Todd Spangler (Populous) | 1 | 2020-09-27 |  | 05 50 00-13 R2 Pipe Bollards.pdf
05 50 00-017-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-017-00 Cable Pass Thrus | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-19 | 2020-08-10 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-08-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07350 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 05 50 00-17.0 From: CHLOE HOEPFINGER Final Due Date: 08/21/20 Subject: CABLE PASS THRUS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09799 | Forwarded | For Review | 2020-08-04 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-11 | Submittal Number: 05 50 00-17.0 From: CHLOE HOEPFINGER Final Due Date: 08/21/20 Subject: CABLE PASS THRUS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 07482 | Review Response | Approved | 2020-08-05 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. Contractor to coordinate reinforcement around CMU openings with details on sheet S6-02. | Info Exchange
| 09964 | Responded and Closed | Approved | 2020-08-10 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | TT has no exceptions. Contractor to coordinate reinforcement around CMU openings with details on sheet S6-02. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-04 |  | 05 50 00-17 Cable Pass Thrus.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-04 |  | 05 50 00-17 Cable Pass Thrus.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-04 |  | 05 50 00-17 Cable Pass Thrus.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-10 |  | 05 50 00-17 Cable Pass Thrus_TT_POP.pdf
05 50 00-019-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-019-00 OHD Support | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-09 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-23 | 2020-09-24 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08000 | Received | For Review | 2020-09-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-09-23 | Submittal Number: 05 50 00-19.0 From: DOMINGO SAMPAYO Final Due Date: 09/17/20 Subject: OHD SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10632 | Forwarded | For Review | 2020-09-09 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-16 | Submittal Number: 05 50 00-19.0 From: DOMINGO SAMPAYO Final Due Date: 09/17/20 Subject: OHD SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11046 | Responded and Closed | Approved as Noted | 2020-09-24 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-08 |  | 05 50 00-19 OHD Support.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-08 |  | 05 50 00-19 OHD Support.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-09-24 |  | 05 50 00-19 OHD Support-POP.pdf
05 50 00-020-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-020-00 Garage Intake Ladder | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-21 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-05 | 2020-09-22 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08237 | Received | For Review | 2020-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-05 | Submittal Number: 05 50 00-20.0 From: DOMINGO SAMPAYO Final Due Date: 10/02/20 Subject: GARAGE INTAKE LADDER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10942 | Forwarded | For Review | 2020-09-21 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-28 | Submittal Number: 05 50 00-20.0 From: DOMINGO SAMPAYO Final Due Date: 10/02/20 Subject: GARAGE INTAKE LADDER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 08263 | Review Response | Rejected | 2020-09-21 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Contractor to provide calcs for ladder and connections for EOR to review. | Info Exchange
| 10967 | Responded and Closed | Rejected | 2020-09-22 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Matt Ross (Thornton Tomasetti) Remarks: Contractor to provide calcs for ladder and connections for EOR to review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 05 50 00-20 Garage Intake Ladder.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-21 |  | 05 50 00-20 Garage Intake Ladder.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-20 02:00 |  | 05 50 00-20 Garage Intake Ladder.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-22 02:00 |  | 05 50 00-20 Garage Intake Ladder_TT REVIEW_pop.pdf
05 50 00-020-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-020-01 Garage Intake Ladder | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-13 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-27 | 2020-11-02 | 21 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-11-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08752 | Received | For Review | 2020-10-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-27 | Submittal Number: 05 50 00-20.1 From: DOMINGO SAMPAYO Final Due Date: 10/12/20 Subject: GARAGE INTAKE LADDER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11566 | Forwarded | For Review | 2020-10-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-20 | Submittal Number: 05 50 00-20.1 From: DOMINGO SAMPAYO Final Due Date: 10/12/20 Subject: GARAGE INTAKE LADDER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09168 | Review Response | Approved as Noted | 2020-10-28 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Arch to review dimensions. | Info Exchange
| 12102 | Responded and Closed | Approved as Noted | 2020-11-02 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 12117 | Sent | For Information Only | 2020-11-02 | Josh Dobken (Populous) | Domingo Sampayo (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Arch to review dimensions. Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-13 |  | 05 50 00-20 R1 Garage Intake Ladder.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-13 |  | 05 50 00-20 R1 Garage Intake Ladder.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-13 |  | 05 50 00-20 R1 Garage Intake Ladder.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-02 |  | 05 50 00-20 R1 Garage Intake Ladder_TT REVIEW-POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-10-12 02:00 |  | 05 50 00-20 R1 Garage Intake Ladder.pdf
05 50 00-021-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-021-00 Pit Ladder Zamboni Room | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-21 | Responded and Closed - Rejected |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-05 | 2020-09-22 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-09-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08238 | Received | For Review | 2020-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-05 | Submittal Number: 05 50 00-21.0 From: DOMINGO SAMPAYO Final Due Date: 10/05/20 Subject: PIT LADDER ZAMBONI ROOM Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10943 | Forwarded | For Review | 2020-09-21 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-28 | Submittal Number: 05 50 00-21.0 From: DOMINGO SAMPAYO Final Due Date: 10/05/20 Subject: PIT LADDER ZAMBONI ROOM Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10950 | Forwarded | For Review | 2020-09-21 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-28 | Submittal Number: 05 50 00-21.0 From: DOMINGO SAMPAYO Final Due Date: 10/05/20 Subject: PIT LADDER ZAMBONI ROOM Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 08262 | Review Response | Rejected | 2020-09-22 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Provide Calcs and Loads Imposed for EOR to review. | Info Exchange
| 10966 | Responded and Closed | Rejected | 2020-09-22 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Matt Ross (Thornton Tomasetti) Remarks: Provide Calcs and Loads Imposed for EOR to review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 05 50 00-21 Pit Ladder Zamboni Room.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-21 |  | 05 50 00-21 Pit Ladder Zamboni Room.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-21 |  | 05 50 00-21 Pit Ladder Zamboni Room.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-20 02:00 |  | 05 50 00-21 Pit Ladder Zamboni Room.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-22 02:00 |  | 05 50 00-21 Pit Ladder Zamboni Room_TT_pop.pdf
05 50 00-021-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-021-01 Pit Ladder Zamboni Room | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-13 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-27 | 2020-11-02 | 21 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-11-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08753 | Received | For Review | 2020-10-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-27 | Submittal Number: 05 50 00-21.1 From: DOMINGO SAMPAYO Final Due Date: 10/12/20 Subject: PIT LADDER ZAMBONI ROOM Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11567 | Forwarded | For Review | 2020-10-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-20 | Submittal Number: 05 50 00-21.1 From: DOMINGO SAMPAYO Final Due Date: 10/12/20 Subject: PIT LADDER ZAMBONI ROOM Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09167 | Review Response | Approved as Noted | 2020-10-28 | Raymond Chou (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 12097 | Responded and Closed | Approved as Noted | 2020-11-02 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 12118 | Sent | For Information Only | 2020-11-02 | Josh Dobken (Populous) | Domingo Sampayo (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Raymond Chou (Thornton Tomasetti) Remarks: Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-13 |  | 05 50 00-21 R1 Pit Ladder Zamboni Room.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-13 |  | 05 50 00-21 R1 Pit Ladder Zamboni Room.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2020-10-28 |  | 05 50 00-21 R1 Pit Ladder Zamboni Room_TT Reviewed.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-02 |  | 05 50 00-21 R1 Pit Ladder Zamboni Room_TT Reviewed-POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-10-12 02:00 |  | 05 50 00-21 R1 Pit Ladder Zamboni Room.pdf
05 50 00-022-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-022-01 Dressing Room Angle | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-26 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-09 | 2020-11-09 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08989 | Received | For Review | 2020-10-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-11-09 | Submittal Number: 05 50 00-22.1 From: DOMINGO SAMPAYO Final Due Date: 11/06/20 Subject: DRESSING ROOM ANGLE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11861 | Forwarded | For Review | 2020-10-26 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-02 | Submittal Number: 05 50 00-22.1 From: DOMINGO SAMPAYO Final Due Date: 11/06/20 Subject: DRESSING ROOM ANGLE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09290 | Review Response | Approved | 2020-11-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Glass panel will be removed from project per client request. No additional panel will be added. | Info Exchange
| 12259 | Responded and Closed | Approved | 2020-11-09 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Glass panel will be removed from project per client request. No additional panel will be added. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-23 |  | 05 50 00-22 R1 Dressing Room Angle.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-23 |  | 05 50 00-22 R1 Dressing Room Angle.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-09 |  | 05 50 00-22 R1 Dressing Room Angle_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-23 |  | 05 50 00-22 R1 Dressing Room Angle.pdf
05 50 00-023-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-023-00 Elevator Sump Pits | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-26 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-09 | 2020-11-23 | 29 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-11-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08988 | Received | For Review | 2020-10-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-11-09 | Submittal Number: 05 50 00-23.0 From: DOMINGO SAMPAYO Final Due Date: 11/06/20 Subject: ELEVATOR SUMP PITS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11860 | Forwarded | For Review | 2020-10-26 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-02 | Submittal Number: 05 50 00-23.0 From: DOMINGO SAMPAYO Final Due Date: 11/06/20 Subject: ELEVATOR SUMP PITS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09190 | Review Response | Revise and Resubmit | 2020-10-28 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Provide Calcs as requested for sump pit cover supports. Arch to review dimensions. | Info Exchange
| 12726 | Responded and Closed | Revise and Resubmit | 2020-11-23 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-23 |  | 05 50 00-23 Elevator Sump Pits.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-23 |  | 05 50 00-23 Elevator Sump Pits.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-23 |  | 05 50 00-23 Elevator Sump Pits.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-23 |  | 05 50 00-23 Elevator Sump Pits_TT_POP.pdf
05 50 00-023-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-023-01 Freight Elevator Ladder & Sump Pit Cover | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-09 | Closed - Void |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-23 |  | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10042 | Received | For Review | 2020-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-23 | Submittal Number: 05 50 00-23.1 From: DOMINGO SAMPAYO Final Due Date: 12/28/20 Subject: FREIGHT ELEVATOR LADDER & SUMP PIT COVER Description: REVISION: ELEVATOR PIT LADDER SHOP DRAWINGS TO ONLY INCLUDE FREIGHT LADDER & SUMP PIT COVER (ANGLES TO BE POST-INSTALLED) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13140 | Forwarded | For Review | 2020-12-09 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-16 | Submittal Number: 05 50 00-23.1 From: DOMINGO SAMPAYO Final Due Date: 12/28/20 Subject: FREIGHT ELEVATOR LADDER & SUMP PIT COVER Description: REVISION: ELEVATOR PIT LADDER SHOP DRAWINGS TO ONLY INCLUDE FREIGHT LADDER & SUMP PIT COVER (ANGLES TO BE POST-INSTALLED) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13195 | Closed | Void | 2020-12-10 | Josh Dobken (Populous) |  |  | Closed per email from Domingo Sampayo. Email attached.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-08 |  | 05 50 00-23 R1 Freight Elevator Ladder & Sump Pit Cover.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-08 |  | 05 50 00-23 R1 Freight Elevator Ladder & Sump Pit Cover.pdf
05 50 00-023-02 | 05 50 00 - METAL FABRICATIONS | 05 50 00-023-02 Freight Elevator Ladder & Sump Pit Cover | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-13 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-28 08:00 | 2021-02-09 | 28 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10676 | Received | For Review | 2021-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-28 08:00 | Submittal Number: 05 50 00-23.2 From: DOMINGO SAMPAYO Final Due Date: 01/28/21 Subject: FREIGHT ELEVATOR LADDER & SUMP PIT COVER Description: REVISION: ELEVATOR PIT LADDER SHOP DRAWINGS TO ONLY INCLUDE FREIGHT LADDER & SUMP PIT COVER (POST-INSTALLED) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13895 | Forwarded | For Review | 2021-01-13 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-20 | Submittal Number: 05 50 00-23.2 From: DOMINGO SAMPAYO Final Due Date: 01/28/21 Subject: FREIGHT ELEVATOR LADDER & SUMP PIT COVER Description: REVISION: ELEVATOR PIT LADDER SHOP DRAWINGS TO ONLY INCLUDE FREIGHT LADDER & SUMP PIT COVER (POST-INSTALLED) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11272 | Review Response | Approved as Noted | 2021-01-25 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 14622 | Responded and Closed | Approved as Noted | 2021-02-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 05 50 00-23.2 Freight Elevator Ladder & Sump Pit Cover (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-13 |  | 05 50 00-23.2 Freight Elevator Ladder & Sump Pit Cover (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-13 |  | 05 50 00-23.2 Freight Elevator Ladder & Sump Pit Cover (MAM Review).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-09 |  | 05 50 00-23.2 Freight Elevator Ladder & Sump Pit Cover MAM_TT_POP.pdf
05 50 00-025-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-025-00 Cage Ladders - Rails - Platforms (NW Snorkel) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-04 | 2020-12-10 | 23 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09555 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-04 | Submittal Number: 05 50 00-25.0 From: DOMINGO SAMPAYO Final Due Date: 12/02/20 Subject: CAGE LADDERS - RAILS - PLATFORMS (NW SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12575 | Forwarded | For Review | 2020-11-18 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-25 | Submittal Number: 05 50 00-25.0 From: DOMINGO SAMPAYO Final Due Date: 12/02/20 Subject: CAGE LADDERS - RAILS - PLATFORMS (NW SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10081 | Review Response | Revise and Resubmit | 2020-12-09 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Refer to TT comments within submittal. | Info Exchange
| 13179 | Responded and Closed | Revise and Resubmit | 2020-12-10 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to TT comments within submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 05 50 00-25 Cage Ladders-Rails-Platf (NW S).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 05 50 00-25 Cage Ladders-Rails-Platf (NW S).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-18 |  | 05 50 00-25 Cage Ladders-Rails-Platf (NW S).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-18 |  | 05 50 00-25 Cage Ladders-Rails-Platf (NW S).pdf
05 50 00-025-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-025-01 Cage Ladders - Rails - Platforms (NE Snorkel) | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-05 | 2021-02-11 | 21 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10885 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-05 | Submittal Number: 05 50 00-25.1 From: DOMINGO SAMPAYO Final Due Date: 02/05/21 Subject: CAGE LADDERS - RAILS - PLATFORMS (NE SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14136 | Forwarded | For Review | 2021-01-21 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-28 | Submittal Number: 05 50 00-25.1 From: DOMINGO SAMPAYO Final Due Date: 02/05/21 Subject: CAGE LADDERS - RAILS - PLATFORMS (NE SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11315 | Review Response | Approved as Noted | 2021-01-25 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 14701 | Responded and Closed | Approved as Noted | 2021-02-11 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-21 |  | 05 50 00-25.1 NE Snorkel Cage Ladders Rails Platforms (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-21 |  | 05 50 00-25.1 NE Snorkel Cage Ladders Rails Platforms (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-21 |  | 05 50 00-25.1 NE Snorkel Cage Ladders Rails Platforms (MAM Review).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-11 |  | 05 50 00-25.1 NE Snorkel Cage Ladders Rails Platforms (MAM Review)_TT-POP.pdf
05 50 00-027-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-027-00 Atrium Gutter | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-19 | 2020-08-05 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-08-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07362 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 05 50 00-27.0 From: CHLOE HOEPFINGER Final Due Date: 08/21/20 Subject: ATRIUM GUTTER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09813 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-12 | Submittal Number: 05 50 00-27.0 From: CHLOE HOEPFINGER Final Due Date: 08/21/20 Subject: ATRIUM GUTTER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09842 | Responded and Closed | Rejected | 2020-08-05 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Rejected - submittal was not prepared for Architect review and has been returned to Contractor court. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-04 |  | 05 50 00-27 Atrium Gutter.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-04 |  | 05 50 00-27 Atrium Gutter.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-05 02:00 |  | 05 50 00-27 Atrium Gutter_POP.pdf
05 50 00-027-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-027-01 Atrium Gutter | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-12 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-08-26 | 2020-08-25 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07521 | Received | For Review | 2020-08-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-26 | Submittal Number: 05 50 00-27.1 From: CHLOE HOEPFINGER Final Due Date: 08/24/20 Subject: ATRIUM GUTTER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10014 | Forwarded | For Review | 2020-08-11 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-18 | Submittal Number: 05 50 00-27.1 From: CHLOE HOEPFINGER Final Due Date: 08/24/20 Subject: ATRIUM GUTTER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10294 | Forwarded | For Review | 2020-08-25 | Todd Spangler (Populous) | Matt Ross (Thornton Tomasetti) |  | Submittal Number: 05 50 00-27.1 From: CHLOE HOEPFINGER Final Due Date: 08/24/20 Subject: ATRIUM GUTTER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 07741 | Review Response | Approved as Noted | 2020-08-25 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  |  | Info Exchange
| 10307 | Responded and Closed | Approved as Noted | 2020-08-25 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-11 |  | 05 50 00-27 Rev1 Atrium Gutter.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-11 |  | 05 50 00-27 Rev1 Atrium Gutter.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-08-11 |  | 05 50 00-27 Rev1 Atrium Gutter.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-11 |  | 05 50 00-27 Rev1 Atrium Gutter.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-25 |  | 05 50 00-27 Rev1 Atrium Gutter_TT_POP.pdf
05 50 00-027-02 | 05 50 00 - METAL FABRICATIONS | 05 50 00-027-02 Atrium Gutter | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2020-10-14 | 2020-10-12 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08448 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-14 | Submittal Number: 05 50 00-27.2 From: DOMINGO SAMPAYO Final Due Date: 10/07/20 Subject: ATRIUM GUTTER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11189 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-07 | Submittal Number: 05 50 00-27.2 From: DOMINGO SAMPAYO Final Due Date: 10/07/20 Subject: ATRIUM GUTTER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11304 | Forwarded | For Review | 2020-10-05 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2020-10-12 | Submittal Number: 05 50 00-27.2 From: DOMINGO SAMPAYO Final Due Date: 10/07/20 Subject: ATRIUM GUTTER Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11510 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-12 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 05 50 00-27 Rev2 Atrium Gutter.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 05 50 00-27 Rev2 Atrium Gutter.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-29 02:00 |  | 05 50 00-27 Rev2 Atrium Gutter.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-12 |  | 05 50 00-27 Rev2 Atrium Gutter_POP.pdf
05 50 00-027-03 | 05 50 00 - METAL FABRICATIONS | 05 50 00-027-03 Atrium Gutter (Revised) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-23 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-06 | 2020-10-26 | 4 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-10-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08955 | Received | For Review | 2020-10-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-11-06 | Submittal Number: 05 50 00-27.3 From: DOMINGO SAMPAYO Final Due Date: 11/02/20 Subject: ATRIUM GUTTER (REVISED) Description: REVISION TO BE CREATED TO RE-SUBMIT PER RFI: #3317: ATRIUM GUTTER (WELDING MODIFICATION) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11825 | Forwarded | For Review | 2020-10-23 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-30 | Submittal Number: 05 50 00-27.3 From: DOMINGO SAMPAYO Final Due Date: 11/02/20 Subject: ATRIUM GUTTER (REVISED) Description: REVISION TO BE CREATED TO RE-SUBMIT PER RFI: #3317: ATRIUM GUTTER (WELDING MODIFICATION) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 08982 | Review Response | Approved | 2020-10-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 11854 | Responded and Closed | Approved as Noted | 2020-10-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-22 |  | 05 50 00-27 Rev3 Atrium Gutter.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-22 |  | 05 50 00-27 Rev3 Atrium Gutter.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-22 |  | 05 50 00-27 Rev3 Atrium Gutter.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-26 |  | 05 50 00-27 Rev3 Atrium Gutter_TT_POP.pdf
05 50 00-029-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-029-00 Steel Lintels for CMU Support | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Closed - Void |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2020-10-09 |  | 36 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08350 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-09 | Submittal Number: 05 50 00-29.0 From: DOMINGO SAMPAYO Final Due Date: 10/05/20 Subject: STEEL LINTELS FOR CMU SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11063 | Forwarded | For Review | 2020-09-25 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-02 | Submittal Number: 05 50 00-29.0 From: DOMINGO SAMPAYO Final Due Date: 10/05/20 Subject: STEEL LINTELS FOR CMU SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11100 | Forwarded | For Review | 2020-09-28 | Josh Dobken (Populous) | Chris Minter (Populous); Chad Francis (Populous) | 2020-10-05 | Submittal Number: 05 50 00-29.0 From: DOMINGO SAMPAYO Final Due Date: 10/05/20 Subject: STEEL LINTELS FOR CMU SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09073 | Review Response | No Action Taken or Required | 2020-10-09 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | These are not CMU walls. No CMU lintels required per Arch. Not reviewed by TT. | Info Exchange
| 12050 | Closed | Void | 2020-10-30 | Josh Dobken (Populous) |  |  | ITEM VOIDED PER 10/27 DOC CONTROL COMMENTS.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 05 50 00-29 Steel Lintels for CMU Support.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 05 50 00-29 Steel Lintels for CMU Support.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-24 02:00 |  | 05 50 00-29 Steel Lintels for CMU Support.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-25 |  | 05 50 00-29 Steel Lintels for CMU Support.pdf
05 50 00-031-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-031-00 Ticket Office Plate | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-06 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-20 | 2020-08-24 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07421 | Received | For Review | 2020-08-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-20 | Submittal Number: 05 50 00-31.0 From: CHLOE HOEPFINGER Final Due Date: 09/11/20 Subject: TICKET OFFICE PLATE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09886 | Forwarded | For Review | 2020-08-06 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-13 | Submittal Number: 05 50 00-31.0 From: CHLOE HOEPFINGER Final Due Date: 09/11/20 Subject: TICKET OFFICE PLATE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10227 | Responded and Closed | Approved as Noted | 2020-08-24 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | 05 50 00-31 Ticket Office Plate.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-06 |  | 05 50 00-31 Ticket Office Plate.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-24 |  | 05 50 00-31 Ticket Office Plate_POP.pdf
05 50 00-031-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-031-01 Ticket Office Plate | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-12 | 2020-10-05 | 8 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08366 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 05 50 00-31.1 From: DOMINGO SAMPAYO Final Due Date: 10/07/20 Subject: TICKET OFFICE PLATE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11079 | Forwarded | For Review | 2020-09-28 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-05 | Submittal Number: 05 50 00-31.1 From: DOMINGO SAMPAYO Final Due Date: 10/07/20 Subject: TICKET OFFICE PLATE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 08532 | Review Response | Approved as Noted | 2020-09-30 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 11284 | Responded and Closed | Approved as Noted | 2020-10-05 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 05 50 00-31 Rev1 Ticket Office Plate.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 05 50 00-31 Rev1 Ticket Office Plate.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-09-25 |  | 05 50 00-31 Rev1 Ticket Office Plate.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-25 |  | 05 50 00-31 Rev1 Ticket Office Plate.pdf
05 50 00-034-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-034-00 Operable Partitions (Suite Level) | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-23 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-15 | 2021-01-27 | 36 |  | Record Copies; Transfers; Submittals |  | 34 |  | 2021-01-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10339 | Received | For Review | 2020-12-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2021-01-15 | Submittal Number: 05 50 00-34.0 From: DOMINGO SAMPAYO Final Due Date: 01/08/21 Subject: OPERABLE PARTITIONS (SUITE LEVEL) Description: ***CURRENTLY WAITING ON SHOP DRAWINGS (DANIELLE SCOTT)*** Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13506 | Forwarded | For Review | 2020-12-23 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-30 | Submittal Number: 05 50 00-34.0 From: DOMINGO SAMPAYO Final Due Date: 01/08/21 Subject: OPERABLE PARTITIONS (SUITE LEVEL) Description: ***CURRENTLY WAITING ON SHOP DRAWINGS (DANIELLE SCOTT)*** Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10967 | Review Response | Approved as Noted | 2021-01-25 | Raymond Chou (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 14280 | Responded and Closed | Approved as Noted | 2021-01-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-22 |  | 05 50 00-34.0 Operable Partition Support Suite Level (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-22 |  | 05 50 00-34.0 Operable Partition Support Suite Level (MAM Review).pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2021-01-25 |  | 05 50 00-34.0 Operable Partition Support Suite Level (MAM Review)_TT REVIEWED.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2021-01-25 |  | SSK-0310 Operable Wall Steel Cope and Splice.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-25 |  | SSK-0310 Operable Wall Steel Cope and Splice.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-27 |  | 05 50 00-34.0 Operable Partition Support Suite Level (MAM Review)_TT REVIEWED_POP.pdf
05 50 00-035-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-035-00 Wear Plates | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2020-10-19 | 2020-11-09 | 36 |  | Record Copies; Transfers; Submittals |  | 36 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08525 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 05 50 00-35.0 From: DOMINGO SAMPAYO Final Due Date: 10/05/20 Subject: WEAR PLATES Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11277 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-12 | Submittal Number: 05 50 00-35.0 From: DOMINGO SAMPAYO Final Due Date: 10/05/20 Subject: WEAR PLATES Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11286 | Forwarded | For Review | 2020-10-05 | Todd Spangler (Populous) | Tom Usher (Populous); Chris Minter (Populous) |  | I think these are for the trash by I'm not sure. Either way I have no clue what this is for. Thanks | Info Exchange
| 12279 | Responded and Closed | Revise and Resubmit | 2020-11-09 | Populous SCA_CCA | Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PROVIDE PROPOSED LAYOUT WITHIN SPACE FOR REVIEW AND COMMENT. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-02 |  | 05 50 00-35 Wear Plates.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-02 |  | 11294 2017-01-10 REV-D SALES LAYOUT.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-02 |  | 05 50 00-35 Wear Plates.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-02 |  | 11294 2017-01-10 REV-D SALES LAYOUT.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-10-02 |  | 05 50 00-35 Wear Plates.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-10-02 |  | 11294 2017-01-10 REV-D SALES LAYOUT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-09 02:00 |  | 05 50 00-35 Wear Plates_pop.pdf
05 50 00-035-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-035-01 Wear Plates | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-04 | 2020-11-20 | 3 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09517 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-04 | Submittal Number: 05 50 00-35.1 From: DOMINGO SAMPAYO Final Due Date: 12/01/20 Subject: WEAR PLATES Description: ATTACHED ARE LAYOUT DRAWINGS RECEIVED FROM JOSH DOBKEN ON MONDAY, 11/16/2020. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12537 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-24 | Submittal Number: 05 50 00-35.1 From: DOMINGO SAMPAYO Final Due Date: 12/01/20 Subject: WEAR PLATES Description: ATTACHED ARE LAYOUT DRAWINGS RECEIVED FROM JOSH DOBKEN ON MONDAY, 11/16/2020. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12692 | Responded and Closed | Approved | 2020-11-20 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | No exceptions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | 05 50 00-35 Rev1 Wear Plates.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | A1-40 - SLAB PLAN - SUB-EVENT LEVEL.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | A1-41 - SLAB PLAN EVENT LEVEL.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | A2-1F - EVENT LEVEL - AREA F.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | 05 50 00-35 Rev1 Wear Plates.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | A1-40 - SLAB PLAN - SUB-EVENT LEVEL.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | A1-41 - SLAB PLAN EVENT LEVEL.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | A2-1F - EVENT LEVEL - AREA F.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-20 02:00 |  | 05 50 00-35 Rev1 Wear Plates_pop.pdf
05 50 00-036-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-036-00 Trash Room OHD Support | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-04 | 2020-12-07 | 20 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09554 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-04 | Submittal Number: 05 50 00-36.0 From: DOMINGO SAMPAYO Final Due Date: 12/02/20 Subject: TRASH ROOM OHD SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12574 | Forwarded | For Review | 2020-11-18 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-25 | Submittal Number: 05 50 00-36.0 From: DOMINGO SAMPAYO Final Due Date: 12/02/20 Subject: TRASH ROOM OHD SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09978 | Review Response | Approved | 2020-12-02 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Arch to verify dimensions. | Info Exchange
| 13056 | Responded and Closed | Approved as Noted | 2020-12-07 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 05 50 00-36 Trash Room OHD Support.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 05 50 00-36 Trash Room OHD Support.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-18 |  | 05 50 00-36 Trash Room OHD Support.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-02 |  | 05 50 00-36 Trash Room OHD Support_TT REVIEW.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-07 |  | 05 50 00-36 Trash Room OHD Support_TT REVIEW-POP.pdf
05 50 00-038-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-038-00 Unistrut at Interview Room | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-13 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-27 | 2020-10-20 | 8 |  | Record Copies; Transfers; Submittals | 05 50 00-038-01 - 05 50 00-038-01 Unistrut at Interview Room | 2 |  | 2020-10-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08754 | Received | For Review | 2020-10-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-27 | Submittal Number: 05 50 00-38.0 From: CHLOE HOEPFINGER Final Due Date: 09/04/20 Subject: UNISTRUT AT INTERVIEW ROOM Description: MCCLEAN WAITING ON RFI # 3063 RESPONSE Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11568 | Forwarded | For Review | 2020-10-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-20 | Submittal Number: 05 50 00-38.0 From: CHLOE HOEPFINGER Final Due Date: 09/04/20 Subject: UNISTRUT AT INTERVIEW ROOM Description: MCCLEAN WAITING ON RFI # 3063 RESPONSE Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 08889 | Review Response | Rejected | 2020-10-14 | Raymond Chou (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 11745 | Responded and Closed | Rejected | 2020-10-20 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Raymond Chou (Thornton Tomasetti) Remarks: PROVIDE CALCS AND LOADS IMPOSED FOR REVIEW. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-13 |  | 05 50 00-38 Unistrut at Interview Room.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-13 |  | 05 50 00-38 Unistrut at Interview Room.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2020-10-14 02:00 |  | 05 50 00-38 Unistrut at Interview Room_TT Reviewed.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-20 02:00 |  | 05 50 00-38 Unistrut at Interview Room_TT Reviewed_pop.pdf
05 50 00-038-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-038-01 Unistrut at Interview Room | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-27 | Responded and Closed - Revise and Resubmit |  | Elliott Veazey (CAA ICON / Strategy Advisory), Mike Tihista (CAA ICON / Strategy Advisory), Byron Noll (CAA ICON / Strategy Advisory), Kuebler Perry (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-02-10 | 2021-02-12 | 17 |  | Record Copies; Transfers; Submittals | 05 50 00-038-00 - 05 50 00-038-00 Unistrut at Interview Room | 15 | 2020-11-03 | 2021-02-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10992 | Received | For Review | 2021-01-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2021-02-10 |  | Email
| 14275 | Forwarded | For Review | 2021-01-27 | Shaina Burris (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); Mike Tihista (CAA ICON / Strategy Advisory); Byron Noll (CAA ICON / Strategy Advisory) | 2021-02-03 |  | Info Exchange
| 14657 | Forwarded | For Review | 2021-02-09 | Josh Dobken (Populous) | Kuebler Perry (Populous); Matt Ross (Thornton Tomasetti) | 2021-02-10 |  | Email
| 11341 | Review Response | Revise and Resubmit | 2021-02-10 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Provide calcs and loads imposed for full unistrut system as noted in review of original submittal. | Info Exchange
| 14740 | Responded and Closed | Revise and Resubmit | 2021-02-12 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 15047 | Sent | For Information Only | 2021-02-23 | Josh Dobken (Populous) | Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Provide calcs and loads imposed for full unistrut system as noted in review of original submittal. Responded and Closed (Revise and Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-20 |  | 05 50 00-38 Unistrut at Interview Room_TT Reviewed_pop.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-20 |  | 05 50 00-38 Unistrut at Interview Room_TT Reviewed_pop.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-19 02:00 |  | 05 50 00-38 Unistrut at Interview Room_TT Reviewed_pop.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-19 |  | 05 50 00-38 Unistrut at Interview Room_TT Reviewed_pop.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-02-10 |  | 05 50 00-038-1 Unistrut at Interview Room & Pipe Grid_TT.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-02-12 |  | 05 50 00-038-1 Unistrut at Interview Room & Pipe Grid_TT-POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-10-19 02:00 |  | 05 50 00-38 Unistrut at Interview Room_TT Reviewed_pop.pdf
05 50 00-039-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-039-00 Press Counter Support | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-22 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-05 | 2020-10-26 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-10-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08940 | Received | For Review | 2020-10-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-11-05 | Submittal Number: 05 50 00-39.0 From: DOMINGO SAMPAYO Final Due Date: 11/04/20 Subject: PRESS COUNTER SUPPORT Description: MCCLEAN WAITING ON RFI # 3064 RESPONSE Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11810 | Forwarded | For Review | 2020-10-22 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-29 | Submittal Number: 05 50 00-39.0 From: DOMINGO SAMPAYO Final Due Date: 11/04/20 Subject: PRESS COUNTER SUPPORT Description: MCCLEAN WAITING ON RFI # 3064 RESPONSE Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 08958 | Review Response | Approved as Noted | 2020-10-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 09008 | Review Response | Approved as Noted | 2020-10-26 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 11886 | Responded and Closed | Approved as Noted | 2020-10-26 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-21 |  | 05 50 00-39 Press Counter Support.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-21 |  | 05 50 00-39 Press Counter Support.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-21 |  | 05 50 00-39 Press Counter Support.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-10-26 |  | 05 50 00-39 Press Counter Support_TT_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-21 |  | 05 50 00-39 Press Counter Support.pdf
05 50 00-039-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-039-01 Press Counter Supports | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-13 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-28 08:00 | 2021-01-31 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-01-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10665 | Received | For Review | 2021-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2021-01-28 08:00 | Submittal Number: 05 50 00-39.1 From: DOMINGO SAMPAYO Final Due Date: 01/27/21 Subject: PRESS COUNTER SUPPORTS Description: TO RE-SUBMIT ON THIS REVISION THE LOWER AND UPPER COUNTER SUPPORTS SINCE ORIGINAL VERSION ONLY HAD ONE. CCD 75: A8-07-3 (MILLWORK DETAILS) DETAIL: 7 (COUNTER DETAIL AT WRITING PRESS COUNTER) CCD 77: A8-07-3 (MILLWORK DETAILS) DETAIL: 3 (COUNTER DETAIL AT PRESS COUNTER) MISC. METALS DESCRIPTION: STEEL PLATE COUNTER SUPPORT SUBMITTAL NUMBER: 05 50 00-39 REVISION 1 SUBMITTAL NAME: PRESS COUNTER SUPPORTS (REVISION 1) ***INCORPORATE NOTE FORM ORIGINAL SUBMITTAL*** Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13886 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-20 | Submittal Number: 05 50 00-39.1 From: DOMINGO SAMPAYO Final Due Date: 01/27/21 Subject: PRESS COUNTER SUPPORTS Description: TO RE-SUBMIT ON THIS REVISION THE LOWER AND UPPER COUNTER SUPPORTS SINCE ORIGINAL VERSION ONLY HAD ONE. CCD 75: A8-07-3 (MILLWORK DETAILS) DETAIL: 7 (COUNTER DETAIL AT WRITING PRESS COUNTER) CCD 77: A8-07-3 (MILLWORK DETAILS) DETAIL: 3 (COUNTER DETAIL AT PRESS COUNTER) MISC. METALS DESCRIPTION: STEEL PLATE COUNTER SUPPORT SUBMITTAL NUMBER: 05 50 00-39 REVISION 1 SUBMITTAL NAME: PRESS COUNTER SUPPORTS (REVISION 1) ***INCORPORATE NOTE FORM ORIGINAL SUBMITTAL*** Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11063 | Review Response | Approved | 2021-01-29 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. Populous to review. | Info Exchange
| 11064 | Review Response | Revise and Resubmit | 2021-01-31 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14363 | Responded and Closed | Revise and Resubmit | 2021-01-31 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. Populous to review. Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 05 50 00-39.1 Press Counter Supports (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 05 50 00-39.1 Press Counter Supports (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-12 |  | 05 50 00-39.1 Press Counter Supports (MAM Review).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-31 |  | 05 50 00-39.1 Press Counter Supports (MAM Review)_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-12 |  | 05 50 00-39.1 Press Counter Supports (MAM Review).pdf
05 50 00-039-02 | 05 50 00 - METAL FABRICATIONS | 05 50 00-039-02 Press Counter Supports Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-29 | 2021-03-22 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11985 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2021-03-29 | Submittal Number: 05 50 00-39.2 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: PRESS COUNTER SUPPORTS SHOP DRAWINGS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 15525 | Forwarded | For Review | 2021-03-15 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-22 | Submittal Number: 05 50 00-39.2 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: PRESS COUNTER SUPPORTS SHOP DRAWINGS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12146 | Review Response | Approved | 2021-03-17 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Populous to review. | Info Exchange
| 12151 | Review Response | Approved as Noted | 2021-03-22 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15723 | Responded and Closed | Approved as Noted | 2021-03-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Populous to review. Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-14 |  | 05 50 00-39.2 Press Counter Supports SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-14 |  | 05 50 00-39.2 Press Counter Supports SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-14 |  | 05 50 00-39.2 Press Counter Supports SD-MAM.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-31 |  | 05 50 00-39.1 Press Counter Supports (MAM Review)_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-31 |  | 05 50 00-39.1 Press Counter Supports (MAM Review)_TT_POP.pdf
05 50 00-043-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-043-00 Steel Framing for the Tunnel Club | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-22 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-04 | 2020-10-30 | 9 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-10-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08939 | Received | For Review | 2020-10-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-11-04 | Submittal Number: 05 50 00-43.0 From: DOMINGO SAMPAYO Final Due Date: 11/04/20 Subject: STEEL FRAMING FOR THE TUNNEL CLUB Description: WE NEED YOU TO ENGINEER, PROVIDE, AND INSTALL THE STEEL FRAMING SHOWN ON A8-07-5 FOR THE TUNNEL CLUB MOCK-UP (B1) ONLY. PLEASE SEE ATTACHED DOCUMENTS IN ORDER TO HAVE ENGINEER THE STEEL TO THE FOLLOWING LOADING REQUIREMENTS: SILL = 200 LBS. HEAD = 100 LBS. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11809 | Forwarded | For Review | 2020-10-22 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-29 | Submittal Number: 05 50 00-43.0 From: DOMINGO SAMPAYO Final Due Date: 11/04/20 Subject: STEEL FRAMING FOR THE TUNNEL CLUB Description: WE NEED YOU TO ENGINEER, PROVIDE, AND INSTALL THE STEEL FRAMING SHOWN ON A8-07-5 FOR THE TUNNEL CLUB MOCK-UP (B1) ONLY. PLEASE SEE ATTACHED DOCUMENTS IN ORDER TO HAVE ENGINEER THE STEEL TO THE FOLLOWING LOADING REQUIREMENTS: SILL = 200 LBS. HEAD = 100 LBS. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09135 | Review Response | Rejected | 2020-10-27 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | There is an open RFI regarding the design of this system. Please coordinate with forthcoming response to RFI 3428. | Info Exchange
| 12055 | Responded and Closed | Rejected | 2020-10-30 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Matt Ross (Thornton Tomasetti) Remarks: There is an open RFI regarding the design of this system. Please coordinate with forthcoming response to RFI 3428. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-21 |  | 05 50 00-43 Steel Framing for the Tunnel Club.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-21 |  | 05 50 00-43 Steel Framing for the Tunnel Club.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-20 02:00 |  | 05 50 00-43 Steel Framing for the Tunnel Club.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-30 02:00 |  | 05 50 00-43 Steel Framing for the Tunnel Club_TT_pop.pdf
05 50 00-044-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-044-00 SE Snorkel Steel Plate | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-11 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-05 | 2020-12-18 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-12-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10095 | Received | For Review | 2020-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2021-01-05 | Submittal Number: 05 50 00-44.0 From: DOMINGO SAMPAYO Final Due Date: 12/16/20 Subject: SE SNORKEL STEEL PLATE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13196 | Forwarded | For Review | 2020-12-10 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-17 | Submittal Number: 05 50 00-44.0 From: DOMINGO SAMPAYO Final Due Date: 12/16/20 Subject: SE SNORKEL STEEL PLATE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10241 | Review Response | Approved | 2020-12-16 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Refer to SSK-0306 for information requested per RFI 3785. Arch to review submittal. | Info Exchange
| 13382 | Responded and Closed | Approved as Noted | 2020-12-18 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-10 |  | 05 50 00-44 SE Snorkel Steel Plate.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-10 |  | 05 50 00-44 SE Snorkel Steel Plate.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-10 |  | 05 50 00-44 SE Snorkel Steel Plate.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-18 |  | SSK-0306 RFI 3785 SE Snorkel Steel Plate - POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-18 |  | 05 50 00-44 SE Snorkel Steel Plate_TT_POP.pdf
05 50 00-045-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-045-00 Welder Certs.(McClean Iron Works) - September 2020 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-13 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-27 | 2020-10-14 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-10-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08749 | Received | For Review | 2020-10-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-27 | Submittal Number: 05 50 00-45.0 From: DOMINGO SAMPAYO Final Due Date: 10/13/20 Subject: WELDER CERTS.(MCCLEAN IRON WORKS) - SEPTEMBER 2020 Description: MCCLEAN WABO CERTIFICATE CARDS FOR SEPTEMBER, 2020 Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11557 | Forwarded | For Review | 2020-10-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-20 | Submittal Number: 05 50 00-45.0 From: DOMINGO SAMPAYO Final Due Date: 10/13/20 Subject: WELDER CERTS.(MCCLEAN IRON WORKS) - SEPTEMBER 2020 Description: MCCLEAN WABO CERTIFICATE CARDS FOR SEPTEMBER, 2020 Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 08775 | Review Response | No Action Taken or Required | 2020-10-14 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Retained for Record. | Info Exchange
| 11604 | Responded and Closed | No Action Taken or Required | 2020-10-14 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Retained for Record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-12 |  | 05 50 00-45 Welder Certs. - September 2020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-12 |  | 05 50 00-45 Welder Certs. - September 2020.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-12 |  | 05 50 00-45 Welder Certs. - September 2020.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-12 |  | 05 50 00-45 Welder Certs. - September 2020.pdf
05 50 00-045-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-045-01 Welder Certs.(McClean Iron Works) - October 2020 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-21 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-04 | 2020-10-22 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-10-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08899 | Received | For Review | 2020-10-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-11-04 | Submittal Number: 05 50 00-45.1 From: DOMINGO SAMPAYO Final Due Date: 11/02/20 Subject: WELDER CERTS.(MCCLEAN IRON WORKS) - OCTOBER 2020 Description: MCCLEAN WABO CERTIFICATE CARDS FOR SEPTEMBER, 2020 Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11771 | Forwarded | For Review | 2020-10-21 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-10-28 | Submittal Number: 05 50 00-45.1 From: DOMINGO SAMPAYO Final Due Date: 11/02/20 Subject: WELDER CERTS.(MCCLEAN IRON WORKS) - OCTOBER 2020 Description: MCCLEAN WABO CERTIFICATE CARDS FOR SEPTEMBER, 2020 Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 08933 | Review Response | No Action Taken or Required | 2020-10-22 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. Retained for Record Only. | Info Exchange
| 11803 | Responded and Closed | Approved | 2020-10-22 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | TT has no exceptions. Retained for Record Only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-20 |  | 05 50 00-45 R1 Welder Certs. - October 2020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-20 |  | 05 50 00-45 R1 Welder Certs. - October 2020.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-20 |  | 05 50 00-45 R1 Welder Certs. - October 2020.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-20 |  | 05 50 00-45 R1 Welder Certs. - October 2020.pdf
05 50 00-045-02 | 05 50 00 - METAL FABRICATIONS | 05 50 00-045-02 Welder Certs.(McClean Iron Works) - November 2020 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-11 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-05 | 2020-12-15 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10096 | Received | For Review | 2020-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2021-01-05 | Submittal Number: 05 50 00-45.2 From: DOMINGO SAMPAYO Final Due Date: 12/25/20 Subject: WELDER CERTS.(MCCLEAN IRON WORKS) - NOVEMBER 2020 Description: MCCLEAN WABO CERTIFICATE CARDS FOR SEPTEMBER, 2020 Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13197 | Forwarded | For Review | 2020-12-10 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-17 | Submittal Number: 05 50 00-45.2 From: DOMINGO SAMPAYO Final Due Date: 12/25/20 Subject: WELDER CERTS.(MCCLEAN IRON WORKS) - NOVEMBER 2020 Description: MCCLEAN WABO CERTIFICATE CARDS FOR SEPTEMBER, 2020 Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10154 | Review Response | No Action Taken or Required | 2020-12-11 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Retained for Record Only. | Info Exchange
| 13288 | Responded and Closed | No Action Taken or Required | 2020-12-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Retained for Record Only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-10 |  | 05 50 00-45 Rev 2 Welder Certs.(McClean Iron Works) - November 2020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-10 |  | 05 50 00-45 Rev 2 Welder Certs.(McClean Iron Works) - November 2020.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-10 |  | 05 50 00-45 Rev 2 Welder Certs.(McClean Iron Works) - November 2020.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-10 |  | 05 50 00-45 Rev 2 Welder Certs.(McClean Iron Works) - November 2020.pdf
05 50 00-045-03 | 05 50 00 - METAL FABRICATIONS | 05 50 00-045-03 Welder Certs.(McClean Iron Works) - January 2021 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-01 | 2021-02-22 | 8 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-02-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11402 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-03-01 | Submittal Number: 05 50 00-45.3 From: DOMINGO SAMPAYO Final Due Date: 02/19/21 Subject: WELDER CERTS.(MCCLEAN IRON WORKS) - JANUARY 2021 Description: MCCLEAN WABO CERTIFICATE CARDS FOR SEPTEMBER, 2020 Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14769 | Forwarded | For Review | 2021-02-15 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-02-22 | Submittal Number: 05 50 00-45.3 From: DOMINGO SAMPAYO Final Due Date: 02/19/21 Subject: WELDER CERTS.(MCCLEAN IRON WORKS) - JANUARY 2021 Description: MCCLEAN WABO CERTIFICATE CARDS FOR SEPTEMBER, 2020 Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11584 | Review Response | No Action Taken or Required | 2021-02-16 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | RECEIVED FOR RECORD. | Info Exchange
| 15007 | Responded and Closed | No Action Taken or Required | 2021-02-22 | Populous SCA_CCA | Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: RECEIVED FOR RECORD. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 05 50 00-45 R3 Welder Certs.(McClean)-Jan 2021.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-15 |  | 05 50 00-45 R3 Welder Certs.(McClean)-Jan 2021.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-14 02:00 |  | 05 50 00-45 R3 Welder Certs.(McClean)-Jan 2021.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-14 02:00 |  | 05 50 00-45 R3 Welder Certs.(McClean)-Jan 2021.pdf
05 50 00-046-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-046-00 NW Snorkel Seismic Joint (Misc. Metals) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-29 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-12 | 2021-02-16 | 19 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-02-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11042 | Received | For Review | 2021-01-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-02-12 | Submittal Number: 05 50 00-46.0 From: DOMINGO SAMPAYO Final Due Date: 02/15/21 Subject: NW SNORKEL SEISMIC JOINT (MISC. METALS) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14337 | Forwarded | For Review | 2021-01-29 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-05 | Submittal Number: 05 50 00-46.0 From: DOMINGO SAMPAYO Final Due Date: 02/15/21 Subject: NW SNORKEL SEISMIC JOINT (MISC. METALS) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11460 | Review Response | Approved | 2021-02-02 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Shaina Burris (Populous) |  |  | Info Exchange
| 14841 | Responded and Closed | Approved as Noted | 2021-02-16 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-28 |  | 05 50 00-46 NW Snorkel Seismic Joint.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-28 |  | 05 50 00-46 NW Snorkel Seismic Joint.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-28 |  | 05 50 00-46 NW Snorkel Seismic Joint.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-16 |  | 05 50 00-46 NW Snorkel Seismic Joint_TT_POP.pdf
05 50 00-047-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-047-00 Freight Elevator Opening Channel Framing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-26 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-09 | 2020-11-19 | 25 |  | Record Copies; Transfers; Submittals |  | 25 |  | 2020-11-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08987 | Received | For Review | 2020-10-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-11-09 | Submittal Number: 05 50 00-47.0 From: DOMINGO SAMPAYO Final Due Date: 11/02/20 Subject: FREIGHT ELEVATOR OPENING CHANNEL FRAMING Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11859 | Forwarded | For Review | 2020-10-26 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-02 | Submittal Number: 05 50 00-47.0 From: DOMINGO SAMPAYO Final Due Date: 11/02/20 Subject: FREIGHT ELEVATOR OPENING CHANNEL FRAMING Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12593 | Responded and Closed | Approved as Noted | 2020-11-19 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-23 |  | 05 50 00-47 Freight Elevator Opening Channel Framing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-23 |  | 05 50 00-47 Freight Elevator Opening Channel Framing.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-19 |  | 05 50 00-47 Freight Elevator Opening Channel Framing_POP.pdf
05 50 00-047-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-047-01 Freight Elevator Opening Channel Framing | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-18 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matt Ross (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2021-01-12 | 2020-12-27 | 10 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-12-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10236 | Received | For Review | 2020-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2021-01-12 | Submittal Number: 05 50 00-47.1 From: DOMINGO SAMPAYO Final Due Date: 12/21/20 Subject: FREIGHT ELEVATOR OPENING CHANNEL FRAMING Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13374 | Forwarded | For Review | 2020-12-17 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-24 | Submittal Number: 05 50 00-47.1 From: DOMINGO SAMPAYO Final Due Date: 12/21/20 Subject: FREIGHT ELEVATOR OPENING CHANNEL FRAMING Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13384 | Forwarded | For Review | 2020-12-18 | Todd Spangler (Populous) | Matt Ross (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti) |  | Submittal Number: 05 50 00-47.1 From: DOMINGO SAMPAYO Final Due Date: 12/21/20 Subject: FREIGHT ELEVATOR OPENING CHANNEL FRAMING Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10356 | Review Response | Approved as Noted | 2020-12-23 | Sean McNeill (Thornton Tomasetti) | Todd Spangler (Populous) |  | Exceptions Noted | Info Exchange
| 13529 | Responded and Closed | Approved as Noted | 2020-12-27 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-17 |  | 05 50 00-47 R1 Freight Elev Open Channel Framing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-17 |  | 05 50 00-47 R1 Freight Elev Open Channel Framing.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-12-17 |  | 05 50 00-47 R1 Freight Elev Open Channel Framing.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-12-17 |  | 05 50 00-47 R1 Freight Elev Open Channel Framing.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-27 |  | A7-06-7 - ELEVATOR CORE PLANS & SECTIONS - FREIGHT & SERV-.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-27 |  | 05 50 00-47 R1 Freight Elev Open Channel Framing_TT_POP.pdf
05 50 00-048-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-048-00 Cage Ladders - Rails - Platforms (SE Snorkel) | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-09 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-23 | 2021-01-13 | 36 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-01-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10063 | Received | For Review | 2020-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-23 | Submittal Number: 05 50 00-48.0 From: DOMINGO SAMPAYO Final Due Date: 01/04/21 Subject: CAGE LADDERS - RAILS - PLATFORMS (SE SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13164 | Forwarded | For Review | 2020-12-09 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-16 | Submittal Number: 05 50 00-48.0 From: DOMINGO SAMPAYO Final Due Date: 01/04/21 Subject: CAGE LADDERS - RAILS - PLATFORMS (SE SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10242 | Review Response | Revise and Resubmit | 2020-12-14 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 13884 | Responded and Closed | Revise and Resubmit | 2021-01-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-09 |  | 05 50 00-48 Cage Ladders - Rails - Platforms (SE Snorkel).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-09 |  | 05 50 00-48 Cage Ladders - Rails - Platforms (SE Snorkel).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-09 |  | 05 50 00-48 Cage Ladders - Rails - Platforms (SE Snorkel).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-06 |  | 05 50 00-48 Cage Ladders - Rails - Platforms (SE Snorkel)_TT_POP.pdf
05 50 00-048-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-048-01 Cage Ladders - Rails - Platforms (SE Snorkel) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-25 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-11 | 2021-03-10 | 14 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11642 | Received | For Review | 2021-02-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-03-11 | Submittal Number: 05 50 00-48.1 From: DOMINGO SAMPAYO Final Due Date: 02/19/21 Subject: CAGE LADDERS - RAILS - PLATFORMS (SE SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 15088 | Forwarded | For Review | 2021-02-24 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-03 | Submittal Number: 05 50 00-48.1 From: DOMINGO SAMPAYO Final Due Date: 02/19/21 Subject: CAGE LADDERS - RAILS - PLATFORMS (SE SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11906 | Review Response | Approved as Noted | 2021-03-04 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | Arch to review. TT does not require a resubmit. | Info Exchange
| 15433 | Responded and Closed | Approved as Noted | 2021-03-10 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-24 |  | 05 50 00-48 Rev1 Cage Ladders - Rails - Platforms (SE Snorkel).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-24 |  | 05 50 00-48 Rev1 Cage Ladders - Rails - Platforms (SE Snorkel).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-24 |  | 05 50 00-48 Rev1 Cage Ladders - Rails - Platforms (SE Snorkel).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-04 |  | 05 50 00-48 Rev1 Cage Ladders - Rails - Platforms (SE Snorkel)_TT.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-10 |  | 05 50 00-48 Rev1 Cage Ladders - Rails - Platforms (SE Snorkel)_TT-POP.pdf
05 50 00-049-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-049-00 Cage Ladders - Rails - Platforms (SW Snorkel) & Cage Ladders & Rails (Ticket Office) | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-29 | 2021-03-26 | 12 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11986 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-03-29 | Submittal Number: 05 50 00-49.0 From: DOMINGO SAMPAYO Final Due Date: 03/22/21 Subject: CAGE LADDERS - RAILS - PLATFORMS (SW SNORKEL) & CAGE LADDERS & RAILS (TICKET OFFICE) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 15526 | Forwarded | For Review | 2021-03-15 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-22 | Submittal Number: 05 50 00-49.0 From: DOMINGO SAMPAYO Final Due Date: 03/22/21 Subject: CAGE LADDERS - RAILS - PLATFORMS (SW SNORKEL) & CAGE LADDERS & RAILS (TICKET OFFICE) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12246 | Review Response | Approved as Noted/Resubmit | 2021-03-22 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See comments in attached submittal review. | Info Exchange
| 15845 | Responded and Closed | Approved as Noted | 2021-03-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-12 |  | 05 50 00-49 Cage Ladders - Rails - Platforms (SW Snorkel) & Cage Ladders & Rails (Ticket Office) REVIEWED.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-12 |  | 05 50 00-49 Cage Ladders - Rails - Platforms (SW Snorkel) & Cage Ladders & Rails (Ticket Office) REVIEWED.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-03-12 |  | 05 50 00-49 Cage Ladders - Rails - Platforms (SW Snorkel) & Cage Ladders & Rails (Ticket Office) REVIEWED.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-03-26 |  | SUBMITTAL - A3-05-4 - ENLARGED PLANS - SW MECH INTAKE & EXHAUST.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-03-26 |  | 05 50 00-49 Cage Ladders - Rails - Platforms (SW Snorkel & Ticket Office)-MAM_TT_POP.pdf
05 50 00-050-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-050-00 Cage Ladders - Rails - Platforms (NW Snorkel) | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-02 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-16 | 2020-12-15 | 14 |  | Record Copies; Transfers; Submittals | 05 50 00-050-01 - 05 50 00-050-01 Cage Ladders - Rails - Platforms (NW Snorkel) | 2 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09811 | Received | For Review | 2020-12-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-16 | Submittal Number: 05 50 00-50.0 From: DOMINGO SAMPAYO Final Due Date: 12/11/20 Subject: CAGE LADDERS - RAILS - PLATFORMS (NW SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12893 | Forwarded | For Review | 2020-12-02 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-09 | Submittal Number: 05 50 00-50.0 From: DOMINGO SAMPAYO Final Due Date: 12/11/20 Subject: CAGE LADDERS - RAILS - PLATFORMS (NW SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10160 | Review Response | Revise and Resubmit | 2020-12-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Arch to review all dimensions. Refer to TT comments within Submittal. | Info Exchange
| 13294 | Responded and Closed | Revise and Resubmit | 2020-12-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-01 |  | 05 50 00-50 Cage Ladders-Rail-Platform (NW Snorkel).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-01 |  | 05 50 00-50 Cage Ladders-Rail-Platform (NW Snorkel).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-01 |  | 05 50 00-50 Cage Ladders-Rail-Platform (NW Snorkel).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-15 |  | 05 50 00-50 Cage Ladders-Rail-Platform (NW Snorkel)_TT_POP.pdf
05 50 00-050-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-050-01 Cage Ladders - Rails - Platforms (NW Snorkel) | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-23 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Matthew Farber (Thornton Tomasetti), Chris Minter (Populous), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-10 08:00 | 2021-03-10 | 16 |  | Record Copies; Transfers; Submittals | 05 50 00-050-00 - 05 50 00-050-00 Cage Ladders - Rails - Platforms (NW Snorkel) | 10 | 2020-12-29 | 2021-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11617 | Received | For Review | 2021-02-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-10 08:00 | Submittal Number: 05 50 00-50.1 From: DOMINGO SAMPAYO Final Due Date: 02/26/21 Subject: CAGE LADDERS - RAILS - PLATFORMS (NW SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 15055 | Forwarded | For Review | 2021-02-24 | Populous SCA_CCA | Todd Spangler (Populous); Matthew Farber (Thornton Tomasetti); Chris Minter (Populous); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Michael Croly (Thornton To... | 2021-03-03 | Submittal Number: 05 50 00-50.1 From: DOMINGO SAMPAYO Final Due Date: 02/26/21 Subject: CAGE LADDERS - RAILS - PLATFORMS (NW SNORKEL) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11925 | Review Response | Approved as Noted | 2021-03-05 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Populous SCA_CCA |  | Arch to review. | Info Exchange
| 15441 | Responded and Closed | Approved as Noted | 2021-03-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-23 02:00 |  | 05 50 00-50 Rev1 Cage Ladders - Rails - Platforms (NW Snorkel).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-23 02:00 |  | 05 50 00-50 Rev1 Cage Ladders - Rails - Platforms (NW Snorkel).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-23 02:00 |  | 05 50 00-50 Rev1 Cage Ladders - Rails - Platforms (NW Snorkel).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-05 |  | 05 50 00-50 Rev1 Cage Ladders - Rails - Platforms (NW Snorkel)_TT REVIEW.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-10 |  | 05 50 00-50 Rev1 Cage Ladders - Rails - Platforms (NW Snorkel)_TT REVIEW-POP.pdf
05 50 00-052-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-052-00 SCL Transformer Grating at South Parcel | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-04 | 2020-12-02 | 15 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09552 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-04 | Submittal Number: 05 50 00-52.0 From: DOMINGO SAMPAYO Final Due Date: 12/01/20 Subject: SCL TRANSFORMER GRATING AT SOUTH PARCEL Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12573 | Forwarded | For Review | 2020-11-18 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-25 | Submittal Number: 05 50 00-52.0 From: DOMINGO SAMPAYO Final Due Date: 12/01/20 Subject: SCL TRANSFORMER GRATING AT SOUTH PARCEL Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 09818 | Review Response | Approved as Noted | 2020-11-24 | Sean McNeill (Thornton Tomasetti) | Shaina Burris (Populous) |  | Exceptions Noted | Info Exchange
| 12901 | Responded and Closed | Approved as Noted | 2020-12-02 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 05 50 00-52 SCL Transformer Grating at SParcel.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 05 50 00-52 SCL Transformer Grating at SParcel.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-11-18 |  | 05 50 00-52 SCL Transformer Grating at SParcel.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-02 |  | 05 50 00-52 SCL Transformer Grating at SParcel_TT-POP.pdf
05 50 00-053-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-053-00 HSS at Tunnel Suite for Glass Wall Support | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Kuebler Perry (Populous) |  |  |  | 2020-12-21 | 2020-12-14 | 8 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-12-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09919 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-21 | Submittal Number: 05 50 00-53.0 From: DOMINGO SAMPAYO Final Due Date: 12/14/20 Subject: HSS AT TUNNEL SUITE FOR GLASS WALL SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12999 | Forwarded | For Review | 2020-12-04 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-11 | Submittal Number: 05 50 00-53.0 From: DOMINGO SAMPAYO Final Due Date: 12/14/20 Subject: HSS AT TUNNEL SUITE FOR GLASS WALL SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10084 | Review Response | Approved as Noted | 2020-12-07 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Field Verify As-Built Locations of all existing steel. | Info Exchange
| 13259 | Forwarded | For Review | 2020-12-14 | Josh Dobken (Populous) | Kuebler Perry (Populous) | 2020-12-21 | Submittal Number: 05 50 00-53.0 From: DOMINGO SAMPAYO Final Due Date: 12/14/20 Subject: HSS AT TUNNEL SUITE FOR GLASS WALL SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10142 | Review Response | Approved as Noted | 2020-12-14 | Kuebler Perry (Populous) | Josh Dobken (Populous) |  | Refer to attached submittal review. | Info Exchange
| 13265 | Responded and Closed | Approved as Noted | 2020-12-14 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-04 |  | 05 50 00-53 HSS Tunnel Suite Glass Wall.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-04 |  | 05 50 00-53 HSS Tunnel Suite Glass Wall.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-04 |  | 05 50 00-53 HSS Tunnel Suite Glass Wall.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-12-03 02:00 |  | 05 50 00-53 HSS Tunnel Suite Glass Wall.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-14 |  | 05 50 00-53 HSS Tunnel Suite Glass Wall_TT_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-04 |  | 05 50 00-53 HSS Tunnel Suite Glass Wall.pdf
05 50 00-054-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-054-00 Cage Ladder - SE Detention Tank | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-22 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Matthew Farber (Thornton Tomasetti), Tom Usher (Populous), Chris Carver (Populous), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-03-08 | 2021-02-25 | 4 |  | Record Copies; Transfers; Submittals | 05 50 00-054-00-01 - 05 50 00-054-00 Cage Ladder - SE Detention Tank | 7 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11556 | Received | For Review | 2021-02-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-03-08 | Submittal Number: 05 50 00-54.0 From: DOMINGO SAMPAYO Final Due Date: 03/05/21 Subject: CAGE LADDER - SE DETENTION TANK Description: CAGE LADDER - SE DETENTION TANK ***SEE RFI #3560: SE DETENTION TANK LADDER*** Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14976 | Forwarded | For Review | 2021-02-19 | Josh Dobken (Populous) | Todd Spangler (Populous); Matthew Farber (Thornton Tomasetti); Tom Usher (Populous); Chris Carver (Populous); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2021-02-26 | Submittal Number: 05 50 00-54.0 From: DOMINGO SAMPAYO Final Due Date: 03/05/21 Subject: CAGE LADDER - SE DETENTION TANK Description: CAGE LADDER - SE DETENTION TANK ***SEE RFI #3560: SE DETENTION TANK LADDER*** Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 15117 | Responded and Closed | Revise and Resubmit | 2021-02-25 | Tom Usher (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for resubmission requirements. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-19 02:00 |  | 05 50 00-54 Cage Ladder-SE Detention Tank.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-19 02:00 |  | 05 50 00-54 Cage Ladder-SE Detention Tank.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2021-02-19 |  | 05 50 00-54 Cage Ladder-SE Detention Tank.pdf
05 50 00-054-00-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-054-00 Cage Ladder - SE Detention Tank | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 50 00-054-00 - 05 50 00-054-00 Cage Ladder - SE Detention Tank | -1 | 2021-03-11
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-19 |  | 05 50 00-54 Cage Ladder-SE Detention Tank.pdf
05 50 00-055-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-055-00 Steel Plate at Coping (SE Snorkel Curtain Wall) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-11 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-05 | 2020-12-11 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-12-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10094 | Received | For Review | 2020-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2021-01-05 | Submittal Number: 05 50 00-55.0 From: DOMINGO SAMPAYO Final Due Date: 12/25/20 Subject: STEEL PLATE AT COPING (SE SNORKEL CURTAIN WALL) Description: A8-01-15 GLAZING DETAILS DETAIL 8 - SECTION DETAIL @ CW2 / ALUMINUM COPING Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13194 | Forwarded | For Review | 2020-12-10 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-17 | Submittal Number: 05 50 00-55.0 From: DOMINGO SAMPAYO Final Due Date: 12/25/20 Subject: STEEL PLATE AT COPING (SE SNORKEL CURTAIN WALL) Description: A8-01-15 GLAZING DETAILS DETAIL 8 - SECTION DETAIL @ CW2 / ALUMINUM COPING Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13203 | Responded and Closed | Approved as Noted | 2020-12-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-10 |  | 05 50 00-55 Steel Plate at Coping (SE Snorkel Curtain Wall).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-10 |  | 05 50 00-55 Steel Plate at Coping (SE Snorkel Curtain Wall).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-11 |  | 05 50 00-55 Steel Plate at Coping (SE Snorkel Curtain Wall)_POP.pdf
05 50 00-056-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-056-00 Closure Plates (Bowl Break Rail Section) | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-21 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-13 | 2021-02-12 | 54 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10280 | Received | For Review | 2020-12-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-13 | Submittal Number: 05 50 00-56.0 From: DOMINGO SAMPAYO Final Due Date: 12/28/20 Subject: CLOSURE PLATES (BOWL BREAK RAIL SECTION) Description: CCD 05 DRAWING NUMBER: A7-07-3 & A8-06-2 DRAWING NAME: SEATING BOWL SECTIONS - FLOOR VOMITORIES & METALWORK DETAILS DETAILS: 1,2,3,4 ("SECTION AT FLOOR VOM) & 17 (BOWL BREAK RAIL SECTION) MISC. METALS DESCRIPTION: CLOSURE PLATES Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13430 | Forwarded | For Review | 2020-12-21 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-28 | Submittal Number: 05 50 00-56.0 From: DOMINGO SAMPAYO Final Due Date: 12/28/20 Subject: CLOSURE PLATES (BOWL BREAK RAIL SECTION) Description: CCD 05 DRAWING NUMBER: A7-07-3 & A8-06-2 DRAWING NAME: SEATING BOWL SECTIONS - FLOOR VOMITORIES & METALWORK DETAILS DETAILS: 1,2,3,4 ("SECTION AT FLOOR VOM) & 17 (BOWL BREAK RAIL SECTION) MISC. METALS DESCRIPTION: CLOSURE PLATES Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11021 | Review Response | Approved as Noted | 2021-01-06 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has provided cursory review of connections to structural steel. Arch to review submittal for conformance. | Info Exchange
| 14742 | Responded and Closed | Approved as Noted | 2021-02-12 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-18 |  | 05 50 00-56 Closure Plates (Bowl Break Rail Section).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-18 |  | 05 50 00-56 Closure Plates (Bowl Break Rail Section).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-18 |  | 05 50 00-56 Closure Plates (Bowl Break Rail Section).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-12 |  | 05 50 00-56 Closure Plates (Bowl Break Rail Section)_TT-POP.pdf
05 50 00-057-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-057-00 NE Snorkel Embedded Plate (RFI # 3580.1) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-06 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-20 | 2021-04-06 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12419 | Received | For Review | 2021-04-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-20 | Submittal Number: 05 50 00-57.0 From: DOMINGO SAMPAYO Final Due Date: 04/09/21 Subject: NE SNORKEL EMBEDDED PLATE (RFI # 3580.1) Description: THE TOP OF WALL CONNECTION THAT CHANGED IN CCD088 (RFI#3580.1). PLEASE PROVIDE THE EMBED PLATE AS SEEN IN DETAIL S8-12. THIS WILL BE ALONG THE HIGHLIGHTED PORTION OF THE NE SNORKEL (SEE ATTACHED). Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16093 | Forwarded | For Review | 2021-04-06 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-13 | Submittal Number: 05 50 00-57.0 From: DOMINGO SAMPAYO Final Due Date: 04/09/21 Subject: NE SNORKEL EMBEDDED PLATE (RFI # 3580.1) Description: THE TOP OF WALL CONNECTION THAT CHANGED IN CCD088 (RFI#3580.1). PLEASE PROVIDE THE EMBED PLATE AS SEEN IN DETAIL S8-12. THIS WILL BE ALONG THE HIGHLIGHTED PORTION OF THE NE SNORKEL (SEE ATTACHED). Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12424 | Review Response | Approved | 2021-04-06 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Arch to review. | Info Exchange
| 16100 | Responded and Closed | Approved as Noted | 2021-04-06 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-06 |  | 05 50 00-57 NE Snorkel Emd Plate (RFI _ 3580.1).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-06 |  | 05 50 00-57 NE Snorkel Emd Plate (RFI _ 3580.1).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-06 |  | 05 50 00-57 NE Snorkel Emd Plate (RFI _ 3580.1).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-06 |  | 05 50 00-57 NE Snorkel Emd Plate _TT_POP.pdf
05 50 00-058-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-058-00 Tunnel Transformer Stairs/Platforms/Grating/Framing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-25 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-09 07:00 | 2021-04-21 | 28 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-04-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12234 | Received | For Review | 2021-03-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-09 07:00 | Submittal Number: 05 50 00-58.0 From: DOMINGO SAMPAYO Final Due Date: 04/07/21 Subject: TUNNEL TRANSFORMER STAIRS/PLATFORMS/GRATING/FRAMING Description: TUNNEL TRANS TRANSFORMER OIL CONTAINMENT DETAIL A1-11 (1&11) - TUNNEL PLAN AND SECTION Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 15824 | Forwarded | For Review | 2021-03-25 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-01 | Submittal Number: 05 50 00-58.0 From: DOMINGO SAMPAYO Final Due Date: 04/07/21 Subject: TUNNEL TRANSFORMER STAIRS/PLATFORMS/GRATING/FRAMING Description: TUNNEL TRANS TRANSFORMER OIL CONTAINMENT DETAIL A1-11 (1&11) - TUNNEL PLAN AND SECTION Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12704 | Review Response | Approved as Noted | 2021-04-07 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See comments in attached submittal. Populous to verify geometry and painting/finish requirements. TT-FK ¦ 2021-04-07 | Info Exchange
| 12577 | Review Response | Approved as Noted | 2021-04-14 | Franz Kogler (Thornton Tomasetti) | Tom Usher (Populous) |  | Pending response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments in attached submittal. Populous to verify geometry and painting/finish requirements. TT-FK ¦ 2021-04-07 | Info Exchange
| 16433 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-21 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See comments in attached submittal. Populous to verify geometry and painting/finish requirements. TT-FK ¦ 2021-04-07 Resubmit one of the stairs with new layout provided on A3-07-4. POP-TAS | Info Exchange
| 16588 | Sent | For Information Only | 2021-04-27 | Populous SCA_CCA | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: See comments in attached submittal. Populous to verify geometry and painting/finish requirements. TT-FK ¦ 2021-04-07 Resubmit one of the stairs with new layout provided on A3-07-4. POP-TAS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-24 |  | 05 50 00-58 Tunnel Transformer Stairs-Platforms-Grating-Framing.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-24 |  | 05 50 00-58 Tunnel Transformer Stairs-Platforms-Grating-Framing.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-03-24 |  | 05 50 00-58 Tunnel Transformer Stairs-Platforms-Grating-Framing.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-21 |  | 05 50 00-58 Tunnel Transformer Stairs-Platforms-Grating-Framing_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-22 |  | A3-07-4 - ENLARGED PLANS - GENERATOR ENCLOSURE.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-03-23 02:00 |  | 05 50 00-58 Tunnel Transformer Stairs-Platforms-Grating-Framing.pdf
05 50 00-058-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-058-01 Tunnel Transformer Stairs/Platforms/Grating/Framing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-08 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-22 | 2021-06-22 | 15 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-06-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13451 | Received | For Review | 2021-06-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-06-22 | Submittal Number: 05 50 00-58.1 From: DOMINGO SAMPAYO Final Due Date: 06/21/21 Subject: TUNNEL TRANSFORMER STAIRS/PLATFORMS/GRATING/FRAMING Description: TUNNEL TRANS TRANSFORMER OIL CONTAINMENT DETAIL A1-11 (1&11) - TUNNEL PLAN AND SECTION Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 17390 | Forwarded | For Review | 2021-06-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-15 | Submittal Number: 05 50 00-58.1 From: DOMINGO SAMPAYO Final Due Date: 06/21/21 Subject: TUNNEL TRANSFORMER STAIRS/PLATFORMS/GRATING/FRAMING Description: TUNNEL TRANS TRANSFORMER OIL CONTAINMENT DETAIL A1-11 (1&11) - TUNNEL PLAN AND SECTION Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13613 | Review Response | Approved as Noted | 2021-06-17 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached submittal for comments. | Info Exchange
| 17627 | Responded and Closed | Approved as Noted | 2021-06-22 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-08 |  | 05 50 00-58 Rev1 Tunnel Transformer Stairs-Platforms-Grating-Framing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-08 |  | 05 50 00-58 Rev1 Tunnel Transformer Stairs-Platforms-Grating-Framing.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-06-08 |  | 05 50 00-58 Rev1 Tunnel Transformer Stairs-Platforms-Grating-Framing.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-06-17 |  | 05 50 00-58 Rev1 Tunnel Transformer Stairs-Platforms-Grating-Framing_TT.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-06-22 |  | 05 50 00-58 Rev1 Tunnel Transformer Stairs-Platforms-Grating-Framing_TT-POP.pdf
05 50 00-059-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-059-00 HSS Snorkel Tubes (NE and SE) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-21 | 2020-12-10 | 4 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09939 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-21 | Submittal Number: 05 50 00-59.0 From: DOMINGO SAMPAYO Final Due Date: 12/11/20 Subject: HSS SNORKEL TUBES (NE AND SE) Description: HSS SNORKEL TUBES (NE AND SE) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13018 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-14 | Submittal Number: 05 50 00-59.0 From: DOMINGO SAMPAYO Final Due Date: 12/11/20 Subject: HSS SNORKEL TUBES (NE AND SE) Description: HSS SNORKEL TUBES (NE AND SE) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10079 | Review Response | Approved as Noted | 2020-12-09 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has provided a cursory review of this submittal per CFMF submittals in NE and SE snorkels as well as RFI 3557. CFMF engineer is to review for conformance to their steel and connections and provide responses to all questions as noted. | Info Exchange
| 13175 | Responded and Closed | Approved as Noted | 2020-12-10 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | TT has provided a cursory review of this submittal per CFMF submittals in NE and SE snorkels as well as RFI 3557. CFMF engineer is to review for conformance to their steel and connections and provide responses to all questions as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-04 |  | 05 50 00-59 HSS Snorkel Tubes.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-04 |  | 05 50 00-59 HSS Snorkel Tubes.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-04 |  | 05 50 00-59 HSS Snorkel Tubes.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-10 |  | 05 50 00-59 HSS Snorkel Tubes_TT_POP.pdf
05 50 00-060-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-060-00 Extra Sump Pit Ladders (NOT INCLUDING Elevator or Snorkels) | Closed | Structural, Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-04-23 | 2021-05-04 | 26 |  | Record Copies; Transfers; Submittals | 05 50 00-060-00-01 - 05 50 00-060-00 Extra Sump Pit Ladders (NOT INCLUDING Elevator or Snorkels) | 2 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12495 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-23 | Submittal Number: 05 50 00-60.0 From: DOMINGO SAMPAYO Final Due Date: 04/12/21 Subject: EXTRA SUMP PIT LADDERS (NOT INCLUDING ELEVATOR OR SNORKELS) Description: EXTRA SUMP PIT LADDERS (ALL NONE-ELEVATOR OR SNORKELS) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16183 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-15 | Submittal Number: 05 50 00-60.0 From: DOMINGO SAMPAYO Final Due Date: 04/12/21 Subject: EXTRA SUMP PIT LADDERS (NOT INCLUDING ELEVATOR OR SNORKELS) Description: EXTRA SUMP PIT LADDERS (ALL NONE-ELEVATOR OR SNORKELS) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12552 | Review Response | Revise and Resubmit | 2021-04-09 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Revise based on TT comments. All pit walls below Event Level are concrete as noted on structural drawings. Provide shop drawings for EOR to review and approve. Arch to review. | Info Exchange
| 16260 | Forwarded | For Review | 2021-04-12 | Populous SCA_CCA | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-04-19 | Submittal Number: 05 50 00-60.0 From: DOMINGO SAMPAYO Final Due Date: 04/12/21 Subject: EXTRA SUMP PIT LADDERS (NOT INCLUDING ELEVATOR OR SNORKELS) Description: EXTRA SUMP PIT LADDERS (ALL NONE-ELEVATOR OR SNORKELS) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16742 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-04 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Approved as noted per architectural comments - please refer to structural comments for revise and resubmit components. | Info Exchange
| 16764 | Sent | For Information Only | 2021-05-05 | Populous SCA_CCA | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Responded and Closed (Approved as Noted/Resubmit) to: Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Approved as noted per architectural comments - please refer to structural comments for revise and resubmit components. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 05 50 00-60 Extra Sump Pit Ladders (NOT INCLUDING Elevator or Snorkels).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 05 50 00-60 Extra Sump Pit Ladders (NOT INCLUDING Elevator or Snorkels).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-07 02:00 |  | 05 50 00-60 Extra Sump Pit Ladders (NOT INCLUDING Elevator or Snorkels).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-07 02:00 |  | 05 50 00-60 Extra Sump Pit Ladders (NOT INCLUDING Elevator or Snorkels).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-04 02:00 |  | 05 50 00-60 Extra Sump Pit Ladders (NOT INCLUDING Elevator or Snorkels)_TT_pop.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-04-07 02:00 |  | 05 50 00-60 Extra Sump Pit Ladders (NOT INCLUDING Elevator or Snorkels).pdf
05 50 00-060-00-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-060-00 Extra Sump Pit Ladders (NOT INCLUDING Elevator or Snorkels) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 50 00-060-00 - 05 50 00-060-00 Extra Sump Pit Ladders (NOT INCLUDING Elevator or Snorkels) | -1 | 2021-05-18
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-04 02:00 |  | 05 50 00-60 Extra Sump Pit Ladders (NOT INCLUDING Elevator or Snorkels)_TT_pop.pdf
05 50 00-061-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-061-00 HSS Snorkel Tubes (NW and SW) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-10 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-24 | 2020-12-15 | 6 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10077 | Received | For Review | 2020-12-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-12-24 | Submittal Number: 05 50 00-61.0 From: DOMINGO SAMPAYO Final Due Date: 12/22/20 Subject: HSS SNORKEL TUBES (NW AND SW) Description: HSS SNORKEL TUBES (NW AND SW) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13173 | Forwarded | For Review | 2020-12-10 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-17 | Submittal Number: 05 50 00-61.0 From: DOMINGO SAMPAYO Final Due Date: 12/22/20 Subject: HSS SNORKEL TUBES (NW AND SW) Description: HSS SNORKEL TUBES (NW AND SW) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10159 | Review Response | Approved as Noted | 2020-12-14 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | CFMF Engineer to review and approve. TT has provided a cursory review. | Info Exchange
| 13292 | Responded and Closed | Approved as Noted | 2020-12-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | CFMF Engineer to review and approve. TT has provided a cursory review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-09 |  | 05 50 00-61 HSS Snorkel Tubes (NW and SW).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-09 |  | 05 50 00-61 HSS Snorkel Tubes (NW and SW).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-09 |  | 05 50 00-61 HSS Snorkel Tubes (NW and SW).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-15 |  | 05 50 00-61 HSS Snorkel Tubes (NW and SW)_TT_POP.pdf
05 50 00-062-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-062-00 Tunnel Suite Base Channel and Angle | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-08 | 2021-02-09 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10932 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-08 | Submittal Number: 05 50 00-62.0 From: DOMINGO SAMPAYO Final Due Date: 02/05/21 Subject: TUNNEL SUITE BASE CHANNEL AND ANGLE Description: TUNNEL SUITE (POWDER COATED C SHAPE & L SHAPE PLATES) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14193 | Forwarded | For Review | 2021-01-25 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-01 | Submittal Number: 05 50 00-62.0 From: DOMINGO SAMPAYO Final Due Date: 02/05/21 Subject: TUNNEL SUITE BASE CHANNEL AND ANGLE Description: TUNNEL SUITE (POWDER COATED C SHAPE & L SHAPE PLATES) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11886 | Review Response | Approved as Noted | 2021-02-03 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Kuebler Perry (Populous) |  | Populous to Review. | Info Exchange
| 11282 | Review Response | Approved as Noted | 2021-02-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14626 | Responded and Closed | Approved as Noted | 2021-02-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 05 50 00-62.1 Tunnel Suite Base Channel and Angle (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-25 |  | 05 50 00-62.1 Tunnel Suite Base Channel and Angle (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-24 02:00 |  | 05 50 00-62.1 Tunnel Suite Base Channel and Angle (MAM Review).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-09 |  | 05 50 00-62.0 Tunnel Suite Base Channel and Angle (MAM Review)_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-25 |  | 05 50 00-62.1 Tunnel Suite Base Channel and Angle (MAM Review).pdf
05 50 00-064-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-064-00 Curtainwall Support Angles at East Elevation of NE Snorkel | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-05 | 2021-02-08 | 18 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10894 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-02-05 | Submittal Number: 05 50 00-64.0 From: DOMINGO SAMPAYO Final Due Date: 02/01/21 Subject: CURTAINWALL SUPPORT ANGLES AT EAST ELEVATION OF NE SNORKEL Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14148 | Forwarded | For Review | 2021-01-22 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-29 | Submittal Number: 05 50 00-64.0 From: DOMINGO SAMPAYO Final Due Date: 02/01/21 Subject: CURTAINWALL SUPPORT ANGLES AT EAST ELEVATION OF NE SNORKEL Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11257 | Review Response | Revise and Resubmit | 2021-02-02 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | Contractor to provide loads imposed from curtainwall to base structural steel for EOR to review and approve. Connection of CW to roof steel to include vertically long slotted holes per 9/S8-12 to allow for deflection. | Info Exchange
| 14577 | Responded and Closed | Approved as Noted | 2021-02-08 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-21 |  | 05 50 00-64 CW Support Angles at East Elev NE Snorkel.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-21 |  | 05 50 00-64 CW Support Angles at East Elev NE Snorkel.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-21 |  | 05 50 00-64 CW Support Angles at East Elev NE Snorkel.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-08 |  | 05 50 00-64 CW Support Angles at East Elev NE Snorkel_TT_POP.pdf
05 50 00-065-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-065-00 Garage Beam Strengthening (Reinforcing Steel) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-05 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-19 | 2021-01-11 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10444 | Received | For Review | 2021-01-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-01-19 | Submittal Number: 05 50 00-65.0 From: DOMINGO SAMPAYO Final Due Date: 01/19/21 Subject: GARAGE BEAM STRENGTHENING (REINFORCING STEEL) Description: ADDED STEEL PER CCD079 Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13632 | Forwarded | For Review | 2021-01-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-12 | Submittal Number: 05 50 00-65.0 From: DOMINGO SAMPAYO Final Due Date: 01/19/21 Subject: GARAGE BEAM STRENGTHENING (REINFORCING STEEL) Description: ADDED STEEL PER CCD079 Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10582 | Review Response | Approved as Noted | 2021-01-06 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 13787 | Responded and Closed | Approved as Noted | 2021-01-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-04 |  | 05 50 00-65 Garage Beam Strengthening (Reinforcing Steel).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-04 |  | 05 50 00-65 Garage Beam Strengthening (Reinforcing Steel).pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2021-01-04 |  | 05 50 00-65 Garage Beam Strengthening (Reinforcing Steel).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-01-11 |  | 05 50 00-65 Garage Beam Strengthening (Reinforcing Steel)_TT_POP.pdf
05 50 00-066-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-066-00 Steel Plate at SE Snorkel CW/FCS Interface | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-05 | 2021-02-08 | 18 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10893 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-02-05 | Submittal Number: 05 50 00-66.0 From: DOMINGO SAMPAYO Final Due Date: 02/01/21 Subject: STEEL PLATE AT SE SNORKEL CW/FCS INTERFACE Description: STEEL PLATE ADDED IN CCD 67. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14147 | Forwarded | For Review | 2021-01-22 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-29 | Submittal Number: 05 50 00-66.0 From: DOMINGO SAMPAYO Final Due Date: 02/01/21 Subject: STEEL PLATE AT SE SNORKEL CW/FCS INTERFACE Description: STEEL PLATE ADDED IN CCD 67. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11884 | Review Response | Approved as Noted | 2021-02-02 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  |  | Info Exchange
| 14576 | Responded and Closed | Approved as Noted | 2021-02-08 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-21 |  | 05 50 00-66 Steel Plate at SE Snorkel CW FCS Interface.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-21 |  | 05 50 00-66 Steel Plate at SE Snorkel CW FCS Interface.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-20 02:00 |  | 05 50 00-66 Steel Plate at SE Snorkel CW FCS Interface.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-08 |  | 05 50 00-66 Steel Plate at SE Snorkel CW FCS Interface_TT_POP.pdf
05 50 00-067-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-067-00 Ice Melt Pit Lid Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-14 | Closed - Void |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Chris Minter (Populous) |  |  |  | 2021-01-06 |  | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-12-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10131 | Received | For Review | 2020-12-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2021-01-06 | Submittal Number: 05 50 00-67.0 From: CHRISTIAN ALBERS Final Due Date: 12/28/20 Subject: ICE MELT PIT LID SHOP DRAWINGS Description: SEE ATTACHED SHOP DRAWINGS FOR THE ICE MELT PIT LID. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13246 | Forwarded | For Review | 2020-12-14 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-21 | Submittal Number: 05 50 00-67.0 From: CHRISTIAN ALBERS Final Due Date: 12/28/20 Subject: ICE MELT PIT LID SHOP DRAWINGS Description: SEE ATTACHED SHOP DRAWINGS FOR THE ICE MELT PIT LID. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13316 | Forwarded | For Review | 2020-12-15 | Todd Spangler (Populous) | Chris Minter (Populous) |  | Submittal Number: 05 50 00-67.0 From: CHRISTIAN ALBERS Final Due Date: 12/28/20 Subject: ICE MELT PIT LID SHOP DRAWINGS Description: SEE ATTACHED SHOP DRAWINGS FOR THE ICE MELT PIT LID. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13500 | Closed | Void | 2020-12-22 | Josh Dobken (Populous) |  |  | Voided per 12/22 Document Control meeting. Item is a duplicate of submittal 08 31 13-005-00
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-14 |  | 05 50 00 - 0067 - Ice Melt Pit Lid Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-14 |  | 05 50 00 - 0067 - Ice Melt Pit Lid Shop Drawings.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-12-14 |  | 05 50 00 - 0067 - Ice Melt Pit Lid Shop Drawings.pdf
05 50 00-069-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-069-00 Suspended Pipe Grid (Press Bridge) | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-08 | 2021-02-12 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-02-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10923 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-02-08 | Submittal Number: 05 50 00-69.0 From: DOMINGO SAMPAYO Final Due Date: 02/03/21 Subject: SUSPENDED PIPE GRID (PRESS BRIDGE) Description: SEE RFI #3640: SUSPENDED PIPE GRID DETAILS NEEDED (PRESS BRIDGE) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14183 | Forwarded | For Review | 2021-01-25 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-01 | Submittal Number: 05 50 00-69.0 From: DOMINGO SAMPAYO Final Due Date: 02/03/21 Subject: SUSPENDED PIPE GRID (PRESS BRIDGE) Description: SEE RFI #3640: SUSPENDED PIPE GRID DETAILS NEEDED (PRESS BRIDGE) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11381 | Review Response | Approved | 2021-02-05 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Contractor to submit connection calcs as noted and loads imposed for EOR to review and approve. Populous to review. | Info Exchange
| 11392 | Review Response | Revise and Resubmit | 2021-02-12 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14757 | Responded and Closed | Revise and Resubmit | 2021-02-12 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Contractor to submit connection calcs as noted and loads imposed for EOR to review and approve. Populous to review. Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-22 |  | 05 50 00-69 Suspended Pipe Grid (Press Bridge).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-22 |  | 05 50 00-69 Suspended Pipe Grid (Press Bridge).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-22 |  | 05 50 00-69 Suspended Pipe Grid (Press Bridge).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-12 |  | 05 50 00-69 Suspended Pipe Grid (Press Bridge)_TT_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-01-22 |  | 05 50 00-69 Suspended Pipe Grid (Press Bridge).pdf
05 50 00-069-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-069-01 Suspended Pipe Grid (Press Bridge) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-25 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-09 | 2021-06-30 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-06-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13656 | Received | For Review | 2021-06-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-09 | Submittal Number: 05 50 00-69.1 From: DOMINGO SAMPAYO Final Due Date: 06/28/21 Subject: SUSPENDED PIPE GRID (PRESS BRIDGE) Description: SEE RFI #3640: SUSPENDED PIPE GRID DETAILS NEEDED (PRESS BRIDGE) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 17681 | Forwarded | For Review | 2021-06-25 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-02 | Submittal Number: 05 50 00-69.1 From: DOMINGO SAMPAYO Final Due Date: 06/28/21 Subject: SUSPENDED PIPE GRID (PRESS BRIDGE) Description: SEE RFI #3640: SUSPENDED PIPE GRID DETAILS NEEDED (PRESS BRIDGE) Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13724 | Review Response | Approved as Noted | 2021-06-28 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Arch to review. | Info Exchange
| 13744 | Review Response | Approved as Noted | 2021-06-30 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17790 | Responded and Closed | Approved as Noted | 2021-06-30 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Arch to review. Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-25 |  | 055000-69.1 Climate Pledge Arena Suspended Pipe Grid.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-25 |  | 055000-69.1 Climate Pledge Arena Suspended Pipe Grid.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-06-25 |  | 055000-69.1 Climate Pledge Arena Suspended Pipe Grid.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-30 |  | 055000-69.1 Climate Pledge Arena Suspended Pipe Grid_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-25 |  | 055000-69.1 Climate Pledge Arena Suspended Pipe Grid.pdf
05 50 00-070-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-070-00 Masonry Wrap Plates | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-29 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2021-02-12 | 2021-02-12 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-02-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11043 | Received | For Review | 2021-01-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-02-12 | Submittal Number: 05 50 00-70.0 From: DOMINGO SAMPAYO Final Due Date: 02/12/21 Subject: MASONRY WRAP PLATES Description: MASONRY WRAP PLATES ADDED PER CCD075. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14338 | Forwarded | For Review | 2021-01-29 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-05 | Submittal Number: 05 50 00-70.0 From: DOMINGO SAMPAYO Final Due Date: 02/12/21 Subject: MASONRY WRAP PLATES Description: MASONRY WRAP PLATES ADDED PER CCD075. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14636 | Forwarded | For Review | 2021-02-09 | Josh Dobken (Populous) | Todd Spangler (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-02-12 | Submittal Number: 05 50 00-70.0 From: DOMINGO SAMPAYO Final Due Date: 02/12/21 Subject: MASONRY WRAP PLATES Description: MASONRY WRAP PLATES ADDED PER CCD075. Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14743 | Responded and Closed | Rejected | 2021-02-12 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | DUE TO WALL TYPE CHANGES AT THESE LOCATIONS, THESE PLATES ARE NO LONGER REQUIRED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-28 |  | 05 50 00-70 Masonry Wrap Plates.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-28 |  | 05 50 00-70 Masonry Wrap Plates.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-27 02:00 |  | 05 50 00-70 Masonry Wrap Plates.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-02-12 |  | 05 50 00-70 Masonry Wrap Plates-POP-2.pdf
05 50 00-071-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-071-00 Metal Rod System at Main Concourse Club Spaces | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-29 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2021-02-12 | 2021-02-23 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2021-02-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11044 | Received | For Review | 2021-01-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2021-02-12 | Submittal Number: 05 50 00-71.0 From: DOMINGO SAMPAYO Final Due Date: 02/05/21 Subject: METAL ROD SYSTEM AT MAIN CONCOURSE CLUB SPACES Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14339 | Forwarded | For Review | 2021-01-29 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-05 | Submittal Number: 05 50 00-71.0 From: DOMINGO SAMPAYO Final Due Date: 02/05/21 Subject: METAL ROD SYSTEM AT MAIN CONCOURSE CLUB SPACES Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14634 | Forwarded | For Review | 2021-02-09 | Josh Dobken (Populous) | Todd Spangler (Populous); Kuebler Perry (Populous); Chad Francis (Populous) | 2021-02-12 | Submittal Number: 05 50 00-71.0 From: DOMINGO SAMPAYO Final Due Date: 02/05/21 Subject: METAL ROD SYSTEM AT MAIN CONCOURSE CLUB SPACES Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 15043 | Responded and Closed | Approved as Noted | 2021-02-23 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED FOR COMMENTS. 1. CM TO COORDINATE ROCKWELL GROUP COMMENTS. REFER TO NOTES FOR ROCKWELL TO PROVIDE SKETCH AT PLATE AND FINISH TYPE FOR RODS ON SHEET E-A3-03-6 A | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-28 |  | 05 50 00-71.0 Metal Rod System at Main Concourse Club Spaces (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-28 |  | 05 50 00-71.0 Metal Rod System at Main Concourse Club Spaces (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-27 02:00 |  | 05 50 00-71.0 Metal Rod System at Main Concourse Club Spaces (MAM Review).pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-23 |  | 05 50 00-71.0 Metal Rod System at Main Concourse Club Spaces (MAM Review)_POP_TT.pdf
05 50 00-072-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-072-00 Glass Canopy Support at Main Concourse Club T-bars | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-08 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-22 | 2021-01-14 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10545 | Received | For Review | 2021-01-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-22 | Submittal Number: 05 50 00-72.0 From: NATE WEINGART Final Due Date: 01/22/21 Subject: GLASS CANOPY SUPPORT AT MAIN CONCOURSE CLUB T-BARS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13744 | Forwarded | For Review | 2021-01-08 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-15 | Submittal Number: 05 50 00-72.0 From: NATE WEINGART Final Due Date: 01/22/21 Subject: GLASS CANOPY SUPPORT AT MAIN CONCOURSE CLUB T-BARS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10837 | Review Response | Approved as Noted | 2021-01-11 | Matt Ross (Thornton Tomasetti) | Kuebler Perry (Populous); Populous SCA_CCA |  | Arch to review clashes within submittal and advise. Solution to be communicated to TT. Coordinate steel branch arm locations to align with canopy attachment points, typ. | Info Exchange
| 10717 | Review Response | Revise and Resubmit | 2021-01-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 13941 | Responded and Closed | Revise and Resubmit | 2021-01-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | 05 50 00-72.0 Glass Canopy Support at Main Con Club T-Bars (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-08 |  | 05 50 00-72.0 Glass Canopy Support at Main Con Club T-Bars (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-07 02:00 |  | 05 50 00-72.0 Glass Canopy Support at Main Con Club T-Bars (MAM Review).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-14 |  | 05 50 00-72.0 Glass Canopy Support at Main Con Club T-Bars (MAM Review)_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-08 |  | 05 50 00-72.0 Glass Canopy Support at Main Con Club T-Bars (MAM Review).pdf
05 50 00-072-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-072-01 Glass Canopy Support at Main Concourse Club T-bars | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-18 | 2021-02-19 | 16 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11178 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-18 | Submittal Number: 05 50 00-72.1 From: DOMINGO SAMPAYO Final Due Date: 02/18/21 Subject: GLASS CANOPY SUPPORT AT MAIN CONCOURSE CLUB T-BARS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14484 | Forwarded | For Review | 2021-02-03 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-10 | Submittal Number: 05 50 00-72.1 From: DOMINGO SAMPAYO Final Due Date: 02/18/21 Subject: GLASS CANOPY SUPPORT AT MAIN CONCOURSE CLUB T-BARS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11559 | Review Response | Approved | 2021-02-04 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has only reviewed submittal for clouded changes, MAM questions, and to be sure previous comments have been addressed. TT assumes all other items remain unchanged since previous review. | Info Exchange
| 11543 | Review Response | Approved as Noted | 2021-02-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14963 | Responded and Closed | Approved as Noted | 2021-02-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-03 |  | 05 50 00-72.1 Glass Canopy Support at Main Con Club T-Bars (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-03 |  | 05 50 00-72.1 Glass Canopy Support at Main Con Club T-Bars (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-02 02:00 |  | 05 50 00-72.1 Glass Canopy Support at Main Con Club T-Bars (MAM Review).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-19 |  | 05 50 00-72.1 Glass Canopy Support at Main Con Club T-Bars (MAM Review)_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-03 |  | 05 50 00-72.1 Glass Canopy Support at Main Con Club T-Bars (MAM Review).pdf
05 50 00-073-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-073-00 Main Concourse Club Craft Beer Bar Canopy Support | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-13 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-28 08:00 | 2021-02-04 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2021-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10666 | Received | For Review | 2021-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2021-01-28 08:00 | Submittal Number: 05 50 00-73.0 From: DOMINGO SAMPAYO Final Due Date: 01/22/21 Subject: MAIN CONCOURSE CLUB CRAFT BEER BAR CANOPY SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13887 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-20 | Submittal Number: 05 50 00-73.0 From: DOMINGO SAMPAYO Final Due Date: 01/22/21 Subject: MAIN CONCOURSE CLUB CRAFT BEER BAR CANOPY SUPPORT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 11611 | Review Response | Approved as Noted | 2021-01-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 11187 | Review Response | Approved as Noted | 2021-02-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14493 | Responded and Closed | Approved as Noted | 2021-02-04 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 05 50 00-73.0 Main Concourse Club Craft Beer Bar Canopy Support (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 05 50 00-73.0 Main Concourse Club Craft Beer Bar Canopy Support (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-11 02:00 |  | 05 50 00-73.0 Main Concourse Club Craft Beer Bar Canopy Support (MAM Review).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-04 |  | 05 50 00-73.0 Main Concourse Club Craft Beer Bar Canopy Support (MAM Review)_TT _POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-12 |  | 05 50 00-73.0 Main Concourse Club Craft Beer Bar Canopy Support (MAM Review).pdf
05 50 00-074-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-074-00 HSS Support for Main Con Club Entry Storefront | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-18 08:00 | 2021-01-14 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10368 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2021-01-18 08:00 | Submittal Number: 05 50 00-74.0 From: NATE WEINGART Final Due Date: 01/13/21 Subject: HSS SUPPORT FOR MAIN CON CLUB ENTRY STOREFRONT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13549 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-11 | Submittal Number: 05 50 00-74.0 From: NATE WEINGART Final Due Date: 01/13/21 Subject: HSS SUPPORT FOR MAIN CON CLUB ENTRY STOREFRONT Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 10836 | Review Response | Approved as Noted | 2021-01-07 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 10716 | Review Response | Approved as Noted | 2021-01-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 13940 | Responded and Closed | Approved as Noted | 2021-01-14 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-29 |  | 05 50 00-74.0 HSS Support for Main Con Club Entry Storefront (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-29 |  | 05 50 00-74.0 HSS Support for Main Con Club Entry Storefront (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-28 02:00 |  | 05 50 00-74.0 HSS Support for Main Con Club Entry Storefront (MAM Review).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-14 |  | 05 50 00-74.0 HSS Support for Main Con Club Entry Storefront (MAM Review)_TT_POP REVIEW.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-29 |  | 05 50 00-74.0 HSS Support for Main Con Club Entry Storefront (MAM Review).pdf
05 50 00-076-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-076-00 CL22 Steel Support Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-29 | 2021-04-09 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2021-04-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11987 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-29 | Submittal Number: 05 50 00-76.0 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: CL22 STEEL SUPPORT SHOP DRAWINGS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 15527 | Forwarded | For Review | 2021-03-15 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-22 | Submittal Number: 05 50 00-76.0 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: CL22 STEEL SUPPORT SHOP DRAWINGS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12524 | Review Response | Approved as Noted | 2021-03-22 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See comments in attached submittal return. Populous to review painting requirements. TT-FK ¦ 2021-03-22 | Info Exchange
| 12505 | Review Response | Approved as Noted | 2021-04-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 16194 | Responded and Closed | Approved as Noted | 2021-04-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-14 |  | 05 50 00-76.0 CL22 Steel Support SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-14 |  | 05 50 00-76.0 CL22 Steel Support SD-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-03-13 02:00 |  | 05 50 00-76.0 CL22 Steel Support SD-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-09 |  | 05 50 00-76.0 CL22 Steel Support SD-MAM_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-14 |  | 05 50 00-76.0 CL22 Steel Support SD-MAM.pdf
05 50 00-077-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-077-00 Counter Brackets for Security Room Wall | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-01 | 2021-03-31 | 14 |  | Record Copies; Transfers; Submittals | 05 50 00-077-00-01 - 05 50 00-077-00 Counter Brackets for Security Room Wall | 14 |  | 2021-03-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12091 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-01 | Submittal Number: 05 50 00-77.0 From: DOMINGO SAMPAYO Final Due Date: 03/31/21 Subject: COUNTER BRACKETS FOR SECURITY ROOM WALL Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 15649 | Forwarded | For Review | 2021-03-18 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-25 | Submittal Number: 05 50 00-77.0 From: DOMINGO SAMPAYO Final Due Date: 03/31/21 Subject: COUNTER BRACKETS FOR SECURITY ROOM WALL Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12325 | Review Response | Revise and Resubmit | 2021-03-23 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Revise calcs and details as noted. Arch to review. | Info Exchange
| 12334 | Review Response | Revise and Resubmit | 2021-03-31 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15972 | Responded and Closed | Revise and Resubmit | 2021-03-31 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Revise calcs and details as noted. Arch to review. Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-17 |  | 05 50 00-77.0 Counter Brackets for Security Room SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-17 |  | 05 50 00-77.0 Counter Brackets for Security Room SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-17 |  | 05 50 00-77.0 Counter Brackets for Security Room SD-MAM.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-31 |  | 05 50 00-77.0 Counter Brackets for Security Room SD-MAM_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-17 |  | 05 50 00-77.0 Counter Brackets for Security Room SD-MAM.pdf
05 50 00-077-00-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-077-00 Counter Brackets for Security Room Wall | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 50 00-077-00 - 05 50 00-077-00 Counter Brackets for Security Room Wall | -1 | 2021-04-14
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-17 |  | 05 50 00-77.0 Counter Brackets for Security Room SD-MAM.pdf
05 50 00-079-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-079-00 SE Detention Tank Ladders | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-04-01 | 2021-04-12 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2021-04-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12092 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-04-01 | Submittal Number: 05 50 00-79.0 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: SE DETENTION TANK LADDERS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 15650 | Forwarded | For Review | 2021-03-18 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-25 | Submittal Number: 05 50 00-79.0 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: SE DETENTION TANK LADDERS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16122 | Forwarded | For Review | 2021-04-06 | Josh Dobken (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-04-01 | Submittal Number: 05 50 00-79.0 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: SE DETENTION TANK LADDERS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Email
| 12549 | Review Response | Approved as Noted | 2021-04-12 | Jarrett Grant (DCI Engineers) | Josh Dobken (Populous) |  |  | Info Exchange
| 16256 | Responded and Closed | Approved as Noted | 2021-04-12 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: Contractor shall use option 1 (poly ladder) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-17 |  | 05 50 00-79 SE Detention Tank Ladders.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-17 |  | 05 50 00-79 SE Detention Tank Ladders.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-16 02:00 |  | 05 50 00-79 SE Detention Tank Ladders.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-04-12 02:00 |  | 05 50 00-79 SE Detention Tank Ladders_DCI.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-12 02:00 |  | 05 50 00-79 SE Detention Tank Ladders_DCI_POP.pdf
05 50 00-080-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-080-00 Grates (Elevators Only) | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-04 | 2021-06-09 | 51 |  | Record Copies; Transfers; Submittals |  | 51 |  | 2021-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12658 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-04 | Submittal Number: 05 50 00-80.0 From: DOMINGO SAMPAYO Final Due Date: 05/03/21 Subject: GRATES (ELEVATORS ONLY) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16380 | Forwarded | For Review | 2021-04-20 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-27 | Submittal Number: 05 50 00-80.0 From: DOMINGO SAMPAYO Final Due Date: 05/03/21 Subject: GRATES (ELEVATORS ONLY) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13465 | Review Response | Approved | 2021-06-09 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | Arch to review. | Info Exchange
| 17410 | Responded and Closed | Approved as Noted | 2021-06-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-19 |  | 05 50 00-80 Grates (Elevators Only).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-19 |  | 05 50 00-80 Grates (Elevators Only).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-19 |  | 05 50 00-80 Grates (Elevators Only).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-09 |  | 05 50 00-80 Grates (Elevators Only) MAM_TT_POP.pdf
05 50 00-081-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-081-00 A6 Elevator Ladders & Rails (Upper Concourse) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-23 | 2021-04-13 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12496 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-23 | Submittal Number: 05 50 00-81.0 From: DOMINGO SAMPAYO Final Due Date: 04/12/21 Subject: A6 ELEVATOR LADDERS & RAILS (UPPER CONCOURSE) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16184 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-15 | Submittal Number: 05 50 00-81.0 From: DOMINGO SAMPAYO Final Due Date: 04/12/21 Subject: A6 ELEVATOR LADDERS & RAILS (UPPER CONCOURSE) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12559 | Review Response | Approved as Noted | 2021-04-09 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Arch to review. Shop drawings are to be submitted to EOR for review and approval. Any attachments/loads imposed to stud wall are to be coordinated with CFMF engineer. Revised calcs/attachments for CFMF to structure are to be sent to EOR for review and approval if revisions are required. | Info Exchange
| 16268 | Responded and Closed | Approved as Noted | 2021-04-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Shop drawings are to be submitted to EOR for review and approval. Any attachments/loads imposed to stud wall are to be coordinated with CFMF engineer. Revised calcs/attachments for CFMF to structure are to be sent to EOR for review and approval if revisions are required. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 05 50 00-81 A6 Elevator Ladders-Rails (Upper).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 05 50 00-81 A6 Elevator Ladders-Rails (Upper).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-08 |  | 05 50 00-81 A6 Elevator Ladders-Rails (Upper).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-13 |  | 05 50 00-81 A6 Elevator Ladders-Rails (Upper)_TT_POP.pdf
05 50 00-082-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-082-00 Space Needle Decorative Curtain (Misc. Metals) | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-19 | 2021-04-09 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-04-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12389 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 05 50 00-82.0 From: DOMINGO SAMPAYO Final Due Date: 04/07/21 Subject: SPACE NEEDLE DECORATIVE CURTAIN (MISC. METALS) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16047 | Forwarded | For Review | 2021-04-05 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-12 | Submittal Number: 05 50 00-82.0 From: DOMINGO SAMPAYO Final Due Date: 04/07/21 Subject: SPACE NEEDLE DECORATIVE CURTAIN (MISC. METALS) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16065 | Forwarded | For Review | 2021-04-05 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-12 | Submittal Number: 05 50 00-82.0 From: DOMINGO SAMPAYO Final Due Date: 04/07/21 Subject: SPACE NEEDLE DECORATIVE CURTAIN (MISC. METALS) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12529 | Review Response | Approved as Noted | 2021-04-05 | Matt Ross (Thornton Tomasetti) | Kuebler Perry (Populous); Populous SCA_CCA |  | Arch to review track layout and dimensions. Submittal only contained Erection Drawings. Shop drawings and unistrut calcs to be submitted to EOR for review and approval. | Info Exchange
| 12514 | Review Response | Approved as Noted/Resubmit | 2021-04-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16202 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 05 50 00-82 Space Decorative Curtain Misc. Metals.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 05 50 00-82 Space Decorative Curtain Misc. Metals.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-04 02:00 |  | 05 50 00-82 Space Decorative Curtain Misc. Metals.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-04 02:00 |  | 05 50 00-82 Space Decorative Curtain Misc. Metals.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-09 |  | 05 50 00-82 Space Decorative Curtain Misc. Metals_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 05 50 00-82 Space Decorative Curtain Misc. Metals.pdf
05 50 00-082-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-082-01 Space Needle Decorative Curtain (Misc. Metals) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-07 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Kelsea Conkright (Populous), Todd Spangler (Populous), Geoff Cheong, Chris Minter (Populous) |  |  |  | 2021-06-21 | 2021-06-16 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-06-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13413 | Received | For Review | 2021-06-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-21 | Submittal Number: 05 50 00-82.1 From: DOMINGO SAMPAYO Final Due Date: 06/18/21 Subject: SPACE NEEDLE DECORATIVE CURTAIN (MISC. METALS) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 17346 | Forwarded | For Review | 2021-06-07 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-14 | Submittal Number: 05 50 00-82.1 From: DOMINGO SAMPAYO Final Due Date: 06/18/21 Subject: SPACE NEEDLE DECORATIVE CURTAIN (MISC. METALS) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 17362 | Forwarded | For Review | 2021-06-07 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Geoff Cheong; Chris Minter (Populous) | 2021-06-14 | Submittal Number: 05 50 00-82.1 From: DOMINGO SAMPAYO Final Due Date: 06/18/21 Subject: SPACE NEEDLE DECORATIVE CURTAIN (MISC. METALS) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13589 | Review Response | Approved as Noted/Resubmit | 2021-06-14 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Arch to review. Contractor to submit final shop drawings for record with all comments addressed. | Info Exchange
| 13549 | Review Response | Approved as Noted | 2021-06-16 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17540 | Responded and Closed | Approved as Noted | 2021-06-16 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-04 |  | 05 50 00-82 R1 Space N Decorative Curtain.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-04 |  | 05 50 00-82 R1 Space N Decorative Curtain.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-03 02:00 |  | 05 50 00-82 R1 Space N Decorative Curtain.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-06-03 02:00 |  | 05 50 00-82 R1 Space N Decorative Curtain.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-16 |  | 05 50 00-82 R1 Space N Decorative Curtain_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-04 |  | 05 50 00-82 R1 Space N Decorative Curtain.pdf
05 50 00-084-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-084-00 Misc. Metals Stone Top Supports (Room 03.03.09 - Event Level Area A & Room 01.37.10 - Event Level Area D) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-04 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-18 | 2021-05-10 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12922 | Received | For Review | 2021-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-18 | Submittal Number: 05 50 00-84.0 From: DOMINGO SAMPAYO Final Due Date: 05/18/21 Subject: MISC. METALS STONE TOP SUPPORTS (ROOM 03.03.09 - EVENT LEVEL AREA A & ROOM 01.37.10 - EVENT LEVEL AREA D) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16704 | Forwarded | For Review | 2021-05-04 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-11 | Submittal Number: 05 50 00-84.0 From: DOMINGO SAMPAYO Final Due Date: 05/18/21 Subject: MISC. METALS STONE TOP SUPPORTS (ROOM 03.03.09 - EVENT LEVEL AREA A & ROOM 01.37.10 - EVENT LEVEL AREA D) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16754 | Forwarded | For Review | 2021-05-05 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-12 | Submittal Number: 05 50 00-84.0 From: DOMINGO SAMPAYO Final Due Date: 05/18/21 Subject: MISC. METALS STONE TOP SUPPORTS (ROOM 03.03.09 - EVENT LEVEL AREA A & ROOM 01.37.10 - EVENT LEVEL AREA D) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16804 | Forwarded | For Review | 2021-05-07 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-14 | Submittal Number: 05 50 00-84.0 From: DOMINGO SAMPAYO Final Due Date: 05/18/21 Subject: MISC. METALS STONE TOP SUPPORTS (ROOM 03.03.09 - EVENT LEVEL AREA A & ROOM 01.37.10 - EVENT LEVEL AREA D) Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 12987 | Review Response | Approved | 2021-05-10 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. Arch to review. | Info Exchange
| 13015 | Review Response | Approved as Noted | 2021-05-10 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16839 | Responded and Closed | Approved as Noted | 2021-05-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. Arch to review. Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-03 |  | 05 50 00-84 Misc. Metals Stone Top Supports (Room 03.03.09 - Event Level Area A & Room 01.37.10 - Event Level Area D).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-03 |  | 05 50 00-84 Misc. Metals Stone Top Supports (Room 03.03.09 - Event Level Area A & Room 01.37.10 - Event Level Area D).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-03 |  | 05 50 00-84 Misc. Metals Stone Top Supports (Room 03.03.09 - Event Level Area A & Room 01.37.10 - Event Level Area D).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-03 |  | 05 50 00-84 Misc. Metals Stone Top Supports (Room 03.03.09 - Event Level Area A & Room 01.37.10 - Event Level Area D).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-03 |  | 05 50 00-84 Misc. Metals Stone Top Supports (Room 03.03.09 - Event Level Area A & Room 01.37.10 - Event Level Area D).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-05-10 |  | 05 50 00-84 Misc. Top Supp (Room 01.03.09 - 01.37.10)_Revised_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-03 |  | 05 50 00-84 Misc. Metals Stone Top Supports (Room 03.03.09 - Event Level Area A & Room 01.37.10 - Event Level Area D).pdf
05 50 00-085-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-085-00 Atrium Overhead Sign Support Steel Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-26 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Kelly Holton (Populous), Mary Lim (Populous) |  |  |  | 2021-05-10 | 2021-05-17 | 22 |  | Record Copies; Transfers; Submittals | 05 50 00-085-00-01 - 05 50 00-085-00 Atrium Overhead Sign Support Steel Shop Drawings | 5 |  | 2021-05-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12747 | Received | For Review | 2021-04-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-10 | Submittal Number: 05 50 00-85.0 From: DOMINGO SAMPAYO Final Due Date: 05/07/21 Subject: ATRIUM OVERHEAD SIGN SUPPORT STEEL SHOP DRAWINGS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 16481 | Forwarded | For Review | 2021-04-24 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-03 | Submittal Number: 05 50 00-85.0 From: DOMINGO SAMPAYO Final Due Date: 05/07/21 Subject: ATRIUM OVERHEAD SIGN SUPPORT STEEL SHOP DRAWINGS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13059 | Review Response | Revise and Resubmit | 2021-04-28 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Bolted splice connection not part of sign frame design. Provide calcs for splice connection. Contractor to advise on why it is required, where it needs to be located, is bolted connection required? Can it be welded on each side of end plate? Sign steel not included in this submittal. Is this part of another submittal? Arch to review. | Info Exchange
| 16880 | Forwarded | For Review | 2021-05-11 | Populous SCA_CCA | Kelly Holton (Populous); Mary Lim (Populous) | 2021-05-10 | Submittal Number: 05 50 00-85.0 From: DOMINGO SAMPAYO Final Due Date: 05/07/21 Subject: ATRIUM OVERHEAD SIGN SUPPORT STEEL SHOP DRAWINGS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Email
| 16967 | Responded and Closed | Revise and Resubmit | 2021-05-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attahed. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-23 |  | 05 50 00-85.0 Atrium Overhead Sign Support SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-23 |  | 05 50 00-85.0 Atrium Overhead Sign Support SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-23 |  | 05 50 00-85.0 Atrium Overhead Sign Support SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-22 02:00 |  | 05 50 00-85.0 Atrium Overhead Sign Support SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-12 |  | A3-05-1A - ENLARGED PLANS - ATRIUM CEILING.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-12 |  | Atrium OH Signage Calcs_Rev 1.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-12 |  | 05 50 00-85.0 Atrium Overhead Sign Support SD-MAM_TT_POP.pdf
05 50 00-085-00-01 | 05 50 00 - METAL FABRICATIONS | 05 50 00-085-00 Atrium Overhead Sign Support Steel Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 50 00-085-00 - 05 50 00-085-00 Atrium Overhead Sign Support Steel Shop Drawings | -1 | 2021-05-31
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-12 |  | A3-05-1A - ENLARGED PLANS - ATRIUM CEILING.pdf
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-12 |  | Atrium OH Signage Calcs_Rev 1.pdf
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-12 |  | 05 50 00-85.0 Atrium Overhead Sign Support SD-MAM_TT_POP.pdf
05 50 00-086-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-086-00 North Wall Window Shade System Connection Angle | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-15 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-29 | 2021-06-22 | 8 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-06-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13526 | Received | For Review | 2021-06-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-06-29 | Submittal Number: 05 50 00-86.0 From: DOMINGO SAMPAYO Final Due Date: 06/25/21 Subject: NORTH WALL WINDOW SHADE SYSTEM CONNECTION ANGLE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 17497 | Forwarded | For Review | 2021-06-15 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-22 | Submittal Number: 05 50 00-86.0 From: DOMINGO SAMPAYO Final Due Date: 06/25/21 Subject: NORTH WALL WINDOW SHADE SYSTEM CONNECTION ANGLE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 17511 | Forwarded | For Review | 2021-06-15 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-22 | Submittal Number: 05 50 00-86.0 From: DOMINGO SAMPAYO Final Due Date: 06/25/21 Subject: NORTH WALL WINDOW SHADE SYSTEM CONNECTION ANGLE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13605 | Review Response | Approved as Noted | 2021-06-18 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Exceptions Noted, no resubmit required, see attachment. | Info Exchange
| 17614 | Responded and Closed | Approved as Noted | 2021-06-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: Exceptions Noted, no resubmit required, see attachment. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-14 |  | 05 50 00-86 North Wall Window Shade System Connection Angle.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-14 |  | 05 50 00-86 North Wall Window Shade System Connection Angle.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-14 |  | 05 50 00-86 North Wall Window Shade System Connection Angle.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-06-14 |  | 05 50 00-86 North Wall Window Shade System Connection Angle.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-22 |  | 05 50 00-86 North Wall Window Shade System Connection Angle_TT_POP.pdf
05 50 00-087-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-087-00 Sump Pit Ladders - Event Level (JR Hayes) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-27 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-11 07:00 | 2021-06-08 | 13 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-06-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13294 | Received | For Review | 2021-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-11 07:00 | Submittal Number: 05 50 00-87.0 From: DOMINGO SAMPAYO Final Due Date: 06/07/21 Subject: SUMP PIT LADDERS - EVENT LEVEL (JR HAYES) Description: SIX (6) SUMP PIT LADDERS AT EVENT LEVEL Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 17194 | Forwarded | For Review | 2021-05-27 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-03 | Submittal Number: 05 50 00-87.0 From: DOMINGO SAMPAYO Final Due Date: 06/07/21 Subject: SUMP PIT LADDERS - EVENT LEVEL (JR HAYES) Description: SIX (6) SUMP PIT LADDERS AT EVENT LEVEL Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13456 | Review Response | Approved | 2021-06-04 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 17397 | Responded and Closed | Approved | 2021-06-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-27 |  | 05 50 00-087-0 Sump Pit Ladders.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-27 |  | 05 50 00-087-0 Sump Pit Ladders.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-04 |  | 05 50 00-087-0 Sump Pit Ladders_TT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-08 |  | 05 50 00-087-0 Sump Pit Ladders_TT-POP.pdf
05 50 00-088-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-088-00 CCD108 - Added Steel at Kraken Bar | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-13 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-27 | 2021-07-20 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13935 | Received | For Review | 2021-07-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-07-27 | Submittal Number: 05 50 00-88.0 From: TYRONE THORNTON Final Due Date: 07/27/21 Subject: CCD108 - ADDED STEEL AT KRAKEN BAR Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 18039 | Forwarded | For Review | 2021-07-14 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-21 | Submittal Number: 05 50 00-88.0 From: TYRONE THORNTON Final Due Date: 07/27/21 Subject: CCD108 - ADDED STEEL AT KRAKEN BAR Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14063 | Review Response | Approved as Noted | 2021-07-20 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 14029 | Review Response | Approved as Noted | 2021-07-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18148 | Responded and Closed | Approved as Noted | 2021-07-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-13 02:00 |  | 055000-88 Climate Pledge Arena Added Steel at Kraken Bar_MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-07-13 02:00 |  | 055000-88 Climate Pledge Arena Added Steel at Kraken Bar_MAM Review.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-07-13 02:00 |  | 055000-88 Climate Pledge Arena Added Steel at Kraken Bar_MAM Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-20 |  | 055000-88 Climate Pledge Arena Added Steel at Kraken Bar_MAM Review_TT_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-13 |  | 055000-88 Climate Pledge Arena Added Steel at Kraken Bar_MAM Review.pdf
05 50 00-089-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-089-00 Guardrail Height Modification at Existing Catwalk Spotlight Platforms | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-02 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2021-07-19 07:00 | 2021-07-13 | 12 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13777 | Received | For Review | 2021-07-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-19 07:00 | Submittal Number: 05 50 00-89.0 From: SKYLER MITCHELL Final Due Date: 07/16/21 Subject: GUARDRAIL HEIGHT MODIFICATION AT EXISTING CATWALK SPOTLIGHT PLATFORMS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 17832 | Forwarded | For Review | 2021-07-06 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-13 | Submittal Number: 05 50 00-89.0 From: SKYLER MITCHELL Final Due Date: 07/16/21 Subject: GUARDRAIL HEIGHT MODIFICATION AT EXISTING CATWALK SPOTLIGHT PLATFORMS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 17869 | Forwarded | For Review | 2021-07-06 | Populous SCA_CCA | Tom Usher (Populous); Chris Minter (Populous) | 2021-07-13 | Submittal Number: 05 50 00-89.0 From: SKYLER MITCHELL Final Due Date: 07/16/21 Subject: GUARDRAIL HEIGHT MODIFICATION AT EXISTING CATWALK SPOTLIGHT PLATFORMS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13916 | Review Response | Approved as Noted | 2021-07-07 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Exceptions noted, no resubmit required. See comments in attachment. TT-FK ¦ 2021-07-07 | Info Exchange
| 18019 | Responded and Closed | Approved as Noted | 2021-07-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-02 |  | 05 50 00-89.0 Guardrail Height Modification At Existing Catwalk.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-02 |  | 05 50 00-89.0 Guardrail Height Modification At Existing Catwalk.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-01 02:00 |  | 05 50 00-89.0 Guardrail Height Modification At Existing Catwalk.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-07-02 |  | 05 50 00-89.0 Guardrail Height Modification At Existing Catwalk.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-13 |  | 05 50 00-89.0 Guardrail Ht Mod At Exist Catwalk_TT_POP.pdf
05 50 00-090-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-090-00 Added Guard Rail at Rigging Grid Catwalk Per SDCI Code | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-08 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-22 | 2021-07-13 | 6 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13837 | Received | For Review | 2021-07-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-07-22 | Submittal Number: 05 50 00-90.0 From: TYRONE THORNTON Final Due Date: 07/21/21 Subject: ADDED GUARD RAIL AT RIGGING GRID CATWALK PER SDCI CODE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 17912 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-15 | Submittal Number: 05 50 00-90.0 From: TYRONE THORNTON Final Due Date: 07/21/21 Subject: ADDED GUARD RAIL AT RIGGING GRID CATWALK PER SDCI CODE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 13904 | Review Response | Approved | 2021-07-12 | Matt Ross (Thornton Tomasetti) | Tom Usher (Populous); Chris Minter (Populous); Shaina Burris (Populous) |  | Arch to review. | Info Exchange
| 18006 | Responded and Closed | Approved | 2021-07-13 | Shaina Burris (Populous) | Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-07 |  | Rigging Grid Stair Rail Fixes Shop Drawings_MAM Comments.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-07 |  | Rigging Grid Stair Rail Fixes Shop Drawings_MAM Comments.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-07-07 |  | Rigging Grid Stair Rail Fixes Shop Drawings_MAM Comments.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-07-13 |  | 05 50 00-090-00 Rigging Grid Stair Rail Fixes Shop Drawings_MAM Comments_TT_POP.pdf
05 50 00-091-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-091-00 Removable Cable Rail at North & South Camera Platforms | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-23 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-09-06 | 2021-09-01 | 10 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14436 | Received | For Review | 2021-08-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-09-06 | Submittal Number: 05 50 00-91.0 From: TYRONE THORNTON Final Due Date: 09/06/21 Subject: 05 50 00 - REMOVABLE CABLE RAIL AT NORTH & SOUTH CAMERA PLATFORMS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 18631 | Forwarded | For Review | 2021-08-23 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-08-30 | Submittal Number: 05 50 00-91.0 From: TYRONE THORNTON Final Due Date: 09/06/21 Subject: 05 50 00 - REMOVABLE CABLE RAIL AT NORTH & SOUTH CAMERA PLATFORMS Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14544 | Review Response | Approved as Noted | 2021-08-30 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Arch to review. | Info Exchange
| 18752 | Responded and Closed | Approved as Noted | 2021-09-01 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-23 |  | CCD 115 Spotlight Platform Cable Rails Shop Drawings_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-23 |  | CCD 115 Spotlight Platform Cable Rails Shop Drawings_MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-08-23 |  | CCD 115 Spotlight Platform Cable Rails Shop Drawings_MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-08-30 |  | CCD 115 Spotlight Platform Cable Rails Shop Drawings_MAM_TT.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-09-01 |  | CCD 115 Spotlight Platform Cable Rails Shop Drawings_MAM_TT-POP.pdf
05 50 00-092-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-092-00 Spanner Deck Support Steel | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-30 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Matthew Farber (Thornton Tomasetti), Tom Usher (Populous), Chris Minter (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-09-13 | 2021-09-01 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14518 | Received | For Review | 2021-08-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-09-13 | Submittal Number: 05 50 00-92.0 From: TYRONE THORNTON Final Due Date: 09/13/21 Subject: 05 50 00 - SPANNER DECK SUPPORT STEEL Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 18721 | Forwarded | For Review | 2021-08-30 | Josh Dobken (Populous) | Todd Spangler (Populous); Matthew Farber (Thornton Tomasetti); Tom Usher (Populous); Chris Minter (Populous); Matt Ross (Thornton Tomasetti) | 2021-09-06 | Submittal Number: 05 50 00-92.0 From: TYRONE THORNTON Final Due Date: 09/13/21 Subject: 05 50 00 - SPANNER DECK SUPPORT STEEL Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14545 | Review Response | Approved | 2021-08-31 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Arch to review. | Info Exchange
| 18754 | Responded and Closed | Approved as Noted | 2021-09-01 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-29 02:00 |  | CPA Spanner Deck Plan Drawings_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-08-29 02:00 |  | 05 50 00-092-00 CPA Spanner Deck Plan Drawings_MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-08-29 |  | 05 50 00-092-00 CPA Spanner Deck Plan Drawings_MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-08-31 |  | 05 50 00-092-00 CPA Spanner Deck Plan Drawings_MAM_TT.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-09-01 |  | 05 50 00-092-00 CPA Spanner Deck Plan Drawings_MAM_TT-POP.pdf
05 50 00-093-00 | 05 50 00 - METAL FABRICATIONS | 05 50 00-093-00 North & South Catwalk Ladder Cage | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-10 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-09-24 | 2021-09-13 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-09-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14619 | Received | For Review | 2021-09-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-09-24 | Submittal Number: 05 50 00-93.0 From: TYRONE THORNTON Final Due Date: 09/24/21 Subject: 05 50 00 - NORTH & SOUTH CATWALK LADDER CAGE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 18859 | Forwarded | For Review | 2021-09-10 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-09-17 | Submittal Number: 05 50 00-93.0 From: TYRONE THORNTON Final Due Date: 09/24/21 Subject: 05 50 00 - NORTH & SOUTH CATWALK LADDER CAGE Description: Spec Section: 05 50 00 - METAL FABRICATIONS Status: OPEN | Info Exchange
| 14638 | Review Response | Approved as Noted | 2021-09-13 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Shop Drawings not included in submittal. Please submit shop drawings for record. Arch to review. | Info Exchange
| 14637 | Review Response | Approved as Noted | 2021-09-13 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Pending response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Shop Drawings not included in submittal. Please submit shop drawings for record. Arch to review. | Info Exchange
| 18877 | Responded and Closed | Approved as Noted | 2021-09-13 | Shaina Burris (Populous) | Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-10 |  | CPA - Catwalk Ladder Cage Plan Drawings SSF Stamped 9.9.21_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-10 |  | CPA - Catwalk Ladder Cage Plan Drawings SSF Stamped 9.9.21_MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-09-10 |  | CPA - Catwalk Ladder Cage Plan Drawings SSF Stamped 9.9.21_MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-09-13 |  | CPA - Catwalk Ladder Cage Plan Drawings SSF Stamped 9.9.21_MAM_TT_POP.pdf
05 51 13-005-00 | 05 51 13 - METAL PAN STAIRS | 05 51 13-005-00 Stairs in Quad E/F | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-27 | 22 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04236 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2020-02-20 | Submittal Number: 05 51 13-5.0 From: JES PELKEY Final Due Date: 02/19/20 Subject: STAIRS IN QUAD E/F Description: SHOP DRAWINGS : INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 05865 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-02-13 | Submittal Number: 05 51 13-5.0 From: JES PELKEY Final Due Date: 02/19/20 Subject: STAIRS IN QUAD E/F Description: SHOP DRAWINGS : INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 05983 | Forwarded | For Review | 2020-02-11 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-02-18 | Submittal Number: 05 51 13-5.0 From: JES PELKEY Final Due Date: 02/19/20 Subject: STAIRS IN QUAD E/F Description: SHOP DRAWINGS : INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 04461 | Review Response | Approved as Noted/Resubmit | 2020-02-23 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 06265 | Responded and Closed | Revise and Resubmit | 2020-02-27 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached fro review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 05 51 13-5.0 Stairs Quad E &F-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | 05 51 13-5.0 Stairs Quad E &F-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-05 02:00 |  | 05 51 13-5.0 Stairs Quad E &F-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-02-05 |  | 05 51 13-5.0 Stairs Quad E &F-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-27 |  | 05 51 13-5.0 Stairs Quad E &F-MAM_TT_POP.pdf
05 51 13-005-01 | 05 51 13 - METAL PAN STAIRS | 05 51 13-005-01 Stairs in Quad E/F - Stair E1 and F1 Only | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-02 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-17 | 2020-04-13 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05187 | Received | For Review | 2020-04-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Brad Kirschenheiter (LeJeune Steel) | 2020-04-17 | Submittal Number: 05 51 13-5.1 From: JES PELKEY Final Due Date: 04/14/20 Subject: STAIRS IN QUAD E/F - STAIR E1 AND F1 ONLY Description: SHOP DRAWINGS : INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 07050 | Forwarded | For Review | 2020-04-02 | Brad Kirschenheiter (LeJeune Steel) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-09 | Submittal Number: 05 51 13-5.1 From: JES PELKEY Final Due Date: 04/14/20 Subject: STAIRS IN QUAD E/F - STAIR E1 AND F1 ONLY Description: SHOP DRAWINGS : INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 07242 | Responded and Closed | Approved as Noted | 2020-04-13 | Brad Kirschenheiter (LeJeune Steel) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-02 |  | 05 51 13-5.1 Stairs in Quad E & F RR-MAM.pdf
| Forwarded |  | Brad Kirschenheiter (LeJeune Steel) | 1 | 2020-04-02 |  | 05 51 13-5.1 Stairs in Quad E & F RR-MAM.pdf
| Responded and Closed |  | Brad Kirschenheiter (LeJeune Steel) | 1 | 2020-04-13 |  | 05 51 13-5.1 Stairs in Quad E & F RR-MAM_TT_POP.pdf
05 51 13-010-00 | 05 51 13 - METAL PAN STAIRS | 05 51 13-010-00 Stair SD-1 Shop Drawings and Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-15 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2019-10-29 | 2019-10-30 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-10-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02770 | Received | For Review | 2019-10-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-10-29 | Submittal Number: 05 51 13-10.0 From: BRAD KIRSCHENHEITER Final Due Date: 10/30/19 Subject: STAIR SD-1 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 04112 | Forwarded | For Review | 2019-10-15 | Populous SCA_CCA | Todd Spangler (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-10-22 | Submittal Number: 05 51 13-10.0 From: BRAD KIRSCHENHEITER Final Due Date: 10/30/19 Subject: STAIR SD-1 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 04117 | Forwarded | For Review | 2019-10-15 | Populous SCA_CCA | Matt Ross (Thornton Tomasetti) |  | Submittal Number: 05 51 13-10.0 From: BRAD KIRSCHENHEITER Final Due Date: 10/30/19 Subject: STAIR SD-1 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 02962 | Review Response | Revise and Resubmit | 2019-10-29 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Provide missing connection calcs. Connection concepts to revise or contractor to provide supplementary steel to eliminate torsion in base structure members per general notes. | Info Exchange
| 04354 | Responded and Closed | Revise and Resubmit | 2019-10-30 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-14 |  | 05 51 13-10.0 Stair SD-1-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-14 |  | 05 51 13-10.0 Stair SD-1-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-10-14 |  | 05 51 13-10.0 Stair SD-1-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-14 |  | 05 51 13-10.0 Stair SD-1-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-10-30 |  | 05 51 13-10.0 Stair SD-1-MAM_TT_POP.pdf
05 51 13-010-01 | 05 51 13 - METAL PAN STAIRS | 05 51 13-010-01 Stair SD-1 and SD-4 Shop Drawings and Calculations | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-02 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-12-16 | 2019-12-23 | 22 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2019-12-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03424 | Received | For Review | 2019-12-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-16 | Submittal Number: 05 51 13-10.1 From: BRAD KIRSCHENHEITER Final Due Date: 12/16/19 Subject: STAIR SD-1 AND SD-4 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 04895 | Forwarded | For Review | 2019-12-02 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-09 | Submittal Number: 05 51 13-10.1 From: BRAD KIRSCHENHEITER Final Due Date: 12/16/19 Subject: STAIR SD-1 AND SD-4 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 05214 | Forwarded | For Review | 2019-12-18 | Populous SCA_CCA | Todd Spangler (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-12-16 | Submittal Number: 05 51 13-10.1 From: BRAD KIRSCHENHEITER Final Due Date: 12/16/19 Subject: STAIR SD-1 AND SD-4 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 03728 | Review Response | Revise and Resubmit | 2019-12-20 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 05262 | Responded and Closed | Revise and Resubmit | 2019-12-23 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-02 |  | 05 51 13-10.1 Stair SD-1 and SD-4-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-02 |  | 05 51 13-10.1 Stair SD-1 and SD-4-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-01 02:00 |  | 05 51 13-10.1 Stair SD-1 and SD-4-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-02 |  | 05 51 13-10.1 Stair SD-1 and SD-4-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-23 |  | 05 51 13-10.1 Stair SD-1 and SD-4-MAM_TT_POP.pdf
05 51 13-010-02 | 05 51 13 - METAL PAN STAIRS | 05 51 13-010-02 Stair SD-1 and SD-4 Shop Drawings and Calculations | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Closed - Void |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 |  | 9 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-02-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04226 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-20 | Submittal Number: 05 51 13-10.2 From: BRAD KIRSCHENHEITER Final Due Date: 02/18/20 Subject: STAIR SD-1 AND SD-4 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 05855 | Forwarded | For Review | 2020-02-06 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-02-13 | Submittal Number: 05 51 13-10.2 From: BRAD KIRSCHENHEITER Final Due Date: 02/18/20 Subject: STAIR SD-1 AND SD-4 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 05966 | Forwarded | For Review | 2020-02-11 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-02-18 | Submittal Number: 05 51 13-10.2 From: BRAD KIRSCHENHEITER Final Due Date: 02/18/20 Subject: STAIR SD-1 AND SD-4 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 04345 | Review Response | Approved as Noted | 2020-02-12 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 06013 | Responded and Closed | Approved as Noted | 2020-02-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| 06014 | Reopened | Additional Information | 2020-02-14 04:31 | Todd Spangler (Populous)
| 06015 | Closed | Void | 2020-02-14 | Todd Spangler (Populous)
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 05 51 13-10.2 Stair SD-1 and SD-4-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-06 |  | 05 51 13-10.2 Stair SD-1 and SD-4-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-05 02:00 |  | 05 51 13-10.2 Stair SD-1 and SD-4-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-05 |  | 05 51 13-10.2 Stair SD-1 and SD-4-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-13 |  | 05 51 13-10.2 Stair SD-1 and SD-4-MAM_TT_POP.pdf
05 51 13-011-00 | 05 51 13 - METAL PAN STAIRS | 05 51 13-011-00 Stairs in Quad A Shop Drawings and Calcs | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-11 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-25 | 2020-04-02 | 23 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-04-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04759 | Received | For Review | 2020-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-03-25 | Submittal Number: 05 51 13-11.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/08/20 Subject: STAIRS IN QUAD A SHOP DRAWINGS AND CALCS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 06529 | Forwarded | For Review | 2020-03-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-18 | Submittal Number: 05 51 13-11.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/08/20 Subject: STAIRS IN QUAD A SHOP DRAWINGS AND CALCS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 05068 | Review Response | Approved as Noted/Resubmit | 2020-03-26 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please resubmit with stair from Upper Concourse to Space Needle Club shop drawings and calcs. | Info Exchange
| 07057 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-02 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 05 51 13-11.0 Stairs in Quad A-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-11 |  | 05 51 13-11.0 Stairs in Quad A-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-11 |  | 05 51 13-11.0 Stairs in Quad A-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-02 |  | 05 51 13-11.0 Stairs in Quad A-MAM_TT_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-02 |  | A1-42 - SLAB PLAN - MECHANICAL MEZZANINE LEVEL.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-02 |  | A1-43 - SLAB PLAN - MAIN CONCOURSE LEVEL.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-02 |  | A1-44 - SLAB PLAN - SUITE LEVEL.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-02 |  | A1-45.5 - SLAB PLAN - SPACE NEEDLE CLUB LEVEL.pdf
05 51 13-011-01 | 05 51 13 - METAL PAN STAIRS | 05 51 13-011-01 Stairs in Quad A Shop Drawings and Calcs - SA-4 Only | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-27 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-11 | 2020-05-11 | 15 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-05-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05557 | Received | For Review | 2020-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-05-11 | Submittal Number: 05 51 13-11.1 From: BRAD KIRSCHENHEITER Final Due Date: 05/11/20 Subject: STAIRS IN QUAD A SHOP DRAWINGS AND CALCS - SA-4 ONLY Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 07533 | Forwarded | For Review | 2020-04-27 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-04 | Submittal Number: 05 51 13-11.1 From: BRAD KIRSCHENHEITER Final Due Date: 05/11/20 Subject: STAIRS IN QUAD A SHOP DRAWINGS AND CALCS - SA-4 ONLY Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 05774 | Review Response | Approved as Noted | 2020-04-29 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | No clouds or other indication of revisions found in submittal so TT has only reviewed parts of submittal related to comments from previous review assuming all other parts have remained unchanged. | Info Exchange
| 07831 | Responded and Closed | Revise and Resubmit | 2020-05-11 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Per conversations during the steel coordination meeting we are returning this revise and resubmit. The mid landing to be support by the W24x104 and at the elevation provided in the arch drawings to maintain head clearance below the bowl duct. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-26 |  | 05 51 13-11.1 Stairs in Quad A SD SA-4 RR-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-26 |  | 05 51 13-11.1 Stairs in Quad A SD SA-4 RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-26 |  | 05 51 13-11.1 Stairs in Quad A SD SA-4 RR-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-11 |  | 05 51 13-11.1 Stairs in Quad A SD SA-4 RR-MAM_TT_POP.pdf
05 51 13-011-02 | 05 51 13 - METAL PAN STAIRS | 05 51 13-011-02 Stairs in Quad A Shop Drawings and Calcs - SA-4 Only | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-20 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-04 07:00 | 2020-06-09 | 21 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05931 | Received | For Review | 2020-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-04 07:00 | Submittal Number: 05 51 13-11.2 From: BRAD KIRSCHENHEITER Final Due Date: 06/02/20 Subject: STAIRS IN QUAD A SHOP DRAWINGS AND CALCS - SA-4 ONLY Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 08050 | Forwarded | For Review | 2020-05-19 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-26 | Submittal Number: 05 51 13-11.2 From: BRAD KIRSCHENHEITER Final Due Date: 06/02/20 Subject: STAIRS IN QUAD A SHOP DRAWINGS AND CALCS - SA-4 ONLY Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 08086 | Forwarded | For Review | 2020-05-20 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-05-27 | Submittal Number: 05 51 13-11.2 From: BRAD KIRSCHENHEITER Final Due Date: 06/02/20 Subject: STAIRS IN QUAD A SHOP DRAWINGS AND CALCS - SA-4 ONLY Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 06293 | Review Response | Approved as Noted/Resubmit | 2020-06-02 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Please provide calcs for connection of stringers to W24 for record. | Info Exchange
| 08522 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-09 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please provide calcs for connection of stringers to W24 for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 |  | 05 51 13-11.2 Quad A Stairs S-A4 RR-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-19 |  | 05 51 13-11.2 Quad A Stairs S-A4 RR-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-18 02:00 |  | 05 51 13-11.2 Quad A Stairs S-A4 RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-18 |  | 05 51 13-11.2 Quad A Stairs S-A4 RR-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-09 |  | 05 51 13-11.2 Quad A Stairs S-A4 RR-MAM_TT_POP.pdf
05 51 13-011-03 | 05 51 13 - METAL PAN STAIRS | 05 51 13-011-03 Stairs in Quad A Shop Drawings and Calcs - SA-4 Calcs For Record | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-06 | 2020-07-31 | 9 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07106 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-06 | Submittal Number: 05 51 13-11.3 From: BRAD KIRSCHENHEITER Final Due Date: 08/04/20 Subject: STAIRS IN QUAD A SHOP DRAWINGS AND CALCS - SA-4 CALCS FOR RECORD Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 09494 | Forwarded | For Review | 2020-07-23 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-30 | Submittal Number: 05 51 13-11.3 From: BRAD KIRSCHENHEITER Final Due Date: 08/04/20 Subject: STAIRS IN QUAD A SHOP DRAWINGS AND CALCS - SA-4 CALCS FOR RECORD Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 07281 | Review Response | Revise and Resubmit | 2020-07-24 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Please submit calcs for connection asked for in previous review. Also note that connection D/8 is to be designed for a horizontal shear as noted in RISA calcs. | Info Exchange
| 09701 | Responded and Closed | Revise and Resubmit | 2020-07-31 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please submit calcs for connection asked for in previous review. Also note that connection D/8 is to be designed for a horizontal shear as noted in RISA calcs. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 05 51 13-11.3 Quad A Stair S-A4 SD and Calcs-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-23 |  | 05 51 13-11.3 Quad A Stair S-A4 SD and Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-23 |  | 05 51 13-11.3 Quad A Stair S-A4 SD and Calcs-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-31 |  | 05 51 13-11.3 Quad A Stair S-A4 SD and Calcs-MAM_TT_POP.pdf
05 51 13-011-04 | 05 51 13 - METAL PAN STAIRS | 05 51 13-011-04 Quad A Stairs - SA-4 Calcs For Record | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-16 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-09-30 | 2020-09-22 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-09-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08134 | Received | For Review | 2020-09-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company) | 2020-09-30 | Submittal Number: 05 51 13-11.4 From: JES PELKEY Final Due Date: 09/29/20 Subject: QUAD A STAIRS - SA-4 CALCS FOR RECORD Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 10806 | Forwarded | For Review | 2020-09-15 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-22 | Submittal Number: 05 51 13-11.4 From: JES PELKEY Final Due Date: 09/29/20 Subject: QUAD A STAIRS - SA-4 CALCS FOR RECORD Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 10920 | Forwarded | For Review | 2020-09-21 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2020-09-28 | Submittal Number: 05 51 13-11.4 From: JES PELKEY Final Due Date: 09/29/20 Subject: QUAD A STAIRS - SA-4 CALCS FOR RECORD Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 08248 | Review Response | Approved | 2020-09-21 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 10954 | Responded and Closed | Approved | 2020-09-22 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-15 |  | 05 51 13-11.4 Quad A Stair S-A4 Calcs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-15 |  | 05 51 13-11.4 Quad A Stair S-A4 Calcs-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-14 02:00 |  | 05 51 13-11.4 Quad A Stair S-A4 Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-14 |  | 05 51 13-11.4 Quad A Stair S-A4 Calcs-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-22 |  | 05 51 13-11.4 Quad A Stair S-A4 Calcs-MAM_TT_POP.pdf
05 51 13-012-00 | 05 51 13 - METAL PAN STAIRS | 05 51 13-012-00 Stairs SC-1 & SC-4 Shop Drawings and Calculations | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-03 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Chris Minter (Populous), Josh Dobken (Populous), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-17 | 2020-01-07 | 36 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-01-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03440 | Received | For Review | 2019-12-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-17 | Submittal Number: 05 51 13-12.0 From: BRAD KIRSCHENHEITER Final Due Date: 12/17/19 Subject: STAIRS SC-1 & SC-4 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 04912 | Forwarded | For Review | 2019-12-03 | Populous SCA_CCA | Todd Spangler (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-12-10 | Submittal Number: 05 51 13-12.0 From: BRAD KIRSCHENHEITER Final Due Date: 12/17/19 Subject: STAIRS SC-1 & SC-4 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 05107 | Forwarded | For Review | 2019-12-12 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth K... | 2019-12-17 | Submittal Number: 05 51 13-12.0 From: BRAD KIRSCHENHEITER Final Due Date: 12/17/19 Subject: STAIRS SC-1 & SC-4 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 03817 | Review Response | Revise and Resubmit | 2019-12-20 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 05364 | Responded and Closed | Revise and Resubmit | 2020-01-07 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-02 |  | 05 51 13-12.0 Stair SC-1 & SC-4 SD and Calcs-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-02 |  | 05 51 13-12.0 Stair SC-1 & SC-4 SD and Calcs-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-01 02:00 |  | 05 51 13-12.0 Stair SC-1 & SC-4 SD and Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-01 |  | 05 51 13-12.0 Stair SC-1 & SC-4 SD and Calcs-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-01-07 |  | 05 51 13-12.0 Stair SC-1 & SC-4 SD and Calcs-MAM_TT_POP.pdf
05 51 13-012-01 | 05 51 13 - METAL PAN STAIRS | 05 51 13-012-01 Stairs SC-1 & SC-4 Shop Drawings and Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-20 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-05 | 2020-03-10 | 20 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04421 | Received | For Review | 2020-02-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company); Brad Kirschenheiter (LeJeune Steel) | 2020-03-05 | Submittal Number: 05 51 13-12.1 From: BRAD KIRSCHENHEITER Final Due Date: 03/05/20 Subject: STAIRS SC-1 & SC-4 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 06105 | Forwarded | For Review | 2020-02-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-27 | Submittal Number: 05 51 13-12.1 From: BRAD KIRSCHENHEITER Final Due Date: 03/05/20 Subject: STAIRS SC-1 & SC-4 SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 04621 | Review Response | Approved as Noted | 2020-02-27 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06517 | Responded and Closed | Approved as Noted | 2020-03-10 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-20 |  | 05 51 13-12.1 Stair SC-1 & SC-4 SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-20 |  | 05 51 13-12.1 Stair SC-1 & SC-4 SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-20 |  | 05 51 13-12.1 Stair SC-1 & SC-4 SD-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-10 |  | 05 51 13-12.1 Stair SC-1 & SC-4 SD-MAM_TT_POP.pdf
05 51 13-013-00 | 05 51 13 - METAL PAN STAIRS | 05 51 13-013-00 Stairs in Quad B Shop Drawings and Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-09 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-23 | 2020-05-12 | 34 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05271 | Received | For Review | 2020-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-04-23 | Submittal Number: 05 51 13-13.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/22/20 Subject: STAIRS IN QUAD B SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 07164 | Forwarded | For Review | 2020-04-09 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-16 | Submittal Number: 05 51 13-13.0 From: BRAD KIRSCHENHEITER Final Due Date: 04/22/20 Subject: STAIRS IN QUAD B SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 05759 | Review Response | Approved as Noted | 2020-04-21 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Note to Populous: some stairs are noted to not meet 1/4" deflection criteria. Please review and advise. Revise per comments and resubmit for record. | Info Exchange
| 07906 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-12 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Resubmit SB4. SB5 approved as design. See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-08 |  | 05 51 13-13.0 Quad B Stair SD and Calcs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-08 |  | 05 51 13-13.0 Quad B Stair SD and Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-08 |  | 05 51 13-13.0 Quad B Stair SD and Calcs-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-12 |  | 05 51 13-13.0 Quad B Stair SD and Calcs-MAM_TT_POP.pdf
05 51 13-013-01 | 05 51 13 - METAL PAN STAIRS | 05 51 13-013-01 Stairs in Quad B Shop Drawings and Calculations - S-B4 | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-20 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2020-06-04 07:00 | 2020-06-09 | 21 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05943 | Received | For Review | 2020-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-04 07:00 | Submittal Number: 05 51 13-13.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/02/20 Subject: STAIRS IN QUAD B SHOP DRAWINGS AND CALCULATIONS - S-B4 Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 08072 | Forwarded | For Review | 2020-05-20 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-27 | Submittal Number: 05 51 13-13.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/02/20 Subject: STAIRS IN QUAD B SHOP DRAWINGS AND CALCULATIONS - S-B4 Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 08085 | Forwarded | For Review | 2020-05-20 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2020-05-27 | Submittal Number: 05 51 13-13.1 From: BRAD KIRSCHENHEITER Final Due Date: 06/02/20 Subject: STAIRS IN QUAD B SHOP DRAWINGS AND CALCULATIONS - S-B4 Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 06317 | Review Response | Revise and Resubmit | 2020-06-02 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Please address comments from previous submittals. Provide calcs for connection of S-B4 stringers to W24 beam. | Info Exchange
| 08521 | Responded and Closed | Revise and Resubmit | 2020-06-09 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please address comments from previous submittals. Provide calcs for connection of S-B4 stringers to W24 beam. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 |  | 05 51 13-13.1 Quad B Stair S-B4 SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-19 |  | 05 51 13-13.1 Quad B Stair S-B4 SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-18 02:00 |  | 05 51 13-13.1 Quad B Stair S-B4 SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-19 |  | 05 51 13-13.1 Quad B Stair S-B4 SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-09 |  | 05 51 13-13.1 Quad B Stair S-B4 SD-MAM_TT_POP.pdf
05 51 13-013-02 | 05 51 13 - METAL PAN STAIRS | 05 51 13-013-02 Stairs in Quad B Shop Drawings and Calculations - S-B4 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-21 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-04 | 2020-08-04 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07056 | Received | For Review | 2020-07-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brad Kirschenheiter (LeJeune Steel) | 2020-08-04 | Submittal Number: 05 51 13-13.2 From: BRAD KIRSCHENHEITER Final Due Date: 08/04/20 Subject: STAIRS IN QUAD B SHOP DRAWINGS AND CALCULATIONS - S-B4 Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 09445 | Forwarded | For Review | 2020-07-21 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-28 | Submittal Number: 05 51 13-13.2 From: BRAD KIRSCHENHEITER Final Due Date: 08/04/20 Subject: STAIRS IN QUAD B SHOP DRAWINGS AND CALCULATIONS - S-B4 Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 09566 | Forwarded | For Review | 2020-07-27 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean... | 2020-08-03 | Submittal Number: 05 51 13-13.2 From: BRAD KIRSCHENHEITER Final Due Date: 08/04/20 Subject: STAIRS IN QUAD B SHOP DRAWINGS AND CALCULATIONS - S-B4 Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 07336 | Review Response | Revise and Resubmit | 2020-08-03 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Resubmit with calcs requested and previous comments addressed. Stair designer to provide reasoning if they do not agree with comment on pdf page 54. | Info Exchange
| 09785 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-04 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW. Resubmit with calcs requested and previous comments addressed. Stair designer to provide reasoning if they do not agree with comment on pdf page 54. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-21 |  | 05 51 13-13.2 Quad B Stair S-B4 SD and Calcs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-21 |  | 05 51 13-13.2 Quad B Stair S-B4 SD and Calcs-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-07-20 02:00 |  | 05 51 13-13.2 Quad B Stair S-B4 SD and Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-20 |  | 05 51 13-13.2 Quad B Stair S-B4 SD and Calcs-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-09 |  | 05 51 13-13.1 Quad B Stair S-B4 SD-MAM_TT_POP.pdf
05 51 13-013-03 | 05 51 13 - METAL PAN STAIRS | 05 51 13-013-03 Stairs in Quad B Calculations - S-B4 | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-15 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-09-29 | 2020-09-22 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-09-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08126 | Received | For Review | 2020-09-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-29 | Submittal Number: 05 51 13-13.3 From: BRAD KIRSCHENHEITER Final Due Date: 09/29/20 Subject: STAIRS IN QUAD B CALCULATIONS - S-B4 Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 10793 | Forwarded | For Review | 2020-09-15 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-22 | Submittal Number: 05 51 13-13.3 From: BRAD KIRSCHENHEITER Final Due Date: 09/29/20 Subject: STAIRS IN QUAD B CALCULATIONS - S-B4 Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 10921 | Forwarded | For Review | 2020-09-21 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2020-09-28 | Submittal Number: 05 51 13-13.3 From: BRAD KIRSCHENHEITER Final Due Date: 09/29/20 Subject: STAIRS IN QUAD B CALCULATIONS - S-B4 Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 08247 | Review Response | Approved | 2020-09-21 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 10953 | Responded and Closed | Approved | 2020-09-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-15 |  | 05 51 13-13.3 Quad B Stair S-B4 Calcs-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-15 |  | 05 51 13-13.3 Quad B Stair S-B4 Calcs-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-14 02:00 |  | 05 51 13-13.3 Quad B Stair S-B4 Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-14 |  | 05 51 13-13.3 Quad B Stair S-B4 Calcs-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-22 |  | 05 51 13-13.3 Quad B Stair S-B4 Calcs-MAM_TT_POP.pdf
05 51 13-013-04 | 05 51 13 - METAL PAN STAIRS | 05 51 13-013-04 Quad B Stair Gate Revision Shop Drawings - For Record Only | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-06 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-08-20 | 2021-08-09 | 4 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14257 | Received | For Review | 2021-08-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-08-20 | Submittal Number: 05 51 13-13.4 From: SKYLER MITCHELL Final Due Date: 08/20/21 Subject: QUAD B STAIR GATE REVISION SHOP DRAWINGS - FOR RECORD ONLY Description: SHOP DRAWINGS FOR THE GATE FIXES AT THE QUAD B STAIRS. SUBMITTED FOR RECORD ONLY. Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 18419 | Forwarded | For Review | 2021-08-09 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-08-16 | Submittal Number: 05 51 13-13.4 From: SKYLER MITCHELL Final Due Date: 08/20/21 Subject: QUAD B STAIR GATE REVISION SHOP DRAWINGS - FOR RECORD ONLY Description: SHOP DRAWINGS FOR THE GATE FIXES AT THE QUAD B STAIRS. SUBMITTED FOR RECORD ONLY. Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 14271 | Review Response | No Action Taken or Required | 2021-08-09 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | RECEIVED FOR RECORD ONLY. | Info Exchange
| 18432 | Responded and Closed | No Action Taken or Required | 2021-08-09 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: RECEIVED FOR RECORD ONLY. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-06 |  | 05 51 13-13.4 - Quad B Stair Gate Revision Shop Drawings - For Record Only.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-06 |  | 05 51 13-13.4 - Quad B Stair Gate Revision Shop Drawings - For Record Only.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-08-05 02:00 |  | 05 51 13-13.4 - Quad B Stair Gate Revision Shop Drawings - For Record Only.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-05 02:00 |  | 05 51 13-13.4 - Quad B Stair Gate Revision Shop Drawings - For Record Only.pdf
05 51 13-014-00 | 05 51 13 - METAL PAN STAIRS | 05 51 13-014-00 Metal Pan Stair Shop Drawings and Calculations - For Record | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-09 | Responded and Closed - No Action Taken or Required |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-08-23 | 2021-08-09 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14258 | Received | For Review | 2021-08-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2021-08-23 | Submittal Number: 05 51 13-14.0 From: BRAD KIRSCHENHEITER Final Due Date: 08/23/21 Subject: METAL PAN STAIR SHOP DRAWINGS AND CALCULATIONS - FOR RECORD Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 18420 | Forwarded | For Review | 2021-08-09 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-08-16 | Submittal Number: 05 51 13-14.0 From: BRAD KIRSCHENHEITER Final Due Date: 08/23/21 Subject: METAL PAN STAIR SHOP DRAWINGS AND CALCULATIONS - FOR RECORD Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 14272 | Review Response | No Action Taken or Required | 2021-08-09 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | RECEIVED FOR RECORD ONLY. | Info Exchange
| 18434 | Responded and Closed | No Action Taken or Required | 2021-08-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: RECEIVED FOR RECORD ONLY. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-09 |  | 05 51 13-14.0 Stair SD and Calcs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-09 |  | 05 51 13-14.0 Stair SD and Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-08-08 02:00 |  | 05 51 13-14.0 Stair SD and Calcs-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-08-08 02:00 |  | 05 51 13-14.0 Stair SD and Calcs-MAM.pdf
05 51 13-014-01 | 05 51 13 - METAL PAN STAIRS | 05 51 13-014-01 Metal Pan Stair Shop Drawings and Calculations - For Record | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-21 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-10-05 | 2021-09-23 | 3 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-09-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14674 | Received | For Review | 2021-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2021-10-05 | Submittal Number: 05 51 13-14.1 From: BRAD KIRSCHENHEITER Final Due Date: 09/17/21 Subject: METAL PAN STAIR SHOP DRAWINGS AND CALCULATIONS - FOR RECORD Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 18924 | Forwarded | For Review | 2021-09-21 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-09-28 | Submittal Number: 05 51 13-14.1 From: BRAD KIRSCHENHEITER Final Due Date: 09/17/21 Subject: METAL PAN STAIR SHOP DRAWINGS AND CALCULATIONS - FOR RECORD Description: Spec Section: 05 51 13 - METAL PAN STAIRS Status: OPEN | Info Exchange
| 14693 | Review Response | Approved | 2021-09-21 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 18947 | Responded and Closed | Approved | 2021-09-23 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-21 |  | 05 51 13-14.1 Metal Pan Stair SD FOR CITY-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-21 |  | 05 51 13-14.1 Metal Pan Stair SD FOR CITY-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-09-21 |  | 05 51 13-14.1 Metal Pan Stair SD FOR CITY-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-23 |  | 05 51 13-14.1 Metal Pan Stair SD FOR CITY-MAM_TT_POP.pdf
05 52 13-009-00 | 05 52 13 - PIPE AND TUBE RAILINGS | 05 52 13-009-00 Parking Garage Railing Shop Drawings | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-08-19 | 2020-08-31 | 27 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07364 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-19 | Submittal Number: 05 52 13-9.0 From: JES PELKEY Final Due Date: 08/19/20 Subject: PARKING GARAGE RAILING SHOP DRAWINGS Description: Spec Section: 05 52 13 - PIPE AND TUBE RAILINGS Status: OPEN | Info Exchange
| 09815 | Forwarded | For Review | 2020-08-05 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-12 | Submittal Number: 05 52 13-9.0 From: JES PELKEY Final Due Date: 08/19/20 Subject: PARKING GARAGE RAILING SHOP DRAWINGS Description: Spec Section: 05 52 13 - PIPE AND TUBE RAILINGS Status: OPEN | Info Exchange
| 10095 | Forwarded | For Review | 2020-08-17 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2020-08-19 | Submittal Number: 05 52 13-9.0 From: JES PELKEY Final Due Date: 08/19/20 Subject: PARKING GARAGE RAILING SHOP DRAWINGS Description: Spec Section: 05 52 13 - PIPE AND TUBE RAILINGS Status: OPEN | Email
| 07670 | Review Response | Approved | 2020-08-19 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 10460 | Responded and Closed | Approved as Noted | 2020-08-31 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-04 |  | 05 52 13-9.0 Parking Garage Railing SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-04 |  | 05 52 13-9.0 Parking Garage Railing SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-03 02:00 |  | 05 52 13-9.0 Parking Garage Railing SD-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-08-19 |  | 05 52 13-9.0 Parking Garage Railing SD-MAM_TT review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-31 |  | 05 52 13-9.0 Parking Garage Railing SD-MAM_TT_POP.pdf
05 52 13-010-00 | 05 52 13 - PIPE AND TUBE RAILINGS | 05 52 13-010-00 Parking Garage Railing Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-06 | Responded and Closed - Approved |  | Todd Spangler (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-20 | 2020-05-19 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05744 | Received | For Review | 2020-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-20 | Submittal Number: 05 52 13-10.0 From: BRAD KIRSCHENHEITER Final Due Date: 05/20/20 Subject: PARKING GARAGE RAILING PRODUCT DATA Description: Spec Section: 05 52 13 - PIPE AND TUBE RAILINGS Status: OPEN | Info Exchange
| 07795 | Forwarded | For Review | 2020-05-06 | Populous SCA_CCA | Todd Spangler (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-13 | Submittal Number: 05 52 13-10.0 From: BRAD KIRSCHENHEITER Final Due Date: 05/20/20 Subject: PARKING GARAGE RAILING PRODUCT DATA Description: Spec Section: 05 52 13 - PIPE AND TUBE RAILINGS Status: OPEN | Info Exchange
| 08046 | Responded and Closed | Approved | 2020-05-19 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-06 |  | 05 52 13-10.0 Parking Garage Railing PD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-06 |  | 05 52 13-10.0 Parking Garage Railing PD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-19 |  | 05 52 13-10.0 Parking Garage Railing PD-MAM _POP1.pdf
05 53 13-003-00 | 05 53 13 - BAR GRATINGS | 05 53 13-003-00 Bar Grating Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-29 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti) |  |  |  | 2020-05-13 | 2020-05-26 | 28 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05619 | Received | For Review | 2020-04-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-13 | Submittal Number: 05 53 13-3.0 From: JES PELKEY Final Due Date: 05/12/20 Subject: BAR GRATING SHOP DRAWINGS Description: SHOP DRAWINGS : INCLUDE PLANS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 53 13 - BAR GRATINGS Status: OPEN | Info Exchange
| 07615 | Forwarded | For Review | 2020-04-29 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-06 | Submittal Number: 05 53 13-3.0 From: JES PELKEY Final Due Date: 05/12/20 Subject: BAR GRATING SHOP DRAWINGS Description: SHOP DRAWINGS : INCLUDE PLANS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 53 13 - BAR GRATINGS Status: OPEN | Info Exchange
| 07914 | Forwarded | For Review | 2020-05-12 | Populous SCA_CCA | Matt Ross (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) |  | Submittal Number: 05 53 13-3.0 From: JES PELKEY Final Due Date: 05/12/20 Subject: BAR GRATING SHOP DRAWINGS Description: SHOP DRAWINGS : INCLUDE PLANS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 53 13 - BAR GRATINGS Status: OPEN | Info Exchange
| 06001 | Review Response | Revise and Resubmit | 2020-05-22 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Ticket Office and Elevator A6 platform changes to be provided with RFI 2509 response. | Info Exchange
| 08188 | Responded and Closed | Revise and Resubmit | 2020-05-26 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-28 |  | 05 53 13-3.0 Bar Grating SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-28 |  | 05 53 13-3.0 Bar Grating SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-28 |  | 05 53 13-3.0 Bar Grating SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-28 |  | 05 53 13-3.0 Bar Grating SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-26 |  | 05 53 13-3.0 Bar Grating SD-MAM_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-26 |  | RFI-2509 - A7-06-7 - ELEVATOR CORE PLANS & SECTIONS - FREIGHT & SERV-.pdf
05 53 13-003-01 | 05 53 13 - BAR GRATINGS | 05 53 13-003-01 Bar Grating Shop Drawings | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-29 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-12 | 2020-08-13 | 16 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-08-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07225 | Received | For Review | 2020-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-12 | Submittal Number: 05 53 13-3.1 From: JES PELKEY Final Due Date: 08/12/20 Subject: BAR GRATING SHOP DRAWINGS Description: SHOP DRAWINGS : INCLUDE PLANS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 53 13 - BAR GRATINGS Status: OPEN | Info Exchange
| 09640 | Forwarded | For Review | 2020-07-29 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-05 | Submittal Number: 05 53 13-3.1 From: JES PELKEY Final Due Date: 08/12/20 Subject: BAR GRATING SHOP DRAWINGS Description: SHOP DRAWINGS : INCLUDE PLANS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 53 13 - BAR GRATINGS Status: OPEN | Info Exchange
| 07402 | Review Response | Approved as Noted | 2020-08-04 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 10025 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-13 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHCED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-29 |  | 05 53 13-3.1 Bar Grating SD RR-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-29 |  | 05 53 13-3.1 Bar Grating SD RR-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-29 |  | 05 53 13-3.1 Bar Grating SD RR-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-12 |  | 05 53 13-3.1 Bar Grating SD RR-MAM_TT_POP.pdf
05 53 13-003-02 | 05 53 13 - BAR GRATINGS | 05 53 13-003-02 Bar Grating Shop Drawings - NW Snorkel Only | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-16 | 2020-11-09 | 8 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09154 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-11-16 | Submittal Number: 05 53 13-3.2 From: JES PELKEY Final Due Date: 11/16/20 Subject: BAR GRATING SHOP DRAWINGS - NW SNORKEL ONLY Description: SHOP DRAWINGS : INCLUDE PLANS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 53 13 - BAR GRATINGS Status: OPEN | Info Exchange
| 12078 | Forwarded | For Review | 2020-11-02 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-11-09 | Submittal Number: 05 53 13-3.2 From: JES PELKEY Final Due Date: 11/16/20 Subject: BAR GRATING SHOP DRAWINGS - NW SNORKEL ONLY Description: SHOP DRAWINGS : INCLUDE PLANS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 53 13 - BAR GRATINGS Status: OPEN | Info Exchange
| 09296 | Review Response | Approved | 2020-11-02 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Populous to coordinate. | Info Exchange
| 12269 | Responded and Closed | Approved as Noted | 2020-11-09 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | 05 53 13-3.2 Bar Grating SD NW Snorkel-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-02 |  | 05 53 13-3.2 Bar Grating SD NW Snorkel-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-02 |  | 05 53 13-3.2 Bar Grating SD NW Snorkel-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-09 |  | 05 53 13-3.2 Bar Grating SD NW Snorkel-MAM_TT_POP.pdf
05 53 13-003-03 | 05 53 13 - BAR GRATINGS | 05 53 13-003-03 Bar Grating Shop Drawings Revisions to A6 Space Needle Access Hatch | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-22 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-05 | 2021-03-26 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12122 | Received | For Review | 2021-03-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-04-05 | Submittal Number: 05 53 13-3.3 From: TYRONE THORNTON Final Due Date: 04/02/21 Subject: BAR GRATING SHOP DRAWINGS REVISIONS TO A6 SPACE NEEDLE ACCESS HATCH Description: SHOP DRAWINGS : INCLUDE PLANS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 53 13 - BAR GRATINGS Status: OPEN | Info Exchange
| 15690 | Forwarded | For Review | 2021-03-19 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-26 | Submittal Number: 05 53 13-3.3 From: TYRONE THORNTON Final Due Date: 04/02/21 Subject: BAR GRATING SHOP DRAWINGS REVISIONS TO A6 SPACE NEEDLE ACCESS HATCH Description: SHOP DRAWINGS : INCLUDE PLANS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. Spec Section: 05 53 13 - BAR GRATINGS Status: OPEN | Info Exchange
| 12245 | Review Response | Approved | 2021-03-23 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous); Shaina Burris (Populous) |  | TT has no exceptions. Arch to review. | Info Exchange
| 15839 | Responded and Closed | Approved | 2021-03-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-19 |  | 05 53 13 - A6 Top Landing Access Hatch.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-19 |  | 05 53 13 - A6 Top Landing Access Hatch.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-19 |  | 05 53 13 - A6 Top Landing Access Hatch.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-03-26 |  | 05 53 13 - A6 Top Landing Access Hatch_TT_POP.pdf
05 53 13-007-00 | 05 53 13 - BAR GRATINGS | 05 53 13-007-00 Cooling Tower Grating Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-22 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-07 07:00 | 2020-07-15 | 24 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2020-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06528 | Received | For Review | 2020-06-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-07 07:00 | Submittal Number: 05 53 13-7.0 From: BRAD KIRSCHENHEITER Final Due Date: 07/03/20 Subject: COOLING TOWER GRATING SHOP DRAWINGS Description: GRATING ADDED IN PROJECT RFI 2334. Spec Section: 05 53 13 - BAR GRATINGS Status: OPEN | Info Exchange
| 08786 | Forwarded | For Review | 2020-06-20 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-29 | Submittal Number: 05 53 13-7.0 From: BRAD KIRSCHENHEITER Final Due Date: 07/03/20 Subject: COOLING TOWER GRATING SHOP DRAWINGS Description: GRATING ADDED IN PROJECT RFI 2334. Spec Section: 05 53 13 - BAR GRATINGS Status: OPEN | Info Exchange
| 09360 | Responded and Closed | No Action Taken or Required | 2020-07-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Brad Kirschenheiter (LeJeune Steel) |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-19 |  | 05 53 13-7.0 Cooling Tower Grating SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-19 |  | 05 53 13-7.0 Cooling Tower Grating SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-15 |  | 05 53 13-7.0 Cooling Tower Grating SD-MAM _POP.pdf
05 70 00-009-00 | 05 70 00 - DECORATIVE METAL | 05 70 00-009-00 Metal Samples Package 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-14 | 2020-10-06 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08446 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-14 | Submittal Number: 05 70 00-9.0 From: MIKE SOLFELT Final Due Date: 10/12/20 Subject: METAL SAMPLES PACKAGE 1 Description: Spec Section: 05 70 00 - DECORATIVE METAL Status: OPEN | Info Exchange
| 11187 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-07 | Submittal Number: 05 70 00-9.0 From: MIKE SOLFELT Final Due Date: 10/12/20 Subject: METAL SAMPLES PACKAGE 1 Description: Spec Section: 05 70 00 - DECORATIVE METAL Status: OPEN | Info Exchange
| 08613 | Review Response | Approved as Noted | 2020-10-06 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. M25 not reviewed, awaiting RG approval. | Info Exchange
| 11383 | Responded and Closed | Approved as Noted | 2020-10-06 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. M25 not reviewed, awaiting RG approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 05 70 00 -009 Decorative Metal Sample Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 05 70 00 -009 Decorative Metal Sample Submittal.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-06 |  | 05 70 00 -009 Decorative Metal Sample Submittal_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-30 |  | 05 70 00 -009 Decorative Metal Sample Submittal.pdf
05 73 00-001-00 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-001-00 Railings Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-10 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-08 | 2021-01-12 | 34 |  | Record Copies; Transfers; Submittals |  | 34 |  | 2021-01-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10082 | Received | For Review | 2020-12-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-08 | Submittal Number: 05 73 00-1.0 From: JES PELKEY Final Due Date: 01/04/21 Subject: RAILINGS PRODUCT DATA Description: PRODUCT DATA : FOR THE FOLLOWING: 1. MANUFACTURER'S PRODUCT LINES OF RAILINGS ASSEMBLED FROM STANDARD COMPONENTS. 2. GROUT, ANCHORING CEMENT, AND PAINT PRODUCTS. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 13180 | Forwarded | For Review | 2020-12-10 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-17 | Submittal Number: 05 73 00-1.0 From: JES PELKEY Final Due Date: 01/04/21 Subject: RAILINGS PRODUCT DATA Description: PRODUCT DATA : FOR THE FOLLOWING: 1. MANUFACTURER'S PRODUCT LINES OF RAILINGS ASSEMBLED FROM STANDARD COMPONENTS. 2. GROUT, ANCHORING CEMENT, AND PAINT PRODUCTS. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 13880 | Responded and Closed | Approved as Noted | 2021-01-12 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to comments within submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-10 |  | 05 73 00-1.0 Railing Product Data-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-10 |  | 05 73 00-1.0 Railing Product Data-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-12 02:00 |  | 05 73 00-1.0 Railing Product Data-MAM_pop.pdf
05 73 00-002-00 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-002-00 Railing Shop Drawings - Site Rails | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-27 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-05-11 | 2020-05-21 | 25 |  | Record Copies; Transfers; Submittals | 05 73 00-002-00-01 - 05 73 00-002-00 Railing Shop Drawings - Site Rails | 25 |  | 2020-05-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05558 | Received | For Review | 2020-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-11 | Submittal Number: 05 73 00-2.0 From: JES PELKEY Final Due Date: 05/08/20 Subject: RAILING SHOP DRAWINGS - SITE RAILS Description: PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 07534 | Forwarded | For Review | 2020-04-27 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-04 | Submittal Number: 05 73 00-2.0 From: JES PELKEY Final Due Date: 05/08/20 Subject: RAILING SHOP DRAWINGS - SITE RAILS Description: PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 07538 | Forwarded | For Review | 2020-04-27 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-05-04 | Submittal Number: 05 73 00-2.0 From: JES PELKEY Final Due Date: 05/08/20 Subject: RAILING SHOP DRAWINGS - SITE RAILS Description: PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 08106 | Responded and Closed | Revise and Resubmit | 2020-05-21 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | 05 73 00-2.0 Site Railing SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-24 |  | 05 73 00-2.0 Site Railing SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-23 02:00 |  | 05 73 00-2.0 Site Railing SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-21 |  | A5-02-5 - EXTERIOR ELEVATIONS - SW MECH INTAKE & EXHAUST.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-21 |  | 05 73 00-2.0 Site Railing SD-MAM_SWIFT_POP.pdf
05 73 00-002-00-01 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-002-00 Railing Shop Drawings - Site Rails | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 73 00-002-00 - 05 73 00-002-00 Railing Shop Drawings - Site Rails | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-21 |  | A5-02-5 - EXTERIOR ELEVATIONS - SW MECH INTAKE & EXHAUST.pdf
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-21 |  | 05 73 00-2.0 Site Railing SD-MAM_SWIFT_POP.pdf
05 73 00-004-00 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-004-00 DECORATIVE METAL RAILINGS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-27 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-11 | 2020-05-19 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05559 | Received | For Review | 2020-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-11 | Submittal Number: 05 73 00-4.0 From: JES PELKEY Final Due Date: 05/04/20 Subject: DECORATIVE METAL RAILINGS - SHOP DRAWINGS Description: SHOP DRAWINGS : INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 1. FOR ILLUMINATED RAILINGS, INCLUDE WIRING DIAGRAMS AND ROUGHING-IN DETAILS. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 07535 | Forwarded | For Review | 2020-04-27 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-04 | Submittal Number: 05 73 00-4.0 From: JES PELKEY Final Due Date: 05/04/20 Subject: DECORATIVE METAL RAILINGS - SHOP DRAWINGS Description: SHOP DRAWINGS : INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 1. FOR ILLUMINATED RAILINGS, INCLUDE WIRING DIAGRAMS AND ROUGHING-IN DETAILS. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 08065 | Responded and Closed | Approved as Noted | 2020-05-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-25 |  | 05 73 00-4.0 Railing Shop Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-25 |  | 05 73 00-4.0 Railing Shop Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-25 |  | 05 73 00-4.0 Railing Shop Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-19 |  | 05 73 00-4.0 Railing Shop Drawings-MAM - POP - CLM.pdf
05 73 00-004-01 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-004-01 DECORATIVE METAL RAILINGS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-12 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-05-26 | 2021-05-20 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-05-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13061 | Received | For Review | 2021-05-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyler Kren (Mortenson Construction) | 2021-05-26 | Submittal Number: 05 73 00-4.1 From: TYLER KREN Final Due Date: 05/25/21 Subject: DECORATIVE METAL RAILINGS - SHOP DRAWINGS Description: SHOP DRAWINGS AND CALCULATIONS FOR CITY SUBMISSION. PLEASE STAMP EACH PAGE FOR CITY SUBMISSION. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 16897 | Forwarded | For Review | 2021-05-12 | Tyler Kren (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-19 | Submittal Number: 05 73 00-4.1 From: TYLER KREN Final Due Date: 05/25/21 Subject: DECORATIVE METAL RAILINGS - SHOP DRAWINGS Description: SHOP DRAWINGS AND CALCULATIONS FOR CITY SUBMISSION. PLEASE STAMP EACH PAGE FOR CITY SUBMISSION. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 16970 | Forwarded | For Review | 2021-05-17 | Tyler Kren (Mortenson Construction) | Matt Ross (Thornton Tomasetti) |  | Submittal Number: 05 73 00-4.1 From: TYLER KREN Final Due Date: 05/25/21 Subject: DECORATIVE METAL RAILINGS - SHOP DRAWINGS Description: SHOP DRAWINGS AND CALCULATIONS FOR CITY SUBMISSION. PLEASE STAMP EACH PAGE FOR CITY SUBMISSION. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 17105 | Responded and Closed | Approved | 2021-05-20 | Tyler Kren (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | 0573004.1 Railings SD CALCS city submission.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | Seattle Center Arena - 48549 calcs_r0_STAMPED.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-11 |  | 0573004.1 Railings SD CALCS city submission.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-11 |  | Seattle Center Arena - 48549 calcs_r0_STAMPED.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-11 |  | 0573004.1 Railings SD CALCS city submission.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-11 |  | Seattle Center Arena - 48549 calcs_r0_STAMPED.pdf
| Responded and Closed |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-20 |  | 0573004.1 Railings SD CALCS city submission-POP.pdf
| Responded and Closed |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-20 |  | Seattle Center Arena - 48549 calcs_r0_STAMPED-POP.pdf
05 73 00-004-02 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-004-02 SW Snorkel Gates SDs | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-17 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kevin Devore (ME Engineers), Rick Lewis (Studio 08 Consultants), Linda Scott (Studio 08 Consultants), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-10-01 | 2021-09-21 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14669 | Received | For Review | 2021-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-10-01 | Submittal Number: 05 73 00-4.2 From: TYLER KREN Final Due Date: 10/01/21 Subject: SW SNORKEL GATES SDS Description: SHOP DRAWINGS AND CALCULATIONS FOR CITY SUBMISSION. PLEASE STAMP EACH PAGE FOR CITY SUBMISSION. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 18918 | Forwarded | For Review | 2021-09-20 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-27 | Submittal Number: 05 73 00-4.2 From: TYLER KREN Final Due Date: 10/01/21 Subject: SW SNORKEL GATES SDS Description: SHOP DRAWINGS AND CALCULATIONS FOR CITY SUBMISSION. PLEASE STAMP EACH PAGE FOR CITY SUBMISSION. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 18921 | Forwarded | For Review | 2021-09-20 | Shaina Burris (Populous) | Kevin Devore (ME Engineers); Rick Lewis (Studio 08 Consultants); Linda Scott (Studio 08 Consultants); Michael Mazzocchi (ME Engineers) | 2021-09-27 | Submittal Number: 05 73 00-4.2 From: TYLER KREN Final Due Date: 10/01/21 Subject: SW SNORKEL GATES SDS Description: SHOP DRAWINGS AND CALCULATIONS FOR CITY SUBMISSION. PLEASE STAMP EACH PAGE FOR CITY SUBMISSION. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 14681 | Review Response | Approved as Noted | 2021-09-21 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal for the SW Snorkel Gates. If you have any questions or comments, please feel free to contact me. Thanks. | Info Exchange
| 18937 | Responded and Closed | Approved as Noted | 2021-09-21 | Chad Francis (Populous) | Tyler Kren (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-17 |  | 057300-4.2 - SW Snorkel Gates.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-17 |  | 057300-4.2 - SW Snorkel Gates.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-17 |  | 057300-4.2 - SW Snorkel Gates.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-09-17 |  | 057300-4.2 - SW Snorkel Gates.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-09-21 |  | 057300-4.2 - SW Snorkel Gates1 ST08 REVIEW_POP.pdf
05 73 00-005-00 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-005-00 Railing Mock Up Cart | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-06 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-20 | 2020-05-22 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-05-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05749 | Received | For Review | 2020-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-20 | Submittal Number: 05 73 00-5.0 From: JES PELKEY Final Due Date: 05/20/20 Subject: RAILING MOCK UP CART Description: SAMPLES FOR INITIAL SELECTION : FOR PRODUCTS INVOLVING SELECTION OF COLOR, TEXTURE, OR DESIGN, INCLUDING MECHANICAL FINISHES. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 07804 | Forwarded | For Review | 2020-05-06 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-13 | Submittal Number: 05 73 00-5.0 From: JES PELKEY Final Due Date: 05/20/20 Subject: RAILING MOCK UP CART Description: SAMPLES FOR INITIAL SELECTION : FOR PRODUCTS INVOLVING SELECTION OF COLOR, TEXTURE, OR DESIGN, INCLUDING MECHANICAL FINISHES. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 08141 | Responded and Closed | Approved as Noted | 2020-05-22 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-06 |  | 05 73 00-5.0 Railing Mock-Up Cart-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-06 |  | 05 73 00-5.0 Railing Mock-Up Cart-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-22 02:00 |  | 05 73 00-5.0 Railing Mock-Up Cart with comments-MAM_pop.pdf
05 73 00-011-00 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-011-00 DECORATIVE METAL RAILINGS - Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-27 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-15 | 2020-05-14 | 18 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-05-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05560 | Received | For Review | 2020-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-15 | Submittal Number: 05 73 00-11.0 From: JES PELKEY Final Due Date: 05/11/20 Subject: DECORATIVE METAL RAILINGS - CALCULATIONS Description: PRODUCT TEST REPORTS : BASED ON EVALUATION OF COMPREHENSIVE TESTS PERFORMED BYA QUALIFIED TESTING AGENCY, ACCORDING TO ASTM E 894 AND ASTM E 935. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 07536 | Forwarded | For Review | 2020-04-27 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-04 | Submittal Number: 05 73 00-11.0 From: JES PELKEY Final Due Date: 05/11/20 Subject: DECORATIVE METAL RAILINGS - CALCULATIONS Description: PRODUCT TEST REPORTS : BASED ON EVALUATION OF COMPREHENSIVE TESTS PERFORMED BYA QUALIFIED TESTING AGENCY, ACCORDING TO ASTM E 894 AND ASTM E 935. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 07537 | Forwarded | For Review | 2020-04-27 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean Mc... | 2020-05-04 | Submittal Number: 05 73 00-11.0 From: JES PELKEY Final Due Date: 05/11/20 Subject: DECORATIVE METAL RAILINGS - CALCULATIONS Description: PRODUCT TEST REPORTS : BASED ON EVALUATION OF COMPREHENSIVE TESTS PERFORMED BYA QUALIFIED TESTING AGENCY, ACCORDING TO ASTM E 894 AND ASTM E 935. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 05870 | Review Response | Approved | 2020-05-13 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 07966 | Responded and Closed | Approved | 2020-05-14 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-25 |  | 05 73 00-11.0 Railing Calculations-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-25 |  | 05 73 00-11.0 Railing Calculations-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-24 02:00 |  | 05 73 00-11.0 Railing Calculations-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-24 02:00 |  | 05 73 00-11.0 Railing Calculations-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-14 02:00 |  | 05 73 00-11.0 Railing Calculations-MAM_TT REVIEW_POP.pdf
05 73 00-013-00 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-013-00 Suite Cable Rail Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-20 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-03 | 2020-09-14 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07636 | Received | For Review | 2020-08-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-03 | Submittal Number: 05 73 00-13.0 From: JES PELKEY Final Due Date: 09/03/20 Subject: SUITE CABLE RAIL SHOP DRAWINGS Description: Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 10172 | Forwarded | For Review | 2020-08-20 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-27 | Submittal Number: 05 73 00-13.0 From: JES PELKEY Final Due Date: 09/03/20 Subject: SUITE CABLE RAIL SHOP DRAWINGS Description: Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 10752 | Responded and Closed | Approved as Noted | 2020-09-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 05 73 00-13.0 Suite Cable Rail SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-20 |  | 05 73 00-13.0 Suite Cable Rail SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-20 |  | 05 73 00-13.0 Suite Cable Rail SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-20 |  | Transmittal_Submittal - 05 73 00-013-00 (Forwarded).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-14 |  | 05 73 00-13.0 Suite Cable Rail SD-MAM-POP.pdf
05 73 00-014-00 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-014-00 Escalator Railing Details | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-21 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-04 | 2020-08-31 | 11 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-08-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07653 | Received | For Review | 2020-08-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-04 | Submittal Number: 05 73 00-14.0 From: JES PELKEY Final Due Date: 09/03/20 Subject: ESCALATOR RAILING DETAILS Description: MOCKUPS : BUILD MOCKUPS TO VERIFY SELECTIONS MADE UNDER SAMPLE SUBMITTALS, TO DEMONSTRATE AESTHETIC EFFECTS, AND TO SET QUALITY STANDARDS FOR FABRICATION AND INSTALLATION. 1. BUILD MOCKUPS AS SHOWN ON DRAWINGS. 2. BUILD MOCKUPS FOR EACH FORM AND FINISH OF RAILING CONSISTING OF TWO POSTS, TOP RAIL, INFILL AREA, AND ANCHORAGE SYSTEM COMPONENTS THAT ARE FULL HEIGHT AND ARE NOT LESS THAN 24 INCHES IN LENGTH. 3. SUBJECT TO COMPLIANCE WITH REQUIREMENTS, APPROVED MOCKUPS MAY BECOME PART OF THE COMPLETED WORK IF UNDISTURBED AT TIME OF SUBSTANTIAL COMPLETION. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 10196 | Forwarded | For Review | 2020-08-20 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-27 | Submittal Number: 05 73 00-14.0 From: JES PELKEY Final Due Date: 09/03/20 Subject: ESCALATOR RAILING DETAILS Description: MOCKUPS : BUILD MOCKUPS TO VERIFY SELECTIONS MADE UNDER SAMPLE SUBMITTALS, TO DEMONSTRATE AESTHETIC EFFECTS, AND TO SET QUALITY STANDARDS FOR FABRICATION AND INSTALLATION. 1. BUILD MOCKUPS AS SHOWN ON DRAWINGS. 2. BUILD MOCKUPS FOR EACH FORM AND FINISH OF RAILING CONSISTING OF TWO POSTS, TOP RAIL, INFILL AREA, AND ANCHORAGE SYSTEM COMPONENTS THAT ARE FULL HEIGHT AND ARE NOT LESS THAN 24 INCHES IN LENGTH. 3. SUBJECT TO COMPLIANCE WITH REQUIREMENTS, APPROVED MOCKUPS MAY BECOME PART OF THE COMPLETED WORK IF UNDISTURBED AT TIME OF SUBSTANTIAL COMPLETION. Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 10444 | Responded and Closed | Approved as Noted | 2020-08-31 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 05 73 00-14.0 Escalator Railing Detail Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-20 |  | 05 73 00-14.0 Escalator Railing Detail Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-31 |  | 05 73 00-14.0 Escalator Railing Detail Drawings-MAM_POP.pdf
05 73 00-015-00 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-015-00 Suite Cable Rail Mockup | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-17 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-31 | 2021-03-30 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-03-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12056 | Received | For Review | 2021-03-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-03-31 | Submittal Number: 05 73 00-15.0 From: TYLER KREN Final Due Date: 03/30/21 Subject: SUITE CABLE RAIL MOCKUP Description: SUITE CABLE RAIL MOCK UP Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 15612 | Forwarded | For Review | 2021-03-16 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-23 | Submittal Number: 05 73 00-15.0 From: TYLER KREN Final Due Date: 03/30/21 Subject: SUITE CABLE RAIL MOCKUP Description: SUITE CABLE RAIL MOCK UP Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 15961 | Responded and Closed | Approved as Noted | 2021-03-30 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Tyler Kren (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Confirm Rockwell approval prior to proceeding. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-16 |  | 05 73 00-15.0 Suite Cable Rail Mock up.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-16 |  | 05 73 00-15.0 Suite Cable Rail Mock up.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-30 02:00 |  | 05 73 00-15.0 Suite Cable Rail Mock up_pop.pdf
05 73 00-016-00 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-016-00 Monumental Stair Handrail Lighting | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-02 | Review Response - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Mark Lievens (ME Engineers) |  |  |  | 2021-06-16 | 2021-06-22 | 21 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2021-06-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13352 | Received | For Review | 2021-06-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-06-16 | Submittal Number: 05 73 00-16.0 From: TYLER KREN Final Due Date: 06/15/21 Subject: MONUMENTAL STAIR HANDRAIL LIGHTING Description: MONUMENTAL STAIR HANDRAIL LIGHTING Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 17279 | Forwarded | For Review | 2021-06-01 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 05 73 00-16.0 From: TYLER KREN Final Due Date: 06/15/21 Subject: MONUMENTAL STAIR HANDRAIL LIGHTING Description: MONUMENTAL STAIR HANDRAIL LIGHTING Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 17356 | Forwarded | For Review | 2021-06-07 | Todd Spangler (Populous) | Mark Lievens (ME Engineers) |  | Submittal Number: 05 73 00-16.0 From: TYLER KREN Final Due Date: 06/15/21 Subject: MONUMENTAL STAIR HANDRAIL LIGHTING Description: MONUMENTAL STAIR HANDRAIL LIGHTING Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 17628 | Responded and Closed | Approved | 2021-06-22 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 13676 | Review Response | Revise and Resubmit | 2021-06-28 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.06.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-01 |  | 057300-16- Monumental Stair Handrail Lighting.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-01 |  | 057300-16- Monumental Stair Handrail Lighting.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2021-06-01 |  | 057300-16- Monumental Stair Handrail Lighting.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-06-22 |  | 057300-16- Monumental Stair Handrail Lighting-POP.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-05-31 02:00 |  | 057300-16- Monumental Stair Handrail Lighting.pdf
05 73 00-017-00 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-017-00 Owner Suite- removable Rail | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-10 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-24 | 2021-06-15 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13480 | Received | For Review | 2021-06-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-06-24 | Submittal Number: 05 73 00-17.0 From: TYLER KREN Final Due Date: 06/23/21 Subject: OWNER SUITE- REMOVABLE RAIL Description: Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 17433 | Forwarded | For Review | 2021-06-10 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-17 | Submittal Number: 05 73 00-17.0 From: TYLER KREN Final Due Date: 06/23/21 Subject: OWNER SUITE- REMOVABLE RAIL Description: Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 17501 | Responded and Closed | Approved as Noted | 2021-06-15 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-10 |  | 057300-17 Owner Suite- Removable Rail.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-10 |  | 057300-17 Owner Suite- Removable Rail.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-06-15 |  | 057300-17 Owner Suite- Removable Rail-POP.pdf
05 73 00-017-01 | 05 73 00 - DECORATIVE METAL RAILINGS | 05 73 00-017-01 Owner Suite- removable Rail | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-04 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-18 | 2021-09-01 | 29 |  | Record Copies; Transfers; Submittals |  | 30 |  | 2021-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14206 | Received | For Review | 2021-08-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-08-18 | Submittal Number: 05 73 00-17.1 From: TYLER KREN Final Due Date: 08/17/21 Subject: OWNER SUITE- REMOVABLE RAIL Description: Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 18360 | Forwarded | For Review | 2021-08-03 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-10 | Submittal Number: 05 73 00-17.1 From: TYLER KREN Final Due Date: 08/17/21 Subject: OWNER SUITE- REMOVABLE RAIL Description: Spec Section: 05 73 00 - DECORATIVE METAL RAILINGS Status: OPEN | Info Exchange
| 18755 | Responded and Closed | Approved | 2021-09-01 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-03 |  | 05730017.1 Owner Suite Frosted Glass Sample- for record only.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-03 |  | 05730017.1 Owner Suite Frosted Glass Sample- for record only.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-08-03 |  | 05730017.1 Owner Suite Frosted Glass Sample- for record only.pdf
05 75 00-001-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-001-00 Metal Base Shop Drawings - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-14 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-28 | 2020-08-05 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-08-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06956 | Received | For Review | 2020-07-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-28 | Submittal Number: 05 75 00-1.0 From: JOSH BROUSSARD Final Due Date: 07/28/20 Subject: METAL BASE SHOP DRAWINGS - BASE BUILDING Description: THIS SUBMITTAL INCLUDES SHOP DRAWINGS FOR ALL METAL BASE IN BASE BUILDING AREAS. Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 09323 | Forwarded | For Review | 2020-07-14 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-21 | Submittal Number: 05 75 00-1.0 From: JOSH BROUSSARD Final Due Date: 07/28/20 Subject: METAL BASE SHOP DRAWINGS - BASE BUILDING Description: THIS SUBMITTAL INCLUDES SHOP DRAWINGS FOR ALL METAL BASE IN BASE BUILDING AREAS. Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 07392 | Review Response | Approved as Noted/Resubmit | 2020-08-05 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached markup. Resubmit corrected location plans for record. | Info Exchange
| 09855 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached markup. Resubmit corrected location plans for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-14 |  | 05 75 00-1.0 Metal Base Shop Dwgs - Base Bldg.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-14 |  | 05 75 00-1.0 Metal Base Shop Dwgs - Base Bldg.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-05 |  | 05 75 00-1.0 Metal Base Shop Dwgs - Base Bldg_POP_Final.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-14 |  | 05 75 00-1.0 Metal Base Shop Dwgs - Base Bldg.pdf
05 75 00-001-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-001-01 Metal Base Shop Drawings - Base Building Rev 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-17 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-01 | 2020-09-30 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-09-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08163 | Received | For Review | 2020-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-01 | Submittal Number: 05 75 00-1.1 From: MIKE SOLFELT Final Due Date: 09/30/20 Subject: METAL BASE SHOP DRAWINGS - BASE BUILDING REV 1 Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10837 | Forwarded | For Review | 2020-09-17 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-24 | Submittal Number: 05 75 00-1.1 From: MIKE SOLFELT Final Due Date: 09/30/20 Subject: METAL BASE SHOP DRAWINGS - BASE BUILDING REV 1 Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 08432 | Review Response | Approved as Noted | 2020-09-30 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11173 | Responded and Closed | Approved as Noted | 2020-09-30 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-16 |  | 05 75 00-001.1 Metal Base Shop Drawings - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-16 |  | 05 75 00-001.1 Metal Base Shop Drawings - Base Building.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-30 |  | 05 75 00-001.1 Metal Base Shop Drawings - Base Building_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-16 |  | 05 75 00-001.1 Metal Base Shop Drawings - Base Building.pdf
05 75 00-002-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-002-00 Metal Base and TV Surround Product Data - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-03 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-18 | 2020-09-23 | 21 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07965 | Received | For Review | 2020-09-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-18 | Submittal Number: 05 75 00-2.0 From: JOSH BROUSSARD Final Due Date: 08/14/20 Subject: METAL BASE AND TV SURROUND PRODUCT DATA - BASE BUILDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10590 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-15 | Submittal Number: 05 75 00-2.0 From: JOSH BROUSSARD Final Due Date: 08/14/20 Subject: METAL BASE AND TV SURROUND PRODUCT DATA - BASE BUILDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 08266 | Review Response | Approved as Noted | 2020-09-23 | Kuebler Perry (Populous) | pop |  | See attached review. | Info Exchange
| 10971 | Responded and Closed | Approved as Noted | 2020-09-23 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-03 |  | 05 75 00-002 Metal Base and TV Surround Product Data - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-03 |  | 05 75 00-002 Metal Base and TV Surround Product Data - Base Building.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-23 |  | 05 75 00-002 Metal Base and TV Surround Product Data - Base Building_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-03 |  | 05 75 00-002 Metal Base and TV Surround Product Data - Base Building.pdf
05 75 00-003-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-003-00 Metal TV Surround Shop Drawings - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-28 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-11 | 2020-08-07 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-08-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07176 | Received | For Review | 2020-07-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-08-11 | Submittal Number: 05 75 00-3.0 From: JOSH BROUSSARD Final Due Date: 08/07/20 Subject: METAL TV SURROUND SHOP DRAWINGS - BASE BUILDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 09578 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-04 | Submittal Number: 05 75 00-3.0 From: JOSH BROUSSARD Final Due Date: 08/07/20 Subject: METAL TV SURROUND SHOP DRAWINGS - BASE BUILDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 07457 | Review Response | Approved as Noted | 2020-08-07 | Kuebler Perry (Populous) | Populous SCA_CCA |  | refer to attached review | Info Exchange
| 09925 | Responded and Closed | Approved as Noted | 2020-08-07 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached review. Provide shop drawings for additional TV's as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-27 |  | 057500-003 - Metal TV Surround Shop Drawings - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-27 |  | 057500-003 - Metal TV Surround Shop Drawings - Base Building.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-07 |  | 057500-003 - Metal TV Surround Shop Drawings - Base Building_POP_Final.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-27 |  | 057500-003 - Metal TV Surround Shop Drawings - Base Building.pdf
05 75 00-003-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-003-01 Metal TV Surround Shop Drawings - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-01 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kelsea Conkright (Populous) |  |  |  | 2021-02-15 | 2021-02-19 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-02-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11081 | Received | For Review | 2021-02-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-15 | Submittal Number: 05 75 00-3.1 From: MIKE SOLFELT Final Due Date: 02/15/21 Subject: METAL TV SURROUND SHOP DRAWINGS - BASE BUILDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14376 | Forwarded | For Review | 2021-02-01 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-08 | Submittal Number: 05 75 00-3.1 From: MIKE SOLFELT Final Due Date: 02/15/21 Subject: METAL TV SURROUND SHOP DRAWINGS - BASE BUILDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14590 | Forwarded | For Review | 2021-02-08 | Josh Dobken (Populous) | Kelsea Conkright (Populous); Chad Francis (Populous) | 2021-02-15 | Submittal Number: 05 75 00-3.1 From: MIKE SOLFELT Final Due Date: 02/15/21 Subject: METAL TV SURROUND SHOP DRAWINGS - BASE BUILDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11546 | Review Response | Approved as Noted | 2021-02-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14966 | Responded and Closed | Approved as Noted | 2021-02-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-01 |  | 05 75 00-003.1 Metal TV Surrounds Shop Drawings - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-01 |  | 05 75 00-003.1 Metal TV Surrounds Shop Drawings - Base Building.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-31 02:00 |  | 05 75 00-003.1 Metal TV Surrounds Shop Drawings - Base Building.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-19 |  | 05 75 00-003.1 Metal TV Surrounds Shop Drawings - Base Building_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-01 |  | 05 75 00-003.1 Metal TV Surrounds Shop Drawings - Base Building.pdf
05 75 00-005-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-005-00 Metal Base Selection Sample - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-10 07:00 | 2020-09-09 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07759 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-10 07:00 | Submittal Number: 05 75 00-5.0 From: JOSH BROUSSARD Final Due Date: 08/07/20 Subject: METAL BASE SELECTION SAMPLE - BASE BUILDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10330 | Forwarded | For Review | 2020-08-26 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 05 75 00-5.0 From: JOSH BROUSSARD Final Due Date: 08/07/20 Subject: METAL BASE SELECTION SAMPLE - BASE BUILDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 08004 | Review Response | Approved | 2020-09-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10638 | Responded and Closed | Approved | 2020-09-09 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 062023-009 Concession and Bar Shop Drawings 4.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-26 |  | 05 75 00-005 Metal Base Selection Samples - Base Building.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-26 |  | 062023-009 Concession and Bar Shop Drawings 4.pdf
05 75 00-005-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-005-01 Metal Base Selection Sample - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-09 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-23 | 2021-03-24 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11876 | Received | For Review | 2021-03-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-23 | Submittal Number: 05 75 00-5.1 From: JOSH BROUSSARD Final Due Date: 03/23/21 Subject: METAL BASE SELECTION SAMPLE - BASE BUILDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 15398 | Forwarded | For Review | 2021-03-09 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-16 | Submittal Number: 05 75 00-5.1 From: JOSH BROUSSARD Final Due Date: 03/23/21 Subject: METAL BASE SELECTION SAMPLE - BASE BUILDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12216 | Review Response | Approved | 2021-03-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 15808 | Responded and Closed | Approved | 2021-03-24 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-09 |  | 05 75 00-5.1 Decorative Metal Submittal (1).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-09 |  | 05 75 00-5.1 Decorative Metal Submittal (1).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-24 |  | 05 75 00-5.1 Decorative Metal Submittal POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-09 |  | 05 75 00-5.1 Decorative Metal Submittal (1).pdf
05 75 00-007-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-007-00 Astound Metal Sample Package #1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-08 07:00 | 2020-09-08 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07699 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-08 07:00 | Submittal Number: 05 75 00-7.0 From: MIKE SOLFELT Final Due Date: 09/03/20 Subject: ASTOUND METAL SAMPLE PACKAGE #1 Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10248 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-31 | Submittal Number: 05 75 00-7.0 From: MIKE SOLFELT Final Due Date: 09/03/20 Subject: ASTOUND METAL SAMPLE PACKAGE #1 Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 07971 | Review Response | Approved as Noted | 2020-09-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Approval as discussed in meeting: · M11 (base building only) o Pre-washed Powder-coated Clear Matte is the preferred sample, IF there is no price increase from what was specified in arch. drawings o idX and Astound to coordinate fabrication and procurement scope. · M21 and M25 (MT-01 and MT-05) o It was discussed that the No wash Powder-coated Clear Matte was expected to achieve the desired look. o Astound to produce a full sheet sample with this finish and send photos for review/approval. · P32 o Cardinal Brass Metallic 30 Gloss T353-YL02 is the preferred color. o Astound to confirm this can be provided with a 50% gloss. · M24 (MT-04) o The submitted sample is confirmed to be the accepted color. o Confirmed M21/M25 will replace M24 at the suite level corridors. | Info Exchange
| 10600 | Responded and Closed | Approved as Noted | 2020-09-08 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Approval as discussed in meeting: · M11 (base building only) o Pre-washed Powder-coated Clear Matte is the preferred sample, IF there is no price increase from what was specified in arch. drawings o idX and Astound to coordinate fabrication and procurement scope. · M21 and M25 (MT-01 and MT-05) o It was discussed that the No wash Powder-coated Clear Matte was expected to achieve the desired look. o Astound to produce a full sheet sample with this finish and send photos for review/approval. · P32 o Cardinal Brass Metallic 30 Gloss T353-YL02 is the preferred color. o Astound to confirm this can be provided with a 50% gloss. · M24 (MT-04) o The submitted sample is confirmed to be the accepted color. o Confirmed M21/M25 will replace M24 at the suite level corridors. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 057500-007 - Decorative Metal Samples - M11&M21&M25.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 057500-007 - Decorative Metal Samples - M11&M21&M25.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-24 |  | 057500-007 - Decorative Metal Samples - M11&M21&M25.pdf
05 75 00-007-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-007-01 M21/M25 Resubmit | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-20 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-03 | 2020-11-03 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-11-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08871 | Received | For Review | 2020-10-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-03 | Submittal Number: 05 75 00-7.1 From: MIKE SOLFELT Final Due Date: 11/02/20 Subject: M21/M25 RESUBMIT Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11729 | Forwarded | For Review | 2020-10-20 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-27 | Submittal Number: 05 75 00-7.1 From: MIKE SOLFELT Final Due Date: 11/02/20 Subject: M21/M25 RESUBMIT Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 09184 | Review Response | Approved as Noted | 2020-11-03 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12128 | Responded and Closed | Approved as Noted | 2020-11-03 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-20 |  | 05 75 00-007.1 M21 and M25 Resubmittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-20 |  | 05 75 00-007.1 M21 and M25 Resubmittal.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-03 |  | 05 75 00-007.1 M21 and M25 Resubmittal_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-20 |  | 05 75 00-007.1 M21 and M25 Resubmittal.pdf
05 75 00-008-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-008-00 Sideline Suite S106 Metal Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-10 07:00 | 2020-09-15 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-09-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07771 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-10 07:00 | Submittal Number: 05 75 00-8.0 From: MIKE SOLFELT Final Due Date: 09/07/20 Subject: SIDELINE SUITE S106 METAL SHOP DRAWINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10343 | Forwarded | For Review | 2020-08-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 05 75 00-8.0 From: MIKE SOLFELT Final Due Date: 09/07/20 Subject: SIDELINE SUITE S106 METAL SHOP DRAWINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10782 | Responded and Closed | Approved as Noted | 2020-09-15 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 05 75 00-008 Sideline Suite S106 Metal Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-26 |  | 05 75 00-008 Sideline Suite S106 Metal Shop Drawings.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-09-15 |  | 05 75 00-008 Sideline Suite S106 Metal Shop Drawings_POP.pdf
05 75 00-009-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-009-00 Tunnel Club B1 Orn Metal Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-31 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-15 07:00 | 2020-09-15 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07849 | Received | For Review | 2020-08-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-15 07:00 | Submittal Number: 05 75 00-9.0 From: JOSH BROUSSARD Final Due Date: 09/09/20 Subject: TUNNEL CLUB B1 ORN METAL SHOP DRAWINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10434 | Forwarded | For Review | 2020-08-31 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-07 | Submittal Number: 05 75 00-9.0 From: JOSH BROUSSARD Final Due Date: 09/09/20 Subject: TUNNEL CLUB B1 ORN METAL SHOP DRAWINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 08136 | Review Response | Approved as Noted | 2020-09-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10809 | Responded and Closed | Approved as Noted | 2020-09-15 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-31 |  | 05 75 00-009 Tuneel Club B1 Orn Metal Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-31 |  | 05 75 00-009 Tuneel Club B1 Orn Metal Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-15 |  | 05 75 00-009 Tuneel Club B1 Orn Metal Shop Drawings_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-31 |  | 05 75 00-009 Tuneel Club B1 Orn Metal Shop Drawings.pdf
05 75 00-010-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-010-00 Tunnel Club B1 Corridor Alum Channel Shop Drawing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-31 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-15 07:00 | 2020-09-15 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07851 | Received | For Review | 2020-08-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-15 07:00 | Submittal Number: 05 75 00-10.0 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: TUNNEL CLUB B1 CORRIDOR ALUM CHANNEL SHOP DRAWING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10436 | Forwarded | For Review | 2020-08-31 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-07 | Submittal Number: 05 75 00-10.0 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: TUNNEL CLUB B1 CORRIDOR ALUM CHANNEL SHOP DRAWING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 08132 | Review Response | Approved as Noted | 2020-09-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10802 | Responded and Closed | Approved as Noted | 2020-09-15 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | GC to submit shop drawings for Tunnel Club corridor glazing components as one package for remaining tunnel club corridors, it is impossible to tell what's missing vs what belongs to another sub | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-31 |  | 05 75 00-010 Tunnel B1 Cooridor Alum Channel Shop Drawing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-31 |  | 05 75 00-010 Tunnel B1 Cooridor Alum Channel Shop Drawing.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-15 |  | 05 75 00-010 Tunnel B1 Cooridor Alum Channel Shop Drawing_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-31 |  | 05 75 00-010 Tunnel B1 Cooridor Alum Channel Shop Drawing.pdf
05 75 00-011-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-011-00 East / West Suite Level Concourse Column Wraps | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-07 | 2020-10-09 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-10-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08283 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 05 75 00-11.0 From: MIKE SOLFELT Final Due Date: 10/08/20 Subject: EAST / WEST SUITE LEVEL CONCOURSE COLUMN WRAPS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10989 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-30 | Submittal Number: 05 75 00-11.0 From: MIKE SOLFELT Final Due Date: 10/08/20 Subject: EAST / WEST SUITE LEVEL CONCOURSE COLUMN WRAPS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11470 | Responded and Closed | Approved as Noted | 2020-10-09 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 05 75 00-011 East and West Suite Level Concourse Column Wraps.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 05 75 00-011 East and West Suite Level Concourse Column Wraps.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-09 |  | 05 75 00-011 East and West Suite Level Concourse Column Wraps_POP.pdf
05 75 00-013-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-013-00 Mount Baker Club | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-16 | 2020-12-03 | 32 |  | Record Copies; Transfers; Submittals |  | 32 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09153 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-16 | Submittal Number: 05 75 00-13.0 From: MIKE SOLFELT Final Due Date: 10/12/20 Subject: MOUNT BAKER CLUB Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12075 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-09 | Submittal Number: 05 75 00-13.0 From: MIKE SOLFELT Final Due Date: 10/12/20 Subject: MOUNT BAKER CLUB Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12906 | Responded and Closed | Revise and Resubmit | 2020-12-03 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | 05 75 00-013 Orn Metal Mount Baker.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | 05 75 00-013 Orn Metal Mount Baker.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-12-03 |  | 05 75 00-013 Orn Metal Mount Baker - RG RESPONSE_POP.pdf
05 75 00-013-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-013-01 Mount Baker Club - Orn Metals | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-05 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-19 | 2021-02-22 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-02-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11229 | Received | For Review | 2021-02-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-19 | Submittal Number: 05 75 00-13.1 From: MIKE SOLFELT Final Due Date: 02/19/21 Subject: MOUNT BAKER CLUB - ORN METALS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14534 | Forwarded | For Review | 2021-02-05 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-12 | Submittal Number: 05 75 00-13.1 From: MIKE SOLFELT Final Due Date: 02/19/21 Subject: MOUNT BAKER CLUB - ORN METALS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14984 | Responded and Closed | Approved as Noted | 2021-02-22 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-05 |  | 05 75 00-13.1 Mt. Baker Club - Orn Metals.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-05 |  | 05 75 00-13.1 Mt. Baker Club - Orn Metals.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-22 |  | 05 75 00-13.1 Mt. Baker Club - Orn Metals_POP.pdf
05 75 00-014-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-014-00 NHL Locker Room | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-12 | 2020-11-09 | 43 |  | Record Copies; Transfers; Submittals |  | 43 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08373 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 05 75 00-14.0 From: MIKE SOLFELT Final Due Date: 10/05/20 Subject: NHL LOCKER ROOM Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11092 | Forwarded | For Review | 2020-09-28 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 05 75 00-14.0 From: MIKE SOLFELT Final Due Date: 10/05/20 Subject: NHL LOCKER ROOM Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 09317 | Review Response | Revise and Resubmit | 2020-11-09 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12295 | Responded and Closed | Revise and Resubmit | 2020-11-09 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-28 |  | 05 75 00-014 Ornn Metal NHL Locker Room East Entry.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-28 |  | 05 75 00-014 Ornn Metal NHL Locker Room East Entry.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-11-09 |  | 05 75 00-014 Ornn Metal NHL Locker Room East Entry_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-09-28 |  | 05 75 00-014 Ornn Metal NHL Locker Room East Entry.pdf
05 75 00-014-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-014-01 NHL Locker Room | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-19 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-01-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10369 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-19 08:00 | Submittal Number: 05 75 00-14.1 From: MIKE SOLFELT Final Due Date: 12/04/20 Subject: NHL LOCKER ROOM Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13550 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 05 75 00-14.1 From: MIKE SOLFELT Final Due Date: 12/04/20 Subject: NHL LOCKER ROOM Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10789 | Review Response | Approved as Noted/Resubmit | 2021-01-19 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14024 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-19 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-28 |  | 05 75 00-14.1 Orn Metal NHL Locker Room East Entry.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-28 |  | 05 75 00-14.1 Orn Metal NHL Locker Room East Entry.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-19 |  | 05 75 00-14.1 Orn Metal NHL Locker Room East Entry_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-12-28 |  | 05 75 00-14.1 Orn Metal NHL Locker Room East Entry.pdf
05 75 00-014-02 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-014-02 NHL Locker Room | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-22 | 2021-02-17 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11265 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-22 | Submittal Number: 05 75 00-14.2 From: MIKE SOLFELT Final Due Date: 02/16/21 Subject: NHL LOCKER ROOM Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14596 | Forwarded | For Review | 2021-02-08 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-15 | Submittal Number: 05 75 00-14.2 From: MIKE SOLFELT Final Due Date: 02/16/21 Subject: NHL LOCKER ROOM Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11517 | Review Response | Approved as Noted | 2021-02-17 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14918 | Responded and Closed | Approved as Noted | 2021-02-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-08 |  | 05 75 00-14.2 Orn Metal NHL Locker Room East Entry.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-08 |  | 05 75 00-14.2 Orn Metal NHL Locker Room East Entry.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-17 |  | 05 75 00-14.2 Orn Metal NHL Locker Room East Entry_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-08 |  | 05 75 00-14.2 Orn Metal NHL Locker Room East Entry.pdf
05 75 00-016-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-016-00 Orn Metals Space Needle Club | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-03 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-17 | 2020-12-18 | 16 |  | Record Copies; Transfers; Submittals | 05 75 00-016-00-01 - 05 75 00-016-00 Orn Metals Space Needle Club | 16 |  | 2020-12-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09889 | Received | For Review | 2020-12-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-12-17 | Submittal Number: 05 75 00-16.0 From: MIKE SOLFELT Final Due Date: 12/17/20 Subject: ORN METALS SPACE NEEDLE CLUB Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12972 | Forwarded | For Review | 2020-12-03 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-10 | Submittal Number: 05 75 00-16.0 From: MIKE SOLFELT Final Due Date: 12/17/20 Subject: ORN METALS SPACE NEEDLE CLUB Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10254 | Review Response | Approved as Noted/Resubmit | 2020-12-18 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13408 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-18 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-03 |  | 05 75 00-16 Orn Metals space Needle Club.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-03 |  | 05 75 00-16 Orn Metals space Needle Club.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-18 |  | 05 75 00-16 Orn Metals space Needle Club_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-03 |  | 05 75 00-16 Orn Metals space Needle Club.pdf
05 75 00-016-00-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-016-00 Orn Metals Space Needle Club | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 75 00-016-00 - 05 75 00-016-00 Orn Metals Space Needle Club | -1 | 2021-01-01
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-03 |  | 05 75 00-16 Orn Metals space Needle Club.pdf
05 75 00-017-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-017-00 Chairman's Club | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-20 | 17 |  | Record Copies; Transfers; Submittals | 05 75 00-017-00-01 - 05 75 00-017-00 Chairman's Club | 17 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10375 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-19 08:00 | Submittal Number: 05 75 00-17.0 From: MIKE SOLFELT Final Due Date: 01/12/21 Subject: CHAIRMAN'S CLUB Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13558 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 05 75 00-17.0 From: MIKE SOLFELT Final Due Date: 01/12/21 Subject: CHAIRMAN'S CLUB Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10815 | Review Response | Approved as Noted/Resubmit | 2021-01-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14060 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-29 |  | 05 75 00-17 Orn Metals Chairmans Club.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-29 |  | 05 75 00-17 Orn Metals Chairmans Club.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-20 |  | 05 75 00-17 Orn Metals Chairmans Club_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-29 |  | 05 75 00-17 Orn Metals Chairmans Club.pdf
05 75 00-017-00-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-017-00 Chairman's Club | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 75 00-017-00 - 05 75 00-017-00 Chairman's Club | -1 | 2021-02-03
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-29 |  | 05 75 00-17 Orn Metals Chairmans Club.pdf
05 75 00-018-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-018-00 Main Concourse Club - East | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-19 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-02 | 2021-02-04 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10787 | Received | For Review | 2021-01-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-02-02 | Submittal Number: 05 75 00-18.0 From: MIKE SOLFELT Final Due Date: 02/02/21 Subject: MAIN CONCOURSE CLUB - EAST Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14017 | Forwarded | For Review | 2021-01-19 | Mike Solfelt (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-26 | Submittal Number: 05 75 00-18.0 From: MIKE SOLFELT Final Due Date: 02/02/21 Subject: MAIN CONCOURSE CLUB - EAST Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11182 | Review Response | Approved as Noted | 2021-02-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14488 | Responded and Closed | Approved as Noted | 2021-02-04 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-19 |  | 05 75 00-18 Orn Metals East Concourse.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-01-19 |  | 05 75 00-18 Orn Metals East Concourse.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-04 |  | 05 75 00-18 Orn Metals East Concourse_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-01-19 |  | 05 75 00-18 Orn Metals East Concourse.pdf
05 75 00-019-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-019-00 Main Concourse Club - West | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-29 08:00 | 2021-02-01 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10700 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-29 08:00 | Submittal Number: 05 75 00-19.0 From: MIKE SOLFELT Final Due Date: 01/29/21 Subject: MAIN CONCOURSE CLUB - WEST Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13921 | Forwarded | For Review | 2021-01-14 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-21 | Submittal Number: 05 75 00-19.0 From: MIKE SOLFELT Final Due Date: 01/29/21 Subject: MAIN CONCOURSE CLUB - WEST Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11078 | Review Response | Approved as Noted | 2021-02-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14377 | Responded and Closed | Approved as Noted | 2021-02-01 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | 05 75 00-19 Orn Metals West Concourse.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-14 |  | 05 75 00-19 Orn Metals West Concourse.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-01 |  | 05 75 00-19 Orn Metals West Concourse_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-14 |  | 05 75 00-19 Orn Metals West Concourse.pdf
05 75 00-020-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-020-00 Metropolitan Club | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-22 | 2021-02-23 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-02-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11266 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-02-22 | Submittal Number: 05 75 00-20.0 From: MIKE SOLFELT Final Due Date: 02/22/21 Subject: METROPOLITAN CLUB Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14597 | Forwarded | For Review | 2021-02-08 | Mike Solfelt (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-15 | Submittal Number: 05 75 00-20.0 From: MIKE SOLFELT Final Due Date: 02/22/21 Subject: METROPOLITAN CLUB Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11601 | Review Response | Approved as Noted/Resubmit | 2021-02-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15032 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-23 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-08 |  | 05 75 00-20 Orn Metals Metro Clurb.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-02-08 |  | 05 75 00-20 Orn Metals Metro Clurb.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-23 |  | 05 75 00-20 Orn Metals Metro Clurb_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-02-08 |  | 05 75 00-20 Orn Metals Metro Clurb.pdf
05 75 00-020-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-020-01 Metropolitan Club Revised Submittals - Orn Metals | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-14 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-28 | 2021-04-28 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12594 | Received | For Review | 2021-04-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-28 | Submittal Number: 05 75 00-20.1 From: JENI REETZ Final Due Date: 04/28/21 Subject: METROPOLITAN CLUB REVISED SUBMITTALS - ORN METALS Description: REVISED AND RESUBMITTED WITH NEW M31. GRAIN DIRECTION IS AN IMPORTANT DETAIL TO CONFIRM. PLEASE ALSO CONFRIM SEAMS ARE ACCURATE AND ACCEPTABLE. Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 16311 | Forwarded | For Review | 2021-04-14 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-21 | Submittal Number: 05 75 00-20.1 From: JENI REETZ Final Due Date: 04/28/21 Subject: METROPOLITAN CLUB REVISED SUBMITTALS - ORN METALS Description: REVISED AND RESUBMITTED WITH NEW M31. GRAIN DIRECTION IS AN IMPORTANT DETAIL TO CONFIRM. PLEASE ALSO CONFRIM SEAMS ARE ACCURATE AND ACCEPTABLE. Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12836 | Review Response | Approved as Noted | 2021-04-28 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16612 | Responded and Closed | Approved as Noted | 2021-04-28 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-14 |  | 05 75 00-20 Orn Metals Metro Clurb - Rev 1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-14 |  | 05 75 00-20 Orn Metals Metro Clurb - Rev 1.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-28 |  | 05 75 00-20 Orn Metals Metro Clurb - Rev 1_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-14 |  | 05 75 00-20 Orn Metals Metro Clurb - Rev 1.pdf
05 75 00-021-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-021-00 Sideline Suites - East (101-120) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-29 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-12 | 2020-11-20 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09097 | Received | For Review | 2020-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-12 | Submittal Number: 05 75 00-21.0 From: MIKE SOLFELT Final Due Date: 11/12/20 Subject: SIDELINE SUITES - EAST (101-120) Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12003 | Forwarded | For Review | 2020-10-29 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-05 | Submittal Number: 05 75 00-21.0 From: MIKE SOLFELT Final Due Date: 11/12/20 Subject: SIDELINE SUITES - EAST (101-120) Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12676 | Responded and Closed | Approved as Noted | 2020-11-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-29 |  | 05 75 00-21 Orn Metals Sideline Suites East.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-29 |  | 05 75 00-21 Orn Metals Sideline Suites East.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-11-20 |  | 05 75 00-21 Orn Metals Sideline Suites East - RG RESPONSE_POP.pdf
05 75 00-022-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-022-00 Sideline Suites - West (121-140) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-29 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-12 | 2020-11-20 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09096 | Received | For Review | 2020-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-12 | Submittal Number: 05 75 00-22.0 From: MIKE SOLFELT Final Due Date: 11/12/20 Subject: SIDELINE SUITES - WEST (121-140) Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12002 | Forwarded | For Review | 2020-10-29 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-05 | Submittal Number: 05 75 00-22.0 From: MIKE SOLFELT Final Due Date: 11/12/20 Subject: SIDELINE SUITES - WEST (121-140) Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12678 | Responded and Closed | Approved as Noted | 2020-11-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-29 |  | 05 75 00-22 Orn Metals Sideline Suites West.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-29 |  | 05 75 00-22 Orn Metals Sideline Suites West.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-11-20 |  | 05 75 00-22 Orn Metals Sideline Suites West - RG RESPONSE_POP.pdf
05 75 00-023-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-023-00 Tunnel Club - East | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-21 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10376 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-19 08:00 | Submittal Number: 05 75 00-23.0 From: MIKE SOLFELT Final Due Date: 02/24/21 Subject: TUNNEL CLUB - EAST Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13559 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 05 75 00-23.0 From: MIKE SOLFELT Final Due Date: 02/24/21 Subject: TUNNEL CLUB - EAST Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10868 | Review Response | Approved as Noted | 2021-01-21 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14112 | Responded and Closed | Approved as Noted | 2021-01-21 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-29 |  | 05 75 00-23 Orn Metals Tunnel Club East.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-29 |  | 05 75 00-23 Orn Metals Tunnel Club East.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-21 |  | 05 75 00-23 Orn Metals Tunnel Club East_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-29 |  | 05 75 00-23 Orn Metals Tunnel Club East.pdf
05 75 00-024-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-024-00 Tunnel Club - West | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-27 08:00 | 2021-01-31 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-01-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10628 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-01-27 08:00 | Submittal Number: 05 75 00-24.0 From: MIKE SOLFELT Final Due Date: 02/08/21 Subject: TUNNEL CLUB - WEST Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13835 | Forwarded | For Review | 2021-01-12 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-19 | Submittal Number: 05 75 00-24.0 From: MIKE SOLFELT Final Due Date: 02/08/21 Subject: TUNNEL CLUB - WEST Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11069 | Review Response | Approved as Noted | 2021-01-31 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14367 | Responded and Closed | Approved as Noted | 2021-01-31 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 05 75 00 - 24 Tunnel Club - West.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-11 |  | 05 75 00 - 24 Tunnel Club - West.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-31 |  | 05 75 00 - 24 Tunnel Club - West_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-11 |  | 05 75 00 - 24 Tunnel Club - West.pdf
05 75 00-025-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-025-00 M14, P39, P24, M34, M26 and M33 Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-07 | 2020-10-06 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08284 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 05 75 00-25.0 From: MIKE SOLFELT Final Due Date: 10/09/20 Subject: M14, P39, P24, M34, M26 AND M33 SAMPLES Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10990 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-30 | Submittal Number: 05 75 00-25.0 From: MIKE SOLFELT Final Due Date: 10/09/20 Subject: M14, P39, P24, M34, M26 AND M33 SAMPLES Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 08607 | Review Response | Approved as Noted/Resubmit | 2020-10-06 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review for individual revise and resubmit criteria. | Info Exchange
| 11376 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-06 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review for individual revise and resubmit criteria. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 05 75 00-025 M14 P39 P24 M34 M26 and M33 Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 05 75 00-025 M14 P39 P24 M34 M26 and M33 Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-06 |  | 05 75 00-025 M14 P39 P24 M34 M26 M33 POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-23 |  | 05 75 00-025 M14 P39 P24 M34 M26 and M33 Samples.pdf
05 75 00-025-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-025-01 M14 and P24 Resubmit | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-12 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-30 08:00 | 2020-11-18 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09397 | Received | For Review | 2020-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-30 08:00 | Submittal Number: 05 75 00-25.1 From: MIKE SOLFELT Final Due Date: 11/26/20 Subject: M14 AND P24 RESUBMIT Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12400 | Forwarded | For Review | 2020-11-12 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-19 | Submittal Number: 05 75 00-25.1 From: MIKE SOLFELT Final Due Date: 11/26/20 Subject: M14 AND P24 RESUBMIT Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 09553 | Review Response | Revise and Resubmit | 2020-11-18 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Revise and Resubmit M14 as noted. P24 Approved. | Info Exchange
| 12576 | Responded and Closed | Revise and Resubmit | 2020-11-18 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: Revise and Resubmit M14 as noted. P24 Approved. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-12 |  | 05 75 00-025.1 M14 and P24 resubmit.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-12 |  | 05 75 00-025.1 M14 and P24 resubmit.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-11-18 |  | 05 75 00-025.1 M14 and P24 resubmit_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-12 |  | 05 75 00-025.1 M14 and P24 resubmit.pdf
05 75 00-026-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-026-00 M11 Metal Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-19 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-02 | 2020-11-03 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-11-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08855 | Received | For Review | 2020-10-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company); Mike Solfelt (M.A. Mortenson Company) | 2020-11-02 | Submittal Number: 05 75 00-26.0 From: MIKE SOLFELT Final Due Date: 11/01/20 Subject: M11 METAL SAMPLE Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11703 | Forwarded | For Review | 2020-10-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-26 | Submittal Number: 05 75 00-26.0 From: MIKE SOLFELT Final Due Date: 11/01/20 Subject: M11 METAL SAMPLE Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 09182 | Review Response | Approved | 2020-11-03 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12124 | Responded and Closed | Approved | 2020-11-03 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-19 |  | 05 75 00-26.0 M11 Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-19 |  | 05 75 00-26.0 M11 Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-03 |  | 05 75 00-26.0 M11 Sample_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-19 |  | 05 75 00-26.0 M11 Sample.pdf
05 75 00-027-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-027-00 Orn Metals Mt Baker Ceilings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-20 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10377 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-19 08:00 | Submittal Number: 05 75 00-27.0 From: MIKE SOLFELT Final Due Date: 01/12/21 Subject: ORN METALS MT BAKER CEILINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13560 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 05 75 00-27.0 From: MIKE SOLFELT Final Due Date: 01/12/21 Subject: ORN METALS MT BAKER CEILINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14062 | Responded and Closed | Approved as Noted | 2021-01-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-29 |  | 05 75 00-27 Mt. Baker Ceilings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-29 |  | 05 75 00-27 Mt. Baker Ceilings.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-20 |  | 05 75 00-27 Mt. Baker Ceilings_POP.pdf
05 75 00-028-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-028-00 WS-5 Product Data / Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-11-23 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-11-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09610 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-07 | Submittal Number: 05 75 00-28.0 From: MIKE SOLFELT Final Due Date: 11/20/20 Subject: WS-5 PRODUCT DATA / SAMPLES Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12645 | Forwarded | For Review | 2020-11-19 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 05 75 00-28.0 From: MIKE SOLFELT Final Due Date: 11/20/20 Subject: WS-5 PRODUCT DATA / SAMPLES Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 09694 | Review Response | Approved | 2020-11-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12749 | Responded and Closed | Approved | 2020-11-23 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-19 |  | 05 75 00-28 WS-5 Product Data and Samples.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-19 |  | 05 75 00-28 WS-5 Product Data and Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-23 |  | 05 75 00-28 WS-5 Product Data and Samples_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-19 |  | 05 75 00-28 WS-5 Product Data and Samples.pdf
05 75 00-029-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-029-00 WS-5 Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-01 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-15 | 2021-02-15 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11082 | Received | For Review | 2021-02-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-15 | Submittal Number: 05 75 00-29.0 From: MIKE SOLFELT Final Due Date: 02/11/21 Subject: WS-5 SHOP DRAWINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14379 | Forwarded | For Review | 2021-02-01 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-08 | Submittal Number: 05 75 00-29.0 From: MIKE SOLFELT Final Due Date: 02/11/21 Subject: WS-5 SHOP DRAWINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11401 | Review Response | Approved as Noted | 2021-02-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14768 | Responded and Closed | Approved as Noted | 2021-02-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-01 |  | 05 75 00-29 WS-5 Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-01 |  | 05 75 00-29 WS-5 Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-15 |  | 05 75 00-29 WS-5 Shop Drawings_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-01 |  | 05 75 00-29 WS-5 Shop Drawings.pdf
05 75 00-030-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-030-00 P32 / P39 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-12 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-30 08:00 | 2020-11-23 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-11-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09393 | Received | For Review | 2020-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-30 08:00 | Submittal Number: 05 75 00-30.0 From: MIKE SOLFELT Final Due Date: 11/23/20 Subject: P32 / P39 SAMPLE Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12397 | Forwarded | For Review | 2020-11-12 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-19 | Submittal Number: 05 75 00-30.0 From: MIKE SOLFELT Final Due Date: 11/23/20 Subject: P32 / P39 SAMPLE Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 09693 | Review Response | Approved as Noted | 2020-11-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12748 | Responded and Closed | Approved as Noted | 2020-11-23 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-11 |  | 05 75 00-30 P32 & P39 Metal Sample Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-11 |  | 05 75 00-30 P32 & P39 Metal Sample Submittal.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-23 |  | 05 75 00-30 P32 & P39 Metal Sample Submittal_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-11 |  | 05 75 00-30 P32 & P39 Metal Sample Submittal.pdf
05 75 00-031-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-031-00 M26, M31, and M14 Orn Metal Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-21 | 2020-12-16 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09945 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (M.A. Mortenson Company) | 2020-12-21 | Submittal Number: 05 75 00-31.0 From: MIKE SOLFELT Final Due Date: 12/21/20 Subject: M26, M31, AND M14 ORN METAL SAMPLE Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13025 | Forwarded | For Review | 2020-12-07 | Mike Solfelt (M.A. Mortenson Company) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 05 75 00-31.0 From: MIKE SOLFELT Final Due Date: 12/21/20 Subject: M26, M31, AND M14 ORN METAL SAMPLE Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10200 | Review Response | Approved | 2020-12-16 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13339 | Responded and Closed | Approved | 2020-12-16 | Mike Solfelt (M.A. Mortenson Company) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 05 75 00-31 M31 M26 and M14 Samples.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2020-12-07 |  | 05 75 00-31 M31 M26 and M14 Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-16 |  | 05 75 00-31 M31 M26 and M14 Samples_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2020-12-07 |  | 05 75 00-31 M31 M26 and M14 Samples.pdf
05 75 00-032-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-032-00 M25 Perf Panel | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-18 | 2021-01-15 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-01-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10378 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-18 | Submittal Number: 05 75 00-32.0 From: MIKE SOLFELT Final Due Date: 01/07/21 Subject: M25 PERF PANEL Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13561 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 05 75 00-32.0 From: MIKE SOLFELT Final Due Date: 01/07/21 Subject: M25 PERF PANEL Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10738 | Review Response | Approved as Noted | 2021-01-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13966 | Responded and Closed | Approved as Noted | 2021-01-15 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-04 |  | 05 75 00-32 M25 Perf Panel.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-04 |  | 05 75 00-32 M25 Perf Panel.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-15 |  | 05 75 00-32 M25 Perf Panel_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-04 |  | 05 75 00-32 M25 Perf Panel.pdf
05 75 00-033-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-033-00 Sideline Suite / Decorative Metal Beam Resubmit | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-08 | 2021-02-05 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-02-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10942 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-08 | Submittal Number: 05 75 00-33.0 From: MIKE SOLFELT Final Due Date: 01/29/21 Subject: SIDELINE SUITE / DECORATIVE METAL BEAM RESUBMIT Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14205 | Forwarded | For Review | 2021-01-25 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-01 | Submittal Number: 05 75 00-33.0 From: MIKE SOLFELT Final Due Date: 01/29/21 Subject: SIDELINE SUITE / DECORATIVE METAL BEAM RESUBMIT Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14528 | Responded and Closed | Approved as Noted | 2021-02-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. SEE COMMENTS ON ATTACHED. 2. COORDINATE ALL COMMENTS FROM ROCKWELL GROUP | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 05 75 00-033 Orn Metals Sideline Suites Column Cladding Submittals.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-25 |  | 05 75 00-033 Orn Metals Sideline Suites Column Cladding Submittals.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-05 |  | 05 75 00-033 Orn Metals Sideline Suites Column Cladding Submittals_POP.pdf
05 75 00-034-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-034-00 M11 Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-09 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-23 | 2021-02-23 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-02-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11275 | Received | For Review | 2021-02-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-23 | Submittal Number: 05 75 00-34.0 From: MIKE SOLFELT Final Due Date: 02/22/21 Subject: M11 SHOP DRAWINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14606 | Forwarded | For Review | 2021-02-08 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-15 | Submittal Number: 05 75 00-34.0 From: MIKE SOLFELT Final Due Date: 02/22/21 Subject: M11 SHOP DRAWINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 11604 | Review Response | Approved as Noted/Resubmit | 2021-02-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 15040 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-23 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-08 |  | 05 75 00-34.0 M11 Wall Cladding & Stair Trim.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-08 |  | 05 75 00-34.0 M11 Wall Cladding & Stair Trim.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-23 |  | 05 75 00-34.0 M11 Wall Cladding & Stair Trim_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-08 |  | 05 75 00-34.0 M11 Wall Cladding & Stair Trim.pdf
05 75 00-034-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-034-01 M11 Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-23 | 2021-04-26 | 18 |  | Record Copies; Transfers; Submittals | 05 75 00-034-01-01 - 05 75 00-034-01 M11 Shop Drawings | 19 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12497 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-23 | Submittal Number: 05 75 00-34.1 From: MIKE SOLFELT Final Due Date: 04/13/21 Subject: M11 SHOP DRAWINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 16185 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 05 75 00-34.1 From: MIKE SOLFELT Final Due Date: 04/13/21 Subject: M11 SHOP DRAWINGS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12762 | Review Response | Approved as Noted/Resubmit | 2021-04-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. Resubmit only clarified items as-required, coordinate with architect. | Info Exchange
| 16497 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. Resubmit only clarified items as-required, coordinate with architect. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 05 75 00-34.1 M11 Metal Wall Cladding & Stair Trim.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 05 75 00-34.1 M11 Metal Wall Cladding & Stair Trim.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-26 |  | 05 75 00-34.1 M11 Metal Wall Cladding & Stair Trim_POP.pdf
05 75 00-034-01-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-034-01 M11 Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 75 00-034-01 - 05 75 00-034-01 M11 Shop Drawings | -1 | 2021-05-10
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-26 |  | 05 75 00-34.1 M11 Metal Wall Cladding & Stair Trim_POP.pdf
05 75 00-035-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-035-00 P39/P24, ST21, SST1 Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-06 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-20 | 2021-01-15 | 10 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-01-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10457 | Received | For Review | 2021-01-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-01-20 | Submittal Number: 05 75 00-35.0 From: MIKE SOLFELT Final Due Date: 01/18/21 Subject: P39/P24, ST21, SST1 SAMPLES Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13653 | Forwarded | For Review | 2021-01-05 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-12 | Submittal Number: 05 75 00-35.0 From: MIKE SOLFELT Final Due Date: 01/18/21 Subject: P39/P24, ST21, SST1 SAMPLES Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 10737 | Review Response | Approved as Noted | 2021-01-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13965 | Responded and Closed | Approved as Noted | 2021-01-15 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-05 |  | 05 75 00-35 - SST1 - P39-P24 - ST21 Sample Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-05 |  | 05 75 00-35 - SST1 - P39-P24 - ST21 Sample Submittal.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-15 |  | 05 75 00-35 - SST1 - P39-P24 - ST21 Sample Submittal_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-05 |  | 05 75 00-35 - SST1 - P39-P24 - ST21 Sample Submittal.pdf
05 75 00-036-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-036-00 Airstream Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-10 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-24 | 2021-03-17 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11904 | Received | For Review | 2021-03-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-03-24 | Submittal Number: 05 75 00-36.0 From: JEREMY INGEBRAND Final Due Date: 03/22/21 Subject: AIRSTREAM SHOP DRAWINGS Description: ATTACHED ARE THE CURRENT AIRSTREAM DRAWINGS. WE ARE LOOKING FOR FINAL APPROVAL ON THE DESIGN AND DIMENSIONS TO PUSH THIS INTO FABRICATION. Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 15424 | Forwarded | For Review | 2021-03-10 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-17 | Submittal Number: 05 75 00-36.0 From: JEREMY INGEBRAND Final Due Date: 03/22/21 Subject: AIRSTREAM SHOP DRAWINGS Description: ATTACHED ARE THE CURRENT AIRSTREAM DRAWINGS. WE ARE LOOKING FOR FINAL APPROVAL ON THE DESIGN AND DIMENSIONS TO PUSH THIS INTO FABRICATION. Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 15633 | Responded and Closed | Approved as Noted | 2021-03-17 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS 1. COORDINATE ALL EQUIPMENT CLEARANCES WITHIN AIRSTREAM. 2. CM TO COORDINATE ALL ROCKWELL GROUP COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-10 |  | 05 75 00-36 - Airstream Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-10 |  | 05 75 00-36 - Airstream Shop Drawings.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-17 |  | 05 75 00-36 - Airstream Shop Drawings_POP.pdf
05 75 00-037-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-037-00 M1 / M8 Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-22 | 18 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-04-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12368 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 05 75 00-37.0 From: MIKE SOLFELT Final Due Date: 04/09/21 Subject: M1 / M8 SAMPLES Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 16024 | Forwarded | For Review | 2021-04-01 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 05 75 00-37.0 From: MIKE SOLFELT Final Due Date: 04/09/21 Subject: M1 / M8 SAMPLES Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12657 | Review Response | Revise and Resubmit | 2021-04-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. In addition to comments on sheets, please provide context for why we are resubmitting substitutions for finishes that have already been approved as specified. | Info Exchange
| 16377 | Responded and Closed | Revise and Resubmit | 2021-04-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. In addition to comments on sheets, please provide context for why we are resubmitting substitutions for finishes that have already been approved as specified. | Info Exchange
| 12720 | Review Response | Approved as Noted | 2021-04-22 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Approved for use where Rimex product will not work. | Info Exchange
| 16443 | Responded and Closed | Approved as Noted | 2021-04-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Approved for use where Rimex product will not work. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 07 75 00-37.0 M1 and M8 Samples.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 05 75 00-37.0 M1 and M8 Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-20 |  | 05 75 00-37.0 M1 and M8 Samples_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 07 75 00-37.0 M1 and M8 Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-22 |  | 05 75 00-37.0 M1 and M8 Samples_POP_R.1.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 07 75 00-37.0 M1 and M8 Samples.pdf
05 75 00-038-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-038-00 South Concourse Metal Cladding | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-23 | 2021-04-20 | 12 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12498 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-23 | Submittal Number: 05 75 00-38.0 From: MIKE SOLFELT Final Due Date: 04/18/21 Subject: SOUTH CONCOURSE METAL CLADDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 16186 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 05 75 00-38.0 From: MIKE SOLFELT Final Due Date: 04/18/21 Subject: SOUTH CONCOURSE METAL CLADDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12670 | Review Response | Approved | 2021-04-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16390 | Responded and Closed | Approved | 2021-04-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 05 75 00-038 South Concourse Soffit Cladding.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 05 75 00-038 South Concourse Soffit Cladding.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-20 |  | 05 75 00-038 South Concourse Soffit Cladding_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 05 75 00-038 South Concourse Soffit Cladding.pdf
05 75 00-039-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-039-00 M15 - CCD Update | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-12 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-26 | 2021-04-26 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12531 | Received | For Review | 2021-04-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-26 | Submittal Number: 05 75 00-39.0 From: MIKE SOLFELT Final Due Date: 04/29/21 Subject: M15 - CCD UPDATE Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 16233 | Forwarded | For Review | 2021-04-12 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-19 | Submittal Number: 05 75 00-39.0 From: MIKE SOLFELT Final Due Date: 04/29/21 Subject: M15 - CCD UPDATE Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 12765 | Review Response | Approved | 2021-04-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 16500 | Responded and Closed | Approved | 2021-04-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-12 |  | 05 75 00-39 M15 CCD Update.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-12 |  | 05 75 00-39 M15 CCD Update.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-26 |  | 05 75 00-39 M15 CCD Update_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-12 |  | 05 75 00-39 M15 CCD Update.pdf
05 75 00-040-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-040-00 Main Con Storage Lid Orn. Metals | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-23 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-07 | 2021-05-10 | 18 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12723 | Received | For Review | 2021-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-07 | Submittal Number: 05 75 00-40.0 From: MIKE SOLFELT Final Due Date: 05/04/21 Subject: MAIN CON STORAGE LID ORN. METALS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 16449 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-29 | Submittal Number: 05 75 00-40.0 From: MIKE SOLFELT Final Due Date: 05/04/21 Subject: MAIN CON STORAGE LID ORN. METALS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13008 | Review Response | Approved | 2021-05-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16833 | Responded and Closed | Approved | 2021-05-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-22 |  | 07 75 00-40 Main Con Storage Lid Orn. Metals.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-22 |  | 07 75 00-40 Main Con Storage Lid Orn. Metals.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-10 |  | 05 75 00-40 Main Con Storage Lid Orn. Metals_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-22 |  | 07 75 00-40 Main Con Storage Lid Orn. Metals.pdf
05 75 00-041-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-041-00 Curtain Track Cladding | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-06-04 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13136 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-06-02 07:00 | Submittal Number: 05 75 00-41.0 From: MIKE SOLFELT Final Due Date: 05/31/21 Subject: CURTAIN TRACK CLADDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 16996 | Forwarded | For Review | 2021-05-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-25 | Submittal Number: 05 75 00-41.0 From: MIKE SOLFELT Final Due Date: 05/31/21 Subject: CURTAIN TRACK CLADDING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13399 | Review Response | Approved as Noted | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17330 | Responded and Closed | Approved as Noted | 2021-06-04 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | 05 75 00-41 Space Needle Curtain Track Assembly.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-18 |  | 05 75 00-41 Space Needle Curtain Track Assembly.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-04 |  | 05 75 00-41 Space Needle Curtain Track Assembly_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-05-18 |  | 05 75 00-41 Space Needle Curtain Track Assembly.pdf
05 75 00-042-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-042-00 Space Needle Shelving | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-06-04 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13137 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-06-02 07:00 | Submittal Number: 05 75 00-42.0 From: MIKE SOLFELT Final Due Date: 05/31/21 Subject: SPACE NEEDLE SHELVING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 16997 | Forwarded | For Review | 2021-05-18 | Mike Solfelt (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-25 | Submittal Number: 05 75 00-42.0 From: MIKE SOLFELT Final Due Date: 05/31/21 Subject: SPACE NEEDLE SHELVING Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13398 | Review Response | Approved as Noted | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17329 | Responded and Closed | Approved as Noted | 2021-06-04 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | 05 75 00-42 Space Needle Club Shelving.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-05-18 |  | 05 75 00-42 Space Needle Club Shelving.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-04 |  | 05 75 00-42 Space Needle Club Shelving_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-05-18 |  | 05 75 00-42 Space Needle Club Shelving.pdf
05 75 00-045-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-045-00 NHL Locker Speaker Covers Orn Metals | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-19 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Ben Cating (Idibri), Brian Elwell (Idibri) |  |  |  | 2021-08-02 | 2021-07-21 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14002 | Received | For Review | 2021-07-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-08-02 | Submittal Number: 05 75 00-45.0 From: MIKE SOLFELT Final Due Date: 06/09/21 Subject: NHL LOCKER SPEAKER COVERS ORN METALS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18112 | Forwarded | For Review | 2021-07-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-26 | Submittal Number: 05 75 00-45.0 From: MIKE SOLFELT Final Due Date: 06/09/21 Subject: NHL LOCKER SPEAKER COVERS ORN METALS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18126 | Forwarded | For Review | 2021-07-19 | Kelsea Conkright (Populous) | Ben Cating (Idibri); Brian Elwell (Idibri) |  | Submittal Number: 05 75 00-45.0 From: MIKE SOLFELT Final Due Date: 06/09/21 Subject: NHL LOCKER SPEAKER COVERS ORN METALS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14034 | Review Response | Approved as Noted | 2021-07-21 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Email
| 18158 | Responded and Closed | Approved as Noted | 2021-07-21 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-19 |  | 05 75 00-47 NHL Locker Room Speaker Cover.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-19 |  | 05 75 00-47 NHL Locker Room Speaker Cover.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-07-19 |  | 05 75 00-47 NHL Locker Room Speaker Cover.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-07-21 |  | 05 75 00-47 NHL Locker Room Speaker Cover_i!iResponse_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-07-19 |  | 05 75 00-47 NHL Locker Room Speaker Cover.pdf
05 75 00-046-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-046-00 Tunnel Club Corridor Metal Panels | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-24 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-09 07:00 | 2021-07-08 | 15 |  | Record Copies; Transfers; Submittals | 05 75 00-046-00-01 - 05 75 00-046-00 Tunnel Club Corridor Metal Panels | 15 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13629 | Received | For Review | 2021-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-09 07:00 | Submittal Number: 05 75 00-46.0 From: MIKE SOLFELT Final Due Date: 07/07/21 Subject: TUNNEL CLUB CORRIDOR METAL PANELS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 17650 | Forwarded | For Review | 2021-06-24 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-01 | Submittal Number: 05 75 00-46.0 From: MIKE SOLFELT Final Due Date: 07/07/21 Subject: TUNNEL CLUB CORRIDOR METAL PANELS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13845 | Review Response | Approved as Noted/Resubmit | 2021-07-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17921 | Responded and Closed | Approved as Noted/Resubmit | 2021-07-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-24 |  | 05 75 00-46.0 Tunnel Club Corridor Wall Panels.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-24 |  | 05 75 00-46.0 Tunnel Club Corridor Wall Panels.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-08 |  | 05 75 00-46.0 Tunnel Club Corridor Wall Panels_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-24 |  | 05 75 00-46.0 Tunnel Club Corridor Wall Panels.pdf
05 75 00-046-00-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-046-00 Tunnel Club Corridor Metal Panels | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 75 00-046-00 - 05 75 00-046-00 Tunnel Club Corridor Metal Panels | -1 | 2021-07-22
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-24 |  | 05 75 00-46.0 Tunnel Club Corridor Wall Panels.pdf
05 75 00-047-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-047-00 Perf Panels for Main Con / Upper Just Walk Out | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-28 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-13 07:00 | 2021-07-08 | 11 |  | Record Copies; Transfers; Submittals | 05 75 00-047-00-01 - 05 75 00-047-00 Perf Panels for Main Con / Upper Just Walk Out | 12 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13665 | Received | For Review | 2021-06-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-07-13 07:00 | Submittal Number: 05 75 00-47.0 From: MIKE SOLFELT Final Due Date: 07/10/21 Subject: PERF PANELS FOR MAIN CON / UPPER JUST WALK OUT Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 17694 | Forwarded | For Review | 2021-06-27 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-05 | Submittal Number: 05 75 00-47.0 From: MIKE SOLFELT Final Due Date: 07/10/21 Subject: PERF PANELS FOR MAIN CON / UPPER JUST WALK OUT Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 13831 | Review Response | Revise and Resubmit | 2021-07-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. Recommend a quick call with Astound to revise. | Info Exchange
| 17906 | Responded and Closed | Revise and Resubmit | 2021-07-08 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. Recommend a quick call with Astound to revise. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-26 |  | 05 75 00-47.0 Perforated Panels at Upper and Main Con JWO.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-26 |  | 05 75 00-47.0 Perforated Panels at Upper and Main Con JWO.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-08 |  | 05 75 00-47.0 Perforated Panels at Upper and Main Con JWO_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-06-26 |  | 05 75 00-47.0 Perforated Panels at Upper and Main Con JWO.pdf
05 75 00-047-00-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-047-00 Perf Panels for Main Con / Upper Just Walk Out | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 05 75 00-047-00 - 05 75 00-047-00 Perf Panels for Main Con / Upper Just Walk Out | -1 | 2021-07-22
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-26 |  | 05 75 00-47.0 Perforated Panels at Upper and Main Con JWO.pdf
05 75 00-048-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-048-00 Main Con Club Column Drink Rails and Footrails | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-18 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-02 | 2021-06-21 | 4 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-06-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13559 | Received | For Review | 2021-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (Mortenson Construction) | 2021-07-02 | Submittal Number: 05 75 00-48.0 From: JOSH BROUSSARD Final Due Date: 07/01/21 Subject: MAIN CON CLUB COLUMN DRINK RAILS AND FOOTRAILS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 17556 | Forwarded | For Review | 2021-06-17 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-24 | Submittal Number: 05 75 00-48.0 From: JOSH BROUSSARD Final Due Date: 07/01/21 Subject: MAIN CON CLUB COLUMN DRINK RAILS AND FOOTRAILS Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 17602 | Responded and Closed | Approved as Noted | 2021-06-21 | Chad Francis (Populous) | Josh Broussard (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-17 |  | 05 75 00-48.0 Main Con Club Column Drink Rails & Footrails.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-17 |  | 05 75 00-48.0 Main Con Club Column Drink Rails & Footrails.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-21 |  | 05 75 00-48.0 Main Con Club Column Drink Rails & Footrails_POP.pdf
05 75 00-049-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-049-00 Craft Beer Roofing Material | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-06 | Responded and Closed - Rejected |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-20 | 2021-07-12 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-07-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13802 | Received | For Review | 2021-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-07-20 | Submittal Number: 05 75 00-49.0 From: JENI REETZ Final Due Date: 07/20/21 Subject: CRAFT BEER ROOFING MATERIAL Description: PER CCD109 - ROOFING CORRUGATE SPEC FOR APPROVAL ON PROFILE. FINAL PRODUCT DIMS TO MATCH ROOF FRAMING. COLOR TBC ON ARCHITECT SELECTION. Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 17874 | Forwarded | For Review | 2021-07-06 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-13 | Submittal Number: 05 75 00-49.0 From: JENI REETZ Final Due Date: 07/20/21 Subject: CRAFT BEER ROOFING MATERIAL Description: PER CCD109 - ROOFING CORRUGATE SPEC FOR APPROVAL ON PROFILE. FINAL PRODUCT DIMS TO MATCH ROOF FRAMING. COLOR TBC ON ARCHITECT SELECTION. Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 17995 | Responded and Closed | Rejected | 2021-07-12 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-06 |  | 05 75 00-49 Orn Metal Craft Beer Roofing Corrugate.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-06 |  | 05 75 00-49 Orn Metal Craft Beer Roofing Corrugate.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-07-12 |  | 05 75 00-49 Orn Metal Craft Beer Roofing Corrugate-POP.pdf
05 75 00-049-01 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-049-01 Craft Beer Roofing Material | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-28 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-11 | 2021-07-29 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14148 | Received | For Review | 2021-07-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-08-11 | Submittal Number: 05 75 00-49.1 From: JENI REETZ Final Due Date: 07/20/21 Subject: CRAFT BEER ROOFING MATERIAL Description: PER CCD109 - ROOFING CORRUGATE SPEC FOR APPROVAL ON PROFILE. FINAL PRODUCT DIMS TO MATCH ROOF FRAMING. COLOR TBC ON ARCHITECT SELECTION. Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18290 | Forwarded | For Review | 2021-07-28 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-04 | Submittal Number: 05 75 00-49.1 From: JENI REETZ Final Due Date: 07/20/21 Subject: CRAFT BEER ROOFING MATERIAL Description: PER CCD109 - ROOFING CORRUGATE SPEC FOR APPROVAL ON PROFILE. FINAL PRODUCT DIMS TO MATCH ROOF FRAMING. COLOR TBC ON ARCHITECT SELECTION. Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18301 | Responded and Closed | Approved as Noted | 2021-07-29 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-28 |  | 05 75 00 -49 Craft Beer Corrugate Cladding V2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-28 |  | 05 75 00 -49 Craft Beer Corrugate Cladding V2.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-07-29 |  | 05 75 00 -49 Craft Beer Corrugate Cladding V2_POP.pdf
05 75 00-050-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-050-00 NHL Locker and Hydrotherapy Soffit Trim | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-27 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-10 | 2021-07-29 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-07-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14135 | Received | For Review | 2021-07-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-08-10 | Submittal Number: 05 75 00-50.0 From: MIKE SOLFELT Final Due Date: 07/23/21 Subject: NHL LOCKER AND HYDROTHERAPY SOFFIT TRIM Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18267 | Forwarded | For Review | 2021-07-27 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-03 | Submittal Number: 05 75 00-50.0 From: MIKE SOLFELT Final Due Date: 07/23/21 Subject: NHL LOCKER AND HYDROTHERAPY SOFFIT TRIM Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 14167 | Review Response | Approved as Noted | 2021-07-29 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18314 | Responded and Closed | Approved as Noted | 2021-07-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-26 |  | 05 75 00-47 NHL Locker Light Cove Cover.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-26 |  | 05 75 00-47 NHL Locker Light Cove Cover.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-07-29 |  | 05 75 00-050 NHL Locker Light Cove Cover_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-26 |  | 05 75 00-47 NHL Locker Light Cove Cover.pdf
05 75 00-051-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-051-00 Decorative Metal LEED Information | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-25 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-08 | 2021-08-30 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-08-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14468 | Received | For Review | 2021-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-09-08 | Submittal Number: 05 75 00-51.0 From: MIKE SOLFELT Final Due Date: 09/08/21 Subject: DECORATIVE METAL LEED INFORMATION Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18662 | Forwarded | For Review | 2021-08-25 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-01 | Submittal Number: 05 75 00-51.0 From: MIKE SOLFELT Final Due Date: 09/08/21 Subject: DECORATIVE METAL LEED INFORMATION Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18709 | Responded and Closed | Approved | 2021-08-30 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-25 |  | 05 75 00-51 Orn Metal LEED info.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-25 |  | 05 75 00-51 Orn Metal LEED info.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-08-30 |  | 05 75 00-51 Orn Metal LEED info_POP.pdf
05 75 00-052-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-052-00 JWO Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-27 | Responded and Closed - Approved | [5 empty] | 2021-09-10 | 2021-08-26 | -1 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14503 | Received | For Review | 2021-08-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-09-10 | Submittal Number: 05 75 00-52.0 From: MIKE SOLFELT Final Due Date: 09/09/21 Subject: JWO SAMPLES Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18699 | Responded and Closed | Approved | 2021-08-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-26 02:00 |  | 05 75 00-52 JWO Samples.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-08-26 02:00 |  | 05 75 00-52 JWO Samples_POP.pdf
05 75 00-053-00 |  | 05 75 00-053-00 Craft Beer Roofing Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-27 | Responded and Closed - Approved |  | Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2021-09-10 | 2021-08-30 | 4 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-08-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14504 | Received | For Review | 2021-08-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-09-10 | Submittal Number: 05 75 00-53.0 From: MIKE SOLFELT Final Due Date: 09/09/21 Subject: CRAFT BEER ROOFING SAMPLE Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18700 | Forwarded | For Review | 2021-08-26 | Josh Dobken (Populous) | Kuebler Perry (Populous); Chad Francis (Populous) | 2021-09-02 | Submittal Number: 05 75 00-53.0 From: MIKE SOLFELT Final Due Date: 09/09/21 Subject: CRAFT BEER ROOFING SAMPLE Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18708 | Responded and Closed | Approved | 2021-08-30 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-26 02:00 |  | 05 75 00-53 Craft Beer Roofing Sample.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-08-26 02:00 |  | 05 75 00-53 Craft Beer Roofing Sample.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-08-30 |  | 05 75 00-53 Craft Beer Roofing Sample_POP.pdf
05 75 00-054-00 | 05 75 00 - DECORATIVE FORMED METAL | 05 75 00-054-00 Decorative Metal Sample Warranty | Closed | Architectural, Owner/Operator | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-30 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Byron Noll (CAA ICON / Strategy Advisory), Chad Francis (Populous) |  |  |  | 2021-09-13 | 2021-09-10 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-09-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14524 | Received | For Review | 2021-08-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-13 | Submittal Number: 05 75 00-54.0 From: MIKE SOLFELT Final Due Date: 09/13/21 Subject: DECORATIVE METAL SAMPLE WARRANTY Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18724 | Forwarded | For Review | 2021-08-30 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Byron Noll (CAA ICON / Strategy Advisory); Chad Francis (Populous) | 2021-09-06 | Submittal Number: 05 75 00-54.0 From: MIKE SOLFELT Final Due Date: 09/13/21 Subject: DECORATIVE METAL SAMPLE WARRANTY Description: Spec Section: 05 75 00 - DECORATIVE FORMED METAL Status: OPEN | Info Exchange
| 18853 | Responded and Closed | Approved as Noted | 2021-09-10 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | SUBMIT IN THE FINAL O&M MANUALS PER CLOSEOUT PROCEDURES | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-30 02:00 |  | 05 75 00-54 Decorative Metal Sample Warranty.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-30 02:00 |  | 05 75 00-54 Decorative Metal Sample Warranty.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-09-10 |  | 05 75 00-54 Decorative Metal Sample Warranty_MAM_POP.pdf
06 10 53-009-00 | 06 10 53 - MISCELLANEOUS ROUGH CARPENTRY | 06 10 53-009-00 Exterior Roof Blocking Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-10 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-24 | 2021-06-23 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-06-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13481 | Received | For Review | 2021-06-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-24 | Submittal Number: 06 10 53-9.0 From: BROOKE BURCHAM Final Due Date: 06/23/21 Subject: EXTERIOR ROOF BLOCKING PRODUCT DATA Description: EXTERIOR ROOF BLOCKING PRODUCT DATA Spec Section: 06 10 53 - MISCELLANEOUS ROUGH CARPENTRY Status: OPEN | Info Exchange
| 17434 | Forwarded | For Review | 2021-06-10 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-17 | Submittal Number: 06 10 53-9.0 From: BROOKE BURCHAM Final Due Date: 06/23/21 Subject: EXTERIOR ROOF BLOCKING PRODUCT DATA Description: EXTERIOR ROOF BLOCKING PRODUCT DATA Spec Section: 06 10 53 - MISCELLANEOUS ROUGH CARPENTRY Status: OPEN | Info Exchange
| 17639 | Responded and Closed | Approved as Noted | 2021-06-23 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-10 |  | 061053-0009-0 Exterior Roof Blocking Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-10 |  | 061053-0009-0 Exterior Roof Blocking Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-23 |  | 061053-0009-0 Exterior Roof Blocking Product Data-POP.pdf
06 16 00-002-00 | 06 16 00 - SHEATHING | 06 16 00-002-00 SHEATHING - Product Data - Glass-Mat Gypsum Wall Sheathing & Fasteners | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-23 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-07 | 2020-05-04 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05515 | Received | For Review | 2020-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-05-07 | Submittal Number: 06 16 00-2.0 From: JES PELKEY Final Due Date: 05/04/20 Subject: SHEATHING - PRODUCT DATA - GLASS-MAT GYPSUM WALL SHEATHING & FASTENERS Description: Spec Section: 06 16 00 - SHEATHING Status: OPEN | Info Exchange
| 07474 | Forwarded | For Review | 2020-04-23 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-04-30 | Submittal Number: 06 16 00-2.0 From: JES PELKEY Final Due Date: 05/04/20 Subject: SHEATHING - PRODUCT DATA - GLASS-MAT GYPSUM WALL SHEATHING & FASTENERS Description: Spec Section: 06 16 00 - SHEATHING Status: OPEN | Info Exchange
| 07729 | Responded and Closed | Approved | 2020-05-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-23 |  | 061000-0001-0 SHEATHING - Product Data (Glass-Mat Gypsum Wall Sheathing & Fasteners)-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-23 |  | 06 16 00-2.0 SHEATHING - Product Data (Glass-Mat Gypsum Wall Sheathing & Fasteners)-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-04-23 |  | 061000-0001-0 SHEATHING - Product Data (Glass-Mat Gypsum Wall Sheathing & Fasteners)-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-05-04 |  | 06 16 00-2.0 SHEATHING - Product Data (Glass-Mat Gypsum Wall Sheathing & Fasteners)-MAM-POP.pdf
06 16 00-007-00 | 06 16 00 - SHEATHING | 06 16 00-007-00 SHEATHING - Evaluation Reports | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-17 | 2021-05-11 | 9 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-05-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12883 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-05-17 | Submittal Number: 06 16 00-7.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: SHEATHING - EVALUATION REPORTS Description: EVALUATION REPORTS : FOR THE FOLLOWING, FROM ICC-ES: 1. AIR-BARRIER AND WATER-RESISTANT GLASS-MAT GYPSUM SHEATHING. Spec Section: 06 16 00 - SHEATHING Status: OPEN | Info Exchange
| 16665 | Forwarded | For Review | 2021-05-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-10 | Submittal Number: 06 16 00-7.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: SHEATHING - EVALUATION REPORTS Description: EVALUATION REPORTS : FOR THE FOLLOWING, FROM ICC-ES: 1. AIR-BARRIER AND WATER-RESISTANT GLASS-MAT GYPSUM SHEATHING. Spec Section: 06 16 00 - SHEATHING Status: OPEN | Info Exchange
| 16668 | Forwarded | For Review | 2021-05-02 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-10 | Submittal Number: 06 16 00-7.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: SHEATHING - EVALUATION REPORTS Description: EVALUATION REPORTS : FOR THE FOLLOWING, FROM ICC-ES: 1. AIR-BARRIER AND WATER-RESISTANT GLASS-MAT GYPSUM SHEATHING. Spec Section: 06 16 00 - SHEATHING Status: OPEN | Info Exchange
| 16756 | Forwarded | For Review | 2021-05-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-12 | Submittal Number: 06 16 00-7.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: SHEATHING - EVALUATION REPORTS Description: EVALUATION REPORTS : FOR THE FOLLOWING, FROM ICC-ES: 1. AIR-BARRIER AND WATER-RESISTANT GLASS-MAT GYPSUM SHEATHING. Spec Section: 06 16 00 - SHEATHING Status: OPEN | Info Exchange
| 16887 | Responded and Closed | Approved | 2021-05-11 | Tom Usher (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-30 |  | Submittal 06 16 00-7 Revision 0 SHEATHING - Evaluation Reports_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-30 |  | Submittal 06 16 00-7 Revision 0 SHEATHING - Evaluation Reports_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-30 |  | Submittal 06 16 00-7 Revision 0 SHEATHING - Evaluation Reports_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-30 |  | Submittal 06 16 00-7 Revision 0 SHEATHING - Evaluation Reports_MAM Reviewed.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2021-05-11 |  | Submittal 06 16 00-7 Revision 0 SHEATHING - Evaluation Reports_MAM _POP.pdf
06 20 23-001-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-001-00 Millwork Hardware Package 1- Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-28 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-11 | 2020-08-06 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07178 | Received | For Review | 2020-07-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-08-11 | Submittal Number: 06 20 23-1.0 From: JOSH BROUSSARD Final Due Date: 08/11/20 Subject: MILLWORK HARDWARE PACKAGE 1- BASE BUILDING Description: THE ATTACHED HARDWARE SUBMITTAL INCLUDES PRODUCT DATA MILLWORK HARDWARE THAT APPLIES ACROSS MULTIPLE SPEC SECTIONS IN THE BASE BUILDING AREAS. Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 09581 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-08-04 | Submittal Number: 06 20 23-1.0 From: JOSH BROUSSARD Final Due Date: 08/11/20 Subject: MILLWORK HARDWARE PACKAGE 1- BASE BUILDING Description: THE ATTACHED HARDWARE SUBMITTAL INCLUDES PRODUCT DATA MILLWORK HARDWARE THAT APPLIES ACROSS MULTIPLE SPEC SECTIONS IN THE BASE BUILDING AREAS. Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 07432 | Review Response | Approved as Noted | 2020-08-06 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached markup. | Info Exchange
| 09898 | Responded and Closed | Approved as Noted | 2020-08-06 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached markup. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-28 |  | 06 20 23-1.0 Millwork Hardware Package 1- Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-28 |  | 06 20 23-1.0 Millwork Hardware Package 1- Base Building.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-06 |  | 06 20 23-1.0 Millwork Hardware Package 1- Base Building_POP_Final.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-28 |  | 06 20 23-1.0 Millwork Hardware Package 1- Base Building.pdf
06 20 23-002-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-002-00 Custom Bench Shop Drawings - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-05 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-19 | 2020-06-23 | 19 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-06-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06248 | Received | For Review | 2020-06-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-06-19 | Submittal Number: 06 20 23-2.0 From: JOSH BROUSSARD Final Due Date: 06/19/20 Subject: CUSTOM BENCH SHOP DRAWINGS - BASE BUILDING Description: SHOP DRAWINGS: FOR BASE BUILDING CUSTOM WOOD ADA BENCHES FOUND IN MISCELLANEOUS SPACES ON THE EVENT LEVEL. Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 08433 | Forwarded | For Review | 2020-06-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-06-15 | Submittal Number: 06 20 23-2.0 From: JOSH BROUSSARD Final Due Date: 06/19/20 Subject: CUSTOM BENCH SHOP DRAWINGS - BASE BUILDING Description: SHOP DRAWINGS: FOR BASE BUILDING CUSTOM WOOD ADA BENCHES FOUND IN MISCELLANEOUS SPACES ON THE EVENT LEVEL. Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 08831 | Responded and Closed | Approved as Noted | 2020-06-23 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 06 20 23-2.0 Custom Bench Shop Drawings - Base Building.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 06 20 23-2.0 Custom Bench Shop Drawings - Base Building(1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 06 20 23-2.0 Custom Bench Shop Drawings - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 06 20 23-2.0 Custom Bench Shop Drawings - Base Building(1).pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-06-23 |  | 06 20 23-2.0 Custom Bench Shop Drawings - Base Building_POP Final.pdf
06 20 23-003-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-003-00 Substrate & Hardwood Product Data - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-20 | 2020-07-07 | 2 |  | Record Copies; Transfers; Submittals | 06 20 23-003-00-01 - 06 20 23-003-00 Substrate & Hardwood Product Data - Base Building | 2 |  | 2020-07-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06764 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 06 20 23-3.0 From: JOSH BROUSSARD Final Due Date: 07/17/20 Subject: SUBSTRATE & HARDWOOD PRODUCT DATA - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 09092 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-07-13 | Submittal Number: 06 20 23-3.0 From: JOSH BROUSSARD Final Due Date: 07/17/20 Subject: SUBSTRATE & HARDWOOD PRODUCT DATA - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 06833 | Review Response | Approved as Noted/Resubmit | 2020-07-07 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to submittal markup | Mail
| 09166 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-07 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to submittal markup. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-03 |  | 06 20 23-3.0 Substrate & Hardwood Product Data - Base Bldg.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-03 |  | 06 20 23-3.0 Substrate & Hardwood Product Data - Base Bldg.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-07-07 |  | 06 20 23-3.0 Substrate & Hardwood Product Data - Base Bldg_POP Final.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-03 |  | 06 20 23-3.0 Substrate & Hardwood Product Data - Base Bldg.pdf
06 20 23-003-00-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-003-00 Substrate & Hardwood Product Data - Base Building | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 20 23-003-00 - 06 20 23-003-00 Substrate & Hardwood Product Data - Base Building | -1 | 2020-07-21
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-03 |  | 06 20 23-3.0 Substrate & Hardwood Product Data - Base Bldg.pdf
06 20 23-004-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-004-00 Millwork Hardware Product Data- Package 2 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-25 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-09 07:00 | 2020-09-09 | 16 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07721 | Received | For Review | 2020-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-09 07:00 | Submittal Number: 06 20 23-4.0 From: JOSH BROUSSARD Final Due Date: 09/07/20 Subject: MILLWORK HARDWARE PRODUCT DATA- PACKAGE 2 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10274 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-31 | Submittal Number: 06 20 23-4.0 From: JOSH BROUSSARD Final Due Date: 09/07/20 Subject: MILLWORK HARDWARE PRODUCT DATA- PACKAGE 2 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 08005 | Review Response | Approved as Noted | 2020-09-09 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached review. | Info Exchange
| 10640 | Responded and Closed | Approved as Noted | 2020-09-09 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 062023-004 Millwork Hardware Product Data - PKG 2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 062023-004 Millwork Hardware Product Data - PKG 2.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-09 |  | 062023-004 Millwork Hardware Product Data - PKG 2_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-24 |  | 062023-004 Millwork Hardware Product Data - PKG 2.pdf
06 20 23-005-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-005-00 Concession & Bar Shop Drawings 1 - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-30 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-13 | 2020-08-17 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-08-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07260 | Received | For Review | 2020-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-08-13 | Submittal Number: 06 20 23-5.0 From: JOSH BROUSSARD Final Due Date: 07/24/20 Subject: CONCESSION & BAR SHOP DRAWINGS 1 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 09672 | Forwarded | For Review | 2020-07-30 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-08-06 | Submittal Number: 06 20 23-5.0 From: JOSH BROUSSARD Final Due Date: 07/24/20 Subject: CONCESSION & BAR SHOP DRAWINGS 1 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 07559 | Review Response | Approved as Noted | 2020-08-17 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | SEE ATTACHED SUBMITTAL REVIEW | Info Exchange
| 10063 | Responded and Closed | Approved as Noted | 2020-08-17 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED SUBMITTAL REVIEW | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-29 |  | 062023-005 Concession and BAr Shop Drawings 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-29 |  | 062023-005 Concession and BAr Shop Drawings 1.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-17 |  | 062023-005 Concession and BAr Shop Drawings POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-29 |  | 062023-005 Concession and BAr Shop Drawings 1.pdf
06 20 23-006-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-006-00 Concession & Bar Shop Drawings 2 - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-29 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-12 | 2020-08-16 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-08-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07238 | Received | For Review | 2020-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-08-12 | Submittal Number: 06 20 23-6.0 From: JOSH BROUSSARD Final Due Date: 08/05/20 Subject: CONCESSION & BAR SHOP DRAWINGS 2 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 09652 | Forwarded | For Review | 2020-07-29 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-08-05 | Submittal Number: 06 20 23-6.0 From: JOSH BROUSSARD Final Due Date: 08/05/20 Subject: CONCESSION & BAR SHOP DRAWINGS 2 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 07558 | Review Response | Revise and Resubmit | 2020-08-16 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached submittal review. | Info Exchange
| 10061 | Responded and Closed | Revise and Resubmit | 2020-08-16 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-29 |  | 062023-006 Concession and Bar Shop Drawings 2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-29 |  | 062023-006 Concession and Bar Shop Drawings 2.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-16 |  | 062023-006 Concession and Bar Shop Drawings 2 POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-29 |  | 062023-006 Concession and Bar Shop Drawings 2.pdf
06 20 23-006-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-006-01 Concession & Bar Shop Drawings 2 - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-29 | 2020-09-29 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08100 | Received | For Review | 2020-09-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-29 | Submittal Number: 06 20 23-6.1 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: CONCESSION & BAR SHOP DRAWINGS 2 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10766 | Forwarded | For Review | 2020-09-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-21 | Submittal Number: 06 20 23-6.1 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: CONCESSION & BAR SHOP DRAWINGS 2 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 08422 | Review Response | Approved as Noted | 2020-09-29 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | See attached submittal review. | Info Exchange
| 11159 | Responded and Closed | Approved as Noted | 2020-09-29 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-14 |  | 062023-006.1 Concession and Bar Shop Drawings 2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-14 |  | 062023-006.1 Concession and Bar Shop Drawings 2.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-29 |  | 062023-006.1 Concession and Bar Shop Drawings 2_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-14 |  | 062023-006.1 Concession and Bar Shop Drawings 2.pdf
06 20 23-008-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-008-00 Concession & Bar Shop Drawings 3 - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-13 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-27 | 2020-08-27 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07527 | Received | For Review | 2020-08-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-08-27 | Submittal Number: 06 20 23-8.0 From: MIKE SOLFELT Final Due Date: 08/26/20 Subject: CONCESSION & BAR SHOP DRAWINGS 3 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10023 | Forwarded | For Review | 2020-08-13 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-20 | Submittal Number: 06 20 23-8.0 From: MIKE SOLFELT Final Due Date: 08/26/20 Subject: CONCESSION & BAR SHOP DRAWINGS 3 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 07791 | Review Response | Approved as Noted/Resubmit | 2020-08-27 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  |  | Info Exchange
| 10370 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-27 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached review, resubmit only marked items. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-12 |  | 062023-008 Concession and Bar Shop Drawings 3.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-12 |  | 062023-008 Concession and Bar Shop Drawings 3.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-27 |  | 062023-008 Concession and Bar Shop Drawings 3 POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-12 |  | 062023-008 Concession and Bar Shop Drawings 3.pdf
06 20 23-008-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-008-01 Concession & Bar Shop Drawings 3 - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-19 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-02 | 2021-02-04 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10760 | Received | For Review | 2021-01-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-02 | Submittal Number: 06 20 23-8.1 From: MIKE SOLFELT Final Due Date: 01/13/21 Subject: CONCESSION & BAR SHOP DRAWINGS 3 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13995 | Forwarded | For Review | 2021-01-19 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-26 | Submittal Number: 06 20 23-8.1 From: MIKE SOLFELT Final Due Date: 01/13/21 Subject: CONCESSION & BAR SHOP DRAWINGS 3 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11183 | Review Response | Approved as Noted | 2021-02-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14489 | Responded and Closed | Approved as Noted | 2021-02-04 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-19 |  | 062023-008.1 Craft Beer Bars Resubmit.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-19 |  | 062023-008.1 Craft Beer Bars Resubmit.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-04 |  | 062023-008.1 Craft Beer Bars Resubmit_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-19 |  | 062023-008.1 Craft Beer Bars Resubmit.pdf
06 20 23-009-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-009-00 Concession & Bar Shop Drawings 4 - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-10 07:00 | 2020-09-09 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07757 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-10 07:00 | Submittal Number: 06 20 23-9.0 From: JOSH BROUSSARD Final Due Date: 08/19/20 Subject: CONCESSION & BAR SHOP DRAWINGS 4 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10328 | Forwarded | For Review | 2020-08-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 06 20 23-9.0 From: JOSH BROUSSARD Final Due Date: 08/19/20 Subject: CONCESSION & BAR SHOP DRAWINGS 4 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 08014 | Review Response | Revise and Resubmit | 2020-09-09 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | See attached review. | Info Exchange
| 10659 | Responded and Closed | Revise and Resubmit | 2020-09-09 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 062023-009 Concession and Bar Shop Drawings 4.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-26 |  | 062023-009 Concession and Bar Shop Drawings 4.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-09 |  | 062023-009 Concession and Bar Shop Drawings POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-26 |  | 062023-009 Concession and Bar Shop Drawings 4.pdf
06 20 23-009-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-009-01 Concession & Bar Shop Drawings 4 - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-14 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-28 | 2020-10-28 | 15 |  | Record Copies; Transfers; Submittals | 06 20 23-009-01-01 - 06 20 23-009-01 Concession & Bar Shop Drawings 4 - Base Building | 15 |  | 2020-10-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08787 | Received | For Review | 2020-10-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-28 | Submittal Number: 06 20 23-9.1 From: MIKE SOLFELT Final Due Date: 10/09/20 Subject: CONCESSION & BAR SHOP DRAWINGS 4 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11617 | Forwarded | For Review | 2020-10-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-21 | Submittal Number: 06 20 23-9.1 From: MIKE SOLFELT Final Due Date: 10/09/20 Subject: CONCESSION & BAR SHOP DRAWINGS 4 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 09065 | Review Response | Approved as Noted/Resubmit | 2020-10-28 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review and comments. Resubmit missing detail sheet for review, no other exceptions. | Info Exchange
| 11955 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-28 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review and comments. Resubmit missing detail sheet for review, no other exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-14 |  | 062023-009.1 Concession and Bar Shop Drawings 4 rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-14 |  | 062023-009.1 Concession and Bar Shop Drawings 4 rev 1.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-28 |  | 062023-009.1 Concession and Bar Shop Drawings 4 rev 1_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-14 |  | 062023-009.1 Concession and Bar Shop Drawings 4 rev 1.pdf
06 20 23-009-01-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-009-01 Concession & Bar Shop Drawings 4 - Base Building | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 20 23-009-01 - 06 20 23-009-01 Concession & Bar Shop Drawings 4 - Base Building | -1 | 2020-11-11
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-14 |  | 062023-009.1 Concession and Bar Shop Drawings 4 rev 1.pdf
06 20 23-010-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-010-00 Tunnel Club B1 Casework Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-10 07:00 | 2020-09-10 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07766 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-10 07:00 | Submittal Number: 06 20 23-10.0 From: JOSH BROUSSARD Final Due Date: 08/20/20 Subject: TUNNEL CLUB B1 CASEWORK SHOP DRAWINGS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10338 | Forwarded | For Review | 2020-08-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 06 20 23-10.0 From: JOSH BROUSSARD Final Due Date: 08/20/20 Subject: TUNNEL CLUB B1 CASEWORK SHOP DRAWINGS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 08038 | Review Response | Revise and Resubmit | 2020-09-10 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  |  | Info Exchange
| 10692 | Responded and Closed | Revise and Resubmit | 2020-09-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 062023-0010 Tunnel Club B1 Casework Shop Drawings (Mock-Up Club).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-26 |  | 062023-0010 Tunnel Club B1 Casework Shop Drawings (Mock-Up Club).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-10 |  | 062023-0010 Tunnel Club B1 Casework Shop Drawings (Mock-Up Club)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-26 |  | 062023-0010 Tunnel Club B1 Casework Shop Drawings (Mock-Up Club).pdf
06 20 23-010-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-010-01 Tunnel Club B1 Casework Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-17 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-01 | 2020-09-24 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08166 | Received | For Review | 2020-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-01 | Submittal Number: 06 20 23-10.1 From: MIKE SOLFELT Final Due Date: 10/02/20 Subject: TUNNEL CLUB B1 CASEWORK SHOP DRAWINGS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10840 | Forwarded | For Review | 2020-09-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-24 | Submittal Number: 06 20 23-10.1 From: MIKE SOLFELT Final Due Date: 10/02/20 Subject: TUNNEL CLUB B1 CASEWORK SHOP DRAWINGS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11042 | Responded and Closed | Approved as Noted | 2020-09-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | See attached submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-17 |  | 062023-0010.1 Tunnel Club B1 Casework Shop Drawings (Mock-Up Club).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-17 |  | 062023-0010.1 Tunnel Club B1 Casework Shop Drawings (Mock-Up Club).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-24 02:00 |  | 062023-0010.1 Tunnel Club B1 Casework Shop Drawings (Mock-Up Club)_POP.pdf
06 20 23-015-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-015-00 Stick Racks - Locker Rooms | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-19 | 2020-10-13 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08546 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 06 20 23-15.0 From: MIKE SOLFELT Final Due Date: 10/19/20 Subject: STICK RACKS - LOCKER ROOMS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11308 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-12 | Submittal Number: 06 20 23-15.0 From: MIKE SOLFELT Final Due Date: 10/19/20 Subject: STICK RACKS - LOCKER ROOMS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 08727 | Review Response | Revise and Resubmit | 2020-10-13 | Kelsea Conkright (Populous) | Shaina Burris (Populous) |  |  | Info Exchange
| 11533 | Responded and Closed | Revise and Resubmit | 2020-10-13 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 062023-015 Stick Racks.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 062023-015 Stick Racks.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-10-13 |  | 062023-015 Stick Racks_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-05 |  | 062023-015 Stick Racks.pdf
06 20 23-015-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-015-01 Stick Racks - Locker Rooms | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-02-22 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-02-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11415 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-03-01 | Submittal Number: 06 20 23-15.1 From: MIKE SOLFELT Final Due Date: 03/01/21 Subject: STICK RACKS - LOCKER ROOMS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14782 | Forwarded | For Review | 2021-02-15 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 06 20 23-15.1 From: MIKE SOLFELT Final Due Date: 03/01/21 Subject: STICK RACKS - LOCKER ROOMS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11579 | Review Response | Revise and Resubmit | 2021-02-22 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15001 | Responded and Closed | Revise and Resubmit | 2021-02-22 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| 15004 | Reopened | Additional Information | 2021-02-22 14:44 | Kelsea Conkright (Populous)
| 11583 | Review Response | Revise and Resubmit | 2021-02-22 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15005 | Responded and Closed | Revise and Resubmit | 2021-02-22 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 062023-015.1-Stick Racks CCD084.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-15 |  | 062023-015.1-Stick Racks CCD084.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-22 |  | 062023-015.1-Stick Racks CCD084_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-02-15 |  | 062023-015.1-Stick Racks CCD084.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-22 |  | 062023-015.1-Stick Racks CCD084_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-02-22 |  | 062023-015.1-Stick Racks CCD084_POP.pdf
06 20 23-015-02 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-015-02 Stick Racks - Locker Rooms | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-12 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-26 | 2021-03-29 | 18 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11961 | Received | For Review | 2021-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-03-26 | Submittal Number: 06 20 23-15.2 From: MIKE SOLFELT Final Due Date: 03/22/21 Subject: STICK RACKS - LOCKER ROOMS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 15490 | Forwarded | For Review | 2021-03-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-18 | Submittal Number: 06 20 23-15.2 From: MIKE SOLFELT Final Due Date: 03/22/21 Subject: STICK RACKS - LOCKER ROOMS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12079 | Review Response | Approved as Noted | 2021-03-17 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15638 | Responded and Closed | Approved as Noted | 2021-03-17 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| 15931 | Reopened | Additional Information | 2021-03-29 21:59 | Kelsea Conkright (Populous) |  |  | Error in the Briq system. Resending original attachment again.
| 15932 | Responded and Closed | Approved as Noted | 2021-03-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-11 |  | 062023-015.2 - Stick Racks.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-11 |  | 062023-015.2 - Stick Racks.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-17 |  | 062023-015.1-Stick Racks CCD084_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-03-11 |  | 062023-015.2 - Stick Racks.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-17 |  | 062023-015.2 - Stick Racks_POP.pdf
06 20 23-016-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-016-00 Millwork Hardware Samples Package 1 - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-10 07:00 | 2020-09-14 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07765 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-10 07:00 | Submittal Number: 06 20 23-16.0 From: MIKE SOLFELT Final Due Date: 09/08/20 Subject: MILLWORK HARDWARE SAMPLES PACKAGE 1 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10337 | Forwarded | For Review | 2020-08-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 06 20 23-16.0 From: MIKE SOLFELT Final Due Date: 09/08/20 Subject: MILLWORK HARDWARE SAMPLES PACKAGE 1 - BASE BUILDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 08071 | Review Response | Approved as Noted | 2020-09-14 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  |  | Info Exchange
| 10740 | Responded and Closed | Approved as Noted | 2020-09-14 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 062023-016 Millwork Hardware Sample Pkg 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-26 |  | 062023-016 Millwork Hardware Sample Pkg 1.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-14 |  | 062023-016 Millwork Hardware Sample Pkg 1 POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-26 |  | 062023-016 Millwork Hardware Sample Pkg 1.pdf
06 20 23-017-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-017-00 NHL Locker Benches | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-02 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-16 | 2020-10-08 | 7 |  | Record Copies; Transfers; Submittals | 06 20 23-017-00-01 - 06 20 23-017-00 NHL Locker Benches | 8 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08503 | Received | For Review | 2020-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-16 | Submittal Number: 06 20 23-17.0 From: MIKE SOLFELT Final Due Date: 09/07/20 Subject: NHL LOCKER BENCHES Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11249 | Forwarded | For Review | 2020-10-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-08 | Submittal Number: 06 20 23-17.0 From: MIKE SOLFELT Final Due Date: 09/07/20 Subject: NHL LOCKER BENCHES Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 08673 | Review Response | Approved as Noted/Resubmit | 2020-10-08 | Kelsea Conkright (Populous) | Shaina Burris (Populous) |  |  | Info Exchange
| 11455 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-08 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 062023-017 NHL Locker Benches.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-01 |  | 062023-017 NHL Locker Benches.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-10-08 |  | 062023-017 NHL Locker Benches_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-01 |  | 062023-017 NHL Locker Benches.pdf
06 20 23-017-00-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-017-00 NHL Locker Benches | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 20 23-017-00 - 06 20 23-017-00 NHL Locker Benches | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 062023-017 NHL Locker Benches.pdf
06 20 23-018-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-018-00 Main Concourse Club For Record | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-08 | Responded and Closed - No Action Taken or Required |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-22 | 2020-12-22 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10003 | Received | For Review | 2020-12-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-12-22 | Submittal Number: 06 20 23-18.0 From: MIKE SOLFELT Final Due Date: 12/21/20 Subject: MAIN CONCOURSE CLUB FOR RECORD Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13091 | Forwarded | For Review | 2020-12-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-15 | Submittal Number: 06 20 23-18.0 From: MIKE SOLFELT Final Due Date: 12/21/20 Subject: MAIN CONCOURSE CLUB FOR RECORD Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13477 | Responded and Closed | No Action Taken or Required | 2020-12-22 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Received for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 062023-018 Main Concourse Club For Record.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-07 |  | 062023-018 Main Concourse Club For Record.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-22 02:00 |  | 062023-018 Main Concourse Club For Record_POP.pdf
06 20 23-019-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-019-00 Oyster Bar - CCD84 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-21 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10398 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-19 08:00 | Submittal Number: 06 20 23-19.0 From: MIKE SOLFELT Final Due Date: 01/12/21 Subject: OYSTER BAR - CCD84 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13582 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 06 20 23-19.0 From: MIKE SOLFELT Final Due Date: 01/12/21 Subject: OYSTER BAR - CCD84 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10889 | Review Response | Approved as Noted | 2021-01-21 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14140 | Responded and Closed | Approved as Noted | 2021-01-21 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-30 |  | 062023-019 Oyster Bar CCD084.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-30 |  | 062023-019 Oyster Bar CCD084.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-21 |  | 062023-019 Oyster Bar CCD084_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-30 |  | 062023-019 Oyster Bar CCD084.pdf
06 20 23-020-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-020-00 West Concourse Club Pkg. 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-26 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-09 | 2020-11-11 | 17 |  | Record Copies; Transfers; Submittals | 06 20 23-020-00-01 - 06 20 23-020-00 West Concourse Club Pkg. 1 | 17 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08986 | Received | For Review | 2020-10-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-09 | Submittal Number: 06 20 23-20.0 From: MIKE SOLFELT Final Due Date: 11/20/20 Subject: WEST CONCOURSE CLUB PKG. 1 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11858 | Forwarded | For Review | 2020-10-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-02 | Submittal Number: 06 20 23-20.0 From: MIKE SOLFELT Final Due Date: 11/20/20 Subject: WEST CONCOURSE CLUB PKG. 1 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 09353 | Review Response | Approved as Noted/Resubmit | 2020-11-11 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Approved as noted: Isek shop drawings - refer to comments marked on sheets Resubmit (when TT has provided structural direction- not reviewed per discussion w/ Mike Solfelt): 1.The T-Bar Display shelving and ceiling from Fish Construction via Isek 2.The lower bar display shelving and ceiling with structural details from Fish Construction via Isek | Info Exchange
| 12342 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-11 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Approved as noted: Isek shop drawings - refer to comments marked on sheets Resubmit (when TT has provided structural direction- not reviewed per discussion w/ Mike Solfelt): 1.The T-Bar Display shelving and ceiling from Fish Construction via Isek 2.The lower bar display shelving and ceiling with structural details from Fish Construction via Isek | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-26 |  | 062023-020 West Concourse Club.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-26 |  | 062023-020 West Concourse Club.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-11 |  | 062023-020 West Concourse Club_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-26 |  | 062023-020 West Concourse Club.pdf
06 20 23-020-00-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-020-00 West Concourse Club Pkg. 1 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 20 23-020-00 - 06 20 23-020-00 West Concourse Club Pkg. 1 | -1 | 2020-11-25
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-26 |  | 062023-020 West Concourse Club.pdf
06 20 23-022-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-022-00 Metropolitan Club pkg. 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-02 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-16 | 2020-10-18 | 17 |  | Record Copies; Transfers; Submittals | 06 20 23-022-00-01 - 06 20 23-022-00 Metropolitan Club pkg. 1 | 18 |  | 2020-10-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08495 | Received | For Review | 2020-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-16 | Submittal Number: 06 20 23-22.0 From: MIKE SOLFELT Final Due Date: 10/02/20 Subject: METROPOLITAN CLUB PKG. 1 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11240 | Forwarded | For Review | 2020-10-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-08 | Submittal Number: 06 20 23-22.0 From: MIKE SOLFELT Final Due Date: 10/02/20 Subject: METROPOLITAN CLUB PKG. 1 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 08836 | Review Response | Revise and Resubmit | 2020-10-18 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11676 | Responded and Closed | Revise and Resubmit | 2020-10-18 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 062023-022 Metropolitan Club Pkg 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-01 |  | 062023-022 Metropolitan Club Pkg 1.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-18 |  | 062023-022 Metropolitan Club Pkg 1_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-01 |  | 062023-022 Metropolitan Club Pkg 1.pdf
06 20 23-022-00-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-022-00 Metropolitan Club pkg. 1 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 20 23-022-00 - 06 20 23-022-00 Metropolitan Club pkg. 1 | -1 | 2020-11-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 062023-022 Metropolitan Club Pkg 1.pdf
06 20 23-023-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-023-00 Metropolitan Club pkg. 2 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-27 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-01-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10397 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-19 08:00 | Submittal Number: 06 20 23-23.0 From: MIKE SOLFELT Final Due Date: 01/13/21 Subject: METROPOLITAN CLUB PKG. 2 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13581 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 06 20 23-23.0 From: MIKE SOLFELT Final Due Date: 01/13/21 Subject: METROPOLITAN CLUB PKG. 2 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10999 | Review Response | Approved as Noted | 2021-01-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14285 | Responded and Closed | Approved as Noted | 2021-01-27 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-30 |  | 062023-023 Metropolitan Club Pkg 2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-30 |  | 062023-023 Metropolitan Club Pkg 2.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-27 |  | 062023-023 Metropolitan Club Pkg 2_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-30 |  | 062023-023 Metropolitan Club Pkg 2.pdf
06 20 23-024-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-024-00 Space Needle Club Pkg. 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-23 07:00 | 2020-10-26 | 27 |  | Record Copies; Transfers; Submittals | 06 20 23-024-00-01 - 06 20 23-024-00 Space Needle Club Pkg. 1 | 27 |  | 2020-10-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08436 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-23 07:00 | Submittal Number: 06 20 23-24.0 From: MIKE SOLFELT Final Due Date: 10/16/20 Subject: SPACE NEEDLE CLUB PKG. 1 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11177 | Forwarded | For Review | 2020-09-30 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-07 | Submittal Number: 06 20 23-24.0 From: MIKE SOLFELT Final Due Date: 10/16/20 Subject: SPACE NEEDLE CLUB PKG. 1 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 08992 | Review Response | Approved as Noted/Resubmit | 2020-10-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11865 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-29 |  | 06 20 23-024 Space Needle Club Pkg. 1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-29 |  | 06 20 23-024 Space Needle Club Pkg. 1.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-26 |  | 06 20 23-024 Space Needle Club Pkg. 1_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-29 |  | 06 20 23-024 Space Needle Club Pkg. 1.pdf
06 20 23-024-00-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-024-00 Space Needle Club Pkg. 1 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 20 23-024-00 - 06 20 23-024-00 Space Needle Club Pkg. 1 | -1 | 2020-11-09
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-29 |  | 06 20 23-024 Space Needle Club Pkg. 1.pdf
06 20 23-025-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-025-00 Space Needle Club Pkg. 2 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-12 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-30 08:00 | 2020-11-30 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-11-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09396 | Received | For Review | 2020-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-30 08:00 | Submittal Number: 06 20 23-25.0 From: MIKE SOLFELT Final Due Date: 11/26/20 Subject: SPACE NEEDLE CLUB PKG. 2 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12399 | Forwarded | For Review | 2020-11-12 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-19 | Submittal Number: 06 20 23-25.0 From: MIKE SOLFELT Final Due Date: 11/26/20 Subject: SPACE NEEDLE CLUB PKG. 2 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 09768 | Review Response | Approved as Noted | 2020-11-30 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12848 | Responded and Closed | Approved as Noted | 2020-11-30 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-12 |  | 062023-025 Space Needle Club Pkg. 2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-12 |  | 062023-025 Space Needle Club Pkg. 2.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-30 |  | 062023-025 Space Needle Club Pkg. 2_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-12 |  | 062023-025 Space Needle Club Pkg. 2.pdf
06 20 23-026-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-026-00 Mount Baker Paneling & Die-Wall Cladding | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-18 | 2021-01-12 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-01-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10396 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-18 | Submittal Number: 06 20 23-26.0 From: MIKE SOLFELT Final Due Date: 01/06/21 Subject: MOUNT BAKER PANELING & DIE-WALL CLADDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13580 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 06 20 23-26.0 From: MIKE SOLFELT Final Due Date: 01/06/21 Subject: MOUNT BAKER PANELING & DIE-WALL CLADDING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13871 | Responded and Closed | Approved as Noted | 2021-01-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments 1. COORDINATE ALL COMMENTS ON SUBMITTALS 06 20 23-029, 030, 031, 034 2. FIELD VERIFY ALL DIMENSIONS. 3. REFER TO ROCKWELL GROUP FINAL COMMENTS 4. SUBMITTAL REVIEWED FOR DIE-WALL CLADDING ONLY AS INDICATED IN SUBMITTAL TITLE | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-30 |  | 06 20 23-26 Mount Baker Paneling and Die-Wall Cladding.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-30 |  | 06 20 23-26 Mount Baker Paneling and Die-Wall Cladding.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-12 |  | 06 20 23-26 Mount Baker Paneling and Die-Wall Cladding_POP.pdf
06 20 23-027-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-027-00 Suite Level Restrooms and Base | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-09 | 2020-11-20 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08985 | Received | For Review | 2020-10-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-09 | Submittal Number: 06 20 23-27.0 From: MIKE SOLFELT Final Due Date: 11/09/20 Subject: SUITE LEVEL RESTROOMS AND BASE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11856 | Forwarded | For Review | 2020-10-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-02 | Submittal Number: 06 20 23-27.0 From: MIKE SOLFELT Final Due Date: 11/09/20 Subject: SUITE LEVEL RESTROOMS AND BASE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12687 | Responded and Closed | Approved as Noted | 2020-11-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS AND COORDINATE ANY ADDITIONAL COMMENTS PROVIDED BY ROCKWELL GROUP | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-26 |  | 062023-027 Suite Level Wood Base and Hand Rail.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-26 |  | 062023-027 Suite Level Wood Base and Hand Rail.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-11-20 |  | 062023-027 Suite Level Wood Base and Hand Rail_POP.pdf
06 20 23-029-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-029-00 Mount Baker Club - Pizza | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-29 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-12 | 2020-11-20 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09099 | Received | For Review | 2020-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-12 | Submittal Number: 06 20 23-29.0 From: MIKE SOLFELT Final Due Date: 11/12/20 Subject: MOUNT BAKER CLUB - PIZZA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12005 | Forwarded | For Review | 2020-10-29 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-05 | Submittal Number: 06 20 23-29.0 From: MIKE SOLFELT Final Due Date: 11/12/20 Subject: MOUNT BAKER CLUB - PIZZA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12669 | Responded and Closed | Approved as Noted | 2020-11-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-29 |  | 06 20 23-029 Mount Baker - Pizza.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-29 |  | 06 20 23-029 Mount Baker - Pizza.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-11-20 |  | 06 20 23-029 Mount Baker - Pizza - RG RESPONSE_POP.pdf
06 20 23-030-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-030-00 Mount Baker - Mean Sandwich | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-28 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-11 | 2020-11-20 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09066 | Received | For Review | 2020-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-11 | Submittal Number: 06 20 23-30.0 From: MIKE SOLFELT Final Due Date: 11/06/20 Subject: MOUNT BAKER - MEAN SANDWICH Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11956 | Forwarded | For Review | 2020-10-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-04 | Submittal Number: 06 20 23-30.0 From: MIKE SOLFELT Final Due Date: 11/06/20 Subject: MOUNT BAKER - MEAN SANDWICH Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12671 | Responded and Closed | Approved as Noted | 2020-11-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-28 |  | 062023-030 Mount Baker Mean Sandwhich.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-28 |  | 062023-030 Mount Baker Mean Sandwhich.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-11-20 |  | 062023-030 Mount Baker Mean Sandwhich - RG RESPONSE_POP.pdf
06 20 23-031-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-031-00 Mount Baker Club - Whiskey Bar | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-29 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-12 | 2020-11-20 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09100 | Received | For Review | 2020-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-12 | Submittal Number: 06 20 23-31.0 From: MIKE SOLFELT Final Due Date: 11/12/20 Subject: MOUNT BAKER CLUB - WHISKEY BAR Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12006 | Forwarded | For Review | 2020-10-29 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-05 | Submittal Number: 06 20 23-31.0 From: MIKE SOLFELT Final Due Date: 11/12/20 Subject: MOUNT BAKER CLUB - WHISKEY BAR Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12672 | Responded and Closed | Approved as Noted | 2020-11-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-29 |  | 062023-031 Mount Baker Club - Whiskey Bar.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-29 |  | 062023-031 Mount Baker Club - Whiskey Bar.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-11-20 |  | 062023-031 Mount Baker Club - Whiskey Bar - RG REVIEW_POP.pdf
06 20 23-032-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-032-00 Chairman’s Club Peninsula Frame Engineering | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-26 08:00 | 2021-01-27 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-01-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10606 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-01-26 08:00 | Submittal Number: 06 20 23-32.0 From: MIKE SOLFELT Final Due Date: 01/12/21 Subject: CHAIRMAN’S CLUB PENINSULA FRAME ENGINEERING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13813 | Forwarded | For Review | 2021-01-11 | Mike Solfelt (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-18 | Submittal Number: 06 20 23-32.0 From: MIKE SOLFELT Final Due Date: 01/12/21 Subject: CHAIRMAN’S CLUB PENINSULA FRAME ENGINEERING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11000 | Review Response | Approved | 2021-01-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14286 | Responded and Closed | Approved | 2021-01-27 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 06 20 23-32 Chairman's Club Peninsula Frame Engineering.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-01-11 |  | 06 20 23-32 Chairman's Club Peninsula Frame Engineering.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-27 |  | 06 20 23-32 Chairman's Club Peninsula Frame Engineering_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-01-11 |  | 06 20 23-32 Chairman's Club Peninsula Frame Engineering.pdf
06 20 23-033-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-033-00 Metro Club Buffet | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-10 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-24 | 2021-03-17 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11914 | Received | For Review | 2021-03-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-03-24 | Submittal Number: 06 20 23-33.0 From: MIKE SOLFELT Final Due Date: 03/22/21 Subject: METRO CLUB BUFFET Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 15437 | Forwarded | For Review | 2021-03-10 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-17 | Submittal Number: 06 20 23-33.0 From: MIKE SOLFELT Final Due Date: 03/22/21 Subject: METRO CLUB BUFFET Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12077 | Review Response | Approved as Noted | 2021-03-17 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15631 | Responded and Closed | Approved as Noted | 2021-03-17 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-10 |  | 06 20 23-33 Metro Club Buffet.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-10 |  | 06 20 23-33 Metro Club Buffet.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-17 |  | 06 20 23-33 Metro Club Buffet_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-03-10 |  | 06 20 23-33 Metro Club Buffet.pdf
06 20 23-034-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-034-00 Mount Baker Club - Wine Bar | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-29 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-12 | 2020-11-20 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09098 | Received | For Review | 2020-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-12 | Submittal Number: 06 20 23-34.0 From: MIKE SOLFELT Final Due Date: 11/12/20 Subject: MOUNT BAKER CLUB - WINE BAR Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12004 | Forwarded | For Review | 2020-10-29 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-05 | Submittal Number: 06 20 23-34.0 From: MIKE SOLFELT Final Due Date: 11/12/20 Subject: MOUNT BAKER CLUB - WINE BAR Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12673 | Responded and Closed | Approved as Noted | 2020-11-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-29 |  | 062023-034 Mount Baker - Wine Bar.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-29 |  | 062023-034 Mount Baker - Wine Bar.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-11-20 |  | 062023-034 Mount Baker - Wine Bar - RG RESPONSE_POP.pdf
06 20 23-035-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-035-00 Chairman's Club Pkg. 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-26 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-09 | 2020-11-09 | 15 |  | Record Copies; Transfers; Submittals | 06 20 23-035-00-01 - 06 20 23-035-00 Chairman's Club Pkg. 1 | 15 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08996 | Received | For Review | 2020-10-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-09 | Submittal Number: 06 20 23-35.0 From: MIKE SOLFELT Final Due Date: 11/06/20 Subject: CHAIRMAN'S CLUB PKG. 1 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11869 | Forwarded | For Review | 2020-10-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-02 | Submittal Number: 06 20 23-35.0 From: MIKE SOLFELT Final Due Date: 11/06/20 Subject: CHAIRMAN'S CLUB PKG. 1 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 09329 | Review Response | Revise and Resubmit | 2020-11-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12310 | Responded and Closed | Revise and Resubmit | 2020-11-09 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-26 |  | 062023-035 Chairmans Club Pkg 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-26 |  | 062023-035 Chairmans Club Pkg 1.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-09 |  | 062023-035 Chairmans Club Pkg 1_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-26 |  | 062023-035 Chairmans Club Pkg 1.pdf
06 20 23-035-00-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-035-00 Chairman's Club Pkg. 1 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 20 23-035-00 - 06 20 23-035-00 Chairman's Club Pkg. 1 | -1 | 2020-11-23
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-26 |  | 062023-035 Chairmans Club Pkg 1.pdf
06 20 23-037-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-037-00 Premium Millwork Product Data Pkg 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-29 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kuebler Perry (Populous) |  |  |  | 2020-10-13 | 2020-10-13 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08403 | Received | For Review | 2020-09-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-13 | Submittal Number: 06 20 23-37.0 From: MIKE SOLFELT Final Due Date: 10/14/20 Subject: PREMIUM MILLWORK PRODUCT DATA PKG 1 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11136 | Forwarded | For Review | 2020-09-29 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-06 | Submittal Number: 06 20 23-37.0 From: MIKE SOLFELT Final Due Date: 10/14/20 Subject: PREMIUM MILLWORK PRODUCT DATA PKG 1 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11294 | Forwarded | For Review | 2020-10-05 | Chad Francis (Populous) | Kuebler Perry (Populous) | 2020-10-12 | Submittal Number: 06 20 23-37.0 From: MIKE SOLFELT Final Due Date: 10/14/20 Subject: PREMIUM MILLWORK PRODUCT DATA PKG 1 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11584 | Responded and Closed | Approved as Noted | 2020-10-13 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-28 |  | 06 20 23-037 Premium Millwork Product Data Pkg 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-28 |  | 06 20 23-037 Premium Millwork Product Data Pkg 1.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2020-09-28 |  | 06 20 23-037 Premium Millwork Product Data Pkg 1.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-13 02:00 |  | 06 20 23-037 Premium Millwork Product Data Pkg 1_POP.pdf
06 20 23-038-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-038-00 Upper Con Bar Balance | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-22 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-05 | 2020-11-05 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-11-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08938 | Received | For Review | 2020-10-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-05 | Submittal Number: 06 20 23-38.0 From: MIKE SOLFELT Final Due Date: 10/30/20 Subject: UPPER CON BAR BALANCE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11808 | Forwarded | For Review | 2020-10-22 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-29 | Submittal Number: 06 20 23-38.0 From: MIKE SOLFELT Final Due Date: 10/30/20 Subject: UPPER CON BAR BALANCE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 09265 | Review Response | Approved as Noted | 2020-11-05 | Kuebler Perry (Populous) | Populous SCA_CCA |  | See attached submittal review. | Info Exchange
| 12217 | Responded and Closed | Approved as Noted | 2020-11-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-21 |  | 062023-038 Upper Con Bar Balance.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-21 |  | 062023-038 Upper Con Bar Balance.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-05 |  | 062023-038 Upper Con Bar Balance_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-21 |  | 062023-038 Upper Con Bar Balance.pdf
06 20 23-039-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-039-00 Chairman's Club Custom Millwork | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-16 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-08 | 2021-01-08 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10198 | Received | For Review | 2020-12-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-08 | Submittal Number: 06 20 23-39.0 From: MIKE SOLFELT Final Due Date: 01/04/21 Subject: CHAIRMAN'S CLUB CUSTOM MILLWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13336 | Forwarded | For Review | 2020-12-16 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-23 | Submittal Number: 06 20 23-39.0 From: MIKE SOLFELT Final Due Date: 01/04/21 Subject: CHAIRMAN'S CLUB CUSTOM MILLWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10546 | Review Response | Approved as Noted | 2021-01-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 13746 | Responded and Closed | Approved as Noted | 2021-01-08 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-16 |  | 062023-039 Chairmans Club Custom Millwork.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-16 |  | 062023-039 Chairmans Club Custom Millwork.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-08 |  | 062023-039 Chairmans Club Custom Millwork_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-16 |  | 062023-039 Chairmans Club Custom Millwork.pdf
06 20 23-040-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-040-00 Green Wall Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-29 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-12 | 2020-11-20 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09101 | Received | For Review | 2020-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-12 | Submittal Number: 06 20 23-40.0 From: MIKE SOLFELT Final Due Date: 11/13/20 Subject: GREEN WALL SAMPLE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12009 | Forwarded | For Review | 2020-10-29 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-05 | Submittal Number: 06 20 23-40.0 From: MIKE SOLFELT Final Due Date: 11/13/20 Subject: GREEN WALL SAMPLE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12675 | Responded and Closed | Approved as Noted | 2020-11-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-29 |  | 062023-040 Green Wall Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-29 |  | 062023-040 Green Wall Sample.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-11-20 |  | 062023-040 Green Wall Sample - RG RESPONSE_POP.pdf
06 20 23-041-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-041-00 F12 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-16 | 2020-11-20 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09160 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (M.A. Mortenson Company) | 2020-11-16 | Submittal Number: 06 20 23-41.0 From: MIKE SOLFELT Final Due Date: 11/15/20 Subject: F12 SAMPLE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12082 | Forwarded | For Review | 2020-11-02 | Mike Solfelt (M.A. Mortenson Company) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-09 | Submittal Number: 06 20 23-41.0 From: MIKE SOLFELT Final Due Date: 11/15/20 Subject: F12 SAMPLE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12674 | Responded and Closed | Approved | 2020-11-20 | Mike Solfelt (M.A. Mortenson Company) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | 062023-041 F12 Sample.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2020-11-02 |  | 062023-041 F12 Sample.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2020-11-20 |  | 062023-041 F12 Sample - RG RESPONSE_POP.pdf
06 20 23-042-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-042-00 Flame Spread Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-08 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-22 | 2020-12-30 | 23 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-12-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09980 | Received | For Review | 2020-12-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-12-22 | Submittal Number: 06 20 23-42.0 From: MIKE SOLFELT Final Due Date: 11/20/20 Subject: FLAME SPREAD PRODUCT DATA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13064 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 06 20 23-42.0 From: MIKE SOLFELT Final Due Date: 11/20/20 Subject: FLAME SPREAD PRODUCT DATA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13541 | Responded and Closed | Approved | 2020-12-30 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 062023-042 Flame Spread Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-07 |  | 062023-042 Flame Spread Product Data.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-30 |  | 062023-042 Flame Spread Product Data-POP.pdf
06 20 23-043-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-043-00 WD6 Match on Maple | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-04 | 2020-12-04 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-12-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09524 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-12-04 | Submittal Number: 06 20 23-43.0 From: MIKE SOLFELT Final Due Date: 12/01/20 Subject: WD6 MATCH ON MAPLE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12544 | Forwarded | For Review | 2020-11-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-25 | Submittal Number: 06 20 23-43.0 From: MIKE SOLFELT Final Due Date: 12/01/20 Subject: WD6 MATCH ON MAPLE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 09915 | Review Response | Approved | 2020-12-04 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12995 | Responded and Closed | Approved | 2020-12-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | 062023-043 WD6 on Maple.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | 062023-043 WD6 on Maple.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-04 |  | 062023-043 WD6 on Maple_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-17 |  | 062023-043 WD6 on Maple.pdf
06 20 23-044-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-044-00 Tunnel Club Type A, B, A1, B1 and E Millwork | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-16 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-08 | 2021-01-08 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10197 | Received | For Review | 2020-12-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-08 | Submittal Number: 06 20 23-44.0 From: MIKE SOLFELT Final Due Date: 12/30/20 Subject: TUNNEL CLUB TYPE A, B, A1, B1 AND E MILLWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13335 | Forwarded | For Review | 2020-12-16 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-23 | Submittal Number: 06 20 23-44.0 From: MIKE SOLFELT Final Due Date: 12/30/20 Subject: TUNNEL CLUB TYPE A, B, A1, B1 AND E MILLWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10550 | Review Response | Approved as Noted | 2021-01-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13749 | Responded and Closed | Approved as Noted | 2021-01-08 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-16 |  | 062023-044 Tunnel Club Type A B A1 B1 and E Millwork.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-16 |  | 062023-044 Tunnel Club Type A B A1 B1 and E Millwork.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-08 |  | 062023-044 Tunnel Club Type A B A1 B1 and E Millwork_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-16 |  | 062023-044 Tunnel Club Type A B A1 B1 and E Millwork.pdf
06 20 23-045-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-045-00 Tunnel Club Type C | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-24 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-01-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10395 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-19 08:00 | Submittal Number: 06 20 23-45.0 From: MIKE SOLFELT Final Due Date: 01/09/21 Subject: TUNNEL CLUB TYPE C Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13579 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 06 20 23-45.0 From: MIKE SOLFELT Final Due Date: 01/09/21 Subject: TUNNEL CLUB TYPE C Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 10918 | Review Response | Approved as Noted | 2021-01-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14175 | Responded and Closed | Approved as Noted | 2021-01-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-30 |  | 06 20 23-45 - Tunnel Club Type C.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-30 |  | 06 20 23-45 - Tunnel Club Type C.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-24 |  | 06 20 23-45 - Tunnel Club Type C_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-30 |  | 06 20 23-45 - Tunnel Club Type C.pdf
06 20 23-047-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-047-00 Millwork Product Data pkg 2 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-27 08:00 | 2021-01-29 | 18 |  | Record Copies; Transfers; Submittals | 06 20 23-047-00-01 - 06 20 23-047-00 Millwork Product Data pkg 2 | 18 |  | 2021-01-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10646 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-27 08:00 | Submittal Number: 06 20 23-47.0 From: MIKE SOLFELT Final Due Date: 01/19/21 Subject: MILLWORK PRODUCT DATA PKG 2 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13856 | Forwarded | For Review | 2021-01-12 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 06 20 23-47.0 From: MIKE SOLFELT Final Due Date: 01/19/21 Subject: MILLWORK PRODUCT DATA PKG 2 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11048 | Review Response | Approved as Noted/Resubmit | 2021-01-29 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14347 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 062023-047 Millwork Product Data pkg 2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-12 |  | 062023-047 Millwork Product Data pkg 2.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-29 |  | 062023-047 Millwork Product Data pkg 2_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-12 |  | 062023-047 Millwork Product Data pkg 2.pdf
06 20 23-047-00-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-047-00 Millwork Product Data pkg 2 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 20 23-047-00 - 06 20 23-047-00 Millwork Product Data pkg 2 | -1 | 2021-02-12
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 062023-047 Millwork Product Data pkg 2.pdf
06 20 23-048-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-048-00 Guest Service Kiosk / Portable Millwork | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-09 | 2021-02-11 | 17 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10944 | Received | For Review | 2021-01-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-09 | Submittal Number: 06 20 23-48.0 From: MIKE SOLFELT Final Due Date: 01/29/21 Subject: GUEST SERVICE KIOSK / PORTABLE MILLWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14208 | Forwarded | For Review | 2021-01-25 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-01 | Submittal Number: 06 20 23-48.0 From: MIKE SOLFELT Final Due Date: 01/29/21 Subject: GUEST SERVICE KIOSK / PORTABLE MILLWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11309 | Review Response | No Action Taken or Required | 2021-02-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Not reviewed. Guest services millwork is changing in upcoming CCD. | Info Exchange
| 14660 | Responded and Closed | No Action Taken or Required | 2021-02-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Not reviewed. Guest services millwork is changing in upcoming CCD. | Info Exchange
| 14700 | Reopened | Additional Information | 2021-02-11 11:27 | Kelsea Conkright (Populous)
| 11343 | Review Response | Approved as Noted | 2021-02-11 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14704 | Responded and Closed | Approved as Noted | 2021-02-11 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 06 20 23-48 - Kiosk_Portable Millwork.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-25 |  | 06 20 23-48 - Kiosk_Portable Millwork.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-10 |  | 06 20 23-48 - Kiosk_Portable Millwork_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-25 |  | 06 20 23-48 - Kiosk_Portable Millwork.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-11 |  | 06 20 23-48 - Kiosk_Portable Millwork_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-01-25 |  | 06 20 23-48 - Kiosk_Portable Millwork.pdf
06 20 23-049-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-049-00 WNBA Misc. Areas | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-03-01 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11416 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-01 | Submittal Number: 06 20 23-49.0 From: MIKE SOLFELT Final Due Date: 02/26/21 Subject: WNBA MISC. AREAS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14783 | Forwarded | For Review | 2021-02-15 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 06 20 23-49.0 From: MIKE SOLFELT Final Due Date: 02/26/21 Subject: WNBA MISC. AREAS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 15167 | Responded and Closed | Approved as Noted | 2021-03-01 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 062023-049-WNBA Misc Areas.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-15 |  | 062023-049-WNBA Misc Areas.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-01 |  | 062023-049-WNBA Misc Areas_POP.pdf
06 20 23-050-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-050-00 Break Room Casework | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-09 | 2021-02-12 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-02-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10958 | Received | For Review | 2021-01-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-09 | Submittal Number: 06 20 23-50.0 From: MIKE SOLFELT Final Due Date: 01/17/21 Subject: BREAK ROOM CASEWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14232 | Forwarded | For Review | 2021-01-26 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-02 | Submittal Number: 06 20 23-50.0 From: MIKE SOLFELT Final Due Date: 01/17/21 Subject: BREAK ROOM CASEWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14752 | Responded and Closed | Approved as Noted | 2021-02-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. FIELD VERIFY ALL DIMENSIONS. 2. VERIFY ALL EQUIPMENT CLEARANCES 3. SEE PLAN FOR ADDITIONAL LOCATION PER DRAWINGS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 062023-050 Breakdown Casework.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-25 |  | 062023-050 Breakdown Casework.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-12 |  | 062023-050 Breakdown Casework_POP.pdf
06 20 23-051-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-051-00 03.06.12 Column Cover | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-28 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-11 | 2021-02-15 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11023 | Received | For Review | 2021-01-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-11 | Submittal Number: 06 20 23-51.0 From: MIKE SOLFELT Final Due Date: 02/05/21 Subject: 03.06.12 COLUMN COVER Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14319 | Forwarded | For Review | 2021-01-28 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-04 | Submittal Number: 06 20 23-51.0 From: MIKE SOLFELT Final Due Date: 02/05/21 Subject: 03.06.12 COLUMN COVER Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11399 | Review Response | Approved as Noted | 2021-02-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14766 | Responded and Closed | Approved as Noted | 2021-02-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-28 |  | 062023-051 03.06.12 Column Cover.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-28 |  | 062023-051 03.06.12 Column Cover.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-15 |  | 062023-051 03.06.12 Column Cover_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-28 |  | 062023-051 03.06.12 Column Cover.pdf
06 20 23-052-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-052-00 03.10.02 Bar | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-28 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-11 | 2021-02-15 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11024 | Received | For Review | 2021-01-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-11 | Submittal Number: 06 20 23-52.0 From: MIKE SOLFELT Final Due Date: 02/06/21 Subject: 03.10.02 BAR Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14320 | Forwarded | For Review | 2021-01-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-04 | Submittal Number: 06 20 23-52.0 From: MIKE SOLFELT Final Due Date: 02/06/21 Subject: 03.10.02 BAR Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11400 | Review Response | Approved as Noted | 2021-02-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal. Some items at this location may change due to sponsorship updates, but those updates have not been incorporated into the contract documents yet. For your convenience, I've noted those item where possible. | Info Exchange
| 14767 | Responded and Closed | Approved as Noted | 2021-02-15 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal. Some items at this location may change due to sponsorship updates, but those updates have not been incorporated into the contract documents yet. For your convenience, I've noted those item where possible. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-28 |  | 06 20 23-52 03.10.02 Bar.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-28 |  | 06 20 23-52 03.10.02 Bar.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-15 |  | 06 20 23-52 03.10.02 Bar_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-28 |  | 06 20 23-52 03.10.02 Bar.pdf
06 20 23-053-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-053-00 Cove Base Product Data - Premium | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-01 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-15 | 2021-02-15 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11086 | Received | For Review | 2021-02-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-02-15 | Submittal Number: 06 20 23-53.0 From: MIKE SOLFELT Final Due Date: 02/12/21 Subject: COVE BASE PRODUCT DATA - PREMIUM Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14384 | Forwarded | For Review | 2021-02-01 | Mike Solfelt (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-08 | Submittal Number: 06 20 23-53.0 From: MIKE SOLFELT Final Due Date: 02/12/21 Subject: COVE BASE PRODUCT DATA - PREMIUM Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11406 | Review Response | Approved as Noted | 2021-02-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14773 | Responded and Closed | Approved as Noted | 2021-02-15 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-01 |  | 062023-053 Cove Base Premium.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-02-01 |  | 062023-053 Cove Base Premium.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-15 |  | 062023-053 Cove Base Premium_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-02-01 |  | 062023-053 Cove Base Premium.pdf
06 20 23-055-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-055-00 Mount Baker Pizza Bar Built-In Shelving | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-22 | 2021-02-23 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-02-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11276 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-22 | Submittal Number: 06 20 23-55.0 From: MIKE SOLFELT Final Due Date: 02/12/21 Subject: MOUNT BAKER PIZZA BAR BUILT-IN SHELVING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14608 | Forwarded | For Review | 2021-02-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-15 | Submittal Number: 06 20 23-55.0 From: MIKE SOLFELT Final Due Date: 02/12/21 Subject: MOUNT BAKER PIZZA BAR BUILT-IN SHELVING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 15028 | Responded and Closed | Approved as Noted | 2021-02-23 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED 1. FIELD VERIFY ALL DIMENSIONS. 2. CM TO COORDINATE ROCKWELL COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-08 |  | 062023-055 Mount Baker Pizza Bar Built-In Shelcing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-08 |  | 062023-055 Mount Baker Pizza Bar Built-In Shelcing.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-23 |  | 062023-055 Mount Baker Pizza Bar Built-In Shelcing_POP.pdf
06 20 23-056-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-056-00 Suite Level Elevator Lobby Base | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-25 | 2021-02-25 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11329 | Received | For Review | 2021-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-02-25 | Submittal Number: 06 20 23-56.0 From: MIKE SOLFELT Final Due Date: 02/14/21 Subject: SUITE LEVEL ELEVATOR LOBBY BASE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14688 | Forwarded | For Review | 2021-02-11 | Mike Solfelt (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-18 | Submittal Number: 06 20 23-56.0 From: MIKE SOLFELT Final Due Date: 02/14/21 Subject: SUITE LEVEL ELEVATOR LOBBY BASE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11659 | Review Response | Approved as Noted | 2021-02-25 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 15110 | Responded and Closed | Approved as Noted | 2021-02-25 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-10 |  | 06 20 23-56 Suite Level Elevator Lobby Base.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-02-10 |  | 06 20 23-56 Suite Level Elevator Lobby Base.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-25 |  | 06 20 23-56 Suite Level Elevator Lobby Base_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-02-10 |  | 06 20 23-56 Suite Level Elevator Lobby Base.pdf
06 20 23-057-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-057-00 01.14.10 Security Room Casework | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-02 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-16 | 2021-02-23 | 22 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-02-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11123 | Received | For Review | 2021-02-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-16 | Submittal Number: 06 20 23-57.0 From: MIKE SOLFELT Final Due Date: 02/18/21 Subject: 01.14.10 SECURITY ROOM CASEWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14433 | Forwarded | For Review | 2021-02-02 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-09 | Submittal Number: 06 20 23-57.0 From: MIKE SOLFELT Final Due Date: 02/18/21 Subject: 01.14.10 SECURITY ROOM CASEWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11496 | Review Response | Approved as Noted | 2021-02-16 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14881 | Responded and Closed | Approved as Noted | 2021-02-16 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| 15027 | Reopened | Additional Information | 2021-02-23 09:46 | Kelsea Conkright (Populous)
| 15029 | Responded and Closed | Approved as Noted | 2021-02-23 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-01 |  | 062023-057 Security Room Casework.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-01 |  | 062023-057 Security Room Casework.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-16 |  | 062023-057 Security Room Casework_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-02-01 |  | 062023-057 Security Room Casework.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-02-01 |  | 062023-057 Security Room Casework.pdf
06 20 23-058-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-058-00: Milk White Acrylic | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-18 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Chad Francis (Populous) |  |  |  | 2021-03-04 | 2021-03-05 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-03-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11530 | Received | For Review | 2021-02-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-03-04 | Submittal Number: 06 20 23-58.0 From: MIKE SOLFELT Final Due Date: 02/20/21 Subject: MILK WHITE ACRYLIC Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 14944 | Forwarded | For Review | 2021-02-19 | Josh Dobken (Populous) | Kelsea Conkright (Populous); Chad Francis (Populous) | 2021-02-26 | Submittal Number: 06 20 23-58.0 From: MIKE SOLFELT Final Due Date: 02/20/21 Subject: MILK WHITE ACRYLIC Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11817 | Review Response | Approved | 2021-03-05 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15322 | Responded and Closed | Approved | 2021-03-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-18 02:00 |  | 06 20 23-058 Milk White Acrylic.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-18 02:00 |  | 06 20 23-058 Milk White Acrylic.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-05 |  | 06 20 23-058 Milk White Acrylic_MAM_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-18 |  | 06 20 23-058 Milk White Acrylic.pdf
06 20 23-059-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-059-00 Street Locker Island | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-25 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2021-03-11 | 2021-03-10 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11664 | Received | For Review | 2021-02-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-03-11 | Submittal Number: 06 20 23-59.0 From: MIKE SOLFELT Final Due Date: 03/11/21 Subject: STREET LOCKER ISLAND Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 15115 | Forwarded | For Review | 2021-02-25 | Josh Dobken (Populous) | Kelsea Conkright (Populous); Kuebler Perry (Populous); Chad Francis (Populous) | 2021-03-04 | Submittal Number: 06 20 23-59.0 From: MIKE SOLFELT Final Due Date: 03/11/21 Subject: STREET LOCKER ISLAND Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 11928 | Review Response | Approved as Noted | 2021-03-10 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15452 | Responded and Closed | Approved as Noted | 2021-03-10 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-25 02:00 |  | 06 20 23-059 Street Locker Island.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-25 02:00 |  | 06 20 23-059 Street Locker Island.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-10 |  | 06 20 23-059 Street Locker Island_MAM_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-02-25 |  | 06 20 23-059 Street Locker Island.pdf
06 20 23-060-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-060-00 Liquor Risers | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-16 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-30 | 2021-04-08 | 24 |  | Record Copies; Transfers; Submittals |  | 25 |  | 2021-04-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12026 | Received | For Review | 2021-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-30 | Submittal Number: 06 20 23-60.0 From: MIKE SOLFELT Final Due Date: 03/29/21 Subject: LIQUOR RISERS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 15564 | Forwarded | For Review | 2021-03-15 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-22 | Submittal Number: 06 20 23-60.0 From: MIKE SOLFELT Final Due Date: 03/29/21 Subject: LIQUOR RISERS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12479 | Review Response | Revise and Resubmit | 2021-04-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16169 | Responded and Closed | Revise and Resubmit | 2021-04-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-15 |  | 062023-060 Liquor Risers.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-15 |  | 062023-060 Liquor Risers.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-08 |  | 062023-060 Liquor Risers_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-15 |  | 062023-060 Liquor Risers.pdf
06 20 23-060-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-060-01 Liquor Risers for Record | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-22 | Responded and Closed - No Action Taken or Required |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-06 | 2021-05-10 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12714 | Received | For Review | 2021-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-05-06 | Submittal Number: 06 20 23-60.1 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: LIQUOR RISERS FOR RECORD Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16437 | Forwarded | For Review | 2021-04-22 | Mike Solfelt (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-29 | Submittal Number: 06 20 23-60.1 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: LIQUOR RISERS FOR RECORD Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13004 | Review Response | No Action Taken or Required | 2021-05-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16829 | Responded and Closed | No Action Taken or Required | 2021-05-10 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-22 |  | 062023-060 Liquor Risers For Record.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-04-22 |  | 062023-060 Liquor Risers For Record.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-04-22 |  | 062023-060 Liquor Risers For Record.pdf
06 20 23-061-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-061-00 WD-13 Revised Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-07 | 3 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-04-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12367 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-04-19 | Submittal Number: 06 20 23-61.0 From: MIKE SOLFELT Final Due Date: 04/03/21 Subject: WD-13 REVISED SAMPLES Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16023 | Forwarded | For Review | 2021-04-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 06 20 23-61.0 From: MIKE SOLFELT Final Due Date: 04/03/21 Subject: WD-13 REVISED SAMPLES Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12452 | Review Response | Approved as Noted | 2021-04-07 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16133 | Responded and Closed | Approved as Noted | 2021-04-07 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 06 20 23-61.0 - WD13 Revised Samples - RG REVIEW.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 06 20 23-61.0 - WD13 Revised Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-01 |  | 06 20 23-61.0 - WD13 Revised Samples - RG REVIEW.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-01 |  | 06 20 23-61.0 - WD13 Revised Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-07 |  | 06 20 23-61.0 - WD13 Revised Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-01 |  | 06 20 23-61.0 - WD13 Revised Samples - RG REVIEW.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-01 |  | 06 20 23-61.0 - WD13 Revised Samples.pdf
06 20 23-062-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-062-00 CCD087 - Admin Area | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-01 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-15 | 2021-04-14 | 14 |  | Record Copies; Transfers; Submittals | 06 20 23-062-00-01 - 06 20 23-062-00 CCD087 - Admin Area | 14 |  | 2021-04-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12348 | Received | For Review | 2021-04-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-04-15 | Submittal Number: 06 20 23-62.0 From: MIKE SOLFELT Final Due Date: 04/18/21 Subject: CCD087 - ADMIN AREA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16002 | Forwarded | For Review | 2021-04-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 06 20 23-62.0 From: MIKE SOLFELT Final Due Date: 04/18/21 Subject: CCD087 - ADMIN AREA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12588 | Review Response | Approved as Noted/Resubmit | 2021-04-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16302 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-14 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 062023-062 - CCD087 Admin Area (1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-01 |  | 062023-062 - CCD087 Admin Area (1).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-14 |  | 062023-062 - CCD087 Admin Area_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-01 |  | 062023-062 - CCD087 Admin Area (1).pdf
06 20 23-062-00-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-062-00 CCD087 - Admin Area | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 20 23-062-00 - 06 20 23-062-00 CCD087 - Admin Area | -1 | 2021-04-28
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 062023-062 - CCD087 Admin Area (1).pdf
06 20 23-063-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-063-00 CCD088 Amazon Music Studio | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-22 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-06 | 2021-05-10 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12715 | Received | For Review | 2021-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-06 | Submittal Number: 06 20 23-63.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: CCD088 AMAZON MUSIC STUDIO Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16438 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-29 | Submittal Number: 06 20 23-63.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: CCD088 AMAZON MUSIC STUDIO Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13001 | Review Response | Approved as Noted | 2021-05-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 16822 | Responded and Closed | Approved as Noted | 2021-05-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-21 |  | 06 20 23-063 Amazon Music Studio-Artist Lounge.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-21 |  | 06 20 23-063 Amazon Music Studio-Artist Lounge.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-10 |  | 06 20 23-063 Amazon Music Studio-Artist Lounge_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-21 |  | 06 20 23-063 Amazon Music Studio-Artist Lounge.pdf
06 20 23-064-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-064-00 CCD094 Ticket Office Revisions | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-19 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13048 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-25 | Submittal Number: 06 20 23-64.0 From: MIKE SOLFELT Final Due Date: 05/25/21 Subject: CCD094 TICKET OFFICE REVISIONS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16883 | Forwarded | For Review | 2021-05-11 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-18 | Submittal Number: 06 20 23-64.0 From: MIKE SOLFELT Final Due Date: 05/25/21 Subject: CCD094 TICKET OFFICE REVISIONS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17077 | Responded and Closed | Approved as Noted | 2021-05-19 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-11 |  | 06 20 23-064 CCD094 Ticket Office.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-19 |  | 06 20 23-064 CCD094 Ticket Office_POP.pdf
06 20 23-065-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-065-00 CCD086 Lockers | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-22 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-06 | 2021-04-29 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-04-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12716 | Received | For Review | 2021-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-06 | Submittal Number: 06 20 23-65.0 From: MIKE SOLFELT Final Due Date: 04/30/21 Subject: CCD086 LOCKERS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16439 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-29 | Submittal Number: 06 20 23-65.0 From: MIKE SOLFELT Final Due Date: 04/30/21 Subject: CCD086 LOCKERS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12867 | Review Response | Approved as Noted | 2021-04-29 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16645 | Responded and Closed | Approved as Noted | 2021-04-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-21 |  | 06 20 23-65 WNBA Auxiliary Lockers CCD086.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-21 |  | 06 20 23-65 WNBA Auxiliary Lockers CCD086.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-29 |  | 06 20 23-65 WNBA Auxiliary Lockers CCD086_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-21 |  | 06 20 23-65 WNBA Auxiliary Lockers CCD086.pdf
06 20 23-066-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-066-00 CCD091 Misc. Revisions | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-10 | 2021-05-14 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-05-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12764 | Received | For Review | 2021-04-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-10 | Submittal Number: 06 20 23-66.0 From: MIKE SOLFELT Final Due Date: 04/30/21 Subject: CCD091 MISC. REVISIONS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16499 | Forwarded | For Review | 2021-04-26 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-03 | Submittal Number: 06 20 23-66.0 From: MIKE SOLFELT Final Due Date: 04/30/21 Subject: CCD091 MISC. REVISIONS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13109 | Review Response | Approved as Noted | 2021-05-14 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16954 | Responded and Closed | Approved as Noted | 2021-05-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-26 |  | 062023-066 CCD091 Misc. Revisions - Hooks&Crash Rails.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-26 |  | 062023-066 CCD091 Misc. Revisions - Hooks&Crash Rails.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-05-14 |  | 062023-066 CCD091 Misc. Revisions - Hooks&Crash Rails_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-26 |  | 062023-066 CCD091 Misc. Revisions - Hooks&Crash Rails.pdf
06 20 23-067-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-067-00 Mount Baker Drink Rails - SSM31 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-12 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-26 | 2021-04-27 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12532 | Received | For Review | 2021-04-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-26 | Submittal Number: 06 20 23-67.0 From: MIKE SOLFELT Final Due Date: 04/23/21 Subject: MOUNT BAKER DRINK RAILS - SSM31 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16234 | Forwarded | For Review | 2021-04-12 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-19 | Submittal Number: 06 20 23-67.0 From: MIKE SOLFELT Final Due Date: 04/23/21 Subject: MOUNT BAKER DRINK RAILS - SSM31 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16559 | Responded and Closed | Approved as Noted | 2021-04-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | PLEASE SEE ATTACHED 1. DIMENSIONS APRROVED. 2. CM TO CONFIRM COUNTERTOP MATERIAL WITH ROCKWELL GROUP COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-12 |  | 062023-067 Mount Baker Drink Rails.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-12 |  | 062023-067 Mount Baker Drink Rails.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-27 |  | 062023-067 Mount Baker Drink Rails_POP.pdf
06 20 23-068-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-068-00 Kraken Bar Area | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-13 | Responded and Closed - Rejected |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-27 | 2021-04-28 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12555 | Received | For Review | 2021-04-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-27 | Submittal Number: 06 20 23-68.0 From: MIKE SOLFELT Final Due Date: 04/26/21 Subject: KRAKEN BAR AREA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16263 | Forwarded | For Review | 2021-04-13 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-20 | Submittal Number: 06 20 23-68.0 From: MIKE SOLFELT Final Due Date: 04/26/21 Subject: KRAKEN BAR AREA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12835 | Review Response | Rejected | 2021-04-28 | Kuebler Perry (Populous) | Populous SCA_CCA |  | This design has not been issued yet and the shop drawings are incomplete. | Info Exchange
| 16611 | Responded and Closed | Rejected | 2021-04-28 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | This design has not been issued yet and the shop drawings are incomplete. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-12 |  | 062023-068 Kraken Bar Area.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-12 |  | 062023-068 Kraken Bar Area.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-28 |  | 062023-068 Kraken Bar Area_POP.pdf
06 20 23-068-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-068-01 Kraken Bar Area CCD 108 Review | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-21 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-05 | 2021-06-21 | 1 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-06-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13570 | Received | For Review | 2021-06-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-07-05 | Submittal Number: 06 20 23-68.1 From: MIKE SOLFELT Final Due Date: 07/02/21 Subject: KRAKEN BAR AREA CCD 108 REVIEW Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17573 | Forwarded | For Review | 2021-06-18 | Mike Solfelt (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-25 | Submittal Number: 06 20 23-68.1 From: MIKE SOLFELT Final Due Date: 07/02/21 Subject: KRAKEN BAR AREA CCD 108 REVIEW Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13598 | Review Response | Approved as Noted | 2021-06-21 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17600 | Responded and Closed | Approved as Noted | 2021-06-21 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-18 |  | 06 20 23-068.1 Kraken Bar Area CCD 108 Review.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-06-18 |  | 06 20 23-068.1 Kraken Bar Area CCD 108 Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-21 |  | 06 20 23-068.1 Kraken Bar Area CCD 108 Review_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-06-18 |  | 06 20 23-068.1 Kraken Bar Area CCD 108 Review.pdf
06 20 23-069-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-069-00 Metro Club Shelving | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-22 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-06 | 2021-05-10 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12712 | Received | For Review | 2021-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-06 | Submittal Number: 06 20 23-69.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: METRO CLUB SHELVING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16435 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-29 | Submittal Number: 06 20 23-69.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: METRO CLUB SHELVING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13007 | Review Response | Approved as Noted | 2021-05-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16832 | Responded and Closed | Approved as Noted | 2021-05-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-22 |  | 062023-069 Metro Club Shelving.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-22 |  | 062023-069 Metro Club Shelving.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-10 |  | 062023-069 Metro Club Shelving_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-22 |  | 062023-069 Metro Club Shelving.pdf
06 20 23-070-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-070-00 Whiskey Bar Front Shelving | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-22 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti) |  |  |  | 2021-05-06 | 2021-05-05 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-05-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12713 | Received | For Review | 2021-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-06 | Submittal Number: 06 20 23-70.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: WHISKEY BAR FRONT SHELVING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16436 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-29 | Submittal Number: 06 20 23-70.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: WHISKEY BAR FRONT SHELVING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16727 | Forwarded | For Review | 2021-05-04 | Chad Francis (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) | 2021-05-06 | Submittal Number: 06 20 23-70.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: WHISKEY BAR FRONT SHELVING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12956 | Review Response | Approved as Noted | 2021-05-05 | Matt Ross (Thornton Tomasetti) | Chad Francis (Populous) |  | Refer to TT comments on seismic parameters. | Info Exchange
| 16760 | Responded and Closed | Approved as Noted | 2021-05-05 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-21 |  | 062023-070 Whiskey Bar Front Shelving.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-21 |  | 062023-070 Whiskey Bar Front Shelving.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2021-04-21 |  | 062023-070 Whiskey Bar Front Shelving.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-21 |  | 062023-070 Whiskey Bar Front Shelving.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-05 |  | 062023-070 Whiskey Bar Front Shelving_TT_POP.pdf
06 20 23-071-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-071-00 Whiskey Bar Back Shelving | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-02 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-16 | 2021-06-09 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13346 | Received | For Review | 2021-06-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-06-16 | Submittal Number: 06 20 23-71.0 From: MIKE SOLFELT Final Due Date: 06/15/21 Subject: WHISKEY BAR BACK SHELVING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17269 | Forwarded | For Review | 2021-06-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 06 20 23-71.0 From: MIKE SOLFELT Final Due Date: 06/15/21 Subject: WHISKEY BAR BACK SHELVING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17423 | Responded and Closed | Approved as Noted | 2021-06-09 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-01 |  | 062023-071 Whiskey Bar back Shelving.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-01 |  | 062023-071 Whiskey Bar back Shelving.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-09 |  | 062023-071 Whiskey Bar back Shelving_POP.pdf
06 20 23-072-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-072-00 Metro Buffet Countertops | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-06-04 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13138 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-06-02 07:00 | Submittal Number: 06 20 23-72.0 From: MIKE SOLFELT Final Due Date: 05/31/21 Subject: METRO BUFFET COUNTERTOPS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16998 | Forwarded | For Review | 2021-05-18 | Mike Solfelt (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-25 | Submittal Number: 06 20 23-72.0 From: MIKE SOLFELT Final Due Date: 05/31/21 Subject: METRO BUFFET COUNTERTOPS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13397 | Review Response | Approved as Noted | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17328 | Responded and Closed | Approved as Noted | 2021-06-04 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | 062023-072 Metro Club Countertops.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-05-17 |  | 062023-072 Metro Club Countertops.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-04 |  | 062023-072 Metro Club Countertops_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-05-17 |  | 062023-072 Metro Club Countertops.pdf
06 20 23-073-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-073-00 Vesuvious Stone / Maharam Leather Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-22 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-06 | 2021-05-03 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-05-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12717 | Received | For Review | 2021-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-06 | Submittal Number: 06 20 23-73.0 From: MIKE SOLFELT Final Due Date: 05/03/21 Subject: VESUVIOUS STONE / MAHARAM LEATHER SAMPLES Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16440 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-29 | Submittal Number: 06 20 23-73.0 From: MIKE SOLFELT Final Due Date: 05/03/21 Subject: VESUVIOUS STONE / MAHARAM LEATHER SAMPLES Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 12893 | Review Response | Approved | 2021-05-03 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16680 | Responded and Closed | Approved | 2021-05-03 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| 16736 | Sent | For Information Only | 2021-05-04 | Populous SCA_CCA | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | Response (Approved) from: Kuebler Perry (Populous) Remarks: Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-21 |  | 06 20 23-73 Vesuvious Stone Maharam Leather SSM11 and SSM12.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-21 |  | 06 20 23-73 Vesuvious Stone Maharam Leather SSM11 and SSM12.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-03 |  | 06 20 23-73 Vesuvious Stone Maharam Leather SSM11 and SSM12_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-21 |  | 06 20 23-73 Vesuvious Stone Maharam Leather SSM11 and SSM12.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-04-20 02:00 |  | 06 20 23-73 Vesuvious Stone Maharam Leather SSM11 and SSM12.pdf
06 20 23-074-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-074-00 WNBA Home Lockers Mock-Up | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-04 | 2021-04-26 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12678 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-05-04 | Submittal Number: 06 20 23-74.0 From: MIKE SOLFELT Final Due Date: 05/04/21 Subject: WNBA HOME LOCKERS MOCK-UP Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16396 | Forwarded | For Review | 2021-04-20 | Mike Solfelt (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 06 20 23-74.0 From: MIKE SOLFELT Final Due Date: 05/04/21 Subject: WNBA HOME LOCKERS MOCK-UP Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16483 | Responded and Closed | Approved as Noted | 2021-04-26 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-20 |  | 06 20 23-74 WNBA Mock-Up.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-04-20 |  | 06 20 23-74 WNBA Mock-Up.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-26 |  | 06 20 23-74 WNBA Mock-Up_POP.pdf
06 20 23-075-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-075-00 Chairmans club shelving | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-02 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-16 | 2021-06-21 | 20 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-06-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13347 | Received | For Review | 2021-06-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-16 | Submittal Number: 06 20 23-75.0 From: MIKE SOLFELT Final Due Date: 06/15/21 Subject: CHAIRMANS CLUB SHELVING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17270 | Forwarded | For Review | 2021-06-01 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 06 20 23-75.0 From: MIKE SOLFELT Final Due Date: 06/15/21 Subject: CHAIRMANS CLUB SHELVING Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13588 | Review Response | Approved as Noted | 2021-06-21 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17588 | Responded and Closed | Approved as Noted | 2021-06-21 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-01 |  | 062023-075 Chairmans Club Shelving.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-01 |  | 062023-075 Chairmans Club Shelving.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-21 |  | 062023-075 Chairmans Club Shelving_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-01 |  | 062023-075 Chairmans Club Shelving.pdf
06 20 23-076-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-076-00 Fire Retardant Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-18 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13049 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-25 | Submittal Number: 06 20 23-76.0 From: MIKE SOLFELT Final Due Date: 05/19/21 Subject: FIRE RETARDANT PRODUCT DATA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16884 | Forwarded | For Review | 2021-05-11 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-18 | Submittal Number: 06 20 23-76.0 From: MIKE SOLFELT Final Due Date: 05/19/21 Subject: FIRE RETARDANT PRODUCT DATA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17040 | Responded and Closed | Approved | 2021-05-18 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | 06 20 23-76 Fire Retardant Treatment PDS.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-11 |  | 06 20 23-76 Fire Retardant Treatment PDS.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-18 |  | 06 20 23-76 Fire Retardant Treatment PDS-POP.pdf
06 20 23-077-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-077-00 Tunnel Club Revisions - CCD099 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-26 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13031 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-05-25 | Submittal Number: 06 20 23-77.0 From: MIKE SOLFELT Final Due Date: 05/24/21 Subject: TUNNEL CLUB REVISIONS - CCD099 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 16864 | Forwarded | For Review | 2021-05-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-18 | Submittal Number: 06 20 23-77.0 From: MIKE SOLFELT Final Due Date: 05/24/21 Subject: TUNNEL CLUB REVISIONS - CCD099 Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13279 | Review Response | Approved as Noted | 2021-05-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17183 | Responded and Closed | Approved as Noted | 2021-05-26 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 06 20 23-77 Tunnel Club Revisions- CCD099.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-10 |  | 06 20 23-77 Tunnel Club Revisions- CCD099.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-26 |  | 06 20 23-77 Tunnel Club Revisions- CCD099_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-05-10 |  | 06 20 23-77 Tunnel Club Revisions- CCD099.pdf
06 20 23-078-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-078-00 Owner's Suite Sink Support / Enclosure | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-01 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-15 | 2021-06-09 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13330 | Received | For Review | 2021-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-06-15 | Submittal Number: 06 20 23-78.0 From: MIKE SOLFELT Final Due Date: 06/08/21 Subject: OWNER'S SUITE SINK SUPPORT / ENCLOSURE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17251 | Forwarded | For Review | 2021-06-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 06 20 23-78.0 From: MIKE SOLFELT Final Due Date: 06/08/21 Subject: OWNER'S SUITE SINK SUPPORT / ENCLOSURE Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17421 | Responded and Closed | Approved as Noted | 2021-06-09 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-01 |  | 062023-078 Owners Suite Vanities.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-01 |  | 062023-078 Owners Suite Vanities.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-09 |  | 062023-078 Owners Suite Vanities_POP.pdf
06 20 23-079-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-079-00 CCD 101 Coors Bars | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-01 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-15 | 2021-06-16 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-06-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13331 | Received | For Review | 2021-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-15 | Submittal Number: 06 20 23-79.0 From: JOSH BROUSSARD Final Due Date: 06/18/21 Subject: CCD 101 COORS BARS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17252 | Forwarded | For Review | 2021-06-01 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 06 20 23-79.0 From: JOSH BROUSSARD Final Due Date: 06/18/21 Subject: CCD 101 COORS BARS Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17413 | Responded and Closed | Approved as Noted | 2021-06-09 | Chad Francis (Populous) | Josh Broussard (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| 17545 | Reopened | Additional Information | 2021-06-16 16:48 | Chad Francis (Populous) |  |  | revised review comments to coordinate counter dims with RFI-3240
| 17546 | Responded and Closed | Approved as Noted | 2021-06-16 | Chad Francis (Populous) | Josh Broussard (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | REVISED RESPONSE TO APPROVE SUBMITTED COUNTER DIMENSIONS PER RFI-3240 RESPONSE. PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-01 |  | 062023-079 Coors Bars.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-01 |  | 062023-079 Coors Bars.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-09 |  | 062023-079 Coors Bars_POP.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-16 |  | 062023-079 Coors Bars_POP rev.pdf
06 20 23-080-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-080-00 06.25.01 Home GM Casework | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-03 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-17 | 2021-06-07 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13374 | Received | For Review | 2021-06-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-06-17 | Submittal Number: 06 20 23-80.0 From: MIKE SOLFELT Final Due Date: 06/17/21 Subject: 06.25.01 HOME GM CASEWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17302 | Forwarded | For Review | 2021-06-03 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-10 | Submittal Number: 06 20 23-80.0 From: MIKE SOLFELT Final Due Date: 06/17/21 Subject: 06.25.01 HOME GM CASEWORK Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13430 | Review Response | Approved as Noted | 2021-06-07 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17368 | Responded and Closed | Approved as Noted | 2021-06-07 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-03 |  | 062023-080 Home GM Casework.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-03 |  | 062023-080 Home GM Casework.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-07 |  | 062023-080 Home GM Casework_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-06-03 |  | 062023-080 Home GM Casework.pdf
06 20 23-081-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-081-00 Misc. Premium Space Millwork Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-28 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-13 07:00 | 2021-07-13 | 16 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13666 | Received | For Review | 2021-06-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (Mortenson Construction) | 2021-07-13 07:00 | Submittal Number: 06 20 23-81.0 From: JOSH BROUSSARD Final Due Date: 07/24/21 Subject: MISC. PREMIUM SPACE MILLWORK SAMPLES Description: SAMPLE 1: WHISKEY BAR BACK BAR SHELVING WOOD VENEER SAMPLE 2: SHELVING ACRYLIC SAMPLE 3: LIQUOR RISER P39 METAL PLATE SAMPLE 4: METRO CLUB CHEMETAL Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17695 | Forwarded | For Review | 2021-06-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-05 | Submittal Number: 06 20 23-81.0 From: JOSH BROUSSARD Final Due Date: 07/24/21 Subject: MISC. PREMIUM SPACE MILLWORK SAMPLES Description: SAMPLE 1: WHISKEY BAR BACK BAR SHELVING WOOD VENEER SAMPLE 2: SHELVING ACRYLIC SAMPLE 3: LIQUOR RISER P39 METAL PLATE SAMPLE 4: METRO CLUB CHEMETAL Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13920 | Review Response | Approved as Noted | 2021-07-13 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18022 | Responded and Closed | Approved as Noted | 2021-07-13 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-26 |  | 06 20 23-81.0 Misc. Premium Space Millwork Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-26 |  | 06 20 23-81.0 Misc. Premium Space Millwork Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-13 |  | 06 20 23-81.0 Misc. Premium Space Millwork Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-06-26 |  | 06 20 23-81.0 Misc. Premium Space Millwork Samples.pdf
06 20 23-082-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-082-00 Kraken Back Bar Display | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-08 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-22 | 2021-07-13 | 6 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13829 | Received | For Review | 2021-07-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-07-22 | Submittal Number: 06 20 23-82.0 From: MIKE SOLFELT Final Due Date: 07/14/21 Subject: KRAKEN BACK BAR DISPLAY Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 17903 | Forwarded | For Review | 2021-07-07 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-14 | Submittal Number: 06 20 23-82.0 From: MIKE SOLFELT Final Due Date: 07/14/21 Subject: KRAKEN BACK BAR DISPLAY Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 13918 | Review Response | Approved as Noted | 2021-07-13 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18020 | Responded and Closed | Approved as Noted | 2021-07-13 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-07 |  | 062023-082 Kraken Bar Back Display.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-07 |  | 062023-082 Kraken Bar Back Display.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-13 |  | 062023-082 Kraken Bar Back Display_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-07 |  | 062023-082 Kraken Bar Back Display.pdf
06 20 23-083-00 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-083-00 Millwork LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-30 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Courtney France (France Sustainable Solutions), Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2021-09-13 | 2021-08-31 | 2 |  | Record Copies; Transfers; Submittals | 06 20 23-083-00-01 - 06 20 23-083-00 Millwork LEED Data | 2 |  | 2021-08-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14525 | Received | For Review | 2021-08-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-13 | Submittal Number: 06 20 23-83.0 From: MIKE SOLFELT Final Due Date: 09/13/21 Subject: MILLWORK LEED DATA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 18726 | Forwarded | For Review | 2021-08-30 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Courtney France (France Sustainable Solutions); Kuebler Perry (Populous); Chad Francis (Populous) | 2021-09-06 | Submittal Number: 06 20 23-83.0 From: MIKE SOLFELT Final Due Date: 09/13/21 Subject: MILLWORK LEED DATA Description: Spec Section: 06 20 23 - INTERIOR FINISH CARPENTRY Status: OPEN | Info Exchange
| 18735 | Responded and Closed | Revise and Resubmit | 2021-08-31 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | RESUBMIT WITH THE FOLLOWING: a)EPD’s noted on coversheet (‘Product Specific’) for all, please provide qualifying EPD’s, if they exist (PS or IW). b)Recycled content claims for products must conform to the definition in ISO 14021–1999, Environmental Labels and Declarations, Self-Declared Environmental Claims (Type II Environmental Labeling), please provide qualifying manufacturer’s back-up. c)Any FSC wood products that contribute to the credit achievement must include the FSC Certificate and the invoice with the vendor’s CoC certificate code. d)For FSC mixed products, the recycled content value is not eligible for the same product value. FSC Mixed [NN]% count for the percentage of FSC wood value only. e)HPD’s noted on coversheet (x9?), please provide qualifying back-up. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-30 02:00 |  | 062023-083 Millwork LEED Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-30 02:00 |  | 062023-083 Millwork LEED Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-08-31 |  | 062023-083 Millwork LEED Data_MAM_POP.pdf
06 20 23-083-00-01 | 06 20 23 - INTERIOR FINISH CARPENTRY | 06 20 23-083-00 Millwork LEED Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 20 23-083-00 - 06 20 23-083-00 Millwork LEED Data | -1 | 2021-09-14
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-31 |  | 062023-083 Millwork LEED Data_MAM_POP.pdf
06 41 13-001-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-001-00 Artist Lounge & Star Dressing Shop Drawings - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-20 | 2020-07-13 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06765 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 06 41 13-1.0 From: JOSH BROUSSARD Final Due Date: 07/17/20 Subject: ARTIST LOUNGE & STAR DRESSING SHOP DRAWINGS - BASE BUILDING Description: THIS SUBMITTAL INCLUDES SHOP DRAWINGS FOR WARDROBES, COUNTERTOPS AND CASEWORK IN THE EVENT LEVEL ARTIST LOUNGE AND STAR DRESSING ROOM. STONE INSERTS WITHIN WOOD COUNTERTOPS ARE ALSO PART OF THIS PACKAGE. Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 09093 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-07-13 | Submittal Number: 06 41 13-1.0 From: JOSH BROUSSARD Final Due Date: 07/17/20 Subject: ARTIST LOUNGE & STAR DRESSING SHOP DRAWINGS - BASE BUILDING Description: THIS SUBMITTAL INCLUDES SHOP DRAWINGS FOR WARDROBES, COUNTERTOPS AND CASEWORK IN THE EVENT LEVEL ARTIST LOUNGE AND STAR DRESSING ROOM. STONE INSERTS WITHIN WOOD COUNTERTOPS ARE ALSO PART OF THIS PACKAGE. Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 06917 | Review Response | Approved as Noted | 2020-07-13 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | See attached submittal review. | Mail
| 09259 | Responded and Closed | Approved as Noted | 2020-07-13 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-03 |  | 06 41 13-1.0 Artist Lounge & Star Dressing Shop Dwgs - Base Bldg.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-03 |  | 06 41 13-1.0 Artist Lounge & Star Dressing Shop Dwgs - Base Bldg.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-07-13 |  | 06 41 13-1.0 Artist Lounge & Star Dressing Shop Dwgs - Base Bldg_POP Final.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-03 |  | 06 41 13-1.0 Artist Lounge & Star Dressing Shop Dwgs - Base Bldg.pdf
06 41 13-005-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-005-00 WOOD-VENEER-FACED ARCHITECTURAL CABINETS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-17 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-01 | 2020-09-29 | 13 |  | Record Copies; Transfers; Submittals | 06 41 13-005-01 - 06 41 13-005-01 WD6 and WD4 Resubmit | 13 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08169 | Received | For Review | 2020-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-01 | Submittal Number: 06 41 13-5.0 From: MIKE SOLFELT Final Due Date: 10/01/20 Subject: WOOD-VENEER-FACED ARCHITECTURAL CABINETS - SAMPLES Description: SAMPLES FOR VERIFICATION : - 1. LUMBER FOR TRANSPARENT FINISH, NOT LESS THAN 5 INCHES WIDE BY 24 INCHES LONG, FOR EACH SPECIES AND CUT, FINISHED ON ONE SIDE AND ONE EDGE. 2. VENEER LEAVES REPRESENTATIVE OF AND SELECTED FROM FLITCHES TO BE USED FOR TRANSPARENT- FINISHED CABINETS. 3. LUMBER AND PANEL PRODUCTS WITH SHOP-APPLIED OPAQUE FINISH, 5 INCHES WIDE BY 12 INCHES LONG FOR LUMBER AND 8 BY 10 INCHES FOR PANELS, FOR EACH FINISH SYSTEM AND COLOR, WITH ONE- HALF OF EXPOSED SURFACE FINISHED. 4. THERMOSET DECORATIVE PANELS, 8 BY 10 INCHES, FOR EACH COLOR, PATTERN, AND SURFACE FINISH, WITH EDGE BANDING ON ONE EDGE. 5. CORNER PIECES AS FOLLOWS: A. CABINET-FRONT FRAME JOINTS BETWEEN STILES AND RAILS, AS WELL AS EXPOSED END PIECES, 18 INCHES HIGH BY 18 INCHES WIDE BY 6 INCHES DEEP. B. MITER JOINTS FOR STANDING TRIM. 6. EXPOSED CABINET HARDWARE AND ACCESSORIES, ONE UNIT FOR EACH TYPE AND FINISH. Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 10847 | Forwarded | For Review | 2020-09-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-24 | Submittal Number: 06 41 13-5.0 From: MIKE SOLFELT Final Due Date: 10/01/20 Subject: WOOD-VENEER-FACED ARCHITECTURAL CABINETS - SAMPLES Description: SAMPLES FOR VERIFICATION : - 1. LUMBER FOR TRANSPARENT FINISH, NOT LESS THAN 5 INCHES WIDE BY 24 INCHES LONG, FOR EACH SPECIES AND CUT, FINISHED ON ONE SIDE AND ONE EDGE. 2. VENEER LEAVES REPRESENTATIVE OF AND SELECTED FROM FLITCHES TO BE USED FOR TRANSPARENT- FINISHED CABINETS. 3. LUMBER AND PANEL PRODUCTS WITH SHOP-APPLIED OPAQUE FINISH, 5 INCHES WIDE BY 12 INCHES LONG FOR LUMBER AND 8 BY 10 INCHES FOR PANELS, FOR EACH FINISH SYSTEM AND COLOR, WITH ONE- HALF OF EXPOSED SURFACE FINISHED. 4. THERMOSET DECORATIVE PANELS, 8 BY 10 INCHES, FOR EACH COLOR, PATTERN, AND SURFACE FINISH, WITH EDGE BANDING ON ONE EDGE. 5. CORNER PIECES AS FOLLOWS: A. CABINET-FRONT FRAME JOINTS BETWEEN STILES AND RAILS, AS WELL AS EXPOSED END PIECES, 18 INCHES HIGH BY 18 INCHES WIDE BY 6 INCHES DEEP. B. MITER JOINTS FOR STANDING TRIM. 6. EXPOSED CABINET HARDWARE AND ACCESSORIES, ONE UNIT FOR EACH TYPE AND FINISH. Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 08429 | Review Response | Approved as Noted/Resubmit | 2020-09-29 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | See attached submittal review. Resubmit WD4 only. | Info Exchange
| 11167 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-29 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal review. Resubmit WD4 only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-17 |  | 06 41 13-005 Wood Veneer Faced Arch. Cabinets Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-17 |  | 06 41 13-005 Wood Veneer Faced Arch. Cabinets Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-29 |  | 06 41 13-005 Wood Veneer Faced Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-17 |  | 06 41 13-005 Wood Veneer Faced Arch. Cabinets Samples.pdf
06 41 13-005-01 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-005-01 WD6 and WD4 Resubmit | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-18 | Responded and Closed - Approved |  | Kuebler Perry (Populous) |  |  |  | 2021-03-04 | 2021-03-05 | 16 |  | Record Copies; Transfers; Submittals | 06 41 13-005-00 - 06 41 13-005-00 WOOD-VENEER-FACED ARCHITECTURAL CABINETS - Samples | 15 | 2020-10-13 | 2021-03-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11531 | Received | For Review | 2021-02-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-03-04 | Submittal Number: 06 41 13-5.1 From: MIKE SOLFELT Final Due Date: 03/01/21 Subject: WD6 AND WD4 RESUBMIT Description: SAMPLES FOR VERIFICATION : - 1. LUMBER FOR TRANSPARENT FINISH, NOT LESS THAN 5 INCHES WIDE BY 24 INCHES LONG, FOR EACH SPECIES AND CUT, FINISHED ON ONE SIDE AND ONE EDGE. 2. VENEER LEAVES REPRESENTATIVE OF AND SELECTED FROM FLITCHES TO BE USED FOR TRANSPARENT- FINISHED CABINETS. 3. LUMBER AND PANEL PRODUCTS WITH SHOP-APPLIED OPAQUE FINISH, 5 INCHES WIDE BY 12 INCHES LONG FOR LUMBER AND 8 BY 10 INCHES FOR PANELS, FOR EACH FINISH SYSTEM AND COLOR, WITH ONE- HALF OF EXPOSED SURFACE FINISHED. 4. THERMOSET DECORATIVE PANELS, 8 BY 10 INCHES, FOR EACH COLOR, PATTERN, AND SURFACE FINISH, WITH EDGE BANDING ON ONE EDGE. 5. CORNER PIECES AS FOLLOWS: A. CABINET-FRONT FRAME JOINTS BETWEEN STILES AND RAILS, AS WELL AS EXPOSED END PIECES, 18 INCHES HIGH BY 18 INCHES WIDE BY 6 INCHES DEEP. B. MITER JOINTS FOR STANDING TRIM. 6. EXPOSED CABINET HARDWARE AND ACCESSORIES, ONE UNIT FOR EACH TYPE AND FINISH. Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14946 | Forwarded | For Review | 2021-02-19 | Josh Dobken (Populous) | Kuebler Perry (Populous) | 2021-02-26 | Submittal Number: 06 41 13-5.1 From: MIKE SOLFELT Final Due Date: 03/01/21 Subject: WD6 AND WD4 RESUBMIT Description: SAMPLES FOR VERIFICATION : - 1. LUMBER FOR TRANSPARENT FINISH, NOT LESS THAN 5 INCHES WIDE BY 24 INCHES LONG, FOR EACH SPECIES AND CUT, FINISHED ON ONE SIDE AND ONE EDGE. 2. VENEER LEAVES REPRESENTATIVE OF AND SELECTED FROM FLITCHES TO BE USED FOR TRANSPARENT- FINISHED CABINETS. 3. LUMBER AND PANEL PRODUCTS WITH SHOP-APPLIED OPAQUE FINISH, 5 INCHES WIDE BY 12 INCHES LONG FOR LUMBER AND 8 BY 10 INCHES FOR PANELS, FOR EACH FINISH SYSTEM AND COLOR, WITH ONE- HALF OF EXPOSED SURFACE FINISHED. 4. THERMOSET DECORATIVE PANELS, 8 BY 10 INCHES, FOR EACH COLOR, PATTERN, AND SURFACE FINISH, WITH EDGE BANDING ON ONE EDGE. 5. CORNER PIECES AS FOLLOWS: A. CABINET-FRONT FRAME JOINTS BETWEEN STILES AND RAILS, AS WELL AS EXPOSED END PIECES, 18 INCHES HIGH BY 18 INCHES WIDE BY 6 INCHES DEEP. B. MITER JOINTS FOR STANDING TRIM. 6. EXPOSED CABINET HARDWARE AND ACCESSORIES, ONE UNIT FOR EACH TYPE AND FINISH. Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11811 | Review Response | Approved | 2021-03-05 | Kuebler Perry (Populous) | Josh Dobken (Populous) |  |  | Info Exchange
| 15314 | Responded and Closed | Approved | 2021-03-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-18 02:00 |  | 064116-005.1 WD4 and WD6 Samples.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-18 02:00 |  | 064116-005.1 WD4 and WD6 Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-05 |  | 064116-005.1 WD4 and WD6 Samples_MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-18 |  | 064116-005.1 WD4 and WD6 Samples.pdf
06 41 13-011-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-011-00 Player Lounge / Kitchen Casework | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-15 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-29 | 2020-09-28 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-09-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08117 | Received | For Review | 2020-09-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-29 | Submittal Number: 06 41 13-11.0 From: MIKE SOLFELT Final Due Date: 09/16/20 Subject: PLAYER LOUNGE / KITCHEN CASEWORK Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 10785 | Forwarded | For Review | 2020-09-15 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-22 | Submittal Number: 06 41 13-11.0 From: MIKE SOLFELT Final Due Date: 09/16/20 Subject: PLAYER LOUNGE / KITCHEN CASEWORK Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 08372 | Review Response | Revise and Resubmit | 2020-09-28 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Revise and Resubmit. See attached for comments. | Info Exchange
| 11091 | Responded and Closed | Revise and Resubmit | 2020-09-28 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: Revise and Resubmit. See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-14 |  | 06 41 13-11 Player Lounge and Kitchen Casework.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-14 |  | 06 41 13-11 Player Lounge and Kitchen Casework.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-09-28 |  | 06 41 13-11 Player Lounge and Kitchen Casework_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-09-14 |  | 06 41 13-11 Player Lounge and Kitchen Casework.pdf
06 41 13-011-01 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-011-01 Player Lounge Kitchen Casework / War Room | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-22 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-05 | 2020-10-26 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-10-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08937 | Received | For Review | 2020-10-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-05 | Submittal Number: 06 41 13-11.1 From: MIKE SOLFELT Final Due Date: 11/04/20 Subject: PLAYER LOUNGE KITCHEN CASEWORK / WAR ROOM Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11807 | Forwarded | For Review | 2020-10-22 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-29 | Submittal Number: 06 41 13-11.1 From: MIKE SOLFELT Final Due Date: 11/04/20 Subject: PLAYER LOUNGE KITCHEN CASEWORK / WAR ROOM Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 08974 | Review Response | Approved as Noted | 2020-10-26 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 11846 | Responded and Closed | Approved as Noted | 2020-10-26 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-22 |  | 06 41 13-11.1 Player Lounge and Kitchen Casework.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-22 |  | 06 41 13-11.1 Player Lounge and Kitchen Casework.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-10-26 |  | 06 41 13-11.1 Player Lounge and Kitchen Casework_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-22 |  | 06 41 13-11.1 Player Lounge and Kitchen Casework.pdf
06 41 13-012-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-012-00 Sideline Suite Millwork Balance / Mock-up Resubmittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-14 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-28 | 2020-10-29 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-10-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08788 | Received | For Review | 2020-10-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-28 | Submittal Number: 06 41 13-12.0 From: MIKE SOLFELT Final Due Date: 10/28/20 Subject: SIDELINE SUITE MILLWORK BALANCE / MOCK-UP RESUBMITTAL Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11618 | Forwarded | For Review | 2020-10-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-21 | Submittal Number: 06 41 13-12.0 From: MIKE SOLFELT Final Due Date: 10/28/20 Subject: SIDELINE SUITE MILLWORK BALANCE / MOCK-UP RESUBMITTAL Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11958 | Responded and Closed | Approved as Noted | 2020-10-28 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| 12007 | Reopened | Additional Information | 2020-10-29 12:44 | Chad Francis (Populous) |  |  | RESENDING ATTACHMENT
| 12008 | Responded and Closed | Approved as Noted | 2020-10-29 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-14 |  | 064113-012 Sideline Suite Millwork Balance and Mock-up Resubmittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-14 |  | 064113-012 Sideline Suite Millwork Balance and Mock-up Resubmittal.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-14 |  | 064113-012 Sideline Suite Millwork Balance and Mock-up Resubmittal.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-28 |  | 064113-012 Sideline Suite Millwork Balance and Mock-up Resubmittal_POP.pdf
06 41 13-013-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-013-00 Sideline Suite Millwork | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-08 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-22 | 2020-10-05 | 28 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07964 | Received | For Review | 2020-09-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-22 | Submittal Number: 06 41 13-13.0 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: TUNNEL SUITE MILLWORK Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 10589 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-15 | Submittal Number: 06 41 13-13.0 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: TUNNEL SUITE MILLWORK Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11148 | Responded and Closed | Rejected | 2020-09-29 | Populous SCA_CCA | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | INCORRECT INFORMATION PROVIDED IN THIS SUBMITTAL. CONTRACTOR TO CONFIRM IF DESIGN TEAM WAS SUPPOSED TO RECEIVE TUNNEL SUITE MILLWORK. PLEASE SEND THIS INFORMATION UNDER A NEW NUMBER FOR OFFICIAL REVIEW. | Info Exchange
| 11171 | Reopened | Additional Information | 2020-09-29 18:09 | Josh Dobken (Populous) |  |  | MAM provided corrected information 9/29. Submittal review response to be updated.
| 11290 | Responded and Closed | Approved as Noted | 2020-10-05 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-08 |  | 064113-013 Tunnel Suite Millwork (Mock-Up).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-08 |  | 064113-013 Tunnel Suite Millwork (Mock-Up).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-29 02:00 |  | 064113-013 Tunnel Suite Millwork (Mock-Up)_pop.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-05 |  | 064113-013 Sideline Suite Millwork (Mock-Up)_pop.pdf
06 41 13-014-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-014-00 Player Lounge Wall Cubby | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-19 | 2020-10-13 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08547 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 06 41 13-14.0 From: MIKE SOLFELT Final Due Date: 09/16/20 Subject: PLAYER LOUNGE WALL CUBBY Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11309 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-12 | Submittal Number: 06 41 13-14.0 From: MIKE SOLFELT Final Due Date: 09/16/20 Subject: PLAYER LOUNGE WALL CUBBY Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 08762 | Review Response | Revise and Resubmit | 2020-10-13 | Kelsea Conkright (Populous) | Shaina Burris (Populous) |  | See comments noted on submittal. | Info Exchange
| 11585 | Responded and Closed | Revise and Resubmit | 2020-10-13 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: See comments noted on submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 064113-014 Player Lounge Wall Cubby and Panel.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 064113-014 Player Lounge Wall Cubby and Panel.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-10-13 |  | 05 75 00-014 Ornn Metal NHL Locker Room East Entry_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-13 |  | 064113-014 Player Lounge Wall Cubby and Panel_POP.pdf
06 41 13-014-01 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-014-01 Player Lounge Wall Cubby | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-10 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-24 | 2020-11-13 | 4 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-11-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09323 | Received | For Review | 2020-11-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-24 | Submittal Number: 06 41 13-14.1 From: MIKE SOLFELT Final Due Date: 11/23/20 Subject: PLAYER LOUNGE WALL CUBBY Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 12304 | Forwarded | For Review | 2020-11-09 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-16 | Submittal Number: 06 41 13-14.1 From: MIKE SOLFELT Final Due Date: 11/23/20 Subject: PLAYER LOUNGE WALL CUBBY Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 09426 | Review Response | Approved as Noted | 2020-11-13 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12432 | Responded and Closed | Approved as Noted | 2020-11-13 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-09 |  | 064113-014.1 Player Lounge Wall Cubby and Panel.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-09 |  | 064113-014.1 Player Lounge Wall Cubby and Panel.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-11-13 |  | 064113-014.1 Player Lounge Wall Cubby and Panel_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-09 |  | 064113-014.1 Player Lounge Wall Cubby and Panel.pdf
06 41 13-015-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-015-00 NHL Locker Room Misc. Lockers | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-09 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-23 | 2021-03-02 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11296 | Received | For Review | 2021-02-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-23 | Submittal Number: 06 41 13-15.0 From: MIKE SOLFELT Final Due Date: 02/19/21 Subject: NHL LOCKER ROOM MISC. LOCKERS Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14644 | Forwarded | For Review | 2021-02-09 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-16 | Submittal Number: 06 41 13-15.0 From: MIKE SOLFELT Final Due Date: 02/19/21 Subject: NHL LOCKER ROOM MISC. LOCKERS Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11760 | Review Response | Revise and Resubmit | 2021-03-02 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15239 | Responded and Closed | Revise and Resubmit | 2021-03-02 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-19 |  | 06 41 13 - 15 NHL Area Lockers.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-09 |  | Transmittal_Submittal - 06 41 13-015-00 (Forwarded).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-19 |  | 06 41 13 - 15 NHL Area Lockers.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-02 |  | 06 41 13 - 15 NHL Area Lockers_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-02-19 |  | 06 41 13 - 15 NHL Area Lockers.pdf
06 41 13-015-01 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-015-01 NHL Locker Room Misc. Lockers | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-07 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-04-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12390 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 06 41 13-15.1 From: MIKE SOLFELT Final Due Date: 04/09/21 Subject: NHL LOCKER ROOM MISC. LOCKERS Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 16048 | Forwarded | For Review | 2021-04-05 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-12 | Submittal Number: 06 41 13-15.1 From: MIKE SOLFELT Final Due Date: 04/09/21 Subject: NHL LOCKER ROOM MISC. LOCKERS Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 12455 | Review Response | Approved as Noted | 2021-04-07 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16140 | Responded and Closed | Approved as Noted | 2021-04-07 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 06 41 13-15.1 NHL Locker Room Misc. Lockers.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 06 41 13-15.1 NHL Locker Room Misc. Lockers.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-07 |  | 06 41 13-15.1 NHL Locker Room Misc. Lockers_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 06 41 13-15.1 NHL Locker Room Misc. Lockers.pdf
06 41 13-016-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-016-00 WD16 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-14 | 2020-10-15 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-10-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08445 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-14 | Submittal Number: 06 41 13-16.0 From: MIKE SOLFELT Final Due Date: 10/09/20 Subject: WD16 SAMPLE Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11186 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-07 | Submittal Number: 06 41 13-16.0 From: MIKE SOLFELT Final Due Date: 10/09/20 Subject: WD16 SAMPLE Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 08802 | Review Response | Approved | 2020-10-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11635 | Responded and Closed | Approved | 2020-10-15 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 06 20 23-0016 WD16 Engineered Flooring Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 06 20 23-0016 WD16 Engineered Flooring Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-15 |  | 06 20 23-0016 WD16 Engineered Flooring Sample POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-15 |  | 06 20 23-0016 WD16 Engineered Flooring Sample POP.pdf
06 41 13-016-01 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-016-01 WD16 Sample - Satin Finish | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-21 | 2020-12-17 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09944 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-21 | Submittal Number: 06 41 13-16.1 From: MIKE SOLFELT Final Due Date: 12/15/20 Subject: WD16 SAMPLE - SATIN FINISH Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 13024 | Forwarded | For Review | 2020-12-07 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 06 41 13-16.1 From: MIKE SOLFELT Final Due Date: 12/15/20 Subject: WD16 SAMPLE - SATIN FINISH Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 10237 | Review Response | Approved | 2020-12-17 | Kuebler Perry (Populous) | pop |  | Refer to attached submittal response. | Info Exchange
| 13377 | Responded and Closed | Approved | 2020-12-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 06 41 13-16.1 - WD16 Satin Finish.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-07 |  | 06 41 13-16.1 - WD16 Satin Finish.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-17 |  | 06 41 13-16.1 - WD16 Satin Finish_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-07 |  | 06 41 13-16.1 - WD16 Satin Finish.pdf
06 41 13-017-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-017-00 Premium WD Samples Pkg. 2 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-07 | Responded and Closed - Approved as Noted/Resubmit |  | Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2020-10-21 | 2020-10-20 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08652 | Received | For Review | 2020-10-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-21 | Submittal Number: 06 41 13-17.0 From: MIKE SOLFELT Final Due Date: 10/19/20 Subject: PREMIUM WD SAMPLES PKG. 2 Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11430 | Forwarded | For Review | 2020-10-08 | Josh Dobken (Populous) | Kuebler Perry (Populous); Chad Francis (Populous) | 2020-10-15 | Submittal Number: 06 41 13-17.0 From: MIKE SOLFELT Final Due Date: 10/19/20 Subject: PREMIUM WD SAMPLES PKG. 2 Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 08872 | Review Response | Approved as Noted/Resubmit | 2020-10-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review for individual R/R criteria. Confirm Rockwell's approval before beginning fabrication. | Info Exchange
| 11731 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review for individual R/R criteria. Confirm Rockwell's approval before beginning fabrication. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-06 02:00 |  | 064113-017 Premium Wood Samples Package 2.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-06 02:00 |  | 064113-017 Premium Wood Samples Package 2.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-20 |  | 064113-017 Premium Wood Samples Package 2 POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-06 |  | 064113-017 Premium Wood Samples Package 2.pdf
06 41 13-017-01 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-017-01 WD12 Sample Resubmit | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-12 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-30 08:00 | 2020-11-23 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-11-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09392 | Received | For Review | 2020-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-30 08:00 | Submittal Number: 06 41 13-17.1 From: MIKE SOLFELT Final Due Date: 11/20/20 Subject: WD12 SAMPLE RESUBMIT Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 12396 | Forwarded | For Review | 2020-11-12 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-19 | Submittal Number: 06 41 13-17.1 From: MIKE SOLFELT Final Due Date: 11/20/20 Subject: WD12 SAMPLE RESUBMIT Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 09692 | Review Response | Approved | 2020-11-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12747 | Responded and Closed | Approved | 2020-11-23 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-11 |  | 064113-017.1 WD12 Sample Resubmit.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-11 |  | 064113-017.1 WD12 Sample Resubmit.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-23 |  | 064113-017.1 WD12 Sample Resubmit_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-11 |  | 064113-017.1 WD12 Sample Resubmit.pdf
06 41 13-018-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-018-00 Locker Room Mock-Up | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-15 | Responded and Closed - No Action Taken or Required |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-29 | 2020-10-26 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-10-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08805 | Received | For Review | 2020-10-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-29 | Submittal Number: 06 41 13-18.0 From: MIKE SOLFELT Final Due Date: 10/29/20 Subject: LOCKER ROOM MOCK-UP Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11638 | Forwarded | For Review | 2020-10-15 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-22 | Submittal Number: 06 41 13-18.0 From: MIKE SOLFELT Final Due Date: 10/29/20 Subject: LOCKER ROOM MOCK-UP Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 09000 | Review Response | No Action Taken or Required | 2020-10-26 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | OWNERSHIP DIRECTED HOLD ON WORK. | Info Exchange
| 11874 | Responded and Closed | No Action Taken or Required | 2020-10-26 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Kelsea Conkright (Populous) Remarks: OWNERSHIP DIRECTED HOLD ON WORK. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-15 |  | 06 41 13-018 Mock-Up Development Drawings for Home Locker.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-15 |  | 06 41 13-018 Mock-Up Development Drawings for Home Locker.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-10-15 |  | 06 41 13-018 Mock-Up Development Drawings for Home Locker.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-15 |  | 06 41 13-018 Mock-Up Development Drawings for Home Locker.pdf
06 41 13-018-01 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-018-01 NHL Locker TV Cabinet | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-27 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-10 | 2021-02-03 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-02-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10990 | Received | For Review | 2021-01-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-10 | Submittal Number: 06 41 16-18.0 From: MIKE SOLFELT Final Due Date: 01/19/21 Subject: NHL LOCKER TV CABINET Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14274 | Forwarded | For Review | 2021-01-27 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-03 | Submittal Number: 06 41 16-18.0 From: MIKE SOLFELT Final Due Date: 01/19/21 Subject: NHL LOCKER TV CABINET Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11177 | Review Response | Approved as Noted | 2021-02-03 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14483 | Responded and Closed | Approved as Noted | 2021-02-03 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-26 |  | 062023-018 Main Concourse Club For Record.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-26 |  | 062023-018 Main Concourse Club For Record.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-03 |  | 064113-018-1 NHL Locker TV Cabinet_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-26 |  | 062023-018 Main Concourse Club For Record.pdf
06 41 13-019-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-019-00 WD11 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-27 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-10 | 2020-11-10 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-11-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09025 | Received | For Review | 2020-10-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-10 | Submittal Number: 06 41 13-19.0 From: MIKE SOLFELT Final Due Date: 11/10/20 Subject: WD11 SAMPLE Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11906 | Forwarded | For Review | 2020-10-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-03 | Submittal Number: 06 41 13-19.0 From: MIKE SOLFELT Final Due Date: 11/10/20 Subject: WD11 SAMPLE Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 09338 | Review Response | Revise and Resubmit | 2020-11-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12319 | Responded and Closed | Revise and Resubmit | 2020-11-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 064113-019 WD11 Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 064113-019 WD11 Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-10 |  | 064113-019 WD11 Sample_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-27 |  | 064113-019 WD11 Sample.pdf
06 41 13-019-01 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-019-01 WD11 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-20 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-08 | 2020-11-24 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-11-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09637 | Received | For Review | 2020-11-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-12-08 | Submittal Number: 06 41 13-19.1 From: MIKE SOLFELT Final Due Date: 12/04/20 Subject: WD11 SAMPLE Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 12680 | Forwarded | For Review | 2020-11-20 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-27 | Submittal Number: 06 41 13-19.1 From: MIKE SOLFELT Final Due Date: 12/04/20 Subject: WD11 SAMPLE Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 09718 | Review Response | Approved | 2020-11-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | See attached submittal review. | Info Exchange
| 12779 | Responded and Closed | Approved | 2020-11-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-20 |  | 064113-019.1 WD11 Sample Rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-20 |  | 064113-019.1 WD11 Sample Rev 1.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-24 |  | 064113-019.1 WD11 Sample Rev 1_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-20 |  | 064113-019.1 WD11 Sample Rev 1.pdf
06 41 13-020-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-020-00 WD10/WD13 Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-04 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-18 | 2020-11-23 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-11-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09226 | Received | For Review | 2020-11-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-18 | Submittal Number: 06 41 13-20.0 From: MIKE SOLFELT Final Due Date: 11/18/20 Subject: WD10/WD13 SAMPLES Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 12182 | Forwarded | For Review | 2020-11-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-11 | Submittal Number: 06 41 13-20.0 From: MIKE SOLFELT Final Due Date: 11/18/20 Subject: WD10/WD13 SAMPLES Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 09678 | Review Response | Approved as Noted | 2020-11-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12731 | Responded and Closed | Approved as Noted | 2020-11-23 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-04 |  | 064113-020 WD10 and WD13 Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-04 |  | 064113-020 WD10 and WD13 Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-23 |  | 064113-020 WD10 and WD13 Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-04 |  | 064113-020 WD10 and WD13 Samples.pdf
06 41 13-021-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-021-00 WNBA Home Lockers | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-02-25 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11417 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-01 | Submittal Number: 06 41 13-21.0 From: MIKE SOLFELT Final Due Date: 02/26/21 Subject: WNBA HOME LOCKERS Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14784 | Forwarded | For Review | 2021-02-15 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 06 41 13-21.0 From: MIKE SOLFELT Final Due Date: 02/26/21 Subject: WNBA HOME LOCKERS Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 15101 | Responded and Closed | Approved as Noted | 2021-02-25 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 064113-21 WNBA Home Lockers.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-15 |  | 064113-21 WNBA Home Lockers.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-25 |  | 064113-21 WNBA Home Lockers_POP.pdf
06 41 13-022-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-022-00 NHL Home Team Locker | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-06 | 2 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12366 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 06 41 13-22.0 From: MIKE SOLFELT Final Due Date: 04/13/21 Subject: NHL HOME TEAM LOCKER Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 16022 | Forwarded | For Review | 2021-04-01 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 06 41 13-22.0 From: MIKE SOLFELT Final Due Date: 04/13/21 Subject: NHL HOME TEAM LOCKER Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 12433 | Review Response | Approved as Noted | 2021-04-06 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16110 | Responded and Closed | Approved as Noted | 2021-04-06 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 06 41 13-22.0 NHL Home Team Locker Room.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 06 41 13-22.0 NHL Home Team Locker Room.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-06 |  | 06 41 13-22.0 NHL Home Team Locker Room_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 06 41 13-22.0 NHL Home Team Locker Room.pdf
06 41 13-023-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-023-00 Sideline Suite - Owner / Corner | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-22 | 2021-02-23 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-02-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11267 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-22 | Submittal Number: 06 41 13-23.0 From: MIKE SOLFELT Final Due Date: 02/22/21 Subject: SIDELINE SUITE - OWNER / CORNER Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14598 | Forwarded | For Review | 2021-02-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-15 | Submittal Number: 06 41 13-23.0 From: MIKE SOLFELT Final Due Date: 02/22/21 Subject: SIDELINE SUITE - OWNER / CORNER Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 15030 | Responded and Closed | Approved as Noted | 2021-02-23 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED 1. FIELD VERIFY ALL DIMENSIONS AND EQUIPMENT CLEARANCES. 2. CM TO COORDINATE ROCKWELL COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-08 |  | 064113-23 Sideline Suite - Owner and Corner.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-08 |  | 064113-23 Sideline Suite - Owner and Corner.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-23 |  | 064113-23 Sideline Suite - Owner and Corner_POP.pdf
06 41 13-024-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-024-00 WD7 Premium Walnut Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-08 | 2021-02-10 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10940 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-08 | Submittal Number: 06 41 13-24.0 From: MIKE SOLFELT Final Due Date: 01/23/21 Subject: WD7 PREMIUM WALNUT SUBMITTAL Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14203 | Forwarded | For Review | 2021-01-25 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-01 | Submittal Number: 06 41 13-24.0 From: MIKE SOLFELT Final Due Date: 01/23/21 Subject: WD7 PREMIUM WALNUT SUBMITTAL Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11308 | Review Response | Approved as Noted | 2021-02-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14659 | Responded and Closed | Approved as Noted | 2021-02-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 064113-024 WD7 Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-25 |  | 064113-024 WD7 Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-10 |  | 064113-024 WD7 Sample_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-25 |  | 064113-024 WD7 Sample.pdf
06 41 13-025-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-025-00 WD13 - IWS | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-27 08:00 | 2021-01-29 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-01-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10645 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-01-27 08:00 | Submittal Number: 06 41 13-25.0 From: MIKE SOLFELT Final Due Date: 01/28/21 Subject: WD13 - IWS Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 13855 | Forwarded | For Review | 2021-01-12 | Mike Solfelt (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-19 | Submittal Number: 06 41 13-25.0 From: MIKE SOLFELT Final Due Date: 01/28/21 Subject: WD13 - IWS Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11049 | Review Response | Approved as Noted | 2021-01-29 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14348 | Responded and Closed | Approved as Noted | 2021-01-29 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 064113-25 WD13 Sample Submittal.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-01-12 |  | 064113-25 WD13 Sample Submittal.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-29 |  | 064113-25 WD13 Sample Submittal_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-01-12 |  | 064113-25 WD13 Sample Submittal.pdf
06 41 13-026-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-026-00 NHL Home Locker Mock Up | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-10 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-24 | 2021-02-22 | 13 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-02-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11303 | Received | For Review | 2021-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Josh Broussard (Mortenson Construction) | 2021-02-24 | Submittal Number: 06 41 13-26.0 From: JOSH BROUSSARD Final Due Date: 02/23/21 Subject: NHL HOME LOCKER MOCK UP Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14654 | Forwarded | For Review | 2021-02-09 | Josh Broussard (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-16 | Submittal Number: 06 41 13-26.0 From: JOSH BROUSSARD Final Due Date: 02/23/21 Subject: NHL HOME LOCKER MOCK UP Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11564 | Review Response | Approved as Noted/Resubmit | 2021-02-22 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14987 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-09 |  | 06 41 13-26.0 NHL Home Locker Mock Up.pdf
| Forwarded |  | Josh Broussard (Mortenson Construction) | 1 | 2021-02-09 |  | 06 41 13-26.0 NHL Home Locker Mock Up.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-22 |  | 06 41 13-26.0 NHL Home Locker Mock Up_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-09 |  | 06 41 13-26.0 NHL Home Locker Mock Up.pdf
06 41 13-026-01 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-026-01 NHL Home Locker Mock Up Rev 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-23 | 2021-04-20 | 12 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12499 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Josh Broussard (Mortenson Construction) | 2021-04-23 | Submittal Number: 06 41 13-26.1 From: JOSH BROUSSARD Final Due Date: 04/15/21 Subject: NHL HOME LOCKER MOCK UP REV 1 Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 16187 | Forwarded | For Review | 2021-04-08 | Josh Broussard (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 06 41 13-26.1 From: JOSH BROUSSARD Final Due Date: 04/15/21 Subject: NHL HOME LOCKER MOCK UP REV 1 Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 12696 | Review Response | Approved | 2021-04-20 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16416 | Responded and Closed | Approved | 2021-04-20 | Josh Broussard (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 06 41 13-26.1 NHL Home Locker Mock Up Rev 1.pdf
| Forwarded |  | Josh Broussard (Mortenson Construction) | 1 | 2021-04-08 |  | 06 41 13-26.1 NHL Home Locker Mock Up Rev 1.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-20 |  | 06 41 13-26.1 NHL Home Locker Mock Up Rev 1_POP.pdf
| Responded and Closed |  | Josh Broussard (Mortenson Construction) | 1 | 2021-04-08 |  | 06 41 13-26.1 NHL Home Locker Mock Up Rev 1.pdf
06 41 13-027-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-027-00 Kraken Team Locker Seat Fabric Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-12 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-26 | 2021-05-05 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-05-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12533 | Received | For Review | 2021-04-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-26 | Submittal Number: 06 41 13-27.0 From: MIKE SOLFELT Final Due Date: 04/26/21 Subject: KRAKEN TEAM LOCKER SEAT FABRIC SAMPLE Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 16235 | Forwarded | For Review | 2021-04-12 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-19 | Submittal Number: 06 41 13-27.0 From: MIKE SOLFELT Final Due Date: 04/26/21 Subject: KRAKEN TEAM LOCKER SEAT FABRIC SAMPLE Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 12953 | Review Response | Approved | 2021-05-05 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16766 | Responded and Closed | Approved | 2021-05-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-12 |  | 064113-27 Kraken Team Locker Seat Fabric.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-12 |  | 064113-27 Kraken Team Locker Seat Fabric.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-05-05 |  | 064113-27 Kraken Team Locker Seat Fabric_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-12 |  | 064113-27 Kraken Team Locker Seat Fabric.pdf
06 41 13-028-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-028-00 Kraken Team Locker Seat Cushion Mock-Up | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-28 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-12 | 2021-05-05 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12831 | Received | For Review | 2021-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Josh Broussard (Mortenson Construction) | 2021-05-12 | Submittal Number: 06 41 13-28.0 From: JOSH BROUSSARD Final Due Date: 05/12/21 Subject: KRAKEN TEAM LOCKER SEAT CUSHION MOCK-UP Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 16607 | Forwarded | For Review | 2021-04-28 | Josh Broussard (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-05 | Submittal Number: 06 41 13-28.0 From: JOSH BROUSSARD Final Due Date: 05/12/21 Subject: KRAKEN TEAM LOCKER SEAT CUSHION MOCK-UP Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 12952 | Review Response | Approved | 2021-05-05 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16753 | Responded and Closed | Approved | 2021-05-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-28 |  | 064113-28 Kraken Team Locker Seat Fabric Mock-Up.pdf
| Forwarded |  | Josh Broussard (Mortenson Construction) | 1 | 2021-04-28 |  | 064113-28 Kraken Team Locker Seat Fabric Mock-Up.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-05-05 |  | 064113-28 Kraken Team Locker Seat Fabric Mock-Up_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-28 |  | 064113-28 Kraken Team Locker Seat Fabric Mock-Up.pdf
06 41 13-029-00 | 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS | 06 41 13-029-00 Whiskey Bar Shelving Veneer / Kraken Bar Acrylic Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-25 | 2021-08-30 | 20 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-08-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14299 | Received | For Review | 2021-08-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-08-25 | Submittal Number: 06 41 13-29.0 From: MIKE SOLFELT Final Due Date: 08/24/21 Subject: WHISKEY BAR SHELVING VENEER / KRAKEN BAR ACRYLIC SAMPLE Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 18468 | Forwarded | For Review | 2021-08-10 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-17 | Submittal Number: 06 41 13-29.0 From: MIKE SOLFELT Final Due Date: 08/24/21 Subject: WHISKEY BAR SHELVING VENEER / KRAKEN BAR ACRYLIC SAMPLE Description: Spec Section: 06 41 13 - WOOD-VENEER-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 18725 | Responded and Closed | Approved as Noted | 2021-08-30 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-10 |  | 064113-029 Whiskey Bar Shelving and Kraken Bar Acrylic Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-10 |  | 064113-029 Whiskey Bar Shelving and Kraken Bar Acrylic Samples.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-08-30 |  | 064113-029 Whiskey Bar Shelving and Kraken Bar Acrylic Samples_POP.pdf
06 41 16-001-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-001-00 P-L Casework & Closet Shelf Shop Drawings Package 1 - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-08 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-22 | 2020-07-21 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06848 | Received | For Review | 2020-07-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-22 | Submittal Number: 06 41 16-1.0 From: JOSH BROUSSARD Final Due Date: 07/21/20 Subject: P-L CASEWORK & CLOSET SHELF SHOP DRAWINGS PACKAGE 1 - BASE BUILDING Description: INCLUDED IN THIS SUBMITTAL ARE PLASTIC LAMINATE CASEWORK SHOP DRAWINGS FOR BASE BUILDING AREAS THROUGHOUT EVENT LEVEL, MACH MEZZANINE, MAIN CONCOURSE, UPPER CONCOURSE, AND BRIDGE LEVEL. WHERE COUNTERTOPS ARE INTEGRAL TO CASEWORK, THOSE SHOP DRAWINGS ARE INCLUDED AS WELL. ADDITIONAL PLASTIC LAMINATE MILLWORK SHOP DRAWINGS WILL BE SUBMITTED AT LATER DATES. Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 09187 | Forwarded | For Review | 2020-07-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-07-15 | Submittal Number: 06 41 16-1.0 From: JOSH BROUSSARD Final Due Date: 07/21/20 Subject: P-L CASEWORK & CLOSET SHELF SHOP DRAWINGS PACKAGE 1 - BASE BUILDING Description: INCLUDED IN THIS SUBMITTAL ARE PLASTIC LAMINATE CASEWORK SHOP DRAWINGS FOR BASE BUILDING AREAS THROUGHOUT EVENT LEVEL, MACH MEZZANINE, MAIN CONCOURSE, UPPER CONCOURSE, AND BRIDGE LEVEL. WHERE COUNTERTOPS ARE INTEGRAL TO CASEWORK, THOSE SHOP DRAWINGS ARE INCLUDED AS WELL. ADDITIONAL PLASTIC LAMINATE MILLWORK SHOP DRAWINGS WILL BE SUBMITTED AT LATER DATES. Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 07065 | Review Response | Approved as Noted/Resubmit | 2020-07-21 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | See attached submittal markup. Refer to individual pages for resubmit criteria. | Mail
| 09454 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-21 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal markup. Refer to individual pages for resubmit criteria. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-07 |  | 06 41 16-1.0 P-L Casework Shop Dwgs Package 1 - Base Bldg.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 06 41 16-1.0 P-L Casework Shop Dwgs Package 1 - Base Bldg.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-07-21 |  | 06 41 16-1.0 P-L Casework Shop Dwgs Package 1 - Base Bldg POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-07 |  | 06 41 16-1.0 P-L Casework Shop Dwgs Package 1 - Base Bldg.pdf
06 41 16-001-01 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-001-01 P-L Casework Shop Drawings - 01.08.05 Resubmit | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-01 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-15 | 2021-02-17 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11087 | Received | For Review | 2021-02-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-15 | Submittal Number: 06 41 16-1.1 From: MIKE SOLFELT Final Due Date: 02/15/21 Subject: P-L CASEWORK SHOP DRAWINGS - 01.08.05 RESUBMIT Description: INCLUDED IN THIS SUBMITTAL ARE PLASTIC LAMINATE CASEWORK SHOP DRAWINGS FOR BASE BUILDING AREAS THROUGHOUT EVENT LEVEL, MACH MEZZANINE, MAIN CONCOURSE, UPPER CONCOURSE, AND BRIDGE LEVEL. WHERE COUNTERTOPS ARE INTEGRAL TO CASEWORK, THOSE SHOP DRAWINGS ARE INCLUDED AS WELL. ADDITIONAL PLASTIC LAMINATE MILLWORK SHOP DRAWINGS WILL BE SUBMITTED AT LATER DATES. Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14385 | Forwarded | For Review | 2021-02-01 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-08 | Submittal Number: 06 41 16-1.1 From: MIKE SOLFELT Final Due Date: 02/15/21 Subject: P-L CASEWORK SHOP DRAWINGS - 01.08.05 RESUBMIT Description: INCLUDED IN THIS SUBMITTAL ARE PLASTIC LAMINATE CASEWORK SHOP DRAWINGS FOR BASE BUILDING AREAS THROUGHOUT EVENT LEVEL, MACH MEZZANINE, MAIN CONCOURSE, UPPER CONCOURSE, AND BRIDGE LEVEL. WHERE COUNTERTOPS ARE INTEGRAL TO CASEWORK, THOSE SHOP DRAWINGS ARE INCLUDED AS WELL. ADDITIONAL PLASTIC LAMINATE MILLWORK SHOP DRAWINGS WILL BE SUBMITTED AT LATER DATES. Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11513 | Review Response | Approved as Noted | 2021-02-17 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14907 | Responded and Closed | Approved as Noted | 2021-02-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-01 |  | 06 41 16-1.1 P-L Casework Shop Drawings - 01.08.05 Resubmit.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-01 |  | 06 41 16-1.1 P-L Casework Shop Drawings - 01.08.05 Resubmit.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-17 |  | 06 41 16-1.1 P-L Casework Shop Drawings - 01.08.05 Resubmit_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-01 |  | 06 41 16-1.1 P-L Casework Shop Drawings - 01.08.05 Resubmit.pdf
06 41 16-002-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-002-00 P-L Lockers Shop Drawings- Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-27 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-10 | 2020-08-10 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07152 | Received | For Review | 2020-07-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-08-10 | Submittal Number: 06 41 16-2.0 From: JOSH BROUSSARD Final Due Date: 07/27/20 Subject: P-L LOCKERS SHOP DRAWINGS- BASE BUILDING Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 09552 | Forwarded | For Review | 2020-07-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-08-03 | Submittal Number: 06 41 16-2.0 From: JOSH BROUSSARD Final Due Date: 07/27/20 Subject: P-L LOCKERS SHOP DRAWINGS- BASE BUILDING Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 07490 | Review Response | Revise and Resubmit | 2020-08-10 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached review. | Info Exchange
| 09976 | Responded and Closed | Revise and Resubmit | 2020-08-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached review | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-27 |  | 064116-002 Plastic-Laminate-Faced Architectural Cabinets.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-27 |  | 064116-002 Plastic-Laminate-Faced Architectural Cabinets.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-10 |  | 064116-002 Plastic-Laminate-Faced Architectural Cabinets_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-27 |  | 064116-002 Plastic-Laminate-Faced Architectural Cabinets.pdf
06 41 16-002-01 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-002-01 P-L Lockers Shop Drawings- Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-04 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-21 | 2020-09-18 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-09-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07963 | Received | For Review | 2020-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-21 | Submittal Number: 06 41 16-2.1 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: P-L LOCKERS SHOP DRAWINGS- BASE BUILDING Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 10588 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-15 | Submittal Number: 06 41 16-2.1 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: P-L LOCKERS SHOP DRAWINGS- BASE BUILDING Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 10878 | Responded and Closed | Approved as Noted | 2020-09-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-04 |  | 064116-002.1 P-L Lockers Shop Drawings - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-04 |  | 064116-002.1 P-L Lockers Shop Drawings - Base Building.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-09-18 |  | 064116-002.1 P-L Lockers Shop Drawings - Base Building_POP.pdf
06 41 16-003-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-003-00 P-L Casework /Countertops Product Data - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-04 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-21 | 2020-09-21 | 18 |  | Record Copies; Transfers; Submittals | 06 41 16-003-00-01 - 06 41 16-003-00 P-L Casework /Countertops Product Data - Base Building | 14 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07962 | Received | For Review | 2020-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-21 | Submittal Number: 06 41 16-3.0 From: JOSH BROUSSARD Final Due Date: 08/14/20 Subject: P-L CASEWORK /COUNTERTOPS PRODUCT DATA - BASE BUILDING Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 10587 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-15 | Submittal Number: 06 41 16-3.0 From: JOSH BROUSSARD Final Due Date: 08/14/20 Subject: P-L CASEWORK /COUNTERTOPS PRODUCT DATA - BASE BUILDING Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 10907 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-21 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SUBMIT REMAINING LAMINATES L12, L13, AND L32 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-04 |  | 064116-003 P-L Casework Countertops Product Data - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-04 |  | 064116-003 P-L Casework Countertops Product Data - Base Building.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-09-21 |  | 064116-003 P-L Casework Countertops Product Data - Base Building_POP.pdf
06 41 16-003-00-01 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-003-00 P-L Casework /Countertops Product Data - Base Building | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 41 16-003-00 - 06 41 16-003-00 P-L Casework /Countertops Product Data - Base Building | -1 | 2020-10-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 064116-003 P-L Casework Countertops Product Data - Base Building_POP.pdf
06 41 16-015-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-015-00 NHL Locker Area Casework | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-21 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-05 | 2020-10-08 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08240 | Received | For Review | 2020-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-05 | Submittal Number: 06 41 16-15.0 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: NHL LOCKER AREA CASEWORK Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 10945 | Forwarded | For Review | 2020-09-21 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-28 | Submittal Number: 06 41 16-15.0 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: NHL LOCKER AREA CASEWORK Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 08659 | Review Response | Revise and Resubmit | 2020-10-08 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Revise and Resubmit | Info Exchange
| 11437 | Responded and Closed | Revise and Resubmit | 2020-10-08 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: Revise and Resubmit | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 064116-015 NHL Locker Area Casework.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-21 |  | 064116-015 NHL Locker Area Casework.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-10-08 |  | 064116-015 NHL Locker Area Casework_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-09-21 |  | 064116-015 NHL Locker Area Casework.pdf
06 41 16-015-01 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-015-01 NHL Locker Room Prototype Drawing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-18 | 2021-01-12 | 9 |  | Record Copies; Transfers; Submittals | 06 41 16-015-01-01 - 06 41 16-015-01 NHL Locker Room Prototype Drawing | 9 |  | 2021-01-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10394 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2021-01-18 | Submittal Number: 06 41 16-15.1 From: MIKE SOLFELT Final Due Date: 01/13/21 Subject: NHL LOCKER ROOM PROTOTYPE DRAWING Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 13578 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 06 41 16-15.1 From: MIKE SOLFELT Final Due Date: 01/13/21 Subject: NHL LOCKER ROOM PROTOTYPE DRAWING Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 10620 | Review Response | Approved as Noted/Resubmit | 2021-01-12 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13828 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-12 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-30 |  | 064116-015.1 NHL Locker Room Protoype.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-30 |  | 064116-015.1 NHL Locker Room Protoype.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-12 |  | 064116-015.1 NHL Locker Room Protoype_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-30 |  | 064116-015.1 NHL Locker Room Protoype.pdf
06 41 16-015-01-01 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-015-01 NHL Locker Room Prototype Drawing | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 41 16-015-01 - 06 41 16-015-01 NHL Locker Room Prototype Drawing | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-30 |  | 064116-015.1 NHL Locker Room Protoype.pdf
06 41 16-016-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-016-00 Vanity / Tower Drop Event Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-08 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-22 | 2020-09-16 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-09-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07976 | Received | For Review | 2020-09-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-09-22 | Submittal Number: 06 41 16-16.0 From: MIKE SOLFELT Final Due Date: 09/07/20 Subject: VANITY / TOWER DROP EVENT LEVEL Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 10606 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-15 | Submittal Number: 06 41 16-16.0 From: MIKE SOLFELT Final Due Date: 09/07/20 Subject: VANITY / TOWER DROP EVENT LEVEL Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 08138 | Review Response | Revise and Resubmit | 2020-09-16 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Revise and Resubmit. | Info Exchange
| 10811 | Responded and Closed | Revise and Resubmit | 2020-09-16 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: Revise and Resubmit. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-08 |  | 064116-016 Vanity and Towel Drop Event Level.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-08 |  | 064116-016 Vanity and Towel Drop Event Level.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-09-16 |  | 064116-016 Vanity and Towel Drop Event Level_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-09-08 |  | 064116-016 Vanity and Towel Drop Event Level.pdf
06 41 16-016-01 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-016-01 Vanity rev 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-14 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-28 | 2020-10-28 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-10-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08786 | Received | For Review | 2020-10-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-28 | Submittal Number: 06 41 16-16.1 From: MIKE SOLFELT Final Due Date: 10/28/20 Subject: VANITY REV 1 Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11616 | Forwarded | For Review | 2020-10-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-21 | Submittal Number: 06 41 16-16.1 From: MIKE SOLFELT Final Due Date: 10/28/20 Subject: VANITY REV 1 Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 09042 | Review Response | Approved as Noted | 2020-10-27 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 11923 | Responded and Closed | Approved as Noted | 2020-10-27 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| 11939 | Reopened | Additional Information | 2020-10-28 10:43 | Kelsea Conkright (Populous)
| 11940 | Responded and Closed | Approved as Noted | 2020-10-28 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-14 |  | 064116-016 Vanity rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-14 |  | 064116-016 Vanity rev 1.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-10-27 |  | 064116-016 Vanity rev 1_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-14 |  | 064116-016 Vanity rev 1.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-14 |  | 064116-016 Vanity rev 1.pdf
06 41 16-017-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-017-00 P-Lam Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-19 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-02 | 2020-11-03 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-11-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08856 | Received | For Review | 2020-10-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-02 | Submittal Number: 06 41 16-17.0 From: MIKE SOLFELT Final Due Date: 11/01/20 Subject: P-LAM SAMPLES Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11704 | Forwarded | For Review | 2020-10-19 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-26 | Submittal Number: 06 41 16-17.0 From: MIKE SOLFELT Final Due Date: 11/01/20 Subject: P-LAM SAMPLES Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 09183 | Review Response | Approved as Noted | 2020-11-03 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12125 | Responded and Closed | Approved as Noted | 2020-11-03 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | For white plam, where PVC edge-band is not an exact manufacturer's match, use the laminate itself for edge band. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-19 |  | 06 41 16-17.0 Plastic Laminate Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-19 |  | 06 41 16-17.0 Plastic Laminate Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-03 |  | 06 41 16-17.0 Plastic Laminate Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-19 |  | 06 41 16-17.0 Plastic Laminate Samples.pdf
06 41 16-019-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-019-00 P-Lam at Main Con | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-09 | 2021-02-15 | 21 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10945 | Received | For Review | 2021-01-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-09 | Submittal Number: 06 41 16-19.0 From: MIKE SOLFELT Final Due Date: 02/06/21 Subject: P-LAM AT MAIN CON Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14209 | Forwarded | For Review | 2021-01-25 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-01 | Submittal Number: 06 41 16-19.0 From: MIKE SOLFELT Final Due Date: 02/06/21 Subject: P-LAM AT MAIN CON Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11412 | Review Response | Approved as Noted | 2021-02-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14779 | Responded and Closed | Approved as Noted | 2021-02-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 06 41 16-19 Main Con PLAM & M25 Samples Submittal.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-25 |  | 06 41 16-19 Main Con PLAM & M25 Samples Submittal.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-15 |  | 06 41 16-19 Main Con PLAM & M25 Samples Submittal_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-25 |  | 06 41 16-19 Main Con PLAM & M25 Samples Submittal.pdf
06 41 16-020-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-020-00 Coat Hook, L32 P-Lam Product and Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-02-25 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11418 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-03-01 | Submittal Number: 06 41 16-20.0 From: MIKE SOLFELT Final Due Date: 03/01/21 Subject: COAT HOOK, L32 P-LAM PRODUCT AND SAMPLES Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14785 | Forwarded | For Review | 2021-02-15 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 06 41 16-20.0 From: MIKE SOLFELT Final Due Date: 03/01/21 Subject: COAT HOOK, L32 P-LAM PRODUCT AND SAMPLES Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11663 | Review Response | Approved as Noted | 2021-02-25 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15114 | Responded and Closed | Approved as Noted | 2021-02-25 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 064116-021 Coat Hook L32 P-Lam Product and Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-15 |  | 064116-021 Coat Hook L32 P-Lam Product and Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-25 |  | 064116-020 Coat Hook L32 P-Lam Product and Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-15 |  | 064116-021 Coat Hook L32 P-Lam Product and Samples.pdf
06 41 16-021-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-021-00 NHL PL Casework | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-22 | 2021-02-18 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-02-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11270 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-22 | Submittal Number: 06 41 16-21.0 From: MIKE SOLFELT Final Due Date: 02/18/21 Subject: NHL PL CASEWORK Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14602 | Forwarded | For Review | 2021-02-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-15 | Submittal Number: 06 41 16-21.0 From: MIKE SOLFELT Final Due Date: 02/18/21 Subject: NHL PL CASEWORK Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 11524 | Review Response | Approved as Noted/Resubmit | 2021-02-18 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14932 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-18 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-08 |  | 064116-021 NHL PL Casework.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-08 |  | 064116-021 NHL PL Casework.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-18 |  | 064116-021 NHL PL Casework_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-02-08 |  | 064116-021 NHL PL Casework.pdf
06 41 16-021-01 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-021-01 NHL PL Casework | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-29 | 2021-03-19 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-03-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11995 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-03-29 | Submittal Number: 06 41 16-21.1 From: MIKE SOLFELT Final Due Date: 03/29/21 Subject: NHL PL CASEWORK Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 15535 | Forwarded | For Review | 2021-03-15 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-22 | Submittal Number: 06 41 16-21.1 From: MIKE SOLFELT Final Due Date: 03/29/21 Subject: NHL PL CASEWORK Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 12126 | Review Response | Approved as Noted | 2021-03-19 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15694 | Responded and Closed | Approved as Noted | 2021-03-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-15 |  | 064116-021.1 NHL PL Casework.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-15 |  | 064116-021.1 NHL PL Casework.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-19 |  | 064116-021.1 NHL PL Casework_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-15 |  | 064116-021.1 NHL PL Casework.pdf
06 41 16-022-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-022-00 L32 Edge Banding / Acrylic Resubmit | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-10 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-24 | 2021-03-31 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-03-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11915 | Received | For Review | 2021-03-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-03-24 | Submittal Number: 06 41 16-22.0 From: MIKE SOLFELT Final Due Date: 03/25/21 Subject: L32 EDGE BANDING / ACRYLIC RESUBMIT Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 15438 | Forwarded | For Review | 2021-03-10 | Mike Solfelt (Mortenson Construction) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-17 | Submittal Number: 06 41 16-22.0 From: MIKE SOLFELT Final Due Date: 03/25/21 Subject: L32 EDGE BANDING / ACRYLIC RESUBMIT Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 12324 | Review Response | Approved as Noted | 2021-03-31 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15962 | Responded and Closed | Approved as Noted | 2021-03-31 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-10 |  | 064116-022 L32 PVC Edgebanding and Acrylic Resubmit.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-03-10 |  | 064116-022 L32 PVC Edgebanding and Acrylic Resubmit.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-31 |  | 064116-022 L32 PVC Edgebanding and Acrylic Resubmit_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-03-10 |  | 064116-022 L32 PVC Edgebanding and Acrylic Resubmit.pdf
06 41 16-023-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-023-00 02.06.02 Countertop Resubmit for Record | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Not Required For Review |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-19 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13050 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-25 | Submittal Number: 06 41 16-23.0 From: MIKE SOLFELT Final Due Date: 05/19/21 Subject: 02.06.02 COUNTERTOP RESUBMIT FOR RECORD Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 16885 | Forwarded | For Review | 2021-05-11 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-18 | Submittal Number: 06 41 16-23.0 From: MIKE SOLFELT Final Due Date: 05/19/21 Subject: 02.06.02 COUNTERTOP RESUBMIT FOR RECORD Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 13176 | Review Response | Not Required For Review | 2021-05-19 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17065 | Responded and Closed | Not Required For Review | 2021-05-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Not Required For Review) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | 06 41 16-23 - 02.06.02-Office Countertop Resubmit for Record.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-11 |  | 06 41 16-23 - 02.06.02-Office Countertop Resubmit for Record.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-05-19 |  | 06 41 16-23 - 02.06.02-Office Countertop Resubmit for Record_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-11 |  | 06 41 16-23 - 02.06.02-Office Countertop Resubmit for Record.pdf
06 41 16-024-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-024-00 L3, L10, L11, L12 and Decometal Brush Black | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-05-18 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13139 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-06-02 07:00 | Submittal Number: 06 41 16-24.0 From: MIKE SOLFELT Final Due Date: 05/24/21 Subject: L3, L10, L11, L12 AND DECOMETAL BRUSH BLACK Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 16999 | Forwarded | For Review | 2021-05-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-25 | Submittal Number: 06 41 16-24.0 From: MIKE SOLFELT Final Due Date: 05/24/21 Subject: L3, L10, L11, L12 AND DECOMETAL BRUSH BLACK Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 13160 | Review Response | Approved | 2021-05-18 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17026 | Responded and Closed | Approved | 2021-05-18 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | 06 41 16-24.0 Plastic Laminate Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-17 |  | 06 41 16-24.0 Plastic Laminate Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-18 |  | 06 41 16-24.0 Plastic Laminate Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-05-17 |  | 06 41 16-24.0 Plastic Laminate Samples.pdf
06 41 16-025-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-025-00 Artist Lounge P-Lam | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-24 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-08 07:00 | 2021-06-04 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13240 | Received | For Review | 2021-05-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-06-08 07:00 | Submittal Number: 06 41 16-25.0 From: MIKE SOLFELT Final Due Date: 05/31/21 Subject: ARTIST LOUNGE P-LAM Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 17129 | Forwarded | For Review | 2021-05-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-31 | Submittal Number: 06 41 16-25.0 From: MIKE SOLFELT Final Due Date: 05/31/21 Subject: ARTIST LOUNGE P-LAM Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 13400 | Review Response | Approved | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17331 | Responded and Closed | Approved | 2021-06-04 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-24 |  | 064116-025 P-Lam Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-24 |  | 064116-025 P-Lam Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-04 |  | 064116-025 P-Lam Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-05-24 |  | 064116-025 P-Lam Samples.pdf
06 41 16-026-00 | 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS | 06 41 16-026-00 CCD116 Millwork Revisions | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-31 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2021-09-14 | 2021-09-03 | 4 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-09-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14552 | Received | For Review | 2021-08-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-14 | Submittal Number: 06 41 16-26.0 From: MIKE SOLFELT Final Due Date: 09/14/21 Subject: CCD116 MILLWORK REVISIONS Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 18765 | Forwarded | For Review | 2021-09-02 | Populous SCA_CCA | Kelsea Conkright (Populous); Kuebler Perry (Populous); Chad Francis (Populous) | 2021-09-09 | Submittal Number: 06 41 16-26.0 From: MIKE SOLFELT Final Due Date: 09/14/21 Subject: CCD116 MILLWORK REVISIONS Description: Spec Section: 06 41 16 - PLASTIC-LAMINATE-FACED ARCHITECTURAL CABINETS Status: OPEN | Info Exchange
| 14567 | Review Response | Approved as Noted | 2021-09-03 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18780 | Responded and Closed | Approved as Noted | 2021-09-03 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-31 02:00 |  | 064116-026 CCD116 Millwork Revisions.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-31 02:00 |  | 064116-026 CCD116 Millwork Revisions.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-09-03 |  | 064116-026 CCD116 Millwork Revisions.pdf_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-31 |  | 064116-026 CCD116 Millwork Revisions.pdf
06 46 00-001-00 | 06 46 00 - WOOD TRIM | 06 46 00-001-00 Wood Base Shop Drawings - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-05 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-19 | 2020-06-10 | 6 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-06-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06249 | Received | For Review | 2020-06-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-06-19 | Submittal Number: 06 46 00-1.0 From: JOSH BROUSSARD Final Due Date: 06/19/20 Subject: WOOD BASE SHOP DRAWINGS - BASE BUILDING Description: SHOP DRAWINGS FOR BASE BUILDING WB3 WOOD BASE ON EVENT LEVEL AND MECH MEZZANINE. Spec Section: 06 46 00 - WOOD TRIM Status: OPEN | Info Exchange
| 08434 | Forwarded | For Review | 2020-06-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-06-15 | Submittal Number: 06 46 00-1.0 From: JOSH BROUSSARD Final Due Date: 06/19/20 Subject: WOOD BASE SHOP DRAWINGS - BASE BUILDING Description: SHOP DRAWINGS FOR BASE BUILDING WB3 WOOD BASE ON EVENT LEVEL AND MECH MEZZANINE. Spec Section: 06 46 00 - WOOD TRIM Status: OPEN | Info Exchange
| 06322 | Review Response | Approved as Noted/Resubmit | 2020-06-10 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to markups in drawing. | Mail
| 08527 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 06 46 00 - Wood Base 06.04.2020.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 06 46 00-1.0 Wood Base Shop Drawings - Base Building.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 06 46 00-1.0 Wood Base Shop Drawings - Base Building(1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 06 46 00 - Wood Base 06.04.2020.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 06 46 00-1.0 Wood Base Shop Drawings - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 06 46 00-1.0 Wood Base Shop Drawings - Base Building(1).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-06-10 |  | 06 46 00-1.0 Wood Base Shop Drawings - Base Building_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-06-05 |  | 06 46 00 - Wood Base 06.04.2020.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-06-05 |  | 06 46 00-1.0 Wood Base Shop Drawings - Base Building.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-06-05 |  | 06 46 00-1.0 Wood Base Shop Drawings - Base Building(1).pdf
06 46 00-001-01 | 06 46 00 - WOOD TRIM | 06 46 00-001-01 Wood Base Shop Drawings - Base Building Rev 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-20 | 2020-07-07 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-07-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06766 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 06 46 00-1.1 From: JOSH BROUSSARD Final Due Date: 07/17/20 Subject: WOOD BASE SHOP DRAWINGS - BASE BUILDING REV 1 Description: REVISION 1 FOR SHOP DRAWINGS FOR BASE BUILDING WB3 AND WD3 WOOD BASE ON EVENT LEVEL AND MECH MEZZANINE. REVISED TO INCLUDE WD3 SCOPE IN THESE AREAS. Spec Section: 06 46 00 - WOOD TRIM Status: OPEN | Info Exchange
| 09094 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-07-13 | Submittal Number: 06 46 00-1.1 From: JOSH BROUSSARD Final Due Date: 07/17/20 Subject: WOOD BASE SHOP DRAWINGS - BASE BUILDING REV 1 Description: REVISION 1 FOR SHOP DRAWINGS FOR BASE BUILDING WB3 AND WD3 WOOD BASE ON EVENT LEVEL AND MECH MEZZANINE. REVISED TO INCLUDE WD3 SCOPE IN THESE AREAS. Spec Section: 06 46 00 - WOOD TRIM Status: OPEN | Info Exchange
| 06818 | Review Response | Approved as Noted | 2020-07-07 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  |  | Mail
| 09151 | Responded and Closed | Approved as Noted | 2020-07-07 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal markup. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-03 |  | 06 46 00-1.1 Wood Base Shop Drawings - Base Bldg R1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-03 |  | 06 46 00-1.1 Wood Base Shop Drawings - Base Bldg R1.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-07-07 |  | 06 46 00-1.1 Wood Base Shop Drawings - Base Bldg R1_POP Final.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-03 |  | 06 46 00-1.1 Wood Base Shop Drawings - Base Bldg R1.pdf
06 64 00-001-00 | 06 64 00 - PLASTIC PANELING | 06 64 00-001-00 PLASTIC PANELING - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-27 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-10 | 2020-06-03 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06039 | Received | For Review | 2020-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-06-10 | Submittal Number: 06 64 00-1.0 From: TYRONE THORNTON Final Due Date: 06/09/20 Subject: PLASTIC PANELING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 08183 | Forwarded | For Review | 2020-05-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-06-02 | Submittal Number: 06 64 00-1.0 From: TYRONE THORNTON Final Due Date: 06/09/20 Subject: PLASTIC PANELING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 08340 | Responded and Closed | Approved | 2020-06-03 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (M.A. Mortenson Company) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-26 |  | SCA 06-64-00 Plastic Paneling Submittal FSI.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-26 |  | SCA 06-64-00 Plastic Paneling Submittal FSI.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-03 02:00 |  | 066400-0001-0 Product Data Plastic Paneling-MAM_POP.pdf
06 64 00-002-00 | 06 64 00 - PLASTIC PANELING | 06 64 00-002-00 PLASTIC PANELING - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-12 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-26 | 2020-06-24 | 13 |  | Record Copies; Transfers; Submittals | 06 64 00-002-00-01 - 06 64 00-002-00 PLASTIC PANELING - Samples | 13 |  | 2020-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06368 | Received | For Review | 2020-06-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-06-26 | Submittal Number: 06 64 00-2.0 From: JES PELKEY Final Due Date: 06/24/20 Subject: PLASTIC PANELING - SAMPLES Description: SAMPLES SENT VIA UPS. Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 08584 | Forwarded | For Review | 2020-06-12 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-06-19 | Submittal Number: 06 64 00-2.0 From: JES PELKEY Final Due Date: 06/24/20 Subject: PLASTIC PANELING - SAMPLES Description: SAMPLES SENT VIA UPS. Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 08861 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-24 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Approved for FRP1 color white. Submit FRP2 color black, and FRP3 Hardstop product, refer to Finish Legend | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-11 |  | 066400-0002-0 Plastic Paneling Samples-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-11 |  | 066400-0002-0 Plastic Paneling Samples-MAM.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-06-24 |  | 066400-0002-0 Plastic Paneling Samples-MAM_POP.pdf
06 64 00-002-00-01 | 06 64 00 - PLASTIC PANELING | 06 64 00-002-00 PLASTIC PANELING - Samples | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 06 64 00-002-00 - 06 64 00-002-00 PLASTIC PANELING - Samples | -1 | 2020-07-08
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-24 |  | 066400-0002-0 Plastic Paneling Samples-MAM_POP.pdf
06 64 00-006-00 | 06 64 00 - PLASTIC PANELING | 06 64 00-006-00 PLASTIC PANELING - Samples_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-14 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-28 | 2020-08-28 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07549 | Received | For Review | 2020-08-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-28 | Submittal Number: 06 64 00-6.0 From: TYRONE THORNTON Final Due Date: 08/28/20 Subject: PLASTIC PANELING - SAMPLES_PCI Description: Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 10049 | Forwarded | For Review | 2020-08-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-21 | Submittal Number: 06 64 00-6.0 From: TYRONE THORNTON Final Due Date: 08/28/20 Subject: PLASTIC PANELING - SAMPLES_PCI Description: Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 07814 | Review Response | Approved as Noted | 2020-08-28 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Notes: Provide samples for FRP2 and FRP3, only FRP1 was provided. FRP1 is approved. | Info Exchange
| 10391 | Responded and Closed | Approved as Noted | 2020-08-28 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Notes: Provide samples for FRP2 and FRP3, only FRP1 was provided. FRP1 is approved. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-14 |  | 06 64 00 Plasitc Samples_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-14 |  | 06 64 00 Plasitc Samples_MAM Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-14 |  | 06 64 00 Plasitc Samples_MAM Review.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-14 |  | 06 64 00 Plasitc Samples_MAM Review.pdf
06 64 00-006-01 | 06 64 00 - PLASTIC PANELING | 06 64 00-006-01 PLASTIC PANELING - Samples_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-11 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-25 | 2020-09-21 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08042 | Received | For Review | 2020-09-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-25 | Submittal Number: 06 64 00-6.1 From: TYRONE THORNTON Final Due Date: 09/25/20 Subject: PLASTIC PANELING - SAMPLES_PCI Description: Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 10708 | Forwarded | For Review | 2020-09-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-18 | Submittal Number: 06 64 00-6.1 From: TYRONE THORNTON Final Due Date: 09/25/20 Subject: PLASTIC PANELING - SAMPLES_PCI Description: Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 10939 | Responded and Closed | Approved | 2020-09-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-10 |  | 066400-6.1- FRP2 (Black) Samples_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-10 |  | 066400-6.1- FRP2 (Black) Samples_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-21 02:00 |  | 066400-6.1- FRP2 (Black) Samples_MAM Review - POP.pdf
06 64 00-007-00 | 06 64 00 - PLASTIC PANELING | 06 64 00-007-00 PLASTIC PANELING - FRP3 Formica Hardstop Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-10 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-24 | 2020-09-28 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-09-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08032 | Received | For Review | 2020-09-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-24 | Submittal Number: 06 64 00-7.0 From: TYRONE THORNTON Final Due Date: 09/24/20 Subject: PLASTIC PANELING - FRP3 FORMICA HARDSTOP PRODUCT DATA Description: Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 10685 | Forwarded | For Review | 2020-09-10 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-17 | Submittal Number: 06 64 00-7.0 From: TYRONE THORNTON Final Due Date: 09/24/20 Subject: PLASTIC PANELING - FRP3 FORMICA HARDSTOP PRODUCT DATA Description: Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 08369 | Review Response | Approved | 2020-09-28 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  |  | Info Exchange
| 11082 | Responded and Closed | Approved | 2020-09-28 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-10 |  | 06 64 00 - FRP 3 - Product Data_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-10 |  | 06 64 00 - FRP 3 - Product Data_MAM Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-10 |  | 06 64 00 - FRP 3 - Product Data_MAM Review.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-10 |  | 06 64 00 - FRP 3 - Product Data_MAM Review.pdf
06 64 00-008-00 | 06 64 00 - PLASTIC PANELING | 06 64 00-008-00 06 64 00 PLASTIC PANELING - FRP3 Formica Hardstop & Trim Accessories | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-09 | 2020-10-11 | 17 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-10-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08323 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Craig Chowaniec; Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-10-09 | Submittal Number: 06 64 00-8.0 From: TYRONE THORNTON Final Due Date: 10/08/20 Subject: 06 64 00 PLASTIC PANELING - FRP3 FORMICA HARDSTOP & TRIM ACCESSORIES Description: Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 11032 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-01 | Submittal Number: 06 64 00-8.0 From: TYRONE THORNTON Final Due Date: 10/08/20 Subject: 06 64 00 PLASTIC PANELING - FRP3 FORMICA HARDSTOP & TRIM ACCESSORIES Description: Spec Section: 06 64 00 - PLASTIC PANELING Status: OPEN | Info Exchange
| 08699 | Review Response | Approved as Noted | 2020-10-11 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11489 | Responded and Closed | Approved as Noted | 2020-10-11 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 06 64 00 Plastic Paneling - FRP3 Formica Hardstop & Trim Accessories (1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 06 64 00 Plastic Paneling - FRP3 Formica Hardstop & Trim Accessories (1).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-11 |  | 06 64 00 Plastic Paneling - FRP3 POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-24 |  | 06 64 00 Plastic Paneling - FRP3 Formica Hardstop & Trim Accessories (1).pdf
07 13 26-001-00 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-001-00 Tunnel Cap Waterproofing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-30 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2019-08-13 | 2019-07-30 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-07-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01909 | Received | For Review | 2019-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt | 2019-08-13 | Submittal Number: 07 13 26-001.0 From: MIKE SOLFELT Final Due Date: 08/12/19 Subject: TUNNEL CAP WATERPROOFING Description: Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 03052 | Forwarded | For Review | 2019-07-30 | Shaina Burris (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2019-08-06 | Submittal Number: 07 13 26-001.0 From: MIKE SOLFELT Final Due Date: 08/12/19 Subject: TUNNEL CAP WATERPROOFING Description: Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 03065 | Responded and Closed | No Action Taken or Required | 2019-07-30 | Josh Dobken (Populous) | Jes Pelkey (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Received for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-29 |  | 07 13 26-001 Waterproofing and Waterstop for North Courtyard Tunnel Cap.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-29 |  | 07 13 26-001 Waterproofing and Waterstop for North Courtyard Tunnel Cap.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-30 02:00 |  | 07 13 26-001 Waterproofing and Waterstop for North Courtyard Tunnel Cap_POP.pdf
07 13 26-002-00 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-002-00 Self-Adhering Sheet Waterproofing PDS Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-30 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2019-10-14 | 2019-10-15 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-10-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02593 | Received | For Review | 2019-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2019-10-14 | Submittal Number: 07 13 26-2.0 From: MIKE O'BRIEN Final Due Date: 10/10/19 Subject: 07 13 26 SELF-ADHERING SHEET WATERPROOFING PDS SUBMITTAL Description: Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 03882 | Forwarded | For Review | 2019-09-30 | Shaina Burris (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2019-10-07 | Submittal Number: 07 13 26-2.0 From: MIKE O'BRIEN Final Due Date: 10/10/19 Subject: 07 13 26 SELF-ADHERING SHEET WATERPROOFING PDS SUBMITTAL Description: Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 02777 | Review Response | Approved as Noted/Resubmit | 2019-10-15 | Tom Usher (Populous) | Josh Dobken (Populous) |  | See attached | Info Exchange
| 04122 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Tom Usher (Populous) Remarks: See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-30 |  | 071326-0002-0 Self Adhering Sheet Waterproofing PD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-30 |  | 071326-0002-0 Self Adhering Sheet Waterproofing PD.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2019-10-15 02:00 |  | 071326-0002-0 Self Adhering Sheet Waterproofing PD_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-29 02:00 |  | 071326-0002-0 Self Adhering Sheet Waterproofing PD.pdf
07 13 26-002-01 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-002-01 Self-Adhering Sheet Waterproofing PDS Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-08 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-11-22 | 2019-11-22 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-11-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03125 | Received | For Review | 2019-11-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2019-11-22 | Submittal Number: 07 13 26-2.1 From: NEIL SHANNON Final Due Date: 11/22/19 Subject: 07 13 26 SELF-ADHERING SHEET WATERPROOFING PDS SUBMITTAL Description: SUB DRAINAGE GRATE FOR WATERPROOFING AT LAGGING WALL. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 04535 | Forwarded | For Review | 2019-11-08 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-11-15 | Submittal Number: 07 13 26-2.1 From: NEIL SHANNON Final Due Date: 11/22/19 Subject: 07 13 26 SELF-ADHERING SHEET WATERPROOFING PDS SUBMITTAL Description: SUB DRAINAGE GRATE FOR WATERPROOFING AT LAGGING WALL. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 04800 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-22 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 05129 | Sent | For Information Only | 2019-12-13 | Josh Dobken (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-07 |  | 071326-0002-1 Sheet Waterproofing - 6inch Drain Grate.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-07 |  | 071326-0002-1 Sheet Waterproofing - 6inch Drain Grate.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2019-11-22 |  | 071326-0002-1 Sheet Waterproofing - 6inch Drain Grate POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2019-11-06 02:00 |  | 071326-0002-1 Sheet Waterproofing - 6inch Drain Grate.pdf
07 13 26-002-02 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-002-02 07 13 26 Self-Adhering Sheet Waterproofing PDS Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-20 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-03 | 2020-01-21 | 2 |  | Record Copies; Transfers; Submittals | 07 13 26-002-03 - 07 13 26-002-03 07 13 26 Self-Adhering Sheet Waterproofing PDS Submittal | 2 |  | 2020-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03981 | Received | For Review | 2020-01-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2020-02-03 | Submittal Number: 07 13 26-2.2 From: NEIL SHANNON Final Due Date: 02/03/20 Subject: 07 13 26 SELF-ADHERING SHEET WATERPROOFING PDS SUBMITTAL Description: SUB DRAINAGE GRATE FOR WATERPROOFING AT LAGGING WALL. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 05553 | Forwarded | For Review | 2020-01-20 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-01-27 | Submittal Number: 07 13 26-2.2 From: NEIL SHANNON Final Due Date: 02/03/20 Subject: 07 13 26 SELF-ADHERING SHEET WATERPROOFING PDS SUBMITTAL Description: SUB DRAINAGE GRATE FOR WATERPROOFING AT LAGGING WALL. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 05585 | Responded and Closed | Approved as Noted/Resubmit | 2020-01-21 | Tom Usher (Populous) | Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | ARCHITECT COMMENTS: NOTE (FOR SUBMITTAL TRACKING PURPOSES): 1. THE 5 ITEMS SIKA REQUIRES FOR THE 15 YEAR WARRANTY REMAIN AS OPEN ITEMS 2. TUNNEL WATERPROOFING NOT YET SUBMITTED The "resubmit" portion of this approval is only to track the 2 items listed above. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-20 |  | 071326-0002-2 Sheet Waterproofing - Strip Drain.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-20 |  | 071326-0002-2 Sheet Waterproofing - Strip Drain.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2020-01-21 |  | 071326-0002-2 Sheet Waterproofing - Strip Drain POP.pdf
07 13 26-002-03 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-002-03 07 13 26 Self-Adhering Sheet Waterproofing PDS Submittal | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 13 26-002-02 - 07 13 26-002-02 07 13 26 Self-Adhering Sheet Waterproofing PDS Submittal | -1 | 2020-02-04
07 13 26-003-00 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-003-00 SELF-ADHERING SHEET WATERPROOFING - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-02 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-12-16 | 2019-12-12 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-12-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03410 | Received | For Review | 2019-12-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2019-12-16 | Submittal Number: 07 13 26-3.0 From: BROOKE BURCHAM Final Due Date: 12/16/19 Subject: SELF-ADHERING SHEET WATERPROOFING - SHOP DRAWINGS Description: SHOP DRAWINGS SHOWING LOCATIONS AND EXTENT OF WATERPROOFING, INCLUDING DETAILS FOR SUBSTRATE JOINTS AND CRACKS, SHEET FLASHINGS, PENETRATIONS, TIE-INS WITH ADJOINING CONSTRUCTION, AND OTHER TERMINATION CONDITIONS. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 04881 | Forwarded | For Review | 2019-12-02 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-12-09 | Submittal Number: 07 13 26-3.0 From: BROOKE BURCHAM Final Due Date: 12/16/19 Subject: SELF-ADHERING SHEET WATERPROOFING - SHOP DRAWINGS Description: SHOP DRAWINGS SHOWING LOCATIONS AND EXTENT OF WATERPROOFING, INCLUDING DETAILS FOR SUBSTRATE JOINTS AND CRACKS, SHEET FLASHINGS, PENETRATIONS, TIE-INS WITH ADJOINING CONSTRUCTION, AND OTHER TERMINATION CONDITIONS. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 03617 | Review Response | Approved as Noted/Resubmit | 2019-12-12 | Tom Usher (Populous) | Shaina Burris (Populous) |  | See attached submittal | Info Exchange
| 05106 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Tom Usher (Populous) Remarks: See attached submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-29 |  | 071326-0003-0 Sheet Waterproofing Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-29 |  | 071326-0003-0 Sheet Waterproofing Shop Drawings.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2019-12-12 02:00 |  | 071326-0003-0 Sheet Waterproofing Shop Drawings_R1 POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-28 02:00 |  | 071326-0003-0 Sheet Waterproofing Shop Drawings.pdf
07 13 26-003-01 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-003-01 SELF-ADHERING SHEET WATERPROOFING - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-18 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-03-03 | 2020-03-03 | 15 |  | Record Copies; Transfers; Submittals | 07 13 26-003-01-01 - 07 13 26-003-01 SELF-ADHERING SHEET WATERPROOFING - Shop Drawings | 15 |  | 2020-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04390 | Received | For Review | 2020-02-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-03-03 | Submittal Number: 07 13 26-3.1 From: BROOKE BURCHAM Final Due Date: 03/03/20 Subject: SELF-ADHERING SHEET WATERPROOFING - SHOP DRAWINGS Description: SHOP DRAWINGS SHOWING LOCATIONS AND EXTENT OF WATERPROOFING, INCLUDING DETAILS FOR SUBSTRATE JOINTS AND CRACKS, SHEET FLASHINGS, PENETRATIONS, TIE-INS WITH ADJOINING CONSTRUCTION, AND OTHER TERMINATION CONDITIONS. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 06066 | Forwarded | For Review | 2020-02-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-02-25 | Submittal Number: 07 13 26-3.1 From: BROOKE BURCHAM Final Due Date: 03/03/20 Subject: SELF-ADHERING SHEET WATERPROOFING - SHOP DRAWINGS Description: SHOP DRAWINGS SHOWING LOCATIONS AND EXTENT OF WATERPROOFING, INCLUDING DETAILS FOR SUBSTRATE JOINTS AND CRACKS, SHEET FLASHINGS, PENETRATIONS, TIE-INS WITH ADJOINING CONSTRUCTION, AND OTHER TERMINATION CONDITIONS. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 06360 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-03 | Shaina Burris (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-18 |  | 071326-0003-1 Sheet Waterproofing Shop Drawings - Resubmittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-18 |  | 071326-0003-1 Sheet Waterproofing Shop Drawings - Resubmittal.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-03-03 |  | 071326-0003-1 Sheet Waterproofing Shop Drawings - Resubmittal_POP.pdf
07 13 26-003-01-01 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-003-01 SELF-ADHERING SHEET WATERPROOFING - Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 13 26-003-01 - 07 13 26-003-01 SELF-ADHERING SHEET WATERPROOFING - Shop Drawings | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-03 |  | 071326-0003-1 Sheet Waterproofing Shop Drawings - Resubmittal_POP.pdf
07 13 26-004-00 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-004-00 SELF-ADHERING SHEET WATERPROOFING - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-03 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-17 | 2021-02-09 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11174 | Received | For Review | 2021-02-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-02-17 | Submittal Number: 07 13 26-4.0 From: BROOKE BURCHAM Final Due Date: 02/17/21 Subject: SELF-ADHERING SHEET WATERPROOFING - SAMPLES Description: SAMPLES, 3-BY-6-INCH (75-BY-150-MM) MINIMUM SIZE, OF EACH WATERPROOFING MATERIAL REQUIRED FOR PROJECT. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 14480 | Forwarded | For Review | 2021-02-03 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-10 | Submittal Number: 07 13 26-4.0 From: BROOKE BURCHAM Final Due Date: 02/17/21 Subject: SELF-ADHERING SHEET WATERPROOFING - SAMPLES Description: SAMPLES, 3-BY-6-INCH (75-BY-150-MM) MINIMUM SIZE, OF EACH WATERPROOFING MATERIAL REQUIRED FOR PROJECT. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 14653 | Responded and Closed | Approved as Noted | 2021-02-09 | Shaina Burris (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-03 |  | 07 13 26 - SikaProof Waterproofing Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-03 |  | 07 13 26 - SikaProof Waterproofing Sample.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-02-09 |  | 07 13 26 - SikaProof Waterproofing Sample_POP.pdf
07 13 26-005-00 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-005-00 SELF-ADHERING SHEET WATERPROOFING - Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-25 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-12-09 | 2019-12-12 | 18 |  | Record Copies; Transfers; Submittals | 07 13 26-005-01 - 07 13 26-005-00 SELF-ADHERING SHEET WATERPROOFING - Warranty | 18 |  | 2019-12-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03364 | Received | For Review | 2019-11-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2019-12-09 | Submittal Number: 07 13 26-5.0 From: BROOKE BURCHAM Final Due Date: 12/11/19 Subject: SELF-ADHERING SHEET WATERPROOFING - WARRANTY Description: WARRANTY : SPECIMEN OF SPECIFIED WATERPROOFING WARRANTY. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 04819 | Forwarded | For Review | 2019-11-25 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-12-02 | Submittal Number: 07 13 26-5.0 From: BROOKE BURCHAM Final Due Date: 12/11/19 Subject: SELF-ADHERING SHEET WATERPROOFING - WARRANTY Description: WARRANTY : SPECIMEN OF SPECIFIED WATERPROOFING WARRANTY. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 05105 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-25 |  | 071326-0005-0 15yr Warranty.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-25 |  | 071326-0005-0 15yr Warranty.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-12 02:00 |  | 071326-0005-0 15yr Warranty POP.pdf
07 13 26-005-01 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-005-00 SELF-ADHERING SHEET WATERPROOFING - Warranty | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 13 26-005-00 - 07 13 26-005-00 SELF-ADHERING SHEET WATERPROOFING - Warranty | -1 | 2019-12-26
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-12 02:00 |  | 071326-0005-0 15yr Warranty POP.pdf
07 13 26-006-00 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-006-00 SELF-ADHERING SHEET WATERPROOFING - Test Reports | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2020-01-10 | 2020-01-14 | 28 | General | Record Copies; Transfers; Submittals |  | 28 |  | 2020-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03675 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2020-01-10 | Submittal Number: 07 13 26-6.0 From: BROOKE BURCHAM Final Due Date: 01/03/20 Subject: SELF-ADHERING SHEET WATERPROOFING - TEST REPORTS Description: PRODUCT TEST REPORTS FROMA QUALIFIED INDEPENDENT TESTING AGENCY EVIDENCING COMPLIANCE OF WATERPROOFING WITH REQUIREMENTS AND OTHER PHYSICAL PROPERTIES REPORTED BY MANUFACTURER BASED ON COMPREHENSIVE TESTING OF PRODUCTS ACCORDING TO CURRENT STANDARD TEST METHODS WITHIN PREVIOUS 5 YEARS. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 05195 | Forwarded | For Review | 2019-12-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2019-12-25 | Submittal Number: 07 13 26-6.0 From: BROOKE BURCHAM Final Due Date: 01/03/20 Subject: SELF-ADHERING SHEET WATERPROOFING - TEST REPORTS Description: PRODUCT TEST REPORTS FROMA QUALIFIED INDEPENDENT TESTING AGENCY EVIDENCING COMPLIANCE OF WATERPROOFING WITH REQUIREMENTS AND OTHER PHYSICAL PROPERTIES REPORTED BY MANUFACTURER BASED ON COMPREHENSIVE TESTING OF PRODUCTS ACCORDING TO CURRENT STANDARD TEST METHODS WITHIN PREVIOUS 5 YEARS. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 03911 | Review Response | No Action Taken or Required | 2020-01-14 | Tom Usher (Populous) | Tom Usher (Populous) |  |  | Info Exchange
| 05470 | Responded and Closed | No Action Taken or Required | 2020-01-14 | Tom Usher (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 071326-0006-0 Waterproofing Test Reports.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-18 |  | 071326-0006-0 Waterproofing Test Reports.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2020-01-14 |  | 071326-0006-0 Waterproofing Test Reports_POP.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2019-12-18 |  | 071326-0006-0 Waterproofing Test Reports.pdf
07 13 26-007-00 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-007-00 Post Applied Waterproofing Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-14 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-28 | 2020-03-03 | 19 |  | Record Copies; Transfers; Submittals | 07 13 26-007-00-01 - 07 13 26-007-00 Post Applied Waterproofing Product Data | 19 |  | 2020-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04347 | Received | For Review | 2020-02-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-02-28 | Submittal Number: 07 13 26-7.0 From: BROOKE BURCHAM Final Due Date: 02/28/20 Subject: POST APPLIED WATERPROOFING PRODUCT DATA Description: PRODUCT DATA FOR POST APPLIED WATERPROOFING Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 06017 | Forwarded | For Review | 2020-02-14 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-02-21 | Submittal Number: 07 13 26-7.0 From: BROOKE BURCHAM Final Due Date: 02/28/20 Subject: POST APPLIED WATERPROOFING PRODUCT DATA Description: PRODUCT DATA FOR POST APPLIED WATERPROOFING Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 06359 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-03 | Shaina Burris (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-13 |  | 071326-0007-0 Post Applied Waterproofing PD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-13 |  | 071326-0007-0 Post Applied Waterproofing PD.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-03-03 |  | 071326-0007-0 Post Applied Waterproofing PD_POP.pdf
07 13 26-007-00-01 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-007-00 Post Applied Waterproofing Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 13 26-007-00 - 07 13 26-007-00 Post Applied Waterproofing Product Data | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-03 |  | 071326-0007-0 Post Applied Waterproofing PD_POP.pdf
07 13 26-008-00 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-008-00 Post Applied Waterproofing Shop Drawings - Pits and Garage Walls | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-10 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-03-23 | 2020-03-18 | 9 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04724 | Received | For Review | 2020-03-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-03-23 | Submittal Number: 07 13 26-8.0 From: BROOKE BURCHAM Final Due Date: 03/23/20 Subject: POST APPLIED WATERPROOFING SHOP DRAWINGS - PITS AND GARAGE WALLS Description: SHOP DRAWINGS FOR POST APPLIED WATERPROOFING. PIT LOCATIONS AND GARAGE WALLS Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 06491 | Forwarded | For Review | 2020-03-10 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-03-17 | Submittal Number: 07 13 26-8.0 From: BROOKE BURCHAM Final Due Date: 03/23/20 Subject: POST APPLIED WATERPROOFING SHOP DRAWINGS - PITS AND GARAGE WALLS Description: SHOP DRAWINGS FOR POST APPLIED WATERPROOFING. PIT LOCATIONS AND GARAGE WALLS Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 04891 | Review Response | Revise and Resubmit | 2020-03-17 | Tom Usher (Populous) | Shaina Burris (Populous) |  | This submittal was difficult to fully understand. I had hoped to approve as noted but the assumptions and comments made this too difficult. I do not doubt Sika and Snyder will properly waterproof the pits and walls that are part of this submittal. I just can't approve the submittal as presented. | Info Exchange
| 06736 | Responded and Closed | Revise and Resubmit | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Tom Usher (Populous) Remarks: This submittal was difficult to fully understand. I had hoped to approve as noted but the assumptions and comments made this too difficult. I do not doubt Sika and Snyder will properly waterproof the pits and walls that are part of this submittal. I just can't approve the submittal as presented. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-09 |  | 071326-0008-0 Post Applied Waterproofing SD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-09 |  | 071326-0008-0 Post Applied Waterproofing SD.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2020-03-09 |  | 071326-0008-0 Post Applied Waterproofing SD.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-17 02:00 |  | 071326-0008-0 Post Applied Waterproofing SD_POP.pdf
07 13 26-008-01 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-008-01 Post Applied Waterproofing Shop Drawings - Pits and Garage Walls | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-09 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-23 | 2020-04-28 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05272 | Received | For Review | 2020-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-04-23 | Submittal Number: 07 13 26-8.1 From: BROOKE BURCHAM Final Due Date: 04/23/20 Subject: POST APPLIED WATERPROOFING SHOP DRAWINGS - PITS AND GARAGE WALLS Description: SHOP DRAWINGS FOR POST APPLIED WATERPROOFING. PIT LOCATIONS AND GARAGE WALLS Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 07165 | Forwarded | For Review | 2020-04-09 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-16 | Submittal Number: 07 13 26-8.1 From: BROOKE BURCHAM Final Due Date: 04/23/20 Subject: POST APPLIED WATERPROOFING SHOP DRAWINGS - PITS AND GARAGE WALLS Description: SHOP DRAWINGS FOR POST APPLIED WATERPROOFING. PIT LOCATIONS AND GARAGE WALLS Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 07611 | Responded and Closed | Approved as Noted | 2020-04-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-08 |  | 071326-0008-1 Resubmittal Pits and Garage Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-08 |  | 071326-0008-1 Resubmittal Pits and Garage Shop Drawings.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-28 02:00 |  | 071326-0008-1 Resubmittal Pits and Garage Shop Drawings_POP.pdf
07 13 26-009-00 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-009-00 Sheet Waterproofing - Below Strip Drain Protection Board | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-13 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-27 | 2020-04-28 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05294 | Received | For Review | 2020-04-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-04-27 | Submittal Number: 07 13 26-9.0 From: BROOKE BURCHAM Final Due Date: 04/24/20 Subject: SHEET WATERPROOFING - BELOW STRIP DRAIN PROTECTION BOARD Description: Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 07202 | Forwarded | For Review | 2020-04-13 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-20 | Submittal Number: 07 13 26-9.0 From: BROOKE BURCHAM Final Due Date: 04/24/20 Subject: SHEET WATERPROOFING - BELOW STRIP DRAIN PROTECTION BOARD Description: Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 07612 | Responded and Closed | Approved | 2020-04-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-11 |  | 071326-0009-0 Below Strip Drain Protection Board.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-11 |  | 071326-0009-0 Below Strip Drain Protection Board.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-28 02:00 |  | 071326-0009-0 Below Strip Drain Protection Board_POP.pdf
07 13 26-010-00 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-010-00 South Parcel - SELF-ADHERING SHEET WATERPROOFING | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-08 07:00 | 2020-09-15 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-09-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07675 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-08 07:00 | Submittal Number: 07 13 26-10.0 From: TYRONE THORNTON Final Due Date: 09/07/20 Subject: SOUTH PARCEL - SELF-ADHERING SHEET WATERPROOFING Description: INCLUDES THE PRODUCT DATA, MANUFACTURER QUALIFICATIONS, AND SAMPLE WARRANTY. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 10219 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-31 | Submittal Number: 07 13 26-10.0 From: TYRONE THORNTON Final Due Date: 09/07/20 Subject: SOUTH PARCEL - SELF-ADHERING SHEET WATERPROOFING Description: INCLUDES THE PRODUCT DATA, MANUFACTURER QUALIFICATIONS, AND SAMPLE WARRANTY. Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 10807 | Responded and Closed | Approved | 2020-09-15 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 071326-10_South Parcel - Self-Adhering Sheet Waterproofing (WP)_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 071326-10_South Parcel - Self-Adhering Sheet Waterproofing (WP)_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-09-15 |  | 071326-10_South Parcel - Self-Adhering Sheet Waterproofing (WP)_MAM Review-POP.pdf
07 13 26-012-00 | 07 13 26 - SELF-ADHERING SHEET WATERPROOFING | 07 13 26-012-00 South Parcel - SELF-ADHERING SHEET WATERPROOFING - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-20 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-08 | 2020-12-07 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-12-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09631 | Received | For Review | 2020-11-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-12-08 | Submittal Number: 07 13 26-12.0 From: TYRONE THORNTON Final Due Date: 12/03/20 Subject: SOUTH PARCEL - SELF-ADHERING SHEET WATERPROOFING - SHOP DRAWINGS Description: Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 12665 | Forwarded | For Review | 2020-11-20 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-27 | Submittal Number: 07 13 26-12.0 From: TYRONE THORNTON Final Due Date: 12/03/20 Subject: SOUTH PARCEL - SELF-ADHERING SHEET WATERPROOFING - SHOP DRAWINGS Description: Spec Section: 07 13 26 - SELF-ADHERING SHEET WATERPROOFING Status: OPEN | Info Exchange
| 13057 | Responded and Closed | Approved | 2020-12-07 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-19 |  | 07 13 26 - South Parcel Decline Ramp WP Shops_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-19 |  | 07 13 26 - South Parcel Decline Ramp WP Shops_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-07 |  | 07 13 26 - South Parcel Decline Ramp WP Shops_MAM Review-POP.pdf
07 13 54-002-00 | 07 13 54 | 07 13 54-002-00 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - Tunnel & North Portal SikaPlan Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-19 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-02 | 2020-11-03 | 16 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-11-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08831 | Received | For Review | 2020-10-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-02 | Submittal Number: 07 13 54-2.0 From: TYRONE THORNTON Final Due Date: 10/30/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - TUNNEL & NORTH PORTAL SIKAPLAN SHOP DRAWINGS Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 11669 | Forwarded | For Review | 2020-10-16 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-23 | Submittal Number: 07 13 54-2.0 From: TYRONE THORNTON Final Due Date: 10/30/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - TUNNEL & NORTH PORTAL SIKAPLAN SHOP DRAWINGS Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 12148 | Responded and Closed | Approved as Noted | 2020-11-03 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-16 |  | CPA - Synder Tunnel Shop Drawings_ Revised 10.15.20_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-16 |  | CPA - Synder Tunnel Shop Drawings_ Revised 10.15.20_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-03 |  | CPA - Synder Tunnel Shop Drawings_ Revised 10.15.20_MAM Review-POP.pdf
07 13 54-002-01 | 07 13 54 | 07 13 54-002-01 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - Tunnel & North Portal SikaPlan Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-09 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-23 | 2020-11-18 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09307 | Received | For Review | 2020-11-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-23 | Submittal Number: 07 13 54-2.1 From: TYRONE THORNTON Final Due Date: 11/23/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - TUNNEL & NORTH PORTAL SIKAPLAN SHOP DRAWINGS Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 12284 | Forwarded | For Review | 2020-11-09 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-16 | Submittal Number: 07 13 54-2.1 From: TYRONE THORNTON Final Due Date: 11/23/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - TUNNEL & NORTH PORTAL SIKAPLAN SHOP DRAWINGS Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 12557 | Responded and Closed | Approved | 2020-11-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-09 |  | CPA - Synder Tunnel Shop Drawings_ Revised 11.5.20_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-09 |  | CPA - Synder Tunnel Shop Drawings_ Revised 11.5.20_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-18 |  | CPA - Synder Tunnel Shop Drawings_ Revised 11.5.20_MAM Review-pop.pdf
07 13 54-002-02 | 07 13 54 | 07 13 54-002-02 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - Tunnel & North Portal SikaPlan Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-02 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-16 | 2020-12-30 | 29 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2020-12-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09840 | Received | For Review | 2020-12-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-12-16 | Submittal Number: 07 13 54-2.2 From: TYRONE THORNTON Final Due Date: 12/16/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - TUNNEL & NORTH PORTAL SIKAPLAN SHOP DRAWINGS Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 12923 | Forwarded | For Review | 2020-12-02 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-09 | Submittal Number: 07 13 54-2.2 From: TYRONE THORNTON Final Due Date: 12/16/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - TUNNEL & NORTH PORTAL SIKAPLAN SHOP DRAWINGS Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 13540 | Responded and Closed | Approved | 2020-12-30 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-02 |  | CPA - Synder Tunnel Shop Drawings_ Revised 11.25.2020_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-02 |  | CPA - Synder Tunnel Shop Drawings_ Revised 11.25.2020_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-30 |  | CPA - Synder Tunnel Shop Drawings_ Revised 11.25.2020_MAM Review-POP.pdf
07 13 54-003-00 | 07 13 54 | 07 13 54-003-00 07 13 54 - THERMOPLASTIC SHEET | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-02 | Responded and Closed - Approved |  | Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-10-16 | 2020-10-21 | 20 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-10-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08772 | Received | For Review | 2020-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2020-10-16 | Submittal Number: 07 13 54-003.0 From: TYRONE THORNTON Final Due Date: 10/13/20 Subject: THERMOPLASTIC SHEET WATERPROOFING - Samples Description: Spec Section: 07 13 54 Status: OPEN | Email
| 11599 | Forwarded | For Review | 2020-10-14 | Shaina Burris (Populous) | Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-10-16 | Submittal Number: 07 13 54-003.0 From: TYRONE THORNTON Final Due Date: 10/13/20 Subject: THERMOPLASTIC SHEET WATERPROOFING - Samples Description: Spec Section: 07 13 54 Status: OPEN | Info Exchange
| 11781 | Responded and Closed | Approved | 2020-10-21 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 11966 | Sent | For Information Only | 2020-10-28 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company) |  | Responded and Closed (Approved) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 07 13 54-CPA Thermoplastic Sheet Waterproofing Tunnel Samples_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-01 |  | 07 13 54-CPA Thermoplastic Sheet Waterproofing Tunnel Samples_MAM Review.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-10-21 |  | 07 13 54-CPA Thermoplastic Sheet Waterproofing Tunnel Samples_MAM Review-POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-09-30 02:00 |  | 07 13 54-CPA Thermoplastic Sheet Waterproofing Tunnel Samples_MAM Review.pdf
07 13 54-004-00 | 07 13 54 | 07 13 54-004-00 THERMOPLASTIC SHEET WATERPROOFING - Field QC Reports | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-18 | 2021-02-23 | 20 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-02-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11175 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-02-18 | Submittal Number: 07 13 54-4.0 From: TYRONE THORNTON Final Due Date: 02/17/21 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - FIELD QC REPORTS Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 14481 | Forwarded | For Review | 2021-02-03 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-10 | Submittal Number: 07 13 54-4.0 From: TYRONE THORNTON Final Due Date: 02/17/21 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - FIELD QC REPORTS Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 15035 | Responded and Closed | No Action Taken or Required | 2021-02-23 | Tom Usher (Populous) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-03 |  | 07 13 54 - Field QC Report.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-03 |  | 07 13 54 - Field QC Report.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2021-02-23 |  | 07 13 54 - Field QC Report_POP.pdf
07 13 54-005-00 | 07 13 54 | 07 13 54-005-00 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - Mock-up | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-03 08:00 | 2020-11-18 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09482 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 07 13 54-5.0 From: TYRONE THORNTON Final Due Date: 11/30/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - MOCK-UP Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 12500 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-24 | Submittal Number: 07 13 54-5.0 From: TYRONE THORNTON Final Due Date: 11/30/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - MOCK-UP Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 12559 | Responded and Closed | Approved | 2020-11-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | South Parcel - SikaPlan Mock-Up.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 07 13 54-005-00 South Parcel - SikaPlan Mock-Up.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-18 |  | 07 13 54-005-00 South Parcel - SikaPlan Mock-Up-POP.pdf
07 13 54-006-00 | 07 13 54 | 07 13 54-006-00 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - Tunnel Geotextile Fabric Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-09 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-23 | 2020-11-18 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09308 | Received | For Review | 2020-11-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-23 | Submittal Number: 07 13 54-6.0 From: TYRONE THORNTON Final Due Date: 11/23/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - TUNNEL GEOTEXTILE FABRIC SAMPLES Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 12285 | Forwarded | For Review | 2020-11-09 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-16 | Submittal Number: 07 13 54-6.0 From: TYRONE THORNTON Final Due Date: 11/23/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - TUNNEL GEOTEXTILE FABRIC SAMPLES Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 12560 | Responded and Closed | Approved | 2020-11-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-09 |  | 07 13 54 - CPA Tunnel Geotextile Fabric Sample_MAM review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-09 |  | 07 13 54 - CPA Tunnel Geotextile Fabric Sample_MAM review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-18 |  | 07 13 54 - CPA Tunnel Geotextile Fabric Sample_MAM review-POP.pdf
07 13 54-007-00 | 07 13 54 | 07 13 54-007-00 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - Sarnadisc RhinoBond Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-26 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-09 | 2020-11-09 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08994 | Received | For Review | 2020-10-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-09 | Submittal Number: 07 13 54-7.0 From: TYRONE THORNTON Final Due Date: 11/10/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - SARNADISC RHINOBOND PRODUCT DATA Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 11866 | Forwarded | For Review | 2020-10-26 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-02 | Submittal Number: 07 13 54-7.0 From: TYRONE THORNTON Final Due Date: 11/10/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - SARNADISC RHINOBOND PRODUCT DATA Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 12300 | Responded and Closed | Approved | 2020-11-09 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-26 |  | Sarnadisc Rhinobond Product Data & Manufacturers Letter_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-26 |  | Sarnadisc Rhinobond Product Data & Manufacturers Letter_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-09 02:00 |  | Sarnadisc Rhinobond Product Data & Manufacturers Letter_MAM Review_pop.pdf
07 13 54-008-00 | 07 13 54 | 07 13 54-008-00 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - Sarnadisc RhinoBond Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-22 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-05 | 2020-11-06 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-11-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08936 | Received | For Review | 2020-10-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-05 | Submittal Number: 07 13 54-8.0 From: TYRONE THORNTON Final Due Date: 11/04/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - SARNADISC RHINOBOND SAMPLES Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 11806 | Forwarded | For Review | 2020-10-22 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-29 | Submittal Number: 07 13 54-8.0 From: TYRONE THORNTON Final Due Date: 11/04/20 Subject: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING - SARNADISC RHINOBOND SAMPLES Description: Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 12224 | Responded and Closed | Approved | 2020-11-06 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-21 |  | 07 13 54- Sarnadisc RhinoBond Samples _MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-21 |  | 07 13 54- Sarnadisc RhinoBond Samples _MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-06 |  | 07 13 54- Sarnadisc RhinoBond Samples _MAM Review-POP.pdf
07 13 54-009-00 | 07 13 54 | 07 13 54-009-00 South Parcel - Thermoplastic Sheet Waterproofing Spears Injection Molded Plugs | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-29 | 2021-04-12 | 29 |  | Record Copies; Transfers; Submittals |  | 32 |  | 2021-04-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11976 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-29 | Submittal Number: 07 13 54-9.0 From: CHRISTIAN GENEROSA Final Due Date: 03/26/21 Subject: SOUTH PARCEL - THERMOPLASTIC SHEET WATERPROOFING SPEARS INJECTION MOLDED PLUGS Description: INJECTION MOLDED PLUGS USED FOR PATCHING PVC WEEPS AT THE SOUTH PARCEL TUNNEL. Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 15515 | Forwarded | For Review | 2021-03-12 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-19 | Submittal Number: 07 13 54-9.0 From: CHRISTIAN GENEROSA Final Due Date: 03/26/21 Subject: SOUTH PARCEL - THERMOPLASTIC SHEET WATERPROOFING SPEARS INJECTION MOLDED PLUGS Description: INJECTION MOLDED PLUGS USED FOR PATCHING PVC WEEPS AT THE SOUTH PARCEL TUNNEL. Spec Section: 07 13 54 - THERMOPLASTIC SHEET WATERPROOFING Status: OPEN | Info Exchange
| 16254 | Responded and Closed | Approved | 2021-04-12 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-12 |  | 2021-03-12 071354-0009-00 Spears Plugs_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-12 |  | 2021-03-12 071354-0009-00 Spears Plugs_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-12 02:00 |  | 07 13 54-009-00 Spears Plugs_MAM_POP.pdf
07 14 13-001-00 | 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING | 07 14 13-001-00 HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-20 | 2020-07-20 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06767 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 07 14 13-1.0 From: ROSHAN ALEX Final Due Date: 03/02/20 Subject: HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE MANUFACTURER'S WRITTEN INSTRUCTIONS FOR EVALUATING, PREPARING, AND TREATING SUBSTRATE, TECHNICAL DATA, AND TESTED PHYSICAL AND PERFORMANCE PROPERTIES OF WATERPROOFING. Spec Section: 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING Status: OPEN | Info Exchange
| 09095 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-13 | Submittal Number: 07 14 13-1.0 From: ROSHAN ALEX Final Due Date: 03/02/20 Subject: HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE MANUFACTURER'S WRITTEN INSTRUCTIONS FOR EVALUATING, PREPARING, AND TREATING SUBSTRATE, TECHNICAL DATA, AND TESTED PHYSICAL AND PERFORMANCE PROPERTIES OF WATERPROOFING. Spec Section: 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING Status: OPEN | Info Exchange
| 09428 | Responded and Closed | Approved | 2020-07-20 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  |  | Info Exchange
| 09772 | Sent | For Information Only | 2020-08-03 | Josh Dobken (Populous) | Brooke Burcham (M.A. Mortenson Company); Roshan.Alex@mortenson.com |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-02 |  | 071413-1.0 HRA & PMMA Waterproofing - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-02 |  | 071413-1.0 HRA & PMMA Waterproofing - Product Data.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-07-02 |  | 071413-1.0 HRA & PMMA Waterproofing - Product Data.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-07-01 02:00 |  | 071413-1.0 HRA & PMMA Waterproofing - Product Data.pdf
07 14 13-002-00 | 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING | 07 14 13-002-00 HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROO - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-17 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-31 | 2020-09-24 | 39 |  | Record Copies; Transfers; Submittals |  | 39 |  | 2020-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07574 | Received | For Review | 2020-08-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-31 | Submittal Number: 07 14 13-2.0 From: BROOKE BURCHAM Final Due Date: 08/31/20 Subject: HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROO - SHOP DRAWINGS Description: SHOP DRAWINGS : SHOW LOCATIONS AND EXTENT OF WATERPROOFING. INCLUDE DETAILS FOR SUBSTRATE JOINTS AND CRACKS, SHEET FLASHINGS, PENETRATIONS, INSIDE AND OUTSIDE CORNERS, TIE-INS TO ADJOINING WATERPROOFING, AND OTHER TERMINATION CONDITIONS. 1. INCLUDE SETTING DRAWINGS SHOWING LAYOUT, SIZES, SECTIONS, PROFILES, AND JOINT DETAILS OF CONCRETE TOPPING. 2. SHOW LOCATION OF THE LEAK DETECTION SYSTEM TEST CONDUCTOR CABLE, MEASUREMENT GRID, AND CONNECTION BOXES. Spec Section: 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING Status: OPEN | Info Exchange
| 10080 | Forwarded | For Review | 2020-08-17 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-24 | Submittal Number: 07 14 13-2.0 From: BROOKE BURCHAM Final Due Date: 08/31/20 Subject: HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROO - SHOP DRAWINGS Description: SHOP DRAWINGS : SHOW LOCATIONS AND EXTENT OF WATERPROOFING. INCLUDE DETAILS FOR SUBSTRATE JOINTS AND CRACKS, SHEET FLASHINGS, PENETRATIONS, INSIDE AND OUTSIDE CORNERS, TIE-INS TO ADJOINING WATERPROOFING, AND OTHER TERMINATION CONDITIONS. 1. INCLUDE SETTING DRAWINGS SHOWING LAYOUT, SIZES, SECTIONS, PROFILES, AND JOINT DETAILS OF CONCRETE TOPPING. 2. SHOW LOCATION OF THE LEAK DETECTION SYSTEM TEST CONDUCTOR CABLE, MEASUREMENT GRID, AND CONNECTION BOXES. Spec Section: 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING Status: OPEN | Info Exchange
| 08322 | Review Response | Approved as Noted | 2020-09-24 | Tom Usher (Populous) | Josh Dobken (Populous) |  | Subject: HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROO - SHOP DRAWINGS Description: SHOP DRAWINGS : SHOW LOCATIONS AND EXTENT OF WATERPROOFING. INCLUDE DETAILS FOR SUBSTRATE JOINTS AND CRACKS, SHEET FLASHINGS, PENETRATIONS, INSIDE AND OUTSIDE CORNERS, TIE-INS TO ADJOINING WATERPROOFING, AND OTHER TERMINATION CONDITIONS. 1. INCLUDE SETTING DRAWINGS SHOWING LAYOUT, SIZES, SECTIONS, PROFILES, AND JOINT DETAILS OF CONCRETE TOPPING. 2. SHOW LOCATION OF THE LEAK DETECTION SYSTEM TEST CONDUCTOR CABLE, MEASUREMENT GRID, AND CONNECTION BOXES. POPULOUS - APPROVED AS NOTED: REFER TO ATTACHED SUBMITTAL FOR NOTES. | Info Exchange
| 11044 | Responded and Closed | Approved as Noted | 2020-09-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Tom Usher (Populous) POPULOUS - APPROVED AS NOTED: REFER TO ATTACHED SUBMITTAL FOR NOTES. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-17 |  | 071413-0002-0 HRA & PMMA Waterproofing - Shop Drawings_Final.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-17 |  | 071413-0002-0 HRA & PMMA Waterproofing - Shop Drawings_Final.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2020-09-24 |  | 071413-0002-0 HRA & PMMA Waterproofing -SD-POP-APPROVED AS NOTED-0924 20.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-16 02:00 |  | 071413-0002-0 HRA & PMMA Waterproofing - Shop Drawings_Final.pdf
07 14 13-002-01 | 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING | 07 14 13-002-01 HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROO - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-13 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-27 08:00 | 2021-01-21 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10667 | Received | For Review | 2021-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2021-01-27 08:00 | Submittal Number: 07 14 13-2.1 From: BROOKE BURCHAM Final Due Date: 01/27/21 Subject: HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROO - SHOP DRAWINGS Description: SHOP DRAWINGS : SHOW LOCATIONS AND EXTENT OF WATERPROOFING. INCLUDE DETAILS FOR SUBSTRATE JOINTS AND CRACKS, SHEET FLASHINGS, PENETRATIONS, INSIDE AND OUTSIDE CORNERS, TIE-INS TO ADJOINING WATERPROOFING, AND OTHER TERMINATION CONDITIONS. 1. INCLUDE SETTING DRAWINGS SHOWING LAYOUT, SIZES, SECTIONS, PROFILES, AND JOINT DETAILS OF CONCRETE TOPPING. 2. SHOW LOCATION OF THE LEAK DETECTION SYSTEM TEST CONDUCTOR CABLE, MEASUREMENT GRID, AND CONNECTION BOXES. Spec Section: 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING Status: OPEN | Info Exchange
| 13888 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-20 | Submittal Number: 07 14 13-2.1 From: BROOKE BURCHAM Final Due Date: 01/27/21 Subject: HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROO - SHOP DRAWINGS Description: SHOP DRAWINGS : SHOW LOCATIONS AND EXTENT OF WATERPROOFING. INCLUDE DETAILS FOR SUBSTRATE JOINTS AND CRACKS, SHEET FLASHINGS, PENETRATIONS, INSIDE AND OUTSIDE CORNERS, TIE-INS TO ADJOINING WATERPROOFING, AND OTHER TERMINATION CONDITIONS. 1. INCLUDE SETTING DRAWINGS SHOWING LAYOUT, SIZES, SECTIONS, PROFILES, AND JOINT DETAILS OF CONCRETE TOPPING. 2. SHOW LOCATION OF THE LEAK DETECTION SYSTEM TEST CONDUCTOR CABLE, MEASUREMENT GRID, AND CONNECTION BOXES. Spec Section: 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING Status: OPEN | Info Exchange
| 14135 | Responded and Closed | Approved as Noted | 2021-01-21 | Shaina Burris (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 071413-0002-1 HRA_PMMA_ILD Waterproofing - SD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 071413-0002-1 HRA_PMMA_ILD Waterproofing - SD.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 071413-0002-1 HRA_PMMA_ILD Waterproofing - SD.pdf
07 14 13-005-00 | 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING | 07 14 13-005-00 HOT FLUID APPLIED - ILD Shop Drawing and Product Data (Leak Detection) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-05 | 2021-02-08 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10892 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-05 | Submittal Number: 07 14 13-5.0 From: BROOKE BURCHAM Final Due Date: 02/05/21 Subject: HOT FLUID APPLIED - ILD SHOP DRAWING AND PRODUCT DATA (LEAK DETECTION) Description: ILD SHOP DRAWINGS AND PRODUCT DATA. Spec Section: 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING Status: OPEN | Info Exchange
| 14146 | Forwarded | For Review | 2021-01-22 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-29 | Submittal Number: 07 14 13-5.0 From: BROOKE BURCHAM Final Due Date: 02/05/21 Subject: HOT FLUID APPLIED - ILD SHOP DRAWING AND PRODUCT DATA (LEAK DETECTION) Description: ILD SHOP DRAWINGS AND PRODUCT DATA. Spec Section: 07 14 13 - HOT FLUID-APPLIED RUBBERIZED ASPHALT WATERPROOFING Status: OPEN | Info Exchange
| 14600 | Responded and Closed | Approved as Noted | 2021-02-08 | Populous SCA_CCA | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-21 |  | 071413-0005-0 ILD Leak Detection - SD-PD.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-21 |  | 071413-0005-0 ILD Leak Detection - SD-PD.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-21 |  | 071413-0005-0 ILD Leak Detection - SD-PD.pdf
07 18 00-001-00 | 07 18 00 - TRAFFIC COATINGS | 07 18 00-001-00 Traffic Coating Submittal Package | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-15 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-29 | 2020-05-06 | 22 |  | Record Copies; Transfers; Submittals | 07 18 00-001-00-01 - 07 18 00-001-00 Traffic Coating Submittal Package | 22 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05374 | Received | For Review | 2020-04-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-04-29 | Submittal Number: 07 18 00-1.0 From: MIKE SOLFELT Final Due Date: 04/29/20 Subject: TRAFFIC COATING SUBMITTAL PACKAGE Description: Spec Section: 07 18 00 - TRAFFIC COATINGS Status: OPEN | Info Exchange
| 07300 | Forwarded | For Review | 2020-04-15 | Shaina Burris (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2020-04-22 | Submittal Number: 07 18 00-1.0 From: MIKE SOLFELT Final Due Date: 04/29/20 Subject: TRAFFIC COATING SUBMITTAL PACKAGE Description: Spec Section: 07 18 00 - TRAFFIC COATINGS Status: OPEN | Info Exchange
| 07787 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-06 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-15 |  | 071800-0001- Traffic Coating @ Garage Slabs.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-15 |  | 071800-0001- Traffic Coating @ Garage Slabs.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-05-06 |  | 071800-0001- Traffic Coating @ Garage Slabs_POP.pdf
07 18 00-001-00-01 | 07 18 00 - TRAFFIC COATINGS | 07 18 00-001-00 Traffic Coating Submittal Package | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 18 00-001-00 - 07 18 00-001-00 Traffic Coating Submittal Package | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-06 |  | 071800-0001- Traffic Coating @ Garage Slabs_POP.pdf
07 18 00-002-00 | 07 18 00 - TRAFFIC COATINGS | 07 18 00-002-00 Traffic Coating Color Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-11 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-25 | 2020-06-22 | 12 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-06-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06328 | Received | For Review | 2020-06-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-25 | Submittal Number: 07 18 00-2.0 From: DEVON WALTERS Final Due Date: 06/24/20 Subject: 071800-0002- TRAFFIC COATING COLOR SAMPLE Description: Spec Section: 07 18 00 - TRAFFIC COATINGS Status: OPEN | Info Exchange
| 08533 | Forwarded | For Review | 2020-06-10 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-17 | Submittal Number: 07 18 00-2.0 From: DEVON WALTERS Final Due Date: 06/24/20 Subject: 071800-0002- TRAFFIC COATING COLOR SAMPLE Description: Spec Section: 07 18 00 - TRAFFIC COATINGS Status: OPEN | Info Exchange
| 08801 | Responded and Closed | Approved as Noted | 2020-06-22 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-10 |  | 071800-0002 -Traffic Coating Color Sample.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-10 |  | 071800-0002 -Traffic Coating Color Sample.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-22 02:00 |  | 071800-0002 -Traffic Coating Color Sample_pop.pdf
07 18 00-003-00 | 07 18 00 - TRAFFIC COATINGS | 07 18 00-003-00 Neogard Permagard III Product Data - Mechanical Intake Shaft | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-07 | 3 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-04-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12364 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-04-19 | Submittal Number: 07 18 00-3.0 From: MIKE SOLFELT Final Due Date: 04/14/21 Subject: NEOGARD PERMAGARD III PRODUCT DATA - MECHANICAL INTAKE SHAFT Description: Spec Section: 07 18 00 - TRAFFIC COATINGS Status: OPEN | Info Exchange
| 16020 | Forwarded | For Review | 2021-04-01 | Mike Solfelt (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 07 18 00-3.0 From: MIKE SOLFELT Final Due Date: 04/14/21 Subject: NEOGARD PERMAGARD III PRODUCT DATA - MECHANICAL INTAKE SHAFT Description: Spec Section: 07 18 00 - TRAFFIC COATINGS Status: OPEN | Info Exchange
| 16144 | Responded and Closed | Approved as Noted | 2021-04-07 | Tom Usher (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 07 14 00 - Neogard Permagard III Product Data.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-04-01 |  | 07 14 00 - Neogard Permagard III Product Data.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2021-04-07 02:00 |  | 07 18 00-003-0 Neogard Permagard III Product Data_POP.pdf
07 21 00-002-00 | 07 21 00 - THERMAL INSULATION | 07 21 00-002-00 Product Data - Thermal Insulation for Drywall | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-21 | Responded and Closed - Approved |  | Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-05 | 2020-05-04 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05465 | Received | For Review | 2020-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-05-05 | Submittal Number: 07 21 00-2.0 From: TYRONE THORNTON Final Due Date: 05/04/20 Subject: PRODUCT DATA - THERMAL INSULATION FOR DRYWALL Description: Spec Section: 07 21 00 - THERMAL INSULATION Status: OPEN | Info Exchange
| 07416 | Forwarded | For Review | 2020-04-21 | Shaina Burris (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2020-04-28 | Submittal Number: 07 21 00-2.0 From: TYRONE THORNTON Final Due Date: 05/04/20 Subject: PRODUCT DATA - THERMAL INSULATION FOR DRYWALL Description: Spec Section: 07 21 00 - THERMAL INSULATION Status: OPEN | Info Exchange
| 07722 | Responded and Closed | Approved | 2020-05-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 07725 | Reopened | Additional Information | 2020-05-04 14:57 | Chris Minter (Populous)
| 07726 | Responded and Closed | Approved | 2020-05-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-20 |  | 072100-0001-0 Product Data Thermal Insulation for Drywall-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-20 |  | 072100-0001-0 Product Data Thermal Insulation for Drywall-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-04-20 |  | 072100-0001-0 Product Data Thermal Insulation for Drywall-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-05-04 |  | 072100-0001-0 Product Data Thermal Insulation for Drywall-MAM-POP.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-04-20 |  | 072100-0001-0 Product Data Thermal Insulation for Drywall-MAM.pdf
07 21 00-003-00 | 07 21 00 - THERMAL INSULATION | 07 21 00-003-00 Thermal Insulation - LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-09 | 2020-07-20 | 33 |  | Record Copies; Transfers; Submittals |  | 33 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06485 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-09 | Submittal Number: 07 21 00-3.0 From: BROOKE BURCHAM Final Due Date: 07/15/20 Subject: THERMAL INSULATION - LEED DATA Description: PRODUCT DATA: FOR ADHESIVES, INDICATING VOC CONTENT. Spec Section: 07 21 00 - THERMAL INSULATION Status: OPEN | Info Exchange
| 08736 | Forwarded | For Review | 2020-06-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-25 | Submittal Number: 07 21 00-3.0 From: BROOKE BURCHAM Final Due Date: 07/15/20 Subject: THERMAL INSULATION - LEED DATA Description: PRODUCT DATA: FOR ADHESIVES, INDICATING VOC CONTENT. Spec Section: 07 21 00 - THERMAL INSULATION Status: OPEN | Info Exchange
| 09403 | Responded and Closed | Approved | 2020-07-20 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 07 21 00 Thermal Insulation - LEED Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 07 21 00 Thermal Insulation - LEED Data_MAM Reviewed.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-07-20 |  | 07 21 00 Thermal Insulation - LEED Data_MAM Reviewed-POP.pdf
07 21 00-004-00 | 07 21 00 - THERMAL INSULATION | 07 21 00-004-00 THERMAL INSULATION - Product Test Reports | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-18 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13039 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-05-25 | Submittal Number: 07 21 00-4.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: THERMAL INSULATION - PRODUCT TEST REPORTS Description: LABORATORY TEST REPORTS: FOR INSULATION AND ADHESIVES, INDICATING COMPLIANCE WITH REQUIREMENTS FOR LOW- EMITTING MATERIALS. Spec Section: 07 21 00 - THERMAL INSULATION Status: OPEN | Info Exchange
| 16871 | Forwarded | For Review | 2021-05-11 | Allie Zimmerman | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-18 | Submittal Number: 07 21 00-4.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: THERMAL INSULATION - PRODUCT TEST REPORTS Description: LABORATORY TEST REPORTS: FOR INSULATION AND ADHESIVES, INDICATING COMPLIANCE WITH REQUIREMENTS FOR LOW- EMITTING MATERIALS. Spec Section: 07 21 00 - THERMAL INSULATION Status: OPEN | Info Exchange
| 17035 | Responded and Closed | Approved | 2021-05-18 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | Submittal 07 21 00-4 Revision 0 THERMAL INSULATION - Product Test Reports_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-11 |  | Submittal 07 21 00-4 Revision 0 THERMAL INSULATION - Product Test Reports_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 07 21 00-4 Revision 0 THERMAL INSULATION - Product Test Reports_MAM Reviewed-POP.pdf
07 21 19-001-00 | 07 21 19 - FOAMED-IN-PLACE INSULATION | 07 21 19-001-00 FOAMED-IN-PLACE INSULATION - Product Data for Drywall | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-27 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-11 | 2020-05-04 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05561 | Received | For Review | 2020-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-05-11 | Submittal Number: 07 21 19-1.0 From: TYRONE THORNTON Final Due Date: 05/08/20 Subject: FOAMED-IN-PLACE INSULATION - PRODUCT DATA FOR DRYWALL Description: PRODUCT DATA: 2.1A-1A SPRAYTITE LWP-L SERIES TDS (BASF) 2 2.3A-1 URE-K- THERMAL BARRIER SYSTEM 4 2.4B-1 IGNITION BARRIER OVER FOAM (DC315 INTUMESCENT COATINGS) Spec Section: 07 21 19 - FOAMED-IN-PLACE INSULATION Status: OPEN | Info Exchange
| 07539 | Forwarded | For Review | 2020-04-27 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-04 | Submittal Number: 07 21 19-1.0 From: TYRONE THORNTON Final Due Date: 05/08/20 Subject: FOAMED-IN-PLACE INSULATION - PRODUCT DATA FOR DRYWALL Description: PRODUCT DATA: 2.1A-1A SPRAYTITE LWP-L SERIES TDS (BASF) 2 2.3A-1 URE-K- THERMAL BARRIER SYSTEM 4 2.4B-1 IGNITION BARRIER OVER FOAM (DC315 INTUMESCENT COATINGS) Spec Section: 07 21 19 - FOAMED-IN-PLACE INSULATION Status: OPEN | Info Exchange
| 07721 | Responded and Closed | Approved | 2020-05-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | 072119-0001-0 Product Data Foamed-in-Place Insulation for Drywall-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-24 |  | 072119-0001-0 Product Data Foamed-in-Place Insulation for Drywall-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-04-24 |  | 072119-0001-0 Product Data Foamed-in-Place Insulation for Drywall-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-05-04 |  | 072119-0001-0 Product Data Foamed-in-Place Insulation for Drywall-MAM-POP.pdf
07 21 19-002-00 | 07 21 19 - FOAMED-IN-PLACE INSULATION | 07 21 19-002-00 FOAMED-IN-PLACE INSULATION - LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-02 | 2020-07-08 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06486 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 07 21 19-2.0 From: TYRONE THORNTON Final Due Date: 07/15/20 Subject: FOAMED-IN-PLACE INSULATION - LEED DATA Description: SUSTAINABLE DESIGN SUBMITTALS : - 1. PRODUCT DATA INDICATING VOC CONTENT, AND RECYCLED CONTENT AND OTHER CHARACTERISTICS. Spec Section: 07 21 19 - FOAMED-IN-PLACE INSULATION Status: OPEN | Info Exchange
| 08737 | Forwarded | For Review | 2020-06-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-25 | Submittal Number: 07 21 19-2.0 From: TYRONE THORNTON Final Due Date: 07/15/20 Subject: FOAMED-IN-PLACE INSULATION - LEED DATA Description: SUSTAINABLE DESIGN SUBMITTALS : - 1. PRODUCT DATA INDICATING VOC CONTENT, AND RECYCLED CONTENT AND OTHER CHARACTERISTICS. Spec Section: 07 21 19 - FOAMED-IN-PLACE INSULATION Status: OPEN | Info Exchange
| 09213 | Responded and Closed | Approved | 2020-07-08 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 07 21 19 Foamed-In-Place Insulation - LEED Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 07 21 19 Foamed-In-Place Insulation - LEED Data_MAM Reviewed.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-08 02:00 |  | 07 21 19 Foamed-In-Place Insulation - LEED Data_MAM Reviewed_POP.pdf
07 21 19-003-00 | 07 21 19 - FOAMED-IN-PLACE INSULATION | 07 21 19-003-00 FOAMED-IN-PLACE INSULATION - Qualification Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-18 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13032 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-05-25 | Submittal Number: 07 21 19-3.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: FOAMED-IN-PLACE INSULATION - QUALIFICATION DATA Description: QUALIFICATION DATA : FOR INSTALLER. Spec Section: 07 21 19 - FOAMED-IN-PLACE INSULATION Status: OPEN | Info Exchange
| 16865 | Forwarded | For Review | 2021-05-11 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-18 | Submittal Number: 07 21 19-3.0 From: ALLIE ZIMMERMAN Spec Section: 07 21 19 - FOAMED-IN-PLACE INSULATION Final Due Date: 05/21/21 Subject: FOAMED-IN-PLACE INSULATION - QUALIFICATION DATA Description: QUALIFICATION DATA : FOR INSTALLER. Status: OPEN | Info Exchange
| 17036 | Responded and Closed | Approved | 2021-05-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | Submittal 07 21 19-3 Revision 0 FOAMED-IN-PLACE INSULATION - Qualification Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-10 |  | Submittal 07 21 19-3 Revision 0 FOAMED-IN-PLACE INSULATION - Qualification Data_MAM Reviewed.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-05-18 |  | Submittal 07 21 19-3 Revision 0 FOAMED-IN-PLACE INSULATION - Qualification Data_MAM Reviewed-POP.pdf
07 21 19-005-00 | 07 21 19 - FOAMED-IN-PLACE INSULATION | 07 21 19-005-00 FOAMED-IN-PLACE INSULATION - Reports | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-18 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13040 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-05-25 | Submittal Number: 07 21 19-5.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: FOAMED-IN-PLACE INSULATION - REPORTS Description: EVALUATION REPORTS : FOR SPRAY-APPLIED POLYURETHANE FOAM-PLASTIC INSULATION AND ALTERNATIVE IGNITION BARRIER MATERIALS, FROM ICC-ES. Spec Section: 07 21 19 - FOAMED-IN-PLACE INSULATION Status: OPEN | Info Exchange
| 16872 | Forwarded | For Review | 2021-05-11 | Allie Zimmerman | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-18 | Submittal Number: 07 21 19-5.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: FOAMED-IN-PLACE INSULATION - REPORTS Description: EVALUATION REPORTS : FOR SPRAY-APPLIED POLYURETHANE FOAM-PLASTIC INSULATION AND ALTERNATIVE IGNITION BARRIER MATERIALS, FROM ICC-ES. Spec Section: 07 21 19 - FOAMED-IN-PLACE INSULATION Status: OPEN | Info Exchange
| 17037 | Responded and Closed | Approved | 2021-05-18 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | Submittal 07 21 19-5 Revision 0 FOAMED-IN-PLACE INSULATION - Reports_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-11 |  | Submittal 07 21 19-5 Revision 0 FOAMED-IN-PLACE INSULATION - Reports_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 07 21 19-5 Revision 0 FOAMED-IN-PLACE INSULATION - Reports_MAM Reviewed-POP.pdf
07 24 13-001-00 | 07 24 13 - POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYSTEM | 07 24 13-001-00 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-19 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-02 | 2020-06-09 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05916 | Received | For Review | 2020-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-06-02 | Submittal Number: 07 24 13-1.0 From: TYRONE THORNTON Final Due Date: 06/01/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE AND COMPONENT OF DAFS INDICATED. Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 08026 | Forwarded | For Review | 2020-05-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-26 | Submittal Number: 07 24 13-1.0 From: TYRONE THORNTON Final Due Date: 06/01/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE AND COMPONENT OF DAFS INDICATED. Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 08504 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-09 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 072413-0001-0 Product Data Polymer-Based Direct Applied Exterior Finish System-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 072413-0001-0 Product Data Polymer-Based Direct Applied Exterior Finish System-MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-06-09 |  | 072413-0001-0 Product Data Polymer-Based Direct Applied Exterior Finish System-MAM_POP.pdf
07 24 13-001-01 | 07 24 13 - POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYSTEM | 07 24 13-001-01 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-12 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-26 | 2020-09-02 | 22 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07520 | Received | For Review | 2020-08-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-26 | Submittal Number: 07 24 13-1.1 From: TYRONE THORNTON Final Due Date: 08/25/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - PRODUCT DATA Description: FOR EACH TYPE AND COMPONENT OF DAFS INDICATED. Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 10013 | Forwarded | For Review | 2020-08-11 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-18 | Submittal Number: 07 24 13-1.1 From: TYRONE THORNTON Final Due Date: 08/25/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - PRODUCT DATA Description: FOR EACH TYPE AND COMPONENT OF DAFS INDICATED. Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 10500 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-02 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | The product is approved. See attachment for resubmittal requirements. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-11 |  | 07 24 13 CPA - Direct Applied Exterior Finish System INDEX Rev 1_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-11 |  | 07 24 13 CPA - Direct Applied Exterior Finish System INDEX Rev 1_MAM Review.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-02 |  | 07 24 13 CPA - Direct Applied Exterior Finish System INDEX Rev 1_MAM_POP.pdf
07 24 13-001-02 | 07 24 13 - POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYSTEM | 07 24 13-001-02 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-16 | 2020-11-09 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09142 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-11-16 | Submittal Number: 07 24 13-1.2 From: TYRONE THORNTON Final Due Date: 08/25/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - PRODUCT DATA Description: FOR EACH TYPE AND COMPONENT OF DAFS INDICATED. Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 12064 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-09 | Submittal Number: 07 24 13-1.2 From: TYRONE THORNTON Final Due Date: 08/25/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - PRODUCT DATA Description: FOR EACH TYPE AND COMPONENT OF DAFS INDICATED. Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 12275 | Responded and Closed | Approved as Noted | 2020-11-09 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-31 |  | 072413-0001-2 Product Data Polymer-Based Direct Applied Exterior Finish System-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-31 |  | 072413-0001-2 Product Data Polymer-Based Direct Applied Exterior Finish System-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-09 |  | 072413-0001-2 Product Data Polymer-Based DAFS-MAM_POP.pdf
07 24 13-001-03 | 07 24 13 - POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYSTEM | 07 24 13-001-03 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Added Details | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-10 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-24 | 2021-06-15 | 37 |  | Record Copies; Transfers; Submittals |  | 37 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12989 | Received | For Review | 2021-05-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-05-24 | Submittal Number: 07 24 13-1.3 From: TYRONE THORNTON Final Due Date: 05/21/21 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - ADDED DETAILS Description: FOR EACH TYPE AND COMPONENT OF DAFS INDICATED. Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 16812 | Forwarded | For Review | 2021-05-10 | Allie Zimmerman | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-17 | Submittal Number: 07 24 13-1.3 From: TYRONE THORNTON Final Due Date: 05/21/21 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - ADDED DETAILS Description: FOR EACH TYPE AND COMPONENT OF DAFS INDICATED. Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 17503 | Responded and Closed | Approved | 2021-06-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Allie Zimmerman |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | Submittal 07 24 13-1 Revision 3 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Added Details_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-10 |  | Submittal 07 24 13-1 Revision 3 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Added Details_MAM Reviewed.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-15 02:00 |  | 07 24 13-1 Revision 3 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Added Details_MAM Reviewed_pop.pdf
07 24 13-003-00 | 07 24 13 - POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYSTEM | 07 24 13-003-00 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-02 | 2020-09-21 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08200 | Received | For Review | 2020-09-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-10-02 | Submittal Number: 07 24 13-3.0 From: BROOKE BURCHAM Final Due Date: 10/02/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - SAMPLES Description: SAMPLES FOR VERIFICATION : 24-INCH- (600-MM-) SQUARE PANELS FOR EACH TYPE OF FINISH-COAT COLOR AND TEXTURE INDICATED, PREPARED USING SAME TOOLS AND TECHNIQUES INTENDED FOR ACTUAL WORK INCLUDING CUSTOM TRIM, EACH PROFILE, AN AESTHETIC REVEAL, A TYPICAL CONTROL JOINT FILLED WITH SEALANT OF COLOR SELECTED. 1. INCLUDE EXPOSED ACCESSORY SAMPLES TO VERIFY COLOR SELECTED. Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 10886 | Forwarded | For Review | 2020-09-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-25 | Submittal Number: 07 24 13-3.0 From: BROOKE BURCHAM Final Due Date: 10/02/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - SAMPLES Description: SAMPLES FOR VERIFICATION : 24-INCH- (600-MM-) SQUARE PANELS FOR EACH TYPE OF FINISH-COAT COLOR AND TEXTURE INDICATED, PREPARED USING SAME TOOLS AND TECHNIQUES INTENDED FOR ACTUAL WORK INCLUDING CUSTOM TRIM, EACH PROFILE, AN AESTHETIC REVEAL, A TYPICAL CONTROL JOINT FILLED WITH SEALANT OF COLOR SELECTED. 1. INCLUDE EXPOSED ACCESSORY SAMPLES TO VERIFY COLOR SELECTED. Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 10934 | Responded and Closed | Approved | 2020-09-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-18 |  | 07 24 13 DAFS Sample_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-18 |  | 07 24 13 DAFS Sample_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-21 02:00 |  | 07 24 13 DAFS Sample_MAM Review_pop.pdf
07 24 13-006-00 | 07 24 13 - POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYSTEM | 07 24 13-006-00 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-02 | 2020-07-07 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-07-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06487 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 07 24 13-6.0 From: TYRONE THORNTON Final Due Date: 07/01/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - LEED DATA Description: Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 08738 | Forwarded | For Review | 2020-06-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-25 | Submittal Number: 07 24 13-6.0 From: TYRONE THORNTON Final Due Date: 07/01/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - LEED DATA Description: Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 06815 | Review Response | Approved | 2020-07-07 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 09149 | Responded and Closed | Approved | 2020-07-07 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 07 24 13 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYSTEM - LEED Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 07 24 13 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYSTEM - LEED Data_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-07-07 |  | 07 24 13 POLYMER-BASED DAFS - LEED Data_MAM Reviewed_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-17 |  | 07 24 13 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYSTEM - LEED Data_MAM Reviewed.pdf
07 24 13-007-00 | 07 24 13 - POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYSTEM | 07 24 13-007-00 POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Color Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-14 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-28 | 2020-10-13 | 30 |  | Record Copies; Transfers; Submittals |  | 30 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08081 | Received | For Review | 2020-09-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-28 | Submittal Number: 07 24 13-7.0 From: TYRONE THORNTON Final Due Date: 09/28/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - COLOR SAMPLES Description: Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 10748 | Forwarded | For Review | 2020-09-14 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-21 | Submittal Number: 07 24 13-7.0 From: TYRONE THORNTON Final Due Date: 09/28/20 Subject: POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - COLOR SAMPLES Description: Spec Section: 07 24 13 - POLYMER-BASED DIRECT APPLIED EXTERIOR FINISH SYSTEM Status: OPEN | Info Exchange
| 11570 | Responded and Closed | Approved as Noted | 2020-10-13 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Contractor to match finish and texture approved in 07 24 19-001 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-14 |  | 07 24 13-7_POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Color Samples_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-14 |  | 07 24 13-7_POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Color Samples_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-13 02:00 |  | 07 24 13-7_POLYMER-BASED DIRECT-APPLIED EXTERIOR FINISH SYS - Color Samples_MAM Review_pop.pdf
07 24 19-001-00 | 07 24 19 | 07 24 19-001-00 Water-Drainage Exterior Finish - SAMPLES | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-02 | 2020-09-21 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08199 | Received | For Review | 2020-09-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-10-02 | Submittal Number: 07 24 19-1.0 From: TYRONE THORNTON Final Due Date: 10/02/20 Subject: WATER-DRAINAGE EXTERIOR FINISH - SAMPLES Description: Spec Section: 07 24 19 - WATER-DRAINAGE EXTERIOR INSULATION AND FINISH SYSTEM Status: OPEN | Info Exchange
| 10885 | Forwarded | For Review | 2020-09-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-25 | Submittal Number: 07 24 19-1.0 From: TYRONE THORNTON Final Due Date: 10/02/20 Subject: WATER-DRAINAGE EXTERIOR FINISH - SAMPLES Description: Spec Section: 07 24 19 - WATER-DRAINAGE EXTERIOR INSULATION AND FINISH SYSTEM Status: OPEN | Info Exchange
| 10935 | Responded and Closed | Approved | 2020-09-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-18 |  | 07 24 19 EIFS Color Sample_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-18 |  | 07 24 19 EIFS Color Sample_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-21 02:00 |  | 07 24 19 EIFS Color Sample_MAM Review_pop.pdf
07 24 19-002-00 | 07 24 19 | 07 24 19-002-00 Water-Drainage Exterior Finish - Product Data Shop Drawing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-14 | 2020-10-12 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08440 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-10-14 | Submittal Number: 07 24 19-2.0 From: YE ZHANG Final Due Date: 10/14/20 Subject: WATER-DRAINAGE EXTERIOR FINISH - PRODUCT DATA SHOP DRAWING Description: Spec Section: 07 24 19 - WATER-DRAINAGE EXTERIOR INSULATION AND FINISH SYSTEM Status: OPEN | Info Exchange
| 11180 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-07 | Submittal Number: 07 24 19-2.0 From: YE ZHANG Final Due Date: 10/14/20 Subject: WATER-DRAINAGE EXTERIOR FINISH - PRODUCT DATA SHOP DRAWING Description: Spec Section: 07 24 19 - WATER-DRAINAGE EXTERIOR INSULATION AND FINISH SYSTEM Status: OPEN | Info Exchange
| 11515 | Responded and Closed | Approved as Noted | 2020-10-12 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 072419-0001-0 Product Data Shop Drawing EIFS-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 072419-0001-0 Product Data Shop Drawing EIFS-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-12 |  | 072419-0001-0 Product Data Shop Drawing EIFS-MAM_POP.pdf
07 24 19-002-01 | 07 24 19 | 07 24 19-002-01 WATER-DRAINAGE EXTERIOR FINISH - Added Details | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-10 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-24 | 2021-06-15 | 37 |  | Record Copies; Transfers; Submittals |  | 37 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12990 | Received | For Review | 2021-05-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-05-24 | Submittal Number: 07 24 19-2.1 From: YE ZHANG Final Due Date: 05/21/21 Subject: WATER-DRAINAGE EXTERIOR FINISH - ADDED DETAILS Description: Spec Section: 07 24 19 - WATER-DRAINAGE EXTERIOR INSULATION AND FINISH SYSTEM Status: OPEN | Info Exchange
| 16813 | Forwarded | For Review | 2021-05-10 | Allie Zimmerman | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-17 | Submittal Number: 07 24 19-2.1 From: YE ZHANG Final Due Date: 05/21/21 Subject: WATER-DRAINAGE EXTERIOR FINISH - ADDED DETAILS Description: Spec Section: 07 24 19 - WATER-DRAINAGE EXTERIOR INSULATION AND FINISH SYSTEM Status: OPEN | Info Exchange
| 17502 | Responded and Closed | Approved | 2021-06-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Ye Zhang (Mortenson Construction); Allie Zimmerman |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | Submittal 07 24 19-2 Revision 1 WATER-DRAINAGE EXTERIOR FINISH - Added Details_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-10 |  | Submittal 07 24 19-2 Revision 1 WATER-DRAINAGE EXTERIOR FINISH - Added Details_MAM Reviewed.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-15 02:00 |  | 07 24 19-2 Revision 1 WATER-DRAINAGE EXTERIOR FINISH - Added Details_MAM Reviewed_pop.pdf
07 26 16-001-00 | 07 26 16 - BELOW-GRADE VAPOR RETARDERS | 07 26 16-001-00 Below Grade Vapor Retarders - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-05 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-19 | 2019-09-23 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2019-09-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02307 | Received | For Review | 2019-09-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC); Mike Solfelt | 2019-09-19 | Submittal Number: 07 26 16-1.0 From: MIKE SOLFELT Final Due Date: 09/18/19 Subject: BELOW GRADE VAPOR RETARDERS - PRODUCT DATA Description: PRODUCT DATA. Spec Section: 07 26 16 - BELOW-GRADE VAPOR RETARDERS Status: OPEN | Info Exchange
| 03534 | Forwarded | For Review | 2019-09-05 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-09-12 | Submittal Number: 07 26 16-1.0 From: MIKE SOLFELT Final Due Date: 09/18/19 Subject: BELOW GRADE VAPOR RETARDERS - PRODUCT DATA Description: PRODUCT DATA. Spec Section: 07 26 16 - BELOW-GRADE VAPOR RETARDERS Status: OPEN | Info Exchange
| 02477 | Review Response | Approved | 2019-09-23 | Tom Usher (Populous) | Kelsea Conkright (Populous) |  | Kelsea - I thought this would be an easy one and it was. It is approved, stamped, flattened and ready to go home! | Info Exchange
| 03759 | Responded and Closed | Approved | 2019-09-23 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt |  | Response (Approved) from: Tom Usher (Populous) Remarks: See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-05 |  | 072616-0001-00 Vapor Barrier.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-05 |  | 072616-0001-00 Vapor Barrier.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2019-09-05 |  | 072616-0001-00 Vapor Barrier.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-23 02:00 |  | 072616-0001-00 Vapor Barrier_POP.pdf
07 27 26-002-00 | 07 27 26 - FLUID-APPLIED MEMBRANE AIR BARRIERS | 07 27 26-002-00 FLUID-APPLIED MEMBRANE AIR BARRIERS - Product Data (Drywall) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-27 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-11 | 2020-05-04 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05562 | Received | For Review | 2020-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-05-11 | Submittal Number: 07 27 26-2.0 From: TYRONE THORNTON Final Due Date: 05/08/20 Subject: FLUID-APPLIED MEMBRANE AIR BARRIERS - PRODUCT DATA (DRYWALL) Description: Spec Section: 07 27 26 - FLUID-APPLIED MEMBRANE AIR BARRIERS Status: OPEN | Info Exchange
| 07540 | Forwarded | For Review | 2020-04-27 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-04 | Submittal Number: 07 27 26-2.0 From: TYRONE THORNTON Final Due Date: 05/08/20 Subject: FLUID-APPLIED MEMBRANE AIR BARRIERS - PRODUCT DATA (DRYWALL) Description: Spec Section: 07 27 26 - FLUID-APPLIED MEMBRANE AIR BARRIERS Status: OPEN | Info Exchange
| 07728 | Responded and Closed | Approved | 2020-05-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | 072726-0002-0 Product Data Fluid-Applied Membrane Air Barriers-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-24 |  | 072726-0002-0 Product Data Fluid-Applied Membrane Air Barriers-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-04-24 |  | 072726-0002-0 Product Data Fluid-Applied Membrane Air Barriers-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-05-04 |  | 072726-0002-0 Product Data Fluid-Applied Membrane Air Barriers-MAM-POP.pdf
07 27 26-003-00 | 07 27 26 - FLUID-APPLIED MEMBRANE AIR BARRIERS | 07 27 26-003-00 FLUID-APPLIED MEMBRANE AIR BARRIERS - LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-02 | 2020-07-06 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06488 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 07 27 26-3.0 From: TYRONE THORNTON Final Due Date: 07/30/20 Subject: FLUID-APPLIED MEMBRANE AIR BARRIERS - LEED DATA Description: LABORATORY TEST REPORTS: FOR COATINGS, INDICATING COMPLIANCE WITH REQUIREMENTS FOR LOW- EMITTING MATERIALS. Spec Section: 07 27 26 - FLUID-APPLIED MEMBRANE AIR BARRIERS Status: OPEN | Info Exchange
| 08739 | Forwarded | For Review | 2020-06-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-25 | Submittal Number: 07 27 26-3.0 From: TYRONE THORNTON Final Due Date: 07/30/20 Subject: FLUID-APPLIED MEMBRANE AIR BARRIERS - LEED DATA Description: LABORATORY TEST REPORTS: FOR COATINGS, INDICATING COMPLIANCE WITH REQUIREMENTS FOR LOW- EMITTING MATERIALS. Spec Section: 07 27 26 - FLUID-APPLIED MEMBRANE AIR BARRIERS Status: OPEN | Info Exchange
| 06794 | Review Response | Approved as Noted | 2020-07-06 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 09135 | Responded and Closed | Approved as Noted | 2020-07-06 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 07 27 26 Fluid-Applied Membrane Air Barrier - LEED Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 07 27 26 Fluid-Applied Membrane Air Barrier - LEED Data_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-07-06 |  | 07 27 26 Fluid-Applied Membrane Air Barrier - LEED Data_MAM Reviewed_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-06-17 |  | 07 27 26 Fluid-Applied Membrane Air Barrier - LEED Data_MAM Reviewed.pdf
07 27 26-004-00 | 07 27 26 - FLUID-APPLIED MEMBRANE AIR BARRIERS | 07 27 26-004-00 FLUID-APPLIED MEMBRANE AIR BARRIERS - Product Data for Concrete Exterior Walls | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-08 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-22 | 2020-07-21 | 14 |  | Record Copies; Transfers; Submittals | 07 27 26-004-00-01 - 07 27 26-004-00 FLUID-APPLIED MEMBRANE AIR BARRIERS - Product Data for Concrete Exterior Walls | 14 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06859 | Received | For Review | 2020-07-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-07-22 | Submittal Number: 07 27 26-4.0 From: TYRONE THORNTON Final Due Date: 07/22/20 Subject: FLUID-APPLIED MEMBRANE AIR BARRIERS - PRODUCT DATA FOR CONCRETE EXTERIOR WALLS Description: Spec Section: 07 27 26 - FLUID-APPLIED MEMBRANE AIR BARRIERS Status: OPEN | Info Exchange
| 09206 | Forwarded | For Review | 2020-07-08 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-15 | Submittal Number: 07 27 26-4.0 From: TYRONE THORNTON Final Due Date: 07/22/20 Subject: FLUID-APPLIED MEMBRANE AIR BARRIERS - PRODUCT DATA FOR CONCRETE EXTERIOR WALLS Description: Spec Section: 07 27 26 - FLUID-APPLIED MEMBRANE AIR BARRIERS Status: OPEN | Info Exchange
| 09443 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-21 | Shaina Burris (Populous) | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-08 |  | 072726-0004-0 Product Data Fluid-Applied Membrane Air Barriers Ext Concrete Walls-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-08 |  | 072726-0004-0 Product Data Fluid-Applied Membrane Air Barriers Ext Concrete Walls-MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-07-20 |  | 072726-0004-0 Product Data Fluid-Applied Membrane Air Barriers-MAM_POP.pdf
07 27 26-004-00-01 | 07 27 26 - FLUID-APPLIED MEMBRANE AIR BARRIERS | 07 27 26-004-00 FLUID-APPLIED MEMBRANE AIR BARRIERS - Product Data for Concrete Exterior Walls | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 27 26-004-00 - 07 27 26-004-00 FLUID-APPLIED MEMBRANE AIR BARRIERS - Product Data for Concrete Exterior Walls | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-20 |  | 072726-0004-0 Product Data Fluid-Applied Membrane Air Barriers-MAM_POP.pdf
07 41 13-001-00 | 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM SHEET METAL ROOF PANELS | 07 41 13-001-00 STANDING SEAM METAL ROOF PANELS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-19 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-02 | 2020-04-05 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04962 | Received | For Review | 2020-03-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-04-02 | Submittal Number: 07 41 13-1.0 From: BROOKE BURCHAM Final Due Date: 04/02/20 Subject: STANDING SEAM METAL ROOF PANELS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR EACH TYPE OF PANEL AND ACCESSORY. Spec Section: 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM METAL ROOFING Status: OPEN | Info Exchange
| 06761 | Forwarded | For Review | 2020-03-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-03-26 | Submittal Number: 07 41 13-1.0 From: BROOKE BURCHAM Final Due Date: 04/02/20 Subject: STANDING SEAM METAL ROOF PANELS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR EACH TYPE OF PANEL AND ACCESSORY. Spec Section: 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM METAL ROOFING Status: OPEN | Info Exchange
| 07093 | Responded and Closed | Approved as Noted | 2020-04-05 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-19 |  | 074113-0001-0 Standing Seam Roof - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-19 |  | 074113-0001-0 Standing Seam Roof - Product Data.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-05 |  | 074113-0001-0 Standing Seam Roof - Product Data_POP.pdf
07 41 13-002-00 | 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM SHEET METAL ROOF PANELS | 07 41 13-002-00 STANDING SEAM METAL ROOF PANELS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-21 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-04 | 2020-06-08 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-06-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05979 | Received | For Review | 2020-05-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-04 | Submittal Number: 07 41 13-2.0 From: BROOKE BURCHAM Final Due Date: 06/05/20 Subject: STANDING SEAM METAL ROOF PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : SHOW FABRICATION AND INSTALLATION LAYOUTS OF SHEET METAL ROOFING, INCLUDING PLANS, ELEVATIONS, AND KEYED REFERENCES TO TERMINATION POINTS. DISTINGUISH BETWEEN SHOP- AND FIELD- ASSEMBLED WORK. INCLUDE THE FOLLOWING. 1. DETAILS FOR FORMING SHEET METAL ROOFING, INCLUDING SEAMS AND DIMENSIONS. 2. DETAILS FOR JOINING AND SECURING SHEET METAL ROOFING, INCLUDING LAYOUT OF FASTENERS, CLIPS, AND OTHER ATTACHMENTS. INCLUDE PATTERN OF SEAMS. 3. DETAILS OF TERMINATION POINTS AND ASSEMBLIES, INCLUDING FIXED POINTS. 4. DETAILS OF EXPANSION JOINTS, INCLUDING SHOWING DIRECTION OF EXPANSION AND CONTRACTION. 5. DETAILS OF ROOF PENETRATIONS. 6. DETAILS OF EDGE CONDITIONS, INCLUDING EAVES, RIDGES, VALLEYS, RAKES, STAINLESS STEEL CRICKETS, AND COUNTERFLASHINGS. 7. DETAILS OF SPECIAL CONDITIONS. 8. DETAILS OF CONNECTIONS TO ADJOINING WORK. 9. DETAILS OF THE FOLLOWING ACCESSORY ITEMS, ATA SCALE OF NOT LESS THAN 1-1/2-INCH. A. FLASHING AND TRIM. B. CONCEALED GUTTERS MADE OF 316 STAINLESS STEEL 24GAUGE, EXPANSION JOINTS, SOLDERED JOINTS. C. DOWNSPOUTS. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 08117 | Forwarded | For Review | 2020-05-21 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-28 | Submittal Number: 07 41 13-2.0 From: BROOKE BURCHAM Final Due Date: 06/05/20 Subject: STANDING SEAM METAL ROOF PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : SHOW FABRICATION AND INSTALLATION LAYOUTS OF SHEET METAL ROOFING, INCLUDING PLANS, ELEVATIONS, AND KEYED REFERENCES TO TERMINATION POINTS. DISTINGUISH BETWEEN SHOP- AND FIELD- ASSEMBLED WORK. INCLUDE THE FOLLOWING. 1. DETAILS FOR FORMING SHEET METAL ROOFING, INCLUDING SEAMS AND DIMENSIONS. 2. DETAILS FOR JOINING AND SECURING SHEET METAL ROOFING, INCLUDING LAYOUT OF FASTENERS, CLIPS, AND OTHER ATTACHMENTS. INCLUDE PATTERN OF SEAMS. 3. DETAILS OF TERMINATION POINTS AND ASSEMBLIES, INCLUDING FIXED POINTS. 4. DETAILS OF EXPANSION JOINTS, INCLUDING SHOWING DIRECTION OF EXPANSION AND CONTRACTION. 5. DETAILS OF ROOF PENETRATIONS. 6. DETAILS OF EDGE CONDITIONS, INCLUDING EAVES, RIDGES, VALLEYS, RAKES, STAINLESS STEEL CRICKETS, AND COUNTERFLASHINGS. 7. DETAILS OF SPECIAL CONDITIONS. 8. DETAILS OF CONNECTIONS TO ADJOINING WORK. 9. DETAILS OF THE FOLLOWING ACCESSORY ITEMS, ATA SCALE OF NOT LESS THAN 1-1/2-INCH. A. FLASHING AND TRIM. B. CONCEALED GUTTERS MADE OF 316 STAINLESS STEEL 24GAUGE, EXPANSION JOINTS, SOLDERED JOINTS. C. DOWNSPOUTS. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 08430 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-08 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached fore review and comments. Warranty submittal required per specifications. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-21 |  | 074113-0002-0 Standing Seam Roof - Shop Drawings_R1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-21 |  | 074113-0002-0 Standing Seam Roof - Shop Drawings_R1.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-08 |  | 074113-0002-0 Standing Seam Roof - Shop Drawings_POP.pdf
07 41 13-002-01 | 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM SHEET METAL ROOF PANELS | 07 41 13-002-01 STANDING SEAM METAL ROOF PANELS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-09 | 2020-10-05 | 11 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08324 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-09 | Submittal Number: 07 41 13-2.1 From: BROOKE BURCHAM Final Due Date: 10/09/20 Subject: STANDING SEAM METAL ROOF PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : SHOW FABRICATION AND INSTALLATION LAYOUTS OF SHEET METAL ROOFING, INCLUDING PLANS, ELEVATIONS, AND KEYED REFERENCES TO TERMINATION POINTS. DISTINGUISH BETWEEN SHOP- AND FIELD- ASSEMBLED WORK. INCLUDE THE FOLLOWING. 1. DETAILS FOR FORMING SHEET METAL ROOFING, INCLUDING SEAMS AND DIMENSIONS. 2. DETAILS FOR JOINING AND SECURING SHEET METAL ROOFING, INCLUDING LAYOUT OF FASTENERS, CLIPS, AND OTHER ATTACHMENTS. INCLUDE PATTERN OF SEAMS. 3. DETAILS OF TERMINATION POINTS AND ASSEMBLIES, INCLUDING FIXED POINTS. 4. DETAILS OF EXPANSION JOINTS, INCLUDING SHOWING DIRECTION OF EXPANSION AND CONTRACTION. 5. DETAILS OF ROOF PENETRATIONS. 6. DETAILS OF EDGE CONDITIONS, INCLUDING EAVES, RIDGES, VALLEYS, RAKES, STAINLESS STEEL CRICKETS, AND COUNTERFLASHINGS. 7. DETAILS OF SPECIAL CONDITIONS. 8. DETAILS OF CONNECTIONS TO ADJOINING WORK. 9. DETAILS OF THE FOLLOWING ACCESSORY ITEMS, ATA SCALE OF NOT LESS THAN 1-1/2-INCH. A. FLASHING AND TRIM. B. CONCEALED GUTTERS MADE OF 316 STAINLESS STEEL 24GAUGE, EXPANSION JOINTS, SOLDERED JOINTS. C. DOWNSPOUTS. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 11033 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-01 | Submittal Number: 07 41 13-2.1 From: BROOKE BURCHAM Final Due Date: 10/09/20 Subject: STANDING SEAM METAL ROOF PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : SHOW FABRICATION AND INSTALLATION LAYOUTS OF SHEET METAL ROOFING, INCLUDING PLANS, ELEVATIONS, AND KEYED REFERENCES TO TERMINATION POINTS. DISTINGUISH BETWEEN SHOP- AND FIELD- ASSEMBLED WORK. INCLUDE THE FOLLOWING. 1. DETAILS FOR FORMING SHEET METAL ROOFING, INCLUDING SEAMS AND DIMENSIONS. 2. DETAILS FOR JOINING AND SECURING SHEET METAL ROOFING, INCLUDING LAYOUT OF FASTENERS, CLIPS, AND OTHER ATTACHMENTS. INCLUDE PATTERN OF SEAMS. 3. DETAILS OF TERMINATION POINTS AND ASSEMBLIES, INCLUDING FIXED POINTS. 4. DETAILS OF EXPANSION JOINTS, INCLUDING SHOWING DIRECTION OF EXPANSION AND CONTRACTION. 5. DETAILS OF ROOF PENETRATIONS. 6. DETAILS OF EDGE CONDITIONS, INCLUDING EAVES, RIDGES, VALLEYS, RAKES, STAINLESS STEEL CRICKETS, AND COUNTERFLASHINGS. 7. DETAILS OF SPECIAL CONDITIONS. 8. DETAILS OF CONNECTIONS TO ADJOINING WORK. 9. DETAILS OF THE FOLLOWING ACCESSORY ITEMS, ATA SCALE OF NOT LESS THAN 1-1/2-INCH. A. FLASHING AND TRIM. B. CONCEALED GUTTERS MADE OF 316 STAINLESS STEEL 24GAUGE, EXPANSION JOINTS, SOLDERED JOINTS. C. DOWNSPOUTS. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 11288 | Responded and Closed | Approved as Noted | 2020-10-05 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 074113-0002-1 Standing Seam Roof - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 074113-0002-1 Standing Seam Roof - Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-24 |  | 074113-0002-1 Standing Seam Roof - Shop Drawings.pdf
07 41 13-003-00 | 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM SHEET METAL ROOF PANELS | 07 41 13-003-00 ZINC DOUBLE LOCK STANDING-SEAM METAL ROOF PANELS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-15 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-29 | 2020-05-04 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05372 | Received | For Review | 2020-04-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-04-29 | Submittal Number: 07 41 13-3.0 From: BROOKE BURCHAM Final Due Date: 04/29/20 Subject: ZINC DOUBLE LOCK STANDING-SEAM METAL ROOF PANELS - SAMPLES Description: SAMPLES : 24-INCH SQUARE METAL SAMPLES WITHA MINIMUM OF ONE SEAM, RIDGE AND EAVE DETAIL, FINISHED AS SPECIFIED. MOUNT ON VMZ DELTA MAT/ UNDERLAYMENT/PLYWOOD SUBSTRATE. Spec Section: 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM METAL ROOFING Status: OPEN | Info Exchange
| 07294 | Forwarded | For Review | 2020-04-15 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-22 | Submittal Number: 07 41 13-3.0 From: BROOKE BURCHAM Final Due Date: 04/29/20 Subject: ZINC DOUBLE LOCK STANDING-SEAM METAL ROOF PANELS - SAMPLES Description: SAMPLES : 24-INCH SQUARE METAL SAMPLES WITHA MINIMUM OF ONE SEAM, RIDGE AND EAVE DETAIL, FINISHED AS SPECIFIED. MOUNT ON VMZ DELTA MAT/ UNDERLAYMENT/PLYWOOD SUBSTRATE. Spec Section: 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM METAL ROOFING Status: OPEN | Info Exchange
| 07747 | Responded and Closed | Approved as Noted | 2020-05-04 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-15 |  | 074113-0003-0 Standing Seam Roof - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-15 |  | 074113-0003-0 Standing Seam Roof - Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-04 |  | 074113-0003-0 Standing Seam Roof - Samples_POP.pdf
07 41 13-003-01 | 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM SHEET METAL ROOF PANELS | 07 41 13-003-01 ZINC DOUBLE LOCK STANDING-SEAM METAL ROOF PANELS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-08 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-22 | 2020-06-10 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-06-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06251 | Received | For Review | 2020-06-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-22 | Submittal Number: 07 41 13-3.1 From: BROOKE BURCHAM Final Due Date: 06/22/20 Subject: ZINC DOUBLE LOCK STANDING-SEAM METAL ROOF PANELS - SAMPLES Description: SAMPLES : 24-INCH SQUARE METAL SAMPLES WITHA MINIMUM OF ONE SEAM, RIDGE AND EAVE DETAIL, FINISHED AS SPECIFIED. MOUNT ON VMZ DELTA MAT/ UNDERLAYMENT/PLYWOOD SUBSTRATE. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 08436 | Forwarded | For Review | 2020-06-08 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) |  | Submittal Number: 07 41 13-3.1 From: BROOKE BURCHAM Final Due Date: 06/22/20 Subject: ZINC DOUBLE LOCK STANDING-SEAM METAL ROOF PANELS - SAMPLES Description: SAMPLES : 24-INCH SQUARE METAL SAMPLES WITHA MINIMUM OF ONE SEAM, RIDGE AND EAVE DETAIL, FINISHED AS SPECIFIED. MOUNT ON VMZ DELTA MAT/ UNDERLAYMENT/PLYWOOD SUBSTRATE. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 08536 | Responded and Closed | Approved | 2020-06-10 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 074113-0003-1 Standing Seam Roof - Color Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 074113-0003-1 Standing Seam Roof - Color Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-10 |  | 074213.19-0005-1 Samples for Color Verification_POP.pdf
07 41 13-005-00 | 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM SHEET METAL ROOF PANELS | 07 41 13-005-00 ZINC DOUBLE LOCK STANDING-SEAM METAL ROOF PANELS - Mockups | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-07 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-21 | 2021-05-21 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-05-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12974 | Received | For Review | 2021-05-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-05-21 | Submittal Number: 07 41 13-5.0 From: CHRISTIAN GENEROSA Final Due Date: 05/21/21 Subject: ZINC DOUBLE LOCK STANDING-SEAM METAL ROOF PANELS - MOCKUPS Description: INITIAL INSPECTION MORTENSON REPORT ON STANDING SEAM METAL ROOF. SUBMITTING FOR RECORD. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 16793 | Forwarded | For Review | 2021-05-07 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-14 | Submittal Number: 07 41 13-5.0 From: CHRISTIAN GENEROSA Final Due Date: 05/21/21 Subject: ZINC DOUBLE LOCK STANDING-SEAM METAL ROOF PANELS - MOCKUPS Description: INITIAL INSPECTION MORTENSON REPORT ON STANDING SEAM METAL ROOF. SUBMITTING FOR RECORD. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 17144 | Responded and Closed | No Action Taken or Required | 2021-05-21 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Received for record. | Info Exchange
| 17163 | Sent | For Information Only | 2021-05-25 | Josh Dobken (Populous) | Tyrone Thornton (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Responded and Closed (No Action Taken or Required) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Received for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-06 |  | 2021-04-22 Standing Seam Roof Initial Inspection Meeting Minutes.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-06 |  | 2021-04-22 Standing Seam Roof Initial Inspection Meeting Minutes.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-05 02:00 |  | 2021-04-22 Standing Seam Roof Initial Inspection Meeting Minutes.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-05-05 02:00 |  | 2021-04-22 Standing Seam Roof Initial Inspection Meeting Minutes.pdf
07 41 13-006-00 | 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM SHEET METAL ROOF PANELS | 07 41 13-006-0 STANDING SEAM METAL ROOF PANELS - Self Adhering Sheet Underlayment PD | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-26 | 2020-06-09 | 30 |  | Record Copies; Transfers; Submittals |  | 30 |  | 2020-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05796 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-26 | Submittal Number: 07 41 13-6.0 From: BROOKE BURCHAM Final Due Date: 05/25/20 Subject: STANDING SEAM METAL ROOF PANELS - SELF ADHERING SHEET UNDERLAYMENT PD Description: PRODUCT DATA FOR UNDERLAYMENT FOR THE STANDING SEAM METAL ROOF. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 07859 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-18 | Submittal Number: 07 41 13-6.0 From: BROOKE BURCHAM Final Due Date: 05/25/20 Subject: STANDING SEAM METAL ROOF PANELS - SELF ADHERING SHEET UNDERLAYMENT PD Description: PRODUCT DATA FOR UNDERLAYMENT FOR THE STANDING SEAM METAL ROOF. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 08505 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-09 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 074113-0006-0 Standing Seam Roof - Underlayment PD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 074113-0006-0 Standing Seam Roof - Underlayment PD.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 074113-0006-0 Standing Seam Roof - Underlayment PD.pdf
07 41 13-006-01 | 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM SHEET METAL ROOF PANELS | 07 41 13-006-01 STANDING SEAM METAL ROOF PANELS - Self Adhering Sheet Underlayment PD | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-10 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-24 | 2020-07-21 | 42 |  | Record Copies; Transfers; Submittals |  | 42 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06321 | Received | For Review | 2020-06-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-24 | Submittal Number: 07 41 13-6.1 From: BROOKE BURCHAM Final Due Date: 06/25/20 Subject: STANDING SEAM METAL ROOF PANELS - SELF ADHERING SHEET UNDERLAYMENT PD Description: PRODUCT DATA FOR UNDERLAYMENT FOR THE STANDING SEAM METAL ROOF. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 08525 | Forwarded | For Review | 2020-06-10 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-17 | Submittal Number: 07 41 13-6.1 From: BROOKE BURCHAM Final Due Date: 06/25/20 Subject: STANDING SEAM METAL ROOF PANELS - SELF ADHERING SHEET UNDERLAYMENT PD Description: PRODUCT DATA FOR UNDERLAYMENT FOR THE STANDING SEAM METAL ROOF. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 09452 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-21 | Tom Usher (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-10 |  | 074113-0006-1 Underlayment Product Data and Warranties.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-10 |  | 074113-0006-1 Underlayment Product Data and Warranties.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2020-07-20 02:00 |  | 074113-0006-1 Underlayment Product Data and Warranties_POP.pdf
07 41 13-006-02 | 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM SHEET METAL ROOF PANELS | 07 41 13-006-02 STANDING SEAM METAL ROOF PANELS - Self Adhering Sheet Underlayment PD | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-29 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-12 | 2020-08-19 | 22 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07223 | Received | For Review | 2020-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-12 | Submittal Number: 07 41 13-6.2 From: BROOKE BURCHAM Final Due Date: 08/12/20 Subject: STANDING SEAM METAL ROOF PANELS - SELF ADHERING SHEET UNDERLAYMENT PD Description: PRODUCT DATA FOR UNDERLAYMENT FOR THE STANDING SEAM METAL ROOF. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 09636 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-04 | Submittal Number: 07 41 13-6.2 From: BROOKE BURCHAM Final Due Date: 08/12/20 Subject: STANDING SEAM METAL ROOF PANELS - SELF ADHERING SHEET UNDERLAYMENT PD Description: PRODUCT DATA FOR UNDERLAYMENT FOR THE STANDING SEAM METAL ROOF. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 10137 | Responded and Closed | Approved | 2020-08-19 | Shaina Burris (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-28 |  | 074113-0006-2 Underlayment Product Data and Warranties.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-28 |  | 074113-0006-2 Underlayment Product Data and Warranties.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-07-28 |  | 074113-0006-2 Underlayment Product Data and Warranties.pdf
07 41 13-008-00 | 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM SHEET METAL ROOF PANELS | 07 41 13-008-00 Standing Seam Metal Roof - #3 Fastener Substitution Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-02 | Responded and Closed - Not Required For Review |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-16 | 2021-02-09 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11135 | Received | For Review | 2021-02-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-02-16 | Submittal Number: 07 41 13-8.0 From: CHRISTIAN GENEROSA Final Due Date: 02/16/21 Subject: STANDING SEAM METAL ROOF - #3 FASTENER SUBSTITUTION PRODUCT DATA Description: THIS SUBMITTAL IS FOR RECORD AND SHOWS A SUBSTITUTE #3 FASTENER FOR THE STANDING SEAM METAL ROOF. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 14446 | Forwarded | For Review | 2021-02-02 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-09 | Submittal Number: 07 41 13-8.0 From: CHRISTIAN GENEROSA Final Due Date: 02/16/21 Subject: STANDING SEAM METAL ROOF - #3 FASTENER SUBSTITUTION PRODUCT DATA Description: THIS SUBMITTAL IS FOR RECORD AND SHOWS A SUBSTITUTE #3 FASTENER FOR THE STANDING SEAM METAL ROOF. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 14624 | Responded and Closed | Not Required For Review | 2021-02-09 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | 074113-0008-00 Standing Seam Metal Roof Fastener Substitution_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-02 |  | 074113-0008-00 Standing Seam Metal Roof Fastener Substitution_MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-09 |  | 07 41 13-008-00 Standing Seam Metal Roof Fastener Substitution_MAM_POP.pdf
07 41 13-009-00 | 07 41 13 - ZINC DOUBLE LOCK STANDING SEAM SHEET METAL ROOF PANELS | 07 41 13-009-00 STANDING SEAM METAL ROOF PANELS - Roof Insulation Product Data (Atlas ACFoam II) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-23 | 2021-04-23 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-04-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12500 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Generosa | 2021-04-23 | Submittal Number: 07 41 13-9.0 From: CHRISTIAN GENEROSA Final Due Date: 04/21/21 Subject: STANDING SEAM METAL ROOF PANELS - ROOF INSULATION PRODUCT DATA (ATLAS ACFOAM II) Description: RESUBMITTAL OF PRODUCT DATA FOR THE ROOFING INSULATION USED AT THE ATRIUM ROOF. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 16188 | Forwarded | For Review | 2021-04-08 | Christian Generosa | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 07 41 13-9.0 From: CHRISTIAN GENEROSA Final Due Date: 04/21/21 Subject: STANDING SEAM METAL ROOF PANELS - ROOF INSULATION PRODUCT DATA (ATLAS ACFOAM II) Description: RESUBMITTAL OF PRODUCT DATA FOR THE ROOFING INSULATION USED AT THE ATRIUM ROOF. Spec Section: 07 41 13 - STANDING SEAM METAL ROOF PANELS Status: OPEN | Info Exchange
| 16478 | Responded and Closed | Approved as Noted | 2021-04-23 | Tom Usher (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com; Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 2021-04-07 074113-0009-00 SSMP Roof Insulation Product Data_MAM.pdf
| Forwarded |  | Christian Generosa | 1 | 2021-04-08 |  | 2021-04-07 074113-0009-00 SSMP Roof Insulation Product Data_MAM.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2021-04-23 |  | 2021-04-07 074113-0009-00 SSMP Roof Insulation Product Data_MAM_POP.pdf
07 42 13.13-001-00 | 07 42 13.13 - FORMED METAL WALL PANELS | 07 42 13.13-001-00 FORMED METAL WALL PANELS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-02 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-16 | 2021-02-08 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11132 | Received | For Review | 2021-02-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction); Christian Generosa | 2021-02-16 | Submittal Number: 07 42 13.13-1.0 From: BROOKE BURCHAM Final Due Date: 02/26/21 Subject: FORMED METAL WALL PANELS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR EACH TYPE OF PANEL AND ACCESSORY. Spec Section: 07 42 13.13 - FORMED METAL WALL PANELS Status: OPEN | Info Exchange
| 14443 | Forwarded | For Review | 2021-02-02 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-09 | Submittal Number: 07 42 13.13-1.0 From: BROOKE BURCHAM Final Due Date: 02/26/21 Subject: FORMED METAL WALL PANELS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR EACH TYPE OF PANEL AND ACCESSORY. Spec Section: 07 42 13.13 - FORMED METAL WALL PANELS Status: OPEN | Info Exchange
| 14570 | Responded and Closed | Approved as Noted | 2021-02-08 | Todd Spangler (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | 2021-02-02 07 42 13.13-0001-00 Formed Metal Wall Panels - Product Data_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-02 |  | 2021-02-02 07 42 13.13-0001-00 Formed Metal Wall Panels - Product Data_MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-08 |  | 07 42 13.13-0001-00 Formed Metal Wall Panels - Product Data_MAM_POP.pdf
07 42 13.13-003-00 | 07 42 13.13 - FORMED METAL WALL PANELS | 07 42 13.13-003-00 FORMED METAL WALL PANELS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-12 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-26 | 2021-03-29 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11973 | Received | For Review | 2021-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-26 | Submittal Number: 07 42 13.13-3.0 From: CHRISTIAN GENEROSA Final Due Date: 03/26/21 Subject: FORMED METAL WALL PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE FABRICATION AND INSTALLATION LAYOUTS OF METAL PANELS; DETAILS OF EDGE CONDITIONS, JOINTS, PANEL PROFILES, CORNERS, ANCHORAGES, ATTACHMENT SYSTEM, TRIM, FLASHINGS, CLOSURES, AND ACCESSORIES; AND SPECIAL DETAILS. 2. ACCESSORIES: INCLUDE DETAILS OF THE FLASHING, TRIM, AND ANCHORAGE SYSTEMS, ATA SCALE OF NOT LESS THAN 1-1/2 INCHES PER 12 INCHES. Spec Section: 07 42 13.13 - FORMED METAL WALL PANELS Status: OPEN | Info Exchange
| 15506 | Forwarded | For Review | 2021-03-12 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-19 | Submittal Number: 07 42 13.13-3.0 From: CHRISTIAN GENEROSA Final Due Date: 03/26/21 Subject: FORMED METAL WALL PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE FABRICATION AND INSTALLATION LAYOUTS OF METAL PANELS; DETAILS OF EDGE CONDITIONS, JOINTS, PANEL PROFILES, CORNERS, ANCHORAGES, ATTACHMENT SYSTEM, TRIM, FLASHINGS, CLOSURES, AND ACCESSORIES; AND SPECIAL DETAILS. 2. ACCESSORIES: INCLUDE DETAILS OF THE FLASHING, TRIM, AND ANCHORAGE SYSTEMS, ATA SCALE OF NOT LESS THAN 1-1/2 INCHES PER 12 INCHES. Spec Section: 07 42 13.13 - FORMED METAL WALL PANELS Status: OPEN | Info Exchange
| 15898 | Responded and Closed | Approved as Noted | 2021-03-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | SEE ATTACHED | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-12 |  | 2021-03-12 074213.13-0003-00 Formed Metal Panel SD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-12 |  | 2021-03-12 074213.13-0003-00 Formed Metal Panel SD_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-26 |  | 07 42 13.13-0003-00 Formed Metal Panel SD_MAM_POP.pdf
07 42 13.13-004-00 | 07 42 13.13 - FORMED METAL WALL PANELS | 07 42 13.13-004-00 FORMED METAL WALL PANELS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-06 | 2 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12365 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 07 42 13.13-4.0 From: CHRISTIAN GENEROSA Final Due Date: 04/12/21 Subject: FORMED METAL WALL PANELS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH, PREPARED ON SAMPLES OF SIZE INDICATED BELOW: 1. METAL PANELS: 12 INCHES LONG BY ACTUAL PANEL WIDTH. INCLUDE FASTENERS, CLOSURES, AND OTHER METAL PANEL ACCESSORIES. Spec Section: 07 42 13.13 - FORMED METAL WALL PANELS Status: OPEN | Info Exchange
| 16021 | Forwarded | For Review | 2021-04-01 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 07 42 13.13-4.0 From: CHRISTIAN GENEROSA Final Due Date: 04/12/21 Subject: FORMED METAL WALL PANELS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH, PREPARED ON SAMPLES OF SIZE INDICATED BELOW: 1. METAL PANELS: 12 INCHES LONG BY ACTUAL PANEL WIDTH. INCLUDE FASTENERS, CLOSURES, AND OTHER METAL PANEL ACCESSORIES. Spec Section: 07 42 13.13 - FORMED METAL WALL PANELS Status: OPEN | Info Exchange
| 16098 | Responded and Closed | Approved | 2021-04-06 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com; Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 2021-03-28 074213.13-0004-00 Atas Panel Samples_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 2021-03-28 074213.13-0004-00 Atas Panel Samples_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-06 |  | 07 42 13.13-0004-00 Atas Panel Samples_MAM_POP.pdf
07 42 13.19-002-00 | 07 42 13.19 - INSULATED METAL WALL PANELS | 07 42 13.19-002-00 INSULATED METAL WALL PANELS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-16 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-30 | 2020-05-12 | 27 |  | Record Copies; Transfers; Submittals | 07 42 13.19-002-00-01 - 07 42 13.19-002-00 INSULATED METAL WALL PANELS - Product Data | 27 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05387 | Received | For Review | 2020-04-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-04-30 | Submittal Number: 07 42 13.19-2.0 From: BROOKE BURCHAM Final Due Date: 04/30/20 Subject: INSULATED METAL WALL PANELS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR EACH TYPE OF PANEL AND ACCESSORY. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 07313 | Forwarded | For Review | 2020-04-16 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-23 | Submittal Number: 07 42 13.19-2.0 From: BROOKE BURCHAM Final Due Date: 04/30/20 Subject: INSULATED METAL WALL PANELS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR EACH TYPE OF PANEL AND ACCESSORY. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 07893 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-12 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-16 |  | 074213.19-0002-0 Insulated Wall Panels - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-16 |  | 074213.19-0002-0 Insulated Wall Panels - Product Data.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-04-16 |  | 074213.19-0002-0 Insulated Wall Panels - Product Data.pdf
07 42 13.19-002-00-01 | 07 42 13.19 - INSULATED METAL WALL PANELS | 07 42 13.19-002-00 INSULATED METAL WALL PANELS - Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 42 13.19-002-00 - 07 42 13.19-002-00 INSULATED METAL WALL PANELS - Product Data | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-16 |  | 074213.19-0002-0 Insulated Wall Panels - Product Data.pdf
07 42 13.19-003-00 | 07 42 13.19 - INSULATED METAL WALL PANELS | 07 42 13.19-003-00 INSULATED METAL WALL PANELS - LEED Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-24 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-07 | 2020-08-20 | 28 |  | Record Copies; Transfers; Submittals | 07 42 13.19-003-01 - 07 42 13.19-003-00 INSULATED METAL WALL PANELS - LEED Product Data | 27 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07139 | Received | For Review | 2020-07-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-07 | Submittal Number: 07 42 13.19-3.0 From: BROOKE BURCHAM Final Due Date: 08/07/20 Subject: INSULATED METAL WALL PANELS - LEED PRODUCT DATA Description: PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 09534 | Forwarded | For Review | 2020-07-25 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-03 | Submittal Number: 07 42 13.19-3.0 From: BROOKE BURCHAM Final Due Date: 08/07/20 Subject: INSULATED METAL WALL PANELS - LEED PRODUCT DATA Description: PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 10194 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-20 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | CONTRACTOR TO SUBMIT LEED v4 PRODUCT DATA REPORTING FORM. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-24 |  | 074213.19-0003-0 Insulated Wall Panels - LEED Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-24 |  | 074213.19-0003-0 Insulated Wall Panels - LEED Product Data.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-20 02:00 |  | 074213.19-0003-0 Insulated Wall Panels - LEED Product Data_pop.pdf
07 42 13.19-003-01 | 07 42 13.19 - INSULATED METAL WALL PANELS | 07 42 13.19-003-00 INSULATED METAL WALL PANELS - LEED Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 42 13.19-003-00 - 07 42 13.19-003-00 INSULATED METAL WALL PANELS - LEED Product Data | -1 | 2020-09-03
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 02:00 |  | 074213.19-0003-0 Insulated Wall Panels - LEED Product Data_pop.pdf
07 42 13.19-004-00 | 07 42 13.19 - INSULATED METAL WALL PANELS | 07 42 13.19-004-00 INSULATED METAL WALL PANELS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-03 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Kristin Long (Populous) |  |  |  | 2020-08-17 | 2020-08-20 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07320 | Received | For Review | 2020-08-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-17 | Submittal Number: 07 42 13.19-4.0 From: BROOKE BURCHAM Final Due Date: 05/08/20 Subject: INSULATED METAL WALL PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE FABRICATION AND INSTALLATION LAYOUTS OF METAL PANELS; DETAILS OF EDGE CONDITIONS, JOINTS, PANEL PROFILES, CORNERS, ANCHORAGES, ATTACHMENT SYSTEM, TRIM, FLASHINGS, CLOSURES, AND ACCESSORIES; AND SPECIAL DETAILS. 2. INCLUDE ANCHORING ACCESSORIES PLACEMENT LOCATIONS FOR COORDINATION WITH GLASS FIBER CONCRETE PANEL PLACEMENT AND OTHER MATERIALS. 3. ACCESSORIES: INCLUDE DETAILS OF THE FLASHING, TRIM, AND ANCHORAGE SYSTEMS, ATA SCALE OF NOT LESS THAN 1-1/2 INCHES PER 12 INCHES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 09759 | Forwarded | For Review | 2020-08-03 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-10 | Submittal Number: 07 42 13.19-4.0 From: BROOKE BURCHAM Final Due Date: 05/08/20 Subject: INSULATED METAL WALL PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE FABRICATION AND INSTALLATION LAYOUTS OF METAL PANELS; DETAILS OF EDGE CONDITIONS, JOINTS, PANEL PROFILES, CORNERS, ANCHORAGES, ATTACHMENT SYSTEM, TRIM, FLASHINGS, CLOSURES, AND ACCESSORIES; AND SPECIAL DETAILS. 2. INCLUDE ANCHORING ACCESSORIES PLACEMENT LOCATIONS FOR COORDINATION WITH GLASS FIBER CONCRETE PANEL PLACEMENT AND OTHER MATERIALS. 3. ACCESSORIES: INCLUDE DETAILS OF THE FLASHING, TRIM, AND ANCHORAGE SYSTEMS, ATA SCALE OF NOT LESS THAN 1-1/2 INCHES PER 12 INCHES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 09779 | Forwarded | For Review | 2020-08-04 | Shaina Burris (Populous) | Kristin Long (Populous) | 2020-08-11 | Submittal Number: 07 42 13.19-4.0 From: BROOKE BURCHAM Final Due Date: 05/08/20 Subject: INSULATED METAL WALL PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE FABRICATION AND INSTALLATION LAYOUTS OF METAL PANELS; DETAILS OF EDGE CONDITIONS, JOINTS, PANEL PROFILES, CORNERS, ANCHORAGES, ATTACHMENT SYSTEM, TRIM, FLASHINGS, CLOSURES, AND ACCESSORIES; AND SPECIAL DETAILS. 2. INCLUDE ANCHORING ACCESSORIES PLACEMENT LOCATIONS FOR COORDINATION WITH GLASS FIBER CONCRETE PANEL PLACEMENT AND OTHER MATERIALS. 3. ACCESSORIES: INCLUDE DETAILS OF THE FLASHING, TRIM, AND ANCHORAGE SYSTEMS, ATA SCALE OF NOT LESS THAN 1-1/2 INCHES PER 12 INCHES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 10176 | Responded and Closed | Revise and Resubmit | 2020-08-20 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-03 |  | 074213.19-0004-0 Insulated Wall Panels - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-03 |  | 074213.19-0004-0 Insulated Wall Panels - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-03 |  | 074213.19-0004-0 Insulated Wall Panels - Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-20 |  | 074213.19-0004-0 Insulated Wall Panels - Shop Drawings_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-20 |  | A2-2A - MECHANICAL MEZZANINE LEVEL - AREA A.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-20 |  | A2-2D - MECHANICAL MEZZANINE LEVEL - AREA D.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-20 |  | A3-05-3 - ENLARGED PLANS - SE MECH INTAKE & EXHAUST.pdf
07 42 13.19-004-01 | 07 42 13.19 - INSULATED METAL WALL PANELS | 07 42 13.19-004-01 INSULATED METAL WALL PANELS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-15 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kristin Long (Populous) |  |  |  | 2020-10-29 | 2020-11-02 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-11-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08799 | Received | For Review | 2020-10-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-29 | Submittal Number: 07 42 13.19-4.1 From: CHRISTIAN GENEROSA Final Due Date: 10/30/20 Subject: INSULATED METAL WALL PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE FABRICATION AND INSTALLATION LAYOUTS OF METAL PANELS; DETAILS OF EDGE CONDITIONS, JOINTS, PANEL PROFILES, CORNERS, ANCHORAGES, ATTACHMENT SYSTEM, TRIM, FLASHINGS, CLOSURES, AND ACCESSORIES; AND SPECIAL DETAILS. 2. INCLUDE ANCHORING ACCESSORIES PLACEMENT LOCATIONS FOR COORDINATION WITH GLASS FIBER CONCRETE PANEL PLACEMENT AND OTHER MATERIALS. 3. ACCESSORIES: INCLUDE DETAILS OF THE FLASHING, TRIM, AND ANCHORAGE SYSTEMS, ATA SCALE OF NOT LESS THAN 1-1/2 INCHES PER 12 INCHES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 11632 | Forwarded | For Review | 2020-10-15 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-22 | Submittal Number: 07 42 13.19-4.1 From: CHRISTIAN GENEROSA Final Due Date: 10/30/20 Subject: INSULATED METAL WALL PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE FABRICATION AND INSTALLATION LAYOUTS OF METAL PANELS; DETAILS OF EDGE CONDITIONS, JOINTS, PANEL PROFILES, CORNERS, ANCHORAGES, ATTACHMENT SYSTEM, TRIM, FLASHINGS, CLOSURES, AND ACCESSORIES; AND SPECIAL DETAILS. 2. INCLUDE ANCHORING ACCESSORIES PLACEMENT LOCATIONS FOR COORDINATION WITH GLASS FIBER CONCRETE PANEL PLACEMENT AND OTHER MATERIALS. 3. ACCESSORIES: INCLUDE DETAILS OF THE FLASHING, TRIM, AND ANCHORAGE SYSTEMS, ATA SCALE OF NOT LESS THAN 1-1/2 INCHES PER 12 INCHES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 11727 | Forwarded | For Review | 2020-10-20 | Todd Spangler (Populous) | Kristin Long (Populous) |  | Submittal Number: 07 42 13.19-4.1 From: CHRISTIAN GENEROSA Final Due Date: 10/30/20 Subject: INSULATED METAL WALL PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE FABRICATION AND INSTALLATION LAYOUTS OF METAL PANELS; DETAILS OF EDGE CONDITIONS, JOINTS, PANEL PROFILES, CORNERS, ANCHORAGES, ATTACHMENT SYSTEM, TRIM, FLASHINGS, CLOSURES, AND ACCESSORIES; AND SPECIAL DETAILS. 2. INCLUDE ANCHORING ACCESSORIES PLACEMENT LOCATIONS FOR COORDINATION WITH GLASS FIBER CONCRETE PANEL PLACEMENT AND OTHER MATERIALS. 3. ACCESSORIES: INCLUDE DETAILS OF THE FLASHING, TRIM, AND ANCHORAGE SYSTEMS, ATA SCALE OF NOT LESS THAN 1-1/2 INCHES PER 12 INCHES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 12088 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-02 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-14 |  | 074213.19-0004- 1 Insulated Wall Panel Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-14 |  | 074213.19-0004- 1 Insulated Wall Panel Shop Drawings.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-10-14 |  | 074213.19-0004- 1 Insulated Wall Panel Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-29 |  | 074213.19-0004- 1 Insulated Wall Panel Shop Drawings_POP.pdf
07 42 13.19-004-02 | 07 42 13.19 - INSULATED METAL WALL PANELS | 07 42 13.19-004-02 INSULATED METAL WALL PANELS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-21 | 2020-12-14 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-12-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09938 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company); Christian Generosa | 2020-12-21 | Submittal Number: 07 42 13.19-4.2 From: CHRISTIAN GENEROSA Final Due Date: 12/18/20 Subject: INSULATED METAL WALL PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE FABRICATION AND INSTALLATION LAYOUTS OF METAL PANELS; DETAILS OF EDGE CONDITIONS, JOINTS, PANEL PROFILES, CORNERS, ANCHORAGES, ATTACHMENT SYSTEM, TRIM, FLASHINGS, CLOSURES, AND ACCESSORIES; AND SPECIAL DETAILS. 2. INCLUDE ANCHORING ACCESSORIES PLACEMENT LOCATIONS FOR COORDINATION WITH GLASS FIBER CONCRETE PANEL PLACEMENT AND OTHER MATERIALS. 3. ACCESSORIES: INCLUDE DETAILS OF THE FLASHING, TRIM, AND ANCHORAGE SYSTEMS, ATA SCALE OF NOT LESS THAN 1-1/2 INCHES PER 12 INCHES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 13017 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 07 42 13.19-4.2 From: CHRISTIAN GENEROSA Final Due Date: 12/18/20 Subject: INSULATED METAL WALL PANELS - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE FABRICATION AND INSTALLATION LAYOUTS OF METAL PANELS; DETAILS OF EDGE CONDITIONS, JOINTS, PANEL PROFILES, CORNERS, ANCHORAGES, ATTACHMENT SYSTEM, TRIM, FLASHINGS, CLOSURES, AND ACCESSORIES; AND SPECIAL DETAILS. 2. INCLUDE ANCHORING ACCESSORIES PLACEMENT LOCATIONS FOR COORDINATION WITH GLASS FIBER CONCRETE PANEL PLACEMENT AND OTHER MATERIALS. 3. ACCESSORIES: INCLUDE DETAILS OF THE FLASHING, TRIM, AND ANCHORAGE SYSTEMS, ATA SCALE OF NOT LESS THAN 1-1/2 INCHES PER 12 INCHES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 13234 | Responded and Closed | Approved | 2020-12-14 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-04 |  | 2020-12-4 200714_48234 IFA - Issue F (MCK)_MAM Markup.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-04 |  | 2020-12-4 200714_48234 IFA - Issue F (MCK)_MAM Markup.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-14 |  | 2020-12-4 200714_48234 IFA - Issue F (MCK)_MAM Markup_POP.pdf
07 42 13.19-005-00 | 07 42 13.19 - INSULATED METAL WALL PANELS | 07 42 13.19-005-00 INSULATED METAL WALL PANELS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-15 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-29 | 2020-05-04 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05373 | Received | For Review | 2020-04-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-04-29 | Submittal Number: 07 42 13.19-5.0 From: BROOKE BURCHAM Final Due Date: 04/28/20 Subject: INSULATED METAL WALL PANELS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH, PREPARED ON SAMPLES OF SIZE INDICATED BELOW. 1. METAL PANELS: 12 INCHES LONG BY ACTUAL PANEL WIDTH. INCLUDE FASTENERS, CLOSURES, AND OTHER METAL PANEL ACCESSORIES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 07295 | Forwarded | For Review | 2020-04-15 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-22 | Submittal Number: 07 42 13.19-5.0 From: BROOKE BURCHAM Final Due Date: 04/28/20 Subject: INSULATED METAL WALL PANELS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH, PREPARED ON SAMPLES OF SIZE INDICATED BELOW. 1. METAL PANELS: 12 INCHES LONG BY ACTUAL PANEL WIDTH. INCLUDE FASTENERS, CLOSURES, AND OTHER METAL PANEL ACCESSORIES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 07748 | Responded and Closed | Approved as Noted | 2020-05-04 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | see attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-15 |  | 074213.19-0005-0 Insulated Wall Panels - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-15 |  | 074213.19-0005-0 Insulated Wall Panels - Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-04 |  | 074213.19-0005-0 Insulated Wall Panels - Samples_POP.pdf
07 42 13.19-005-01 | 07 42 13.19 - INSULATED METAL WALL PANELS | 07 42 13.19-005-01 INSULATED METAL WALL PANELS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-02 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-16 | 2020-06-10 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-06-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06148 | Received | For Review | 2020-06-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-16 | Submittal Number: 07 42 13.19-5.1 From: BROOKE BURCHAM Final Due Date: 06/16/20 Subject: INSULATED METAL WALL PANELS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH, PREPARED ON SAMPLES OF SIZE INDICATED BELOW. 1. METAL PANELS: 12 INCHES LONG BY ACTUAL PANEL WIDTH. INCLUDE FASTENERS, CLOSURES, AND OTHER METAL PANEL ACCESSORIES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 08316 | Forwarded | For Review | 2020-06-02 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-09 | Submittal Number: 07 42 13.19-5.1 From: BROOKE BURCHAM Final Due Date: 06/16/20 Subject: INSULATED METAL WALL PANELS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH, PREPARED ON SAMPLES OF SIZE INDICATED BELOW. 1. METAL PANELS: 12 INCHES LONG BY ACTUAL PANEL WIDTH. INCLUDE FASTENERS, CLOSURES, AND OTHER METAL PANEL ACCESSORIES. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 08535 | Responded and Closed | Approved | 2020-06-10 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-01 |  | 074213.19-0005-1 Samples for Color Verification.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-01 |  | 074213.19-0005-1 Samples for Color Verification.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-10 |  | 074213.19-0005-1 Samples for Color Verification_POP.pdf
07 42 13.19-011-00 | 07 42 13.19 - INSULATED METAL WALL PANELS | 07 42 13.19-011-00 INSULATED METAL WALL PANELS - Mockups | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Not Required For Review |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-02 | 2021-02-25 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11461 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-02 | Submittal Number: 07 42 13.19-11.0 From: CHRISTIAN GENEROSA Final Due Date: 03/02/21 Subject: INSULATED METAL WALL PANELS - MOCKUPS Description: MOCKUPS : BUILD MOCKUPS TO VERIFY SELECTIONS MADE UNDER SAMPLE SUBMITTALS AND TO DEMONSTRATE AESTHETIC EFFECTS AND SET QUALITY STANDARDS FOR FABRICATION AND INSTALLATION. 1. BUILD MOCKUP OF TYPICAL METAL PANEL ASSEMBLY AS SHOWN ON DRAWINGS, INCLUDING CORNER, SOFFITS, SUPPORTS, ATTACHMENTS, AND ACCESSORIES. 2. WATER-SPRAY TEST: CONDUCT WATER-SPRAY TEST OF METAL PANEL ASSEMBLY MOCKUP, TESTING FOR WATER PENETRATION ACCORDING TO AAMA 501.2. 3. APPROVAL OF MOCKUPS DOES NOT CONSTITUTE APPROVAL OF DEVIATIONS FROM THE CONTRACT DOCUMENTS CONTAINED IN MOCKUPS UNLESS ARCHITECT SPECIFICALLY APPROVES SUCH DEVIATIONS IN WRITING. 4. SUBJECT TO COMPLIANCE WITH REQUIREMENTS, APPROVED MOCKUPS MAY BECOME PART OF THE COMPLETED WORK IF UNDISTURBED AT TIME OF SUBSTANTIAL COMPLETION. THIS SUBMITTAL IS TO RECORD THE DOCUMENTATION OF THE INSULATED METAL PANEL INITIAL INSPECTION AT THE EAST PLENUM ON 12/17/20. PLEASE SEE THE ATTACHED FOR BOTH POPULOUS SITE VISIT REPORT AND MORTENSON'S RESPONSE. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 14846 | Forwarded | For Review | 2021-02-16 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-23 | Submittal Number: 07 42 13.19-11.0 From: CHRISTIAN GENEROSA Final Due Date: 03/02/21 Subject: INSULATED METAL WALL PANELS - MOCKUPS Description: MOCKUPS : BUILD MOCKUPS TO VERIFY SELECTIONS MADE UNDER SAMPLE SUBMITTALS AND TO DEMONSTRATE AESTHETIC EFFECTS AND SET QUALITY STANDARDS FOR FABRICATION AND INSTALLATION. 1. BUILD MOCKUP OF TYPICAL METAL PANEL ASSEMBLY AS SHOWN ON DRAWINGS, INCLUDING CORNER, SOFFITS, SUPPORTS, ATTACHMENTS, AND ACCESSORIES. 2. WATER-SPRAY TEST: CONDUCT WATER-SPRAY TEST OF METAL PANEL ASSEMBLY MOCKUP, TESTING FOR WATER PENETRATION ACCORDING TO AAMA 501.2. 3. APPROVAL OF MOCKUPS DOES NOT CONSTITUTE APPROVAL OF DEVIATIONS FROM THE CONTRACT DOCUMENTS CONTAINED IN MOCKUPS UNLESS ARCHITECT SPECIFICALLY APPROVES SUCH DEVIATIONS IN WRITING. 4. SUBJECT TO COMPLIANCE WITH REQUIREMENTS, APPROVED MOCKUPS MAY BECOME PART OF THE COMPLETED WORK IF UNDISTURBED AT TIME OF SUBSTANTIAL COMPLETION. THIS SUBMITTAL IS TO RECORD THE DOCUMENTATION OF THE INSULATED METAL PANEL INITIAL INSPECTION AT THE EAST PLENUM ON 12/17/20. PLEASE SEE THE ATTACHED FOR BOTH POPULOUS SITE VISIT REPORT AND MORTENSON'S RESPONSE. Spec Section: 07 42 13.19 - INSULATED METAL WALL PANELS Status: OPEN | Info Exchange
| 15008 | Responded and Closed | Rejected | 2021-02-22 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Not an appropriate channel for any open questions. Please submit an RFI for any open questions relating to this scope of work. | Info Exchange
| 15108 | Reopened | Additional Information | 2021-02-25 16:33 | Josh Dobken (Populous) |  |  | Revising submittal disposition from rejected to not reviewed - not required for review.
| 15109 | Responded and Closed | Not Required For Review | 2021-02-25 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Greg Goebel (Mortenson Construction); Christian Generosa |  | Not reviewed - Received for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-16 |  | SiteVisit_20201217_080_Insulated Metal Panel_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-16 |  | SiteVisit_20201217_080_Insulated Metal Panel_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-22 02:00 |  | SiteVisit_20201217_080_Insulated Metal Panel_MAM_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-25 02:00 |  | SiteVisit_20201217_080_Insulated Metal Panel_MAM_POP.pdf
07 42 13-001-00 | 07 42 13.13 - FORMED METAL WALL PANELS | 07 42 13-001-00 Main Concourse Living Wall Metal Panel - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-25 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-08 | 2021-09-01 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14469 | Received | For Review | 2021-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Shaina Burris (Populous) | 2021-09-08 | Submittal Number: 07 42 13-1.0 From: NICK NOWOJ Final Due Date: 08/30/21 Subject: MAIN CONCOURSE LIVING WALL METAL PANEL - SAMPLE Description: SAMPLES OF LIVING WALL PANEL COLOR Spec Section: 07 42 13 - METAL WALL PANELS Status: OPEN | Info Exchange
| 18663 | Forwarded | For Review | 2021-08-25 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-01 | Submittal Number: 07 42 13-1.0 From: NICK NOWOJ Final Due Date: 08/30/21 Subject: MAIN CONCOURSE LIVING WALL METAL PANEL - SAMPLE Description: SAMPLES OF LIVING WALL PANEL COLOR Spec Section: 07 42 13 - METAL WALL PANELS Status: OPEN | Info Exchange
| 18742 | Responded and Closed | Approved | 2021-09-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-25 |  | 07 42 13-1.0 Living Wall Panel - Samples_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-08-25 |  | 07 42 13-1.0 Living Wall Panel - Samples_POP.pdf
07 42 13-002-00 | 07 42 13.13 - FORMED METAL WALL PANELS | 07 42 13-002-00 Living wall interior metal panels shop drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-25 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-08 | 2021-09-08 | 15 |  | Record Copies; Transfers; Submittals | 07 42 13-002-00-01 - 07 42 13-002-00 Living wall interior metal panels shop drawings | 15 |  | 2021-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14470 | Received | For Review | 2021-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Shaina Burris (Populous) | 2021-09-08 | Submittal Number: 07 42 13-2.0 From: NICK NOWOJ Final Due Date: 08/30/21 Subject: LIVING WALL INTERIOR METAL PANELS SHOP DRAWINGS Description: LIVING WALL INTERIOR METAL PANEL SHOP DRAWINGS Spec Section: 07 42 13 - METAL WALL PANELS Status: OPEN | Info Exchange
| 18664 | Forwarded | For Review | 2021-08-25 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-01 | Submittal Number: 07 42 13-2.0 From: NICK NOWOJ Final Due Date: 08/30/21 Subject: LIVING WALL INTERIOR METAL PANELS SHOP DRAWINGS Description: LIVING WALL INTERIOR METAL PANEL SHOP DRAWINGS Spec Section: 07 42 13 - METAL WALL PANELS Status: OPEN | Info Exchange
| 18810 | Responded and Closed | Approved as Noted/Resubmit | 2021-09-08 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-25 |  | 07 42 13-2.0 Living wall interior metal panel shop drawings_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-09-08 |  | 07 42 13-2.0 Living wall interior metal panel shop drawings_POP.pdf
07 42 13-002-00-01 | 07 42 13.13 - FORMED METAL WALL PANELS | 07 42 13-002-00 Living wall interior metal panels shop drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 42 13-002-00 - 07 42 13-002-00 Living wall interior metal panels shop drawings | -1 | 2021-09-22
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-08 |  | 07 42 13-2.0 Living wall interior metal panel shop drawings_POP.pdf
07 46 00-001-00 | 07 46 00 - FIBER CEMENT SIDING | 07 46 00-001-00 FIBER CEMENT (UHPC) SIDING - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-11 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-03-25 | 2020-03-31 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-03-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04757 | Received | For Review | 2020-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-03-25 | Submittal Number: 07 46 00-1.0 From: BROOKE BURCHAM Final Due Date: 04/06/20 Subject: FIBER CEMENT (UHPC) SIDING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 06527 | Forwarded | For Review | 2020-03-11 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-03-18 | Submittal Number: 07 46 00-1.0 From: BROOKE BURCHAM Final Due Date: 04/06/20 Subject: FIBER CEMENT (UHPC) SIDING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 06974 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-31 | Shaina Burris (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-10 |  | 074600-0001-0 Fiber Cement Siding Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-10 |  | 074600-0001-0 Fiber Cement Siding Product Data.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-03-31 |  | 074600-0001-0 Fiber Cement Siding Product Data_POP.pdf
07 46 00-001-01 | 07 46 00 - FIBER CEMENT SIDING | 07 46 00-001-01 FIBER CEMENT (UHPC) SIDING - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-02 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-16 | 2020-04-06 | 5 |  | Record Copies; Transfers; Submittals | 07 46 00-001-01-01 - 07 46 00-001-01 FIBER CEMENT (UHPC) SIDING - Product Data | 5 |  | 2020-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05188 | Received | For Review | 2020-04-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-04-16 | Submittal Number: 07 46 00-1.1 From: BROOKE BURCHAM Final Due Date: 04/16/20 Subject: FIBER CEMENT (UHPC) SIDING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 07051 | Forwarded | For Review | 2020-04-02 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-09 | Submittal Number: 07 46 00-1.1 From: BROOKE BURCHAM Final Due Date: 04/16/20 Subject: FIBER CEMENT (UHPC) SIDING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 07100 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-06 | Shaina Burris (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-02 |  | 074600-0001-1 Fiber Cement Siding Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-02 |  | 074600-0001-1 Fiber Cement Siding Product Data.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-04-06 |  | 074600-0001-1 Fiber Cement Siding Product Data_POP.pdf
07 46 00-001-01-01 | 07 46 00 - FIBER CEMENT SIDING | 07 46 00-001-01 FIBER CEMENT (UHPC) SIDING - Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 46 00-001-01 - 07 46 00-001-01 FIBER CEMENT (UHPC) SIDING - Product Data | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-06 |  | 074600-0001-1 Fiber Cement Siding Product Data_POP.pdf
07 46 00-002-00 | 07 46 00 - FIBER CEMENT SIDING | 07 46 00-002-00 FIBER CEMENT (UHPC) SIDING - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-08 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-22 | 2020-07-06 | 29 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06250 | Received | For Review | 2020-06-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-22 | Submittal Number: 07 46 00-2.0 From: BROOKE BURCHAM Final Due Date: 06/23/20 Subject: FIBER CEMENT (UHPC) SIDING - SAMPLES Description: SAMPLES FOR VERIFICATION : 8-1/2 X 11 ONLY. Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 08435 | Forwarded | For Review | 2020-06-08 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-15 | Submittal Number: 07 46 00-2.0 From: BROOKE BURCHAM Final Due Date: 06/23/20 Subject: FIBER CEMENT (UHPC) SIDING - SAMPLES Description: SAMPLES FOR VERIFICATION : 8-1/2 X 11 ONLY. Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 09090 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-06 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | GRAY 52 IS REJECTED. CLASSIC GRAY REQUIRED AND BEING RESUBMITTED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 074600-0002-0 Fiber Cement Siding - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 074600-0002-0 Fiber Cement Siding - Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-06 |  | 074600-0002-0 Fiber Cement Siding - Samples_POP.pdf
07 46 00-002-01 | 07 46 00 - FIBER CEMENT SIDING | 07 46 00-002-01 FIBER CEMENT (UHPC) SIDING - Samples (Grey) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-19 | 2020-08-20 | 16 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07346 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 07 46 00-2.1 From: BROOKE BURCHAM Final Due Date: 08/18/20 Subject: FIBER CEMENT (UHPC) SIDING - SAMPLES (GREY) Description: SAMPLES FOR VERIFICATION : 8-1/2 X 11 ONLY. Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 09795 | Forwarded | For Review | 2020-08-04 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-11 | Submittal Number: 07 46 00-2.1 From: BROOKE BURCHAM Final Due Date: 08/18/20 Subject: FIBER CEMENT (UHPC) SIDING - SAMPLES (GREY) Description: SAMPLES FOR VERIFICATION : 8-1/2 X 11 ONLY. Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 10181 | Responded and Closed | Approved as Noted | 2020-08-20 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | THIS COLOR IS APPROVE FOR THE NW SNORKEL ONLY. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-04 |  | 074600-0002-1 Fiber Cement Siding - Samples_Grey.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-04 |  | 074600-0002-1 Fiber Cement Siding - Samples_Grey.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-20 |  | 074600-0002-1 Fiber Cement Siding - Samples_Grey_POP.pdf
07 46 00-002-02 | 07 46 00 - FIBER CEMENT SIDING | 07 46 00-002-02 FIBER CEMENT (UHPC) SIDING - Samples (Graphite 40) SE/SW Snorkel | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-09 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-23 | 2020-09-09 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07978 | Received | For Review | 2020-09-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-23 | Submittal Number: 07 46 00-2.2 From: BROOKE BURCHAM Final Due Date: 09/18/20 Subject: FIBER CEMENT (UHPC) SIDING - SAMPLES (GRAPHITE 40) SE/SW SNORKEL Description: SAMPLES FOR VERIFICATION Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 10608 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-15 | Submittal Number: 07 46 00-2.2 From: BROOKE BURCHAM Final Due Date: 09/18/20 Subject: FIBER CEMENT (UHPC) SIDING - SAMPLES (GRAPHITE 40) SE/SW SNORKEL Description: SAMPLES FOR VERIFICATION Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 10639 | Responded and Closed | Approved | 2020-09-09 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-08 |  | 074600-0002-2 Fiber Cement Siding - Samples_Graphite 40.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-08 |  | 074600-0002-2 Fiber Cement Siding - Samples_Graphite 40.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-09 |  | 074600-0002-2 Fiber Cement Siding - Samples_Graphite 40_POP.pdf
07 46 00-010-00 | 07 46 00 - FIBER CEMENT SIDING | 07 46 00-010-00 Fiber Cement Siding - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kristin Long (Populous) |  |  |  | 2020-09-08 07:00 | 2020-09-14 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07717 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-08 07:00 | Submittal Number: 07 46 00-10.0 From: BROOKE BURCHAM Final Due Date: 09/07/20 Subject: FIBER CEMENT SIDING - SHOP DRAWINGS Description: Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 10266 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-31 | Submittal Number: 07 46 00-10.0 From: BROOKE BURCHAM Final Due Date: 09/07/20 Subject: FIBER CEMENT SIDING - SHOP DRAWINGS Description: Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 10268 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Kristin Long (Populous) | 2020-08-31 | Submittal Number: 07 46 00-10.0 From: BROOKE BURCHAM Final Due Date: 09/07/20 Subject: FIBER CEMENT SIDING - SHOP DRAWINGS Description: Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 10438 | Forwarded | For Review | 2020-08-31 | Todd Spangler (Populous) | Kristin Long (Populous) |  | Submittal Number: 07 46 00-10.0 From: BROOKE BURCHAM Final Due Date: 09/07/20 Subject: FIBER CEMENT SIDING - SHOP DRAWINGS Description: Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 10732 | Responded and Closed | Revise and Resubmit | 2020-09-14 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 074600-0010-0 Fiber Cement Siding - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 074600-0010-0 Fiber Cement Siding - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 074600-0010-0 Fiber Cement Siding - Shop Drawings.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-08-24 |  | 074600-0010-0 Fiber Cement Siding - Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-14 |  | 074600-0010-0 Fiber Cement Siding - Shop Drawings_POP.pdf
07 46 00-010-01 | 07 46 00 - FIBER CEMENT SIDING | 07 46 00-010-01 Fiber Cement Siding - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-04 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-18 | 2020-12-15 | 12 |  | Record Copies; Transfers; Submittals | 07 46 00-010-01-01 - 07 46 00-010-01 Fiber Cement Siding - Shop Drawings | 12 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09907 | Received | For Review | 2020-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2020-12-18 | Submittal Number: 07 46 00-10.1 From: CHRISTIAN GENEROSA Final Due Date: 12/18/20 Subject: FIBER CEMENT SIDING - SHOP DRAWINGS Description: Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 12987 | Forwarded | For Review | 2020-12-04 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-11 | Submittal Number: 07 46 00-10.1 From: CHRISTIAN GENEROSA Final Due Date: 12/18/20 Subject: FIBER CEMENT SIDING - SHOP DRAWINGS Description: Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 13320 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-03 |  | 2020-12-2 SCA20_TAKTL Panel Layout Drawings_MAM Markup.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-03 |  | 2020-12-2 SCA20_TAKTL Panel Layout Drawings_MAM Markup.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-15 |  | 07 46 00-010-01_TAKTL Panel Layout Drawings_MAM_POP.pdf
07 46 00-010-01-01 | 07 46 00 - FIBER CEMENT SIDING | 07 46 00-010-01 Fiber Cement Siding - Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 46 00-010-01 - 07 46 00-010-01 Fiber Cement Siding - Shop Drawings | -1 | 2020-12-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-15 |  | 07 46 00-010-01_TAKTL Panel Layout Drawings_MAM_POP.pdf
07 46 00-011-00 | 07 46 00 - FIBER CEMENT SIDING | 07 46 00-011-00 Fiber Cement (UHPC) Siding - Samples (Ticket Office - Color TBD) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-03 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-17 | 2021-02-16 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-02-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11171 | Received | For Review | 2021-02-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-02-17 | Submittal Number: 07 46 00-11.0 From: CHRISTIAN GENEROSA Final Due Date: 02/17/21 Subject: FIBER CEMENT (UHPC) SIDING - SAMPLES (TICKET OFFICE - COLOR TBD) Description: SAMPLES FOR VERIFICATION Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 14478 | Forwarded | For Review | 2021-02-03 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-10 | Submittal Number: 07 46 00-11.0 From: CHRISTIAN GENEROSA Final Due Date: 02/17/21 Subject: FIBER CEMENT (UHPC) SIDING - SAMPLES (TICKET OFFICE - COLOR TBD) Description: SAMPLES FOR VERIFICATION Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 14844 | Responded and Closed | Approved | 2021-02-16 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-03 |  | 2021-02-03 074600-0011-00 Fiber Cement (UHPC) Siding - Sample (Ticket Office)_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-03 |  | 2021-02-03 074600-0011-00 Fiber Cement (UHPC) Siding - Sample (Ticket Office)_MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-09 |  | 07 46 00-011-00 Fiber Cement (UHPC) Siding - Sample (Ticket Office)_MAM_POP.pdf
07 46 00-012-00 | 07 46 00 - FIBER CEMENT SIDING | 07 46 00-012-00 Fiber Cement Siding (UHPC) - Ticket Office Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-18 | 2021-02-16 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-02-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11188 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-02-18 | Submittal Number: 07 46 00-12.0 From: CHRISTIAN GENEROSA Final Due Date: 02/18/21 Subject: FIBER CEMENT SIDING (UHPC) - TICKET OFFICE SHOP DRAWINGS Description: THESE SHOP DRAWINGS REFLECT THE ADDED TICKET OFFICE SCOPE. Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 14494 | Forwarded | For Review | 2021-02-04 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-11 | Submittal Number: 07 46 00-12.0 From: CHRISTIAN GENEROSA Final Due Date: 02/18/21 Subject: FIBER CEMENT SIDING (UHPC) - TICKET OFFICE SHOP DRAWINGS Description: THESE SHOP DRAWINGS REFLECT THE ADDED TICKET OFFICE SCOPE. Spec Section: 07 46 00 - FIBER CEMENT (UHPC) SIDING Status: OPEN | Info Exchange
| 14623 | Responded and Closed | Approved | 2021-02-09 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| 14843 | Reopened | Additional Information | 2021-02-16 11:28 | Todd Spangler (Populous)
| 14845 | Responded and Closed | Approved as Noted | 2021-02-16 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-03 |  | 2021-02-03 074600-0012-00 Fiber Cement Siding (UHPC) - Ticket Office Shop Drawings_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-03 |  | 2021-02-03 074600-0012-00 Fiber Cement Siding (UHPC) - Ticket Office Shop Drawings_MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-09 |  | 07 46 00-011-00 Fiber Cement (UHPC) Siding - Sample (Ticket Office)_MAM_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-16 |  | 07 46 00-012 Fiber Cement Siding - Ticket Office_MAM_POP.pdf
07 54 19-001-00 | 07 54 19 - POLYVINYL-CHLORIDE (PVC) ROOFING | 07 54 19-001-00 POLYVINYL-CHLORIDE (PVC) ROOFING - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-09 | 2020-10-13 | 19 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08330 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-09 | Submittal Number: 07 54 19-1.0 From: BROOKE BURCHAM Final Due Date: 10/09/20 Subject: POLYVINYL-CHLORIDE (PVC) ROOFING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 07 54 19 - POLYVINYL-CHLORIDE ROOFING Status: OPEN | Info Exchange
| 11038 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-01 | Submittal Number: 07 54 19-1.0 From: BROOKE BURCHAM Final Due Date: 10/09/20 Subject: POLYVINYL-CHLORIDE (PVC) ROOFING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 07 54 19 - POLYVINYL-CHLORIDE ROOFING Status: OPEN | Info Exchange
| 11583 | Responded and Closed | Approved as Noted | 2020-10-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. Provide 5/8" Densdeck board, submit Sarnaclad sheet metal for 07 62 00 as required. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 075419-0001-0 PVC Roofing Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 075419-0001-0 PVC Roofing Product Data.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-13 02:00 |  | 075419-0001-0 PVC Roofing Product Data_pop.pdf
07 54 19-003-00 | 07 54 19 - POLYVINYL-CHLORIDE (PVC) ROOFING | 07 54 19-003-00 POLYVINYL-CHLORIDE (PVC) ROOFING - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-29 08:00 | 2021-01-29 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-01-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10699 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2021-01-29 08:00 | Submittal Number: 07 54 19-3.0 From: BROOKE BURCHAM Final Due Date: 01/28/21 Subject: POLYVINYL-CHLORIDE (PVC) ROOFING - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR ROOFING SYSTEM. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK, INCLUDING: 1. BASE FLASHINGS AND MEMBRANE TERMINATIONS. 2. TAPERED INSULATION, INCLUDING SLOPES. 3. ROOF PLAN SHOWING ORIENTATION OF STEEL ROOF DECK AND ORIENTATION OF ROOFING, FASTENING SPACINGS, AND PATTERNS FOR MECHANICALLY FASTENED ROOFING. 4. INSULATION FASTENING PATTERNS FOR CORNER, PERIMETER, AND FIELD-OF-ROOF LOCATIONS. Spec Section: 07 54 19 - POLYVINYL-CHLORIDE ROOFING Status: OPEN | Info Exchange
| 13920 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-21 | Submittal Number: 07 54 19-3.0 From: BROOKE BURCHAM Final Due Date: 01/28/21 Subject: POLYVINYL-CHLORIDE (PVC) ROOFING - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR ROOFING SYSTEM. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK, INCLUDING: 1. BASE FLASHINGS AND MEMBRANE TERMINATIONS. 2. TAPERED INSULATION, INCLUDING SLOPES. 3. ROOF PLAN SHOWING ORIENTATION OF STEEL ROOF DECK AND ORIENTATION OF ROOFING, FASTENING SPACINGS, AND PATTERNS FOR MECHANICALLY FASTENED ROOFING. 4. INSULATION FASTENING PATTERNS FOR CORNER, PERIMETER, AND FIELD-OF-ROOF LOCATIONS. Spec Section: 07 54 19 - POLYVINYL-CHLORIDE ROOFING Status: OPEN | Info Exchange
| 14355 | Responded and Closed | Approved as Noted | 2021-01-29 | Shaina Burris (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 075419-0003-0 PVC Roofing Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 075419-0003-0 PVC Roofing Shop Drawings.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 075419-0003-0 PVC Roofing Shop Drawings.pdf
07 56 00-001-00 | 07 56 00 | 07 56 00-001-00 FLUID APPLIED ROOFING RECOVER - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Sent and Closed - For Construction |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 |  | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12488 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-22 | Submittal Number: 07 56 00-1.0 From: ROSHAN ALEX Final Due Date: 04/21/21 Subject: FLUID APPLIED ROOFING RECOVER - PRODUCT DATA Description: PRODUCT DATA SUBMITTAL FOR ROOFING RECOVER SYSTEM ON EXISTING ROOF. Spec Section: 07 56 00 - FLUID-APPLIED ROOFING Status: OPEN | Info Exchange
| 16178 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 07 56 00-1.0 From: ROSHAN ALEX Final Due Date: 04/21/21 Subject: FLUID APPLIED ROOFING RECOVER - PRODUCT DATA Description: PRODUCT DATA SUBMITTAL FOR ROOFING RECOVER SYSTEM ON EXISTING ROOF. Spec Section: 07 56 00 - FLUID-APPLIED ROOFING Status: OPEN | Info Exchange
| 12571 | Review Response | Approved as Noted | 2021-04-13 | Tom Usher (Populous) | Populous SCA_CCA |  | submittal comments are on cover page | Info Exchange
| 16286 | Sent and Closed | For Construction | 2021-04-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  | Response (Approved as Noted) from: Tom Usher (Populous) Remarks: submittal comments are on cover page | Info Exchange
| 16589 | Sent | For Information Only | 2021-04-27 | Populous SCA_CCA | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  | Sent and Closed: AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com Remarks: Response (Approved as Noted) from: Tom Usher (Populous) Remarks: submittal comments are on cover page | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 07 56 00-1-0 Fluid Applied Roofing Recover PD_Mort.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 07 56 00-1-0 Fluid Applied Roofing Recover PD_Mort.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2021-04-13 |  | 07 56 00-1-0 Fluid Applied Roofing Recover PD_Mort_POP.pdf
| Sent and Closed |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 07 56 00-1-0 Fluid Applied Roofing Recover PD_Mort.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-04-07 02:00 |  | 07 56 00-1-0 Fluid Applied Roofing Recover PD_Mort.pdf
07 56 00-002-00 | 07 56 00 | 07 56 00-002-00 FLUID APPLIED ROOFING RECOVER - Shop Drawings (Main Roof) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-06-02 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-06-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13140 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-02 07:00 | Submittal Number: 07 56 00-2.0 From: ROSHAN ALEX Final Due Date: 05/25/21 Subject: FLUID APPLIED ROOFING RECOVER - SHOP DRAWINGS (MAIN ROOF) Description: Spec Section: 07 56 00 - FLUID-APPLIED ROOFING Status: OPEN | Info Exchange
| 17000 | Forwarded | For Review | 2021-05-18 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-25 | Submittal Number: 07 56 00-2.0 From: ROSHAN ALEX Final Due Date: 05/25/21 Subject: FLUID APPLIED ROOFING RECOVER - SHOP DRAWINGS (MAIN ROOF) Description: Spec Section: 07 56 00 - FLUID-APPLIED ROOFING Status: OPEN | Info Exchange
| 17282 | Responded and Closed | Approved as Noted | 2021-06-02 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | 07 56 00-2-0 Fluid Applied Roofing Recover SD_Mort.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-17 |  | 07 56 00-2-0 Fluid Applied Roofing Recover SD_Mort.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-01 |  | 07 56 00-2-0 Fluid Applied Roofing Recover SD_Mort_POP.pdf
07 62 00-003-00 | 07 62 00 - SHEET METAL FLASHING AND TRIM | 07 62 00-003-00 SHEET METAL FLASHING AND TRIM - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-14 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kristin Long (Populous) |  |  |  | 2020-09-28 | 2020-10-01 | 18 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-10-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08060 | Received | For Review | 2020-09-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-28 | Submittal Number: 07 62 00-3.0 From: BROOKE BURCHAM Final Due Date: 09/25/20 Subject: SHEET METAL FLASHING AND TRIM - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR SHEET METAL FLASHING AND TRIM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 2. DETAIL FABRICATION AND INSTALLATION LAYOUTS, EXPANSION-JOINT LOCATIONS, AND KEYED DETAILS. DISTINGUISH BETWEEN SHOP- AND FIELD-ASSEMBLED WORK. 3. INCLUDE IDENTIFICATION OF MATERIAL, THICKNESS, WEIGHT, AND FINISH FOR EACH ITEM AND LOCATION IN PROJECT. 4. INCLUDE DETAILS FOR FORMING, INCLUDING PROFILES, SHAPES, SEAMS, AND DIMENSIONS. 5. INCLUDE DETAILS FOR JOINING, SUPPORTING, AND SECURING, INCLUDING LAYOUT AND SPACING OF FASTENERS, CLEATS, CLIPS, AND OTHER ATTACHMENTS. INCLUDE PATTERN OF SEAMS. 6. INCLUDE DETAILS OF TERMINATION POINTS AND ASSEMBLIES. 7. INCLUDE DETAILS OF EXPANSION JOINTS AND EXPANSION-JOINT COVERS, INCLUDING SHOWING DIRECTION OF EXPANSION AND CONTRACTION FROM FIXED POINTS. 8. INCLUDE DETAILS OF ROOF-PENETRATION FLASHING. 9. INCLUDE DETAILS OF EDGE CONDITIONS, INCLUDING EAVES, RIDGES, VALLEYS, RAKES, CRICKETS, AND COUNTERFLASHINGS AS APPLICABLE. 10. INCLUDE DETAILS OF SPECIAL CONDITIONS. 11. INCLUDE DETAILS OF CONNECTIONS TO ADJOINING WORK. 12. DETAIL FORMED FLASHING AND TRIM AT SCALE OF NOT LESS THAN 3 INCHES PER 12 INCHES. Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 10724 | Forwarded | For Review | 2020-09-11 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-18 | Submittal Number: 07 62 00-3.0 From: BROOKE BURCHAM Final Due Date: 09/25/20 Subject: SHEET METAL FLASHING AND TRIM - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR SHEET METAL FLASHING AND TRIM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 2. DETAIL FABRICATION AND INSTALLATION LAYOUTS, EXPANSION-JOINT LOCATIONS, AND KEYED DETAILS. DISTINGUISH BETWEEN SHOP- AND FIELD-ASSEMBLED WORK. 3. INCLUDE IDENTIFICATION OF MATERIAL, THICKNESS, WEIGHT, AND FINISH FOR EACH ITEM AND LOCATION IN PROJECT. 4. INCLUDE DETAILS FOR FORMING, INCLUDING PROFILES, SHAPES, SEAMS, AND DIMENSIONS. 5. INCLUDE DETAILS FOR JOINING, SUPPORTING, AND SECURING, INCLUDING LAYOUT AND SPACING OF FASTENERS, CLEATS, CLIPS, AND OTHER ATTACHMENTS. INCLUDE PATTERN OF SEAMS. 6. INCLUDE DETAILS OF TERMINATION POINTS AND ASSEMBLIES. 7. INCLUDE DETAILS OF EXPANSION JOINTS AND EXPANSION-JOINT COVERS, INCLUDING SHOWING DIRECTION OF EXPANSION AND CONTRACTION FROM FIXED POINTS. 8. INCLUDE DETAILS OF ROOF-PENETRATION FLASHING. 9. INCLUDE DETAILS OF EDGE CONDITIONS, INCLUDING EAVES, RIDGES, VALLEYS, RAKES, CRICKETS, AND COUNTERFLASHINGS AS APPLICABLE. 10. INCLUDE DETAILS OF SPECIAL CONDITIONS. 11. INCLUDE DETAILS OF CONNECTIONS TO ADJOINING WORK. 12. DETAIL FORMED FLASHING AND TRIM AT SCALE OF NOT LESS THAN 3 INCHES PER 12 INCHES. Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 10736 | Forwarded | For Review | 2020-09-14 | Todd Spangler (Populous) | Kristin Long (Populous) |  | Submittal Number: 07 62 00-3.0 From: BROOKE BURCHAM Final Due Date: 09/25/20 Subject: SHEET METAL FLASHING AND TRIM - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR SHEET METAL FLASHING AND TRIM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 2. DETAIL FABRICATION AND INSTALLATION LAYOUTS, EXPANSION-JOINT LOCATIONS, AND KEYED DETAILS. DISTINGUISH BETWEEN SHOP- AND FIELD-ASSEMBLED WORK. 3. INCLUDE IDENTIFICATION OF MATERIAL, THICKNESS, WEIGHT, AND FINISH FOR EACH ITEM AND LOCATION IN PROJECT. 4. INCLUDE DETAILS FOR FORMING, INCLUDING PROFILES, SHAPES, SEAMS, AND DIMENSIONS. 5. INCLUDE DETAILS FOR JOINING, SUPPORTING, AND SECURING, INCLUDING LAYOUT AND SPACING OF FASTENERS, CLEATS, CLIPS, AND OTHER ATTACHMENTS. INCLUDE PATTERN OF SEAMS. 6. INCLUDE DETAILS OF TERMINATION POINTS AND ASSEMBLIES. 7. INCLUDE DETAILS OF EXPANSION JOINTS AND EXPANSION-JOINT COVERS, INCLUDING SHOWING DIRECTION OF EXPANSION AND CONTRACTION FROM FIXED POINTS. 8. INCLUDE DETAILS OF ROOF-PENETRATION FLASHING. 9. INCLUDE DETAILS OF EDGE CONDITIONS, INCLUDING EAVES, RIDGES, VALLEYS, RAKES, CRICKETS, AND COUNTERFLASHINGS AS APPLICABLE. 10. INCLUDE DETAILS OF SPECIAL CONDITIONS. 11. INCLUDE DETAILS OF CONNECTIONS TO ADJOINING WORK. 12. DETAIL FORMED FLASHING AND TRIM AT SCALE OF NOT LESS THAN 3 INCHES PER 12 INCHES. Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 11224 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-01 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-11 |  | 076200-0003-0 Sheet Metal - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-11 |  | 076200-0003-0 Sheet Metal - Shop Drawings.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-09-11 |  | 076200-0003-0 Sheet Metal - Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-01 |  | 076200-0003-0 Sheet Metal - Shop Drawings_POP.pdf
07 62 00-003-01 | 07 62 00 - SHEET METAL FLASHING AND TRIM | 07 62 00-003-01 SHEET METAL FLASHING AND TRIM - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-17 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-11 | 2020-12-18 | 2 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-12-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10207 | Received | For Review | 2020-12-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-01-11 | Submittal Number: 07 62 00-3.1 From: CHRISTIAN GENEROSA Final Due Date: 12/28/20 Subject: SHEET METAL FLASHING AND TRIM - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR SHEET METAL FLASHING AND TRIM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 2. DETAIL FABRICATION AND INSTALLATION LAYOUTS, EXPANSION-JOINT LOCATIONS, AND KEYED DETAILS. DISTINGUISH BETWEEN SHOP- AND FIELD-ASSEMBLED WORK. 3. INCLUDE IDENTIFICATION OF MATERIAL, THICKNESS, WEIGHT, AND FINISH FOR EACH ITEM AND LOCATION IN PROJECT. 4. INCLUDE DETAILS FOR FORMING, INCLUDING PROFILES, SHAPES, SEAMS, AND DIMENSIONS. 5. INCLUDE DETAILS FOR JOINING, SUPPORTING, AND SECURING, INCLUDING LAYOUT AND SPACING OF FASTENERS, CLEATS, CLIPS, AND OTHER ATTACHMENTS. INCLUDE PATTERN OF SEAMS. 6. INCLUDE DETAILS OF TERMINATION POINTS AND ASSEMBLIES. 7. INCLUDE DETAILS OF EXPANSION JOINTS AND EXPANSION-JOINT COVERS, INCLUDING SHOWING DIRECTION OF EXPANSION AND CONTRACTION FROM FIXED POINTS. 8. INCLUDE DETAILS OF ROOF-PENETRATION FLASHING. 9. INCLUDE DETAILS OF EDGE CONDITIONS, INCLUDING EAVES, RIDGES, VALLEYS, RAKES, CRICKETS, AND COUNTERFLASHINGS AS APPLICABLE. 10. INCLUDE DETAILS OF SPECIAL CONDITIONS. 11. INCLUDE DETAILS OF CONNECTIONS TO ADJOINING WORK. 12. DETAIL FORMED FLASHING AND TRIM AT SCALE OF NOT LESS THAN 3 INCHES PER 12 INCHES. Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 13348 | Forwarded | For Review | 2020-12-16 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-23 | Submittal Number: 07 62 00-3.1 From: CHRISTIAN GENEROSA Final Due Date: 12/28/20 Subject: SHEET METAL FLASHING AND TRIM - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR SHEET METAL FLASHING AND TRIM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 2. DETAIL FABRICATION AND INSTALLATION LAYOUTS, EXPANSION-JOINT LOCATIONS, AND KEYED DETAILS. DISTINGUISH BETWEEN SHOP- AND FIELD-ASSEMBLED WORK. 3. INCLUDE IDENTIFICATION OF MATERIAL, THICKNESS, WEIGHT, AND FINISH FOR EACH ITEM AND LOCATION IN PROJECT. 4. INCLUDE DETAILS FOR FORMING, INCLUDING PROFILES, SHAPES, SEAMS, AND DIMENSIONS. 5. INCLUDE DETAILS FOR JOINING, SUPPORTING, AND SECURING, INCLUDING LAYOUT AND SPACING OF FASTENERS, CLEATS, CLIPS, AND OTHER ATTACHMENTS. INCLUDE PATTERN OF SEAMS. 6. INCLUDE DETAILS OF TERMINATION POINTS AND ASSEMBLIES. 7. INCLUDE DETAILS OF EXPANSION JOINTS AND EXPANSION-JOINT COVERS, INCLUDING SHOWING DIRECTION OF EXPANSION AND CONTRACTION FROM FIXED POINTS. 8. INCLUDE DETAILS OF ROOF-PENETRATION FLASHING. 9. INCLUDE DETAILS OF EDGE CONDITIONS, INCLUDING EAVES, RIDGES, VALLEYS, RAKES, CRICKETS, AND COUNTERFLASHINGS AS APPLICABLE. 10. INCLUDE DETAILS OF SPECIAL CONDITIONS. 11. INCLUDE DETAILS OF CONNECTIONS TO ADJOINING WORK. 12. DETAIL FORMED FLASHING AND TRIM AT SCALE OF NOT LESS THAN 3 INCHES PER 12 INCHES. Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 13383 | Responded and Closed | Approved as Noted | 2020-12-18 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-16 |  | 07 62 00-003-01 MISC METALS SHOP DRAWINGS R1_MAMmarkup.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-16 |  | 07 62 00-003-01 MISC METALS SHOP DRAWINGS R1_MAMmarkup.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-18 |  | 07 62 00-003-01 MISC METALS SHOP DRAWINGS R1_MAM_POP.pdf
07 62 00-004-00 | 07 62 00 - SHEET METAL FLASHING AND TRIM | 07 62 00-004-00 SHEET METAL FLASHING AND TRIM - Samples (EP1, EP2, EP3) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-11 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-05 | 2021-01-14 | 35 |  | Record Copies; Transfers; Submittals |  | 35 |  | 2021-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10099 | Received | For Review | 2020-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-05 | Submittal Number: 07 62 00-4.0 From: BROOKE BURCHAM Final Due Date: 12/25/20 Subject: SHEET METAL FLASHING AND TRIM - SAMPLES (EP1, EP2, EP3) Description: SAMPLES FOR INITIAL SELECTION : FOR EACH TYPE OF SHEET METAL AND ACCESSORY INDICATED WITH FACTORY- APPLIED FINISHES. Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 13201 | Forwarded | For Review | 2020-12-11 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-18 | Submittal Number: 07 62 00-4.0 From: BROOKE BURCHAM Final Due Date: 12/25/20 Subject: SHEET METAL FLASHING AND TRIM - SAMPLES (EP1, EP2, EP3) Description: SAMPLES FOR INITIAL SELECTION : FOR EACH TYPE OF SHEET METAL AND ACCESSORY INDICATED WITH FACTORY- APPLIED FINISHES. Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 13928 | Responded and Closed | Approved | 2021-01-14 | Populous SCA_CCA | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-10 |  | 076200-0004 Sheet Metal Flashing and Trim Samples (inital).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-10 |  | 076200-0004 Sheet Metal Flashing and Trim Samples (inital).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-14 |  | 076200-0004 Sheet Metal Flashing and Trim Samples (inital)_POP.pdf
07 62 00-012-00 | 07 62 00 - SHEET METAL FLASHING AND TRIM | 07 62 00-012-00 Sheet Metal Flashing and Trim - Atrium Coping Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-03-01 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11419 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2021-03-01 | Submittal Number: 07 62 00-12.0 From: BROOKE BURCHAM Final Due Date: 03/01/21 Subject: SHEET METAL FLASHING AND TRIM - ATRIUM COPING PRODUCT DATA Description: PRODUCT DATA FOR COPING AT THE PVC ROOFING. INCLUDES ALUMINUM PRODUCT DATA, FASTENERS, WRB PRODUCT DATA, MINERAL WOOL, AEP COLOR CHART. Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 14786 | Forwarded | For Review | 2021-02-15 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 07 62 00-12.0 From: BROOKE BURCHAM Final Due Date: 03/01/21 Subject: SHEET METAL FLASHING AND TRIM - ATRIUM COPING PRODUCT DATA Description: PRODUCT DATA FOR COPING AT THE PVC ROOFING. INCLUDES ALUMINUM PRODUCT DATA, FASTENERS, WRB PRODUCT DATA, MINERAL WOOL, AEP COLOR CHART. Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 15162 | Responded and Closed | Approved as Noted | 2021-03-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 076200-0012-0 Atrium Roof Coping Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-15 |  | 076200-0012-0 Atrium Roof Coping Product Data.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-03-01 |  | 07 62 00-0012-0 Atrium Roof Coping Product Data_POP.pdf
07 62 00-013-00 | 07 62 00 - SHEET METAL FLASHING AND TRIM | 07 62 00-013-00 Sheet Metal Flashing and Trim - Atrium Coping and Ticket Office Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-06 | 2 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12361 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 07 62 00-13.0 From: BROOKE BURCHAM Final Due Date: 04/15/21 Subject: SHEET METAL FLASHING AND TRIM - ATRIUM COPING AND TICKET OFFICE PRODUCT DATA Description: Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 16017 | Forwarded | For Review | 2021-04-01 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 07 62 00-13.0 From: BROOKE BURCHAM Final Due Date: 04/15/21 Subject: SHEET METAL FLASHING AND TRIM - ATRIUM COPING AND TICKET OFFICE PRODUCT DATA Description: Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 16099 | Responded and Closed | Approved as Noted | 2021-04-06 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 076200-0013-0 Atrium and Ticket Office Roof Coping Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 076200-0013-0 Atrium and Ticket Office Roof Coping Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 07 62 00-0013-0 Atrium and Ticket Office Roof Coping Shop Drawings_POP.pdf
07 62 00-014-00 | 07 62 00 - SHEET METAL FLASHING AND TRIM | 07 62 00-014-00 Sheet Metal Flashing and Trim - Color Samples (EP4-EP8) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-04 | 2021-05-12 | 23 |  | Record Copies; Transfers; Submittals | 07 62 00-014-00-01 - 07 62 00-014-00 Sheet Metal Flashing and Trim - Color Samples (EP4-EP8) | 23 |  | 2021-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12660 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Generosa | 2021-05-04 | Submittal Number: 07 62 00-14.0 From: CHRISTIAN GENEROSA Final Due Date: 05/04/21 Subject: SHEET METAL FLASHING AND TRIM - COLOR SAMPLES (EP4-EP8) Description: PAINT SAMPLES FOR VERIFICATION (EP4-EP8) Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 16381 | Forwarded | For Review | 2021-04-20 | Christian Generosa | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 07 62 00-14.0 From: CHRISTIAN GENEROSA Final Due Date: 05/04/21 Subject: SHEET METAL FLASHING AND TRIM - COLOR SAMPLES (EP4-EP8) Description: PAINT SAMPLES FOR VERIFICATION (EP4-EP8) Spec Section: 07 62 00 - SHEET METAL FLASHING AND TRIM Status: OPEN | Info Exchange
| 16923 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-12 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Refer to attached report for further context. Match EP4 and EP6 to previously approved samples. Resubmit EP5 and EP8. EP7 Approved. Confirm existing fascia conditions prior to application of any paint at new fascia, typ. New fascia to match existing fascia. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-19 |  | 2021-04-19 076200-14-00 Sheet Metal Flashing and Trim - Samples (EP4-EP8)_MAM.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-19 |  | 2021-04-19 076200-14-00 Sheet Metal Flashing and Trim - Samples (EP4-EP8)_MAM(1).pdf
| Forwarded |  | Christian Generosa | 1 | 2021-04-19 |  | 2021-04-19 076200-14-00 Sheet Metal Flashing and Trim - Samples (EP4-EP8)_MAM.pdf
| Forwarded |  | Christian Generosa | 1 | 2021-04-19 |  | 2021-04-19 076200-14-00 Sheet Metal Flashing and Trim - Samples (EP4-EP8)_MAM(1).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-12 02:00 |  | 07 62 00-014-00 Sheet Metal Flashing and Trim - Samples (EP4-EP8)_MAM_POP.pdf
07 62 00-014-00-01 | 07 62 00 - SHEET METAL FLASHING AND TRIM | 07 62 00-014-00 Sheet Metal Flashing and Trim - Color Samples (EP4-EP8) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 62 00-014-00 - 07 62 00-014-00 Sheet Metal Flashing and Trim - Color Samples (EP4-EP8) | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-12 02:00 |  | 07 62 00-014-00 Sheet Metal Flashing and Trim - Samples (EP4-EP8)_MAM_POP.pdf
07 72 53-001-00 | 07 72 53 - SNOW GUARDS | 07 72 53-001-00 Metal Roof Snowguards Product Data (For Standing Seam Metal Roof) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-12 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-26 | 2021-03-01 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11382 | Received | For Review | 2021-02-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-26 | Submittal Number: 07 72 53-1.0 From: CHRISTIAN GENEROSA Final Due Date: 02/26/21 Subject: METAL ROOF SNOWGUARDS PRODUCT DATA (FOR STANDING SEAM METAL ROOF) Description: PRODUCT DATA: INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR SNOW GUARDS. Spec Section: 07 72 53 - SNOW GUARDS Status: OPEN | Info Exchange
| 14734 | Forwarded | For Review | 2021-02-12 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-19 | Submittal Number: 07 72 53-1.0 From: CHRISTIAN GENEROSA Final Due Date: 02/26/21 Subject: METAL ROOF SNOWGUARDS PRODUCT DATA (FOR STANDING SEAM METAL ROOF) Description: PRODUCT DATA: INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR SNOW GUARDS. Spec Section: 07 72 53 - SNOW GUARDS Status: OPEN | Info Exchange
| 15137 | Responded and Closed | Approved as Noted | 2021-03-01 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-11 |  | 2021-02-11 077253-0001-00 Snowguards PD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-11 |  | 2021-02-11 077253-0001-00 Snowguards PD_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-01 |  | 07 72 53-0001-00 Snowguards PD_MAM_POP.pdf
07 81 00-001-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-001-00 APPLIED FIREPROOFING - Cafco 300 Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-06 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-20 | 2019-09-25 | 20 |  | Record Copies; Transfers; Submittals | 07 81 00-001-00-01 - 07 81 00-001-00 APPLIED FIREPROOFING - Cafco 300 Submittal | 20 |  | 2019-09-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02326 | Received | For Review | 2019-09-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2019-09-20 | Submittal Number: 07 81 00-1.0 From: RYAN CROOKSTON Final Due Date: 09/20/19 Subject: APPLIED FIREPROOFING - CAFCO 300 SUBMITTAL Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03559 | Forwarded | For Review | 2019-09-06 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-09-13 | Submittal Number: 07 81 00-1.0 From: RYAN CROOKSTON Final Due Date: 09/20/19 Subject: APPLIED FIREPROOFING - CAFCO 300 SUBMITTAL Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 02521 | Review Response | Approved as Noted/Resubmit | 2019-09-25 | Tom Usher (Populous) | Shaina Burris (Populous) |  |  | Info Exchange
| 03801 | Responded and Closed | Approved as Noted/Resubmit | 2019-09-25 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Product Data approved. This submittal is missing many items: 1.4 - ACTION SUBMITTALS B.Sustainable Design Submittals: 1.Product Data: For paints and coatings, indicating VOC content. 2.Laboratory Test Reports: For paints and coatings, indicating compliance with requirements for low-emitting materials. 1.5 - INFORMATIONAL SUBMITTALS A.Qualification Data: For Installer. B.Product Certificates: For each type of fireproofing. C.Evaluation Reports: For fireproofing, from ICC-ES. D.Preconstruction Test Reports: For fireproofing. Last but not least being: 1.4 - ACTION SUBMITTALS: C.Shop Drawings: Framing plans or schedules, or both, indicating the following: 1.Extent of fireproofing for each construction and fire-resistance rating. 2.Applicable fire-resistance design designations of a qualified testing and inspecting agency acceptable to authorities having jurisdiction. 3.Minimum fireproofing thicknesses needed to achieve required fire-resistance rating of each structural component and assembly. 4.Treatment of fireproofing after application. Please be mindful of language in 01 33 00 -Submittal Requirements, 1.5F: Incomplete submittals, defined as lacking required information, such as Product Data, Samples, identified options or deviations, will be cause for extended review time and rejection. Shop drawings can understandably be submitted separately from other outstanding submittals. | Info Exchange
| 03950 | Sent | For Information Only | 2019-10-02 | Josh Dobken (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Product Data approved. This submittal is missing many items: 1.4 - ACTION SUBMITTALS B.Sustainable Design Submittals: 1.Product Data: For paints and coatings, indicating VOC content. 2.Laboratory Test Reports: For paints and coatings, indicating compliance with requirements for low-emitting materials. 1.5 - INFORMATIONAL SUBMITTALS A.Qualification Data: For Installer. B.Product Certificates: For each type of fireproofing. C.Evaluation Reports: For fireproofing, from ICC-ES. D.Preconstruction Test Reports: For fireproofing. Last but not least being: 1.4 - ACTION SUBMITTALS: C.Shop Drawings: Framing plans or schedules, or both, indicating the following: 1.Extent of fireproofing for each construction and fire-resistance rating. 2.Applicable fire-resistance design designations of a qualified testing and inspecting agency acceptable to authorities having jurisdiction. 3.Minimum fireproofing thicknesses needed to achieve required fire-resistance rating of each structural component and assembly. 4.Treatment of fireproofing after application. Please be mindful of language in 01 33 00 -Submittal Requirements, 1.5F: Incomplete submittals, defined as lacking required information, such as Product Data, Samples, identified options or deviations, will be cause for extended review time and rejection. Shop drawings can understandably be submitted separately from other outstanding submittals. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-06 |  | 07 81 00-1.0 Cafco 300 Submittal (MAM review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-06 |  | 07 81 00-1.0 Cafco 300 Submittal (MAM review).pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2019-09-24 |  | 078100-PD-001.0 SFRM for Dry Interior Concealed Surfaces_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2019-09-06 |  | 07 81 00-1.0 Cafco 300 Submittal (MAM review).pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2019-09-05 02:00 |  | 07 81 00-1.0 Cafco 300 Submittal (MAM review).pdf
07 81 00-001-00-01 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-001-00 APPLIED FIREPROOFING - Cafco 300 Submittal | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 81 00-001-00 - 07 81 00-001-00 APPLIED FIREPROOFING - Cafco 300 Submittal | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-06 |  | 07 81 00-1.0 Cafco 300 Submittal (MAM review).pdf
07 81 00-002-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-002-00 APPLIED FIREPROOFING - Cafco MII Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-09 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-23 | 2019-09-25 | 17 |  | Record Copies; Transfers; Submittals | 07 81 00-002-00-01 - 07 81 00-002-00 APPLIED FIREPROOFING - Cafco MII Submittal | 20 |  | 2019-09-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02333 | Received | For Review | 2019-09-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2019-09-23 | Submittal Number: 07 81 00-2.0 From: RYAN CROOKSTON Final Due Date: 09/20/19 Subject: APPLIED FIREPROOFING - CAFCO MII SUBMITTAL Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03570 | Forwarded | For Review | 2019-09-06 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-09-13 | Submittal Number: 07 81 00-2.0 From: RYAN CROOKSTON Final Due Date: 09/20/19 Subject: APPLIED FIREPROOFING - CAFCO MII SUBMITTAL Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 02522 | Review Response | Approved as Noted/Resubmit | 2019-09-25 | Tom Usher (Populous) | Shaina Burris (Populous) |  | Product Data approved. This submittal is missing many items: 1.4 - ACTION SUBMITTALS B.Sustainable Design Submittals: 1.Product Data: For paints and coatings, indicating VOC content. 2.Laboratory Test Reports: For paints and coatings, indicating compliance with requirements for low-emitting materials. 1.5 - INFORMATIONAL SUBMITTALS A.Qualification Data: For Installer. B.Product Certificates: For each type of fireproofing. C.Evaluation Reports: For fireproofing, from ICC-ES. D.Preconstruction Test Reports: For fireproofing. Last but not least being: 1.4 - ACTION SUBMITTALS: C.Shop Drawings: Framing plans or schedules, or both, indicating the following: 1.Extent of fireproofing for each construction and fire-resistance rating. 2.Applicable fire-resistance design designations of a qualified testing and inspecting agency acceptable to authorities having jurisdiction. 3.Minimum fireproofing thicknesses needed to achieve required fire-resistance rating of each structural component and assembly. 4.Treatment of fireproofing after application. Please be mindful of language in 01 33 00 -Submittal Requirements, 1.5F: Incomplete submittals, defined as lacking required information, such as Product Data, Samples, identified options or deviations, will be cause for extended review time and rejection. Shop drawings can understandably be submitted separately from other outstanding submittals. | Info Exchange
| 03802 | Responded and Closed | Approved as Noted/Resubmit | 2019-09-25 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Tom Usher (Populous) Remarks: Product Data approved. This submittal is missing many items: 1.4 - ACTION SUBMITTALS B.Sustainable Design Submittals: 1.Product Data: For paints and coatings, indicating VOC content. 2.Laboratory Test Reports: For paints and coatings, indicating compliance with requirements for low-emitting materials. 1.5 - INFORMATIONAL SUBMITTALS A.Qualification Data: For Installer. B.Product Certificates: For each type of fireproofing. C.Evaluation Reports: For fireproofing, from ICC-ES. D.Preconstruction Test Reports: For fireproofing. Last but not least being: 1.4 - ACTION SUBMITTALS: C.Shop Drawings: Framing plans or schedules, or both, indicating the following: 1.Extent of fireproofing for each construction and fire-resistance rating. 2.Applicable fire-resistance design designations of a qualified testing and inspecting agency acceptable to authorities having jurisdiction. 3.Minimum fireproofing thicknesses needed to achieve required fire-resistance rating of each structural component and assembly. 4.Treatment of fireproofing after application. Please be mindful of language in 01 33 00 -Submittal Requirements, 1.5F: Incomplete submittals, defined as lacking required information, such as Product Data, Samples, identified options or deviations, will be cause for extended review time and rejection. Shop drawings can understandably be submitted separately from other outstanding submittals. | Info Exchange
| 03951 | Sent | For Information Only | 2019-10-02 | Josh Dobken (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Tom Usher (Populous) Remarks: Product Data approved. This submittal is missing many items: 1.4 - ACTION SUBMITTALS B.Sustainable Design Submittals: 1.Product Data: For paints and coatings, indicating VOC content. 2.Laboratory Test Reports: For paints and coatings, indicating compliance with requirements for low-emitting materials. 1.5 - INFORMATIONAL SUBMITTALS A.Qualification Data: For Installer. B.Product Certificates: For each type of fireproofing. C.Evaluation Reports: For fireproofing, from ICC-ES. D.Preconstruction Test Reports: For fireproofing. Last but not least being: 1.4 - ACTION SUBMITTALS: C.Shop Drawings: Framing plans or schedules, or both, indicating the following: 1.Extent of fireproofing for each construction and fire-resistance rating. 2.Applicable fire-resistance design designations of a qualified testing and inspecting agency acceptable to authorities having jurisdiction. 3.Minimum fireproofing thicknesses needed to achieve required fire-resistance rating of each structural component and assembly. 4.Treatment of fireproofing after application. Please be mindful of language in 01 33 00 -Submittal Requirements, 1.5F: Incomplete submittals, defined as lacking required information, such as Product Data, Samples, identified options or deviations, will be cause for extended review time and rejection. Shop drawings can understandably be submitted separately from other outstanding submittals. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-06 |  | 7 81 00-2.0 Cafco MII Submittal (MAM review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-06 |  | 07 81 00-2.0 Cafco MII Submittal (MAM review).pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2019-09-24 |  | 078100-PD-002.0 SFRM for Dry Interior Exposed Surfaces_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2019-09-06 |  | 7 81 00-2.0 Cafco MII Submittal (MAM review).pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2019-09-05 02:00 |  | 07 81 00-2.0 Cafco MII Submittal (MAM review).pdf
07 81 00-002-00-01 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-002-00 APPLIED FIREPROOFING - Cafco MII Submittal | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 81 00-002-00 - 07 81 00-002-00 APPLIED FIREPROOFING - Cafco MII Submittal | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-06 |  | 7 81 00-2.0 Cafco MII Submittal (MAM review).pdf
07 81 00-003-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-003-00 APPLIED FIREPROOFING - Cafco 400 Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-09 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-23 | 2019-09-25 | 17 |  | Record Copies; Transfers; Submittals | 07 81 00-003-00-01 - 07 81 00-003-00 APPLIED FIREPROOFING - Cafco 400 Submittal | 20 |  | 2019-09-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02334 | Received | For Review | 2019-09-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2019-09-23 | Submittal Number: 07 81 00-3.0 From: RYAN CROOKSTON Final Due Date: 09/20/19 Subject: APPLIED FIREPROOFING - CAFCO 400 SUBMITTAL Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03571 | Forwarded | For Review | 2019-09-06 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-09-13 | Submittal Number: 07 81 00-3.0 From: RYAN CROOKSTON Final Due Date: 09/20/19 Subject: APPLIED FIREPROOFING - CAFCO 400 SUBMITTAL Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 02523 | Review Response | Approved as Noted/Resubmit | 2019-09-25 | Tom Usher (Populous) | Shaina Burris (Populous) |  | Product Data approved. This submittal is missing many items: 1.4 - ACTION SUBMITTALS B.Sustainable Design Submittals: 1.Product Data: For paints and coatings, indicating VOC content. 2.Laboratory Test Reports: For paints and coatings, indicating compliance with requirements for low-emitting materials. 1.5 - INFORMATIONAL SUBMITTALS A.Qualification Data: For Installer. B.Product Certificates: For each type of fireproofing. C.Evaluation Reports: For fireproofing, from ICC-ES. D.Preconstruction Test Reports: For fireproofing. Last but not least being: 1.4 - ACTION SUBMITTALS: C.Shop Drawings: Framing plans or schedules, or both, indicating the following: 1.Extent of fireproofing for each construction and fire-resistance rating. 2.Applicable fire-resistance design designations of a qualified testing and inspecting agency acceptable to authorities having jurisdiction. 3.Minimum fireproofing thicknesses needed to achieve required fire-resistance rating of each structural component and assembly. 4.Treatment of fireproofing after application. Please be mindful of language in 01 33 00 -Submittal Requirements, 1.5F: Incomplete submittals, defined as lacking required information, such as Product Data, Samples, identified options or deviations, will be cause for extended review time and rejection. Shop drawings can understandably be submitted separately from other outstanding submittals. | Info Exchange
| 03804 | Responded and Closed | Approved as Noted/Resubmit | 2019-09-25 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Tom Usher (Populous) Remarks: Product Data approved. This submittal is missing many items: 1.4 - ACTION SUBMITTALS B.Sustainable Design Submittals: 1.Product Data: For paints and coatings, indicating VOC content. 2.Laboratory Test Reports: For paints and coatings, indicating compliance with requirements for low-emitting materials. 1.5 - INFORMATIONAL SUBMITTALS A.Qualification Data: For Installer. B.Product Certificates: For each type of fireproofing. C.Evaluation Reports: For fireproofing, from ICC-ES. D.Preconstruction Test Reports: For fireproofing. Last but not least being: 1.4 - ACTION SUBMITTALS: C.Shop Drawings: Framing plans or schedules, or both, indicating the following: 1.Extent of fireproofing for each construction and fire-resistance rating. 2.Applicable fire-resistance design designations of a qualified testing and inspecting agency acceptable to authorities having jurisdiction. 3.Minimum fireproofing thicknesses needed to achieve required fire-resistance rating of each structural component and assembly. 4.Treatment of fireproofing after application. Please be mindful of language in 01 33 00 -Submittal Requirements, 1.5F: Incomplete submittals, defined as lacking required information, such as Product Data, Samples, identified options or deviations, will be cause for extended review time and rejection. Shop drawings can understandably be submitted separately from other outstanding submittals. | Info Exchange
| 03952 | Sent | For Information Only | 2019-10-02 | Josh Dobken (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Tom Usher (Populous) Remarks: Product Data approved. This submittal is missing many items: 1.4 - ACTION SUBMITTALS B.Sustainable Design Submittals: 1.Product Data: For paints and coatings, indicating VOC content. 2.Laboratory Test Reports: For paints and coatings, indicating compliance with requirements for low-emitting materials. 1.5 - INFORMATIONAL SUBMITTALS A.Qualification Data: For Installer. B.Product Certificates: For each type of fireproofing. C.Evaluation Reports: For fireproofing, from ICC-ES. D.Preconstruction Test Reports: For fireproofing. Last but not least being: 1.4 - ACTION SUBMITTALS: C.Shop Drawings: Framing plans or schedules, or both, indicating the following: 1.Extent of fireproofing for each construction and fire-resistance rating. 2.Applicable fire-resistance design designations of a qualified testing and inspecting agency acceptable to authorities having jurisdiction. 3.Minimum fireproofing thicknesses needed to achieve required fire-resistance rating of each structural component and assembly. 4.Treatment of fireproofing after application. Please be mindful of language in 01 33 00 -Submittal Requirements, 1.5F: Incomplete submittals, defined as lacking required information, such as Product Data, Samples, identified options or deviations, will be cause for extended review time and rejection. Shop drawings can understandably be submitted separately from other outstanding submittals. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-06 |  | 7 81 00-3.0 Cafco 400 Submittal (MAM review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-06 |  | 07 81 00-3.0 Cafco 400 Submittal (MAM review).pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2019-09-24 |  | 078100-PD-003.0 SFRM Exposed to View & Moisture_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2019-09-06 |  | 7 81 00-3.0 Cafco 400 Submittal (MAM review).pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2019-09-05 02:00 |  | 07 81 00-3.0 Cafco 400 Submittal (MAM review).pdf
07 81 00-003-00-01 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-003-00 APPLIED FIREPROOFING - Cafco 400 Submittal | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 81 00-003-00 - 07 81 00-003-00 APPLIED FIREPROOFING - Cafco 400 Submittal | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-06 |  | 7 81 00-3.0 Cafco 400 Submittal (MAM review).pdf
07 81 00-004-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-004-00 Applied Fireproofing - Action Submittals | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-23 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-06 | 2020-02-20 | 29 |  | Record Copies; Transfers; Submittals |  | 30 |  | 2020-02-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04027 | Received | For Review | 2020-01-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-02-06 | Submittal Number: 07 81 00-4.0 From: RYAN CROOKSTON Final Due Date: 02/06/20 Subject: APPLIED FIREPROOFING - ACTION SUBMITTALS Description: PRODUCT DATA SUSTAINABLE DESIGN SUBMITTAL Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 05614 | Forwarded | For Review | 2020-01-22 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-01-29 | Submittal Number: 07 81 00-4.0 From: RYAN CROOKSTON Final Due Date: 02/06/20 Subject: APPLIED FIREPROOFING - ACTION SUBMITTALS Description: PRODUCT DATA SUSTAINABLE DESIGN SUBMITTAL Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 06123 | Responded and Closed | Approved | 2020-02-20 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Approved. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-22 |  | Applied Fireproofing - Action Submittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-22 |  | Applied Fireproofing - Action Submittal (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-20 |  | 07 81 00-004-00 Applied Fireproofing - Action Submittal MAM_POP.pdf
07 81 00-004-01 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-004-01 Applied Fireproofing - Action Submittal for Cafco 400AC (Replacement for Cafco 400) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-19 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-06 07:00 | 2020-07-08 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06513 | Received | For Review | 2020-06-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-07-06 07:00 | Submittal Number: 07 81 00-4.1 From: RYAN CROOKSTON Final Due Date: 07/03/20 Subject: APPLIED FIREPROOFING - ACTION SUBMITTAL FOR CAFCO 400AC (REPLACEMENT FOR CAFCO 400) Description: PRODUCT DATA SUSTAINABLE DESIGN SUBMITTAL Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 08767 | Forwarded | For Review | 2020-06-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-26 | Submittal Number: 07 81 00-4.1 From: RYAN CROOKSTON Final Due Date: 07/03/20 Subject: APPLIED FIREPROOFING - ACTION SUBMITTAL FOR CAFCO 400AC (REPLACEMENT FOR CAFCO 400) Description: PRODUCT DATA SUSTAINABLE DESIGN SUBMITTAL Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 09212 | Responded and Closed | Approved as Noted | 2020-07-08 | Tom Usher (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | CAFCO 400 AC is acceptable for the electrical room columns but NOT acceptable for the parking garage. The cement-based CAFCO 400 is to be provided in the garage as specified. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 |  | 07 81 00-4.1 Applied Fireproofing Action Submittal - Cafco 400AC (MAM Review).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 |  | Rolling Plains Cafco 400AC Proposal Email.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-18 |  | 07 81 00-4.1 Applied Fireproofing Action Submittal - Cafco 400AC (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-18 |  | Rolling Plains Cafco 400AC Proposal Email.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2020-07-08 02:00 |  | 07 81 00-4.1 Applied Fireproofing Action Submittal - Cafco 400AC (MAM Review)_POP.pdf
07 81 00-005-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-005-00 Shop Drawings - Applied Fireproofing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-03-30 | 2020-04-17 | 33 |  | Record Copies; Transfers; Submittals |  | 33 |  | 2020-04-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04860 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company); Ryan Crookston (Mortenson Construction) | 2020-03-30 | Submittal Number: 07 81 00-5.0 From: NATE WEINGART Final Due Date: 03/30/20 Subject: SHOP DRAWINGS - APPLIED FIREPROOFING Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 06637 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-03-23 | Submittal Number: 07 81 00-5.0 From: NATE WEINGART Final Due Date: 03/30/20 Subject: SHOP DRAWINGS - APPLIED FIREPROOFING Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 07339 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-17 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company); Ryan Crookston (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | Applied Fireproofing Shop Drawings - Cafco 300 (MAM Review).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | Applied Fireproofing Shop Drawings- Cafco 400 (MAM Review).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | Applied Fireproofing Shop Drawings- Isolatek M-II (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | Applied Fireproofing Shop Drawings - Cafco 300 (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | Applied Fireproofing Shop Drawings- Cafco 400 (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | Applied Fireproofing Shop Drawings- Isolatek M-II (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-17 |  | Applied Fireproofing Shop Drawings- Isolatek M-II_MAM_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-17 |  | Applied Fireproofing Shop Drawings - Cafco 300_MAM_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-17 |  | Applied Fireproofing Shop Drawings- Cafco 400_MAM_POP.pdf
07 81 00-005-01 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-005-01 Shop Drawings - Applied Fireproofing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-25 | 2020-05-18 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05777 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-25 | Submittal Number: 07 81 00-5.1 From: RYAN CROOKSTON Final Due Date: 05/15/20 Subject: SHOP DRAWINGS - APPLIED FIREPROOFING Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 07834 | Forwarded | For Review | 2020-05-11 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-18 | Submittal Number: 07 81 00-5.1 From: RYAN CROOKSTON Final Due Date: 05/15/20 Subject: SHOP DRAWINGS - APPLIED FIREPROOFING Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 07970 | Responded and Closed | Approved as Noted | 2020-05-18 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | See attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | HOURLY RATING COLORED UP SUBMITTAL DRAWINGS.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | SEATTLE ARENA 078100 (MII)(REV 1)_(MAM Approved).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-11 |  | HOURLY RATING COLORED UP SUBMITTAL DRAWINGS.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-11 |  | SEATTLE ARENA 078100 (MII)(REV 1)_(MAM Approved).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-14 |  | 07 81 00-005-01 - SEATTLE ARENA 078100 (MII)-MAM_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-18 |  | 07 81 00-005-01 - HOURLY RATING COLORED UP SUBMITTAL DRAWINGS_POP.pdf
07 81 00-006-02 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-006-02 Applied Fireproofing - Shop Drawings for City Submission | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-03 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-17 | 2020-06-05 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-06-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06172 | Received | For Review | 2020-06-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-06-17 | Submittal Number: 07 81 00-6.2 From: RYAN CROOKSTON Final Due Date: 06/17/20 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS FOR CITY SUBMISSION Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 08346 | Forwarded | For Review | 2020-06-03 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-10 | Submittal Number: 07 81 00-6.2 From: RYAN CROOKSTON Final Due Date: 06/17/20 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS FOR CITY SUBMISSION Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 08422 | Responded and Closed | Approved | 2020-06-05 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-03 |  | 07 81 00-6.2 Applied Fireproofing - Shop Drawings for City Submission (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-03 |  | 07 81 00-6.2 Applied Fireproofing - Shop Drawings for City Submission (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-05 |  | 07 81 00-6.2 Applied Fireproofing - Shop Drawings for City Submission-MAM_POP.pdf
07 81 00-006-03 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-006-03 Applied Fireproofing - Shop Drawings re-submission for City Comments | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-06 | 2020-07-23 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-07-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07107 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 07 81 00-6.3 From: RYAN CROOKSTON Final Due Date: 07/22/20 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS RE-SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 09495 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-30 | Submittal Number: 07 81 00-6.3 From: RYAN CROOKSTON Final Due Date: 07/22/20 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS RE-SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 09507 | Responded and Closed | Approved | 2020-07-23 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) |  | The design team has not performed an exhaustive review of this set – and that we defer to previous approvals. This set was re-stamped approved assuming all previous comments have been picked up. We understand some of the thicknesses have been revised and that no rating changes for any member have been revised. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 07 81 00-6.3 Applied Fireproofing - Shop Drawings Re-submission for City Comments.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | 07 81 00-6.3 Applied Fireproofing - Shop Drawings Re-submission for City Comments.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-22 |  | 07 81 00-6.3 Applied Fireproofing - SD Re-submission for City Comments_POP.pdf
07 81 00-006-04 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-006-04 Applied Fireproofing - Shop Drawings re-submission for City Comments | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-15 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-29 | 2020-09-15 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-09-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08099 | Received | For Review | 2020-09-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-29 | Submittal Number: 07 81 00-6.4 From: RYAN CROOKSTON Final Due Date: 09/28/20 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS RE-SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 10765 | Forwarded | For Review | 2020-09-14 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-21 | Submittal Number: 07 81 00-6.4 From: RYAN CROOKSTON Final Due Date: 09/28/20 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS RE-SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 10804 | Responded and Closed | Approved | 2020-09-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | The design team assumed these were revised to meet contract documents per the permit comments and included any revisions the permit reviewer requested. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-14 |  | 07 81 00-6.4 Applied Fireproofing - Shop Drawings for City.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-14 |  | 07 81 00-6.4 Applied Fireproofing - Shop Drawings for City.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-15 |  | 07 81 00-6.4 Applied Fireproofing - Shop Drawings for City_POP.pdf
07 81 00-006-05 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-006-05 Applied Fireproofing - Shop Drawings re-submission for City Comments | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-19 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-02 | 2021-01-19 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10766 | Received | For Review | 2021-01-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-02-02 | Submittal Number: 07 81 00-6.5 From: RYAN CROOKSTON Final Due Date: 02/02/21 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS RE-SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 14001 | Forwarded | For Review | 2021-01-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-26 | Submittal Number: 07 81 00-6.5 From: RYAN CROOKSTON Final Due Date: 02/02/21 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS RE-SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 14007 | Responded and Closed | Approved | 2021-01-19 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-19 |  | 07 81 00 - 6.5 Applied fireproofing SDs resubmission for city.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-19 |  | 07 81 00 - 6.5 Applied fireproofing SDs resubmission for city.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-01-19 |  | 07 81 00 - 6.5 Applied fireproofing SDs resubmission for city_POP.pdf
07 81 00-006-06 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-006-06 Applied Fireproofing - Shop Drawings re-submission for City Comments | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-29 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-12 | 2021-02-08 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11045 | Received | For Review | 2021-01-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-02-12 | Submittal Number: 07 81 00-6.6 From: TYLER KREN Final Due Date: 02/12/21 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS RE-SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. UPDATED 1-S3-81 AND 2-S3-81, MAKING COLUMNS ON EACH END OF THE TWO DETAILS LOW DENSITY TO MATCH DESIGN DOCUMENTS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 14340 | Forwarded | For Review | 2021-01-29 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-05 | Submittal Number: 07 81 00-6.6 From: TYLER KREN Final Due Date: 02/12/21 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS RE-SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. UPDATED 1-S3-81 AND 2-S3-81, MAKING COLUMNS ON EACH END OF THE TWO DETAILS LOW DENSITY TO MATCH DESIGN DOCUMENTS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 14569 | Responded and Closed | Approved | 2021-02-08 | Todd Spangler (Populous) | Tyler Kren (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-28 |  | 07 81 00 - 6.6 Applied fireproofing SDs resubmission for city.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-28 |  | 07 81 00 - 6.6 Applied fireproofing SDs resubmission for city.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-08 |  | 07 81 00 - 6.6 Applied fireproofing SDs resubmission for city_POP.pdf
07 81 00-006-07 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-006-07 Applied Fireproofing - Shop Drawings re-submission for City Comments | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-05 | 2021-04-28 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12690 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyler Kren (Mortenson Construction) | 2021-05-05 | Submittal Number: 07 81 00-6.7 From: TYLER KREN Final Due Date: 05/04/21 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS RE-SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. UPDATED TO INCLUDED SFRM ON THE ROOF DECKING IN THE ATRIUM ON LOW CEILINGS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 16410 | Forwarded | For Review | 2021-04-20 | Tyler Kren (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 07 81 00-6.7 From: TYLER KREN Final Due Date: 05/04/21 Subject: APPLIED FIREPROOFING - SHOP DRAWINGS RE-SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. UPDATED TO INCLUDED SFRM ON THE ROOF DECKING IN THE ATRIUM ON LOW CEILINGS. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 16622 | Responded and Closed | Approved | 2021-04-28 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Tyler Kren (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-20 |  | 07 81 00-6.7 Applied Fireproofing - SDs for City.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-04-20 |  | 07 81 00-6.7 Applied Fireproofing - SDs for City.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-28 02:00 |  | 07 81 00-6.7 Applied Fireproofing - SDs for City_POP.pdf
07 81 00-009-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-009-00 Applied Fireproofing - Informational Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-06 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-11-20 | 2019-11-19 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-11-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03063 | Received | For Review | 2019-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2019-11-20 | Submittal Number: 07 81 00-9.0 From: RYAN CROOKSTON Final Due Date: 11/20/19 Subject: APPLIED FIREPROOFING - INFORMATIONAL SUBMITTAL Description: A - QUALIFICATION DATA: FOR INSTALLER AND TESTING AGENCY B - PRODUCT CERTIFICATES: FOR EACH TYPE OF FIREPROOFING C - EVALUATION REPORTS: FOR FIREPROOFING, FROM ICC-ES D - PRE-CONSTRUCTION TEST REPORTS: FOR FIREPROOFING Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 04458 | Forwarded | For Review | 2019-11-05 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-11-12 | Submittal Number: 07 81 00-9.0 From: RYAN CROOKSTON Final Due Date: 11/20/19 Subject: APPLIED FIREPROOFING - INFORMATIONAL SUBMITTAL Description: A - QUALIFICATION DATA: FOR INSTALLER AND TESTING AGENCY B - PRODUCT CERTIFICATES: FOR EACH TYPE OF FIREPROOFING C - EVALUATION REPORTS: FOR FIREPROOFING, FROM ICC-ES D - PRE-CONSTRUCTION TEST REPORTS: FOR FIREPROOFING Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 04711 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-19 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-05 |  | 07 81 00-9 Applied Fireproofing Informational Submittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-05 |  | 07 81 00-9 Applied Fireproofing Informational Submittal (MAM Review).pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2019-11-19 |  | 07 81 00-9 Applied Fireproofing Informational Submittal (MAM Review) POP.pdf
07 81 00-009-01 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-009-01 Applied Fireproofing - Informational Submittal for Cafco 400AC (Replacement for Cafco 400) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-19 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-06 07:00 | 2020-07-08 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06514 | Received | For Review | 2020-06-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-07-06 07:00 | Submittal Number: 07 81 00-9.1 From: RYAN CROOKSTON Final Due Date: 07/03/20 Subject: APPLIED FIREPROOFING - INFORMATIONAL SUBMITTAL FOR CAFCO 400AC (REPLACEMENT FOR CAFCO 400) Description: A - QUALIFICATION DATA: FOR INSTALLER AND TESTING AGENCY B - PRODUCT CERTIFICATES: FOR EACH TYPE OF FIREPROOFING C - EVALUATION REPORTS: FOR FIREPROOFING, FROM ICC-ES D - PRE-CONSTRUCTION TEST REPORTS: FOR FIREPROOFING Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 08768 | Forwarded | For Review | 2020-06-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-26 | Submittal Number: 07 81 00-9.1 From: RYAN CROOKSTON Final Due Date: 07/03/20 Subject: APPLIED FIREPROOFING - INFORMATIONAL SUBMITTAL FOR CAFCO 400AC (REPLACEMENT FOR CAFCO 400) Description: A - QUALIFICATION DATA: FOR INSTALLER AND TESTING AGENCY B - PRODUCT CERTIFICATES: FOR EACH TYPE OF FIREPROOFING C - EVALUATION REPORTS: FOR FIREPROOFING, FROM ICC-ES D - PRE-CONSTRUCTION TEST REPORTS: FOR FIREPROOFING Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 09214 | Responded and Closed | Approved as Noted | 2020-07-08 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | CAFCO 400 AC is acceptable for the electrical room columns but NOT acceptable for the parking garage. The cement-based CAFCO 400 is to be provided in the garage as specified. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 |  | Applied Fireproofing Informational Submittal - Cafco 400AC.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 |  | Rolling Plains Cafco 400AC Proposal Email.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-18 |  | Applied Fireproofing Informational Submittal - Cafco 400AC.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-18 |  | Rolling Plains Cafco 400AC Proposal Email.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-08 02:00 |  | 07 81 00-9.1 Applied Fireproofing Informational Submittal - Cafco 400AC_POP.pdf
07 81 00-010-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-010-00 Applied Fireproofing - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-20 | 2020-02-18 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-02-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04239 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-02-20 | Submittal Number: 07 81 00-10.0 From: RYAN CROOKSTON Final Due Date: 02/19/20 Subject: APPLIED FIREPROOFING - SAMPLES Description: APPLIED FIREPROOFING SAMPLES, FOR ALL 3 PRODUCTS: CAFCO 300, CAFCO 400, AND CAFCO FENDOLITE M-II. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 05868 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-02-13 | Submittal Number: 07 81 00-10.0 From: RYAN CROOKSTON Final Due Date: 02/19/20 Subject: APPLIED FIREPROOFING - SAMPLES Description: APPLIED FIREPROOFING SAMPLES, FOR ALL 3 PRODUCTS: CAFCO 300, CAFCO 400, AND CAFCO FENDOLITE M-II. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 06072 | Responded and Closed | Approved as Noted | 2020-02-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | FINAL APPROVAL PENDING MOCKUP | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | Applied Fireproofing - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | Applied Fireproofing - Samples.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-18 02:00 |  | Applied Fireproofing - Samples_POP.pdf
07 81 00-011-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-011-00 Applied Fireproofing - Cafco 300 Extended Set Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-06 | 2020-08-20 | 29 |  | Record Copies; Transfers; Submittals | 07 81 00-011-01 - 07 81 00-011-00 Applied Fireproofing - Cafco 300 Extended Set Submittal | 29 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07108 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 07 81 00-11.0 From: RYAN CROOKSTON Final Due Date: 08/06/20 Subject: APPLIED FIREPROOFING - CAFCO 300 EXTENDED SET SUBMITTAL Description: PLEASE SEE THE ATTACHED SHORT-FORM PRODUCT DATA FOR THE CAFCO 300 EXTENDED SET PRODUCT. PLEASE ALSO REFERENCE THE ATTACHED LETTER FROM ISOLATEK DATED 7/22/2020 DESCRIBING THE USAGE OF THIS PRODUCT AND IT'S IDENTICAL NATURE TO CAFCO 300. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 09497 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-30 | Submittal Number: 07 81 00-11.0 From: RYAN CROOKSTON Final Due Date: 08/06/20 Subject: APPLIED FIREPROOFING - CAFCO 300 EXTENDED SET SUBMITTAL Description: PLEASE SEE THE ATTACHED SHORT-FORM PRODUCT DATA FOR THE CAFCO 300 EXTENDED SET PRODUCT. PLEASE ALSO REFERENCE THE ATTACHED LETTER FROM ISOLATEK DATED 7/22/2020 DESCRIBING THE USAGE OF THIS PRODUCT AND IT'S IDENTICAL NATURE TO CAFCO 300. Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 10171 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-20 | Tom Usher (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) |  | See attached resposne | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 07 81 00-11 Applied Fireproofing - Cafco 300ES Submittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | 07 81 00-11 Applied Fireproofing - Cafco 300ES Submittal (MAM Review).pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2020-08-07 02:00 |  | 07 81 00-11 Applied Fireproofing - Cafco 300ES Submittal (MAM Review)_POP.pdf
07 81 00-011-01 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-011-00 Applied Fireproofing - Cafco 300 Extended Set Submittal | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 81 00-011-00 - 07 81 00-011-00 Applied Fireproofing - Cafco 300 Extended Set Submittal | -1 | 2020-09-03
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-07 02:00 |  | 07 81 00-11 Applied Fireproofing - Cafco 300ES Submittal (MAM Review)_POP.pdf
07 81 00-012-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-012-00 Applied Fireproofing - Cementitious In-place Mockup | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-28 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-11 | 2020-08-17 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-08-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07175 | Received | For Review | 2020-07-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (M.A. Mortenson Company) | 2020-08-11 | Submittal Number: 07 81 00-12.0 From: RYAN CROOKSTON Final Due Date: 08/11/20 Subject: APPLIED FIREPROOFING - CEMENTITIOUS IN-PLACE MOCKUP Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 09577 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-04 | Submittal Number: 07 81 00-12.0 From: RYAN CROOKSTON Final Due Date: 08/11/20 Subject: APPLIED FIREPROOFING - CEMENTITIOUS IN-PLACE MOCKUP Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 10107 | Responded and Closed | Approved as Noted | 2020-08-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company); Ryan Crookston (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-27 |  | Applied Fireproofing - Cementitious In-place Mockup.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-27 |  | Applied Fireproofing - Cementitious In-place Mockup.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-17 02:00 |  | 07 81 00-012-00 Applied Fireproofing - Cementitious In-place Mockup_POP.pdf
07 81 00-CE-001.0 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-CE-001.0 Cafco 300 Product Certificate | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02101 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 00-CE-001.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: 078100-CE-001 CAFCO 300 PRODUCT CERTIFICATE Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03278 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 00-CE-001.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: 078100-CE-001 CAFCO 300 PRODUCT CERTIFICATE Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03339 | Responded and Closed | Rejected | 2019-08-20 | Tom Usher (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 00 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-16 |  | 078100-CE-001.0 Cafco 300 Product Certificate (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-16 |  | 078100-CE-001.0 Cafco 300 Product Certificate (MAM Review).pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2019-08-15 02:00 |  | 078100-CE-001.0 Cafco 300 Product Certificate (MAM Review).pdf
07 81 00-CE-002.0 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-CE-002.0 Cafco 400 Product Certificate | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02102 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 00-CE-002.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: CAFCO 400 PRODUCT CERTIFICATE Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03279 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 00-CE-002.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: CAFCO 400 PRODUCT CERTIFICATE Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03340 | Responded and Closed | Rejected | 2019-08-20 | Tom Usher (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 00 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-16 |  | 078100-CE-002.0 Cafco 400 Product Certificate (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-16 |  | 078100-CE-002.0 Cafco 400 Product Certificate (MAM Review).pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2019-08-15 02:00 |  | 078100-CE-002.0 Cafco 400 Product Certificate (MAM Review).pdf
07 81 00-CE-003.0 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-CE-003.0 Fendolite MII Product Certificate | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02103 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 00-CE-003.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: FENDOLITE MII PRODUCT CERTIFICATE Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03280 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 00-CE-003.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: FENDOLITE MII PRODUCT CERTIFICATE Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03341 | Responded and Closed | Rejected | 2019-08-20 | Tom Usher (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 00 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-16 |  | 078100-CE-003.0 Fendolite MII Product Certificate (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-16 |  | 078100-CE-003.0 Fendolite MII Product Certificate (MAM Review).pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2019-08-15 02:00 |  | 078100-CE-003.0 Fendolite MII Product Certificate (MAM Review).pdf
07 81 00-PD-001-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-PD-001-00 SFRM for Dry Interior Concealed Surfaces | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-16 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-08-30 | 2019-08-20 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02110 | Received | For Review | 2019-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-08-30 | Submittal Number: 07 81 00-PD-001.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: SFRM FOR DRY INTERIOR CONCEALED SURFACES Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03287 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Tom Usher (Populous); Josh Dobken (Populous) |  | Submittal Number: 07 81 00-PD-001.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: SFRM FOR DRY INTERIOR CONCEALED SURFACES Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03338 | Responded and Closed | Rejected | 2019-08-20 | Tom Usher (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 80 00 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-16 |  | 078100-PD-001.0 SFRM for Dry Interior Concealed Surfaces (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-16 |  | 078100-PD-001.0 SFRM for Dry Interior Concealed Surfaces (MAM Review).pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2019-08-15 02:00 |  | 078100-PD-001.0 SFRM for Dry Interior Concealed Surfaces (MAM Review).pdf
07 81 00-PD-002-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-PD-002-00 SFRM for Dry Interior Exposed Surfaces | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-16 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-08-30 | 2019-08-20 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02111 | Received | For Review | 2019-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-08-30 | Submittal Number: 07 81 00-PD-002.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: SFRM FOR DRY INTERIOR EXPOSED SURFACES Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03288 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 00-PD-002.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: SFRM FOR DRY INTERIOR EXPOSED SURFACES Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03342 | Responded and Closed | Rejected | 2019-08-20 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 00 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-16 |  | 078100-PD-002.0 SFRM for Dry Interior Exposed Surfaces (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-16 |  | 078100-PD-002.0 SFRM for Dry Interior Exposed Surfaces (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-15 02:00 |  | 078100-PD-002.0 SFRM for Dry Interior Exposed Surfaces (MAM Review).pdf
07 81 00-PD-003-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-PD-003-00 SFRM Exposed to View & Moisture | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-16 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-08-30 | 2019-08-20 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02112 | Received | For Review | 2019-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-08-30 | Submittal Number: 07 81 00-PD-003.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: SFRM EXPOSED TO VIEW & MOISTURE Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03289 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 00-PD-003.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: SFRM EXPOSED TO VIEW & MOISTURE Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03343 | Responded and Closed | Rejected | 2019-08-20 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 00 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-16 |  | 078100-PD-003.0 SFRM Exposed to View & Moisture (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-16 |  | 078100-PD-003.0 SFRM Exposed to View & Moisture (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-15 02:00 |  | 078100-PD-003.0 SFRM Exposed to View & Moisture (MAM Review).pdf
07 81 00-QD-001-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-QD-001-00 SFRM Qualification Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02113 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 00-QD-001.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: SFRM QUALIFICATION DATA Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03290 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 00-QD-001.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: SFRM QUALIFICATION DATA Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03344 | Responded and Closed | Rejected | 2019-08-20 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 00 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-16 |  | 078100-QD-001.0 SFRM Qualification Data (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-16 |  | 078100-QD-001.0 SFRM Qualification Data (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-15 02:00 |  | 078100-QD-001.0 SFRM Qualification Data (MAM Review).pdf
07 81 00-RE-001-00 | 07 81 00 - APPLIED FIREPROOFING | 07 81 00-RE-001-00 SFRM Evaluation Reports | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02114 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 00-RE-001.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: SFRM EVALUATION REPORTS Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03291 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 00-RE-001.0 From: NATE WEINGART Final Due Date: 08/30/19 Subject: SFRM EVALUATION REPORTS Description: Spec Section: 07 81 00 - APPLIED FIREPROOFING Status: OPEN | Info Exchange
| 03345 | Responded and Closed | Rejected | 2019-08-20 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 00 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-16 |  | 078100-RE-001.0 SFRM Evaluation Reports (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-16 |  | 078100-RE-001.0 SFRM Evaluation Reports (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-15 02:00 |  | 078100-RE-001.0 SFRM Evaluation Reports (MAM Review).pdf
07 81 23-001-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-001-00 Carboline Thermo-Sorb Product Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-11 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-25 | 2019-10-08 | 28 |  | Record Copies; Transfers; Submittals | 07 81 23-001-01 - 07 81 23-001-00 Carboline Thermo-Sorb Product Submittal | 28 |  | 2019-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02374 | Received | For Review | 2019-09-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2019-09-25 | Submittal Number: 07 81 23-1.0 From: RYAN CROOKSTON Final Due Date: 09/24/19 Subject: CARBOLINE THERMO-SORB PRODUCT SUBMITTAL Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03617 | Forwarded | For Review | 2019-09-11 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-09-18 | Submittal Number: 07 81 23-1.0 From: RYAN CROOKSTON Final Due Date: 09/24/19 Subject: CARBOLINE THERMO-SORB PRODUCT SUBMITTAL Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 02700 | Review Response | Approved as Noted/Resubmit | 2019-10-08 | Tom Usher (Populous) | Josh Dobken (Populous) |  | See attached submittal for comments. | Info Exchange
| 04032 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Tom Usher (Populous) Remarks: See attached submittal for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-10 |  | 07 81 23-1.0 Carboline Thermo-Sorb Submittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-10 |  | 07 81 23-1.0 Carboline Thermo-Sorb Submittal (MAM Review).pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2019-10-08 02:00 |  | 07 81 23-1.0 Carboline Thermo-Sorb Submittal (MAM Review)_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-09 02:00 |  | 07 81 23-1.0 Carboline Thermo-Sorb Submittal (MAM Review).pdf
07 81 23-001-01 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-001-00 Carboline Thermo-Sorb Product Submittal | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 81 23-001-00 - 07 81 23-001-00 Carboline Thermo-Sorb Product Submittal | -1 | 2019-10-22
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-09 02:00 |  | 07 81 23-1.0 Carboline Thermo-Sorb Submittal (MAM Review).pdf
07 81 23-002-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-002-00 Intumescent Fireproofing - Action Submittals | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-23 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-06 | 2020-02-10 | 19 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-02-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04028 | Received | For Review | 2020-01-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-02-06 | Submittal Number: 07 81 23-2.0 From: RYAN CROOKSTON Final Due Date: 02/06/20 Subject: INTUMESCENT FIREPROOFING - ACTION SUBMITTALS Description: PRODUCT DATA SUSTAINABLE DESIGN SUBMITTAL SHOP DRAWINGS SAMPLES Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 05615 | Forwarded | For Review | 2020-01-22 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-01-29 | Submittal Number: 07 81 23-2.0 From: RYAN CROOKSTON Final Due Date: 02/06/20 Subject: INTUMESCENT FIREPROOFING - ACTION SUBMITTALS Description: PRODUCT DATA SUSTAINABLE DESIGN SUBMITTAL SHOP DRAWINGS SAMPLES Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 05926 | Responded and Closed | No Action Taken or Required | 2020-02-10 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-22 |  | Intumescent Fireproofing - Action Submittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-22 |  | Intumescent Fireproofing - Action Submittal (MAM Review).pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 07 81 23-002-00 Intumescent Fireproofing - Action Submittal (MAM Review) POP.pdf
07 81 23-003-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-003-00 Intumescent Fireproofing - Informational Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-16 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-01-30 | 2020-02-10 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2020-02-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03942 | Received | For Review | 2020-01-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-01-30 | Submittal Number: 07 81 23-3.0 From: RYAN CROOKSTON Final Due Date: 01/30/20 Subject: INTUMESCENT FIREPROOFING - INFORMATIONAL SUBMITTAL Description: A - QUALIFICATION DATA: FOR INSTALLER AND TESTING AGENCY B - PRODUCT CERTIFICATES: FOR EACH TYPE OF FIREPROOFING C - EVALUATION REPORTS: FOR FIREPROOFING, FROM ICC-ES D - PRE-CONSTRUCTION TEST REPORTS: FOR FIREPROOFING E - CONFORMATION THAT INTUMESCENT COATING IS COMPATIBLE WITH STEEL PRIMER. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 05509 | Forwarded | For Review | 2020-01-16 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-01-23 | Submittal Number: 07 81 23-3.0 From: RYAN CROOKSTON Final Due Date: 01/30/20 Subject: INTUMESCENT FIREPROOFING - INFORMATIONAL SUBMITTAL Description: A - QUALIFICATION DATA: FOR INSTALLER AND TESTING AGENCY B - PRODUCT CERTIFICATES: FOR EACH TYPE OF FIREPROOFING C - EVALUATION REPORTS: FOR FIREPROOFING, FROM ICC-ES D - PRE-CONSTRUCTION TEST REPORTS: FOR FIREPROOFING E - CONFORMATION THAT INTUMESCENT COATING IS COMPATIBLE WITH STEEL PRIMER. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 05927 | Responded and Closed | No Action Taken or Required | 2020-02-10 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-16 |  | Intumescent Fireproofing - Informational Submittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-16 |  | Intumescent Fireproofing - Informational Submittal (MAM Review).pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 07 81 23-003-00 Intumescent Fireproofing Info Submittal (MAM Review) POP.pdf
07 81 23-003-01 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-003-01 Intumescent Fireproofing - Informational Submittal (Topcoat Product Data) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-16 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-30 | 2020-07-24 | 39 |  | Record Copies; Transfers; Submittals | 07 81 23-003-02 - 07 81 23-003-01 Intumescent Fireproofing - Informational Submittal (Topcoat Product Data) | 40 |  | 2020-07-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06411 | Received | For Review | 2020-06-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-06-30 | Submittal Number: 07 81 23-3.1 From: RYAN CROOKSTON Final Due Date: 06/30/20 Subject: INTUMESCENT FIREPROOFING - INFORMATIONAL SUBMITTAL (TOPCOAT PRODUCT DATA) Description: RESUBMITTAL FOR THE INTUMESCENT TOPCOAT PRODUCT DATA. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 08631 | Forwarded | For Review | 2020-06-15 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-22 | Submittal Number: 07 81 23-3.1 From: RYAN CROOKSTON Final Due Date: 06/30/20 Subject: INTUMESCENT FIREPROOFING - INFORMATIONAL SUBMITTAL (TOPCOAT PRODUCT DATA) Description: RESUBMITTAL FOR THE INTUMESCENT TOPCOAT PRODUCT DATA. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 07135 | Review Response | Approved as Noted/Resubmit | 2020-07-24 | Tom Usher (Populous) | Shaina Burris (Populous) |  | Topcoat is approved, the resubmit comment is to track the color samples that have not yet been submitted. | Info Exchange
| 09527 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Tom Usher (Populous) Remarks: Topcoat is approved, the resubmit comment is to track the color samples that have not yet been submitted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-15 |  | 07 81 23-3.1 Intumescent Fireproofing - Informational Submittal Topcoat Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-15 |  | 07 81 23-3.1 Intumescent Fireproofing - Informational Submittal Topcoat Product Data.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2020-07-20 02:00 |  | 07 81 23-3.1 Intumescent Fireproofing - Informational Submittal Topcoat Product Data_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-14 02:00 |  | 07 81 23-3.1 Intumescent Fireproofing - Informational Submittal Topcoat Product Data.pdf
07 81 23-003-02 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-003-01 Intumescent Fireproofing - Informational Submittal (Topcoat Product Data) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 81 23-003-01 - 07 81 23-003-01 Intumescent Fireproofing - Informational Submittal (Topcoat Product Data) | -1 | 2020-08-07
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-14 02:00 |  | 07 81 23-3.1 Intumescent Fireproofing - Informational Submittal Topcoat Product Data.pdf
07 81 23-004-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-004-00 Shop Drawings - Intumescent Fireproofing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-24 | 2020-02-27 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04273 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-02-24 | Submittal Number: 07 81 23-4.0 From: NATE WEINGART Final Due Date: 02/24/20 Subject: SHOP DRAWINGS - INTUMESCENT FIREPROOFING Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 05914 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-02-17 | Submittal Number: 07 81 23-4.0 From: NATE WEINGART Final Due Date: 02/24/20 Subject: SHOP DRAWINGS - INTUMESCENT FIREPROOFING Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 06263 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-27 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company); Ryan Crookston (Mortenson Construction) |  | See attached for review and comments. Resubmit for record. | Info Exchange
| 06395 | Sent | For Construction | 2020-03-04 | Josh Dobken (Populous) | Nate Weingart (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company); Ryan Crookston (Mortenson Construction) Remarks: See attached for review and comments. Resubmit for record. | Email
| 06713 | Sent | For Construction | 2020-03-18 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company); Ryan Crookston (Mortenson Construction) |  | Sent to: Nate Weingart (M.A. Mortenson Company) Remarks: Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company); Ryan Crookston (Mortenson Construction) Remarks: See attached for review and comments. Resubmit for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-10 |  | Intumescent FP Shop Drawings (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | Intumescent FP Shop Drawings (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-27 |  | 07 81 23-004-00 - Intumescent FP Shop Drawings MAM_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-02-27 02:00 |  | 07 81 23-004-00 - Intumescent FP Shop Drawings MAM_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-02-09 02:00 |  | Intumescent FP Shop Drawings (MAM Review).pdf
07 81 23-004-01 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-004-01 Shop Drawings - Intumescent Fireproofing - FOR RECORD ONLY | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-31 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-14 | 2020-04-06 | 7 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05127 | Received | For Review | 2020-03-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-04-14 | Submittal Number: 07 81 23-4.1 From: RYAN CROOKSTON Final Due Date: 04/14/20 Subject: SHOP DRAWINGS - INTUMESCENT FIREPROOFING - FOR RECORD ONLY Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 06959 | Forwarded | For Review | 2020-03-30 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-06 | Submittal Number: 07 81 23-4.1 From: RYAN CROOKSTON Final Due Date: 04/14/20 Subject: SHOP DRAWINGS - INTUMESCENT FIREPROOFING - FOR RECORD ONLY Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 07101 | Responded and Closed | Approved as Noted | 2020-04-06 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | Previous comments were not reflected in this for record submittal. Please update and submit for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-30 |  | Intumescent FP Shop Drawings - Resubmittal For Record Only (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-30 |  | Intumescent FP Shop Drawings - Resubmittal For Record Only (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-06 |  | 07 81 23-004-01 - Intumescent FP Shop Drawings _MAM_POP.pdf
07 81 23-005-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-005-00 Intumescent Fireproofing CAFCO SprayFilm WB4 Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-28 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-14 07:00 | 2020-09-14 | 18 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07804 | Received | For Review | 2020-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (M.A. Mortenson Company) | 2020-09-14 07:00 | Submittal Number: 07 81 23-5.0 From: TYLER KREN Final Due Date: 09/11/20 Subject: INTUMESCENT FIREPROOFING CAFCO SPRAYFILM WB4 PRODUCT DATA Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 10382 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-03 | Submittal Number: 07 81 23-5.0 From: TYLER KREN Final Due Date: 09/11/20 Subject: INTUMESCENT FIREPROOFING CAFCO SPRAYFILM WB4 PRODUCT DATA Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 10771 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyler Kren (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Provide VOC Content in resubmission. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 07 81 23 - 5 Intumescent Fireproofing CAFCO SprayFilm WB4 Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-27 |  | 07 81 23 - 5 Intumescent Fireproofing CAFCO SprayFilm WB4 Product Data.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-14 02:00 |  | 07 81 23 - 5 Intumescent Fireproofing CAFCO SprayFilm WB4 Product Data_POP.pdf
07 81 23-005-01 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-005-01 Intumescent Fireproofing CAFCO SprayFilm WB4 Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-15 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-29 | 2020-09-24 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08124 | Received | For Review | 2020-09-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-29 | Submittal Number: 07 81 23-5.1 From: TYLER KREN Final Due Date: 09/29/20 Subject: INTUMESCENT FIREPROOFING CAFCO SPRAYFILM WB4 PRODUCT DATA Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 10791 | Forwarded | For Review | 2020-09-15 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-22 | Submittal Number: 07 81 23-5.1 From: TYLER KREN Final Due Date: 09/29/20 Subject: INTUMESCENT FIREPROOFING CAFCO SPRAYFILM WB4 PRODUCT DATA Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 08335 | Review Response | Approved | 2020-09-24 | Josh Dobken (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 11043 | Responded and Closed | Approved | 2020-09-24 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Tyler Kren (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Josh Dobken (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-15 |  | 07 81 23 - 5.1 Intumescent Fireproofing CAFCO SprayFilm WB4 Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-15 |  | 07 81 23 - 5.1 Intumescent Fireproofing CAFCO SprayFilm WB4 Product Data.pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2020-09-24 02:00 |  | 07 81 23 - 5.1 Intumescent Fireproofing CAFCO SprayFilm WB4 Product Data_pop.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-14 02:00 |  | 07 81 23 - 5.1 Intumescent Fireproofing CAFCO SprayFilm WB4 Product Data.pdf
07 81 23-006-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-006-00 Intumescent Fireproofing - Shop Drawings for City Submission | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-21 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-04 | 2020-05-28 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-05-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05967 | Received | For Review | 2020-05-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-06-04 | Submittal Number: 07 81 23-6.0 From: RYAN CROOKSTON Final Due Date: 06/04/20 Subject: INTUMESCENT FIREPROOFING - SHOP DRAWINGS FOR CITY SUBMISSION Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 08101 | Forwarded | For Review | 2020-05-20 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-27 | Submittal Number: 07 81 23-6.0 From: RYAN CROOKSTON Final Due Date: 06/04/20 Subject: INTUMESCENT FIREPROOFING - SHOP DRAWINGS FOR CITY SUBMISSION Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 08242 | Responded and Closed | Approved | 2020-05-28 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-20 |  | SEATTLE ARENA 078123 (INT)(REV 1 CLEAN) (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-20 |  | SEATTLE ARENA 078123 (INT)(REV 1 CLEAN) (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-28 |  | SEATTLE ARENA 078123 (INT)(REV 1 CLEAN)_MAM_POP.pdf
07 81 23-006-01 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-006-01 Intumescent Fireproofing - Shop Drawings Re--submission for City Comments | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-06 | 2020-07-23 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-07-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07109 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 07 81 23-6.1 From: RYAN CROOKSTON Final Due Date: 07/22/20 Subject: INTUMESCENT FIREPROOFING - SHOP DRAWINGS RE--SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 09498 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-30 | Submittal Number: 07 81 23-6.1 From: RYAN CROOKSTON Final Due Date: 07/22/20 Subject: INTUMESCENT FIREPROOFING - SHOP DRAWINGS RE--SUBMISSION FOR CITY COMMENTS Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 09506 | Responded and Closed | Approved | 2020-07-23 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) |  | The design team has not performed an exhaustive review of this set – and that we defer to previous approvals. This set was re-stamped approved assuming all previous comments have been picked up. We understand some of the thicknesses have been revised and that no rating changes for any member have been revised. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | Intumescent Fireproofing - Shop Drawings Re-submission for City Comments.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | Intumescent Fireproofing - Shop Drawings Re-submission for City Comments.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-07-23 |  | 07 81 23-6.1 Intumescent Fireproofing - SD Re-submission for City Comments_POP.pdf
07 81 23-006-02 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-006-02 Intumescent Fireproofing - Bridge Truss Shop Drawing Revision | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-28 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-11 | 2020-08-31 | 4 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-08-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07805 | Received | For Review | 2020-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-11 | Submittal Number: 07 81 23-6.2 From: TYLER KREN Final Due Date: 09/11/20 Subject: INTUMESCENT FIREPROOFING - BRIDGE TRUSS SHOP DRAWING REVISION Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 10383 | Forwarded | For Review | 2020-08-27 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-03 | Submittal Number: 07 81 23-6.2 From: TYLER KREN Final Due Date: 09/11/20 Subject: INTUMESCENT FIREPROOFING - BRIDGE TRUSS SHOP DRAWING REVISION Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 10437 | Responded and Closed | Approved | 2020-08-31 | Populous SCA_CCA | Tyler Kren (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATATCHED FOR APPROVAL. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 07 81 23 - 6.2 Intumescent Fireproofing - Bridge Truss Shop Drawing Revision.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-27 |  | 07 81 23 - 6.2 Intumescent Fireproofing - Bridge Truss Shop Drawing Revision.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-27 |  | 07 81 23 - 6.2 Intumescent Fireproofing - Bridge Truss Shop Drawing Revision.pdf
07 81 23-006-03 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-006-03 Intumescent Fireproofing - Intumescent Shop Drawing Revision | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-19 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-02 | 2021-01-19 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10767 | Received | For Review | 2021-01-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-02-02 | Submittal Number: 07 81 23-6.3 From: TYLER KREN Final Due Date: 02/02/21 Subject: INTUMESCENT FIREPROOFING - INTUMESCENT SHOP DRAWING REVISION Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. UPDATING Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 14002 | Forwarded | For Review | 2021-01-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-26 | Submittal Number: 07 81 23-6.3 From: TYLER KREN Final Due Date: 02/02/21 Subject: INTUMESCENT FIREPROOFING - INTUMESCENT SHOP DRAWING REVISION Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. UPDATING Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 14004 | Responded and Closed | Approved | 2021-01-19 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-19 |  | 07 81 23 6.3 - Intumescent Fireproofing -SDs for city submission.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-19 |  | 07 81 23 6.3 - Intumescent Fireproofing -SDs for city submission.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-01-19 |  | 07 81 00 - 6.5 Applied fireproofing SDs resubmission for city_POP.pdf
07 81 23-006-04 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-006-04 Intumescent Fireproofing - Intumescent Shop Drawing Revision | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-05 | 2021-04-28 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12683 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyler Kren (Mortenson Construction) | 2021-05-05 | Submittal Number: 07 81 23-6.4 From: TYLER KREN Final Due Date: 05/04/21 Subject: INTUMESCENT FIREPROOFING - INTUMESCENT SHOP DRAWING REVISION Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. UPDATED TO INCLUDE APPLICATION TO BEAM ALONG THE EXTERIOR ON SE2 LINE. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 16402 | Forwarded | For Review | 2021-04-20 | Tyler Kren (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 07 81 23-6.4 From: TYLER KREN Final Due Date: 05/04/21 Subject: INTUMESCENT FIREPROOFING - INTUMESCENT SHOP DRAWING REVISION Description: SHOP DRAWING SUBMITTAL IN PREPARATION FOR SUBMISSION TO THE CITY. EVERY SINGLE PAGE NEEDS AN OFFICIAL STAMP FROM POPULOUS. UPDATED TO INCLUDE APPLICATION TO BEAM ALONG THE EXTERIOR ON SE2 LINE. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 16623 | Responded and Closed | Approved | 2021-04-28 | Tyler Kren (Mortenson Construction) | Danny Keim (Mortenson Construction); Tyler Kren (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-20 |  | 07 81 23 -6.4 Intumescent Fireproofing SDs revision for city.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-04-20 |  | 07 81 23 -6.4 Intumescent Fireproofing SDs revision for city.pdf
| Responded and Closed |  | Tyler Kren (Mortenson Construction) | 1 | 2021-04-28 02:00 |  | 07 81 23 -6.4 Intumescent Fireproofing SDs revision for city_POP.pdf
07 81 23-007-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-007-00 Intumescent Fireproofing - Topcoat Color Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-06 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-20 | 2020-08-25 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-08-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07404 | Received | For Review | 2020-08-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (M.A. Mortenson Company) | 2020-08-20 | Submittal Number: 07 81 23-7.0 From: RYAN CROOKSTON Final Due Date: 08/20/20 Subject: INTUMESCENT FIREPROOFING - TOPCOAT COLOR SAMPLES Description: SAMPLES OF THE INTUMESCENT FIREPROOFING WITH TOPCOAT APPLIED IN DIFFERENT COLORS AND FINISHES AS CALLED FOR IN THE SPEC. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 09868 | Forwarded | For Review | 2020-08-06 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-13 | Submittal Number: 07 81 23-7.0 From: RYAN CROOKSTON Final Due Date: 08/20/20 Subject: INTUMESCENT FIREPROOFING - TOPCOAT COLOR SAMPLES Description: SAMPLES OF THE INTUMESCENT FIREPROOFING WITH TOPCOAT APPLIED IN DIFFERENT COLORS AND FINISHES AS CALLED FOR IN THE SPEC. Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 10293 | Responded and Closed | Approved | 2020-08-25 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-05 |  | 07 81 23-7 Intumescent Fireproofing - Topcoat Color Samples (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-05 |  | 07 81 23-7 Intumescent Fireproofing - Topcoat Color Samples (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-25 |  | 07 81 23-7 Intumescent Fireproofing - Topcoat Color Samples MAM_POP.pdf
07 81 23-008-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-008-00 Intumescent fireproofing primer shop drawings for galvanized steel | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-05 | 2021-02-15 | 25 |  | Record Copies; Transfers; Submittals |  | 25 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10891 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-02-05 | Submittal Number: 07 81 23-8.0 From: TYLER KREN Final Due Date: 02/05/21 Subject: INTUMESCENT FIREPROOFING PRIMER SHOP DRAWINGS FOR GALVANIZED STEEL Description: SURFACE PREP PROCEDURE AND PRIMER PRODUCT DATA FOR APPLICATION OF THERMO SORB ON GALVANIZED STEEL MEMBERS Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 14145 | Forwarded | For Review | 2021-01-22 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-29 | Submittal Number: 07 81 23-8.0 From: TYLER KREN Final Due Date: 02/05/21 Subject: INTUMESCENT FIREPROOFING PRIMER SHOP DRAWINGS FOR GALVANIZED STEEL Description: SURFACE PREP PROCEDURE AND PRIMER PRODUCT DATA FOR APPLICATION OF THERMO SORB ON GALVANIZED STEEL MEMBERS Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 14806 | Responded and Closed | Approved as Noted | 2021-02-15 | Shaina Burris (Populous) | Tyler Kren (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-21 |  | Intumescent fireproofing primer SDs for galvanized steel.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-21 |  | Intumescent fireproofing primer SDs for galvanized steel.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-01-21 |  | Intumescent fireproofing primer SDs for galvanized steel.pdf
07 81 23-CE-001-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-CE-001-00 Product Certificate - Carboline Thermo-Sorb | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02115 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 23-CE-001.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: PRODUCT CERTIFICATE - CARBOLINE THERMO-SORB Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03292 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 23-CE-001.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: PRODUCT CERTIFICATE - CARBOLINE THERMO-SORB Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03354 | Responded and Closed | Rejected | 2019-08-20 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 23 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 078123-CE-001.0 Certificate - Carboline Thermo-Sorb (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-19 |  | 078123-CE-001.0 Certificate - Carboline Thermo-Sorb (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-18 02:00 |  | 078123-CE-001.0 Certificate - Carboline Thermo-Sorb (MAM Review).pdf
07 81 23-CE-002-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-CE-002-00 Product Certificate - Carboline Firefilm III | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02116 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 23-CE-002.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: PRODUCT CERTIFICATE - CARBOLINE FIREFILM III Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03293 | Forwarded | For Review | 2019-08-19 | Nate Weingart (Mortenson Construction) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 23-CE-002.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: PRODUCT CERTIFICATE - CARBOLINE FIREFILM III Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03353 | Responded and Closed | Rejected | 2019-08-20 | Nate Weingart (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 23 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 078123-CE-002.0 Certificate - Carboline Firefilm III (MAM Review).pdf
| Forwarded |  | Nate Weingart (Mortenson Construction) | 1 | 2019-08-19 |  | 078123-CE-002.0 Certificate - Carboline Firefilm III (MAM Review).pdf
| Responded and Closed |  | Nate Weingart (Mortenson Construction) | 1 | 2019-08-18 02:00 |  | 078123-CE-002.0 Certificate - Carboline Firefilm III (MAM Review).pdf
07 81 23-LE-001-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-LE-001-00 LEED Submittal - Carboline Thermo-Sorb | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02117 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 23-LE-001.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: LEED SUBMITTAL - CARBOLINE THERMO-SORB Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03294 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 23-LE-001.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: LEED SUBMITTAL - CARBOLINE THERMO-SORB Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03352 | Responded and Closed | Rejected | 2019-08-20 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 23 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 078123-LE-001.0 LEED Submittal - Carboline Thermo-Sorb (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-19 |  | 078123-LE-001.0 LEED Submittal - Carboline Thermo-Sorb (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-18 02:00 |  | 078123-LE-001.0 LEED Submittal - Carboline Thermo-Sorb (MAM Review).pdf
07 81 23-LE-002-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-LE-002-00 LEED Submittal - Carboline Firefilm III | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02118 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 23-LE-002.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: LEED SUBMITTAL - CARBOLINE FIREFILM III Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03295 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 23-LE-002.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: LEED SUBMITTAL - CARBOLINE FIREFILM III Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03351 | Responded and Closed | Rejected | 2019-08-20 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 23 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 078123-LE-002.0 LEED Submittal - Carboline Firefilm III (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-19 |  | 078123-LE-002.0 LEED Submittal - Carboline Firefilm III (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-18 02:00 |  | 078123-LE-002.0 LEED Submittal - Carboline Firefilm III (MAM Review).pdf
07 81 23-PD-001-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-PD-001-00 Product Data - Carboline Thermo-Sorb | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02119 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 23-PD-001.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: PRODUCT DATA - CARBOLINE THERMO-SORB Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03296 | Forwarded | For Review | 2019-08-19 | Nate Weingart (Mortenson Construction) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 23-PD-001.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: PRODUCT DATA - CARBOLINE THERMO-SORB Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03350 | Responded and Closed | Rejected | 2019-08-20 | Nate Weingart (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 23 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 078123-PD-001.0 Product Data - Carboline Thermo-Sorb (MAM Review).pdf
| Forwarded |  | Nate Weingart (Mortenson Construction) | 1 | 2019-08-19 |  | 078123-PD-001.0 Product Data - Carboline Thermo-Sorb (MAM Review).pdf
| Responded and Closed |  | Nate Weingart (Mortenson Construction) | 1 | 2019-08-18 02:00 |  | 078123-PD-001.0 Product Data - Carboline Thermo-Sorb (MAM Review).pdf
07 81 23-PD-002-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-PD-002-00 Product Data - Carboline Firefilm III | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02120 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-09-02 | Submittal Number: 07 81 23-PD-002.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: PRODUCT DATA - CARBOLINE FIREFILM III Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03297 | Forwarded | For Review | 2019-08-19 | Populous SCA_CCA | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 23-PD-002.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: PRODUCT DATA - CARBOLINE FIREFILM III Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03349 | Responded and Closed | Rejected | 2019-08-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 23 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 078123-PD-002.0 Product Data - Carboline Firefilm III (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-08-19 |  | 078123-PD-002.0 Product Data - Carboline Firefilm III (MAM Review).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-08-18 02:00 |  | 078123-PD-002.0 Product Data - Carboline Firefilm III (MAM Review).pdf
07 81 23-QD-001-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-QD-001-00 Intumescent Fireproofing Qualification Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02121 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 23-QD-001.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: INTUMESCENT FIREPROOFING QUALIFICATION DATA Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03298 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 23-QD-001.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: INTUMESCENT FIREPROOFING QUALIFICATION DATA Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03348 | Responded and Closed | Rejected | 2019-08-20 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 23 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 078123-QD-001.0 Intumescent FP Qualification Data (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-19 |  | 078123-QD-001.0 Intumescent FP Qualification Data (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-18 02:00 |  | 078123-QD-001.0 Intumescent FP Qualification Data (MAM Review).pdf
07 81 23-RE-001-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-RE-001-00 Evaluation Report Templates - Carboline Thermo-Sorb | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02122 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-09-02 | Submittal Number: 07 81 23-RE-001.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: EVALUATION REPORT TEMPLATES - CARBOLINE THERMO-SORB Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03299 | Forwarded | For Review | 2019-08-19 | Populous SCA_CCA | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 23-RE-001.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: EVALUATION REPORT TEMPLATES - CARBOLINE THERMO-SORB Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03347 | Responded and Closed | Rejected | 2019-08-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 23 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 078123-RE-001.0 Evaluation Template - Thermo-Sorb (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-08-19 |  | 078123-RE-001.0 Evaluation Template - Thermo-Sorb (MAM Review).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-08-18 02:00 |  | 078123-RE-001.0 Evaluation Template - Thermo-Sorb (MAM Review).pdf
07 81 23-RE-002-00 | 07 81 23 - INTUMESCENT FIREPROOFING | 07 81 23-RE-002-00 Evaluation Report Templates - Carboline Firefilm III | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-19 | Responded and Closed - Rejected |  | Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-02 | 2019-08-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02123 | Received | For Review | 2019-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-09-02 | Submittal Number: 07 81 23-RE-002.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: EVALUATION REPORT TEMPLATES - CARBOLINE FIREFILM III Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03300 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-26 | Submittal Number: 07 81 23-RE-002.0 From: NATE WEINGART Final Due Date: 09/03/19 Subject: EVALUATION REPORT TEMPLATES - CARBOLINE FIREFILM III Description: Spec Section: 07 81 23 - INTUMESCENT FIREPROOFING Status: OPEN | Info Exchange
| 03346 | Responded and Closed | Rejected | 2019-08-20 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Please combine all 07 81 23 submittals into one complete submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 078123-RE-002.0 Evaluation Templates - Firefilm III (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-19 |  | 078123-RE-002.0 Evaluation Templates - Firefilm III (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-18 02:00 |  | 078123-RE-002.0 Evaluation Templates - Firefilm III (MAM Review).pdf
07 84 13-001-00 | 07 84 13 - PENETRATION FIRESTOPPING | 07 84 13-001-00 PENETRATION FIRESTOPPING - Fire Protection Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-28 | 2021-01-14 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10713 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2021-01-28 | Submittal Number: 07 84 13-1.0 From: SIMRAN GEORGE Final Due Date: 01/28/21 Subject: PENETRATION FIRESTOPPING - FIRE PROTECTION PRODUCT DATA Description: PRODUCT DATA : FOR HILTI PRODUCT. Spec Section: 07 84 13 - PENETRATION FIRESTOPPING Status: OPEN | Info Exchange
| 13935 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-21 | Submittal Number: 07 84 13-1.0 From: SIMRAN GEORGE Final Due Date: 01/28/21 Subject: PENETRATION FIRESTOPPING - FIRE PROTECTION PRODUCT DATA Description: PRODUCT DATA : FOR HILTI PRODUCT. Spec Section: 07 84 13 - PENETRATION FIRESTOPPING Status: OPEN | Info Exchange
| 13938 | Responded and Closed | Approved | 2021-01-14 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | 07 84 13-1.0 Fire Protection PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | 07 84 13-1.0 Fire Protection PD-MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | 07 84 13-1.0 Fire Protection PD-MAM.pdf
07 84 13-002-00 | 07 84 13 - PENETRATION FIRESTOPPING | 07 84 13-002-00 PENETRATION FIRESTOPPING - Cochran Electrical Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-21 | Responded and Closed - Approved |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-13 | 2021-01-11 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10279 | Received | For Review | 2020-12-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2021-01-13 | Submittal Number: 07 84 13-2.0 From: PATRICK KLEIN Final Due Date: 01/06/21 Subject: PENETRATION FIRESTOPPING - COCHRAN ELECTRICAL PRODUCT DATA Description: PRODUCT DATA: FOR SEALANTS, INDICATING VOC CONTENT. Spec Section: 07 84 13 - PENETRATION FIRESTOPPING Status: OPEN | Info Exchange
| 13429 | Forwarded | For Review | 2020-12-21 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-28 | Submittal Number: 07 84 13-2.0 From: PATRICK KLEIN Final Due Date: 01/06/21 Subject: PENETRATION FIRESTOPPING - COCHRAN ELECTRICAL PRODUCT DATA Description: PRODUCT DATA: FOR SEALANTS, INDICATING VOC CONTENT. Spec Section: 07 84 13 - PENETRATION FIRESTOPPING Status: OPEN | Info Exchange
| 13809 | Responded and Closed | Approved | 2021-01-11 | Shaina Burris (Populous) | Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-20 |  | 07 84 13-2.0 Cochran Electrical PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-20 |  | 07 84 13-2.0 Cochran Electrical PD-MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-12-20 |  | 07 84 13-2.0 Cochran Electrical PD-MAM.pdf
07 84 13-008-00 | 07 84 13 - PENETRATION FIRESTOPPING | 07 84 13-008-00 PENETRATION FIRESTOPPING - Electrical Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-08 | Responded and Closed - Approved |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-22 | 2020-12-22 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10011 | Received | For Review | 2020-12-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-12-22 | Submittal Number: 07 84 13-8.0 From: PATRICK KLEIN Final Due Date: 12/22/20 Subject: PENETRATION FIRESTOPPING - ELECTRICAL PRODUCT DATA Description: Spec Section: 07 84 13 - PENETRATION FIRESTOPPING Status: OPEN | Info Exchange
| 13102 | Forwarded | For Review | 2020-12-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-15 | Submittal Number: 07 84 13-8.0 From: PATRICK KLEIN Final Due Date: 12/22/20 Subject: PENETRATION FIRESTOPPING - ELECTRICAL PRODUCT DATA Description: Spec Section: 07 84 13 - PENETRATION FIRESTOPPING Status: OPEN | Info Exchange
| 10336 | Review Response | Approved | 2020-12-22 | Tom Usher (Populous) | Tom Usher (Populous); Josh Dobken (Populous) |  |  | Info Exchange
| 13503 | Responded and Closed | Approved | 2020-12-22 | Tom Usher (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Tom Usher (Populous) Remarks: | Info Exchange
| 13689 | Sent | For Information Only | 2021-01-06 | Josh Dobken (Populous) | Patrick Klein (Mortenson Construction) |  | Response (Approved) from: Tom Usher (Populous) Remarks: | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-08 |  | 07 84 13-8.0 Electrical PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-08 |  | 07 84 13-8.0 Electrical PD-MAM.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2020-12-22 |  | 07 84 13-8.0 Electrical PD-MAM_POP.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2020-12-08 |  | 07 84 13-8.0 Electrical PD-MAM.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-12-07 02:00 |  | 07 84 13-8.0 Electrical PD-MAM.pdf
07 84 43-001-00 | 07 84 43 - JOINT FIRESTOPPING | 07 84 43-001-00 Product Data - Joint Firestopping Systems for Drywall | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-21 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-05 | 2020-05-04 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05447 | Received | For Review | 2020-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-05-05 | Submittal Number: 07 84 43-0001.0 From: TYRONE THORNTON Final Due Date: 05/04/20 Subject: PRODUCT DATA - JOINT FIRESTOPPING SYSTEMS FOR DRYWALL Description: Spec Section: 07 84 43 - JOINT FIRESTOPPING Status: OPEN | Info Exchange
| 07392 | Forwarded | For Review | 2020-04-20 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-27 | Submittal Number: 07 84 43-0001.0 From: TYRONE THORNTON Final Due Date: 05/04/20 Subject: PRODUCT DATA - JOINT FIRESTOPPING SYSTEMS FOR DRYWALL Description: Spec Section: 07 84 43 - JOINT FIRESTOPPING Status: OPEN | Info Exchange
| 07718 | Responded and Closed | Approved | 2020-05-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-20 |  | 078443-0001-0 Product Data Joint Firestopping Systems-MAM.PDF
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-20 |  | 078443-0001-0 Product Data Joint Firestopping Systems-MAM.PDF
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-04-20 |  | 078443-0001-0 Product Data Joint Firestopping Systems-MAM.PDF
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-05-04 |  | 078443-0001-0 Product Data Joint Firestopping Systems-MAM-POP.pdf
07 84 43-002-00 | 07 84 43 - JOINT FIRESTOPPING | 07 84 43-002-00 JOINT FIRESTOPPING - LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-02 | 2020-07-08 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06507 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 07 84 43-2.0 From: TYRONE THORNTON Final Due Date: 07/02/20 Subject: JOINT FIRESTOPPING - LEED DATA Description: Spec Section: 07 84 43 - JOINT FIRESTOPPING Status: OPEN | Info Exchange
| 08762 | Forwarded | For Review | 2020-06-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) |  | Submittal Number: 07 84 43-2.0 From: TYRONE THORNTON Final Due Date: 07/02/20 Subject: JOINT FIRESTOPPING - LEED DATA Description: Spec Section: 07 84 43 - JOINT FIRESTOPPING Status: OPEN | Info Exchange
| 09190 | Responded and Closed | Approved | 2020-07-08 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 |  | 07 84 43 - Joint Firestopping - LEED Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-18 |  | 07 84 43 - Joint Firestopping - LEED Data_MAM Reviewed.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-08 |  | 07 84 43 - Joint Firestopping - LEED Data_MAM_POP.pdf
07 84 43-008-00 | 07 84 43 - JOINT FIRESTOPPING | 07 84 43-008-00 JOINT FIRESTOPPING - LEED Data_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-06 | 2020-08-17 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2020-08-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07110 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 07 84 43-8.0 From: TYRONE THORNTON Final Due Date: 08/07/20 Subject: JOINT FIRESTOPPING - LEED DATA_PCI Description: Spec Section: 07 84 43 - JOINT FIRESTOPPING Status: OPEN | Info Exchange
| 09499 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-30 | Submittal Number: 07 84 43-8.0 From: TYRONE THORNTON Final Due Date: 08/07/20 Subject: JOINT FIRESTOPPING - LEED DATA_PCI Description: Spec Section: 07 84 43 - JOINT FIRESTOPPING Status: OPEN | Info Exchange
| 10105 | Responded and Closed | Approved as Noted | 2020-08-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) |  | See attached submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | PCI Material Submittal 07 84 43 Joint Firestopping - LEED_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | PCI Material Submittal 07 84 43 Joint Firestopping - LEED_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-17 02:00 |  | 07 84 43-008-00 PCI Material Submittal 07 84 43 Joint Firestopping - LEED_MAM Review_POP.pdf
07 84 43-012-00 | 07 84 43 - JOINT FIRESTOPPING | 07 84 43-012-00 JOINT FIRESTOPPING - Product Data_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-18 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13033 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-05-25 | Submittal Number: 07 84 43-12.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: JOINT FIRESTOPPING - PRODUCT DATA_PCI Description: Spec Section: 07 84 43 - JOINT FIRESTOPPING Status: OPEN | Info Exchange
| 16866 | Forwarded | For Review | 2021-05-11 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 07 84 43-12.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: JOINT FIRESTOPPING - PRODUCT DATA_PCI Description: Spec Section: 07 84 43 - JOINT FIRESTOPPING Status: OPEN | Info Exchange
| 17033 | Responded and Closed | Approved | 2021-05-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | Submittal 07 84 43-12 Revision 0 JOINT FIRESTOPPING - Product Data_PCI_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-10 |  | Submittal 07 84 43-12 Revision 0 JOINT FIRESTOPPING - Product Data_PCI_MAM Reviewed.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-05-18 |  | Submittal 07 84 43-12 Revision 0 JOINT FIRESTOPPING - Product Data_PCI_MAM Reviewed-POP.pdf
07 92 00-001-00 | 07 92 00 - JOINT SEALANTS | 07 92 00-001-00 JOINT SEALANTS - Product Data (MISSION GLASS) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-26 07:00 | 2020-06-09 | 30 |  | Record Copies; Transfers; Submittals | 07 92 00-001-00-01 - 07 92 00-001-00 JOINT SEALANTS - Product Data (MISSION GLASS) | 30 |  | 2020-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05797 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Brooke Burcham (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 07 92 00-1.0 From: BROOKE BURCHAM Final Due Date: 05/25/20 Subject: JOINT SEALANTS - PRODUCT DATA (MISSION GLASS) Description: FOR CURTAIN WALL AND ALUMINUM STORE FRONTS. PRODUCT DATA : FOR EACH JOINT-SEALANT PRODUCT. Spec Section: 07 92 00 - JOINT SEALANTS Status: OPEN | Info Exchange
| 07860 | Forwarded | For Review | 2020-05-11 | Brooke Burcham (M.A. Mortenson Company) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-18 | Submittal Number: 07 92 00-1.0 From: BROOKE BURCHAM Final Due Date: 05/25/20 Subject: JOINT SEALANTS - PRODUCT DATA (MISSION GLASS) Description: FOR CURTAIN WALL AND ALUMINUM STORE FRONTS. PRODUCT DATA : FOR EACH JOINT-SEALANT PRODUCT. Spec Section: 07 92 00 - JOINT SEALANTS Status: OPEN | Info Exchange
| 08500 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-09 | Brooke Burcham (M.A. Mortenson Company) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 079200-0001-0 Joint Sealant - Curtianwall and Storefronts.pdf
| Forwarded |  | Brooke Burcham (Mortenson Construction) | 1 | 2020-05-11 |  | 079200-0001-0 Joint Sealant - Curtianwall and Storefronts.pdf
| Responded and Closed |  | Brooke Burcham (Mortenson Construction) | 1 | 2020-05-11 |  | 079200-0001-0 Joint Sealant - Curtianwall and Storefronts.pdf
07 92 00-001-00-01 | 07 92 00 - JOINT SEALANTS | 07 92 00-001-00 JOINT SEALANTS - Product Data (MISSION GLASS) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 92 00-001-00 - 07 92 00-001-00 JOINT SEALANTS - Product Data (MISSION GLASS) | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 079200-0001-0 Joint Sealant - Curtianwall and Storefronts.pdf
07 92 00-009-00 | 07 92 00 - JOINT SEALANTS | 07 92 00-009-00: South Parcel - Slab on Grade Joint Sealant Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-19 | Responded and Closed - Approved |  | Tom Usher (Populous) |  |  |  | 2021-03-05 | 2021-02-24 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11532 | Received | For Review | 2021-02-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-05 | Submittal Number: 07 92 00-9.0 From: CHRISTIAN GENEROSA Final Due Date: 03/19/21 Subject: SOUTH PARCEL - SLAB ON GRADE JOINT SEALANT PRODUCT DATA Description: PRODUCT DATA SUBMITTAL FOR THE JOINT SEALANT PROSED TO USE FOR THE SOG JOINTS. THIS WOULD BE INSTALLED IN THE SAW CUT JOINTS AS WELL AS OVER THE TOP OF THE PRE-MOLDED JOINT FILLER. Spec Section: 07 92 00 - JOINT SEALANTS Status: OPEN | Info Exchange
| 14947 | Forwarded | For Review | 2021-02-19 | Josh Dobken (Populous) | Tom Usher (Populous) | 2021-02-26 | Submittal Number: 07 92 00-9.0 From: CHRISTIAN GENEROSA Final Due Date: 03/19/21 Subject: SOUTH PARCEL - SLAB ON GRADE JOINT SEALANT PRODUCT DATA Description: PRODUCT DATA SUBMITTAL FOR THE JOINT SEALANT PROSED TO USE FOR THE SOG JOINTS. THIS WOULD BE INSTALLED IN THE SAW CUT JOINTS AS WELL AS OVER THE TOP OF THE PRE-MOLDED JOINT FILLER. Spec Section: 07 92 00 - JOINT SEALANTS Status: OPEN | Info Exchange
| 15056 | Responded and Closed | Approved | 2021-02-24 | Tom Usher (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-18 02:00 |  | 2021-02-18 079200-0009-00 SOG Joint Sealant PD_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-18 02:00 |  | 2021-02-18 079200-0009-00 SOG Joint Sealant PD_MAM.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2021-02-24 |  | 2021-02-18 079200-0009-00 SOG Joint Sealant PD_MAM_POP.pdf
07 92 00-010-00 | 07 92 00 - JOINT SEALANTS | 07 92 00-010-00 Concrete Joint Sealant for South Parcel Decline Paving Joints | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Closed - Void |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 |  | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-05-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13041 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Generosa | 2021-05-25 | Submittal Number: 07 92 00-10.0 From: CHRISTIAN GENEROSA Final Due Date: 05/25/21 Subject: CONCRETE JOINT SEALANT FOR SOUTH PARCEL DECLINE PAVING JOINTS Description: CONCRETE JOINT SEALANT FOR SOUTH PARCEL DECLINE PAVING JOINTS Spec Section: 07 92 00 - JOINT SEALANTS Status: OPEN | Info Exchange
| 16873 | Forwarded | For Review | 2021-05-11 | Christian Generosa | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-18 | Submittal Number: 07 92 00-10.0 From: CHRISTIAN GENEROSA Final Due Date: 05/25/21 Subject: CONCRETE JOINT SEALANT FOR SOUTH PARCEL DECLINE PAVING JOINTS Description: CONCRETE JOINT SEALANT FOR SOUTH PARCEL DECLINE PAVING JOINTS Spec Section: 07 92 00 - JOINT SEALANTS Status: OPEN | Info Exchange
| 16881 | Closed | Void | 2021-05-11 | Josh Dobken (Populous) |  |  | Voided per 05/11/21 Document Control Notes
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | 2021-05-11 079200-0010-00 Concrete Joint Sealant SP_MAM.pdf
| Forwarded |  | Christian Generosa | 1 | 2021-05-11 |  | 2021-05-11 079200-0010-00 Concrete Joint Sealant SP_MAM.pdf
07 95 00-001-00 | 07 95 00 - EXPANSION CONTROL | 07 95 00-001-00 EXPANSION CONTROL - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Revise and Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-11-23 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-11-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09573 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-07 | Submittal Number: 07 95 00-1.0 From: BROOKE BURCHAM Final Due Date: 12/07/20 Subject: EXPANSION CONTROL - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH EXPANSION CONTROL SYSTEM SPECIFIED. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, SPLICES, BLOCKOUT REQUIREMENT, ATTACHMENTS TO OTHER WORK, AND LINE DIAGRAMS SHOWING ENTIRE ROUTE OF EACH EXPANSION CONTROL SYSTEM. WHERE EXPANSION CONTROL SYSTEMS CHANGE PLANES, PROVIDE ISOMETRIC OR CLEARLY DETAILED DRAWING DEPICTING HOW COMPONENTS INTERCONNECT. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 12602 | Forwarded | For Review | 2020-11-19 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 07 95 00-1.0 From: BROOKE BURCHAM Final Due Date: 12/07/20 Subject: EXPANSION CONTROL - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH EXPANSION CONTROL SYSTEM SPECIFIED. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, SPLICES, BLOCKOUT REQUIREMENT, ATTACHMENTS TO OTHER WORK, AND LINE DIAGRAMS SHOWING ENTIRE ROUTE OF EACH EXPANSION CONTROL SYSTEM. WHERE EXPANSION CONTROL SYSTEMS CHANGE PLANES, PROVIDE ISOMETRIC OR CLEARLY DETAILED DRAWING DEPICTING HOW COMPONENTS INTERCONNECT. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 12745 | Responded and Closed | Revise and Resubmit | 2020-11-23 | Populous SCA_CCA | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 07 95 00-0001-0 Expansion Control - Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-18 |  | 07 95 00-0001-0 Expansion Control - Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-23 |  | 07 95 00-0001-0 Expansion Control - Shop Drawings_POP.pdf
07 95 00-001-01 | 07 95 00 - EXPANSION CONTROL | 07 95 00-001-01 EXPANSION CONTROL - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-01 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-15 | 2021-02-16 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-02-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11074 | Received | For Review | 2021-02-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2021-02-15 | Submittal Number: 07 95 00-1.1 From: BROOKE BURCHAM Final Due Date: 02/15/21 Subject: EXPANSION CONTROL - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH EXPANSION CONTROL SYSTEM SPECIFIED. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, SPLICES, BLOCKOUT REQUIREMENT, ATTACHMENTS TO OTHER WORK, AND LINE DIAGRAMS SHOWING ENTIRE ROUTE OF EACH EXPANSION CONTROL SYSTEM. WHERE EXPANSION CONTROL SYSTEMS CHANGE PLANES, PROVIDE ISOMETRIC OR CLEARLY DETAILED DRAWING DEPICTING HOW COMPONENTS INTERCONNECT. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 14372 | Forwarded | For Review | 2021-02-01 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-08 | Submittal Number: 07 95 00-1.1 From: BROOKE BURCHAM Final Due Date: 02/15/21 Subject: EXPANSION CONTROL - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH EXPANSION CONTROL SYSTEM SPECIFIED. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, SPLICES, BLOCKOUT REQUIREMENT, ATTACHMENTS TO OTHER WORK, AND LINE DIAGRAMS SHOWING ENTIRE ROUTE OF EACH EXPANSION CONTROL SYSTEM. WHERE EXPANSION CONTROL SYSTEMS CHANGE PLANES, PROVIDE ISOMETRIC OR CLEARLY DETAILED DRAWING DEPICTING HOW COMPONENTS INTERCONNECT. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 14842 | Responded and Closed | Approved as Noted | 2021-02-16 | Todd Spangler (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-29 |  | 07 95 00-0001-1 Expansion Control - UC Y-Columns Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-29 |  | 07 95 00-0001-1 Expansion Control - UC Y-Columns Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-16 |  | 07 95 00-0001-1 Expansion Control - UC Y-Columns Shop Drawings_POP.pdf
07 95 00-002-00 | 07 95 00 - EXPANSION CONTROL | 07 95 00-002-00 EXPANSION CONTROL - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-12-08 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-12-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09572 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-12-07 | Submittal Number: 07 95 00-2.0 From: BROOKE BURCHAM Final Due Date: 12/07/20 Subject: EXPANSION CONTROL - SAMPLES Description: SAMPLES FOR INITIAL SELECTION : FOR EACH TYPE OF EXPANSION CONTROL SYSTEM INDICATED. 1. INCLUDE MANUFACTURER'S COLOR CHARTS SHOWING THE FULL RANGE OF COLORS AND FINISHES AVAILABLE FOR EACH EXPOSED METAL AND ELASTOMERIC SEAL MATERIAL. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 12601 | Forwarded | For Review | 2020-11-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 07 95 00-2.0 From: BROOKE BURCHAM Final Due Date: 12/07/20 Subject: EXPANSION CONTROL - SAMPLES Description: SAMPLES FOR INITIAL SELECTION : FOR EACH TYPE OF EXPANSION CONTROL SYSTEM INDICATED. 1. INCLUDE MANUFACTURER'S COLOR CHARTS SHOWING THE FULL RANGE OF COLORS AND FINISHES AVAILABLE FOR EACH EXPOSED METAL AND ELASTOMERIC SEAL MATERIAL. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 13098 | Responded and Closed | Approved as Noted | 2020-12-08 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 07 95 00-0002-0 Expansion Control Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 07 95 00-0002-0 Expansion Control Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-08 |  | 07 95 00-0002-0 Expansion Control Samples_POP.pdf
07 95 00-003-00 | 07 95 00 - EXPANSION CONTROL | 07 95 00-003-00 EXPANSION CONTROL - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-17 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-01 | 2020-10-08 | 22 |  | Record Copies; Transfers; Submittals | 07 95 00-003-00-01 - 07 95 00-003-00 EXPANSION CONTROL - Product Data | 22 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08164 | Received | For Review | 2020-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-01 | Submittal Number: 07 95 00-3.0 From: BROOKE BURCHAM Final Due Date: 09/03/20 Subject: EXPANSION CONTROL - PRODUCT DATA Description: PRODUCT DATA INCLUDING TEST REPORTS, LEED INFORMATION, PRODUCT INFORMATION Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 10838 | Forwarded | For Review | 2020-09-17 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-24 | Submittal Number: 07 95 00-3.0 From: BROOKE BURCHAM Final Due Date: 09/03/20 Subject: EXPANSION CONTROL - PRODUCT DATA Description: PRODUCT DATA INCLUDING TEST REPORTS, LEED INFORMATION, PRODUCT INFORMATION Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 11406 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-08 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. Submit LEED date per DIV 1. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-16 |  | 07 95 00-0003-0 Expansion Control Product Data (Mort Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-16 |  | 07 95 00-0003-0 Expansion Control Product Data (Mort Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-08 |  | 07 95 00-0003-0 Expansion Control Product Data-MAM_POP.pdf
07 95 00-003-00-01 | 07 95 00 - EXPANSION CONTROL | 07 95 00-003-00 EXPANSION CONTROL - Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 95 00-003-00 - 07 95 00-003-00 EXPANSION CONTROL - Product Data | -1 | 2020-10-22
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-08 |  | 07 95 00-0003-0 Expansion Control Product Data-MAM_POP.pdf
07 95 00-006-00 | 07 95 00 - EXPANSION CONTROL | 07 95 00-006-00 Expansion Control Product Data for Expansion Joints at Insulated Metal Panels | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-28 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-11 | 2020-11-09 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09063 | Received | For Review | 2020-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-11-11 | Submittal Number: 07 95 00-6.0 From: CHRISTIAN GENEROSA Final Due Date: 11/10/20 Subject: EXPANSION CONTROL PRODUCT DATA FOR EXPANSION JOINTS AT INSULATED METAL PANELS Description: EMSEAL EXPANSION JOINT PRODUCT DATA. THESE EXPANSION JOINTS OCCUR AT SECTIONS WITH INSULATED METAL PANELS. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 11951 | Forwarded | For Review | 2020-10-28 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-04 | Submittal Number: 07 95 00-6.0 From: CHRISTIAN GENEROSA Final Due Date: 11/10/20 Subject: EXPANSION CONTROL PRODUCT DATA FOR EXPANSION JOINTS AT INSULATED METAL PANELS Description: EMSEAL EXPANSION JOINT PRODUCT DATA. THESE EXPANSION JOINTS OCCUR AT SECTIONS WITH INSULATED METAL PANELS. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 12266 | Responded and Closed | Approved as Noted | 2020-11-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 2020-10-21 079500-0006 Expansion Control Product Data At IMP.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-27 |  | 2020-10-21 079500-0006 Expansion Control Product Data At IMP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-09 |  | 07 95 00-0006 Expansion Control Product Data At IMP_POP.pdf
07 95 00-007-00 | 07 95 00 - EXPANSION CONTROL | 07 95 00-007-00 Expansion Control - Mech Mezz Slab to Wall DFR2 Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Chris Minter (Populous) |  |  |  | 2021-01-12 | 2021-01-21 | 35 |  | Record Copies; Transfers; Submittals |  | 35 |  | 2021-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10258 | Received | For Review | 2020-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2021-01-12 | Submittal Number: 07 95 00-7.0 From: BROOKE BURCHAM Final Due Date: 01/12/21 Subject: EXPANSION CONTROL - MECH MEZZ SLAB TO WALL DFR2 SHOP DRAWINGS Description: MECH MEZZ LEVEL - DFR2 SLAB TO WALL EXPANSION JOINT. NO COVER PLATES WITH THIS EXPANSION JOINT. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 13413 | Forwarded | For Review | 2020-12-18 | Josh Dobken (Populous) | Todd Spangler (Populous); Chris Minter (Populous) | 2020-12-25 | Submittal Number: 07 95 00-7.0 From: BROOKE BURCHAM Final Due Date: 01/12/21 Subject: EXPANSION CONTROL - MECH MEZZ SLAB TO WALL DFR2 SHOP DRAWINGS Description: MECH MEZZ LEVEL - DFR2 SLAB TO WALL EXPANSION JOINT. NO COVER PLATES WITH THIS EXPANSION JOINT. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 14131 | Responded and Closed | Approved | 2021-01-21 | Todd Spangler (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-18 02:00 |  | 07 95 00-0007-0 Mech Mezz DFR2 SD.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-12-18 02:00 |  | 07 95 00-0007-0 Mech Mezz DFR2 SD.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-01-21 |  | 07 95 00-0007-0 Mech Mezz DFR2 SD_POP.pdf
07 95 00-008-00 | 07 95 00 - EXPANSION CONTROL | 07 95 00-008-00 Expansion Control - Suite Level Y-Column - BASF - UniPro | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-22 08:00 | 2021-01-21 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10496 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2021-01-22 08:00 | Submittal Number: 07 95 00-8.0 From: BROOKE BURCHAM Final Due Date: 01/21/21 Subject: EXPANSION CONTROL - SUITE LEVEL Y-COLUMN - BASF - UNIPRO Description: PRODUCT DATA, LOCATION AND SHOP DRAWINGS Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 13699 | Forwarded | For Review | 2021-01-06 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-13 | Submittal Number: 07 95 00-8.0 From: BROOKE BURCHAM Final Due Date: 01/21/21 Subject: EXPANSION CONTROL - SUITE LEVEL Y-COLUMN - BASF - UNIPRO Description: PRODUCT DATA, LOCATION AND SHOP DRAWINGS Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 14132 | Responded and Closed | Approved as Noted | 2021-01-21 | Todd Spangler (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-06 |  | 07 95 00-0008-0 Suite Level Y-Col - BASF PD_SD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-06 |  | 07 95 00-0008-0 Suite Level Y-Col - BASF PD_SD.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-01-21 |  | 07 95 00-0008-0 Suite Level Y-Col - BASF PD_SD_POP.pdf
07 95 00-009-00 | 07 95 00 - EXPANSION CONTROL | 07 95 00-009-00 Expansion Control - Mech Mezz Wall to Wall SJS-FR2 Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-13 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-28 08:00 | 2021-01-21 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10677 | Received | For Review | 2021-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2021-01-28 08:00 | Submittal Number: 07 95 00-9.0 From: BROOKE BURCHAM Final Due Date: 01/27/21 Subject: EXPANSION CONTROL - MECH MEZZ WALL TO WALL SJS-FR2 SHOP DRAWINGS Description: Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 13896 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-20 | Submittal Number: 07 95 00-9.0 From: BROOKE BURCHAM Final Due Date: 01/27/21 Subject: EXPANSION CONTROL - MECH MEZZ WALL TO WALL SJS-FR2 SHOP DRAWINGS Description: Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 14130 | Responded and Closed | Approved | 2021-01-21 | Todd Spangler (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 07 95 00-0009-0 Mech Mezz SJS-FR SD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 07 95 00-0009-0 Mech Mezz SJS-FR SD.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-01-21 |  | 07 95 00-0009-0 Mech Mezz SJS-FR SD_POP.pdf
07 95 00-010-00 | 07 95 00 - EXPANSION CONTROL | 07 95 00-010-00 Expansion Control - Upper Concourse Stadia Ramp Horizontal and Vertical Joints | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-17 | 2021-05-17 | 15 |  | Record Copies; Transfers; Submittals | 07 95 00-010-00-01 - 07 95 00-010-00 Expansion Control - Upper Concourse Stadia Ramp Horizontal and Vertical Joints | 17 |  | 2021-05-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12884 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-17 | Submittal Number: 07 95 00-10.0 From: BROOKE BURCHAM Final Due Date: 05/14/21 Subject: EXPANSION CONTROL - UPPER CONCOURSE STADIA RAMP HORIZONTAL AND VERTICAL JOINTS Description: UPPER CONCOURSE PRECAST RAMP EXPANSION CONTROL. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 16666 | Forwarded | For Review | 2021-05-01 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-10 | Submittal Number: 07 95 00-10.0 From: BROOKE BURCHAM Final Due Date: 05/14/21 Subject: EXPANSION CONTROL - UPPER CONCOURSE STADIA RAMP HORIZONTAL AND VERTICAL JOINTS Description: UPPER CONCOURSE PRECAST RAMP EXPANSION CONTROL. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 16669 | Forwarded | For Review | 2021-05-02 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-10 | Submittal Number: 07 95 00-10.0 From: BROOKE BURCHAM Final Due Date: 05/14/21 Subject: EXPANSION CONTROL - UPPER CONCOURSE STADIA RAMP HORIZONTAL AND VERTICAL JOINTS Description: UPPER CONCOURSE PRECAST RAMP EXPANSION CONTROL. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 16755 | Forwarded | For Review | 2021-05-05 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-12 | Submittal Number: 07 95 00-10.0 From: BROOKE BURCHAM Final Due Date: 05/14/21 Subject: EXPANSION CONTROL - UPPER CONCOURSE STADIA RAMP HORIZONTAL AND VERTICAL JOINTS Description: UPPER CONCOURSE PRECAST RAMP EXPANSION CONTROL. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 16968 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-30 |  | 07 95 00-0010-0 Expansion Control - UC Stadia Ramp Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-30 |  | 07 95 00-0010-0 Expansion Control - UC Stadia Ramp Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-30 |  | 07 95 00-0010-0 Expansion Control - UC Stadia Ramp Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-30 |  | 07 95 00-0010-0 Expansion Control - UC Stadia Ramp Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-17 |  | 07 95 00-0010-0 Expansion Control - UC Stadia Ramp Shop Drawings_POP.pdf
07 95 00-010-00-01 | 07 95 00 - EXPANSION CONTROL | 07 95 00-010-00 Expansion Control - Upper Concourse Stadia Ramp Horizontal and Vertical Joints | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 07 95 00-010-00 - 07 95 00-010-00 Expansion Control - Upper Concourse Stadia Ramp Horizontal and Vertical Joints | -1 | 2021-05-31
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | 07 95 00-0010-0 Expansion Control - UC Stadia Ramp Shop Drawings_POP.pdf
07 95 00-011-00 | 07 95 00 - EXPANSION CONTROL | 07 95 00-011-00 South Buttress Expansion Control Joint Sealant | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-17 | 2021-05-18 | 16 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12879 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-17 | Submittal Number: 07 95 00-11.0 From: BROOKE BURCHAM Final Due Date: 05/17/21 Subject: SOUTH BUTTRESS EXPANSION CONTROL JOINT SEALANT Description: Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 16661 | Forwarded | For Review | 2021-04-30 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-07 | Submittal Number: 07 95 00-11.0 From: BROOKE BURCHAM Final Due Date: 05/17/21 Subject: SOUTH BUTTRESS EXPANSION CONTROL JOINT SEALANT Description: Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 17032 | Responded and Closed | Approved as Noted | 2021-05-18 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-30 |  | 07 95 00-0011-0 Expansion Control - South Buttress Expansion Control Joint Sealant.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-30 |  | 07 95 00-0011-0 Expansion Control - South Buttress Expansion Control Joint Sealant.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-18 |  | 07 95 00-0011-0 Expansion Control - South Buttress Expansion Control Joint Sealant-POP.pdf
07 95 00-012-00 | 07 95 00 - EXPANSION CONTROL | 07 95 00-012-00 Expansion Control - Situra Redline - Y-13 Product Data and Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-02 | 2021-07-15 | 28 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2021-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13571 | Received | For Review | 2021-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Brooke Burcham (Mortenson Construction) | 2021-07-02 | Submittal Number: 07 95 00-12.0 From: BROOKE BURCHAM Final Due Date: 07/02/21 Subject: EXPANSION CONTROL - SITURA REDLINE - Y-13 PRODUCT DATA AND SHOP DRAWINGS Description: PRODUCT DATA AND SHOP DRAWINGS FOR THE SITURA REDLINE PRODUCT. THIS DOES NOT CHANGE THE EXPANSION MATERIAL IN THE JOINT BUT GIVES A COMPLETE WATERTIGHT SYSTEM FOR THE HRA TO TIE INTO. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 17574 | Forwarded | For Review | 2021-06-18 | Brooke Burcham (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-25 | Submittal Number: 07 95 00-12.0 From: BROOKE BURCHAM Final Due Date: 07/02/21 Subject: EXPANSION CONTROL - SITURA REDLINE - Y-13 PRODUCT DATA AND SHOP DRAWINGS Description: PRODUCT DATA AND SHOP DRAWINGS FOR THE SITURA REDLINE PRODUCT. THIS DOES NOT CHANGE THE EXPANSION MATERIAL IN THE JOINT BUT GIVES A COMPLETE WATERTIGHT SYSTEM FOR THE HRA TO TIE INTO. Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 18064 | Responded and Closed | Approved | 2021-07-15 | Brooke Burcham (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-17 |  | 07 95 00-0012-0 Expansion Control - Y-13 Redline PD and SD.pdf
| Forwarded |  | Brooke Burcham (Mortenson Construction) | 1 | 2021-06-17 |  | 07 95 00-0012-0 Expansion Control - Y-13 Redline PD and SD.pdf
| Responded and Closed |  | Brooke Burcham (Mortenson Construction) | 1 | 2021-07-15 |  | 07 95 00-0012-0 Expansion Control - Y-13 Redline PD and SD_POP.pdf
07 95 00-013-00 | 07 95 00 - EXPANSION CONTROL | 07 95 00-013-00 (UniPro) Silicone Sealant Product Data and Color Chart for South Buttress Edges on Upper Con and Top of Concrete Y-Columns. | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-09 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-23 | 2021-09-03 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2021-09-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14259 | Received | For Review | 2021-08-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-08-23 | Submittal Number: 07 95 00-13.0 From: CHRISTIAN GENEROSA Final Due Date: 08/23/21 Subject: (UNIPRO) SILICONE SEALANT PRODUCT DATA AND COLOR CHART FOR SOUTH BUTTRESS EDGES ON UPPER CON AND TOP OF CONCRETE Y-COLUMNS. Description: Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 18421 | Forwarded | For Review | 2021-08-09 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-16 | Submittal Number: 07 95 00-13.0 From: CHRISTIAN GENEROSA Final Due Date: 08/23/21 Subject: (UNIPRO) SILICONE SEALANT PRODUCT DATA AND COLOR CHART FOR SOUTH BUTTRESS EDGES ON UPPER CON AND TOP OF CONCRETE Y-COLUMNS. Description: Spec Section: 07 95 00 - EXPANSION CONTROL Status: OPEN | Info Exchange
| 18784 | Responded and Closed | Approved as Noted | 2021-09-03 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-09 |  | 079500-0013-00 UniPro Silicone Sealant Product Data and Color Chart_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-09 |  | 079500-0013-00 UniPro Silicone Sealant Product Data and Color Chart_MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-09-03 |  | 079500-0013-00 UniPro Silicone Sealant Product Data and Color Chart_MAM_POP.pdf
08 03 51.23-001-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-001-00 Historic Curtain Wall Labeling for Disassembly | Closed | Architectural | Brooke Burcham (Mortenson Construction) | 2019-04-04 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-04-18 | 2019-04-09 | 6 |  | Record Copies; Transfers; Submittals | 08 03 51.23-001-01 - 08 03 51.23-001-01 Historic Curtain Wall Labeling for Disassembly | 6 |  | 2019-04-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01125 | Received | For Review | 2019-04-04 | Brooke Burcham (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-18 |  | Email
| 01998 | Forwarded | For Review | 2019-04-04 | SCA_CCA@populous.com | Kelsea Conkright (Populous); Todd Spangler (Populous); Chris Minter (Populous); Josh Dobken (Populous) |  |  | Info Exchange
| 02032 | Responded and Closed | Revise and Resubmit | 2019-04-09 | SCA_CCA@populous.com | Brooke Burcham (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-04-04 |  | 08 03 51.23-001-0 Historic Curtain Wall Labeling for Disassembly.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-04 |  | 08 03 51.23-001-0 Historic Curtain Wall Labeling for Disassembly.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-09 |  | 08 03 51.23-001-0 Historic Curtain Wall Labeling for Disassembly_POP.pdf
08 03 51.23-001-01 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-001-01 Historic Curtain Wall Labeling for Disassembly | Expected - Overdue | Architectural | Brooke Burcham (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 03 51.23-001-00 - 08 03 51.23-001-00 Historic Curtain Wall Labeling for Disassembly | -1 | 2019-05-28
08 03 51.23-002-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-002-00 Historic Curtainwall Mockup - Details | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-31 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-08-14 | 2019-08-16 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2019-08-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01920 | Received | For Review | 2019-07-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Brooke Burcham (Mortenson Construction); . (Seattle Arena Company, LLC); Tyler Kren (Mortenson Construction) | 2019-08-14 | Submittal Number: 08 03 51.23-2.0 From: BROOKE BURCHAM Final Due Date: 08/14/19 Subject: HISTORIC CURTAINWALL MOCKUP - DETAILS Description: MOCKUPS : PREPARE MOCKUP OF HISTORIC TREATMENT REPAIR PROCESSES TO DEMONSTRATE AESTHETIC EFFECTS AND TO SET QUALITY STANDARDS FOR MATERIALS AND EXECUTION, AND FOR FABRICATION AND INSTALLATION. 1. LOCATE MOCKUPS IN LOCATIONS THAT ENABLE VIEWING UNDER SAME CONDITIONS AS THE COMPLETED WORK. 2. STEEL CURTAIN WALL REFURBISH AND REINSTALLATION: PREPARE ONE FULL HEIGHT BY 20 FEET WIDE BAY. 3. MOCK-UP SHALL INCLUDE PORTION OF WORK THAT WILL REMAIN IN PLACE. 4. APPROVAL OF MOCKUPS DOES NOT CONSTITUTE APPROVAL OF DEVIATIONS FROM THE CONTRACT DOCUMENTS CONTAINED IN MOCKUPS UNLESS ARCHITECT SPECIFICALLY APPROVES SUCH DEVIATIONS IN WRITING. 5. SUBJECT TO COMPLIANCE WITH REQUIREMENTS, APPROVED MOCKUPS MAY BECOME PART OF THE COMPLETED WORK IF UNDISTURBED AT TIME OF SUBSTANTIAL COMPLETION. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 03066 | Forwarded | For Review | 2019-07-31 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-08-07 | Submittal Number: 08 03 51.23-2.0 From: BROOKE BURCHAM Final Due Date: 08/14/19 Subject: HISTORIC CURTAINWALL MOCKUP - DETAILS Description: MOCKUPS : PREPARE MOCKUP OF HISTORIC TREATMENT REPAIR PROCESSES TO DEMONSTRATE AESTHETIC EFFECTS AND TO SET QUALITY STANDARDS FOR MATERIALS AND EXECUTION, AND FOR FABRICATION AND INSTALLATION. 1. LOCATE MOCKUPS IN LOCATIONS THAT ENABLE VIEWING UNDER SAME CONDITIONS AS THE COMPLETED WORK. 2. STEEL CURTAIN WALL REFURBISH AND REINSTALLATION: PREPARE ONE FULL HEIGHT BY 20 FEET WIDE BAY. 3. MOCK-UP SHALL INCLUDE PORTION OF WORK THAT WILL REMAIN IN PLACE. 4. APPROVAL OF MOCKUPS DOES NOT CONSTITUTE APPROVAL OF DEVIATIONS FROM THE CONTRACT DOCUMENTS CONTAINED IN MOCKUPS UNLESS ARCHITECT SPECIFICALLY APPROVES SUCH DEVIATIONS IN WRITING. 5. SUBJECT TO COMPLIANCE WITH REQUIREMENTS, APPROVED MOCKUPS MAY BECOME PART OF THE COMPLETED WORK IF UNDISTURBED AT TIME OF SUBSTANTIAL COMPLETION. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 03272 | Responded and Closed | Approved as Noted | 2019-08-16 | Todd Spangler (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-30 |  | 080351.23-0002-0 Historic Curtainwall Mockup.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-31 |  | 080351.23-002-0 Historic Curtainwall Mockup.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-16 |  | 080351.23-002-0 Historic Curtainwall Mockup_POP.pdf
08 03 51.23-003-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-003-00 HISTORIC TREATMENT OF CW - Mock Up Paint | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-28 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-12 07:00 | 2019-09-18 | 22 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2019-09-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02215 | Received | For Review | 2019-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2019-09-12 07:00 | Submittal Number: 08 03 51.23-3.0 From: BROOKE BURCHAM Final Due Date: 09/10/19 Subject: HISTORIC TREATMENT OF CW - MOCK UP PAINT Description: PAINTING PRODUCT DATA FOR THE HISTORIC CURTAINWALL MOCK UP. PPG IS ADDED IN THIS SUBMITTAL PER CAAICON'S REQUEST. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 03423 | Forwarded | For Review | 2019-08-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-09-03 | Submittal Number: 08 03 51.23-3.0 From: BROOKE BURCHAM Final Due Date: 09/10/19 Subject: HISTORIC TREATMENT OF CW - MOCK UP PAINT Description: PAINTING PRODUCT DATA FOR THE HISTORIC CURTAINWALL MOCK UP. PPG IS ADDED IN THIS SUBMITTAL PER CAAICON'S REQUEST. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 03722 | Responded and Closed | Approved as Noted | 2019-09-18 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attachment of approval for Tnemec paint product. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-27 |  | 080351.23-0003-0 HCW Mock-up - Paint Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-27 |  | 080351.23-003-0 HCW Mock-up - Paint Product Data.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-09-18 |  | 080351.23-003-0 HCW Mock-up - Paint Product Data - POP.pdf
08 03 51.23-004-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-004-00 HISTORIC TREATMENT OF CURTAIN WALLS - Mock Up Paint Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-29 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-09-13 07:00 | 2019-09-11 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-09-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02247 | Received | For Review | 2019-08-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2019-09-13 07:00 | Submittal Number: 08 03 51.23-4.0 From: BROOKE BURCHAM Final Due Date: 09/26/19 Subject: HISTORIC TREATMENT OF CURTAIN WALLS - MOCK UP PAINT SAMPLES Description: PAINT SAMPLES FOR THE MOCK UP. THESE ARE BEING MAILED VIA UPS ON 08/29/19. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 03467 | Forwarded | For Review | 2019-08-29 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-09-05 | Submittal Number: 08 03 51.23-4.0 From: BROOKE BURCHAM Final Due Date: 09/26/19 Subject: HISTORIC TREATMENT OF CURTAIN WALLS - MOCK UP PAINT SAMPLES Description: PAINT SAMPLES FOR THE MOCK UP. THESE ARE BEING MAILED VIA UPS ON 08/29/19. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 03626 | Responded and Closed | Approved as Noted | 2019-09-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-29 |  | 080351.23-0004-0 HCW Mock Up - Paint Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-29 |  | 080351.23-0004-0 HCW Mock Up - Paint Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-09-11 |  | 080351.23-0004-0 HCW Mock Up - Paint Samples_POP.pdf
08 03 51.23-005-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-005-00 HISTORIC TREATMENT OF CURTAIN WALLS - MOCK UP JOINT SEALANT | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-19 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-10-03 | 2019-09-24 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2019-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02456 | Received | For Review | 2019-09-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Brooke Burcham (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-10-03 | Submittal Number: 08 03 51.23-5.0 From: BROOKE BURCHAM Final Due Date: 10/03/19 Subject: HISTORIC TREATMENT OF CURTAIN WALLS - MOCK UP JOINT SEALANT Description: PRODUCT DATA FOR A PAINTABLE SEALANT FOR THE MOCK UP. THIS IS FOR APPROVAL OF THE MOCK UP ONLY. A FULL SUBMITTAL FOR THE REINSTALLATION WILL BE SENT AT A LATE DATE. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 03726 | Forwarded | For Review | 2019-09-19 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-09-26 | Submittal Number: 08 03 51.23-5.0 From: BROOKE BURCHAM Final Due Date: 10/03/19 Subject: HISTORIC TREATMENT OF CURTAIN WALLS - MOCK UP JOINT SEALANT Description: PRODUCT DATA FOR A PAINTABLE SEALANT FOR THE MOCK UP. THIS IS FOR APPROVAL OF THE MOCK UP ONLY. A FULL SUBMITTAL FOR THE REINSTALLATION WILL BE SENT AT A LATE DATE. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 03779 | Responded and Closed | Approved as Noted | 2019-09-24 | Todd Spangler (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Winston Williams (Mortenson Construction) |  | See attached. Approved as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-19 |  | 080351.23-0005-0 HCW Mock Up - Joint Sealant.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-19 |  | 080351.23-0005-0 HCW Mock Up - Joint Sealant.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-09-24 |  | 080351.23-0005-0 HCW Mock Up - Joint Sealant_GASKETING_POP.pdf
08 03 51.23-005-01 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-005-01 HISTORIC TREATMENT OF CURTAIN WALLS - MOCK UP JOINT SEALANT | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-30 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-10-14 | 2019-09-30 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-09-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02572 | Received | For Review | 2019-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-10-14 | Submittal Number: 08 03 51.23-5.1 From: BROOKE BURCHAM Final Due Date: 10/11/19 Subject: HISTORIC TREATMENT OF CURTAIN WALLS - MOCK UP JOINT SEALANT Description: PRODUCT DATA FOR A PAINTABLE SEALANT FOR THE MOCK UP. THIS IS FOR APPROVAL OF THE MOCK UP ONLY. A FULL SUBMITTAL FOR THE REINSTALLATION WILL BE SENT AT A LATE DATE. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 03859 | Forwarded | For Review | 2019-09-30 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-10-07 | Submittal Number: 08 03 51.23-5.1 From: BROOKE BURCHAM Final Due Date: 10/11/19 Subject: HISTORIC TREATMENT OF CURTAIN WALLS - MOCK UP JOINT SEALANT Description: PRODUCT DATA FOR A PAINTABLE SEALANT FOR THE MOCK UP. THIS IS FOR APPROVAL OF THE MOCK UP ONLY. A FULL SUBMITTAL FOR THE REINSTALLATION WILL BE SENT AT A LATE DATE. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 03862 | Responded and Closed | Approved | 2019-09-30 | Populous SCA_CCA | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See approved joint sealant for mock-up only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-27 |  | 080351.23-0005-1 Mock Up Joint Sealant_Resub.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-27 |  | 080351.23-0005-1 Mock Up Joint Sealant_Resub.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-30 |  | 080351.23-0005-1 Mock Up Joint Sealant_Resub_POP.pdf
08 03 51.23-006-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-006-00 HISTORIC CURTAIN WALLS - Shop Drawings - Corona NORTH ELEVATION ONLY | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-13 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Greg Briggs (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti) |  |  |  | 2020-03-27 | 2020-04-02 | 21 |  | Record Copies; Transfers; Submittals | 08 03 51.23-006-01 - 08 03 51.23-006-00 HISTORIC CURTAIN WALLS - Shop Drawings - Corona NORTH ELEVATION ONLY | 22 |  | 2020-04-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04798 | Received | For Review | 2020-03-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-03-27 | Submittal Number: 08 03 51.23-6.0 From: BROOKE BURCHAM Final Due Date: 03/30/20 Subject: HISTORIC CURTAIN WALLS - SHOP DRAWINGS - CORONA NORTH ELEVATION ONLY Description: SHOP DRAWINGS : INCLUDE PLANS, ELEVATIONS, AND SECTIONS SHOWING LOCATIONS AND EXTENT OF REPAIR AND REPLACEMENT WORK, WITH ENLARGED DETAILS OF REPLACEMENT PARTS INDICATING MATERIALS, PROFILES, CONNECTIONS, REINFORCING, METHOD OF SPLICING INTO OR ATTACHING TO EXISTING STEEL WINDOW, ACCESSORY ITEMS, AND FINISHES. INCLUDE FIELD-VERIFIED DIMENSIONS AND THE FOLLOWING: 1. SCHEDULE REPAIRS, USING SAME REFERENCE NUMBER FOR OPENINGS AS THOSE ON CONTRACT DRAWINGS. 2. SCHEDULE OF WORK TO REMAIN IN PLACE, PROTECTED, REFURBISHED, AND CLEANED AS REQUIRED. 3. FULL-SIZE SHAPES AND PROFILES WITH COMPLETE DIMENSIONS FOR REPLACEMENT COMPONENTS AND THEIR CONNECTIONS, SHOWING RELATIONSHIP OF EXISTING COMPONENTS TO NEW COMPONENTS. 4. DETAILS OF TEMPORARY PROTECTION AND SECURITY AT WINDOW OPENINGS. 5. IDENTIFICATION OF EACH UNIT AND ITS CORRESPONDING WINDOW LOCATIONS IN THE BUILDING ON ANNOTATED PLANS AND ELEVATIONS. 6. HARDWARE SCHEDULE USING SAME REFERENCE NUMBERS FOR OPENINGS. 7. PROVISIONS FOR SEALANT JOINTS AND FLASHING AS REQUIRED FOR LOCATION. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 06575 | Forwarded | For Review | 2020-03-12 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-03-19 | Submittal Number: 08 03 51.23-6.0 From: BROOKE BURCHAM Final Due Date: 03/30/20 Subject: HISTORIC CURTAIN WALLS - SHOP DRAWINGS - CORONA NORTH ELEVATION ONLY Description: SHOP DRAWINGS : INCLUDE PLANS, ELEVATIONS, AND SECTIONS SHOWING LOCATIONS AND EXTENT OF REPAIR AND REPLACEMENT WORK, WITH ENLARGED DETAILS OF REPLACEMENT PARTS INDICATING MATERIALS, PROFILES, CONNECTIONS, REINFORCING, METHOD OF SPLICING INTO OR ATTACHING TO EXISTING STEEL WINDOW, ACCESSORY ITEMS, AND FINISHES. INCLUDE FIELD-VERIFIED DIMENSIONS AND THE FOLLOWING: 1. SCHEDULE REPAIRS, USING SAME REFERENCE NUMBER FOR OPENINGS AS THOSE ON CONTRACT DRAWINGS. 2. SCHEDULE OF WORK TO REMAIN IN PLACE, PROTECTED, REFURBISHED, AND CLEANED AS REQUIRED. 3. FULL-SIZE SHAPES AND PROFILES WITH COMPLETE DIMENSIONS FOR REPLACEMENT COMPONENTS AND THEIR CONNECTIONS, SHOWING RELATIONSHIP OF EXISTING COMPONENTS TO NEW COMPONENTS. 4. DETAILS OF TEMPORARY PROTECTION AND SECURITY AT WINDOW OPENINGS. 5. IDENTIFICATION OF EACH UNIT AND ITS CORRESPONDING WINDOW LOCATIONS IN THE BUILDING ON ANNOTATED PLANS AND ELEVATIONS. 6. HARDWARE SCHEDULE USING SAME REFERENCE NUMBERS FOR OPENINGS. 7. PROVISIONS FOR SEALANT JOINTS AND FLASHING AS REQUIRED FOR LOCATION. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 06666 | Forwarded | For Review | 2020-03-17 | Todd Spangler (Populous) | Greg Briggs (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti) |  | Submittal Number: 08 03 51.23-6.0 From: BROOKE BURCHAM Final Due Date: 03/30/20 Subject: HISTORIC CURTAIN WALLS - SHOP DRAWINGS - CORONA NORTH ELEVATION ONLY Description: SHOP DRAWINGS : INCLUDE PLANS, ELEVATIONS, AND SECTIONS SHOWING LOCATIONS AND EXTENT OF REPAIR AND REPLACEMENT WORK, WITH ENLARGED DETAILS OF REPLACEMENT PARTS INDICATING MATERIALS, PROFILES, CONNECTIONS, REINFORCING, METHOD OF SPLICING INTO OR ATTACHING TO EXISTING STEEL WINDOW, ACCESSORY ITEMS, AND FINISHES. INCLUDE FIELD-VERIFIED DIMENSIONS AND THE FOLLOWING: 1. SCHEDULE REPAIRS, USING SAME REFERENCE NUMBER FOR OPENINGS AS THOSE ON CONTRACT DRAWINGS. 2. SCHEDULE OF WORK TO REMAIN IN PLACE, PROTECTED, REFURBISHED, AND CLEANED AS REQUIRED. 3. FULL-SIZE SHAPES AND PROFILES WITH COMPLETE DIMENSIONS FOR REPLACEMENT COMPONENTS AND THEIR CONNECTIONS, SHOWING RELATIONSHIP OF EXISTING COMPONENTS TO NEW COMPONENTS. 4. DETAILS OF TEMPORARY PROTECTION AND SECURITY AT WINDOW OPENINGS. 5. IDENTIFICATION OF EACH UNIT AND ITS CORRESPONDING WINDOW LOCATIONS IN THE BUILDING ON ANNOTATED PLANS AND ELEVATIONS. 6. HARDWARE SCHEDULE USING SAME REFERENCE NUMBERS FOR OPENINGS. 7. PROVISIONS FOR SEALANT JOINTS AND FLASHING AS REQUIRED FOR LOCATION. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 07020 | Responded and Closed | Revise and Resubmit | 2020-04-01 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | This is an incomplete submittal. As discussed during the page turn review the design team will provide a cursory review through email to be incorporated into the revise and resubmit submittal. | Info Exchange
| 07042 | Reopened | Additional Information | 2020-04-02 09:22 | Josh Dobken (Populous) |  |  | Reopened due to errors responding in Newforma
| 07043 | Responded and Closed | Revise and Resubmit | 2020-04-02 | Todd Spangler (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Responded and Closed (Revise and Resubmit) to: Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: This is an incomplete submittal. As discussed during the page turn review the design team will provide a cursory review through email to be incorporated into the revise and resubmit submittal. Reopened (Additional Information) by: Josh Dobken Remarks: Reopened due to errors responding in Newforma | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-12 |  | 080351.23-0006-0 North Elevation Steel Shops.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-12 |  | 080351.23-0006-0 North Elevation Steel Shops.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-03-12 |  | 080351.23-0006-0 North Elevation Steel Shops.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-12 |  | 080351.23-0006-0 North Elevation Steel Shops.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-02 02:00 |  | 080351.23-0006-0 North Elevation Steel Shops_TT CURSORY REVIEW_POP.pdf
08 03 51.23-006-01 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-006-00 HISTORIC CURTAIN WALLS - Shop Drawings - Corona NORTH ELEVATION ONLY | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 03 51.23-006-00 - 08 03 51.23-006-00 HISTORIC CURTAIN WALLS - Shop Drawings - Corona NORTH ELEVATION ONLY | -1 | 2020-04-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-02 02:00 |  | 080351.23-0006-0 North Elevation Steel Shops_TT CURSORY REVIEW_POP.pdf
08 03 51.23-007-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-007-00 HISTORIC CURTAIN WALLS - Shop Drawings - Goldfinch | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-05 | Responded and Closed - Not Required For Review |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-19 | 2021-02-09 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11237 | Received | For Review | 2021-02-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2021-02-19 | Submittal Number: 08 03 51.23-7.0 From: BROOKE BURCHAM Final Due Date: 02/19/21 Subject: HISTORIC CURTAIN WALLS - SHOP DRAWINGS - GOLDFINCH Description: SHOP DRAWINGS FROM GLAZING COMPANY. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 14551 | Forwarded | For Review | 2021-02-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-12 | Submittal Number: 08 03 51.23-7.0 From: BROOKE BURCHAM Final Due Date: 02/19/21 Subject: HISTORIC CURTAIN WALLS - SHOP DRAWINGS - GOLDFINCH Description: SHOP DRAWINGS FROM GLAZING COMPANY. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 14635 | Responded and Closed | Not Required For Review | 2021-02-09 | Todd Spangler (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-05 |  | 080351.23-0007-0 HCW Glazing Shop Drawing_Updated.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-05 |  | 080351.23-0007-0 HCW Glazing Shop Drawing_Updated.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-09 |  | 080351.23-0007-0 HCW Glazing Shop Drawing_Updated_POP.pdf
08 03 51.23-008-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-008-00 HISTORIC CURTAIN WALLS - Glazing Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-25 | 2020-03-03 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04319 | Received | For Review | 2020-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-02-25 | Submittal Number: 08 03 51.23-8.0 From: BROOKE BURCHAM Final Due Date: 02/25/20 Subject: HISTORIC CURTAIN WALLS - GLAZING PRODUCT DATA Description: PRODUCT DATA FOR ALL GLAZING ITEMS. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 05969 | Forwarded | For Review | 2020-02-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-02-18 | Submittal Number: 08 03 51.23-8.0 From: BROOKE BURCHAM Final Due Date: 02/25/20 Subject: HISTORIC CURTAIN WALLS - GLAZING PRODUCT DATA Description: PRODUCT DATA FOR ALL GLAZING ITEMS. Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 06367 | Responded and Closed | Approved as Noted | 2020-03-03 | Shaina Burris (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-11 |  | 080351.23-0008-0 Glazing Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-11 |  | 080351.23-0008-0 Glazing Product Data.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-03-03 |  | 080351.23-0008-0 Glazing Product Data_POP.pdf
08 03 51.23-010-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-010-00 HISTORIC CURTAIN WALLS - Custom Color Sealant Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-27 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-03-12 | 2020-03-03 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04532 | Received | For Review | 2020-02-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-03-12 | Submittal Number: 08 03 51.23-10.0 From: BROOKE BURCHAM Final Due Date: 03/12/20 Subject: HISTORIC CURTAIN WALLS - CUSTOM COLOR SEALANT SAMPLE Description: CUSTOM COLOR SEALANT SAMPLE. COLOR MATCH BENJAMIN MOORE 2124-10 WROUGHT IRON Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 06239 | Forwarded | For Review | 2020-02-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-03-05 | Submittal Number: 08 03 51.23-10.0 From: BROOKE BURCHAM Final Due Date: 03/12/20 Subject: HISTORIC CURTAIN WALLS - CUSTOM COLOR SEALANT SAMPLE Description: CUSTOM COLOR SEALANT SAMPLE. COLOR MATCH BENJAMIN MOORE 2124-10 WROUGHT IRON Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 06362 | Responded and Closed | Approved | 2020-03-03 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  | See attached for approved submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-26 |  | 080351.23-0010-0 Custom Color Sealant Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-26 |  | 080351.23-0010-0 Custom Color Sealant Sample.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-03-03 |  | 080351.23-0010-0 Custom Color Sealant Sample_POP.pdf
08 03 51.23-011-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-011-00 HISTORIC CURTAIN WALLS - Shop Drawings - Corona NORTH, EAST, WEST ELEVATIONS | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-04 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian MacRae (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti) |  |  |  | 2020-06-18 | 2020-06-17 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-06-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06185 | Received | For Review | 2020-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-18 | Submittal Number: 08 03 51.23-11.0 From: BROOKE BURCHAM Final Due Date: 06/10/20 Subject: HISTORIC CURTAIN WALLS - SHOP DRAWINGS - CORONA NORTH, EAST, WEST ELEVATIONS Description: HISTORIC CURTAINWALL SHOP STEEL SHOP DRAWINGS FOR NORTH, EAST AND WEST ELEVATIONS Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 08358 | Forwarded | For Review | 2020-06-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-11 | Submittal Number: 08 03 51.23-11.0 From: BROOKE BURCHAM Final Due Date: 06/10/20 Subject: HISTORIC CURTAIN WALLS - SHOP DRAWINGS - CORONA NORTH, EAST, WEST ELEVATIONS Description: HISTORIC CURTAINWALL SHOP STEEL SHOP DRAWINGS FOR NORTH, EAST AND WEST ELEVATIONS Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 08495 | Forwarded | For Review | 2020-06-09 | Todd Spangler (Populous) | Brian MacRae (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti) | 2020-06-15 | Submittal Number: 08 03 51.23-11.0 From: BROOKE BURCHAM Final Due Date: 06/10/20 Subject: HISTORIC CURTAIN WALLS - SHOP DRAWINGS - CORONA NORTH, EAST, WEST ELEVATIONS Description: HISTORIC CURTAINWALL SHOP STEEL SHOP DRAWINGS FOR NORTH, EAST AND WEST ELEVATIONS Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 08698 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-17 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  | SEE ATTACHED FOR REVIEW AND COMMTENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-03 |  | 080351.23-0011-0 Historic Curtainwall - Steel Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-03 |  | 080351.23-0011-0 Historic Curtainwall - Steel Shop Drawings.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-06-03 |  | 080351.23-0011-0 Historic Curtainwall - Steel Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-17 |  | 080351.23-0011-0 Historic Curtainwall - Steel Shop Drawings_TT_POP.pdf
08 03 51.23-011-01 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-011-01 HISTORIC CURTAIN WALLS - Shop Drawings - Corona NORTH, EAST, WEST ELEVATIONS | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-31 | Responded and Closed - Rejected |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian MacRae (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti) |  |  |  | 2020-09-15 07:00 | 2020-10-08 | 39 |  | Record Copies; Transfers; Submittals |  | 39 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07860 | Received | For Review | 2020-08-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-15 07:00 | Submittal Number: 08 03 51.23-11.1 From: BROOKE BURCHAM Final Due Date: 09/14/20 Subject: HISTORIC CURTAIN WALLS - SHOP DRAWINGS - CORONA NORTH, EAST, WEST ELEVATIONS Description: HISTORIC CURTAINWALL SHOP STEEL SHOP DRAWINGS FOR NORTH, EAST AND WEST ELEVATIONS Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 10450 | Forwarded | For Review | 2020-08-31 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-07 | Submittal Number: 08 03 51.23-11.1 From: BROOKE BURCHAM Final Due Date: 09/14/20 Subject: HISTORIC CURTAIN WALLS - SHOP DRAWINGS - CORONA NORTH, EAST, WEST ELEVATIONS Description: HISTORIC CURTAINWALL SHOP STEEL SHOP DRAWINGS FOR NORTH, EAST AND WEST ELEVATIONS Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 10469 | Forwarded | For Review | 2020-09-01 | Todd Spangler (Populous) | Brian MacRae (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti) | 2020-09-10 | Submittal Number: 08 03 51.23-11.1 From: BROOKE BURCHAM Final Due Date: 09/14/20 Subject: HISTORIC CURTAIN WALLS - SHOP DRAWINGS - CORONA NORTH, EAST, WEST ELEVATIONS Description: HISTORIC CURTAINWALL SHOP STEEL SHOP DRAWINGS FOR NORTH, EAST AND WEST ELEVATIONS Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 11446 | Responded and Closed | Rejected | 2020-10-08 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  | Send calcs. and clouded revised drawings. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-31 |  | 080351.23-0011-1 Historic Curtainwall - Steel Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-31 |  | 080351.23-0011-1 Historic Curtainwall - Steel Shop Drawings.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-08-31 |  | 080351.23-0011-1 Historic Curtainwall - Steel Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-31 |  | 080351.23-0011-1 Historic Curtainwall - Steel Shop Drawings.pdf
08 03 51.23-011-02 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-011-02 HISTORIC CURTAIN WALLS - Steel Shops - Corona | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-13 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian MacRae (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti) |  |  |  | 2020-11-02 | 2020-11-16 | 35 |  | Record Copies; Transfers; Submittals |  | 32 |  | 2020-11-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08748 | Received | For Review | 2020-10-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-11-02 | Submittal Number: 08 03 51.23-11.2 From: BROOKE BURCHAM Final Due Date: 10/27/20 Subject: HISTORIC CURTAIN WALLS - STEEL SHOPS - CORONA Description: HISTORIC CURTAINWALL SHOP STEEL SHOP DRAWINGS FOR NORTH, EAST AND WEST ELEVATIONS Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 11556 | Forwarded | For Review | 2020-10-13 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-20 | Submittal Number: 08 03 51.23-11.2 From: BROOKE BURCHAM Final Due Date: 10/27/20 Subject: HISTORIC CURTAIN WALLS - STEEL SHOPS - CORONA Description: HISTORIC CURTAINWALL SHOP STEEL SHOP DRAWINGS FOR NORTH, EAST AND WEST ELEVATIONS Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 11607 | Forwarded | For Review | 2020-10-14 | Todd Spangler (Populous) | Brian MacRae (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti) |  | Submittal Number: 08 03 51.23-11.2 From: BROOKE BURCHAM Final Due Date: 10/27/20 Subject: HISTORIC CURTAIN WALLS - STEEL SHOPS - CORONA Description: HISTORIC CURTAINWALL SHOP STEEL SHOP DRAWINGS FOR NORTH, EAST AND WEST ELEVATIONS Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 09435 | Review Response | Approved as Noted | 2020-11-13 | Samar Kenkre (Thornton Tomasetti) | Todd Spangler (Populous) |  |  | Info Exchange
| 12445 | Responded and Closed | Approved as Noted | 2020-11-16 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-12 |  | 080351.23-0011-2 Historic Curtainwall - Steel Shops - IFC Design Team Comments.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-12 |  | Historic Curtainwall - Steel Shops - Clean Set.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-12 |  | 080351.23-0011-2 Historic Curtainwall - Steel Shops - IFC Design Team Comments.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-12 |  | Historic Curtainwall - Steel Shops - Clean Set.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-10-12 |  | 080351.23-0011-2 Historic Curtainwall - Steel Shops - IFC Design Team Comments.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-10-12 |  | Historic Curtainwall - Steel Shops - Clean Set.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-10-12 |  | 080351.23-0011-2 Historic Curtainwall - Steel Shops - IFC Design Team Comments.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-10-12 |  | Historic Curtainwall - Steel Shops - Clean Set.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-16 |  | 080351.23-0011-2 Historic Curtainwall - Steel Shops - TT_POP.pdf
08 03 51.23-012-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-012-00 HISTORIC CURTAIN WALLS - Calculations North, East and West | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-04 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-18 | 2020-06-25 | 22 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06186 | Received | For Review | 2020-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-18 | Submittal Number: 08 03 51.23-12.0 From: BROOKE BURCHAM Final Due Date: 06/18/20 Subject: HISTORIC CURTAIN WALLS - CALCULATIONS NORTH, EAST AND WEST Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 08359 | Forwarded | For Review | 2020-06-04 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-11 | Submittal Number: 08 03 51.23-12.0 From: BROOKE BURCHAM Final Due Date: 06/18/20 Subject: HISTORIC CURTAIN WALLS - CALCULATIONS NORTH, EAST AND WEST Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 08466 | Forwarded | For Review | 2020-06-08 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth K... | 2020-06-15 | Submittal Number: 08 03 51.23-12.0 From: BROOKE BURCHAM Final Due Date: 06/18/20 Subject: HISTORIC CURTAIN WALLS - CALCULATIONS NORTH, EAST AND WEST Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 06598 | Review Response | Approved as Noted/Resubmit | 2020-06-23 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  | Please see comments in blue by TT on various parts of this calc package. SDK ¦ TT ¦ 6/ 23/2020 | Info Exchange
| 08894 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-25 | Populous SCA_CCA | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-03 |  | 080351.23-0012-0 North East and West Calcs.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-03 |  | 080351.23-0012-0 North East and West Calcs.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-02 02:00 |  | 080351.23-0012-0 North East and West Calcs.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-06-02 |  | 080351.23-0012-0 North East and West Calcs.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-25 |  | 080351.23-0012-0 North East and West Calcs_TT_POP.pdf
08 03 51.23-012-01 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-012-01 HISTORIC CURTAIN WALLS - Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-13 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian MacRae (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti) |  |  |  | 2020-11-02 | 2020-11-16 | 35 |  | Record Copies; Transfers; Submittals |  | 32 |  | 2020-11-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08747 | Received | For Review | 2020-10-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-11-02 | Submittal Number: 08 03 51.23-12.1 From: BROOKE BURCHAM Final Due Date: 10/27/20 Subject: HISTORIC CURTAIN WALLS - CALCULATIONS Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 11555 | Forwarded | For Review | 2020-10-13 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-20 | Submittal Number: 08 03 51.23-12.1 From: BROOKE BURCHAM Final Due Date: 10/27/20 Subject: HISTORIC CURTAIN WALLS - CALCULATIONS Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 11606 | Forwarded | For Review | 2020-10-14 | Todd Spangler (Populous) | Brian MacRae (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti) |  | Submittal Number: 08 03 51.23-12.1 From: BROOKE BURCHAM Final Due Date: 10/27/20 Subject: HISTORIC CURTAIN WALLS - CALCULATIONS Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 09433 | Review Response | Approved as Noted | 2020-11-13 | Samar Kenkre (Thornton Tomasetti) | Todd Spangler (Populous) |  |  | Info Exchange
| 12440 | Responded and Closed | Approved as Noted | 2020-11-16 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-12 |  | 080351.23-0012-1 HCW Calculations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-12 |  | 080351.23-0012-1 HCW Calculations.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-10-12 |  | 080351.23-0012-1 HCW Calculations.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-10-12 |  | 080351.23-0012-1 HCW Calculations.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-16 |  | 080351.23-0012-1 HCW Calculations_TT_POP.pdf
08 03 51.23-013-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-013-00 Grout Infill Product Data - Historic Curtainwall Sill - Sikadur-42 | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-19 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-09-02 | 2020-08-28 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07613 | Received | For Review | 2020-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-02 | Submittal Number: 08 03 51.23-13.0 From: BROOKE BURCHAM Final Due Date: 09/02/20 Subject: GROUT INFILL PRODUCT DATA - HISTORIC CURTAINWALL SILL - SIKADUR-42 Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 10140 | Forwarded | For Review | 2020-08-19 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-26 | Submittal Number: 08 03 51.23-13.0 From: BROOKE BURCHAM Final Due Date: 09/02/20 Subject: GROUT INFILL PRODUCT DATA - HISTORIC CURTAINWALL SILL - SIKADUR-42 Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 10305 | Forwarded | For Review | 2020-08-25 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2020-09-01 | Submittal Number: 08 03 51.23-13.0 From: BROOKE BURCHAM Final Due Date: 09/02/20 Subject: GROUT INFILL PRODUCT DATA - HISTORIC CURTAINWALL SILL - SIKADUR-42 Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 07818 | Review Response | Approved | 2020-08-27 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 10395 | Responded and Closed | Approved | 2020-08-28 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-19 |  | 080351.23-0013-0 Grout Infill Product Data - HCW.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-19 |  | 080351.23-0013-0 Grout Infill Product Data - HCW.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-08-18 02:00 |  | 080351.23-0013-0 Grout Infill Product Data - HCW.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-08-27 |  | 080351.23-0013-0 Grout Infill Product Data - HCW_TT REVIEW.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-28 |  | 080351.23-0013-0 Grout Infill Product Data - HCW_TT_POP.pdf
08 03 51.23-014-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-014-00 HISTORIC CURTAIN WALLS - South Elevation Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-01 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian MacRae (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti) |  |  |  | 2020-09-16 | 2020-09-17 | 17 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-09-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07863 | Received | For Review | 2020-09-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-16 | Submittal Number: 08 03 51.23-14.0 From: BROOKE BURCHAM Final Due Date: 09/14/20 Subject: HISTORIC CURTAIN WALLS - SOUTH ELEVATION SHOP DRAWINGS Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 10462 | Forwarded | For Review | 2020-09-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-08 | Submittal Number: 08 03 51.23-14.0 From: BROOKE BURCHAM Final Due Date: 09/14/20 Subject: HISTORIC CURTAIN WALLS - SOUTH ELEVATION SHOP DRAWINGS Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 10468 | Forwarded | For Review | 2020-09-01 | Todd Spangler (Populous) | Brian MacRae (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti) | 2020-09-10 | Submittal Number: 08 03 51.23-14.0 From: BROOKE BURCHAM Final Due Date: 09/14/20 Subject: HISTORIC CURTAIN WALLS - SOUTH ELEVATION SHOP DRAWINGS Description: Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 08130 | Review Response | Approved as Noted | 2020-09-15 | Samar Kenkre (Thornton Tomasetti) | Todd Spangler (Populous) |  |  | Info Exchange
| 10844 | Responded and Closed | Approved as Noted | 2020-09-17 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-31 |  | 080351.23-0014-0 Historic Curtainwall - South Steel Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-31 |  | 080351.23-0014-0 Historic Curtainwall - South Steel Shop Drawings.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-08-31 |  | 080351.23-0014-0 Historic Curtainwall - South Steel Shop Drawings.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-08-31 |  | 080351.23-0014-0 Historic Curtainwall - South Steel Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-17 |  | 080351.23-0014-0 Historic Curtainwall - South Steel Shop Drawings_TT_POP.pdf
08 03 51.23-014-01 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-014-01 HISTORIC CURTAIN WALLS - South Elevation Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-02-08 | 2021-02-08 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10937 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2021-02-08 | Submittal Number: 08 03 51.23-14.1 From: BROOKE BURCHAM Final Due Date: 02/08/21 Subject: HISTORIC CURTAIN WALLS - SOUTH ELEVATION SHOP DRAWINGS Description: ISSUED FOR FABRICATION SET Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 14199 | Forwarded | For Review | 2021-01-25 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-01 | Submittal Number: 08 03 51.23-14.1 From: BROOKE BURCHAM Final Due Date: 02/08/21 Subject: HISTORIC CURTAIN WALLS - SOUTH ELEVATION SHOP DRAWINGS Description: ISSUED FOR FABRICATION SET Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 14406 | Forwarded | For Review | 2021-02-01 | Todd Spangler (Populous) | Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) |  | Submittal Number: 08 03 51.23-14.1 From: BROOKE BURCHAM Final Due Date: 02/08/21 Subject: HISTORIC CURTAIN WALLS - SOUTH ELEVATION SHOP DRAWINGS Description: ISSUED FOR FABRICATION SET Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 11251 | Review Response | Approved | 2021-02-05 | Samar Kenkre (Thornton Tomasetti) | Todd Spangler (Populous) |  | Hey Todd, We have completed our review. There are a few items for you to look at - please review and return. Thanks SDK ¦ TT ¦ 2/4/202 | Info Exchange
| 14567 | Responded and Closed | Approved as Noted | 2021-02-08 | Todd Spangler (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 080351.23-0014-1 HCW - South Steel Shop Drawings_R1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-25 |  | 080351.23-0014-1 HCW - South Steel Shop Drawings_R1.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2021-01-25 |  | 080351.23-0014-1 HCW - South Steel Shop Drawings_R1.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2021-02-05 |  | 080351.23-0014-1 HCW - South Steel Shop Drawings_R1_TT REVIEW.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-08 |  | 080351.23-0014-1 HCW - South Steel Shop Drawings_R1_TT_POP.pdf
08 03 51.23-015-00 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-015-00 HISTORIC CURTAIN WALLS - Sill Flashing Product Data and Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-16 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-30 | 2020-11-09 | 25 |  | Record Copies; Transfers; Submittals |  | 25 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08824 | Received | For Review | 2020-10-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-30 | Submittal Number: 08 03 51.23-15.0 From: BROOKE BURCHAM Final Due Date: 10/30/20 Subject: HISTORIC CURTAIN WALLS - SILL FLASHING PRODUCT DATA AND SHOP DRAWINGS Description: PRODUCT DATA AND SHOP DRAWINGS FOR THE HISTORIC CURTAINWALL SILL FLASHING Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 11660 | Forwarded | For Review | 2020-10-16 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-23 | Submittal Number: 08 03 51.23-15.0 From: BROOKE BURCHAM Final Due Date: 10/30/20 Subject: HISTORIC CURTAIN WALLS - SILL FLASHING PRODUCT DATA AND SHOP DRAWINGS Description: PRODUCT DATA AND SHOP DRAWINGS FOR THE HISTORIC CURTAINWALL SILL FLASHING Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 12267 | Responded and Closed | Approved as Noted | 2020-11-09 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-16 |  | 080351.23-0015-0 Historic Curtainwall - Sill Flashing - PD and SD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-16 |  | 080351.23-0015-0 Historic Curtainwall - Sill Flashing - PD and SD.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-09 |  | 080351.23-0015-0 Historic Curtainwall - Sill Flashing - PD and SD_POP.pdf
08 03 51.23-015-01 | 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALL | 08 03 51.23-015-01 HISTORIC CURTAIN WALLS - Sill Flashing Product Data and Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-05 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-19 | 2021-02-08 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11238 | Received | For Review | 2021-02-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2021-02-19 | Submittal Number: 08 03 51.23-15.1 From: BROOKE BURCHAM Final Due Date: 02/19/21 Subject: HISTORIC CURTAIN WALLS - SILL FLASHING PRODUCT DATA AND SHOP DRAWINGS Description: PRODUCT DATA AND SHOP DRAWINGS FOR THE HISTORIC CURTAINWALL SILL FLASHING Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 14552 | Forwarded | For Review | 2021-02-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-12 | Submittal Number: 08 03 51.23-15.1 From: BROOKE BURCHAM Final Due Date: 02/19/21 Subject: HISTORIC CURTAIN WALLS - SILL FLASHING PRODUCT DATA AND SHOP DRAWINGS Description: PRODUCT DATA AND SHOP DRAWINGS FOR THE HISTORIC CURTAINWALL SILL FLASHING Spec Section: 08 03 51.23 - HISTORIC TREATMENT OF CURTAIN WALLS Status: OPEN | Info Exchange
| 14568 | Responded and Closed | Approved | 2021-02-08 | Todd Spangler (Populous) | Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-05 |  | 080351.23-0015-1 Historic Curtainwall - Sill Flashing - SD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-05 |  | 080351.23-0015-1 Historic Curtainwall - Sill Flashing - SD.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-08 |  | 080351.23-0015-1 Historic Curtainwall - Sill Flashing - SD_POP.pdf
08 11 13-010-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-010-00 Hollow Metal and Hardware - Priority Openings_Part 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-02 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Linda Scott (Studio 08 Consultants) |  |  |  | 2020-04-17 07:00 | 2020-04-24 | 23 |  | Record Copies; Transfers; Submittals | 08 11 13-010-00-01 - 08 11 13-010-00 Hollow Metal and Hardware - Priority Openings_Part 1 | 23 |  | 2020-04-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05181 | Received | For Review | 2020-04-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-04-17 07:00 | Submittal Number: 08 11 13-10.0 From: YE ZHANG Final Due Date: 04/30/20 Subject: HOLLOW METAL AND HARDWARE - PRIORITY OPENINGS_PART 1 Description: THIS SUBMITTAL DOES NOT INLCUDE THE PRIORITY DOORS/FRAMES INDICATED ON PAGE 17 OF 48. THE MISSING DOORS WILL BE UPLOADED AS "HOLLOW METAL AND HARDWARE - PRIORITY OPENINGS_PART 2" Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07033 | Forwarded | For Review | 2020-04-02 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-09 | Submittal Number: 08 11 13-10.0 From: YE ZHANG Final Due Date: 04/30/20 Subject: HOLLOW METAL AND HARDWARE - PRIORITY OPENINGS_PART 1 Description: THIS SUBMITTAL DOES NOT INLCUDE THE PRIORITY DOORS/FRAMES INDICATED ON PAGE 17 OF 48. THE MISSING DOORS WILL BE UPLOADED AS "HOLLOW METAL AND HARDWARE - PRIORITY OPENINGS_PART 2" Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07395 | Forwarded | For Review | 2020-04-20 | Josh Dobken (Populous) | Chad Francis (Populous) | 2020-04-17 | Submittal Number: 08 11 13-10.0 From: YE ZHANG Final Due Date: 04/30/20 Subject: HOLLOW METAL AND HARDWARE - PRIORITY OPENINGS_PART 1 Description: THIS SUBMITTAL DOES NOT INLCUDE THE PRIORITY DOORS/FRAMES INDICATED ON PAGE 17 OF 48. THE MISSING DOORS WILL BE UPLOADED AS "HOLLOW METAL AND HARDWARE - PRIORITY OPENINGS_PART 2" Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07424 | Forwarded | For Review | 2020-04-21 | Chad Francis (Populous) | Linda Scott (Studio 08 Consultants) | 2020-04-17 | Linda - As discussed sending submittal for reference. Thanks Submittal Number: 08 11 13-10.0 From: YE ZHANG Final Due Date: 04/30/20 Subject: HOLLOW METAL AND HARDWARE - PRIORITY OPENINGS_PART 1 Description: THIS SUBMITTAL DOES NOT INLCUDE THE PRIORITY DOORS/FRAMES INDICATED ON PAGE 17 OF 48. THE MISSING DOORS WILL BE UPLOADED AS "HOLLOW METAL AND HARDWARE - PRIORITY OPENINGS_PART 2" Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07518 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-24 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached for all comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-02 |  | Hollow Metal Submittal Priority Openings - MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-02 |  | Hollow Metal Submittal Priority Openings - MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-04-01 02:00 |  | Hollow Metal Submittal Priority Openings - MAM Review.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2020-04-02 |  | Hollow Metal Submittal Priority Openings - MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-04-24 |  | Hollow Metal Submittal Priority Openings - MAM Review - POP.pdf
08 11 13-010-00-01 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-010-00 Hollow Metal and Hardware - Priority Openings_Part 1 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 11 13-010-00 - 08 11 13-010-00 Hollow Metal and Hardware - Priority Openings_Part 1 | -1 | 2020-05-08
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | Hollow Metal Submittal Priority Openings - MAM Review - POP.pdf
08 11 13-011-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-011-00 Hollow Metal and Door Frames - Priority Openings_Part 2 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-02 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Linda Scott (Studio 08 Consultants) |  |  |  | 2020-04-17 07:00 | 2020-04-24 | 23 |  | Record Copies; Transfers; Submittals | 08 11 13-011-00-01 - 08 11 13-011-00 Hollow Metal and Door Frames - Priority Openings_Part 2 | 23 |  | 2020-04-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05182 | Received | For Review | 2020-04-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-04-17 07:00 | Submittal Number: 08 11 13-11.0 From: TYRONE THORNTON Final Due Date: 05/06/20 Subject: HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2 Description: PLEASE SEE ATTACHED PART 2 OF PRIORITY HOLLOW METAL AND DOOR FRAMES SUBMITTALS. THESE OPENINGS WERE MISTAKENLY LEFT OUT OF THE PRIORITY SUBMITTALS. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07034 | Forwarded | For Review | 2020-04-02 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-09 | Submittal Number: 08 11 13-11.0 From: TYRONE THORNTON Final Due Date: 05/06/20 Subject: HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2 Description: PLEASE SEE ATTACHED PART 2 OF PRIORITY HOLLOW METAL AND DOOR FRAMES SUBMITTALS. THESE OPENINGS WERE MISTAKENLY LEFT OUT OF THE PRIORITY SUBMITTALS. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07394 | Forwarded | For Review | 2020-04-20 | Josh Dobken (Populous) | Chad Francis (Populous) | 2020-04-17 | Submittal Number: 08 11 13-11.0 From: TYRONE THORNTON Final Due Date: 05/06/20 Subject: HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2 Description: PLEASE SEE ATTACHED PART 2 OF PRIORITY HOLLOW METAL AND DOOR FRAMES SUBMITTALS. THESE OPENINGS WERE MISTAKENLY LEFT OUT OF THE PRIORITY SUBMITTALS. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07425 | Forwarded | For Review | 2020-04-21 | Chad Francis (Populous) | Linda Scott (Studio 08 Consultants) | 2020-04-17 | Linda - As discussed sending submittal for reference. Thanks Submittal Number: 08 11 13-11.0 From: TYRONE THORNTON Final Due Date: 05/06/20 Subject: HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2 Description: PLEASE SEE ATTACHED PART 2 OF PRIORITY HOLLOW METAL AND DOOR FRAMES SUBMITTALS. THESE OPENINGS WERE MISTAKENLY LEFT OUT OF THE PRIORITY SUBMITTALS. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07519 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-24 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached for all comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-02 |  | Priority HM Doors & Frames_Part 2_ MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-02 |  | Priority HM Doors & Frames_Part 2_ MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-04-01 02:00 |  | Priority HM Doors & Frames_Part 2_ MAM Review.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2020-04-02 |  | Priority HM Doors & Frames_Part 2_ MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-04-24 |  | Priority HM Doors & Frames_Part 2_ MAM Review - POP.pdf
08 11 13-011-00-01 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-011-00 Hollow Metal and Door Frames - Priority Openings_Part 2 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 11 13-011-00 - 08 11 13-011-00 Hollow Metal and Door Frames - Priority Openings_Part 2 | -1 | 2020-05-08
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | Priority HM Doors & Frames_Part 2_ MAM Review - POP.pdf
08 11 13-046-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-046-00 Non-Priority Doors & Frames - Event Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-20 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-04 | 2020-05-05 | 16 |  | Record Copies; Transfers; Submittals | 08 11 13-046-00-01 - 08 11 13-046-00 Non-Priority Doors & Frames - Event Level | 16 |  | 2020-05-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05438 | Received | For Review | 2020-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-04 | Submittal Number: 08 11 13-46.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: NON-PRIORITY DOORS & FRAMES - EVENT LEVEL Description: THIS SUBMITTAL WILL INCLUDE ALL REMAINING NON-PRIORITY DOORS AND FRAMES ON EVENT LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07380 | Forwarded | For Review | 2020-04-20 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-27 | Submittal Number: 08 11 13-46.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: NON-PRIORITY DOORS & FRAMES - EVENT LEVEL Description: THIS SUBMITTAL WILL INCLUDE ALL REMAINING NON-PRIORITY DOORS AND FRAMES ON EVENT LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07647 | Forwarded | For Review | 2020-04-30 | Josh Dobken (Populous) | Chad Francis (Populous) | 2020-05-04 | Submittal Number: 08 11 13-46.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: NON-PRIORITY DOORS & FRAMES - EVENT LEVEL Description: THIS SUBMITTAL WILL INCLUDE ALL REMAINING NON-PRIORITY DOORS AND FRAMES ON EVENT LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Email
| 07755 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-05 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. PROVIDE SUBMITTAL NUMBER IN ALL ATTACHMENT FILENAMES, TYP 2. SEE ATTACHED FOR ADDITIONAL COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-20 |  | SCA - Event Level (Remaining) Doors Submittal_ MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-20 |  | SCA - Event Level (Remaining) Doors Submittal_ MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-04-19 02:00 |  | SCA - Event Level (Remaining) Doors Submittal_ MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-05 |  | SCA - Event Level (Remaining) Doors Submittal_ MAM Review - POP.pdf
08 11 13-046-00-01 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-046-00 Non-Priority Doors & Frames - Event Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 11 13-046-00 - 08 11 13-046-00 Non-Priority Doors & Frames - Event Level | -1 | 2020-05-19
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | SCA - Event Level (Remaining) Doors Submittal_ MAM Review - POP.pdf
08 11 13-047-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-047-00 HM Doors & Frames – Mezzanine Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-22 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-06 | 2020-05-05 | 14 |  | Record Copies; Transfers; Submittals | 08 11 13-047-00-01 - 08 11 13-047-00 HM Doors & Frames – Mezzanine Level | 14 |  | 2020-05-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05491 | Received | For Review | 2020-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-06 | Submittal Number: 08 11 13-47.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: HM DOORS & FRAMES – MEZZANINE LEVEL Description: THIS SUBMITTAL WILL INCLUDE THE HOLLOW METAL DOORS AND FRAMES FOR THE MECHANICAL MEZZANINE LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07445 | Forwarded | For Review | 2020-04-22 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-04-29 | Submittal Number: 08 11 13-47.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: HM DOORS & FRAMES – MEZZANINE LEVEL Description: THIS SUBMITTAL WILL INCLUDE THE HOLLOW METAL DOORS AND FRAMES FOR THE MECHANICAL MEZZANINE LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07765 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-05 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. SEE ATTACHED FOR ADDITIONAL COMMENTS 2. SUBMIT ALL SUSTAINABLE DESIGN SUBMITTALS 08 11 13 1.5-B 3. SUBMIT ALL SHOP DRAWING REQUIREMENTS REFER TO 08 11 13 1.5-B 4. SUBMIT REMAINING DOOR/FRAMES 5.PROVIDE SUBMITTAL NUMBER IN ALL ATTACHMENT FILENAMES, TYP | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | Seattle Center Arena Mezzanine Hollow Metal Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 08 11 13-47.0 Seattle Center Arena Mezzanine Hollow Metal Submittal.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-05 |  | Seattle Center Arena Mezzanine Hollow Metal Submittal - POP.pdf
08 11 13-047-00-01 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-047-00 HM Doors & Frames – Mezzanine Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 11 13-047-00 - 08 11 13-047-00 HM Doors & Frames – Mezzanine Level | -1 | 2020-05-19
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | Seattle Center Arena Mezzanine Hollow Metal Submittal - POP.pdf
08 11 13-048-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-048-00 HM Doors & Frames – Main Concourse | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-22 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-06 | 2020-05-05 | 14 |  | Record Copies; Transfers; Submittals | 08 11 13-048-00-01 - 08 11 13-048-00 HM Doors & Frames – Main Concourse | 14 |  | 2020-05-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05494 | Received | For Review | 2020-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-06 | Submittal Number: 08 11 13-48.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: HM DOORS & FRAMES – MAIN CONCOURSE Description: THIS SUBMITTAL INCLUDES THE REMAINING HOLLOW METAL DOORS AND FRAMES FOR MAIN CONOURSE LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07448 | Forwarded | For Review | 2020-04-22 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-04-29 | Submittal Number: 08 11 13-48.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: HM DOORS & FRAMES – MAIN CONCOURSE Description: THIS SUBMITTAL INCLUDES THE REMAINING HOLLOW METAL DOORS AND FRAMES FOR MAIN CONOURSE LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07763 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-05 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. PROVIDE SUBMITTAL NUMBER IN ALL ATTACHMENT FILENAMES, TYP 2. SEE ATTACHED FOR ADDITIONAL COMMENTS 3. SUBMIT REMAINING DOORS/FRAMES | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | SCA - Main Concourse Hollow Metal Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 08 11 13-48.0 SCA - Main Concourse Hollow Metal Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-05 |  | SCA - Main Concourse Hollow Metal Submittal_MAM Review - POP.pdf
08 11 13-048-00-01 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-048-00 HM Doors & Frames – Main Concourse | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 11 13-048-00 - 08 11 13-048-00 HM Doors & Frames – Main Concourse | -1 | 2020-05-19
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | SCA - Main Concourse Hollow Metal Submittal_MAM Review - POP.pdf
08 11 13-049-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-049-00 HM Doors & Frames – Upper Concourse | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-04 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-18 | 2020-05-06 | 3 |  | Record Copies; Transfers; Submittals | 08 11 13-049-00-01 - 08 11 13-049-00 HM Doors & Frames – Upper Concourse | 3 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05681 | Received | For Review | 2020-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-18 | Submittal Number: 08 11 13-49.0 From: TYRONE THORNTON Final Due Date: 05/16/20 Subject: HM DOORS & FRAMES – UPPER CONCOURSE Description: THIS SUBMITTAL WILL INCLUDE ALL HOLLOW METAL DOORS AND FRAMES FOR THE UPPER CONCOURSE LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07692 | Forwarded | For Review | 2020-05-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-11 | Submittal Number: 08 11 13-49.0 From: TYRONE THORNTON Final Due Date: 05/16/20 Subject: HM DOORS & FRAMES – UPPER CONCOURSE Description: THIS SUBMITTAL WILL INCLUDE ALL HOLLOW METAL DOORS AND FRAMES FOR THE UPPER CONCOURSE LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07791 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. REFER TO PAGE 9 FOR MISSING DOORS 2. PROVIDE SUBMITTAL NUMBER IN FILENAME ATTACHMENTS 3. SEE ADDITIONAL COMMENTS ON SHEETS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-02 |  | SCA - Upper Concourse Hollow Metal Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-02 |  | 08 11 13-49.0 SCA - Upper Concourse Hollow Metal Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-06 |  | 08 11 13-49.0 SCA - Upper Concourse Hollow Metal Submittal_MAM Review - POP.pdf
08 11 13-049-00-01 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-049-00 HM Doors & Frames – Upper Concourse | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 11 13-049-00 - 08 11 13-049-00 HM Doors & Frames – Upper Concourse | -1 | 2020-05-20
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-06 |  | 08 11 13-49.0 SCA - Upper Concourse Hollow Metal Submittal_MAM Review - POP.pdf
08 11 13-050-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-050-00 HM Doors & Frames – Bridge & Catwalk | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-04 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-18 | 2020-05-12 | 9 |  | Record Copies; Transfers; Submittals | 08 11 13-050-00-01 - 08 11 13-050-00 HM Doors & Frames – Bridge & Catwalk | 9 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05682 | Received | For Review | 2020-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-18 | Submittal Number: 08 11 13-50.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: HM DOORS & FRAMES – BRIDGE & CATWALK Description: THIS SUBMITTAL INCLUDES ALL HOLLOW METAL DOORS FOR THE BRIDGE AND CATWALK LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07693 | Forwarded | For Review | 2020-05-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-11 | Submittal Number: 08 11 13-50.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: HM DOORS & FRAMES – BRIDGE & CATWALK Description: THIS SUBMITTAL INCLUDES ALL HOLLOW METAL DOORS FOR THE BRIDGE AND CATWALK LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07931 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-02 |  | SCA - Bridge & Catwalk Hollow Metal Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-02 |  | 08 11 13-50.0 SCA - Bridge & Catwalk Hollow Metal Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-12 |  | 08 11 13-50.0 SCA - Bridge & Catwalk Hollow Metal Submittal_MAM Review - POP.pdf
08 11 13-050-00-01 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-050-00 HM Doors & Frames – Bridge & Catwalk | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 11 13-050-00 - 08 11 13-050-00 HM Doors & Frames – Bridge & Catwalk | -1 | 2020-05-26
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-12 |  | 08 11 13-50.0 SCA - Bridge & Catwalk Hollow Metal Submittal_MAM Review - POP.pdf
08 11 13-051-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-051-00 HM Doors & Frames - Suite Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-30 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-14 | 2020-05-06 | 7 |  | Record Copies; Transfers; Submittals | 08 11 13-051-00-01 - 08 11 13-051-00 HM Doors & Frames - Suite Level | 7 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05641 | Received | For Review | 2020-04-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-14 | Submittal Number: 08 11 13-51.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: HM DOORS & FRAMES - SUITE LEVEL Description: THIS SUBMITTAL INCLUDES HOLLOW METAL DOORS AND FRAMES FOR THE SUITE LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07637 | Forwarded | For Review | 2020-04-30 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-07 | Submittal Number: 08 11 13-51.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: HM DOORS & FRAMES - SUITE LEVEL Description: THIS SUBMITTAL INCLUDES HOLLOW METAL DOORS AND FRAMES FOR THE SUITE LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 07785 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. SUBMIT REMAINING SUITE LEVEL DOORS ISSUED ON SHEET A9-01-4 IN LATEST CCD-058 2. PROVIDE SUBMITTAL NUMBER IN ATTACHMENT FILENAMES, TYP | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-29 |  | SCA - Suite Level HM Doors & Frames Submittal_ MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-29 |  | 08 11 13-51.0 SCA - Suite Level HM Doors & Frames Submittal_ MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-06 |  | SCA - Suite Level HM Doors & Frames Submittal_ MAM Review - POP.pdf
08 11 13-051-00-01 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-051-00 HM Doors & Frames - Suite Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 11 13-051-00 - 08 11 13-051-00 HM Doors & Frames - Suite Level | -1 | 2020-05-20
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-06 |  | SCA - Suite Level HM Doors & Frames Submittal_ MAM Review - POP.pdf
08 11 13-052-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-052-00 08 11 13 - Premium Spaces - HM Doors & Frames - Event Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-14 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-07-28 | 2020-07-28 | 15 |  | Record Copies; Transfers; Submittals | 08 11 13-052-00-01 - 08 11 13-052-00 08 11 13 - Premium Spaces - HM Doors & Frames - Event Level | 15 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06944 | Received | For Review | 2020-07-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-28 | Submittal Number: 08 11 13-52.0 From: TYRONE THORNTON Final Due Date: 07/27/20 Subject: 08 11 13 - PREMIUM SPACES - HM DOORS & FRAMES - EVENT LEVEL Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE HM DOORS AND FRAMES ON EVENT LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 09302 | Forwarded | For Review | 2020-07-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-07-21 | Submittal Number: 08 11 13-52.0 From: TYRONE THORNTON Final Due Date: 07/27/20 Subject: 08 11 13 - PREMIUM SPACES - HM DOORS & FRAMES - EVENT LEVEL Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE HM DOORS AND FRAMES ON EVENT LEVEL. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 09570 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached comments | Info Exchange
| 09571 | Reopened | Additional Information | 2020-07-28 08:08 | Chad Francis (Populous) |  |  | Delete comment for 01.36.12 height change to 7'-10" in future CCD
| 09573 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-28 | Chad Francis (Populous) | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please replace previous submittal response with attached. RESUBMIT MISSING DOORS: 01.03.10B (FOUND IN BASE BUILDING HM DOOR SUBMITTAL 08 11 13-057) 01.36.05 01.36.09 ALL SUBMITTED ITEMS ARE APPROVED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | CPA - 081113 Premium Spaces Event Level Hollow Metal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | CPA - 081113 Premium Spaces Event Level Hollow Metal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-27 |  | CPA - 081113 Premium Spaces Event Level Hollow Metal_MAM Review_POP.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-28 |  | CPA - 081113 Premium Spaces Event Level Hollow Metal_MAM Review_POP.pdf
08 11 13-052-00-01 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-052-00 08 11 13 - Premium Spaces - HM Doors & Frames - Event Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 11 13-052-00 - 08 11 13-052-00 08 11 13 - Premium Spaces - HM Doors & Frames - Event Level | -1 | 2020-08-10
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-27 |  | CPA - 081113 Premium Spaces Event Level Hollow Metal_MAM Review_POP.pdf
08 11 13-053-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-053-00 08 11 13 - Premium Spaces - HM Doors & Frames - Main Concourse/Garage 03 and Suite Level/Garage 04 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-29 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-12 | 2020-08-07 | 10 |  | Record Copies; Transfers; Submittals | 08 11 13-053-00-01 - 08 11 13-053-00 08 11 13 - Premium Spaces - HM Doors & Frames - Main Concourse/Garage 03 and Suite Level/Garage 04 | 11 |  | 2020-08-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07224 | Received | For Review | 2020-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-12 | Submittal Number: 08 11 13-53.0 From: TYRONE THORNTON Final Due Date: 08/11/20 Subject: 08 11 13 - PREMIUM SPACES - HM DOORS & FRAMES - MAIN CONCOURSE/GARAGE 03 AND SUITE LEVEL/GARAGE 04 Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE HM DOORS AND FRAMES ON THE MAIN CONCOURSE/GARAGE 03 Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 09637 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-04 | Submittal Number: 08 11 13-53.0 From: TYRONE THORNTON Final Due Date: 08/11/20 Subject: 08 11 13 - PREMIUM SPACES - HM DOORS & FRAMES - MAIN CONCOURSE/GARAGE 03 AND SUITE LEVEL/GARAGE 04 Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE HM DOORS AND FRAMES ON THE MAIN CONCOURSE/GARAGE 03 Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 09928 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-07 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-28 |  | CPA_Premium Spaces Main Concourse & Suite Level Hollow Metal Submital_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-28 |  | CPA_Premium Spaces Main Concourse & Suite Level Hollow Metal Submital_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-07 |  | CPA_Premium Spaces Main Concourse & Suite Level Hollow Metal Submital_MAM Review_POP.pdf
08 11 13-053-00-01 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-053-00 08 11 13 - Premium Spaces - HM Doors & Frames - Main Concourse/Garage 03 and Suite Level/Garage 04 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 11 13-053-00 - 08 11 13-053-00 08 11 13 - Premium Spaces - HM Doors & Frames - Main Concourse/Garage 03 and Suite Level/Garage 04 | -1 | 2020-08-21
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-07 |  | CPA_Premium Spaces Main Concourse & Suite Level Hollow Metal Submital_MAM Review_POP.pdf
08 11 13-056-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-056-00 08 11 13 - Hollow Metal Doors and Frames- LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-23 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-07-08 07:00 | 2020-06-25 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06565 | Received | For Review | 2020-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-08 07:00 | Submittal Number: 08 11 13-56.0 From: TYRONE THORNTON Final Due Date: 07/07/20 Subject: 08 11 13 - HOLLOW METAL DOORS AND FRAMES- LEED DATA Description: THIS SUBMITTAL INCLUDES THE HOLLOW METAL DOORS LEED PRODUCT DATA Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 08839 | Forwarded | For Review | 2020-06-23 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-30 | Submittal Number: 08 11 13-56.0 From: TYRONE THORNTON Final Due Date: 07/07/20 Subject: 08 11 13 - HOLLOW METAL DOORS AND FRAMES- LEED DATA Description: THIS SUBMITTAL INCLUDES THE HOLLOW METAL DOORS LEED PRODUCT DATA Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 08897 | Responded and Closed | Approved | 2020-06-25 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-23 |  | 081113_SCA Hollow Metal LEED Submittal_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-23 |  | 081113_SCA Hollow Metal LEED Submittal_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-06-25 |  | 08 11 13-56.0 SCA Hollow Metal LEED Submittal_MAM Reviewed_POP.pdf
08 11 13-057-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-057-00 08 11 13 - All Base Building Hollow Metal Doors & Frames Schedule | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-17 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-07-31 | 2020-07-31 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-07-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07007 | Received | For Review | 2020-07-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-31 | Submittal Number: 08 11 13-57.0 From: TYRONE THORNTON Final Due Date: 07/31/20 Subject: 08 11 13 - ALL BASE BUILDING HOLLOW METAL DOORS & FRAMES SCHEDULE Description: PLEASE NOTE, THIS SUBMITTAL WILL SERVE AS THE FOR RECORD COPY FOR ALL LEVELS OF THE BASE BUILDING HOLLOW METAL DOORS AND FRAMES. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 09384 | Forwarded | For Review | 2020-07-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-07-24 | Submittal Number: 08 11 13-57.0 From: TYRONE THORNTON Final Due Date: 07/31/20 Subject: 08 11 13 - ALL BASE BUILDING HOLLOW METAL DOORS & FRAMES SCHEDULE Description: PLEASE NOTE, THIS SUBMITTAL WILL SERVE AS THE FOR RECORD COPY FOR ALL LEVELS OF THE BASE BUILDING HOLLOW METAL DOORS AND FRAMES. Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 09713 | Responded and Closed | Approved as Noted | 2020-07-31 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-17 |  | CPA - HM Doors & Frames Submittal Revised 06.10.20_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-17 |  | CPA - HM Doors & Frames Submittal Revised 06.10.20_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-31 |  | CPA - HM Doors & Frames Submittal Revised 06.10.20_MAM Review_POP.pdf
08 11 13-058-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-058-00 HM Doors & Frames Added CCD 058 - 063 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-06 | 2020-08-04 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07112 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 08 11 13-58.0 From: TYRONE THORNTON Final Due Date: 08/04/20 Subject: HM DOORS & FRAMES ADDED CCD 058 - 063 Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 09501 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-07-30 | Submittal Number: 08 11 13-58.0 From: TYRONE THORNTON Final Due Date: 08/04/20 Subject: HM DOORS & FRAMES ADDED CCD 058 - 063 Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 09806 | Responded and Closed | Approved as Noted | 2020-08-04 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | CPA HM Doors & Frames Submittal for Openings Added in CCD-058 to CCD-063_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | CPA HM Doors & Frames Submittal for Openings Added in CCD-058 to CCD-063_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-04 |  | CPA HM Doors & Frames Submittal for Openings Added in CCD-058 to CCD-063_MAM Review_POP.pdf
08 11 13-059-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-059-00 Doors Added CCD 065 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-17 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-01 | 2020-09-24 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08170 | Received | For Review | 2020-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-01 | Submittal Number: 08 11 13-59.0 From: TYRONE THORNTON Final Due Date: 08/26/20 Subject: DOORS ADDED CCD 065 Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 10849 | Forwarded | For Review | 2020-09-17 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-24 | Submittal Number: 08 11 13-59.0 From: TYRONE THORNTON Final Due Date: 08/26/20 Subject: DOORS ADDED CCD 065 Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 11027 | Responded and Closed | Approved as Noted | 2020-09-24 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-17 |  | CPA CCD-065 Hollow Metal Submittal_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-17 |  | CPA CCD-065 Hollow Metal Submittal_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-24 |  | CPA CCD-065 Hollow Metal Submittal_MAM Review_POP.pdf
08 11 13-060-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-060-00 Doors Added CCD 066-073 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-09 | 2020-10-08 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08328 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-10-09 | Submittal Number: 08 11 13-60.0 From: TYRONE THORNTON Final Due Date: 10/01/20 Subject: DOORS ADDED CCD 066-073 Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 11036 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-01 | Submittal Number: 08 11 13-60.0 From: TYRONE THORNTON Final Due Date: 10/01/20 Subject: DOORS ADDED CCD 066-073 Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 11438 | Responded and Closed | Approved | 2020-10-08 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 08 11 13-60 CCD-067 to CCD-073 Hollow Metal Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 08 11 13-60 CCD-067 to CCD-073 Hollow Metal Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-08 |  | 08 11 13-60 CCD-067 to CCD-073 Hollow Metal Submittal_MAM Review_POP.pdf
08 11 13-061-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-061-00 CCD-075 - CCD-079 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-05 | 2020-12-21 | 11 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-12-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10088 | Received | For Review | 2020-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-01-05 | Submittal Number: 08 11 13-61.0 From: ALLIE ZIMMERMAN Final Due Date: 01/04/21 Subject: CCD-075 - CCD-079 ADDED OPENINGS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 13189 | Forwarded | For Review | 2020-12-10 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-17 | Submittal Number: 08 11 13-61.0 From: ALLIE ZIMMERMAN Final Due Date: 01/04/21 Subject: CCD-075 - CCD-079 ADDED OPENINGS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 13437 | Responded and Closed | Approved as Noted | 2020-12-21 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-10 |  | Seatttle Center Arena CCD-075 to CCD-079 Hollow Metal Submittal_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-10 |  | Seatttle Center Arena CCD-075 to CCD-079 Hollow Metal Submittal_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-12-21 |  | Seatttle Center Arena CCD-075 to CCD-079 Hollow Metal Submittal_MAM Reviewed_POP.pdf
08 11 13-062-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-062-00 CCD-082 - CCD-084 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-26 08:00 | 2021-01-27 | 17 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-01-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10554 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-01-26 08:00 | Submittal Number: 08 11 13-62.0 From: ALLIE ZIMMERMAN Final Due Date: 01/27/21 Subject: CCD-082 - CCD-084 ADDED OPENINGS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 13752 | Forwarded | For Review | 2021-01-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-15 | Submittal Number: 08 11 13-62.0 From: ALLIE ZIMMERMAN Final Due Date: 01/27/21 Subject: CCD-082 - CCD-084 ADDED OPENINGS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 14276 | Responded and Closed | Approved as Noted | 2021-01-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | Submittal 08 11 13_62 Revision 0 CCD_082 _ CCD_084 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-08 |  | Submittal 08 11 13_62 Revision 0 CCD_082 _ CCD_084 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-27 |  | Submittal 08 11 13_62 Revision 0 CCD_082 _ CCD_084 Added Openings_MAM Reviewed_POP.pdf
08 11 13-063-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-063-00 HM DOORS & FRAMES - CCD-086 - CCD-087 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-03 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-17 | 2021-03-12 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-03-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11765 | Received | For Review | 2021-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-03-17 | Submittal Number: 08 11 13-63.0 From: ALLIE ZIMMERMAN Final Due Date: 03/17/21 Subject: HM DOORS & FRAMES - CCD-086 - CCD-087 ADDED OPENINGS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 15242 | Forwarded | For Review | 2021-03-03 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-10 | Submittal Number: 08 11 13-63.0 From: ALLIE ZIMMERMAN Final Due Date: 03/17/21 Subject: HM DOORS & FRAMES - CCD-086 - CCD-087 ADDED OPENINGS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 15507 | Responded and Closed | Approved | 2021-03-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-03 |  | Submittal 08 11 13-63 Revision 0 HM DOORS FRAMES - CCD-086 - CCD-087 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-03 |  | Submittal 08 11 13-63 Revision 0 HM DOORS FRAMES - CCD-086 - CCD-087 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-12 |  | Submittal 08 11 13-63 Revision 0 HM DOORS FRAMES - CCD-086 - CCD-087 Added Openings_MAM Reviewed_POP.pdf
08 11 13-064-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-064-00 HM DOORS & FRAMES - CCD 088 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-01 | 2021-03-26 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12093 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-04-01 | Submittal Number: 08 11 13-64.0 From: ALLIE ZIMMERMAN Final Due Date: 03/31/21 Subject: HM DOORS & FRAMES - CCD 088 ADDED OPENINGS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 15651 | Forwarded | For Review | 2021-03-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-25 | Submittal Number: 08 11 13-64.0 From: ALLIE ZIMMERMAN Final Due Date: 03/31/21 Subject: HM DOORS & FRAMES - CCD 088 ADDED OPENINGS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 15880 | Responded and Closed | Approved | 2021-03-26 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-17 |  | Submittal 08 11 13-64 Revision 0 HM DOORS FRAMES - CCD 088 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-17 |  | Submittal 08 11 13-64 Revision 0 HM DOORS FRAMES - CCD 088 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-26 |  | Submittal 08 11 13-64 Revision 0 HM DOORS FRAMES - CCD 088 Added Openings_MAM Reviewed_POP.pdf
08 11 13-065-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-065-00 HM DOORS & FRAMES - Product Test Reports | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-01 | 2021-03-26 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12094 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-04-01 | Submittal Number: 08 11 13-65.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: HM DOORS & FRAMES - PRODUCT TEST REPORTS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 15652 | Forwarded | For Review | 2021-03-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-25 | Submittal Number: 08 11 13-65.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: HM DOORS & FRAMES - PRODUCT TEST REPORTS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 15881 | Responded and Closed | Approved | 2021-03-26 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-17 |  | Submittal 08 11 13-65 Revision 0 HM DOORS FRAMES - Product Test Reports_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-17 |  | Submittal 08 11 13-65 Revision 0 HM DOORS FRAMES - Product Test Reports_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-26 |  | Submittal 08 11 13-65 Revision 0 HM DOORS FRAMES - Product Test Reports_MAM Reviewed_POP.pdf
08 11 13-066-00 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | 08 11 13-066-00 HM DOORS & FRAMES - CCD 091 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-19 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-03 | 2021-04-27 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12634 | Received | For Review | 2021-04-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-03 | Submittal Number: 08 11 13-66.0 From: ALLIE ZIMMERMAN Final Due Date: 05/03/21 Subject: HM DOORS & FRAMES - CCD 091 ADDED OPENINGS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 16351 | Forwarded | For Review | 2021-04-19 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-26 | Submittal Number: 08 11 13-66.0 From: ALLIE ZIMMERMAN Final Due Date: 05/03/21 Subject: HM DOORS & FRAMES - CCD 091 ADDED OPENINGS Description: Spec Section: 08 11 13 - HOLLOW METAL DOORS AND FRAMES Status: OPEN | Info Exchange
| 16557 | Responded and Closed | Approved as Noted | 2021-04-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED 1. RESUBMIT DOORS 03.07.02 AND 03.13.01 REVISED TO GATES PER OWNER DIRECTION IN CCD-094 SPEC 08 38 00, RESUBMIT ACCORDINGLY AND UNDER CORRECT SPEC. 2. ALL OTHER HM DOOR/FRAMES SUBMITTED ARE APPROVED | Info Exchange
| 16737 | Sent | For Information Only | 2021-05-04 | Populous SCA_CCA | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Allie Zimmerman |  | Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman Remarks: PLEASE SEE ATTACHED 1. RESUBMIT DOORS 03.07.02 AND 03.13.01 REVISED TO GATES PER OWNER DIRECTION IN CCD-094 SPEC 08 38 00, RESUBMIT ACCORDINGLY AND UNDER CORRECT SPEC. 2. ALL OTHER HM DOOR/FRAMES SUBMITTED ARE APPROVED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-18 |  | Submittal 08 11 13-66 Revision 0 HM DOORS FRAMES - CCD 091 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-18 |  | Submittal 08 11 13-66 Revision 0 HM DOORS FRAMES - CCD 091 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-27 |  | Submittal 08 11 13-66 Revision 0 HM DOORS FRAMES - CCD 091 Added Openings_MAM Reviewed_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-04-17 02:00 |  | Submittal 08 11 13-66 Revision 0 HM DOORS FRAMES - CCD 091 Added Openings_MAM Reviewed.pdf
08 14 16-002-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-002-00 08 14 16 - FLUSH WOOD DOORS - LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-24 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-07-08 | 2020-06-25 | 2 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06576 | Received | For Review | 2020-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-08 | Submittal Number: 08 14 16-2.0 From: TYRONE THORNTON Final Due Date: 07/17/20 Subject: 08 14 16 - FLUSH WOOD DOORS - LEED DATA Description: SUSTAINABLE DESIGN SUBMITTALS : - 1. PRODUCT CERTIFICATES: FOR MATERIALS MANUFACTURED WITHIN 100 MILES (160 KM) OF PROJECT, INDICATING LOCATION OF MATERIAL MANUFACTURER AND POINT OF EXTRACTION, HARVEST, OR RECOVERY FOR EACH RAW MATERIAL. INCLUDE DISTANCE TO PROJECT AND COST FOR EACH RAW MATERIAL. 2. CHAIN-OF-CUSTODY CERTIFICATES: FOR CERTIFIED WOOD PRODUCTS. INCLUDE STATEMENT OF COSTS. 3. CHAIN-OF-CUSTODY QUALIFICATION DATA: FOR MANUFACTURER AND VENDOR. 4. LABORATORY TEST REPORTS: FOR ADHESIVES, INDICATING COMPLIANCE WITH REQUIREMENTS FOR LOW- EMITTING MATERIALS. 5. LABORATORY TEST REPORTS: FOR COMPOSITE WOOD PRODUCTS, INDICATING COMPLIANCE WITH REQUIREMENTS FOR LOW-EMITTING MATERIALS. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 08856 | Forwarded | For Review | 2020-06-23 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-30 | Submittal Number: 08 14 16-2.0 From: TYRONE THORNTON Final Due Date: 07/17/20 Subject: 08 14 16 - FLUSH WOOD DOORS - LEED DATA Description: SUSTAINABLE DESIGN SUBMITTALS : - 1. PRODUCT CERTIFICATES: FOR MATERIALS MANUFACTURED WITHIN 100 MILES (160 KM) OF PROJECT, INDICATING LOCATION OF MATERIAL MANUFACTURER AND POINT OF EXTRACTION, HARVEST, OR RECOVERY FOR EACH RAW MATERIAL. INCLUDE DISTANCE TO PROJECT AND COST FOR EACH RAW MATERIAL. 2. CHAIN-OF-CUSTODY CERTIFICATES: FOR CERTIFIED WOOD PRODUCTS. INCLUDE STATEMENT OF COSTS. 3. CHAIN-OF-CUSTODY QUALIFICATION DATA: FOR MANUFACTURER AND VENDOR. 4. LABORATORY TEST REPORTS: FOR ADHESIVES, INDICATING COMPLIANCE WITH REQUIREMENTS FOR LOW- EMITTING MATERIALS. 5. LABORATORY TEST REPORTS: FOR COMPOSITE WOOD PRODUCTS, INDICATING COMPLIANCE WITH REQUIREMENTS FOR LOW-EMITTING MATERIALS. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 08902 | Responded and Closed | Approved | 2020-06-25 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-23 |  | 081416 - SCA Flush Wood Doors LEED_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-23 |  | 081416 - SCA Flush Wood Doors LEED_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-06-25 |  | 081416 - SCA Flush Wood Doors LEED_MAM Reviewed_POP.pdf
08 14 16-004-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-004-00 FLUSH WOOD DOORS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-28 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-12 | 2020-05-11 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-05-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05606 | Received | For Review | 2020-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-12 | Submittal Number: 08 14 16-4.0 From: TYRONE THORNTON Final Due Date: 06/05/20 Subject: FLUSH WOOD DOORS - SAMPLES Description: SAMPLES FOR VERIFICATION : - 1. FACTORY FINISHES APPLIED TO ACTUAL DOOR FACE MATERIALS, APPROXIMATELY 8 BY 10 INCHES, FOR EACH MATERIAL AND FINISH. FOR EACH WOOD SPECIES AND TRANSPARENT FINISH, PROVIDE SET OF THREE SAMPLES SHOWING TYPICAL RANGE OF COLOR AND GRAIN TO BE EXPECTED IN FINISHED WORK. 2. PLASTIC LAMINATE, 6 INCHES SQUARE, FOR EACH COLOR, TEXTURE, AND PATTERN SELECTED. 3. CORNER SECTIONS OF DOORS, APPROXIMATELY 8 BY 10 INCHES, WITH DOOR FACES AND EDGES REPRESENTING ACTUAL MATERIALS TO BE USED. A. PROVIDE SAMPLES FOR EACH SPECIES OF VENEER AND SOLID LUMBER REQUIRED. B. PROVIDE SAMPLES FOR EACH COLOR, TEXTURE, AND PATTERN OF PLASTIC LAMINATE REQUIRED. C. FINISH VENEER-FACED DOOR SAMPLES WITH SAME MATERIALS PROPOSED FOR FACTORY- FINISHED DOORS. 4. LOUVER BLADE AND FRAME SECTIONS, 6 INCHES LONG, FOR EACH MATERIAL AND FINISH SPECIFIED. 5. FRAMES FOR LIGHT OPENINGS, 6 INCHES LONG, FOR EACH MATERIAL, TYPE, AND FINISH REQUIRED. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07598 | Forwarded | For Review | 2020-04-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-05 | Submittal Number: 08 14 16-4.0 From: TYRONE THORNTON Final Due Date: 06/05/20 Subject: FLUSH WOOD DOORS - SAMPLES Description: SAMPLES FOR VERIFICATION : - 1. FACTORY FINISHES APPLIED TO ACTUAL DOOR FACE MATERIALS, APPROXIMATELY 8 BY 10 INCHES, FOR EACH MATERIAL AND FINISH. FOR EACH WOOD SPECIES AND TRANSPARENT FINISH, PROVIDE SET OF THREE SAMPLES SHOWING TYPICAL RANGE OF COLOR AND GRAIN TO BE EXPECTED IN FINISHED WORK. 2. PLASTIC LAMINATE, 6 INCHES SQUARE, FOR EACH COLOR, TEXTURE, AND PATTERN SELECTED. 3. CORNER SECTIONS OF DOORS, APPROXIMATELY 8 BY 10 INCHES, WITH DOOR FACES AND EDGES REPRESENTING ACTUAL MATERIALS TO BE USED. A. PROVIDE SAMPLES FOR EACH SPECIES OF VENEER AND SOLID LUMBER REQUIRED. B. PROVIDE SAMPLES FOR EACH COLOR, TEXTURE, AND PATTERN OF PLASTIC LAMINATE REQUIRED. C. FINISH VENEER-FACED DOOR SAMPLES WITH SAME MATERIALS PROPOSED FOR FACTORY- FINISHED DOORS. 4. LOUVER BLADE AND FRAME SECTIONS, 6 INCHES LONG, FOR EACH MATERIAL AND FINISH SPECIFIED. 5. FRAMES FOR LIGHT OPENINGS, 6 INCHES LONG, FOR EACH MATERIAL, TYPE, AND FINISH REQUIRED. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07849 | Responded and Closed | Approved | 2020-05-11 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-28 |  | 08 14 16 Flush Wood Door Samples_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-28 |  | 08 14 16 Flush Wood Door Samples_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-11 |  | 08 14 16 Flush Wood Door Samples_MAM Review - POP.pdf
08 14 16-007-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-007-00 Non-Priority Wood Doors - Event Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-20 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-04 | 2020-05-04 | 15 |  | Record Copies; Transfers; Submittals | 08 14 16-007-00 -01 - 08 14 16-007-00 Non-Priority Wood Doors - Event Level | 15 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05439 | Received | For Review | 2020-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-04 | Submittal Number: 08 14 16-7.0 From: TYRONE THORNTON Final Due Date: 06/01/20 Subject: NON-PRIORITY WOOD DOORS - EVENT LEVEL Description: THI SUBMITTAL WILL INCLUDE THE NON-PRIORITY WOOD DOORS FOR THE EVENT LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07381 | Forwarded | For Review | 2020-04-20 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-27 | Submittal Number: 08 14 16-7.0 From: TYRONE THORNTON Final Due Date: 06/01/20 Subject: NON-PRIORITY WOOD DOORS - EVENT LEVEL Description: THI SUBMITTAL WILL INCLUDE THE NON-PRIORITY WOOD DOORS FOR THE EVENT LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07504 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Chad Francis (Populous) |  | Submittal Number: 08 14 16-7.0 From: TYRONE THORNTON Final Due Date: 06/01/20 Subject: NON-PRIORITY WOOD DOORS - EVENT LEVEL Description: THI SUBMITTAL WILL INCLUDE THE NON-PRIORITY WOOD DOORS FOR THE EVENT LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07730 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-04 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1.10 OF 59 EVENT LVL WD DOORS SUBMITTED, SUBMIT REMAINING DOORS AS NOTED IN CURRENT CD DOOR SCHEDULES 2. SEE ATTACHED FOR ADDITIONAL COMMENTS 3. SUBMIT ALL SUSTAINABLE DESIGN SUBMITTALS 08 14 16-1.2-B 4. SUBMIT ALL SHOP DRAWING REQUIREMENTS REFER TO 08 14 16-1.2-C 5. PROVIDE SUBMITTAL NUMBER IN ALL ATTACHMENT FILENAMES, TYP | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-20 |  | SCA- Event Level Wood Door Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-20 |  | SCA- Event Level Wood Door Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-20 |  | SCA- Event Level Wood Door Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-04 |  | SCA- Event Level Wood Door Submittal_MAM Review - POP.pdf
08 14 16-007-00 -01 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-007-00 Non-Priority Wood Doors - Event Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 14 16-007-00 - 08 14 16-007-00 Non-Priority Wood Doors - Event Level | -1 | 2020-05-18
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-04 |  | SCA- Event Level Wood Door Submittal_MAM Review - POP.pdf
08 14 16-008-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-008-00 Non-Priority Wood Doors - Mechanical Mezzanine Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-22 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-06 | 2020-05-04 | 13 |  | Record Copies; Transfers; Submittals | 08 14 16-008-00-01 - 08 14 16-008-00 Non-Priority Wood Doors - Mechanical Mezzanine Level | 13 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05492 | Received | For Review | 2020-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-06 | Submittal Number: 08 14 16-8.0 From: TYRONE THORNTON Final Due Date: 05/19/20 Subject: NON-PRIORITY WOOD DOORS - MECHANICAL MEZZANINE LEVEL Description: THIS SUBMITTAL INCLUDES THE NON-PRIORITY WOOD DOORS FOR THE MECHANICAL MEZZANINE LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07446 | Forwarded | For Review | 2020-04-22 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-29 | Submittal Number: 08 14 16-8.0 From: TYRONE THORNTON Final Due Date: 05/19/20 Subject: NON-PRIORITY WOOD DOORS - MECHANICAL MEZZANINE LEVEL Description: THIS SUBMITTAL INCLUDES THE NON-PRIORITY WOOD DOORS FOR THE MECHANICAL MEZZANINE LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07505 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Chad Francis (Populous) |  | Submittal Number: 08 14 16-8.0 From: TYRONE THORNTON Final Due Date: 05/19/20 Subject: NON-PRIORITY WOOD DOORS - MECHANICAL MEZZANINE LEVEL Description: THIS SUBMITTAL INCLUDES THE NON-PRIORITY WOOD DOORS FOR THE MECHANICAL MEZZANINE LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07750 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-04 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. SEE ATTACHED FOR ADDITIONAL COMMENTS 2. SUBMIT ALL SUSTAINABLE DESIGN SUBMITTALS 08 14 16-1.2-B 3. SUBMIT ALL SHOP DRAWING REQUIREMENTS REFER TO 08 14 16-1.2-C 4. SPEC 08 14 16-2.3A-3 INDICATES RIFT CUT CM TO COORDINATE 5. PROVIDE SUBMITTAL NUMBER IN ALL ATTACHMENT FILENAMES, TYP | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | SCA - Mechanical Mezzanine Wood Door Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 08 14 16-8.0 SCA - Mechanical Mezzanine Wood Door Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | SCA - Mechanical Mezzanine Wood Door Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-04 |  | SCA - Mechanical Mezzanine Wood Door Submittal_MAM Review - POP.pdf
08 14 16-008-00-01 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-008-00 Non-Priority Wood Doors - Mechanical Mezzanine Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 14 16-008-00 - 08 14 16-008-00 Non-Priority Wood Doors - Mechanical Mezzanine Level | -1 | 2020-05-18
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-04 |  | SCA - Mechanical Mezzanine Wood Door Submittal_MAM Review - POP.pdf
08 14 16-009-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-009-00 Wood Doors - Bridge & Catwalk | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-04 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-18 | 2020-05-12 | 9 |  | Record Copies; Transfers; Submittals | 08 14 16-009-00-01 - 08 14 16-009-00 Wood Doors - Bridge & Catwalk | 9 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05683 | Received | For Review | 2020-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-18 | Submittal Number: 08 14 16-9.0 From: TYRONE THORNTON Final Due Date: 05/29/20 Subject: WOOD DOORS - BRIDGE & CATWALK Description: THIS SUBMITTAL INCLUDES THE BASE BUILDING WOOD DOORS ON UPPER CONCOURSE, SPACE NEEDLE, AND BRIDGE LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07694 | Forwarded | For Review | 2020-05-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-11 | Submittal Number: 08 14 16-9.0 From: TYRONE THORNTON Final Due Date: 05/29/20 Subject: WOOD DOORS - BRIDGE & CATWALK Description: THIS SUBMITTAL INCLUDES THE BASE BUILDING WOOD DOORS ON UPPER CONCOURSE, SPACE NEEDLE, AND BRIDGE LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07932 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-02 |  | SCA - Bridge & Catwalk Wood Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-02 |  | 08 14 16-9.0 SCA - Bridge & Catwalk Wood Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-12 |  | 08 14 16-9.0 SCA - Bridge & Catwalk Wood Submittal_MAM Review - POP.pdf
08 14 16-009-00-01 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-009-00 Wood Doors - Bridge & Catwalk | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 14 16-009-00 - 08 14 16-009-00 Wood Doors - Bridge & Catwalk | -1 | 2020-05-26
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-12 |  | 08 14 16-9.0 SCA - Bridge & Catwalk Wood Submittal_MAM Review - POP.pdf
08 14 16-010-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-010-00 Wood Doors - Space Needle Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-06 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-20 | 2020-05-12 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05745 | Received | For Review | 2020-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-20 | Submittal Number: 08 14 16-10.0 From: TYRONE THORNTON Final Due Date: 06/02/20 Subject: WOOD DOORS - SPACE NEEDLE LEVEL Description: THIS SUBMITTAL INCLUDES THE WOOD DOORS ON THE SPACE NEEDLE LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07796 | Forwarded | For Review | 2020-05-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-13 | Submittal Number: 08 14 16-10.0 From: TYRONE THORNTON Final Due Date: 06/02/20 Subject: WOOD DOORS - SPACE NEEDLE LEVEL Description: THIS SUBMITTAL INCLUDES THE WOOD DOORS ON THE SPACE NEEDLE LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 07933 | Responded and Closed | Approved | 2020-05-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-06 |  | 08 14 16-10 Rev 0 _SCA - Space Needle Wood Door Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-06 |  | 08 14 16-10 Rev 0 _SCA - Space Needle Wood Door Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-12 |  | 08 14 16-10 Rev 0 _SCA - Space Needle Wood Door Submittal_MAM Review - POP.pdf
08 14 16-011-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-011-00 08 14 16 - Premium Spaces - WD Doors - Event Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-16 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-07-30 | 2020-07-28 | 13 |  | Record Copies; Transfers; Submittals | 08 14 16-011-00-01 - 08 14 16-011-00 08 14 16 - Premium Spaces - WD Doors - Event Level | 13 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06987 | Received | For Review | 2020-07-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-30 | Submittal Number: 08 14 16-11.0 From: TYRONE THORNTON Final Due Date: 07/30/20 Subject: 08 14 16 - PREMIUM SPACES - WD DOORS - EVENT LEVEL Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE WOOD DOORS ON THE EVENT LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 09362 | Forwarded | For Review | 2020-07-16 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-07-23 | Submittal Number: 08 14 16-11.0 From: TYRONE THORNTON Final Due Date: 07/30/20 Subject: 08 14 16 - PREMIUM SPACES - WD DOORS - EVENT LEVEL Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE WOOD DOORS ON THE EVENT LEVEL. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 09586 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-28 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-15 |  | CPA - 081416 Premium Spaces Event Level Wood Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-15 |  | CPA - 081416 Premium Spaces Event Level Wood Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-28 |  | CPA - 081416 Premium Spaces Event Level Wood Submittal_MAM Review_POP.pdf
08 14 16-011-00-01 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-011-00 08 14 16 - Premium Spaces - WD Doors - Event Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 14 16-011-00 - 08 14 16-011-00 08 14 16 - Premium Spaces - WD Doors - Event Level | -1 | 2020-08-11
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-28 |  | CPA - 081416 Premium Spaces Event Level Wood Submittal_MAM Review_POP.pdf
08 14 16-013-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-013-00 08 14 16 - Premium Spaces - WD Doors - Suite Level/Garage 04 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-07 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-21 | 2020-08-07 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-08-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07439 | Received | For Review | 2020-08-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-21 | Submittal Number: 08 14 16-13.0 From: TYRONE THORNTON Final Due Date: 08/20/20 Subject: 08 14 16 - PREMIUM SPACES - WD DOORS - SUITE LEVEL/GARAGE 04 Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE WOOD DOORS ON THE SUITE LEVEL/GARAGE 04. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 09907 | Forwarded | For Review | 2020-08-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-13 | Submittal Number: 08 14 16-13.0 From: TYRONE THORNTON Final Due Date: 08/20/20 Subject: 08 14 16 - PREMIUM SPACES - WD DOORS - SUITE LEVEL/GARAGE 04 Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE WOOD DOORS ON THE SUITE LEVEL/GARAGE 04. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 09929 | Responded and Closed | Approved | 2020-08-07 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | CPA Premium Spaces Suites Level Wood Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-06 |  | CPA Premium Spaces Suites Level Wood Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-07 |  | 08 14 16-13.0 CPA Premium Spaces Suites Level Wood Submittal_MAM Review_POP.pdf
08 14 16-014-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-014-00 08 14 16 - All Base Building Flush Wood Doors Schedule | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-24 | Responded and Closed - No Action Taken or Required |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-07-09 07:00 | 2020-07-08 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06581 | Received | For Review | 2020-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-09 07:00 | Submittal Number: 08 14 16-14.0 From: TYRONE THORNTON Final Due Date: 07/08/20 Subject: 08 14 16 - ALL BASE BUILDING FLUSH WOOD DOORS SCHEDULE Description: PLEASE NOTE, THIS WILL SERVE AS A FOR RECORD COPY OF ALL THE BASE BUILDING FLUSH WOOD DOORS. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 08863 | Forwarded | For Review | 2020-06-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-07-01 | Submittal Number: 08 14 16-14.0 From: TYRONE THORNTON Final Due Date: 07/08/20 Subject: 08 14 16 - ALL BASE BUILDING FLUSH WOOD DOORS SCHEDULE Description: PLEASE NOTE, THIS WILL SERVE AS A FOR RECORD COPY OF ALL THE BASE BUILDING FLUSH WOOD DOORS. Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 09197 | Responded and Closed | No Action Taken or Required | 2020-07-08 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | For Record Only | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-24 |  | 081416 - SCA Base Building Flush Wood Doors_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-24 |  | 081416 - SCA Base Building Flush Wood Doors_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-08 |  | 081416 - SCA Base Building Flush Wood Doors_MAM Reviewed - POP.pdf
08 14 16-015-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-015-00 WD Doors Added CCD 058 - 063 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-06 | 2020-08-04 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07113 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 08 14 16-15.0 From: TYRONE THORNTON Final Due Date: 08/04/20 Subject: WD DOORS ADDED CCD 058 - 063 Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 09502 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-07-30 | Submittal Number: 08 14 16-15.0 From: TYRONE THORNTON Final Due Date: 08/04/20 Subject: WD DOORS ADDED CCD 058 - 063 Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 09805 | Responded and Closed | Approved | 2020-08-04 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | CPA Wood Door Submittal for Openings Added in CCD-058 to CCD-063_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | CPA Wood Door Submittal for Openings Added in CCD-058 to CCD-063_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-04 |  | CPA Wood Door Submittal for Openings Added in CCD-058 to CCD-063_MAM Review_POP.pdf
08 14 16-016-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-016-00 Tunnel Club Custom Doors | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kuebler Perry (Populous) |  |  |  | 2020-10-19 | 2020-10-19 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08526 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-19 | Submittal Number: 08 14 16-16.0 From: MIKE SOLFELT Final Due Date: 10/16/20 Subject: TUNNEL CLUB CUSTOM DOORS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 11278 | Forwarded | For Review | 2020-10-05 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-12 | Submittal Number: 08 14 16-16.0 From: MIKE SOLFELT Final Due Date: 10/16/20 Subject: TUNNEL CLUB CUSTOM DOORS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 11444 | Forwarded | For Review | 2020-10-08 | Populous SCA_CCA | Kuebler Perry (Populous) | 2020-10-15 | Submittal Number: 08 14 16-16.0 From: MIKE SOLFELT Final Due Date: 10/16/20 Subject: TUNNEL CLUB CUSTOM DOORS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 08858 | Review Response | Revise and Resubmit | 2020-10-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Missing concealed closer and extended lip strike. Please incorporate. | Info Exchange
| 11708 | Responded and Closed | Revise and Resubmit | 2020-10-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Missing concealed closer and extended lip strike. Please incorporate. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-02 |  | 08 14 16 -16 - Door Mock Up.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-02 |  | 08 14 16 -16 - Door Mock Up.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-02 |  | 08 14 16 -16 - Door Mock Up.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-19 |  | 08 14 16 -16 - Door Mock Up_POP response.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-02 |  | 08 14 16 -16 - Door Mock Up.pdf
08 14 16-016-01 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-016-01 Tunnel Club Custom Doors | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Linda Scott (Studio 08 Consultants) |  |  |  | 2021-01-27 08:00 | 2021-01-21 | 10 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10639 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-01-27 08:00 | Submittal Number: 08 14 16-16.1 From: MIKE SOLFELT Final Due Date: 01/26/21 Subject: TUNNEL CLUB CUSTOM DOORS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 13849 | Forwarded | For Review | 2021-01-12 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-19 | Submittal Number: 08 14 16-16.1 From: MIKE SOLFELT Final Due Date: 01/26/21 Subject: TUNNEL CLUB CUSTOM DOORS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 13993 | Forwarded | For Review | 2021-01-17 | Chad Francis (Populous) | Linda Scott (Studio 08 Consultants) | 2021-01-21 | Submittal Number: 08 14 16-16.1 From: MIKE SOLFELT Final Due Date: 01/26/21 Subject: TUNNEL CLUB CUSTOM DOORS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 10884 | Review Response | Approved as Noted | 2021-01-18 | Linda Scott (Studio 08 Consultants) | Chad Francis (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thanks. | Info Exchange
| 14134 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-21 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments. Resubmit corrections for record | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 08 14 16 -16.1 Tunnel Club Custom Door.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 08 14 16 -16.1 Tunnel Club Custom Door.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2021-01-12 |  | 08 14 16 -16.1 Tunnel Club Custom Door.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-01-12 |  | 08 14 16 -16.1 Tunnel Club Custom Door.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-21 |  | 08 14 16 - 16.1 - Tunnel Club Custom Door_POP Reviewed ST08.pdf
08 14 16-016-02 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-016-02 Tunnel Club Custom Doors | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-13 | 9 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12360 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-04-19 | Submittal Number: 08 14 16-16.2 From: MIKE SOLFELT Final Due Date: 04/09/21 Subject: TUNNEL CLUB CUSTOM DOORS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 16016 | Forwarded | For Review | 2021-04-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 08 14 16-16.2 From: MIKE SOLFELT Final Due Date: 04/09/21 Subject: TUNNEL CLUB CUSTOM DOORS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 16266 | Responded and Closed | Approved | 2021-04-13 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 08 14 16-16.2 - Tunnel Club Doors For Record.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-01 |  | 08 14 16-16.2 - Tunnel Club Doors For Record.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-13 |  | 08 14 16-16.2 - Tunnel Club Doors For Record_POP.pdf
08 14 16-017-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-017-00 Flush Wood Doors added CCD 066-073 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-14 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-28 | 2020-10-23 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-10-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08785 | Received | For Review | 2020-10-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-28 | Submittal Number: 08 14 16-17.0 From: TYRONE THORNTON Final Due Date: 10/28/20 Subject: FLUSH WOOD DOORS ADDED CCD 066-073 Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 11615 | Forwarded | For Review | 2020-10-14 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-21 | Submittal Number: 08 14 16-17.0 From: TYRONE THORNTON Final Due Date: 10/28/20 Subject: FLUSH WOOD DOORS ADDED CCD 066-073 Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 11831 | Responded and Closed | Approved | 2020-10-23 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-14 |  | Seattle Center Arena CCD-067 to CCD-073 Wood Door Submittal _MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-14 |  | Seattle Center Arena CCD-067 to CCD-073 Wood Door Submittal _MAM Reviewed.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-23 |  | Seattle Center Arena CCD-067 to CCD-073 Wood Door Submittal _MAM Reviewed_POP.pdf
08 14 16-018-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-018-00 08 14 16 - Flush Wood Doors - Verification Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-24 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-08 | 2020-10-08 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08318 | Received | For Review | 2020-09-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-10-08 | Submittal Number: 08 14 16-18.0 From: TYRONE THORNTON Final Due Date: 10/08/20 Subject: 08 14 16 - FLUSH WOOD DOORS - VERIFICATION SAMPLES Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 11025 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 08 14 16-18.0 From: TYRONE THORNTON Final Due Date: 10/08/20 Subject: 08 14 16 - FLUSH WOOD DOORS - VERIFICATION SAMPLES Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 08668 | Review Response | Approved | 2020-10-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. Confirm approval from Rockwell before proceeding. | Info Exchange
| 11449 | Responded and Closed | Approved | 2020-10-08 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. Confirm approval from Rockwell before proceeding. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 08 14 16 Flush Wood Door - Verfication Samples_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 08 14 16-18.0 Flush Wood Door - Verfication Samples_MAM Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-08 |  | 08 14 16-18.0 Flush Wood Door - Verfication Samples_MAM Review_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-24 |  | 08 14 16 Flush Wood Door - Verfication Samples_MAM Review.pdf
08 14 16-019-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-019-00 CCD-075 - CCD-079 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-05 | 2020-12-21 | 11 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-12-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10090 | Received | For Review | 2020-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-01-05 | Submittal Number: 08 14 16-19.0 From: ALLIE ZIMMERMAN Final Due Date: 01/07/21 Subject: CCD-075 - CCD-079 ADDED OPENINGS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 13191 | Forwarded | For Review | 2020-12-10 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-17 | Submittal Number: 08 14 16-19.0 From: ALLIE ZIMMERMAN Final Due Date: 01/07/21 Subject: CCD-075 - CCD-079 ADDED OPENINGS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 13440 | Responded and Closed | Approved as Noted | 2020-12-21 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-10 |  | Seatttle Center Arena CCD-075 to CCD-079 Wood Door Submittal_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-10 |  | Seatttle Center Arena CCD-075 to CCD-079 Wood Door Submittal_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-12-21 |  | Seatttle Center Arena CCD-075 to CCD-079 Wood Door Submittal_MAM Reviewed_POP.pdf
08 14 16-020-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-020-00 FLUSH WOOD DOORS - WC22 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-17 | Closed - Void |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-11 |  | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-01-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10224 | Received | For Review | 2020-12-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-01-11 | Submittal Number: 08 14 16-20.0 From: ALLIE ZIMMERMAN Final Due Date: 12/31/20 Subject: FLUSH WOOD DOORS - WC22 SAMPLE Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 13363 | Forwarded | For Review | 2020-12-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-24 | Submittal Number: 08 14 16-20.0 From: ALLIE ZIMMERMAN Final Due Date: 12/31/20 Subject: FLUSH WOOD DOORS - WC22 SAMPLE Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 13613 | Closed | Void | 2021-01-04 | Josh Dobken (Populous) |  |  | No content was provided in submittal. Item voided.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-17 |  | WC22 Flush Wood Door Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-17 |  | WC22 Flush Wood Door Sample.pdf
08 14 16-020-01 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-020-01 FLUSH WOOD DOORS - WC22 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-05 | Responded and Closed - Approved as Noted |  | Chad Francis (Populous) |  |  |  | 2021-01-20 08:00 | 2021-01-25 | 21 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-01-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10428 | Received | For Review | 2021-01-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-20 08:00 |  | Email
| 13614 | Forwarded | For Review | 2021-01-04 | Populous SCA_CCA | Chad Francis (Populous) | 2021-01-11 |  | Info Exchange
| 10935 | Review Response | Approved as Noted | 2021-01-25 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14197 | Responded and Closed | Approved as Noted | 2021-01-25 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-04 02:00 |  | 08 14 16-0-20-01 WC22 Flush Wood Door Sample.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-04 02:00 |  | 08 14 16-0-20-01 WC22 Flush Wood Door Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-25 |  | 08 14 16-0-20-01 WC22 Flush Wood Door Sample_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-04 |  | 08 14 16-0-20-01 WC22 Flush Wood Door Sample.pdf
08 14 16-021-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-021-00 CCD-082 - CCD-084 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-29 08:00 | 2021-01-27 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-01-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10685 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-01-29 08:00 | Submittal Number: 08 14 16-21.0 From: ALLIE ZIMMERMAN Final Due Date: 01/22/21 Subject: CCD-082 - CCD-084 ADDED OPENINGS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 13906 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-20 | Submittal Number: 08 14 16-21.0 From: ALLIE ZIMMERMAN Final Due Date: 01/22/21 Subject: CCD-082 - CCD-084 ADDED OPENINGS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 14277 | Responded and Closed | Approved | 2021-01-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | Submittal 08 14 16_21 Revision 0 CCD_082 CCD_084 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | Submittal 08 14 16_21 Revision 0 CCD_082 CCD_084 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-27 |  | Submittal 08 14 16_21 Revision 0 CCD_082 CCD_084 Added Openings_MAM Reviewed_POP.pdf
08 14 16-022-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-022-00 FLUSH WOOD DOORS - CCD-086 - CCD-087 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-03 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-17 | 2021-03-12 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-03-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11766 | Received | For Review | 2021-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-03-17 | Submittal Number: 08 14 16-22.0 From: ALLIE ZIMMERMAN Final Due Date: 03/17/21 Subject: FLUSH WOOD DOORS - CCD-086 - CCD-087 ADDED OPENINGS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 15243 | Forwarded | For Review | 2021-03-03 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-10 | Submittal Number: 08 14 16-22.0 From: ALLIE ZIMMERMAN Final Due Date: 03/17/21 Subject: FLUSH WOOD DOORS - CCD-086 - CCD-087 ADDED OPENINGS Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 15508 | Responded and Closed | Approved | 2021-03-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-03 |  | Submittal 08 14 16-22 Revision 0 FLUSH WOOD DOORS - CCD-086 - CCD-087 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-03 |  | Submittal 08 14 16-22 Revision 0 FLUSH WOOD DOORS - CCD-086 - CCD-087 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-12 |  | Submittal 08 14 16-22 Revision 0 FLUSH WOOD DOORS - CCD-086 - CCD-087 Added Openings_MAM Reviewed_POP.pdf
08 14 16-024-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-024-00 FLUSH WOOD DOORS - Sample Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-01 | 2021-03-26 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12095 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-04-01 | Submittal Number: 08 14 16-24.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: FLUSH WOOD DOORS - SAMPLE WARRANTY Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 15653 | Forwarded | For Review | 2021-03-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-25 | Submittal Number: 08 14 16-24.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: FLUSH WOOD DOORS - SAMPLE WARRANTY Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 15882 | Responded and Closed | Approved | 2021-03-26 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-17 |  | Submittal 08 14 16-24 Revision 0 FLUSH WOOD DOORS - Sample Warranty_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-17 |  | Submittal 08 14 16-24 Revision 0 FLUSH WOOD DOORS - Sample Warranty_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-26 |  | Submittal 08 14 16-24 Revision 0 FLUSH WOOD DOORS - Sample Warranty_MAM Reviewed_POP.pdf
08 14 16-027-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-027-00 FLUSH WOOD DOORS - WD6 Verification Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-05-20 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-05-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13141 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-02 07:00 | Submittal Number: 08 14 16-27.0 From: ALLIE ZIMMERMAN Final Due Date: 05/31/21 Subject: FLUSH WOOD DOORS - WD6 VERIFICATION SAMPLE Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 17001 | Forwarded | For Review | 2021-05-18 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-25 | Submittal Number: 08 14 16-27.0 From: ALLIE ZIMMERMAN Final Due Date: 05/31/21 Subject: FLUSH WOOD DOORS - WD6 VERIFICATION SAMPLE Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 13198 | Review Response | Approved | 2021-05-20 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17086 | Responded and Closed | Approved | 2021-05-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | Submittal 08 14 16-27 Revision 0 FLUSH WOOD DOORS - WD6 Verification Sample_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-17 |  | Submittal 08 14 16-27 Revision 0 FLUSH WOOD DOORS - WD6 Verification Sample_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-05-20 |  | Submittal 08 14 16-27 Revision 0 FLUSH WOOD DOORS - WD6 Verification Sample_MAM Reviewed_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-17 |  | Submittal 08 14 16-27 Revision 0 FLUSH WOOD DOORS - WD6 Verification Sample_MAM Reviewed.pdf
08 14 16-028-00 | 08 14 16 - FLUSH WOOD DOORS | 08 14 16-028-00 FLUSH WOOD DOORS - WD17 Verification Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-28 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-14 07:00 | 2021-06-08 | 12 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-06-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13314 | Received | For Review | 2021-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-06-14 07:00 | Submittal Number: 08 14 16-28.0 From: ALLIE ZIMMERMAN Final Due Date: 06/10/21 Subject: FLUSH WOOD DOORS - WD17 VERIFICATION SAMPLE Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 17229 | Forwarded | For Review | 2021-06-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 08 14 16-28.0 From: ALLIE ZIMMERMAN Final Due Date: 06/10/21 Subject: FLUSH WOOD DOORS - WD17 VERIFICATION SAMPLE Description: Spec Section: 08 14 16 - FLUSH WOOD DOORS Status: OPEN | Info Exchange
| 13462 | Review Response | Approved | 2021-06-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17407 | Responded and Closed | Approved | 2021-06-08 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-27 |  | Submittal 08 14 16-28 Revision 0 FLUSH WOOD DOORS - WD17 Verification Sample_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-27 |  | Submittal 08 14 16-28 Revision 0 FLUSH WOOD DOORS - WD17 Verification Sample_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-08 |  | Submittal 08 14 16-28 Revision 0 FLUSH WOOD DOORS - WD17 Verification Sample_MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-05-27 |  | Submittal 08 14 16-28 Revision 0 FLUSH WOOD DOORS - WD17 Verification Sample_MAM Reviewed.pdf
08 31 13-005-00 | 08 31 13 - ACCESS DOORS AND FRAMES | 08 31 13-005-00 Ice Melt Pit Lid Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-14 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-06 | 2021-01-05 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2021-01-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10136 | Received | For Review | 2020-12-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2021-01-06 | Submittal Number: 08 31 13-5.0 From: CHRISTIAN ALBERS Final Due Date: 12/28/20 Subject: ICE MELT PIT LID SHOP DRAWINGS Description: PLEASE SEE ATTACHED SHOP DRAWINGS FOR ICE MELT PIT LID. Spec Section: 08 31 13 - ACCESS DOORS AND FRAMES Status: OPEN | Info Exchange
| 13256 | Forwarded | For Review | 2020-12-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-21 | Submittal Number: 08 31 13-5.0 From: CHRISTIAN ALBERS Final Due Date: 12/28/20 Subject: ICE MELT PIT LID SHOP DRAWINGS Description: PLEASE SEE ATTACHED SHOP DRAWINGS FOR ICE MELT PIT LID. Spec Section: 08 31 13 - ACCESS DOORS AND FRAMES Status: OPEN | Info Exchange
| 13636 | Responded and Closed | Approved | 2021-01-05 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-14 |  | 08 31 13 - 005 - Ice Melt Pit Lid Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-14 |  | 08 31 13 - 005 - Ice Melt Pit Lid Shop Drawings.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-01-05 |  | 08 31 13 - 005 - Ice Melt Pit Lid Shop Drawings-POP.pdf
08 31 13-006-00 | 08 31 13 - ACCESS DOORS AND FRAMES | 08 31 13-006-00 24x48 access panel for 400lvl Suites | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-22 08:00 | 2021-01-20 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10497 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-22 08:00 | Submittal Number: 08 31 13-6.0 From: GRETCHEN TOSHACH Final Due Date: 01/20/21 Subject: 24X48 ACCESS PANEL FOR 400LVL SUITES Description: Spec Section: 08 31 13 - ACCESS DOORS AND FRAMES Status: OPEN | Info Exchange
| 13700 | Forwarded | For Review | 2021-01-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-13 | Submittal Number: 08 31 13-6.0 From: GRETCHEN TOSHACH Final Due Date: 01/20/21 Subject: 24X48 ACCESS PANEL FOR 400LVL SUITES Description: Spec Section: 08 31 13 - ACCESS DOORS AND FRAMES Status: OPEN | Info Exchange
| 14064 | Responded and Closed | Approved | 2021-01-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-06 |  | 08 31 13-6.0 Lvl 400 Suites Access Panels - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-06 |  | 08 31 13-6.0 Lvl 400 Suites Access Panels - MAM.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-20 |  | 08 31 13-6.0 Lvl 400 Suites Access Panels - MAM_POP.pdf
08 31 13-007-00 | 08 31 13 - ACCESS DOORS AND FRAMES | 08 31 13-007-00 ACCESS DOORS AND FRAMES - NW/NE Snorkel Egress - Kendell | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-01 | Responded and Closed - No Action Taken or Required |  | Bryan Klote (Populous), Todd Spangler (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-09-15 | 2021-09-21 | 21 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14555 | Received | For Review | 2021-09-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-09-15 | Submittal Number: 08 31 13-7.0 From: ALLIE ZIMMERMAN Final Due Date: 09/14/21 Subject: ACCESS DOORS AND FRAMES - NW/NE SNORKEL EGRESS - KENDELL Description: Spec Section: 08 31 13 - ACCESS DOORS AND FRAMES Status: OPEN | Info Exchange
| 18767 | Forwarded | For Review | 2021-09-02 | Populous SCA_CCA | Bryan Klote (Populous); Todd Spangler (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-09-09 | Submittal Number: 08 31 13-7.0 From: ALLIE ZIMMERMAN Final Due Date: 09/14/21 Subject: ACCESS DOORS AND FRAMES - NW/NE SNORKEL EGRESS - KENDELL Description: Spec Section: 08 31 13 - ACCESS DOORS AND FRAMES Status: OPEN | Info Exchange
| 18941 | Responded and Closed | No Action Taken or Required | 2021-09-21 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | Voided per Mortenson's request. -POP 9/21/2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-01 02:00 |  | Submittal 08 31 13-7 Revision 0 ACCESS DOORS AND FRAMES - NWNE Snorkel Egress - Kendell_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-09-01 02:00 |  | Submittal 08 31 13-7 Revision 0 ACCESS DOORS AND FRAMES - NWNE Snorkel Egress - Kendell_MAM Reviewed.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-09-01 |  | Submittal 08 31 13-7 Revision 0 ACCESS DOORS AND FRAMES - NWNE Snorkel Egress - Kendell_MAM Reviewed.pdf
08 32 13-001-00 | 08 32 13 | 08 32 13-001-00 SLIDING ALUMINUM-FRAMED GLASS DOORS - Mechanical Mezzanine Shop Drawings - Herzog | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-04 | 2021-04-27 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12665 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-04 | Submittal Number: 08 32 13-1.0 From: ALLIE ZIMMERMAN Final Due Date: 05/03/21 Subject: SLIDING ALUMINUM-FRAMED GLASS DOORS - MECHANICAL MEZZANINE SHOP DRAWINGS - HERZOG Description: Spec Section: 08 32 13 - SLIDING ALUMINUM-FRAMED GLASS DOORS Status: OPEN | Info Exchange
| 16385 | Forwarded | For Review | 2021-04-20 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 08 32 13-1.0 From: ALLIE ZIMMERMAN Final Due Date: 05/03/21 Subject: SLIDING ALUMINUM-FRAMED GLASS DOORS - MECHANICAL MEZZANINE SHOP DRAWINGS - HERZOG Description: Spec Section: 08 32 13 - SLIDING ALUMINUM-FRAMED GLASS DOORS Status: OPEN | Info Exchange
| 16536 | Responded and Closed | Approved | 2021-04-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-19 |  | Submittal 08 32 13-1 Revision 0 SLIDING ALUMINUM-FRAMED GLASS DOORS - Mechanical Mezzanine Shop Drawings - Herzog_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-19 |  | Submittal 08 32 13-1 Revision 0 SLIDING ALUMINUM-FRAMED GLASS DOORS - Mechanical Mezzanine Shop Drawings - Herzog_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-27 |  | Submittal 08 32 13-1 Revision 0 SLIDING ALUMINUM-FRAMED GLASS DOORS_MAM_POP.pdf
08 32 13-002-00 | 08 32 13 | 08 32 13-002-00 SLIDING ALUMINUM-FRAMED GLASS DOORS - Mechanical Mezzanine Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-17 | 2021-05-10 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12923 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-05-17 | Submittal Number: 08 32 13-2.0 From: ALLIE ZIMMERMAN Final Due Date: 05/17/21 Subject: SLIDING ALUMINUM-FRAMED GLASS DOORS - MECHANICAL MEZZANINE SAMPLE Description: Spec Section: 08 32 13 - SLIDING ALUMINUM-FRAMED GLASS DOORS Status: OPEN | Info Exchange
| 16705 | Forwarded | For Review | 2021-05-04 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-11 | Submittal Number: 08 32 13-2.0 From: ALLIE ZIMMERMAN Final Due Date: 05/17/21 Subject: SLIDING ALUMINUM-FRAMED GLASS DOORS - MECHANICAL MEZZANINE SAMPLE Description: Spec Section: 08 32 13 - SLIDING ALUMINUM-FRAMED GLASS DOORS Status: OPEN | Info Exchange
| 16843 | Responded and Closed | Approved | 2021-05-10 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-03 |  | Submittal 08 32 13-2 Revision 0 SLIDING ALUMINUM-FRAMED GLASS DOORS - Mechanical Mezzanine Sample_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-03 |  | Submittal 08 32 13-2 Revision 0 SLIDING ALUMINUM-FRAMED GLASS DOORS - Mechanical Mezzanine Sample_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-10 |  | Submittal 08 32 13-2 Revision 0 SLIDING ALUMINUM-FRAMED GLASS DOORS - Mechanical Mezzanine Sample_MAM Reviewed_POP.pdf
08 33 23-003-00 | 08 33 23 - OVERHEAD COILING DOORS | 08 33 23-003-00 OVERHEAD COILING DOORS - Fire and Service Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-22 | Responded and Closed - Approved |  | Tom Usher (Populous), Chad Francis (Populous) |  |  |  | 2021-03-08 | 2021-02-25 | 4 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11557 | Received | For Review | 2021-02-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ye Zhang (Mortenson Construction) | 2021-03-08 | Submittal Number: 08 33 23-3.0 From: ALLIE ZIMMERMAN Final Due Date: 02/22/21 Subject: OVERHEAD COILING DOORS - FIRE AND SERVICE SAMPLES Description: SAMPLES FOR VERIFICATION : OF EACH TYPE OF EXPOSED FINISH REQUIRED, PREPARED ON SAMPLES OF SIZE INDICATED BELOW. 1. CURTAIN SLATS: 12 INCHES (305 MM) LONG. 2. BOTTOM BAR: 6 INCHES (150 MM) LONG. 3. GUIDES: 6 INCHES (150 MM) LONG. 4. BRACKETS: 6 INCHES (150 MM) SQUARE. 5. HOOD: 6 INCHES (150 MM) SQUARE. Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 14977 | Forwarded | For Review | 2021-02-19 | Ye Zhang (Mortenson Construction) | Tom Usher (Populous); Chad Francis (Populous) | 2021-02-26 | Submittal Number: 08 33 23-3.0 From: ALLIE ZIMMERMAN Final Due Date: 02/22/21 Subject: OVERHEAD COILING DOORS - FIRE AND SERVICE SAMPLES Description: SAMPLES FOR VERIFICATION : OF EACH TYPE OF EXPOSED FINISH REQUIRED, PREPARED ON SAMPLES OF SIZE INDICATED BELOW. 1. CURTAIN SLATS: 12 INCHES (305 MM) LONG. 2. BOTTOM BAR: 6 INCHES (150 MM) LONG. 3. GUIDES: 6 INCHES (150 MM) LONG. 4. BRACKETS: 6 INCHES (150 MM) SQUARE. 5. HOOD: 6 INCHES (150 MM) SQUARE. Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 15100 | Responded and Closed | Approved | 2021-02-25 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-19 02:00 |  | Submittal 08 33 23-3 Revision 0 OVERHEAD COILING DOORS - Fire and Service Samples_MAM Reviewed.pdf
| Forwarded |  | Ye Zhang (Mortenson Construction) | 1 | 2021-02-19 02:00 |  | 08 33 23-3.0 - Fire and Service Samples_MAM.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-25 |  | 08 33 23-3.0 - Fire and Service Samples_MAM_POP.pdf
08 33 23-005-00 | 08 33 23 - OVERHEAD COILING DOORS | 08 33 23-005-00 OVERHEAD COILING DOORS - Certifications and Qualification Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-18 | 2021-02-18 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-02-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11214 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-02-18 | Submittal Number: 08 33 23-5.0 From: ALLIE ZIMMERMAN Final Due Date: 02/18/21 Subject: OVERHEAD COILING DOORS - CERTIFICATIONS AND QUALIFICATION DATA Description: OVERSIZE CONSTRUCTION CERTIFICATION : FOR DOOR ASSEMBLIES REQUIRED TO BE FIRE-RATED AND THAT EXCEED SIZE LIMITATIONS OF LABELED ASSEMBLIES. Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 14511 | Forwarded | For Review | 2021-02-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-11 | Submittal Number: 08 33 23-5.0 From: ALLIE ZIMMERMAN Final Due Date: 02/18/21 Subject: OVERHEAD COILING DOORS - CERTIFICATIONS AND QUALIFICATION DATA Description: OVERSIZE CONSTRUCTION CERTIFICATION : FOR DOOR ASSEMBLIES REQUIRED TO BE FIRE-RATED AND THAT EXCEED SIZE LIMITATIONS OF LABELED ASSEMBLIES. Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 14934 | Responded and Closed | Approved | 2021-02-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-04 |  | Submittal 08 33 23-5 Revision 0 OVERHEAD COILING DOORS - Certifications and Qualification Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-04 |  | Submittal 08 33 23-5 Revision 0 OVERHEAD COILING DOORS - Certifications and Qualification Data_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-18 |  | Submittal 08 33 23-5 Revision 0 OVERHEAD COILING DOORS - Certifications and Qualification Data_MAM Reviewed_POP.pdf
08 33 23-006-00 | 08 33 23 - OVERHEAD COILING DOORS | 08 33 23-006-00 OVERHEAD COILING DOORS - SERVICE - Shop Drawings and Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-01 08:00 | 2021-02-04 | 21 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10721 | Received | For Review | 2021-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-02-01 08:00 | Submittal Number: 08 33 23-6.0 From: ALLIE ZIMMERMAN Final Due Date: 01/26/21 Subject: OVERHEAD COILING DOORS - SERVICE - SHOP DRAWINGS AND PRODUCT DATA Description: PRODUCT DATA: FOR EACH TYPE AND SIZE OF OVERHEAD COILING DOOR AND ACCESSORY. INCLUDE THE FOLLOWING: (1) SUMMARY OF FORCES AND LOADS GENERATED BY DOOR SYSTEM ON WALLS AND JAMBS. (2) FIRE-RATED DOORS: INCLUDE DESCRIPTION OF FIRE-RELEASE SYSTEM INCLUDING TESTING AND RESETTING INSTRUCTIONS. SHOP DRAWINGS: FOR SPECIAL COMPONENTS AND INSTALLATIONS NOT DIMENSIONED OR DETAILED IN MANUFACTURER'S PRODUCT DATA. Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 13949 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-21 | Submittal Number: 08 33 23-6.0 From: ALLIE ZIMMERMAN Final Due Date: 01/26/21 Subject: OVERHEAD COILING DOORS - SERVICE - SHOP DRAWINGS AND PRODUCT DATA Description: PRODUCT DATA: FOR EACH TYPE AND SIZE OF OVERHEAD COILING DOOR AND ACCESSORY. INCLUDE THE FOLLOWING: (1) SUMMARY OF FORCES AND LOADS GENERATED BY DOOR SYSTEM ON WALLS AND JAMBS. (2) FIRE-RATED DOORS: INCLUDE DESCRIPTION OF FIRE-RELEASE SYSTEM INCLUDING TESTING AND RESETTING INSTRUCTIONS. SHOP DRAWINGS: FOR SPECIAL COMPONENTS AND INSTALLATIONS NOT DIMENSIONED OR DETAILED IN MANUFACTURER'S PRODUCT DATA. Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 14519 | Responded and Closed | Approved as Noted | 2021-02-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | CCD_054_Combined Arch.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | Submittal 08 33 23_6 Revision 0 OVERHEAD COILING DOORS _ SERVICE _ Shop Drawings and Product Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | CCD_054_Combined Arch.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | Submittal 08 33 23_6 Revision 0 OVERHEAD COILING DOORS _ SERVICE _ Shop Drawings and Product Data_MAM Reviewed.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-02-04 |  | Submittal 08 33 23_6 Revision 0 OVERHEAD COILING DOORS _ SERVICE _ Shop Drawings and Product Data_MAM Reviewed-POP-CLM.pdf
08 33 23-007-00 | 08 33 23 - OVERHEAD COILING DOORS | 08 33 23-007-00 OVERHEAD COILING DOORS - FIRE - Shop Drawings and Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-15 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-01 08:00 | 2021-02-04 | 21 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10722 | Received | For Review | 2021-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-02-01 08:00 | Submittal Number: 08 33 23-7.0 From: ALLIE ZIMMERMAN Final Due Date: 01/26/21 Subject: OVERHEAD COILING DOORS - FIRE - SHOP DRAWINGS AND PRODUCT DATA Description: PRODUCT DATA: FOR EACH TYPE AND SIZE OF OVERHEAD COILING DOOR AND ACCESSORY. INCLUDE THE FOLLOWING: (1) SUMMARY OF FORCES AND LOADS GENERATED BY DOOR SYSTEM ON WALLS AND JAMBS. (2) FIRE-RATED DOORS: INCLUDE DESCRIPTION OF FIRE-RELEASE SYSTEM INCLUDING TESTING AND RESETTING INSTRUCTIONS. SHOP DRAWINGS: FOR SPECIAL COMPONENTS AND INSTALLATIONS NOT DIMENSIONED OR DETAILED IN MANUFACTURER'S PRODUCT DATA. Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 13950 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-21 | Submittal Number: 08 33 23-7.0 From: ALLIE ZIMMERMAN Final Due Date: 01/26/21 Subject: OVERHEAD COILING DOORS - FIRE - SHOP DRAWINGS AND PRODUCT DATA Description: PRODUCT DATA: FOR EACH TYPE AND SIZE OF OVERHEAD COILING DOOR AND ACCESSORY. INCLUDE THE FOLLOWING: (1) SUMMARY OF FORCES AND LOADS GENERATED BY DOOR SYSTEM ON WALLS AND JAMBS. (2) FIRE-RATED DOORS: INCLUDE DESCRIPTION OF FIRE-RELEASE SYSTEM INCLUDING TESTING AND RESETTING INSTRUCTIONS. SHOP DRAWINGS: FOR SPECIAL COMPONENTS AND INSTALLATIONS NOT DIMENSIONED OR DETAILED IN MANUFACTURER'S PRODUCT DATA. Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 14522 | Responded and Closed | Approved | 2021-02-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | CCD_054_Combined Arch.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | Submittal 08 33 23_7 Revision 0 OVERHEAD COILING DOORS _ FIRE _ Shop Drawings and Product Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | CCD_054_Combined Arch.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | Submittal 08 33 23_7 Revision 0 OVERHEAD COILING DOORS _ FIRE _ Shop Drawings and Product Data_MAM Reviewed.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-02-04 |  | Submittal 08 33 23_7-OVERHEAD COILING DOORS_FIRE_MAM_POP.pdf
08 33 23-008-00 | 08 33 23 - OVERHEAD COILING DOORS | 08 33 23-008-00 OVERHEAD COILING DOORS - COUNTER - Shop Drawings and Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-01 08:00 | 2021-01-29 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-01-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10723 | Received | For Review | 2021-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-02-01 08:00 | Submittal Number: 08 33 23-8.0 From: ALLIE ZIMMERMAN Final Due Date: 01/26/21 Subject: OVERHEAD COILING DOORS - COUNTER - SHOP DRAWINGS AND PRODUCT DATA Description: PRODUCT DATA: FOR EACH TYPE AND SIZE OF OVERHEAD COILING DOOR AND ACCESSORY. INCLUDE THE FOLLOWING: (1) SUMMARY OF FORCES AND LOADS GENERATED BY DOOR SYSTEM ON WALLS AND JAMBS. (2) FIRE-RATED DOORS: INCLUDE DESCRIPTION OF FIRE-RELEASE SYSTEM INCLUDING TESTING AND RESETTING INSTRUCTIONS. SHOP DRAWINGS: FOR SPECIAL COMPONENTS AND INSTALLATIONS NOT DIMENSIONED OR DETAILED IN MANUFACTURER'S PRODUCT DATA. Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 13951 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-21 | Submittal Number: 08 33 23-8.0 From: ALLIE ZIMMERMAN Final Due Date: 01/26/21 Subject: OVERHEAD COILING DOORS - COUNTER - SHOP DRAWINGS AND PRODUCT DATA Description: PRODUCT DATA: FOR EACH TYPE AND SIZE OF OVERHEAD COILING DOOR AND ACCESSORY. INCLUDE THE FOLLOWING: (1) SUMMARY OF FORCES AND LOADS GENERATED BY DOOR SYSTEM ON WALLS AND JAMBS. (2) FIRE-RATED DOORS: INCLUDE DESCRIPTION OF FIRE-RELEASE SYSTEM INCLUDING TESTING AND RESETTING INSTRUCTIONS. SHOP DRAWINGS: FOR SPECIAL COMPONENTS AND INSTALLATIONS NOT DIMENSIONED OR DETAILED IN MANUFACTURER'S PRODUCT DATA. Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 14344 | Responded and Closed | Approved as Noted | 2021-01-29 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | CCD_054_Combined Arch.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | Submittal 08 33 23_8 Revision 0 OVERHEAD COILING DOORS _ COUNTER -_ Shop Drawings _ Product Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | CCD_054_Combined Arch.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | Submittal 08 33 23_8 Revision 0 OVERHEAD COILING DOORS _ COUNTER -_ Shop Drawings _ Product Data_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-29 |  | Submittal 08 33 23_8 Revision 0 OVERHEAD COILING DOORS _ COUNTER -_ Shop Drawings _ Product Data_MAM Reviewed_POP.pdf
08 33 23-009-00 | 08 33 23 - OVERHEAD COILING DOORS | 08 33 23-009-00 OVERHEAD COILING DOORS - Counter Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-01 | 2021-03-26 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12103 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-04-01 | Submittal Number: 08 33 23-9.0 From: ALLIE ZIMMERMAN Final Due Date: 04/01/21 Subject: OVERHEAD COILING DOORS - COUNTER SAMPLES Description: Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 15662 | Forwarded | For Review | 2021-03-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-25 | Submittal Number: 08 33 23-9.0 From: ALLIE ZIMMERMAN Final Due Date: 04/01/21 Subject: OVERHEAD COILING DOORS - COUNTER SAMPLES Description: Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 15883 | Responded and Closed | Approved | 2021-03-26 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-18 |  | Submittal 08 33 23-9 Revision 0 OVERHEAD COILING DOORS - Counter Samples_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-18 |  | Submittal 08 33 23-9 Revision 0 OVERHEAD COILING DOORS - Counter Samples_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-26 |  | Submittal 08 33 23-9 Revision 0 OVERHEAD COILING DOORS - Counter Samples_MAM Reviewed_POP.pdf
08 33 23-010-00 | 08 33 23 - OVERHEAD COILING DOORS | 08 33 23-010-00 OVERHEAD COILING DOORS - SERVICE - Garage Entry Door Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-04 | 2021-05-06 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12664 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-05-04 | Submittal Number: 08 33 23-10.0 From: ALLIE ZIMMERMAN Final Due Date: 05/03/21 Subject: OVERHEAD COILING DOORS - SERVICE - GARAGE ENTRY DOOR SHOP DRAWINGS Description: Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 16384 | Forwarded | For Review | 2021-04-20 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 08 33 23-10.0 From: ALLIE ZIMMERMAN Final Due Date: 05/03/21 Subject: OVERHEAD COILING DOORS - SERVICE - GARAGE ENTRY DOOR SHOP DRAWINGS Description: Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 16779 | Responded and Closed | Approved as Noted | 2021-05-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-19 |  | Submittal 08 33 23-10 Revision 0 OVERHEAD COILING DOORS - SERVICE - Garage Entry Door Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-19 |  | Submittal 08 33 23-10 Revision 0 OVERHEAD COILING DOORS - SERVICE - Garage Entry Door Shop Drawings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-06 |  | Submittal 08 33 23-10 Revision 0 OVERHEAD COILING DOORS - SERVICE - Garage Entry Door Shop Drawings_MAM Reviewed_POP.pdf
08 33 23-011-00 | 08 33 23 - OVERHEAD COILING DOORS | 08 33 23-011-00 OVERHEAD COILING DOORS - Loading Dock Fabric Door C01.12.01D1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Mark Lievens (ME Engineers) |  |  |  | 2021-06-03 07:00 | 2021-06-03 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13173 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-03 07:00 | Submittal Number: 08 33 23-11.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: OVERHEAD COILING DOORS - LOADING DOCK FABRIC DOOR C01.12.01D1 Description: Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 17055 | Forwarded | For Review | 2021-05-19 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-26 | Submittal Number: 08 33 23-11.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: OVERHEAD COILING DOORS - LOADING DOCK FABRIC DOOR C01.12.01D1 Description: Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 17223 | Forwarded | For Review | 2021-06-01 | Allie Zimmerman | Mark Lievens (ME Engineers) | 2021-06-03 | Submittal Number: 08 33 23-11.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: OVERHEAD COILING DOORS - LOADING DOCK FABRIC DOOR C01.12.01D1 Description: Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 13376 | Review Response | Approved as Noted | 2021-06-03 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.06.03 | Info Exchange
| 17306 | Responded and Closed | Approved as Noted | 2021-06-03 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 08 33 23-11 Revision 0 OVERHEAD COILING DOORS - Loading Dock Fabric Door C01.12.01D1_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 08 33 23-11 Revision 0 OVERHEAD COILING DOORS - Loading Dock Fabric Door C01.12.01D1_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 08 33 23-11 Revision 0 OVERHEAD COILING DOORS - Loading Dock Fabric Door C01.12.01D1_MAM Reviewed.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-05-18 |  | Submittal 08 33 23-11 Revision 0 OVERHEAD COILING DOORS - Loading Dock Fabric Door C01.12.01D1_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-06-03 |  | Submittal 08 33 23-11 Revision 0 OVERHEAD COILING DOORS - Loading Dock Fabric Door C01.12.01D1_MAM Reviewed-ME.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-06-03 |  | Submittal 08 33 23-11- Loading Dock Fabric Door C01.12.01D1_MAM-ME-POP.pdf
08 33 23-012-00 | 08 33 23 - OVERHEAD COILING DOORS | 08 33 23-012-00 OVERHEAD COILING DOORS - Loading Dock Fabric Door C01.12.01D1 Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Mark Lievens (ME Engineers) |  |  |  | 2021-06-03 07:00 | 2021-06-03 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13172 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-03 07:00 | Submittal Number: 08 33 23-12.0 From: ALLIE ZIMMERMAN Final Due Date: 06/02/21 Subject: OVERHEAD COILING DOORS - LOADING DOCK FABRIC DOOR C01.12.01D1 SAMPLES Description: Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 17054 | Forwarded | For Review | 2021-05-19 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-26 | Submittal Number: 08 33 23-12.0 From: ALLIE ZIMMERMAN Final Due Date: 06/02/21 Subject: OVERHEAD COILING DOORS - LOADING DOCK FABRIC DOOR C01.12.01D1 SAMPLES Description: Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 17224 | Forwarded | For Review | 2021-06-01 | Allie Zimmerman | Mark Lievens (ME Engineers) | 2021-06-03 | Submittal Number: 08 33 23-12.0 From: ALLIE ZIMMERMAN Final Due Date: 06/02/21 Subject: OVERHEAD COILING DOORS - LOADING DOCK FABRIC DOOR C01.12.01D1 SAMPLES Description: Spec Section: 08 33 23 - OVERHEAD COILING DOORS Status: OPEN | Info Exchange
| 13379 | Review Response | Not Required For Review | 2021-06-03 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Samples not required for electrical review. Thanks, Mark Lievens ME Engineers 2021.06.03 | Info Exchange
| 17307 | Responded and Closed | Approved as Noted | 2021-06-03 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 08 33 23-12 Revision 0 OVERHEAD COILING DOORS - Loading Dock Fabric Door C01.12.01D1 Samples_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 08 33 23-12 Revision 0 OVERHEAD COILING DOORS - Loading Dock Fabric Door C01.12.01D1 Samples_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 08 33 23-12 Revision 0 OVERHEAD COILING DOORS - Loading Dock Fabric Door C01.12.01D1 Samples_MAM Reviewed.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-05-18 |  | Submittal 08 33 23-12 Revision 0 OVERHEAD COILING DOORS - Loading Dock Fabric Door C01.12.01D1 Samples_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-06-03 |  | Submittal 08 33 23-12 - Loading Dock Fabric Door C01.12.01D1-MAM-POP.pdf
08 38 00-001-00 | 08 38 00 | 08 38 00-001-00 TRAFFIC DOORS - CCD 094 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-30 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-14 | 2021-05-10 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12871 | Received | For Review | 2021-04-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-14 | Submittal Number: 083800-1.0 From: ALLIE ZIMMERMAN Final Due Date: 05/14/21 Subject: TRAFFIC DOORS - CCD 094 ADDED OPENINGS Description: Spec Section: 083800 - TRAFFIC DOORS Status: OPEN | Info Exchange
| 16653 | Forwarded | For Review | 2021-04-30 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-07 | Submittal Number: 083800-1.0 From: ALLIE ZIMMERMAN Final Due Date: 05/14/21 Subject: TRAFFIC DOORS - CCD 094 ADDED OPENINGS Description: Spec Section: 083800 - TRAFFIC DOORS Status: OPEN | Info Exchange
| 16842 | Responded and Closed | Approved as Noted | 2021-05-10 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-30 |  | Submittal 08 38 00-1 Revision 0 TRAFFIC DOORS - CCD 094 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-30 |  | Submittal 08 38 00-1 Revision 0 TRAFFIC DOORS - CCD 094 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-10 |  | Submittal 08 38 00-1 Revision 0 TRAFFIC DOORS - CCD 094 Added Openings_MAM Reviewed_POP.pdf
08 38 00-002-00 | 08 38 00 | 08 38 00-002-00 TRAFFIC DOORS - CCD 094 Added Openings Verification Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-14 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-28 | 2021-06-16 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-06-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13521 | Received | For Review | 2021-06-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-06-28 | Submittal Number: 083800-2.0 From: ALLIE ZIMMERMAN Final Due Date: 06/28/21 Subject: TRAFFIC DOORS - CCD 094 ADDED OPENINGS VERIFICATION SAMPLES Description: Spec Section: 083800 - TRAFFIC DOORS Status: OPEN | Info Exchange
| 17491 | Forwarded | For Review | 2021-06-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-21 | Submittal Number: 083800-2.0 From: ALLIE ZIMMERMAN Final Due Date: 06/28/21 Subject: TRAFFIC DOORS - CCD 094 ADDED OPENINGS VERIFICATION SAMPLES Description: Spec Section: 083800 - TRAFFIC DOORS Status: OPEN | Info Exchange
| 17537 | Responded and Closed | Approved | 2021-06-16 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-14 |  | Submittal 083800-2 Revision 0 TRAFFIC DOORS - CCD 094 Added Openings Verification Samples_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-14 |  | Submittal 083800-2 Revision 0 TRAFFIC DOORS - CCD 094 Added Openings Verification Samples_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-16 |  | Submittal 083800-2 Revision 0 TRAFFIC DOORS - CCD 094 Added Openings Verification Samples_MAM Reviewed_POP.pdf
08 41 13-001-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-001-00 084113 - 1.3-A - SF AND DOOR PRODUCT DATA | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-05 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-19 | 2020-05-18 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05720 | Received | For Review | 2020-05-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-19 | Submittal Number: 08 41 13-1.0 From: BROOKE BURCHAM Final Due Date: 06/08/20 Subject: 084113 - 1.3-A - SF AND DOOR PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 07754 | Forwarded | For Review | 2020-05-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-12 | Submittal Number: 08 41 13-1.0 From: BROOKE BURCHAM Final Due Date: 06/08/20 Subject: 084113 - 1.3-A - SF AND DOOR PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 07997 | Responded and Closed | Approved as Noted | 2020-05-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-04 |  | 084113-0001-0 SF and Door Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-04 |  | 084113-0001-0 SF and Door Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-18 |  | 084113-0001-0 SF and Door Product Data - POP.pdf
08 41 13-002-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-002-00 08 41 13_Premium Space - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-08 07:00 | 2020-09-02 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07682 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-08 07:00 | Submittal Number: 08 41 13-2.0 From: TYRONE THORNTON Final Due Date: 09/01/20 Subject: 08 41 13_PREMIUM SPACE - PRODUCT DATA Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10228 | Forwarded | For Review | 2020-08-24 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-31 | Submittal Number: 08 41 13-2.0 From: TYRONE THORNTON Final Due Date: 09/01/20 Subject: 08 41 13_PREMIUM SPACE - PRODUCT DATA Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10506 | Responded and Closed | Approved as Noted | 2020-09-02 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | APPROVED AT MAIN CON. CLUB, OTHER AREAS ARE CUSTOM AS DETAILED AND TO BE SUBMITTED THROUGH SHOP DRAWINGS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 08 41 13-2_CPA Storefront Product Data_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-24 |  | 08 41 13-2_CPA Storefront Product Data_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-02 |  | 08 41 13-2_CPA Storefront Product Data_MAM Review_POP.pdf
08 41 13-002-01 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-002-01 08 41 13_Premium Space - CRL Tunnel Club Base Shoe Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-04 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-21 | 2020-09-08 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07961 | Received | For Review | 2020-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-21 | Submittal Number: 08 41 13-2.1 From: TYRONE THORNTON Final Due Date: 09/18/20 Subject: 08 41 13_PREMIUM SPACE - CRL TUNNEL CLUB BASE SHOE PRODUCT DATA Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10586 | Forwarded | For Review | 2020-09-08 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-15 | Submittal Number: 08 41 13-2.1 From: TYRONE THORNTON Final Due Date: 09/18/20 Subject: 08 41 13_PREMIUM SPACE - CRL TUNNEL CLUB BASE SHOE PRODUCT DATA Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 07972 | Review Response | Approved | 2020-09-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10601 | Responded and Closed | Approved | 2020-09-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-04 |  | 08 41 13-2- CPA - Base Shoe PD1_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-04 |  | 08 41 13-2- CPA - Base Shoe PD1_MAM Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-08 |  | 08 41 13-2- CPA - Base Shoe PD1_MAM Review_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-04 |  | 08 41 13-2- CPA - Base Shoe PD1_MAM Review.pdf
08 41 13-003-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-003-00 ALUM. FRAMED ENTRANCES & STOREFRONT - Test Reports - Glazing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-17 | Responded and Closed - No Action Taken or Required |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-03 | 2021-03-29 | 41 |  | Record Copies; Transfers; Submittals |  | 41 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11508 | Received | For Review | 2021-02-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-03-03 | Submittal Number: 08 41 13-3.0 From: ALLIE ZIMMERMAN Final Due Date: 02/19/21 Subject: ALUM. FRAMED ENTRANCES & STOREFRONT - TEST REPORTS - GLAZING Description: LABORATORY TEST REPORTS: FOR SEALANTS, INDICATING COMPLIANCE WITH REQUIREMENTS FOR LOW- EMITTING MATERIALS. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 14902 | Forwarded | For Review | 2021-02-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-24 | Submittal Number: 08 41 13-3.0 From: ALLIE ZIMMERMAN Final Due Date: 02/19/21 Subject: ALUM. FRAMED ENTRANCES & STOREFRONT - TEST REPORTS - GLAZING Description: LABORATORY TEST REPORTS: FOR SEALANTS, INDICATING COMPLIANCE WITH REQUIREMENTS FOR LOW- EMITTING MATERIALS. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 15900 | Responded and Closed | No Action Taken or Required | 2021-03-29 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-17 |  | Submittal 08 41 13-3 Revision 0 ALUM. FRAMED ENTRANCES & STOREFRONT - Test Reports - Glazing_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-17 |  | Submittal 08 41 13-3 Revision 0 ALUM. FRAMED ENTRANCES & STOREFRONT - Test Reports - Glazing_MAM Reviewed.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-03-29 |  | 08 41 13-3 Revision 0 ALUM. FRAMED ENTRANCES & STOREFRONT - Test Reports - Glazing_MAM_POP.pdf
08 41 13-009-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-009-00 084113 - 1.3-C - FINISH SAMPLES | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-05 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-27 07:00 | 2020-06-15 | 42 |  | Record Copies; Transfers; Submittals | 08 41 13-009-00-01 - 08 41 13-009-00 084113 - 1.3-C - FINISH SAMPLES | 42 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05729 | Received | For Review | 2020-05-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-27 07:00 | Submittal Number: 08 41 13-9.0 From: BROOKE BURCHAM Final Due Date: 05/19/20 Subject: 084113 - 1.3-C - FINISH SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH REQUIRED, IN MANUFACTURER'S STANDARD SIZES. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 07774 | Forwarded | For Review | 2020-05-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-12 | Submittal Number: 08 41 13-9.0 From: BROOKE BURCHAM Final Due Date: 05/19/20 Subject: 084113 - 1.3-C - FINISH SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH REQUIRED, IN MANUFACTURER'S STANDARD SIZES. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 08625 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-15 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | 084113-0009-0 Finish Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-05 |  | 084113-0009-0 Finish Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-15 |  | 084113-0009-0 Finish Samples_POP.pdf
08 41 13-009-00-01 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-009-00 084113 - 1.3-C - FINISH SAMPLES | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 41 13-009-00 - 08 41 13-009-00 084113 - 1.3-C - FINISH SAMPLES | -1 | 2020-06-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-15 |  | 084113-0009-0 Finish Samples_POP.pdf
08 41 13-012-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-012-00 084113 - 1.3F - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-14 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Linda Scott (Studio 08 Consultants) |  |  |  | 2020-07-28 | 2020-08-04 | 22 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06945 | Received | For Review | 2020-07-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-07-28 | Submittal Number: 08 41 13-12.0 From: BROOKE BURCHAM Final Due Date: 07/27/20 Subject: 084113 - 1.3F - SHOP DRAWINGS Description: DELEGATED-DESIGN SUBMITTAL : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS INDICATED TO COMPLY WITH PERFORMANCE REQUIREMENTS AND DESIGN CRITERIA, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 09303 | Forwarded | For Review | 2020-07-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-07-21 | Submittal Number: 08 41 13-12.0 From: BROOKE BURCHAM Final Due Date: 07/27/20 Subject: 084113 - 1.3F - SHOP DRAWINGS Description: DELEGATED-DESIGN SUBMITTAL : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS INDICATED TO COMPLY WITH PERFORMANCE REQUIREMENTS AND DESIGN CRITERIA, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 09389 | Forwarded | For Review | 2020-07-17 | Chad Francis (Populous) | Linda Scott (Studio 08 Consultants) | 2020-07-24 | Submittal Number: 08 41 13-12.0 From: BROOKE BURCHAM Final Due Date: 07/27/20 Subject: 084113 - 1.3F - SHOP DRAWINGS Description: DELEGATED-DESIGN SUBMITTAL : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS INDICATED TO COMPLY WITH PERFORMANCE REQUIREMENTS AND DESIGN CRITERIA, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 07342 | Review Response | Approved as Noted/Resubmit | 2020-07-27 | Linda Scott (Studio 08 Consultants) | Chad Francis (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 09790 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-04 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 084113-0012-0 Alum. Storefront SD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 084113-0012-0 Alum. Storefront SD.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2020-07-13 |  | 084113-0012-0 Alum. Storefront SD.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-07-13 |  | 084113-0012-0 Alum. Storefront SD.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-04 |  | 084113-0012-0 Alum. Storefront SD - POP.pdf
08 41 13-012-01 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-012-01 084113 - 1.3F - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-08 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Linda Scott (Studio 08 Consultants) |  |  |  | 2020-12-22 | 2021-01-06 | 30 |  | Record Copies; Transfers; Submittals | 08 41 13-012-02 - 08 41 13-012-02 084113 - 1.3F - Shop Drawings | 16 |  | 2021-01-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09981 | Received | For Review | 2020-12-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-12-22 | Submittal Number: 08 41 13-12.1 From: BROOKE BURCHAM Final Due Date: 12/22/20 Subject: 084113 - 1.3F - SHOP DRAWINGS Description: DELEGATED-DESIGN SUBMITTAL : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS INDICATED TO COMPLY WITH PERFORMANCE REQUIREMENTS AND DESIGN CRITERIA, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 13065 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 08 41 13-12.1 From: BROOKE BURCHAM Final Due Date: 12/22/20 Subject: 084113 - 1.3F - SHOP DRAWINGS Description: DELEGATED-DESIGN SUBMITTAL : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS INDICATED TO COMPLY WITH PERFORMANCE REQUIREMENTS AND DESIGN CRITERIA, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 13441 | Forwarded | For Review | 2020-12-21 | Chad Francis (Populous) | Linda Scott (Studio 08 Consultants) | 2020-12-22 | Submittal Number: 08 41 13-12.1 From: BROOKE BURCHAM Final Due Date: 12/22/20 Subject: 084113 - 1.3F - SHOP DRAWINGS Description: DELEGATED-DESIGN SUBMITTAL : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS INDICATED TO COMPLY WITH PERFORMANCE REQUIREMENTS AND DESIGN CRITERIA, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10490 | Review Response | Approved as Noted | 2020-12-22 | Linda Scott (Studio 08 Consultants) | Chad Francis (Populous) |  | Chad, It appears that the hardware should work but since they didn't provide detailed drawings including the approved hardware, I noted as Reviewed with Comments. If you have any questions or comments, please feel free to contact me. Have a great holiday. Thanks. | Info Exchange
| 13690 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached for comments REVISE/RESUBMIT SHEETS 3022, 3023 PER NOTES ON SHEETS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 084113-0012-1 Alum. Storefront SD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-07 |  | 084113-0012-1 Alum. Storefront SD.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2020-12-07 |  | 084113-0012-1 Alum. Storefront SD.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-12-07 |  | 084113-0012-1 Alum. Storefront SD.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-06 |  | 084113-0012-1 Alum. Storefront SD REVIEWED ST08_POP.pdf
08 41 13-012-02 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-012-02 084113 - 1.3F - Shop Drawings | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-22 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-12 | 2021-03-29 | 36 |  | Record Copies; Transfers; Submittals | 08 41 13-012-01 - 08 41 13-012-01 084113 - 1.3F - Shop Drawings | 15 | 2021-01-20 | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11570 | Received | For Review | 2021-02-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-12 | Submittal Number: 08 41 13-12.2 From: BROOKE BURCHAM Final Due Date: 03/08/21 Subject: 084113 - 1.3F - SHOP DRAWINGS Description: DELEGATED-DESIGN SUBMITTAL : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS INDICATED TO COMPLY WITH PERFORMANCE REQUIREMENTS AND DESIGN CRITERIA, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 14992 | Forwarded | For Review | 2021-02-22 | Populous SCA_CCA | Todd Spangler (Populous); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (T... | 2021-03-01 | Submittal Number: 08 41 13-12.2 From: BROOKE BURCHAM Final Due Date: 03/08/21 Subject: 084113 - 1.3F - SHOP DRAWINGS Description: DELEGATED-DESIGN SUBMITTAL : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS INDICATED TO COMPLY WITH PERFORMANCE REQUIREMENTS AND DESIGN CRITERIA, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 11932 | Review Response | Approved as Noted | 2021-03-08 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 15899 | Responded and Closed | Approved as Noted | 2021-03-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-22 02:00 |  | 084113-0012-2 Alum. Storefront SD_Cals.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-22 02:00 |  | 084113-0012-2 Alum. Storefront SD_Cals.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-22 |  | 084113-0012-2 Alum. Storefront SD_Cals.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-29 |  | 08 41 13-0012-2 Alum. Storefront SD_Cals_TT_POPpdf.pdf
08 41 13-014-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-014-00 084113 - 1.4-B - NFRC CERTIFICATES | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-21 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-04 | 2020-09-21 | 32 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07678 | Received | For Review | 2020-08-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-04 | Submittal Number: 08 41 13-14.0 From: BROOKE BURCHAM Final Due Date: 08/28/20 Subject: 084113 - 1.4-B - NFRC CERTIFICATES Description: ENERGY PERFORMANCE CERTIFICATES : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS, ACCESSORIES, AND COMPONENTS, FROM MANUFACTURER. 1. BASIS FOR CERTIFICATION: NFRC-CERTIFIED ENERGY PERFORMANCE VALUES FOR EACH ALUMINUM- FRAMED ENTRANCE AND STOREFRONT. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10223 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-31 | Submittal Number: 08 41 13-14.0 From: BROOKE BURCHAM Final Due Date: 08/28/20 Subject: 084113 - 1.4-B - NFRC CERTIFICATES Description: ENERGY PERFORMANCE CERTIFICATES : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS, ACCESSORIES, AND COMPONENTS, FROM MANUFACTURER. 1. BASIS FOR CERTIFICATION: NFRC-CERTIFIED ENERGY PERFORMANCE VALUES FOR EACH ALUMINUM- FRAMED ENTRANCE AND STOREFRONT. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10507 | Forwarded | For Review | 2020-09-02 | Chad Francis (Populous) | Todd Spangler (Populous) | 2020-09-04 | Submittal Number: 08 41 13-14.0 From: BROOKE BURCHAM Final Due Date: 08/28/20 Subject: 084113 - 1.4-B - NFRC CERTIFICATES Description: ENERGY PERFORMANCE CERTIFICATES : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS, ACCESSORIES, AND COMPONENTS, FROM MANUFACTURER. 1. BASIS FOR CERTIFICATION: NFRC-CERTIFIED ENERGY PERFORMANCE VALUES FOR EACH ALUMINUM- FRAMED ENTRANCE AND STOREFRONT. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10553 | Forwarded | For Review | 2020-09-04 | Josh Dobken (Populous) | Josh Dobken (Populous) | 2020-09-04 | Submittal Number: 08 41 13-14.0 From: BROOKE BURCHAM Final Due Date: 08/28/20 Subject: 084113 - 1.4-B - NFRC CERTIFICATES Description: ENERGY PERFORMANCE CERTIFICATES : FOR ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS, ACCESSORIES, AND COMPONENTS, FROM MANUFACTURER. 1. BASIS FOR CERTIFICATION: NFRC-CERTIFIED ENERGY PERFORMANCE VALUES FOR EACH ALUMINUM- FRAMED ENTRANCE AND STOREFRONT. Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10931 | Responded and Closed | Approved | 2020-09-21 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 084413-0014-0 NFRC Certificates.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-20 |  | 08 41 13-14.0 NFRC Certificates.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2020-08-20 |  | 084413-0014-0 NFRC Certificates.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-08-19 02:00 |  | 084413-0014-0 NFRC Certificates.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-21 |  | 08 41 13-14.0 NFRC Certificates_POP.pdf
08 41 13-026-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-026-00 08 41 13_Premium Space - Tunnel Club Metal Cladding Paint Verification Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-11 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-25 | 2020-09-21 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08043 | Received | For Review | 2020-09-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-25 | Submittal Number: 08 41 13-26.0 From: TYRONE THORNTON Final Due Date: 09/24/20 Subject: 08 41 13_PREMIUM SPACE - TUNNEL CLUB METAL CLADDING PAINT VERIFICATION SAMPLES Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10709 | Forwarded | For Review | 2020-09-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-18 | Submittal Number: 08 41 13-26.0 From: TYRONE THORNTON Final Due Date: 09/24/20 Subject: 08 41 13_PREMIUM SPACE - TUNNEL CLUB METAL CLADDING PAINT VERIFICATION SAMPLES Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10938 | Responded and Closed | Approved | 2020-09-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-10 |  | 08 41 13- 26 - Tunnel Club Metal Cladding Paint Samples_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-10 |  | 08 41 13- 26 - Tunnel Club Metal Cladding Paint Samples_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-21 02:00 |  | 08 41 13- 26 - Tunnel Club Metal Cladding Paint Samples_MAM Review_pop.pdf
08 41 13-028-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-028-00 08 41 13_Premium Space - Qualification Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-17 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-31 | 2020-08-20 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07571 | Received | For Review | 2020-08-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-31 | Submittal Number: 08 41 13-28.0 From: TYRONE THORNTON Final Due Date: 08/31/20 Subject: 08 41 13_PREMIUM SPACE - QUALIFICATION DATA Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10077 | Forwarded | For Review | 2020-08-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-24 | Submittal Number: 08 41 13-28.0 From: TYRONE THORNTON Final Due Date: 08/31/20 Subject: 08 41 13_PREMIUM SPACE - QUALIFICATION DATA Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10175 | Responded and Closed | Revise and Resubmit | 2020-08-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | QUALIFICATION DATA SUBMITTED INDICATES WORK WITH ARCADIA, HOWEVER ARCADIA IS NOT LISTED AS AN APPROVED MFR NOR HAS THE PRODUCT DATA BEEN SUBMITTED FOR REVIEW REVISE/RESUBMIT CORRECT SCOPE FOLLOWING APPROVED PRODUCT DATA SUBMITTAL | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-17 |  | 081413 CPA- Manufacturers Certificate_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-17 |  | 081413 CPA- Manufacturers Certificate_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-20 |  | 081413 CPA- Manufacturers Certificate_MAM Review_POP.pdf
08 41 13-028-01 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-028-01 08 41 13_Premium Space - Qualification Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-08 07:00 | 2020-09-02 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07680 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-08 07:00 | Submittal Number: 08 41 13-28.1 From: TYRONE THORNTON Final Due Date: 09/08/20 Subject: 08 41 13_PREMIUM SPACE - QUALIFICATION DATA Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10224 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-31 | Submittal Number: 08 41 13-28.1 From: TYRONE THORNTON Final Due Date: 09/08/20 Subject: 08 41 13_PREMIUM SPACE - QUALIFICATION DATA Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10508 | Responded and Closed | Approved | 2020-09-02 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 084113-28_CPA Storefront Qualification Data_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 084113-28_CPA Storefront Qualification Data_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-09-02 |  | 084113-28_CPA Storefront Qualification Data_MAM Review_POP.pdf
08 41 13-032-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-032-00 08 41 13_Premium Space - Warranties | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-17 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-31 | 2020-08-20 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07573 | Received | For Review | 2020-08-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-31 | Submittal Number: 08 41 13-32.0 From: TYRONE THORNTON Final Due Date: 08/13/20 Subject: 08 41 13_PREMIUM SPACE - WARRANTIES Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10079 | Forwarded | For Review | 2020-08-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-24 | Submittal Number: 08 41 13-32.0 From: TYRONE THORNTON Final Due Date: 08/13/20 Subject: 08 41 13_PREMIUM SPACE - WARRANTIES Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10174 | Responded and Closed | Revise and Resubmit | 2020-08-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | WARRANTY SUBMITTED INDICATES WORK FOR GLAZED RAILINGS AND NOT 08 41 13 ALUMINUM FRAMED ENTRANCES AND STOREFRONTS THAT THE SUBMITTAL WAS CREATED FOR. REVISE/RESUBMIT CORRECT SCOPE FOLLOWING APPROVED PRODUCT DATA SUBMITTAL | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-17 |  | 084113 CPA - CRL GRS Warranty_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-17 |  | 084113 CPA - CRL GRS Warranty_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-20 |  | 084113 CPA - CRL GRS Warranty_MAM Review_POP.pdf
08 41 13-032-01 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-032-01 08 41 13_Premium Space - Warranties | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-03 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-18 | 2020-09-14 | 12 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07960 | Received | For Review | 2020-09-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-18 | Submittal Number: 08 41 13-32.1 From: TYRONE THORNTON Final Due Date: 09/10/20 Subject: 08 41 13_PREMIUM SPACE - WARRANTIES Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10585 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-15 | Submittal Number: 08 41 13-32.1 From: TYRONE THORNTON Final Due Date: 09/10/20 Subject: 08 41 13_PREMIUM SPACE - WARRANTIES Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 10753 | Responded and Closed | Approved | 2020-09-14 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-03 |  | 08 41 13-32 CPA- Sample Warranties.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-03 |  | 08 41 13-32 CPA- Sample Warranties.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-09-14 |  | 08 41 13-32 CPA- Sample Warranties_POP.pdf
08 41 13-033-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-033-00 1.3F - Hardware Coordination Atrium Doors - Mission Glass | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-19 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Linda Scott (Studio 08 Consultants) |  |  |  | 2021-02-02 | 2021-01-28 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-01-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10761 | Received | For Review | 2021-01-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2021-02-02 | Submittal Number: 08 41 13-33.0 From: BROOKE BURCHAM Final Due Date: 02/02/21 Subject: 084113 - 1.3F - HARDWARE COORDINATION ATRIUM DOORS - MISSION GLASS Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 13996 | Forwarded | For Review | 2021-01-19 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-26 | Submittal Number: 08 41 13-33.0 From: BROOKE BURCHAM Final Due Date: 02/02/21 Subject: 084113 - 1.3F - HARDWARE COORDINATION ATRIUM DOORS - MISSION GLASS Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 14314 | Forwarded | For Review | 2021-01-28 | Chad Francis (Populous) | Linda Scott (Studio 08 Consultants) | 2021-02-02 | Submittal Number: 08 41 13-33.0 From: BROOKE BURCHAM Final Due Date: 02/02/21 Subject: 084113 - 1.3F - HARDWARE COORDINATION ATRIUM DOORS - MISSION GLASS Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 11032 | Review Response | Approved | 2021-01-28 | Linda Scott (Studio 08 Consultants) | Chad Francis (Populous) |  | Please find attached the reviewed submittal referenced above. If you have questions or comments, please call. Thanks. | Info Exchange
| 14327 | Responded and Closed | Approved | 2021-01-28 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-19 |  | 084414-0033-0 Hardware Coordination - Atrium Doors.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-19 |  | 084414-0033-0 Hardware Coordination - Atrium Doors.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2021-01-19 |  | 084414-0033-0 Hardware Coordination - Atrium Doors.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-01-19 |  | 084414-0033-0 Hardware Coordination - Atrium Doors.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-28 |  | 084414-0033-0 Hardware Coordination - Atrium Doors REVIEWED ST08_POP.pdf
08 41 13-034-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-034-00 ALUM. FRAMED ENTRANCES & STOREFRONT - Clear Anodized Profile | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-26 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-09 | 2021-03-26 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12269 | Received | For Review | 2021-03-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2021-04-09 | Submittal Number: 08 41 13-34.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: ALUM. FRAMED ENTRANCES & STOREFRONT - Clear Anodized Profile Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Email
| 15868 | Forwarded | For Review | 2021-03-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-02 | Submittal Number: 08 41 13-34.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: ALUM. FRAMED ENTRANCES & STOREFRONT - Clear Anodized Profile Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 15884 | Responded and Closed | Approved | 2021-03-26 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-26 |  | 08 41 13-034-00 ALUM. FRAMED ENTRANCES & STOREFRONT.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-26 |  | 08 41 13-034-00 ALUM. FRAMED ENTRANCES & STOREFRONT.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-23 |  | Submittal 08 41 13-34 Revision 0 ALUM. FRAMED ENTRANCES STOREFRONT - Clear Anodized Profile Samples_POP.pdf
08 41 13-035-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-035-00 ALUM. FRAMED ENTRANCES & STOREFRONT - Arcadia A450 Series - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-10 07:00 | 2021-06-08 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-06-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13272 | Received | For Review | 2021-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-10 07:00 | Submittal Number: 08 41 13-35.0 From: ALLIE ZIMMERMAN Final Due Date: 06/09/21 Subject: ALUM. FRAMED ENTRANCES & STOREFRONT - ARCADIA A450 SERIES - PRODUCT DATA Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 17173 | Forwarded | For Review | 2021-05-26 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-02 | Submittal Number: 08 41 13-35.0 From: ALLIE ZIMMERMAN Final Due Date: 06/09/21 Subject: ALUM. FRAMED ENTRANCES & STOREFRONT - ARCADIA A450 SERIES - PRODUCT DATA Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 17399 | Responded and Closed | Approved as Noted | 2021-06-08 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-25 |  | Submittal 08 41 13-35 Revision 0 ALUM. FRAMED ENTRANCES STOREFRONT - Arcadia A450 Series - Product Data_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-25 |  | Submittal 08 41 13-35 Revision 0 ALUM. FRAMED ENTRANCES STOREFRONT - Arcadia A450 Series - Product Data_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-08 |  | Submittal 08 41 13-35 Revision 0 ALUM. FRAMED ENTRANCES STOREFRONT - Arcadia A450 Series - Product Data_MAM Reviewed_POP.pdf
08 41 13-036-00 | 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS | 08 41 13-036-00 ALUM. FRAMED ENTRANCES & STOREFRONT - Black Anodized Profile Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-24 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-07 | 2021-03-26 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12200 | Received | For Review | 2021-03-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-04-07 | Submittal Number: 08 41 13-36.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: ALUM. FRAMED ENTRANCES & STOREFRONT - BLACK ANODIZED PROFILE SAMPLES Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 15786 | Forwarded | For Review | 2021-03-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-31 | Submittal Number: 08 41 13-36.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: ALUM. FRAMED ENTRANCES & STOREFRONT - BLACK ANODIZED PROFILE SAMPLES Description: Spec Section: 08 41 13 - ALUMINUM-FRAMED ENTRANCES AND STOREFRONTS Status: OPEN | Info Exchange
| 15842 | Responded and Closed | Approved | 2021-03-26 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-24 |  | Submittal 08 41 13-34 Revision 0 ALUM. FRAMED ENTRANCES & STOREFRONT - Black Anodized Profile - RG REVIEW.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-24 |  | Submittal 08 41 13-34 Revision 0 ALUM. FRAMED ENTRANCES & STOREFRONT - Black Anodized Profile Samples_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-24 |  | Submittal 08 41 13-34 Revision 0 ALUM. FRAMED ENTRANCES & STOREFRONT - Black Anodized Profile - RG REVIEW.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-24 |  | Submittal 08 41 13-34 Revision 0 ALUM. FRAMED ENTRANCES & STOREFRONT - Black Anodized Profile Samples_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-26 |  | Submittal 08 41 13-34 Revision 0 ALUM. FRAMED ENTRANCES & STOREFRONT - Black Anodized Profile Samples_MAM Reviewed_POP.pdf
08 42 29-001-00 | 08 42 29 | 08 42 29-001-00 AUTOMATIC ENTRANCES - NHL Home and WNBA Locker | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Rick Lewis (Studio 08 Consultants), Linda Scott (Studio 08 Consultants), Mark Lievens (ME Engineers) |  |  |  | 2021-04-19 | 2021-04-16 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-04-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12400 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-19 | Submittal Number: 08 42 29-1.0 From: ALLIE ZIMMERMAN Final Due Date: 4/13/2021 Subject: AUTOMATIC ENTRANCES - NHL Home and WNBA Locker Spec Section: 08 42 29 Status: OPEN | Email
| 16072 | Forwarded | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 08 42 29-1.0 From: ALLIE ZIMMERMAN Final Due Date: 4/13/2021 Subject: AUTOMATIC ENTRANCES - NHL Home and WNBA Locker Spec Section: 08 42 29 Status: OPEN | Info Exchange
| 16213 | Forwarded | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Rick Lewis (Studio 08 Consultants); Linda Scott (Studio 08 Consultants) |  | Submittal Number: 08 42 29-1.0 From: ALLIE ZIMMERMAN Final Due Date: 4/13/2021 Subject: AUTOMATIC ENTRANCES - NHL Home and WNBA Locker Spec Section: 08 42 29 Status: OPEN | Info Exchange
| 16253 | Forwarded | For Review | 2021-04-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mark Lievens (ME Engineers) |  | Submittal Number: 08 42 29-1.0 From: ALLIE ZIMMERMAN Final Due Date: 4/13/2021 Subject: AUTOMATIC ENTRANCES - NHL Home and WNBA Locker Spec Section: 08 42 29 Status: OPEN | Info Exchange
| 12578 | Review Response | Approved | 2021-04-14 | Mark Lievens (ME Engineers) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 12629 | Review Response | Approved as Noted | 2021-04-16 | Rick Lewis (Studio 08 Consultants) | Populous SCA_CCA |  | Approved as Noted. Resubmit for Record. | Info Exchange
| 12630 | Review Response | Approved as Noted/Resubmit | 2021-04-16 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16346 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Response (Approved as Noted) from: Rick Lewis (Studio 08 Consultants) Remarks: Approved as Noted. Resubmit for Record. Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 08 42 29-001-00 AUTOMATIC ENTRANCES_MAM Reviewed.pdf
| Forwarded |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 08 42 29-001-00 AUTOMATIC ENTRANCES_MAM Reviewed.pdf
| Forwarded |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 08 42 29-001-00 AUTOMATIC ENTRANCES_MAM Reviewed.pdf
| Forwarded |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 08 42 29-001-00 AUTOMATIC ENTRANCES_MAM Reviewed.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-14 |  | 08 42 29-001-00 AUTOMATIC ENTRANCES_MAM Reviewed-ME Review.pdf
| Review Response |  | Rick Lewis (Studio 08 Consultants) | 1 | 2021-04-16 |  | Studio 08 Transmittal - 084229 Automatic Entrances.pdf
| Review Response |  | Rick Lewis (Studio 08 Consultants) | 1 | 2021-04-16 |  | 08 42 29-001-00 AUTOMATIC ENTRANCES_ST08 Review.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-16 |  | 08 42 29-001-00 AUTOMATIC ENTRANCES_MAM Reviewed_POP_MEE_STUDIO08.pdf
| Responded and Closed |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 08 42 29-001-00 AUTOMATIC ENTRANCES_MAM Reviewed.pdf
08 42 29-001-01 | 08 42 29 | 08 42 29-001-01 AUTOMATIC ENTRANCES - NHL Home & WNBA Locker Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Rick Lewis (Studio 08 Consultants), Linda Scott (Studio 08 Consultants) |  |  |  | 2021-06-03 07:00 | 2021-06-03 | 16 |  | Record Copies; Transfers; Submittals | 08 42 29-001-01-01 - 08 42 29-001-01 AUTOMATIC ENTRANCES - NHL Home & WNBA Locker Shop Drawings | 16 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13175 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-03 07:00 | Submittal Number: 08 42 29-1.1 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: AUTOMATIC ENTRANCES - NHL HOME & WNBA LOCKER SHOP DRAWINGS Description: Spec Section: 08 42 29 - AUTOMATIC ENTRANCES Status: OPEN | Info Exchange
| 17063 | Forwarded | For Review | 2021-05-19 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-26 | Submittal Number: 08 42 29-1.1 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: AUTOMATIC ENTRANCES - NHL HOME & WNBA LOCKER SHOP DRAWINGS Description: Spec Section: 08 42 29 - AUTOMATIC ENTRANCES Status: OPEN | Info Exchange
| 17083 | Forwarded | For Review | 2021-05-19 | Populous SCA_CCA | Rick Lewis (Studio 08 Consultants); Linda Scott (Studio 08 Consultants) |  | Submittal Number: 08 42 29-1.1 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: AUTOMATIC ENTRANCES - NHL HOME & WNBA LOCKER SHOP DRAWINGS Description: Spec Section: 08 42 29 - AUTOMATIC ENTRANCES Status: OPEN | Info Exchange
| 13370 | Review Response | Approved as Noted/Resubmit | 2021-06-03 | Linda Scott (Studio 08 Consultants) | Populous SCA_CCA |  | Resubmit for Record. | Info Exchange
| 13371 | Review Response | Approved as Noted/Resubmit | 2021-06-03 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Provide separate submittal outlining floor plan locations and finish options for touchless wave plates, as requested in previous submittal. | Info Exchange
| 17299 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-03 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Linda Scott (Studio 08 Consultants) Remarks: Resubmit for Record. Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: Provide separate submittal outlining floor plan locations and finish options for touchless wave plates, as requested in previous submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 08 42 29-1 Revision 1 AUTOMATIC ENTRANCES - NHL Home WNBA Locker Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 08 42 29-1 Revision 1 AUTOMATIC ENTRANCES - NHL Home WNBA Locker Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-18 |  | Submittal 08 42 29-1 Revision 1 AUTOMATIC ENTRANCES - NHL Home WNBA Locker Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-19 |  | Submittal 08 42 29-1 Revision 1 AUTOMATIC ENTRANCES - NHL Home WNBA_POP.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-06-03 |  | Submittal 08 42 29-1 Revision 1 AUTOMATIC ENTRANCES - NHL Home WNBA_POP ST08 REVIEW.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-03 |  | Submittal 08 42 29-1 Revision 1 AUTOMATIC ENTRANCES - NHL Home WNBA_POP ST08 REVIEW.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-18 |  | Submittal 08 42 29-1 Revision 1 AUTOMATIC ENTRANCES - NHL Home WNBA Locker Shop Drawings_MAM Reviewed.pdf
08 42 29-001-01-01 | 08 42 29 | 08 42 29-001-01 AUTOMATIC ENTRANCES - NHL Home & WNBA Locker Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 42 29-001-01 - 08 42 29-001-01 AUTOMATIC ENTRANCES - NHL Home & WNBA Locker Shop Drawings | -1 | 2021-06-17
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 08 42 29-1 Revision 1 AUTOMATIC ENTRANCES - NHL Home WNBA Locker Shop Drawings_MAM Reviewed.pdf
08 42 29-002-00 | 08 42 29 | 08 42 29-002-00 AUTOMATIC ENTRANCES - Sample Warranty Assa Abloy | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 | 2021-04-13 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12484 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-04-22 | Submittal Number: 08 42 29-2.0 From: ALLIE ZIMMERMAN Final Due Date: 04/13/21 Subject: AUTOMATIC ENTRANCES - SAMPLE WARRANTY ASSA ABLOY Description: Spec Section: 08 42 29 - AUTOMATIC ENTRANCES Status: OPEN | Info Exchange
| 16174 | Forwarded | For Review | 2021-04-08 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 08 42 29-2.0 From: ALLIE ZIMMERMAN Final Due Date: 04/13/21 Subject: AUTOMATIC ENTRANCES - SAMPLE WARRANTY ASSA ABLOY Description: Spec Section: 08 42 29 - AUTOMATIC ENTRANCES Status: OPEN | Info Exchange
| 16267 | Responded and Closed | Approved as Noted | 2021-04-13 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | Submittal 08 42 29-2 Revision 0 AUTOMATIC ENTRANCES - Sample Warranty Assa Abloy_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-04-08 |  | Submittal 08 42 29-2 Revision 0 AUTOMATIC ENTRANCES - Sample Warranty Assa Abloy_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-13 |  | Submittal 08 42 29-2 Revision 0 AUTOMATIC ENTRANCES - Sample Warranty Assa Abloy_MAM Reviewed_POP.pdf
08 42 29-003-00 | 08 42 29 | 08 42 29-003-00 AUTOMATIC ENTRANCES - WD6 Verification Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-26 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-10 07:00 | 2021-05-31 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-05-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13273 | Received | For Review | 2021-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-10 07:00 | Submittal Number: 08 42 29-3.0 From: ALLIE ZIMMERMAN Final Due Date: 06/09/21 Subject: AUTOMATIC ENTRANCES - WD6 VERIFICATION SAMPLES Description: Spec Section: 08 42 29 - AUTOMATIC ENTRANCES Status: OPEN | Info Exchange
| 17178 | Forwarded | For Review | 2021-05-26 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-02 | Submittal Number: 08 42 29-3.0 From: ALLIE ZIMMERMAN Final Due Date: 06/09/21 Subject: AUTOMATIC ENTRANCES - WD6 VERIFICATION SAMPLES Description: Spec Section: 08 42 29 - AUTOMATIC ENTRANCES Status: OPEN | Info Exchange
| 13305 | Review Response | Approved | 2021-05-31 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17217 | Responded and Closed | Approved | 2021-05-31 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-25 |  | Submittal 08 14 16-27 Revision 0 FLUSH WOOD DOORS - WD6 Verification Sample_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-25 |  | Submittal 08 14 16-27 Revision 0 FLUSH WOOD DOORS - WD6 Verification Sample_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-05-31 |  | Submittal 08 42 29-3 Revision 0 AUTOMATIC ENTRANCES - WD6 Verification Samples_MAM Reviewed_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-25 |  | Submittal 08 14 16-27 Revision 0 FLUSH WOOD DOORS - WD6 Verification Sample_MAM Reviewed.pdf
08 42 29-005-00 | 08 42 29 | 08 42 29-005-00 AUTOMATIC ENTRANCES - NHL Home Entry Horton Door Verification Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-04 | 2021-04-21 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-04-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12672 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-05-04 | Submittal Number: 08 42 29-5.0 From: ALLIE ZIMMERMAN Final Due Date: 05/04/21 Subject: AUTOMATIC ENTRANCES - NHL HOME ENTRY HORTON DOOR VERIFICATION SAMPLES Description: Spec Section: 08 42 29 - AUTOMATIC ENTRANCES Status: OPEN | Info Exchange
| 16391 | Forwarded | For Review | 2021-04-20 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 08 42 29-5.0 From: ALLIE ZIMMERMAN Final Due Date: 05/04/21 Subject: AUTOMATIC ENTRANCES - NHL HOME ENTRY HORTON DOOR VERIFICATION SAMPLES Description: Spec Section: 08 42 29 - AUTOMATIC ENTRANCES Status: OPEN | Info Exchange
| 12711 | Review Response | Approved as Noted | 2021-04-21 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16432 | Responded and Closed | Approved as Noted | 2021-04-21 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-20 |  | Submittal 08 42 29-5 Revision 0 AUTOMATIC ENTRANCES - NHL Home Entry Horton Door Verification Samples_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-04-20 |  | Submittal 08 42 29-5 Revision 0 AUTOMATIC ENTRANCES - NHL Home Entry Horton Door Verification Samples_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-21 |  | Submittal 08 42 29-5 Revision 0 AUTOMATIC ENTRANCES - NHL Home Entry_MAM_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-20 |  | Submittal 08 42 29-5 Revision 0 AUTOMATIC ENTRANCES - NHL Home Entry Horton Door Verification Samples_MAM Reviewed.pdf
08 42 29-008-00 | 08 42 29 | 08 42 29-008-00 AUTOMATIC ENTRANCES - Clear Anodized Aluminum Verification Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-09 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-23 | 2021-06-10 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-06-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13467 | Received | For Review | 2021-06-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-23 | Submittal Number: 08 42 29-8.0 From: ALLIE ZIMMERMAN Final Due Date: 06/22/21 Subject: AUTOMATIC ENTRANCES - CLEAR ANODIZED ALUMINUM VERIFICATION SAMPLE Description: Spec Section: 08 42 29 - AUTOMATIC ENTRANCES Status: OPEN | Info Exchange
| 17414 | Forwarded | For Review | 2021-06-09 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-16 | Submittal Number: 08 42 29-8.0 From: ALLIE ZIMMERMAN Final Due Date: 06/22/21 Subject: AUTOMATIC ENTRANCES - CLEAR ANODIZED ALUMINUM VERIFICATION SAMPLE Description: Spec Section: 08 42 29 - AUTOMATIC ENTRANCES Status: OPEN | Info Exchange
| 17438 | Responded and Closed | Approved | 2021-06-10 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-08 |  | Submittal 10 28 80-5 Revision 0 GLASS SHOWER DOORS - Samples for Verification_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-06-09 |  | 08 42 29-008-0 AUTOMATIC ENTRANCES - Clear Anodized_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-10 |  | 08 42 29-008-0 AUTOMATIC ENTRANCES - Clear Anodized_MAM Reviewed_POP.pdf
08 44 13-001-00 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-001-00 084413 - 1.3-A - PRODUCT DATA - ALL EXTERIOR CW SYSTEMS | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-26 07:00 | 2020-05-19 | 9 |  | Record Copies; Transfers; Submittals | 08 44 13-001-00-01 - 08 44 13-001-00 084413 - 1.3-A - PRODUCT DATA - ALL EXTERIOR CW SYSTEMS | 9 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05798 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 08 44 13-1.0 From: BROOKE BURCHAM Final Due Date: 06/01/20 Subject: 084413 - 1.3-A - PRODUCT DATA - ALL EXTERIOR CW SYSTEMS Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 07861 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-18 | Submittal Number: 08 44 13-1.0 From: BROOKE BURCHAM Final Due Date: 06/01/20 Subject: 084413 - 1.3-A - PRODUCT DATA - ALL EXTERIOR CW SYSTEMS Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 08042 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-19 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 084413-0001-0 Product Data - 1600UT and 2500UT.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 084413-0001-0 Product Data - 1600UT and 2500UT.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-19 |  | 084413-0001-0 Product Data - 1600UT and 2500UT_POP.pdf
08 44 13-001-00-01 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-001-00 084413 - 1.3-A - PRODUCT DATA - ALL EXTERIOR CW SYSTEMS | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 44 13-001-00 - 08 44 13-001-00 084413 - 1.3-A - PRODUCT DATA - ALL EXTERIOR CW SYSTEMS | -1 | 2020-06-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 |  | 084413-0001-0 Product Data - 1600UT and 2500UT_POP.pdf
08 44 13-009-00 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-009-00 084413 - 1.3-C - CW Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-26 07:00 | 2020-05-28 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-05-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05784 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 08 44 13-9.0 From: BROOKE BURCHAM Final Due Date: 05/25/20 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS Description: SHOP DRAWINGS : FOR GLAZED ALUMINUM CURTAIN WALLS. INCLUDE PLANS, ELEVATIONS, SECTIONS, FULL-SIZE DETAILS, AND ATTACHMENTS TO OTHER WORK. 1. INCLUDE DETAILS OF PROVISIONS FOR ASSEMBLY EXPANSION AND CONTRACTION AND FOR DRAINING MOISTURE OCCURRING WITHIN THE ASSEMBLY TO THE EXTERIOR. 2. INCLUDE FULL-SIZE ISOMETRIC DETAILS OF EACH VERTICAL-TO-HORIZONTAL INTERSECTION OF GLAZED ALUMINUM CURTAIN WALLS, SHOWING THE FOLLOWING: A. JOINERY, INCLUDING CONCEALED WELDS. B. ANCHORAGE. C. EXPANSION PROVISIONS. D. GLAZING. E. FLASHING AND DRAINAGE. 3. SHOW CONNECTION TO AND CONTINUITY WITH ADJACENT THERMAL, WEATHER, AIR, AND VAPOR BARRIERS. 4. SHOW SUPPORTS FOR SIGN MOUNTING BRACKETS. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 07841 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-18 | Submittal Number: 08 44 13-9.0 From: BROOKE BURCHAM Final Due Date: 05/25/20 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS Description: SHOP DRAWINGS : FOR GLAZED ALUMINUM CURTAIN WALLS. INCLUDE PLANS, ELEVATIONS, SECTIONS, FULL-SIZE DETAILS, AND ATTACHMENTS TO OTHER WORK. 1. INCLUDE DETAILS OF PROVISIONS FOR ASSEMBLY EXPANSION AND CONTRACTION AND FOR DRAINING MOISTURE OCCURRING WITHIN THE ASSEMBLY TO THE EXTERIOR. 2. INCLUDE FULL-SIZE ISOMETRIC DETAILS OF EACH VERTICAL-TO-HORIZONTAL INTERSECTION OF GLAZED ALUMINUM CURTAIN WALLS, SHOWING THE FOLLOWING: A. JOINERY, INCLUDING CONCEALED WELDS. B. ANCHORAGE. C. EXPANSION PROVISIONS. D. GLAZING. E. FLASHING AND DRAINAGE. 3. SHOW CONNECTION TO AND CONTINUITY WITH ADJACENT THERMAL, WEATHER, AIR, AND VAPOR BARRIERS. 4. SHOW SUPPORTS FOR SIGN MOUNTING BRACKETS. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 08254 | Responded and Closed | Revise and Resubmit | 2020-05-28 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 084413-0009-0 CW-06 Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 084413-0009-0 CW-06 Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-28 |  | 084413-0009-0 CW-06 Shop Drawings-MAM_POP.pdf
08 44 13-009-01 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-009-01 084413 - 1.3-C - CW Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-13 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-12-01 08:00 | 2020-11-30 | 18 |  | Record Copies; Transfers; Submittals | 08 44 13-009-01-01 - 08 44 13-009-01 084413 - 1.3-C - CW Shop Drawings | 12 |  | 2020-11-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09418 | Received | For Review | 2020-11-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-12-01 08:00 | Submittal Number: 08 44 13-9.1 From: BROOKE BURCHAM Final Due Date: 12/02/20 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS Description: SHOP DRAWINGS : FOR GLAZED ALUMINUM CURTAIN WALLS. INCLUDE PLANS, ELEVATIONS, SECTIONS, FULL-SIZE DETAILS, AND ATTACHMENTS TO OTHER WORK. 1. INCLUDE DETAILS OF PROVISIONS FOR ASSEMBLY EXPANSION AND CONTRACTION AND FOR DRAINING MOISTURE OCCURRING WITHIN THE ASSEMBLY TO THE EXTERIOR. 2. INCLUDE FULL-SIZE ISOMETRIC DETAILS OF EACH VERTICAL-TO-HORIZONTAL INTERSECTION OF GLAZED ALUMINUM CURTAIN WALLS, SHOWING THE FOLLOWING: A. JOINERY, INCLUDING CONCEALED WELDS. B. ANCHORAGE. C. EXPANSION PROVISIONS. D. GLAZING. E. FLASHING AND DRAINAGE. 3. SHOW CONNECTION TO AND CONTINUITY WITH ADJACENT THERMAL, WEATHER, AIR, AND VAPOR BARRIERS. 4. SHOW SUPPORTS FOR SIGN MOUNTING BRACKETS. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 12422 | Forwarded | For Review | 2020-11-13 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-20 | Submittal Number: 08 44 13-9.1 From: BROOKE BURCHAM Final Due Date: 12/02/20 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS Description: SHOP DRAWINGS : FOR GLAZED ALUMINUM CURTAIN WALLS. INCLUDE PLANS, ELEVATIONS, SECTIONS, FULL-SIZE DETAILS, AND ATTACHMENTS TO OTHER WORK. 1. INCLUDE DETAILS OF PROVISIONS FOR ASSEMBLY EXPANSION AND CONTRACTION AND FOR DRAINING MOISTURE OCCURRING WITHIN THE ASSEMBLY TO THE EXTERIOR. 2. INCLUDE FULL-SIZE ISOMETRIC DETAILS OF EACH VERTICAL-TO-HORIZONTAL INTERSECTION OF GLAZED ALUMINUM CURTAIN WALLS, SHOWING THE FOLLOWING: A. JOINERY, INCLUDING CONCEALED WELDS. B. ANCHORAGE. C. EXPANSION PROVISIONS. D. GLAZING. E. FLASHING AND DRAINAGE. 3. SHOW CONNECTION TO AND CONTINUITY WITH ADJACENT THERMAL, WEATHER, AIR, AND VAPOR BARRIERS. 4. SHOW SUPPORTS FOR SIGN MOUNTING BRACKETS. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 12442 | Forwarded | For Review | 2020-11-16 | Todd Spangler (Populous) | Matt Ross (Thornton Tomasetti) |  | TT, PLEASE TAKE QUICK LOAD AT CALCULATIONS. THANKS Submittal Number: 08 44 13-9.1 From: BROOKE BURCHAM Final Due Date: 12/02/20 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS Description: SHOP DRAWINGS : FOR GLAZED ALUMINUM CURTAIN WALLS. INCLUDE PLANS, ELEVATIONS, SECTIONS, FULL-SIZE DETAILS, AND ATTACHMENTS TO OTHER WORK. 1. INCLUDE DETAILS OF PROVISIONS FOR ASSEMBLY EXPANSION AND CONTRACTION AND FOR DRAINING MOISTURE OCCURRING WITHIN THE ASSEMBLY TO THE EXTERIOR. 2. INCLUDE FULL-SIZE ISOMETRIC DETAILS OF EACH VERTICAL-TO-HORIZONTAL INTERSECTION OF GLAZED ALUMINUM CURTAIN WALLS, SHOWING THE FOLLOWING: A. JOINERY, INCLUDING CONCEALED WELDS. B. ANCHORAGE. C. EXPANSION PROVISIONS. D. GLAZING. E. FLASHING AND DRAINAGE. 3. SHOW CONNECTION TO AND CONTINUITY WITH ADJACENT THERMAL, WEATHER, AIR, AND VAPOR BARRIERS. 4. SHOW SUPPORTS FOR SIGN MOUNTING BRACKETS. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 09753 | Review Response | Approved as Noted | 2020-11-24 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  |  | Info Exchange
| 12822 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-30 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-12 |  | 084413-0009-1 CW-06 Shop Drawings - Resubmittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-12 |  | 084413-0009-1 CW-06 Shop Drawings - Resubmittal.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-11-12 |  | 084413-0009-1 CW-06 Shop Drawings - Resubmittal.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-12 |  | 084413-0009-1 CW-06 Shop Drawings - Resubmittal.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-30 |  | 084413-0009-1 CW-06 Shop Drawings - Resubmittal_TT_POP.pdf
08 44 13-009-01-01 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-009-01 084413 - 1.3-C - CW Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 44 13-009-01 - 08 44 13-009-01 084413 - 1.3-C - CW Shop Drawings | -1 | 2020-12-14
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-30 |  | 084413-0009-1 CW-06 Shop Drawings - Resubmittal_TT_POP.pdf
08 44 13-010-00 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-010-00 084413 - 1.3-D - CW FINISH SAMPLES | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-05 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-27 07:00 | 2020-06-15 | 42 |  | Record Copies; Transfers; Submittals |  | 42 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05728 | Received | For Review | 2020-05-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-27 07:00 | Submittal Number: 08 44 13-10.0 From: BROOKE BURCHAM Final Due Date: 05/19/20 Subject: 084413 - 1.3-D - CW FINISH SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH REQUIRED, IN MANUFACTURER'S STANDARD SIZES. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 07773 | Forwarded | For Review | 2020-05-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-12 | Submittal Number: 08 44 13-10.0 From: BROOKE BURCHAM Final Due Date: 05/19/20 Subject: 084413 - 1.3-D - CW FINISH SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH REQUIRED, IN MANUFACTURER'S STANDARD SIZES. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 08628 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-15 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | 084413-0010-0 Finish Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-05 |  | 084413-0010-0 Finish Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-15 |  | 084413-0010-0 Finish Samples_POP.pdf
08 44 13-010-01 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-010-01 084413 - 1.3-D - CW FINISH SAMPLES | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-07 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-21 | 2020-08-24 | 18 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07441 | Received | For Review | 2020-08-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-21 | Submittal Number: 08 44 13-10.1 From: BROOKE BURCHAM Final Due Date: 08/19/20 Subject: 084413 - 1.3-D - CW FINISH SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH REQUIRED, IN MANUFACTURER'S STANDARD SIZES. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 09908 | Forwarded | For Review | 2020-08-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 08 44 13-10.1 From: BROOKE BURCHAM Final Due Date: 08/19/20 Subject: 084413 - 1.3-D - CW FINISH SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED FINISH REQUIRED, IN MANUFACTURER'S STANDARD SIZES. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 10242 | Responded and Closed | Approved | 2020-08-24 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | 084413-0010-0 Curtainwall Samples - EP1 and EP2 re-submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-06 |  | 084413-0010-1 Curtainwall Samples - EP1 and EP2 re-submittal.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-24 |  | 084413-0010-1 Curtainwall Samples - EP1 and EP2 re-submittal_POP.pdf
08 44 13-014-00 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-014-00 084413 - 1.4-B - CW NFRC CERTIFICATES | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-29 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-06-12 | 2020-06-19 | 22 |  | Record Copies; Transfers; Submittals | 08 44 13-014-01 - 08 44 13-014-00 084413 - 1.4-B - CW NFRC CERTIFICATES | 22 |  | 2020-06-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06106 | Received | For Review | 2020-05-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-12 | Submittal Number: 08 44 13-14.0 From: BROOKE BURCHAM Final Due Date: 06/11/20 Subject: 084413 - 1.4-B - CW NFRC CERTIFICATES Description: ENERGY PERFORMANCE CERTIFICATES : FOR GLAZED ALUMINUM CURTAIN WALLS, ACCESSORIES, AND COMPONENTS FROM MANUFACTURER. 1. BASIS FOR CERTIFICATION: NFRC-CERTIFIED ENERGY PERFORMANCE VALUES FOR EACH GLAZED ALUMINUM CURTAIN WALL. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 08262 | Forwarded | For Review | 2020-05-29 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-05 | Submittal Number: 08 44 13-14.0 From: BROOKE BURCHAM Final Due Date: 06/11/20 Subject: 084413 - 1.4-B - CW NFRC CERTIFICATES Description: ENERGY PERFORMANCE CERTIFICATES : FOR GLAZED ALUMINUM CURTAIN WALLS, ACCESSORIES, AND COMPONENTS FROM MANUFACTURER. 1. BASIS FOR CERTIFICATION: NFRC-CERTIFIED ENERGY PERFORMANCE VALUES FOR EACH GLAZED ALUMINUM CURTAIN WALL. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 08771 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-19 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Submittal is missing Mortenson Stamp. Resubmit per comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-28 |  | 084413-0013-0 CW NFRC Certificates.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-28 |  | 084413-0013-0 CW NFRC Certificates.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-18 02:00 |  | 084413-0014-0 CW NFRC Certificates_POP.pdf
08 44 13-014-01 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-014-00 084413 - 1.4-B - CW NFRC CERTIFICATES | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 44 13-014-00 - 08 44 13-014-00 084413 - 1.4-B - CW NFRC CERTIFICATES | -1 | 2020-07-03
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 02:00 |  | 084413-0014-0 CW NFRC Certificates_POP.pdf
08 44 13-025-00 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-025-00 084413 - 1.3-C - CW Shop Drawings - Shallow Unitized 3" 1600 UT | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-01 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-06-15 | 2020-06-30 | 30 |  | Record Copies; Transfers; Submittals |  | 30 |  | 2020-06-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06116 | Received | For Review | 2020-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-15 | Submittal Number: 08 44 13-25.0 From: BROOKE BURCHAM Final Due Date: 06/08/20 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS - SHALLOW UNITIZED 3" 1600 UT Description: SHOP DRAWINGS FOR SHALLOW UNITIZED CURTAINWALL 3" 1600 UT Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 08275 | Forwarded | For Review | 2020-06-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-08 | Submittal Number: 08 44 13-25.0 From: BROOKE BURCHAM Final Due Date: 06/08/20 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS - SHALLOW UNITIZED 3" 1600 UT Description: SHOP DRAWINGS FOR SHALLOW UNITIZED CURTAINWALL 3" 1600 UT Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 09021 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-30 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  | SEE ATTACHED FOR REVIEW AND COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-29 |  | 084413-0025-0 CW SD - SHALLOW UNITIZED AND 1600UT.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-29 |  | 084413-0025-0 CW SD - SHALLOW UNITIZED AND 1600UT.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-30 |  | 084413-0025-0 CW SD - SHALLOW UNITIZED AND 1600UT_POP.pdf
08 44 13-025-01 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-025-01 084413 - 1.3-C - CW Shop Drawings - Shallow Unitized 3" 1600 UT | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-16 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-30 | 2020-10-20 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-10-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08823 | Received | For Review | 2020-10-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-30 | Submittal Number: 08 44 13-25.1 From: BROOKE BURCHAM Final Due Date: 10/30/20 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS - SHALLOW UNITIZED 3" 1600 UT Description: SHOP DRAWINGS FOR SHALLOW UNITIZED CURTAINWALL 3" 1600 UT Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 11657 | Forwarded | For Review | 2020-10-16 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-23 | Submittal Number: 08 44 13-25.1 From: BROOKE BURCHAM Final Due Date: 10/30/20 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS - SHALLOW UNITIZED 3" 1600 UT Description: SHOP DRAWINGS FOR SHALLOW UNITIZED CURTAINWALL 3" 1600 UT Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 11741 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-20 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. MG to submit calcs for loads imposed to the steel plate above the curtain wall for hanging the curtain wall at the corners. Outriggers added to guest service building on the south elevation. See attached bootleg drawings. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-15 |  | 084413-0025-1 CW SD - SHALLOW UNITIZED AND 1600UT.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-15 |  | 084413-0025-1 CW SD - SHALLOW UNITIZED AND 1600UT.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-20 |  | 084413-0025-1 CW SD - SHALLOW UNITIZED AND 1600UT_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-20 |  | A5-02-3 - EXTERIOR ELEVATIONS - TICKET OFFICE & ENTRIES.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-20 |  | A7-03-4 - EXTERIOR WALL SECTIONS - TICKET OFFICE.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-20 |  | A8-01-6 - EXTERIOR DETAILS - TICKET OFFICE.pdf
08 44 13-025-02 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-025-02 1.3-C - CW Shop Drawings - Shallow Unitized 3" 1600 UT STAMPED CALS AND SD | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-05 07:00 | 2021-05-12 | 28 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2021-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12601 | Received | For Review | 2021-04-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-05 07:00 | Submittal Number: 08 44 13-25.2 From: BROOKE BURCHAM Final Due Date: 04/29/21 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS - SHALLOW UNITIZED 3" 1600 UT STAMPED CALS AND SD Description: SHOP DRAWINGS FOR SHALLOW UNITIZED CURTAINWALL 3" 1600 UT Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 16320 | Forwarded | For Review | 2021-04-15 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-22 | Submittal Number: 08 44 13-25.2 From: BROOKE BURCHAM Final Due Date: 04/29/21 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS - SHALLOW UNITIZED 3" 1600 UT STAMPED CALS AND SD Description: SHOP DRAWINGS FOR SHALLOW UNITIZED CURTAINWALL 3" 1600 UT Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 16573 | Forwarded | For Review | 2021-04-27 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-29 | Submittal Number: 08 44 13-25.2 From: BROOKE BURCHAM Final Due Date: 04/29/21 Subject: 084413 - 1.3-C - CW SHOP DRAWINGS - SHALLOW UNITIZED 3" 1600 UT STAMPED CALS AND SD Description: SHOP DRAWINGS FOR SHALLOW UNITIZED CURTAINWALL 3" 1600 UT Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 13058 | Review Response | Approved as Noted | 2021-05-11 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Field verify all relevant dimensions, elevations, and locations as required. Arch to review. | Info Exchange
| 16895 | Responded and Closed | Approved as Noted | 2021-05-12 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-14 |  | 19-955143 Seattle Ctr Phase 2-RTO_REI Stamped Calcs (1).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-14 |  | 19-955143 Seattle Ctr Phase 2-RTO_REI Stamped Shops (1).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-14 |  | SCA Sign Page_084413-0025-2 Stamped SD and Cals.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-14 |  | 19-955143 Seattle Ctr Phase 2-RTO_REI Stamped Calcs (1).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-14 |  | 19-955143 Seattle Ctr Phase 2-RTO_REI Stamped Shops (1).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-14 |  | SCA Sign Page_084413-0025-2 Stamped SD and Cals.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-13 02:00 |  | 19-955143 Seattle Ctr Phase 2-RTO_REI Stamped Calcs (1).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-13 02:00 |  | 19-955143 Seattle Ctr Phase 2-RTO_REI Stamped Shops (1).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-13 02:00 |  | SCA Sign Page_084413-0025-2 Stamped SD and Cals.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-13 |  | 19-955143 Seattle Ctr Phase 2-RTO_REI Stamped Calcs (1).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-13 |  | 19-955143 Seattle Ctr Phase 2-RTO_REI Stamped Shops (1).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-13 |  | SCA Sign Page_084413-0025-2 Stamped SD and Cals.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-12 |  | 08 44 13-025-02 - SCA Sign Page_084413-0025-2 Stamped SD and Cals.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-12 |  | 08 44 13-025-02 - 19-955143 Seattle Ctr Phase 2-RTO_REI Stamped Calcs (1)_TT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-12 |  | 08 44 13-025-02 - 19-955143 Seattle Ctr Phase 2-RTO_REI Stamped Shops (1)_TT.pdf
08 44 13-026-00 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-026-00 EP4 - Finish Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-01 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-15 | 2020-10-20 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-10-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08480 | Received | For Review | 2020-10-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-15 | Submittal Number: 08 44 13-26.0 From: BROOKE BURCHAM Final Due Date: 10/15/20 Subject: EP4 - FINISH SAMPLE Description: Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 11225 | Forwarded | For Review | 2020-10-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-08 | Submittal Number: 08 44 13-26.0 From: BROOKE BURCHAM Final Due Date: 10/15/20 Subject: EP4 - FINISH SAMPLE Description: Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 11520 | Forwarded | For Review | 2020-10-12 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2020-10-15 | Submittal Number: 08 44 13-26.0 From: BROOKE BURCHAM Final Due Date: 10/15/20 Subject: EP4 - FINISH SAMPLE Description: Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 11747 | Responded and Closed | Approved | 2020-10-20 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 084413-0026-0 EP4 Finish Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-01 |  | 084413-0026-0 EP4 Finish Sample.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-30 02:00 |  | 084413-0026-0 EP4 Finish Sample.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-20 02:00 |  | 084413-0026-0 EP4 Finish Sample_pop.pdf
08 44 13-027-00 | 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS | 08 44 13-027-00 Aluminum Curtainwall - Spandrel Panel Color Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-26 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-09 | 2021-02-10 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-02-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10961 | Received | For Review | 2021-01-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (Mortenson Construction) | 2021-02-09 | Submittal Number: 08 44 13-27.0 From: BROOKE BURCHAM Final Due Date: 02/09/21 Subject: ALUMINUM CURTAINWALL - SPANDREL PANEL COLOR SAMPLES Description: SAMPLES TO BE KEPT AT MORTENSON OFFICE FOR COLOR MATCH ONSITE. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 14235 | Forwarded | For Review | 2021-01-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-02 | Submittal Number: 08 44 13-27.0 From: BROOKE BURCHAM Final Due Date: 02/09/21 Subject: ALUMINUM CURTAINWALL - SPANDREL PANEL COLOR SAMPLES Description: SAMPLES TO BE KEPT AT MORTENSON OFFICE FOR COLOR MATCH ONSITE. Spec Section: 08 44 13 - GLAZED ALUMINUM CURTAIN WALLS Status: OPEN | Info Exchange
| 14754 | Responded and Closed | Approved | 2021-02-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 084413-0027-0 Spandrel Panel Finish Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-25 |  | 084413-0027-0 Spandrel Panel Finish Sample.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-12 02:00 |  | 084413-0027-0 Spandrel Panel Finish Sample_pop.pdf
08 51 13-001-00 | 08 51 13 - ALUMINUM WINDOWS | 08 51 13-001-00 085113 - 1.2-A - PRODUCT DATA | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-21 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-04 | 2020-09-14 | 25 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07676 | Received | For Review | 2020-08-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-04 | Submittal Number: 08 51 13-1.0 From: BROOKE BURCHAM Final Due Date: 08/28/20 Subject: 085113 - 1.2-A - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, GLAZING AND FABRICATION METHODS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, HARDWARE, AND FINISHES FOR ALUMINUM WINDOWS/DOORS. Spec Section: 08 51 13 - ALUMINUM WINDOWS/DOORS Status: OPEN | Info Exchange
| 10221 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 08 51 13-1.0 From: BROOKE BURCHAM Final Due Date: 08/28/20 Subject: 085113 - 1.2-A - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, GLAZING AND FABRICATION METHODS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, HARDWARE, AND FINISHES FOR ALUMINUM WINDOWS/DOORS. Spec Section: 08 51 13 - ALUMINUM WINDOWS/DOORS Status: OPEN | Info Exchange
| 10731 | Responded and Closed | Approved | 2020-09-14 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 085113-0001-0 Alum. Windows and Doors PD QD and Warranty.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-20 |  | 085113-0001-0 Alum. Windows and Doors PD QD and Warranty.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-09-14 |  | 085113-0001-0 Alum. Windows and Doors PD QD and Warranty_POP.pdf
08 51 13-007-00 | 08 51 13 - ALUMINUM WINDOWS | 08 51 13-007-00 ALUM. WINDOWS DOORS - Clear Anodized Finish Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-26 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2021-03-12 | 2021-03-08 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11691 | Received | For Review | 2021-02-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-03-12 | Submittal Number: 08 51 13-7.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: ALUM. WINDOWS/DOORS - CLEAR ANODIZED FINISH SAMPLE Description: Spec Section: 08 51 13 - ALUMINUM WINDOWS/DOORS Status: OPEN | Info Exchange
| 15149 | Forwarded | For Review | 2021-03-01 | Josh Dobken (Populous) | Kelsea Conkright (Populous); Kuebler Perry (Populous); Chad Francis (Populous) | 2021-03-08 | Submittal Number: 08 51 13-7.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: ALUM. WINDOWS/DOORS - CLEAR ANODIZED FINISH SAMPLE Description: Spec Section: 08 51 13 - ALUMINUM WINDOWS/DOORS Status: OPEN | Info Exchange
| 15369 | Responded and Closed | Approved | 2021-03-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-26 02:00 |  | Submittal 08 51 13-7 Revision 0 ALUM. WINDOWSDOORS - Clear Anodized Finish Sample_MAM Reviewed.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-26 02:00 |  | 08 51 13-007-00 - Clear Anodized Finish Sample_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-08 02:00 |  | 08 51 13-007-00 - Clear Anodized Finish Sample_MAM_pop.pdf
08 51 13-008-00 | 08 51 13 - ALUMINUM WINDOWS | 08 51 13-008-00 ALUM. WINDOWS/DOORS - Black Anodized Finish Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-26 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2021-03-12 | 2021-03-08 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11690 | Received | For Review | 2021-02-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-03-12 | Submittal Number: 08 51 13-8.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: ALUM. WINDOWS/DOORS - BLACK ANODIZED FINISH SAMPLE Description: Spec Section: 08 51 13 - ALUMINUM WINDOWS/DOORS Status: OPEN | Info Exchange
| 15148 | Forwarded | For Review | 2021-03-01 | Josh Dobken (Populous) | Kelsea Conkright (Populous); Kuebler Perry (Populous); Chad Francis (Populous) | 2021-03-08 | Submittal Number: 08 51 13-8.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: ALUM. WINDOWS/DOORS - BLACK ANODIZED FINISH SAMPLE Description: Spec Section: 08 51 13 - ALUMINUM WINDOWS/DOORS Status: OPEN | Info Exchange
| 15370 | Responded and Closed | Approved | 2021-03-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-26 02:00 |  | Submittal 08 51 13-8 Revision 0 ALUM. WINDOWSDOORS - Black Anodized Finish Sample_MAM Reviewed.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-26 02:00 |  | 08 51 13-008-00 - Black Anodized Finish Sample_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-08 02:00 |  | 08 51 13-008-00 - Black Anodized Finish Sample_MAM_POP.pdf
08 56 53-001-00 | 08 56 53 - SECURITY WINDOWS | 08 56 53-001-00 085653 - 1.4-A - PRODUCT DATA | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-20 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-03 | 2020-09-14 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07641 | Received | For Review | 2020-08-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-03 | Submittal Number: 08 56 53-1.0 From: BROOKE BURCHAM Final Due Date: 09/03/20 Subject: 085653 - 1.4-A - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR WINDOW UNITS. Spec Section: 08 56 53 - SECURITY WINDOWS Status: OPEN | Info Exchange
| 10182 | Forwarded | For Review | 2020-08-20 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-27 | Submittal Number: 08 56 53-1.0 From: BROOKE BURCHAM Final Due Date: 09/03/20 Subject: 085653 - 1.4-A - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR WINDOW UNITS. Spec Section: 08 56 53 - SECURITY WINDOWS Status: OPEN | Info Exchange
| 10730 | Responded and Closed | Approved | 2020-09-14 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 085653-0001-0 Security Window Product Data and Ballistics Test.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-20 |  | 085653-0001-0 Security Window Product Data and Ballistics Test.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-09-14 |  | 085653-0001-0 Security Window Product Data and Ballistics Test_POP.pdf
08 56 53-007-00 | 08 56 53 - SECURITY WINDOWS | 08 56 53-007-00 SECURITY WINDOWS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-09 | 2020-10-06 | 12 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08329 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-09 | Submittal Number: 08 56 53-7.0 From: BROOKE BURCHAM Final Due Date: 10/09/20 Subject: SECURITY WINDOWS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR SECURITY WINDOWS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENTS TO OTHER WORK. 2. FULL-SIZE SECTION DETAILS OF FRAMING MEMBERS, INCLUDING INTERNAL ARMORING, REINFORCEMENT, AND STIFFENERS. 3. GLAZING DETAILS. 4. DETAILS OF DEAL TRAY TRANSACTION COUNTER AND SPEAKING APERTURE. Spec Section: 08 56 53 - SECURITY WINDOWS Status: OPEN | Info Exchange
| 11037 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-01 | Submittal Number: 08 56 53-7.0 From: BROOKE BURCHAM Final Due Date: 10/09/20 Subject: SECURITY WINDOWS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR SECURITY WINDOWS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENTS TO OTHER WORK. 2. FULL-SIZE SECTION DETAILS OF FRAMING MEMBERS, INCLUDING INTERNAL ARMORING, REINFORCEMENT, AND STIFFENERS. 3. GLAZING DETAILS. 4. DETAILS OF DEAL TRAY TRANSACTION COUNTER AND SPEAKING APERTURE. Spec Section: 08 56 53 - SECURITY WINDOWS Status: OPEN | Info Exchange
| 11379 | Responded and Closed | Approved as Noted | 2020-10-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 085653-0007-0 Security Window Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 085653-0007-0 Security Window Shop Drawings.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-06 |  | 085653-0007-0 Security Window Shop Drawings_POP.pdf
08 58 30-001-00 | 08 58 30 | 08 58 30-001-00 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge Shop Drawings - Herzog | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-07 | Responded and Closed - Rejected |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-21 | 2021-06-09 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13424 | Received | For Review | 2021-06-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-06-21 | Submittal Number: 08 58 30-1.0 From: ALLIE ZIMMERMAN Final Due Date: 06/21/21 Subject: ALUMINUM SLIDING SERVICE WINDOW - PRESS BRIDGE SHOP DRAWINGS - HERZOG Description: Spec Section: 08 58 30 - ALUMINUM SLIDING SERVICE WINDOW Status: OPEN | Info Exchange
| 17364 | Forwarded | For Review | 2021-06-07 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-14 | Submittal Number: 08 58 30-1.0 From: ALLIE ZIMMERMAN Final Due Date: 06/21/21Spec Section: 08 58 30 - ALUMINUM SLIDING SERVICE WINDOW Status: OPEN Subject: ALUMINUM SLIDING SERVICE WINDOW - PRESS BRIDGE SHOP DRAWINGS - HERZOG Description: | Info Exchange
| 13471 | Review Response | Rejected | 2021-06-09 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17419 | Responded and Closed | Rejected | 2021-06-09 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-07 |  | Submittal 08 58 30-1 Revision 0 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge Shop Drawings - Herzog_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-07 |  | Submittal 08 58 30-1 Revision 0 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge Shop Drawings - Herzog_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-09 |  | Submittal 08 58 30-1 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge SDs - POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-06-07 |  | Submittal 08 58 30-1 Revision 0 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge Shop Drawings - Herzog_MAM Reviewed.pdf
08 58 30-001-01 | 08 58 30 | 08 58 30-001-01 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge Shop Drawings - Herzog | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-22 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-06 | 2021-06-30 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-06-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13603 | Received | For Review | 2021-06-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-07-06 | Submittal Number: 08 58 30-1.1 From: ALLIE ZIMMERMAN Final Due Date: 07/05/21 Subject: ALUMINUM SLIDING SERVICE WINDOW - PRESS BRIDGE SHOP DRAWINGS - HERZOG Description: Spec Section: 08 58 30 - ALUMINUM SLIDING SERVICE WINDOW Status: OPEN | Info Exchange
| 17606 | Forwarded | For Review | 2021-06-22 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-29 | Submittal Number: 08 58 30-1.1 From: ALLIE ZIMMERMAN Final Due Date: 07/05/21 Subject: ALUMINUM SLIDING SERVICE WINDOW - PRESS BRIDGE SHOP DRAWINGS - HERZOG Description: Spec Section: 08 58 30 - ALUMINUM SLIDING SERVICE WINDOW Status: OPEN | Info Exchange
| 17780 | Responded and Closed | Approved as Noted | 2021-06-30 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-21 |  | Submittal 08 58 30-1 Revision 1 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge Shop Drawings - Herzog_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-06-21 |  | Submittal 08 58 30-1 Revision 1 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge Shop Drawings - Herzog_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-06-30 |  | 08 58 30-1 Revision 1 ALUMINUM SLIDING SERVICE WINDOW_Herzog_MAM Reviewed_POP.pdf
08 58 30-001-02 | 08 58 30 | 08 58 30-001-02 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge Shop Drawings - Herzog | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-10 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-24 | 2021-08-19 | 10 |  | Record Copies; Transfers; Submittals | 08 58 30-001-02-01 - 08 58 30-001-02 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge Shop Drawings - Herzog | 10 |  | 2021-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14297 | Received | For Review | 2021-08-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-08-24 | Submittal Number: 08 58 30-1.2 From: ALLIE ZIMMERMAN Final Due Date: 08/13/21 Subject: ALUMINUM SLIDING SERVICE WINDOW - PRESS BRIDGE SHOP DRAWINGS - HERZOG Description: Spec Section: 08 58 30 - ALUMINUM SLIDING SERVICE WINDOW Status: OPEN | Info Exchange
| 18462 | Forwarded | For Review | 2021-08-10 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-17 | Submittal Number: 08 58 30-1.2 From: ALLIE ZIMMERMAN Final Due Date: 08/13/21 Subject: ALUMINUM SLIDING SERVICE WINDOW - PRESS BRIDGE SHOP DRAWINGS - HERZOG Description: Spec Section: 08 58 30 - ALUMINUM SLIDING SERVICE WINDOW Status: OPEN | Info Exchange
| 14414 | Review Response | Approved as Noted/Resubmit | 2021-08-19 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18607 | Responded and Closed | Approved as Noted/Resubmit | 2021-08-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-10 |  | 08 58 30-1 Rev 2 Press Bridge Shop Drawings - Herzog-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-10 |  | 08 58 30-1 Rev 2 Press Bridge Shop Drawings - Herzog-MAM.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-08-19 |  | 08 58 30-1 Rev 2 Press Bridge Shop Drawings - Herzog-MAM_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-10 |  | 08 58 30-1 Rev 2 Press Bridge Shop Drawings - Herzog-MAM.pdf
08 58 30-001-02-01 | 08 58 30 | 08 58 30-001-02 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge Shop Drawings - Herzog | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 58 30-001-02 - 08 58 30-001-02 ALUMINUM SLIDING SERVICE WINDOW - Press Bridge Shop Drawings - Herzog | -1 | 2021-09-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-10 |  | 08 58 30-1 Rev 2 Press Bridge Shop Drawings - Herzog-MAM.pdf
08 63 00-001-00 | 08 63 00 | 08 63 00-001-00 Skylight Profile - Rafter Design Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-13 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-05-28 07:00 | 2020-05-19 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05854 | Received | For Review | 2020-05-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-28 07:00 | Submittal Number: 08 63 00-1.0 From: BROOKE BURCHAM Final Due Date: 05/28/20 Subject: SKYLIGHT PROFILE - RAFTER DESIGN SHOP DRAWINGS Description: Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 07943 | Forwarded | For Review | 2020-05-13 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-20 | Submittal Number: 08 63 00-1.0 From: BROOKE BURCHAM Final Due Date: 05/28/20 Subject: SKYLIGHT PROFILE - RAFTER DESIGN SHOP DRAWINGS Description: Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 08035 | Responded and Closed | Approved | 2020-05-19 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Design intent and rafter profiles approved. Design team anticipates a complete submittal with all requirements noted in the specification. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-13 |  | 086300-0001-0 SKylight Profile - Rafter Design SD.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-13 |  | 20020 SCA - Skylight Profile-Rafter Drawings DD 5-5-20.dwg
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-13 |  | 086300-0001-0 SKylight Profile - Rafter Design SD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-13 |  | 20020 SCA - Skylight Profile-Rafter Drawings DD 5-5-20.dwg
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-19 |  | 086300-0001-0 SKylight Profile - Rafter Design SD_POP.pdf
08 63 00-002-00 | 08 63 00 | 08 63 00-002-00 Skylight Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-24 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-07 | 2020-08-07 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07133 | Received | For Review | 2020-07-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-07 | Submittal Number: 08 63 00-2.0 From: BROOKE BURCHAM Final Due Date: 08/07/20 Subject: SKYLIGHT PRODUCT DATA Description: SKYLIGHT PRODUCT DATA Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 09524 | Forwarded | For Review | 2020-07-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-07-31 | Submittal Number: 08 63 00-2.0 From: BROOKE BURCHAM Final Due Date: 08/07/20 Subject: SKYLIGHT PRODUCT DATA Description: SKYLIGHT PRODUCT DATA Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 09926 | Responded and Closed | Approved | 2020-08-07 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-24 |  | 086300-0002-0 Skylight Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-24 |  | 086300-0002-0 Skylight Product Data.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-06 |  | 086300-0002-0 Skylight Product Data_POP.pdf
08 63 00-003-00 | 08 63 00 | 08 63 00-003-00 Skylight - Atrium Diamond - Shop Drawings and Calculations | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-24 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti) |  |  |  | 2020-08-07 | 2020-08-08 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07134 | Received | For Review | 2020-07-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-07 | Submittal Number: 08 63 00-3.0 From: BROOKE BURCHAM Final Due Date: 08/07/20 Subject: SKYLIGHT - ATRIUM DIAMOND - SHOP DRAWINGS AND CALCULATIONS Description: SHOP DRAWINGS AND CALCULATIONS FOR THE ATRIUM DIAMOND SKYLIGHT Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 09525 | Forwarded | For Review | 2020-07-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-07-31 | Submittal Number: 08 63 00-3.0 From: BROOKE BURCHAM Final Due Date: 08/07/20 Subject: SKYLIGHT - ATRIUM DIAMOND - SHOP DRAWINGS AND CALCULATIONS Description: SHOP DRAWINGS AND CALCULATIONS FOR THE ATRIUM DIAMOND SKYLIGHT Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 09927 | Forwarded | For Review | 2020-08-07 | Todd Spangler (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) | 2020-08-07 | Submittal Number: 08 63 00-3.0 From: BROOKE BURCHAM Final Due Date: 08/07/20 Subject: SKYLIGHT - ATRIUM DIAMOND - SHOP DRAWINGS AND CALCULATIONS Description: SHOP DRAWINGS AND CALCULATIONS FOR THE ATRIUM DIAMOND SKYLIGHT Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 07461 | Review Response | Approved | 2020-08-07 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | TT has no exceptions. | Info Exchange
| 09939 | Responded and Closed | Approved as Noted | 2020-08-08 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR REVIEW AND RESPONSE. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-24 |  | 086300-0003-0 Skylight - Atrium Diamond - Shop Drawings and Calcs.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-24 |  | 086300-0003-0 Skylight - Atrium Diamond - Shop Drawings and Calcs.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-07-24 |  | 086300-0003-0 Skylight - Atrium Diamond - Shop Drawings and Calcs.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-24 |  | 086300-0003-0 Skylight - Atrium Diamond - Shop Drawings and Calcs.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-08 |  | 086300-0003-0 Skylight - Atrium Diamond - Shop Drawings and Calcs_TT_POP.pdf
08 63 00-003-01 | 08 63 00 | 08 63 00-003-01 Skylight - Atrium Diamond - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-10 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-24 | 2020-11-11 | 2 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09314 | Received | For Review | 2020-11-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-11-24 | Submittal Number: 08 63 00-3.1 From: BROOKE BURCHAM Final Due Date: 11/23/20 Subject: SKYLIGHT - ATRIUM DIAMOND - SHOP DRAWINGS Description: SHOP DRAWINGS AND CALCULATIONS FOR THE ATRIUM DIAMOND SKYLIGHT Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 12290 | Forwarded | For Review | 2020-11-09 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-16 | Submittal Number: 08 63 00-3.1 From: BROOKE BURCHAM Final Due Date: 11/23/20 Subject: SKYLIGHT - ATRIUM DIAMOND - SHOP DRAWINGS Description: SHOP DRAWINGS AND CALCULATIONS FOR THE ATRIUM DIAMOND SKYLIGHT Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 12359 | Responded and Closed | Approved | 2020-11-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-09 |  | 086300-0003-1 Skylight - Atrium Diamond - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-09 |  | 086300-0003-1 Skylight - Atrium Diamond - Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-11 |  | 086300-0003-1 Skylight - Atrium Diamond - Shop Drawings_POP.pdf
08 63 00-004-00 | 08 63 00 | 08 63 00-004-00 Skylight - Samples (Glazing and EP2) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-07 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-21 | 2020-08-28 | 22 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07446 | Received | For Review | 2020-08-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-21 | Submittal Number: 08 63 00-4.0 From: BROOKE BURCHAM Final Due Date: 08/20/20 Subject: SKYLIGHT - SAMPLES (GLAZING AND EP2) Description: Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 09913 | Forwarded | For Review | 2020-08-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-13 | Submittal Number: 08 63 00-4.0 From: BROOKE BURCHAM Final Due Date: 08/20/20 Subject: SKYLIGHT - SAMPLES (GLAZING AND EP2) Description: Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 10394 | Responded and Closed | Approved | 2020-08-28 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | 086300-0007-0 Skylight - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-06 |  | 086300-0004-0 Skylight - Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-28 |  | 086300-0004-0 Skylight - Samples_POP.pdf
08 63 00-005-00 | 08 63 00 | 08 63 00-005-00 Skylight - Space Needle - Shop Drawings and Calculations | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti) |  |  |  | 2020-08-19 | 2020-08-24 | 20 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07382 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 08 63 00-5.0 From: BROOKE BURCHAM Final Due Date: 08/19/20 Subject: SKYLIGHT - SPACE NEEDLE - SHOP DRAWINGS AND CALCULATIONS Description: SHOP DRAWINGS FOR THE SPACE NEEDLE SKYLIGHT. Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 09837 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-12 | Submittal Number: 08 63 00-5.0 From: BROOKE BURCHAM Final Due Date: 08/19/20 Subject: SKYLIGHT - SPACE NEEDLE - SHOP DRAWINGS AND CALCULATIONS Description: SHOP DRAWINGS FOR THE SPACE NEEDLE SKYLIGHT. Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 09935 | Forwarded | For Review | 2020-08-07 | Todd Spangler (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) | 2020-08-10 | Submittal Number: 08 63 00-5.0 From: BROOKE BURCHAM Final Due Date: 08/19/20 Subject: SKYLIGHT - SPACE NEEDLE - SHOP DRAWINGS AND CALCULATIONS Description: SHOP DRAWINGS FOR THE SPACE NEEDLE SKYLIGHT. Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 07662 | Review Response | Approved | 2020-08-21 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | TT has no exceptions. | Info Exchange
| 10236 | Responded and Closed | Approved as Noted | 2020-08-24 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-05 |  | 086300-0005-0 Skylight - Space Needle - Shop Drawings and Calcs.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-05 |  | 086300-0005-0 Skylight - Space Needle - Shop Drawings and Calcs.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-08-05 |  | 086300-0005-0 Skylight - Space Needle - Shop Drawings and Calcs.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-05 |  | 086300-0005-0 Skylight - Space Needle - Shop Drawings and Calcs.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-24 |  | 086300-0005-0 Skylight - Space Needle - Shop Drawings and Calcs_TT_POP.pdf
08 63 00-005-01 | 08 63 00 | 08 63 00-005-01 Skylight - Space Needle - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-03 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-17 | 2020-11-09 | 7 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09179 | Received | For Review | 2020-11-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-11-17 | Submittal Number: 08 63 00-5.1 From: BROOKE BURCHAM Final Due Date: 11/17/20 Subject: SKYLIGHT - SPACE NEEDLE - SHOP DRAWINGS Description: SHOP DRAWINGS FOR THE SPACE NEEDLE SKYLIGHT. Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 12111 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-09 | Submittal Number: 08 63 00-5.1 From: BROOKE BURCHAM Final Due Date: 11/17/20 Subject: SKYLIGHT - SPACE NEEDLE - SHOP DRAWINGS Description: SHOP DRAWINGS FOR THE SPACE NEEDLE SKYLIGHT. Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 12280 | Responded and Closed | Approved as Noted | 2020-11-09 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | 086300-0005-1 Skylight - Space Needle - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | 086300-0005-1 Skylight - Space Needle - Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-09 |  | 08 63 00-005-01 Skylight
08 63 00-006-00 | 08 63 00 | 08 63 00-006-00 Skylight - Space Needle - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - No Action Taken or Required |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-19 | 2020-08-06 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07383 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 08 63 00-6.0 From: BROOKE BURCHAM Final Due Date: 08/19/20 Subject: SKYLIGHT - SPACE NEEDLE - PRODUCT DATA Description: Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 09838 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-12 | Submittal Number: 08 63 00-6.0 From: BROOKE BURCHAM Final Due Date: 08/19/20 Subject: SKYLIGHT - SPACE NEEDLE - PRODUCT DATA Description: Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 09867 | Responded and Closed | No Action Taken or Required | 2020-08-06 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | DO NOT SUBMIT PRODUCT DATA TWICE. THIS WAS APPROVED IN 08 63 00-002. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-05 |  | 086300-0006-0 Skylight - Space Needle - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-05 |  | 086300-0006-0 Skylight - Space Needle - Product Data.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-05 |  | 086300-0006-0 Skylight - Space Needle - Product Data.pdf
08 63 00-007-00 | 08 63 00 | 08 63 00-007-00 Atrium Glass Canopy - Product Data, Shop Drawings, Calculations, Samples | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-15 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-29 | 2020-10-28 | 14 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-10-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08804 | Received | For Review | 2020-10-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-29 | Submittal Number: 08 63 00-7.0 From: BROOKE BURCHAM Final Due Date: 10/29/20 Subject: ATRIUM GLASS CANOPY - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, SAMPLES Description: PRODUCT DATA, SAMPLES, SHOP DRAWINGS, CALCULATIONS. SAMPLES SENT TO TODD SPANGLER ON 10/15/2020. Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 11637 | Forwarded | For Review | 2020-10-15 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-22 | Submittal Number: 08 63 00-7.0 From: BROOKE BURCHAM Final Due Date: 10/29/20 Subject: ATRIUM GLASS CANOPY - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, SAMPLES Description: PRODUCT DATA, SAMPLES, SHOP DRAWINGS, CALCULATIONS. SAMPLES SENT TO TODD SPANGLER ON 10/15/2020. Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 11723 | Forwarded | For Review | 2020-10-19 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2020-10-26 | Submittal Number: 08 63 00-7.0 From: BROOKE BURCHAM Final Due Date: 10/29/20 Subject: ATRIUM GLASS CANOPY - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, SAMPLES Description: PRODUCT DATA, SAMPLES, SHOP DRAWINGS, CALCULATIONS. SAMPLES SENT TO TODD SPANGLER ON 10/15/2020. Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 08926 | Review Response | Approved | 2020-10-21 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 11953 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-28 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | see attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-15 |  | 086300-0007-0 Atrium Canopy - PD_SD_Cals_Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-15 |  | 086300-0007-0 Atrium Canopy - PD_SD_Cals_Samples.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-14 02:00 |  | 086300-0007-0 Atrium Canopy - PD_SD_Cals_Samples.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-14 |  | 086300-0007-0 Atrium Canopy - PD_SD_Cals_Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-28 |  | 086300-0007-0 Atrium Canopy - PD_SD_Cals_Samples_TT_POP.pdf
08 63 00-007-01 | 08 63 00 | 08 63 00-007-01 Atrium Glass Canopy - Product Data, Shop Drawings, Calculations, Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-11-30 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-11-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09571 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-12-07 | Submittal Number: 08 63 00-7.1 From: BROOKE BURCHAM Final Due Date: 12/08/20 Subject: ATRIUM GLASS CANOPY - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, SAMPLES Description: PRODUCT DATA, SAMPLES, SHOP DRAWINGS, CALCULATIONS. SAMPLES SENT TO TODD SPANGLER ON 10/15/2020. Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 12600 | Forwarded | For Review | 2020-11-19 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 08 63 00-7.1 From: BROOKE BURCHAM Final Due Date: 12/08/20 Subject: ATRIUM GLASS CANOPY - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, SAMPLES Description: PRODUCT DATA, SAMPLES, SHOP DRAWINGS, CALCULATIONS. SAMPLES SENT TO TODD SPANGLER ON 10/15/2020. Spec Section: 08 63 00 - METAL-FRAMED SKYLIGHTS Status: OPEN | Info Exchange
| 12833 | Responded and Closed | Approved | 2020-11-30 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 086300-0007-1 Atrium Canopy - Sample Resubmittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 086300-0007-1 Atrium Canopy - Sample Resubmittal.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-11-30 |  | 086300-0007-1 Atrium Canopy - Sample Resubmittal_POP.pdf
08 71 00-001-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-001-00 085653 - 1.4-A PRODUCT DATA (MISSION GLASS) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-21 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-05-05 | 2020-05-05 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-05-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05445 | Received | For Review | 2020-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-05 | Submittal Number: 08 71 00-1.0 From: BROOKE BURCHAM Final Due Date: 05/04/20 Subject: 085653 - 1.4-A PRODUCT DATA (MISSION GLASS) Description: PRODUCT DATA : MANUFACTURER'S PRODUCT DATA SHEETS INCLUDING INSTALLATION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, OPERATIONAL DESCRIPTIONS AND FINISHES. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07390 | Forwarded | For Review | 2020-04-20 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants) | 2020-04-27 | Submittal Number: 08 71 00-1.0 From: BROOKE BURCHAM Final Due Date: 05/04/20 Subject: 085653 - 1.4-A PRODUCT DATA (MISSION GLASS) Description: PRODUCT DATA : MANUFACTURER'S PRODUCT DATA SHEETS INCLUDING INSTALLATION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, OPERATIONAL DESCRIPTIONS AND FINISHES. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07499 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Chad Francis (Populous) | 2020-05-01 | Submittal Number: 08 71 00-1.0 From: BROOKE BURCHAM Final Due Date: 05/04/20 Subject: 085653 - 1.4-A PRODUCT DATA (MISSION GLASS) Description: PRODUCT DATA : MANUFACTURER'S PRODUCT DATA SHEETS INCLUDING INSTALLATION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, OPERATIONAL DESCRIPTIONS AND FINISHES. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05732 | Review Response | Approved as Noted/Resubmit | 2020-05-05 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous); Chad Francis (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 07778 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-05 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | To be resubmitted as corrected with aluminum door hardware schedule when lever/manufacturer RFI 2446 has been finalized. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-20 |  | 087100-0001-0 - Product Data Alum. Door Hardware.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-20 |  | 087100-0001-0 - Product Data Alum. Door Hardware.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-20 |  | 087100-0001-0 - Product Data Alum. Door Hardware.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-04-20 |  | 087100-0001-0 - Product Data Alum. Door Hardware.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-05 |  | 087100-0001-0 - Product Data Alum. Door Hardware ST08 REVIEWED - POP.pdf
08 71 00-001-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-001-01 085653 - 1.4-A PRODUCT DATA (MISSION GLASS) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-29 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-07-14 07:00 | 2020-07-13 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06647 | Received | For Review | 2020-06-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-07-14 07:00 | Submittal Number: 08 71 00-1.1 From: BROOKE BURCHAM Final Due Date: 07/13/20 Subject: 085653 - 1.4-A PRODUCT DATA (MISSION GLASS) Description: PRODUCT DATA : MANUFACTURER'S PRODUCT DATA SHEETS INCLUDING INSTALLATION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, OPERATIONAL DESCRIPTIONS AND FINISHES. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 08952 | Forwarded | For Review | 2020-06-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-07-06 | Submittal Number: 08 71 00-1.1 From: BROOKE BURCHAM Final Due Date: 07/13/20 Subject: 085653 - 1.4-A PRODUCT DATA (MISSION GLASS) Description: PRODUCT DATA : MANUFACTURER'S PRODUCT DATA SHEETS INCLUDING INSTALLATION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, OPERATIONAL DESCRIPTIONS AND FINISHES. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 06854 | Review Response | Approved | 2020-07-07 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 09278 | Responded and Closed | Approved as Noted | 2020-07-13 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-26 |  | 087100-0001-1 - Alum. Door Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-26 |  | 087100-0001-1 - Alum. Door Product Data.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-06-26 |  | 087100-0001-1 - Alum. Door Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-13 |  | 087100-0001-1 - Alum. Door Product Data REVIEWED ST08_POP.pdf
08 71 00-002-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-002-00 0871000 - 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-21 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants) |  |  |  | 2020-05-05 | 2020-04-24 | 4 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-04-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05446 | Received | For Review | 2020-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-05 | Submittal Number: 08 71 00-2.0 From: BROOKE BURCHAM Final Due Date: 05/04/20 Subject: 0871000 - 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) Description: DOOR HARDWARE SCHEDULE : PREPARED BY OR UNDER THE SUPERVISION OF SUPPLIER, DETAILING FABRICATION AND ASSEMBLY OF DOOR HARDWARE, AS WELL AS PROCEDURES AND DIAGRAMS. COORDINATE THE FINAL DOOR HARDWARE SCHEDULE WITH DOORS, FRAMES, AND RELATED WORK TO ENSURE PROPER SIZE, THICKNESS, HAND, FUNCTION, AND FINISH OF DOOR HARDWARE. 1. FORMAT: COMPLY WITH SCHEDULING SEQUENCE AND VERTICAL FORMAT IN DHI'S "SEQUENCE AND FORMAT FOR THE HARDWARE SCHEDULE." 2. ORGANIZATION: ORGANIZE THE DOOR HARDWARE SCHEDULE INTO DOOR HARDWARE SETS INDICATING COMPLETE DESIGNATIONS OF EVERY ITEM REQUIRED FOR EACH DOOR OR OPENING. ORGANIZE DOOR HARDWARE SETS IN SAME ORDER AS IN THE DOOR HARDWARE SETS AT THE END OF PART 3. SUBMITTALS THAT DO NOT FOLLOW THE SAME FORMAT AND ORDER AS THE DOOR HARDWARE SETS WILL BE REJECTED AND SUBJECT TO RESUBMISSION. 3. CONTENT: INCLUDE THE FOLLOWING INFORMATION: A. TYPE, STYLE, FUNCTION, SIZE, LABEL, HAND, AND FINISH OF EACH DOOR HARDWARE ITEM. B. MANUFACTURER OF EACH ITEM. C. FASTENINGS AND OTHER PERTINENT INFORMATION. D. LOCATION OF DOOR HARDWARE SET, CROSS-REFERENCED TO DRAWINGS, BOTH ON FLOOR PLANS AND IN DOOR AND FRAME SCHEDULE. E. EXPLANATION OF ABBREVIATIONS, SYMBOLS, AND CODES CONTAINED IN SCHEDULE. F. MOUNTING LOCATIONS FOR DOOR HARDWARE. G. DOOR AND FRAME SIZES AND MATERIALS. H. WARRANTY INFORMATION FOR EACH PRODUCT. 4. SUBMITTAL SEQUENCE: SUBMIT THE FINAL DOOR HARDWARE SCHEDULE AT EARLIEST POSSIBLE DATE, PARTICULARLY WHERE APPROVAL OF THE DOOR HARDWARE SCHEDULE MUST PRECEDE FABRICATION OF OTHER WORK THAT IS CRITICAL IN THE PROJECT CONSTRUCTION SCHEDULE. INCLUDE PRODUCT DATA, SAMPLES, SHOP DRAWINGS OF OTHER WORK AFFECTED BY DOOR HARDWARE, AND OTHER INFORMATION ESSENTIAL TO THE COORDINATED REVIEW OF THE DOOR HARDWARE SCHEDULE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07391 | Forwarded | For Review | 2020-04-20 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants) | 2020-04-27 | Submittal Number: 08 71 00-2.0 From: BROOKE BURCHAM Final Due Date: 05/04/20 Subject: 0871000 - 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) Description: DOOR HARDWARE SCHEDULE : PREPARED BY OR UNDER THE SUPERVISION OF SUPPLIER, DETAILING FABRICATION AND ASSEMBLY OF DOOR HARDWARE, AS WELL AS PROCEDURES AND DIAGRAMS. COORDINATE THE FINAL DOOR HARDWARE SCHEDULE WITH DOORS, FRAMES, AND RELATED WORK TO ENSURE PROPER SIZE, THICKNESS, HAND, FUNCTION, AND FINISH OF DOOR HARDWARE. 1. FORMAT: COMPLY WITH SCHEDULING SEQUENCE AND VERTICAL FORMAT IN DHI'S "SEQUENCE AND FORMAT FOR THE HARDWARE SCHEDULE." 2. ORGANIZATION: ORGANIZE THE DOOR HARDWARE SCHEDULE INTO DOOR HARDWARE SETS INDICATING COMPLETE DESIGNATIONS OF EVERY ITEM REQUIRED FOR EACH DOOR OR OPENING. ORGANIZE DOOR HARDWARE SETS IN SAME ORDER AS IN THE DOOR HARDWARE SETS AT THE END OF PART 3. SUBMITTALS THAT DO NOT FOLLOW THE SAME FORMAT AND ORDER AS THE DOOR HARDWARE SETS WILL BE REJECTED AND SUBJECT TO RESUBMISSION. 3. CONTENT: INCLUDE THE FOLLOWING INFORMATION: A. TYPE, STYLE, FUNCTION, SIZE, LABEL, HAND, AND FINISH OF EACH DOOR HARDWARE ITEM. B. MANUFACTURER OF EACH ITEM. C. FASTENINGS AND OTHER PERTINENT INFORMATION. D. LOCATION OF DOOR HARDWARE SET, CROSS-REFERENCED TO DRAWINGS, BOTH ON FLOOR PLANS AND IN DOOR AND FRAME SCHEDULE. E. EXPLANATION OF ABBREVIATIONS, SYMBOLS, AND CODES CONTAINED IN SCHEDULE. F. MOUNTING LOCATIONS FOR DOOR HARDWARE. G. DOOR AND FRAME SIZES AND MATERIALS. H. WARRANTY INFORMATION FOR EACH PRODUCT. 4. SUBMITTAL SEQUENCE: SUBMIT THE FINAL DOOR HARDWARE SCHEDULE AT EARLIEST POSSIBLE DATE, PARTICULARLY WHERE APPROVAL OF THE DOOR HARDWARE SCHEDULE MUST PRECEDE FABRICATION OF OTHER WORK THAT IS CRITICAL IN THE PROJECT CONSTRUCTION SCHEDULE. INCLUDE PRODUCT DATA, SAMPLES, SHOP DRAWINGS OF OTHER WORK AFFECTED BY DOOR HARDWARE, AND OTHER INFORMATION ESSENTIAL TO THE COORDINATED REVIEW OF THE DOOR HARDWARE SCHEDULE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05536 | Review Response | Revise and Resubmit | 2020-04-24 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the aluminum door hardware submittal. It does not meet the required format and needs to be revised and resubmitted. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 07500 | Responded and Closed | Revise and Resubmit | 2020-04-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Linda Scott (Studio 08 Consultants) Remarks: Please find attached the aluminum door hardware submittal. It does not meet the required format and needs to be revised and resubmitted. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-20 |  | 087100-0002-0 - Alum. Door Hardware Schedule.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-20 |  | 087100-0002-0 - Alum. Door Hardware Schedule.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-04-19 02:00 |  | 087100-0002-0 - Alum. Door Hardware Schedule.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-24 02:00 |  | 087100-0002-0 - Alum. Door Hardware Schedule REVIEWED ST08_POP.pdf
08 71 00-002-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-002-01 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-12 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-05-27 07:00 | 2020-05-26 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05835 | Received | For Review | 2020-05-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-27 07:00 | Submittal Number: 08 71 00-2.1 From: BROOKE BURCHAM Final Due Date: 05/26/20 Subject: 0871000 - 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) Description: DOOR HARDWARE SCHEDULE : PREPARED BY OR UNDER THE SUPERVISION OF SUPPLIER, DETAILING FABRICATION AND ASSEMBLY OF DOOR HARDWARE, AS WELL AS PROCEDURES AND DIAGRAMS. COORDINATE THE FINAL DOOR HARDWARE SCHEDULE WITH DOORS, FRAMES, AND RELATED WORK TO ENSURE PROPER SIZE, THICKNESS, HAND, FUNCTION, AND FINISH OF DOOR HARDWARE. 1. FORMAT: COMPLY WITH SCHEDULING SEQUENCE AND VERTICAL FORMAT IN DHI'S "SEQUENCE AND FORMAT FOR THE HARDWARE SCHEDULE." 2. ORGANIZATION: ORGANIZE THE DOOR HARDWARE SCHEDULE INTO DOOR HARDWARE SETS INDICATING COMPLETE DESIGNATIONS OF EVERY ITEM REQUIRED FOR EACH DOOR OR OPENING. ORGANIZE DOOR HARDWARE SETS IN SAME ORDER AS IN THE DOOR HARDWARE SETS AT THE END OF PART 3. SUBMITTALS THAT DO NOT FOLLOW THE SAME FORMAT AND ORDER AS THE DOOR HARDWARE SETS WILL BE REJECTED AND SUBJECT TO RESUBMISSION. 3. CONTENT: INCLUDE THE FOLLOWING INFORMATION: A. TYPE, STYLE, FUNCTION, SIZE, LABEL, HAND, AND FINISH OF EACH DOOR HARDWARE ITEM. B. MANUFACTURER OF EACH ITEM. C. FASTENINGS AND OTHER PERTINENT INFORMATION. D. LOCATION OF DOOR HARDWARE SET, CROSS-REFERENCED TO DRAWINGS, BOTH ON FLOOR PLANS AND IN DOOR AND FRAME SCHEDULE. E. EXPLANATION OF ABBREVIATIONS, SYMBOLS, AND CODES CONTAINED IN SCHEDULE. F. MOUNTING LOCATIONS FOR DOOR HARDWARE. G. DOOR AND FRAME SIZES AND MATERIALS. H. WARRANTY INFORMATION FOR EACH PRODUCT. 4. SUBMITTAL SEQUENCE: SUBMIT THE FINAL DOOR HARDWARE SCHEDULE AT EARLIEST POSSIBLE DATE, PARTICULARLY WHERE APPROVAL OF THE DOOR HARDWARE SCHEDULE MUST PRECEDE FABRICATION OF OTHER WORK THAT IS CRITICAL IN THE PROJECT CONSTRUCTION SCHEDULE. INCLUDE PRODUCT DATA, SAMPLES, SHOP DRAWINGS OF OTHER WORK AFFECTED BY DOOR HARDWARE, AND OTHER INFORMATION ESSENTIAL TO THE COORDINATED REVIEW OF THE DOOR HARDWARE SCHEDULE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07917 | Forwarded | For Review | 2020-05-12 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-05-19 | Submittal Number: 08 71 00-2.1 From: BROOKE BURCHAM Final Due Date: 05/26/20 Subject: 0871000 - 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) Description: DOOR HARDWARE SCHEDULE : PREPARED BY OR UNDER THE SUPERVISION OF SUPPLIER, DETAILING FABRICATION AND ASSEMBLY OF DOOR HARDWARE, AS WELL AS PROCEDURES AND DIAGRAMS. COORDINATE THE FINAL DOOR HARDWARE SCHEDULE WITH DOORS, FRAMES, AND RELATED WORK TO ENSURE PROPER SIZE, THICKNESS, HAND, FUNCTION, AND FINISH OF DOOR HARDWARE. 1. FORMAT: COMPLY WITH SCHEDULING SEQUENCE AND VERTICAL FORMAT IN DHI'S "SEQUENCE AND FORMAT FOR THE HARDWARE SCHEDULE." 2. ORGANIZATION: ORGANIZE THE DOOR HARDWARE SCHEDULE INTO DOOR HARDWARE SETS INDICATING COMPLETE DESIGNATIONS OF EVERY ITEM REQUIRED FOR EACH DOOR OR OPENING. ORGANIZE DOOR HARDWARE SETS IN SAME ORDER AS IN THE DOOR HARDWARE SETS AT THE END OF PART 3. SUBMITTALS THAT DO NOT FOLLOW THE SAME FORMAT AND ORDER AS THE DOOR HARDWARE SETS WILL BE REJECTED AND SUBJECT TO RESUBMISSION. 3. CONTENT: INCLUDE THE FOLLOWING INFORMATION: A. TYPE, STYLE, FUNCTION, SIZE, LABEL, HAND, AND FINISH OF EACH DOOR HARDWARE ITEM. B. MANUFACTURER OF EACH ITEM. C. FASTENINGS AND OTHER PERTINENT INFORMATION. D. LOCATION OF DOOR HARDWARE SET, CROSS-REFERENCED TO DRAWINGS, BOTH ON FLOOR PLANS AND IN DOOR AND FRAME SCHEDULE. E. EXPLANATION OF ABBREVIATIONS, SYMBOLS, AND CODES CONTAINED IN SCHEDULE. F. MOUNTING LOCATIONS FOR DOOR HARDWARE. G. DOOR AND FRAME SIZES AND MATERIALS. H. WARRANTY INFORMATION FOR EACH PRODUCT. 4. SUBMITTAL SEQUENCE: SUBMIT THE FINAL DOOR HARDWARE SCHEDULE AT EARLIEST POSSIBLE DATE, PARTICULARLY WHERE APPROVAL OF THE DOOR HARDWARE SCHEDULE MUST PRECEDE FABRICATION OF OTHER WORK THAT IS CRITICAL IN THE PROJECT CONSTRUCTION SCHEDULE. INCLUDE PRODUCT DATA, SAMPLES, SHOP DRAWINGS OF OTHER WORK AFFECTED BY DOOR HARDWARE, AND OTHER INFORMATION ESSENTIAL TO THE COORDINATED REVIEW OF THE DOOR HARDWARE SCHEDULE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 06010 | Review Response | Approved as Noted | 2020-05-22 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thanks. | Info Exchange
| 08152 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-26 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-12 |  | 087100-0002-1 - Alum. Door Hardware Schedule.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-12 |  | 087100-0002-1 - Alum. Door Hardware Schedule.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-05-12 |  | 087100-0002-1 - Alum. Door Hardware Schedule.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-26 |  | 087100-0002-1 - Alum. Door Hardware Schedule REVIEWED ST08 - POP.pdf
08 71 00-002-02 | 08 71 00 - DOOR HARDWARE | 08 71 00-002-02 0871000 - 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-29 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-07-14 07:00 | 2020-07-13 | 15 |  | Record Copies; Transfers; Submittals | 08 71 00-002-02-01 - 08 71 00-002-02 0871000 - 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) | 13 |  | 2020-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06648 | Received | For Review | 2020-06-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Brooke Burcham (M.A. Mortenson Company) | 2020-07-14 07:00 | Submittal Number: 08 71 00-2.2 From: BROOKE BURCHAM Final Due Date: 07/13/20 Subject: 0871000 - 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) Description: DOOR HARDWARE SCHEDULE : PREPARED BY OR UNDER THE SUPERVISION OF SUPPLIER, DETAILING FABRICATION AND ASSEMBLY OF DOOR HARDWARE, AS WELL AS PROCEDURES AND DIAGRAMS. COORDINATE THE FINAL DOOR HARDWARE SCHEDULE WITH DOORS, FRAMES, AND RELATED WORK TO ENSURE PROPER SIZE, THICKNESS, HAND, FUNCTION, AND FINISH OF DOOR HARDWARE. 1. FORMAT: COMPLY WITH SCHEDULING SEQUENCE AND VERTICAL FORMAT IN DHI'S "SEQUENCE AND FORMAT FOR THE HARDWARE SCHEDULE." 2. ORGANIZATION: ORGANIZE THE DOOR HARDWARE SCHEDULE INTO DOOR HARDWARE SETS INDICATING COMPLETE DESIGNATIONS OF EVERY ITEM REQUIRED FOR EACH DOOR OR OPENING. ORGANIZE DOOR HARDWARE SETS IN SAME ORDER AS IN THE DOOR HARDWARE SETS AT THE END OF PART 3. SUBMITTALS THAT DO NOT FOLLOW THE SAME FORMAT AND ORDER AS THE DOOR HARDWARE SETS WILL BE REJECTED AND SUBJECT TO RESUBMISSION. 3. CONTENT: INCLUDE THE FOLLOWING INFORMATION: A. TYPE, STYLE, FUNCTION, SIZE, LABEL, HAND, AND FINISH OF EACH DOOR HARDWARE ITEM. B. MANUFACTURER OF EACH ITEM. C. FASTENINGS AND OTHER PERTINENT INFORMATION. D. LOCATION OF DOOR HARDWARE SET, CROSS-REFERENCED TO DRAWINGS, BOTH ON FLOOR PLANS AND IN DOOR AND FRAME SCHEDULE. E. EXPLANATION OF ABBREVIATIONS, SYMBOLS, AND CODES CONTAINED IN SCHEDULE. F. MOUNTING LOCATIONS FOR DOOR HARDWARE. G. DOOR AND FRAME SIZES AND MATERIALS. H. WARRANTY INFORMATION FOR EACH PRODUCT. 4. SUBMITTAL SEQUENCE: SUBMIT THE FINAL DOOR HARDWARE SCHEDULE AT EARLIEST POSSIBLE DATE, PARTICULARLY WHERE APPROVAL OF THE DOOR HARDWARE SCHEDULE MUST PRECEDE FABRICATION OF OTHER WORK THAT IS CRITICAL IN THE PROJECT CONSTRUCTION SCHEDULE. INCLUDE PRODUCT DATA, SAMPLES, SHOP DRAWINGS OF OTHER WORK AFFECTED BY DOOR HARDWARE, AND OTHER INFORMATION ESSENTIAL TO THE COORDINATED REVIEW OF THE DOOR HARDWARE SCHEDULE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 08953 | Forwarded | For Review | 2020-06-27 | Brooke Burcham (M.A. Mortenson Company) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-07-06 | Submittal Number: 08 71 00-2.2 From: BROOKE BURCHAM Final Due Date: 07/13/20 Subject: 0871000 - 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) Description: DOOR HARDWARE SCHEDULE : PREPARED BY OR UNDER THE SUPERVISION OF SUPPLIER, DETAILING FABRICATION AND ASSEMBLY OF DOOR HARDWARE, AS WELL AS PROCEDURES AND DIAGRAMS. COORDINATE THE FINAL DOOR HARDWARE SCHEDULE WITH DOORS, FRAMES, AND RELATED WORK TO ENSURE PROPER SIZE, THICKNESS, HAND, FUNCTION, AND FINISH OF DOOR HARDWARE. 1. FORMAT: COMPLY WITH SCHEDULING SEQUENCE AND VERTICAL FORMAT IN DHI'S "SEQUENCE AND FORMAT FOR THE HARDWARE SCHEDULE." 2. ORGANIZATION: ORGANIZE THE DOOR HARDWARE SCHEDULE INTO DOOR HARDWARE SETS INDICATING COMPLETE DESIGNATIONS OF EVERY ITEM REQUIRED FOR EACH DOOR OR OPENING. ORGANIZE DOOR HARDWARE SETS IN SAME ORDER AS IN THE DOOR HARDWARE SETS AT THE END OF PART 3. SUBMITTALS THAT DO NOT FOLLOW THE SAME FORMAT AND ORDER AS THE DOOR HARDWARE SETS WILL BE REJECTED AND SUBJECT TO RESUBMISSION. 3. CONTENT: INCLUDE THE FOLLOWING INFORMATION: A. TYPE, STYLE, FUNCTION, SIZE, LABEL, HAND, AND FINISH OF EACH DOOR HARDWARE ITEM. B. MANUFACTURER OF EACH ITEM. C. FASTENINGS AND OTHER PERTINENT INFORMATION. D. LOCATION OF DOOR HARDWARE SET, CROSS-REFERENCED TO DRAWINGS, BOTH ON FLOOR PLANS AND IN DOOR AND FRAME SCHEDULE. E. EXPLANATION OF ABBREVIATIONS, SYMBOLS, AND CODES CONTAINED IN SCHEDULE. F. MOUNTING LOCATIONS FOR DOOR HARDWARE. G. DOOR AND FRAME SIZES AND MATERIALS. H. WARRANTY INFORMATION FOR EACH PRODUCT. 4. SUBMITTAL SEQUENCE: SUBMIT THE FINAL DOOR HARDWARE SCHEDULE AT EARLIEST POSSIBLE DATE, PARTICULARLY WHERE APPROVAL OF THE DOOR HARDWARE SCHEDULE MUST PRECEDE FABRICATION OF OTHER WORK THAT IS CRITICAL IN THE PROJECT CONSTRUCTION SCHEDULE. INCLUDE PRODUCT DATA, SAMPLES, SHOP DRAWINGS OF OTHER WORK AFFECTED BY DOOR HARDWARE, AND OTHER INFORMATION ESSENTIAL TO THE COORDINATED REVIEW OF THE DOOR HARDWARE SCHEDULE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 06883 | Review Response | Approved as Noted | 2020-07-09 | Linda Scott (Studio 08 Consultants) | Brooke Burcham (M.A. Mortenson Company) |  | Sent via email. | Info Exchange
| 09279 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-13 | Brooke Burcham (M.A. Mortenson Company) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-26 |  | 087100-0002-2 - Alum. Door Hardware Schedule.pdf
| Forwarded |  | Brooke Burcham (Mortenson Construction) | 1 | 2020-06-26 |  | 087100-0002-2 - Alum. Door Hardware Schedule.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-07-09 |  | 087100-0002-2 - Alum. Door Hardware Schedule REVIEWED ST08.pdf
| Responded and Closed |  | Brooke Burcham (Mortenson Construction) | 1 | 2020-07-13 |  | 087100-0002-2 - Alum. Door Hardware Schedule REVIEWED ST08_POP.pdf
08 71 00-002-02-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-002-02 0871000 - 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-002-02 - 08 71 00-002-02 0871000 - 1.3-B - HARDWARE SCHEDULE (MISSION GLASS) | -1 | 2020-07-27
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 087100-0002-2 - Alum. Door Hardware Schedule REVIEWED ST08_POP.pdf
08 71 00-003-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-003-00 087100 - 1.3-C SHOP DRAWINGS - ELECTRICAL COORDINATION (MISSION GLASS) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-02 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers) |  |  |  | 2020-10-16 | 2020-10-19 | 18 |  | Record Copies; Transfers; Submittals | 08 71 00-003-00-01 - 08 71 00-003-00 087100 - 1.3-C SHOP DRAWINGS - ELECTRICAL COORDINATION (MISSION GLASS) | 19 |  | 2020-10-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08496 | Received | For Review | 2020-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-16 | Submittal Number: 08 71 00-3.0 From: BROOKE BURCHAM Final Due Date: 10/16/20 Subject: 087100 - 1.3-C SHOP DRAWINGS - ELECTRICAL COORDINATION (MISSION GLASS) Description: SHOP DRAWINGS : DETAILS OF ELECTRIFIED ACCESS CONTROL HARDWARE INDICATING THE FOLLOWING: 1. WIRING DIAGRAMS: UPON RECEIPT OF APPROVED SCHEDULES, SUBMIT DETAILED SYSTEM WIRING DIAGRAMS FOR POWER, SIGNALING, MONITORING, COMMUNICATION, AND CONTROL OF THE ACCESS CONTROL SYSTEM ELECTRIFIED HARDWARE. DIFFERENTIATE BETWEEN MANUFACTURER-INSTALLED AND FIELD-INSTALLED WIRING. INCLUDE THE FOLLOWING: A. ELEVATION DIAGRAM OF EACH UNIQUE ACCESS-CONTROLLED OPENING SHOWING LOCATION AND INTERCONNECTION OF MAJOR SYSTEM COMPONENTS WITH RESPECT TO THEIR PLACEMENT IN THE RESPECTIVE DOOR OPENINGS. B. COMPLETE (RISERS, POINT-TO-POINT) ACCESS CONTROL SYSTEM BLOCK WIRING DIAGRAMS. C. WIRING INSTRUCTIONS FOR EACH ELECTRONIC COMPONENT SCHEDULED HEREIN. 2. ELECTRICAL COORDINATION: COORDINATE WITH RELATED SECTIONS THE VOLTAGES AND WIRING DETAILS REQUIRED AT ELECTRICALLY CONTROLLED AND OPERATED HARDWARE OPENINGS. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 11241 | Forwarded | For Review | 2020-10-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-10-08 | Submittal Number: 08 71 00-3.0 From: BROOKE BURCHAM Final Due Date: 10/16/20 Subject: 087100 - 1.3-C SHOP DRAWINGS - ELECTRICAL COORDINATION (MISSION GLASS) Description: SHOP DRAWINGS : DETAILS OF ELECTRIFIED ACCESS CONTROL HARDWARE INDICATING THE FOLLOWING: 1. WIRING DIAGRAMS: UPON RECEIPT OF APPROVED SCHEDULES, SUBMIT DETAILED SYSTEM WIRING DIAGRAMS FOR POWER, SIGNALING, MONITORING, COMMUNICATION, AND CONTROL OF THE ACCESS CONTROL SYSTEM ELECTRIFIED HARDWARE. DIFFERENTIATE BETWEEN MANUFACTURER-INSTALLED AND FIELD-INSTALLED WIRING. INCLUDE THE FOLLOWING: A. ELEVATION DIAGRAM OF EACH UNIQUE ACCESS-CONTROLLED OPENING SHOWING LOCATION AND INTERCONNECTION OF MAJOR SYSTEM COMPONENTS WITH RESPECT TO THEIR PLACEMENT IN THE RESPECTIVE DOOR OPENINGS. B. COMPLETE (RISERS, POINT-TO-POINT) ACCESS CONTROL SYSTEM BLOCK WIRING DIAGRAMS. C. WIRING INSTRUCTIONS FOR EACH ELECTRONIC COMPONENT SCHEDULED HEREIN. 2. ELECTRICAL COORDINATION: COORDINATE WITH RELATED SECTIONS THE VOLTAGES AND WIRING DETAILS REQUIRED AT ELECTRICALLY CONTROLLED AND OPERATED HARDWARE OPENINGS. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 08718 | Review Response | Approved as Noted | 2020-10-08 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any question or comments, please feel free to contact us. Thanks. | Info Exchange
| 11490 | Forwarded | For Review | 2020-10-11 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers) | 2020-10-16 | Submittal Number: 08 71 00-3.0 From: BROOKE BURCHAM Final Due Date: 10/16/20 Subject: 087100 - 1.3-C SHOP DRAWINGS - ELECTRICAL COORDINATION (MISSION GLASS) Description: SHOP DRAWINGS : DETAILS OF ELECTRIFIED ACCESS CONTROL HARDWARE INDICATING THE FOLLOWING: 1. WIRING DIAGRAMS: UPON RECEIPT OF APPROVED SCHEDULES, SUBMIT DETAILED SYSTEM WIRING DIAGRAMS FOR POWER, SIGNALING, MONITORING, COMMUNICATION, AND CONTROL OF THE ACCESS CONTROL SYSTEM ELECTRIFIED HARDWARE. DIFFERENTIATE BETWEEN MANUFACTURER-INSTALLED AND FIELD-INSTALLED WIRING. INCLUDE THE FOLLOWING: A. ELEVATION DIAGRAM OF EACH UNIQUE ACCESS-CONTROLLED OPENING SHOWING LOCATION AND INTERCONNECTION OF MAJOR SYSTEM COMPONENTS WITH RESPECT TO THEIR PLACEMENT IN THE RESPECTIVE DOOR OPENINGS. B. COMPLETE (RISERS, POINT-TO-POINT) ACCESS CONTROL SYSTEM BLOCK WIRING DIAGRAMS. C. WIRING INSTRUCTIONS FOR EACH ELECTRONIC COMPONENT SCHEDULED HEREIN. 2. ELECTRICAL COORDINATION: COORDINATE WITH RELATED SECTIONS THE VOLTAGES AND WIRING DETAILS REQUIRED AT ELECTRICALLY CONTROLLED AND OPERATED HARDWARE OPENINGS. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 08850 | Review Response | Approved as Noted | 2020-10-19 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.19 | Info Exchange
| 11698 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-19 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 087100-0003-0 - Alum. Door Hardware Electrical Coordination.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-01 |  | 087100-0003-0 - Alum. Door Hardware Electrical Coordination.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-10-01 |  | 087100-0003-0 - Alum. Door Hardware Electrical Coordination.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-30 02:00 |  | 087100-0003-0 - Alum. Door Hardware Electrical Coordination.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-30 |  | 087100-0003-0 - Alum. Door Hardware Electrical Coordination.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-19 |  | 087100-0003-0 - Alum. Door Hardware Electrical Coordination ME_ST08_POP REVIEWED.pdf
08 71 00-003-00-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-003-00 087100 - 1.3-C SHOP DRAWINGS - ELECTRICAL COORDINATION (MISSION GLASS) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-003-00 - 08 71 00-003-00 087100 - 1.3-C SHOP DRAWINGS - ELECTRICAL COORDINATION (MISSION GLASS) | -1 | 2020-11-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-19 |  | 087100-0003-0 - Alum. Door Hardware Electrical Coordination ME_ST08_POP REVIEWED.pdf
08 71 00-004-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-004-00 DOOR HARDWARE - Keying Schedule | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-11 | Review Response - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-11-25 | 2020-11-20 | 10 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09357 | Received | For Review | 2020-11-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-11-25 | Submittal Number: 08 71 00-4.0 From: JES PELKEY Final Due Date: 11/24/20 Subject: DOOR HARDWARE - KEYING SCHEDULE Description: KEYING SCHEDULE : AFTER A KEYING MEETING WITH THE OWNER HAS TAKEN PLACE PREPARE A SEPARATE KEYING SCHEDULE DETAILING FINAL INSTRUCTIONS. SUBMIT THE KEYING SCHEDULE IN ELECTRONIC FORMAT. INCLUDE KEYING SYSTEM EXPLANATION, DOOR NUMBERS, KEY SET SYMBOLS, HARDWARE SET NUMBERS AND SPECIAL INSTRUCTIONS. OWNER MUST APPROVE SUBMITTED KEYING SCHEDULE PRIOR TO THE ORDERING OF PERMANENT CYLINDERS/CORES. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 12346 | Forwarded | For Review | 2020-11-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-11-18 | Submittal Number: 08 71 00-4.0 From: JES PELKEY Final Due Date: 11/24/20 Subject: DOOR HARDWARE - KEYING SCHEDULE Description: KEYING SCHEDULE : AFTER A KEYING MEETING WITH THE OWNER HAS TAKEN PLACE PREPARE A SEPARATE KEYING SCHEDULE DETAILING FINAL INSTRUCTIONS. SUBMIT THE KEYING SCHEDULE IN ELECTRONIC FORMAT. INCLUDE KEYING SYSTEM EXPLANATION, DOOR NUMBERS, KEY SET SYMBOLS, HARDWARE SET NUMBERS AND SPECIAL INSTRUCTIONS. OWNER MUST APPROVE SUBMITTED KEYING SCHEDULE PRIOR TO THE ORDERING OF PERMANENT CYLINDERS/CORES. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 12688 | Responded and Closed | No Action Taken or Required | 2020-11-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | THIS IS TO BE SUBMITTED TO OWNER FOR APPROVAL | Info Exchange
| 10069 | Review Response | Approved as Noted | 2020-12-02 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the review submittal reference above. If you have any questions or comments, please feel free to contact us. Thanks. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-10 |  | 08 71 00_4 Rev0 DOOR HARDWARE_Keying Schedule_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-10 |  | 08 71 00_4 Rev0 DOOR HARDWARE_Keying Schedule_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-11-20 |  | 08 71 00_4 Rev0 DOOR HARDWARE_Keying Schedule_MAM Reviewed_POP.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-11-10 |  | 08 71 00_4 Rev0 DOOR HARDWARE_Keying Schedule_MAM Reviewed.pdf
08 71 00-004-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-004-01 DOOR HARDWARE - Keying Schedule | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-11 | Responded and Closed - No Action Taken or Required |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-01-05 | 2020-12-16 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10109 | Received | For Review | 2020-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Populous SCA_CCA; Allie Zimmerman | 2021-01-05 | Submittal Number: 08 71 00-4.1 From: ALLIE ZIMMERMAN Final Due Date: 12/22/20 Subject: DOOR HARDWARE - KEYING SCHEDULE Description: FOR RECORD ONLY - AFTER A KEYING MEETING WITH THE OWNER HAS TAKEN PLACE PREPARE A SEPARATE KEYING SCHEDULE DETAILING FINAL INSTRUCTIONS. SUBMIT THE KEYING SCHEDULE IN ELECTRONIC FORMAT. INCLUDE KEYING SYSTEM EXPLANATION, DOOR NUMBERS, KEY SET SYMBOLS, HARDWARE SET NUMBERS AND SPECIAL INSTRUCTIONS. OWNER MUST APPROVE SUBMITTED KEYING SCHEDULE PRIOR TO THE ORDERING OF PERMANENT CYLINDERS/CORES. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 13218 | Forwarded | For Review | 2020-12-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-12-18 | Submittal Number: 08 71 00-4.1 From: ALLIE ZIMMERMAN Final Due Date: 12/22/20 Subject: DOOR HARDWARE - KEYING SCHEDULE Description: FOR RECORD ONLY - AFTER A KEYING MEETING WITH THE OWNER HAS TAKEN PLACE PREPARE A SEPARATE KEYING SCHEDULE DETAILING FINAL INSTRUCTIONS. SUBMIT THE KEYING SCHEDULE IN ELECTRONIC FORMAT. INCLUDE KEYING SYSTEM EXPLANATION, DOOR NUMBERS, KEY SET SYMBOLS, HARDWARE SET NUMBERS AND SPECIAL INSTRUCTIONS. OWNER MUST APPROVE SUBMITTED KEYING SCHEDULE PRIOR TO THE ORDERING OF PERMANENT CYLINDERS/CORES. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 13346 | Responded and Closed | No Action Taken or Required | 2020-12-16 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | For Record Only | Info Exchange
| 13664 | Sent | For Information Only | 2021-01-05 | Josh Dobken (Populous) | Simran George (Mortenson Construction); Allie Zimmerman |  | Responded and Closed (No Action Taken or Required) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: For Record Only | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-11 |  | SCA Key Schedule Submittal Rev1 _MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-11 |  | SCA Key Schedule Submittal Rev1 _MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-12-16 |  | SCA Key Schedule Submittal Rev1 _MAM Reviewed_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-12-10 02:00 |  | SCA Key Schedule Submittal Rev1 _MAM Reviewed.pdf
08 71 00-006-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-006-00 087100 - 1.3-F - OPERATION AND MAINTENANCE MANUALS (MISSION GLASS) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-14 | Responded and Closed - Rejected |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-05-29 07:00 | 2020-05-27 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-05-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05860 | Received | For Review | 2020-05-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-29 07:00 | Submittal Number: 08 71 00-6.0 From: BROOKE BURCHAM Final Due Date: 06/03/20 Subject: 087100 - 1.3-F - OPERATION AND MAINTENANCE MANUALS (MISSION GLASS) Description: OPERATING AND MAINTENANCE MANUALS : PROVIDE MANUFACTURERS OPERATING AND MAINTENANCE MANUALS FOR EACH ITEM COMPRISING THE COMPLETE DOOR HARDWARE INSTALLATION IN QUANTITY AS REQUIRED IN DIVISION 01, CLOSEOUT SUBMITTALS. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07951 | Forwarded | For Review | 2020-05-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-05-21 | Submittal Number: 08 71 00-6.0 From: BROOKE BURCHAM Final Due Date: 06/03/20 Subject: 087100 - 1.3-F - OPERATION AND MAINTENANCE MANUALS (MISSION GLASS) Description: OPERATING AND MAINTENANCE MANUALS : PROVIDE MANUFACTURERS OPERATING AND MAINTENANCE MANUALS FOR EACH ITEM COMPRISING THE COMPLETE DOOR HARDWARE INSTALLATION IN QUANTITY AS REQUIRED IN DIVISION 01, CLOSEOUT SUBMITTALS. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 08223 | Responded and Closed | Rejected | 2020-05-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | O & M manuals should not be submitted until after all associated submittals are complete and work is installed | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-13 |  | 087100-0006-0 HARDWARE - O AND M MANUALS.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-13 |  | 087100-0006-0 HARDWARE - O AND M MANUALS.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-27 |  | 087100-0006-0 HARDWARE - O AND M MANUALS - POP.pdf
08 71 00-009-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-009-00 Door Hardware - Priority Openings_Part 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-02 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-04-17 07:00 | 2020-05-05 | 34 |  | Record Copies; Transfers; Submittals |  | 34 |  | 2020-05-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05183 | Received | For Review | 2020-04-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-04-17 07:00 | Submittal Number: 08 71 00-9.0 From: TYRONE THORNTON Final Due Date: 05/01/20 Subject: DOOR HARDWARE - PRIORITY OPENINGS_PART 1 Description: "DOOR HARDWARE - PRIORITY OPENINGS_PART 1" DOES NOT INCLUDE THE HARDWARE MISSING DOORS FROM THE "HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2" SUBMITTAL. "DOOR HARDWARE - PRIORITY OPENINGS_PART 2" WILL CAPTURE THE DOOR HARDWARE WITHIN THE "HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2"PRIORITY DOORS/FRAMES SUBMITTAL PACKAGE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07035 | Forwarded | For Review | 2020-04-02 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-09 | Submittal Number: 08 71 00-9.0 From: TYRONE THORNTON Final Due Date: 05/01/20 Subject: DOOR HARDWARE - PRIORITY OPENINGS_PART 1 Description: "DOOR HARDWARE - PRIORITY OPENINGS_PART 1" DOES NOT INCLUDE THE HARDWARE MISSING DOORS FROM THE "HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2" SUBMITTAL. "DOOR HARDWARE - PRIORITY OPENINGS_PART 2" WILL CAPTURE THE DOOR HARDWARE WITHIN THE "HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2"PRIORITY DOORS/FRAMES SUBMITTAL PACKAGE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07417 | Forwarded | For Review | 2020-04-21 | Josh Dobken (Populous) | Rick Lewis (Studio 08 Consultants); Linda Scott (Studio 08 Consultants) | 2020-04-17 | Submittal Number: 08 71 00-9.0 From: TYRONE THORNTON Final Due Date: 05/01/20 Subject: DOOR HARDWARE - PRIORITY OPENINGS_PART 1 Description: "DOOR HARDWARE - PRIORITY OPENINGS_PART 1" DOES NOT INCLUDE THE HARDWARE MISSING DOORS FROM THE "HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2" SUBMITTAL. "DOOR HARDWARE - PRIORITY OPENINGS_PART 2" WILL CAPTURE THE DOOR HARDWARE WITHIN THE "HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2"PRIORITY DOORS/FRAMES SUBMITTAL PACKAGE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07501 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Chad Francis (Populous) | 2020-04-17 | Submittal Number: 08 71 00-9.0 From: TYRONE THORNTON Final Due Date: 05/01/20 Subject: DOOR HARDWARE - PRIORITY OPENINGS_PART 1 Description: "DOOR HARDWARE - PRIORITY OPENINGS_PART 1" DOES NOT INCLUDE THE HARDWARE MISSING DOORS FROM THE "HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2" SUBMITTAL. "DOOR HARDWARE - PRIORITY OPENINGS_PART 2" WILL CAPTURE THE DOOR HARDWARE WITHIN THE "HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 2"PRIORITY DOORS/FRAMES SUBMITTAL PACKAGE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05731 | Review Response | Rejected | 2020-05-05 | Linda Scott (Studio 08 Consultants) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Here is the original Part 1 which has already been resubmitted. I noted it as Not Approved - Revise and Resubmit on our transmittal but also added that the resubmittal was already received and being reviewed. Thanks. | Info Exchange
| 07777 | Responded and Closed | Revise and Resubmit | 2020-05-05 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Resubmittal has been received, and will be reviewed and returned. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-02 |  | Seattle Center Arena Priority Hardware Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-02 |  | Seattle Center Arena Priority Hardware Submittal_MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-04-01 02:00 |  | Seattle Center Arena Priority Hardware Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-02 |  | Seattle Center Arena Priority Hardware Submittal_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-04-01 |  | Seattle Center Arena Priority Hardware Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-05 |  | Seattle Center Arena Priority Hardware Submittal_MAM Review ST08 - NO REVIEW - POP.pdf
08 71 00-009-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-009-01 HM Door Hardware - Priority Openings (Event Level, Mech Mezz, Main Con) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-24 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-05-08 | 2020-05-06 | 13 |  | Record Copies; Transfers; Submittals | 08 71 00-009-02 - 08 71 00-009-01 HM Door Hardware - Priority Openings (Event Level, Mech Mezz, Main Con) | 12 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05532 | Received | For Review | 2020-04-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-08 | Submittal Number: 08 71 00-9.1 From: TYRONE THORNTON Final Due Date: 05/07/20 Subject: HM DOOR HARDWARE - PRIORITY OPENINGS (EVENT LEVEL, MECH MEZZ, MAIN CON) Description: THIS SUBMITTAL WILL INCLUDE PRIORITY HOLLOW METAL DOOR HARDWARE FOR EVENT LEVEL, MECHANICAL MEZZANINE, AND MAIN CONCOURSE LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07494 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants) | 2020-05-01 | Submittal Number: 08 71 00-9.1 From: TYRONE THORNTON Final Due Date: 05/07/20 Subject: HM DOOR HARDWARE - PRIORITY OPENINGS (EVENT LEVEL, MECH MEZZ, MAIN CON) Description: THIS SUBMITTAL WILL INCLUDE PRIORITY HOLLOW METAL DOOR HARDWARE FOR EVENT LEVEL, MECHANICAL MEZZANINE, AND MAIN CONCOURSE LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07502 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Chad Francis (Populous) |  | Submittal Number: 08 71 00-9.1 From: TYRONE THORNTON Final Due Date: 05/07/20 Subject: HM DOOR HARDWARE - PRIORITY OPENINGS (EVENT LEVEL, MECH MEZZ, MAIN CON) Description: THIS SUBMITTAL WILL INCLUDE PRIORITY HOLLOW METAL DOOR HARDWARE FOR EVENT LEVEL, MECHANICAL MEZZANINE, AND MAIN CONCOURSE LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05736 | Review Response | Approved as Noted | 2020-05-05 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous); Chad Francis (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 07782 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. Provide complete riser and point-to-point wiring diagrams for approval and coordination with other trades, as noted in the hardware specification. These should include all electrified hardware for a complete system, even if product is provided by others (such as card readers). 2. Contractor and Supplier to coordinate keying requirements with the owner prior to the order of any locks or cylinders. 3. ME1 lever is not approved – See RFI 2446R1 for lever selection. 4. Everest 29XP Primus cores are required per specification. 5. Request-to-exit switches to be RX-LC. 6. Push plates and pull plates are specified as .125 thick. Provide as specified. 7. See individual hardware sets and product data for additional comments and markups. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-23 |  | SCA - Hardware Submittal Revised 4.21.20 (Event MM Main)_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-23 |  | SCA - Hardware Submittal Revised 4.21.20 (Event MM Main)_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-23 |  | SCA - Hardware Submittal Revised 4.21.20 (Event MM Main)_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-04-23 |  | SCA - Hardware Submittal Revised 4.21.20 (Event MM Main)_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-06 |  | SCA - Hardware Submittal Revised 4.21.20 (Event MM Main)_MAM Review ST08 REVIEW - POP.pdf
08 71 00-009-02 | 08 71 00 - DOOR HARDWARE | 08 71 00-009-01 HM Door Hardware - Priority Openings (Event Level, Mech Mezz, Main Con) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-009-01 - 08 71 00-009-01 HM Door Hardware - Priority Openings (Event Level, Mech Mezz, Main Con) | -1 | 2020-05-20
08 71 00-010-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-010-00 Door Hardware - Priority Openings_Part 2 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-03 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-20 07:00 | 2020-04-20 | 18 |  | Record Copies; Transfers; Submittals | 08 71 00-010-00-01 - 08 71 00-010-00 Door Hardware - Priority Openings_Part 2 | 14 |  | 2020-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05206 | Received | For Review | 2020-04-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-20 07:00 | Submittal Number: 08 71 00-10.0 From: TYRONE THORNTON Final Due Date: 05/06/20 Subject: DOOR HARDWARE - PRIORITY OPENINGS_PART 2 Description: "DOOR HARDWARE - PRIORITY OPENINGS_PART 2" INCLUDES THE HARDWARE MISSING DOORS FROM THE "HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 1" SUBMITTAL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07078 | Forwarded | For Review | 2020-04-03 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-10 | Submittal Number: 08 71 00-10.0 From: TYRONE THORNTON Final Due Date: 05/06/20 Subject: DOOR HARDWARE - PRIORITY OPENINGS_PART 2 Description: "DOOR HARDWARE - PRIORITY OPENINGS_PART 2" INCLUDES THE HARDWARE MISSING DOORS FROM THE "HOLLOW METAL AND DOOR FRAMES - PRIORITY OPENINGS_PART 1" SUBMITTAL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05423 | Review Response | Approved as Noted/Resubmit | 2020-04-16 | Rick Lewis (Studio 08 Consultants) | Populous SCA_CCA |  | Please find attached the reviewed submittal. Note the levers are still not approved and we have not received the Allegion options as discussed on the conference call on April 7th. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 07370 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-03 |  | Priority Door Hardware_Part 2_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-03 |  | Priority Door Hardware_Part 2_MAM Review.pdf
| Review Response |  | Rick Lewis (Studio 08 Consultants) | 1 | 2020-04-03 |  | Priority Door Hardware_Part 2_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-16 |  | Priority Door Hardware_Part 2_MAM Review REVIEWED ST08.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-20 |  | Priority Door Hardware_Part 2_MAM Review REVIEWED ST08-POP.pdf
08 71 00-010-00-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-010-00 Door Hardware - Priority Openings_Part 2 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-010-00 - 08 71 00-010-00 Door Hardware - Priority Openings_Part 2 | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-16 |  | Priority Door Hardware_Part 2_MAM Review REVIEWED ST08.pdf
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-20 |  | Priority Door Hardware_Part 2_MAM Review REVIEWED ST08-POP.pdf
08 71 00-011-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-011-00 Non-Priority Door Hardware - Event Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-16 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants) |  |  |  | 2020-04-30 | 2020-04-20 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05392 | Received | For Review | 2020-04-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-04-30 | Submittal Number: 08 71 00-11.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: NON-PRIORITY DOOR HARDWARE - EVENT LEVEL Description: THIS SUBMITTAL WILL INCLUDE ALL REMAINING NON-PRIORITY DOOR HARDWARE ON EVENT LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07317 | Forwarded | For Review | 2020-04-16 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-23 | Submittal Number: 08 71 00-11.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: NON-PRIORITY DOOR HARDWARE - EVENT LEVEL Description: THIS SUBMITTAL WILL INCLUDE ALL REMAINING NON-PRIORITY DOOR HARDWARE ON EVENT LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07320 | Forwarded | For Review | 2020-04-16 | Shaina Burris (Populous) | Linda Scott (Studio 08 Consultants) | 2020-04-23 | Submittal Number: 08 71 00-11.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: NON-PRIORITY DOOR HARDWARE - EVENT LEVEL Description: THIS SUBMITTAL WILL INCLUDE ALL REMAINING NON-PRIORITY DOOR HARDWARE ON EVENT LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05432 | Review Response | Rejected | 2020-04-17 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the submittal noted above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 07371 | Responded and Closed | Revise and Resubmit | 2020-04-20 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-16 |  | SCA - Remaining Event Level Hardware_ MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-16 |  | SCA - Remaining Event Level Hardware_ MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-16 |  | SCA - Remaining Event Level Hardware_ MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-04-16 |  | SCA - Remaining Event Level Hardware_ MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-04-17 |  | SCA - Remaining Event Level Hardware_ MAM Review ST08 REVIEW.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-04-20 |  | SCA - Remaining Event Level Hardware_ MAM Review ST08 REVIEW-POP.pdf
08 71 00-011-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-011-01 Non-Priority Door Hardware - Event Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-24 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-05-08 | 2020-05-12 | 19 |  | Record Copies; Transfers; Submittals | 08 71 00-011-01-01 - 08 71 00-011-01 Non-Priority Door Hardware - Event Level | 19 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05533 | Received | For Review | 2020-04-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-08 | Submittal Number: 08 71 00-11.1 From: TYRONE THORNTON Final Due Date: 05/07/20 Subject: NON-PRIORITY DOOR HARDWARE - EVENT LEVEL Description: THIS SUBMITTAL WILL INCLUDE ALL REMAINING NON-PRIORITY DOOR HARDWARE ON EVENT LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07495 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants) | 2020-05-01 | Submittal Number: 08 71 00-11.1 From: TYRONE THORNTON Final Due Date: 05/07/20 Subject: NON-PRIORITY DOOR HARDWARE - EVENT LEVEL Description: THIS SUBMITTAL WILL INCLUDE ALL REMAINING NON-PRIORITY DOOR HARDWARE ON EVENT LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07503 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Chad Francis (Populous) | 2020-05-01 | Submittal Number: 08 71 00-11.1 From: TYRONE THORNTON Final Due Date: 05/07/20 Subject: NON-PRIORITY DOOR HARDWARE - EVENT LEVEL Description: THIS SUBMITTAL WILL INCLUDE ALL REMAINING NON-PRIORITY DOOR HARDWARE ON EVENT LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05836 | Review Response | Approved as Noted | 2020-05-12 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 07921 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-23 |  | SCA - Event Level Hardware Submittal Revised 4.22.20_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-23 |  | SCA - Event Level Hardware Submittal Revised 4.22.20_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-23 |  | SCA - Event Level Hardware Submittal Revised 4.22.20_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-04-23 |  | SCA - Event Level Hardware Submittal Revised 4.22.20_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-12 |  | SCA - Event Level Hardware Submittal Revised 4.22.20_MAM Review ST08 REVIEW - POP.pdf
08 71 00-011-01-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-011-01 Non-Priority Door Hardware - Event Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-011-01 - 08 71 00-011-01 Non-Priority Door Hardware - Event Level | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-12 |  | SCA - Event Level Hardware Submittal Revised 4.22.20_MAM Review ST08 REVIEW - POP.pdf
08 71 00-012-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-012-01 HM Door Hardware - Mechanical Mezzanine Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-28 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-05-12 | 2020-05-12 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05578 | Received | For Review | 2020-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-12 | Submittal Number: 08 71 00-12.1 From: TYRONE THORNTON Final Due Date: 05/11/20 Subject: HM DOOR HARDWARE - MECHANICAL MEZZANNINE LEVEL Description: THIS SUBMITTAL INCLUDES THE REMAINDER OF THE HOLLOW METAL DOOR HARDWARE FOR THE MECHANICAL MEZZANINE LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07565 | Forwarded | For Review | 2020-04-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants) | 2020-05-04 | Submittal Number: 08 71 00-12.1 From: TYRONE THORNTON Final Due Date: 05/11/20 Subject: HM DOOR HARDWARE - MECHANICAL MEZZANNINE LEVEL Description: THIS SUBMITTAL INCLUDES THE REMAINDER OF THE HOLLOW METAL DOOR HARDWARE FOR THE MECHANICAL MEZZANINE LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07855 | Forwarded | For Review | 2020-05-11 | Chad Francis (Populous) | Chad Francis (Populous) | 2020-05-12 | Submittal Number: 08 71 00-12.1 From: TYRONE THORNTON Final Due Date: 05/11/20 Subject: HM DOOR HARDWARE - MECHANICAL MEZZANNINE LEVEL Description: THIS SUBMITTAL INCLUDES THE REMAINDER OF THE HOLLOW METAL DOOR HARDWARE FOR THE MECHANICAL MEZZANINE LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05843 | Review Response | Approved as Noted | 2020-05-12 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thanks. | Info Exchange
| 07928 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-27 |  | SCA - Mezzanine Hardware Submittal Revised 4.27.20_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-27 |  | 08 71 00-12.1 SCA - Mezzanine Hardware Submittal Revised 4.27.20_MAM Review.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2020-04-27 |  | SCA - Mezzanine Hardware Submittal Revised 4.27.20_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-04-27 |  | 08 71 00-12.1 SCA - Mezzanine Hardware Submittal Revised 4.27.20_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-12 |  | 08 71 00-12.1 SCA - Mezzanine Hardware Submittal Revised 4.27.20_MAM Review ST08 REVIEWED - POP.pdf
08 71 00-013-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-013-01 HM Door Hardware – Main Concourse | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-28 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-05-12 | 2020-05-12 | 15 |  | Record Copies; Transfers; Submittals | 08 71 00-013-01-01 - 08 71 00-013-01 HM Door Hardware – Main Concourse | 15 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05593 | Received | For Review | 2020-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-12 | Submittal Number: 08 71 00-13.1 From: TYRONE THORNTON Final Due Date: 05/22/20 Subject: HM DOOR HARDWARE – MAIN CONCOURSE Description: THIS SUBMITTAL INCLUDES ALL REMAINING HOLLOW METAL DOOR HARDWARE FOR THE MAIN CONCOURSE LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07579 | Forwarded | For Review | 2020-04-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants) | 2020-05-05 | Submittal Number: 08 71 00-13.1 From: TYRONE THORNTON Final Due Date: 05/22/20 Subject: HM DOOR HARDWARE – MAIN CONCOURSE Description: THIS SUBMITTAL INCLUDES ALL REMAINING HOLLOW METAL DOOR HARDWARE FOR THE MAIN CONCOURSE LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07856 | Forwarded | For Review | 2020-05-11 | Chad Francis (Populous) | Chad Francis (Populous) | 2020-05-12 | Submittal Number: 08 71 00-13.1 From: TYRONE THORNTON Final Due Date: 05/22/20 Subject: HM DOOR HARDWARE – MAIN CONCOURSE Description: THIS SUBMITTAL INCLUDES ALL REMAINING HOLLOW METAL DOOR HARDWARE FOR THE MAIN CONCOURSE LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05837 | Review Response | Approved as Noted | 2020-05-12 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 07927 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-27 |  | SCA - Main Concourse HM Door Hardware Submittal_Rev1_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-27 |  | 08 71 00-13.1 SCA - Main Concourse HM Door Hardware Submittal_Rev1_MAM Review.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2020-04-27 |  | SCA - Main Concourse HM Door Hardware Submittal_Rev1_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-04-27 |  | 08 71 00-13.1 SCA - Main Concourse HM Door Hardware Submittal_Rev1_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-12 |  | 08 71 00-13.1 SCA - Main Concourse HM Door Hardware Submittal_Rev1_MAM Review ST08 REVIEW - POP.pdf
08 71 00-013-01-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-013-01 HM Door Hardware – Main Concourse | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-013-01 - 08 71 00-013-01 HM Door Hardware – Main Concourse | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-12 |  | 08 71 00-13.1 SCA - Main Concourse HM Door Hardware Submittal_Rev1_MAM Review ST08 REVIEW - POP.pdf
08 71 00-014-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-014-01 Door Hardware – Suite Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-05 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-05-19 | 2020-05-18 | 14 |  | Record Copies; Transfers; Submittals | 08 71 00-014-01-01 - 08 71 00-014-01 Door Hardware – Suite Level | 11 |  | 2020-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05724 | Received | For Review | 2020-05-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-19 | Submittal Number: 08 71 00-14.1 From: TYRONE THORNTON Final Due Date: 05/22/20 Subject: DOOR HARDWARE – SUITE LEVEL Description: THIS SUBMITTAL INCLUDES ALL REMAINING DOOR HARDWARE FOR THE SUITE LEVEL Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07769 | Forwarded | For Review | 2020-05-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-05-12 | Submittal Number: 08 71 00-14.1 From: TYRONE THORNTON Final Due Date: 05/22/20 Subject: DOOR HARDWARE – SUITE LEVEL Description: THIS SUBMITTAL INCLUDES ALL REMAINING DOOR HARDWARE FOR THE SUITE LEVEL Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05883 | Review Response | Approved as Noted | 2020-05-15 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 07983 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | SCA - Suite Level Hardware Submittal Rev 1_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-05 |  | 08 71 00-14.1 SCA - Suite Level Hardware Submittal Rev 1_MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-05-05 |  | 08 71 00-14.1 SCA - Suite Level Hardware Submittal Rev 1_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-18 |  | 08 71 00-14.1 SCA - Suite Level Hardware Submittal Rev 1_MAM Reviewed REVIEWED ST08 - POP.pdf
08 71 00-014-01-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-014-01 Door Hardware – Suite Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-014-01 - 08 71 00-014-01 Door Hardware – Suite Level | -1 | 2020-06-01
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 08 71 00-14.1 SCA - Suite Level Hardware Submittal Rev 1_MAM Reviewed REVIEWED ST08 - POP.pdf
08 71 00-015-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-015-01 Door Hardware – Upper Concourse | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-06 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-05-20 | 2020-05-18 | 13 |  | Record Copies; Transfers; Submittals | 08 71 00-015-01-01 - 08 71 00-015-01 Door Hardware – Upper Concourse | 12 |  | 2020-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05741 | Received | For Review | 2020-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-20 | Submittal Number: 08 71 00-15.1 From: TYRONE THORNTON Final Due Date: 05/20/20 Subject: DOOR HARDWARE – UPPER CONCOURSE Description: THIS SUBMITTAL INCLUDES ALL REMAINING DOOR HARDWARE FOR THE BASE BUILDING ON THE UPPER CONCOURSE LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07789 | Forwarded | For Review | 2020-05-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-05-13 | Submittal Number: 08 71 00-15.1 From: TYRONE THORNTON Final Due Date: 05/20/20 Subject: DOOR HARDWARE – UPPER CONCOURSE Description: THIS SUBMITTAL INCLUDES ALL REMAINING DOOR HARDWARE FOR THE BASE BUILDING ON THE UPPER CONCOURSE LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05884 | Review Response | Approved as Noted | 2020-05-17 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 07986 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-06 |  | 08 71 00-15 Rev 1 SCA - Upper Concourse Hardware Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-06 |  | 08 71 00-15 Rev 1 SCA - Upper Concourse Hardware Submittal_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-05-06 |  | 08 71 00-15 Rev 1 SCA - Upper Concourse Hardware Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-18 |  | 08 71 00-15 Rev 1 SCA - Upper Concourse Hardware Submittal_MAM Review ST08 REVIEWED - POP.pdf
08 71 00-015-01-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-015-01 Door Hardware – Upper Concourse | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-015-01 - 08 71 00-015-01 Door Hardware – Upper Concourse | -1 | 2020-06-01
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 08 71 00-15 Rev 1 SCA - Upper Concourse Hardware Submittal_MAM Review ST08 REVIEWED - POP.pdf
08 71 00-016-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-016-01 Door Hardware – Bridge & Catwalk | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-06 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-05-20 | 2020-05-18 | 13 |  | Record Copies; Transfers; Submittals | 08 71 00-016-01-01 - 08 71 00-016-01 Door Hardware – Bridge & Catwalk | 12 |  | 2020-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05742 | Received | For Review | 2020-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-20 | Submittal Number: 08 71 00-16.1 From: TYRONE THORNTON Final Due Date: 05/20/20 Subject: DOOR HARDWARE – BRIDGE & CATWALK Description: THIS SUBMITTAL INCLUDES ALL REMAINING DOOR HARDWARE IN THE BASE BUILDING FOR THE BRIDGE AND CATWALK LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07790 | Forwarded | For Review | 2020-05-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-05-13 | Submittal Number: 08 71 00-16.1 From: TYRONE THORNTON Final Due Date: 05/20/20 Subject: DOOR HARDWARE – BRIDGE & CATWALK Description: THIS SUBMITTAL INCLUDES ALL REMAINING DOOR HARDWARE IN THE BASE BUILDING FOR THE BRIDGE AND CATWALK LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05893 | Review Response | Approved as Noted | 2020-05-17 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 07993 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-06 |  | 08 71 00-16 Rev 1_ SCA - Bridge & Catwalk Hardware Submittal Revised_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-06 |  | 08 71 00-16 Rev 1_ SCA - Bridge & Catwalk Hardware Submittal Revised_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-05-06 |  | 08 71 00-16 Rev 1_ SCA - Bridge & Catwalk Hardware Submittal Revised_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-18 |  | 08 71 00-16 Rev 1_ SCA - Bridge & Catwalk Hardware Submittal Revised_MAM Review REVIEWED ST08 - POP.pdf
08 71 00-016-01-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-016-01 Door Hardware – Bridge & Catwalk | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-016-01 - 08 71 00-016-01 Door Hardware – Bridge & Catwalk | -1 | 2020-06-01
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 08 71 00-16 Rev 1_ SCA - Bridge & Catwalk Hardware Submittal Revised_MAM Review REVIEWED ST08 - POP.pdf
08 71 00-017-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-017-01 Auto Operators | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-05 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-05-19 | 2020-05-18 | 14 |  | Record Copies; Transfers; Submittals | 08 71 00-017-01-01 - 08 71 00-017-01 Auto Operators | 11 |  | 2020-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05725 | Received | For Review | 2020-05-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-19 | Submittal Number: 08 71 00-17.1 From: TYRONE THORNTON Final Due Date: 05/19/20 Subject: AUTO OPERATORS Description: THIS SUBMITTAL WILL ENCOMPASS THE HOLLOW METAL AUTO OPERATOR HARDWARE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07770 | Forwarded | For Review | 2020-05-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-05-12 | Submittal Number: 08 71 00-17.1 From: TYRONE THORNTON Final Due Date: 05/19/20 Subject: AUTO OPERATORS Description: THIS SUBMITTAL WILL ENCOMPASS THE HOLLOW METAL AUTO OPERATOR HARDWARE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 05890 | Review Response | Approved as Noted | 2020-05-15 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 07991 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | SCA - Auto Operator Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-05 |  | 08 71 00-17.1 SCA - Auto Operator Submittal_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-05-05 |  | 08 71 00-17.1 SCA - Auto Operator Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-05-18 |  | 08 71 00-17.1 SCA - Auto Operator Submittal_MAM Review REVIEWED ST08 - POP.pdf
08 71 00-017-01-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-017-01 Auto Operators | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-017-01 - 08 71 00-017-01 Auto Operators | -1 | 2020-06-01
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 08 71 00-17.1 SCA - Auto Operator Submittal_MAM Review REVIEWED ST08 - POP.pdf
08 71 00-018-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-018-00 08 71 00 - Premium Spaces - Door Hardware - Event Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-14 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-07-28 | 2020-07-27 | 14 |  | Record Copies; Transfers; Submittals | 08 71 00-018-00-01 - 08 71 00-018-00 08 71 00 - Premium Spaces - Door Hardware - Event Level | 11 |  | 2020-07-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06946 | Received | For Review | 2020-07-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-28 | Submittal Number: 08 71 00-18.0 From: TYRONE THORNTON Final Due Date: 07/27/20 Subject: 08 71 00 - PREMIUM SPACES - DOOR HARDWARE - EVENT LEVEL Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE HM/WD DOOR HARDWARE FOR THE EVENT LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 09304 | Forwarded | For Review | 2020-07-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-07-21 | Submittal Number: 08 71 00-18.0 From: TYRONE THORNTON Final Due Date: 07/27/20 Subject: 08 71 00 - PREMIUM SPACES - DOOR HARDWARE - EVENT LEVEL Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE HM/WD DOOR HARDWARE FOR THE EVENT LEVEL. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07155 | Review Response | Approved as Noted | 2020-07-24 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 09568 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | SCA Premium Spaces Event Level Hardware Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 08 71 00-18.0 SCA Premium Spaces Event Level Hardware Submittal_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-07-13 |  | 08 71 00-18.0 SCA Premium Spaces Event Level Hardware Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-27 |  | 08 71 00-18.0 SCA Premium Spaces Event Level Hardware Submittal_MAM Review ST08 REVIEW_POP.pdf
08 71 00-018-00-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-018-00 08 71 00 - Premium Spaces - Door Hardware - Event Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-018-00 - 08 71 00-018-00 08 71 00 - Premium Spaces - Door Hardware - Event Level | -1 | 2020-08-10
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-27 |  | 08 71 00-18.0 SCA Premium Spaces Event Level Hardware Submittal_MAM Review ST08 REVIEW_POP.pdf
08 71 00-019-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-019-00 08 71 00 - Premium Spaces - Door Hardware - Main Concourse/Garage 03 & Suite Levels | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-20 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-08-03 | 2020-07-28 | 9 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07015 | Received | For Review | 2020-07-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-03 | Submittal Number: 08 71 00-19.0 From: TYRONE THORNTON Final Due Date: 07/30/20 Subject: 08 71 00 - PREMIUM SPACES - DOOR HARDWARE - MAIN CONCOURSE/GARAGE 03 & SUITE LEVELS Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE HM/WD DOOR HARDWARE FOR THE MAIN CONCOURSE/GARAGE 03. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 09397 | Forwarded | For Review | 2020-07-20 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-07-27 | Submittal Number: 08 71 00-19.0 From: TYRONE THORNTON Final Due Date: 07/30/20 Subject: 08 71 00 - PREMIUM SPACES - DOOR HARDWARE - MAIN CONCOURSE/GARAGE 03 & SUITE LEVELS Description: THIS SUBMITTAL INCLUDES ALL THE PREMIUM SPACE HM/WD DOOR HARDWARE FOR THE MAIN CONCOURSE/GARAGE 03. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07170 | Review Response | Approved as Noted | 2020-07-27 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 09625 | Responded and Closed | Approved as Noted | 2020-07-28 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-20 |  | CPA - Premium Spaces Main Concourse & Suite Level Hardware Submittal_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-20 |  | CPA - Premium Spaces Main Concourse & Suite Level Hardware Submittal_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-07-20 |  | CPA - Premium Spaces Main Concourse & Suite Level Hardware Submittal_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-28 |  | CPA - Premium Spaces Main Concourse & Suite Level Hardware Submittal_MAM Review ST08 REVIEWED_POP.pdf
08 71 00-022-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-022-01 08 71 00 - All Base Building Door Hardware | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-16 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-07-30 | 2020-07-27 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-07-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06988 | Received | For Review | 2020-07-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-30 | Submittal Number: 08 71 00-22.1 From: TYRONE THORNTON Final Due Date: 07/29/20 Subject: 08 71 00 - ALL BASE BUILDING DOOR HARDWARE Description: PLEASE NOTE, THIS IS A FOR RECORD COPY OF THE COMPRESSIVE SUBMITTAL FOR ALL BASE BUILDING DOOR HARDWARE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 09363 | Forwarded | For Review | 2020-07-16 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-07-23 | Submittal Number: 08 71 00-22.1 From: TYRONE THORNTON Final Due Date: 07/29/20 Subject: 08 71 00 - ALL BASE BUILDING DOOR HARDWARE Description: PLEASE NOTE, THIS IS A FOR RECORD COPY OF THE COMPRESSIVE SUBMITTAL FOR ALL BASE BUILDING DOOR HARDWARE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07156 | Review Response | Approved as Noted | 2020-07-27 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thanks. | Info Exchange
| 09569 | Responded and Closed | Approved as Noted | 2020-07-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached ccomments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-15 |  | 08 71 00 - SCA Hardware Submittal Revised 07.06.20_MAM Reivew.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-15 |  | 08 71 00-22.1 SCA Hardware Submittal Revised 07.06.20_MAM Reivew.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-07-15 |  | 08 71 00-22.1 SCA Hardware Submittal Revised 07.06.20_MAM Reivew.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-27 |  | 08 71 00-22.1 SCA Hardware Submittal Revised 07.06.20_MAM Reivew ST08 REVIEW_POP.pdf
08 71 00-023-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-023-00 08 71 00 - Door Hardware Wiring Diagrams | Closed | Architectural, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-23 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous), Mark Lievens (ME Engineers), Abby Harrison (ME Engineers) |  |  |  | 2020-07-08 07:00 | 2020-07-13 | 21 |  | Record Copies; Transfers; Submittals | 08 71 00-023-00-01 - 08 71 00-023-00 08 71 00 - Door Hardware Wiring Diagrams | 21 |  | 2020-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06566 | Received | For Review | 2020-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-08 07:00 | Submittal Number: 08 71 00-23.0 From: TYRONE THORNTON Final Due Date: 07/07/20 Subject: 08 71 00 - DOOR HARDWARE WIRING DIAGRAMS Description: DOOR HARDWARE WIRING DIAGRAMS Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 08840 | Forwarded | For Review | 2020-06-23 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-06-30 | Submittal Number: 08 71 00-23.0 From: TYRONE THORNTON Final Due Date: 07/07/20 Subject: 08 71 00 - DOOR HARDWARE WIRING DIAGRAMS Description: DOOR HARDWARE WIRING DIAGRAMS Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 08848 | Forwarded | For Review | 2020-06-23 | Chad Francis (Populous) | Mark Lievens (ME Engineers); Abby Harrison (ME Engineers) | 2020-06-30 | Submittal Number: 08 71 00-23.0 From: TYRONE THORNTON Final Due Date: 07/07/20 Subject: 08 71 00 - DOOR HARDWARE WIRING DIAGRAMS Description: DOOR HARDWARE WIRING DIAGRAMS Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 06825 | Review Response | Approved as Noted | 2020-07-03 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thanks. | Info Exchange
| 06927 | Review Response | Approved as Noted | 2020-07-13 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.13 | Info Exchange
| 09277 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-13 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached comments, Resubmit as required for current documents. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-23 |  | SCA Wiring Diagrams Submittal_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-23 |  | 08 71 00-23.0 SCA Wiring Diagrams Submittal_MAM Reviewed.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2020-06-23 |  | SCA Wiring Diagrams Submittal_MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-06-23 |  | 08 71 00-23.0 SCA Wiring Diagrams Submittal_MAM Reviewed.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-06-23 |  | SCA Wiring Diagrams Submittal_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-13 |  | 08 71 00-23.0 SCA Wiring Diagrams Submittal_MAM Reviewed_ST08_ME_POP.pdf
08 71 00-023-00-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-023-00 08 71 00 - Door Hardware Wiring Diagrams | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-023-00 - 08 71 00-023-00 08 71 00 - Door Hardware Wiring Diagrams | -1 | 2020-07-27
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 08 71 00-23.0 SCA Wiring Diagrams Submittal_MAM Reviewed_ST08_ME_POP.pdf
08 71 00-024-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-024-00 Door Hardware Added CCD 058 -063 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-20 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-08-03 | 2020-08-04 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07025 | Received | For Review | 2020-07-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-03 | Submittal Number: 08 71 00-24.0 From: TYRONE THORNTON Final Due Date: 08/03/20 Subject: DOOR HARDWARE ADDED CCD 058 -063 Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 09408 | Forwarded | For Review | 2020-07-20 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-07-27 | Submittal Number: 08 71 00-24.0 From: TYRONE THORNTON Final Due Date: 08/03/20 Subject: DOOR HARDWARE ADDED CCD 058 -063 Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07356 | Review Response | Approved as Noted | 2020-08-04 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thanks. | Info Exchange
| 09807 | Responded and Closed | Approved as Noted | 2020-08-04 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-20 |  | CPA - Door Hardware Submittal for Openings Added in CCD-058 to CCD-063_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-20 |  | CPA - Door Hardware Submittal for Openings Added in CCD-058 to CCD-063_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-07-20 |  | CPA - Door Hardware Submittal for Openings Added in CCD-058 to CCD-063_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-04 |  | CPA - Door Hardware Submittal for Openings Added in CCD-058 to CCD-063_MAM Review ST08 REVIEW_POP.pdf
08 71 00-025-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-025-00 08 71 00_Premium Space - Product Data & Hardware Schedule_Tunnel Corridors Doors (Hdw# 84.1) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-17 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-08-31 | 2020-08-18 | 2 |  | Record Copies; Transfers; Submittals | 08 71 00-025-00-01 - 08 71 00-025-00 08 71 00_Premium Space - Product Data & Hardware Schedule_Tunnel Corridors Doors (Hdw# 84.1) | 2 |  | 2020-08-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07572 | Received | For Review | 2020-08-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-31 | Submittal Number: 08 71 00-25.0 From: TYRONE THORNTON Final Due Date: 08/31/20 Subject: 08 71 00_PREMIUM SPACE - PRODUCT DATA & HARDWARE SCHEDULE_TUNNEL CORRIDORS DOORS (HDW# 84.1) Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 10078 | Forwarded | For Review | 2020-08-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-08-24 | Submittal Number: 08 71 00-25.0 From: TYRONE THORNTON Final Due Date: 08/31/20 Subject: 08 71 00_PREMIUM SPACE - PRODUCT DATA & HARDWARE SCHEDULE_TUNNEL CORRIDORS DOORS (HDW# 84.1) Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07604 | Review Response | Approved as Noted | 2020-08-18 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 10124 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-17 |  | 08 71 00-25.0 CPA - Door Product Data & Hardware Schedule_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-17 |  | 08 71 00-25.0 CPA - Door Product Data & Hardware Schedule_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-08-17 |  | 08 71 00-25.0 CPA - Door Product Data & Hardware Schedule_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-18 |  | 08 71 00-25.0 CPA - Door Product Data & Hardware Schedule_MAM Review ST08 REVIEW_POP.pdf
08 71 00-025-00-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-025-00 08 71 00_Premium Space - Product Data & Hardware Schedule_Tunnel Corridors Doors (Hdw# 84.1) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-025-00 - 08 71 00-025-00 08 71 00_Premium Space - Product Data & Hardware Schedule_Tunnel Corridors Doors (Hdw# 84.1) | -1 | 2020-09-01
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-18 |  | 08 71 00-25.0 CPA - Door Product Data & Hardware Schedule_MAM Review ST08 REVIEW_POP.pdf
08 71 00-030-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-030-00 Door Hardware Added CCD 065 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-19 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-09-02 | 2020-08-31 | 13 |  | Record Copies; Transfers; Submittals | 08 71 00-030-00-01 - 08 71 00-030-00 Door Hardware Added CCD 065 | 8 |  | 2020-08-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07612 | Received | For Review | 2020-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-02 | Submittal Number: 08 71 00-30.0 From: TYRONE THORNTON Final Due Date: 09/01/20 Subject: DOOR HARDWARE ADDED CCD 065 Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 10139 | Forwarded | For Review | 2020-08-19 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-08-26 | Submittal Number: 08 71 00-30.0 From: TYRONE THORNTON Final Due Date: 09/01/20 Subject: DOOR HARDWARE ADDED CCD 065 Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 07861 | Review Response | Approved as Noted | 2020-08-26 | Linda Scott (Studio 08 Consultants) | Populous SCA_CCA |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact me. Thank you. | Info Exchange
| 10451 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-31 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-19 |  | 087100 CPA_CCD-065 Door Hardware Submittal_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-19 |  | 08 71 00-30.0 CPA_CCD-065 Door Hardware Submittal_MAM Review.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-08-19 |  | 08 71 00-30.0 CPA_CCD-065 Door Hardware Submittal_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-31 |  | 08 71 00-30.0 CPA_CCD-065 Door Hardware Submittal_MAM Review ST08 REVIEW_POP.pdf
08 71 00-030-00-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-030-00 Door Hardware Added CCD 065 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-030-00 - 08 71 00-030-00 Door Hardware Added CCD 065 | -1 | 2020-09-14
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-31 |  | 08 71 00-30.0 CPA_CCD-065 Door Hardware Submittal_MAM Review ST08 REVIEW_POP.pdf
08 71 00-031-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-031-00 CCD 066-073 Door Hardware | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-01 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-10-15 | 2020-10-08 | 8 |  | Record Copies; Transfers; Submittals | 08 71 00-031-00-01 - 08 71 00-031-00 CCD 066-073 Door Hardware | 8 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08475 | Received | For Review | 2020-10-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-10-15 | Submittal Number: 08 71 00-31.0 From: ALLIE ZIMMERMAN Final Due Date: 10/15/20 Subject: CCD 066-073 DOOR HARDWARE Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 11219 | Forwarded | For Review | 2020-10-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-10-08 | Submittal Number: 08 71 00-31.0 From: ALLIE ZIMMERMAN Final Due Date: 10/15/20 Subject: CCD 066-073 DOOR HARDWARE Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 08660 | Review Response | Approved as Noted | 2020-10-08 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have questions or comments, please feel free to contact us. Thanks. | Info Exchange
| 11439 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-08 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | CPA CCD-067 to CCD-073 Harware Submittal _ MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-01 |  | 08 71 00-31.0 CPA CCD-067 to CCD-073 Harware Submittal _ MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-10-01 |  | 08 71 00-31.0 CPA CCD-067 to CCD-073 Harware Submittal _ MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-08 |  | 08 71 00-31.0 CPA CCD-067 to CCD-073 Harware Submittal _ MAM Reviewed REVIEWED ST08_POP.pdf
08 71 00-031-00-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-031-00 CCD 066-073 Door Hardware | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-031-00 - 08 71 00-031-00 CCD 066-073 Door Hardware | -1 | 2020-10-22
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-08 |  | 08 71 00-31.0 CPA CCD-067 to CCD-073 Harware Submittal _ MAM Reviewed REVIEWED ST08_POP.pdf
08 71 00-032-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-032-00 03 71 00 - Door Hardware - Decorative Glass Glazing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-26 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-11-09 | 2020-11-11 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08984 | Received | For Review | 2020-10-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-11-09 | Submittal Number: 08 71 00-32.0 From: ALLIE ZIMMERMAN Final Due Date: 11/09/20 Subject: 03 71 00 - DOOR HARDWARE - DECORATIVE GLASS GLAZING Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 11855 | Forwarded | For Review | 2020-10-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-11-02 | Submittal Number: 08 71 00-32.0 From: ALLIE ZIMMERMAN Final Due Date: 11/09/20 Subject: 03 71 00 - DOOR HARDWARE - DECORATIVE GLASS GLAZING Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 09387 | Review Response | Revise and Resubmit | 2020-11-11 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal marked Revise and Resubmit with shop drawings for doors and frames. If you have any questions or comments, please feel free to contact us. Thanks. | Info Exchange
| 12389 | Responded and Closed | Revise and Resubmit | 2020-11-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | Pending response (Revise and Resubmit) from: Linda Scott (Studio 08 Consultants) Remarks: Please find attached the reviewed submittal marked Revise and Resubmit with shop drawings for doors and frames. If you have any questions or comments, please feel free to contact us. Thanks. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-26 |  | 08 71 00-32 - Door Hardware - Decorative Glass Glazing _MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-26 |  | 08 71 00-32 - Door Hardware - Decorative Glass Glazing _MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-10-25 02:00 |  | 08 71 00-32 - Door Hardware - Decorative Glass Glazing _MAM Reviewed.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-11 02:00 |  | 08 71 00-32 - Door Hardware - Decorative Glass Glazing _MAM Reviewed_ST08 REVIEWED_POP.pdf
08 71 00-032-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-032-01 Door Hardware - Decorative Glass Glazing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-04 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2020-12-18 | 2020-12-16 | 13 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09892 | Received | For Review | 2020-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-12-18 | Submittal Number: 08 71 00-32.1 From: ALLIE ZIMMERMAN Final Due Date: 12/04/20 Subject: 03 71 00 - DOOR HARDWARE - DECORATIVE GLASS GLAZING Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 12976 | Forwarded | For Review | 2020-12-03 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-12-10 | Submittal Number: 08 71 00-32.1 From: ALLIE ZIMMERMAN Final Due Date: 12/04/20 Subject: 03 71 00 - DOOR HARDWARE - DECORATIVE GLASS GLAZING Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 10205 | Review Response | Approved as Noted | 2020-12-16 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal. If you have any questions or comments, please contact me. Thanks. | Info Exchange
| 13345 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-16 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. REFER TO ST08 COMMENTS 2. REVIEWED FOR DOOR HARDWARE ONLY, RESUBMIT SHOP DRAWINGS UNDER 08 81 13 AND INCORORATE MOCKUP REVIEW COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-03 |  | Submittal 08 71 00-32 Revision 1 03 71 00 - Door Hardware - Decorative Glass Glazing_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-03 |  | Submittal 08 71 00-32 Revision 1 03 71 00 - Door Hardware - Decorative Glass Glazing_MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-12-03 |  | Submittal 08 71 00-32 Revision 1 03 71 00 - Door Hardware - Decorative Glass Glazing_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-12-16 |  | Submittal 08 71 00-32 Revision 1 03 71 00 - Door Hardware - Decorative Glass Glazing_MAM Reviewed-POP.pdf
08 71 00-032-02 | 08 71 00 - DOOR HARDWARE | 08 71 00-032-02 DOOR HARDWARE - Shop Drawings, Product Data, Schedule - Glazing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-03-02 | 2021-02-25 | 10 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11448 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-02 | Submittal Number: 08 71 00-32.2 From: ALLIE ZIMMERMAN Final Due Date: 02/24/21 Subject: DOOR HARDWARE - SHOP DRAWINGS, PRODUCT DATA, SCHEDULE - GLAZING Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 14830 | Forwarded | For Review | 2021-02-16 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-02-23 | Submittal Number: 08 71 00-32.2 From: ALLIE ZIMMERMAN Final Due Date: 02/24/21 Subject: DOOR HARDWARE - SHOP DRAWINGS, PRODUCT DATA, SCHEDULE - GLAZING Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 11650 | Review Response | Approved as Noted | 2021-02-23 | Linda Scott (Studio 08 Consultants) | Populous SCA_CCA |  | Please find attached the reviewed submittal referenced above. If you have questions or comments, please feel free to contact us. Thanks. | Info Exchange
| 15096 | Responded and Closed | Approved as Noted | 2021-02-25 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. REFER TO ST08 COMMENTS 2. REVIEWED FOR DOOR HARDWARE ONLY, RESUBMIT SHOP DRAWINGS UNDER 08 81 13 AND INCORORATE MOCKUP REVIEW COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | Submittal 08 71 00-32 Revision 2 DOOR HARDWARE - Shop Drawings Product Data Schedule - Glazing_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-15 |  | Submittal 08 71 00-32 Revision 2 DOOR HARDWARE - Shop Drawings Product Data Schedule - Glazing_MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-02-15 |  | Submittal 08 71 00-32 Revision 2 DOOR HARDWARE - Shop Drawings Product Data Schedule - Glazing_MAM Reviewed.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-16 |  | Submittal 08 71 00-32 Revision 1 03 71 00 - Door Hardware - Decorative Glass Glazing_MAM Reviewed-POP.pdf
08 71 00-033-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-033-00 CCD-075 - CCD-079 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-11 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-01-05 | 2021-01-06 | 27 |  | Record Copies; Transfers; Submittals | 08 71 00-033-00-01 - 08 71 00-033-00 CCD-075 - CCD-079 Added Openings | 27 |  | 2021-01-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10089 | Received | For Review | 2020-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-01-05 | Submittal Number: 08 71 00-33.0 From: ALLIE ZIMMERMAN Final Due Date: 01/07/21 Subject: CCD-075 - CCD-079 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 13190 | Forwarded | For Review | 2020-12-10 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2020-12-17 | Submittal Number: 08 71 00-33.0 From: ALLIE ZIMMERMAN Final Due Date: 01/07/21 Subject: CCD-075 - CCD-079 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 10468 | Review Response | Approved as Noted | 2021-01-05 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact me. Thanks. | Info Exchange
| 13667 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for comments. 1. Refer to ST08 Comments, any revisions listed will be issued in future CCD on 1/22/21 2. Submit Riser and point-to-point wiring diagrams are required per specification. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-10 |  | Seatttle Center Arena CCD-075 to CCD-079 Hardware Submittal_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-10 |  | Seatttle Center Arena CCD-075 to CCD-079 Hardware Submittal_MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2020-12-10 |  | Seatttle Center Arena CCD-075 to CCD-079 Hardware Submittal_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-06 |  | Seatttle Center Arena CCD-075 to CCD-079 Hardware Submittal_MAM Reviewed ST08 REVIEWED_POP.pdf
08 71 00-033-00-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-033-00 CCD-075 - CCD-079 Added Openings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-033-00 - 08 71 00-033-00 CCD-075 - CCD-079 Added Openings | -1 | 2021-01-20
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-06 |  | Seatttle Center Arena CCD-075 to CCD-079 Hardware Submittal_MAM Reviewed ST08 REVIEWED_POP.pdf
08 71 00-034-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-034-00 CCD-082 - CCD-084 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-01-29 08:00 | 2021-01-28 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-01-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10686 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-01-29 08:00 | Submittal Number: 08 71 00-34.0 From: ALLIE ZIMMERMAN Final Due Date: 01/27/21 Subject: CCD-082 - CCD-084 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 13907 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-01-20 | Submittal Number: 08 71 00-34.0 From: ALLIE ZIMMERMAN Final Due Date: 01/27/21 Subject: CCD-082 - CCD-084 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 11031 | Review Response | Approved as Noted | 2021-01-27 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have any questions or comments, please feel free to contact us. Thanks. | Info Exchange
| 14325 | Responded and Closed | Approved as Noted | 2021-01-28 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | Submittal 08 71 00_34 Revision 0_ CCD_082 _ CCD_084 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | Submittal 08 71 00_34 Revision 0_ CCD_082 _ CCD_084 Added Openings_MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-01-13 |  | Submittal 08 71 00_34 Revision 0_ CCD_082 _ CCD_084 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-28 |  | Submittal 08 71 00_34 Revision 0_ CCD_082 _ CCD_084 Added Openings_MAM Reviewed_ST08 Review_POP.pdf
08 71 00-036-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-036-00 Premium Space - Wiring Diagram | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous), Mark Lievens (ME Engineers), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-02-01 08:00 | 2021-02-10 | 27 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2021-02-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10740 | Received | For Review | 2021-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ye Zhang (Mortenson Construction) | 2021-02-01 08:00 | Submittal Number: 08 71 00-36.0 From: ALLIE ZIMMERMAN Final Due Date: 01/27/21 Subject: PREMIUM SPACE - WIRING DIAGRAM Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 13968 | Forwarded | For Review | 2021-01-15 | Ye Zhang (Mortenson Construction) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-01-22 | Submittal Number: 08 71 00-36.0 From: ALLIE ZIMMERMAN Final Due Date: 01/27/21 Subject: PREMIUM SPACE - WIRING DIAGRAM Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 14281 | Forwarded | For Review | 2021-01-27 | Ye Zhang (Mortenson Construction) | Mark Lievens (ME Engineers); Michael Mazzocchi (ME Engineers) | 2021-02-01 | Submittal Number: 08 71 00-36.0 From: ALLIE ZIMMERMAN Final Due Date: 01/27/21 Subject: PREMIUM SPACE - WIRING DIAGRAM Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 11029 | Review Response | Approved as Noted | 2021-01-28 | Linda Scott (Studio 08 Consultants) | Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| 11322 | Review Response | Approved as Noted | 2021-02-09 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.02.08 | Info Exchange
| 14680 | Responded and Closed | Approved as Noted | 2021-02-10 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-15 |  | Submittal 08 71 00_36 Revision 0 Premium Space _ Wiring Diagram_MAM Reviewed.pdf
| Forwarded |  | Ye Zhang (Mortenson Construction) | 1 | 2021-01-15 |  | Submittal 08 71 00_36 Revision 0 Premium Space _ Wiring Diagram_MAM Reviewed.pdf
| Forwarded |  | Ye Zhang (Mortenson Construction) | 1 | 2021-01-15 |  | Submittal 08 71 00_36 Revision 0 Premium Space _ Wiring Diagram_MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-01-28 |  | Submittal 08 71 00_36 Revision 0 Premium Space _ Wiring Diagram_MAM Reviewed ST08 REVIEWED.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-01-15 |  | Submittal 08 71 00_36 Revision 0 Premium Space _ Wiring Diagram_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-10 |  | Submittal 08 71 00_36 Revision 0 Premium Space _ Wiring Diagram_MAM Reviewed ST08 REVIEWED_ME_POP.pdf
08 71 00-037-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-037-00 DOOR HARDWARE - CCD-086 - CCD-087 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-04 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-03-18 | 2021-03-12 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-03-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11784 | Received | For Review | 2021-03-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-03-18 | Submittal Number: 08 71 00-37.0 From: ALLIE ZIMMERMAN Final Due Date: 03/10/21 Subject: DOOR HARDWARE - CCD-086 - CCD-087 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 15272 | Forwarded | For Review | 2021-03-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-03-11 | Submittal Number: 08 71 00-37.0 From: ALLIE ZIMMERMAN Final Due Date: 03/10/21 Subject: DOOR HARDWARE - CCD-086 - CCD-087 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 11974 | Review Response | Approved as Noted | 2021-03-12 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have questions or comments, please feel free to contact me. Thanks. | Info Exchange
| 15509 | Responded and Closed | Approved as Noted | 2021-03-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED SEE ST08 COMMENTS AND SUBMIT MISSING HARDWARE IN A SEPARATE SUBMITTAL | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-03 |  | Submittal 08 71 00-37 Revision 0 DOOR HARDWARE - CCD-086 - CCD-087 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-03 |  | Submittal 08 71 00-37 Revision 0 DOOR HARDWARE - CCD-086 - CCD-087 Added Openings_MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-03-03 |  | Submittal 08 71 00-37 Revision 0 DOOR HARDWARE - CCD-086 - CCD-087 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-12 |  | Submittal 08 71 00-37 Revision 0 DOOR HARDWARE - CCD-086 - CCD-087 Added Openings_MAM Reviewed_ST08 Review_POP.pdf
08 71 00-038-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-038-00 DOOR HARDWARE - CCD 088 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-04-01 | 2021-03-29 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12096 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-04-01 | Submittal Number: 08 71 00-38.0 From: ALLIE ZIMMERMAN Final Due Date: 03/31/21 Subject: DOOR HARDWARE - CCD 088 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 15655 | Forwarded | For Review | 2021-03-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-03-25 | Submittal Number: 08 71 00-38.0 From: ALLIE ZIMMERMAN Final Due Date: 03/31/21 Subject: DOOR HARDWARE - CCD 088 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 12287 | Review Response | Approved as Noted | 2021-03-29 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have questions or comments, please feel free to contact me. Thanks. | Info Exchange
| 15916 | Responded and Closed | Approved as Noted | 2021-03-29 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-17 |  | Submittal 08 71 00-38 Revision 0 DOOR HARDWARE - CCD 088 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-17 |  | Submittal 08 71 00-38 Revision 0 DOOR HARDWARE - CCD 088 Added Openings_MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-03-17 |  | Submittal 08 71 00-38 Revision 0 DOOR HARDWARE - CCD 088 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-29 |  | Submittal 08 71 00-38 Revision 0 DOOR HARDWARE - CCD 088 Added Openings_MAM Reviewed ST08 REVIEWED_POP.pdf
08 71 00-040-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-040-00 DOOR HARDWARE - CCD 091 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-19 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-05-03 | 2021-04-27 | 9 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12633 | Received | For Review | 2021-04-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-03 | Submittal Number: 08 71 00-40.0 From: ALLIE ZIMMERMAN Final Due Date: 05/03/21 Subject: DOOR HARDWARE - CCD 091 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 16350 | Forwarded | For Review | 2021-04-19 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-04-26 | Submittal Number: 08 71 00-40.0 From: ALLIE ZIMMERMAN Final Due Date: 05/03/21 Subject: DOOR HARDWARE - CCD 091 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 12794 | Review Response | Approved | 2021-04-23 | Rick Lewis (Studio 08 Consultants) | Populous SCA_CCA |  |  | Info Exchange
| 16537 | Responded and Closed | Approved | 2021-04-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-18 |  | Submittal 08 71 00-40 Revision 0 DOOR HARDWARE - CCD 091 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-18 |  | Submittal 08 71 00-40 Revision 0 DOOR HARDWARE - CCD 091 Added Openings_MAM Reviewed.pdf
| Review Response |  | Rick Lewis (Studio 08 Consultants) | 1 | 2021-04-18 |  | Submittal 08 71 00-40 Revision 0 DOOR HARDWARE - CCD 091 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-27 |  | Submittal 08 71 00-40 Revision 0 DOOR HARDWARE - CCD 091 Added Openings_Studio 08 Review_POP.pdf
08 71 00-041-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-041-00 DOOR HARDWARE - CCD 094 Added Openings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-05-17 | 2021-05-10 | 8 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12875 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-17 | Submittal Number: 08 71 00-41.0 From: ALLIE ZIMMERMAN Final Due Date: 05/18/21 Subject: DOOR HARDWARE - CCD 094 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 16657 | Forwarded | For Review | 2021-04-30 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-05-07 | Submittal Number: 08 71 00-41.0 From: ALLIE ZIMMERMAN Final Due Date: 05/18/21 Subject: DOOR HARDWARE - CCD 094 ADDED OPENINGS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 13016 | Review Response | Approved | 2021-05-05 | Linda Scott (Studio 08 Consultants) | Populous SCA_CCA |  | Please find attached the reviewed submittal referenced above. If you have questions or comments, please feel free to contact us. Thank you. | Info Exchange
| 16840 | Responded and Closed | Approved | 2021-05-10 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-30 |  | Submittal 08 71 00-41 Revision 0 DOOR HARDWARE - CCD 094 Added Openings_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-30 |  | Submittal 08 71 00-41 Revision 0 DOOR HARDWARE - CCD 094 Added Openings_MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-04-30 |  | Submittal 08 71 00-41 Revision 0 DOOR HARDWARE - CCD 094 Added Openings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-10 |  | Submittal 08 71 00-41 Revision 0 DOOR HARDWARE - CCD 094 Added Openings_MAM Reviewed ST08 REVIEW_POP.pdf
08 71 00-042-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-042-00 DOOR HARDWARE - Tunnel Club Wiring Diagrams | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-02 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous), Mark Lievens (ME Engineers), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-06-16 | 2021-06-18 | 17 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13361 | Received | For Review | 2021-06-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-06-16 | Submittal Number: 08 71 00-42.0 From: ALLIE ZIMMERMAN Final Due Date: 06/16/21 Subject: DOOR HARDWARE - TUNNEL CLUB WIRING DIAGRAMS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 17290 | Forwarded | For Review | 2021-06-02 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-06-09 | Submittal Number: 08 71 00-42.0 From: ALLIE ZIMMERMAN Final Due Date: 06/16/21 Subject: DOOR HARDWARE - TUNNEL CLUB WIRING DIAGRAMS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 17370 | Forwarded | For Review | 2021-06-07 | Chad Francis (Populous) | Mark Lievens (ME Engineers); Michael Mazzocchi (ME Engineers) | 2021-06-14 | Submittal Number: 08 71 00-42.0 From: ALLIE ZIMMERMAN Final Due Date: 06/16/21 Subject: DOOR HARDWARE - TUNNEL CLUB WIRING DIAGRAMS Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 13548 | Review Response | Approved | 2021-06-16 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have questions or comments, please feel free to contact us. Thanks. | Info Exchange
| 17564 | Responded and Closed | Approved as Noted | 2021-06-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-02 |  | Submittal 08 71 00-42 Revision 0 DOOR HARDWARE - Tunnel Club Wiring Diagrams_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-02 |  | Submittal 08 71 00-42 Revision 0 DOOR HARDWARE - Tunnel Club Wiring Diagrams_MAM Reviewed.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2021-06-02 |  | Submittal 08 71 00-42 Revision 0 DOOR HARDWARE - Tunnel Club Wiring Diagrams_MAM Reviewed.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-06-02 |  | Submittal 08 71 00-42 Revision 0 DOOR HARDWARE - Tunnel Club Wiring Diagrams_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-18 |  | Submittal 08 71 00-42 Revision 0 DOOR HARDWARE - Tunnel Club Wiring Diagrams_MAM Reviewed ST08 REVIEWED_POP.pdf
08 71 00-043-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-043-00 Gates and Hardware Shop Drawings and Product Data at the Cooling Towers and South Parcel Generator Enclosure | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-07 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-06-21 | 2021-06-16 | 10 |  | Record Copies; Transfers; Submittals | 08 71 00-043-00-01 - 08 71 00-043-00 Gates and Hardware Shop Drawings and Product Data at the Cooling Towers and South Parcel Generator Enclosure | 10 |  | 2021-06-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13414 | Received | For Review | 2021-06-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-21 | Submittal Number: 08 71 00-43.0 From: CHRISTIAN GENEROSA Final Due Date: 06/21/21 Subject: GATES AND HARDWARE SHOP DRAWINGS AND PRODUCT DATA AT THE COOLING TOWERS AND SOUTH PARCEL GENERATOR ENCLOSURE Description: GATE AND HARDWARE SHOP DRAWINGS AND PRODUCT DATA FOR COOLING TOWERS AND SOUTH PARCEL GENERATOR ENCLOSURE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 17347 | Forwarded | For Review | 2021-06-07 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-06-14 | Submittal Number: 08 71 00-43.0 From: CHRISTIAN GENEROSA Final Due Date: 06/21/21 Subject: GATES AND HARDWARE SHOP DRAWINGS AND PRODUCT DATA AT THE COOLING TOWERS AND SOUTH PARCEL GENERATOR ENCLOSURE Description: GATE AND HARDWARE SHOP DRAWINGS AND PRODUCT DATA FOR COOLING TOWERS AND SOUTH PARCEL GENERATOR ENCLOSURE. Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 17538 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-16 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-05 |  | 2021-06-05 Gate Hardware SD PD for Cooling Tower and Generator Enclosure_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-05 |  | 2021-06-05 Gate Hardware SD PD for Cooling Tower and Generator Enclosure_MAM.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-16 |  | 08 71 00-043-00 - Gate Hardware SD PD for Cooling Tower and Generator Enclosure_MAM_ST08_POP.pdf
08 71 00-043-00-01 | 08 71 00 - DOOR HARDWARE | 08 71 00-043-00 Gates and Hardware Shop Drawings and Product Data at the Cooling Towers and South Parcel Generator Enclosure | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 71 00-043-00 - 08 71 00-043-00 Gates and Hardware Shop Drawings and Product Data at the Cooling Towers and South Parcel Generator Enclosure | -1 | 2021-06-30
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-16 |  | 08 71 00-043-00 - Gate Hardware SD PD for Cooling Tower and Generator Enclosure_MAM_ST08_POP.pdf
08 71 00-044-00 | 08 71 00 - DOOR HARDWARE | 08 71 00-044-00 DOOR HARDWARE - Artist Lounge Sound Booth 01.06.07A | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-21 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-07-05 | 2021-06-29 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-06-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13584 | Received | For Review | 2021-06-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-07-05 | Submittal Number: 08 71 00-44.0 From: ALLIE ZIMMERMAN Final Due Date: 07/03/21 Subject: DOOR HARDWARE - ARTIST LOUNGE SOUND BOOTH 01.06.07A Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 17585 | Forwarded | For Review | 2021-06-21 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-06-28 | Submittal Number: 08 71 00-44.0 From: ALLIE ZIMMERMAN Final Due Date: 07/03/21 Subject: DOOR HARDWARE - ARTIST LOUNGE SOUND BOOTH 01.06.07A Description: Spec Section: 08 71 00 - DOOR HARDWARE Status: OPEN | Info Exchange
| 17747 | Responded and Closed | Approved as Noted | 2021-06-29 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-19 |  | Submittal 08 71 00-44 Revision 0 DOOR HARDWARE - Artist Lounge Sound Booth 01.06.07A_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-06-19 |  | Submittal 08 71 00-44 Revision 0 DOOR HARDWARE - Artist Lounge Sound Booth 01.06.07A_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-29 |  | Submittal 08 71 00-44 Revision 0 DOOR HARDWARE - Artist Lounge Sound Booth 01.06.07A_MAM Reviewed ST08 REVIEWED_POP.pdf
08 80 00-001-00 | 08 80 00 - GLAZING | 08 80 00-001-00 088000 - 1.5-A - PRODUCT DATA FOR EACH GLASS TYPE | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-29 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-06-12 | 2020-06-25 | 28 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2020-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06096 | Received | For Review | 2020-05-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-12 | Submittal Number: 08 80 00-1.0 From: BROOKE BURCHAM Final Due Date: 06/11/20 Subject: 088000 - 1.5-A - PRODUCT DATA FOR EACH GLASS TYPE Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08252 | Forwarded | For Review | 2020-05-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-04 | Submittal Number: 08 80 00-1.0 From: BROOKE BURCHAM Final Due Date: 06/11/20 Subject: 088000 - 1.5-A - PRODUCT DATA FOR EACH GLASS TYPE Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08889 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-25 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR COMMNENTS. G7 IS NOT APPROVED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-28 |  | 088000-0001-0 088000 - 1.5-A - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-28 |  | 088000-0001-0 088000 - 1.5-A - Product Data.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-25 |  | 088000-0001-0 088000 - 1.5-A - Product Data_POP.pdf
08 80 00-001-01 | 08 80 00 - GLAZING | 08 80 00-001-01 088000 - 1.5-A - PRODUCT DATA FOR EACH GLASS TYPE | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-15 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-29 | 2020-11-09 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08803 | Received | For Review | 2020-10-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-29 | Submittal Number: 08 80 00-1.1 From: TYRONE THORNTON Final Due Date: 10/29/20 Subject: 088000 - 1.5-A - PRODUCT DATA FOR EACH GLASS TYPE Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 11636 | Forwarded | For Review | 2020-10-15 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-22 | Submittal Number: 08 80 00-1.1 From: TYRONE THORNTON Final Due Date: 10/29/20 Subject: 088000 - 1.5-A - PRODUCT DATA FOR EACH GLASS TYPE Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 12303 | Responded and Closed | Approved | 2020-11-09 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-15 |  | 088000-0001-1 G7 Glazing - Resubmittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-15 |  | 088000-0001-1 G7 Glazing - Resubmittal.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-09 02:00 |  | 088000-0001-1 G7 Glazing - Resubmittal_pop.pdf
08 80 00-002-00 | 08 80 00 - GLAZING | 08 80 00-002-00 GLAZING - Product Data_HG | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-10 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-24 | 2020-09-02 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07477 | Received | For Review | 2020-08-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-24 | Submittal Number: 08 80 00-2.0 From: TYRONE THORNTON Final Due Date: 08/21/20 Subject: GLAZING - PRODUCT DATA_HG Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 09956 | Forwarded | For Review | 2020-08-10 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-17 | Submittal Number: 08 80 00-2.0 From: TYRONE THORNTON Final Due Date: 08/21/20 Subject: GLAZING - PRODUCT DATA_HG Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 10502 | Responded and Closed | Approved | 2020-09-02 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-10 |  | 088000-2_Climate Pledge Arena-Hartung Product Data_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-10 |  | 088000-2_Climate Pledge Arena-Hartung Product Data_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-02 |  | 088000-2_Climate Pledge Arena-Hartung Product Data_MAM Review_POP.pdf
08 80 00-004-00 | 08 80 00 - GLAZING | 08 80 00-004-00 Glazing Historic Curtainwall Samples | Closed | Architectural | Brooke Burcham (Mortenson Construction) | 2019-06-20 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Chris Minter (Populous), Josh Dobken (Populous), Tom Usher (Populous) |  |  |  | 2019-07-04 | 2019-06-25 | 6 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2019-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01595 | Received | For Review | 2019-06-20 | Brooke Burcham (Mortenson Construction) | Shaina Burris (Populous) | 2019-07-04 |  | Email
| 02635 | Forwarded | For Review | 2019-06-21 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-06-28 |  | Info Exchange
| 02646 | Forwarded | For Review | 2019-06-21 | Shaina Burris (Populous) | Tom Usher (Populous) | 2019-06-28 |  | Info Exchange
| 02677 | Responded and Closed | Approved as Noted | 2019-06-25 | Shaina Burris (Populous) | Brooke Burcham (Mortenson Construction) |  | See attached pdf for approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Brooke Burcham (Mortenson Construction) | 1 | 2019-06-21 |  | 08 80 00-004-00 Glazing Historic Curtainwall Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-06-21 |  | 08 80 00-004-00 Glazing Historic Curtainwall Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-06-21 |  | 08 80 00-004-00 Glazing Historic Curtainwall Samples.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2019-06-25 |  | 08 80 00-004-00 Glazing Historic Curtainwall Samples.pdf
08 80 00-005-00 | 08 80 00 - GLAZING | 08 80 00-005-00 088000 - 1.5-C - GLASS SAMPLE - G1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-03 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-20 07:00 | 2020-04-13 | 11 |  | Record Copies; Transfers; Submittals | 08 80 00-005-00-01 - 08 80 00-005-00 088000 - 1.5-C - GLASS SAMPLE - G1 | 11 |  | 2020-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05195 | Received | For Review | 2020-04-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-04-20 07:00 | Submittal Number: 08 80 00-5.0 From: BROOKE BURCHAM Final Due Date: 04/16/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G1 Description: 12"SQ GLASS SAMPLE - 1" IGU Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 07063 | Forwarded | For Review | 2020-04-03 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-10 | Submittal Number: 08 80 00-5.0 From: BROOKE BURCHAM Final Due Date: 04/16/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G1 Description: 12"SQ GLASS SAMPLE - 1" IGU Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 07247 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-13 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Glass type approved. Submit additional submittal requirements in 08 80 00 sections 1.5 and 1.6. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-02 |  | 088000-0005-0 Glass Sample - G1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-02 |  | 088000-0005-0 Glass Sample - G1.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-02 |  | 088000-0005-0 Glass Sample - G1.pdf
08 80 00-005-00-01 | 08 80 00 - GLAZING | 08 80 00-005-00 088000 - 1.5-C - GLASS SAMPLE - G1 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 80 00-005-00 - 08 80 00-005-00 088000 - 1.5-C - GLASS SAMPLE - G1 | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-02 |  | 088000-0005-0 Glass Sample - G1.pdf
08 80 00-008-00 | 08 80 00 - GLAZING | 08 80 00-008-00 088000 - 1.6-A - IGU MANUFACTURER QUALIFICATION | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-29 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-06-12 | 2020-06-25 | 28 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2020-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06094 | Received | For Review | 2020-05-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-12 | Submittal Number: 08 80 00-8.0 From: BROOKE BURCHAM Final Due Date: 06/11/20 Subject: 088000 - 1.6-A - IGU MANUFACTURER QUALIFICATION Description: QUALIFICATION DATA : FOR [INSTALLER] MANUFACTURERS OF INSULATING-GLASS UNITS WITH SPUTTER-COATED, LOW-E COATINGS GLASS TESTING AGENCY AND SEALANT TESTING AGENCY. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08250 | Forwarded | For Review | 2020-05-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 08 80 00-8.0 From: BROOKE BURCHAM Final Due Date: 06/11/20 Subject: 088000 - 1.6-A - IGU MANUFACTURER QUALIFICATION Description: QUALIFICATION DATA : FOR [INSTALLER] MANUFACTURERS OF INSULATING-GLASS UNITS WITH SPUTTER-COATED, LOW-E COATINGS GLASS TESTING AGENCY AND SEALANT TESTING AGENCY. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08893 | Responded and Closed | Approved | 2020-06-25 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-28 |  | 088000-0008-0 IGU Manufacturer Qualification.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-28 |  | 088000-0008-0 IGU Manufacturer Qualification.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-25 |  | 088000-0008-0 IGU Manufacturer Qualification_POP.pdf
08 80 00-010-00 | 08 80 00 - GLAZING | 08 80 00-010-00 GLAZING - TEST REPORTS FOR GLAZING SEALANTS_HG | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-19 | 2020-09-02 | 29 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07374 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 08 80 00-10.0 From: TYRONE THORNTON Final Due Date: 08/13/20 Subject: GLAZING - TEST REPORTS FOR GLAZING SEALANTS_HG Description: PRODUCT TEST REPORTS : FOR TINTED GLASS COATED GLASS INSULATING GLASS AND GLAZING SEALANTS, FOR TESTS PERFORMED BYA QUALIFIED TESTING AGENCY. 1. FOR GLAZING SEALANTS, PROVIDE TEST REPORTS BASED ON TESTING CURRENT SEALANT FORMULATIONS WITHIN PREVIOUS 36-MONTH PERIOD. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 09824 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-12 | Submittal Number: 08 80 00-10.0 From: TYRONE THORNTON Final Due Date: 08/13/20 Subject: GLAZING - TEST REPORTS FOR GLAZING SEALANTS_HG Description: PRODUCT TEST REPORTS : FOR TINTED GLASS COATED GLASS INSULATING GLASS AND GLAZING SEALANTS, FOR TESTS PERFORMED BYA QUALIFIED TESTING AGENCY. 1. FOR GLAZING SEALANTS, PROVIDE TEST REPORTS BASED ON TESTING CURRENT SEALANT FORMULATIONS WITHIN PREVIOUS 36-MONTH PERIOD. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 10503 | Responded and Closed | Approved | 2020-09-02 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-05 |  | 088000-10_Climate Pledge Arena-Dow 1199_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-05 |  | 088000-10_Climate Pledge Arena-Dow 1199_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-09-02 |  | 088000-2_Climate Pledge Arena-Hartung Product Data_MAM Review_POP.pdf
08 80 00-011-00 | 08 80 00 - GLAZING | 08 80 00-011-00 GLAZING - PRE-CON ADHESION TESTING_HG | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-08 07:00 | 2020-09-02 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07677 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-08 07:00 | Submittal Number: 08 80 00-11.0 From: TYRONE THORNTON Final Due Date: 08/13/20 Subject: GLAZING - PRE-CON ADHESION TESTING_HG Description: PRECONSTRUCTION ADHESION AND COMPATIBILITY TEST REPORT. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 10222 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-31 | Submittal Number: 08 80 00-11.0 From: TYRONE THORNTON Final Due Date: 08/13/20 Subject: GLAZING - PRE-CON ADHESION TESTING_HG Description: PRECONSTRUCTION ADHESION AND COMPATIBILITY TEST REPORT. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 10504 | Responded and Closed | Approved | 2020-09-02 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 088000-11_CPA Precon Adhesion Testing_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 088000-11_CPA Precon Adhesion Testing_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-09-02 |  | 088000-2_Climate Pledge Arena-Hartung Product Data_MAM Review_POP.pdf
08 80 00-012-00 | 08 80 00 - GLAZING | 08 80 00-012-00 088000 - 1.6-E - SAMPLE WARRANTY | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-13 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-04-27 | 2020-04-30 | 18 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-04-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05277 | Received | For Review | 2020-04-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-04-27 | Submittal Number: 08 80 00-12.0 From: BROOKE BURCHAM Final Due Date: 04/23/20 Subject: 088000 - 1.6-E - SAMPLE WARRANTY Description: SAMPLE WARRANTIES : FOR SPECIAL WARRANTIES. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 07177 | Forwarded | For Review | 2020-04-09 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-16 | Submittal Number: 08 80 00-12.0 From: BROOKE BURCHAM Final Due Date: 04/23/20 Subject: 088000 - 1.6-E - SAMPLE WARRANTY Description: SAMPLE WARRANTIES : FOR SPECIAL WARRANTIES. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 07506 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Chad Francis (Populous) |  | Submittal Number: 08 80 00-12.0 From: BROOKE BURCHAM Final Due Date: 04/23/20 Subject: 088000 - 1.6-E - SAMPLE WARRANTY Description: SAMPLE WARRANTIES : FOR SPECIAL WARRANTIES. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 05656 | Review Response | Approved as Noted | 2020-04-30 | Josh Dobken (Populous) | Shaina Burris (Populous) |  | Oversized IGU required to be 10 year warranty per specification. | Info Exchange
| 07660 | Responded and Closed | Approved as Noted | 2020-04-30 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Josh Dobken (Populous) Remarks: Oversized IGU required to be 10 year warranty per specification. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-09 |  | 088000-0012-0 Sample Warranties.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-09 |  | 088000-0012-0 Sample Warranties.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-09 |  | 088000-0012-0 Sample Warranties.pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2020-04-30 02:00 |  | 088000-0012-0 Sample Warranties_pop.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-08 02:00 |  | 088000-0012-0 Sample Warranties.pdf
08 80 00-014-00 | 08 80 00 - GLAZING | 08 80 00-014-00 088000-1.5-C - GLASS SAMPLES FOR G2 AND G11 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-12 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-26 | 2020-02-27 | 16 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04323 | Received | For Review | 2020-02-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-02-26 | Submittal Number: 08 80 00-14.0 From: JAKE DEBOER Final Due Date: 02/25/20 Subject: 088000-1.5-C - GLASS SAMPLES FOR G2 AND G11 Description: AGNORA GLASS SAMPLES FOR G2 AND G11. SEE ATTACHED PHOTOS. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 05982 | Forwarded | For Review | 2020-02-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-02-18 | Submittal Number: 08 80 00-14.0 From: JAKE DEBOER Final Due Date: 02/25/20 Subject: 088000-1.5-C - GLASS SAMPLES FOR G2 AND G11 Description: AGNORA GLASS SAMPLES FOR G2 AND G11. SEE ATTACHED PHOTOS. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 06267 | Responded and Closed | Approved | 2020-02-27 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-11 |  | 088000-0014-0 G2 and G11 Jumbo Glass Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-11 |  | 088000-0014-0 G2 and G11 Jumbo Glass Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-27 |  | 088000-0014-0 G2 and G11 Jumbo Glass Samples_POP.pdf
08 80 00-015-00 | 08 80 00 - GLAZING | 08 80 00-015-00 088000 - 1.5-C - GLASS SAMPLE - G3 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-29 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-06-12 | 2020-06-15 | 18 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06095 | Received | For Review | 2020-05-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Brooke Burcham (M.A. Mortenson Company) | 2020-06-12 | Submittal Number: 08 80 00-15.0 From: BROOKE BURCHAM Final Due Date: 06/11/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G3 Description: 12"SQ GLASS SAMPLE - 1" IGU - PANELITE Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08251 | Forwarded | For Review | 2020-05-28 | Brooke Burcham (M.A. Mortenson Company) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-04 | Submittal Number: 08 80 00-15.0 From: BROOKE BURCHAM Final Due Date: 06/11/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G3 Description: 12"SQ GLASS SAMPLE - 1" IGU - PANELITE Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08626 | Responded and Closed | Approved | 2020-06-15 | Brooke Burcham (M.A. Mortenson Company) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-28 |  | 088000-0015-0 Glass Sample - G3.pdf
| Forwarded |  | Brooke Burcham (Mortenson Construction) | 1 | 2020-05-28 |  | 088000-0015-0 Glass Sample - G3.pdf
| Responded and Closed |  | Brooke Burcham (Mortenson Construction) | 1 | 2020-06-15 |  | 088000-0015-0 Glass Sample - G3_POP.pdf
08 80 00-016-00 | 08 80 00 - GLAZING | 08 80 00-016-00 088000 - 1.5-C - GLASS SAMPLE - G8 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-01 | Responded and Closed - Not Required For Review |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-16 07:00 | 2020-04-20 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05160 | Received | For Review | 2020-04-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-04-16 07:00 | Submittal Number: 08 80 00-16.0 From: BROOKE BURCHAM Final Due Date: 04/14/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G8 Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 06995 | Forwarded | For Review | 2020-04-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-08 | Submittal Number: 08 80 00-16.0 From: BROOKE BURCHAM Final Due Date: 04/14/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G8 Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 07403 | Responded and Closed | Not Required For Review | 2020-04-20 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Not reviewed. G8 glass was deleted in CCD054. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-31 |  | 088000-0016-0 Glass Sample - G8.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-31 |  | 088000-0016-0 Glass Sample - G8.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-20 02:00 |  | 088000-0016-0 Glass Sample - G8_POP.pdf
08 80 00-016-01 | 08 80 00 - GLAZING | 08 80 00-016-01 1.5-C - GLASS SAMPLE - G8 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-20 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-06-02 | 2020-05-26 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05944 | Received | For Review | 2020-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-02 | Submittal Number: 08 80 00-16.1 From: BROOKE BURCHAM Final Due Date: 06/02/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G8 Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08073 | Forwarded | For Review | 2020-05-20 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-27 | Submittal Number: 08 80 00-16.1 From: BROOKE BURCHAM Final Due Date: 06/02/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G8 Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08193 | Responded and Closed | Approved | 2020-05-26 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 |  | 088000-0016-1 Glass Sample - G8.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-19 |  | 088000-0016-1 Glass Sample - G8.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-05-26 |  | 088000-0016-1 Glass Sample - G8_POP.pdf
08 80 00-017-00 | 08 80 00 - GLAZING | 08 80 00-017-00 088000 - 1.5-C - GLASS SAMPLE - G13 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-29 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-06-12 | 2020-06-15 | 18 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06093 | Received | For Review | 2020-05-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-12 | Submittal Number: 08 80 00-17.0 From: BROOKE BURCHAM Final Due Date: 06/11/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G13 Description: 12"SQ GLASS SAMPLE - 1" IGU - PANELITE W/FILM OR ETCH Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08249 | Forwarded | For Review | 2020-05-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-04 | Submittal Number: 08 80 00-17.0 From: BROOKE BURCHAM Final Due Date: 06/11/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G13 Description: 12"SQ GLASS SAMPLE - 1" IGU - PANELITE W/FILM OR ETCH Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08627 | Responded and Closed | Approved | 2020-06-15 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-28 |  | 088000-0017-0 Glass Sample - G13.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-28 |  | 088000-0017-0 Glass Sample - G13.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-15 |  | 088000-0017-0 Glass Sample - G13_POP.pdf
08 80 00-018-00 | 08 80 00 - GLAZING | 08 80 00-018-00 088000 - 1.5-C - GLASS SAMPLE - G14 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-11 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-06-25 | 2020-06-29 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-06-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06351 | Received | For Review | 2020-06-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-25 | Submittal Number: 08 80 00-18.0 From: BROOKE BURCHAM Final Due Date: 06/25/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G14 Description: 12"SQ GLASS SAMPLE - 9/16" LAMINATED FOR TICKET OFFICE SUNSHADE Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08566 | Forwarded | For Review | 2020-06-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-18 | Submittal Number: 08 80 00-18.0 From: BROOKE BURCHAM Final Due Date: 06/25/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G14 Description: 12"SQ GLASS SAMPLE - 9/16" LAMINATED FOR TICKET OFFICE SUNSHADE Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08982 | Responded and Closed | Approved | 2020-06-29 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-11 |  | 088000-0018-0 Glass Sample - G14 Entry Canopies.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-11 |  | 088000-0018-0 Glass Sample - G14 Entry Canopies.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-29 |  | 088000-0018-0 Glass Sample - G14 Entry Canopies_POP.pdf
08 80 00-022-00 | 08 80 00 - GLAZING | 08 80 00-022-00 088000 - 1.5-C - GLASS SAMPLE - G2 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-01 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-16 07:00 | 2020-04-13 | 13 |  | Record Copies; Transfers; Submittals | 08 80 00-022-00-01 - 08 80 00-022-00 088000 - 1.5-C - GLASS SAMPLE - G2 | 13 |  | 2020-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05161 | Received | For Review | 2020-04-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-04-16 07:00 | Submittal Number: 08 80 00-22.0 From: BROOKE BURCHAM Final Due Date: 04/15/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G2 Description: GLASS SAMPLE FOR G2 GLASS Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 06996 | Forwarded | For Review | 2020-04-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-04-08 | Submittal Number: 08 80 00-22.0 From: BROOKE BURCHAM Final Due Date: 04/15/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - G2 Description: GLASS SAMPLE FOR G2 GLASS Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 07248 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-13 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Glass type approved. Submit additional submittal requirements in 08 80 00 sections 1.5 and 1.6. Don't believe G2 is used anymore. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-31 |  | 088000-0022-0 Glass Sample - G2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-31 |  | 088000-0022-0 Glass Sample - G2.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-04-13 |  | 088000-0022-0 Glass Sample - G2-MAM _POP.pdf
08 80 00-022-00-01 | 08 80 00 - GLAZING | 08 80 00-022-00 088000 - 1.5-C - GLASS SAMPLE - G2 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 80 00-022-00 - 08 80 00-022-00 088000 - 1.5-C - GLASS SAMPLE - G2 | -1 | 2020-04-27
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-13 |  | 088000-0022-0 Glass Sample - G2-MAM _POP.pdf
08 80 00-023-00 | 08 80 00 - GLAZING | 08 80 00-023-00 1.5-C - GLASS SAMPLE - CLEARSTORY VIRCON | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-20 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-06-03 | 2020-06-10 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-06-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05945 | Received | For Review | 2020-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-03 | Submittal Number: 08 80 00-23.0 From: BROOKE BURCHAM Final Due Date: 06/03/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - CLEARSTORY VIRCON Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08074 | Forwarded | For Review | 2020-05-20 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-27 | Submittal Number: 08 80 00-23.0 From: BROOKE BURCHAM Final Due Date: 06/03/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - CLEARSTORY VIRCON Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08534 | Responded and Closed | Approved | 2020-06-10 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please send approved sample to Populous office for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 |  | 088000-0023-0 Glass Sample - Clearstory.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-19 |  | 088000-0023-0 Glass Sample - Clearstory.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-10 |  | 088000-0023-0 Glass Sample - Clearstory_POP.pdf
08 80 00-023-01 | 08 80 00 - GLAZING | 08 80 00-023-01 088000 - 1.5-C - GLASS SAMPLE - CLEARSTORY AGNORA | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-08 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-22 | 2020-12-09 | 2 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-12-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09982 | Received | For Review | 2020-12-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Brooke Burcham (M.A. Mortenson Company) | 2020-12-22 | Submittal Number: 08 80 00-23.1 From: BROOKE BURCHAM Final Due Date: 12/16/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - CLEARSTORY AGNORA Description: REVISION FOR AGNORA GLASS ACID ETCH FOR CENTER OF THE CLEARSTORY IN LIEU OF VIRCON GLAZING. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 13066 | Forwarded | For Review | 2020-12-07 | Brooke Burcham (M.A. Mortenson Company) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 08 80 00-23.1 From: BROOKE BURCHAM Final Due Date: 12/16/20 Subject: 088000 - 1.5-C - GLASS SAMPLE - CLEARSTORY AGNORA Description: REVISION FOR AGNORA GLASS ACID ETCH FOR CENTER OF THE CLEARSTORY IN LIEU OF VIRCON GLAZING. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 13153 | Responded and Closed | Approved | 2020-12-09 | Brooke Burcham (M.A. Mortenson Company) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 088000-0023-1 Glass Sample - Clearstory_Center_Agnora.pdf
| Forwarded |  | Brooke Burcham (Mortenson Construction) | 1 | 2020-12-07 |  | 088000-0023-1 Glass Sample - Clearstory_Center_Agnora.pdf
| Responded and Closed |  | Brooke Burcham (Mortenson Construction) | 1 | 2020-12-09 |  | 088000-0023-1 Glass Sample - Clearstory_Center_Agnora_POP.pdf
08 80 00-024-00 | 08 80 00 - GLAZING | 08 80 00-024-00 GLAZING - GLS10 Glass Samples_HG | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-04 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-21 | 2020-09-28 | 25 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-09-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07959 | Received | For Review | 2020-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-21 | Submittal Number: 08 80 00-24.0 From: TYRONE THORNTON Final Due Date: 09/18/20 Subject: GLAZING - GLS10 GLASS SAMPLES_HG Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 10584 | Forwarded | For Review | 2020-09-08 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-15 | Submittal Number: 08 80 00-24.0 From: TYRONE THORNTON Final Due Date: 09/18/20 Subject: GLAZING - GLS10 GLASS SAMPLES_HG Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08368 | Review Response | Approved as Noted | 2020-09-28 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Provide sample of GLS10A with required film. | Info Exchange
| 11081 | Responded and Closed | Approved as Noted | 2020-09-28 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Provide sample of GLS10A with required film. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-04 |  | 08 80 00-24 GLS10 Glass Sample.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-04 |  | 08 80 00-24 GLS10 Glass Sample.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-04 |  | 08 80 00-24 GLS10 Glass Sample.pdf
08 80 00-025-01 | 08 80 00 - GLAZING | 08 80 00-025-01 GLAZING - Glass Accessory Samples_HG | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-10 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-24 | 2020-09-14 | 36 |  | Record Copies; Transfers; Submittals |  | 36 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07468 | Received | For Review | 2020-08-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-24 | Submittal Number: 08 80 00-25.1 From: TYRONE THORNTON Final Due Date: 08/19/20 Subject: GLAZING - GLASS ACCESSORY SAMPLES_HG Description: GLAZING ACCESSORY SAMPLES : FOR SEALANTS AND COLORED SPACERS, IN 12-INCH LENGTHS. INSTALL SEALANT SAMPLES BETWEEN TWO STRIPS OF MATERIAL REPRESENTATIVE IN COLOR OF THE ADJOINING FRAMING SYSTEM. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 09947 | Forwarded | For Review | 2020-08-10 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-17 | Submittal Number: 08 80 00-25.1 From: TYRONE THORNTON Final Due Date: 08/19/20 Subject: GLAZING - GLASS ACCESSORY SAMPLES_HG Description: GLAZING ACCESSORY SAMPLES : FOR SEALANTS AND COLORED SPACERS, IN 12-INCH LENGTHS. INSTALL SEALANT SAMPLES BETWEEN TWO STRIPS OF MATERIAL REPRESENTATIVE IN COLOR OF THE ADJOINING FRAMING SYSTEM. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08085 | Review Response | Approved | 2020-09-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10750 | Responded and Closed | Approved | 2020-09-14 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-07 |  | 088000-25 CPA- Glazing Mockup_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-07 |  | 088000-25 CPA- Glazing Mockup_MAM Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-14 |  | 088000-25 CPA- Glazing Mockup_MAM Review_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-07 |  | 088000-25 CPA- Glazing Mockup_MAM Review.pdf
08 80 00-026-00 | 08 80 00 - GLAZING | 08 80 00-026-00 GLAZING - Product Certificates_HG | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-19 | 2020-09-02 | 29 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2020-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07366 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 08 80 00-26.0 From: TYRONE THORNTON Final Due Date: 08/13/20 Subject: GLAZING - PRODUCT CERTIFICATES_HG Description: PRODUCT CERTIFICATES : FOR GLASS. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 09816 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-12 | Submittal Number: 08 80 00-26.0 From: TYRONE THORNTON Final Due Date: 08/13/20 Subject: GLAZING - PRODUCT CERTIFICATES_HG Description: PRODUCT CERTIFICATES : FOR GLASS. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 10505 | Responded and Closed | Approved | 2020-09-02 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-05 |  | 088000-26_Climate Pledge Arena - Hartung Cert Data_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-05 |  | 088000-26_Climate Pledge Arena - Hartung Cert Data_MAM Review.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-09-02 |  | 088000-26_Climate Pledge Arena - Hartung Cert Data_MAM Review_POP.pdf
08 80 00-029-00 | 08 80 00 - GLAZING | 08 80 00-029-00 GLASS SAMPLE - GLS10A | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-29 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-13 | 2020-10-13 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08409 | Received | For Review | 2020-09-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-13 | Submittal Number: 08 80 00-29.0 From: ALLIE ZIMMERMAN Final Due Date: 10/12/20 Subject: 088000 - GLASS SAMPLE - GLS10A Description: GLS10A SAMPLE: 12MM STARPHIRE TEMPERED WITH FLAT POLISH EDGES Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 11146 | Forwarded | For Review | 2020-09-29 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-06 | Submittal Number: 08 80 00-29.0 From: ALLIE ZIMMERMAN Final Due Date: 10/12/20 Subject: 088000 - GLASS SAMPLE - GLS10A Description: GLS10A SAMPLE: 12MM STARPHIRE TEMPERED WITH FLAT POLISH EDGES Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 08735 | Review Response | Approved as Noted | 2020-10-13 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11542 | Responded and Closed | Approved as Noted | 2020-10-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-29 |  | 088000 29 GLASS SAMPLE GLS10A.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-29 |  | 088000 29 GLASS SAMPLE GLS10A.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-13 |  | 088000 29 GLASS SAMPLE GLS10A_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-29 |  | 088000 29 GLASS SAMPLE GLS10A.pdf