08 80 00-029-01 | 08 80 00 - GLAZING | 08 80 00-029-01 GLASS SAMPLE - GLS10A Rev1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-06 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-20 | 2020-11-17 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-11-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09278 | Received | For Review | 2020-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-11-20 | Submittal Number: 08 80 00-29.1 From: ALLIE ZIMMERMAN Final Due Date: 12/18/20 Subject: GLASS SAMPLE - GLS10A REV1 Description: GLS10A SAMPLE REV1. PROVIDED THREE DIFFERENT TYPES OF FILM: 3M ONE WAY, V14, AND MADICO OPTI 5. FILMS ARE APPLIED TO 1/2" TEMPERED CLEAR GLASS. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 12234 | Forwarded | For Review | 2020-11-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-13 | Submittal Number: 08 80 00-29.1 From: ALLIE ZIMMERMAN Final Due Date: 12/18/20 Subject: GLASS SAMPLE - GLS10A REV1 Description: GLS10A SAMPLE REV1. PROVIDED THREE DIFFERENT TYPES OF FILM: 3M ONE WAY, V14, AND MADICO OPTI 5. FILMS ARE APPLIED TO 1/2" TEMPERED CLEAR GLASS. Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 09468 | Review Response | Approved as Noted | 2020-11-17 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Confirm selection with Rockwell. Populous will ship these samples to Rockwell. | Info Exchange
| 12486 | Responded and Closed | Approved as Noted | 2020-11-17 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Confirm selection with Rockwell. Populous will ship these samples to Rockwell. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 08 80 00-29.1 GLASS SAMPLE GLS10A Rev1 _MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 08 80 00-29.1 GLASS SAMPLE GLS10A Rev1 _MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-17 |  | 08 80 00-29.1 GLASS SAMPLE GLS10A Rev1 _MAM Reviewed_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-06 |  | 08 80 00-29.1 GLASS SAMPLE GLS10A Rev1 _MAM Reviewed.pdf
08 80 00-030-00 | 08 80 00 - GLAZING | 08 80 00-030-00 GLAZING - Sealants and Colored Spacers Accessory Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-01 | 2021-04-09 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2021-04-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12097 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-04-01 | Submittal Number: 08 80 00-30.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: GLAZING - SEALANTS AND COLORED SPACERS ACCESSORY SAMPLES Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 15656 | Forwarded | For Review | 2021-03-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-25 | Submittal Number: 08 80 00-30.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: GLAZING - SEALANTS AND COLORED SPACERS ACCESSORY SAMPLES Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 12503 | Review Response | Approved as Noted | 2021-04-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Use black at all locations in submittal. Refer to attached submittal review. | Info Exchange
| 16192 | Responded and Closed | Approved as Noted | 2021-04-09 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Use black at all locations in submittal. Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-17 |  | Submittal 08 80 00-30 Revision 0 GLAZING - Sealants and Colored Spacers Accessory Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-17 |  | Submittal 08 80 00-30 Revision 0 GLAZING - Sealants and Colored Spacers Accessory Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-09 |  | Submittal 08 80 00-30 Revision 0 GLAZING - Sealants and Colored Spacers_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-03-17 |  | Submittal 08 80 00-30 Revision 0 GLAZING - Sealants and Colored Spacers Accessory Samples.pdf
08 80 00-031-00 | 08 80 00 - GLAZING | 08 80 00-031-00 GLAZING - Press Bridge Window Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-19 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-03 | 2021-04-30 | 12 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-04-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12632 | Received | For Review | 2021-04-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-05-03 | Submittal Number: 08 80 00-31.0 From: ALLIE ZIMMERMAN Final Due Date: 04/30/21 Subject: GLAZING - PRESS BRIDGE WINDOW SHOP DRAWINGS Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 16349 | Forwarded | For Review | 2021-04-19 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 08 80 00-31.0 From: ALLIE ZIMMERMAN Final Due Date: 04/30/21 Subject: GLAZING - PRESS BRIDGE WINDOW SHOP DRAWINGS Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 12863 | Review Response | Approved as Noted | 2021-04-29 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16642 | Responded and Closed | Approved as Noted | 2021-04-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| 16647 | Reopened | Additional Information | 2021-04-30 10:18 | Kelsea Conkright (Populous)
| 16648 | Responded and Closed | Approved as Noted | 2021-04-30 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-16 |  | Submittal 08 80 00-31 Revision 0 GLAZING - Press Bridge Window Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-04-16 |  | Submittal 08 80 00-31 Revision 0 GLAZING - Press Bridge Window Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-29 |  | Submittal 08 80 00-31 Revision 0 GLAZING - Press Bridge Window Shop Drawings_MAM Reviewed_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-16 |  | Submittal 08 80 00-31 Revision 0 GLAZING - Press Bridge Window Shop Drawings_MAM Reviewed.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-16 |  | Submittal 08 80 00-31 Revision 0 GLAZING - Press Bridge Window Shop Drawings_MAM Reviewed.pdf
08 80 00-032-00 | 08 80 00 - GLAZING | 08 80 00-032-00 GLAZING - Artist Lounge | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-21 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-05 | 2021-06-24 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13585 | Received | For Review | 2021-06-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-07-05 | Submittal Number: 08 80 00-32.0 From: ALLIE ZIMMERMAN Final Due Date: 07/03/21 Subject: GLAZING - ARTIST LOUNGE Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 17586 | Forwarded | For Review | 2021-06-21 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-28 | Submittal Number: 08 80 00-32.0 From: ALLIE ZIMMERMAN Final Due Date: 07/03/21 Subject: GLAZING - ARTIST LOUNGE Description: Spec Section: 08 80 00 - GLAZING Status: OPEN | Info Exchange
| 13635 | Review Response | Approved as Noted | 2021-06-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17660 | Responded and Closed | Approved as Noted | 2021-06-24 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-19 |  | Submittal 08 80 00-32 Revision 0 GLAZING - Artist Lounge_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-06-19 |  | Submittal 08 80 00-32 Revision 0 GLAZING - Artist Lounge_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-24 02:00 |  | Submittal 08 80 00-32 Revision 0 GLAZING - Artist Lounge_MAM Reviewed_POP.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-06-18 02:00 |  | Submittal 08 80 00-32 Revision 0 GLAZING - Artist Lounge_MAM Reviewed.pdf
08 81 13-001-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-001-00 DECORATIVE GLASS GLAZING - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-19 | 2020-08-19 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07373 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 08 81 13-1.0 From: TYRONE THORNTON Final Due Date: 08/18/20 Subject: DECORATIVE GLASS GLAZING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 09823 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-12 | Submittal Number: 08 81 13-1.0 From: TYRONE THORNTON Final Due Date: 08/18/20 Subject: DECORATIVE GLASS GLAZING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 07628 | Review Response | Approved | 2020-08-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10157 | Responded and Closed | Approved | 2020-08-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-05 |  | 088113-1_Climate Pledge Arena-Goldray Antique Mirror_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-05 |  | 088113-1_Climate Pledge Arena-Goldray Antique Mirror_MAM Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-19 |  | 088113-1_Climate Pledge Arena-Goldray Antique Mirror_MAM Review_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-05 |  | 088113-1_Climate Pledge Arena-Goldray Antique Mirror_MAM Review.pdf
08 81 13-002-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-002-00 DECORATIVE GLASS GLAZING - LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 | 2021-04-27 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12485 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-04-22 | Submittal Number: 08 81 13-2.0 From: ALLIE ZIMMERMAN Final Due Date: 04/09/21 Subject: DECORATIVE GLASS GLAZING - LEED DATA Description: SUSTAINABLE DESIGN SUBMITTALS : - 1. PRODUCT DATA.. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 16175 | Forwarded | For Review | 2021-04-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 08 81 13-2.0 From: ALLIE ZIMMERMAN Final Due Date: 04/09/21 Subject: DECORATIVE GLASS GLAZING - LEED DATA Description: SUSTAINABLE DESIGN SUBMITTALS : - 1. PRODUCT DATA.. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 12797 | Review Response | Approved | 2021-04-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16540 | Responded and Closed | Approved | 2021-04-27 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | Submittal 08 81 13-2 Revision 0 DECORATIVE GLASS GLAZING - LEED Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-08 |  | Submittal 08 81 13-2 Revision 0 DECORATIVE GLASS GLAZING - LEED Data_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-27 |  | Submittal 09 29 00-12 Revision 0 GYPSUM BOARD - Aluminum Knife Edge Product Data_MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-08 |  | Submittal 08 81 13-2 Revision 0 DECORATIVE GLASS GLAZING - LEED Data_MAM Reviewed.pdf
08 81 13-003-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-003-00 DECORATIVE GLASS GLAZING - Mock-Up Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-03 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2020-09-18 | 2020-09-18 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-09-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07925 | Received | For Review | 2020-09-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-18 | Submittal Number: 08 81 13-3.0 From: TYRONE THORNTON Final Due Date: 09/17/20 Subject: DECORATIVE GLASS GLAZING - MOCK-UP SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 10541 | Forwarded | For Review | 2020-09-04 | Josh Dobken (Populous) | Todd Spangler (Populous); Kuebler Perry (Populous); Chad Francis (Populous) | 2020-09-11 | Submittal Number: 08 81 13-3.0 From: TYRONE THORNTON Final Due Date: 09/17/20 Subject: DECORATIVE GLASS GLAZING - MOCK-UP SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 10888 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-03 02:00 |  | 08 81 13-3_CPA - Mock Up Shop Drawings_MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-03 02:00 |  | 08 81 13-3_CPA - Mock Up Shop Drawings_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-18 02:00 |  | 08 81 13-3_CPA - Mock Up Shop Drawings_MAM ReviewPOP.pdf
08 81 13-003-01 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-003-01 DECORATIVE GLASS GLAZING - Mock-Up Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Linda Scott (Studio 08 Consultants) |  |  |  | 2020-11-16 | 2020-11-19 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-11-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09141 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-11-16 | Submittal Number: 08 81 13-3.1 From: TYRONE THORNTON Final Due Date: 11/13/20 Subject: DECORATIVE GLASS GLAZING - MOCK-UP SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 12063 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-09 | Submittal Number: 08 81 13-3.1 From: TYRONE THORNTON Final Due Date: 11/13/20 Subject: DECORATIVE GLASS GLAZING - MOCK-UP SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 12373 | Forwarded | For Review | 2020-11-11 | Josh Dobken (Populous) | Linda Scott (Studio 08 Consultants) | 2020-11-16 | Submittal Number: 08 81 13-3.1 From: TYRONE THORNTON Final Due Date: 11/13/20 Subject: DECORATIVE GLASS GLAZING - MOCK-UP SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 09562 | Review Response | Approved as Noted/Resubmit | 2020-11-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12587 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-31 |  | Climate Pledge Arena - 10.23.20R _ Tunnel Club Mock Up Shop Drawings_ MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-31 |  | Climate Pledge Arena - 10.23.20R _ Tunnel Club Mock Up Shop Drawings_ MAM Reviewed.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-30 02:00 |  | Climate Pledge Arena - 10.23.20R _ Tunnel Club Mock Up Shop Drawings_ MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-19 |  | Climate Pledge Arena - 10.23.20R _ Tunnel Club Mock Up Shop Drawings_ MAM Reviewed_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-31 |  | Climate Pledge Arena - 10.23.20R _ Tunnel Club Mock Up Shop Drawings_ MAM Reviewed.pdf
08 81 13-003-02 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-003-02 DECORATIVE GLASS GLAZING - Mock-Up Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-02 | Responded and Closed - No Action Taken or Required |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-16 | 2020-12-16 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09789 | Received | For Review | 2020-12-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company); Allie Zimmerman | 2020-12-16 | Submittal Number: 08 81 13-3.2 From: ALLIE ZIMMERMAN Final Due Date: 12/15/20 Subject: DECORATIVE GLASS GLAZING - MOCK-UP SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 12871 | Forwarded | For Review | 2020-12-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-08 | Submittal Number: 08 81 13-3.2 From: ALLIE ZIMMERMAN Final Due Date: 12/15/20 Subject: DECORATIVE GLASS GLAZING - MOCK-UP SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 10201 | Review Response | No Action Taken or Required | 2020-12-16 | Kuebler Perry (Populous) | Populous SCA_CCA |  | For record only. | Info Exchange
| 13340 | Responded and Closed | No Action Taken or Required | 2020-12-16 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | For record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-01 |  | Submittal 08 81 13_3 Revision 2_ DECORATIVE GLASS GLAZING _ Mock Up Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-01 |  | Submittal 08 81 13_3 Revision 2_ DECORATIVE GLASS GLAZING _ Mock Up Shop Drawings_MAM Reviewed.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-01 |  | Submittal 08 81 13_3 Revision 2_ DECORATIVE GLASS GLAZING _ Mock Up Shop Drawings_MAM Reviewed.pdf
08 81 13-004-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-004-00 DECORATIVE GLASS GLAZING - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-02 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-17 | 2020-09-17 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07905 | Received | For Review | 2020-09-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-17 | Submittal Number: 08 81 13-4.0 From: TYRONE THORNTON Final Due Date: 09/16/20 Subject: DECORATIVE GLASS GLAZING - SAMPLES Description: GLASS SAMPLES : FOR THE FOLLOWING PRODUCTS, 12 INCHES SQUARE: 1. EACH TYPE OF DECORATIVE GLASS. 2. EACH EDGE TREATMENT ON TYPE OF DECORATIVE GLASS. 3. EACH DECORATIVE FILM OVERLAY ON TYPE OF DECORATIVE GLASS. 4. EACH APPLIED COATING ON TYPE OF DECORATIVE GLASS. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 10517 | Forwarded | For Review | 2020-09-02 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-09 | Submittal Number: 08 81 13-4.0 From: TYRONE THORNTON Final Due Date: 09/16/20 Subject: DECORATIVE GLASS GLAZING - SAMPLES Description: GLASS SAMPLES : FOR THE FOLLOWING PRODUCTS, 12 INCHES SQUARE: 1. EACH TYPE OF DECORATIVE GLASS. 2. EACH EDGE TREATMENT ON TYPE OF DECORATIVE GLASS. 3. EACH DECORATIVE FILM OVERLAY ON TYPE OF DECORATIVE GLASS. 4. EACH APPLIED COATING ON TYPE OF DECORATIVE GLASS. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 08174 | Review Response | Approved as Noted | 2020-09-17 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10859 | Responded and Closed | Approved as Noted | 2020-09-17 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-02 |  | CPA - Soft Spots Physical Sample_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-02 |  | CPA - Soft Spots Physical Sample_MAM Review.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-17 |  | CPA - Soft Spots Physical Sample_MAM Review_POP.pdf
08 81 13-007-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-007-00 DECORATIVE GLASS GLAZING - Qualification Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Not Required For Review |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-05 | 2021-02-10 | 20 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-02-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10886 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-02-05 | Submittal Number: 08 81 13-7.0 From: ALLIE ZIMMERMAN Final Due Date: 02/04/21 Subject: DECORATIVE GLASS GLAZING - QUALIFICATION DATA Description: QUALIFICATION DATA : FOR INSTALLER. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 14137 | Forwarded | For Review | 2021-01-21 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-28 | Submittal Number: 08 81 13-7.0 From: ALLIE ZIMMERMAN Final Due Date: 02/04/21 Subject: DECORATIVE GLASS GLAZING - QUALIFICATION DATA Description: QUALIFICATION DATA : FOR INSTALLER. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 11304 | Review Response | Not Required For Review | 2021-02-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14642 | Responded and Closed | Not Required For Review | 2021-02-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-21 |  | Submittal 08 81 13_7 Revision 0 DECORATIVE GLASS GLAZING Qualification Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-21 |  | Submittal 08 81 13_7 Revision 0 DECORATIVE GLASS GLAZING Qualification Data_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-10 |  | Submittal 08 81 13_7 Revision 0 DECORATIVE GLASS GLAZING Qualification Data_MAM Reviewed_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-21 |  | Submittal 08 81 13_7 Revision 0 DECORATIVE GLASS GLAZING Qualification Data_MAM Reviewed.pdf
08 81 13-010-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-010-00 DECORATIVE GLASS GLAZING - Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-19 | 2020-08-19 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07370 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 08 81 13-10.0 From: TYRONE THORNTON Final Due Date: 08/19/20 Subject: DECORATIVE GLASS GLAZING - WARRANTY Description: WARRANTY : PROVIDE MANUFACTURERS WRITTEN WARRANTY AGREEING TO REPAIR OR REPLACE DECORATIVE GLASS UNITS THAT FAIL IN MATERIALS OR WORKMANSHIP OR DETERIORATE WITHIN 5 YEARS OF SUBSTANTIAL COMPLETION. WARRANTY SUBJECT TO NORMAL CONDITIONS OF USE ONLY, NOT TO HANDLING, INSTALLING, AND CLEANING PRACTICES CONTRARY TO DECORATIVE GLASS MANUFACTURERS PUBLISHED INSTRUCTIONS. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 09821 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-12 | Submittal Number: 08 81 13-10.0 From: TYRONE THORNTON Final Due Date: 08/19/20 Subject: DECORATIVE GLASS GLAZING - WARRANTY Description: WARRANTY : PROVIDE MANUFACTURERS WRITTEN WARRANTY AGREEING TO REPAIR OR REPLACE DECORATIVE GLASS UNITS THAT FAIL IN MATERIALS OR WORKMANSHIP OR DETERIORATE WITHIN 5 YEARS OF SUBSTANTIAL COMPLETION. WARRANTY SUBJECT TO NORMAL CONDITIONS OF USE ONLY, NOT TO HANDLING, INSTALLING, AND CLEANING PRACTICES CONTRARY TO DECORATIVE GLASS MANUFACTURERS PUBLISHED INSTRUCTIONS. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 07627 | Review Response | Approved | 2020-08-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10156 | Responded and Closed | Approved | 2020-08-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-05 |  | 088113-10_Climate Pledge Arena - Goldray Standard 5 Year Warranty_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-05 |  | 088113-10_Climate Pledge Arena - Goldray Standard 5 Year Warranty_MAM Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-19 |  | 088113-10_Climate Pledge Arena - Goldray Standard 5 Year Warranty_MAM Review_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-05 |  | 088113-10_Climate Pledge Arena - Goldray Standard 5 Year Warranty_MAM Review.pdf
08 81 13-011-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-011-00 DECORATIVE GLASS GLAZING - Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-19 | 2020-08-19 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07371 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-19 | Submittal Number: 08 81 13-11.0 From: TYRONE THORNTON Final Due Date: 08/18/20 Subject: DECORATIVE GLASS GLAZING - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR EACH TYPE OF DECORATIVE GLASS TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 09822 | Forwarded | For Review | 2020-08-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-12 | Submittal Number: 08 81 13-11.0 From: TYRONE THORNTON Final Due Date: 08/18/20 Subject: DECORATIVE GLASS GLAZING - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR EACH TYPE OF DECORATIVE GLASS TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 07626 | Review Response | Approved | 2020-08-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10155 | Responded and Closed | Approved | 2020-08-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-05 |  | 088113-11_Climate Pledge Arena - Goldray Glass Maintenance Info_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-05 |  | 088113-11_Climate Pledge Arena - Goldray Glass Maintenance Info_MAM Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-19 |  | 088113-11_Climate Pledge Arena - Goldray Glass Maintenance Info_MAM Review_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-05 |  | 088113-11_Climate Pledge Arena - Goldray Glass Maintenance Info_MAM Review.pdf
08 81 13-013-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-013-00 Tunnel Club Back Bars Mirror Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-21 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-05 | 2020-10-05 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08239 | Received | For Review | 2020-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-05 | Submittal Number: 08 81 13-13.0 From: MIKE SOLFELT Final Due Date: 09/30/20 Subject: TUNNEL CLUB BACK BARS MIRROR SAMPLE Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 10944 | Forwarded | For Review | 2020-09-21 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-28 | Submittal Number: 08 81 13-13.0 From: MIKE SOLFELT Final Due Date: 09/30/20 Subject: TUNNEL CLUB BACK BARS MIRROR SAMPLE Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 08523 | Review Response | Approved as Noted/Resubmit | 2020-10-05 | Kuebler Perry (Populous) | Populous SCA_CCA |  | PRODUCT IS CORRECT FOR GLS12, BUT BACK-BAR MIRRORS IN TUNNEL CLUBS ARE SUPPOSED TO BE GLS11- THIS HAS BEEN UPDATED IN A VERY RECENT CCD. PLEASE SUBMIT GLS11 PRODUCT. | Info Exchange
| 11275 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PRODUCT IS CORRECT FOR GLS12, BUT BACK-BAR MIRRORS IN TUNNEL CLUBS ARE SUPPOSED TO BE GLS11- THIS HAS BEEN UPDATED IN A VERY RECENT CCD. PLEASE SUBMIT GLS11 PRODUCT. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 08 81 13-13 Tunnel Club Back Bars Mirror Sampl.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-21 |  | 08 81 13-13 Tunnel Club Back Bars Mirror Sampl.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-05 |  | 08 81 13-13 Tunnel Club Back Bars Mirror Sampl_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-21 |  | 08 81 13-13 Tunnel Club Back Bars Mirror Sampl.pdf
08 81 13-013-01 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-013-01 Tunnel Club Back Bars Mirror Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-27 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-10 | 2020-11-10 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-11-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09024 | Received | For Review | 2020-10-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-10 | Submittal Number: 08 81 13-13.1 From: MIKE SOLFELT Final Due Date: 11/10/20 Subject: TUNNEL CLUB BACK BARS MIRROR SAMPLE Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 11905 | Forwarded | For Review | 2020-10-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-03 | Submittal Number: 08 81 13-13.1 From: MIKE SOLFELT Final Due Date: 11/10/20 Subject: TUNNEL CLUB BACK BARS MIRROR SAMPLE Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 09340 | Review Response | Approved | 2020-11-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12320 | Responded and Closed | Approved | 2020-11-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 08 81 13-13.1 GLS11 Tunnel Club Mirror.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 08 81 13-13.1 GLS11 Tunnel Club Mirror.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-10 |  | 08 81 13-13.1 GLS11 Tunnel Club Mirror_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-27 |  | 08 81 13-13.1 GLS11 Tunnel Club Mirror.pdf
08 81 13-014-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-014-00 NHL Home Locker Room Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-03 08:00 | 2020-12-02 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09481 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-12-03 08:00 | Submittal Number: 08 81 13-14.0 From: ALLIE ZIMMERMAN Final Due Date: 11/30/20 Subject: NHL HOME LOCKER ROOM SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 12499 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-24 | Submittal Number: 08 81 13-14.0 From: ALLIE ZIMMERMAN Final Due Date: 11/30/20 Subject: NHL HOME LOCKER ROOM SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 09815 | Review Response | Revise and Resubmit | 2020-12-02 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12896 | Responded and Closed | Revise and Resubmit | 2020-12-02 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | Submittal 08 81 13-14 Revision 0 NHL Home Locker Room Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | Submittal 08 81 13-14 Revision 0 NHL Home Locker Room Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-02 |  | Submittal 08 81 13-14 Revision 0 NHL Home Locker Room Shop Drawings_MAM Reviewed_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-16 |  | Submittal 08 81 13-14 Revision 0 NHL Home Locker Room Shop Drawings_MAM Reviewed.pdf
08 81 13-014-01 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-014-01 NHL Home Locker Room Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-26 08:00 | 2021-01-20 | 10 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10555 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-01-26 08:00 | Submittal Number: 08 81 13-14.1 From: ALLIE ZIMMERMAN Final Due Date: 01/22/21 Subject: NHL HOME LOCKER ROOM SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 13753 | Forwarded | For Review | 2021-01-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-15 | Submittal Number: 08 81 13-14.1 From: ALLIE ZIMMERMAN Final Due Date: 01/22/21 Subject: NHL HOME LOCKER ROOM SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 10845 | Review Response | Approved as Noted/Resubmit | 2021-01-20 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14088 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-20 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | Submittal 08 81 13_14 Revision 1 NHL Home Locker Room Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-08 |  | Submittal 08 81 13_14 Revision 1 NHL Home Locker Room Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-20 |  | Submittal 08 81 13_14 Revision 1 NHL Home Locker Room Shop Drawings_MAM Reviewed_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-01-08 |  | Submittal 08 81 13_14 Revision 1 NHL Home Locker Room Shop Drawings_MAM Reviewed.pdf
08 81 13-015-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-015-00 NHL Visitor Locker Room Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-03 08:00 | 2020-12-03 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09480 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-12-03 08:00 | Submittal Number: 08 81 13-15.0 From: ALLIE ZIMMERMAN Final Due Date: 11/30/20 Subject: NHL VISITOR LOCKER ROOM SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 12498 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-24 | Submittal Number: 08 81 13-15.0 From: ALLIE ZIMMERMAN Final Due Date: 11/30/20 Subject: NHL VISITOR LOCKER ROOM SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 09860 | Review Response | Revise and Resubmit | 2020-12-03 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12943 | Responded and Closed | Revise and Resubmit | 2020-12-03 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | Submittal 08 81 13-15 Revision 0 NHL Visitor Locker Room Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | Submittal 08 81 13-15 Revision 0 NHL Visitor Locker Room Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-03 |  | Submittal 08 81 13-15 Revision 0 NHL Visitor Locker Room Shop Drawings_MAM Reviewed_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-16 |  | Submittal 08 81 13-15 Revision 0 NHL Visitor Locker Room Shop Drawings_MAM Reviewed.pdf
08 81 13-015-01 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-015-01 NHL Visitor Locker Room Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-26 08:00 | 2021-01-20 | 10 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10556 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-01-26 08:00 | Submittal Number: 08 81 13-15.1 From: ALLIE ZIMMERMAN Final Due Date: 01/22/21 Subject: NHL VISITOR LOCKER ROOM SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 13754 | Forwarded | For Review | 2021-01-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-15 | Submittal Number: 08 81 13-15.1 From: ALLIE ZIMMERMAN Final Due Date: 01/22/21 Subject: NHL VISITOR LOCKER ROOM SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 10846 | Review Response | Approved as Noted | 2021-01-20 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14089 | Responded and Closed | Approved as Noted | 2021-01-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | Submittal 08 81 13_15 Revision 1 NHL Visitor Locker Room Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-08 |  | Submittal 08 81 13_15 Revision 1 NHL Visitor Locker Room Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-20 |  | Submittal 08 81 13_15 Revision 1 NHL Visitor Locker Room Shop Drawings_MAM Reviewed_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-08 |  | Submittal 08 81 13_15 Revision 1 NHL Visitor Locker Room Shop Drawings_MAM Reviewed.pdf
08 81 13-016-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-016-00 Main Concourse Club Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-04 | 2020-12-06 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-12-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09523 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-12-04 | Submittal Number: 08 81 13-16.0 From: ALLIE ZIMMERMAN Final Due Date: 12/02/20 Subject: MAIN CONCOURSE CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 12543 | Forwarded | For Review | 2020-11-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-25 | Submittal Number: 08 81 13-16.0 From: ALLIE ZIMMERMAN Final Due Date: 12/02/20 Subject: MAIN CONCOURSE CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 09927 | Review Response | Approved as Noted | 2020-12-06 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13006 | Responded and Closed | Approved as Noted | 2020-12-06 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | Submittal 08 81 13-16 Revision 0 Main Concourse Club Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | Submittal 08 81 13-16 Revision 0 Main Concourse Club Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-06 |  | Submittal 08 81 13-16 Revision 0 Main Concourse Club Shop Drawings_MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-17 |  | Submittal 08 81 13-16 Revision 0 Main Concourse Club Shop Drawings_MAM Reviewed.pdf
08 81 13-016-01 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-016-01 DECORATIVE GLASS GLAZING - Main Concourse Club Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-17 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-03 | 2021-03-05 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-03-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11509 | Received | For Review | 2021-02-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-03 | Submittal Number: 08 81 13-16.1 From: ALLIE ZIMMERMAN Final Due Date: 02/26/21 Subject: DECORATIVE GLASS GLAZING - MAIN CONCOURSE CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 14903 | Forwarded | For Review | 2021-02-17 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-24 | Submittal Number: 08 81 13-16.1 From: ALLIE ZIMMERMAN Final Due Date: 02/26/21 Subject: DECORATIVE GLASS GLAZING - MAIN CONCOURSE CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 11810 | Review Response | Approved as Noted | 2021-03-05 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15313 | Responded and Closed | Approved as Noted | 2021-03-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-17 |  | Submittal 08 81 13-16 Revision 1 DECORATIVE GLASS GLAZING - Main Concourse Club Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-17 |  | Submittal 08 81 13-16 Revision 1 DECORATIVE GLASS GLAZING - Main Concourse Club Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-05 |  | Submittal 08 81 13-16 Revision 1 DECORATIVE GLASS GLAZING - MCC Shop Drawings_MAM _POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-17 |  | Submittal 08 81 13-16 Revision 1 DECORATIVE GLASS GLAZING - Main Concourse Club Shop Drawings_MAM Reviewed.pdf
08 81 13-016-02 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-016-02 DECORATIVE GLASS GLAZING - Main Concourse Club Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-22 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-06 | 2021-06-04 | 44 |  | Record Copies; Transfers; Submittals |  | 45 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12708 | Received | For Review | 2021-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-05-06 | Submittal Number: 08 81 13-16.2 From: ALLIE ZIMMERMAN Final Due Date: 05/05/21 Subject: DECORATIVE GLASS GLAZING - MAIN CONCOURSE CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 16429 | Forwarded | For Review | 2021-04-21 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 08 81 13-16.2 From: ALLIE ZIMMERMAN Final Due Date: 05/05/21 Subject: DECORATIVE GLASS GLAZING - MAIN CONCOURSE CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 13005 | Review Response | Approved | 2021-05-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16830 | Responded and Closed | Approved | 2021-05-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| 17210 | Reopened | Additional Information | 2021-05-27 17:11 | Chad Francis (Populous) |  |  | INCORRECT SUBMITTAL RETURNED
| 13404 | Review Response | Approved as Noted | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17337 | Responded and Closed | Approved as Noted | 2021-06-04 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-21 |  | Submittal 08 81 13-16 Revision 2 DECORATIVE GLASS GLAZING - Main Concourse Club Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-21 |  | Submittal 08 81 13-16 Revision 2 DECORATIVE GLASS GLAZING - Main Concourse Club Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-27 |  | Submittal 08 81 13-2 Revision 0 DECORATIVE GLASS GLAZING - LEED Data_MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-21 |  | Submittal 08 81 13-16 Revision 2 DECORATIVE GLASS GLAZING - Main Concourse Club Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-28 |  | Submittal 08 81 13-16 Revision 2 DECORATIVE GLASS GLAZING - MCC_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-21 |  | Submittal 08 81 13-16 Revision 2 DECORATIVE GLASS GLAZING - Main Concourse Club Shop Drawings_MAM Reviewed.pdf
08 81 13-017-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-017-00 Metropolitan Club Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-04 | 2020-12-06 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-12-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09522 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-12-04 | Submittal Number: 08 81 13-17.0 From: ALLIE ZIMMERMAN Final Due Date: 12/04/20 Subject: METROPOLITAN CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 12542 | Forwarded | For Review | 2020-11-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-25 | Submittal Number: 08 81 13-17.0 From: ALLIE ZIMMERMAN Final Due Date: 12/04/20 Subject: METROPOLITAN CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 09928 | Review Response | Approved as Noted/Resubmit | 2020-12-06 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13007 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-06 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | Submittal 08 81 13-17 Revision 0 Metropolitan Club Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | Submittal 08 81 13-17 Revision 0 Metropolitan Club Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-06 |  | Submittal 08 81 13-17 Revision 0 Metropolitan Club Shop Drawings_MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-17 |  | Submittal 08 81 13-17 Revision 0 Metropolitan Club Shop Drawings_MAM Reviewed.pdf
08 81 13-017-01 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-017-01 Metropolitan Club Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-26 08:00 | 2021-01-31 | 21 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-01-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10557 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-01-26 08:00 | Submittal Number: 08 81 13-17.1 From: ALLIE ZIMMERMAN Final Due Date: 01/22/21 Subject: METROPOLITAN CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 13755 | Forwarded | For Review | 2021-01-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-15 | Submittal Number: 08 81 13-17.1 From: ALLIE ZIMMERMAN Final Due Date: 01/22/21 Subject: METROPOLITAN CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 11067 | Review Response | Approved as Noted | 2021-01-31 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14365 | Responded and Closed | Approved as Noted | 2021-01-31 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | Submittal 08 81 13_17 Revision 1 Metropolitan Club Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-08 |  | Submittal 08 81 13_17 Revision 1 Metropolitan Club Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-31 |  | Submittal 08 81 13_17 Revision 1 Metropolitan Club Shop Drawings_MAM Reviewed_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-08 |  | Submittal 08 81 13_17 Revision 1 Metropolitan Club Shop Drawings_MAM Reviewed.pdf
08 81 13-018-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-018-00 Mount Baker Whiskey & Wine Bar Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-04 | 2020-12-08 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-12-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09521 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-12-04 | Submittal Number: 08 81 13-18.0 From: ALLIE ZIMMERMAN Final Due Date: 12/04/20 Subject: MOUNT BAKER WHISKEY & WINE BAR SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 12541 | Forwarded | For Review | 2020-11-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-25 | Submittal Number: 08 81 13-18.0 From: ALLIE ZIMMERMAN Final Due Date: 12/04/20 Subject: MOUNT BAKER WHISKEY & WINE BAR SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 13124 | Responded and Closed | Approved as Noted | 2020-12-08 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | Submittal 08 81 13-18 Revision 0 Mount Baker Whiskey and Wine Bar Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | Submittal 08 81 13-18 Revision 0 Mount Baker Whiskey and Wine Bar Shop Drawings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-12-08 |  | Submittal 08 81 13-18 Revision 0 Mount Baker Whiskey and Wine Bar Shop Drawings_MAM Reviewed_RG_POP.pdf
08 81 13-019-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-019-00 Space Needle Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-03 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-17 | 2020-12-18 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-12-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09871 | Received | For Review | 2020-12-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-12-17 | Submittal Number: 08 81 13-19.0 From: ALLIE ZIMMERMAN Final Due Date: 12/16/20 Subject: SPACE NEEDLE SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 12954 | Forwarded | For Review | 2020-12-03 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-10 | Submittal Number: 08 81 13-19.0 From: ALLIE ZIMMERMAN Final Due Date: 12/16/20 Subject: SPACE NEEDLE SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 10253 | Review Response | Revise and Resubmit | 2020-12-18 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 13407 | Responded and Closed | Revise and Resubmit | 2020-12-18 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-03 |  | 08 81 13-19 Decorative Glass Glazing Space Needle Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-03 |  | 08 81 13-19 Decorative Glass Glazing Space Needle Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-18 |  | 08 81 13-19 Decorative Glass Glazing Space Needle Shop Drawings_MAM Reviewed_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-03 |  | 08 81 13-19 Decorative Glass Glazing Space Needle Shop Drawings_MAM Reviewed.pdf
08 81 13-019-01 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-019-01 Space Needle Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-26 08:00 | 2021-01-31 | 21 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-01-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10559 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-01-26 08:00 | Submittal Number: 08 81 13-19.1 From: ALLIE ZIMMERMAN Final Due Date: 01/22/21 Subject: SPACE NEEDLE SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 13758 | Forwarded | For Review | 2021-01-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-15 | Submittal Number: 08 81 13-19.1 From: ALLIE ZIMMERMAN Final Due Date: 01/22/21Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN Subject: SPACE NEEDLE SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DECORATIVE GLASS. SHOW FABRICATION AND INSTALLATION DETAILS. INCLUDE THE FOLLOWING: 1. SIZE AND LOCATION OF PENETRATIONS. 2. GLAZING METHOD. 3. MOUNTING METHOD. 4. ATTACHMENTS TO OTHER WORK. 5. FULL-SIZE DETAILS OF EDGE-FINISHED PROFILES. | Info Exchange
| 11068 | Review Response | Approved as Noted | 2021-01-31 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14366 | Responded and Closed | Approved as Noted | 2021-01-31 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | Submittal 08 81 13_19 Revision 1 Space Needle Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-08 |  | Submittal 08 81 13_19 Revision 1 Space Needle Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-31 |  | Submittal 08 81 13_19 Revision 1 Space Needle Shop Drawings_MAM Reviewed_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-08 |  | Submittal 08 81 13_19 Revision 1 Space Needle Shop Drawings_MAM Reviewed.pdf
08 81 13-020-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-020-00 DECORATIVE GLASS GLAZING - WNBA Locker Room | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-02-25 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11449 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-03-01 | Submittal Number: 08 81 13-20.0 From: ALLIE ZIMMERMAN Final Due Date: 03/01/21 Subject: DECORATIVE GLASS GLAZING - WNBA LOCKER ROOM Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 14831 | Forwarded | For Review | 2021-02-16 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-23 | Submittal Number: 08 81 13-20.0 From: ALLIE ZIMMERMAN Final Due Date: 03/01/21 Subject: DECORATIVE GLASS GLAZING - WNBA LOCKER ROOM Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 15099 | Responded and Closed | Approved as Noted | 2021-02-25 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. FIELD VERIFY ALL DIMENSIONS. 2. SUBMIT ITEMS NOTED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | Submittal 08 81 13-20 Revision 0 DECORATIVE GLASS GLAZING - WNBA Locker Room _MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-02-15 |  | Submittal 08 81 13-20 Revision 0 DECORATIVE GLASS GLAZING - WNBA Locker Room _MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-25 |  | Submittal 08 81 13-20 Revision 0 DECORATIVE GLASS GLAZING - WNBA Locker Room _MAM Reviewed_POP.pdf
08 81 13-021-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-021-00 DECORATIVE GLASS GLAZING - Herzog Full Set Shop Drawings - For Record Only | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-22 | Responded and Closed - No Action Taken or Required |  | Kuebler Perry (Populous) |  |  |  | 2021-03-08 | 2021-03-10 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11585 | Received | For Review | 2021-02-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-03-08 | Submittal Number: 08 81 13-21.0 From: ALLIE ZIMMERMAN Final Due Date: 03/08/21 Subject: DECORATIVE GLASS GLAZING - HERZOG FULL SET SHOP DRAWINGS - FOR RECORD ONLY Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 15011 | Forwarded | For Review | 2021-02-22 | Josh Dobken (Populous) | Kuebler Perry (Populous) | 2021-03-01 | Submittal Number: 08 81 13-21.0 From: ALLIE ZIMMERMAN Final Due Date: 03/08/21 Subject: DECORATIVE GLASS GLAZING - HERZOG FULL SET SHOP DRAWINGS - FOR RECORD ONLY Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 15419 | Responded and Closed | No Action Taken or Required | 2021-03-10 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | FOR RECORD ONLY, ALL PREVIOUS SUBMITTAL COMMENTS TO BE FOLLOWED, CM TO COORDINATE | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-22 02:00 |  | Submittal 08 81 13-21 Revision 0 DECORATIVE GLASS GLAZING - Herzog Full Set Shop Drawings - For Record Only.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-22 02:00 |  | Submittal 08 81 13-21 Revision 0 DECORATIVE GLASS GLAZING - Herzog Full Set Shop Drawings - For Record Only.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-10 |  | 08 81 13-21-00 DECORATIVE GLASS GLAZING - Herzog SD - For Record Only_POP.pdf
08 81 13-022-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-022-00 DECORATIVE GLASS GLAZING - Markerboard MB1 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-26 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2021-03-12 | 2021-03-05 | 8 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-03-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11689 | Received | For Review | 2021-02-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-03-12 | Submittal Number: 08 81 13-22.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: DECORATIVE GLASS GLAZING - MARKERBOARD MB1 SAMPLE Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 15147 | Forwarded | For Review | 2021-03-01 | Josh Dobken (Populous) | Kelsea Conkright (Populous); Kuebler Perry (Populous); Chad Francis (Populous) | 2021-03-08 | Submittal Number: 08 81 13-22.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: DECORATIVE GLASS GLAZING - MARKERBOARD MB1 SAMPLE Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 11820 | Review Response | Approved | 2021-03-05 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15326 | Responded and Closed | Approved | 2021-03-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-26 02:00 |  | Submittal 08 81 13-22 Revision 0 DECORATIVE GLASS GLAZING - Markerboard MB1 Sample_MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-26 02:00 |  | 08 81 13-022-00 Markerboard MB1 Sample_MAM.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-05 |  | 08 81 13-022-00 Markerboard MB1 Sample_MAM_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-26 |  | Submittal 08 81 13-22 Revision 0 DECORATIVE GLASS GLAZING - Markerboard MB1 Sample_MAM Review.pdf
08 81 13-023-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-023-00 DECORATIVE GLASS GLAZING - Herzog Doors - Tunnel Club and NHL Home Locker Room | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2021-03-12 | 2021-03-11 | 14 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-03-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11692 | Received | For Review | 2021-02-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-03-12 | Submittal Number: 08 81 13-23.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: DECORATIVE GLASS GLAZING - HERZOG DOORS (TUNNEL CLUB & NHL HOME LOCKER ROOM) Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 15150 | Forwarded | For Review | 2021-03-01 | Josh Dobken (Populous) | Kelsea Conkright (Populous); Kuebler Perry (Populous); Chad Francis (Populous) | 2021-03-08 | Submittal Number: 08 81 13-23.0 From: ALLIE ZIMMERMAN Final Due Date: 03/12/21 Subject: DECORATIVE GLASS GLAZING - HERZOG DOORS (TUNNEL CLUB & NHL HOME LOCKER ROOM) Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 15492 | Responded and Closed | Approved as Noted | 2021-03-11 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED 1. REVIEWED FOR DOORS ONLY, ALL HARDWARE REVIEWED IN PREVIOUS 08 71 00 SUBMITTAL. 2. CM TO COORDINATE ALL MOCKUP COMMENTS HAVE BEEN INCORPORATED FOR EACH AREA. 3. CM TO COORDINATE ALL ROCKWELL GROUP COMMENTS FOR TUNNEL CLUB SUITES | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-26 02:00 |  | Submittal 08 81 13-23 Revision 0 DECORATIVE GLASS GLAZING - Herzog Doors (Tunnel Club NHL Home Locker Room)_MAM Reviewed.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-26 02:00 |  | 08 81 13-023-00 Herzog Doors - Tunnel Club NHL Home Locker Room_MAM.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-11 |  | 08 81 13-023-00 Herzog Doors - Tunnel Club NHL Home Locker Room_MAM_POP.pdf
08 81 13-024-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-024-00 DECORATIVE GLASS GLAZING - GL13 & GLS17 Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-03 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-17 | 2021-03-15 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-03-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11761 | Received | For Review | 2021-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-03-17 | Submittal Number: 08 81 13-24.0 From: ALLIE ZIMMERMAN Final Due Date: 03/16/21 Subject: DECORATIVE GLASS GLAZING - GL13 & GLS17 SAMPLES Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 15241 | Forwarded | For Review | 2021-03-03 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-10 | Submittal Number: 08 81 13-24.0 From: ALLIE ZIMMERMAN Final Due Date: 03/16/21 Subject: DECORATIVE GLASS GLAZING - GL13 & GLS17 SAMPLES Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 12029 | Review Response | Approved as Noted | 2021-03-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15569 | Responded and Closed | Approved as Noted | 2021-03-15 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-02 |  | Submittal 08 81 13-24 Revision 0 DECORATIVE GLASS GLAZING - GL13 GLS17 Samples_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-02 |  | Submittal 08 81 13-24 Revision 0 DECORATIVE GLASS GLAZING - GL13 GLS17 Samples_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-15 |  | Submittal 08 81 13-24 Revision 0 GL13 GLS17 _POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-03-02 |  | Submittal 08 81 13-24 Revision 0 DECORATIVE GLASS GLAZING - GL13 GLS17 Samples_MAM Reviewed.pdf
08 81 13-025-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-025-00 DECORATIVE GLASS GLAZING - GLS13 Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-25 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-05-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13019 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-05-25 | Submittal Number: 08 81 13-25.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: DECORATIVE GLASS GLAZING - GLS13 PRODUCT DATA Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 16847 | Forwarded | For Review | 2021-05-10 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-17 | Submittal Number: 08 81 13-25.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: DECORATIVE GLASS GLAZING - GLS13 PRODUCT DATA Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 17147 | Responded and Closed | Approved as Noted | 2021-05-25 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | Submittal 08 81 13-25 Revision 0 DECORATIVE GLASS GLAZING - GLS13 Product Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-10 |  | Submittal 08 81 13-25 Revision 0 DECORATIVE GLASS GLAZING - GLS13 Product Data_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-25 |  | Submittal 08 81 13-25 Revision 0 DECORATIVE GLASS GLAZING - GLS13 Product Data_MAM Reviewed_POP.pdf
08 81 13-026-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-026-00 DECORATIVE GLASS GLAZING - GLS12 Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-17 | 2021-05-17 | 15 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-05-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12876 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-05-17 | Submittal Number: 08 81 13-26.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: DECORATIVE GLASS GLAZING - GLS12 PRODUCT DATA Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 16658 | Forwarded | For Review | 2021-04-30 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-07 | Submittal Number: 08 81 13-26.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: DECORATIVE GLASS GLAZING - GLS12 PRODUCT DATA Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 16977 | Responded and Closed | Approved as Noted | 2021-05-17 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-30 |  | Submittal 08 81 13-26 Revision 0 DECORATIVE GLASS GLAZING - GLS12 Product Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-30 |  | Submittal 08 81 13-26 Revision 0 DECORATIVE GLASS GLAZING - GLS12 Product Data_MAM Reviewed.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-17 02:00 |  | 08 81 13-26 Revision 0 DECORATIVE GLASS GLAZING - GLS12 PD_MAM_POP.pdf
08 81 13-027-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-027-00 DECORATIVE GLASS GLAZING - Main Concourse Club Storefront Accessories | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-05 | 2021-05-10 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12709 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-05-05 | Submittal Number: 08 81 13-27.0 From: ALLIE ZIMMERMAN Final Due Date: 05/05/21 Subject: DECORATIVE GLASS GLAZING - MAIN CONCOURSE CLUB STOREFRONT ACCESSORIES Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 16430 | Forwarded | For Review | 2021-04-21 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-28 | Submittal Number: 08 81 13-27.0 From: ALLIE ZIMMERMAN Final Due Date: 05/05/21 Subject: DECORATIVE GLASS GLAZING - MAIN CONCOURSE CLUB STOREFRONT ACCESSORIES Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 13003 | Review Response | Approved | 2021-05-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16828 | Responded and Closed | Approved | 2021-05-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-21 |  | Submittal 08 81 13-27 Revision 0 DECORATIVE GLASS GLAZING - Main Concourse Club Storefront Accessories_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-21 |  | Submittal 08 81 13-27 Revision 0 DECORATIVE GLASS GLAZING - Main Concourse Club Storefront Accessories_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-10 |  | Submittal 08 81 13-27 Revision 0 DECORATIVE GLASS GLAZING - MCC_MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-21 |  | Submittal 08 81 13-27 Revision 0 DECORATIVE GLASS GLAZING - Main Concourse Club Storefront Accessories_MAM Reviewed.pdf
08 81 13-028-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-028-00 DECORATIVE GLASS GLAZING - GLS3 Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-27 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-11 07:00 | 2021-06-04 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13293 | Received | For Review | 2021-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-11 07:00 | Submittal Number: 08 81 13-28.0 From: ALLIE ZIMMERMAN Final Due Date: 06/09/21 Subject: DECORATIVE GLASS GLAZING - GLS3 SAMPLES Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 17193 | Forwarded | For Review | 2021-05-27 | Allie Zimmerman | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-03 | Submittal Number: 08 81 13-28.0 From: ALLIE ZIMMERMAN Final Due Date: 06/09/21 Subject: DECORATIVE GLASS GLAZING - GLS3 SAMPLES Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 13402 | Review Response | Approved | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17335 | Responded and Closed | Approved | 2021-06-04 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-27 |  | Submittal 08 81 13-28 Revision 0 DECORATIVE GLASS GLAZING - GLS3 Samples_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-27 |  | Submittal 08 81 13-28 Revision 0 DECORATIVE GLASS GLAZING - GLS3 Samples_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-04 |  | Submittal 08 81 13-28 Revision 0 DECORATIVE GLASS GLAZING - GLS3 Samples_POP.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-05-27 |  | Submittal 08 81 13-28 Revision 0 DECORATIVE GLASS GLAZING - GLS3 Samples_MAM Reviewed.pdf
08 81 13-029-00 | 08 81 13 - DECORATIVE GLASS GLAZING | 08 81 13-029-00 DECORATIVE GLASS GLAZING - Artist Lounge Film Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-28 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-13 07:00 | 2021-07-13 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13675 | Received | For Review | 2021-06-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-07-13 07:00 | Submittal Number: 08 81 13-29.0 From: ALLIE ZIMMERMAN Final Due Date: 07/12/21 Subject: DECORATIVE GLASS GLAZING - ARTIST LOUNGE FILM SAMPLE Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 17711 | Forwarded | For Review | 2021-06-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-05 | Submittal Number: 08 81 13-29.0 From: ALLIE ZIMMERMAN Final Due Date: 07/12/21 Subject: DECORATIVE GLASS GLAZING - ARTIST LOUNGE FILM SAMPLE Description: Spec Section: 08 81 13 - DECORATIVE GLASS GLAZING Status: OPEN | Info Exchange
| 13912 | Review Response | Approved | 2021-07-13 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18015 | Responded and Closed | Approved | 2021-07-13 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-28 |  | Submittal 08 81 13-29 Revision 0 DECORATIVE GLASS GLAZING - Artist Lounge Film Sample_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-28 |  | Submittal 08 81 13-29 Revision 0 DECORATIVE GLASS GLAZING - Artist Lounge Film Sample_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-13 |  | Submittal 08 81 13-29 Revision 0 DECORATIVE GLASS GLAZING - Artist Lounge Film Sample_MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-06-28 |  | Submittal 08 81 13-29 Revision 0 DECORATIVE GLASS GLAZING - Artist Lounge Film Sample_MAM Reviewed.pdf
08 83 00-001-00 | 08 83 00 - MIRRORS | 08 83 00-001-00 MIRRORS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-09 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-06-23 | 2020-06-23 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-06-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06283 | Received | For Review | 2020-06-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-23 | Submittal Number: 08 83 00-1.0 From: BROOKE BURCHAM Final Due Date: 06/22/20 Subject: MIRRORS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. MIRRORS. INCLUDE DESCRIPTION OF MATERIALS AND PROCESS USED TO PRODUCE EACH TYPE OF SILVERED FLAT GLASS MIRROR SPECIFIED THAT INDICATES SOURCES OF GLASS, GLASS COATING COMPONENTS, EDGE SEALER, AND QUALITY-CONTROL PROVISIONS. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 08478 | Forwarded | For Review | 2020-06-09 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-16 | Submittal Number: 08 83 00-1.0 From: BROOKE BURCHAM Final Due Date: 06/22/20 Subject: MIRRORS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. MIRRORS. INCLUDE DESCRIPTION OF MATERIALS AND PROCESS USED TO PRODUCE EACH TYPE OF SILVERED FLAT GLASS MIRROR SPECIFIED THAT INDICATES SOURCES OF GLASS, GLASS COATING COMPONENTS, EDGE SEALER, AND QUALITY-CONTROL PROVISIONS. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 08835 | Responded and Closed | Revise and Resubmit | 2020-06-23 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. Spec 2.2A indicates product should be Copper free 2. Submit product data for hardware indicated in 2.4 3. Submit Laminated mirror at weight room areas | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-08 |  | 088300-0001-0 Mirror Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-08 |  | 088300-0001-0 Mirror Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-06-23 |  | 088300-0001-0 Mirror Product Data_POP.pdf
08 83 00-001-01 | 08 83 00 - MIRRORS | 08 83 00-001-01 MIRRORS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-02 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-16 | 2020-10-13 | 12 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08497 | Received | For Review | 2020-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-16 | Submittal Number: 08 83 00-1.1 From: BROOKE BURCHAM Final Due Date: 10/16/20 Subject: MIRRORS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. MIRRORS. INCLUDE DESCRIPTION OF MATERIALS AND PROCESS USED TO PRODUCE EACH TYPE OF SILVERED FLAT GLASS MIRROR SPECIFIED THAT INDICATES SOURCES OF GLASS, GLASS COATING COMPONENTS, EDGE SEALER, AND QUALITY-CONTROL PROVISIONS. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 11242 | Forwarded | For Review | 2020-10-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-08 | Submittal Number: 08 83 00-1.1 From: BROOKE BURCHAM Final Due Date: 10/16/20 Subject: MIRRORS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. MIRRORS. INCLUDE DESCRIPTION OF MATERIALS AND PROCESS USED TO PRODUCE EACH TYPE OF SILVERED FLAT GLASS MIRROR SPECIFIED THAT INDICATES SOURCES OF GLASS, GLASS COATING COMPONENTS, EDGE SEALER, AND QUALITY-CONTROL PROVISIONS. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 11569 | Responded and Closed | Approved | 2020-10-13 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 088300-0001-1 Mirror Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-01 |  | 088300-0001-1 Mirror Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-13 |  | 088300-0001-1 Mirror Product Data_POP.pdf
08 83 00-004-00 | 08 83 00 - MIRRORS | 08 83 00-004-00 MIRRORS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-07 | 2020-10-06 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08285 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 08 83 00-4.0 From: BROOKE BURCHAM Final Due Date: 10/07/20 Subject: MIRRORS - SHOP DRAWINGS Description: SHOP DRAWINGS : INCLUDE MIRROR ELEVATIONS, EDGE DETAILS, MIRROR HARDWARE, AND ATTACHMENT DETAILS. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 10991 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-30 | Submittal Number: 08 83 00-4.0 From: BROOKE BURCHAM Final Due Date: 10/07/20 Subject: MIRRORS - SHOP DRAWINGS Description: SHOP DRAWINGS : INCLUDE MIRROR ELEVATIONS, EDGE DETAILS, MIRROR HARDWARE, AND ATTACHMENT DETAILS. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 11361 | Responded and Closed | Approved as Noted | 2020-10-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 088300-0004-0 Mirror Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 088300-0004-0 Mirror Shop Drawings.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-06 |  | 088300-0004-0 Mirror Shop Drawings_POP.pdf
08 83 00-005-00 | 08 83 00 - MIRRORS | 08 83 00-005-00 MIRRORS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-14 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-28 | 2020-09-28 | 15 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-09-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08061 | Received | For Review | 2020-09-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-28 | Submittal Number: 08 83 00-5.0 From: BROOKE BURCHAM Final Due Date: 09/28/20 Subject: MIRRORS - SAMPLES Description: SAMPLES : FOR EACH TYPE OF THE FOLLOWING: 1. MIRRORS: 12 INCHES SQUARE, INCLUDING EDGE TREATMENT ON TWO ADJOINING EDGES. 2. MIRROR CLIPS: FULL SIZE. 3. MIRROR TRIM: 12 INCHES LONG. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 10725 | Forwarded | For Review | 2020-09-11 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-18 | Submittal Number: 08 83 00-5.0 From: BROOKE BURCHAM Final Due Date: 09/28/20 Subject: MIRRORS - SAMPLES Description: SAMPLES : FOR EACH TYPE OF THE FOLLOWING: 1. MIRRORS: 12 INCHES SQUARE, INCLUDING EDGE TREATMENT ON TWO ADJOINING EDGES. 2. MIRROR CLIPS: FULL SIZE. 3. MIRROR TRIM: 12 INCHES LONG. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 11108 | Responded and Closed | Approved as Noted | 2020-09-28 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. MIRROR SUBMITTED APPROVED 2. SUBMIT HARDWARE SAMPLES PER SPEC REQUIREMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-11 |  | 088300-0005-0 Mirrors - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-11 |  | 088300-0005-0 Mirrors - Samples.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-09-28 |  | 088300-0005-0 Mirrors - Samples_POP.pdf
08 83 00-009-00 | 08 83 00 - MIRRORS | 08 83 00-009-00 MIRRORS - Sample Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-07 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-21 | 2020-08-10 | 4 |  | Record Copies; Transfers; Submittals | 08 83 00-009-00-01 - 08 83 00-009-00 MIRRORS - Sample Warranty | 5 |  | 2020-08-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07442 | Received | For Review | 2020-08-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-08-21 | Submittal Number: 08 83 00-9.0 From: BROOKE BURCHAM Final Due Date: 08/20/20 Subject: MIRRORS - SAMPLE WARRANTY Description: SAMPLE WARRANTY : FOR SPECIAL WARRANTY. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 09909 | Forwarded | For Review | 2020-08-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-13 | Submittal Number: 08 83 00-9.0 From: BROOKE BURCHAM Final Due Date: 08/20/20 Subject: MIRRORS - SAMPLE WARRANTY Description: SAMPLE WARRANTY : FOR SPECIAL WARRANTY. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 09965 | Responded and Closed | Revise and Resubmit | 2020-08-10 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | 088300-0009-0 Mirror Warranty_Mission Glass.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-06 |  | 088300-0009-0 Mirror Warranty_Mission Glass.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-10 |  | 088300-0009-0 Mirror Warranty_Mission Glass_POP.pdf
08 83 00-009-00-01 | 08 83 00 - MIRRORS | 08 83 00-009-00 MIRRORS - Sample Warranty | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 83 00-009-00 - 08 83 00-009-00 MIRRORS - Sample Warranty | -1 | 2020-08-24
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-10 |  | 088300-0009-0 Mirror Warranty_Mission Glass_POP.pdf
08 83 00-011-00 | 08 83 00 - MIRRORS | 08 83 00-011-00 08 83 00 GLS 11 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-23 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-06 | 2020-11-09 | 18 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08948 | Received | For Review | 2020-10-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-11-06 | Submittal Number: 08 83 00-11.0 From: ALLIE ZIMMERMAN Final Due Date: 11/05/20 Subject: 08 83 00 GLS 11 SAMPLE Description: GLS11 SPANCRAFT GLASS SAMPLE Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 11819 | Forwarded | For Review | 2020-10-22 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 08 83 00-11.0 From: ALLIE ZIMMERMAN Final Due Date: 11/05/20 Subject: 08 83 00 GLS 11 SAMPLE Description: GLS11 SPANCRAFT GLASS SAMPLE Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 09289 | Review Response | Approved | 2020-11-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Confirm approval with Rockwell. | Info Exchange
| 12258 | Responded and Closed | Approved | 2020-11-09 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Confirm approval with Rockwell. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-22 |  | GLS11 Glass Samples Spancraft.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-22 |  | 08 83 00-011-00 GLS11 Glass Samples Spancraft.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-09 |  | 08 83 00-011-00 GLS11 Glass Samples Spancraft_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-22 |  | GLS11 Glass Samples Spancraft.pdf
08 83 00-011-01 | 08 83 00 - MIRRORS | 08 83 00-011-01 08 83 00 GLS 11 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-04 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-18 | 2020-12-17 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09912 | Received | For Review | 2020-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-12-18 | Submittal Number: 08 83 00-11.1 From: ALLIE ZIMMERMAN Final Due Date: 12/18/20 Subject: 08 83 00 GLS 11 SAMPLE Description: GLS11 GOLDRAY GLASS SAMPLE Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 12992 | Forwarded | For Review | 2020-12-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-11 | Submittal Number: 08 83 00-11.1 From: ALLIE ZIMMERMAN Final Due Date: 12/18/20 Subject: 08 83 00 GLS 11 SAMPLE Description: GLS11 GOLDRAY GLASS SAMPLE Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 10220 | Review Response | Approved | 2020-12-17 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 13359 | Responded and Closed | Approved | 2020-12-17 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-04 |  | GLS11 Glass Samples GoldRay_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-04 |  | GLS11 Glass Samples GoldRay_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-17 |  | GLS11 Glass Samples GoldRay_MAM Reviewed-POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-04 |  | GLS11 Glass Samples GoldRay_MAM Reviewed.pdf
08 83 00-012-00 | 08 83 00 - MIRRORS | 08 83 00-012-00 Chairman's Club Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-03 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-17 | 2020-11-19 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-11-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09206 | Received | For Review | 2020-11-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2020-11-17 | Submittal Number: 08 83 00-12.0 From: ALLIE ZIMMERMAN Final Due Date: 11/16/20 Subject: 08 83 00-12 REV0 CHAIRMAN'S CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : INCLUDE MIRROR ELEVATIONS, EDGE DETAILS, MIRROR HARDWARE, AND ATTACHMENT DETAILS. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 12155 | Forwarded | For Review | 2020-11-03 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-10 | Submittal Number: 08 83 00-12.0 From: ALLIE ZIMMERMAN Final Due Date: 11/16/20 Subject: 08 83 00-12 REV0 CHAIRMAN'S CLUB SHOP DRAWINGS Description: SHOP DRAWINGS : INCLUDE MIRROR ELEVATIONS, EDGE DETAILS, MIRROR HARDWARE, AND ATTACHMENT DETAILS. Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 09565 | Review Response | Approved as Noted | 2020-11-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12590 | Responded and Closed | Approved as Noted | 2020-11-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | Climate Pledge Arena - 10.23.20R _ Chairmans Club Shop Drawings _MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | Climate Pledge Arena - 10.23.20R _ Chairmans Club Shop Drawings _MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-19 |  | Climate Pledge Arena - 10.23.20R _ Chairmans Club Shop Drawings _MAM Reviewed_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-02 |  | Climate Pledge Arena - 10.23.20R _ Chairmans Club Shop Drawings _MAM Reviewed.pdf
08 83 00-014-00 | 08 83 00 - MIRRORS | 08 83 00-014-00 MIRRORS - GLS11 Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 | 2021-04-28 | 21 |  | Record Copies; Transfers; Submittals | 08 83 00-014-00-01 - 08 83 00-014-00 MIRRORS - GLS11 Product Data | 21 |  | 2021-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12486 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-04-22 | Submittal Number: 08 83 00-14.0 From: ALLIE ZIMMERMAN Final Due Date: 04/22/21 Subject: MIRRORS - GLS11 PRODUCT DATA Description: Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 16176 | Forwarded | For Review | 2021-04-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 08 83 00-14.0 From: ALLIE ZIMMERMAN Final Due Date: 04/22/21 Subject: MIRRORS - GLS11 PRODUCT DATA Description: Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 12832 | Review Response | Revise and Resubmit | 2021-04-28 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Data does not match specified product. It is from Walker textures and the mirror for GLS11 is Goldray frosted smoke mirror. | Info Exchange
| 16609 | Responded and Closed | Revise and Resubmit | 2021-04-28 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Data does not match specified product. It is from Walker textures and the mirror for GLS11 is Goldray frosted smoke mirror. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | Submittal 08 83 00-14 Revision 0 MIRRORS - GLS11 Product Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-08 |  | Submittal 08 83 00-14 Revision 0 MIRRORS - GLS11 Product Data_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-28 |  | Submittal 08 83 00-14 Revision 0 MIRRORS - GLS11 Product Data_MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-08 |  | Submittal 08 83 00-14 Revision 0 MIRRORS - GLS11 Product Data_MAM Reviewed.pdf
08 83 00-014-00-01 | 08 83 00 - MIRRORS | 08 83 00-014-00 MIRRORS - GLS11 Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 08 83 00-014-00 - 08 83 00-014-00 MIRRORS - GLS11 Product Data | -1 | 2021-05-12
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | Submittal 08 83 00-14 Revision 0 MIRRORS - GLS11 Product Data_MAM Reviewed.pdf
08 83 00-015-00 | 08 83 00 - MIRRORS | 08 83 00-015-00 Alternate Mirrors Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-12 | Responded and Closed - Approved |  | Tom Usher (Populous) |  |  |  | 2021-05-26 | 2021-05-12 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13071 | Received | For Review | 2021-05-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2021-05-26 | Submittal Number: 08 83 00-15.0 From: ALEX ROSHAN Final Due Date: 05/26/21 Subject: MIRRORS - Alternate Mirrors Product Data Description: Spec Section: 08 83 00 - MIRRORS Status: OPEN | Email
| 16909 | Forwarded | For Review | 2021-05-12 | Shaina Burris (Populous) | Tom Usher (Populous) | 2021-05-19 | Submittal Number: 08 83 00-15.0 From: ALEX ROSHAN Final Due Date: 05/26/21 Subject: MIRRORS - Alternate Mirrors Product Data Description: Spec Section: 08 83 00 - MIRRORS Status: OPEN | Info Exchange
| 16911 | Responded and Closed | Approved | 2021-05-12 | Shaina Burris (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Roshan.Alex@mortenson.com |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-12 |  | 088300-015-0 ALTERNATE Mirror Product Data (MG)_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-12 |  | 088300-015-0 ALTERNATE Mirror Product Data (MG)_MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-05-12 02:00 |  | 088300-015-0 ALTERNATE Mirror Product Data (MG)_MAM_POP.pdf
08 91 19-001-00 | 08 91 19 - FIXED LOUVERS | 08 91 19-001-00 FIXED LOUVERS - Product Data | Closed | Architectural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Nick Theimer (ME Engineers) |  |  |  | 2020-06-01 07:00 | 2020-06-12 | 29 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-06-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05875 | Received | For Review | 2020-05-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-01 07:00 | Submittal Number: 08 91 19-1.0 From: BROOKE BURCHAM Final Due Date: 05/28/20 Subject: FIXED LOUVERS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. FOR LOUVERS SPECIFIED TO BEAR AMCA SEAL, INCLUDE PRINTED CATALOG PAGES SHOWING SPECIFIED MODELS WITH APPROPRIATE AMCA CERTIFIED RATINGS SEALS. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 07971 | Forwarded | For Review | 2020-05-15 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-05-22 | Submittal Number: 08 91 19-1.0 From: BROOKE BURCHAM Final Due Date: 05/28/20 Subject: FIXED LOUVERS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. FOR LOUVERS SPECIFIED TO BEAR AMCA SEAL, INCLUDE PRINTED CATALOG PAGES SHOWING SPECIFIED MODELS WITH APPROPRIATE AMCA CERTIFIED RATINGS SEALS. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 08365 | Forwarded | For Review | 2020-06-04 | Josh Dobken (Populous) | Nick Theimer (ME Engineers) | 2020-06-01 | Submittal Number: 08 91 19-1.0 From: BROOKE BURCHAM Final Due Date: 05/28/20 Subject: FIXED LOUVERS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. FOR LOUVERS SPECIFIED TO BEAR AMCA SEAL, INCLUDE PRINTED CATALOG PAGES SHOWING SPECIFIED MODELS WITH APPROPRIATE AMCA CERTIFIED RATINGS SEALS. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 06384 | Review Response | Approved | 2020-06-04 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.06.04 | Info Exchange
| 08586 | Responded and Closed | Approved as Noted | 2020-06-12 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Note: Populous requests physical samples for selected colors. Bryan Klote/Populous 06.12.2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-14 |  | 089119-0001-0 Fixed Louvers Product Data_R2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-14 |  | 089119-0001-0 Fixed Louvers Product Data_R2.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-13 02:00 |  | 089119-0001-0 Fixed Louvers Product Data_R2.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-13 02:00 |  | 089119-0001-0 Fixed Louvers Product Data_R2.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-12 |  | 089119-0001-0 Fixed Louvers Product Data_R2_ME_POP.pdf
08 91 19-002-00 | 08 91 19 - FIXED LOUVERS | 08 91 19-002-00 FIXED LOUVERS - Shop Drawings | Closed | Architectural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Nick Theimer (ME Engineers), Kuebler Perry (Populous) |  |  |  | 2020-06-09 | 2020-06-12 | 18 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-06-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06018 | Received | For Review | 2020-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-09 | Submittal Number: 08 91 19-2.0 From: BROOKE BURCHAM Final Due Date: 06/09/20 Subject: FIXED LOUVERS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR LOUVERS AND ACCESSORIES. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. SHOW FRAME PROFILES AND BLADE PROFILES, ANGLES, AND SPACING. 1. SHOW WEEP PATHS, GASKETS, FLASHING, SEALANT, AND OTHER MEANS OF PREVENTING WATER INTRUSION. 2. SHOW MULLION PROFILES AND LOCATIONS. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 08161 | Forwarded | For Review | 2020-05-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-02 | Submittal Number: 08 91 19-2.0 From: BROOKE BURCHAM Final Due Date: 06/09/20 Subject: FIXED LOUVERS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR LOUVERS AND ACCESSORIES. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. SHOW FRAME PROFILES AND BLADE PROFILES, ANGLES, AND SPACING. 1. SHOW WEEP PATHS, GASKETS, FLASHING, SEALANT, AND OTHER MEANS OF PREVENTING WATER INTRUSION. 2. SHOW MULLION PROFILES AND LOCATIONS. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 08305 | Forwarded | For Review | 2020-06-01 | Josh Dobken (Populous) | Todd Spangler (Populous); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Chad Francis (Populous) | 2020-06-08 | Submittal Number: 08 91 19-2.0 From: BROOKE BURCHAM Final Due Date: 06/09/20 Subject: FIXED LOUVERS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR LOUVERS AND ACCESSORIES. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. SHOW FRAME PROFILES AND BLADE PROFILES, ANGLES, AND SPACING. 1. SHOW WEEP PATHS, GASKETS, FLASHING, SEALANT, AND OTHER MEANS OF PREVENTING WATER INTRUSION. 2. SHOW MULLION PROFILES AND LOCATIONS. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 06385 | Review Response | Approved | 2020-06-04 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.06.04 | Info Exchange
| 08585 | Responded and Closed | Approved as Noted | 2020-06-12 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review. Nick Theimer ME Engineers 2020.06.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-26 |  | 089119-0002-0 Fixed Louver Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-26 |  | 089119-0002-0 Fixed Louver Shop Drawings.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-25 02:00 |  | 089119-0002-0 Fixed Louver Shop Drawings.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-25 02:00 |  | 089119-0002-0 Fixed Louver Shop Drawings.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-12 |  | 089119-0002-0 Fixed Louver Shop Drawings_ME_POP.pdf
08 91 19-002-01 | 08 91 19 - FIXED LOUVERS | 08 91 19-002-01 FIXED LOUVERS - Shop Drawings | Closed | Mechanical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-03 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-18 | 2020-09-24 | 22 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07907 | Received | For Review | 2020-09-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-18 | Submittal Number: 08 91 19-2.1 From: BROOKE BURCHAM Final Due Date: 06/09/20 Subject: FIXED LOUVERS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR LOUVERS AND ACCESSORIES. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. SHOW FRAME PROFILES AND BLADE PROFILES, ANGLES, AND SPACING. 1. SHOW WEEP PATHS, GASKETS, FLASHING, SEALANT, AND OTHER MEANS OF PREVENTING WATER INTRUSION. 2. SHOW MULLION PROFILES AND LOCATIONS. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 10519 | Forwarded | For Review | 2020-09-02 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-09 | Submittal Number: 08 91 19-2.1 From: BROOKE BURCHAM Final Due Date: 06/09/20 Subject: FIXED LOUVERS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR LOUVERS AND ACCESSORIES. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. SHOW FRAME PROFILES AND BLADE PROFILES, ANGLES, AND SPACING. 1. SHOW WEEP PATHS, GASKETS, FLASHING, SEALANT, AND OTHER MEANS OF PREVENTING WATER INTRUSION. 2. SHOW MULLION PROFILES AND LOCATIONS. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 08224 | Review Response | Approved as Noted | 2020-09-15 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.09.15 | Info Exchange
| 11013 | Responded and Closed | Approved | 2020-09-24 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | see attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-02 |  | 089119-0002-1 Fixed Louver Shop Drawings_R2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-02 |  | 089119-0002-1 Fixed Louver Shop Drawings_R2.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-02 |  | 089119-0002-1 Fixed Louver Shop Drawings_R2.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-24 |  | 089119-0002-1 Fixed Louver Shop Drawings_R2_ME_POP.pdf
08 91 19-002-02 | 08 91 19 - FIXED LOUVERS | 08 91 19-002-02 FIXED LOUVERS - Shop Drawings FOR RECORD ONLY | Closed | Architectural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-14 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-06 | 2020-12-15 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10121 | Received | For Review | 2020-12-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-01-06 | Submittal Number: 08 91 19-2.2 From: BROOKE BURCHAM Final Due Date: 12/24/20 Subject: FIXED LOUVERS - SHOP DRAWINGS FOR RECORD ONLY Description: SHOP DRAWINGS : FOR LOUVERS AND ACCESSORIES. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. SHOW FRAME PROFILES AND BLADE PROFILES, ANGLES, AND SPACING. 1. SHOW WEEP PATHS, GASKETS, FLASHING, SEALANT, AND OTHER MEANS OF PREVENTING WATER INTRUSION. 2. SHOW MULLION PROFILES AND LOCATIONS. THIS REVISION IS FOR RECORD ONLY. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 13229 | Forwarded | For Review | 2020-12-14 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-21 | Submittal Number: 08 91 19-2.2 From: BROOKE BURCHAM Final Due Date: 12/24/20 Subject: FIXED LOUVERS - SHOP DRAWINGS FOR RECORD ONLY Description: SHOP DRAWINGS : FOR LOUVERS AND ACCESSORIES. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. SHOW FRAME PROFILES AND BLADE PROFILES, ANGLES, AND SPACING. 1. SHOW WEEP PATHS, GASKETS, FLASHING, SEALANT, AND OTHER MEANS OF PREVENTING WATER INTRUSION. 2. SHOW MULLION PROFILES AND LOCATIONS. THIS REVISION IS FOR RECORD ONLY. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 13237 | Forwarded | For Review | 2020-12-14 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-21 | Submittal Number: 08 91 19-2.2 From: BROOKE BURCHAM Final Due Date: 12/24/20 Subject: FIXED LOUVERS - SHOP DRAWINGS FOR RECORD ONLY Description: SHOP DRAWINGS : FOR LOUVERS AND ACCESSORIES. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. SHOW FRAME PROFILES AND BLADE PROFILES, ANGLES, AND SPACING. 1. SHOW WEEP PATHS, GASKETS, FLASHING, SEALANT, AND OTHER MEANS OF PREVENTING WATER INTRUSION. 2. SHOW MULLION PROFILES AND LOCATIONS. THIS REVISION IS FOR RECORD ONLY. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 10178 | Review Response | No Action Taken or Required | 2020-12-15 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Reviewed for record only. Nick Theimer ME Engineers 2020.12.15 | Info Exchange
| 13314 | Responded and Closed | Approved as Noted | 2020-12-15 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-14 |  | 08 91 19-2.2 LOUVER ATTACHMENT SHOP DRAWINGS R2_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-14 |  | 08 91 19-2.2 LOUVER ATTACHMENT SHOP DRAWINGS R2_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-14 |  | 08 91 19-2.2 LOUVER ATTACHMENT SHOP DRAWINGS R2_MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-12-14 |  | 08 91 19-2.2 LOUVER ATTACHMENT SHOP DRAWINGS R2_MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-15 |  | 08 91 19-2.2 LOUVER ATTACHMENT SHOP DRAWINGS R2_MAM_ME_POP.pdf
08 91 19-003-00 | 08 91 19 - FIXED LOUVERS | 08 91 19-003-00 FIXED LOUVERS - Color Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-17 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-07-31 | 2020-09-10 | 56 |  | Record Copies; Transfers; Submittals |  | 56 |  | 2020-09-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07008 | Received | For Review | 2020-07-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-07-31 | Submittal Number: 08 91 19-3.0 From: BROOKE BURCHAM Final Due Date: 07/31/20 Subject: FIXED LOUVERS - COLORSAMPLES Description: SAMPLES : FOR EACH TYPE OF METAL FINISH REQUIRED. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 09385 | Forwarded | For Review | 2020-07-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-07-24 | Submittal Number: 08 91 19-3.0 From: BROOKE BURCHAM Final Due Date: 07/31/20 Subject: FIXED LOUVERS - COLORSAMPLES Description: SAMPLES : FOR EACH TYPE OF METAL FINISH REQUIRED. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 10688 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-10 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR APPROVED COLORS. SEE LOUVEER SHOPS FOR ASSIGNED COLORS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-16 |  | 089119-0003-0 Fixed Louver Color Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-16 |  | 089119-0003-0 Fixed Louver Color Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-10 |  | 089119-0003-0 Fixed Louver Color Samples_POP.pdf
08 91 19-003-01 | 08 91 19 - FIXED LOUVERS | 08 91 19-003-01 FIXED LOUVERS - ColorSamples - Graphite 40 (Exterior Louvers) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-22 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-05 | 2020-11-02 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-11-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08935 | Received | For Review | 2020-10-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-11-05 | Submittal Number: 08 91 19-3.1 From: CHRISTIAN GENEROSA Final Due Date: 11/05/20 Subject: FIXED LOUVERS - COLORSAMPLES - GRAPHITE 40 (EXTERIOR LOUVERS) Description: SAMPLES : FOR EACH TYPE OF METAL FINISH REQUIRED. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 11805 | Forwarded | For Review | 2020-10-22 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-29 | Submittal Number: 08 91 19-3.1 From: CHRISTIAN GENEROSA Final Due Date: 11/05/20 Subject: FIXED LOUVERS - COLORSAMPLES - GRAPHITE 40 (EXTERIOR LOUVERS) Description: SAMPLES : FOR EACH TYPE OF METAL FINISH REQUIRED. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 12090 | Responded and Closed | Approved | 2020-11-02 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 12119 | Sent | For Information Only | 2020-11-02 | Populous SCA_CCA | Tyrone Thornton (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company) |  | Responded and Closed (Approved) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-21 |  | 2020-10-21 089119-0003-1 Fixed Louver ColorSamples - Graphite 40.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-21 |  | 2020-10-21 089119-0003-1 Fixed Louver ColorSamples - Graphite 40.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-02 |  | 2020-10-21 089119-0003-1 Fixed Louver ColorSamples_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2020-10-20 02:00 |  | 2020-10-21 089119-0003-1 Fixed Louver ColorSamples - Graphite 40.pdf
08 91 19-005-00 | 08 91 19 - FIXED LOUVERS | 08 91 19-005-00 FIXED LOUVER - LEED LETTERS | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-26 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-06-09 | 2020-06-16 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-06-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06019 | Received | For Review | 2020-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-09 | Submittal Number: 08 91 19-5.0 From: BROOKE BURCHAM Final Due Date: 06/09/20 Subject: FIXED LOUVER - LEED LETTERS Description: GREENHECK LEED LETTER. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 08162 | Forwarded | For Review | 2020-05-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-06-02 | Submittal Number: 08 91 19-5.0 From: BROOKE BURCHAM Final Due Date: 06/09/20 Subject: FIXED LOUVER - LEED LETTERS Description: GREENHECK LEED LETTER. Spec Section: 08 91 19 - FIXED LOUVERS Status: OPEN | Info Exchange
| 08683 | Responded and Closed | Approved | 2020-06-16 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-26 |  | 089119-0005-0 Fixed Louver LEED Greenheck Letter.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-26 |  | 089119-0005-0 Fixed Louver LEED Greenheck Letter.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-16 |  | 089119-0005-0 Fixed Louver LEED Greenheck Letter_POP.pdf
09 21 16.23-001-00 | 09 21 16.23 - GYPSUM BOARD SHAFT WALL ASSEMBLIES | 09 21 16.23-001-00 GYPSUM BOARD SHAFT WALL ASSEMBLIES - Product Data Shaftliner | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-15 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chris Minter (Populous) |  |  |  | 2020-07-29 | 2020-07-28 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06980 | Received | For Review | 2020-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-07-29 | Submittal Number: 09 21 16.23-1.0 From: TYRONE THORNTON Final Due Date: 07/29/20 Subject: GYPSUM BOARD SHAFT WALL ASSEMBLIES - PRODUCT DATA SHAFTLINER Description: PRODUCT DATA : FOR EACH COMPONENT OF GYPSUM BOARD SHAFT WALL ASSEMBLY. Spec Section: 09 21 16.23 - GYPSUM BOARD ASSEMBLIES Status: OPEN | Info Exchange
| 09346 | Forwarded | For Review | 2020-07-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-07-22 | Submittal Number: 09 21 16.23-1.0 From: TYRONE THORNTON Final Due Date: 07/29/20 Subject: GYPSUM BOARD SHAFT WALL ASSEMBLIES - PRODUCT DATA SHAFTLINER Description: PRODUCT DATA : FOR EACH COMPONENT OF GYPSUM BOARD SHAFT WALL ASSEMBLY. Spec Section: 09 21 16.23 - GYPSUM BOARD ASSEMBLIES Status: OPEN | Info Exchange
| 09414 | Forwarded | For Review | 2020-07-20 | Josh Dobken (Populous) | Chris Minter (Populous) | 2020-07-27 | Submittal Number: 09 21 16.23-1.0 From: TYRONE THORNTON Final Due Date: 07/29/20 Subject: GYPSUM BOARD SHAFT WALL ASSEMBLIES - PRODUCT DATA SHAFTLINER Description: PRODUCT DATA : FOR EACH COMPONENT OF GYPSUM BOARD SHAFT WALL ASSEMBLY. Spec Section: 09 21 16.23 - GYPSUM BOARD ASSEMBLIES Status: OPEN | Info Exchange
| 09621 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-28 | Shaina Burris (Populous) | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-15 |  | 09 21 16.23-1 GYPSUM BOARD SHAFT WALL ASSEMBLIES - PD Shaftline-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-15 |  | 09 21 16.23-1 GYPSUM BOARD SHAFT WALL ASSEMBLIES - PD Shaftline-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-07-14 02:00 |  | 09 21 16.23-1 GYPSUM BOARD SHAFT WALL ASSEMBLIES - PD Shaftline-MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-07-15 |  | 09 21 16.23-1 GYPSUM BOARD SHAFT WALL ASSEMBLIES - PD Shaftline-MAM.pdf
09 21 16.23-001-01 | 09 21 16.23 - GYPSUM BOARD SHAFT WALL ASSEMBLIES | 09 21 16.23-001-01 GYPSUM BOARD SHAFT WALL ASSEMBLIES - Product Data Shaftliner | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-03 | Responded and Closed - Approved |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-18 | 2020-09-24 | 22 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07958 | Received | For Review | 2020-09-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-09-18 | Submittal Number: 09 21 16.23-1.1 From: TYRONE THORNTON Final Due Date: 09/17/20 Subject: GYPSUM BOARD SHAFT WALL ASSEMBLIES - PRODUCT DATA SHAFTLINER Description: PRODUCT DATA : FOR EACH COMPONENT OF GYPSUM BOARD SHAFT WALL ASSEMBLY. Spec Section: 09 21 16.23 - GYPSUM BOARD ASSEMBLIES Status: OPEN | Info Exchange
| 10583 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-15 | Submittal Number: 09 21 16.23-1.1 From: TYRONE THORNTON Final Due Date: 09/17/20 Subject: GYPSUM BOARD SHAFT WALL ASSEMBLIES - PRODUCT DATA SHAFTLINER Description: PRODUCT DATA : FOR EACH COMPONENT OF GYPSUM BOARD SHAFT WALL ASSEMBLY. Spec Section: 09 21 16.23 - GYPSUM BOARD ASSEMBLIES Status: OPEN | Info Exchange
| 11039 | Responded and Closed | Approved | 2020-09-24 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-03 |  | 09 21 16.23-1.1 GYPSUM BOARD SHAFT WALL ASSEMBLIES - Shaftline LEED-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-03 |  | 09 21 16.23-1.1 GYPSUM BOARD SHAFT WALL ASSEMBLIES - Shaftline LEED-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-09-24 |  | 09 21 16.23-1.1 GYPSUM BOARD SHAFT WALL ASSEMBLIES - Shaftline LEED-MAM-POP.pdf
09 21 16.23-004-00 | 09 21 16.23 - GYPSUM BOARD SHAFT WALL ASSEMBLIES | 09 21 16.23-004-00 GYPSUM BOARD SHAFT WALL ASSEMBLIES - Evaluation Reports | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-17 | 2021-05-17 | 15 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-05-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12877 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ye Zhang (Mortenson Construction); Allie Zimmerman | 2021-05-17 | Submittal Number: 09 21 16.23-4.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: GYPSUM BOARD SHAFT WALL ASSEMBLIES - EVALUATION REPORTS Description: PRODUCT CERTIFICATES: FOR MATERIALS MANUFACTURED WITHIN 100 MILES (160 KM) OF PROJECT, INDICATING LOCATION OF MATERIAL MANUFACTURER AND POINT OF EXTRACTION, HARVEST, OR RECOVERY FOR EACH RAW MATERIAL. INCLUDE DISTANCE TO PROJECT AND COST FOR EACH RAW MATERIAL. Spec Section: 09 21 16.23 - GYPSUM BOARD ASSEMBLIES Status: OPEN | Info Exchange
| 16659 | Forwarded | For Review | 2021-04-30 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-07 | Submittal Number: 09 21 16.23-4.0 From: ALLIE ZIMMERMAN Final Due Date: 05/21/21 Subject: GYPSUM BOARD SHAFT WALL ASSEMBLIES - EVALUATION REPORTS Description: PRODUCT CERTIFICATES: FOR MATERIALS MANUFACTURED WITHIN 100 MILES (160 KM) OF PROJECT, INDICATING LOCATION OF MATERIAL MANUFACTURER AND POINT OF EXTRACTION, HARVEST, OR RECOVERY FOR EACH RAW MATERIAL. INCLUDE DISTANCE TO PROJECT AND COST FOR EACH RAW MATERIAL. Spec Section: 09 21 16.23 - GYPSUM BOARD ASSEMBLIES Status: OPEN | Info Exchange
| 16976 | Responded and Closed | Approved | 2021-05-17 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-30 |  | Submittal 09 21 16.23-4 Revision 0 GYPSUM BOARD SHAFT WALL ASSEMBLIES - Evaluation Reports_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-30 |  | Submittal 09 21 16.23-4 Revision 0 GYPSUM BOARD SHAFT WALL ASSEMBLIES - Evaluation Reports_MAM Reviewed.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-17 02:00 |  | Submittal 09 21 16.23-4 Revision 0 GYPSUM BOARD SHAFT WALL ASSEMBLIES - Evaluation Reports_MAM Reviewed_POP.pdf
09 22 16-001-00 | 09 22 16 - NON-STRUCTURAL METAL FRAMING | 09 22 16-001-00 NON-STRUCTURAL METAL FRAMING - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-05 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-19 | 2020-05-19 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05726 | Received | For Review | 2020-05-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-05-19 | Submittal Number: 09 22 16-1.0 From: TYRONE THORNTON Final Due Date: 05/19/20 Subject: NON-STRUCTURAL METAL FRAMING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 07771 | Forwarded | For Review | 2020-05-05 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-12 | Submittal Number: 09 22 16-1.0 From: TYRONE THORNTON Final Due Date: 05/19/20 Subject: NON-STRUCTURAL METAL FRAMING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 08049 | Responded and Closed | Approved as Noted | 2020-05-19 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | 092216-0001-0 Non-Structural Metal Framing Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-05 |  | 092216-0001-0 Non-Structural Metal Framing Product Data-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-19 02:00 |  | 092216-0001-0 Non-Structural Metal Framing Product Data-MAM_pop.pdf
09 22 16-002-00 | 09 22 16 - NON-STRUCTURAL METAL FRAMING | 09 22 16-002-00 NON-STRUCTURAL METAL FRAMING - LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-19 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-06 07:00 | 2020-07-08 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06518 | Received | For Review | 2020-06-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-06 07:00 | Submittal Number: 09 22 16-2.0 From: TYRONE THORNTON Final Due Date: 07/03/20 Subject: NON-STRUCTURAL METAL FRAMING - LEED DATA Description: PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 08773 | Forwarded | For Review | 2020-06-19 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-26 | Submittal Number: 09 22 16-2.0 From: TYRONE THORNTON Final Due Date: 07/03/20 Subject: NON-STRUCTURAL METAL FRAMING - LEED DATA Description: PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 09216 | Responded and Closed | Approved | 2020-07-08 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-19 |  | 09 21 16 Non-Structural Metal Framing - LEED Submittal_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-19 |  | 09 21 16 Non-Structural Metal Framing - LEED Submittal_MAM Reviewed.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-08 02:00 |  | 09 21 16 Non-Structural Metal Framing - LEED Submittal_MAM Reviewed_pop.pdf
09 22 16-003-00 | 09 22 16 - NON-STRUCTURAL METAL FRAMING | 09 22 16-003-00 NON-STRUCTURAL METAL FRAMING - Product Data Z-Furring | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-13 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-27 | 2020-07-15 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06921 | Received | For Review | 2020-07-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-07-27 | Submittal Number: 09 22 16-3.0 From: TYRONE THORNTON Final Due Date: 07/15/20 Subject: NON-STRUCTURAL METAL FRAMING - PRODUCT DATA Z-FURRING Description: EVALUATION REPORTS : FOR FIRESTOP TRACKS, FROM ICC-ES. Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 09263 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-20 | Submittal Number: 09 22 16-3.0 From: TYRONE THORNTON Final Due Date: 07/15/20 Subject: NON-STRUCTURAL METAL FRAMING - PRODUCT DATA Z-FURRING Description: EVALUATION REPORTS : FOR FIRESTOP TRACKS, FROM ICC-ES. Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 09330 | Responded and Closed | Approved | 2020-07-15 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | APPROVED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 092216-0003-0 Non-Structural Metal Framing Product Data Z Furring-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 092216-0003-0 Non-Structural Metal Framing Product Data Z Furring-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-07-15 |  | 092216-0003-0 Non-Structural Metal Framing Product Data Z Furring-MAM-pop.pdf
09 22 16-004-00 | 09 22 16 - NON-STRUCTURAL METAL FRAMING | 09 22 16-004-00 NON-STRUCTURAL METAL FRAMING - Shop Drawings & Calculations | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-28 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-12 | 2020-05-04 | 7 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05576 | Received | For Review | 2020-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-05-12 | Submittal Number: 09 22 16-4.0 From: YE ZHANG Final Due Date: 05/11/20 Subject: NON-STRUCTURAL METAL FRAMING - SHOP DRAWINGS & CALCULATIONS Description: Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 07563 | Forwarded | For Review | 2020-04-27 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-04 | Submittal Number: 09 22 16-4.0 From: YE ZHANG Final Due Date: 05/11/20 Subject: NON-STRUCTURAL METAL FRAMING - SHOP DRAWINGS & CALCULATIONS Description: Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 07714 | Responded and Closed | Approved | 2020-05-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-27 |  | 092216-0004-0 Non-Structural Metal Framing Shop Drawings Calcs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-27 |  | 092216-0004-0 Non-Structural Metal Framing Shop Drawings Calcs-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-05-04 |  | 092216-0004-0 Non-Structural Metal Framing Shop Drawings Calcs-MAM-POP.pdf
09 22 16-006-00 | 09 22 16 - NON-STRUCTURAL METAL FRAMING | 09 22 16-006-00 NON-STRUCTURAL METAL FRAMING - LEED Data_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-22 | Responded and Closed - Approved |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-05 | 2020-08-17 | 27 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2020-08-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07090 | Received | For Review | 2020-07-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-05 | Submittal Number: 09 22 16-6.0 From: TYRONE THORNTON Final Due Date: 08/07/20 Subject: NON-STRUCTURAL METAL FRAMING - LEED DATA_PCI Description: Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 09476 | Forwarded | For Review | 2020-07-22 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-07-29 | Submittal Number: 09 22 16-6.0 From: TYRONE THORNTON Final Due Date: 08/07/20 Subject: NON-STRUCTURAL METAL FRAMING - LEED DATA_PCI Description: Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 10102 | Responded and Closed | Approved | 2020-08-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED SUBMITTAL | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-22 |  | PCI Material Submittal 09 21 16 Non Structural Metal Framing - LEED_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-22 |  | PCI Material Submittal 09 21 16 Non Structural Metal Framing - LEED_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-14 02:00 |  | PCI Material Submittal 09 21 16 Non Structural Metal Framing - LEED_MAM Review_POP.pdf
09 22 16-007-02 | 09 22 16 - NON-STRUCTURAL METAL FRAMING | 09 22 16-007-02 NON-STRUCTURAL METAL FRAMING -Product Data_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-28 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-11 | 2020-08-17 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-08-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07192 | Received | For Review | 2020-07-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-11 | Submittal Number: 09 22 16-7.2 From: TYRONE THORNTON Final Due Date: 08/12/20 Subject: NON-STRUCTURAL METAL FRAMING -PRODUCT DATA_PCI Description: Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 09595 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-08-04 | Submittal Number: 09 22 16-7.2 From: TYRONE THORNTON Final Due Date: 08/12/20 Subject: NON-STRUCTURAL METAL FRAMING -PRODUCT DATA_PCI Description: Spec Section: 09 22 16 - NON-STRUCTURAL METAL FRAMING Status: OPEN | Info Exchange
| 10101 | Responded and Closed | Approved as Noted | 2020-08-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED SUBMITTAL | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-28 |  | PCI Material Submittal 09 22 16 Non Structural Metal Framing - PRODUCT DATA_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-28 |  | PCI Material Submittal 09 22 16 Non Structural Metal Framing - PRODUCT DATA_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-17 02:00 |  | PCI Material Submittal 09 22 16 Non Structural Metal Framing - PRODUCT DATA_MAM Review_POP.pdf
09 26 13-001-00 | 09 26 13 | 09 26 13-001-00 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-03-01 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11410 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-03-01 | Submittal Number: 09 26 13-1.0 From: ALLIE ZIMMERMAN Final Due Date: 03/01/21 Subject: GYPSUM VENEER PLASTERING - SF9 VENETIAN PLASTER SAMPLE Description: Spec Section: 09 26 13 - GYPSUM VENEER PLASTERING Status: OPEN | Info Exchange
| 14777 | Forwarded | For Review | 2021-02-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 09 26 13-1.0 From: ALLIE ZIMMERMAN Final Due Date: 03/01/21 Subject: GYPSUM VENEER PLASTERING - SF9 VENETIAN PLASTER SAMPLE Description: Spec Section: 09 26 13 - GYPSUM VENEER PLASTERING Status: OPEN | Info Exchange
| 11699 | Review Response | Approved as Noted | 2021-03-01 | Kuebler Perry (Populous) | Kuebler Perry (Populous) |  | Refer to attached submittal response. Confirm finish intent with Rockwell. | Info Exchange
| 15156 | Responded and Closed | Approved as Noted | 2021-03-01 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. Confirm finish intent with Rockwell. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | Submittal 09 26 13-1 Revision 0 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-15 |  | Submittal 09 26 13-1 Revision 0 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-01 |  | Submittal 09 26 13-1 Revision 0 GYPSUM VENEER PLASTERING - SF9 POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-15 |  | Submittal 09 26 13-1 Revision 0 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample.pdf
09 26 13-001-01 | 09 26 13 | 09 26 13-001-01 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-11 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-25 | 2021-04-06 | 27 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2021-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11948 | Received | For Review | 2021-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-03-25 | Submittal Number: 09 26 13-1.1 From: ALLIE ZIMMERMAN Final Due Date: 03/24/21 Subject: GYPSUM VENEER PLASTERING - SF9 VENETIAN PLASTER SAMPLE Description: Spec Section: 09 26 13 - GYPSUM VENEER PLASTERING Status: OPEN | Info Exchange
| 15471 | Forwarded | For Review | 2021-03-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-18 | Submittal Number: 09 26 13-1.1 From: ALLIE ZIMMERMAN Final Due Date: 03/24/21 Subject: GYPSUM VENEER PLASTERING - SF9 VENETIAN PLASTER SAMPLE Description: Spec Section: 09 26 13 - GYPSUM VENEER PLASTERING Status: OPEN | Info Exchange
| 12416 | Review Response | Approved | 2021-04-06 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16088 | Responded and Closed | Approved | 2021-04-06 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-10 |  | Submittal 09 26 13-1 Revision 1 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-10 |  | Submittal 09 26 13-1 Revision 1 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-26 |  | Submittal 09 26 13-1 Revision 2 GYPSUM VENEER PLASTERING - SF9 _ POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-03-10 |  | Submittal 09 26 13-1 Revision 1 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample_MAM Reviewed.pdf
09 26 13-001-02 | 09 26 13 | 09 26 13-001-02 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-25 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-08 | 2021-03-26 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12236 | Received | For Review | 2021-03-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-04-08 | Submittal Number: 09 26 13-1.2 From: ALLIE ZIMMERMAN Final Due Date: 04/08/21 Subject: GYPSUM VENEER PLASTERING - SF9 VENETIAN PLASTER SAMPLE Description: Spec Section: 09 26 13 - GYPSUM VENEER PLASTERING Status: OPEN | Info Exchange
| 15826 | Forwarded | For Review | 2021-03-25 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-01 | Submittal Number: 09 26 13-1.2 From: ALLIE ZIMMERMAN Final Due Date: 04/08/21 Subject: GYPSUM VENEER PLASTERING - SF9 VENETIAN PLASTER SAMPLE Description: Spec Section: 09 26 13 - GYPSUM VENEER PLASTERING Status: OPEN | Info Exchange
| 12267 | Review Response | Approved | 2021-03-26 | Kuebler Perry (Populous) | Kuebler Perry (Populous) |  | Refer to attached submittal response. Confirm Rockwell approval for final selection. | Info Exchange
| 15866 | Responded and Closed | Approved | 2021-03-26 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. Confirm Rockwell approval for final selection. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-25 |  | Submittal 09 26 13-1 Revision 2 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-25 |  | Submittal 09 26 13-1 Revision 2 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-26 |  | Submittal 09 26 13-1 Revision 2 GYPSUM VENEER PLASTERING - SF9 _ POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-03-25 |  | Submittal 09 26 13-1 Revision 2 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Sample_MAM Reviewed.pdf
09 26 13-002-00 | 09 26 13 | 09 26 13-002-00 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 | 2021-04-27 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12487 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-04-22 | Submittal Number: 09 26 13-2.0 From: ALLIE ZIMMERMAN Final Due Date: 04/22/21 Subject: GYPSUM VENEER PLASTERING - SF9 VENETIAN PLASTER PRODUCT DATA Description: Spec Section: 09 26 13 - GYPSUM VENEER PLASTERING Status: OPEN | Info Exchange
| 16177 | Forwarded | For Review | 2021-04-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 09 26 13-2.0 From: ALLIE ZIMMERMAN Final Due Date: 04/22/21 Subject: GYPSUM VENEER PLASTERING - SF9 VENETIAN PLASTER PRODUCT DATA Description: Spec Section: 09 26 13 - GYPSUM VENEER PLASTERING Status: OPEN | Info Exchange
| 12799 | Review Response | Approved | 2021-04-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16543 | Responded and Closed | Approved | 2021-04-27 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | Submittal 09 26 13-2 Revision 0 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Product Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-08 |  | Submittal 09 26 13-2 Revision 0 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Product Data_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-27 |  | 09 72 00-19 Revision 0 Wallcovering Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-08 |  | Submittal 09 26 13-2 Revision 0 GYPSUM VENEER PLASTERING - SF9 Venetian Plaster Product Data_MAM Reviewed.pdf
09 27 13-001-00 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-001-00 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Product Data & Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-04 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-18 | 2020-05-12 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05690 | Received | For Review | 2020-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-05-18 | Submittal Number: 09 27 13-1.0 From: TYRONE THORNTON Final Due Date: 05/18/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - PRODUCT DATA & SHOP DRAWINGS Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, WEIGHTS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 07701 | Forwarded | For Review | 2020-05-04 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-05-11 | Submittal Number: 09 27 13-1.0 From: TYRONE THORNTON Final Due Date: 05/18/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - PRODUCT DATA & SHOP DRAWINGS Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, WEIGHTS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 05841 | Review Response | Revise and Resubmit | 2020-05-12 | Kuebler Perry (Populous) | Josh Dobken (Populous) |  | See attached. | Info Exchange
| 07925 | Responded and Closed | Revise and Resubmit | 2020-05-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kuebler Perry (Populous) Remarks: See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-04 |  | 092713-0001-0 GFRG Product Data and Shop Drawings-MAM.PDF
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-04 |  | 092713-0001-0 GFRG Product Data and Shop Drawings-MAM.PDF
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-05-12 02:00 |  | 092713-0001-0 GFRG Product Data and Shop Drawings-MAM_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-03 02:00 |  | 092713-0001-0 GFRG Product Data and Shop Drawings-MAM.PDF
09 27 13-001-01 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-001-01 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Product Data & Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-30 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-15 07:00 | 2020-08-05 | 37 |  | Record Copies; Transfers; Submittals |  | 37 |  | 2020-08-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06671 | Received | For Review | 2020-06-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-07-15 07:00 | Submittal Number: 09 27 13-1.1 From: TYRONE THORNTON Final Due Date: 07/13/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - PRODUCT DATA & SHOP DRAWINGS Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, WEIGHTS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 08985 | Forwarded | For Review | 2020-06-30 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-07 | Submittal Number: 09 27 13-1.1 From: TYRONE THORNTON Final Due Date: 07/13/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - PRODUCT DATA & SHOP DRAWINGS Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, WEIGHTS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 07378 | Review Response | Approved as Noted/Resubmit | 2020-08-05 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached markup. | Info Exchange
| 09830 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached markup. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-29 |  | 092713-0001-1 GFRG Product Data and Shop Drawings-MAM-Rev1.PDF
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-29 |  | 092713-0001-1 GFRG Product Data and Shop Drawings-MAM-Rev1.PDF
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-05 |  | 092713-0001-1 GFRG Product Data and Shop Drawings-MAM-Rev1_POP_Final.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-06-29 |  | 092713-0001-1 GFRG Product Data and Shop Drawings-MAM-Rev1.PDF
09 27 13-001-02 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-001-02 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Product Data & Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-25 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-11 | 2020-12-13 | 19 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-12-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09756 | Received | For Review | 2020-11-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-11 | Submittal Number: 09 27 13-1.2 From: YE ZHANG Final Due Date: 12/09/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - PRODUCT DATA & SHOP DRAWINGS Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, WEIGHTS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 12824 | Forwarded | For Review | 2020-11-30 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-07 | Submittal Number: 09 27 13-1.2 From: YE ZHANG Final Due Date: 12/09/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - PRODUCT DATA & SHOP DRAWINGS Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, WEIGHTS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 10114 | Review Response | Revise and Resubmit | 2020-12-13 | Kuebler Perry (Populous) | Populous SCA_CCA |  | 1. Several type quantities don't match the schedule, please confirm column types and locations 2. Provide codes for the added letters at each column type, such as 10-E2 or 13-AE1 etc. 3. Comments not picked-up from last review. | Info Exchange
| 13223 | Responded and Closed | Revise and Resubmit | 2020-12-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. Several type quantities don't match the schedule, please confirm column types and locations 2. Provide codes for the added letters at each column type, such as 10-E2 or 13-AE1 etc. 3. Comments not picked-up from last review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-25 |  | 092713-0001-2 GFRG Product Data and Shop Drawings-MAM-Rev2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-25 |  | 092713-0001-2 GFRG Product Data and Shop Drawings-MAM-Rev2.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-13 |  | 092713-0001-2 GFRG Product Data and Shop Drawings-MAM-Rev2_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-25 |  | 092713-0001-2 GFRG Product Data and Shop Drawings-MAM-Rev2.pdf
09 27 13-001-03 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-001-03 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Shop Drawings for Main Concourse | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-11 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-25 | 2021-02-25 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11330 | Received | For Review | 2021-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-02-25 | Submittal Number: 09 27 13-1.3 From: YE ZHANG Final Due Date: 02/24/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SHOP DRAWINGS FOR MAIN CONCOURSE Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, WEIGHTS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 14689 | Forwarded | For Review | 2021-02-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-18 | Submittal Number: 09 27 13-1.3 From: YE ZHANG Final Due Date: 02/24/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SHOP DRAWINGS FOR MAIN CONCOURSE Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, WEIGHTS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 11666 | Review Response | Approved as Noted | 2021-02-25 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 15118 | Responded and Closed | Approved as Noted | 2021-02-25 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-10 |  | 092713-0001-3 GFRG Shop Drawings Main Con-MAM-Rev3.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-10 |  | 092713-0001-3 GFRG Shop Drawings Main Con-MAM-Rev3.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-25 |  | 092713-0001-3 GFRG Shop Drawings Main Con-MAM-Rev3_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-10 |  | 092713-0001-3 GFRG Shop Drawings Main Con-MAM-Rev3.pdf
09 27 13-001-04 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-001-04 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Shop Drawings for Upper Concourse | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-24 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-09 07:00 | 2021-07-08 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13637 | Received | For Review | 2021-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-09 07:00 | Submittal Number: 09 27 13-1.4 From: YE ZHANG Final Due Date: 07/02/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SHOP DRAWINGS FOR UPPER CONCOURSE Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, WEIGHTS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 17661 | Forwarded | For Review | 2021-06-24 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-01 | Submittal Number: 09 27 13-1.4 From: YE ZHANG Final Due Date: 07/02/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SHOP DRAWINGS FOR UPPER CONCOURSE Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, WEIGHTS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 13866 | Review Response | Approved | 2021-07-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17943 | Responded and Closed | Approved | 2021-07-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-24 |  | 092713-0001-4 GFRG Shop Drawings Upper Con-MAM-Rev4.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-24 |  | 092713-0001-4 GFRG Shop Drawings Upper Con-MAM-Rev4.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-08 |  | 092713-0001-4 GFRG Shop Drawings Upper Con-MAM-Rev4-0708_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-24 |  | 092713-0001-4 GFRG Shop Drawings Upper Con-MAM-Rev4.pdf
09 27 13-002-00 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-002-00 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Mock-Up Shop Drawing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-13 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-01 08:00 | 2020-11-20 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09417 | Received | For Review | 2020-11-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-12-01 08:00 | Submittal Number: 09 27 13-2.0 From: YE ZHANG Final Due Date: 11/26/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - MOCK-UP SHOP DRAWING Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 12421 | Forwarded | For Review | 2020-11-13 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-20 | Submittal Number: 09 27 13-2.0 From: YE ZHANG Final Due Date: 11/26/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - MOCK-UP SHOP DRAWING Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 09635 | Review Response | Approved | 2020-11-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | See attached submittal review. | Info Exchange
| 12679 | Responded and Closed | Approved | 2020-11-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-12 |  | 092713-0002-0 GFRG Mockup Shop-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-12 |  | 092713-0002-0 GFRG Mockup Shop-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-20 |  | 092713-0002-0 GFRG Mockup Shop-MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-12 |  | 092713-0002-0 GFRG Mockup Shop-MAM.pdf
09 27 13-004-00 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-004-00 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Mockups (For Record) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-10 | Responded and Closed - Not Required For Review |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-24 | 2021-02-23 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-02-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11317 | Received | For Review | 2021-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ye Zhang (Mortenson Construction) | 2021-02-24 | Submittal Number: 09 27 13-4.0 From: YE ZHANG Final Due Date: 02/24/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - MOCKUPS (FOR RECORD) Description: MOCKUPS : BUILD MOCKUPS TO SET QUALITY STANDARDS FOR FABRICATION AND INSTALLATION. 1. BUILD MOCKUP OF EACH TYPE OF GLASS-FIBER-REINFORCED GYPSUM FABRICATION. 2. PAINT MOCKUPS TO MATCH FINAL DECORATION SCHEDULED OR INDICATED AND TO COMPLY WITH REQUIREMENTS SPECIFIED SECTION 09 96 00 HIGH PERFORMANCE COATINGS AND SECTION 09 91 23 "INTERIOR PAINTING." 3. APPROVAL OF MOCKUPS DOES NOT CONSTITUTE APPROVAL OF DEVIATIONS FROM THE CONTRACT DOCUMENTS CONTAINED IN MOCKUPS UNLESS ARCHITECT SPECIFICALLY APPROVES SUCH DEVIATIONS IN WRITING. 4. SUBJECT TO COMPLIANCE WITH REQUIREMENTS, APPROVED MOCKUPS MAY BECOME PART OF THE COMPLETED WORK IF UNDISTURBED AT TIME OF SUBSTANTIAL COMPLETION. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 14672 | Forwarded | For Review | 2021-02-10 | Ye Zhang (Mortenson Construction) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-17 | Submittal Number: 09 27 13-4.0 From: YE ZHANG Final Due Date: 02/24/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - MOCKUPS (FOR RECORD) Description: MOCKUPS : BUILD MOCKUPS TO SET QUALITY STANDARDS FOR FABRICATION AND INSTALLATION. 1. BUILD MOCKUP OF EACH TYPE OF GLASS-FIBER-REINFORCED GYPSUM FABRICATION. 2. PAINT MOCKUPS TO MATCH FINAL DECORATION SCHEDULED OR INDICATED AND TO COMPLY WITH REQUIREMENTS SPECIFIED SECTION 09 96 00 HIGH PERFORMANCE COATINGS AND SECTION 09 91 23 "INTERIOR PAINTING." 3. APPROVAL OF MOCKUPS DOES NOT CONSTITUTE APPROVAL OF DEVIATIONS FROM THE CONTRACT DOCUMENTS CONTAINED IN MOCKUPS UNLESS ARCHITECT SPECIFICALLY APPROVES SUCH DEVIATIONS IN WRITING. 4. SUBJECT TO COMPLIANCE WITH REQUIREMENTS, APPROVED MOCKUPS MAY BECOME PART OF THE COMPLETED WORK IF UNDISTURBED AT TIME OF SUBSTANTIAL COMPLETION. Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 11607 | Review Response | Not Required For Review | 2021-02-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to site visit 086 notes and attached submittal review. | Info Exchange
| 15044 | Responded and Closed | Not Required For Review | 2021-02-23 | Ye Zhang (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to site visit 086 notes and attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-10 |  | 092713-0004-0 GFRG Mockup-MAM.pdf
| Forwarded |  | Ye Zhang (Mortenson Construction) | 1 | 2021-02-10 |  | 092713-0004-0 GFRG Mockup-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-23 |  | 092713-0004-0 GFRG Mockup-MAM_POP.pdf
| Responded and Closed |  | Ye Zhang (Mortenson Construction) | 1 | 2021-02-10 |  | 092713-0004-0 GFRG Mockup-MAM.pdf
09 27 13-008-00 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-008-00 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Product Data_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-10 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-24 | 2020-08-24 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07469 | Received | For Review | 2020-08-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-24 | Submittal Number: 09 27 13-8.0 From: TYRONE THORNTON Final Due Date: 08/24/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - PRODUCT DATA_PCI Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 09948 | Forwarded | For Review | 2020-08-10 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-17 | Submittal Number: 09 27 13-8.0 From: TYRONE THORNTON Final Due Date: 08/24/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - PRODUCT DATA_PCI Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 07666 | Review Response | Approved | 2020-08-24 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  |  | Info Exchange
| 10210 | Responded and Closed | Approved | 2020-08-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-10 |  | 09 27 13 - Glass Fiber Reinforced Gypsum Fabrications_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-10 |  | 09 27 13 - Glass Fiber Reinforced Gypsum Fabrications_MAM Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-24 |  | 09 27 13-8.0 Glass Fiber Reinforced Gypsum Fabrications_MAM Review_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-10 |  | 09 27 13 - Glass Fiber Reinforced Gypsum Fabrications_MAM Review.pdf
09 27 13-009-00 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-009-00 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Shop Drawings_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-21 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-04 | 2020-09-04 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07649 | Received | For Review | 2020-08-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-04 | Submittal Number: 09 27 13-9.0 From: TYRONE THORNTON Final Due Date: 09/03/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SHOP DRAWINGS_PCI Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 10191 | Forwarded | For Review | 2020-08-20 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-27 | Submittal Number: 09 27 13-9.0 From: TYRONE THORNTON Final Due Date: 09/03/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SHOP DRAWINGS_PCI Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 07924 | Review Response | Revise and Resubmit | 2020-09-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  | This looks like a boilerplate submittal that is barely adapted for our project. The column covers have no relationship to the ceilings and there are only 2 heights shown. GC to review shop drawings prior to submitting to architect. | Info Exchange
| 10540 | Responded and Closed | Revise and Resubmit | 2020-09-04 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | This looks like a boilerplate submittal that is barely adapted for our project. The column covers have no relationship to the ceilings and there are only 2 heights shown. GC to review shop drawings prior to submitting to architect. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | PCI Material Submittal - 09 29 13 - GFRG - Shop Drawings_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-20 |  | PCI Material Submittal - 09 29 13 - GFRG - Shop Drawings_MAM Review.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-04 |  | PCI Material Submittal - 09 29 13 - GFRG - Shop Drawings_MAM Review_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-20 |  | PCI Material Submittal - 09 29 13 - GFRG - Shop Drawings_MAM Review.pdf
09 27 13-009-01 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-009-01 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Shop Drawings_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-14 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-06 | 2021-01-12 | 30 |  | Record Copies; Transfers; Submittals |  | 33 |  | 2021-01-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10111 | Received | For Review | 2020-12-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2021-01-06 | Submittal Number: 09 27 13-9.1 From: ALLIE ZIMMERMAN Final Due Date: 12/28/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SHOP DRAWINGS_PCI Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 13220 | Forwarded | For Review | 2020-12-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-18 | Submittal Number: 09 27 13-9.1 From: ALLIE ZIMMERMAN Final Due Date: 12/28/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SHOP DRAWINGS_PCI Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 10642 | Review Response | Revise and Resubmit | 2021-01-12 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13850 | Responded and Closed | Revise and Resubmit | 2021-01-12 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-11 |  | 092713-0009-1 GFRG Product Data and Shop Drawings Premium-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-11 |  | 092713-0009-1 GFRG Product Data and Shop Drawings Premium-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-12 |  | 092713-0009-1 GFRG Product Data and Shop Drawings Premium-MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-11 |  | 092713-0009-1 GFRG Product Data and Shop Drawings Premium-MAM.pdf
09 27 13-009-02 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-009-02 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Shop Drawings_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-02 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-16 | 2021-03-15 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-03-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11738 | Received | For Review | 2021-03-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-16 | Submittal Number: 09 27 13-9.2 From: YE ZHANG Final Due Date: 01/29/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SHOP DRAWINGS_PCI Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 15210 | Forwarded | For Review | 2021-03-02 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-09 | Submittal Number: 09 27 13-9.2 From: YE ZHANG Final Due Date: 01/29/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SHOP DRAWINGS_PCI Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 12027 | Review Response | Approved as Noted | 2021-03-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15568 | Responded and Closed | Approved as Noted | 2021-03-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-01 |  | 092713-0009-2 GFRG Product Data and Shop Drawings Premium-MAM-Rev2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-01 |  | 092713-0009-2 GFRG Product Data and Shop Drawings Premium-MAM-Rev2.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-15 |  | 092713-0009-2 GFRG Product Data and Shop Drawings Premium-MAM-Rev2_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-01 |  | 092713-0009-2 GFRG Product Data and Shop Drawings Premium-MAM-Rev2.pdf
09 27 13-010-00 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-010-00 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SAMPLES | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-10 07:00 | 2020-09-09 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07750 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-09-10 07:00 | Submittal Number: 09 27 13-10.0 From: TYRONE THORNTON Final Due Date: 09/08/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SAMPLES Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 10319 | Forwarded | For Review | 2020-08-26 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 09 27 13-10.0 From: TYRONE THORNTON Final Due Date: 09/08/20 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SAMPLES Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 10637 | Responded and Closed | Approved | 2020-09-09 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-25 |  | 092713-10_CPA GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SAMPLES_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-25 |  | 092713-10_CPA GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SAMPLES_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-09 02:00 |  | 092713-10_CPA GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - SAMPLES_MAM _POP.pdf
09 27 13-011-00 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-011-00 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-05-26 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13142 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-06-02 07:00 | Submittal Number: 09 27 13-11.0 From: ALLIE ZIMMERMAN Final Due Date: 05/31/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - MAIN CONCOURSE CLUB COLUMN CAP SAMPLES Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 17002 | Forwarded | For Review | 2021-05-18 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-25 | Submittal Number: 09 27 13-11.0 From: ALLIE ZIMMERMAN Final Due Date: 05/31/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - MAIN CONCOURSE CLUB COLUMN CAP SAMPLES Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 13281 | Review Response | Approved | 2021-05-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17185 | Responded and Closed | Approved | 2021-05-26 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | Submittal 09 27 13-11 Revision 0 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Samples_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-17 |  | Submittal 09 27 13-11 Revision 0 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Samples_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-26 |  | Submittal 09 27 13-11 Revision 0 GFRG - Main Concourse Club Column Cap Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-05-17 |  | Submittal 09 27 13-11 Revision 0 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Samples_MAM Reviewed.pdf
09 27 13-012-00 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-012-00 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-03 07:00 | 2021-06-04 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13177 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-03 07:00 | Submittal Number: 09 27 13-12.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - MAIN CONCOURSE CLUB COLUMN CAP SHOP DRAWINGS Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 17064 | Forwarded | For Review | 2021-05-19 | Allie Zimmerman | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-26 | Submittal Number: 09 27 13-12.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - MAIN CONCOURSE CLUB COLUMN CAP SHOP DRAWINGS Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 13403 | Review Response | Approved as Noted | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17336 | Responded and Closed | Approved as Noted | 2021-06-04 | Allie Zimmerman | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 09 27 13-12 Revision 0 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 09 27 13-12 Revision 0 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-04 |  | Submittal 09 27 13-12 Revision 0 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Shop Drawings_POP.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 09 27 13-12 Revision 0 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Shop Drawings_MAM Reviewed.pdf
09 27 13-012-01 | 09 27 13 - GLASS-FIBER-REINFORCED PLASTER FABRICATIONS | 09 27 13-012-01 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-24 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-08 | 2021-07-01 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-07-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13639 | Received | For Review | 2021-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-07-08 | Submittal Number: 09 27 13-12.1 From: ALLIE ZIMMERMAN Final Due Date: 07/08/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - MAIN CONCOURSE CLUB COLUMN CAP SHOP DRAWINGS Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS Status: OPEN | Info Exchange
| 17662 | Forwarded | For Review | 2021-06-24 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-01 | Submittal Number: 09 27 13-12.1 From: ALLIE ZIMMERMAN Final Due Date: 07/08/21 Subject: GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - MAIN CONCOURSE CLUB COLUMN CAP SHOP DRAWINGS atus: OPEN Description: Spec Section: 09 27 13 - GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS St | Info Exchange
| 17792 | Responded and Closed | Approved as Noted | 2021-07-01 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-24 |  | Submittal 09 27 13-12 Revision 1 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-24 |  | Submittal 09 27 13-12 Revision 1 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Shop Drawings_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-01 |  | Submittal 09 27 13-12 Revision 1 GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Main Concourse Club Column Cap Shop Drawings_MAM Reviewed_POP.pdf
09 29 00-001-00 | 09 29 00 - GYPSUM BOARD | 09 29 00-001-00 Gypsum Board Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-09 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-04-23 | 2020-04-23 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-04-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05261 | Received | For Review | 2020-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-04-23 | Submittal Number: 09 29 00-0001.0 From: YE ZHANG Final Due Date: 04/22/20 Subject: GYPSUM BOARD PRODUCT DATA Description: 09 29 00 - GYPSUM BOARD PRODUCT DATA 2.3 INTERIOR GYPSUM BOARD 2.4 TILE BACKING PANELS 2.5 TRIM ACCESSORIES 2.6 JOINT TREATMENT MATERIALS (EXCLUDING 2.6D AND 2.6E WHICH WILL BE SUBMITTED AFTER COORDINATION WITH THE TILE SUBCONTRACTOR) 2.7 AUXILIARY MATERIALS (EXCLUDING ACOUSTICAL JOINT SEALANT) Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 07154 | Forwarded | For Review | 2020-04-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-04-15 | Submittal Number: 09 29 00-0001.0 From: YE ZHANG Final Due Date: 04/22/20 Subject: GYPSUM BOARD PRODUCT DATA Description: 09 29 00 - GYPSUM BOARD PRODUCT DATA 2.3 INTERIOR GYPSUM BOARD 2.4 TILE BACKING PANELS 2.5 TRIM ACCESSORIES 2.6 JOINT TREATMENT MATERIALS (EXCLUDING 2.6D AND 2.6E WHICH WILL BE SUBMITTED AFTER COORDINATION WITH THE TILE SUBCONTRACTOR) 2.7 AUXILIARY MATERIALS (EXCLUDING ACOUSTICAL JOINT SEALANT) Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 07493 | Responded and Closed | Approved as Noted | 2020-04-23 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (M.A. Mortenson Company) |  | See attached submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-08 |  | 092900-0001-0 Gypsum Board Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-08 |  | 092900-0001-0 Gypsum Board Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-23 02:00 |  | 092900-0001-0 Gypsum Board Product Data-MAM_POP.pdf
09 29 00-002-00 | 09 29 00 - GYPSUM BOARD | 09 29 00-002-00 Gypsum Board Product Data - Tile Backing Panels & Fire Rated Expansion Joint | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-20 | Responded and Closed - Approved |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-04 | 2020-05-04 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05440 | Received | For Review | 2020-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-05-04 | Submittal Number: 09 29 00-0002.0 From: TYRONE THORNTON Final Due Date: 05/04/20 Subject: GYPSUM BOARD PRODUCT DATA - TILE BACKING PANELS & FIRE RATED EXPANSION JOINT Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 07382 | Forwarded | For Review | 2020-04-20 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-04-27 | Submittal Number: 09 29 00-0002.0 From: TYRONE THORNTON Final Due Date: 05/04/20 Subject: GYPSUM BOARD PRODUCT DATA - TILE BACKING PANELS & FIRE RATED EXPANSION JOINT Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 07710 | Responded and Closed | Approved | 2020-05-04 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-20 |  | 092900-0002-0 Gypsum Board Product Data-Tile Backing Panels & Fire Rated Expansion Joint-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-20 |  | 092900-0002-0 Gypsum Board Product Data-Tile Backing Panels & Fire Rated Expansion Joint-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-04-20 |  | 092900-0002-0 Gypsum Board Product Data-Tile Backing Panels & Fire Rated Expansion Joint-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-05-04 |  | 092900-0002-0 Gypsum Board Product Data-Tile Backing Panels & Fire Rated Expansion Joint-MAM-POP.pdf
09 29 00-004-00 | 09 29 00 - GYPSUM BOARD | 09 29 00-004-00 GYPSUM BOARD - Product Data LEED | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-02 | 2020-07-08 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06489 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 09 29 00-4.0 From: TYRONE THORNTON Final Due Date: 07/01/20 Subject: GYPSUM BOARD - PRODUCT DATA LEED Description: PRODUCT DATA: FOR ADHESIVES AND SEALANTS, INDICATING VOC CONTENT. PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 08741 | Forwarded | For Review | 2020-06-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-25 | Submittal Number: 09 29 00-4.0 From: TYRONE THORNTON Final Due Date: 07/01/20 Subject: GYPSUM BOARD - PRODUCT DATA LEED Description: PRODUCT DATA: FOR ADHESIVES AND SEALANTS, INDICATING VOC CONTENT. PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 09189 | Responded and Closed | Approved as Noted | 2020-07-08 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 09 29 00 GYPSUM BOARD - LEED Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 09 29 00 GYPSUM BOARD - LEED Data.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-08 |  | 09 29 00 GYPSUM BOARD - LEED Data_POP.pdf
09 29 00-005-00 | 09 29 00 - GYPSUM BOARD | 09 29 00-005-00 Gypsum Board Product Data - Steel Drill Screws | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-14 | Responded and Closed - Approved |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-28 | 2020-08-20 | 7 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07538 | Received | For Review | 2020-08-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-08-28 | Submittal Number: 09 29 00-5.0 From: TYRONE THORNTON Final Due Date: 08/27/20 Subject: GYPSUM BOARD PRODUCT DATA - STEEL DRILL SCREWS Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 10038 | Forwarded | For Review | 2020-08-13 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-20 | Submittal Number: 09 29 00-5.0 From: TYRONE THORNTON Final Due Date: 08/27/20 Subject: GYPSUM BOARD PRODUCT DATA - STEEL DRILL SCREWS Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 10166 | Responded and Closed | Approved | 2020-08-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-13 |  | 092900-0005-0 Gypsum Board Product Data Steel Drill Screws-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-13 |  | 092900-0005-0 Gypsum Board Product Data Steel Drill Screws-MAM.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-20 |  | 092900-0005-0 Gypsum Board Product Data Steel Drill Screws-MAM_POP.pdf
09 29 00-007-01 | 09 29 00 - GYPSUM BOARD | 09 29 00-007-01 GYPSUM BOARD - Product Data_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-28 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-11 | 2020-08-05 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-08-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07193 | Received | For Review | 2020-07-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-11 | Submittal Number: 09 29 00-7.1 From: TYRONE THORNTON Final Due Date: 08/12/20 Subject: GYPSUM BOARD - PRODUCT DATA_PCI Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 09596 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-08-04 | Submittal Number: 09 29 00-7.1 From: TYRONE THORNTON Final Due Date: 08/12/20 Subject: GYPSUM BOARD - PRODUCT DATA_PCI Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 07384 | Review Response | Approved as Noted | 2020-08-05 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached markup. | Info Exchange
| 09839 | Responded and Closed | Approved as Noted | 2020-08-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached markup. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-28 |  | PCI Material Submittal 09 29 00 Gypsum Board Wall Assemblies PRODUCT DATA.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-28 |  | PCI Material Submittal 09 29 00 Gypsum Board Wall Assemblies PRODUCT DATA.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-05 |  | PCI Material Submittal 09 29 00 Gypsum Board Wall Assemblies PRODUCT DATA_POP FINAL.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-28 |  | PCI Material Submittal 09 29 00 Gypsum Board Wall Assemblies PRODUCT DATA.pdf
09 29 00-008-00 | 09 29 00 - GYPSUM BOARD | 09 29 00-008-00 GYPSUM BOARD - Product Data LEED_PCI | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-21 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-04 | 2020-08-12 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-08-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07077 | Received | For Review | 2020-07-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-08-04 | Submittal Number: 09 29 00-8.0 From: TYRONE THORNTON Final Due Date: 08/04/20 Subject: GYPSUM BOARD - PRODUCT DATA LEED_PCI Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 09467 | Forwarded | For Review | 2020-07-21 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-07-28 | Submittal Number: 09 29 00-8.0 From: TYRONE THORNTON Final Due Date: 08/04/20 Subject: GYPSUM BOARD - PRODUCT DATA LEED_PCI Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 10022 | Responded and Closed | Approved as Noted | 2020-08-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-21 |  | PCI Material Submittal - 09 29 00 - Gypsum Board Shaft Walls - LEED_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-21 |  | PCI Material Submittal - 09 29 00 - Gypsum Board Shaft Walls - LEED_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-12 |  | PCI Material Submittal - 09 29 00 - Gypsum Board Shaft Walls - LEED_MAM_POP.pdf
09 29 00-009-00 | 09 29 00 - GYPSUM BOARD | 09 29 00-009-00 GYPSUM BOARD - Product Data - Acoustical Joint Sealant | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-08 | Responded and Closed - Revise and Resubmit | [5 empty] | 2020-10-22 | 2020-10-09 | 2 |  | Record Copies; Transfers; Submittals | 09 29 00-009-01 - 09 29 00-009-00 GYPSUM BOARD - Product Data - Acoustical Joint Sealant | -1 |  | 2020-10-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08687 | Received | For Review | 2020-10-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (M.A. Mortenson Company) | 2020-10-22 | Submittal Number: 09 29 00-9.0 From: YE ZHANG Final Due Date: 10/22/20 Subject: GYPSUM BOARD - PRODUCT DATA - ACOUSTICAL JOINT SEALANT Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 11474 | Responded and Closed | Revise and Resubmit | 2020-10-09 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (M.A. Mortenson Company) |  | Provide VOC content for product. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-08 02:00 |  | 092900-09 GypBoardPDAcousticalJointSealant-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-09 02:00 |  | 092900-09 GypBoardPDAcousticalJointSealant-MAM_POP.pdf
09 29 00-009-01 | 09 29 00 - GYPSUM BOARD | 09 29 00-009-00 GYPSUM BOARD - Product Data - Acoustical Joint Sealant | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 29 00-009-00 - 09 29 00-009-00 GYPSUM BOARD - Product Data - Acoustical Joint Sealant | -1 | 2020-10-23
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-09 02:00 |  | 092900-09 GypBoardPDAcousticalJointSealant-MAM_POP.pdf
09 29 00-010-00 | 09 29 00 - GYPSUM BOARD | 09 29 00-010-00 GYPSUM BOARD - Alternative Product - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-01 08:00 | 2021-02-10 | 27 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2021-02-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10741 | Received | For Review | 2021-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-02-01 08:00 | Submittal Number: 09 29 00-10.0 From: ALLIE ZIMMERMAN Final Due Date: 02/26/21 Subject: GYPSUM BOARD - ALTERNATIVE PRODUCT - PRODUCT DATA Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 13969 | Forwarded | For Review | 2021-01-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-22 | Submittal Number: 09 29 00-10.0 From: ALLIE ZIMMERMAN Final Due Date: 02/26/21 Subject: GYPSUM BOARD - ALTERNATIVE PRODUCT - PRODUCT DATA Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 14670 | Responded and Closed | Approved as Noted | 2021-02-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | APPROVAL IS CONTINGENT ON COMMENTS IN 09 29 00-011-00 (LEED PRODUCT DATA) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-15 |  | Submittal 09 29 00_10 Revision 0 GYPSUM BOARD _ Alternative Product _ Product Data _ MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-15 |  | Submittal 09 29 00_10 Revision 0 GYPSUM BOARD _ Alternative Product _ Product Data _ MAM Reviewed.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-10 02:00 |  | Submittal 09 29 00_10 Revision 0 GYPSUM BOARD _ Alternative Product _ Product Data _ MAM Reviewed_POP.pdf
09 29 00-011-00 | 09 29 00 - GYPSUM BOARD | 09 29 00-011-00 GYPSUM BOARD - Alternative Product - LEED Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-08 | 2021-02-10 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10933 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-02-08 | Submittal Number: 09 29 00-11.0 From: ALLIE ZIMMERMAN Final Due Date: 02/08/21 Subject: GYPSUM BOARD - ALTERNATIVE PRODUCT - LEED DATA Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 14194 | Forwarded | For Review | 2021-01-25 | Allie Zimmerman | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-01 | Submittal Number: 09 29 00-11.0 From: ALLIE ZIMMERMAN Final Due Date: 02/08/21 Subject: GYPSUM BOARD - ALTERNATIVE PRODUCT - LEED DATA Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 14671 | Responded and Closed | Approved as Noted | 2021-02-10 | Allie Zimmerman | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | MORTENSON TO CONFIRM RECYCLED CONTENT WILL NOT IMPACT LEED SCORE. SEE PAGE 2 FOR COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | Submittal 09 29 00-11 Revision 0 GYPSUM BOARD - Alternative Product - LEED Data_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-01-25 |  | Submittal 09 29 00-11 Revision 0 GYPSUM BOARD - Alternative Product - LEED Data_MAM Reviewed.pdf
| Responded and Closed |  | Allie Zimmerman | 1 | 2021-02-10 02:00 |  | Submittal 09 29 00-11 Revision 0 GYPSUM BOARD - Alternative Product - LEED Data_MAM Reviewed_POP.pdf
09 29 00-012-00 | 09 29 00 - GYPSUM BOARD | 09 29 00-012-00 GYPSUM BOARD - Aluminum Knife Edge Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 | 2021-04-27 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12464 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-04-22 | Submittal Number: 09 29 00-12.0 From: ALLIE ZIMMERMAN Final Due Date: 04/15/21 Subject: GYPSUM BOARD - ALUMINUM KNIFE EDGE PRODUCT DATA Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 16154 | Forwarded | For Review | 2021-04-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 09 29 00-12.0 From: ALLIE ZIMMERMAN Final Due Date: 04/15/21 Subject: GYPSUM BOARD - ALUMINUM KNIFE EDGE PRODUCT DATA Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 12796 | Review Response | Approved | 2021-04-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16539 | Responded and Closed | Approved | 2021-04-27 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | Submittal 09 29 00-12 Revision 0 GYPSUM BOARD - Aluminum Knife Edge Product Data_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-08 |  | Submittal 09 29 00-12 Revision 0 GYPSUM BOARD - Aluminum Knife Edge Product Data_MAM Reviewed.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-27 |  | Submittal 09 29 00-12 Revision 0 GYPSUM BOARD - Aluminum Knife Edge Product Data_MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-08 |  | Submittal 09 29 00-12 Revision 0 GYPSUM BOARD - Aluminum Knife Edge Product Data_MAM Reviewed.pdf
09 29 00-013-00 | 09 29 00 - GYPSUM BOARD | 09 29 00-013-00 GYPSUM BOARD - Alternative Product - Extreme Abuse & Extreme Impact Boards | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-02 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-19 07:00 | 2021-07-07 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13778 | Received | For Review | 2021-07-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-07-19 07:00 | Submittal Number: 09 29 00-13.0 From: YE ZHANG Final Due Date: 07/09/21 Subject: GYPSUM BOARD - ALTERNATIVE PRODUCT - EXTREME ABUSE & EXTREME IMPACT BOARDS Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 17833 | Forwarded | For Review | 2021-07-06 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-13 | Submittal Number: 09 29 00-13.0 From: YE ZHANG Final Due Date: 07/09/21 Subject: GYPSUM BOARD - ALTERNATIVE PRODUCT - EXTREME ABUSE & EXTREME IMPACT BOARDS Description: Spec Section: 09 29 00 - GYPSUM BOARD Status: OPEN | Info Exchange
| 17897 | Responded and Closed | Approved | 2021-07-07 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-01 |  | 092900-0013-0 Alternative Product - Extreme Abuse & Extreme Impact Boards-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-01 |  | 092900-0013-0 Alternative Product - Extreme Abuse & Extreme Impact Boards-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-07-07 |  | 092900-0013-0 Alternative Product - Extreme Abuse & Extreme Impact Boards-MAM-POP.pdf
09 30 13-001-00 | 09 30 13 - CERAMIC TILING | 09 30 13-001-00 TILE - Product Data (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-12 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-30 08:00 | 2020-12-02 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09399 | Received | For Review | 2020-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-11-30 08:00 | Submittal Number: 09 30 13-1.0 From: DANIELLE SCOTT Final Due Date: 11/26/20 Subject: TILE - PRODUCT DATA (BASE BUILDING) Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 12402 | Forwarded | For Review | 2020-11-12 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-19 | Submittal Number: 09 30 13-1.0 From: DANIELLE SCOTT Final Due Date: 11/26/20 Subject: TILE - PRODUCT DATA (BASE BUILDING) Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 09821 | Review Response | Approved as Noted/Resubmit | 2020-12-02 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12903 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-02 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-12 |  | 09 30 13-1 Tile Product Data Submittal (Base Building).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-12 |  | 09 30 13-1 Tile Product Data Submittal (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-02 |  | 09 30 13-1 Tile Product Data Submittal (Base Building)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-12 |  | 09 30 13-1 Tile Product Data Submittal (Base Building).pdf
09 30 13-001-01 | 09 30 13 - CERAMIC TILING | 09 30 13-001-01 TILE - Product Data (Base Building) - T74, T76, & T79 Resubmittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-20 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-04 07:00 | 2021-06-04 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13205 | Received | For Review | 2021-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-04 07:00 | Submittal Number: 09 30 13-1.1 From: KIM DOWALIBY Final Due Date: 06/03/21 Subject: TILE - PRODUCT DATA (BASE BUILDING) - T74, T76, & T79 RESUBMITTAL Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 17093 | Forwarded | For Review | 2021-05-20 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-27 | Submittal Number: 09 30 13-1.1 From: KIM DOWALIBY Final Due Date: 06/03/21 Subject: TILE - PRODUCT DATA (BASE BUILDING) - T74, T76, & T79 RESUBMITTAL Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 13407 | Review Response | Approved | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17340 | Responded and Closed | Approved | 2021-06-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-20 |  | 09 30 13-1.1 Tile Product Data Submittal (Base Building) - T74-76-79.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-20 |  | 09 30 13-1.1 Tile Product Data Submittal (Base Building) - T74-76-79.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-04 |  | 09 30 13-1.1 Tile Product Data Submittal (Base Building) - T74-76-79_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-20 |  | 09 30 13-1.1 Tile Product Data Submittal (Base Building) - T74-76-79.pdf
09 30 13-004-00 | 09 30 13 - CERAMIC TILING | 09 30 13-004-00 TILE - Shop Drawings (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-12 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-26 | 2021-02-27 | 16 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11368 | Received | For Review | 2021-02-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-26 | Submittal Number: 09 30 13-4.0 From: DANIELLE SCOTT Final Due Date: 02/25/21 Subject: TILE - SHOP DRAWINGS (BASE BUILDING) Description: SHOP DRAWINGS : SHOW LOCATIONS OF EACH TYPE OF TILE AND TILE PATTERN. SHOW WIDTHS, DETAILS, AND LOCATIONS OF EXPANSION, CONTRACTION, CONTROL, AND ISOLATION JOINTS IN TILE SUBSTRATES AND FINISHED TILE SURFACES. 1. PERFORM FIELD SURVEY AND LOCATE THE JOINTS PRIOR TO SHOP DRAWING GENERATION. NOTE ON SHOP DRAWING WHAT TYPE OF JOINT IT IS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 14725 | Forwarded | For Review | 2021-02-11 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-18 | Submittal Number: 09 30 13-4.0 From: DANIELLE SCOTT Final Due Date: 02/25/21 Subject: TILE - SHOP DRAWINGS (BASE BUILDING) Description: SHOP DRAWINGS : SHOW LOCATIONS OF EACH TYPE OF TILE AND TILE PATTERN. SHOW WIDTHS, DETAILS, AND LOCATIONS OF EXPANSION, CONTRACTION, CONTROL, AND ISOLATION JOINTS IN TILE SUBSTRATES AND FINISHED TILE SURFACES. 1. PERFORM FIELD SURVEY AND LOCATE THE JOINTS PRIOR TO SHOP DRAWING GENERATION. NOTE ON SHOP DRAWING WHAT TYPE OF JOINT IT IS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 11672 | Review Response | Approved as Noted/Resubmit | 2021-02-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15128 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-27 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-11 |  | 09 30 13 Tile Shop Drawing (Base Building).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-11 |  | 09 30 13 Tile Shop Drawing (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-27 |  | 09 30 13 Tile Shop Drawing (Base Building)_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-11 |  | 09 30 13 Tile Shop Drawing (Base Building).pdf
09 30 13-004-01 | 09 30 13 - CERAMIC TILING | 09 30 13-004-01 TILE - Shop Drawings Updated Restroom Base Detail & Amazon Lounge (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-07 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-21 | 2021-04-27 | 21 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12438 | Received | For Review | 2021-04-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-21 | Submittal Number: 09 30 13-4.1 From: DANIELLE SCOTT Final Due Date: 04/20/21 Subject: TILE - SHOP DRAWINGS UPDATED RESTROOM BASE DETAIL & AMAZON LOUNGE (BASE BUILDING) Description: SHOP DRAWINGS : SHOW LOCATIONS OF EACH TYPE OF TILE AND TILE PATTERN. SHOW WIDTHS, DETAILS, AND LOCATIONS OF EXPANSION, CONTRACTION, CONTROL, AND ISOLATION JOINTS IN TILE SUBSTRATES AND FINISHED TILE SURFACES. 1. PERFORM FIELD SURVEY AND LOCATE THE JOINTS PRIOR TO SHOP DRAWING GENERATION. NOTE ON SHOP DRAWING WHAT TYPE OF JOINT IT IS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 16116 | Forwarded | For Review | 2021-04-06 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-13 | Submittal Number: 09 30 13-4.1 From: DANIELLE SCOTT Final Due Date: 04/20/21 Subject: TILE - SHOP DRAWINGS UPDATED RESTROOM BASE DETAIL & AMAZON LOUNGE (BASE BUILDING) Description: SHOP DRAWINGS : SHOW LOCATIONS OF EACH TYPE OF TILE AND TILE PATTERN. SHOW WIDTHS, DETAILS, AND LOCATIONS OF EXPANSION, CONTRACTION, CONTROL, AND ISOLATION JOINTS IN TILE SUBSTRATES AND FINISHED TILE SURFACES. 1. PERFORM FIELD SURVEY AND LOCATE THE JOINTS PRIOR TO SHOP DRAWING GENERATION. NOTE ON SHOP DRAWING WHAT TYPE OF JOINT IT IS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 12803 | Review Response | Approved as Noted | 2021-04-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16550 | Responded and Closed | Approved as Noted | 2021-04-27 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-06 |  | 09 30 13-4 Revision 1 TILE - Shop Drawings Updated Restroom Base Detail & Amazon Lounge (Base Building).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-06 |  | 09 30 13-4 Revision 1 TILE - Shop Drawings Updated Restroom Base Detail & Amazon Lounge (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-27 |  | 09 30 13-4 Revision 1 TILE - Shop Drawings Updated Restroom Base Detail & Amazon Lounge_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-06 |  | 09 30 13-4 Revision 1 TILE - Shop Drawings Updated Restroom Base Detail & Amazon Lounge (Base Building).pdf
09 30 13-005-00 | 09 30 13 - CERAMIC TILING | 09 30 13-005-00 TILE - Samples (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-21 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-04 | 2020-09-04 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07656 | Received | For Review | 2020-08-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-04 | Submittal Number: 09 30 13-5.0 From: DANIELLE SCOTT Final Due Date: 09/03/20 Subject: TILE - SAMPLES (BASE BUILDING) Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS, IN MANUFACTURER'S STANDARD SIZES UNLESS OTHERWISE INDICATED. FOR OF EACH TYPE TILE THAT COMES IN COLOR BLEND PATTERNS, PROVIDE FULL SHEETS OF EACH COLOR BLEND. FULL-SIZE UNITS OF EACH TYPE OF TRIM AND ACCESSORY FOR EACH COLOR AND FINISH REQUIRED. METAL EDGE STRIPS IN 6-INCH LENGTHS. 5. GROUT SAMPLES FOR FINAL COLOR SELECTION. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 10199 | Forwarded | For Review | 2020-08-20 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-27 | Submittal Number: 09 30 13-5.0 From: DANIELLE SCOTT Final Due Date: 09/03/20 Subject: TILE - SAMPLES (BASE BUILDING) Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS, IN MANUFACTURER'S STANDARD SIZES UNLESS OTHERWISE INDICATED. FOR OF EACH TYPE TILE THAT COMES IN COLOR BLEND PATTERNS, PROVIDE FULL SHEETS OF EACH COLOR BLEND. FULL-SIZE UNITS OF EACH TYPE OF TRIM AND ACCESSORY FOR EACH COLOR AND FINISH REQUIRED. METAL EDGE STRIPS IN 6-INCH LENGTHS. 5. GROUT SAMPLES FOR FINAL COLOR SELECTION. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 07917 | Review Response | Approved as Noted | 2020-09-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to comments and grout selections marked on sheets. NHL locker tile not reviewed, they are changing per team selection. | Info Exchange
| 10534 | Responded and Closed | Approved as Noted | 2020-09-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to comments and grout selections marked on sheets. NHL locker tile not reviewed, they are changing per team selection. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 09 30 13-5 TILE - Samples (Base Building).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-20 |  | 09 30 13-5 TILE - Samples (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-04 |  | 09 30 13-5 TILE - Samples (Base Building)_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-20 |  | 09 30 13-5 TILE - Samples (Base Building).pdf
09 30 13-017-00 | 09 30 13 - CERAMIC TILING | 09 30 13-017-00 TILE - Tile Samples (Premium Spaces) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-20 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kuebler Perry (Populous) |  |  |  | 2020-09-03 | 2020-09-14 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07635 | Received | For Review | 2020-08-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-03 | Submittal Number: 09 30 13-17.0 From: DANIELLE SCOTT Final Due Date: 09/02/20 Subject: TILE - TILE SAMPLES (PREMIUM SPACES) Description: PREMIUM SPACE TILE SAMPLES. EXCLUDES GROUT SAMPLES AND T116 Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 10165 | Forwarded | For Review | 2020-08-20 | Populous SCA_CCA | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-27 | Submittal Number: 09 30 13-17.0 From: DANIELLE SCOTT Final Due Date: 09/02/20 Subject: TILE - TILE SAMPLES (PREMIUM SPACES) Description: PREMIUM SPACE TILE SAMPLES. EXCLUDES GROUT SAMPLES AND T116 Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 10169 | Forwarded | For Review | 2020-08-20 | Populous SCA_CCA | Kuebler Perry (Populous) | 2020-08-27 | Submittal Number: 09 30 13-17.0 From: DANIELLE SCOTT Final Due Date: 09/02/20 Subject: TILE - TILE SAMPLES (PREMIUM SPACES) Description: PREMIUM SPACE TILE SAMPLES. EXCLUDES GROUT SAMPLES AND T116 Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 08066 | Review Response | Approved as Noted | 2020-09-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Matrice Essenza - Laticrete #78 Sterling Silver Black granite - Laticrete #22 Midnight black Nero Marquina - Laticrete #22 Midnight black Reclaimed Brick Veneer - confirmed Laticrete MVIS, Grey (only option) | Info Exchange
| 10729 | Responded and Closed | Approved as Noted | 2020-09-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Matrice Essenza - Laticrete #78 Sterling Silver Black granite - Laticrete #22 Midnight black Nero Marquina - Laticrete #22 Midnight black Reclaimed Brick Veneer - confirmed Laticrete MVIS, Grey (only option) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-19 |  | 09 30 13-7 TILE - Tile Samples (Premium Spaces).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-19 |  | 09 30 13-17 TILE - Tile Samples (Premium Spaces).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-19 |  | 09 30 13-7 TILE - Tile Samples (Premium Spaces).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-14 |  | 09 30 13-17 TILE - Tile Samples (Premium Spaces)_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-19 |  | 09 30 13-7 TILE - Tile Samples (Premium Spaces).pdf
09 30 13-018-00 | 09 30 13 - CERAMIC TILING | 09 30 13-018-00 TILE - Shop Drawings - Suite Level Area D Suites & Restrooms (Premium Spaces) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-18 | 2021-02-19 | 16 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11179 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-18 | Submittal Number: 09 30 13-18.0 From: DANIELLE SCOTT Final Due Date: 02/17/21 Subject: TILE - SHOP DRAWINGS - SUITE LEVEL AREA D SUITES & RESTROOMS (PREMIUM SPACES) Description: SHOP DRAWINGS : SHOW LOCATIONS OF EACH TYPE OF TILE AND TILE PATTERN. SHOW WIDTHS, DETAILS, AND LOCATIONS OF EXPANSION, CONTRACTION, CONTROL, AND ISOLATION JOINTS IN TILE SUBSTRATES AND FINISHED TILE SURFACES. 1. PERFORM FIELD SURVEY AND LOCATE THE JOINTS PRIOR TO SHOP DRAWING GENERATION. NOTE ON SHOP DRAWING WHAT TYPE OF JOINT IT IS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 14485 | Forwarded | For Review | 2021-02-03 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-10 | Submittal Number: 09 30 13-18.0 From: DANIELLE SCOTT Final Due Date: 02/17/21 Subject: TILE - SHOP DRAWINGS - SUITE LEVEL AREA D SUITES & RESStatus: OPENTROOMS (PREMIUM SPACES) Description: SHOP DRAWINGS : SHOW LOCATIONS OF EACH TYPE OF TILE AND TILE PATTERN. SHOW WIDTHS, DETAILS, AND LOCATIONS OF EXPANSION, CONTRACTION, CONTROL, AND ISOLATION JOINTS IN TILE SUBSTRATES AND FINISHED TILE SURFACES. 1. PERFORM FIELD SURVEY AND LOCATE THE JOINTS PRIOR TO SHOP DRAWING GENERATION. NOTE ON SHOP DRAWING WHAT TYPE OF JOINT IT IS. Spec Section: 09 30 13 - CERAMIC TILE | Info Exchange
| 14964 | Responded and Closed | Approved as Noted | 2021-02-19 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. FIELD VERIFY ALL DIMENSIONS 2. EQUAL TILES IN EACH DIRECTION IN ROOMS 3. APPLY ALL COMMENTS FROM MOCKUP SUITE SUBMITTALS AND REVIEWS 5. COORDINATE ALL COUNTERS WITH MILLWORK CABINETS BELOW. 4. CM TO COORDINATE ALL ROCKWELL GROUP COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-03 |  | 09 30 13-18 TILE - Shop Drawings - Suite Level Area D Suites & Restrooms (Premium Spaces).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-03 |  | 09 30 13-18 TILE - Shop Drawings - Suite Level Area D Suites & Restrooms (Premium Spaces).pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-19 |  | 09 30 13-18 TILE - Shop Drawings - Suite Level Area D Suites & Restrooms (Premium Spaces)_POP.pdf
09 30 13-021-00 | 09 30 13 - CERAMIC TILING | 09 30 13-021-00 TILE - Product Data, LEED, Testing, Qualification Data & Master Grade Certificates (Premium Spaces) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-09 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-23 | 2020-11-24 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-11-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09300 | Received | For Review | 2020-11-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-11-23 | Submittal Number: 09 30 13-21.0 From: DANIELLE SCOTT Final Due Date: 11/20/20 Subject: TILE - PRODUCT DATA, LEED, TESTING, QUALIFICATION DATA & MASTER GRADE CERTIFICATES (PREMIUM SPACES) Description: PRODUCT DATA, LEED, TESTING, QUALIFICATION DATA & MASTER GRADE CERTIFICATES (PREMIUM SPACES). INCLUDES NEW TILE ST22 AND T128. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 12272 | Forwarded | For Review | 2020-11-09 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-16 | Submittal Number: 09 30 13-21.0 From: DANIELLE SCOTT Final Due Date: 11/20/20 Subject: TILE - PRODUCT DATA, LEED, TESTING, QUALIFICATION DATA & MASTER GRADE CERTIFICATES (PREMIUM SPACES) Description: PRODUCT DATA, LEED, TESTING, QUALIFICATION DATA & MASTER GRADE CERTIFICATES (PREMIUM SPACES). INCLUDES NEW TILE ST22 AND T128. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 09721 | Review Response | Approved | 2020-11-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12783 | Responded and Closed | Approved | 2020-11-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 09 30 13-21 TILE - Product Data LEED Testing Qualification Data Master Grade Certificates.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 09 30 13-21 TILE - Product Data LEED Testing Qualification Data Master Grade Certificates.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-24 |  | 09 30 13-21 TILE - Product Data LEED Testing Qualification Data MGC POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-06 |  | 09 30 13-21 TILE - Product Data LEED Testing Qualification Data Master Grade Certificates.pdf
09 30 13-022-00 | 09 30 13 - CERAMIC TILING | 09 30 13-022-00 TILE - Tile Grout Samples (Premium Spaces) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-10 07:00 | 2020-09-09 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07767 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-10 07:00 | Submittal Number: 09 30 13-22.0 From: DANIELLE SCOTT Final Due Date: 09/09/20 Subject: TILE - TILE GROUT SAMPLES (PREMIUM SPACES) Description: PREMIUM SPACE GROUT SAMPLES. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 10339 | Forwarded | For Review | 2020-08-26 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 09 30 13-22.0 From: DANIELLE SCOTT Final Due Date: 09/09/20 Subject: TILE - TILE GROUT SAMPLES (PREMIUM SPACES) Description: PREMIUM SPACE GROUT SAMPLES. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 10636 | Responded and Closed | Approved as Noted | 2020-09-09 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  | REFER TO FINISH LEGEND FOR GROUT SPEC IN PREMIUM SPACES. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 09 30 13-22 TILE - Tile Grout Samples (Premium Spaces).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-26 |  | 09 30 13-22 TILE - Tile Grout Samples (Premium Spaces).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-09 02:00 |  | 09 30 13-22 TILE - Tile Grout Samples (Premium Spaces)_POP.pdf
09 30 13-023-00 | 09 30 13 - CERAMIC TILING | 09 30 13-023-00 TILE - Tile ST10 and T116 Sample (Premium Spaces) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-07 | 2020-10-05 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08286 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-07 | Submittal Number: 09 30 13-23.0 From: DANIELLE SCOTT Final Due Date: 10/06/20 Subject: TILE - TILE ST10 AND T116 SAMPLE (PREMIUM SPACES) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 10992 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 09 30 13-23.0 From: DANIELLE SCOTT Final Due Date: 10/06/20 Subject: TILE - TILE ST10 AND T116 SAMPLE (PREMIUM SPACES) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 08545 | Review Response | Approved | 2020-10-05 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11307 | Responded and Closed | Approved | 2020-10-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 09 30 13-23 TILE - Tile ST10 and T116 Sample (Premium Spaces).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 09 30 13-23 TILE - Tile ST10 and T116 Sample (Premium Spaces).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-05 |  | 09 30 13-23 TILE - Tile ST10 and T116 Sample POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-23 |  | 09 30 13-23 TILE - Tile ST10 and T116 Sample (Premium Spaces).pdf
09 30 13-024-00 | 09 30 13 - CERAMIC TILING | 09 30 13-024-00 Tile Bostik Grout Samples (Premium Spaces) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-24 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-08 | 2020-10-05 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08317 | Received | For Review | 2020-09-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-08 | Submittal Number: 09 30 13-24.0 From: DANIELLE SCOTT Final Due Date: 10/08/20 Subject: 09 30 13-24 TILE BOSTIK GROUT SAMPLES (PREMIUM SPACES) Description: BOSTIK GROUT IS NEEDED FOR T102 AND T123 DUE TO THE TILE'S MATERIAL COMPOSITION. PLEASE SELECT A BOSTIK GROUT COLOR FOR THESE TWO TILE TYPES. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 11023 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-01 | Submittal Number: 09 30 13-24.0 From: DANIELLE SCOTT Final Due Date: 10/08/20 Subject: 09 30 13-24 TILE BOSTIK GROUT SAMPLES (PREMIUM SPACES) Description: BOSTIK GROUT IS NEEDED FOR T102 AND T123 DUE TO THE TILE'S MATERIAL COMPOSITION. PLEASE SELECT A BOSTIK GROUT COLOR FOR THESE TWO TILE TYPES. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 08534 | Review Response | Approved as Noted | 2020-10-05 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11287 | Responded and Closed | Approved as Noted | 2020-10-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 09 30 13-24 TILE - Tile Bostik Grout Samples (Premium Spaces).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 09 30 13-24 TILE - Tile Bostik Grout Samples (Premium Spaces).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-05 |  | 09 30 13-24 TILE - Bostik Grout (Premium Spaces)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-24 |  | 09 30 13-24 TILE - Tile Bostik Grout Samples (Premium Spaces).pdf
09 30 13-025-00 | 09 30 13 - CERAMIC TILING | 09 30 13-025-00 TILE - Mockup Shop Drawings (Premium Spaces) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-14 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-28 | 2020-10-28 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08783 | Received | For Review | 2020-10-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-28 | Submittal Number: 09 30 13-25.0 From: DANIELLE SCOTT Final Due Date: 10/28/20 Subject: TILE - MOCKUP SHOP DRAWINGS (PREMIUM SPACES) Description: SHOP DRAWINGS : SHOW LOCATIONS OF EACH TYPE OF TILE AND TILE PATTERN. SHOW WIDTHS, DETAILS, AND LOCATIONS OF EXPANSION, CONTRACTION, CONTROL, AND ISOLATION JOINTS IN TILE SUBSTRATES AND FINISHED TILE SURFACES. 1. PERFORM FIELD SURVEY AND LOCATE THE JOINTS PRIOR TO SHOP DRAWING GENERATION. NOTE ON SHOP DRAWING WHAT TYPE OF JOINT IT IS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 11613 | Forwarded | For Review | 2020-10-14 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-21 | Submittal Number: 09 30 13-25.0 From: DANIELLE SCOTT Final Due Date: 10/28/20 Subject: TILE - MOCKUP SHOP DRAWINGS (PREMIUM SPACES) Description: SHOP DRAWINGS : SHOW LOCATIONS OF EACH TYPE OF TILE AND TILE PATTERN. SHOW WIDTHS, DETAILS, AND LOCATIONS OF EXPANSION, CONTRACTION, CONTROL, AND ISOLATION JOINTS IN TILE SUBSTRATES AND FINISHED TILE SURFACES. 1. PERFORM FIELD SURVEY AND LOCATE THE JOINTS PRIOR TO SHOP DRAWING GENERATION. NOTE ON SHOP DRAWING WHAT TYPE OF JOINT IT IS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 09048 | Review Response | Approved as Noted | 2020-10-28 | Kuebler Perry (Populous) | pop |  | Refer to attached submittal review. | Info Exchange
| 11933 | Responded and Closed | Approved as Noted | 2020-10-28 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-14 |  | 09 30 13-25 TILE - Mockup Shop Drawings (Premium Space).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-14 |  | 09 30 13-25 TILE - Mockup Shop Drawings (Premium Space).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-28 |  | 09 30 13-25 TILE - Mockup Shop Drawings (Premium Space)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-14 |  | 09 30 13-25 TILE - Mockup Shop Drawings (Premium Space).pdf
09 30 13-026-00 | 09 30 13 - CERAMIC TILING | 09 30 13-026-00 TILE - Mockup Shop Drawings (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-14 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-28 | 2020-10-28 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08784 | Received | For Review | 2020-10-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-28 | Submittal Number: 09 30 13-26.0 From: DANIELLE SCOTT Final Due Date: 10/28/20 Subject: TILE - MOCKUP SHOP DRAWINGS (BASE BUILDING) Description: SHOP DRAWINGS : SHOW LOCATIONS OF EACH TYPE OF TILE AND TILE PATTERN. SHOW WIDTHS, DETAILS, AND LOCATIONS OF EXPANSION, CONTRACTION, CONTROL, AND ISOLATION JOINTS IN TILE SUBSTRATES AND FINISHED TILE SURFACES. 1. PERFORM FIELD SURVEY AND LOCATE THE JOINTS PRIOR TO SHOP DRAWING GENERATION. NOTE ON SHOP DRAWING WHAT TYPE OF JOINT IT IS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 11614 | Forwarded | For Review | 2020-10-14 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-21 | Submittal Number: 09 30 13-26.0 From: DANIELLE SCOTT Final Due Date: 10/28/20 Subject: TILE - MOCKUP SHOP DRAWINGS (BASE BUILDING) Description: SHOP DRAWINGS : SHOW LOCATIONS OF EACH TYPE OF TILE AND TILE PATTERN. SHOW WIDTHS, DETAILS, AND LOCATIONS OF EXPANSION, CONTRACTION, CONTROL, AND ISOLATION JOINTS IN TILE SUBSTRATES AND FINISHED TILE SURFACES. 1. PERFORM FIELD SURVEY AND LOCATE THE JOINTS PRIOR TO SHOP DRAWING GENERATION. NOTE ON SHOP DRAWING WHAT TYPE OF JOINT IT IS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 09054 | Review Response | Approved | 2020-10-28 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 11938 | Responded and Closed | Approved | 2020-10-28 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-14 |  | 09 30 13-26 TILE - Mockup Shop Drawings (Base Building).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-14 |  | 09 30 13-26 TILE - Mockup Shop Drawings (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-28 |  | 09 30 13-26 TILE - Mockup Shop Drawings (Base Building)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-14 |  | 09 30 13-26 TILE - Mockup Shop Drawings (Base Building).pdf
09 30 13-027-00 | 09 30 13 - CERAMIC TILING | 09 30 13-027-00 Porcelain Edge Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-16 | 2020-11-19 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-11-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09161 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-11-16 | Submittal Number: 09 30 13-27.0 From: MIKE SOLFELT Final Due Date: 11/15/20 Subject: PORCELAIN EDGE SAMPLE Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 12083 | Forwarded | For Review | 2020-11-02 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-09 | Submittal Number: 09 30 13-27.0 From: MIKE SOLFELT Final Due Date: 11/15/20 Subject: PORCELAIN EDGE SAMPLE Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 09563 | Review Response | Approved | 2020-11-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12588 | Responded and Closed | Approved | 2020-11-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | 09 30 13-27 Porcelain Edge Sample.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-02 |  | 09 30 13-27 Porcelain Edge Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-19 |  | 09 30 13-27 Porcelain Edge Sample_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-02 |  | 09 30 13-27 Porcelain Edge Sample.pdf
09 30 13-028-00 | 09 30 13 - CERAMIC TILING | 09 30 13-028-00 TILE - Samples & Grout Colors (NHL Locker Room) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-06 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-20 | 2020-11-18 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09280 | Received | For Review | 2020-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-11-20 | Submittal Number: 09 30 13-28.0 From: DANIELLE SCOTT Final Due Date: 11/20/20 Subject: TILE - SAMPLES & GROUT COLORS (NHL LOCKER ROOM) Description: SAMPLES OF ALL NHL TILES. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 12235 | Forwarded | For Review | 2020-11-06 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-13 | Submittal Number: 09 30 13-28.0 From: DANIELLE SCOTT Final Due Date: 11/20/20 Subject: TILE - SAMPLES & GROUT COLORS (NHL LOCKER ROOM) Description: SAMPLES OF ALL NHL TILES. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 09556 | Review Response | Approved as Noted | 2020-11-18 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Please note submittal contains both NHL & WNBA Locker Room tile. | Info Exchange
| 12577 | Responded and Closed | Approved as Noted | 2020-11-18 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: Please note submittal contains both NHL & WNBA Locker Room tile. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 09 30 13-28 TILE Sample NHL.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 09 30 13-28 TILE Sample NHL.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-11-18 |  | 09 30 13-28 TILE Sample NHL_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-06 |  | 09 30 13-28 TILE Sample NHL.pdf
09 30 13-029-00 | 09 30 13 - CERAMIC TILING | 09 30 13-029-00 TILE - ST22 & T128 (Premium Spaces) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-09 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-23 | 2020-11-23 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-11-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09299 | Received | For Review | 2020-11-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-11-23 | Submittal Number: 09 30 13-29.0 From: DANIELLE SCOTT Final Due Date: 11/20/20 Subject: TILE - ST22 & T128 (PREMIUM SPACES) Description: SAMPLES FOR NEW TILE ADDED TO THE PROJECT. PLEASE ALSO SPECIFY LATACRETE GROUT COLORS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 12271 | Forwarded | For Review | 2020-11-09 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-16 | Submittal Number: 09 30 13-29.0 From: DANIELLE SCOTT Final Due Date: 11/20/20 Subject: TILE - ST22 & T128 (PREMIUM SPACES) Description: SAMPLES FOR NEW TILE ADDED TO THE PROJECT. PLEASE ALSO SPECIFY LATACRETE GROUT COLORS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 09679 | Review Response | Approved | 2020-11-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12732 | Responded and Closed | Approved | 2020-11-23 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 09 30 13 - 29 TILE - ST22 & T128.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 09 30 13 - 29 TILE - ST22 & T128.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-11-23 |  | 09 30 13 - 29 TILE - ST22 & T128_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-06 |  | 09 30 13 - 29 TILE - ST22 & T128.pdf
09 30 13-030-00 | 09 30 13 - CERAMIC TILING | 09 30 13-030-00 TILE - T119 Sample (Premium Spaces) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-16 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-08 | 2020-12-17 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10196 | Received | For Review | 2020-12-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-08 | Submittal Number: 09 30 13-30.0 From: DANIELLE SCOTT Final Due Date: 12/29/20 Subject: TILE - T119 SAMPLE (PREMIUM SPACES) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 13334 | Forwarded | For Review | 2020-12-16 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-23 | Submittal Number: 09 30 13-30.0 From: DANIELLE SCOTT Final Due Date: 12/29/20 Subject: TILE - T119 SAMPLE (PREMIUM SPACES) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 10226 | Review Response | Approved | 2020-12-17 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 13365 | Responded and Closed | Approved | 2020-12-17 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-16 |  | 09 30 13-30 T119 Sample (Premium Spaces).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-16 |  | 09 30 13-30 T119 Sample (Premium Spaces).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-17 |  | 09 30 13-30 T119 Sample (Premium Spaces)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-16 |  | 09 30 13-30 T119 Sample (Premium Spaces).pdf
09 30 13-031-00 | 09 30 13 - CERAMIC TILING | 09 30 13-031-00 TILE - Shop Drawings, Event Level (Premium Spaces) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-22 08:00 | 2021-01-24 | 18 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-01-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10493 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-22 08:00 | Submittal Number: 09 30 13-31.0 From: DANIELLE SCOTT Final Due Date: 01/20/21 Subject: TILE - SHOP DRAWINGS, EVENT LEVEL (PREMIUM SPACES) Description: SHOP DRAWINGS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 13696 | Forwarded | For Review | 2021-01-06 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-13 | Submittal Number: 09 30 13-31.0 From: DANIELLE SCOTT Final Due Date: 01/20/21 Subject: TILE - SHOP DRAWINGS, EVENT LEVEL (PREMIUM SPACES) Description: SHOP DRAWINGS. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 10920 | Review Response | Approved as Noted | 2021-01-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14177 | Responded and Closed | Approved as Noted | 2021-01-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-06 |  | 09 30 13-31 TILE - Shop Drawings Event Level (Premium Spaces).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-06 |  | 09 30 13-31 TILE - Shop Drawings Event Level (Premium Spaces).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-24 |  | 09 30 13-31 TILE - Shop Drawings, Event Level (Premium Spaces)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-06 |  | 09 30 13-31 TILE - Shop Drawings Event Level (Premium Spaces).pdf
09 30 13-032-00 | 09 30 13 - CERAMIC TILING | 09 30 13-032-00 TILE - Main Con Food Service Mockup Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-15 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-01 08:00 | 2021-02-01 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10746 | Received | For Review | 2021-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-01 08:00 | Submittal Number: 09 30 13-32.0 From: DANIELLE SCOTT Final Due Date: 01/29/21 Subject: TILE - MAIN CON FOOD SERVICE MOCKUP SHOP DRAWINGS Description: SHOPS FOR THE FOOD SERVICE MOCK-UP. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 13980 | Forwarded | For Review | 2021-01-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-22 | Submittal Number: 09 30 13-32.0 From: DANIELLE SCOTT Final Due Date: 01/29/21 Subject: TILE - MAIN CON FOOD SERVICE MOCKUP SHOP DRAWINGS Description: SHOPS FOR THE FOOD SERVICE MOCK-UP. Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 11083 | Review Response | Approved | 2021-02-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14381 | Responded and Closed | Approved | 2021-02-01 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-15 |  | 09 30 13 Tile Shop Drawing (Mock-Up Food Service).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-15 |  | 09 30 13 Tile Shop Drawing (Mock-Up Food Service).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-01 |  | 09 30 13 Tile Shop Drawing (Mock-Up Food Service)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-15 |  | 09 30 13 Tile Shop Drawing (Mock-Up Food Service).pdf
09 30 13-033-00 | 09 30 13 - CERAMIC TILING | 09 30 13-033-00 TILE - Suite Level Shop Drawings (Premium) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-03-03 | 17 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11395 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-03-01 | Submittal Number: 09 30 13-33.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: TILE - SUITE LEVEL SHOP DRAWINGS (PREMIUM) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 14762 | Forwarded | For Review | 2021-02-12 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-19 | Submittal Number: 09 30 13-33.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: TILE - SUITE LEVEL SHOP DRAWINGS (PREMIUM) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 11779 | Review Response | Approved as Noted | 2021-03-03 | Kuebler Perry (Populous) | Populous SCA_CCA |  | REFER TO ATTACHED SUBMITTAL REVIEW. | Info Exchange
| 15262 | Responded and Closed | Approved as Noted | 2021-03-03 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | REFER TO ATTACHED SUBMITTAL REVIEW. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-12 |  | 09 30 13-33 Revision 0 TILE - Suite Level Shop Drawings (Premium).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-12 |  | 09 30 13-33 Revision 0 TILE - Suite Level Shop Drawings (Premium).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-03 |  | 09 30 13-33 Revision 0 TILE - Suite Level Shop Drawings (Premium)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-12 |  | 09 30 13-33 Revision 0 TILE - Suite Level Shop Drawings (Premium).pdf
09 30 13-033-01 | 09 30 13 - CERAMIC TILING | 09 30 13-033-01 TILE - Suite Level Shop Drawings (Premium) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-14 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-28 | 2021-05-04 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12585 | Received | For Review | 2021-04-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-28 | Submittal Number: 09 30 13-33.1 From: DANIELLE SCOTT Final Due Date: 04/27/21 Subject: TILE - SUITE LEVEL SHOP DRAWINGS (PREMIUM) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 16299 | Forwarded | For Review | 2021-04-14 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-21 | Submittal Number: 09 30 13-33.1 From: DANIELLE SCOTT Final Due Date: 04/27/21 Subject: TILE - SUITE LEVEL SHOP DRAWINGS (PREMIUM) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 16715 | Responded and Closed | Approved as Noted | 2021-05-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-14 |  | 09 30 13-33 Revision 1 TILE - Suite Level Shop Drawings (Premium).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-14 |  | 09 30 13-33 Revision 1 TILE - Suite Level Shop Drawings (Premium).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-04 |  | 09 30 13-33 Revision 1 TILE - Suite Level Shop Drawings (Premium)_POP.pdf
09 30 13-034-00 | 09 30 13 - CERAMIC TILING | 09 30 13-034-00 TILE - Space Needle Shop Drawings (Premium) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-03-01 | 15 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11394 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-01 | Submittal Number: 09 30 13-34.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: TILE - SPACE NEEDLE SHOP DRAWINGS (PREMIUM) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 14761 | Forwarded | For Review | 2021-02-12 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-19 | Submittal Number: 09 30 13-34.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: TILE - SPACE NEEDLE SHOP DRAWINGS (PREMIUM) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 11719 | Review Response | Approved as Noted | 2021-03-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 15187 | Responded and Closed | Approved as Noted | 2021-03-01 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-12 |  | 09 30 13-34 Revision 0 TILE - Space Needle Shop Drawings (Premium).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-12 |  | 09 30 13-34 Revision 0 TILE - Space Needle Shop Drawings (Premium).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-01 |  | 09 30 13-34 Revision 0 TILE - Space Needle Shop_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-12 |  | 09 30 13-34 Revision 0 TILE - Space Needle Shop Drawings (Premium).pdf
09 30 13-035-00 | 09 30 13 - CERAMIC TILING | 09 30 13-035-00 TILE - Main Concourse Shop Drawings (Premium) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-03-02 | 16 |  | Record Copies; Transfers; Submittals | 09 30 13-035-00-01 - 09 30 13-035-00 TILE - Main Concourse Shop Drawings (Premium) | 19 |  | 2021-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11393 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-03-01 | Submittal Number: 09 30 13-35.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: TILE - MAIN CONCOURSE SHOP DRAWINGS (PREMIUM) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 14760 | Forwarded | For Review | 2021-02-12 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-19 | Submittal Number: 09 30 13-35.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: TILE - MAIN CONCOURSE SHOP DRAWINGS (PREMIUM) Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 11754 | Review Response | Approved as Noted/Resubmit | 2021-03-02 | Kuebler Perry (Populous) | Josh Dobken (Populous) |  | Refer to attached submittal response. | Info Exchange
| 15231 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-02 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-12 |  | 09 30 13-35 Revision 0 TILE - Main Concourse Shop Drawings (Premium).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-12 |  | 09 30 13-35 Revision 0 TILE - Main Concourse Shop Drawings (Premium).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-02 |  | 09 30 13-35 Revision 0 TILE - Main Concourse_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-12 |  | 09 30 13-35 Revision 0 TILE - Main Concourse Shop Drawings (Premium).pdf
09 30 13-035-00-01 | 09 30 13 - CERAMIC TILING | 09 30 13-035-00 TILE - Main Concourse Shop Drawings (Premium) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 30 13-035-00 - 09 30 13-035-00 TILE - Main Concourse Shop Drawings (Premium) | -1 | 2021-03-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-12 |  | 09 30 13-35 Revision 0 TILE - Main Concourse Shop Drawings (Premium).pdf
09 30 13-036-00 | 09 30 13 - CERAMIC TILING | 09 30 13-036-00 Tile - Amazon Lounge Tile Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-26 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-12 07:00 | 2021-04-01 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-04-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12247 | Received | For Review | 2021-03-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-04-12 07:00 | Submittal Number: 09 30 13-36.0 From: DANIELLE SCOTT Final Due Date: 04/05/21 Subject: TILE - AMAZON LOUNGE TILE SAMPLES Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 15847 | Forwarded | For Review | 2021-03-26 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-02 | Submittal Number: 09 30 13-36.0 From: DANIELLE SCOTT Final Due Date: 04/05/21 Subject: TILE - AMAZON LOUNGE TILE SAMPLES Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 12372 | Review Response | Approved as Noted | 2021-04-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16028 | Responded and Closed | Approved as Noted | 2021-04-01 | Danielle Scott | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-25 |  | 09 30 13-36 Revision 0 Tile - Amazon Lounge Tile Samples.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-03-25 |  | 09 30 13-36 Revision 0 Tile - Amazon Lounge Tile Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-01 |  | 09 30 13-36 Revision 0 Tile - Amazon Lounge Tile Samples_POP.pdf
| Responded and Closed |  | Danielle Scott | 1 | 2021-03-25 |  | 09 30 13-36 Revision 0 Tile - Amazon Lounge Tile Samples.pdf
09 30 13-037-00 | 09 30 13 - CERAMIC TILING | 09 30 13-037-00 T119 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-14 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-28 | 2021-04-27 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12586 | Received | For Review | 2021-04-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-04-28 | Submittal Number: 09 30 13-37.0 From: DANIELLE SCOTT Final Due Date: 04/28/21 Subject: T119 SAMPLE Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 16300 | Forwarded | For Review | 2021-04-14 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-21 | Submittal Number: 09 30 13-37.0 From: DANIELLE SCOTT Final Due Date: 04/28/21 Subject: T119 SAMPLE Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 12802 | Review Response | Approved as Noted | 2021-04-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16548 | Responded and Closed | Approved as Noted | 2021-04-27 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-14 |  | 09 30 13-37 Revision 0 T119 Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-14 |  | 09 30 13-37 Revision 0 T119 Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-27 |  | 09 30 13-37 Revision 0 T119 Sample_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-14 |  | 09 30 13-37 Revision 0 T119 Sample.pdf
09 30 13-038-00 | 09 30 13 - CERAMIC TILING | 09 30 13-038-00 TILE - Shop Drawings Event Level (Premium Spaces) - Added Prefunction Corridor Elevation | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-10 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-24 | 2021-05-19 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12991 | Received | For Review | 2021-05-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-05-24 | Submittal Number: 09 30 13-38.0 From: KIM DOWALIBY Final Due Date: 05/21/21 Subject: TILE - SHOP DRAWINGS EVENT LEVEL (PREMIUM SPACES) - ADDED PREFUNCTION CORRIDOR ELEVATION Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 16814 | Forwarded | For Review | 2021-05-10 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-17 | Submittal Number: 09 30 13-38.0 From: KIM DOWALIBY Final Due Date: 05/21/21 Subject: TILE - SHOP DRAWINGS EVENT LEVEL (PREMIUM SPACES) - ADDED PREFUNCTION CORRIDOR ELEVATION Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 17073 | Responded and Closed | Approved as Noted | 2021-05-19 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 09 30 13-38 - TILE - Shop Drawings Event Level (Premium Spaces) - Added Prefunction Corridor Elevation.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-05-10 |  | 09 30 13-38 - TILE - Shop Drawings Event Level (Premium Spaces) - Added Prefunction Corridor Elevation.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-19 |  | 09 30 13-38 - TILE - Shop Drawings Event Level (Premium Spaces) - Added Prefunction Corridor Elevation_POP.pdf
09 30 13-039-00 | 09 30 13 - CERAMIC TILING | 09 30 13-039-00 TILE - T18 (Coors Light Bar) - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-28 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-14 07:00 | 2021-06-03 | 7 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13315 | Received | For Review | 2021-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-06-14 07:00 | Submittal Number: 09 30 13-39.0 From: KIM DOWALIBY Final Due Date: 06/11/21 Subject: TILE - T18 (COORS LIGHT BAR) - SAMPLE Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 17230 | Forwarded | For Review | 2021-06-01 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 09 30 13-39.0 From: KIM DOWALIBY Final Due Date: 06/11/21 Subject: TILE - T18 (COORS LIGHT BAR) - SAMPLE Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 13380 | Review Response | Approved | 2021-06-03 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17308 | Responded and Closed | Approved | 2021-06-03 | Kim Dowaliby | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-28 |  | 09 30 13.39 - TILE - T18 (Coors Light Bar) - Sample.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-05-28 |  | 09 30 13.39 - TILE - T18 (Coors Light Bar) - Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-03 |  | 09 30 13.39 - TILE - T18 (Coors Light Bar) - Sample_POP.pdf
| Responded and Closed |  | Kim Dowaliby | 1 | 2021-05-28 |  | 09 30 13.39 - TILE - T18 (Coors Light Bar) - Sample.pdf
09 30 13-040-00 | 09 30 13 - CERAMIC TILING | 09 30 13-040-00 TILE - Coors Light Bar T18 Grout - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-10 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-24 | 2021-06-21 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-06-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13482 | Received | For Review | 2021-06-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-06-24 | Submittal Number: 09 30 13-40.0 From: KIM DOWALIBY Final Due Date: 06/23/21 Subject: TILE - COORS LIGHT BAR T18 GROUT - PRODUCT DATA Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 17435 | Forwarded | For Review | 2021-06-10 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-17 | Submittal Number: 09 30 13-40.0 From: KIM DOWALIBY Final Due Date: 06/23/21 Subject: TILE - COORS LIGHT BAR T18 GROUT - PRODUCT DATA Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 13594 | Review Response | Approved | 2021-06-21 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17596 | Responded and Closed | Approved | 2021-06-21 | Kim Dowaliby | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-10 |  | 09 30 13-40 TILE - Coors Light Bar T18 Grout - Product Data.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-06-10 |  | 09 30 13-40 TILE - Coors Light Bar T18 Grout - Product Data.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-21 |  | 09 30 13-40 TILE - Coors Light Bar T18 Grout - Product Data_POP.pdf
| Responded and Closed |  | Kim Dowaliby | 1 | 2021-06-10 |  | 09 30 13-40 TILE - Coors Light Bar T18 Grout - Product Data.pdf
09 30 13-041-00 | 09 30 13 - CERAMIC TILING | 09 30 13-041-00 TILE - Tunnel Club Suites T-Bar Schluter for Bar Delineation - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-02 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-19 07:00 | 2021-07-19 | 18 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-07-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13779 | Received | For Review | 2021-07-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-19 07:00 | Submittal Number: 09 30 13-41.0 From: KIM DOWALIBY Final Due Date: 07/16/21 Subject: TILE - TUNNEL CLUB SUITES T-BAR SCHLUTER FOR BAR DELINEATION - SAMPLE Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 17834 | Forwarded | For Review | 2021-07-06 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-13 | Submittal Number: 09 30 13-41.0 From: KIM DOWALIBY Final Due Date: 07/16/21 Subject: TILE - TUNNEL CLUB SUITES T-BAR SCHLUTER FOR BAR DELINEATION - SAMPLE Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 13998 | Review Response | Approved as Noted | 2021-07-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18107 | Responded and Closed | Approved as Noted | 2021-07-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-02 |  | 09 30 13-41 - TILE - Tunnel Club Suites T-Bar Schluter for Bar Delineation - Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-02 |  | 09 30 13-41 - TILE - Tunnel Club Suites T-Bar Schluter for Bar Delineation - Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-19 |  | 09 30 13-41 - TILE - Tunnel Club Suites T-Bar Schluter for Bar Delineation - Sample_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-02 |  | 09 30 13-41 - TILE - Tunnel Club Suites T-Bar Schluter for Bar Delineation - Sample.pdf
09 30 13-042-00 | 09 30 13 - CERAMIC TILING | 09 30 13-042-00 TILE - CCD 101 Changes (Base Building) - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-07 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-21 | 2021-07-19 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-07-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13815 | Received | For Review | 2021-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-21 | Submittal Number: 09 30 13-42.0 From: KIM DOWALIBY Final Due Date: 07/20/21 Subject: TILE - CCD 101 CHANGES (BASE BUILDING) - SHOP DRAWINGS Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 17885 | Forwarded | For Review | 2021-07-07 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-14 | Submittal Number: 09 30 13-42.0 From: KIM DOWALIBY Final Due Date: 07/20/21 Subject: TILE - CCD 101 CHANGES (BASE BUILDING) - SHOP DRAWINGS Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 14011 | Review Response | Approved | 2021-07-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18124 | Responded and Closed | Approved | 2021-07-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-06 |  | 09 30 13-42 - TILE - CCD 101 Changes (Base Building) - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-06 |  | 09 30 13-42 - TILE - CCD 101 Changes (Base Building) - Shop Drawings.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-19 |  | 09 30 13-42 - TILE - CCD 101 Changes (Base Building) - Shop Drawings_POP.pdf
09 30 13-043-00 | 09 30 13 - CERAMIC TILING | 09 30 13-043-00 Western Tile Mastergrade Certificates | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-29 | Responded and Closed - No Action Taken or Required |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-12 | 2021-07-29 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-07-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14158 | Received | For Review | 2021-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-08-12 | Submittal Number: 09 30 13-43.0 From: LUCAS TRADAL Final Due Date: 08/11/21 Subject: WESTERN TILE MASTERGRADE CERTIFICATES Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 18300 | Forwarded | For Review | 2021-07-29 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-05 | Submittal Number: 09 30 13-43.0 From: LUCAS TRADAL Final Due Date: 08/11/21 Subject: WESTERN TILE MASTERGRADE CERTIFICATES Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 18303 | Responded and Closed | No Action Taken or Required | 2021-07-29 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-29 |  | 09 30 13-43 - TILE - Western Tile Mastergrade Certificates.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-29 |  | Climate Pledge Arena Transmittal - Mastergrade Certificates.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-29 |  | 09 30 13-43 - TILE - Western Tile Mastergrade Certificates_POP.pdf
09 30 13-044-00 | 09 30 13 - CERAMIC TILING | 09 30 13-044-00 TILE - Joint Sealant to Match Grout - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-02 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-16 | 2021-08-05 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-08-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14190 | Received | For Review | 2021-08-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-08-16 | Submittal Number: 09 30 13-44.0 From: LUCAS TRADAL Final Due Date: 08/16/21 Subject: TILE - JOINT SEALANT TO MATCH GROUT - PRODUCT DATA Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 18344 | Forwarded | For Review | 2021-08-02 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-09 | Submittal Number: 09 30 13-44.0 From: LUCAS TRADAL Final Due Date: 08/16/21 Subject: TILE - JOINT SEALANT TO MATCH GROUT - PRODUCT DATA Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 14234 | Review Response | Approved as Noted | 2021-08-05 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18391 | Responded and Closed | Approved as Noted | 2021-08-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-02 |  | 09 30 13-44 - TILE - Joint Sealant to Match Grout - Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-02 |  | 09 30 13-44 - TILE - Joint Sealant to Match Grout - Product Data.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-05 |  | 09 30 13-44 - TILE - Joint Sealant to Match Grout_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-02 |  | 09 30 13-44 - TILE - Joint Sealant to Match Grout - Product Data.pdf
09 30 13-045-00 | 09 30 13 - CERAMIC TILING | 09 30 13-045-00 Coors Light Marketplace T18 Added Tile - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-11 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-25 | 2021-08-24 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14302 | Received | For Review | 2021-08-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-08-25 | Submittal Number: 09 30 13-45.0 From: KIM DOWALIBY Final Due Date: 08/25/21 Subject: COORS LIGHT MARKETPLACE T18 ADDED TILE - SHOP DRAWINGS Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 18472 | Forwarded | For Review | 2021-08-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-18 | Submittal Number: 09 30 13-45.0 From: KIM DOWALIBY Final Due Date: 08/25/21 Subject: COORS LIGHT MARKETPLACE T18 ADDED TILE - SHOP DRAWINGS Description: Spec Section: 09 30 13 - CERAMIC TILE Status: OPEN | Info Exchange
| 14449 | Review Response | Approved | 2021-08-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18650 | Responded and Closed | Approved | 2021-08-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-10 |  | 09 30 13-45 - Coors Light Marketplace T18 Added Tile - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-10 |  | 09 30 13-45 - Coors Light Marketplace T18 Added Tile - Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-24 02:00 |  | 09 30 13-45 - Coors Light Marketplace T18 Added Tile - Shop Drawings_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-09 02:00 |  | 09 30 13-45 - Coors Light Marketplace T18 Added Tile - Shop Drawings.pdf
09 51 00-001-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-001-00 SUSPENDED CEILING SYSTEMS - Product Data Wood Ceilings (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-19 | 2020-08-19 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07367 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-19 | Submittal Number: 09 51 00-1.0 From: DANIELLE SCOTT Final Due Date: 08/18/20 Subject: SUSPENDED CEILING SYSTEMS - PRODUCT DATA WOOD CEILINGS (BASE BUILDING) Description: PRODUCT DATA : FOR ALL WOOD CEILING TYPES SPECIFIED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 09818 | Forwarded | For Review | 2020-08-05 | Populous SCA_CCA | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-08-12 | Submittal Number: 09 51 00-1.0 From: DANIELLE SCOTT Final Due Date: 08/18/20 Subject: SUSPENDED CEILING SYSTEMS - PRODUCT DATA WOOD CEILINGS (BASE BUILDING) Description: PRODUCT DATA : FOR ALL WOOD CEILING TYPES SPECIFIED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 07629 | Review Response | Approved as Noted | 2020-08-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10159 | Responded and Closed | Approved as Noted | 2020-08-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-04 |  | 09 51 00-3 Suspended Ceiling Systems Submittal - Product Data - Wood.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-04 |  | 09 51 00-001-0 Suspended Ceiling Systems Submittal - Product Data - Wood.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-19 |  | 09 51 00-001-0 Suspended Ceiling Systems Submittal - Product Data - Wood_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-04 |  | 09 51 00-3 Suspended Ceiling Systems Submittal - Product Data - Wood.pdf
09 51 00-006-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-006-00 SUSPENDED CEILING SYSTEMS - Samples (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-27 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-11 07:00 | 2020-09-14 | 19 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07775 | Received | For Review | 2020-08-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-11 07:00 | Submittal Number: 09 51 00-6.0 From: DANIELLE SCOTT Final Due Date: 09/08/20 Subject: SUSPENDED CEILING SYSTEMS - SAMPLES (BASE BUILDING) Description: EXCLUDES CL51, 52 AND 53 SAMPLES FOR VERIFICATION : FULL-SIZE UNITS OF EACH TYPE OF CEILING ASSEMBLY INDICATED; IN SETS FOR EACH COLOR, TEXTURE, AND PATTERN SPECIFIED, SHOWING THE FULL RANGE OF VARIATIONS EXPECTED IN THESE CHARACTERISTICS. 1. 6-INCH-SQUARE SAMPLES OF EACH ACOUSTICAL PANEL TYPE, PATTERN, AND COLOR. 2. SET OF 12-INCH-LONG SAMPLES OF EXPOSED SUSPENSION SYSTEM MEMBERS, INCLUDING MOLDINGS, FOR EACH COLOR AND SYSTEM TYPE REQUIRED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10350 | Forwarded | For Review | 2020-08-26 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 09 51 00-6.0 From: DANIELLE SCOTT Final Due Date: 09/08/20 Subject: SUSPENDED CEILING SYSTEMS - SAMPLES (BASE BUILDING) Description: EXCLUDES CL51, 52 AND 53 SAMPLES FOR VERIFICATION : FULL-SIZE UNITS OF EACH TYPE OF CEILING ASSEMBLY INDICATED; IN SETS FOR EACH COLOR, TEXTURE, AND PATTERN SPECIFIED, SHOWING THE FULL RANGE OF VARIATIONS EXPECTED IN THESE CHARACTERISTICS. 1. 6-INCH-SQUARE SAMPLES OF EACH ACOUSTICAL PANEL TYPE, PATTERN, AND COLOR. 2. SET OF 12-INCH-LONG SAMPLES OF EXPOSED SUSPENSION SYSTEM MEMBERS, INCLUDING MOLDINGS, FOR EACH COLOR AND SYSTEM TYPE REQUIRED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 08092 | Review Response | Approved as Noted | 2020-09-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10761 | Responded and Closed | Approved as Noted | 2020-09-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 09 51 00-6 Samples (Base Building).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-26 |  | 09 51 00-6 Samples (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-14 |  | 09 51 00-6 Samples (Base Building)_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-14 |  | 09 51 00-6 Samples Base Building_POP.pdf
09 51 00-009-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-009-00 SUSPENDED CEILING SYSTEMS - Maintenance Data (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-24 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-08 07:00 | 2021-04-09 | 17 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-04-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12185 | Received | For Review | 2021-03-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-08 07:00 | Submittal Number: 09 51 00-9.0 From: DANIELLE SCOTT Final Due Date: 04/06/21 Subject: SUSPENDED CEILING SYSTEMS - MAINTENANCE DATA (BASE BUILDING) Description: MAINTENANCE DATA : FOR FINISHES TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 15771 | Forwarded | For Review | 2021-03-23 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-30 | Submittal Number: 09 51 00-9.0 From: DANIELLE SCOTT Final Due Date: 04/06/21 Subject: SUSPENDED CEILING SYSTEMS - MAINTENANCE DATA (BASE BUILDING) Description: MAINTENANCE DATA : FOR FINISHES TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12502 | Review Response | Approved | 2021-04-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16191 | Responded and Closed | Approved | 2021-04-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-23 |  | 09 51 00-9 Revision 0 SUSPENDED CEILING SYSTEMS - Maintenance Data (Base Building).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-23 |  | 09 51 00-9 Revision 0 SUSPENDED CEILING SYSTEMS - Maintenance Data (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-08 |  | 09 51 00-9 Revision 0 S CEILING SYSTEMS - Maintenance Data_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-23 |  | 09 51 00-9 Revision 0 SUSPENDED CEILING SYSTEMS - Maintenance Data (Base Building).pdf
09 51 00-012-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-012-00 SUSPENDED CEILING SYSTEMS - Standard ACT Shop Drawings (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-11 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-25 | 2020-12-01 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09384 | Received | For Review | 2020-11-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-11-25 | Submittal Number: 09 51 00-12.0 From: DANIELLE SCOTT Final Due Date: 11/25/20 Subject: SUSPENDED CEILING SYSTEMS - STANDARD ACT SHOP DRAWINGS (BASE BUILDING) Description: SHOP DRAWINGS FOR ALL STANDARD ACT CEILINGS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12384 | Forwarded | For Review | 2020-11-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-18 | Submittal Number: 09 51 00-12.0 From: DANIELLE SCOTT Final Due Date: 11/25/20 Subject: SUSPENDED CEILING SYSTEMS - STANDARD ACT SHOP DRAWINGS (BASE BUILDING) Description: SHOP DRAWINGS FOR ALL STANDARD ACT CEILINGS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 09788 | Review Response | Approved as Noted | 2020-12-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12870 | Responded and Closed | Approved as Noted | 2020-12-01 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-11 |  | 09 51 00-12 Suspended Ceiling Systems -Standard ACT Shops (Base Building).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-11 |  | 09 51 00-12 Suspended Ceiling Systems -Standard ACT Shops (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-01 |  | 09 51 00-12 Suspended Ceiling Systems -Standard ACT Shops (Base Building)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-11 |  | 09 51 00-12 Suspended Ceiling Systems -Standard ACT Shops (Base Building).pdf
09 51 00-013-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-013-00 SUSPENDED CEILING SYSTEMS - Product Data Metal Ceiling (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-19 | 2020-08-20 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07368 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-19 | Submittal Number: 09 51 00-13.0 From: DANIELLE SCOTT Final Due Date: 08/18/20 Subject: SUSPENDED CEILING SYSTEMS - PRODUCT DATA METAL CEILING (BASE BUILDING) Description: PRODUCT DATA FOR BASE BUILDING METAL CEILINGS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 09819 | Forwarded | For Review | 2020-08-05 | Populous SCA_CCA | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-08-12 | Submittal Number: 09 51 00-13.0 From: DANIELLE SCOTT Final Due Date: 08/18/20 Subject: SUSPENDED CEILING SYSTEMS - PRODUCT DATA METAL CEILING (BASE BUILDING) Description: PRODUCT DATA FOR BASE BUILDING METAL CEILINGS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 07633 | Review Response | Approved as Noted | 2020-08-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10163 | Responded and Closed | Approved as Noted | 2020-08-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-04 |  | 09 51 00-13 Suspended Ceiling Systems Submittal - Product Data - Metal.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-04 |  | 09 51 00-13 Suspended Ceiling Systems Submittal - Product Data - Metal.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-20 |  | 09 51 00-13 Suspended Ceiling Systems Submittal - Product Data - Metal_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-04 |  | 09 51 00-13 Suspended Ceiling Systems Submittal - Product Data - Metal.pdf
09 51 00-014-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-014-00 SUSPENDED CEILING SYSTEMS - Product Data Standard ACT (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-05 | Responded and Closed - Approved |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-19 | 2020-08-20 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07369 | Received | For Review | 2020-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-19 | Submittal Number: 09 51 00-14.0 From: DANIELLE SCOTT Final Due Date: 08/18/20 Subject: SUSPENDED CEILING SYSTEMS - PRODUCT DATA STANDARD ACT (BASE BUILDING) Description: PRODUCT DATA FOR BASE BUILDING STANDARD ACT CEILINGS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 09820 | Forwarded | For Review | 2020-08-05 | Populous SCA_CCA | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2020-08-12 | Submittal Number: 09 51 00-14.0 From: DANIELLE SCOTT Final Due Date: 08/18/20 Subject: SUSPENDED CEILING SYSTEMS - PRODUCT DATA STANDARD ACT (BASE BUILDING) Description: PRODUCT DATA FOR BASE BUILDING STANDARD ACT CEILINGS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 07638 | Review Response | Approved | 2020-08-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10177 | Responded and Closed | Approved | 2020-08-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-04 |  | 09 51 00-14 Suspended Ceiling Systems Submittal - Product Data - Standard ACT.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-04 |  | 09 51 00-14 Suspended Ceiling Systems Submittal - Product Data - Standard ACT.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-20 |  | 09 51 00-14 Suspended Ceiling Systems Submittal - Product Data - Standard ACT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-04 |  | 09 51 00-14 Suspended Ceiling Systems Submittal - Product Data - Standard ACT.pdf
09 51 00-015-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-015-00 SUSPENDED CEILING SYSTEMS - Maintenance Data (Premium & NHL) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-23 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-07 | 2021-05-10 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12742 | Received | For Review | 2021-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-07 | Submittal Number: 09 51 00-15.0 From: DANIELLE SCOTT Final Due Date: 03/04/21 Subject: SUSPENDED CEILING SYSTEMS - MAINTENANCE DATA (PREMIUM & NHL) Description: MAINTENANCE DATA : FOR FINISHES TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 16472 | Forwarded | For Review | 2021-04-23 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-30 | Submittal Number: 09 51 00-15.0 From: DANIELLE SCOTT Final Due Date: 03/04/21 Subject: SUSPENDED CEILING SYSTEMS - MAINTENANCE DATA (PREMIUM & NHL) Description: MAINTENANCE DATA : FOR FINISHES TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13006 | Review Response | Approved | 2021-05-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16831 | Responded and Closed | Approved | 2021-05-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-23 |  | 09 51 00-15 Revision 0 SUSPENDED CEILING SYSTEMS - Maintenance Data (Premium & NHL).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-23 |  | 09 51 00-15 Revision 0 SUSPENDED CEILING SYSTEMS - Maintenance Data (Premium & NHL).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-10 |  | 09 51 00-15 Revision 0 SUSPENDED CEILING SYSTEMS Maint. POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-23 |  | 09 51 00-15 Revision 0 SUSPENDED CEILING SYSTEMS - Maintenance Data (Premium & NHL).pdf
09 51 00-016-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-016-00 SUSPENDED CEILING SYSTEMS - Product Data (Premium Spaces & NHL) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-12 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-30 08:00 | 2020-12-02 | 21 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09385 | Received | For Review | 2020-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-11-30 08:00 | Submittal Number: 09 51 00-16.0 From: DANIELLE SCOTT Final Due Date: 11/25/20 Subject: SUSPENDED CEILING SYSTEMS - PRODUCT DATA (PREMIUM SPACES & NHL) Description: PRODUCT DATA : FOR ALL CEILING TYPES SPECIFIED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12385 | Forwarded | For Review | 2020-11-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-18 | Submittal Number: 09 51 00-16.0 From: DANIELLE SCOTT Final Due Date: 11/25/20 Subject: SUSPENDED CEILING SYSTEMS - PRODUCT DATA (PREMIUM SPACES & NHL) Description: PRODUCT DATA : FOR ALL CEILING TYPES SPECIFIED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 09813 | Review Response | Revise and Resubmit | 2020-12-02 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Appears to be an incorrect title or submittal. No ceilings in this package. | Info Exchange
| 12895 | Responded and Closed | Revise and Resubmit | 2020-12-02 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Appears to be an incorrect title or submittal. No ceilings in this package. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-11 |  | 09 51 00-16 Suspended Ceiling Systems - Product Data (Premium).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-11 |  | 09 51 00-16 Suspended Ceiling Systems - Product Data (Premium).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-02 |  | 09 51 00-16 Suspended Ceiling Systems - Product Data (Premium)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-11 |  | 09 51 00-16 Suspended Ceiling Systems - Product Data (Premium).pdf
09 51 00-016-01 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-016-01 SUSPENDED CEILING SYSTEMS - Product Data (Premium Spaces & NHL) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-03 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-17 | 2020-12-16 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09864 | Received | For Review | 2020-12-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-17 | Submittal Number: 09 51 00-16.1 From: DANIELLE SCOTT Final Due Date: 12/16/20 Subject: SUSPENDED CEILING SYSTEMS - PRODUCT DATA (PREMIUM SPACES & NHL) Description: PRODUCT DATA : FOR ALL CEILING TYPES SPECIFIED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12947 | Forwarded | For Review | 2020-12-03 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-10 | Submittal Number: 09 51 00-16.1 From: DANIELLE SCOTT Final Due Date: 12/16/20 Subject: SUSPENDED CEILING SYSTEMS - PRODUCT DATA (PREMIUM SPACES & NHL) Description: PRODUCT DATA : FOR ALL CEILING TYPES SPECIFIED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10192 | Review Response | Approved as Noted | 2020-12-16 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response | Info Exchange
| 13330 | Responded and Closed | Approved as Noted | 2020-12-16 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-02 |  | PCI Material Submittal - 09 51 00 R1 - Suspended Ceiling Systems - PRODUCT DATA.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-02 |  | PCI Material Submittal - 09 51 00 R1 - Suspended Ceiling Systems - PRODUCT DATA.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-16 |  | PCI Material Submittal - 09 51 00 R1 - Suspended Ceiling Systems - PRODUCT DATA_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-02 |  | PCI Material Submittal - 09 51 00 R1 - Suspended Ceiling Systems - PRODUCT DATA.pdf
09 51 00-025-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-025-00 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44 (NHL) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), David Riffel (ME Engineers) |  |  |  | 2020-12-21 | 2020-12-17 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09936 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-21 | Submittal Number: 09 51 00-25.0 From: DANIELLE SCOTT Final Due Date: 12/18/20 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL44 (NHL) Description: SHOP DRAWINGS FOR CL44. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13014 | Forwarded | For Review | 2020-12-07 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 09 51 00-25.0 From: DANIELLE SCOTT Final Due Date: 12/18/20 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL44 (NHL) Description: SHOP DRAWINGS FOR CL44. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13311 | Forwarded | For Review | 2020-12-15 | Populous SCA_CCA | David Riffel (ME Engineers) |  | Submittal Number: 09 51 00-25.0 From: DANIELLE SCOTT Final Due Date: 12/18/20 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL44 (NHL) Description: SHOP DRAWINGS FOR CL44. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10221 | Review Response | Revise and Resubmit | 2020-12-17 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Refer to submittal response for revised ceiling layout. | Info Exchange
| 13360 | Responded and Closed | Revise and Resubmit | 2020-12-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: Refer to submittal response for revised ceiling layout. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-04 |  | 09 51 00-25 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44 (NHL).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-04 |  | 09 51 00-25 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44 (NHL).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-04 |  | 09 51 00-25 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44 (NHL).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-17 |  | 09 51 00-25 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44 (NHL)_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-04 |  | 09 51 00-25 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44 (NHL).pdf
09 51 00-025-01 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-025-01 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44/45 (NHL) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-17 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Mark Lievens (ME Engineers), Jackie Lybarger (ME Engineers), David Riffel (ME Engineers) |  |  |  | 2021-03-03 | 2021-03-02 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11510 | Received | For Review | 2021-02-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-03 | Submittal Number: 09 51 00-25.1 From: DANIELLE SCOTT Final Due Date: 03/02/21 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL44/45 (NHL) Description: SHOP DRAWINGS FOR CL44. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 14904 | Forwarded | For Review | 2021-02-17 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-24 | Submittal Number: 09 51 00-25.1 From: DANIELLE SCOTT Final Due Date: 03/02/21 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL44/45 (NHL) Description: SHOP DRAWINGS FOR CL44. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 15048 | Forwarded | For Review | 2021-02-23 | Populous SCA_CCA | Mark Lievens (ME Engineers); Jackie Lybarger (ME Engineers); David Riffel (ME Engineers) |  | Submittal Number: 09 51 00-25.1 From: DANIELLE SCOTT Final Due Date: 03/02/21 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL44/45 (NHL) Description: SHOP DRAWINGS FOR CL44. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 11744 | Review Response | Approved as Noted | 2021-03-02 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15216 | Responded and Closed | Approved as Noted | 2021-03-02 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-16 |  | 09 51 00-25 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44 CL45 (NHL) Rev1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-16 |  | 09 51 00-25 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44 CL45 (NHL) Rev1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-16 |  | 09 51 00-25 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44 CL45 (NHL) Rev1.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-02 |  | 09 51 00-25 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44 CL45 (NHL) Rev1_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-16 |  | 09 51 00-25 SUSPENDED CEILING SYSTEMS - Shop Drawings CL44 CL45 (NHL) Rev1.pdf
09 51 00-026-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-026-00 SUSPENDED CEILING SYSTEMS - CL39 Sample (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-27 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-11 07:00 | 2020-09-14 | 19 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07776 | Received | For Review | 2020-08-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-11 07:00 | Submittal Number: 09 51 00-26.0 From: DANIELLE SCOTT Final Due Date: 09/09/20 Subject: SUSPENDED CEILING SYSTEMS - CL39 SAMPLE (BASE BUILDING) Description: CL 39 SAMPLE - BASE BUILDING Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10351 | Forwarded | For Review | 2020-08-26 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 09 51 00-26.0 From: DANIELLE SCOTT Final Due Date: 09/09/20 Subject: SUSPENDED CEILING SYSTEMS - CL39 SAMPLE (BASE BUILDING) Description: CL 39 SAMPLE - BASE BUILDING Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 08074 | Review Response | Approved | 2020-09-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10742 | Responded and Closed | Approved | 2020-09-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 09 51 00-26 Suspended Ceiling Systems - CL39 Samples (Base Building).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-26 |  | 09 51 00-26 Suspended Ceiling Systems - CL39 Samples (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-14 |  | 09 51 00-26 Suspended Ceiling Systems - CL39 Samples (Base Building)_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-26 |  | 09 51 00-26 Suspended Ceiling Systems - CL39 Samples (Base Building).pdf
09 51 00-027-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-027-00 SUSPENDED CEILING SYSTEMS - CL60 Sample (Premium Spaces) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-27 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-11 07:00 | 2020-09-14 | 19 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07777 | Received | For Review | 2020-08-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-11 07:00 | Submittal Number: 09 51 00-27.0 From: DANIELLE SCOTT Final Due Date: 09/09/20 Subject: SUSPENDED CEILING SYSTEMS - CL60 SAMPLE (PREMIUM SPACES) Description: CL60 SAMPLE (PREMIUM SPACES) Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10352 | Forwarded | For Review | 2020-08-26 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 09 51 00-27.0 From: DANIELLE SCOTT Final Due Date: 09/09/20 Subject: SUSPENDED CEILING SYSTEMS - CL60 SAMPLE (PREMIUM SPACES) Description: CL60 SAMPLE (PREMIUM SPACES) Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 08075 | Review Response | Approved | 2020-09-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10743 | Responded and Closed | Approved | 2020-09-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 09 51 00-27 Suspended Ceiling Systems - CL60 Samples (Premium Spaces).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-26 |  | 09 51 00-27 Suspended Ceiling Systems - CL60 Samples (Premium Spaces).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-14 |  | 09 51 00-27 Suspended Ceiling Systems - CL60 Samples (Premium Spaces)_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-26 |  | 09 51 00-27 Suspended Ceiling Systems - CL60 Samples (Premium Spaces).pdf
09 51 00-028-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-028-00 SUSPENDED CEILING SYSTEMS - CL21 Atrium Ceiling Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-21 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-05 | 2020-10-06 | 16 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08208 | Received | For Review | 2020-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-05 | Submittal Number: 09 51 00-28.0 From: DANIELLE SCOTT Final Due Date: 10/02/20 Subject: SUSPENDED CEILING SYSTEMS - CL21 ATRIUM CEILING SHOP DRAWINGS Description: SHOP DRAWINGS FOR CL21 IN THE ATRIUM. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10898 | Forwarded | For Review | 2020-09-18 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-25 | Submittal Number: 09 51 00-28.0 From: DANIELLE SCOTT Final Due Date: 10/02/20 Subject: SUSPENDED CEILING SYSTEMS - CL21 ATRIUM CEILING SHOP DRAWINGS Description: SHOP DRAWINGS FOR CL21 IN THE ATRIUM. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 11369 | Responded and Closed | Revise and Resubmit | 2020-10-06 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-18 |  | 09 51 00-28 Suspended Ceiling Systems - CL21 Atrium Ceiling Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-18 |  | 09 51 00-28 Suspended Ceiling Systems - CL21 Atrium Ceiling Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-06 |  | A3-05-1B - ENLARGED PLANS - ATRIUM CEILING.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-06 |  | 09 51 00-28 Suspended Ceiling Systems - Atrium Ceiling Shop_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-06 |  | A3-05-1A - ENLARGED PLANS - ATRIUM CEILING.pdf
09 51 00-028-01 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-028-01 SUSPENDED CEILING SYSTEMS - CL21 Atrium Ceiling Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-04 | 2020-12-01 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09518 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-04 | Submittal Number: 09 51 00-28.1 From: DANIELLE SCOTT Final Due Date: 12/01/20 Subject: SUSPENDED CEILING SYSTEMS - CL21 ATRIUM CEILING SHOP DRAWINGS Description: SHOP DRAWINGS FOR CL21 IN THE ATRIUM. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12538 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-24 | Submittal Number: 09 51 00-28.1 From: DANIELLE SCOTT Final Due Date: 12/01/20 Subject: SUSPENDED CEILING SYSTEMS - CL21 ATRIUM CEILING SHOP DRAWINGS Description: SHOP DRAWINGS FOR CL21 IN THE ATRIUM. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12853 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | 09 51 00-28 Revision 1 Suspended Ceiling Systems - CL21 Atrium Ceiling Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | 09 51 00-28 Revision 1 Suspended Ceiling Systems - CL21 Atrium Ceiling Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-01 |  | 09 51 00-28 Revision 1 Suspended Ceiling Systems - CL21 Atrium Ceiling Shop Drawings_POP.pdf
09 51 00-028-02 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-028-02 SUSPENDED CEILING SYSTEMS - CL21 Atrium Ceiling Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-23 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-15 | 2021-01-13 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-01-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10346 | Received | For Review | 2020-12-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-15 | Submittal Number: 09 51 00-28.2 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: SUSPENDED CEILING SYSTEMS - CL21 ATRIUM CEILING SHOP DRAWINGS Description: SHOP DRAWINGS (REVISION 2) FOR CL21 IN THE ATRIUM. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13515 | Forwarded | For Review | 2020-12-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-30 | Submittal Number: 09 51 00-28.2 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: SUSPENDED CEILING SYSTEMS - CL21 ATRIUM CEILING SHOP DRAWINGS Description: SHOP DRAWINGS (REVISION 2) FOR CL21 IN THE ATRIUM. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13883 | Responded and Closed | Approved as Noted | 2021-01-13 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-23 |  | 09 51 00-28 SUSPENDED CEILING SYSTEMS - CL21 Atrium Ceiling Shop Drawings R2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-23 |  | 09 51 00-28 SUSPENDED CEILING SYSTEMS - CL21 Atrium Ceiling Shop Drawings R2.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-01-13 |  | 09 51 00-28 SUSPENDED CEILING SYSTEMS - CL21 Atrium Ceiling Shop Drawings R2 - POP.pdf
09 51 00-029-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-029-00 SUSPENDED CEILING SYSTEMS - CL23 Sample (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-07 | 2020-10-08 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08287 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-07 | Submittal Number: 09 51 00-29.0 From: DANIELLE SCOTT Final Due Date: 10/06/20 Subject: SUSPENDED CEILING SYSTEMS - CL23 SAMPLE (BASE BUILDING) Description: SAMPLE COLOR FOR CL23. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10993 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-30 | Submittal Number: 09 51 00-29.0 From: DANIELLE SCOTT Final Due Date: 10/06/20 Subject: SUSPENDED CEILING SYSTEMS - CL23 SAMPLE (BASE BUILDING) Description: SAMPLE COLOR FOR CL23. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 08667 | Review Response | Approved as Noted | 2020-10-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11448 | Responded and Closed | Approved as Noted | 2020-10-08 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 09 51 00-29 Suspended Ceiling Systems - CL23 Samples (Base Building).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 09 51 00-29 Suspended Ceiling Systems - CL23 Samples (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-08 |  | 09 51 00-29 Suspended Ceiling Systems - CL23 Samples (Base Building)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-23 |  | 09 51 00-29 Suspended Ceiling Systems - CL23 Samples (Base Building).pdf
09 51 00-030-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-030-00 SUSPENDED CEILING SYSTEMS - CL51, CL52 and CL53 Sample (Base Building & Premium Space) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-09 | 2020-10-06 | 12 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08325 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-09 | Submittal Number: 09 51 00-30.0 From: DANIELLE SCOTT Final Due Date: 10/08/20 Subject: SUSPENDED CEILING SYSTEMS - CL51, CL52 AND CL53 SAMPLE (BASE BUILDING & PREMIUM SPACE) Description: SAMPLES FOR VERIFICATION : FULL-SIZE UNITS OF EACH TYPE OF CEILING ASSEMBLY INDICATED; IN SETS FOR EACH COLOR, TEXTURE, AND PATTERN SPECIFIED, SHOWING THE FULL RANGE OF VARIATIONS EXPECTED IN THESE CHARACTERISTICS. 1. 6-INCH-SQUARE SAMPLES OF EACH ACOUSTICAL PANEL TYPE, PATTERN, AND COLOR. 2. SET OF 12-INCH-LONG SAMPLES OF EXPOSED SUSPENSION SYSTEM MEMBERS, INCLUDING MOLDINGS, FOR EACH COLOR AND SYSTEM TYPE REQUIRED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 11034 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-01 | Submittal Number: 09 51 00-30.0 From: DANIELLE SCOTT Final Due Date: 10/08/20 Subject: SUSPENDED CEILING SYSTEMS - CL51, CL52 AND CL53 SAMPLE (BASE BUILDING & PREMIUM SPACE) Description: SAMPLES FOR VERIFICATION : FULL-SIZE UNITS OF EACH TYPE OF CEILING ASSEMBLY INDICATED; IN SETS FOR EACH COLOR, TEXTURE, AND PATTERN SPECIFIED, SHOWING THE FULL RANGE OF VARIATIONS EXPECTED IN THESE CHARACTERISTICS. 1. 6-INCH-SQUARE SAMPLES OF EACH ACOUSTICAL PANEL TYPE, PATTERN, AND COLOR. 2. SET OF 12-INCH-LONG SAMPLES OF EXPOSED SUSPENSION SYSTEM MEMBERS, INCLUDING MOLDINGS, FOR EACH COLOR AND SYSTEM TYPE REQUIRED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 08581 | Review Response | Approved as Noted | 2020-10-06 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. Ensure lay-in grid matches color of open-cell products. | Info Exchange
| 11343 | Responded and Closed | Approved as Noted | 2020-10-06 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. Ensure lay-in grid matches color of open-cell products. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 09 51 00-30 SUSPENDED CEILING SYSTEMS - CL51 CL52 and CL53 Sample (Base Building & Premium Space).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 09 51 00-30 SUSPENDED CEILING SYSTEMS - CL51 CL52 and CL53 Sample (Base Building & Premium Space).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-06 |  | 09 51 00-30 SUSPENDED CEILING SYSTEMS - CL51 CL52 and CL53 Sample_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-24 |  | 09 51 00-30 SUSPENDED CEILING SYSTEMS - CL51 CL52 and CL53 Sample (Base Building & Premium Space).pdf
09 51 00-031-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-031-00 SUSPENDED CEILING SYSTEMS - Wood Shop Drawings (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-14 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-06 | 2021-01-08 | 26 |  | Record Copies; Transfers; Submittals | 09 51 00-031-00-01 - 09 51 00-031-00 SUSPENDED CEILING SYSTEMS - Wood Shop Drawings (Base Building) | 26 |  | 2021-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10122 | Received | For Review | 2020-12-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-06 | Submittal Number: 09 51 00-31.0 From: DANIELLE SCOTT Final Due Date: 12/26/20 Subject: SUSPENDED CEILING SYSTEMS - WOOD SHOP DRAWINGS (BASE BUILDING) Description: SHOP DRAWINGS FOR WOOD CEILINGS IN THE BASE BUILDING. EXCLUDES CL40. CL40 WAS SUBMITTED AND APPROVED AS NOTED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13230 | Forwarded | For Review | 2020-12-14 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-21 | Submittal Number: 09 51 00-31.0 From: DANIELLE SCOTT Final Due Date: 12/26/20 Subject: SUSPENDED CEILING SYSTEMS - WOOD SHOP DRAWINGS (BASE BUILDING) Description: SHOP DRAWINGS FOR WOOD CEILINGS IN THE BASE BUILDING. EXCLUDES CL40. CL40 WAS SUBMITTED AND APPROVED AS NOTED. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10544 | Review Response | Approved as Noted/Resubmit | 2021-01-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13743 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-08 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attache submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-12 |  | 09 51 00-31 SUSPENDED CEILING SYSTEMS - Wood Shop Drawings (Base Building).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-12 |  | 09 51 00-31 SUSPENDED CEILING SYSTEMS - Wood Shop Drawings (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-08 |  | 09 51 00-31 SUSPENDED CEILING SYSTEMS - Wood Shop Drawings (Base Building) POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-12 |  | 09 51 00-31 SUSPENDED CEILING SYSTEMS - Wood Shop Drawings (Base Building).pdf
09 51 00-031-00-01 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-031-00 SUSPENDED CEILING SYSTEMS - Wood Shop Drawings (Base Building) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 51 00-031-00 - 09 51 00-031-00 SUSPENDED CEILING SYSTEMS - Wood Shop Drawings (Base Building) | -1 | 2021-01-22
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-12 |  | 09 51 00-31 SUSPENDED CEILING SYSTEMS - Wood Shop Drawings (Base Building).pdf
09 51 00-032-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-032-00 SUSPENDED CEILING SYSTEMS - CL23 Shop Drawings (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-21 | 2020-12-18 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-12-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09935 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-21 | Submittal Number: 09 51 00-32.0 From: DANIELLE SCOTT Final Due Date: 12/18/20 Subject: SUSPENDED CEILING SYSTEMS - CL23 SHOP DRAWINGS (BASE BUILDING) Description: BASE BUILDING CL23 CEILING SHOP DRAWINGS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13013 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 09 51 00-32.0 From: DANIELLE SCOTT Final Due Date: 12/18/20 Subject: SUSPENDED CEILING SYSTEMS - CL23 SHOP DRAWINGS (BASE BUILDING) Description: BASE BUILDING CL23 CEILING SHOP DRAWINGS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10252 | Review Response | Approved as Noted | 2020-12-18 | Kuebler Perry (Populous) | Populous SCA_CCA |  | REFER TO ATTACHED SUBMITTAL REVIEW | Info Exchange
| 13406 | Responded and Closed | Approved as Noted | 2020-12-18 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | REFER TO ATTACHED SUBMITTAL REVIEW | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-04 |  | 09 51 00-32 CL23 Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-04 |  | 09 51 00-32 CL23 Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-18 |  | 09 51 00-32 CL23 Shop Drawings_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-04 |  | 09 51 00-32 CL23 Shop Drawings.pdf
09 51 00-033-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-033-00 SUSPENDED CEILING SYSTEMS - 03.35.02 & 03.35.03 Main Con Restrooms Mockup Shop Drawings & Engineering | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-19 | 2020-10-19 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08527 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-19 | Submittal Number: 09 51 00-33.0 From: DANIELLE SCOTT Final Due Date: 10/16/20 Subject: SUSPENDED CEILING SYSTEMS - 03.35.02 & 03.35.03 MAIN CON RESTROOMS MOCKUP SHOP DRAWINGS & ENGINEERING Description: SHOP DRAWINGS AND STRUCTURAL DESIGN CALCULATIONS FOR MOCKUP ROOMS 03.35.02 & 03.35.03. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 11279 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-12 | Submittal Number: 09 51 00-33.0 From: DANIELLE SCOTT Final Due Date: 10/16/20 Subject: SUSPENDED CEILING SYSTEMS - 03.35.02 & 03.35.03 MAIN CON RESTROOMS MOCKUP SHOP DRAWINGS & ENGINEERING Description: SHOP DRAWINGS AND STRUCTURAL DESIGN CALCULATIONS FOR MOCKUP ROOMS 03.35.02 & 03.35.03. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 11521 | Forwarded | For Review | 2020-10-12 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2020-10-19 | Submittal Number: 09 51 00-33.0 From: DANIELLE SCOTT Final Due Date: 10/16/20 Subject: SUSPENDED CEILING SYSTEMS - 03.35.02 & 03.35.03 MAIN CON RESTROOMS MOCKUP SHOP DRAWINGS & ENGINEERING Description: SHOP DRAWINGS AND STRUCTURAL DESIGN CALCULATIONS FOR MOCKUP ROOMS 03.35.02 & 03.35.03. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 08866 | Review Response | Approved | 2020-10-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 11721 | Responded and Closed | Approved | 2020-10-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-02 |  | 09 51 00-33 Suspended Ceiling Systems - 03.35.02 & 03.35.03 Main Con Mockup Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-02 |  | 09 51 00-33 Suspended Ceiling Systems - 03.35.02 & 03.35.03 Main Con Mockup Shop Drawings.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-01 02:00 |  | 09 51 00-33 Suspended Ceiling Systems - 03.35.02 & 03.35.03 Main Con Mockup Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-19 |  | 09 51 00-33 Suspended Ceiling Systems - Mockup Shop Drawings_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-02 |  | 09 51 00-33 Suspended Ceiling Systems - 03.35.02 & 03.35.03 Main Con Mockup Shop Drawings.pdf
09 51 00-034-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-034-00 SUSPENDED CEILING SYSTEMS - Shop Drawings CL22 - Metal Ceiling | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-02-27 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11420 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-03-01 | Submittal Number: 09 51 00-34.0 From: DANIELLE SCOTT Final Due Date: 01/25/21 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL22 - METAL CEILING Description: SHOP DRAWINGS FOR CL22. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 14787 | Forwarded | For Review | 2021-02-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 09 51 00-34.0 From: DANIELLE SCOTT Final Due Date: 01/25/21 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL22 - METAL CEILING Description: SHOP DRAWINGS FOR CL22. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 11673 | Review Response | Revise and Resubmit | 2021-02-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 15129 | Responded and Closed | Revise and Resubmit | 2021-02-27 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 09 51 00-34 Suspended Ceiling Systems - CL22 Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-15 |  | 09 51 00-34 Suspended Ceiling Systems - CL22 Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-27 |  | 09 51 00-34 Suspended Ceiling Systems - CL22 Shop Drawings_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-15 |  | 09 51 00-34 Suspended Ceiling Systems - CL22 Shop Drawings.pdf
09 51 00-034-01 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-034-01 SUSPENDED CEILING SYSTEMS - Shop Drawings CL22 - Metal Ceiling | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-25 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kuebler Perry (Populous) |  |  |  | 2021-04-09 07:00 | 2021-04-05 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12235 | Received | For Review | 2021-03-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-04-09 07:00 | Submittal Number: 09 51 00-34.1 From: DANIELLE SCOTT Final Due Date: 04/07/21 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL22 - METAL CEILING Description: SHOP DRAWINGS FOR CL22. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 15825 | Forwarded | For Review | 2021-03-25 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-01 | Submittal Number: 09 51 00-34.1 From: DANIELLE SCOTT Final Due Date: 04/07/21 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL22 - METAL CEILING Description: SHOP DRAWINGS FOR CL22. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 16064 | Forwarded | For Review | 2021-04-05 | Josh Dobken (Populous) | Kuebler Perry (Populous) | 2021-04-09 | Submittal Number: 09 51 00-34.1 From: DANIELLE SCOTT Final Due Date: 04/07/21 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL22 - METAL CEILING Description: SHOP DRAWINGS FOR CL22. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12398 | Review Response | Approved as Noted | 2021-04-05 | Kuebler Perry (Populous) | Josh Dobken (Populous) |  | Refer to attached submittal review. | Info Exchange
| 16070 | Responded and Closed | Approved as Noted | 2021-04-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-24 |  | 09 51 00-34 Revision 1 SUSPENDED CEILING SYSTEMS - Shop Drawings CL22 - Metal Ceiling.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-24 |  | 09 51 00-34 Revision 1 SUSPENDED CEILING SYSTEMS - Shop Drawings CL22 - Metal Ceiling.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-23 02:00 |  | 09 51 00-34 Revision 1 SUSPENDED CEILING SYSTEMS - Shop Drawings CL22 - Metal Ceiling.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-23 |  | 09 51 00-34 Revision 1 SUSPENDED CEILING SYSTEMS - Shop Drawings CL22 - Metal Ceiling.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-05 |  | 09 51 00-34 Revision 1 SUSPENDED CEILING SYSTEMS_CL22 POP.pdf
09 51 00-035-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-035-00 SUSPENDED CEILING SYSTEMS - Shop Drawings CL05A, CL46, CL51, CL52, & CL53 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-04 | 2020-12-03 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09520 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-04 | Submittal Number: 09 51 00-35.0 From: DANIELLE SCOTT Final Due Date: 12/01/20 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL05A, CL46, CL51, CL52, & CL53 Description: SHOP DRAWINGS FOR CL05A, CL46, CL51, CL52, & CL53. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12540 | Forwarded | For Review | 2020-11-18 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-25 | Submittal Number: 09 51 00-35.0 From: DANIELLE SCOTT Final Due Date: 12/01/20 Subject: SUSPENDED CEILING SYSTEMS - SHOP DRAWINGS CL05A, CL46, CL51, CL52, & CL53 Description: SHOP DRAWINGS FOR CL05A, CL46, CL51, CL52, & CL53. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 09895 | Review Response | Approved as Noted | 2020-12-03 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12979 | Responded and Closed | Approved as Noted | 2020-12-03 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | 09 51 00-35 Suspended Ceiling Systems - Shop Drawings CL05A. CL46 Cl51 CL52 & CL53.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | 09 51 00-35 Suspended Ceiling Systems - Shop Drawings CL05A. CL46 Cl51 CL52 & CL53.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-03 |  | 09 51 00-35 Suspended Ceiling Systems - Shop Drawings CL05A. CL46 Cl51 CL52 & CL53_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-17 |  | 09 51 00-35 Suspended Ceiling Systems - Shop Drawings CL05A. CL46 Cl51 CL52 & CL53.pdf
09 51 00-036-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-036-00 SUSPENDED CEILING SYSTEMS - Standard ACT Shop Drawings (NHL & Premium Space) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-20 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10393 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-19 08:00 | Submittal Number: 09 51 00-36.0 From: DANIELLE SCOTT Final Due Date: 01/13/21 Subject: SUSPENDED CEILING SYSTEMS - STANDARD ACT SHOP DRAWINGS (NHL & PREMIUM SPACE) Description: SHOP DRAWINGS FOR CL10, CL43, & CL48. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13577 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 09 51 00-36.0 From: DANIELLE SCOTT Final Due Date: 01/13/21 Subject: SUSPENDED CEILING SYSTEMS - STANDARD ACT SHOP DRAWINGS (NHL & PREMIUM SPACE) Description: SHOP DRAWINGS FOR CL10, CL43, & CL48. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 14066 | Responded and Closed | Approved as Noted | 2021-01-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-30 |  | PCI Submittal - 09 51 00 - ACT Shop Drawings (002).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-30 |  | PCI Submittal - 09 51 00 - ACT Shop Drawings (002).pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-20 |  | PCI Submittal - 09 51 00 - ACT Shop Drawings_POP.pdf
09 51 00-037-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-037-00 SUSPENDED CEILING SYSTEMS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-05 08:00 | 2020-12-16 | 28 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2020-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09570 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-05 08:00 | Submittal Number: 09 51 00-37.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: SUSPENDED CEILING SYSTEMS - SAMPLES Description: CL12, CL44, CL48, CL5A, CL22 & CL23 PERF PATTERN, CL46 SAMPLES. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12599 | Forwarded | For Review | 2020-11-19 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 09 51 00-37.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: SUSPENDED CEILING SYSTEMS - SAMPLES Description: CL12, CL44, CL48, CL5A, CL22 & CL23 PERF PATTERN, CL46 SAMPLES. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10191 | Review Response | Approved as Noted | 2020-12-16 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response | Info Exchange
| 13329 | Responded and Closed | Approved as Noted | 2020-12-16 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 09 51 00-37 Suspended Ceiling Systems - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 09 51 00-37 Suspended Ceiling Systems - Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-16 |  | 09 51 00-37 Suspended Ceiling Systems - Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-18 |  | 09 51 00-37 Suspended Ceiling Systems - Samples.pdf
09 51 00-038-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-038-00 Suspended Ceiling Systems - CL40 Shop Drawings (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-12-02 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09609 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-07 | Submittal Number: 09 51 00-38.0 From: DANIELLE SCOTT Final Due Date: 12/03/20 Subject: SUSPENDED CEILING SYSTEMS - CL40 SHOP DRAWINGS (BASE BUILDING) Description: CL40 SHOP DRAWINGS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12644 | Forwarded | For Review | 2020-11-19 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 09 51 00-38.0 From: DANIELLE SCOTT Final Due Date: 12/03/20 Subject: SUSPENDED CEILING SYSTEMS - CL40 SHOP DRAWINGS (BASE BUILDING) Description: CL40 SHOP DRAWINGS. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 09834 | Review Response | Approved as Noted | 2020-12-02 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12918 | Responded and Closed | Approved as Noted | 2020-12-02 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-19 |  | 09 51 00-38 Suspended Ceiling Systems - CL40 Shop Drawings (Base Building).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-19 |  | 09 51 00-38 Suspended Ceiling Systems - CL40 Shop Drawings (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-02 |  | 09 51 00-38 Suspended Ceiling Systems - CL40 Shop Drawings (Base Building)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-19 |  | 09 51 00-38 Suspended Ceiling Systems - CL40 Shop Drawings (Base Building).pdf
09 51 00-039-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-039-00 Ceiling Sample CL42 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-16 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-08 | 2020-12-17 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10195 | Received | For Review | 2020-12-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-08 | Submittal Number: 09 51 00-39.0 From: DANIELLE SCOTT Final Due Date: 12/30/20 Subject: CEILING SAMPLE CL42 Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13333 | Forwarded | For Review | 2020-12-16 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-23 | Submittal Number: 09 51 00-39.0 From: DANIELLE SCOTT Final Due Date: 12/30/20 Subject: CEILING SAMPLE CL42 Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10225 | Review Response | Approved as Noted | 2020-12-17 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 13364 | Responded and Closed | Approved as Noted | 2020-12-17 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-16 |  | 09 51 00-39 Ceiling Sample CL42 (Base Building).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-16 |  | 09 51 00-39 Ceiling Sample CL42 (Base Building).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-17 |  | 09 51 13-10 Linear Wood Grill Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-16 |  | 09 51 00-39 Ceiling Sample CL42 (Base Building).pdf
09 51 00-040-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-040-00 SUSPENDED CEILING SYSTEMS - CL44, CL46, CL43, and CL24 Samples (Locker Rooms) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-11 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-05 | 2020-12-16 | 6 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10097 | Received | For Review | 2020-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-05 | Submittal Number: 09 51 00-40.0 From: DANIELLE SCOTT Final Due Date: 12/24/20 Subject: SUSPENDED CEILING SYSTEMS - CL44, CL46, CL43, AND CL24 SAMPLES (LOCKER ROOMS) Description: SAMPLES FOR CL44, CL46, CL43, AND CL24. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13198 | Forwarded | For Review | 2020-12-10 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-17 | Submittal Number: 09 51 00-40.0 From: DANIELLE SCOTT Final Due Date: 12/24/20 Subject: SUSPENDED CEILING SYSTEMS - CL44, CL46, CL43, AND CL24 SAMPLES (LOCKER ROOMS) Description: SAMPLES FOR CL44, CL46, CL43, AND CL24. Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 10193 | Review Response | Approved as Noted | 2020-12-16 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13331 | Responded and Closed | Approved as Noted | 2020-12-16 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-10 |  | 09 51 00-40 SUSPENDED CEILING SYSTEMS - CL44 CL46 43 and CL24 Samples (Locker Rooms).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-10 |  | 09 51 00-40 SUSPENDED CEILING SYSTEMS - CL44 CL46 43 and CL24 Samples (Locker Rooms).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-16 |  | 09 51 00-40 SUSPENDED CEILING SYSTEMS - CL44 CL46 43 and CL24 Samples (Locker Rooms)_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-12-10 |  | 09 51 00-40 SUSPENDED CEILING SYSTEMS - CL44 CL46 43 and CL24 Samples (Locker Rooms).pdf
09 51 00-041-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-041-00 CL41/M11 Soffit | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-03-01 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11421 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-03-01 | Submittal Number: 09 51 00-41.0 From: MIKE SOLFELT Final Due Date: 02/26/21 Subject: CL41/M11 SOFFIT Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 14788 | Forwarded | For Review | 2021-02-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 09 51 00-41.0 From: MIKE SOLFELT Final Due Date: 02/26/21 Subject: CL41/M11 SOFFIT Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 11705 | Review Response | Approved as Noted | 2021-03-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 15169 | Responded and Closed | Approved as Noted | 2021-03-01 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 09 51 00-41.0 CL41-M11 Soffit.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-15 |  | 09 51 00-41.0 CL41-M11 Soffit.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-01 |  | 09 51 00-41.0 CL41-M11 Soffit_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-15 |  | 09 51 00-41.0 CL41-M11 Soffit.pdf
09 51 00-042-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-042-00 CL41 East/West Con Stair | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-08 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-22 | 2021-03-24 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11834 | Received | For Review | 2021-03-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-03-22 | Submittal Number: 09 51 00-42.0 From: MIKE SOLFELT Final Due Date: 03/22/21 Subject: CL41 EAST/WEST CON STAIR Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 15341 | Forwarded | For Review | 2021-03-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-15 | Submittal Number: 09 51 00-42.0 From: MIKE SOLFELT Final Due Date: 03/22/21 Subject: CL41 EAST/WEST CON STAIR Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12214 | Review Response | Approved as Noted | 2021-03-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 15804 | Responded and Closed | Approved as Noted | 2021-03-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-08 |  | 09 51 00 -42 CL41.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-08 |  | 09 51 00 -42 CL41.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-24 |  | 09 51 00 -42 CL41_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-03-08 |  | 09 51 00 -42 CL41.pdf
09 51 00-043-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-043-00 CL22 Engineering & Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-08 | Review Response - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-22 | 2021-01-08 | 1 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10523 | Received | For Review | 2021-01-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-22 | Submittal Number: 09 51 00-43.0 From: DANIELLE SCOTT Final Due Date: 01/21/21 Subject: CL22 ENGINEERING & CALCULATIONS Description: CL22 STRUCTURAL CALCULATIONS Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13726 | Forwarded | For Review | 2021-01-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-01-15 | Submittal Number: 09 51 00-43.0 From: DANIELLE SCOTT Final Due Date: 01/21/21 Subject: CL22 ENGINEERING & CALCULATIONS Description: CL22 STRUCTURAL CALCULATIONS Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13773 | Responded and Closed | Approved | 2021-01-08 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 10838 | Review Response | Revise and Resubmit | 2021-01-13 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous); Shaina Burris (Populous) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-07 |  | 09 51 00-43 CL22 Engineering & Calculations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-07 |  | 09 51 00-43 CL22 Engineering & Calculations.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-01-08 |  | 09 51 00-43 CL22 Engineering & Calculations-pop.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-01-06 02:00 |  | 09 51 00-43 CL22 Engineering & Calculations.pdf
09 51 00-043-01 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-043-01 CL22 Engineering & Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-26 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-09 | 2021-01-28 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-01-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10962 | Received | For Review | 2021-01-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-02-09 | Submittal Number: 09 51 00-43.1 From: DANIELLE SCOTT Final Due Date: 02/08/21 Subject: CL22 ENGINEERING & CALCULATIONS Description: CL22 STRUCTURAL CALCULATIONS Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 14236 | Forwarded | For Review | 2021-01-26 | Danielle Scott | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-02 | Submittal Number: 09 51 00-43.1 From: DANIELLE SCOTT Final Due Date: 02/08/21 Subject: CL22 ENGINEERING & CALCULATIONS Description: CL22 STRUCTURAL CALCULATIONS Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 11027 | Review Response | Approved as Noted | 2021-01-27 | Franz Kogler (Thornton Tomasetti) | Danielle Scott |  | See review comments on attachment | Info Exchange
| 14323 | Responded and Closed | Approved as Noted | 2021-01-28 | Danielle Scott | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 09 51 00-43 R1 CL22 Engineering & Calculations.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-01-25 |  | 09 51 00-43 R1 CL22 Engineering & Calculations.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-01-25 |  | 09 51 00-43 R1 CL22 Engineering & Calculations.pdf
| Responded and Closed |  | Danielle Scott | 1 | 2021-01-27 |  | 09 51 00-43 R1 CL22 Engineering & Calculations_TTReview.pdf
| Responded and Closed |  | Danielle Scott | 1 | 2021-01-28 |  | 09 51 00-43 R1 CL22 Engineering & Calculations_TTReview-POP.pdf
09 51 00-044-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-044-00 Ceiling Systems - CL1 Amazon Ceiling Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-29 | 2021-04-19 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-04-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12602 | Received | For Review | 2021-04-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-04-29 | Submittal Number: 09 51 00-44.0 From: DANIELLE SCOTT Final Due Date: 04/27/21 Subject: CEILING SYSTEMS - CL1 AMAZON CEILING SHOP DRAWINGS Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 16321 | Forwarded | For Review | 2021-04-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-22 | Submittal Number: 09 51 00-44.0 From: DANIELLE SCOTT Final Due Date: 04/27/21 Subject: CEILING SYSTEMS - CL1 AMAZON CEILING SHOP DRAWINGS Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12643 | Review Response | Approved as Noted | 2021-04-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 16360 | Responded and Closed | Approved as Noted | 2021-04-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-14 |  | 09 51 00-44 Revision 0 Ceiling Systems - CL1 Amazon Ceiling Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-14 |  | 09 51 00-44 Revision 0 Ceiling Systems - CL1 Amazon Ceiling Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-19 |  | 09 51 00-44 Revision 0 Ceiling Systems - CL1 Amazon POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-14 |  | 09 51 00-44 Revision 0 Ceiling Systems - CL1 Amazon Ceiling Shop Drawings.pdf
09 51 00-045-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-045-00 CL22 Shop Drawings - Upper Con Area A and B Added Scope | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-06 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kuebler Perry (Populous) |  |  |  | 2021-05-20 | 2021-05-09 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-05-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12965 | Received | For Review | 2021-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-20 | Submittal Number: 09 51 00-45.0 From: KIM DOWALIBY Final Due Date: 05/19/21 Subject: CL22 SHOP DRAWINGS - UPPER CON AREA A AND B ADDED SCOPE Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 16772 | Forwarded | For Review | 2021-05-06 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 09 51 00-45.0 From: KIM DOWALIBY Final Due Date: 05/19/21 Subject: CL22 SHOP DRAWINGS - UPPER CON AREA A AND B ADDED SCOPE Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 16774 | Forwarded | For Review | 2021-05-06 | Populous SCA_CCA | Kuebler Perry (Populous) | 2021-05-13 | Submittal Number: 09 51 00-45.0 From: KIM DOWALIBY Final Due Date: 05/19/21 Subject: CL22 SHOP DRAWINGS - UPPER CON AREA A AND B ADDED SCOPE Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12983 | Review Response | Approved | 2021-05-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16807 | Responded and Closed | Approved | 2021-05-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-05 |  | 09 51 00-45 - CL22 Shop Drawings - Upper Con Area A and B Added Scope.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-05 |  | 09 51 00-45 - CL22 Shop Drawings - Upper Con Area A and B Added Scope.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-05 |  | 09 51 00-45 - CL22 Shop Drawings - Upper Con Area A and B Added Scope.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-09 |  | 09 51 00-45 - CL22 Shop Drawings - Upper Con Area A and B Added Scope_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-05 |  | 09 51 00-45 - CL22 Shop Drawings - Upper Con Area A and B Added Scope.pdf
09 51 00-046-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-046-00 CL22 Shop Drawings - Main Con Food Service Added Scope | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-17 | 2021-05-09 | 7 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-05-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12874 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-17 | Submittal Number: 09 51 00-46.0 From: KIM DOWALIBY Final Due Date: 05/14/21 Subject: CL22 SHOP DRAWINGS - MAIN CON FOOD SERVICE ADDED SCOPE Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 16656 | Forwarded | For Review | 2021-04-30 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-07 | Submittal Number: 09 51 00-46.0 From: KIM DOWALIBY Final Due Date: 05/14/21 Subject: CL22 SHOP DRAWINGS - MAIN CON FOOD SERVICE ADDED SCOPE Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12984 | Review Response | Approved as Noted | 2021-05-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 16808 | Responded and Closed | Approved as Noted | 2021-05-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-30 |  | 09 51 00-46 - CL22 Shop Drawings - Main Con Food Service Added Scope.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-30 |  | 09 51 00-46 - CL22 Shop Drawings - Main Con Food Service Added Scope.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-09 |  | 09 51 00-46 - CL22 Shop Drawings - Main Con Food Service Added Scope_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-30 |  | 09 51 00-46 - CL22 Shop Drawings - Main Con Food Service Added Scope.pdf
09 51 00-047-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-047-00 SUSPENDED CEILING SYSTEM - CL1 Sample - Updated per CCD088 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-18 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13035 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-25 | Submittal Number: 09 51 00-47.0 From: KIM DOWALIBY Final Due Date: 05/24/21 Subject: SUSPENDED CEILING SYSTEM - CL1 SAMPLE - UPDATED PER CCD088 Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 16868 | Forwarded | For Review | 2021-05-11 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-18 | Submittal Number: 09 51 00-47.0 From: KIM DOWALIBY Final Due Date: 05/24/21 Subject: SUSPENDED CEILING SYSTEM - CL1 SAMPLE - UPDATED PER CCD088 Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13156 | Review Response | Approved | 2021-05-18 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 17024 | Responded and Closed | Approved | 2021-05-18 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 09 51 00-47 - SUSPENDED CEILING SYSTEM - CL1 Sample - Updated per CCD088.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-10 |  | 09 51 00-47 - SUSPENDED CEILING SYSTEM - CL1 Sample - Updated per CCD088.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-18 |  | 09 51 00-47 - SUSPENDED CEILING SYSTEM - CL1_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-10 |  | 09 51 00-47 - SUSPENDED CEILING SYSTEM - CL1 Sample - Updated per CCD088.pdf
09 51 00-048-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-048-00 CL22 Attachment to Ring Beam Alternate Condition Stamped Shop Drawing | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matt Ross (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-29 | 2021-04-28 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12603 | Received | For Review | 2021-04-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-04-29 | Submittal Number: 09 51 00-48.0 From: DANIELLE SCOTT Final Due Date: 04/28/21 Subject: CL22 ATTACHMENT TO RING BEAM ALTERNATE CONDITION STAMPED SHOP DRAWING Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 16322 | Forwarded | For Review | 2021-04-15 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-22 | Submittal Number: 09 51 00-48.0 From: DANIELLE SCOTT Final Due Date: 04/28/21 Subject: CL22 ATTACHMENT TO RING BEAM ALTERNATE CONDITION STAMPED SHOP DRAWING Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 16552 | Forwarded | For Review | 2021-04-27 | Danielle Scott | Matt Ross (Thornton Tomasetti) |  | Submittal Number: 09 51 00-48.0 From: DANIELLE SCOTT Final Due Date: 04/28/21 Subject: CL22 ATTACHMENT TO RING BEAM ALTERNATE CONDITION STAMPED SHOP DRAWING Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 16574 | Forwarded | For Review | 2021-04-27 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-29 | Submittal Number: 09 51 00-48.0 From: DANIELLE SCOTT Final Due Date: 04/28/21 Subject: CL22 ATTACHMENT TO RING BEAM ALTERNATE CONDITION STAMPED SHOP DRAWING Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 12843 | Review Response | Approved as Noted | 2021-04-27 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See attached comments in submittal. | Info Exchange
| 16621 | Responded and Closed | Approved as Noted | 2021-04-28 | Danielle Scott | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attached comments in submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-14 |  | 09 51 00-48 Revision 0 CL22 Attachment to Ring Beam Alternate Condition Stamped Shop Drawing.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-04-14 |  | 09 51 00-48 Revision 0 CL22 Attachment to Ring Beam Alternate Condition Stamped Shop Drawing.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-04-14 |  | 09 51 00-48 Revision 0 CL22 Attachment to Ring Beam Alternate Condition Stamped Shop Drawing.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-13 02:00 |  | 09 51 00-48 Revision 0 CL22 Attachment to Ring Beam Alternate Condition Stamped Shop Drawing.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-04-13 02:00 |  | 09 51 00-48 Revision 0 CL22 Attachment to Ring Beam Alternate Condition Stamped Shop Drawing.pdf
| Responded and Closed |  | Danielle Scott | 1 | 2021-04-28 02:00 |  | 09 51 00-48 Revision 0 CL22 Attachment to Ring Beam Alternate Condition Stamped Shop Drawing_TTReview_POP.pdf
09 51 00-049-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-049-00 SUSPENDED CEILING SYSTEM - CL22 Supplemental Attachment Detail | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-10 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-05-24 | 2021-05-20 | 11 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-05-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13011 | Received | For Review | 2021-05-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-05-24 | Submittal Number: 09 51 00-49.0 From: KIM DOWALIBY Final Due Date: 05/24/21 Subject: 09 51 00 - SUSPENDED CEILING SYSTEM - CL22 SUPPLEMENTAL ATTACHMENT DETAIL Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 16834 | Forwarded | For Review | 2021-05-10 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-17 | Submittal Number: 09 51 00-49.0 From: KIM DOWALIBY Final Due Date: 05/24/21 Subject: 09 51 00 - SUSPENDED CEILING SYSTEM - CL22 SUPPLEMENTAL ATTACHMENT DETAIL Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 17049 | Forwarded | For Review | 2021-05-19 | Chad Francis (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) |  | Submittal Number: 09 51 00-49.0 From: KIM DOWALIBY Final Due Date: 05/24/21 Subject: 09 51 00 - SUSPENDED CEILING SYSTEM - CL22 SUPPLEMENTAL ATTACHMENT DETAIL Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13197 | Review Response | Approved as Noted/Resubmit | 2021-05-19 | Franz Kogler (Thornton Tomasetti) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Kim Dowaliby |  | Exceptions noted, see attached. TT-FK ¦ 2021-05-19 | Info Exchange
| 17085 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED, SUBMIT ITEMS LISTED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 09 51 00-49 - SUSPENDED CEILING SYSTEM - CL22 Supplemental Attachment Detail.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-05-10 |  | 09 51 00-49 - SUSPENDED CEILING SYSTEM - CL22 Supplemental Attachment Detail.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2021-05-10 |  | 09 51 00-49 - SUSPENDED CEILING SYSTEM - CL22 Supplemental Attachment Detail.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-05-19 |  | 09 51 00-49 - SUSPENDED CEILING SYSTEM - CL22 Supplemental Attachment Detail_TTReview.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-20 |  | 09 51 00-49 - SUSPENDED CEILING SYSTEM - CL22 Supplemental Attachment Detail_TTReview_POP.pdf
09 51 00-049-01 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-049-01 SUSPENDED CEILING SYSTEM - CL22 Supplemental Attachment Detail | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-15 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2021-06-29 | 2021-06-29 | 15 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-06-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13532 | Received | For Review | 2021-06-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-29 | Submittal Number: 09 51 00-49.1 From: KIM DOWALIBY Final Due Date: 06/29/21 Subject: 09 51 00 - SUSPENDED CEILING SYSTEM - CL22 SUPPLEMENTAL ATTACHMENT DETAIL Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 17508 | Forwarded | For Review | 2021-06-15 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-22 | Submittal Number: 09 51 00-49.1 From: KIM DOWALIBY Final Due Date: 06/29/21 Subject: 09 51 00 - SUSPENDED CEILING SYSTEM - CL22 SUPPLEMENTAL ATTACHMENT DETAIL Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 17582 | Forwarded | For Review | 2021-06-21 | Chad Francis (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) | 2021-06-24 | Submittal Number: 09 51 00-49.1 From: KIM DOWALIBY Final Due Date: 06/29/21 Subject: 09 51 00 - SUSPENDED CEILING SYSTEM - CL22 SUPPLEMENTAL ATTACHMENT DETAIL Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13711 | Review Response | Approved | 2021-06-21 | Franz Kogler (Thornton Tomasetti) | Chad Francis (Populous) |  | No exceptions TT-FK ¦ 2021-06-21 | Info Exchange
| 17748 | Responded and Closed | Approved | 2021-06-29 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-15 |  | 09 51 00-49.1 - SUSPENDED CEILING SYSTEM - CL22 Supplemental Attachment Detail Rev 1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-15 |  | 09 51 00-49.1 - SUSPENDED CEILING SYSTEM - CL22 Supplemental Attachment Detail Rev 1.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2021-06-15 |  | 09 51 00-49.1 - SUSPENDED CEILING SYSTEM - CL22 Supplemental Attachment Detail Rev 1.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-06-15 |  | 09 51 00-49.1 - SUSPENDED CEILING SYSTEM - CL22 Supplemental Attachment Detail Rev 1.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-29 |  | 09 51 00-49.1 - SUSPENDED CEILING SYSTEM - CL22 Supp Attach Detail R1_TT_POP.pdf
09 51 00-050-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-050-00 SUSPENDED CEILING SAMPLE - CL22 Matte Black Sample Added Scope | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-06-04 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13152 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-02 07:00 | Submittal Number: 09 51 00-50.0 From: KIM DOWALIBY Final Due Date: 06/01/21 Subject: SUSPENDED CEILING SAMPLE - CL22 MATTE BLACK SAMPLE ADDED SCOPE Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 17013 | Forwarded | For Review | 2021-05-18 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-25 | Submittal Number: 09 51 00-50.0 From: KIM DOWALIBY Final Due Date: 06/01/21 Subject: SUSPENDED CEILING SAMPLE - CL22 MATTE BLACK SAMPLE ADDED SCOPE Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13401 | Review Response | Approved | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17332 | Responded and Closed | Approved | 2021-06-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | 09 51 00-50 - SUSPENDED CEILING SAMPLE - CL22 Matte Black Sample Added Scope.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-18 |  | 09 51 00-50 - SUSPENDED CEILING SAMPLE - CL22 Matte Black Sample Added Scope.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-04 |  | 09 51 00-50 - SUSPENDED CEILING SAMPLE - CL22 Matte Black_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-18 |  | 09 51 00-50 - SUSPENDED CEILING SAMPLE - CL22 Matte Black Sample Added Scope.pdf
09 51 00-051-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-051-00 SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-01 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-14 | 2021-07-02 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13746 | Received | For Review | 2021-07-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-14 | Submittal Number: 09 51 00-51.0 From: KIM DOWALIBY Final Due Date: 07/14/21 Subject: SUSPENDED CEILING SYSTEM - CL13 COORS LIGHT BAR - SHOP DRAWINGS Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 17795 | Forwarded | For Review | 2021-07-01 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-08 | Submittal Number: 09 51 00-51.0 From: KIM DOWALIBY Final Due Date: 07/14/21 Subject: SUSPENDED CEILING SYSTEM - CL13 COORS LIGHT BAR - SHOP DRAWINGS Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 17829 | Responded and Closed | Approved as Noted | 2021-07-02 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-30 |  | 09 51 00-51 - SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-30 |  | 09 51 00-51 - SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Shop Drawings.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-02 |  | 09 51 00-51 - SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Shop Drawings_POP.pdf
09 51 00-052-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-052-00 SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Product Data, Maintenance Data, and Sample Warranty. | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-07 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-21 | 2021-07-14 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13816 | Received | For Review | 2021-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-21 | Submittal Number: 09 51 00-52.0 From: KIM DOWALIBY Final Due Date: 07/20/21 Subject: SUSPENDED CEILING SYSTEM - CL13 COORS LIGHT BAR - PRODUCT DATA, MAINTENANCE DATA, AND SAMPLE WARRANTY. Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 17887 | Forwarded | For Review | 2021-07-07 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-14 | Submittal Number: 09 51 00-52.0 From: KIM DOWALIBY Final Due Date: 07/20/21 Subject: SUSPENDED CEILING SYSTEM - CL13 COORS LIGHT BAR - PRODUCT DATA, MAINTENANCE DATA, AND SAMPLE WARRANTY. Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 18037 | Responded and Closed | Approved | 2021-07-14 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-06 |  | 09 51 00-52 - SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Product Data Maintenance Data and Sample Warranty..pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-06 |  | 09 51 00-52 - SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Product Data Maintenance Data and Sample Warranty..pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-14 |  | 09 51 00-52 - SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Product Data Maintenance Data and Sample Warranty._POP.pdf
09 51 00-053-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | 09 51 00-053-00 SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-28 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-12 | 2021-06-30 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-06-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13679 | Received | For Review | 2021-06-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-12 | Submittal Number: 09 51 00-53.0 From: KIM DOWALIBY Final Due Date: 07/12/21 Subject: SUSPENDED CEILING SYSTEM - CL13 COORS LIGHT BAR - SAMPLES Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 17714 | Forwarded | For Review | 2021-06-28 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-05 | Submittal Number: 09 51 00-53.0 From: KIM DOWALIBY Final Due Date: 07/12/21 Subject: SUSPENDED CEILING SYSTEM - CL13 COORS LIGHT BAR - SAMPLES Description: Spec Section: 09 51 00 - SUSPENDED CEILING SYSTEMS Status: OPEN | Info Exchange
| 13723 | Review Response | Approved | 2021-06-30 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17766 | Responded and Closed | Approved | 2021-06-30 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-28 |  | 09 51 00-53 - SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-28 |  | 09 51 00-53 - SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-29 23:00 |  | 09 51 00-53 - SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-06-27 23:00 |  | 09 51 00-53 - SUSPENDED CEILING SYSTEM - CL13 Coors Light Bar - Samples.pdf
09 51 13-001-00 | 09 51 13 | 09 51 13-001-00 CL41/42 Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-21 | 2020-12-17 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09947 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-12-21 | Submittal Number: 09 51 13-1.0 From: MIKE SOLFELT Final Due Date: 12/17/20 Subject: CL41/42 SAMPLES Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 13027 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 09 51 13-1.0 From: MIKE SOLFELT Final Due Date: 12/17/20 Subject: CL41/42 SAMPLES Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 10223 | Review Response | Approved as Noted | 2020-12-17 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 13362 | Responded and Closed | Approved as Noted | 2020-12-17 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 09 51 13-10 Linear Wood Grill Samples (1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-07 |  | 09 51 13-10 Linear Wood Grill Samples (1).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-17 |  | 09 51 13-10 Linear Wood Grill Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-07 |  | 09 51 13-10 Linear Wood Grill Samples (1).pdf
09 51 13-002-00 | 09 51 13 | 09 51 13-002-00 Acoustic Baffles - Shop Drawings | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-21 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Brian Elwell (Idibri) |  |  |  | 2021-01-13 | 2021-01-12 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2021-01-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10278 | Received | For Review | 2020-12-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Alex Brown (M.A. Mortenson Company) | 2021-01-13 | Submittal Number: 09 51 13-2.0 From: ALEX BROWN Final Due Date: 01/06/21 Subject: ACOUSTIC BAFFLES - SHOP DRAWINGS Description: 2020.12.19AB: PLEASE SEE THE ATTACHED SHOP DRAWINGS FOR THE ACOUSTIC BAFFLES. Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 13428 | Forwarded | For Review | 2020-12-21 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-28 | Submittal Number: 09 51 13-2.0 From: ALEX BROWN Final Due Date: 01/06/21 Subject: ACOUSTIC BAFFLES - SHOP DRAWINGS Description: 2020.12.19AB: PLEASE SEE THE ATTACHED SHOP DRAWINGS FOR THE ACOUSTIC BAFFLES. Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 13622 | Forwarded | For Review | 2021-01-05 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2021-01-12 | Submittal Number: 09 51 13-2.0 From: ALEX BROWN Final Due Date: 01/06/21 Subject: ACOUSTIC BAFFLES - SHOP DRAWINGS Description: 2020.12.19AB: PLEASE SEE THE ATTACHED SHOP DRAWINGS FOR THE ACOUSTIC BAFFLES. Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 10641 | Review Response | Approved as Noted | 2021-01-11 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | MAM provided additional information regarding this submittal on 1/4/2021. Approval is only in conjunction with additional materials provided, which have been appended to the submittal return for reference. | Info Exchange
| 13866 | Forwarded | For Review | 2021-01-12 | Kelsea Conkright (Populous) | Brian Elwell (Idibri) |  | Submittal Number: 09 51 13-2.0 From: ALEX BROWN Final Due Date: 01/06/21 Subject: ACOUSTIC BAFFLES - SHOP DRAWINGS Description: 2020.12.19AB: PLEASE SEE THE ATTACHED SHOP DRAWINGS FOR THE ACOUSTIC BAFFLES. Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 10662 | Review Response | Approved as Noted | 2021-01-12 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13879 | Responded and Closed | Approved as Noted | 2021-01-12 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: MAM provided additional information regarding this submittal on 1/4/2021. Approval is only in conjunction with additional materials provided, which have been appended to the submittal return for reference. Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-19 |  | 09 51 13-2_Acoustic Baffles Shops_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-19 |  | 09 51 13-2_Acoustic Baffles Shops_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-12-18 02:00 |  | 09 51 13-2_Acoustic Baffles Shops_MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-12-18 |  | 09 51 13-2_Acoustic Baffles Shops_MAM.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-01-12 |  | 09 51 13-2_Acoustic Baffles Shops_MAM_TT_POP.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-12 |  | 09 51 13-2_Acoustic Baffles Shops_MAM_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-19 |  | 09 51 13-2_Acoustic Baffles Shops_MAM.pdf
09 51 13-003-00 | 09 51 13 | 09 51 13-003-00 Acoustic Baffles - Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-21 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Brian Elwell (Idibri) |  |  |  | 2021-01-13 | 2021-01-12 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2021-01-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10285 | Received | For Review | 2020-12-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Alex Brown (M.A. Mortenson Company) | 2021-01-13 | Submittal Number: 09 51 13-3.0 From: ALEX BROWN Final Due Date: 01/06/21 Subject: ACOUSTIC BAFFLES - CALCULATIONS Description: 2020.12.19AB: PLEASE SEE THE ATTACHED ACOUSTIC BAFFLE CALCULATIONS FOR REVIEW AND APPROVAL. Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 13442 | Forwarded | For Review | 2020-12-21 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-28 | Submittal Number: 09 51 13-3.0 From: ALEX BROWN Final Due Date: 01/06/21 Subject: ACOUSTIC BAFFLES - CALCULATIONS Description: 2020.12.19AB: PLEASE SEE THE ATTACHED ACOUSTIC BAFFLE CALCULATIONS FOR REVIEW AND APPROVAL. Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 13662 | Forwarded | For Review | 2021-01-05 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2021-01-12 | Submittal Number: 09 51 13-3.0 From: ALEX BROWN Final Due Date: 01/06/21 Subject: ACOUSTIC BAFFLES - CALCULATIONS Description: 2020.12.19AB: PLEASE SEE THE ATTACHED ACOUSTIC BAFFLE CALCULATIONS FOR REVIEW AND APPROVAL. Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 10640 | Review Response | Approved as Noted | 2021-01-11 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | MAM provided additional information regarding this submittal on 1/4/2021. Approval is only in conjunction with additional materials provided, which have been appended to the submittal return for reference. | Info Exchange
| 13867 | Forwarded | For Review | 2021-01-12 | Kelsea Conkright (Populous) | Brian Elwell (Idibri) |  | Submittal Number: 09 51 13-3.0 From: ALEX BROWN Final Due Date: 01/06/21 Subject: ACOUSTIC BAFFLES - CALCULATIONS Description: 2020.12.19AB: PLEASE SEE THE ATTACHED ACOUSTIC BAFFLE CALCULATIONS FOR REVIEW AND APPROVAL. Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 10661 | Review Response | Approved as Noted | 2021-01-12 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13878 | Responded and Closed | Approved as Noted | 2021-01-12 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: MAM provided additional information regarding this submittal on 1/4/2021. Approval is only in conjunction with additional materials provided, which have been appended to the submittal return for reference. Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-21 |  | 09 51 13-3_Acoustic Baffles Calcs_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-21 |  | 09 51 13-3_Acoustic Baffles Calcs_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-12-20 02:00 |  | 09 51 13-3_Acoustic Baffles Calcs_MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-12-20 |  | 09 51 13-3_Acoustic Baffles Calcs_MAM.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-01-12 |  | 09 51 13-3_Acoustic Baffles Calcs_MAM_TT_POP.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-12 |  | 09 51 13-3_Acoustic Baffles Calcs_MAM_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-21 |  | 09 51 13-3_Acoustic Baffles Calcs_MAM.pdf
09 51 13-004-00 | 09 51 13 | 09 51 13-004-00 Sound Absorbing Acoustic Baffles - CL12 Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian Elwell (Idibri), Franz Kogler (Thornton Tomasetti) |  |  |  | 2021-02-08 | 2021-02-09 | 16 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10911 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-08 | Submittal Number: 09 51 13-4.0 From: DANIELLE SCOTT Final Due Date: 02/05/21 Subject: SOUND ABSORBING ACOUSTIC BAFFLES - CL12 PRODUCT DATA Description: PRODUCT DATA CL12 Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 14166 | Forwarded | For Review | 2021-01-22 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-29 | Submittal Number: 09 51 13-4.0 From: DANIELLE SCOTT Final Due Date: 02/05/21 Subject: SOUND ABSORBING ACOUSTIC BAFFLES - CL12 PRODUCT DATA Description: PRODUCT DATA CL12 Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 14535 | Forwarded | For Review | 2021-02-05 | Kelsea Conkright (Populous) | Brian Elwell (Idibri); Franz Kogler (Thornton Tomasetti) |  | Submittal Number: 09 51 13-4.0 From: DANIELLE SCOTT Final Due Date: 02/05/21 Subject: SOUND ABSORBING ACOUSTIC BAFFLES - CL12 PRODUCT DATA Description: PRODUCT DATA CL12 Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 11235 | Review Response | Approved as Noted | 2021-02-05 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See attached comments. | Info Exchange
| 11297 | Review Response | Approved | 2021-02-08 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 14645 | Responded and Closed | Approved as Noted | 2021-02-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attached comments. Response (Approved) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-22 |  | Sound Absorbing Acoustic Baffles - CL12 Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-22 |  | Sound Absorbing Acoustic Baffles - CL12 Product Data.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-01-22 |  | Sound Absorbing Acoustic Baffles - CL12 Product Data.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-02-05 |  | Sound Absorbing Acoustic Baffles - CL12 Product Data_TTReview.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-01-22 |  | Sound Absorbing Acoustic Baffles - CL12 Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-09 |  | Sound Absorbing Acoustic Baffles - CL12 Product Data_TT_Idibri_POP.pdf
09 51 13-005-00 | 09 51 13 | 09 51 13-005-00 CL12 Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-03-01 | 15 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11396 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-03-01 | Submittal Number: 09 51 13-5.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: CL12 SHOP DRAWINGS Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 14763 | Forwarded | For Review | 2021-02-13 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 09 51 13-5.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: CL12 SHOP DRAWINGS Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 11701 | Review Response | Approved as Noted | 2021-03-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15159 | Responded and Closed | Approved as Noted | 2021-03-01 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-12 |  | 09 51 13-5 Revision 0 CL12 Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-12 |  | 09 51 13-5 Revision 0 CL12 Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-01 |  | 09 51 13-5 Revision 0 CL12 Shop Drawings_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-12 |  | 09 51 13-5 Revision 0 CL12 Shop Drawings.pdf
09 51 13-006-00 | 09 51 13 | 09 51 13-006-00 Acoustical Baffle Color Match Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-23 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-09 | 2021-02-25 | 3 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11598 | Received | For Review | 2021-02-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-03-09 | Submittal Number: 09 51 13-6.0 From: TYRONE THORNTON Final Due Date: 03/08/21 Subject: ACOUSTICAL BAFFLE COLOR MATCH SAMPLES Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 15026 | Forwarded | For Review | 2021-02-22 | Tyrone Thornton (Mortenson Construction) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-01 | Submittal Number: 09 51 13-6.0 From: TYRONE THORNTON Final Due Date: 03/08/21 Subject: ACOUSTICAL BAFFLE COLOR MATCH SAMPLES Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 11644 | Review Response | Approved as Noted | 2021-02-25 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15090 | Responded and Closed | Approved as Noted | 2021-02-25 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: Custom Color match rejected. Proceed with Standard Beige, as noted in submittal comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-22 |  | 09 51 13 - Acoustic Baffle Color Match Samples.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-02-22 |  | 09 51 13 - Acoustic Baffle Color Match Samples.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-25 |  | 09 51 13 - Acoustic Baffle Color Match Samples_pop.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-22 |  | 09 51 13 - Acoustic Baffle Color Match Samples.pdf
09 51 13-007-00 | 09 51 13 | 09 51 13-007-00 Polysorb Acoustical Baffle Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-18 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-02 | 2021-06-30 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-06-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13572 | Received | For Review | 2021-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-07-02 | Submittal Number: 09 51 13-7.0 From: TYRONE THORNTON Final Due Date: 07/02/21 Subject: POLYSORB ACOUSTICAL BAFFLE SAMPLES Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 17575 | Forwarded | For Review | 2021-06-18 | Tyrone Thornton (Mortenson Construction) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-25 | Submittal Number: 09 51 13-7.0 From: TYRONE THORNTON Final Due Date: 07/02/21 Subject: POLYSORB ACOUSTICAL BAFFLE SAMPLES Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 13730 | Review Response | Approved as Noted | 2021-06-30 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17771 | Responded and Closed | Approved as Noted | 2021-06-30 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-18 |  | 09 51 13 - Polysorb Baffle Samples_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-06-18 |  | 09 51 13 - Polysorb Baffle Samples_MAM Review.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-30 |  | 09 51 13 - Polysorb Baffle Samples_MAM Review_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-18 |  | 09 51 13 - Polysorb Baffle Samples_MAM Review.pdf
09 51 13-008-00 | 09 51 13 | 09 51 13-008-00 Polysorb Acoustical Baffle Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-18 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian Elwell (Idibri), Ryan Knox (Idibri), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-07-02 | 2021-07-06 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13573 | Received | For Review | 2021-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-07-02 | Submittal Number: 09 51 13-8.0 From: TYRONE THORNTON Final Due Date: 07/02/21 Subject: POLYSORB ACOUSTICAL BAFFLE PRODUCT DATA Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 17576 | Forwarded | For Review | 2021-06-18 | Tyrone Thornton (Mortenson Construction) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-25 | Submittal Number: 09 51 13-8.0 From: TYRONE THORNTON Final Due Date: 07/02/21 Subject: POLYSORB ACOUSTICAL BAFFLE PRODUCT DATA Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 17772 | Forwarded | For Review | 2021-06-30 | Tyrone Thornton (Mortenson Construction) | Brian Elwell (Idibri); Ryan Knox (Idibri) |  | Submittal Number: 09 51 13-8.0 From: TYRONE THORNTON Final Due Date: 07/02/21 Subject: POLYSORB ACOUSTICAL BAFFLE PRODUCT DATA Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 17774 | Forwarded | For Review | 2021-06-30 | Tyrone Thornton (Mortenson Construction) | Matt Ross (Thornton Tomasetti) |  | Submittal Number: 09 51 13-8.0 From: TYRONE THORNTON Final Due Date: 07/02/21 Subject: POLYSORB ACOUSTICAL BAFFLE PRODUCT DATA Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 13799 | Review Response | Approved as Noted | 2021-07-06 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 13800 | Review Response | Approved as Noted | 2021-07-06 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13810 | Review Response | Approved | 2021-07-06 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 17882 | Responded and Closed | Approved as Noted | 2021-07-06 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: Response (Approved) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-18 |  | Polysorb Acoustical Baffle Product Data_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-06-18 |  | Polysorb Acoustical Baffle Product Data_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-06-18 |  | Polysorb Acoustical Baffle Product Data_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-06-18 |  | Polysorb Acoustical Baffle Product Data_MAM Review.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-07-02 |  | Polysorb Acoustical Baffle Product Data_MAM Review_TTReview.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-07-06 |  | Polysorb Acoustical Baffle Product Data_MAM Review_POP_TT.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-06-18 |  | Polysorb Acoustical Baffle Product Data_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-18 |  | Polysorb Acoustical Baffle Product Data_MAM Review.pdf
09 51 13-009-00 | 09 51 13 | 09 51 13-009-00 Salvage Panel Replacement Shop Drawings | Closed | Architectural, Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-27 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Ben Cating (Idibri), Brian Elwell (Idibri), Ryan Knox (Idibri) |  |  |  | 2021-10-11 | 2021-10-04 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-10-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14703 | Received | For Review | 2021-09-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-10-11 | Submittal Number: 09 51 13-9.0 From: TYRONE THORNTON Final Due Date: 10/08/21 Subject: 09 51 13 - SALVAGE PANEL REPLACEMENT SHOP DRAWINGS Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 18962 | Forwarded | For Review | 2021-09-27 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-10-04 | Submittal Number: 09 51 13-9.0 From: TYRONE THORNTON Final Due Date: 10/08/21 Subject: 09 51 13 - SALVAGE PANEL REPLACEMENT SHOP DRAWINGS Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 14752 | Review Response | Approved as Noted | 2021-09-29 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 19019 | Forwarded | For Review | 2021-09-29 | Kelsea Conkright (Populous) | Ben Cating (Idibri); Brian Elwell (Idibri); Ryan Knox (Idibri) |  | Submittal Number: 09 51 13-9.0 From: TYRONE THORNTON Final Due Date: 10/08/21 Subject: 09 51 13 - SALVAGE PANEL REPLACEMENT SHOP DRAWINGS Description: Spec Section: 09 51 13 - SOUND ABSORBING ACOUSTIC BAFFLES Status: OPEN | Info Exchange
| 14776 | Review Response | Approved | 2021-10-04 | Brian Elwell (Idibri) | Populous SCA_CCA |  | This matches a phone call discussion Idibri had with Mortenson and Populous a few weeks ago. The submittal matches what was discussed. | Info Exchange
| 19047 | Responded and Closed | Approved as Noted | 2021-10-04 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Brian Elwell (Idibri) Remarks: This matches a phone call discussion Idibri had with Mortenson and Populous a few weeks ago. The submittal matches what was discussed. Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-24 |  | Polysorb Baffles Shop Drawings_ADI_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-24 |  | Polysorb Baffles Shop Drawings_ADI_MAM Review.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-09-29 |  | Polysorb Baffles Shop Drawings_ADI_MAM Review_POP.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-09-24 |  | Polysorb Baffles Shop Drawings_ADI_MAM Review.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-09-24 |  | Polysorb Baffles Shop Drawings_ADI_MAM Review.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-09-24 |  | Polysorb Baffles Shop Drawings_ADI_MAM Review.pdf
09 53 23-001-00 | 09 53 23 | 09 53 23-001-00 MODULAR METAL CEILINGS - Shop Drawings CL24 WMBA | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-03 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-17 | 2021-02-18 | 16 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11139 | Received | For Review | 2021-02-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-17 | Submittal Number: 09 53 23-1.0 From: DANIELLE SCOTT Final Due Date: 02/16/21 Subject: MODULAR METAL CEILINGS - SHOP DRAWINGS CL24 WMBA Description: SHOP DRAWINGS FOR CL24 WMBA. Spec Section: 09 53 23 - MODULAR METAL CEILING SYSTEM Status: OPEN | Info Exchange
| 14450 | Forwarded | For Review | 2021-02-02 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-09 | Submittal Number: 09 53 23-1.0 From: DANIELLE SCOTT Final Due Date: 02/16/21 Subject: MODULAR METAL CEILINGS - SHOP DRAWINGS CL24 WMBA Description: SHOP DRAWINGS FOR CL24 WMBA. Spec Section: 09 53 23 - MODULAR METAL CEILING SYSTEM Status: OPEN | Info Exchange
| 14933 | Responded and Closed | Approved as Noted | 2021-02-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | 09 53 23-1 MODULAR METAL CEILINGS - Shop Drawings CL24 WMBA.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-02 |  | 09 53 23-1 MODULAR METAL CEILINGS - Shop Drawings CL24 WMBA.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-18 |  | 09 53 23-1 MODULAR METAL CEILINGS - Shop Drawings CL24 WMBA_POP.pdf
09 54 43-002-00 | 09 54 43 | 09 54 43-002-00 Stretched Fabric Ceiling - CL60 Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-19 | 15 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-04-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12362 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-04-19 | Submittal Number: 09 54 43-2.0 From: DANIELLE SCOTT Final Due Date: 04/14/21 Subject: STRETCHED FABRIC CEILING - CL60 SHOP DRAWINGS Description: Spec Section: 09 54 43 - STRETCHED-FABRIC CEILING SYSTEMS Status: OPEN | Info Exchange
| 16018 | Forwarded | For Review | 2021-04-01 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 09 54 43-2.0 From: DANIELLE SCOTT Final Due Date: 04/14/21 Subject: STRETCHED FABRIC CEILING - CL60 SHOP DRAWINGS Description: Spec Section: 09 54 43 - STRETCHED-FABRIC CEILING SYSTEMS Status: OPEN | Info Exchange
| 12644 | Review Response | Approved as Noted | 2021-04-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16361 | Responded and Closed | Approved as Noted | 2021-04-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 09 54 43-2 Revision 0 Stretched Fabric Ceiling - CL60 Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-01 |  | 09 54 43-2 Revision 0 Stretched Fabric Ceiling - CL60 Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-19 |  | 09 54 43-2 Revision 0 Stretched Fabric Ceiling - CL60 Shop Drawings_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-01 |  | 09 54 43-2 Revision 0 Stretched Fabric Ceiling - CL60 Shop Drawings.pdf
09 54 43-003-00 | 09 54 43 | 09 54 43-003-00 CL60 Shop Drawings - Added Scope Tunnel Corridors | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-06-04 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13143 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-06-02 07:00 | Submittal Number: 09 54 43-3.0 From: KIM DOWALIBY Final Due Date: 05/31/21 Subject: CL60 SHOP DRAWINGS - ADDED SCOPE TUNNEL CORRIDORS Description: Spec Section: 09 54 43 - STRETCHED-FABRIC CEILING SYSTEMS Status: OPEN | Info Exchange
| 17003 | Forwarded | For Review | 2021-05-18 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-25 | Submittal Number: 09 54 43-3.0 From: KIM DOWALIBY Final Due Date: 05/31/21 Subject: CL60 SHOP DRAWINGS - ADDED SCOPE TUNNEL CORRIDORS Description: Spec Section: 09 54 43 - STRETCHED-FABRIC CEILING SYSTEMS Status: OPEN | Info Exchange
| 13405 | Review Response | Approved as Noted | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17338 | Responded and Closed | Approved as Noted | 2021-06-04 | Kim Dowaliby | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | 09 54 43-3 - CL60 Shop Drawings - Added Scope Tunnel Corridors.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-05-17 |  | 09 54 43-3 - CL60 Shop Drawings - Added Scope Tunnel Corridors.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-04 |  | 09 54 43-3 - CL60 Shop Drawings - Added Scope Tunnel Corridors_POP.pdf
| Responded and Closed |  | Kim Dowaliby | 1 | 2021-05-17 |  | 09 54 43-3 - CL60 Shop Drawings - Added Scope Tunnel Corridors.pdf
09 61 13-001-00 | 09 61 13 - FLOOR SEALERS | 09 61 13-001-00 FLOOR SEALERS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-12 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-30 08:00 | 2020-11-17 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-11-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09400 | Received | For Review | 2020-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-11-30 08:00 | Submittal Number: 09 61 13-1.0 From: DANIELLE SCOTT Final Due Date: 11/26/20 Subject: FLOOR SEALERS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 12404 | Forwarded | For Review | 2020-11-12 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-19 | Submittal Number: 09 61 13-1.0 From: DANIELLE SCOTT Final Due Date: 11/26/20 Subject: FLOOR SEALERS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 12514 | Responded and Closed | Approved | 2020-11-17 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-12 |  | 09 61 13-1 Floor Sealers - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-12 |  | 09 61 13-1 Floor Sealers - Product Data.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-11-12 |  | 09 61 13-1 Floor Sealers - Product Data.pdf
09 61 13-001-01 | 09 61 13 - FLOOR SEALERS | 09 61 13-001-01 FLOOR SEALERS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-18 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-12 | 2021-01-11 | 25 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10235 | Received | For Review | 2020-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-12 | Submittal Number: 09 61 13-1.1 From: DANIELLE SCOTT Final Due Date: 12/31/20 Subject: FLOOR SEALERS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. ALTERNATE PRODUCT. Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 13373 | Forwarded | For Review | 2020-12-17 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-24 | Submittal Number: 09 61 13-1.1 From: DANIELLE SCOTT Final Due Date: 12/31/20 Subject: FLOOR SEALERS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. ALTERNATE PRODUCT. Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 10619 | Review Response | Approved | 2021-01-11 | Tom Usher (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13827 | Responded and Closed | Approved | 2021-01-11 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  | Response (Approved) from: Tom Usher (Populous) Remarks: | Info Exchange
| 14027 | Sent | For Information Only | 2021-01-19 | Populous SCA_CCA | Simran George (Mortenson Construction); Danielle Scott |  | Responded and Closed (Approved) to: Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott Remarks: Response (Approved) from: Tom Usher (Populous) Remarks: | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-17 |  | 09 61 13-1 Revision 1 Floor Sealers - Product Data R1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-17 |  | 09 61 13-1 Revision 1 Floor Sealers - Product Data R1.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2021-01-11 02:00 |  | 09 61 13-1 Revision 1 Floor Sealers - Product Data R1_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-16 02:00 |  | 09 61 13-1 Revision 1 Floor Sealers - Product Data R1.pdf
| Sent |  | Populous SCA_CCA | 1 | 2020-12-16 02:00 |  | 09 61 13-1 Revision 1 Floor Sealers - Product Data R1.pdf
09 61 13-001-02 | 09 61 13 - FLOOR SEALERS | 09 61 13-001-02 FLOOR SEALERS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-16 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-30 | 2021-06-18 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13546 | Received | For Review | 2021-06-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-06-30 | Submittal Number: 09 61 13-1.2 From: KIM DOWALIBY Final Due Date: 06/29/21 Subject: FLOOR SEALERS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. ALTERNATE PRODUCT. Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 17533 | Forwarded | For Review | 2021-06-16 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-23 | Submittal Number: 09 61 13-1.2 From: KIM DOWALIBY Final Due Date: 06/29/21 Subject: FLOOR SEALERS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. ALTERNATE PRODUCT. Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 17569 | Responded and Closed | Approved | 2021-06-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-15 |  | 09 61 13-1.2 Floor Sealers - Product Data Rev 2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-15 |  | 09 61 13-1.2 Floor Sealers - Product Data Rev 2.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-18 |  | 09 61 13-1.2 Floor Sealers - Product Data Rev 2_POP.pdf
09 61 13-004-00 | 09 61 13 - FLOOR SEALERS | 09 61 13-004-00 FLOOR SEALERS - Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-17 | 2021-05-04 | 2 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12878 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-17 | Submittal Number: 09 61 13-4.0 From: KIM DOWALIBY Final Due Date: 05/14/21 Subject: FLOOR SEALERS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR FLOOR SEALERS TO INCLUDE IN MAINTENANCE MANUALS. INCLUDE THE FOLLOWING: 1. METHODS FOR MAINTAINING FLOOR SEALERS, INCLUDING CLEANING AND STAIN-REMOVAL PRODUCTS. 2. PRECAUTIONS FOR CLEANING MATERIALS AND METHODS THAT COULD BE DETRIMENTAL TO FLOOR SEALERS. Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 16660 | Forwarded | For Review | 2021-04-30 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-07 | Submittal Number: 09 61 13-4.0 From: KIM DOWALIBY Final Due Date: 05/14/21 Subject: FLOOR SEALERS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR FLOOR SEALERS TO INCLUDE IN MAINTENANCE MANUALS. INCLUDE THE FOLLOWING: 1. METHODS FOR MAINTAINING FLOOR SEALERS, INCLUDING CLEANING AND STAIN-REMOVAL PRODUCTS. 2. PRECAUTIONS FOR CLEANING MATERIALS AND METHODS THAT COULD BE DETRIMENTAL TO FLOOR SEALERS. Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 16717 | Responded and Closed | Revise and Resubmit | 2021-05-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); KIM.DOWALIBY@MORTENSON.COM |  | Please resubmit with maintenance data for all products submitted and approved under this section. Refer to pdf for additional comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-30 |  | 09 61 13.4 - Floor Sealers - Maintenance Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-30 |  | 09 61 13.4 - Floor Sealers - Maintenance Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-04 |  | 09 61 13.4 - Floor Sealers - Maintenance Data_POP.pdf
09 61 13-004-01 | 09 61 13 - FLOOR SEALERS | 09 61 13-004-01 FLOOR SEALERS - Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-08 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-22 | 2021-07-14 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13838 | Received | For Review | 2021-07-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-22 | Submittal Number: 09 61 13-4.1 From: KIM DOWALIBY Final Due Date: 07/21/21 Subject: FLOOR SEALERS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR FLOOR SEALERS TO INCLUDE IN MAINTENANCE MANUALS. INCLUDE THE FOLLOWING: 1. METHODS FOR MAINTAINING FLOOR SEALERS, INCLUDING CLEANING AND STAIN-REMOVAL PRODUCTS. 2. PRECAUTIONS FOR CLEANING MATERIALS AND METHODS THAT COULD BE DETRIMENTAL TO FLOOR SEALERS. Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 17913 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-15 | Submittal Number: 09 61 13-4.1 From: KIM DOWALIBY Final Due Date: 07/21/21 Subject: FLOOR SEALERS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR FLOOR SEALERS TO INCLUDE IN MAINTENANCE MANUALS. INCLUDE THE FOLLOWING: 1. METHODS FOR MAINTAINING FLOOR SEALERS, INCLUDING CLEANING AND STAIN-REMOVAL PRODUCTS. 2. PRECAUTIONS FOR CLEANING MATERIALS AND METHODS THAT COULD BE DETRIMENTAL TO FLOOR SEALERS. Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 18033 | Responded and Closed | Approved | 2021-07-14 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | RECIEVED FOR RECORD | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-07 |  | 09 61 13.4.1 - Floor Sealers - Maintenance Data Rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-07 |  | 09 61 13.4.1 - Floor Sealers - Maintenance Data Rev 1.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-07-14 |  | 09 61 13.4.1 - Floor Sealers - Maintenance Data Rev 1-POP.pdf
09 61 13-005-00 | 09 61 13 - FLOOR SEALERS | 09 61 13-005-00 1st Ave. N. Garage Floor Sealer Package | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-08 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-22 | 2021-09-08 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14596 | Received | For Review | 2021-09-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-09-22 | Submittal Number: 09 61 13-5.0 From: ALLIE ZIMMERMAN Final Due Date: 09/22/21 Subject: 1ST AVE. N. GARAGE FLOOR SEALER PACKAGE Description: Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 18816 | Forwarded | For Review | 2021-09-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-15 | Submittal Number: 09 61 13-5.0 From: ALLIE ZIMMERMAN Final Due Date: 09/22/21 Subject: 1ST AVE. N. GARAGE FLOOR SEALER PACKAGE Description: Spec Section: 09 61 13 - FLOOR SEALERS Status: OPEN | Info Exchange
| 18819 | Responded and Closed | Approved | 2021-09-08 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-08 |  | Submittal 09 61 13-5 Revision 0 1st Ave. N. Garage Floor Sealer Package_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-08 |  | Submittal 09 61 13-5 Revision 0 1st Ave. N. Garage Floor Sealer Package_MAM Reviewed.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-09-08 |  | Submittal 09 61 13-5 Revision 0 1st Ave. N. Garage Floor Sealer Package_MAM Reviewed_POP.pdf
09 65 13-007-00 | 09 65 13 - RESILIENT BASE AND ACCESSORIES | 09 65 13-007-00 RESILIENT BASE AND ACCESSORIES - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-20 | 17 |  | Record Copies; Transfers; Submittals | 09 65 13-007-00-01 - 09 65 13-007-00 RESILIENT BASE AND ACCESSORIES - Samples | 17 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10392 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-19 08:00 | Submittal Number: 09 65 13-7.0 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: RESILIENT BASE AND ACCESSORIES - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF PRODUCT INDICATED AND FOR EACH COLOR, TEXTURE, AND PATTERN REQUIRED IN MANUFACTURER'S STANDARD-SIZE SAMPLES, BUT NOT LESS THAN 12 INCHES LONG. Spec Section: 09 65 13 - RESILIENT BASE AND ACCESSORIES Status: OPEN | Info Exchange
| 13576 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 09 65 13-7.0 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: RESILIENT BASE AND ACCESSORIES - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF PRODUCT INDICATED AND FOR EACH COLOR, TEXTURE, AND PATTERN REQUIRED IN MANUFACTURER'S STANDARD-SIZE SAMPLES, BUT NOT LESS THAN 12 INCHES LONG. Spec Section: 09 65 13 - RESILIENT BASE AND ACCESSORIES Status: OPEN | Info Exchange
| 10841 | Review Response | Approved as Noted/Resubmit | 2021-01-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14084 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-23 |  | 09 65 13-7 Resilient Base Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-23 |  | 09 65 13-7 Resilient Base Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-20 |  | 09 65 13-7 Resilient Base Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-23 |  | 09 65 13-7 Resilient Base Samples.pdf
09 65 13-007-00-01 | 09 65 13 - RESILIENT BASE AND ACCESSORIES | 09 65 13-007-00 RESILIENT BASE AND ACCESSORIES - Samples | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 65 13-007-00 - 09 65 13-007-00 RESILIENT BASE AND ACCESSORIES - Samples | -1 | 2021-02-03
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-23 |  | 09 65 13-7 Resilient Base Samples.pdf
09 65 13-011-00 | 09 65 13 - RESILIENT BASE AND ACCESSORIES | 09 65 13-011-00 RESILIENT BASE AND ACCESSORIES - RB3 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-12-01 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09569 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-07 | Submittal Number: 09 65 13-11.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: RESILIENT BASE AND ACCESSORIES - RB3 SAMPLE Description: RB3 SAMPLES FOR APPROVAL. 3 DIFFERENT COLORS WERE PROVIDED TO HELP WITH SELECTION. Spec Section: 09 65 13 - RESILIENT BASE AND ACCESSORIES Status: OPEN | Info Exchange
| 12598 | Forwarded | For Review | 2020-11-19 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 09 65 13-11.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: RESILIENT BASE AND ACCESSORIES - RB3 SAMPLE Description: RB3 SAMPLES FOR APPROVAL. 3 DIFFERENT COLORS WERE PROVIDED TO HELP WITH SELECTION. Spec Section: 09 65 13 - RESILIENT BASE AND ACCESSORIES Status: OPEN | Info Exchange
| 09794 | Review Response | Approved as Noted | 2020-12-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | See attached submittal review. We will not be using just one RB3. From the finish legend: RB3 = Base to match wall color. If RB3 is scheduled: Use white on all P1 walls. Use black on P3 and P10 walls. Use Snow White on P6 walls. | Info Exchange
| 12876 | Responded and Closed | Approved as Noted | 2020-12-01 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal review. We will not be using just one RB3. From the finish legend: RB3 = Base to match wall color. If RB3 is scheduled: Use white on all P1 walls. Use black on P3 and P10 walls. Use Snow White on P6 walls. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 09 65 13-11 Resilient Base Sample RB3.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 09 65 13-11 Resilient Base Sample RB3.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-01 |  | 09 65 13-11 Resilient Base Sample RB3_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-18 |  | 09 65 13-11 Resilient Base Sample RB3.pdf
09 65 13-012-00 | 09 65 13 - RESILIENT BASE AND ACCESSORIES | 09 65 13-012-00 Resilient Base RB5 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-11 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-25 | 2021-02-25 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11331 | Received | For Review | 2021-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-25 | Submittal Number: 09 65 13-12.0 From: DANIELLE SCOTT Final Due Date: 02/24/21 Subject: RESILIENT BASE RB5 SAMPLE Description: Spec Section: 09 65 13 - RESILIENT BASE AND ACCESSORIES Status: OPEN | Info Exchange
| 14690 | Forwarded | For Review | 2021-02-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-18 | Submittal Number: 09 65 13-12.0 From: DANIELLE SCOTT Final Due Date: 02/24/21 Subject: RESILIENT BASE RB5 SAMPLE Description: Spec Section: 09 65 13 - RESILIENT BASE AND ACCESSORIES Status: OPEN | Info Exchange
| 11660 | Review Response | Approved | 2021-02-25 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15111 | Responded and Closed | Approved | 2021-02-25 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-10 |  | 09 65 13-12 Revision 0 Resilient Base RB5 Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-10 |  | 09 65 13-12 Revision 0 Resilient Base RB5 Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-25 |  | 09 65 13-12 Revision 0 Resilient Base RB5 Sample_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-10 |  | 09 65 13-12 Revision 0 Resilient Base RB5 Sample.pdf
09 65 19-008-00 | 09 65 19 - RESILIENT TILE FLOORING | 09 65 19-008-00 RESILIENT FLOORING - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-24 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-08 | 2020-10-06 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08312 | Received | For Review | 2020-09-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-08 | Submittal Number: 09 65 19-8.0 From: DANIELLE SCOTT Final Due Date: 10/07/20 Subject: RESILIENT FLOORING - SAMPLES Description: SAMPLE FOR ALL RESILIENT FLOORING TYPES. Spec Section: 09 65 19 - RESILIENT TILE FLOORING Status: OPEN | Info Exchange
| 11020 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-01 | Submittal Number: 09 65 19-8.0 From: DANIELLE SCOTT Final Due Date: 10/07/20 Subject: RESILIENT FLOORING - SAMPLES Description: SAMPLE FOR ALL RESILIENT FLOORING TYPES. Spec Section: 09 65 19 - RESILIENT TILE FLOORING Status: OPEN | Info Exchange
| 08580 | Review Response | Approved | 2020-10-06 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11342 | Responded and Closed | Approved | 2020-10-06 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 09 65 19-8 Resilient Flooring.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 09 65 19-8 Resilient Flooring.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-06 |  | 09 65 19-8 Resilient Flooring_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-23 |  | 09 65 19-8 Resilient Flooring.pdf
09 65 19-015-00 | 09 65 19 - RESILIENT TILE FLOORING | 09 65 19-015-00 Resilient Flooring Sample RF11 (Premium) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-12-01 | 13 |  | Record Copies; Transfers; Submittals | 09 65 19-015-00-01 - 09 65 19-015-00 Resilient Flooring Sample RF11 (Premium) | 13 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09568 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-07 | Submittal Number: 09 65 19-15.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: RESILIENT FLOORING SAMPLE RF11 (PREMIUM) Description: SAMPLE FOR RF11. Spec Section: 09 65 19 - RESILIENT TILE FLOORING Status: OPEN | Info Exchange
| 12597 | Forwarded | For Review | 2020-11-19 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 09 65 19-15.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: RESILIENT FLOORING SAMPLE RF11 (PREMIUM) Description: SAMPLE FOR RF11. Spec Section: 09 65 19 - RESILIENT TILE FLOORING Status: OPEN | Info Exchange
| 09796 | Review Response | Revise and Resubmit | 2020-12-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Provide Mondo Sport Impact per finish legend. Sample is Mondo Ramflex. | Info Exchange
| 12878 | Responded and Closed | Revise and Resubmit | 2020-12-01 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Provide Mondo Sport Impact per finish legend. Sample is Mondo Ramflex. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 09 65 19-15 Resilient Flooring Sample RF11 -.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 09 65 19-15 Resilient Flooring Sample RF11 -.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-01 |  | 09 65 19-15 Resilient Flooring Sample RF11 - POP.pdf
09 65 19-015-00-01 | 09 65 19 - RESILIENT TILE FLOORING | 09 65 19-015-00 Resilient Flooring Sample RF11 (Premium) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 65 19-015-00 - 09 65 19-015-00 Resilient Flooring Sample RF11 (Premium) | -1 | 2020-12-15
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-01 |  | 09 65 19-15 Resilient Flooring Sample RF11 - POP.pdf
09 65 19-016-00 | 09 65 19 - RESILIENT TILE FLOORING | 09 65 19-016-00 RF7 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-26 08:00 | 2021-01-21 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10592 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-26 08:00 | Submittal Number: 09 65 19-16.0 From: DANIELLE SCOTT Final Due Date: 01/25/21 Subject: RF7 SAMPLE Description: RF& SAMPLE Spec Section: 09 65 19 - RESILIENT TILE FLOORING Status: OPEN | Info Exchange
| 13796 | Forwarded | For Review | 2021-01-11 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-18 | Submittal Number: 09 65 19-16.0 From: DANIELLE SCOTT Final Due Date: 01/25/21 Subject: RF7 SAMPLE Description: RF& SAMPLE Spec Section: 09 65 19 - RESILIENT TILE FLOORING Status: OPEN | Info Exchange
| 10887 | Review Response | Approved as Noted | 2021-01-21 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Confirm product size is 20"x40" as stated on Finish Legend in lieu of 3x6 listed on sample. | Info Exchange
| 14138 | Responded and Closed | Approved as Noted | 2021-01-21 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: Confirm product size is 20"x40" as stated on Finish Legend in lieu of 3x6 listed on sample. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 09 65 19-16 Resilient Flooring Sample - RF7.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-11 |  | 09 65 19-16 Resilient Flooring Sample - RF7.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-21 |  | 09 65 19-16 Resilient Flooring Sample - RF7_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-11 |  | 09 65 19-16 Resilient Flooring Sample - RF7.pdf
09 67 23-001-00 | 09 67 23 - RESINOUS FLOORING | 09 67 23-001-00 RESINOUS FLOORING - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-27 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-10 | 2020-08-28 | 33 |  | Record Copies; Transfers; Submittals |  | 35 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07141 | Received | For Review | 2020-07-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-10 | Submittal Number: 09 67 23-1.0 From: JOSH BROUSSARD Final Due Date: 08/07/20 Subject: RESINOUS FLOORING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE MANUFACTURER'S TECHNICAL DATA, APPLICATION INSTRUCTIONS, AND RECOMMENDATIONS FOR EACH RESINOUS FLOORING COMPONENT REQUIRED. Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 09536 | Forwarded | For Review | 2020-07-25 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-08-03 | Submittal Number: 09 67 23-1.0 From: JOSH BROUSSARD Final Due Date: 08/07/20 Subject: RESINOUS FLOORING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE MANUFACTURER'S TECHNICAL DATA, APPLICATION INSTRUCTIONS, AND RECOMMENDATIONS FOR EACH RESINOUS FLOORING COMPONENT REQUIRED. Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 07833 | Review Response | Approved as Noted/Resubmit | 2020-08-28 | Tom Usher (Populous) | Populous SCA_CCA |  | See submittal for comments. | Info Exchange
| 10411 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-28 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Josh Broussard (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Tom Usher (Populous) Remarks: See submittal for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-25 |  | 09 67 23-1.0 MMA Flooring Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-25 |  | 09 67 23-1.0 MMA Flooring Product Data.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2020-08-27 02:00 |  | 09 67 23-1.0 MMA Flooring Product Data_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-24 02:00 |  | 09 67 23-1.0 MMA Flooring Product Data.pdf
09 67 23-001-01 | 09 67 23 - RESINOUS FLOORING | 09 67 23-001-01 RESINOUS FLOORING - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-14 | 2020-10-13 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08449 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-14 | Submittal Number: 09 67 23-1.1 From: JOSH BROUSSARD Final Due Date: 10/14/20 Subject: RESINOUS FLOORING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE MANUFACTURER'S TECHNICAL DATA, APPLICATION INSTRUCTIONS, AND RECOMMENDATIONS FOR EACH RESINOUS FLOORING COMPONENT REQUIRED. Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 11190 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-07 | Submittal Number: 09 67 23-1.1 From: JOSH BROUSSARD Final Due Date: 10/14/20 Subject: RESINOUS FLOORING - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE MANUFACTURER'S TECHNICAL DATA, APPLICATION INSTRUCTIONS, AND RECOMMENDATIONS FOR EACH RESINOUS FLOORING COMPONENT REQUIRED. Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 11561 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-13 | Shaina Burris (Populous) | Josh Broussard (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 09 67 23-1.1 MMA Flooring Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 09 67 23-1.1 MMA Flooring Product Data.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 09 67 23-1.1 MMA Flooring Product Data.pdf
09 67 23-001-02 | 09 67 23 - RESINOUS FLOORING | 09 67 23-001-02 RESINOUS FLOORING - Product Data Primer Resubmit | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-03 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-17 | 2020-11-17 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-11-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09180 | Received | For Review | 2020-11-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-17 | Submittal Number: 09 67 23-1.2 From: MIKE SOLFELT Final Due Date: 11/16/20 Subject: RESINOUS FLOORING - PRODUCT DATA PRIMER RESUBMIT Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE MANUFACTURER'S TECHNICAL DATA, APPLICATION INSTRUCTIONS, AND RECOMMENDATIONS FOR EACH RESINOUS FLOORING COMPONENT REQUIRED. Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 12113 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-09 | Submittal Number: 09 67 23-1.2 From: MIKE SOLFELT Final Due Date: 11/16/20 Subject: RESINOUS FLOORING - PRODUCT DATA PRIMER RESUBMIT Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE MANUFACTURER'S TECHNICAL DATA, APPLICATION INSTRUCTIONS, AND RECOMMENDATIONS FOR EACH RESINOUS FLOORING COMPONENT REQUIRED. Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 12512 | Responded and Closed | Approved | 2020-11-17 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | 09 67 23-1.2 MMA Flooring Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | 09 67 23-1.2 MMA Flooring Product Data.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | 09 67 23-1.2 MMA Flooring Product Data.pdf
09 67 23-012-00 | 09 67 23 - RESINOUS FLOORING | 09 67 23-012-00 MMA Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-14 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-28 | 2020-10-29 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-10-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08782 | Received | For Review | 2020-10-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-28 | Submittal Number: 09 67 23-12.0 From: MIKE SOLFELT Final Due Date: 11/23/20 Subject: MMA SHOP DRAWINGS Description: Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 11612 | Forwarded | For Review | 2020-10-14 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-21 | Submittal Number: 09 67 23-12.0 From: MIKE SOLFELT Final Due Date: 11/23/20 Subject: MMA SHOP DRAWINGS Description: Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 09103 | Review Response | Approved as Noted/Resubmit | 2020-10-29 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12014 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-29 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-14 |  | 09 67 23-12 MMA Flooring Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-14 |  | 09 67 23-12 MMA Flooring Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-29 |  | 09 67 23-12 MMA Flooring Shop Drawings_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-14 |  | 09 67 23-12 MMA Flooring Shop Drawings.pdf
09 67 23-012-01 | 09 67 23 - RESINOUS FLOORING | 09 67 23-012-01 MMA Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-08 | 2021-02-17 | 24 |  | Record Copies; Transfers; Submittals | 09 67 23-012-01-01 - 09 67 23-012-01 MMA Shop Drawings | 24 |  | 2021-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10938 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-08 | Submittal Number: 09 67 23-12.1 From: MIKE SOLFELT Final Due Date: 11/23/20 Subject: MMA SHOP DRAWINGS Description: Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 14200 | Forwarded | For Review | 2021-01-25 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-01 | Submittal Number: 09 67 23-12.1 From: MIKE SOLFELT Final Due Date: 11/23/20 Subject: MMA SHOP DRAWINGS Description: Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 14910 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-17 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR COMMENTS 1. FIELD VERIFY ALL DIMENSIONS 2. RESUBMIT REVISED AREAS ISSUED IN CCD-087 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 09 67 23-12.1 MMA Flooring Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-25 |  | 09 67 23-12.1 MMA Flooring Shop Drawings.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-02-17 |  | 09 67 23-12.1 MMA Flooring Shop Drawings_POP.pdf
09 67 23-012-01-01 | 09 67 23 - RESINOUS FLOORING | 09 67 23-012-01 MMA Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 67 23-012-01 - 09 67 23-012-01 MMA Shop Drawings | -1 | 2021-03-03
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-17 |  | 09 67 23-12.1 MMA Flooring Shop Drawings_POP.pdf
09 67 23-013-00 | 09 67 23 - RESINOUS FLOORING | 09 67 23-013-00 Floor Solutions Installer Certifications | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-16 | 2020-11-17 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-11-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09140 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-11-16 | Submittal Number: 09 67 23-13.0 From: MIKE SOLFELT Final Due Date: 11/16/20 Subject: FLOOR SOLUTIONS INSTALLER CERTIFICATIONS Description: Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 12062 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-09 | Submittal Number: 09 67 23-13.0 From: MIKE SOLFELT Final Due Date: 11/16/20 Subject: FLOOR SOLUTIONS INSTALLER CERTIFICATIONS Description: Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 12513 | Responded and Closed | Approved | 2020-11-17 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | 09 67 23-13 Floor Solutions Installer Certifications.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | 09 67 23-13 Floor Solutions Installer Certifications.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | 09 67 23-13 Floor Solutions Installer Certifications.pdf
09 67 23-014-00 | 09 67 23 - RESINOUS FLOORING | 09 67 23-014-00 MMA Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-23 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-09 | 2020-12-07 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09673 | Received | For Review | 2020-11-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-12-09 | Submittal Number: 09 67 23-14.0 From: MIKE SOLFELT Final Due Date: 12/07/20 Subject: MMA SAMPLE Description: THIS SUBMITTAL IS FOR REVIEW AND APPROVAL OF THE FT3 FLOOR TYPE - MMA PER SPECIFICATION 09 67 23 AND DRAWING A9-02-1. Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 12724 | Forwarded | For Review | 2020-11-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-30 | Submittal Number: 09 67 23-14.0 From: MIKE SOLFELT Final Due Date: 12/07/20 Subject: MMA SAMPLE Description: THIS SUBMITTAL IS FOR REVIEW AND APPROVAL OF THE FT3 FLOOR TYPE - MMA PER SPECIFICATION 09 67 23 AND DRAWING A9-02-1. Spec Section: 09 67 23 - RESINOUS FLOORING Status: OPEN | Info Exchange
| 09942 | Review Response | Approved as Noted | 2020-12-07 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13021 | Responded and Closed | Approved as Noted | 2020-12-07 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-23 |  | 09 67 23-14.0 MMA Flooring Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-23 |  | 09 67 23-14.0 MMA Flooring Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-07 |  | 09 67 23-14.0 MMA Flooring Sample v2 POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-23 |  | 09 67 23-14.0 MMA Flooring Sample.pdf
09 68 00-001-00 | 09 68 00 - CARPETING | 09 68 00-001-00 Carpet & Resilient - Product Data, Testing, Maintenance, & Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-23 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-07 07:00 | 2021-04-08 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-04-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12175 | Received | For Review | 2021-03-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-04-07 07:00 | Submittal Number: 09 68 00-1.0 From: DAVID REINDL Final Due Date: 04/05/21 Subject: CARPET & RESILIENT - PRODUCT DATA, TESTING, MAINTENANCE, & WARRANTY Description: CARPET PRODUCT DATA & WARRANTY. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 15759 | Forwarded | For Review | 2021-03-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-30 | Submittal Number: 09 68 00-1.0 From: DAVID REINDL Final Due Date: 04/05/21 Subject: CARPET & RESILIENT - PRODUCT DATA, TESTING, MAINTENANCE, & WARRANTY Description: CARPET PRODUCT DATA & WARRANTY. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 12480 | Review Response | Approved as Noted | 2021-04-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16173 | Responded and Closed | Approved as Noted | 2021-04-08 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-22 |  | 09 68 00-1 Revision 0 Carpet Product Data & Warranty.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-22 |  | 09 68 00-1 Revision 0 Carpet Product Data & Warranty.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-08 |  | 09 68 00-1 Revision 0 Carpet Product Data & Warranty_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-03-22 |  | 09 68 00-1 Revision 0 Carpet Product Data & Warranty.pdf
09 68 00-001-01 | 09 68 00 - CARPETING | 09 68 00-001-01 Carpet & Resilient - Product Data, Testing, Maintenance, & Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-25 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kuebler Perry (Populous) |  |  |  | 2021-06-09 07:00 | 2021-06-07 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13254 | Received | For Review | 2021-05-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-09 07:00 | Submittal Number: 09 68 00-1.1 From: KIM DOWALIBY Final Due Date: 06/08/21 Subject: CARPET & RESILIENT - PRODUCT DATA, TESTING, MAINTENANCE, & WARRANTY Description: CARPET PRODUCT DATA & WARRANTY. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17150 | Forwarded | For Review | 2021-05-25 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-01 | Submittal Number: 09 68 00-1.1 From: KIM DOWALIBY Final Due Date: 06/08/21 Subject: CARPET & RESILIENT - PRODUCT DATA, TESTING, MAINTENANCE, & WARRANTY Description: CARPET PRODUCT DATA & WARRANTY. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17209 | Forwarded | For Review | 2021-05-27 | Populous SCA_CCA | Kuebler Perry (Populous) |  | Submittal Number: 09 68 00-1.1 From: KIM DOWALIBY Final Due Date: 06/08/21 Subject: CARPET & RESILIENT - PRODUCT DATA, TESTING, MAINTENANCE, & WARRANTY Description: CARPET PRODUCT DATA & WARRANTY. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17369 | Responded and Closed | Approved | 2021-06-07 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-25 |  | 09 68 00-1.1 - Carpet & Resilient - Product Data Testing Maintenance & Warranty.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-25 |  | 09 68 00-1.1 - Carpet & Resilient - Product Data Testing Maintenance & Warranty.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-25 |  | 09 68 00-1.1 - Carpet & Resilient - Product Data Testing Maintenance & Warranty.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-07 |  | 09 68 00-1.1 - Carpet & Resilient - Product Data Testing Maintenance & Warranty_POP.pdf
09 68 00-004-00 | 09 68 00 - CARPETING | 09 68 00-004-00 Carpet, Resilient Base, and Resilient Flooring Shop and Seam Diagrams | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-26 08:00 | 2021-01-26 | 16 |  | Record Copies; Transfers; Submittals | 09 68 00-004-00-01 - 09 68 00-004-00 Carpet, Resilient Base, and Resilient Flooring Shop and Seam Diagrams | 16 |  | 2021-01-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10593 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-26 08:00 | Submittal Number: 09 68 00-4.0 From: DAVID REINDL Final Due Date: 01/22/21 Subject: CARPET, RESILIENT BASE, AND RESILIENT FLOORING SHOP AND SEAM DIAGRAMS Description: SHOP DRAWINGS : SHOW THE FOLLOWING: 1. COLUMNS, DOORWAYS, ENCLOSING WALLS OR PARTITIONS, BUILT-IN CABINETS, AND LOCATIONS WHERE CUTOUTS ARE REQUIRED IN CARPET. 2. CARPET TYPE, COLOR, AND DYE LOT. 3. LOCATIONS WHERE DYE LOT CHANGES OCCUR. 4. SEAM LOCATIONS, TYPES, AND METHODS. 5. TYPE OF SUBFLOOR. 6. TYPE OF INSTALLATION. 7. PATTERN TYPE, REPEAT SIZE, LOCATION, DIRECTION, AND STARTING POINT. 8. PILE DIRECTION. 9. TYPE, COLOR, AND LOCATION OF INSETS AND BORDERS. 10. TYPE, COLOR, AND LOCATION OF EDGE, TRANSITION, AND OTHER ACCESSORY STRIPS. 11. TRANSITION DETAILS TO OTHER FLOORING MATERIALS. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 13797 | Forwarded | For Review | 2021-01-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-18 | Submittal Number: 09 68 00-4.0 From: DAVID REINDL Final Due Date: 01/22/21 Subject: CARPET, RESILIENT BASE, AND RESILIENT FLOORING SHOP AND SEAM DIAGRAMS Description: SHOP DRAWINGS : SHOW THE FOLLOWING: 1. COLUMNS, DOORWAYS, ENCLOSING WALLS OR PARTITIONS, BUILT-IN CABINETS, AND LOCATIONS WHERE CUTOUTS ARE REQUIRED IN CARPET. 2. CARPET TYPE, COLOR, AND DYE LOT. 3. LOCATIONS WHERE DYE LOT CHANGES OCCUR. 4. SEAM LOCATIONS, TYPES, AND METHODS. 5. TYPE OF SUBFLOOR. 6. TYPE OF INSTALLATION. 7. PATTERN TYPE, REPEAT SIZE, LOCATION, DIRECTION, AND STARTING POINT. 8. PILE DIRECTION. 9. TYPE, COLOR, AND LOCATION OF INSETS AND BORDERS. 10. TYPE, COLOR, AND LOCATION OF EDGE, TRANSITION, AND OTHER ACCESSORY STRIPS. 11. TRANSITION DETAILS TO OTHER FLOORING MATERIALS. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 10970 | Review Response | Approved as Noted/Resubmit | 2021-01-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14249 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-26 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | 09 68 00-4 Carpet Resilient Base and Resilient Flooring Shop and Seam Diagrams.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-08 |  | 09 68 00-4 Carpet Resilient Base and Resilient Flooring Shop and Seam Diagrams.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-26 |  | 09 68 00-4 Carpet Resilient Base and Resilient Flooring Shop and Seam Diagrams_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-08 |  | 09 68 00-4 Carpet Resilient Base and Resilient Flooring Shop and Seam Diagrams.pdf
09 68 00-004-00-01 | 09 68 00 - CARPETING | 09 68 00-004-00 Carpet, Resilient Base, and Resilient Flooring Shop and Seam Diagrams | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 68 00-004-00 - 09 68 00-004-00 Carpet, Resilient Base, and Resilient Flooring Shop and Seam Diagrams | -1 | 2021-02-09
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | 09 68 00-4 Carpet Resilient Base and Resilient Flooring Shop and Seam Diagrams.pdf
09 68 00-005-00 | 09 68 00 - CARPETING | 09 68 00-005-00 CARPETING - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-07 | 2020-10-05 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08288 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-07 | Submittal Number: 09 68 00-5.0 From: DANIELLE SCOTT Final Due Date: 10/07/20 Subject: CARPETING - SAMPLES Description: SAMPLES : FOR EACH OF THE FOLLOWING PRODUCTS AND FOR EACH COLOR AND TEXTURE REQUIRED. LABEL EACH SAMPLE WITH MANUFACTURER'S NAME, MATERIAL DESCRIPTION, COLOR, PATTERN, AND DESIGNATION INDICATED ON DRAWINGS AND IN SCHEDULES. 1. CARPET: 30CM (12-INCH)- SQUARE SAMPLE. 2. EXPOSED EDGE, TRANSITION, AND OTHER ACCESSORY STRIPPING: 12-INCH-LONG SAMPLES. 3. CARPET SEAM: 6-INCH SAMPLE. 4. MITERED CARPET BORDER SEAM: 12-INCH-SQUARE SAMPLE. SHOW CARPET PATTERN ALIGNMENT. CA1 & CA2 IS NOT ON THE FINISH SCHEDULE OR SHOWN ON PLAN. IT IS EXCLUDED FROM OUR CARPET SAMPLES. CA14 SAMPLE IS PENDING SHIPMENT FROM THE MANUFACTURER. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 10994 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-30 | Submittal Number: 09 68 00-5.0 From: DANIELLE SCOTT Final Due Date: 10/07/20 Subject: CARPETING - SAMPLES Description: SAMPLES : FOR EACH OF THE FOLLOWING PRODUCTS AND FOR EACH COLOR AND TEXTURE REQUIRED. LABEL EACH SAMPLE WITH MANUFACTURER'S NAME, MATERIAL DESCRIPTION, COLOR, PATTERN, AND DESIGNATION INDICATED ON DRAWINGS AND IN SCHEDULES. 1. CARPET: 30CM (12-INCH)- SQUARE SAMPLE. 2. EXPOSED EDGE, TRANSITION, AND OTHER ACCESSORY STRIPPING: 12-INCH-LONG SAMPLES. 3. CARPET SEAM: 6-INCH SAMPLE. 4. MITERED CARPET BORDER SEAM: 12-INCH-SQUARE SAMPLE. SHOW CARPET PATTERN ALIGNMENT. CA1 & CA2 IS NOT ON THE FINISH SCHEDULE OR SHOWN ON PLAN. IT IS EXCLUDED FROM OUR CARPET SAMPLES. CA14 SAMPLE IS PENDING SHIPMENT FROM THE MANUFACTURER. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 08544 | Review Response | Approved | 2020-10-05 | Kuebler Perry (Populous) | Populous SCA_CCA |  | See attached submittal review. | Info Exchange
| 11305 | Responded and Closed | Approved | 2020-10-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 09 68 00-5 Carpet Samples excludes CA14.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 09 68 00-5 Carpet Samples excludes CA14.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-05 |  | 09 68 00-5 Carpet Samples excludes CA14_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-23 |  | 09 68 00-5 Carpet Samples excludes CA14.pdf
09 68 00-006-00 | 09 68 00 - CARPETING | 09 68 00-006-00 Carpet, Resilient Floor, & Resilient Base - Product Schedule | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-03 | Responded and Closed - Rejected |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-17 | 2021-02-15 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11153 | Received | For Review | 2021-02-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-17 | Submittal Number: 09 68 00-6.0 From: DANIELLE SCOTT Final Due Date: 02/16/21 Subject: CARPET, RESILIENT FLOOR, & RESILIENT BASE - PRODUCT SCHEDULE Description: PRODUCT SCHEDULE : FOR CARPET. USE SAME DESIGNATIONS INDICATED ON DRAWINGS. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 14459 | Forwarded | For Review | 2021-02-03 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-10 | Submittal Number: 09 68 00-6.0 From: DANIELLE SCOTT Final Due Date: 02/16/21 Subject: CARPET, RESILIENT FLOOR, & RESILIENT BASE - PRODUCT SCHEDULE Description: PRODUCT SCHEDULE : FOR CARPET. USE SAME DESIGNATIONS INDICATED ON DRAWINGS. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 14821 | Responded and Closed | Rejected | 2021-02-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  | Please review specification section 01 33 00 and resubmit for review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | 09 68 00-6 CARPETING - Product Schedule.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | Room Schedule-Material Locations.xlsx
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-02 |  | 09 68 00-6 CARPETING - Product Schedule.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-02 |  | Room Schedule-Material Locations.xlsx
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-15 02:00 |  | 09 68 00-6 CARPETING - Product Schedule_pop.pdf
09 68 00-013-00 | 09 68 00 - CARPETING | 09 68 00-013-00 Carpet CA14 Sample (NHL Locker Room) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-09 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-23 | 2020-11-13 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-11-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09298 | Received | For Review | 2020-11-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-11-23 | Submittal Number: 09 68 00-13.0 From: DANIELLE SCOTT Final Due Date: 11/20/20 Subject: CARPET CA14 SAMPLE (NHL LOCKER ROOM) Description: CA14 SAMPLE Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 12270 | Forwarded | For Review | 2020-11-09 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-16 | Submittal Number: 09 68 00-13.0 From: DANIELLE SCOTT Final Due Date: 11/20/20 Subject: CARPET CA14 SAMPLE (NHL LOCKER ROOM) Description: CA14 SAMPLE Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 09427 | Review Response | Revise and Resubmit | 2020-11-13 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12434 | Responded and Closed | Revise and Resubmit | 2020-11-13 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 09 68 00-13 Carpet Sample CA14.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 09 68 00-13 Carpet Sample CA14.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-11-13 |  | 09 68 00-13 Carpet Sample CA14_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-06 |  | 09 68 00-13 Carpet Sample CA14.pdf
09 68 00-013-01 | 09 68 00 - CARPETING | 09 68 00-013-01 Carpet CA14 Sample (NHL Locker Room) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-21 | 2020-12-15 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09943 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-21 | Submittal Number: 09 68 00-13.1 From: DANIELLE SCOTT Final Due Date: 12/21/20 Subject: CARPET CA14 SAMPLE (NHL LOCKER ROOM) Description: CA14 SAMPLE Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 13023 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 09 68 00-13.1 From: DANIELLE SCOTT Final Due Date: 12/21/20 Subject: CARPET CA14 SAMPLE (NHL LOCKER ROOM) Description: CA14 SAMPLE Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 10180 | Review Response | Approved | 2020-12-15 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13317 | Responded and Closed | Approved | 2020-12-15 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 09 68 00-13 Revision 1 Carpet Sample CA14.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-07 |  | 09 68 00-13 Revision 1 Carpet Sample CA14.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-15 |  | 09 68 00-13 Revision 1 Carpet Sample CA14_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-12-07 |  | 09 68 00-13 Revision 1 Carpet Sample CA14.pdf
09 68 00-014-00 | 09 68 00 - CARPETING | 09 68 00-014-00 Carpet CA14 Seam Diagram & Pattern (NHL Locker Room) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-27 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-10 | 2021-02-03 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-02-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10974 | Received | For Review | 2021-01-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-10 | Submittal Number: 09 68 00-14.0 From: DANIELLE SCOTT Final Due Date: 02/09/21 Subject: CARPET CA14 SEAM DIAGRAM & PATTERN (NHL LOCKER ROOM) Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 14252 | Forwarded | For Review | 2021-01-26 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-02 | Submittal Number: 09 68 00-14.0 From: DANIELLE SCOTT Final Due Date: 02/09/21 Subject: CARPET CA14 SEAM DIAGRAM & PATTERN (NHL LOCKER ROOM) Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 11161 | Review Response | Approved as Noted | 2021-02-03 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14466 | Responded and Closed | Approved as Noted | 2021-02-03 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-26 |  | 09 68 00-14 Carpet CA14 Seam Diagram & Pattern (NHL Locker Room).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-26 |  | 09 68 00-14 Carpet CA14 Seam Diagram & Pattern (NHL Locker Room).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-02 |  | 09 68 00-14 Carpet CA14 Seam Diagram & Pattern (NHL Locker Room)_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-01-26 |  | 09 68 00-14 Carpet CA14 Seam Diagram & Pattern (NHL Locker Room).pdf
09 68 00-014-01 | 09 68 00 - CARPETING | 09 68 00-014-01 Carpet CA14 Seam Diagram & Pattern (NHL Locker Room) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-11 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-25 | 2021-02-11 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11332 | Received | For Review | 2021-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-25 | Submittal Number: 09 68 00-14.1 From: DANIELLE SCOTT Final Due Date: 02/24/21 Subject: CARPET CA14 SEAM DIAGRAM & PATTERN (NHL LOCKER ROOM) Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 14691 | Forwarded | For Review | 2021-02-11 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-18 | Submittal Number: 09 68 00-14.1 From: DANIELLE SCOTT Final Due Date: 02/24/21 Subject: CARPET CA14 SEAM DIAGRAM & PATTERN (NHL LOCKER ROOM) Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 11340 | Review Response | Approved as Noted | 2021-02-11 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14699 | Responded and Closed | Approved as Noted | 2021-02-11 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-10 |  | 09 68 00-14 Revision 1 Carpet CA14 Seam Diagram & Pattern (NHL Locker Room).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-10 |  | 09 68 00-14 Revision 1 Carpet CA14 Seam Diagram & Pattern (NHL Locker Room).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-11 |  | 09 68 00-14 Revision 1 Carpet CA14 Seam Diagram & Pattern (NHL Locker Room)_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-10 |  | 09 68 00-14 Revision 1 Carpet CA14 Seam Diagram & Pattern (NHL Locker Room).pdf
09 68 00-015-00 | 09 68 00 - CARPETING | 09 68 00-015-00 CA11 Sample Revision 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-11 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-25 | 2021-02-25 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11333 | Received | For Review | 2021-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-25 | Submittal Number: 09 68 00-15.0 From: DANIELLE SCOTT Final Due Date: 02/24/21 Subject: CA11 SAMPLE REVISION 1 Description: THE MANUFACTURER REQUIRES A RESUBMITTAL OF THIS CARPET TYPE DUE TO MINOR CHANGES IN THE CARPET. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 14692 | Forwarded | For Review | 2021-02-11 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-18 | Submittal Number: 09 68 00-15.0 From: DANIELLE SCOTT Final Due Date: 02/24/21 Subject: CA11 SAMPLE REVISION 1 Description: THE MANUFACTURER REQUIRES A RESUBMITTAL OF THIS CARPET TYPE DUE TO MINOR CHANGES IN THE CARPET. Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 11661 | Review Response | Approved | 2021-02-25 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15112 | Responded and Closed | Approved | 2021-02-25 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-10 |  | 09 68 00-15 Revision 0 CA11 Sample Revision 1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-10 |  | 09 68 00-15 Revision 0 CA11 Sample Revision 1.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-25 |  | 09 68 00-15 Revision 0 CA11 Sample Revision 1_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-10 |  | 09 68 00-15 Revision 0 CA11 Sample Revision 1.pdf
09 68 00-016-00 | 09 68 00 - CARPETING | 09 68 00-016-00 Carpet Sample - Amazon Lounge and Star Dressing Rooms | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-23 | 2021-04-27 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12518 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-04-23 | Submittal Number: 09 68 00-16.0 From: DANIELLE SCOTT Final Due Date: 04/23/21 Subject: CARPET SAMPLE - AMAZON LOUNGE AND STAR DRESSING ROOMS Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 16207 | Forwarded | For Review | 2021-04-09 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-16 | Submittal Number: 09 68 00-16.0 From: DANIELLE SCOTT Final Due Date: 04/23/21 Subject: CARPET SAMPLE - AMAZON LOUNGE AND STAR DRESSING ROOMS Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 12801 | Review Response | Approved | 2021-04-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16547 | Responded and Closed | Approved | 2021-04-27 | Danielle Scott | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-09 |  | 09 68 00-16 Revision 0 Carpet Sample - Amazon Lounge and Star Dressing Rooms.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-04-09 |  | 09 68 00-16 Revision 0 Carpet Sample - Amazon Lounge and Star Dressing Rooms.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-27 |  | 09 68 00-16 Revision 0 Carpet Sample - Amazon Lounge and Star Dressing Rooms_POP.pdf
| Responded and Closed |  | Danielle Scott | 1 | 2021-04-09 |  | 09 68 00-16 Revision 0 Carpet Sample - Amazon Lounge and Star Dressing Rooms.pdf
09 68 00-017-00 | 09 68 00 - CARPETING | 09 68 00-017-00 CARPETING - Transition Strips Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-18 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13034 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-05-25 | Submittal Number: 09 68 00-17.0 From: KIM DOWALIBY Final Due Date: 05/24/21 Subject: 09 68 00 - CARPETING - TRANSITION STRIPS PRODUCT DATA Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 16867 | Forwarded | For Review | 2021-05-11 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-18 | Submittal Number: 09 68 00-17.0 From: KIM DOWALIBY Final Due Date: 05/24/21 Subject: 09 68 00 - CARPETING - TRANSITION STRIPS PRODUCT DATA Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17009 | Responded and Closed | Revise and Resubmit | 2021-05-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | SUBMIT ACTUAL PRODUCT DATA FOR EACH TRANSITION YOU LISTED. SUBMITTAL DOES NOT INCLUDE ACTUAL PRODUCT DATA FOR EACH TYPE THAT INCLUDE PROFILE, DIMENSIONS, ETC | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 09 68 00-17 - CARPETING - Transition Strips Product Data.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-05-10 |  | 09 68 00-17 - CARPETING - Transition Strips Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-18 |  | 09 68 00-17 - CARPETING - Transition Strips Product Data_POP.pdf
09 68 00-017-01 | 09 68 00 - CARPETING | 09 68 00-017-01 CARPETING - Transition Strips - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-24 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-08 07:00 | 2021-05-27 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-05-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13241 | Received | For Review | 2021-05-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-06-08 07:00 | Submittal Number: 09 68 00-17.1 From: KIM DOWALIBY Final Due Date: 06/01/21 Subject: CARPETING - TRANSITION STRIPS - PRODUCT DATA Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17130 | Forwarded | For Review | 2021-05-24 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-31 | Submittal Number: 09 68 00-17.1 From: KIM DOWALIBY Final Due Date: 06/01/21 Subject: CARPETING - TRANSITION STRIPS - PRODUCT DATA Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17207 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | 1. SEE ATTACHED, DELETE ROPPE, PROVIDE SINGLE MFR TARKETT FOR ALL PROFILES, TYPES NOTED ON PAGES 3-5 2. SEE PAGE 4 FOR COLOR LOCATIONS. 3. CONTRACTOR TO COORDINATE ALL PROFILE TYPES WITH FLOOR THICKNESS SUBMITTED ROPPE #65 TO CONCRETE PROFILE WERE TO 1/8" THICKNESS INSTEAD OF 0, AND ROPPE #75 CARPET TO RESILIENT HAD 3/8" TO 1/4" WHICH APPEARS THICKER THAN FLOOR FINISHES. 4. CM TO COORDINATE ALL ROCKWELL GROUP COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-24 |  | 09 68 00-19 - CARPETING - Transition Strips - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-24 |  | 09 68 00-19 - CARPETING - Transition Strips - Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-27 |  | 09 68 00-17.01 - CARPETING - Transition Strips - Product Data_POP.pdf
09 68 00-017-02 | 09 68 00 - CARPETING | 09 68 00-017-02 CARPETING - Transition Strips - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-30 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-14 | 2021-07-02 | 3 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13716 | Received | For Review | 2021-06-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-14 | Submittal Number: 09 68 00-17.2 From: KIM DOWALIBY Final Due Date: 07/13/21 Subject: CARPETING - TRANSITION STRIPS - PRODUCT DATA Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17757 | Forwarded | For Review | 2021-06-29 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-06 | Submittal Number: 09 68 00-17.2 From: KIM DOWALIBY Final Due Date: 07/13/21 Subject: CARPETING - TRANSITION STRIPS - PRODUCT DATA Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17826 | Responded and Closed | Approved | 2021-07-02 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-29 |  | 09 68 00-17.2 - CARPETING - Transition Strips - Product Data Rev. 2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-29 |  | 09 68 00-17.2 - CARPETING - Transition Strips - Product Data Rev. 2.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-02 |  | 09 68 00-17.2 - CARPETING - Transition Strips - Product Data Rev. 2_POP.pdf
09 68 00-018-00 | 09 68 00 - CARPETING | 09 68 00-018-00 CARPETING - Transition Strips Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-27 | 17 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-05-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13022 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-05-25 | Submittal Number: 09 68 00-18.0 From: KIM DOWALIBY Final Due Date: 05/24/21 Subject: 09 68 00 - CARPETING - TRANSITION STRIPS SAMPLES Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 16852 | Forwarded | For Review | 2021-05-10 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-17 | Submittal Number: 09 68 00-18.0 From: KIM DOWALIBY Final Due Date: 05/24/21 Subject: 09 68 00 - CARPETING - TRANSITION STRIPS SAMPLES Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17208 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. RESUBMIT PER 09 68 00-017-01 PRODUCT DATA COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 09 68 00-18 - CARPETING - Transition Strips Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-10 |  | 09 68 00-18 - CARPETING - Transition Strips Samples.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-27 |  | 09 68 00-18 - CARPETING - Transition Strips Samples_POP.pdf
09 68 00-018-01 | 09 68 00 - CARPETING | 09 68 00-018-01 CARPETING - Transition Strips Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-30 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-14 | 2021-07-02 | 3 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13717 | Received | For Review | 2021-06-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-14 | Submittal Number: 09 68 00-18.1 From: KIM DOWALIBY Final Due Date: 07/13/21 Subject: 09 68 00 - CARPETING - TRANSITION STRIPS SAMPLES Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17758 | Forwarded | For Review | 2021-06-29 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-06 | Submittal Number: 09 68 00-18.1 From: KIM DOWALIBY Final Due Date: 07/13/21 Subject: 09 68 00 - CARPETING - TRANSITION STRIPS SAMPLES Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17828 | Responded and Closed | Approved | 2021-07-02 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-29 |  | 09 68 00-18.1 - CARPETING - Transition Strips Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-29 |  | 09 68 00-18.1 - CARPETING - Transition Strips Samples.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-02 |  | 09 68 00-18.1 - CARPETING - Transition Strips Samples_POP.pdf
09 68 00-019-00 | 09 68 00 - CARPETING | 09 68 00-019-00 CARPETING - Transition Strips - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Closed - Void |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-03 07:00 |  | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-05-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13178 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-06-03 07:00 | Submittal Number: 09 68 00-19.0 From: KIM DOWALIBY Final Due Date: 06/01/21 Subject: CARPETING - TRANSITION STRIPS - PRODUCT DATA Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17066 | Forwarded | For Review | 2021-05-19 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-26 | Submittal Number: 09 68 00-19.0 From: KIM DOWALIBY Final Due Date: 06/01/21 Subject: CARPETING - TRANSITION STRIPS - PRODUCT DATA Description: Spec Section: 09 68 00 - CARPETING Status: OPEN | Info Exchange
| 17135 | Closed | Void | 2021-05-24 | Chad Francis (Populous) |  |  | Discussed with Kim Dowaliby(Mortenson), this is to be submitted as a revision to original submittal 09 68 00-017
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | 09 68 00-19 - CARPETING - Transition Strips - Product Data.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-05-18 |  | 09 68 00-19 - CARPETING - Transition Strips - Product Data.pdf
09 72 00-004-00 | 09 72 00 - WALL COVERINGS | 09 72 00-004-00 WALL COVERINGS - Product Data (Premium) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-12 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-26 | 2020-10-19 | 8 |  | Record Copies; Transfers; Submittals | 09 72 00-004-00-01 - 09 72 00-004-00 WALL COVERINGS - Product Data (Premium) | 8 |  | 2020-10-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08715 | Received | For Review | 2020-10-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-26 | Submittal Number: 09 72 00-4.0 From: DANIELLE SCOTT Final Due Date: 10/23/20 Subject: WALL COVERINGS - PRODUCT DATA (PREMIUM) Description: PRODUCT DATA: FOR ADHESIVES, INDICATING VOC CONTENT. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 11504 | Forwarded | For Review | 2020-10-12 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-19 | Submittal Number: 09 72 00-4.0 From: DANIELLE SCOTT Final Due Date: 10/23/20 Subject: WALL COVERINGS - PRODUCT DATA (PREMIUM) Description: PRODUCT DATA: FOR ADHESIVES, INDICATING VOC CONTENT. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 11714 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-19 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SUBMIT MISSING PRODUCT DATA FOR WC1, 4, 5. AND WC23, 24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-09 |  | 09 72 00-4 WALL COVERINGS - Product Data (Premium).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-09 |  | 09 72 00-4 WALL COVERINGS - Product Data (Premium).pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-19 |  | 09 72 00-4 WALL COVERINGS - Product Data (Premium)_POP.pdf
09 72 00-004-00-01 | 09 72 00 - WALL COVERINGS | 09 72 00-004-00 WALL COVERINGS - Product Data (Premium) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 72 00-004-00 - 09 72 00-004-00 WALL COVERINGS - Product Data (Premium) | -1 | 2020-11-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-19 |  | 09 72 00-4 WALL COVERINGS - Product Data (Premium)_POP.pdf
09 72 00-007-00 | 09 72 00 - WALL COVERINGS | 09 72 00-007-00 WALL COVERINGS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-19 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-02 | 2021-02-04 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10762 | Received | For Review | 2021-01-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-02 | Submittal Number: 09 72 00-7.0 From: DANIELLE SCOTT Final Due Date: 01/29/21 Subject: WALL COVERINGS - SHOP DRAWINGS Description: SHOP DRAWINGS : SHOW LOCATION AND EXTENT OF EACH WALL-COVERING TYPE. INDICATE PATTERN PLACEMENT, SEAMS AND TERMINATION POINTS. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 13997 | Forwarded | For Review | 2021-01-19 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-26 | Submittal Number: 09 72 00-7.0 From: DANIELLE SCOTT Final Due Date: 01/29/21 Subject: WALL COVERINGS - SHOP DRAWINGS Description: SHOP DRAWINGS : SHOW LOCATION AND EXTENT OF EACH WALL-COVERING TYPE. INDICATE PATTERN PLACEMENT, SEAMS AND TERMINATION POINTS. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 11194 | Review Response | Approved as Noted | 2021-02-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14500 | Responded and Closed | Approved as Noted | 2021-02-04 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-15 |  | 09 72 00-7 Wall Covering Shops (Premium & NHL).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-15 |  | 09 72 00-7 Wall Covering Shops (Premium & NHL).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-04 |  | 09 72 00-7 Wall Covering Shops (Premium & NHL)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-15 |  | 09 72 00-7 Wall Covering Shops (Premium & NHL).pdf
09 72 00-008-00 | 09 72 00 - WALL COVERINGS | 09 72 00-008-00 WALL COVERINGS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-09 | 2020-10-05 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08349 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-09 | Submittal Number: 09 72 00-8.0 From: DANIELLE SCOTT Final Due Date: 10/09/20 Subject: WALL COVERINGS - SAMPLES Description: WALL-COVERING SAMPLE: FROM SAME PRODUCTION RUN TO BE USED FOR THE WORK, WITH SPECIFIED TREATMENTS PAINT APPLIED. SHOW COMPLETE PATTERN REPEAT. MARK TOP AND FACE OF FABRIC. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 11062 | Forwarded | For Review | 2020-09-25 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-02 | Submittal Number: 09 72 00-8.0 From: DANIELLE SCOTT Final Due Date: 10/09/20 Subject: WALL COVERINGS - SAMPLES Description: WALL-COVERING SAMPLE: FROM SAME PRODUCTION RUN TO BE USED FOR THE WORK, WITH SPECIFIED TREATMENTS PAINT APPLIED. SHOW COMPLETE PATTERN REPEAT. MARK TOP AND FACE OF FABRIC. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 08577 | Review Response | Approved as Noted | 2020-10-05 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11338 | Responded and Closed | Approved as Noted | 2020-10-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| 11968 | Sent | For Information Only | 2020-10-28 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Danielle Scott |  | Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 09 72 00-8 Wall Coverings - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 09 72 00-8 Wall Coverings - Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-05 |  | 09 72 00-8 Wall Coverings - Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-25 |  | 09 72 00-8 Wall Coverings - Samples.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-09-24 02:00 |  | 09 72 00-8 Wall Coverings - Samples.pdf
09 72 00-013-00 | 09 72 00 - WALL COVERINGS | 09 72 00-013-00 WALL COVERINGS | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-09 | 2020-08-31 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-08-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07772 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2020-09-09 | Submittal Number: 09 72 00-13.0 From: DANIELLE SCOTT Final Due Date: 09/02/20 Subject: WALL COVERINGS Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 10344 | Forwarded | For Review | 2020-08-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 09 72 00-13.0 From: DANIELLE SCOTT Final Due Date: 09/02/20 Subject: WALL COVERINGS Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 07859 | Review Response | Approved | 2020-08-31 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  |  | Info Exchange
| 10449 | Responded and Closed | Approved | 2020-08-31 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 09 72 00-13 WALL COVERINGS - WC15, WC19 and WC22 SAMPLES (1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 09 72 00-13 WALL COVERINGS - WC15, WC19 and WC22 SAMPLES (1).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-31 |  | 09 72 00-13 WALL COVERINGS - WC15, WC19 and WC22 SAMPLES _POP.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 09 72 00-13 WALL COVERINGS - WC15, WC19 and WC22 SAMPLES (1).pdf
09 72 00-014-00 | 09 72 00 - WALL COVERINGS | 09 72 00-014-00 WALL COVERINGS - WC20 and WC21 Product Data (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-05 | 2021-05-06 | 16 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12691 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-05-05 | Submittal Number: 09 72 00-14.0 From: DANIELLE SCOTT Final Due Date: 05/04/21 Subject: WALL COVERINGS - WC20 AND WC21 PRODUCT DATA (BASE BUILDING) Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 16411 | Forwarded | For Review | 2021-04-20 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 09 72 00-14.0 From: DANIELLE SCOTT Final Due Date: 05/04/21 Subject: WALL COVERINGS - WC20 AND WC21 PRODUCT DATA (BASE BUILDING) Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 16777 | Responded and Closed | Approved | 2021-05-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-20 |  | 09 72 00-14 Revision 0 WALL COVERINGS - Product Data (Base Building).pdf
| Forwarded |  | Danielle Scott | 1 | 2021-04-20 |  | 09 72 00-14 Revision 0 WALL COVERINGS - Product Data (Base Building).pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-06 |  | 09 72 00-14 Revision 0 WALL COVERINGS - Product Data (Base Building)_POP.pdf
09 72 00-015-00 | 09 72 00 - WALL COVERINGS | 09 72 00-015-00 WALL COVERINGS - WC23 & WC24 Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-12-01 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09593 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-07 | Submittal Number: 09 72 00-15.0 From: DANIELLE SCOTT Final Due Date: 12/03/20 Subject: WALL COVERINGS - WC23 & WC24 SAMPLES Description: WALLCOVERING SAMPLES FOR WC23 & WC24. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 12627 | Forwarded | For Review | 2020-11-19 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 09 72 00-15.0 From: DANIELLE SCOTT Final Due Date: 12/03/20 Subject: WALL COVERINGS - WC23 & WC24 SAMPLES Description: WALLCOVERING SAMPLES FOR WC23 & WC24. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 09798 | Review Response | Approved | 2020-12-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12880 | Responded and Closed | Approved | 2020-12-01 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-19 |  | 09 72 00-15 Wall Coverings - WC23 & WC24 Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-19 |  | 09 72 00-15 Wall Coverings - WC23 & WC24 Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-01 |  | 09 72 00-15 Wall Coverings - WC23 & WC24 Samples-POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-19 |  | 09 72 00-15 Wall Coverings - WC23 & WC24 Samples.pdf
09 72 00-016-00 | 09 72 00 - WALL COVERINGS | 09 72 00-016-00 Mockup Wall Covering Shop Drawings (Tunnel Suite) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-01 08:00 | 2021-02-01 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10747 | Received | For Review | 2021-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-01 08:00 | Submittal Number: 09 72 00-16.0 From: DANIELLE SCOTT Final Due Date: 01/29/21 Subject: MOCKUP WALL COVERING SHOP DRAWINGS (TUNNEL SUITE) Description: TUNNEL CLUB AND SIDELINE SUITE MOCKUP SHOPS FOR WALL COVERING. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 13981 | Forwarded | For Review | 2021-01-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-22 | Submittal Number: 09 72 00-16.0 From: DANIELLE SCOTT Final Due Date: 01/29/21 Subject: MOCKUP WALL COVERING SHOP DRAWINGS (TUNNEL SUITE) Description: TUNNEL CLUB AND SIDELINE SUITE MOCKUP SHOPS FOR WALL COVERING. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 11108 | Review Response | Approved as Noted | 2021-02-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14411 | Responded and Closed | Approved as Noted | 2021-02-01 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-15 |  | 09 72 00-16 Tunnel Suite Wall Covering Shops (Premium).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-15 |  | 09 72 00-16 Tunnel Suite Wall Covering Shops (Premium).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-01 |  | 09 72 00-16 Tunnel Suite Wall Covering Shops (Premium)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-15 |  | 09 72 00-16 Tunnel Suite Wall Covering Shops (Premium).pdf
09 72 00-017-00 | 09 72 00 - WALL COVERINGS | 09 72 00-017-00 Wall Covering - Sideline Suite Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-11 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-05 | 2020-12-21 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-12-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10110 | Received | For Review | 2020-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-05 | Submittal Number: 09 72 00-17.0 From: DANIELLE SCOTT Final Due Date: 12/25/20 Subject: WALL COVERING - SIDELINE SUITE SHOP DRAWINGS Description: ONLY SIDELINE SUITE SHOP DRAWINGS. SUITE CORRIDOR WALL COVERING SHOPS WILL BE INCLUDED IN A DIFFERENT SUBMITTAL. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 13219 | Forwarded | For Review | 2020-12-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-18 | Submittal Number: 09 72 00-17.0 From: DANIELLE SCOTT Final Due Date: 12/25/20 Subject: WALL COVERING - SIDELINE SUITE SHOP DRAWINGS Description: ONLY SIDELINE SUITE SHOP DRAWINGS. SUITE CORRIDOR WALL COVERING SHOPS WILL BE INCLUDED IN A DIFFERENT SUBMITTAL. Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 13446 | Responded and Closed | Approved as Noted | 2020-12-21 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED POP HAS NO EXCEPTIONS. CM TO COORDINATE ALL ROCKWELL REVIEW COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-11 |  | 19 72 00-17 Wall Covering Sideline Suite Shop Dwg.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-11 |  | 19 72 00-17 Wall Covering Sideline Suite Shop Dwg.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-12-21 |  | 09 72 00-17.0 Wall Covering Sideline Suite Shop Dwg_POP.pdf
09 72 00-018-00 | 09 72 00 - WALL COVERINGS | 09 72 00-018-00 WC20 & WC21 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-03-01 | 15 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11397 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-03-01 | Submittal Number: 09 72 00-18.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: WC20 & WC21 SAMPLE Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 14764 | Forwarded | For Review | 2021-02-13 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 09 72 00-18.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: WC20 & WC21 SAMPLE Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 11700 | Review Response | Approved | 2021-03-01 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 15157 | Responded and Closed | Approved | 2021-03-01 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-12 |  | 09 72 00-18 Revision 0 WC20 & WC21 Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-12 |  | 09 72 00-18 Revision 0 WC20 & WC21 Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-01 |  | 09 72 00-18 Revision 0 WC20 & WC21 Sample_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-12 |  | 09 72 00-18 Revision 0 WC20 & WC21 Sample.pdf
09 72 00-019-00 | 09 72 00 - WALL COVERINGS | 09 72 00-019-00 Wallcovering Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-23 | 2021-04-27 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12519 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-04-23 | Submittal Number: 09 72 00-19.0 From: DANIELLE SCOTT Final Due Date: 04/23/21 Subject: WALLCOVERING SAMPLES Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 16208 | Forwarded | For Review | 2021-04-09 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-16 | Submittal Number: 09 72 00-19.0 From: DANIELLE SCOTT Final Due Date: 04/23/21 Subject: WALLCOVERING SAMPLES Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 12798 | Review Response | Approved | 2021-04-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16542 | Responded and Closed | Approved | 2021-04-27 | Danielle Scott | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-09 |  | 09 72 00-19 Revision 0 Wallcovering Samples.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-04-09 |  | 09 72 00-19 Revision 0 Wallcovering Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-27 |  | 09 72 00-19 Revision 0 Wallcovering Samples_POP.pdf
| Responded and Closed |  | Danielle Scott | 1 | 2021-04-09 |  | 09 72 00-19 Revision 0 Wallcovering Samples.pdf
09 72 00-020-00 | 09 72 00 - WALL COVERINGS | 09 72 00-020-00 WC7 and WC8 Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-05 | 2021-05-06 | 16 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12692 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-05-05 | Submittal Number: 09 72 00-20.0 From: DANIELLE SCOTT Final Due Date: 05/04/21 Subject: WC7 AND WC8 PRODUCT DATA Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 16412 | Forwarded | For Review | 2021-04-20 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 09 72 00-20.0 From: DANIELLE SCOTT Final Due Date: 05/04/21 Subject: WC7 AND WC8 PRODUCT DATA Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 16776 | Responded and Closed | Approved as Noted | 2021-05-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-20 |  | 09 72 00-20 Revision 0 WC7 and WC8 Product Data.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-04-20 |  | 09 72 00-20 Revision 0 WC7 and WC8 Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-06 |  | 09 72 00-20 Revision 0 WC7 and WC8 Product Data_POP.pdf
09 72 00-021-00 | 09 72 00 - WALL COVERINGS | 09 72 00-021-00 WALL COVERINGS - NHL WC6 - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-28 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-14 07:00 | 2021-06-01 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-06-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13316 | Received | For Review | 2021-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-06-14 07:00 | Submittal Number: 09 72 00-21.0 From: KIM DOWALIBY Final Due Date: 06/09/21 Subject: WALL COVERINGS - NHL WC6 - SAMPLE Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 17231 | Forwarded | For Review | 2021-06-01 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 09 72 00-21.0 From: KIM DOWALIBY Final Due Date: 06/09/21 Subject: WALL COVERINGS - NHL WC6 - SAMPLE Description: Spec Section: 09 72 00 - WALL COVERINGS Status: OPEN | Info Exchange
| 13338 | Review Response | Approved | 2021-06-01 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17258 | Responded and Closed | Approved | 2021-06-01 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-27 |  | 09 72 00-21 WALL COVERINGS - NHL WC6 - Sample.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-05-27 |  | 09 72 00-21 WALL COVERINGS - NHL WC6 - Sample.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-01 |  | 09 72 00-21 WALL COVERINGS - NHL WC6 - Sample_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-27 |  | 09 72 00-21 WALL COVERINGS - NHL WC6 - Sample.pdf
09 77 13-002-00 | 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS | 09 77 13-002-00 STRETCHED-FABRIC WALL SYSTEMS - Product Data & Sustainability | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-20 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10391 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-19 08:00 | Submittal Number: 09 77 13-2.0 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - PRODUCT DATA & SUSTAINABILITY Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE FABRIC FACING, FRAME EDGE AND TRIM, CORE MATERIAL, AND MOUNTING INDICATED. SUSTAINABILITY INFORMATION ALSO INCLUDED ON SHEET 7. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 13575 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 09 77 13-2.0 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - PRODUCT DATA & SUSTAINABILITY Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE FABRIC FACING, FRAME EDGE AND TRIM, CORE MATERIAL, AND MOUNTING INDICATED. SUSTAINABILITY INFORMATION ALSO INCLUDED ON SHEET 7. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 10819 | Review Response | Approved as Noted | 2021-01-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14067 | Responded and Closed | Approved as Noted | 2021-01-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-23 |  | 09 77 13-2 STRETCHED-FABRIC WALL SYSTEMS - Product Data & Sustainability.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-23 |  | 09 77 13-2 STRETCHED-FABRIC WALL SYSTEMS - Product Data & Sustainability.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-20 |  | 09 77 13-2 STRETCHED-FABRIC WALL SYSTEMS - Product Data & Sustainability_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-23 |  | 09 77 13-2 STRETCHED-FABRIC WALL SYSTEMS - Product Data & Sustainability.pdf
09 77 13-004-00 | 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS | 09 77 13-004-00 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-21 | 18 |  | Record Copies; Transfers; Submittals | 09 77 13-004-01 - 09 77 13-004-01 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings | 18 |  | 2021-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10390 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-19 08:00 | Submittal Number: 09 77 13-4.0 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH STRETCHED-FABRIC SYSTEM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND INSTALLATION AND SYSTEM DETAILS. 2. INCLUDE DETAILS AT HEAD, BASE, JOINTS, AND CORNERS; AND DETAILS AT CEILING, FLOOR BASE, AND WALL INTERSECTIONS. INDICATE FRAME-EDGE PROFILE AND CORE MATERIALS. 3. INCLUDE DETAILS AT CUTOUTS AND PENETRATIONS FOR OTHER WORK. 4. INCLUDE DIRECTION OF FABRIC WEAVE AND PATTERN MATCHING. 5. SHOW SEWN-SEAM LOCATIONS, TYPES, AND METHODS. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 13574 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 09 77 13-4.0 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH STRETCHED-FABRIC SYSTEM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND INSTALLATION AND SYSTEM DETAILS. 2. INCLUDE DETAILS AT HEAD, BASE, JOINTS, AND CORNERS; AND DETAILS AT CEILING, FLOOR BASE, AND WALL INTERSECTIONS. INDICATE FRAME-EDGE PROFILE AND CORE MATERIALS. 3. INCLUDE DETAILS AT CUTOUTS AND PENETRATIONS FOR OTHER WORK. 4. INCLUDE DIRECTION OF FABRIC WEAVE AND PATTERN MATCHING. 5. SHOW SEWN-SEAM LOCATIONS, TYPES, AND METHODS. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 10856 | Review Response | Revise and Resubmit | 2021-01-21 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14102 | Responded and Closed | Revise and Resubmit | 2021-01-21 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-23 |  | 09 77 13-4 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-23 |  | 09 77 13-4 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-21 |  | 09 77 13-4 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-23 |  | 09 77 13-4 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings.pdf
09 77 13-004-01 | 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS | 09 77 13-004-01 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-24 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2021-03-10 | 2021-03-10 | 15 |  | Record Copies; Transfers; Submittals | 09 77 13-004-00 - 09 77 13-004-00 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings | 15 | 2021-02-04 | 2021-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11624 | Received | For Review | 2021-02-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-10 | Submittal Number: 09 77 13-4.1 From: DANIELLE SCOTT Final Due Date: 03/10/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH STRETCHED-FABRIC SYSTEM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND INSTALLATION AND SYSTEM DETAILS. 2. INCLUDE DETAILS AT HEAD, BASE, JOINTS, AND CORNERS; AND DETAILS AT CEILING, FLOOR BASE, AND WALL INTERSECTIONS. INDICATE FRAME-EDGE PROFILE AND CORE MATERIALS. 3. INCLUDE DETAILS AT CUTOUTS AND PENETRATIONS FOR OTHER WORK. 4. INCLUDE DIRECTION OF FABRIC WEAVE AND PATTERN MATCHING. 5. SHOW SEWN-SEAM LOCATIONS, TYPES, AND METHODS. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 15067 | Forwarded | For Review | 2021-02-24 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-03-03 | Submittal Number: 09 77 13-4.1 From: DANIELLE SCOTT Final Due Date: 03/10/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH STRETCHED-FABRIC SYSTEM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND INSTALLATION AND SYSTEM DETAILS. 2. INCLUDE DETAILS AT HEAD, BASE, JOINTS, AND CORNERS; AND DETAILS AT CEILING, FLOOR BASE, AND WALL INTERSECTIONS. INDICATE FRAME-EDGE PROFILE AND CORE MATERIALS. 3. INCLUDE DETAILS AT CUTOUTS AND PENETRATIONS FOR OTHER WORK. 4. INCLUDE DIRECTION OF FABRIC WEAVE AND PATTERN MATCHING. 5. SHOW SEWN-SEAM LOCATIONS, TYPES, AND METHODS. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 11923 | Review Response | Approved as Noted | 2021-03-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15449 | Responded and Closed | Approved as Noted | 2021-03-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-24 02:00 |  | 09 77 13-4 Revision 1 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-24 02:00 |  | 09 77 13-4 Revision 1 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-10 |  | 09 77 13-004-01 STRETCHED-FABRIC WALL SYSTEMS - SD _POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-24 |  | 09 77 13-4 Revision 1 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings.pdf
09 77 13-004-02 | 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS | 09 77 13-004-02 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-27 | 23 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12363 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-04-19 | Submittal Number: 09 77 13-4.2 From: DANIELLE SCOTT Final Due Date: 04/14/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH STRETCHED-FABRIC SYSTEM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND INSTALLATION AND SYSTEM DETAILS. 2. INCLUDE DETAILS AT HEAD, BASE, JOINTS, AND CORNERS; AND DETAILS AT CEILING, FLOOR BASE, AND WALL INTERSECTIONS. INDICATE FRAME-EDGE PROFILE AND CORE MATERIALS. 3. INCLUDE DETAILS AT CUTOUTS AND PENETRATIONS FOR OTHER WORK. 4. INCLUDE DIRECTION OF FABRIC WEAVE AND PATTERN MATCHING. 5. SHOW SEWN-SEAM LOCATIONS, TYPES, AND METHODS. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 16019 | Forwarded | For Review | 2021-04-01 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 09 77 13-4.2 From: DANIELLE SCOTT Final Due Date: 04/14/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH STRETCHED-FABRIC SYSTEM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND INSTALLATION AND SYSTEM DETAILS. 2. INCLUDE DETAILS AT HEAD, BASE, JOINTS, AND CORNERS; AND DETAILS AT CEILING, FLOOR BASE, AND WALL INTERSECTIONS. INDICATE FRAME-EDGE PROFILE AND CORE MATERIALS. 3. INCLUDE DETAILS AT CUTOUTS AND PENETRATIONS FOR OTHER WORK. 4. INCLUDE DIRECTION OF FABRIC WEAVE AND PATTERN MATCHING. 5. SHOW SEWN-SEAM LOCATIONS, TYPES, AND METHODS. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 12666 | Review Response | Approved as Noted | 2021-04-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 16387 | Responded and Closed | Approved as Noted | 2021-04-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| 16566 | Reopened | Additional Information | 2021-04-27 11:42 | Kelsea Conkright (Populous)
| 12812 | Review Response | Approved as Noted/Resubmit | 2021-04-27 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16567 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-27 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 09 77 13-4 Revision 2 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-01 |  | 09 77 13-4 Revision 2 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-20 |  | 09 77 13-4 Revision 2 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-01 |  | 09 77 13-4 Revision 2 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-27 |  | 09 77 13-4 Revision 2 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 09 77 13-4 Revision 2 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings.pdf
09 77 13-004-03 | 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS | 09 77 13-004-03 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-01 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-16 07:00 | 2021-07-13 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13747 | Received | For Review | 2021-07-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-16 07:00 | Submittal Number: 09 77 13-4.3 From: KIM DOWALIBY Final Due Date: 07/14/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH STRETCHED-FABRIC SYSTEM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND INSTALLATION AND SYSTEM DETAILS. 2. INCLUDE DETAILS AT HEAD, BASE, JOINTS, AND CORNERS; AND DETAILS AT CEILING, FLOOR BASE, AND WALL INTERSECTIONS. INDICATE FRAME-EDGE PROFILE AND CORE MATERIALS. 3. INCLUDE DETAILS AT CUTOUTS AND PENETRATIONS FOR OTHER WORK. 4. INCLUDE DIRECTION OF FABRIC WEAVE AND PATTERN MATCHING. 5. SHOW SEWN-SEAM LOCATIONS, TYPES, AND METHODS. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 17796 | Forwarded | For Review | 2021-07-01 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-08 | Submittal Number: 09 77 13-4.3 From: KIM DOWALIBY Final Due Date: 07/14/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH STRETCHED-FABRIC SYSTEM. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND INSTALLATION AND SYSTEM DETAILS. 2. INCLUDE DETAILS AT HEAD, BASE, JOINTS, AND CORNERS; AND DETAILS AT CEILING, FLOOR BASE, AND WALL INTERSECTIONS. INDICATE FRAME-EDGE PROFILE AND CORE MATERIALS. 3. INCLUDE DETAILS AT CUTOUTS AND PENETRATIONS FOR OTHER WORK. 4. INCLUDE DIRECTION OF FABRIC WEAVE AND PATTERN MATCHING. 5. SHOW SEWN-SEAM LOCATIONS, TYPES, AND METHODS. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 13911 | Review Response | Approved as Noted | 2021-07-13 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18014 | Responded and Closed | Approved as Noted | 2021-07-13 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| 18023 | Reopened | Additional Information | 2021-07-13 17:17 | Kelsea Conkright (Populous)
| 13921 | Review Response | Approved as Noted | 2021-07-13 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18024 | Responded and Closed | Approved as Noted | 2021-07-13 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-30 |  | 09 77 13-4.3 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings Rev 3.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-30 |  | 09 77 13-4.3 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings Rev 3.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-13 |  | 09 77 13-4.3 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings Rev 3_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-06-30 |  | 09 77 13-4.3 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings Rev 3.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-07-13 |  | 09 77 13-4.3 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings Rev 3_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-06-30 |  | 09 77 13-4.3 STRETCHED-FABRIC WALL SYSTEMS - Shop Drawings Rev 3.pdf
09 77 13-005-00 | 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS | 09 77 13-005-00 STRETCHED-FABRIC WALL SYSTEMS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-20 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10389 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-19 08:00 | Submittal Number: 09 77 13-5.0 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS: 1. FABRIC: FULL-WIDTH BY APPROXIMATELY 36-INCH- LONG SAMPLE, BUT NOT SMALLER THAN REQUIRED TO SHOW COMPLETE PATTERN REPEAT, FROM DYE LOT TO BE USED FOR THE WORK, AND WITH SPECIFIED TREATMENTS APPLIED. MARK TOP AND FACE OF FABRIC. 2. FRAME SYSTEM: 12-INCH-SQUARE SAMPLE(S) SHOWING EACH EDGE PROFILE AND CORNER. 3. CORE MATERIAL: 12-INCH-SQUARE SAMPLE AT CORNER. 4. ASSEMBLED SYSTEM: APPROXIMATELY 36 BY 36 INCHES, INCLUDING JOINTS AND SEAMS IN MOCKUP. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 13572 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 09 77 13-5.0 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS: 1. FABRIC: FULL-WIDTH BY APPROXIMATELY 36-INCH- LONG SAMPLE, BUT NOT SMALLER THAN REQUIRED TO SHOW COMPLETE PATTERN REPEAT, FROM DYE LOT TO BE USED FOR THE WORK, AND WITH SPECIFIED TREATMENTS APPLIED. MARK TOP AND FACE OF FABRIC. 2. FRAME SYSTEM: 12-INCH-SQUARE SAMPLE(S) SHOWING EACH EDGE PROFILE AND CORNER. 3. CORE MATERIAL: 12-INCH-SQUARE SAMPLE AT CORNER. 4. ASSEMBLED SYSTEM: APPROXIMATELY 36 BY 36 INCHES, INCLUDING JOINTS AND SEAMS IN MOCKUP. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 10820 | Review Response | Approved as Noted | 2021-01-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14069 | Responded and Closed | Approved as Noted | 2021-01-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-23 |  | 09 77 13-5 STRETCHED-FABRIC WALL SYSTEMS - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-23 |  | 09 77 13-5 STRETCHED-FABRIC WALL SYSTEMS - Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-20 |  | 09 77 13-5 STRETCHED-FABRIC WALL SYSTEMS - Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-23 |  | 09 77 13-5 STRETCHED-FABRIC WALL SYSTEMS - Samples.pdf
09 77 13-009-00 | 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS | 09 77 13-009-00 STRETCHED-FABRIC WALL SYSTEMS - Sample Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-24 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-08 07:00 | 2021-04-09 | 17 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-04-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12184 | Received | For Review | 2021-03-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-08 07:00 | Submittal Number: 09 77 13-9.0 From: DANIELLE SCOTT Final Due Date: 04/06/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SAMPLE WARRANTY Description: SAMPLE WARRANTY : FOR SPECIAL WARRANTY. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 15770 | Forwarded | For Review | 2021-03-23 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-30 | Submittal Number: 09 77 13-9.0 From: DANIELLE SCOTT Final Due Date: 04/06/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - SAMPLE WARRANTY Description: SAMPLE WARRANTY : FOR SPECIAL WARRANTY. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 12504 | Review Response | Approved | 2021-04-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 16193 | Responded and Closed | Approved | 2021-04-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-23 |  | 09 77 13-9 Revision 0 STRETCHED-FABRIC WALL SYSTEMS - Sample Warranty.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-23 |  | 09 77 13-9 Revision 0 STRETCHED-FABRIC WALL SYSTEMS - Sample Warranty.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-09 |  | 09 77 13-9 Revision 0 STRETCHED-FABRIC WALL SYSTEMS - Sample Warranty_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-23 |  | 09 77 13-9 Revision 0 STRETCHED-FABRIC WALL SYSTEMS - Sample Warranty.pdf
09 77 13-010-01 | 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS | 09 77 13-010-01 STRETCHED-FABRIC WALL SYSTEMS - Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-10 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-24 | 2021-08-10 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-08-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14286 | Received | For Review | 2021-08-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-08-24 | Submittal Number: 09 77 13-10.1 From: KIM DOWALIBY Final Due Date: 08/23/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR STRETCHED-FABRIC SYSTEMS TO INCLUDE IN MAINTENANCE MANUALS. INCLUDE FABRIC MANUFACTURER'S WRITTEN CLEANING, STAIN-REMOVAL, RESTRETCHING, AND REUPHOLSTERING INSTRUCTIONS. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 18453 | Forwarded | For Review | 2021-08-10 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-17 | Submittal Number: 09 77 13-10.1 From: KIM DOWALIBY Final Due Date: 08/23/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR STRETCHED-FABRIC SYSTEMS TO INCLUDE IN MAINTENANCE MANUALS. INCLUDE FABRIC MANUFACTURER'S WRITTEN CLEANING, STAIN-REMOVAL, RESTRETCHING, AND REUPHOLSTERING INSTRUCTIONS. Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 14289 | Review Response | Approved | 2021-08-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18456 | Responded and Closed | Approved | 2021-08-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-09 |  | 09 77 13-10.1 STRETCHED-FABRIC WALL SYSTEMS - Maintenance Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-09 |  | 09 77 13-10.1 STRETCHED-FABRIC WALL SYSTEMS - Maintenance Data.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-10 |  | 09 77 13-10.1 STRETCHED-FABRIC WALL SYSTEMS - MD_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-09 |  | 09 77 13-10.1 STRETCHED-FABRIC WALL SYSTEMS - Maintenance Data.pdf
09 77 13-011-00 | 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS | 09 77 13-011-00 Stretched Fabric Wall Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-23 | 2021-04-27 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12520 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-04-23 | Submittal Number: 09 77 13-11.0 From: DANIELLE SCOTT Final Due Date: 04/23/21 Subject: STRETCHED FABRIC WALL SAMPLES Description: Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 16209 | Forwarded | For Review | 2021-04-09 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-16 | Submittal Number: 09 77 13-11.0 From: DANIELLE SCOTT Final Due Date: 04/23/21 Subject: STRETCHED FABRIC WALL SAMPLES Description: Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 12800 | Review Response | Approved as Noted | 2021-04-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16544 | Responded and Closed | Approved as Noted | 2021-04-27 | Danielle Scott | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-09 |  | 09 77 13-11 Revision 0 Stretched Fabric Wall Samples.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-04-09 |  | 09 77 13-11 Revision 0 Stretched Fabric Wall Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-27 |  | 09 72 00-19 Revision 0 Wallcovering Samples_POP.pdf
| Responded and Closed |  | Danielle Scott | 1 | 2021-04-09 |  | 09 77 13-11 Revision 0 Stretched Fabric Wall Samples.pdf
09 77 13-012-00 | 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS | 09 77 13-012-00 STRETCHED-FABRIC WALL SYSTEMS - F-3 Green Room Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-21 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-07 07:00 | 2021-06-04 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13219 | Received | For Review | 2021-05-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-06-07 07:00 | Submittal Number: 09 77 13-12.0 From: KIM DOWALIBY Final Due Date: 06/03/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - F-3 GREEN ROOM SAMPLE Description: Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 17109 | Forwarded | For Review | 2021-05-21 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-28 | Submittal Number: 09 77 13-12.0 From: KIM DOWALIBY Final Due Date: 06/03/21 Subject: STRETCHED-FABRIC WALL SYSTEMS - F-3 GREEN ROOM SAMPLE Description: Spec Section: 09 77 13 - STRETCHED-FABRIC WALL SYSTEMS Status: OPEN | Info Exchange
| 13406 | Review Response | Approved | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17339 | Responded and Closed | Approved | 2021-06-04 | Kim Dowaliby | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-20 |  | 09 77 13-12 - STRETCHED-FABRIC WALL SYSTEMS - F-3 Green Room Sample.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-05-20 |  | 09 77 13-12 - STRETCHED-FABRIC WALL SYSTEMS - F-3 Green Room Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-04 |  | 09 77 13-12 - STRETCHED-FABRIC WALL SYSTEMS - F-3_POP.pdf
| Responded and Closed |  | Kim Dowaliby | 1 | 2021-05-20 |  | 09 77 13-12 - STRETCHED-FABRIC WALL SYSTEMS - F-3 Green Room Sample.pdf
09 84 33-010-00 | 09 84 33 - SOUND-ABSORBING WALL UNITS | 09 84 33-010-00 SOUND-ABSORBING WALL UNITS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-20 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10387 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-19 08:00 | Submittal Number: 09 84 33-10.0 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: SOUND-ABSORBING WALL UNITS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS: 1. FABRIC: FULL-WIDTH BY APPROXIMATELY 36-INCH- LONG SAMPLE, BUT NOT SMALLER THAN REQUIRED TO SHOW COMPLETE PATTERN REPEAT, FROM DYE LOT TO BE USED FOR THE WORK, AND WITH SPECIFIED TREATMENTS APPLIED. MARK TOP AND FACE OF FABRIC. 2. PERFORATED METAL: 12-INCH-SQUARE SAMPLE. 3. PANEL EDGE: 12-INCH-LONG SAMPLE(S) SHOWING EACH EDGE PROFILE, CORNER, AND FINISH. 4. CORE MATERIAL: 12-INCH-SQUARE SAMPLE AT CORNER. 5. MOUNTING DEVICES: FULL-SIZE SAMPLES. 6. ASSEMBLED PANELS: APPROXIMATELY 36 BY 36 INCHES, INCLUDING JOINTS AND MOUNTING METHODS. Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 13571 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 09 84 33-10.0 From: DANIELLE SCOTT Final Due Date: 01/06/21 Subject: SOUND-ABSORBING WALL UNITS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS: 1. FABRIC: FULL-WIDTH BY APPROXIMATELY 36-INCH- LONG SAMPLE, BUT NOT SMALLER THAN REQUIRED TO SHOW COMPLETE PATTERN REPEAT, FROM DYE LOT TO BE USED FOR THE WORK, AND WITH SPECIFIED TREATMENTS APPLIED. MARK TOP AND FACE OF FABRIC. 2. PERFORATED METAL: 12-INCH-SQUARE SAMPLE. 3. PANEL EDGE: 12-INCH-LONG SAMPLE(S) SHOWING EACH EDGE PROFILE, CORNER, AND FINISH. 4. CORE MATERIAL: 12-INCH-SQUARE SAMPLE AT CORNER. 5. MOUNTING DEVICES: FULL-SIZE SAMPLES. 6. ASSEMBLED PANELS: APPROXIMATELY 36 BY 36 INCHES, INCLUDING JOINTS AND MOUNTING METHODS. Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 10817 | Review Response | Approved | 2021-01-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14065 | Responded and Closed | Approved | 2021-01-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-23 |  | 09 84 33-10 Sound Aborbing Wall Units Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-23 |  | 09 84 33-10 Sound Aborbing Wall Units Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-20 |  | 09 84 33-10 Sound Aborbing Wall Units Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-23 |  | 09 84 33-10 Sound Aborbing Wall Units Samples.pdf
09 84 33-016-00 | 09 84 33 - SOUND-ABSORBING WALL UNITS | 09 84 33-016-00 Sound Absorbing Wall Units Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-16 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-02 08:00 | 2020-12-02 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09439 | Received | For Review | 2020-11-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-12-02 08:00 | Submittal Number: 09 84 33-16.0 From: MIKE SOLFELT Final Due Date: 11/30/20 Subject: SOUND ABSORBING WALL UNITS PRODUCT DATA Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 12448 | Forwarded | For Review | 2020-11-16 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-23 | Submittal Number: 09 84 33-16.0 From: MIKE SOLFELT Final Due Date: 11/30/20 Subject: SOUND ABSORBING WALL UNITS PRODUCT DATA Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 09823 | Review Response | Approved as Noted | 2020-12-02 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12909 | Responded and Closed | Approved as Noted | 2020-12-02 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 09 84 33-16 Sound Absorbing Wall Units Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 09 84 33-16 Sound Absorbing Wall Units Product Data.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-02 |  | 09 84 33-16 Sound Absorbing Wall Units Product Data_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-16 |  | 09 84 33-16 Sound Absorbing Wall Units Product Data.pdf
09 84 33-017-00 | 09 84 33 - SOUND-ABSORBING WALL UNITS | 09 84 33-017-00 Sound Absorbing Wall Units Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-21 | 2020-12-10 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09968 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-12-21 | Submittal Number: 09 84 33-17.0 From: MIKE SOLFELT Final Due Date: 12/21/20 Subject: SOUND ABSORBING WALL UNITS SAMPLES Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 13044 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 09 84 33-17.0 From: MIKE SOLFELT Final Due Date: 12/21/20 Subject: SOUND ABSORBING WALL UNITS SAMPLES Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 10091 | Review Response | Approved | 2020-12-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13192 | Responded and Closed | Approved | 2020-12-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 09 84 33-17 Sound Aborbing Wall Units Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-07 |  | 09 84 33-17 Sound Aborbing Wall Units Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-07 |  | 09 84 33-17 Sound Aborbing Wall Units Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-07 |  | 09 84 33-17 Sound Aborbing Wall Units Samples.pdf
09 84 33-018-00 | 09 84 33 - SOUND-ABSORBING WALL UNITS | 09 84 33-018-00 Sound Absorbing Wall Units Layout - Space Needle | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-21 | 2021-01-15 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-01-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10505 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-01-21 | Submittal Number: 09 84 33-18.0 From: MIKE SOLFELT Final Due Date: 01/21/21 Subject: SOUND ABSORBING WALL UNITS LAYOUT - SPACE NEEDLE Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 13707 | Forwarded | For Review | 2021-01-07 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-14 | Submittal Number: 09 84 33-18.0 From: MIKE SOLFELT Final Due Date: 01/21/21 Subject: SOUND ABSORBING WALL UNITS LAYOUT - SPACE NEEDLE Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 10754 | Review Response | Approved as Noted | 2021-01-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13987 | Responded and Closed | Approved as Noted | 2021-01-15 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-07 |  | 09 84 33-18 Sound Aborbing Wall Units Layout - Space Needle.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-07 |  | 09 84 33-18 Sound Aborbing Wall Units Layout - Space Needle.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-15 |  | 09 84 33-18 Sound Aborbing Wall Units Layout - Space Needle_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-07 |  | 09 84 33-18 Sound Aborbing Wall Units Layout - Space Needle.pdf
09 84 33-019-00 | 09 84 33 - SOUND-ABSORBING WALL UNITS | 09 84 33-019-00 Space Needle Sound Absorbing Wall Units - Back Walls and Corners | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-10 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-24 | 2021-03-26 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11916 | Received | For Review | 2021-03-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-03-24 | Submittal Number: 09 84 33-19.0 From: MIKE SOLFELT Final Due Date: 03/24/21 Subject: SPACE NEEDLE SOUND ABSORBING WALL UNITS - BACK WALLS AND CORNERS Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 15439 | Forwarded | For Review | 2021-03-10 | Mike Solfelt (Mortenson Construction) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-17 | Submittal Number: 09 84 33-19.0 From: MIKE SOLFELT Final Due Date: 03/24/21 Subject: SPACE NEEDLE SOUND ABSORBING WALL UNITS - BACK WALLS AND CORNERS Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 12264 | Review Response | Approved as Noted | 2021-03-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15863 | Responded and Closed | Approved as Noted | 2021-03-26 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-10 |  | 09 84 33-19 Sound Aborbing Wall Units Layout - Space Needle and Elevator Corners.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-03-10 |  | 09 84 33-19 Sound Aborbing Wall Units Layout - Space Needle and Elevator Corners.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-26 |  | 09 84 33-19 Sound Aborbing Wall Units - Space Needle and Elevator Corners_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-03-10 |  | 09 84 33-19 Sound Aborbing Wall Units Layout - Space Needle and Elevator Corners.pdf
09 84 33-020-00 | 09 84 33 - SOUND-ABSORBING WALL UNITS | 09 84 33-020-00 Sound Absorbing Wall Units - Bridge Level | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-12 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-26 | 2021-04-28 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12534 | Received | For Review | 2021-04-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-04-26 | Submittal Number: 09 84 33-20.0 From: MIKE SOLFELT Final Due Date: 04/26/21 Subject: SOUND ABSORBING WALL UNITS - BRIDGE LEVEL Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 16236 | Forwarded | For Review | 2021-04-12 | Mike Solfelt (Mortenson Construction) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-19 | Submittal Number: 09 84 33-20.0 From: MIKE SOLFELT Final Due Date: 04/26/21 Subject: SOUND ABSORBING WALL UNITS - BRIDGE LEVEL Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 12834 | Review Response | Approved as Noted | 2021-04-28 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 16610 | Responded and Closed | Approved as Noted | 2021-04-28 | Mike Solfelt (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-12 |  | 09 84 33-20 Sound Aborbing Wall Units Layout - Bridge Level.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-04-12 |  | 09 84 33-20 Sound Aborbing Wall Units Layout - Bridge Level.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-28 |  | 09 84 33-20 Sound Aborbing Wall Units Layout - Bridge Level_POP.pdf
| Responded and Closed |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-04-12 |  | 09 84 33-20 Sound Aborbing Wall Units Layout - Bridge Level.pdf
09 84 33-021-00 | 09 84 33 - SOUND-ABSORBING WALL UNITS | 09 84 33-021-00 SP5 Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-01 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-16 07:00 | 2021-07-13 | 13 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13743 | Received | For Review | 2021-07-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-07-16 07:00 | Submittal Number: 09 84 33-21.0 From: MIKE SOLFELT Final Due Date: 07/13/21 Subject: SP5 SAMPLES Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 17789 | Forwarded | For Review | 2021-06-30 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-07 | Submittal Number: 09 84 33-21.0 From: MIKE SOLFELT Final Due Date: 07/13/21 Subject: SP5 SAMPLES Description: Spec Section: 09 84 33 - SOUND-ABSORBING WALL UNITS Status: OPEN | Info Exchange
| 13909 | Review Response | Approved | 2021-07-13 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18011 | Responded and Closed | Approved | 2021-07-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-30 |  | 09 84 33-21 SP5 Linear Wood Grill.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-30 |  | 09 84 33-21 SP5 Linear Wood Grill.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-07-12 |  | 09 84 33-21 SP5 Linear Wood Grill_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-30 |  | 09 84 33-21 SP5 Linear Wood Grill.pdf
09 91 23-001-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-001-00 Interior Painting - Miscellaneous Metals Primer Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-02 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-16 | 2020-07-10 | 9 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-07-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06768 | Received | For Review | 2020-07-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-07-16 | Submittal Number: 09 91 23-1.0 From: NATE WEINGART Final Due Date: 07/16/20 Subject: INTERIOR PAINTING - MISCELLANEOUS METALS PRIMER PRODUCT DATA Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 09096 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-07-13 | Submittal Number: 09 91 23-1.0 From: NATE WEINGART Final Due Date: 07/16/20 Subject: INTERIOR PAINTING - MISCELLANEOUS METALS PRIMER PRODUCT DATA Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 06908 | Review Response | Revise and Resubmit | 2020-07-10 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Submit primer with topcoat; provide data for the entire coating system together. | Mail
| 09248 | Responded and Closed | Revise and Resubmit | 2020-07-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Primer does not match specification. Submit primer and topcoat together as one system. Provide proof that primer is compatible with paint, and that submitted primer is equal to specified primer. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-02 |  | 099123-1.0 Interior Painting - Miscellaneous Metals Primer Product Data (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-02 |  | 099123-1.0 Interior Painting - Miscellaneous Metals Primer Product Data (MAM Review).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-07-02 |  | 099123-1.0 Interior Painting - Miscellaneous Metals Primer Product Data (MAM Review).pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-02 |  | 099123-1.0 Interior Painting - Miscellaneous Metals Primer Product Data (MAM Review).pdf
09 91 23-001-01 | 09 91 23 - INTERIOR PAINTING | 09 91 23-001-01 Interior Painting - Miscellaneous Metals Primer Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-13 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-27 | 2020-08-20 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07534 | Received | For Review | 2020-08-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-27 | Submittal Number: 09 91 23-1.1 From: NATE WEINGART Final Due Date: 08/21/20 Subject: INTERIOR PAINTING - MISCELLANEOUS METALS PRIMER PRODUCT DATA Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 10034 | Forwarded | For Review | 2020-08-13 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-20 | Submittal Number: 09 91 23-1.1 From: NATE WEINGART Final Due Date: 08/21/20 Subject: INTERIOR PAINTING - MISCELLANEOUS METALS PRIMER PRODUCT DATA Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 10168 | Responded and Closed | Approved | 2020-08-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-13 |  | 09 91 23-1 R1 Interior Painting - MM Primer.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-13 |  | 09 91 23-1 R1 Interior Painting - MM Primer.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-20 |  | 09 91 23-1 R1 Interior Painting - MM Primer_POP.pdf
09 91 23-003-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-003-00 INTERIOR PAINTING - Samples (Premium & NHL) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-18 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-04 | 2020-12-04 | 17 |  | Record Copies; Transfers; Submittals | 09 91 23-003-00-01 - 09 91 23-003-00 INTERIOR PAINTING - Samples (Premium & NHL) | 17 |  | 2020-12-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09535 | Received | For Review | 2020-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-04 | Submittal Number: 09 91 23-3.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: INTERIOR PAINTING - SAMPLES (PREMIUM & NHL) Description: SAMPLES FOR VERIFICATION: FOR EACH TYPE OF PAINT SYSTEM AND IN EACH COLOR AND GLOSS OF TOPCOAT. 1. SUBMIT SAMPLES ON RIGID BACKING, 8 INCHES SQUARE. 2. APPLY COATS ON SAMPLES IN STEPS TO SHOW EACH COAT REQUIRED FOR THE SYSTEM. 3. LABEL EACH COAT OF EACH SAMPLE. 4. LABEL EACH SAMPLE FOR LOCATION AND APPLICATION AREA. Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 12555 | Forwarded | For Review | 2020-11-18 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-25 | Submittal Number: 09 91 23-3.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: INTERIOR PAINTING - SAMPLES (PREMIUM & NHL) Description: SAMPLES FOR VERIFICATION: FOR EACH TYPE OF PAINT SYSTEM AND IN EACH COLOR AND GLOSS OF TOPCOAT. 1. SUBMIT SAMPLES ON RIGID BACKING, 8 INCHES SQUARE. 2. APPLY COATS ON SAMPLES IN STEPS TO SHOW EACH COAT REQUIRED FOR THE SYSTEM. 3. LABEL EACH COAT OF EACH SAMPLE. 4. LABEL EACH SAMPLE FOR LOCATION AND APPLICATION AREA. Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 09922 | Review Response | Approved as Noted/Resubmit | 2020-12-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 13002 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-04 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 09 91 23-3 INTERIOR PAINTING - Samples (Premium & NHL).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 09 91 23-3 INTERIOR PAINTING - Samples (Premium & NHL).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-04 |  | 09 91 23-3 INTERIOR PAINTING - Samples (Premium & NHL)_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-18 |  | 09 91 23-3 INTERIOR PAINTING - Samples (Premium & NHL).pdf
09 91 23-003-00-01 | 09 91 23 - INTERIOR PAINTING | 09 91 23-003-00 INTERIOR PAINTING - Samples (Premium & NHL) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 91 23-003-00 - 09 91 23-003-00 INTERIOR PAINTING - Samples (Premium & NHL) | -1 | 2020-12-18
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 09 91 23-3 INTERIOR PAINTING - Samples (Premium & NHL).pdf
09 91 23-004-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-004-00 INTERIOR PAINTING - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-12 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-26 | 2020-10-19 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-10-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08713 | Received | For Review | 2020-10-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-26 | Submittal Number: 09 91 23-4.0 From: DANIELLE SCOTT Final Due Date: 10/23/20 Subject: INTERIOR PAINTING - PRODUCT DATA Description: PRODUCT DATA FOR PAINT PRODUCTS. Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 11503 | Forwarded | For Review | 2020-10-12 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-19 | Submittal Number: 09 91 23-4.0 From: DANIELLE SCOTT Final Due Date: 10/23/20 Subject: INTERIOR PAINTING - PRODUCT DATA Description: PRODUCT DATA FOR PAINT PRODUCTS. Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 11692 | Responded and Closed | Approved | 2020-10-19 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-09 |  | 09 91 23-4 INTERIOR PAINTING - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-09 |  | 09 91 23-4 INTERIOR PAINTING - Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-10-19 |  | 09 91 23-4 INTERIOR PAINTING - Product Data_POP.pdf
09 91 23-007-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-007-00 INTERIOR PAINTING - P1 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-14 | 2020-10-19 | 20 |  | Record Copies; Transfers; Submittals | 09 91 23-007-00-01 - 09 91 23-007-00 INTERIOR PAINTING - P1 Sample | 20 |  | 2020-10-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08437 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-14 | Submittal Number: 09 91 23-7.0 From: DANIELLE SCOTT Final Due Date: 10/14/20 Subject: INTERIOR PAINTING - P1 SAMPLE Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF PAINT SYSTEM AND IN EACH COLOR AND GLOSS OF TOPCOAT. 1. SUBMIT SAMPLES ON RIGID BACKING, 8 INCHES SQUARE. 2. APPLY COATS ON SAMPLES IN STEPS TO SHOW EACH COAT REQUIRED FOR SYSTEM. 3. LABEL EACH COAT OF EACH SAMPLE. 4. LABEL EACH SAMPLE FOR LOCATION AND APPLICATION AREA. Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 11178 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-07 | Submittal Number: 09 91 23-7.0 From: DANIELLE SCOTT Final Due Date: 10/14/20 Subject: INTERIOR PAINTING - P1 SAMPLE Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF PAINT SYSTEM AND IN EACH COLOR AND GLOSS OF TOPCOAT. 1. SUBMIT SAMPLES ON RIGID BACKING, 8 INCHES SQUARE. 2. APPLY COATS ON SAMPLES IN STEPS TO SHOW EACH COAT REQUIRED FOR SYSTEM. 3. LABEL EACH COAT OF EACH SAMPLE. 4. LABEL EACH SAMPLE FOR LOCATION AND APPLICATION AREA. Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 08849 | Review Response | Approved as Noted/Resubmit | 2020-10-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Submit eggshell sample. Approved flat for ceiling. | Info Exchange
| 11697 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-19 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Submit eggshell sample. Approved flat for ceiling. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-29 |  | 09 91 23-7 INTERIOR PAINTING - P1 Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-29 |  | 09 91 23-7 INTERIOR PAINTING - P1 Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-19 |  | 09 91 23-7 INTERIOR PAINTING - P1 Sample_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-29 |  | 09 91 23-7 INTERIOR PAINTING - P1 Sample.pdf
09 91 23-007-00-01 | 09 91 23 - INTERIOR PAINTING | 09 91 23-007-00 INTERIOR PAINTING - P1 Sample | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 91 23-007-00 - 09 91 23-007-00 INTERIOR PAINTING - P1 Sample | -1 | 2020-11-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-29 |  | 09 91 23-7 INTERIOR PAINTING - P1 Sample.pdf
09 91 23-008-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-008-00 INTERIOR PAINTING - P1 Eggshell Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-23 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-06 | 2020-10-29 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-10-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08956 | Received | For Review | 2020-10-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-11-06 | Submittal Number: 09 91 23-8.0 From: DANIELLE SCOTT Final Due Date: 11/05/20 Subject: INTERIOR PAINTING - P1 EGGSHELL SAMPLE Description: P1 EGGSHELL SAMPLE. Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 11826 | Forwarded | For Review | 2020-10-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-30 | Submittal Number: 09 91 23-8.0 From: DANIELLE SCOTT Final Due Date: 11/05/20 Subject: INTERIOR PAINTING - P1 EGGSHELL SAMPLE Description: P1 EGGSHELL SAMPLE. Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 09110 | Review Response | Approved as Noted | 2020-10-29 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 12022 | Responded and Closed | Approved as Noted | 2020-10-29 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-22 |  | 09 91 23-8 INTERIOR PAINTING - P1 Eggshell Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-22 |  | 09 91 23-8 INTERIOR PAINTING - P1 Eggshell Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-29 |  | 09 91 23-8 INTERIOR PAINTING - P1 Eggshell POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-29 |  | 09 91 23-8 INTERIOR PAINTING - P1 Eggshell POP.pdf
09 91 23-009-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-009-00 INTERIOR PAINTING - Samples (Base Building & Premium) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-19 08:00 | 2021-01-24 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-01-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10386 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-19 08:00 | Submittal Number: 09 91 23-9.0 From: DANIELLE SCOTT Final Due Date: 02/04/21 Subject: INTERIOR PAINTING - SAMPLES (BASE BUILDING & PREMIUM) Description: SAMPLES FOR VERIFICATION: FOR EACH TYPE OF PAINT SYSTEM AND IN EACH COLOR AND GLOSS OF TOPCOAT. 1. SUBMIT SAMPLES ON RIGID BACKING, 8 INCHES SQUARE. 2. APPLY COATS ON SAMPLES IN STEPS TO SHOW EACH COAT REQUIRED FOR SYSTEM. 3. LABEL EACH COAT OF EACH SAMPLE. 4. LABEL EACH SAMPLE FOR LOCATION AND APPLICATION AREA. Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 13570 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 09 91 23-9.0 From: DANIELLE SCOTT Final Due Date: 02/04/21 Subject: INTERIOR PAINTING - SAMPLES (BASE BUILDING & PREMIUM) Description: SAMPLES FOR VERIFICATION: FOR EACH TYPE OF PAINT SYSTEM AND IN EACH COLOR AND GLOSS OF TOPCOAT. 1. SUBMIT SAMPLES ON RIGID BACKING, 8 INCHES SQUARE. 2. APPLY COATS ON SAMPLES IN STEPS TO SHOW EACH COAT REQUIRED FOR SYSTEM. 3. LABEL EACH COAT OF EACH SAMPLE. 4. LABEL EACH SAMPLE FOR LOCATION AND APPLICATION AREA. Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 10919 | Review Response | Approved as Noted | 2021-01-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 14176 | Responded and Closed | Approved as Noted | 2021-01-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-23 |  | 09 91 23-9 INTERIOR PAINTING - Samples (Base Building & Premium).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-23 |  | 09 91 23-9 INTERIOR PAINTING - Samples (Base Building & Premium).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-24 |  | 09 91 23-9 INTERIOR PAINTING - Samples (Base Building & Premium) POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-23 |  | 09 91 23-9 INTERIOR PAINTING - Samples (Base Building & Premium).pdf
09 91 23-010-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-010-00 Paint Samples (Base and Premium Space) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-23 | 2021-04-26 | 18 |  | Record Copies; Transfers; Submittals | 09 91 23-010-00-01 - 09 91 23-010-00 Paint Samples (Base and Premium Space) | 18 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12507 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-04-23 | Submittal Number: 09 91 23-10.0 From: DANIELLE SCOTT Final Due Date: 04/23/21 Subject: PAINT SAMPLES (BASE AND PREMIUM SPACE) Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 16199 | Forwarded | For Review | 2021-04-09 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-16 | Submittal Number: 09 91 23-10.0 From: DANIELLE SCOTT Final Due Date: 04/23/21 Subject: PAINT SAMPLES (BASE AND PREMIUM SPACE) Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 12767 | Review Response | Approved as Noted/Resubmit | 2021-04-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 16505 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-26 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-09 |  | 09 91 23-10 Revision 0 Paint Samples (Base and Premium Space).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-09 |  | 09 91 23-10 Revision 0 Paint Samples (Base and Premium Space).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-26 |  | 09 91 23-10 Revision 0 Paint Samples POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-09 |  | 09 91 23-10 Revision 0 Paint Samples (Base and Premium Space).pdf
09 91 23-010-00-01 | 09 91 23 - INTERIOR PAINTING | 09 91 23-010-00 Paint Samples (Base and Premium Space) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 91 23-010-00 - 09 91 23-010-00 Paint Samples (Base and Premium Space) | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-09 |  | 09 91 23-10 Revision 0 Paint Samples (Base and Premium Space).pdf
09 91 23-011-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-011-00 INTERIOR PAINTING - Dry Erase Paint PD | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-30 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-14 | 2021-05-12 | 13 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12864 | Received | For Review | 2021-04-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-14 | Submittal Number: 09 91 23-11.0 From: KIM DOWALIBY Final Due Date: 05/13/21 Subject: INTERIOR PAINTING - DRY ERASE PAINT PD Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 16643 | Forwarded | For Review | 2021-04-29 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-06 | Submittal Number: 09 91 23-11.0 From: KIM DOWALIBY Final Due Date: 05/13/21 Subject: INTERIOR PAINTING - DRY ERASE PAINT PD Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 13067 | Review Response | Approved | 2021-05-12 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16905 | Responded and Closed | Approved | 2021-05-12 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-29 |  | 09 91 23-11 Dry Erase Paint PD.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-29 |  | 09 91 23-11 Dry Erase Paint PD.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-05-12 |  | 09 91 23-11 Dry Erase Paint PD_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-29 |  | 09 91 23-11 Dry Erase Paint PD.pdf
09 91 23-012-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-012-00 INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-20 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-04 07:00 | 2021-06-04 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13212 | Received | For Review | 2021-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-04 07:00 | Submittal Number: 09 91 23-12.0 From: KIM DOWALIBY Final Due Date: 06/03/21 Subject: INTERIOR PAINTING - CEILING DRY FALL PAINT SUBSTITUTION - PRODUCT DATA Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 17101 | Forwarded | For Review | 2021-05-20 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-27 | Submittal Number: 09 91 23-12.0 From: KIM DOWALIBY Final Due Date: 06/03/21 Subject: INTERIOR PAINTING - CEILING DRY FALL PAINT SUBSTITUTION - PRODUCT DATA Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 13408 | Review Response | Approved | 2021-06-04 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17341 | Responded and Closed | Approved | 2021-06-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-20 |  | 09 91 23-12 - INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-20 |  | 09 91 23-12 - INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Product Data.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-04 |  | 09 91 23-12 - INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Product Data_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-20 |  | 09 91 23-12 - INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Product Data.pdf
09 91 23-014-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-014-00 INTERIOR PAINTING - NHL Home Locker Room Paint Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-28 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-14 07:00 | 2021-06-03 | 7 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13317 | Received | For Review | 2021-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-06-14 07:00 | Submittal Number: 09 91 23-14.0 From: KIM DOWALIBY Final Due Date: 06/11/21 Subject: INTERIOR PAINTING - NHL HOME LOCKER ROOM PAINT SAMPLES Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 17232 | Forwarded | For Review | 2021-06-01 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 09 91 23-14.0 From: KIM DOWALIBY Final Due Date: 06/11/21 Subject: INTERIOR PAINTING - NHL HOME LOCKER ROOM PAINT SAMPLES Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 13375 | Review Response | Approved as Noted | 2021-06-03 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17303 | Responded and Closed | Approved as Noted | 2021-06-03 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-28 |  | 09 91 23-14 - INTERIOR PAINTING - NHL Home Locker Room Paint Samples.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-05-28 |  | 09 91 23-14 - INTERIOR PAINTING - NHL Home Locker Room Paint Samples.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-03 |  | 09 91 23-14 - INTERIOR PAINTING - NHL Home Locker Room Paint Samples_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-28 |  | 09 91 23-14 - INTERIOR PAINTING - NHL Home Locker Room Paint Samples.pdf
09 91 23-015-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-015-00 INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-01 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-15 | 2021-06-18 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13318 | Received | For Review | 2021-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-15 | Submittal Number: 09 91 23-15.0 From: KIM DOWALIBY Final Due Date: 06/11/21 Subject: INTERIOR PAINTING - CEILING DRY FALL PAINT SUBSTITUTION - PRODUCT DATA Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 17233 | Forwarded | For Review | 2021-06-01 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 09 91 23-15.0 From: KIM DOWALIBY Final Due Date: 06/11/21 Subject: INTERIOR PAINTING - CEILING DRY FALL PAINT SUBSTITUTION - PRODUCT DATA Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 17570 | Responded and Closed | Approved | 2021-06-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-28 |  | 09 91 23-15 - INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-28 |  | 09 91 23-15 - INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-18 |  | 09 91 23-15 - INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Product Data_POP.pdf
09 91 23-016-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-016-00 INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-04 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-18 | 2021-06-24 | 21 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13415 | Received | For Review | 2021-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-06-18 | Submittal Number: 09 91 23-16.0 From: KIM DOWALIBY Final Due Date: 06/18/21 Subject: INTERIOR PAINTING - CEILING DRY FALL PAINT SUBSTITUTION - SAMPLES Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 17348 | Forwarded | For Review | 2021-06-07 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-14 | Submittal Number: 09 91 23-16.0 From: KIM DOWALIBY Final Due Date: 06/18/21 Subject: INTERIOR PAINTING - CEILING DRY FALL PAINT SUBSTITUTION - SAMPLES Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 13634 | Review Response | Approved as Noted | 2021-06-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 17659 | Responded and Closed | Approved as Noted | 2021-06-24 | Kim Dowaliby | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-04 |  | 09 91 23-16 - INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Samples.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-06-04 |  | 09 91 23-16 - INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-24 02:00 |  | 09 91 23-16 - INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Samples_POP.pdf
| Responded and Closed |  | Kim Dowaliby | 1 | 2021-06-03 02:00 |  | 09 91 23-16 - INTERIOR PAINTING - Ceiling Dry Fall Paint Substitution - Samples.pdf
09 91 23-017-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-017-00 INTERIOR PAINTING - P46 - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-10 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-24 | 2021-06-22 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-06-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13488 | Received | For Review | 2021-06-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-06-24 | Submittal Number: 09 91 23-17.0 From: KIM DOWALIBY Final Due Date: 06/24/21 Subject: INTERIOR PAINTING - P46 - SAMPLE Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 17442 | Forwarded | For Review | 2021-06-10 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-17 | Submittal Number: 09 91 23-17.0 From: KIM DOWALIBY Final Due Date: 06/24/21 Subject: INTERIOR PAINTING - P46 - SAMPLE Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 17610 | Responded and Closed | Approved | 2021-06-22 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-10 |  | 09 91 23-17 - INTERIOR PAINTING - P46 - Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-10 |  | 09 91 23-17 - INTERIOR PAINTING - P46 - Sample.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-06-22 |  | 09 91 23-17 - INTERIOR PAINTING - P46 - Sample_POP.pdf
09 91 23-018-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-018-00 INTERIOR PAINTING - Sherwin Williams Ceiling Dry Fall Paint Substitution - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-02 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-16 | 2021-07-06 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13781 | Received | For Review | 2021-07-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-16 | Submittal Number: 09 91 23-18.0 From: KIM DOWALIBY Final Due Date: 07/16/21 Subject: INTERIOR PAINTING - SHERWIN WILLIAMS CEILING DRY FALL PAINT SUBSTITUTION - PRODUCT DATA Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 17836 | Forwarded | For Review | 2021-07-06 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-13 | Submittal Number: 09 91 23-18.0 From: KIM DOWALIBY Final Due Date: 07/16/21 Subject: INTERIOR PAINTING - SHERWIN WILLIAMS CEILING DRY FALL PAINT SUBSTITUTION - PRODUCT DATA Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 17857 | Responded and Closed | Approved | 2021-07-06 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-02 |  | 09 91 23-18 - INTERIOR PAINTING - Sherwin Williams Ceiling Dry Fall Paint Substitution - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-02 |  | 09 91 23-18 - INTERIOR PAINTING - Sherwin Williams Ceiling Dry Fall Paint Substitution - Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-06 |  | 09 91 23-18 - INTERIOR PAINTING - Sherwin Williams Ceiling Dry Fall Paint Substitution - Product Data_POP.pdf
09 91 23-019-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-019-00 INTERIOR PAINTING - Amazon JWO Pantone Paint Color Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-23 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-06 | 2021-09-07 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-09-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14431 | Received | For Review | 2021-08-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-09-06 | Submittal Number: 09 91 23-19.0 From: KIM DOWALIBY Final Due Date: 09/03/21 Subject: INTERIOR PAINTING - AMAZON JWO PANTONE PAINT COLOR SAMPLES Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 18626 | Forwarded | For Review | 2021-08-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-30 | Submittal Number: 09 91 23-19.0 From: KIM DOWALIBY Final Due Date: 09/03/21 Subject: INTERIOR PAINTING - AMAZON JWO PANTONE PAINT COLOR SAMPLES Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 14581 | Review Response | Approved | 2021-09-07 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18799 | Responded and Closed | Approved | 2021-09-07 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-20 |  | 09 91 23-19 - INTERIOR PAINTING - Amazon JWO Pantone Paint Color Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-20 |  | 09 91 23-19 - INTERIOR PAINTING - Amazon JWO Pantone Paint Color Samples.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-09-07 |  | 09 91 23-19 - INTERIOR PAINTING - Amazon JWO Pantone Paint Color Samples.pdf_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-08-20 |  | 09 91 23-19 - INTERIOR PAINTING - Amazon JWO Pantone Paint Color Samples.pdf
09 91 23-020-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-020-00 White Dryfall Paint for Upper Concourse - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-24 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-07 | 2021-09-08 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14441 | Received | For Review | 2021-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-07 | Submittal Number: 09 91 23-20.0 From: LUCAS TRADAL Final Due Date: 09/06/21 Subject: WHITE DRYFALL PAINT FOR UPPER CONCOURSE - SAMPLE Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 18640 | Forwarded | For Review | 2021-08-24 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-31 | Submittal Number: 09 91 23-20.0 From: LUCAS TRADAL Final Due Date: 09/06/21 Subject: WHITE DRYFALL PAINT FOR UPPER CONCOURSE - SAMPLE Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 14595 | Review Response | Approved | 2021-09-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18813 | Responded and Closed | Approved | 2021-09-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-23 |  | 09 91 23-20 - INTERIOR PAINTING - White Dryfall Paint for Upper Concourse Sample.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-23 |  | 09 91 23-20 - INTERIOR PAINTING - White Dryfall Paint for Upper Concourse Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-09-08 02:00 |  | 09 91 23-20 - INTERIOR PAINTING - White Dryfall Paint POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-22 02:00 |  | 09 91 23-20 - INTERIOR PAINTING - White Dryfall Paint for Upper Concourse Sample.pdf
09 91 23-021-00 | 09 91 23 - INTERIOR PAINTING | 09 91 23-021-00 INTERIOR PAINTING - Metro Club Seating Area Wall Paint - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-14 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-28 | 2021-09-14 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14643 | Received | For Review | 2021-09-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-09-28 | Submittal Number: 09 91 23-21.0 From: KIM DOWALIBY Final Due Date: 09/27/21 Subject: INTERIOR PAINTING - METRO CLUB SEATING AREA WALL PAINT - SAMPLE Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 18883 | Forwarded | For Review | 2021-09-14 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-21 | Submittal Number: 09 91 23-21.0 From: KIM DOWALIBY Final Due Date: 09/27/21 Subject: INTERIOR PAINTING - METRO CLUB SEATING AREA WALL PAINT - SAMPLE Description: Spec Section: 09 91 23 - INTERIOR PAINTING Status: OPEN | Info Exchange
| 14645 | Review Response | Approved as Noted | 2021-09-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18885 | Responded and Closed | Approved as Noted | 2021-09-14 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-13 |  | 09 91 23-21 - INTERIOR PAINTING - Metro Club Seating Area Wall Paint - Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-13 |  | 09 91 23-21 - INTERIOR PAINTING - Metro Club Seating Area Wall Paint - Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-09-14 |  | 09 91 23-21 - INTERIOR PAINTING - Metro Seating_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-09-13 |  | 09 91 23-21 - INTERIOR PAINTING - Metro Club Seating Area Wall Paint - Sample.pdf
09 96 00-001-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-001-00 Roof Strengthening Steel High-Performance Coating Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-24 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2019-11-07 | 2019-11-11 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2019-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02912 | Received | For Review | 2019-10-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-11-07 | Submittal Number: 09 96 00-1.0 From: NATE WEINGART Final Due Date: 11/07/19 Subject: ROOF STRENGTHENING STEEL HIGH-PERFORMANCE COATING PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 04282 | Forwarded | For Review | 2019-10-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2019-10-31 | Submittal Number: 09 96 00-1.0 From: NATE WEINGART Final Due Date: 11/07/19 Subject: ROOF STRENGTHENING STEEL HIGH-PERFORMANCE COATING PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 04540 | Forwarded | For Review | 2019-11-08 | Todd Spangler (Populous) | Tom Usher (Populous) | 2019-11-07 | Submittal Number: 09 96 00-1.0 From: NATE WEINGART Final Due Date: 11/07/19 Subject: ROOF STRENGTHENING STEEL HIGH-PERFORMANCE COATING PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 04580 | Responded and Closed | Approved as Noted | 2019-11-11 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 04878 | Sent | For Information Only | 2019-11-27 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-24 |  | 099600-1.0 Roof Strength Steel HP Coating (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-24 |  | 099600-1.0 Roof Strength Steel HP Coating (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-10-24 |  | 099600-1.0 Roof Strength Steel HP Coating (MAM Review).pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2019-11-11 |  | 099600-1.0 Roof Strength Steel HP Coating (MAM Review) POP2.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2019-10-23 02:00 |  | 099600-1.0 Roof Strength Steel HP Coating (MAM Review).pdf
09 96 00-002-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-002-00: Steel Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-05 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2019-12-19 | 2019-12-16 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03519 | Received | For Review | 2019-12-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2019-12-19 | Submittal Number: 09 96 00-2.0 From: TYRONE THORNTON Final Due Date: 12/19/19 Subject: STEEL PRODUCT DATA Description: PRODUCT DATA: FOR PAINTS AND COATINGS, INDICATING VOC CONTENT. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 04985 | Forwarded | For Review | 2019-12-05 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2019-12-12 | Submittal Number: 09 96 00-2.0 From: TYRONE THORNTON Final Due Date: 12/19/19 Subject: STEEL PRODUCT DATA Description: PRODUCT DATA: FOR PAINTS AND COATINGS, INDICATING VOC CONTENT. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 05170 | Responded and Closed | Approved as Noted | 2019-12-16 | Tom Usher (Populous) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-05 02:00 |  | 09 96 00-2.0 Steel Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-05 02:00 |  | 09 96 00-2.0 Steel Product Data-MAM.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2019-12-16 02:00 |  | 09 96 00-2.0 Steel Product Data-MAM POP.pdf
09 96 00-003-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-003-00 High-Performance Coatings - Miscellaneous Metals Primer Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-02 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-16 | 2020-07-13 | 12 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06769 | Received | For Review | 2020-07-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-07-16 | Submittal Number: 09 96 00-3.0 From: NATE WEINGART Final Due Date: 07/16/20 Subject: HIGH-PERFORMANCE COATINGS - MISCELLANEOUS METALS PRIMER PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 09097 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-07-13 | Submittal Number: 09 96 00-3.0 From: NATE WEINGART Final Due Date: 07/16/20 Subject: HIGH-PERFORMANCE COATINGS - MISCELLANEOUS METALS PRIMER PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 09280 | Responded and Closed | Revise and Resubmit | 2020-07-13 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. Submit full paint system as indicated in Specification 099600-3.6-Q 2. Product does not match what is specified in Specification 099600-3.6-Q-1. Please explain substitution. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-02 |  | 09 96 00-3.0 Miscellaneous Metals Primer Product Data (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-02 |  | 09 96 00-3.0 Miscellaneous Metals Primer Product Data (MAM Review).pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-07-13 |  | 09 96 00-3.0 Miscellaneous Metals Primer Product Data (MAM Review)_POP.pdf
09 96 00-003-01 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-003-01 High-Performance Coatings - Miscellaneous Metals Primer Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-13 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-27 | 2020-08-20 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07535 | Received | For Review | 2020-08-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-08-27 | Submittal Number: 09 96 00-3.1 From: NATE WEINGART Final Due Date: 08/21/20 Subject: HIGH-PERFORMANCE COATINGS - MISCELLANEOUS METALS PRIMER PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 10035 | Forwarded | For Review | 2020-08-13 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-20 | Submittal Number: 09 96 00-3.1 From: NATE WEINGART Final Due Date: 08/21/20 Subject: HIGH-PERFORMANCE COATINGS - MISCELLANEOUS METALS PRIMER PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 10167 | Responded and Closed | Approved | 2020-08-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-13 |  | 09 96 00-3 R1 High-Perform Coatings-Primer.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-13 |  | 09 96 00-3 R1 High-Perform Coatings-Primer.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-08-20 |  | 09 96 00-3 R1 High-Perform Coatings-Primer_POP.pdf
09 96 00-004-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-004-00 HIGH-PERFORMANCE COATINGS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-23 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-07 | 2021-05-04 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12743 | Received | For Review | 2021-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-05-07 | Submittal Number: 09 96 00-4.0 From: DANIELLE SCOTT Final Due Date: 04/07/21 Subject: HIGH-PERFORMANCE COATINGS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF COATING SYSTEM AND EACH COLOR AND GLOSS OF TOPCOAT INDICATED. 1. SUBMIT SAMPLES ON RIGID BACKING, 8 INCHES (200 MM) SQUARE. 2. APPLY COATS ON SAMPLES IN STEPS TO SHOW EACH COAT REQUIRED FOR SYSTEM. 3. LABEL EACH COAT OF EACH SAMPLE. 4. LABEL EACH SAMPLE FOR LOCATION AND APPLICATION AREA. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 16473 | Forwarded | For Review | 2021-04-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-30 | Submittal Number: 09 96 00-4.0 From: DANIELLE SCOTT Final Due Date: 04/07/21 Subject: HIGH-PERFORMANCE COATINGS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF COATING SYSTEM AND EACH COLOR AND GLOSS OF TOPCOAT INDICATED. 1. SUBMIT SAMPLES ON RIGID BACKING, 8 INCHES (200 MM) SQUARE. 2. APPLY COATS ON SAMPLES IN STEPS TO SHOW EACH COAT REQUIRED FOR SYSTEM. 3. LABEL EACH COAT OF EACH SAMPLE. 4. LABEL EACH SAMPLE FOR LOCATION AND APPLICATION AREA. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 16735 | Responded and Closed | Approved | 2021-05-04 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-23 |  | 09 96 00-4 Revision 0 HIGH-PERFORMANCE COATINGS - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-23 |  | 09 96 00-4 Revision 0 HIGH-PERFORMANCE COATINGS - Samples.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-05-04 02:00 |  | 09 96 00-4 Revision 0 HIGH-PERFORMANCE COATINGS - Samples_pop.pdf
09 96 00-005-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-005-00 HIGH-PERFORMANCE COATINGS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-05 | 2021-02-11 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10890 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-05 | Submittal Number: 09 96 00-5.0 From: DANIELLE SCOTT Final Due Date: 02/04/21 Subject: HIGH-PERFORMANCE COATINGS - PRODUCT DATA Description: PRODUCT LIST : CROSS-REFERENCE TO COATING SYSTEM AND LOCATIONS OF APPLICATION AREAS. USE SAME DESIGNATIONS INDICATED ON DRAWINGS AND IN SCHEDULES. INCLUDE COLOR DESIGNATIONS. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 14144 | Forwarded | For Review | 2021-01-22 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-29 | Submittal Number: 09 96 00-5.0 From: DANIELLE SCOTT Final Due Date: 02/04/21 Subject: HIGH-PERFORMANCE COATINGS - PRODUCT DATA Description: PRODUCT LIST : CROSS-REFERENCE TO COATING SYSTEM AND LOCATIONS OF APPLICATION AREAS. USE SAME DESIGNATIONS INDICATED ON DRAWINGS AND IN SCHEDULES. INCLUDE COLOR DESIGNATIONS. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 14702 | Responded and Closed | Approved as Noted | 2021-02-11 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-21 |  | 09 96 00-5 Revision 0 HIGH-PERFORMANCE COATINGS - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-21 |  | 09 96 00-5 Revision 0 HIGH-PERFORMANCE COATINGS - Product Data.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-01-21 |  | 09 96 00-5 Revision 0 HIGH-PERFORMANCE COATINGS - Product Data.pdf
09 96 00-008-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-008-00 Roof Steel Paint: Tnemec Series 115 - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-01-10 | 2020-01-07 | 21 | General | Record Copies; Transfers; Submittals |  | 21 |  | 2020-01-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03676 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-01-10 | Submittal Number: 09 96 00-8.0 From: RYAN CROOKSTON Final Due Date: 12/27/19 Subject: ROOF STEEL PAINT: TNEMEC SERIES 115 - PRODUCT DATA Description: 12/12/19 RC: AS DISCUSSED WITH CHRIS MINTER, PLEASE SEE THE ATTACHED PRODUCT DATA FOR THE PAINT THAT WILL BE APPLIED TO THE NEW ROOF STRENGTHENING STEEL. SAMPLES TO BE SUBMITTED UNDER SEPARATE COVER. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 05196 | Forwarded | For Review | 2019-12-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-12-25 | Submittal Number: 09 96 00-8.0 From: RYAN CROOKSTON Final Due Date: 12/27/19 Subject: ROOF STEEL PAINT: TNEMEC SERIES 115 - PRODUCT DATA Description: 12/12/19 RC: AS DISCUSSED WITH CHRIS MINTER, PLEASE SEE THE ATTACHED PRODUCT DATA FOR THE PAINT THAT WILL BE APPLIED TO THE NEW ROOF STRENGTHENING STEEL. SAMPLES TO BE SUBMITTED UNDER SEPARATE COVER. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 05363 | Responded and Closed | Approved | 2020-01-07 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | APPROVED. CLM | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | Tnemec Series 115 Unibond - Product Data (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-18 |  | Tnemec Series 115 Unibond - Product Data (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-01-07 02:00 |  | Tnemec Series 115 Unibond - Product Data (MAM Review)-POP.pdf
09 96 00-009-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-009-00 Trichord Steel Touch-Up Paint: Tnemec Series 115 - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-30 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-13 | 2020-02-06 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-02-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04118 | Received | For Review | 2020-01-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-02-13 | Submittal Number: 09 96 00-9.0 From: RYAN CROOKSTON Final Due Date: 02/13/20 Subject: TRICHORD STEEL TOUCH-UP PAINT: TNEMEC SERIES 115 - SAMPLE Description: THIS IS THE GREEN COLORED PAINT THAT WILL BE APPLIED TO THE NECESSARY TOUCH-UP AREAS ON THE TRICHORDS. TOUCH-UP AREAS ARE GENERALLY AREAS THAT HAVE HAD EXISTING PAINT ABATEMENT FOR THE PURPOSE OF ROOF STRENGTHENING STEEL WORK TO BE DONE. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 05724 | Forwarded | For Review | 2020-01-29 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-02-05 | Submittal Number: 09 96 00-9.0 From: RYAN CROOKSTON Final Due Date: 02/13/20 Subject: TRICHORD STEEL TOUCH-UP PAINT: TNEMEC SERIES 115 - SAMPLE Description: THIS IS THE GREEN COLORED PAINT THAT WILL BE APPLIED TO THE NECESSARY TOUCH-UP AREAS ON THE TRICHORDS. TOUCH-UP AREAS ARE GENERALLY AREAS THAT HAVE HAD EXISTING PAINT ABATEMENT FOR THE PURPOSE OF ROOF STRENGTHENING STEEL WORK TO BE DONE. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 04257 | Review Response | Approved as Noted/Resubmit | 2020-02-06 | Josh Dobken (Populous) | Shaina Burris (Populous) |  | Paint is approved for application in a mockup. Per spec, final approval of color selections will be based on mockup, please resubmit once paint has been applied to an area of the Trichord prepared to receive paint that is similar in size to typical application. | Info Exchange
| 05892 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction); Alex Brown (MA Mortenson) |  | Response (Approved as Noted/Resubmit) from: Josh Dobken (Populous) Remarks: Paint is approved for application in a mockup. Per spec, final approval of color selections will be based on mockup, please resubmit once paint has been applied to an area of the Trichord prepared to receive paint that is similar in size to typical application. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-29 |  | Trichord Steel Touch-Up Paint-Tnemec Series 115 - Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-29 |  | Trichord Steel Touch-Up Paint-Tnemec Series 115 - Sample.pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2020-02-06 02:00 |  | Trichord Steel Touch-Up Paint-Tnemec Series 115 - Sample_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-28 02:00 |  | Trichord Steel Touch-Up Paint-Tnemec Series 115 - Sample.pdf
09 96 00-009-01 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-009-01 Trichord Steel Touch-Up Paint: Tnemec Series 1029 - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-20 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-04 | 2020-05-20 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-05-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05936 | Received | For Review | 2020-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ryan Crookston (Mortenson Construction) | 2020-06-04 | Submittal Number: 09 96 00-9.1 From: RYAN CROOKSTON Final Due Date: 06/03/20 Subject: TRICHORD STEEL TOUCH-UP PAINT: TNEMEC SERIES 1029 - SAMPLE Description: THIS IS THE GREEN COLORED PAINT THAT WILL BE APPLIED TO THE NECESSARY TOUCH-UP AREAS ON THE TRICHORDS. TOUCH-UP AREAS ARE GENERALLY AREAS THAT HAVE HAD EXISTING PAINT ABATEMENT FOR THE PURPOSE OF ROOF STRENGTHENING STEEL WORK TO BE DONE. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 08064 | Forwarded | For Review | 2020-05-19 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-05-26 | Submittal Number: 09 96 00-9.1 From: RYAN CROOKSTON Final Due Date: 06/03/20 Subject: TRICHORD STEEL TOUCH-UP PAINT: TNEMEC SERIES 1029 - SAMPLE Description: THIS IS THE GREEN COLORED PAINT THAT WILL BE APPLIED TO THE NECESSARY TOUCH-UP AREAS ON THE TRICHORDS. TOUCH-UP AREAS ARE GENERALLY AREAS THAT HAVE HAD EXISTING PAINT ABATEMENT FOR THE PURPOSE OF ROOF STRENGTHENING STEEL WORK TO BE DONE. Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 08094 | Responded and Closed | Approved | 2020-05-20 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (Mortenson Construction) |  | See attached. Provide updated draw down sample to Populous and Icon | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 |  | Tnemec Series 1029 - Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-19 |  | Tnemec Series 1029 - Sample.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-20 02:00 |  | 09 96 00-009-01 Tnemec Series 1029 - Sample_pop.pdf
09 96 00-010-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-010-00 High Performance Coating - Historic Curtainwall Painting System | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-04 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-05-18 | 2020-05-12 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05684 | Received | For Review | 2020-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-05-18 | Submittal Number: 09 96 00-10.0 From: BROOKE BURCHAM Final Due Date: 05/18/20 Subject: HIGH PERFORMANCE COATING - HISTORIC CURTAINWALL PAINTING SYSTEM Description: HISTORIC CURTAINWALL PAINTING SYSTEM Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 07695 | Forwarded | For Review | 2020-05-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-05-11 | Submittal Number: 09 96 00-10.0 From: BROOKE BURCHAM Final Due Date: 05/18/20 Subject: HIGH PERFORMANCE COATING - HISTORIC CURTAINWALL PAINTING SYSTEM Description: HISTORIC CURTAINWALL PAINTING SYSTEM Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 07892 | Responded and Closed | Approved | 2020-05-12 | Shaina Burris (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-01 |  | 099600-0010-0 Historic Curtainwall Paint System.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-01 |  | 099600-0010-0 Historic Curtainwall Paint System.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-05-01 |  | 099600-0010-0 Historic Curtainwall Paint System.pdf
09 96 00-011-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-011-00 High Performance Coatings - Wrought Iron and White Diamond PPG Paint Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-01 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-15 | 2020-06-15 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06132 | Received | For Review | 2020-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-06-15 | Submittal Number: 09 96 00-11.0 From: BROOKE BURCHAM Final Due Date: 06/15/20 Subject: HIGH PERFORMANCE COATINGS - WROUGHT IRON AND WHITE DIAMOND PPG PAINT SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 08290 | Forwarded | For Review | 2020-06-01 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-08 | Submittal Number: 09 96 00-11.0 From: BROOKE BURCHAM Final Due Date: 06/15/20 Subject: HIGH PERFORMANCE COATINGS - WROUGHT IRON AND WHITE DIAMOND PPG PAINT SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 08624 | Responded and Closed | Approved | 2020-06-15 | Todd Spangler (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-01 |  | 099600-0011-0 Wrought Iron and White Diamond - PPG Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-01 |  | 099600-0011-0 Wrought Iron and White Diamond - PPG Samples.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-15 |  | 099600-0011-0 Wrought Iron and White Diamond - PPG Samples_POP.pdf
09 96 00-012-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-012-00 Steel Paint Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-24 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Todd Spangler (Populous) |  |  |  | 2020-07-09 07:00 | 2020-08-06 | 44 |  | Record Copies; Transfers; Submittals |  | 44 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06582 | Received | For Review | 2020-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (M.A. Mortenson Company) | 2020-07-09 07:00 | Submittal Number: 09 96 00-12.0 From: JES PELKEY Final Due Date: 07/09/20 Subject: STEEL PAINT SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 08864 | Forwarded | For Review | 2020-06-24 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-07-01 | Submittal Number: 09 96 00-12.0 From: JES PELKEY Final Due Date: 07/09/20 Subject: STEEL PAINT SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 09471 | Forwarded | For Review | 2020-07-21 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2020-07-09 | Submittal Number: 09 96 00-12.0 From: JES PELKEY Final Due Date: 07/09/20 Subject: STEEL PAINT SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 09866 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-06 | Todd Spangler (Populous) | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Wrought Iron - Resubmit - It seems darker then the control sample but this may be because it is glossy instead of satin. The control sample is a satin finish. White Diamond - Resubmit - The provided sample is glossy instead of satin. The control sample is a satin finish. Pearl gray - Approved The control sample is from the exterior cladding paint contractor - Purcell Painting | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-24 |  | 09 96 00-12.0 Steel Paint Samples - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-24 |  | 09 96 00-12.0 Steel Paint Samples - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-23 02:00 |  | 09 96 00-12.0 Steel Paint Samples - MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-06-24 |  | 09 96 00-12.0 Steel Paint Samples - MAM.pdf
09 96 00-012-01 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-012-01 Steel Paint Samples - Wrought Iron, White Diamond, & Peppercorn | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-19 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-02 | 2020-09-10 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-09-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07617 | Received | For Review | 2020-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-02 | Submittal Number: 09 96 00-12.1 From: JES PELKEY Final Due Date: 09/02/20 Subject: STEEL PAINT SAMPLES - WROUGHT IRON, WHITE DIAMOND, & PEPPERCORN Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 10146 | Forwarded | For Review | 2020-08-19 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-26 | Submittal Number: 09 96 00-12.1 From: JES PELKEY Final Due Date: 09/02/20 Subject: STEEL PAINT SAMPLES - WROUGHT IRON, WHITE DIAMOND, & PEPPERCORN Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 10689 | Responded and Closed | Approved as Noted | 2020-09-10 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | All colors approved. See attached comments for locations where the colors are approved. The design team needs to confirm the color for the metal pan stairs still. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-19 |  | 09 96 00-12.1 Steel Paint Samples-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-19 |  | 09 96 00-12.1 Steel Paint Samples-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-10 |  | 09 96 00-12.1 Steel Paint Samples-MAM_POP.pdf
09 96 00-013-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-013-00 Interior and Exterior Exposed Galvanized Metal Paint PD | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-30 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-14 | 2021-05-03 | 4 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-05-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12865 | Received | For Review | 2021-04-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-14 | Submittal Number: 09 96 00-13.0 From: KIM DOWALIBY Final Due Date: 05/13/21 Subject: INTERIOR AND EXTERIOR EXPOSED GALVANIZED METAL PAINT PD Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 16644 | Forwarded | For Review | 2021-04-29 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-06 | Submittal Number: 09 96 00-13.0 From: KIM DOWALIBY Final Due Date: 05/13/21 Subject: INTERIOR AND EXTERIOR EXPOSED GALVANIZED METAL PAINT PD Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 16692 | Responded and Closed | Approved | 2021-05-03 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-29 |  | 09 96 00-13.0 Int and Ext Exposed Galvanized Metal Paint PD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-29 |  | 09 96 00-13.0 Int and Ext Exposed Galvanized Metal Paint PD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-03 02:00 |  | 09 96 00-13.0 Int and Ext Exposed Galvanized Metal Paint PD-MAM_POP.pdf
09 96 00-014-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-014-00 High-Performance Coatings - Tnemec Coatings Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-30 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-14 | 2021-05-18 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12870 | Received | For Review | 2021-04-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-14 | Submittal Number: 09 96 00-14.0 From: KIM DOWALIBY Final Due Date: 05/14/21 Subject: 09 96 00 - HIGH-PERFORMANCE COATINGS - TNEMEC COATINGS PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 16651 | Forwarded | For Review | 2021-04-30 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-07 | Submittal Number: 09 96 00-14.0 From: KIM DOWALIBY Final Due Date: 05/14/21 Subject: 09 96 00 - HIGH-PERFORMANCE COATINGS - TNEMEC COATINGS PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 17034 | Responded and Closed | Approved | 2021-05-18 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-30 |  | 09 96 00-14 HIGH-PERFORMANCE COATINGS - Tnemec Coatings Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-30 |  | 09 96 00-14 HIGH-PERFORMANCE COATINGS - Tnemec Coatings Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-18 |  | 09 96 00-14 HIGH-PERFORMANCE COATINGS - Tnemec Coatings Product Data-POP.pdf
09 96 00-015-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-015-00 HIGH-PERFORMANCE COATINGS - EP9 and EP10 Color Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-25 | 2021-05-18 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13036 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-05-25 | Submittal Number: 09 96 00-15.0 From: KIM DOWALIBY Final Due Date: 05/24/21 Subject: HIGH-PERFORMANCE COATINGS - EP9 AND EP10 COLOR SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 16869 | Forwarded | For Review | 2021-05-11 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-18 | Submittal Number: 09 96 00-15.0 From: KIM DOWALIBY Final Due Date: 05/24/21 Subject: HIGH-PERFORMANCE COATINGS - EP9 AND EP10 COLOR SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 17038 | Responded and Closed | Approved | 2021-05-18 | Kim Dowaliby | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 09 96 00-15 HIGH-PERFORMANCE COATINGS - EP9 and EP10 Color Samples.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-05-10 |  | 09 96 00-15 HIGH-PERFORMANCE COATINGS - EP9 and EP10 Color Samples.pdf
| Responded and Closed |  | Kim Dowaliby | 1 | 2021-05-18 |  | 09 96 00-15 HIGH-PERFORMANCE COATINGS - EP9 and EP10 Color Samples-POP.pdf
09 96 00-016-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-016-00 HIGH PERFORMANCE - Stair Nose Striping - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-01 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-15 | 2021-06-03 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13319 | Received | For Review | 2021-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-15 | Submittal Number: 09 96 00-16.0 From: KIM DOWALIBY Final Due Date: 06/11/21 Subject: HIGH PERFORMANCE - STAIR NOSE STRIPING - PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 17234 | Forwarded | For Review | 2021-06-01 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 09 96 00-16.0 From: KIM DOWALIBY Final Due Date: 06/11/21 Subject: HIGH PERFORMANCE - STAIR NOSE STRIPING - PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 17309 | Responded and Closed | Approved | 2021-06-03 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-28 |  | 09 96 00-16 HIGH PERFORMANCE - Stair Nose Striping - Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-28 |  | 09 96 00-16 HIGH PERFORMANCE - Stair Nose Striping - Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-03 |  | 09 96 00-16 HIGH PERFORMANCE - Stair Nose Striping - Product Data-POP.pdf
09 96 00-016-01 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-016-01 HIGH PERFORMANCE - Stair Nose Striping - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-15 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-28 | 2021-09-15 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-09-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14652 | Received | For Review | 2021-09-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-09-28 | Submittal Number: 09 96 00-16.1 From: KIM DOWALIBY Final Due Date: 09/28/21 Subject: HIGH PERFORMANCE - STAIR NOSE STRIPING - PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 18891 | Forwarded | For Review | 2021-09-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-22 | Submittal Number: 09 96 00-16.1 From: KIM DOWALIBY Final Due Date: 09/28/21 Subject: HIGH PERFORMANCE - STAIR NOSE STRIPING - PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 18894 | Responded and Closed | Approved | 2021-09-15 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-14 |  | 09 96 00-16.1 HIGH PERFORMANCE - Stair Nose Striping - Product Data Rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-14 |  | 09 96 00-16.1 HIGH PERFORMANCE - Stair Nose Striping - Product Data Rev 1.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-09-15 |  | 09 96 00-16.1 HIGH PERFORMANCE - Stair Nose Striping - Product Data Rev 1_POP.pdf
09 96 00-017-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-017-00 HIGH PERFORMANCE - Stair Nose Striping - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-04 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-18 | 2021-06-14 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-06-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13416 | Received | For Review | 2021-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Kim Dowaliby | 2021-06-18 | Submittal Number: 09 96 00-17.0 From: KIM DOWALIBY Final Due Date: 06/18/21 Subject: HIGH PERFORMANCE - STAIR NOSE STRIPING - SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 17349 | Forwarded | For Review | 2021-06-07 | Kim Dowaliby | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-14 | Submittal Number: 09 96 00-17.0 From: KIM DOWALIBY Final Due Date: 06/18/21 Subject: HIGH PERFORMANCE - STAIR NOSE STRIPING - SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 17479 | Responded and Closed | Approved | 2021-06-14 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-04 |  | 09 96 00-17 HIGH PERFORMANCE - Stair Nose Striping - Samples.pdf
| Forwarded |  | Kim Dowaliby | 1 | 2021-06-04 |  | 09 96 00-17 HIGH PERFORMANCE - Stair Nose Striping - Samples.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-14 02:00 |  | 09 96 00-17 HIGH PERFORMANCE - Stair Nose Striping - Samples_POP.pdf
09 96 00-017-01 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-017-01 HIGH PERFORMANCE - Stair Nose Striping - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-16 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-30 | 2021-06-23 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-06-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13547 | Received | For Review | 2021-06-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-06-30 | Submittal Number: 09 96 00-17.1 From: KIM DOWALIBY Final Due Date: 06/29/21 Subject: HIGH PERFORMANCE - STAIR NOSE STRIPING - SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 17534 | Forwarded | For Review | 2021-06-16 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-23 | Submittal Number: 09 96 00-17.1 From: KIM DOWALIBY Final Due Date: 06/29/21 Subject: HIGH PERFORMANCE - STAIR NOSE STRIPING - SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 17640 | Responded and Closed | Approved | 2021-06-23 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-15 |  | 09 96 00-17.1 - HIGH PERFORMANCE - Stair Nose Striping - Samples Rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-15 |  | 09 96 00-17.1 - HIGH PERFORMANCE - Stair Nose Striping - Samples Rev 1.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-06-23 |  | 09 96 00-17.1 - HIGH PERFORMANCE - Stair Nose Striping - Samples Rev 1-POP.pdf
09 96 00-018-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-018-00 Kraken Rum Bar Floor - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-24 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-07 | 2021-08-30 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-08-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14442 | Received | For Review | 2021-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-07 | Submittal Number: 09 96 00-18.0 From: LUCAS TRADAL Final Due Date: 09/06/21 Subject: KRAKEN RUM BAR FLOOR - SAMPLE Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 18641 | Forwarded | For Review | 2021-08-24 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-31 | Submittal Number: 09 96 00-18.0 From: LUCAS TRADAL Final Due Date: 09/06/21 Subject: KRAKEN RUM BAR FLOOR - SAMPLE Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 18723 | Responded and Closed | Approved | 2021-08-30 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-23 |  | 09 96 00-18 - HIGH PERFORMANCE - Kraken Rum Bar Floor Sample.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-23 |  | 09 96 00-18 - HIGH PERFORMANCE - Kraken Rum Bar Floor Sample.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-08-30 |  | 09 96 00-18 - HIGH PERFORMANCE - Kraken Rum Bar Floor Sample_POP.pdf
09 96 00-019-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-019-00 HIGH-PERFORMANCE COATINGS - Mt. Baker Floor Graphics Coating - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-14 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-28 | 2021-09-20 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-09-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14644 | Received | For Review | 2021-09-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-09-28 | Submittal Number: 09 96 00-19.0 From: KIM DOWALIBY Final Due Date: 09/27/21 Subject: HIGH-PERFORMANCE COATINGS - MT. BAKER FLOOR GRAPHICS COATING - PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 18884 | Forwarded | For Review | 2021-09-14 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-21 | Submittal Number: 09 96 00-19.0 From: KIM DOWALIBY Final Due Date: 09/27/21 Subject: HIGH-PERFORMANCE COATINGS - MT. BAKER FLOOR GRAPHICS COATING - PRODUCT DATA Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 18915 | Responded and Closed | Approved | 2021-09-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-13 |  | 09 96 00-19 - HIGH-PERFORMANCE COATINGS - Mt. Baker Floor Graphics Coating - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-13 |  | 09 96 00-19 - HIGH-PERFORMANCE COATINGS - Mt. Baker Floor Graphics Coating - Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-09-20 |  | 09 96 00-19 - HIGH-PERFORMANCE COATINGS - Mt. Baker Floor Graphics Coating - Product Data_POP.pdf
09 96 00-020-00 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-020-00 HIGH PERFORMANCE COATINGS - Mt. Baker Floor Graphics Paint Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-22 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-10-06 | 2021-09-23 | 2 |  | Record Copies; Transfers; Submittals | 09 96 00-020-00-01 - 09 96 00-020-00 HIGH PERFORMANCE COATINGS - Mt. Baker Floor Graphics Paint Samples | 2 |  | 2021-09-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14690 | Received | For Review | 2021-09-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-10-06 | Submittal Number: 09 96 00-20.0 From: KIM DOWALIBY Final Due Date: 10/06/21 Subject: HIGH PERFORMANCE COATINGS - MT. BAKER FLOOR GRAPHICS PAINT SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 18944 | Forwarded | For Review | 2021-09-22 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-29 | Submittal Number: 09 96 00-20.0 From: KIM DOWALIBY Final Due Date: 10/06/21 Subject: HIGH PERFORMANCE COATINGS - MT. BAKER FLOOR GRAPHICS PAINT SAMPLES Description: Spec Section: 09 96 00 - HIGH-PERFORMANCE COATINGS Status: OPEN | Info Exchange
| 18950 | Responded and Closed | Revise and Resubmit | 2021-09-23 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | Revise/resubmit blue paint color to match more closely to PMS 296 C. Communicated to Mortenson via email 09/22/2021. Black color approved. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-22 |  | 09 96 00-20 - HIGH PERFORMANCE COATINGS - Mt. Baker Floor Graphics Paint Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-22 |  | 09 96 00-20 - HIGH PERFORMANCE COATINGS - Mt. Baker Floor Graphics Paint Samples.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-09-23 |  | 09 96 00-20 - HIGH PERFORMANCE COATINGS - Mt. Baker Floor Graphics Paint Samples_POP.pdf
09 96 00-020-00-01 | 09 96 00 - HIGH-PERFORMANCE COATINGS | 09 96 00-020-00 HIGH PERFORMANCE COATINGS - Mt. Baker Floor Graphics Paint Samples | Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 09 96 00-020-00 - 09 96 00-020-00 HIGH PERFORMANCE COATINGS - Mt. Baker Floor Graphics Paint Samples | -1 | 2021-10-07
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-23 |  | 09 96 00-20 - HIGH PERFORMANCE COATINGS - Mt. Baker Floor Graphics Paint Samples_POP.pdf
09 97 23-001-00 | 09 97 23 - CONCRETE STORM WATER DETENTION LINING | 09 97 23-001-00 CONCRETE STORM WATER DETENTION LINING - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-08 07:00 | 2020-09-10 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-09-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07681 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-08 07:00 | Submittal Number: 09 97 23-1.0 From: BROOKE BURCHAM Final Due Date: 08/28/20 Subject: CONCRETE STORM WATER DETENTION LINING - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURER'S PRODUCT DATA FOR EACH COATING, INCLUDING GENERIC DESCRIPTION, COMPLETE TECHNICAL DATA, SURFACE PREPARATION, AND APPLICATION INSTRUCTIONS. Spec Section: 09 97 23 - CONCRETE STORM WATER DETENTION LINING Status: OPEN | Info Exchange
| 10225 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-31 | Submittal Number: 09 97 23-1.0 From: BROOKE BURCHAM Final Due Date: 08/28/20 Subject: CONCRETE STORM WATER DETENTION LINING - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURER'S PRODUCT DATA FOR EACH COATING, INCLUDING GENERIC DESCRIPTION, COMPLETE TECHNICAL DATA, SURFACE PREPARATION, AND APPLICATION INSTRUCTIONS. Spec Section: 09 97 23 - CONCRETE STORM WATER DETENTION LINING Status: OPEN | Info Exchange
| 10357 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-27 | Shaina Burris (Populous) | Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 10539 | Reopened | Additional Information | 2020-09-04 13:35 | Josh Dobken (Populous) |  |  | Incorrect submittal provided in closing of this number. Reopening to provide correct information.
| 10679 | Responded and Closed | Approved | 2020-09-10 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-21 |  | 099723-0001-0 Storm Water Detention Lining - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-21 |  | 099723-0001-0 Storm Water Detention Lining - Product Data.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-08-21 |  | 099723-0001-0 Storm Water Detention Lining - Product Data.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-09 02:00 |  | 099723-0001-0 Storm Water Detention Lining - Product Data_POP.pdf
09 97 23-007-00 | 09 97 23 - CONCRETE STORM WATER DETENTION LINING | 09 97 23-007-00 CONCRETE STORM DETENTION LINING - SHOP DRAWINGS | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-03 | Responded and Closed - Approved |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-18 | 2020-09-10 | 8 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-09-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07957 | Received | For Review | 2020-09-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Brooke Burcham (M.A. Mortenson Company) | 2020-09-18 | Submittal Number: 09 97 23-7.0 From: BROOKE BURCHAM Final Due Date: 09/17/20 Subject: CONCRETE STORM DETENTION LINING - SHOP DRAWINGS Description: Spec Section: 09 97 23 - CONCRETE STORM WATER DETENTION LINING Status: OPEN | Info Exchange
| 10581 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-15 | Submittal Number: 09 97 23-7.0 From: BROOKE BURCHAM Final Due Date: 09/17/20 Subject: CONCRETE STORM DETENTION LINING - SHOP DRAWINGS Description: Spec Section: 09 97 23 - CONCRETE STORM WATER DETENTION LINING Status: OPEN | Info Exchange
| 10693 | Responded and Closed | Approved | 2020-09-10 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Brooke Burcham (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-03 |  | 099723-0007-0 Storm Water Detention Lining - SD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-03 |  | 099723-0007-0 Storm Water Detention Lining - SD.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-10 02:00 |  | 099723-0007-0 Storm Water Detention Lining - SD_POP.pdf
10 11 00-001-00 | 10 11 00 | 10 11 00-001-00 VISUAL DISPLAY UNITS - MB1 Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 | 2021-04-20 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12465 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-04-22 | Submittal Number: 10 11 00-1.0 From: ALLIE ZIMMERMAN Final Due Date: 04/15/21 Subject: VISUAL DISPLAY UNITS - MB1 SAMPLE Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 16155 | Forwarded | For Review | 2021-04-08 | Allie Zimmerman | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 10 11 00-1.0 From: ALLIE ZIMMERMAN Final Due Date: 04/15/21 Subject: VISUAL DISPLAY UNITS - MB1 SAMPLE Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 12681 | Review Response | Approved as Noted | 2021-04-20 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16401 | Responded and Closed | Approved as Noted | 2021-04-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | Submittal 10 11 00-1 Revision 0 VISUAL DISPLAY UNITS - MB1 Sample_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-04-08 |  | Submittal 10 11 00-1 Revision 0 VISUAL DISPLAY UNITS - MB1 Sample_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-20 |  | Submittal 10 11 00-1 Revision 0 VISUAL DISPLAY UNITS - MB1 Sample_MAM Reviewed_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-08 |  | Submittal 10 11 00-1 Revision 0 VISUAL DISPLAY UNITS - MB1 Sample_MAM Reviewed.pdf
10 11 00-002-00 | 10 11 00 | 10 11 00-002-00 VISUAL DISPLAY UNITS - NHL Home/Visitor Locker Shop Drawings | Closed | Architectural, Audio-Visual, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Brian Elwell (Idibri), Jackie Lybarger (ME Engineers) |  |  |  | 2021-06-03 07:00 | 2021-05-19 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13179 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-03 07:00 | Submittal Number: 10 11 00-2.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: VISUAL DISPLAY UNITS - NHL HOME/VISITOR LOCKER SHOP DRAWINGS Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 17067 | Forwarded | For Review | 2021-05-19 | Allie Zimmerman | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-26 | Submittal Number: 10 11 00-2.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: VISUAL DISPLAY UNITS - NHL HOME/VISITOR LOCKER SHOP DRAWINGS Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 17071 | Forwarded | For Review | 2021-05-19 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Brian Elwell (Idibri); Jackie Lybarger (ME Engineers) | 2021-05-26 | Submittal Number: 10 11 00-2.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: VISUAL DISPLAY UNITS - NHL HOME/VISITOR LOCKER SHOP DRAWINGS Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 13183 | Review Response | Approved as Noted | 2021-05-19 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17072 | Responded and Closed | Approved as Noted | 2021-05-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | Submittal 10 11 00-2 Revision 0 VISUAL DISPLAY UNITS - NHL HomeVisitor Locker Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-18 |  | Submittal 10 11 00-2 Revision 0 VISUAL DISPLAY UNITS - NHL HomeVisitor Locker Shop Drawings_MAM Reviewed.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-05-17 02:00 |  | Submittal 10 11 00-2 Revision 0 VISUAL DISPLAY UNITS - NHL HomeVisitor Locker Shop Drawings_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-05-19 |  | Submittal 10 11 00-2 Revision 0 VISUAL DISPLAY UNITS - NHL HomeVisitor_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-18 |  | Submittal 10 11 00-2 Revision 0 VISUAL DISPLAY UNITS - NHL HomeVisitor Locker Shop Drawings_MAM Reviewed.pdf
10 11 00-003-00 | 10 11 00 | 10 11 00-003-00 VISUAL DISPLAY UNITS - MB1 Product Data & LEED | Closed | Architectural, Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-25 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian Elwell (Idibri) |  |  |  | 2021-09-08 | 2021-09-02 | 9 |  | Record Copies; Transfers; Submittals | 10 11 00-003-00-01 - 10 11 00-003-00 VISUAL DISPLAY UNITS - MB1 Product Data & LEED | 9 |  | 2021-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14457 | Received | For Review | 2021-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-09-08 | Submittal Number: 10 11 00-3.0 From: ALLIE ZIMMERMAN Final Due Date: 09/08/21 Subject: VISUAL DISPLAY UNITS - MB1 PRODUCT DATA & LEED Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 18653 | Forwarded | For Review | 2021-08-25 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-01 | Submittal Number: 10 11 00-3.0 From: ALLIE ZIMMERMAN Final Due Date: 09/08/21 Subject: VISUAL DISPLAY UNITS - MB1 PRODUCT DATA & LEED Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 18748 | Forwarded | For Review | 2021-09-01 | Populous SCA_CCA | Brian Elwell (Idibri) | 2021-09-08 | Submittal Number: 10 11 00-3.0 From: ALLIE ZIMMERMAN Final Due Date: 09/08/21 Subject: VISUAL DISPLAY UNITS - MB1 PRODUCT DATA & LEED Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 18762 | Responded and Closed | Revise and Resubmit | 2021-09-02 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | SUBMIT 01 81 13.14B LEED PRODUCT SUBMIT FORM | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-25 |  | Submittal 10 11 00-3 Revision 0 VISUAL DISPLAY UNITS - MB1 Product Data LEED_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-25 |  | Submittal 10 11 00-3 Revision 0 VISUAL DISPLAY UNITS - MB1 Product Data LEED_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-24 02:00 |  | Submittal 10 11 00-3 Revision 0 VISUAL DISPLAY UNITS - MB1 Product Data LEED_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-09-02 |  | Submittal 10 11 00-3 Revision 0 VISUAL DISPLAY UNITS - MB1 Product Data LEED_MAM Reviewed_POP.pdf
10 11 00-003-00-01 | 10 11 00 | 10 11 00-003-00 VISUAL DISPLAY UNITS - MB1 Product Data & LEED | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 11 00-003-00 - 10 11 00-003-00 VISUAL DISPLAY UNITS - MB1 Product Data & LEED | -1 | 2021-09-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-02 |  | Submittal 10 11 00-3 Revision 0 VISUAL DISPLAY UNITS - MB1 Product Data LEED_MAM Reviewed_POP.pdf
10 11 00-004-00 | 10 11 00 | 10 11 00-004-00 VISUAL DISPLAY UNITS - MB3 Product Data & LEED | Closed | Architectural, Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-25 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian Elwell (Idibri) |  |  |  | 2021-09-08 | 2021-09-02 | 9 |  | Record Copies; Transfers; Submittals | 10 11 00-004-00-01 - 10 11 00-004-00 VISUAL DISPLAY UNITS - MB3 Product Data & LEED, 10 11 00-004-00-01 - 10 11 00-004-00 VISUAL DISPLAY UNITS - MB3 Product Data & LEED | 9 |  | 2021-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14458 | Received | For Review | 2021-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-09-08 | Submittal Number: 10 11 00-4.0 From: ALLIE ZIMMERMAN Final Due Date: 09/08/21 Subject: VISUAL DISPLAY UNITS - MB3 PRODUCT DATA & LEED Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 18654 | Forwarded | For Review | 2021-08-25 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-01 | Submittal Number: 10 11 00-4.0 From: ALLIE ZIMMERMAN Final Due Date: 09/08/21 Subject: VISUAL DISPLAY UNITS - MB3 PRODUCT DATA & LEED Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 18749 | Forwarded | For Review | 2021-09-01 | Populous SCA_CCA | Brian Elwell (Idibri) | 2021-09-08 | Submittal Number: 10 11 00-4.0 From: ALLIE ZIMMERMAN Final Due Date: 09/08/21 Subject: VISUAL DISPLAY UNITS - MB3 PRODUCT DATA & LEED Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 18759 | Responded and Closed | Revise and Resubmit | 2021-09-02 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SUBMIT 01 81 13.14B LEED PRODUCT SUBMIT FORM | Info Exchange
| 18760 | Reopened | Additional Information | 2021-09-02 08:30 | Chad Francis (Populous) |  |  | INCORRECT SUBMITTAL RETURN
| 18761 | Responded and Closed | Revise and Resubmit | 2021-09-02 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | SUBMIT 01 81 13.14B LEED PRODUCT SUBMIT FORM | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-25 |  | Submittal 10 11 00-4 Revision 0 VISUAL DISPLAY UNITS - MB3 Product Data LEED_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-25 |  | Submittal 10 11 00-4 Revision 0 VISUAL DISPLAY UNITS - MB3 Product Data LEED_MAM Reviewed.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-24 02:00 |  | Submittal 10 11 00-4 Revision 0 VISUAL DISPLAY UNITS - MB3 Product Data LEED_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-09-02 |  | Submittal 10 11 00-3 Revision 0 VISUAL DISPLAY UNITS - MB1 Product Data LEED_MAM Reviewed_POP.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-09-02 |  | Submittal 10 11 00-4 Revision 0 VISUAL DISPLAY UNITS - MB3 Product Data LEED_MAM Reviewed_POP.pdf
10 11 00-004-00-01 | 10 11 00 | 10 11 00-004-00 VISUAL DISPLAY UNITS - MB3 Product Data & LEED | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 11 00-004-00 - 10 11 00-004-00 VISUAL DISPLAY UNITS - MB3 Product Data & LEED | -1 | 2021-09-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-02 |  | Submittal 10 11 00-3 Revision 0 VISUAL DISPLAY UNITS - MB1 Product Data LEED_MAM Reviewed_POP.pdf
10 11 00-004-00-01 | 10 11 00 | 10 11 00-004-00 VISUAL DISPLAY UNITS - MB3 Product Data & LEED | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 11 00-004-00 - 10 11 00-004-00 VISUAL DISPLAY UNITS - MB3 Product Data & LEED | -1 | 2021-09-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-02 |  | Submittal 10 11 00-4 Revision 0 VISUAL DISPLAY UNITS - MB3 Product Data LEED_MAM Reviewed_POP.pdf
10 11 00-006-00 | 10 11 00 | 10 11 00-006-00 VISUAL DISPLAY UNITS - MB3 Verification Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-28 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-11 | 2021-06-01 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-06-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13320 | Received | For Review | 2021-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-11 | Submittal Number: 10 11 00-6.0 From: ALLIE ZIMMERMAN Final Due Date: 06/16/21 Subject: VISUAL DISPLAY UNITS - MB3 VERIFICATION SAMPLE Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 17235 | Forwarded | For Review | 2021-06-01 | Allie Zimmerman | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 10 11 00-6.0 From: ALLIE ZIMMERMAN Final Due Date: 06/16/21 Subject: VISUAL DISPLAY UNITS - MB3 VERIFICATION SAMPLE Description: Spec Section: 10 11 00 - VISUAL DISPLAY UNITS Status: OPEN | Info Exchange
| 13328 | Review Response | Approved as Noted | 2021-06-01 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17241 | Responded and Closed | Approved as Noted | 2021-06-01 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-28 |  | Submittal 10 11 00-6 Revision 0 VISUAL DISPLAY UNITS - MB3 Verification Sample_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-28 |  | Submittal 10 11 00-6 Revision 0 VISUAL DISPLAY UNITS - MB3 Verification Sample_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-01 |  | Submittal 10 11 00-6 Revision 0 VISUAL DISPLAY UNITS - MB3 Sample_POP.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-01 |  | MARKER BOARD NHL RINK DIAGRAM_REVISION 1.ai
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-28 |  | Submittal 10 11 00-6 Revision 0 VISUAL DISPLAY UNITS - MB3 Verification Sample_MAM Reviewed.pdf
10 14 00-001-00 | 10 14 00 | 10 14 00-001-00 Code Signage Pkg. 1 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Kelly Holton (Populous), Mary Lim (Populous) |  |  |  | 2021-04-19 | 2021-04-08 | 4 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-04-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12395 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 10 14 00-1.0 From: MIKE SOLFELT Final Due Date: 04/19/21 Subject: CODE SIGNAGE PKG. 1 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16101 | Forwarded | For Review | 2021-04-06 | Populous SCA_CCA | Kelly Holton (Populous); Mary Lim (Populous) |  | Submittal Number: 10 14 00-1.0 From: MIKE SOLFELT Final Due Date: 04/19/21 Subject: CODE SIGNAGE PKG. 1 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16190 | Responded and Closed | Approved as Noted | 2021-04-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Colors and finishes under review. Populous to provide final color and finish selections once confirmed. Revised art for SS-06 also attached, with updated "The PitchBook Suites" logo. Fabricator to resubmit TC-06 Tunnel Suite ID once sign design is finalized. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 101400-001 Mock-Up Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 101400-001 Mock-Up Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 101400-001 Mock-Up Shop Drawings_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-08 |  | SS-06 Suiteline Suite ID_Revised Logo.ai
10 14 00-002-00 | 10 14 00 | 10 14 00-002-00 Code Signage Pkg. 2 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved as Noted/Resubmit |  | Kuebler Perry (Populous), Kelly Holton (Populous) |  |  |  | 2021-05-05 | 2021-05-14 | 24 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-05-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12705 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-05 | Submittal Number: 10 14 00-2.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: CODE SIGNAGE PKG. 2 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16534 | Forwarded | For Review | 2021-04-26 | Populous SCA_CCA | Kuebler Perry (Populous); Kelly Holton (Populous) | 2021-05-03 | Submittal Number: 10 14 00-2.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: CODE SIGNAGE PKG. 2 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16947 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | SEE INDIVIDUAL SHEETS FOR ACTION STATUS. | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-21 |  | 101400-002 Code Signage Pkg 2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-20 02:00 |  | 101400-002 Code Signage Pkg 2.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-14 |  | 101400-002 Code Signage Pkg 2_ POP_CPA_COMPILED.pdf
10 14 00-002-01 | 10 14 00 | 10 14 00-002-01 Code Signage Pkg. 2 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-28 | Responded and Closed - Approved as Noted | [5 empty] | 2021-06-14 07:00 | 2021-06-08 | 12 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-06-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13322 | Received | For Review | 2021-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-14 07:00 | Submittal Number: 10 14 00-2.1 From: MIKE SOLFELT Final Due Date: 06/11/21 Subject: CODE SIGNAGE PKG. 2 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17389 | Responded and Closed | Approved as Noted | 2021-06-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Approved as noted. Shop drawing mark-ups to take precedence over all other documents moving forward. All future changes to be captured in shop drawings. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-08 |  | 101400-002.1 Code Signage Pkg 2 rev1_POP COMPILED.pdf
10 14 00-004-00 | 10 14 00 | 10 14 00-004-00 Signage Paint Samples | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-23 | Responded and Closed - Approved as Noted/Resubmit |  | Kuebler Perry (Populous), Kelly Holton (Populous) |  |  |  | 2021-05-07 | 2021-05-13 | 21 |  | Record Copies; Transfers; Submittals | 10 14 00-004-00-01 - 10 14 00-004-00 Signage Paint Samples | 18 |  | 2021-05-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12744 | Received | For Review | 2021-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-05-07 | Submittal Number: 10 14 00-4.0 From: MIKE SOLFELT Final Due Date: 05/08/21 Subject: SIGNAGE PAINT SAMPLES Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16535 | Forwarded | For Review | 2021-04-26 | Josh Dobken (Populous) | Kuebler Perry (Populous); Kelly Holton (Populous) | 2021-05-03 | Submittal Number: 10 14 00-4.0 From: MIKE SOLFELT Final Due Date: 05/08/21 Subject: SIGNAGE PAINT SAMPLES Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16945 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-13 | Mary Lim (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | COLORS HAVE BEEN REVISED FOR LEVELS 600 (UL), 400 (LL1), 200 (LL3), AND 100 (LL4) PER OWNERSHIP FEEDBACK ON 05/13/2021. SEE INDIVIDUAL SHEETS. 4 SHEETS ARE NOTED AS "REVISE/RESUBMIT". ALL OTHERS ARE APPROVED OR APPROVED AS NOTED. | Email
| 17061 | Sent | For Information Only | 2021-05-19 | Josh Dobken (Populous) | Brooke Burcham (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) Remarks: COLORS HAVE BEEN REVISED FOR LEVELS 600 (UL), 400 (LL1), 200 (LL3), AND 100 (LL4) PER OWNERSHIP FEEDBACK ON 05/13/2021. SEE INDIVIDUAL SHEETS. 4 SHEETS ARE NOTED AS "REVISE/RESUBMIT". ALL OTHERS ARE APPROVED OR APPROVED AS NOTED. | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-23 |  | 101400-004 Signage Paint Samples.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-04-22 02:00 |  | 101400-004 Signage Paint Samples.pdf
| Responded and Closed |  | Mary Lim (Populous) | 1 | 2021-05-13 |  | 101400-004 Signage Paint Samples_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-04-22 02:00 |  | 101400-004 Signage Paint Samples.pdf
10 14 00-004-00-01 | 10 14 00 | 10 14 00-004-00 Signage Paint Samples | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 14 00-004-00 - 10 14 00-004-00 Signage Paint Samples | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-13 |  | 101400-004 Signage Paint Samples_POP.pdf
10 14 00-005-00 | 10 14 00 | 10 14 00-005-00 Signage Shop Drawings Pkg. #3 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-29 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Geoff Cheong, Kelly Holton (Populous) |  |  |  | 2021-05-13 | 2021-05-14 | 16 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-05-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12861 | Received | For Review | 2021-04-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-13 | Submittal Number: 10 14 00-5.0 From: MIKE SOLFELT Final Due Date: 05/13/21 Subject: SIGNAGE SHOP DRAWINGS PKG. #3 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16677 | Forwarded | For Review | 2021-05-03 | Populous SCA_CCA | Todd Spangler (Populous); Geoff Cheong; Kelly Holton (Populous) | 2021-05-10 | Submittal Number: 10 14 00-5.0 From: MIKE SOLFELT Final Due Date: 05/13/21 Subject: SIGNAGE SHOP DRAWINGS PKG. #3 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16948 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | SEE INDIVIDUAL SHEETS FOR ACTION STATUS. | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-29 02:00 |  | 101400-005 Signage Shop Drawings Pkg. #3.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-14 |  | 101400-005 Signage Shop Drawings Pkg. #3_POP.pdf
10 14 00-005-01 | 10 14 00 | 10 14 00-005-01 Signage Shop Drawings Pkg. #3 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-04 | Responded and Closed - Approved as Noted | [5 empty] | 2021-06-18 | 2021-06-15 | 12 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13417 | Received | For Review | 2021-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-18 | Submittal Number: 10 14 00-5.1 From: MIKE SOLFELT Final Due Date: 06/15/21 Subject: SIGNAGE SHOP DRAWINGS PKG. #3 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17530 | Responded and Closed | Approved as Noted | 2021-06-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Approved as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-15 |  | 101400-005.1 Signage Shop Drawings Pkg. #3 rev 1_POP COMPILED.pdf
10 14 00-006-00 | 10 14 00 | 10 14 00-006-00 Vinyl Samples | Closed | Graphics/Signage | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-29 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Geoff Cheong, Kuebler Perry (Populous), Kelly Holton (Populous) |  |  |  | 2021-05-13 | 2021-05-13 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-05-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12866 | Received | For Review | 2021-04-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-13 | Submittal Number: 10 14 00-6.0 From: MIKE SOLFELT Final Due Date: 05/15/21 Subject: VINYL SAMPLES Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16678 | Forwarded | For Review | 2021-05-03 | Populous SCA_CCA | Todd Spangler (Populous); Geoff Cheong; Kuebler Perry (Populous); Kelly Holton (Populous) | 2021-05-10 | Submittal Number: 10 14 00-6.0 From: MIKE SOLFELT Final Due Date: 05/15/21 Subject: VINYL SAMPLES Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16928 | Responded and Closed | Approved as Noted | 2021-05-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Vinyl samples approved as noted. Fabricator to brighten V5 to more closely match PMS 2270C (Climate Pledge Arena - Tropical Leaf green) if possible. See attached with mark-ups. | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-29 |  | 101400-006 Signage Vinyl Samples.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-28 02:00 |  | 101400-006 Signage Vinyl Samples.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-03 |  | Transmittal_Submittal - 10 14 00-006-00 (Forwarded).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-13 |  | 101400-006 Signage Vinyl Samples_POP_AN.pdf
10 14 00-007-00 | 10 14 00 | 10 14 00-007-00 Gradient Signage Samples | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - Approved as Noted/Resubmit |  | Geoff Cheong, Kelly Holton (Populous), Mary Lim (Populous) |  |  |  | 2021-05-17 | 2021-05-13 | 11 |  | Record Copies; Transfers; Submittals | 10 14 00-007-00-01 - 10 14 00-007-00 Gradient Signage Samples | 4 |  | 2021-05-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12925 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-17 | Submittal Number: 10 14 00-7.0 From: MIKE SOLFELT Final Due Date: 05/20/21 Subject: GRADIENT SIGNAGE SAMPLES Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16823 | Forwarded | For Review | 2021-05-10 | Populous SCA_CCA | Geoff Cheong; Kelly Holton (Populous); Mary Lim (Populous) | 2021-05-17 | Submittal Number: 10 14 00-7.0 From: MIKE SOLFELT Final Due Date: 05/20/21 Subject: GRADIENT SIGNAGE SAMPLES Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16946 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | SEE INDIVIDUAL SHEETS FOR APPROVAL STATUS. SOME ARE APPROVED, APPROVED AS NOTED, OR REVISE/RESUBMIT. FABRICATOR TO CLARIFY WHAT M-14 IS USED FOR. | Email
| 17164 | Sent | For Information Only | 2021-05-25 | Populous SCA_CCA | Tyrone Thornton (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) Remarks: SEE INDIVIDUAL SHEETS FOR APPROVAL STATUS. SOME ARE APPROVED, APPROVED AS NOTED, OR REVISE/RESUBMIT. FABRICATOR TO CLARIFY WHAT M-14 IS USED FOR. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-03 |  | 101400-007 Gradiant and Material Samples.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-02 02:00 |  | 101400-007 Gradiant and Material Samples.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-13 |  | 101400-007 Gradiant and Material Samples_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-05-02 02:00 |  | 101400-007 Gradiant and Material Samples.pdf
10 14 00-007-00-01 | 10 14 00 | 10 14 00-007-00 Gradient Signage Samples | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 14 00-007-00 - 10 14 00-007-00 Gradient Signage Samples | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-13 |  | 101400-007 Gradiant and Material Samples_POP.pdf
10 14 00-008-00 | 10 14 00 | 10 14 00-008-00 Signage Package #4 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved as Noted/Resubmit |  | Kelly Holton (Populous), Mary Lim (Populous) |  |  |  | 2021-05-25 | 2021-05-19 | 9 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13037 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-05-25 | Submittal Number: 10 14 00-8.0 From: MIKE SOLFELT Final Due Date: 05/21/21 Subject: SIGNAGE PACKAGE #4 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16913 | Forwarded | For Review | 2021-05-12 | Josh Dobken (Populous) | Kelly Holton (Populous); Mary Lim (Populous) | 2021-05-19 | Submittal Number: 10 14 00-8.0 From: MIKE SOLFELT Final Due Date: 05/21/21 Subject: SIGNAGE PACKAGE #4 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17084 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-19 | Mary Lim (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | SEE INDIVIDUAL SHEETS FOR ACTION STATUS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | 101400-008 Signage Pkg. 4.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-05-10 02:00 |  | 101400-008 Signage Pkg. 4.pdf
| Responded and Closed |  | Mary Lim (Populous) | 1 | 2021-05-19 |  | 101400-008 Signage Pkg 4_POP.pdf
10 14 00-008-01 | 10 14 00 | 10 14 00-008-01 Signage Package #4 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-08 | Responded and Closed - Approved as Noted | [5 empty] | 2021-07-22 | 2021-07-21 | 14 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13830 | Received | For Review | 2021-07-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-07-22 | Submittal Number: 10 14 00-8.1 From: MIKE SOLFELT Final Due Date: 07/16/21 Subject: SIGNAGE PACKAGE #4 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18153 | Responded and Closed | Approved as Noted | 2021-07-21 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-07-21 |  | 101400-008.1 Signage Pkg. 4 rev 1_POP.pdf
10 14 00-009-00 | 10 14 00 | 10 14 00-009-00 Signage Package #5 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved as Noted/Resubmit | [5 empty] | 2021-06-02 07:00 | 2021-05-28 | 11 |  | Record Copies; Transfers; Submittals | 10 14 00-009-00-01 - 10 14 00-009-00 Signage Package #5 | -1 |  | 2021-05-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13145 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-02 07:00 | Submittal Number: 10 14 00-9.0 From: MIKE SOLFELT Final Due Date: 05/28/21 Subject: SIGNAGE PACKAGE #5 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17215 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-28 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | See individual sheets for action status. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-28 |  | 10 14 00-009-0 Signage Pkg _5_POP.pdf
10 14 00-009-00-01 | 10 14 00 | 10 14 00-009-00 Signage Package #5 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 14 00-009-00 - 10 14 00-009-00 Signage Package #5 | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-28 |  | 10 14 00-009-0 Signage Pkg _5_POP.pdf
10 14 00-010-00 | 10 14 00 | 10 14 00-010-00 Signage Package #6 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-24 | Responded and Closed - Approved as Noted/Resubmit |  | Kelly Holton (Populous), Mary Lim (Populous) |  |  |  | 2021-06-08 07:00 | 2021-06-15 | 23 |  | Record Copies; Transfers; Submittals | 10 14 00-010-00-01 - 10 14 00-010-00 Signage Package #6 | 23 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13237 | Received | For Review | 2021-05-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-06-08 07:00 | Submittal Number: 10 14 00-10.0 From: MIKE SOLFELT Final Due Date: 06/04/21 Subject: SIGNAGE PACKAGE #6 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17134 | Forwarded | For Review | 2021-05-24 | Josh Dobken (Populous) | Kelly Holton (Populous); Mary Lim (Populous) | 2021-05-31 | Submittal Number: 10 14 00-10.0 From: MIKE SOLFELT Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN Final Due Date: 06/04/21 Subject: SIGNAGE PACKAGE #6 | Info Exchange
| 17531 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-15 | Mary Lim (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | See individual sheets for action status. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-05-24 02:00 |  | 10 14 00-010-0 Signage Pkg #6.pdf
| Responded and Closed |  | Mary Lim (Populous) | 1 | 2021-06-15 |  | 10 14 00-010-0 Signage Pkg #6_POP.pdf
10 14 00-010-00-01 | 10 14 00 | 10 14 00-010-00 Signage Package #6 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 14 00-010-00 - 10 14 00-010-00 Signage Package #6 | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-15 |  | 10 14 00-010-0 Signage Pkg #6_POP.pdf
10 14 00-011-00 | 10 14 00 | 10 14 00-011-00 Signage Package #7 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-01 | Responded and Closed - Approved as Noted | [5 empty] | 2021-06-15 | 2021-06-16 | 16 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-06-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13332 | Received | For Review | 2021-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-15 | Submittal Number: 10 14 00-11.0 From: MIKE SOLFELT Final Due Date: 06/11/21 Subject: SIGNAGE PACKAGE #7 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17547 | Responded and Closed | Approved as Noted | 2021-06-16 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Approved as noted. Please submit all message layouts for review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-16 |  | 101400-011 Signage Pkg #7_POP.pdf
10 14 00-011-01 | 10 14 00 | 10 14 00-011-01 Signage Packages 5-8 Resubmittal | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-21 | Responded and Closed - Approved as Noted/Resubmit | [5 empty] | 2021-08-04 | 2021-08-11 | 22 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-08-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14038 | Received | For Review | 2021-07-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-08-04 | Submittal Number: 10 14 00-11.1 From: MIKE SOLFELT Final Due Date: 07/16/21 Subject: SIGNAGE PACKAGES 5-8 RESUBMITTAL Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18470 | Responded and Closed | Approved as Noted/Resubmit | 2021-08-11 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-21 |  | 101400-011.1 Signage Package 5-8 REsubmittal.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-08-10 |  | 101400-011.1 Signage Package 5-8 REsubmittal_Pop2.pdf
10 14 00-012-00 | 10 14 00 | 10 14 00-012-00 Signage Mock-Up Submittal #1 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved as Noted |  | Kelly Holton (Populous), Mary Lim (Populous) |  |  |  | 2021-05-25 | 2021-05-14 | 4 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-05-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13038 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-25 | Submittal Number: 10 14 00-12.0 From: MIKE SOLFELT Final Due Date: 05/21/21 Subject: SIGNAGE MOCK-UP SUBMITTAL #1 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16914 | Forwarded | For Review | 2021-05-12 | Populous SCA_CCA | Kelly Holton (Populous); Mary Lim (Populous) | 2021-05-19 | Submittal Number: 10 14 00-12.0 From: MIKE SOLFELT Final Due Date: 05/21/21 Subject: SIGNAGE MOCK-UP SUBMITTAL #1 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 16965 | Responded and Closed | Approved as Noted | 2021-05-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | SIGN MOCK-UPS IN THIS SUBMITTAL ARE APPROVED AS NOTED. FABRICATOR TO SEND REMAINING SIGN MOCK-UPS FOR REVIEW. PER OWNERSHIP FEEDBACK, COLORS HAVE BEEN CHANGED FOR FOUR LEVELS, SEE RETURNED SUBMITTAL 101400-004 PAINT SAMPLES. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-11 02:00 |  | 101400-012 Signage Mock-Up Samples _1.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-14 |  | 101400-012 Signage Mock-Up Samples _1_POP.pdf
10 14 00-013-00 | 10 14 00 | 10 14 00-013-00 Signage Paint Samples #2 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-28 | Responded and Closed - Approved as Noted/Resubmit | [5 empty] | 2021-06-14 07:00 | 2021-06-07 | 11 |  | Record Copies; Transfers; Submittals | 10 14 00-013-00-01 - 10 14 00-013-00 Signage Paint Samples #2 | -1 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13321 | Received | For Review | 2021-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-14 07:00 | Submittal Number: 10 14 00-13.0 From: MIKE SOLFELT Final Due Date: 06/14/21 Subject: SIGNAGE PAINT SAMPLES #2 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17388 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-07 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | See individual sheets for action status. | Info Exchange
| 17527 | Sent | For Information Only | 2021-06-15 | Populous SCA_CCA | Brooke Burcham (Mortenson Construction); Christian Albers (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) Remarks: See individual sheets for action status. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-08 |  | 101400-013 Signage Paint and Materials #2_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-06-08 02:00 |  | 101400-013 Signage Paint and Materials #2_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-06-08 02:00 |  | Transmittal_Submittal - 10 14 00-013-00 (Responded and Closed).pdf
10 14 00-013-00-01 | 10 14 00 | 10 14 00-013-00 Signage Paint Samples #2 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 14 00-013-00 - 10 14 00-013-00 Signage Paint Samples #2 | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-08 |  | 101400-013 Signage Paint and Materials #2_POP.pdf
10 14 00-014-00 | 10 14 00 | 10 14 00-014-00 Signage Mock-Up Submittal #2 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-01 | Responded and Closed - Approved as Noted | [5 empty] | 2021-06-15 | 2021-06-22 | 22 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-06-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13333 | Received | For Review | 2021-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-06-15 | Submittal Number: 10 14 00-14.0 From: MIKE SOLFELT Final Due Date: 06/14/21 Subject: SIGNAGE MOCK-UP SUBMITTAL #2 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17626 | Responded and Closed | Approved as Noted | 2021-06-22 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-06-22 |  | 101400-014 Signage Mock-Ups #2_POP.pdf
10 14 00-015-00 | 10 14 00 | 10 14 00-015-00 Signage Mock-Up Submittal #3 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-07 | Responded and Closed - Approved as Noted | [5 empty] | 2021-06-21 | 2021-06-16 | 10 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-06-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13425 | Received | For Review | 2021-06-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-21 | Submittal Number: 10 14 00-15.0 From: MIKE SOLFELT Final Due Date: 06/18/21 Subject: SIGNAGE MOCK-UP SUBMITTAL #3 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17548 | Responded and Closed | Approved as Noted | 2021-06-16 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Approved as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-16 |  | 101400-015-00 Signage Paint and Materials #3_POP.pdf
10 14 00-016-00 | 10 14 00 | 10 14 00-016-00 Paint and Digital Print Samples | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-08 | Responded and Closed - Approved as Noted | [5 empty] | 2021-06-22 | 2021-06-24 | 17 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13452 | Received | For Review | 2021-06-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-22 | Submittal Number: 10 14 00-16.0 From: MIKE SOLFELT Final Due Date: 06/24/21 Subject: PAINT AND DIGITAL PRINT SAMPLES Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17647 | Responded and Closed | Approved as Noted | 2021-06-24 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-08 |  | 101400-016 Paint and Digital Print Samples.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-24 |  | 101400-016 Paint and Digital Print Samples_POP.pdf
10 14 00-017-00 | 10 14 00 | 10 14 00-017-00 X-03B Shop Drawing | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-09 | Responded and Closed - Approved as Noted | [5 empty] | 2021-06-23 | 2021-06-15 | 7 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13474 | Received | For Review | 2021-06-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-23 | Submittal Number: 10 14 00-17.0 From: YE ZHANG Final Due Date: 06/18/21 Subject: X-03B SHOP DRAWING Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17523 | Responded and Closed | Approved as Noted | 2021-06-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  | Approved as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-09 |  | 101400-017 X-03B - Ticket Concierge Shop Drawing.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-15 |  | 101400-017 X-03B - Ticket Concierge Shop Drawing_POP.pdf
10 14 00-018-00 | 10 14 00 | 10 14 00-018-00 Signage Mock-Up Submittal #4 (ID-04B, ID-22, MC-04, ID-03C, D-06A) | Closed | Architectural, Graphics/Signage | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-18 | Responded and Closed - Approved as Noted | [5 empty] | 2021-07-02 | 2021-06-24 | 7 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13574 | Received | For Review | 2021-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-02 | Submittal Number: 10 14 00-18.0 From: YE ZHANG Final Due Date: 06/25/21 Subject: SIGNAGE MOCK-UP SUBMITTAL #4 (ID-04B, ID-22, MC-04, ID-03C, D-06A) Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17648 | Responded and Closed | Approved as Noted | 2021-06-24 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-24 |  | 10 14 00-018-0 Signage Mock-Ups #4_POP.pdf
10 14 00-019-00 | 10 14 00 | 10 14 00-019-00 Paints and Digital samples (P8, P6, P3, P9, SW7068 + Digital Prints) | Closed | Architectural, Graphics/Signage | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-21 | Responded and Closed - Approved | [5 empty] | 2021-07-05 | 2021-06-24 | 4 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13575 | Received | For Review | 2021-06-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-05 | Submittal Number: 10 14 00-19.0 From: YE ZHANG Final Due Date: 06/18/21 Subject: PAINTS AND DIGITAL SAMPLES (P8, P6, P3, P9, SW7068 + DIGITAL PRINTS) Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17649 | Responded and Closed | Approved | 2021-06-24 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-18 |  | 101400-019 Paints and Digital samples (P8 P6 P3 P9 SW7068 Digital Prints).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-24 |  | 101400-019 Paints and Digital samples (P8 P6 P3 P9 SW7068 Digital Prints)_POP.pdf
10 14 00-020-00 | 10 14 00 | 10 14 00-020-00 Signage Package #8 | Closed | Architectural, Graphics/Signage | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-21 | Responded and Closed - Approved as Noted | [5 empty] | 2021-07-05 | 2021-06-30 | 10 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-06-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13587 | Received | For Review | 2021-06-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-05 | Submittal Number: 10 14 00-20.0 From: YE ZHANG Final Due Date: 06/25/21 Subject: SIGNAGE PACKAGE #8 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17761 | Responded and Closed | Approved as Noted | 2021-06-30 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-30 |  | 101400-020 Signage Pkg #8 _POP COMPILED.pdf
10 14 00-021-00 | 10 14 00 | 10 14 00-021-00 Paints and Digital Samples (DP3, DP6, DP8, DP9, DP11 & P36) | Closed | Graphics/Signage | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-25 | Responded and Closed - Approved as Noted | [5 empty] | 2021-07-09 | 2021-06-29 | 5 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-06-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13659 | Received | For Review | 2021-06-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-07-09 | Submittal Number: 10 14 00-21.0 From: YE ZHANG Final Due Date: 07/02/21 Subject: PAINTS AND DIGITAL SAMPLES (DP3, DP6, DP8, DP9, DP11 & P36) Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17756 | Responded and Closed | Approved as Noted | 2021-06-29 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-25 |  | 101400-021 Paints and Digital samples (DP3 DP6 DP8 DP9 DP11 & P36).pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-06-29 |  | 101400-021 Paints and Digital samples (DP3 DP6 DP8 DP9 DP11 & P36)_POP.pdf
10 14 00-022-00 | 10 14 00 | 10 14 00-022-00 Signage Package #9 - SS-06 & TC-06 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-28 | Responded and Closed - Approved as Noted | [5 empty] | 2021-07-13 07:00 | 2021-07-15 | 18 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13677 | Received | For Review | 2021-06-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ye Zhang (Mortenson Construction) | 2021-07-13 07:00 | Submittal Number: 10 14 00-22.0 From: YE ZHANG Final Due Date: 07/02/21 Subject: SIGNAGE PACKAGE #9 - SS-06 & TC-06 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18069 | Responded and Closed | Approved as Noted | 2021-07-15 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-15 02:00 |  | 101400-022 Signage Package #9 - SS-06 & TC-06_Pop.pdf
10 14 00-023-00 | 10 14 00 | 10 14 00-023-00 Kraken Bar - Ceiling Element Shop Drawings | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-29 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Kuebler Perry (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-07-14 07:00 | 2021-07-09 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-07-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13702 | Received | For Review | 2021-06-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Alex Brown (Mortenson Construction) | 2021-07-14 07:00 | Submittal Number: 10 14 00-23.0 From: ALEX BROWN Final Due Date: 07/12/21 Subject: KRAKEN BAR - CEILING ELEMENT SHOP DRAWINGS Description: 2021.06.28AB: PLEASE SEE THE ATTACHED SHOP DRAWINGS FOR THE KRAKEN BAR CEILING ELEMENT FOR REVIEW AND APPROVAL. Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17741 | Forwarded | For Review | 2021-06-29 | Chad Francis (Populous) | Matthew Farber (Thornton Tomasetti); Kuebler Perry (Populous); Matt Ross (Thornton Tomasetti) | 2021-07-02 | Submittal Number: 10 14 00-23.0 From: ALEX BROWN Final Due Date: 07/12/21 Subject: KRAKEN BAR - CEILING ELEMENT SHOP DRAWINGS Description: 2021.06.28AB: PLEASE SEE THE ATTACHED SHOP DRAWINGS FOR THE KRAKEN BAR CEILING ELEMENT FOR REVIEW AND APPROVAL. Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 13874 | Review Response | Approved as Noted | 2021-07-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17959 | Responded and Closed | Approved as Noted | 2021-07-09 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-28 |  | 101400-23_Kraken Bar - Ceiling Element Shop Drawings.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2021-06-28 |  | 101400-23_Kraken Bar - Ceiling Element Shop Drawings.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-09 |  | 101400-23_Kraken Bar - Ceiling Element Shop Drawings_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-06-28 |  | 101400-23_Kraken Bar - Ceiling Element Shop Drawings.pdf
10 14 00-024-00 | 10 14 00 | 10 14 00-024-00 Kraken Bar - Ceiling Element Samples | Closed | Graphics/Signage | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-09 | Responded and Closed - Approved | [5 empty] | 2021-07-23 | 2021-07-08 | -1 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13858 | Received | For Review | 2021-07-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-23 | Submittal Number: 10 14 00-24.0 From: LUCAS TRADAL Final Due Date: 07/08/21 Subject: KRAKEN BAR - CEILING ELEMENT SAMPLES Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 17939 | Responded and Closed | Approved | 2021-07-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-08 |  | 101400 - 024 Kraken Bar Ceiling Samples.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-08 |  | 101400 - 024 Kraken Bar Ceiling Samples.pdf
10 14 00-025-00 | 10 14 00 | 10 14 00-025-00 Signage Paint Samples #3 | Closed | Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-15 | Responded and Closed - Approved as Noted/Resubmit | [5 empty] | 2021-07-29 | 2021-07-27 | 13 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-07-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13952 | Received | For Review | 2021-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-07-29 | Submittal Number: 10 14 00-25.0 From: MIKE SOLFELT Final Due Date: 07/25/21 Subject: SIGNAGE PAINT SAMPLES #3 Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18256 | Responded and Closed | Approved as Noted/Resubmit | 2021-07-27 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-07-27 |  | 2021_0708_CPA P37-P45 Sample Submittal_POP.pdf
10 14 00-026-00 | 10 14 00 | 10 14 00-026-00 Signage On Site Paint Samples | Closed | Graphics/Signage | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-27 | Responded and Closed - Approved | [5 empty] | 2021-08-10 | 2021-07-27 | 1 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-07-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14137 | Received | For Review | 2021-07-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-08-10 | Submittal Number: 10 14 00-26. From: MIKE SOLFELT Final Due Date: 07/30/21 Subject: SIGNAGE ON SITE PAINT SAMPLES Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18269 | Responded and Closed | Approved | 2021-07-27 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-27 |  | 101400-026 Signage Paint On Site Samples.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-07-27 |  | 101400-026 Signage Paint On Site Samples_POP[8].pdf
10 14 00-027-00 | 10 14 00 | 10 14 00-027-00 P46 / P47 Paint Samples | Closed | Graphics/Signage | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-03 | Responded and Closed - Approved | [5 empty] | 2021-08-17 | 2021-08-03 | 1 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-08-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14201 | Received | For Review | 2021-08-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-08-17 | Submittal Number: 10 14 00-27.0 From: MIKE SOLFELT Final Due Date: 08/14/21 Subject: P46 / P47 PAINT SAMPLES Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18359 | Responded and Closed | Approved | 2021-08-03 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-03 |  | 101400-027 P46 and P47 Paint Samples.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-08-03 |  | 101400-027 P46 and P47 Paint Samples_POP.pdf
10 14 00-028-00 | 10 14 00 | 10 14 00-028-00 Garage Signage Package | Closed | Graphics/Signage | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-03 | Responded and Closed - Approved as Noted | [5 empty] | 2021-08-17 | 2021-08-12 | 10 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-08-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14202 | Received | For Review | 2021-08-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-08-17 | Submittal Number: 10 14 00-28.0 From: MIKE SOLFELT Final Due Date: 08/10/21 Subject: GARAGE SIGNAGE PACKAGE Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18503 | Responded and Closed | Approved as Noted | 2021-08-12 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-03 |  | 101400-028 Garage Signage Package.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-08-12 |  | 101400-028 Garage Signage Package_POP COMPILED.pdf
10 14 00-029-00 | 10 14 00 | 10 14 00-029-00 Bondo's Booth Sign | Closed | Graphics/Signage | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-05 | Responded and Closed - Approved as Noted | [5 empty] | 2021-08-19 | 2021-08-05 | 1 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-08-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14233 | Received | For Review | 2021-08-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-08-19 | Submittal Number: 10 14 00-29.0 From: MIKE SOLFELT Final Due Date: 08/06/21 Subject: BONDO'S BOOTH SIGN Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18389 | Responded and Closed | Approved as Noted | 2021-08-05 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-05 |  | 101400-29 Bondos Booth Sign.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-08-05 |  | CC-24 - Bondo's Booth_POP[8].pdf
10 14 00-030-00 | 10 14 00 | 10 14 00-030-00 D-01B Structural Engineering | Closed | Graphics/Signage, Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-10 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Todd Spangler (Populous), Mary Lim (Populous) |  |  |  | 2021-08-24 | 2021-09-01 | 23 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14298 | Received | For Review | 2021-08-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-08-24 | Submittal Number: 10 14 00-30.0 From: MIKE SOLFELT Final Due Date: 08/24/21 Subject: D-01B STRUCTURAL ENGINEERING Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18469 | Forwarded | For Review | 2021-08-10 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2021-08-17 | Submittal Number: 10 14 00-30.0 From: MIKE SOLFELT Final Due Date: 08/24/21 Subject: D-01B STRUCTURAL ENGINEERING Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 14317 | Review Response | Approved | 2021-08-11 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Arch to review sign and attachment concept. | Info Exchange
| 18703 | Forwarded | For Review | 2021-08-27 | Josh Dobken (Populous) | Todd Spangler (Populous); Mary Lim (Populous) | 2021-08-24 | Submittal Number: 10 14 00-30.0 From: MIKE SOLFELT Final Due Date: 08/24/21 Subject: D-01B STRUCTURAL ENGINEERING Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18744 | Responded and Closed | Approved | 2021-09-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Approved | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-10 |  | 101400-030 D-01B structural Engineering.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-08-09 02:00 |  | 101400-030 D-01B structural Engineering.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-08-09 |  | 101400-030 D-01B structural Engineering.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-08-09 02:00 |  | 101400-030 D-01B structural Engineering.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-09-01 |  | 101400-030 D-01B structural Engineering_TT_POP.pdf
10 14 00-031-00 | 10 14 00 | 10 14 00-031-00 G-14B Signage | Closed | Graphics/Signage | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-11 | Responded and Closed - Approved as Noted | [5 empty] | 2021-08-25 | 2021-08-18 | 8 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2021-08-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14319 | Received | For Review | 2021-08-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-08-25 | Submittal Number: 10 14 00-31.0 From: MIKE SOLFELT Final Due Date: 08/28/21 Subject: G-14B SIGNAGE Description: Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18577 | Responded and Closed | Approved as Noted | 2021-08-18 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction); Ye Zhang (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-11 |  | 101400-031 G-14B Signage.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-08-17 |  | 101400-031 G-14B Signage_POP.pdf
10 14 00-032-00 | 10 14 00 | 10 14 00-032-00 Kraken Rum Sign Shop Drawings | Closed | Graphics/Signage, Owner/Operator, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-25 | Responded and Closed - Not Required For Review |  | Elliott Veazey (CAA ICON / Strategy Advisory), Byron Noll (CAA ICON / Strategy Advisory) |  |  |  | 2021-09-08 | 2021-09-08 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14471 | Received | For Review | 2021-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Shaina Burris (Populous) | 2021-09-08 | Submittal Number: 10 14 00-32.0 From: NICK NOWOJ Final Due Date: 08/31/21 Subject: KRAKEN RUM SIGN SHOP DRAWINGS Description: KRAKEN RUM BAR SIGN SHOP DRAWINGS Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18698 | Forwarded | For Review | 2021-08-26 | Josh Dobken (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); Byron Noll (CAA ICON / Strategy Advisory) | 2021-09-02 | Submittal Number: 10 14 00-32.0 From: NICK NOWOJ Final Due Date: 08/31/21 Subject: KRAKEN RUM SIGN SHOP DRAWINGS Description: KRAKEN RUM BAR SIGN SHOP DRAWINGS Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18812 | Responded and Closed | Not Required For Review | 2021-09-08 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Scope is Owner directed | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-08-25 02:00 |  | 10 14 00-32.0 Kraken rum sign shop drawings.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-09-08 |  | 10 14 00-32.0 Kraken rum sign shop drawings_POP.pdf
10 14 00-033-00 | 10 14 00 | 10 14 00-033-00 Kraken Rum Bar Sign Structural Calculations | Closed | Graphics/Signage, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-31 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-09-17 | 2021-09-16 | 17 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-09-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14557 | Received | For Review | 2021-08-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-17 | Submittal Number: 10 14 00-33.0 From: NICK NOWOJ Final Due Date: 09/14/21 Subject: KRAKEN RUM BAR SIGN STRUCTURAL CALCULATIONS Description: STRUCTURAL CALCULATIONS FOR KRAKEN RUM BAR SIGN Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 18802 | Forwarded | For Review | 2021-09-07 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-09-14 | Submittal Number: 10 14 00-33.0 From: NICK NOWOJ Final Due Date: 09/14/21 Subject: KRAKEN RUM BAR SIGN STRUCTURAL CALCULATIONS Description: STRUCTURAL CALCULATIONS FOR KRAKEN RUM BAR SIGN Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 14636 | Review Response | Approved as Noted | 2021-09-13 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Calcs missing for connection angle between panel support system and TT-designed back-up structure. Please submit these calcs for record. | Info Exchange
| 14659 | Review Response | Approved as Noted | 2021-09-16 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to engineer's comments. Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Calcs missing for connection angle between panel support system and TT-designed back-up structure. Please submit these calcs for record. | Info Exchange
| 18904 | Responded and Closed | Approved as Noted | 2021-09-16 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to engineer's comments. Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Calcs missing for connection angle between panel support system and TT-designed back-up structure. Please submit these calcs for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2021-09-03 |  | 10 14 00-33.0 Kraken rum sign structural calculations.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-09-03 |  | 10 14 00-33.0 Kraken rum sign structural calculations.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-13 |  | 10 14 00-33.0 Kraken rum sign structural calculations_TT.pdf
10 14 00-033-01 | 10 14 00 | 10 14 00-033-01 Kraken Rum Bar Sign Structural Calculations | Open - Overdue | Structural, Graphics/Signage, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-29 | Review Response - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen | 2021-10-05 | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  | 2021-10-13 |  | 9 |  | Record Copies; Transfers; Submittals |  | 2
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14746 | Received | For Review | 2021-09-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-10-13 | Submittal Number: 10 14 00-33.1 From: NICK NOWOJ Final Due Date: 10/12/21 Subject: KRAKEN RUM BAR SIGN STRUCTURAL CALCULATIONS Description: STRUCTURAL CALCULATIONS FOR KRAKEN RUM BAR SIGN Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 19014 | Forwarded | For Review | 2021-09-28 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-10-05 | Submittal Number: 10 14 00-33.1 From: NICK NOWOJ Final Due Date: 10/12/21 Subject: KRAKEN RUM BAR SIGN STRUCTURAL CALCULATIONS Description: STRUCTURAL CALCULATIONS FOR KRAKEN RUM BAR SIGN Spec Section: 10 14 00 - SIGNAGE Status: OPEN | Info Exchange
| 14748 | Review Response | Approved | 2021-09-29 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2021-09-28 |  | 10 14 00-33.1 Kraken rum sign structural calculations rev1.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-09-28 |  | 10 14 00-33.1 Kraken rum sign structural calculations rev1.pdf
10 21 13.15-001-00 | 10 21 13.15 - STAINLESS-STEEL TOILET COMPARTMENTS | 10 21 13.15-001-00 Toilet, Bath, and Laundry Accessories - TA87 Product Data & Product Schedule | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-09 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-23 | 2021-03-17 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11872 | Received | For Review | 2021-03-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-03-23 | Submittal Number: 10 21 13-1.0 From: DANIELLE SCOTT Final Due Date: 03/22/21 Subject: TOILET, BATH, AND LAUNDRY ACCESSORIES - TA87 PRODUCT DATA & PRODUCT SCHEDULE Description: Spec Section: 10 21 13 - TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 15388 | Forwarded | For Review | 2021-03-09 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-16 | Submittal Number: 10 21 13-1.0 From: DANIELLE SCOTT Final Due Date: 03/22/21 Subject: TOILET, BATH, AND LAUNDRY ACCESSORIES - TA87 PRODUCT DATA & PRODUCT SCHEDULE Description: Spec Section: 10 21 13 - TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 15637 | Responded and Closed | Approved | 2021-03-17 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-08 |  | 10 21 13-1 Revision 0 Toilet Bath and Laundry Accessories - TA87 Product Data & Product Schedule.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-08 |  | 10 21 13-1 Revision 0 Toilet Bath and Laundry Accessories - TA87 Product Data & Product Schedule.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-17 |  | 10 21 13-1 Revision 0 Toilet Bath and Laundry Accessories - TA87 Product Data & Product Schedule_POP.pdf
10 21 13.15-002-00 | 10 21 13.15 - STAINLESS-STEEL TOILET COMPARTMENTS | 10 21 13.15-002-00 STAINLESS-STEEL TOILET COMPARTMENTS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-06 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-20 | 2021-04-15 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12429 | Received | For Review | 2021-04-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-20 | Submittal Number: 10 21 13.15-2.0 From: KIM DOWALIBY Final Due Date: 04/20/21 Subject: STAINLESS-STEEL TOILET COMPARTMENTS - PRODUCT DATA Description: PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 10 21 13.15 - STAINLESS STEEL TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 16107 | Forwarded | For Review | 2021-04-06 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-13 | Submittal Number: 10 21 13.15-2.0 From: KIM DOWALIBY Final Due Date: 04/20/21 Subject: STAINLESS-STEEL TOILET COMPARTMENTS - PRODUCT DATA Description: PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 10 21 13.15 - STAINLESS STEEL TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 16323 | Responded and Closed | Approved | 2021-04-15 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-06 |  | 10 21 13.15-2 Stainless Steel Toilet Compartment - Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-06 |  | 10 21 13.15-2 Stainless Steel Toilet Compartment - Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-15 |  | 10 21 13.15-2 Stainless Steel Toilet Compartment - Product Data_POP.pdf
10 21 13.15-003-00 | 10 21 13.15 - STAINLESS-STEEL TOILET COMPARTMENTS | 10 21 13.15-003-00 STAINLESS-STEEL TOILET COMPARTMENTS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-21 | 2020-12-18 | 12 |  | Record Copies; Transfers; Submittals | 10 21 13.15-003-00-01 - 10 21 13.15-003-00 STAINLESS-STEEL TOILET COMPARTMENTS - Shop Drawings | 12 |  | 2020-12-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09934 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-21 | Submittal Number: 10 21 13.15-3.0 From: DANIELLE SCOTT Final Due Date: 12/18/20 Subject: STAINLESS-STEEL TOILET COMPARTMENTS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR TOILET COMPARTMENTS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENT DETAILS. 2. SHOW LOCATIONS OF CUTOUTS FOR COMPARTMENT-MOUNTED TOILET ACCESSORIES. 3. SHOW LOCATIONS OF REINFORCEMENTS FOR COMPARTMENT-MOUNTED GRAB BARS AND LOCATIONS OF BLOCKING FOR SURFACE-MOUNTED TOILET ACCESSORIES. 4. SHOW LOCATIONS OF CENTERLINES OF TOILET FIXTURES. 5. SHOW LOCATIONS OF FLOOR DRAINS. Spec Section: 10 21 13.15 - STAINLESS STEEL TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 13012 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 10 21 13.15-3.0 From: DANIELLE SCOTT Final Due Date: 12/18/20 Subject: STAINLESS-STEEL TOILET COMPARTMENTS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR TOILET COMPARTMENTS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENT DETAILS. 2. SHOW LOCATIONS OF CUTOUTS FOR COMPARTMENT-MOUNTED TOILET ACCESSORIES. 3. SHOW LOCATIONS OF REINFORCEMENTS FOR COMPARTMENT-MOUNTED GRAB BARS AND LOCATIONS OF BLOCKING FOR SURFACE-MOUNTED TOILET ACCESSORIES. 4. SHOW LOCATIONS OF CENTERLINES OF TOILET FIXTURES. 5. SHOW LOCATIONS OF FLOOR DRAINS. Spec Section: 10 21 13.15 - STAINLESS STEEL TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 10251 | Review Response | Revise and Resubmit | 2020-12-18 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13401 | Responded and Closed | Revise and Resubmit | 2020-12-18 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-04 |  | 10 21 13.15-3 STAINLESS-STEEL TOILET COMPARTMENTS - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-04 |  | 10 21 13.15-3 STAINLESS-STEEL TOILET COMPARTMENTS - Shop Drawings.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-18 |  | 10 21 13.15-3 STAINLESS-STEEL TOILET COMPARTMENTS - Shop Drawings_pop.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-12-04 |  | 10 21 13.15-3 STAINLESS-STEEL TOILET COMPARTMENTS - Shop Drawings.pdf
10 21 13.15-003-00-01 | 10 21 13.15 - STAINLESS-STEEL TOILET COMPARTMENTS | 10 21 13.15-003-00 STAINLESS-STEEL TOILET COMPARTMENTS - Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 21 13.15-003-00 - 10 21 13.15-003-00 STAINLESS-STEEL TOILET COMPARTMENTS - Shop Drawings | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-04 |  | 10 21 13.15-3 STAINLESS-STEEL TOILET COMPARTMENTS - Shop Drawings.pdf
10 21 13.15-004-00 | 10 21 13.15 - STAINLESS-STEEL TOILET COMPARTMENTS | 10 21 13.15-004-00 STAINLESS-STEEL TOILET COMPARTMENTS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-12-04 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-12-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09608 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-07 | Submittal Number: 10 21 13.15-4.0 From: DANIELLE SCOTT Final Due Date: 12/03/20 Subject: STAINLESS-STEEL TOILET COMPARTMENTS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS, IN MANUFACTURER'S STANDARD SIZES UNLESS OTHERWISE INDICATED: 1. EACH TYPE OF MATERIAL, COLOR, AND FINISH REQUIRED FOR TOILET COMPARTMENTS, PREPARED ON 6- INCH-SQUARE SAMPLES OF SAME THICKNESS AND MATERIAL INDICATED FOR WORK. 2. EACH TYPE OF HARDWARE AND ACCESSORY. Spec Section: 10 21 13.15 - STAINLESS STEEL TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 12643 | Forwarded | For Review | 2020-11-19 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 10 21 13.15-4.0 From: DANIELLE SCOTT Final Due Date: 12/03/20 Subject: STAINLESS-STEEL TOILET COMPARTMENTS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS, IN MANUFACTURER'S STANDARD SIZES UNLESS OTHERWISE INDICATED: 1. EACH TYPE OF MATERIAL, COLOR, AND FINISH REQUIRED FOR TOILET COMPARTMENTS, PREPARED ON 6- INCH-SQUARE SAMPLES OF SAME THICKNESS AND MATERIAL INDICATED FOR WORK. 2. EACH TYPE OF HARDWARE AND ACCESSORY. Spec Section: 10 21 13.15 - STAINLESS STEEL TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 09921 | Review Response | Approved | 2020-12-04 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13001 | Responded and Closed | Approved | 2020-12-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-19 |  | 10 21 13.15-4 STAINLESS-STEEL TOILET COMPARTMENTS -Samples.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-19 |  | 10 21 13.15-4 STAINLESS-STEEL TOILET COMPARTMENTS -Samples.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-04 |  | 10 21 13.15-4 STAINLESS-STEEL TOILET COMPARTMENTS -Samples_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-19 |  | 10 21 13.15-4 STAINLESS-STEEL TOILET COMPARTMENTS -Samples.pdf
10 21 13.15-007-00 | 10 21 13.15 - STAINLESS-STEEL TOILET COMPARTMENTS | 10 21 13.15-007-00 STAINLESS-STEEL TOILET COMPARTMENTS - Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-04 | 2021-05-04 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12674 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-04 | Submittal Number: 10 21 13.15-7.0 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: STAINLESS-STEEL TOILET COMPARTMENTS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR TOILET COMPARTMENTS TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 10 21 13.15 - STAINLESS STEEL TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 16392 | Forwarded | For Review | 2021-04-20 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 10 21 13.15-7.0 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: STAINLESS-STEEL TOILET COMPARTMENTS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR TOILET COMPARTMENTS TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 10 21 13.15 - STAINLESS STEEL TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 16714 | Responded and Closed | Approved as Noted | 2021-05-04 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Final approval pending submittal of O&M Manuals per specification section 01 78 23. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-19 |  | 10 21 13.15-7 Stainless Steel Toilet Compartment - Maintenance Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-19 |  | 10 21 13.15-7 Stainless Steel Toilet Compartment - Maintenance Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-04 02:00 |  | 10 21 13.15-7 Stainless Steel Toilet Compartment - Maintenance Data_pop.pdf
10 21 13.15-008-00 | 10 21 13.15 - STAINLESS-STEEL TOILET COMPARTMENTS | 10 21 13.15-008-00 Stainless Steel Toilet Compartment Shop Drawings (Base Building & Locker Rooms) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-12 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-26 | 2021-03-23 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11967 | Received | For Review | 2021-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-26 | Submittal Number: 10 21 13.15-8.0 From: DANIELLE SCOTT Final Due Date: 03/22/21 Subject: STAINLESS STEEL TOILET COMPARTMENT SHOP DRAWINGS (BASE BUILDING & LOCKER ROOMS) Description: Spec Section: 10 21 13.15 - STAINLESS STEEL TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 15502 | Forwarded | For Review | 2021-03-12 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-19 | Submittal Number: 10 21 13.15-8.0 From: DANIELLE SCOTT Final Due Date: 03/22/21 Subject: STAINLESS STEEL TOILET COMPARTMENT SHOP DRAWINGS (BASE BUILDING & LOCKER ROOMS) Description: Spec Section: 10 21 13.15 - STAINLESS STEEL TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 12180 | Review Response | Approved as Noted | 2021-03-23 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15766 | Responded and Closed | Approved as Noted | 2021-03-23 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-12 |  | 10 21 13.15-8 Revision 1 Stainless Steel Toilet Compartment Shop Drawings (Base Building & Locker Rooms).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-12 |  | 10 21 13.15-8 Revision 1 Stainless Steel Toilet Compartment Shop Drawings (Base Building & Locker Rooms).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-23 |  | 10 21 13.15-8 Revision 1 Stainless Steel Toilet (Base Building & Locker Rooms)_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-12 |  | 10 21 13.15-8 Revision 1 Stainless Steel Toilet Compartment Shop Drawings (Base Building & Locker Rooms).pdf
10 21 13.17-002-00 | 10 21 13.17 - PHENOLIC-CORE TOILET COMPARTMENTS | 10 21 13.17-002-00 PHENOLIC-CORE TOILET COMPARTMENTS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-04 | 2021-05-04 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12677 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-04 | Submittal Number: 10 21 13.17-2.0 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - PRODUCT DATA Description: PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 16395 | Forwarded | For Review | 2021-04-20 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 10 21 13.17-2.0 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - PRODUCT DATA Description: PRODUCT DATA: FOR RECYCLED CONTENT, INDICATING POSTCONSUMER AND PRECONSUMER RECYCLED CONTENT AND COST. Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 16723 | Responded and Closed | Approved | 2021-05-04 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-19 |  | 0 21 13.17-2 Revision 0 PHENOLIC-CORE TOILET COMPARTMENTS - Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-19 |  | 0 21 13.17-2 Revision 0 PHENOLIC-CORE TOILET COMPARTMENTS - Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-04 |  | 10 21 13.17-2 Revision 0 PHENOLIC-CORE TOILET COMPARTMENTS_POP.pdf
10 21 13.17-003-00 | 10 21 13.17 - PHENOLIC-CORE TOILET COMPARTMENTS | 10 21 13.17-003-00 PHENOLIC-CORE TOILET COMPARTMENTS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-11 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-05 | 2020-12-23 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-12-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10100 | Received | For Review | 2020-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-01-05 | Submittal Number: 10 21 13.17-3.0 From: DANIELLE SCOTT Final Due Date: 12/24/20 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR TOILET COMPARTMENTS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENT DETAILS. 2. SHOW LOCATIONS OF CUTOUTS FOR COMPARTMENT-MOUNTED TOILET ACCESSORIES. 3. SHOW LOCATIONS OF CENTERLINES OF TOILET FIXTURES. 4. SHOW LOCATIONS OF FLOOR DRAINS. 5. SHOW CEILING GRID, CEILING-MOUNTED ITEMS, AND OVERHEAD SUPPORT OR BRACING LOCATIONS. (EXCLUDES WNBA) Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 13202 | Forwarded | For Review | 2020-12-11 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-18 | Submittal Number: 10 21 13.17-3.0 From: DANIELLE SCOTT Final Due Date: 12/24/20 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR TOILET COMPARTMENTS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENT DETAILS. 2. SHOW LOCATIONS OF CUTOUTS FOR COMPARTMENT-MOUNTED TOILET ACCESSORIES. 3. SHOW LOCATIONS OF CENTERLINES OF TOILET FIXTURES. 4. SHOW LOCATIONS OF FLOOR DRAINS. 5. SHOW CEILING GRID, CEILING-MOUNTED ITEMS, AND OVERHEAD SUPPORT OR BRACING LOCATIONS. (EXCLUDES WNBA) Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 13518 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-23 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached comments and resubmit | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-10 |  | 10 21 13.17-4 Phenolic Toliet Compartments - Shop Drawings (excludes WNBA).pdf
| Forwarded |  | Danielle Scott | 1 | 2020-12-10 |  | 10 21 13.17-4 Phenolic Toliet Compartments - Shop Drawings (excludes WNBA).pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-12-23 |  | 10 21 13.17-003-0 Phenolic Toliet Compartments - Shop Drawings (excludes WNBA)_POP.pdf
10 21 13.17-003-01 | 10 21 13.17 - PHENOLIC-CORE TOILET COMPARTMENTS | 10 21 13.17-003-01 Phenolic Shop Drawings - (Base Building & Premium) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-12 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-26 | 2021-03-18 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11966 | Received | For Review | 2021-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-03-26 | Submittal Number: 10 21 13.17-3.1 From: DANIELLE SCOTT Final Due Date: 03/22/21 Subject: PHENOLIC SHOP DRAWINGS - (BASE BUILDING & PREMIUM) Description: SHOP DRAWINGS : FOR TOILET COMPARTMENTS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENT DETAILS. 2. SHOW LOCATIONS OF CUTOUTS FOR COMPARTMENT-MOUNTED TOILET ACCESSORIES. 3. SHOW LOCATIONS OF CENTERLINES OF TOILET FIXTURES. 4. SHOW LOCATIONS OF FLOOR DRAINS. 5. SHOW CEILING GRID, CEILING-MOUNTED ITEMS, AND OVERHEAD SUPPORT OR BRACING LOCATIONS. (EXCLUDES WNBA) Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 15501 | Forwarded | For Review | 2021-03-12 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-19 | Submittal Number: 10 21 13.17-3.1 From: DANIELLE SCOTT Final Due Date: 03/22/21 Subject: PHENOLIC SHOP DRAWINGS - (BASE BUILDING & PREMIUM) Description: SHOP DRAWINGS : FOR TOILET COMPARTMENTS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENT DETAILS. 2. SHOW LOCATIONS OF CUTOUTS FOR COMPARTMENT-MOUNTED TOILET ACCESSORIES. 3. SHOW LOCATIONS OF CENTERLINES OF TOILET FIXTURES. 4. SHOW LOCATIONS OF FLOOR DRAINS. 5. SHOW CEILING GRID, CEILING-MOUNTED ITEMS, AND OVERHEAD SUPPORT OR BRACING LOCATIONS. (EXCLUDES WNBA) Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 15671 | Responded and Closed | Approved as Noted | 2021-03-18 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED 1. FIELD VERIFY ALL DIMENSIONS 2. CM TO COORDINATE ALL ROCKWELL GROUP COMMENTS 3. SUBMIT PARTITION FINISH SAMPLES FOR APPROVAL. 4. SUBMIT ADA AND AMBULATORY STALLS IN 05.18.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-12 |  | 10 21 13.17-3 Revision 1 Phenolic Shop Drawings - (Base Building & Premium).pdf
| Forwarded |  | Danielle Scott | 1 | 2021-03-12 |  | 10 21 13.17-3 Revision 1 Phenolic Shop Drawings - (Base Building & Premium).pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-18 |  | 10 21 13.17-3 Revision 1 Phenolic Shop Drawings - (Base Building & Premium)_POP.pdf
10 21 13.17-004-00 | 10 21 13.17 - PHENOLIC-CORE TOILET COMPARTMENTS | 10 21 13.17-004-00 PHENOLIC-CORE TOILET COMPARTMENTS - Sample for Partitions @ Concourse Restrooms | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-16 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-30 | 2020-09-28 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-09-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08144 | Received | For Review | 2020-09-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-09-30 | Submittal Number: 10 21 13.17-4.0 From: DANIELLE SCOTT Final Due Date: 09/29/20 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - SAMPLE FOR PARTITIONS @ CONCOURSE RESTROOMS Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS, IN MANUFACTURER'S STANDARD SIZES UNLESS OTHERWISE INDICATED: 1. EACH TYPE OF MATERIAL, COLOR, AND FINISH REQUIRED FOR TOILET COMPARTMENTS, PREPARED ON 6- INCH-SQUARE SAMPLES OF SAME THICKNESS AND MATERIAL INDICATED FOR WORK. Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 10817 | Forwarded | For Review | 2020-09-16 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-23 | Submittal Number: 10 21 13.17-4.0 From: DANIELLE SCOTT Final Due Date: 09/29/20 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - SAMPLE FOR PARTITIONS @ CONCOURSE RESTROOMS Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS, IN MANUFACTURER'S STANDARD SIZES UNLESS OTHERWISE INDICATED: 1. EACH TYPE OF MATERIAL, COLOR, AND FINISH REQUIRED FOR TOILET COMPARTMENTS, PREPARED ON 6- INCH-SQUARE SAMPLES OF SAME THICKNESS AND MATERIAL INDICATED FOR WORK. Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 08377 | Review Response | Approved | 2020-09-28 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  |  | Info Exchange
| 11098 | Responded and Closed | Approved | 2020-09-28 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-15 |  | 10 21 13.17-4 PHENOLIC-CORE TOILET COMPARTMENTS - Sample for Partitions @ Concourse Restrooms.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-15 |  | 10 21 13.17-4 PHENOLIC-CORE TOILET COMPARTMENTS - Sample for Partitions @ Concourse Restrooms.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-15 |  | 10 21 13.17-4 PHENOLIC-CORE TOILET COMPARTMENTS - Sample for Partitions @ Concourse Restrooms.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-15 |  | 10 21 13.17-4 PHENOLIC-CORE TOILET COMPARTMENTS - Sample for Partitions @ Concourse Restrooms.pdf
10 21 13.17-005-00 | 10 21 13.17 - PHENOLIC-CORE TOILET COMPARTMENTS | 10 21 13.17-005-00 PHENOLIC-CORE TOILET COMPARTMENTS - Product Schedule | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-23 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-07 | 2021-05-05 | 13 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-05-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12724 | Received | For Review | 2021-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-07 | Submittal Number: 10 21 13.17-5.0 From: KIM DOWALIBY Final Due Date: 05/06/21 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - PRODUCT SCHEDULE Description: PRODUCT SCHEDULE : FOR TOILET COMPARTMENTS, PREPARED BY OR UNDER THE SUPERVISION OF SUPPLIER, DETAILING LOCATION AND SELECTED COLORS FOR TOILET COMPARTMENT MATERIAL. Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 16450 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-29 | Submittal Number: 10 21 13.17-5.0 From: KIM DOWALIBY Final Due Date: 05/06/21 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - PRODUCT SCHEDULE Description: PRODUCT SCHEDULE : FOR TOILET COMPARTMENTS, PREPARED BY OR UNDER THE SUPERVISION OF SUPPLIER, DETAILING LOCATION AND SELECTED COLORS FOR TOILET COMPARTMENT MATERIAL. Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 16761 | Responded and Closed | Approved as Noted | 2021-05-05 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-22 |  | 10 21 13.17-5 PHENOLIC-CORE TOILET COMPARTMENTS - Product Schedule.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-22 |  | 10 21 13.17-5 PHENOLIC-CORE TOILET COMPARTMENTS - Product Schedule.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-05 |  | 10 21 13.17-5 PHENOLIC-CORE TOILET COMPARTMENTS - Product Schedule_POP.pdf
10 21 13.17-007-00 | 10 21 13.17 - PHENOLIC-CORE TOILET COMPARTMENTS | 10 21 13.17-007-00 PHENOLIC-CORE TOILET COMPARTMENTS - Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-04 | 2021-05-04 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12676 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-04 | Submittal Number: 10 21 13.17-7.0 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR TOILET COMPARTMENTS TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 16394 | Forwarded | For Review | 2021-04-20 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 10 21 13.17-7.0 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR TOILET COMPARTMENTS TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 16726 | Responded and Closed | Approved as Noted | 2021-05-04 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-19 |  | 0 21 13.17-7 PHENOLIC-CORE TOILET COMPARTMENTS - Maintenance Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-19 |  | 0 21 13.17-7 PHENOLIC-CORE TOILET COMPARTMENTS - Maintenance Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-04 |  | 0 21 13.17-7 PHENOLIC-CORE TOILET COMPARTMENTS - Maintenance Data_POP.pdf
10 21 13.17-009-00 | 10 21 13.17 - PHENOLIC-CORE TOILET COMPARTMENTS | 10 21 13.17-009-00 PHENOLIC-CORE TOILET COMPARTMENTS - Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-16 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-30 | 2021-03-17 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12047 | Received | For Review | 2021-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-03-30 | Submittal Number: 10 21 13.17-9.0 From: DANIELLE SCOTT Final Due Date: 03/29/21 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - WARRANTY Description: WARRANTY : 10-YEAR, LIMITED COMMERCIAL WARRANTY. Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 15596 | Forwarded | For Review | 2021-03-16 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-23 | Submittal Number: 10 21 13.17-9.0 From: DANIELLE SCOTT Final Due Date: 03/29/21 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - WARRANTY Description: WARRANTY : 10-YEAR, LIMITED COMMERCIAL WARRANTY. Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 15639 | Responded and Closed | Approved | 2021-03-17 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-15 |  | 0 21 13.17-9 Revision 0 PHENOLIC-CORE TOILET COMPARTMENTS - Warranty.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-15 |  | 0 21 13.17-9 Revision 0 PHENOLIC-CORE TOILET COMPARTMENTS - Warranty.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-17 |  | 10 21 13.17-9 Revision 0 PHENOLIC-CORE TOILET COMPARTMENTS - Warranty_POP.pdf
10 21 13.17-010-00 | 10 21 13.17 - PHENOLIC-CORE TOILET COMPARTMENTS | 10 21 13.17-010-00 PHENOLIC-CORE TOILET COMPARTMENTS - Mockup Shop Drawings Rooms 03.35.03 & 03.35.02 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-08 07:00 | 2020-09-08 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07683 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-08 07:00 | Submittal Number: 10 21 13.17-10.0 From: DANIELLE SCOTT Final Due Date: 09/04/20 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - MOCKUP SHOP DRAWINGS ROOMS 03.35.03 & 03.35.02 Description: SHOP DRAWINGS FOR MOCKUP LOCATIONS ONLY. SHOP DRAWINGS : FOR TOILET COMPARTMENTS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENT DETAILS. 2. SHOW LOCATIONS OF CUTOUTS FOR COMPARTMENT-MOUNTED TOILET ACCESSORIES. EXCLUDED - NO CUTOUTS 3. SHOW LOCATIONS OF CENTERLINES OF TOILET FIXTURES. 4. SHOW LOCATIONS OF FLOOR DRAINS. 5. SHOW CEILING GRID, CEILING-MOUNTED ITEMS, AND OVERHEAD SUPPORT OR BRACING LOCATIONS. EXCLUDED - NOT MOUNTED OVERHEAD Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 10229 | Forwarded | For Review | 2020-08-24 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-31 | Submittal Number: 10 21 13.17-10.0 From: DANIELLE SCOTT Final Due Date: 09/04/20 Subject: PHENOLIC-CORE TOILET COMPARTMENTS - MOCKUP SHOP DRAWINGS ROOMS 03.35.03 & 03.35.02 Description: SHOP DRAWINGS FOR MOCKUP LOCATIONS ONLY. SHOP DRAWINGS : FOR TOILET COMPARTMENTS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENT DETAILS. 2. SHOW LOCATIONS OF CUTOUTS FOR COMPARTMENT-MOUNTED TOILET ACCESSORIES. EXCLUDED - NO CUTOUTS 3. SHOW LOCATIONS OF CENTERLINES OF TOILET FIXTURES. 4. SHOW LOCATIONS OF FLOOR DRAINS. 5. SHOW CEILING GRID, CEILING-MOUNTED ITEMS, AND OVERHEAD SUPPORT OR BRACING LOCATIONS. EXCLUDED - NOT MOUNTED OVERHEAD Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 07974 | Review Response | Approved as Noted | 2020-09-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 10604 | Responded and Closed | Approved as Noted | 2020-09-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-21 |  | 10 21 13.17-10 PHENOLIC-CORE TOILET COMPARTMENTS - Mockup Shop Drawings Rooms 03.35.03 & 03.35.02.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-21 |  | 10 21 13.17-10 PHENOLIC-CORE TOILET COMPARTMENTS - Mockup Shop Drawings Rooms 03.35.03 & 03.35.02.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-08 |  | 10 21 13.17-10 PHENOLIC TOILET COMP - Mockup Shop Drawings Rooms 03.35.03 & 03.35.02_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-21 |  | 10 21 13.17-10 PHENOLIC-CORE TOILET COMPARTMENTS - Mockup Shop Drawings Rooms 03.35.03 & 03.35.02.pdf
10 21 13.17-011-00 | 10 21 13.17 - PHENOLIC-CORE TOILET COMPARTMENTS | 10 21 13.17-011-00 Premium Space Phenolic Partition Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-11 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-25 | 2021-02-25 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11334 | Received | For Review | 2021-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-02-25 | Submittal Number: 10 21 13.17-11.0 From: DANIELLE SCOTT Final Due Date: 02/24/21 Subject: PREMIUM SPACE PHENOLIC PARTITION SAMPLE Description: Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 14693 | Forwarded | For Review | 2021-02-11 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-18 | Submittal Number: 10 21 13.17-11.0 From: DANIELLE SCOTT Final Due Date: 02/24/21 Subject: PREMIUM SPACE PHENOLIC PARTITION SAMPLE Description: Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 11662 | Review Response | Approved as Noted | 2021-02-25 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. Confirm finish with Rockwell Group. | Info Exchange
| 15113 | Responded and Closed | Approved as Noted | 2021-02-25 | Danielle Scott | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. Confirm finish with Rockwell Group. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-10 |  | 10 21 13.17-11 Revision 0 Premium Space Phenolic Partition Sample.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-02-10 |  | 10 21 13.17-11 Revision 0 Premium Space Phenolic Partition Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-25 |  | 10 21 13.17-11 Revision 0 Premium Space Phenolic Partition Sample_POP.pdf
| Responded and Closed |  | Danielle Scott | 1 | 2021-02-10 |  | 10 21 13.17-11 Revision 0 Premium Space Phenolic Partition Sample.pdf
10 21 13.17-012-00 | 10 21 13.17 - PHENOLIC-CORE TOILET COMPARTMENTS | 10 21 13.17-012-00 Phenolic Toilet Compartment - Suite Level Area D and C Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-23 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2021-03-09 | 2021-03-09 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11623 | Received | For Review | 2021-02-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-03-09 | Submittal Number: 10 21 13.17-12.0 From: DANIELLE SCOTT Final Due Date: 03/09/21 Subject: PHENOLIC TOILET COMPARTMENT - SUITE LEVEL AREA D AND C SHOP DRAWINGS Description: SUITE LEVEL SHOP DRAWINGS Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 15064 | Forwarded | For Review | 2021-02-24 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Kuebler Perry (Populous); Chad Francis (Populous) | 2021-03-03 | Submittal Number: 10 21 13.17-12.0 From: DANIELLE SCOTT Final Due Date: 03/09/21 Subject: PHENOLIC TOILET COMPARTMENT - SUITE LEVEL AREA D AND C SHOP DRAWINGS Description: SUITE LEVEL SHOP DRAWINGS Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 15405 | Responded and Closed | Approved as Noted | 2021-03-09 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS 1. FIELD VERIY ALL DIMENSIONS, TOILETS TO BE CENTERED IN STALL, RE: A0-05 TOILET LAYOUT TYPES 2. SUBMIT FINISH SAMPLES FOR REVIEW/APPROVAL | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-23 02:00 |  | 10 21 13.17-12 Revision 0 Phenolic Toilet Compartment - Shop Drawings.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-02-23 02:00 |  | 10 21 13.17-12 Revision 0 Phenolic Toilet Compartment - Shop Drawings.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-09 |  | 10 21 13.17-012-00 Phenolic Toilet Compartment - SD_POP.pdf
10 21 13.17-013-00 | 10 21 13.17 - PHENOLIC-CORE TOILET COMPARTMENTS | 10 21 13.17-013-00 Phenolic Shop Drawings - WNBA | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-13 | 9 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12369 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 10 21 13.17-13.0 From: DANIELLE SCOTT Final Due Date: 04/09/21 Subject: PHENOLIC SHOP DRAWINGS - WNBA Description: Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 16025 | Forwarded | For Review | 2021-04-01 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 10 21 13.17-13.0 From: DANIELLE SCOTT Final Due Date: 04/09/21 Subject: PHENOLIC SHOP DRAWINGS - WNBA Description: Spec Section: 10 21 13.17 - PHENOLIC-CORE TOILET PARTITIONS Status: OPEN | Info Exchange
| 16271 | Responded and Closed | Approved | 2021-04-13 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 10 21 13.17-13 Revision 0 - Phenolic Shop Drawings - WNBA.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 10 21 13.17-13 Revision 0 - Phenolic Shop Drawings - WNBA.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-13 |  | 10 21 13.17-13 Revision 0 - Phenolic Shop Drawings - WNBA_POP.pdf
10 21 13-001-01 | 10 21 13.15 - STAINLESS-STEEL TOILET COMPARTMENTS | 10 21 13-001-01 Toilet, Bath, and Laundry Accessories - TA87 Product Data & Product Schedule | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-24 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-07 | 2021-03-26 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12209 | Received | For Review | 2021-03-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-07 | Submittal Number: 10 21 13-1.1 From: KIM DOWALIBY Final Due Date: 04/07/21 Subject: TOILET, BATH, AND LAUNDRY ACCESSORIES - TA87 PRODUCT DATA & PRODUCT SCHEDULE Description: Spec Section: 10 21 13 - TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 15798 | Forwarded | For Review | 2021-03-24 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-31 | Submittal Number: 10 21 13-1.1 From: KIM DOWALIBY Final Due Date: 04/07/21 Subject: TOILET, BATH, AND LAUNDRY ACCESSORIES - TA87 PRODUCT DATA & PRODUCT SCHEDULE Description: Spec Section: 10 21 13 - TOILET COMPARTMENTS Status: OPEN | Info Exchange
| 15885 | Responded and Closed | Approved as Noted | 2021-03-26 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached. 1. This is a Mortenson directed substitution and is approved for all TA87 locations | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-24 |  | 10 21 13-1.1 Revision 0 Toilet Bath and Laundry Accessories - TA87 Product Data & Product Schedule Rev 1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-24 |  | 10 21 13-1.1 Revision 0 Toilet Bath and Laundry Accessories - TA87 Product Data & Product Schedule Rev 1.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-26 |  | 10 21 13-1.1 Revision 0 Toilet Bath and Laundry Accessories - TA87 Product Data & Product Schedule Rev 1_POP.pdf
10 22 39-002-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-002-00 FOLDING PANEL PARTITIONS - Product Data, Warranty, & Test Reports | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-21 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-04 | 2021-01-29 | 9 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-01-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10842 | Received | For Review | 2021-01-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-04 | Submittal Number: 10 22 39-2.0 From: DANIELLE SCOTT Final Due Date: 02/01/21 Subject: FOLDING PANEL PARTITIONS - PRODUCT DATA, WARRANTY, & TEST REPORTS Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. WARRANTY TEST REPORTS Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 14085 | Forwarded | For Review | 2021-01-20 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-27 | Submittal Number: 10 22 39-2.0 From: DANIELLE SCOTT Final Due Date: 02/01/21 Subject: FOLDING PANEL PARTITIONS - PRODUCT DATA, WARRANTY, & TEST REPORTS Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. WARRANTY TEST REPORTS Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 14345 | Responded and Closed | Approved | 2021-01-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-20 |  | 10 22 39 - 2 Folding Panel Partition Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-20 |  | 10 22 39 - 2 Folding Panel Partition Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-29 |  | 10 22 39 - 2 Folding Panel Partition Product Data_POP.pdf
10 22 39-007-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-007-00 FOLDING PANEL PARTITIONS - Shop Drawings (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-21 | 2020-12-21 | 15 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-12-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09926 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-21 | Submittal Number: 10 22 39-7.0 From: DANIELLE SCOTT Final Due Date: 12/18/20 Subject: FOLDING PANEL PARTITIONS - SHOP DRAWINGS (BASE BUILDING) Description: SHOP DRAWINGS : FOR OPERABLE PANEL PARTITIONS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, NUMBERED PANEL INSTALLATION SEQUENCE, AND ATTACHMENTS TO OTHER WORK. 2. INDICATE STACKING AND OPERATING CLEARANCES. INDICATE LOCATION AND INSTALLATION REQUIREMENTS FOR HARDWARE AND TRACK, BLOCKING, AND DIRECTION OF TRAVEL. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 13005 | Forwarded | For Review | 2020-12-04 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-11 | Submittal Number: 10 22 39-7.0 From: DANIELLE SCOTT Final Due Date: 12/18/20 Subject: FOLDING PANEL PARTITIONS - SHOP DRAWINGS (BASE BUILDING) Description: SHOP DRAWINGS : FOR OPERABLE PANEL PARTITIONS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, NUMBERED PANEL INSTALLATION SEQUENCE, AND ATTACHMENTS TO OTHER WORK. 2. INDICATE STACKING AND OPERATING CLEARANCES. INDICATE LOCATION AND INSTALLATION REQUIREMENTS FOR HARDWARE AND TRACK, BLOCKING, AND DIRECTION OF TRAVEL. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 13448 | Responded and Closed | Approved as Noted | 2020-12-21 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-04 |  | 10 22 39-7 Folding Panel Partitions - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-04 |  | 10 22 39-7 Folding Panel Partitions - Shop Drawings.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-12-21 |  | 10 22 39-7 Folding Panel Partitions - Shop Drawings_POP.pdf
10 22 39-008-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-008-00 FOLDING PANEL PARTITIONS - Samples for MAARS Living Wall & Hufcor Partition | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-08 | 2021-02-16 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2021-02-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10924 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-08 | Submittal Number: 10 22 39-8.0 From: DANIELLE SCOTT Final Due Date: 02/05/21 Subject: FOLDING PANEL PARTITIONS - SAMPLES FOR MAARS LIVING WALL & HUFCOR PARTITION Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED MATERIAL, FINISH, COVERING, OR FACING, PREPARED ON SAMPLES OF SIZE INDICATED BELOW: 1. PANEL FACING MATERIAL: MANUFACTURER'S STANDARD-SIZE UNIT, NOT LESS THAN 3 INCHES SQUARE. 2. PANEL EDGE MATERIAL: NOT LESS THAN 3 INCHES LONG. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 14184 | Forwarded | For Review | 2021-01-25 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-01 | Submittal Number: 10 22 39-8.0 From: DANIELLE SCOTT Final Due Date: 02/05/21 Subject: FOLDING PANEL PARTITIONS - SAMPLES FOR MAARS LIVING WALL & HUFCOR PARTITION Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF EXPOSED MATERIAL, FINISH, COVERING, OR FACING, PREPARED ON SAMPLES OF SIZE INDICATED BELOW: 1. PANEL FACING MATERIAL: MANUFACTURER'S STANDARD-SIZE UNIT, NOT LESS THAN 3 INCHES SQUARE. 2. PANEL EDGE MATERIAL: NOT LESS THAN 3 INCHES LONG. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 11445 | Review Response | Approved as Noted | 2021-02-16 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. Rockwell to select for Owner's suite partitions. | Info Exchange
| 14827 | Responded and Closed | Approved as Noted | 2021-02-16 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. Rockwell to select for Owner's suite partitions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-22 |  | 10 22 39-8 Revision 0 FOLDING PANEL PARTITIONS - Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-22 |  | 10 22 39-8 Revision 0 FOLDING PANEL PARTITIONS - Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-16 |  | 10 22 39-8 Revision 0 FOLDING PANEL PARTITIONS - Samples_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-22 |  | 10 22 39-8 Revision 0 FOLDING PANEL PARTITIONS - Samples.pdf
10 22 39-009-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-009-00 FOLDING PANEL PARTITIONS - Delegated-Design Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-21 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-04 | 2021-02-16 | 27 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2021-02-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10872 | Received | For Review | 2021-01-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-04 | Submittal Number: 10 22 39-9.0 From: DANIELLE SCOTT Final Due Date: 02/03/21 Subject: FOLDING PANEL PARTITIONS - DELEGATED-DESIGN SUBMITTAL Description: DELEGATED-DESIGN SUBMITTAL : FOR OPERABLE PANEL PARTITIONS. 1. INCLUDE DESIGN CALCULATIONS FOR SEISMIC RESTRAINTS. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 14113 | Forwarded | For Review | 2021-01-21 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-28 | Submittal Number: 10 22 39-9.0 From: DANIELLE SCOTT Final Due Date: 02/03/21 Subject: FOLDING PANEL PARTITIONS - DELEGATED-DESIGN SUBMITTAL Description: DELEGATED-DESIGN SUBMITTAL : FOR OPERABLE PANEL PARTITIONS. 1. INCLUDE DESIGN CALCULATIONS FOR SEISMIC RESTRAINTS. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 14346 | Forwarded | For Review | 2021-01-29 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) | 2021-02-04 | Submittal Number: 10 22 39-9.0 From: DANIELLE SCOTT Final Due Date: 02/03/21 Subject: FOLDING PANEL PARTITIONS - DELEGATED-DESIGN SUBMITTAL Description: DELEGATED-DESIGN SUBMITTAL : FOR OPERABLE PANEL PARTITIONS. 1. INCLUDE DESIGN CALCULATIONS FOR SEISMIC RESTRAINTS. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 14758 | Forwarded | For Review | 2021-02-12 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-02-04 | Submittal Number: 10 22 39-9.0 From: DANIELLE SCOTT Final Due Date: 02/03/21 Subject: FOLDING PANEL PARTITIONS - DELEGATED-DESIGN SUBMITTAL Description: DELEGATED-DESIGN SUBMITTAL : FOR OPERABLE PANEL PARTITIONS. 1. INCLUDE DESIGN CALCULATIONS FOR SEISMIC RESTRAINTS. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 11446 | Review Response | Approved as Noted | 2021-02-16 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Arch to advise on seismic kickers as noted by TT. | Info Exchange
| 14828 | Responded and Closed | Approved as Noted | 2021-02-16 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-20 |  | 10 22 39 - 9 12 Delegated Design Submittals and Seismic Qualification Certificates.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-20 |  | 10 22 39 - 9 12 Delegated Design Submittals and Seismic Qualification Certificates.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-20 |  | 10 22 39 - 9 12 Delegated Design Submittals and Seismic Qualification Certificates.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-20 |  | 10 22 39 - 9 12 Delegated Design Submittals and Seismic Qualification Certificates.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-20 |  | 10 22 39 - 9 12 Delegated Design Submittals and Seismic Qualification Certificates.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-20 |  | 10 22 39 - 9 12 Delegated Design Submittals and Seismic Qualification Certificates.pdf
10 22 39-015-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-015-00 FOLDING PANEL PARTITIONS - O&M Manuals | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-21 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-04 | 2021-02-05 | 16 |  | Record Copies; Transfers; Submittals | 10 22 39-015-00-01 - 10 22 39-015-00 FOLDING PANEL PARTITIONS - O&M Manuals | 17 |  | 2021-02-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10843 | Received | For Review | 2021-01-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-04 | Submittal Number: 10 22 39-15.0 From: DANIELLE SCOTT Final Due Date: 02/03/21 Subject: FOLDING PANEL PARTITIONS - O&M MANUALS Description: OPERATION AND MAINTENANCE DATA : FOR OPERABLE PANEL PARTITIONS TO INCLUDE IN MAINTENANCE MANUALS. 1. IN ADDITION TO ITEMS SPECIFIED IN SECTION 01 78 23 "OPERATION AND MAINTENANCE DATA," INCLUDE THE FOLLOWING: A. PANEL FINISH FACINGS AND FINISHES FOR EXPOSED TRIM AND ACCESSORIES. INCLUDE PRECAUTIONS FOR CLEANING MATERIALS AND METHODS THAT COULD BE DETRIMENTAL TO FINISHES AND PERFORMANCE. B. SEALS, HARDWARE, TRACK, TRACK SWITCHES, CARRIERS, AND OTHER OPERATING COMPONENTS. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 14086 | Forwarded | For Review | 2021-01-20 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-27 | Submittal Number: 10 22 39-15.0 From: DANIELLE SCOTT Final Due Date: 02/03/21 Subject: FOLDING PANEL PARTITIONS - O&M MANUALS Description: OPERATION AND MAINTENANCE DATA : FOR OPERABLE PANEL PARTITIONS TO INCLUDE IN MAINTENANCE MANUALS. 1. IN ADDITION TO ITEMS SPECIFIED IN SECTION 01 78 23 "OPERATION AND MAINTENANCE DATA," INCLUDE THE FOLLOWING: A. PANEL FINISH FACINGS AND FINISHES FOR EXPOSED TRIM AND ACCESSORIES. INCLUDE PRECAUTIONS FOR CLEANING MATERIALS AND METHODS THAT COULD BE DETRIMENTAL TO FINISHES AND PERFORMANCE. B. SEALS, HARDWARE, TRACK, TRACK SWITCHES, CARRIERS, AND OTHER OPERATING COMPONENTS. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 14529 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. SUBMIT ITEMS LISTED IN 10 22 39-A-1A AND B 2. RESUBMIT IN FINAL MANUAL SUBMITTAL PER 01 78 23-1.4- D | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-20 |  | 10 22 39-15 Folding Panel Partition O and M Manuals (002).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-20 |  | 10 22 39-15 Folding Panel Partition O and M Manuals (002).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-05 |  | 10 22 39-15 Folding Panel Partition O and M Manuals (002)_POP.pdf
10 22 39-015-00-01 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-015-00 FOLDING PANEL PARTITIONS - O&M Manuals | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 22 39-015-00 - 10 22 39-015-00 FOLDING PANEL PARTITIONS - O&M Manuals | -1 | 2021-02-19
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-05 |  | 10 22 39-15 Folding Panel Partition O and M Manuals (002)_POP.pdf
10 22 39-018-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-018-00 Folding Panel Partition Sample for Initial Selection | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-11-30 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-11-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09567 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-07 | Submittal Number: 10 22 39-18.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: FOLDING PANEL PARTITION SAMPLE FOR INITIAL SELECTION Description: SAMPLES FOR INITIAL SELECTION: FOR EACH TYPE OF EXPOSED MATERIAL, FINISH, COVERING, OR FACING. 1. INCLUDE SAMPLES OF ACCESSORIES INVOLVING COLOR SELECTION Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 12595 | Forwarded | For Review | 2020-11-19 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 10 22 39-18.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: FOLDING PANEL PARTITION SAMPLE FOR INITIAL SELECTION Description: SAMPLES FOR INITIAL SELECTION: FOR EACH TYPE OF EXPOSED MATERIAL, FINISH, COVERING, OR FACING. 1. INCLUDE SAMPLES OF ACCESSORIES INVOLVING COLOR SELECTION Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 12839 | Responded and Closed | Revise and Resubmit | 2020-11-30 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  | Not enough information submitted. Provide this information as part of product data for submission. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 10 22 39-18 Folding Panel Partitions - Sample for Initial Selection.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 10 22 39-18 Folding Panel Partitions - Sample for Initial Selection.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-30 02:00 |  | 10 22 39-18 Folding Panel Partitions - Sample for Initial Selection_POP.pdf
10 22 39-018-01 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-018-01 Folding Panel Partition Sample for Initial Selection (Event Level) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-03 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-17 | 2020-12-08 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-12-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09862 | Received | For Review | 2020-12-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-17 | Submittal Number: 10 22 39-18.1 From: DANIELLE SCOTT Final Due Date: 12/04/20 Subject: FOLDING PANEL PARTITION SAMPLE FOR INITIAL SELECTION (EVENT LEVEL) Description: SAMPLES FOR INITIAL SELECTION: FOR EACH TYPE OF EXPOSED MATERIAL, FINISH, COVERING, OR FACING. 1. INCLUDE SAMPLES OF ACCESSORIES INVOLVING COLOR SELECTION NOTE: THE WALL COVERING IS SHOWN AS PLAM, BUT A SPECIFIC FINISH IS NOT CALLED OUT. PLEASE SPECIFY THE DESIRED PLAM FINISH. PHYSICAL COLOR CHARTS WERE MAILED ON 11/19. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 12945 | Forwarded | For Review | 2020-12-03 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-10 | Submittal Number: 10 22 39-18.1 From: DANIELLE SCOTT Final Due Date: 12/04/20 Subject: FOLDING PANEL PARTITION SAMPLE FOR INITIAL SELECTION (EVENT LEVEL) Description: SAMPLES FOR INITIAL SELECTION: FOR EACH TYPE OF EXPOSED MATERIAL, FINISH, COVERING, OR FACING. 1. INCLUDE SAMPLES OF ACCESSORIES INVOLVING COLOR SELECTION NOTE: THE WALL COVERING IS SHOWN AS PLAM, BUT A SPECIFIC FINISH IS NOT CALLED OUT. PLEASE SPECIFY THE DESIRED PLAM FINISH. PHYSICAL COLOR CHARTS WERE MAILED ON 11/19. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 10005 | Review Response | Approved | 2020-12-08 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13096 | Responded and Closed | Approved | 2020-12-08 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-02 |  | 10 22 39-18 R1 Folding Panel Partitions - Sample for Initial Selection.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-02 |  | 10 22 39-18 R1 Folding Panel Partitions - Sample for Initial Selection.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-08 |  | 10 22 39-18 R1 Folding Panel Partitions - Sample for Initial Selection_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-12-02 |  | 10 22 39-18 R1 Folding Panel Partitions - Sample for Initial Selection.pdf
10 22 39-019-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-019-00 Folding Panel & Demountable Partitions Shop Drawings - Owner's Suite | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-26 08:00 | 2021-01-26 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-01-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10594 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-01-26 08:00 | Submittal Number: 10 22 39-19.0 From: DANIELLE SCOTT Final Due Date: 01/25/21 Subject: FOLDING PANEL & DEMOUNTABLE PARTITIONS SHOP DRAWINGS - OWNER'S SUITE Description: FOLDING PANEL & DEMOUNTABLE PARTITIONS SHOP DRAWINGS - OWNER'S SUITE Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 13798 | Forwarded | For Review | 2021-01-11 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-18 | Submittal Number: 10 22 39-19.0 From: DANIELLE SCOTT Final Due Date: 01/25/21 Subject: FOLDING PANEL & DEMOUNTABLE PARTITIONS SHOP DRAWINGS - OWNER'S SUITE Description: FOLDING PANEL & DEMOUNTABLE PARTITIONS SHOP DRAWINGS - OWNER'S SUITE Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 14245 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-26 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. SEE ATTACHED COMMENTS 2. COORDINATE ROCKWELL REVIEW COMMENTS. 3. SUBMIT ALL TRIM COLORS WITH CUSTOM COLOR AVAILABILITY FOR ROCKWELL TO SELECT. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 10 22 39-19 Folding Panel & Demountable Partitions - Shop Drawings Owners Suite.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-01-11 |  | 10 22 39-19 Folding Panel & Demountable Partitions - Shop Drawings Owners Suite.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-26 |  | 10 22 39-19 Folding Panel & Demountable Partitions - Shop Drawings Owners Suite_POP.pdf
10 22 39-019-01 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-019-01 Demountable Partitions Shop Drawings - Owner's Suite | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 | 2021-04-14 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-04-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12466 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-22 | Submittal Number: 10 22 39-19.1 From: KIM DOWALIBY Final Due Date: 04/15/21 Subject: DEMOUNTABLE PARTITIONS SHOP DRAWINGS - OWNER'S SUITE Description: FOLDING PANEL & DEMOUNTABLE PARTITIONS SHOP DRAWINGS - OWNER'S SUITE Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 16156 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 10 22 39-19.1 From: KIM DOWALIBY Final Due Date: 04/15/21 Subject: DEMOUNTABLE PARTITIONS SHOP DRAWINGS - OWNER'S SUITE Description: FOLDING PANEL & DEMOUNTABLE PARTITIONS SHOP DRAWINGS - OWNER'S SUITE Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 16290 | Responded and Closed | Approved as Noted | 2021-04-14 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 10 22 39-19.1 - Demountable Partitions - Shop Drawings Owners Suite Rev 1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 10 22 39-19.1 - Demountable Partitions - Shop Drawings Owners Suite Rev 1.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-14 |  | 10 22 39-19.1 - Demountable Partitions - Shop Drawings Owner's Suite Rev_RG_POP.pdf
10 22 39-021-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-021-00 FOLDING PANEL PARTITIONS - Owner's Suite - Shop Drawings, Product Data, & Sample Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-14 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-04-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12391 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 10 22 39-21.0 From: KIM DOWALIBY Final Due Date: 04/15/21 Subject: FOLDING PANEL PARTITIONS - OWNER'S SUITE - SHOP DRAWINGS, PRODUCT DATA, & SAMPLE WARRANTY Description: 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, NUMBERED PANEL INSTALLATION SEQUENCE, AND ATTACHMENTS TO OTHER WORK. 2. INDICATE STACKING AND OPERATING CLEARANCES. INDICATE LOCATION AND INSTALLATION REQUIREMENTS FOR HARDWARE AND TRACK, BLOCKING, AND DIRECTION OF TRAVEL. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 16049 | Forwarded | For Review | 2021-04-05 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-12 | Submittal Number: 10 22 39-21.0 From: KIM DOWALIBY Final Due Date: 04/15/21 Subject: FOLDING PANEL PARTITIONS - OWNER'S SUITE - SHOP DRAWINGS, PRODUCT DATA, & SAMPLE WARRANTY Description: 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, NUMBERED PANEL INSTALLATION SEQUENCE, AND ATTACHMENTS TO OTHER WORK. 2. INDICATE STACKING AND OPERATING CLEARANCES. INDICATE LOCATION AND INSTALLATION REQUIREMENTS FOR HARDWARE AND TRACK, BLOCKING, AND DIRECTION OF TRAVEL. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 16289 | Responded and Closed | Approved as Noted | 2021-04-14 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 10 22 39-21 - FOLDING PANEL PARTITIONS - Owners Suite - Shop Drawings Product Data & Sample Warranty.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 10 22 39-21 - FOLDING PANEL PARTITIONS - Owners Suite - Shop Drawings Product Data & Sample Warranty.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-14 |  | 10 22 39-21 - FOLDING PANEL PARTITIONS - Owner's Suite - Shop Drawings_RG_POP.pdf
10 22 39-021-01 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-021-01 FOLDING PANEL PARTITIONS - Owner's Suite - Shop Drawings, Product Data, & Sample Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-30 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-14 | 2021-05-10 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12872 | Received | For Review | 2021-04-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-14 | Submittal Number: 10 22 39-21.1 From: KIM DOWALIBY Final Due Date: 05/14/21 Subject: FOLDING PANEL PARTITIONS - OWNER'S SUITE - SHOP DRAWINGS, PRODUCT DATA, & SAMPLE WARRANTY Description: 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, NUMBERED PANEL INSTALLATION SEQUENCE, AND ATTACHMENTS TO OTHER WORK. 2. INDICATE STACKING AND OPERATING CLEARANCES. INDICATE LOCATION AND INSTALLATION REQUIREMENTS FOR HARDWARE AND TRACK, BLOCKING, AND DIRECTION OF TRAVEL. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 16654 | Forwarded | For Review | 2021-04-30 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-07 | Submittal Number: 10 22 39-21.1 From: KIM DOWALIBY Final Due Date: 05/14/21 Subject: FOLDING PANEL PARTITIONS - OWNER'S SUITE - SHOP DRAWINGS, PRODUCT DATA, & SAMPLE WARRANTY Description: 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, NUMBERED PANEL INSTALLATION SEQUENCE, AND ATTACHMENTS TO OTHER WORK. 2. INDICATE STACKING AND OPERATING CLEARANCES. INDICATE LOCATION AND INSTALLATION REQUIREMENTS FOR HARDWARE AND TRACK, BLOCKING, AND DIRECTION OF TRAVEL. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 16844 | Responded and Closed | Approved as Noted | 2021-05-10 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-30 |  | 10 22 39-21.1 - FOLDING PANEL PARTITIONS - Owners Suite - Shop Drawings Rev 1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-30 |  | 10 22 39-21.1 - FOLDING PANEL PARTITIONS - Owners Suite - Shop Drawings Rev 1.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-10 |  | 10 22 39-21.1 - FOLDING PANEL PARTITIONS - Owners Suite - Shop Drawings Rev 1_POP.pdf
10 22 39-023-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-023-00 FOLDING PANEL PARTITIONS - Samples for Verification | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-07 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-21 | 2021-04-14 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-04-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12456 | Received | For Review | 2021-04-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-21 | Submittal Number: 10 22 39-23.0 From: KIM DOWALIBY Final Due Date: 04/21/21 Subject: FOLDING PANEL PARTITIONS - SAMPLES FOR VERIFICATION Description: FOR EACH TYPE OF EXPOSED MATERIAL, FINISH, COVERING, OR FACING, PREPARED ON SAMPLES OF SIZE INDICATED BELOW: 1. PANEL FACING MATERIAL: MANUFACTURER'S STANDARD-SIZE UNIT, NOT LESS THAN 3 INCHESSQUARE. 2. PANEL EDGE MATERIAL: NOT LESS THAN 3 INCHES LONG Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 16141 | Forwarded | For Review | 2021-04-07 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-14 | Submittal Number: 10 22 39-23.0 From: KIM DOWALIBY Final Due Date: 04/21/21 Subject: FOLDING PANEL PARTITIONS - SAMPLES FOR VERIFICATION Description: FOR EACH TYPE OF EXPOSED MATERIAL, FINISH, COVERING, OR FACING, PREPARED ON SAMPLES OF SIZE INDICATED BELOW: 1. PANEL FACING MATERIAL: MANUFACTURER'S STANDARD-SIZE UNIT, NOT LESS THAN 3 INCHESSQUARE. 2. PANEL EDGE MATERIAL: NOT LESS THAN 3 INCHES LONG Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 16291 | Responded and Closed | Approved as Noted | 2021-04-14 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-07 |  | 10 22 39-23 - FOLDING PANEL PARTITIONS - Owner's Suite - Samples.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-07 |  | 10 22 39-23 - FOLDING PANEL PARTITIONS - Owner's Suite - Samples.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-14 |  | 10 22 39-23 - FOLDING PANEL PARTITIONS - Owner's Suite - Samples_POP.pdf
10 22 39-025-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-025-00 FOLDING PANEL PARTITIONS - Seismic Qualification Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-10 | Responded and Closed - No Action Taken or Required |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-08-24 | 2021-08-12 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-08-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14287 | Received | For Review | 2021-08-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-08-24 | Submittal Number: 10 22 39-25.0 From: KIM DOWALIBY Final Due Date: 08/23/21 Subject: FOLDING PANEL PARTITIONS - SEISMIC QUALIFICATION DATA Description: FOR OPERABLE PANEL PARTITIONS, TRACKS, ACCESSORIES, AND COMPONENTS, FROM MANUFACTURER. INCLUDE SEISMIC CAPACITY OF PARTITION ASSEMBLIES TO REMAIN IN VERTICAL POSITION DURING A SEISMIC EVENT AND THE FOLLOWING: 1. BASIS FOR CERTIFICATION: INDICATE WHETHER CERTIFICATION IS BASED ON ANALYSIS, TESTING, OR EXPERIENCE DATA, ACCORDING TO ASCE/SEI 7. 2. DETAILED DESCRIPTION OF PARTITION ANCHORAGE DEVICES ON WHICH THE CERTIFICATION IS BASED AND THEIR INSTALLATION REQUIREMENTS. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 18454 | Forwarded | For Review | 2021-08-10 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-17 | Submittal Number: 10 22 39-25.0 From: KIM DOWALIBY Final Due Date: 08/23/21 Subject: FOLDING PANEL PARTITIONS - SEISMIC QUALIFICATION DATA Description: FOR OPERABLE PANEL PARTITIONS, TRACKS, ACCESSORIES, AND COMPONENTS, FROM MANUFACTURER. INCLUDE SEISMIC CAPACITY OF PARTITION ASSEMBLIES TO REMAIN IN VERTICAL POSITION DURING A SEISMIC EVENT AND THE FOLLOWING: 1. BASIS FOR CERTIFICATION: INDICATE WHETHER CERTIFICATION IS BASED ON ANALYSIS, TESTING, OR EXPERIENCE DATA, ACCORDING TO ASCE/SEI 7. 2. DETAILED DESCRIPTION OF PARTITION ANCHORAGE DEVICES ON WHICH THE CERTIFICATION IS BASED AND THEIR INSTALLATION REQUIREMENTS. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 18473 | Forwarded | For Review | 2021-08-11 | Chad Francis (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2021-08-16 | Submittal Number: 10 22 39-25.0 From: KIM DOWALIBY Final Due Date: 08/23/21 Subject: FOLDING PANEL PARTITIONS - SEISMIC QUALIFICATION DATA Description: FOR OPERABLE PANEL PARTITIONS, TRACKS, ACCESSORIES, AND COMPONENTS, FROM MANUFACTURER. INCLUDE SEISMIC CAPACITY OF PARTITION ASSEMBLIES TO REMAIN IN VERTICAL POSITION DURING A SEISMIC EVENT AND THE FOLLOWING: 1. BASIS FOR CERTIFICATION: INDICATE WHETHER CERTIFICATION IS BASED ON ANALYSIS, TESTING, OR EXPERIENCE DATA, ACCORDING TO ASCE/SEI 7. 2. DETAILED DESCRIPTION OF PARTITION ANCHORAGE DEVICES ON WHICH THE CERTIFICATION IS BASED AND THEIR INSTALLATION REQUIREMENTS. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 14339 | Review Response | No Action Taken or Required | 2021-08-11 | Matt Ross (Thornton Tomasetti) | Chad Francis (Populous) |  | RECEIVED FOR RECORD. | Info Exchange
| 18512 | Responded and Closed | No Action Taken or Required | 2021-08-12 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | For Record Only | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-09 |  | 10 22 39-25 - FOLDING PANEL PARTITIONS - Seismic Qualification Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-09 |  | 10 22 39-25 - FOLDING PANEL PARTITIONS - Seismic Qualification Data.pdf
| Forwarded |  | Chad Francis (Populous) | 1 | 2021-08-09 |  | 10 22 39-25 - FOLDING PANEL PARTITIONS - Seismic Qualification Data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-08-09 |  | 10 22 39-25 - FOLDING PANEL PARTITIONS - Seismic Qualification Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-08-12 |  | 10 22 39-25 - FOLDING PANEL PARTITIONS - Seismic Qualification Data_POP.pdf
10 22 39-026-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-026-00 FOLDING PANEL PARTITIONS - Sample Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-10 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-24 | 2021-08-11 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-08-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14288 | Received | For Review | 2021-08-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-08-24 | Submittal Number: 10 22 39-26.0 From: KIM DOWALIBY Final Due Date: 08/23/21 Subject: FOLDING PANEL PARTITIONS - SAMPLE WARRANTY Description: FOR EACH TYPE OF OPERABLE PANEL PARTITION. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 18455 | Forwarded | For Review | 2021-08-10 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-17 | Submittal Number: 10 22 39-26.0 From: KIM DOWALIBY Final Due Date: 08/23/21 Subject: FOLDING PANEL PARTITIONS - SAMPLE WARRANTY Description: FOR EACH TYPE OF OPERABLE PANEL PARTITION. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 18474 | Responded and Closed | Approved | 2021-08-11 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | Please see attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-09 |  | 10 22 39-26 - FOLDING PANEL PARTITIONS - Sample Warranty.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-09 |  | 10 22 39-26 - FOLDING PANEL PARTITIONS - Sample Warranty.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-08-11 |  | 10 22 39-26 - FOLDING PANEL PARTITIONS - Sample Warranty_POP.pdf
10 22 39-027-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-027-00 FOLDING PANEL PARTITIONS - Product Test Reports | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-30 | Responded and Closed - No Action Taken or Required |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-13 | 2021-08-11 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-08-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14170 | Received | For Review | 2021-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-08-13 | Submittal Number: 10 22 39-27.0 From: LUCAS TRADAL Final Due Date: 08/13/21 Subject: FOLDING PANEL PARTITIONS - PRODUCT TEST REPORTS Description: FOR EACH OPERABLE PANEL PARTITION, FOR TESTS PERFORMED BY A QUALIFIED TESTING AGENCY. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 18318 | Forwarded | For Review | 2021-07-30 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-06 | Submittal Number: 10 22 39-27.0 From: LUCAS TRADAL Final Due Date: 08/13/21 Subject: FOLDING PANEL PARTITIONS - PRODUCT TEST REPORTS Description: FOR EACH OPERABLE PANEL PARTITION, FOR TESTS PERFORMED BY A QUALIFIED TESTING AGENCY. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 18481 | Responded and Closed | No Action Taken or Required | 2021-08-11 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | For Record Only | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-30 |  | 10 22 39-27 - FOLDING PANEL PARTITIONS - Product Test Reports.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-30 |  | 10 22 39-27 - FOLDING PANEL PARTITIONS - Product Test Reports.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-08-11 |  | 10 22 39-27 - FOLDING PANEL PARTITIONS - Product Test Reports_POP.pdf
10 22 39-029-00 | 10 22 39 - FOLDING PANEL PARTITIONS | 10 22 39-029-00 FOLDING PANEL PARTITIONS - Operation and Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-13 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-27 | 2021-07-14 | 2 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13898 | Received | For Review | 2021-07-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-27 | Submittal Number: 10 22 39-29.0 From: LUCAS TRADAL Final Due Date: 07/26/21 Subject: FOLDING PANEL PARTITIONS - OPERATION AND MAINTENANCE DATA Description: OPERATION AND MAINTENANCE DATA: FOR OPERABLE PANEL PARTITIONS TO INCLUDE IN MAINTENANCE MANUALS. 1. IN ADDITION TO ITEMS SPECIFIED IN SECTION 01 78 23 "OPERATION AND MAINTENANCE DATA," INCLUDE THE FOLLOWING: A. PANEL FINISH FACINGS AND FINISHES FOR EXPOSED TRIM AND ACCESSORIES. INCLUDE PRECAUTIONS FOR CLEANING MATERIALS AND METHODS THAT COULD BE DETRIMENTAL TO FINISHES AND PERFORMANCE. B. SEALS, HARDWARE, TRACK, TRACK SWITCHES, CARRIERS, AND OTHER OPERATING COMPONENTS. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 18000 | Forwarded | For Review | 2021-07-12 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-19 | Submittal Number: 10 22 39-29.0 From: LUCAS TRADAL Final Due Date: 07/26/21 Subject: FOLDING PANEL PARTITIONS - OPERATION AND MAINTENANCE DATA Description: OPERATION AND MAINTENANCE DATA: FOR OPERABLE PANEL PARTITIONS TO INCLUDE IN MAINTENANCE MANUALS. 1. IN ADDITION TO ITEMS SPECIFIED IN SECTION 01 78 23 "OPERATION AND MAINTENANCE DATA," INCLUDE THE FOLLOWING: A. PANEL FINISH FACINGS AND FINISHES FOR EXPOSED TRIM AND ACCESSORIES. INCLUDE PRECAUTIONS FOR CLEANING MATERIALS AND METHODS THAT COULD BE DETRIMENTAL TO FINISHES AND PERFORMANCE. B. SEALS, HARDWARE, TRACK, TRACK SWITCHES, CARRIERS, AND OTHER OPERATING COMPONENTS. Spec Section: 10 22 39 - FOLDING PANEL PARTITIONS Status: OPEN | Info Exchange
| 18040 | Responded and Closed | Approved as Noted | 2021-07-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-12 |  | 10 22 39-29 - FOLDING PANEL PARTITIONS - Operation and Maintenance Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-12 |  | 10 22 39-29 - FOLDING PANEL PARTITIONS - Operation and Maintenance Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-14 |  | 10 22 39-29 - FOLDING PANEL PARTITIONS - Operation and Maintenance Data_POP.pdf
10 26 00-001-00 | 10 26 00 - WALL AND DOOR PROTECTION | 10 26 00-001-00 WALL AND DOOR PROTECTION - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-16 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-02 08:00 | 2020-12-02 | 17 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09430 | Received | For Review | 2020-11-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-02 08:00 | Submittal Number: 10 26 00-1.0 From: DANIELLE SCOTT Final Due Date: 12/24/20 Subject: WALL AND DOOR PROTECTION - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, IMPACT STRENGTH; DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. 2. INCLUDE FIRE RATINGS OF UNITS RECESSED IN FIRE-RATED WALLS AND LISTINGS FOR DOOR-PROTECTION ITEMS ATTACHED TO FIRE-RATED DOORS. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 12437 | Forwarded | For Review | 2020-11-13 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-20 | Submittal Number: 10 26 00-1.0 From: DANIELLE SCOTT Final Due Date: 12/24/20 Subject: WALL AND DOOR PROTECTION - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, IMPACT STRENGTH; DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. 2. INCLUDE FIRE RATINGS OF UNITS RECESSED IN FIRE-RATED WALLS AND LISTINGS FOR DOOR-PROTECTION ITEMS ATTACHED TO FIRE-RATED DOORS. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 12931 | Responded and Closed | Approved | 2020-12-02 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-13 |  | 10 26 00-1 Wall and Door Protection.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-13 |  | 10 26 00-1 Wall and Door Protection.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-13 |  | 10 26 00-1 Wall and Door Protection.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-13 |  | Transmittal_Submittal - 10 26 00-001-00 (Forwarded).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-12-02 |  | 10 26 00-1 Wall and Door Protection-POP.pdf
10 26 00-002-00 | 10 26 00 - WALL AND DOOR PROTECTION | 10 26 00-002-00 WALL AND DOOR PROTECTION - Crash Rail Product Data, Shop Drawings, & Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-08 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-22 | 2021-03-23 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11828 | Received | For Review | 2021-03-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-03-22 | Submittal Number: 10 26 00-2.0 From: DANIELLE SCOTT Final Due Date: 04/07/21 Subject: WALL AND DOOR PROTECTION - CRASH RAIL PRODUCT DATA, SHOP DRAWINGS, & WARRANTY Description: PRODUCT DATA: FOR ADHESIVES, INDICATING VOC CONTENT. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 15334 | Forwarded | For Review | 2021-03-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-15 | Submittal Number: 10 26 00-2.0 From: DANIELLE SCOTT Final Due Date: 04/07/21 Subject: WALL AND DOOR PROTECTION - CRASH RAIL PRODUCT DATA, SHOP DRAWINGS, & WARRANTY Description: PRODUCT DATA: FOR ADHESIVES, INDICATING VOC CONTENT. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 12174 | Review Response | Approved as Noted | 2021-03-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15758 | Responded and Closed | Approved as Noted | 2021-03-23 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-05 |  | 10 26 00-2 Revision 0 WALL AND DOOR PROTECTION - Crash Rail Product Data Shop Drawings & Warranty.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-05 |  | 10 26 00-2 Revision 0 WALL AND DOOR PROTECTION - Crash Rail Product Data Shop Drawings & Warranty.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-23 |  | 10 26 00-2 Revision 0 WALL AND DOOR PROTECTION - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-03-05 |  | 10 26 00-2 Revision 0 WALL AND DOOR PROTECTION - Crash Rail Product Data Shop Drawings & Warranty.pdf
10 26 00-004-00 | 10 26 00 - WALL AND DOOR PROTECTION | 10 26 00-004-00 WALL AND DOOR PROTECTION - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-04 | 2021-05-24 | 35 |  | Record Copies; Transfers; Submittals | 10 26 00-004-00-01 - 10 26 00-004-00 WALL AND DOOR PROTECTION - Shop Drawings | 35 |  | 2021-05-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12675 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-04 | Submittal Number: 10 26 00-4.0 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: WALL AND DOOR PROTECTION - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH TYPE OF WALL AND DOOR PROTECTION SHOWING LOCATIONS AND EXTENT. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 16393 | Forwarded | For Review | 2021-04-20 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-27 | Submittal Number: 10 26 00-4.0 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: WALL AND DOOR PROTECTION - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH TYPE OF WALL AND DOOR PROTECTION SHOWING LOCATIONS AND EXTENT. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 17143 | Responded and Closed | Revise and Resubmit | 2021-05-24 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | NO CORNER GUARDS AT CMU. REMOVE CORNER GUARDS FROM CMU WALLS, TYP. REFER TO A0-01 FOR WALL TYPE LEGEND. NO CORNER GUARDS TO BE PLACED ON TILE. COORDINATE WITH FINISHES AT ELEVATOR LOBBIES AND OTHER LOCATIONS WITH TILE, TYP. REFER TO 09 30 13-004-00. NO CORNER GUARDS IN MAIN CONCOURSE CLUB SPACES, AT SUITE LEVEL, OR AT SPACE NEEDLE LEVEL. UPDATE WITH CURRENT BACKGROUNDS. REFER TO COMMENTS MARKED ON SHEETS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-19 |  | 10 26 00-4 WALL AND DOOR PROTECTION - Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-19 |  | 10 26 00-4 WALL AND DOOR PROTECTION - Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-24 02:00 |  | 10 26 00-4 WALL AND DOOR PROTECTION - Shop Drawings_POP.pdf
10 26 00-004-00-01 | 10 26 00 - WALL AND DOOR PROTECTION | 10 26 00-004-00 WALL AND DOOR PROTECTION - Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 26 00-004-00 - 10 26 00-004-00 WALL AND DOOR PROTECTION - Shop Drawings | -1 | 2021-06-07
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-24 02:00 |  | 10 26 00-4 WALL AND DOOR PROTECTION - Shop Drawings_POP.pdf
10 26 00-004-01 | 10 26 00 - WALL AND DOOR PROTECTION | 10 26 00-004-01 WALL AND DOOR PROTECTION - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-10 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-24 | 2021-06-24 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13483 | Received | For Review | 2021-06-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-24 | Submittal Number: 10 26 00-4.1 From: KIM DOWALIBY Final Due Date: 06/23/21 Subject: WALL AND DOOR PROTECTION - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH TYPE OF WALL AND DOOR PROTECTION SHOWING LOCATIONS AND EXTENT. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 17436 | Forwarded | For Review | 2021-06-10 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-17 | Submittal Number: 10 26 00-4.1 From: KIM DOWALIBY Final Due Date: 06/23/21 Subject: WALL AND DOOR PROTECTION - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR EACH TYPE OF WALL AND DOOR PROTECTION SHOWING LOCATIONS AND EXTENT. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 17663 | Responded and Closed | Approved as Noted | 2021-06-24 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | Refer to comments within submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-10 |  | 10 26 00-4.1 WALL AND DOOR PROTECTION - Shop Drawings Rev 1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-10 |  | 10 26 00-4.1 WALL AND DOOR PROTECTION - Shop Drawings Rev 1.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-24 02:00 |  | 10 26 00-4.1 WALL AND DOOR PROTECTION - Shop Drawings Rev 1_pop.pdf
10 26 00-005-00 | 10 26 00 - WALL AND DOOR PROTECTION | 10 26 00-005-00 WALL AND DOOR PROTECTION - Corner Guard Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-12-03 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09566 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-07 | Submittal Number: 10 26 00-5.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: WALL AND DOOR PROTECTION - CORNER GUARD SAMPLE Description: SAMPLES FOR VERIFICATION : CORNER GUARD Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 12594 | Forwarded | For Review | 2020-11-19 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 10 26 00-5.0 From: DANIELLE SCOTT Final Due Date: 12/02/20 Subject: WALL AND DOOR PROTECTION - CORNER GUARD SAMPLE Description: SAMPLES FOR VERIFICATION : CORNER GUARD Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 12974 | Responded and Closed | Approved | 2020-12-03 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  | No exceptions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-18 |  | 10 26 00-5 WALL AND DOOR PROTECTION - Corner Guard Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-18 |  | 10 26 00-5 WALL AND DOOR PROTECTION - Corner Guard Sample.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-03 02:00 |  | 10 26 00-5 WALL AND DOOR PROTECTION - Corner Guard Sample_POP.pdf
10 26 00-008-00 | 10 26 00 - WALL AND DOOR PROTECTION | 10 26 00-008-00 WALL AND DOOR PROTECTION - Sample Warranty | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-20 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-04 07:00 | 2021-06-08 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-06-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13203 | Received | For Review | 2021-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-04 07:00 | Submittal Number: 10 26 00-8.0 From: KIM DOWALIBY Final Due Date: 06/03/21 Subject: WALL AND DOOR PROTECTION - SAMPLE WARRANTY Description: SAMPLE WARRANTY : FOR SPECIAL WARRANTY. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 17091 | Forwarded | For Review | 2021-05-20 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-27 | Submittal Number: 10 26 00-8.0 From: KIM DOWALIBY Final Due Date: 06/03/21 Subject: WALL AND DOOR PROTECTION - SAMPLE WARRANTY Description: SAMPLE WARRANTY : FOR SPECIAL WARRANTY. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 17398 | Responded and Closed | Approved | 2021-06-08 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-20 |  | 10 26 00-8 WALL AND DOOR PROTECTION - Sample Warranty.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-20 |  | 10 26 00-8 WALL AND DOOR PROTECTION - Sample Warranty.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-08 |  | 10 26 00-8 WALL AND DOOR PROTECTION - Sample Warranty_POP.pdf
10 26 00-009-00 | 10 26 00 - WALL AND DOOR PROTECTION | 10 26 00-009-00 WALL AND DOOR PROTECTION - Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-04 | 2021-05-10 | 21 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12648 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-04 | Submittal Number: 10 26 00-9.0 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: WALL AND DOOR PROTECTION - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR EACH TYPE OF WALL AND DOOR PROTECTION PRODUCT TO INCLUDE IN MAINTENANCE MANUALS. 1. INCLUDE RECOMMENDED METHODS AND FREQUENCY OF MAINTENANCE FOR MAINTAINING BEST CONDITION OF PLASTIC COVERS UNDER ANTICIPATED TRAFFIC AND USE CONDITIONS. INCLUDE PRECAUTIONS AGAINST USING CLEANING MATERIALS AND METHODS THAT MAY BE DETRIMENTAL TO FINISHES AND PERFORMANCE. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 16365 | Forwarded | For Review | 2021-04-19 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-26 | Submittal Number: 10 26 00-9.0 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: WALL AND DOOR PROTECTION - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR EACH TYPE OF WALL AND DOOR PROTECTION PRODUCT TO INCLUDE IN MAINTENANCE MANUALS. 1. INCLUDE RECOMMENDED METHODS AND FREQUENCY OF MAINTENANCE FOR MAINTAINING BEST CONDITION OF PLASTIC COVERS UNDER ANTICIPATED TRAFFIC AND USE CONDITIONS. INCLUDE PRECAUTIONS AGAINST USING CLEANING MATERIALS AND METHODS THAT MAY BE DETRIMENTAL TO FINISHES AND PERFORMANCE. Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 16863 | Responded and Closed | Approved as Noted | 2021-05-10 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  | This submittal is approved as noted. Final approval pending submittal of O&M manuals per section 01 78 23. | Info Exchange
| 17060 | Sent | For Information Only | 2021-05-19 | Populous SCA_CCA | Brooke Burcham (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Responded and Closed (Approved as Noted) to: Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby Remarks: This submittal is approved as noted. Final approval pending submittal of O&M manuals per section 01 78 23. | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-19 |  | 10 26 00-9 WALL AND DOOR PROTECTION - Maintenance Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-19 |  | 10 26 00-9 WALL AND DOOR PROTECTION - Maintenance Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-10 02:00 |  | 10 26 00-9 WALL AND DOOR PROTECTION - Maintenance Data_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-04-18 02:00 |  | 10 26 00-9 WALL AND DOOR PROTECTION - Maintenance Data.pdf
10 26 00-011-00 | 10 26 00 - WALL AND DOOR PROTECTION | 10 26 00-011-00 Crash Rail Sample (Premium) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-16 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-08 | 2021-01-08 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10194 | Received | For Review | 2020-12-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-01-08 | Submittal Number: 10 26 00-11.0 From: DANIELLE SCOTT Final Due Date: 12/30/20 Subject: CRASH RAIL SAMPLE (PREMIUM) Description: CRASH RAIL SAMPLE - EVENT LEVEL Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 13332 | Forwarded | For Review | 2020-12-16 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-23 | Submittal Number: 10 26 00-11.0 From: DANIELLE SCOTT Final Due Date: 12/30/20 Subject: CRASH RAIL SAMPLE (PREMIUM) Description: CRASH RAIL SAMPLE - EVENT LEVEL Spec Section: 10 26 00 - WALL AND DOOR PROTECTION Status: OPEN | Info Exchange
| 10541 | Review Response | Approved | 2021-01-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 13740 | Responded and Closed | Approved | 2021-01-08 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-16 |  | 10 26 00-11 Crash Rail Sample (Event Level).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-16 |  | 10 26 00-11 Crash Rail Sample (Event Level).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-08 |  | 10 26 00-11 Crash Rail Sample (Event Level)-POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-12-16 |  | 10 26 00-11 Crash Rail Sample (Event Level).pdf
10 28 00-001-00 | 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES | 10 28 00-001-00 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Base Building) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-09 | Responded and Closed - Approved as Noted/Resubmit | [5 empty] | 2020-10-23 | 2020-10-29 | 21 |  | Record Copies; Transfers; Submittals | 10 28 00-001-01 - 10 28 00-001-00 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Base Building) | -1 |  | 2020-10-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08698 | Received | For Review | 2020-10-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-23 | Submittal Number: 10 28 00-1.0 From: DANIELLE SCOTT Final Due Date: 10/23/20 Subject: TOILET BATH AND LAUNDRY ACCESSORIES - PRODUCT DATA & TA SCHEDULE (BASE BUILDING) Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. 2. INCLUDE ANCHORING AND MOUNTING REQUIREMENTS, INCLUDING REQUIREMENTS FOR CUTOUTS IN OTHER WORK AND SUBSTRATE PREPARATION. 3. INCLUDE ELECTRICAL REQUIREMENTS. TA SCHEDULE Spec Section: 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES Status: OPEN | Info Exchange
| 12020 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-29 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  | CONTRACTOR SHALL CONFIRM WALL CAVITY DEPTHS TO ENSURE PROPER FIT OF ALL SCHEDULED, RECESSED ACCESSORIES. CONTRACTOR SHALL COORDINATE BLOCKING REQUIREMENTS FOR INSTALLATION OF SCHEDULED ACCESSORIES. CONTRACTOR SHALL COORDINATE INSTALLATION LOCATIONS, HEIGHTS, AND CLEARANCES WITH WORK OF OTHER TRADES (MILLWORK, TOILET PARTITIONS, WALL FINISHES, PLUMBING, ETC.) TO ENSURE PROPER FIT OF ALL ACCESSORIES. CONTRACTOR TO VERIFY AND COORDINATE NUMBER AND LOCATION OF ACCESSORIES. SEE ADDITIONAL COMMENTS WITHIN SUBMITTAL. RESUBMIT ACCESSORIES AS REQUIRED. REFER TO RFI 3312 AND CCD078 (TO BE ISSUED 10/30) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-09 02:00 |  | 10 28 00-1 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Base Building).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-29 02:00 |  | 10 28 00-1 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Base Building)_pop.pdf
10 28 00-001-01 | 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES | 10 28 00-001-00 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Base Building) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 28 00-001-00 - 10 28 00-001-00 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Base Building) | -1 | 2020-11-12
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-29 02:00 |  | 10 28 00-1 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Base Building)_pop.pdf
10 28 00-002-00 | 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES | 10 28 00-002-00 TOILET BATH AND LAUNDRY ACCESSORIES - Mock Up 03.35.02 &03.35.03 Product Data & Product Schedule | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-21 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-05 | 2020-09-23 | 3 |  | Record Copies; Transfers; Submittals | 10 28 00-002-00-01 - 10 28 00-002-00 TOILET BATH AND LAUNDRY ACCESSORIES - Mock Up 03.35.02 &03.35.03 Product Data & Product Schedule | 6 |  | 2020-09-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08209 | Received | For Review | 2020-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-05 | Submittal Number: 10 28 00-2.0 From: DANIELLE SCOTT Final Due Date: 10/02/20 Subject: TOILET BATH AND LAUNDRY ACCESSORIES - MOCK UP 03.35.02 &03.35.03 PRODUCT DATA & PRODUCT SCHEDULE Description: ONLY MOCK UP ROOMS 03.35.02 AND 03.35.03. PRODUCT SCHEDULE : INDICATING TYPES, QUANTITIES, SIZES, AND INSTALLATION LOCATIONS BY ROOM OF EACH ACCESSORY REQUIRED. 1. IDENTIFY LOCATIONS USING ROOM DESIGNATIONS INDICATED. 2. IDENTIFY PRODUCTS USING DESIGNATIONS INDICATED. PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. 2. INCLUDE ANCHORING AND MOUNTING REQUIREMENTS, INCLUDING REQUIREMENTS FOR CUTOUTS IN OTHER WORK AND SUBSTRATE PREPARATION. 3. INCLUDE ELECTRICAL REQUIREMENTS. Spec Section: 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES Status: OPEN | Info Exchange
| 10899 | Forwarded | For Review | 2020-09-18 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-25 | Submittal Number: 10 28 00-2.0 From: DANIELLE SCOTT Final Due Date: 10/02/20 Subject: TOILET BATH AND LAUNDRY ACCESSORIES - MOCK UP 03.35.02 &03.35.03 PRODUCT DATA & PRODUCT SCHEDULE Description: ONLY MOCK UP ROOMS 03.35.02 AND 03.35.03. PRODUCT SCHEDULE : INDICATING TYPES, QUANTITIES, SIZES, AND INSTALLATION LOCATIONS BY ROOM OF EACH ACCESSORY REQUIRED. 1. IDENTIFY LOCATIONS USING ROOM DESIGNATIONS INDICATED. 2. IDENTIFY PRODUCTS USING DESIGNATIONS INDICATED. PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. 2. INCLUDE ANCHORING AND MOUNTING REQUIREMENTS, INCLUDING REQUIREMENTS FOR CUTOUTS IN OTHER WORK AND SUBSTRATE PREPARATION. 3. INCLUDE ELECTRICAL REQUIREMENTS. Spec Section: 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES Status: OPEN | Info Exchange
| 08301 | Review Response | Approved as Noted/Resubmit | 2020-09-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Resubmit TA04 only. Provide shop drawings for mirrors, the submitted RR's have a continuous mirror across the whole sink area, with an upper halo light. | Info Exchange
| 11006 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-23 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. Resubmit TA04 only. 2. Provide shop drawings for mirrors, the submitted RR's have a continuous mirror across the whole sink area, with an upper halo light. 3. Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-18 |  | 10 28 00-2 Toliet Bath and Laundry Accessories 03.35.02 & 03.35.03.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-18 |  | 10 28 00-2 Toliet Bath and Laundry Accessories 03.35.02 & 03.35.03.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-23 |  | 10 28 00-2 Toliet Bath and Laundry Accessories 03.35.02 & 03.35.03 POP.pdf
10 28 00-002-00-01 | 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES | 10 28 00-002-00 TOILET BATH AND LAUNDRY ACCESSORIES - Mock Up 03.35.02 &03.35.03 Product Data & Product Schedule | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 10 28 00-002-00 - 10 28 00-002-00 TOILET BATH AND LAUNDRY ACCESSORIES - Mock Up 03.35.02 &03.35.03 Product Data & Product Schedule | -1 | 2020-10-07
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 10 28 00-2 Toliet Bath and Laundry Accessories 03.35.02 & 03.35.03 POP.pdf
10 28 00-004-00 | 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES | 10 28 00-004-00 TOILET BATH AND LAUNDRY ACCESSORIES - Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 | 2021-04-27 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12467 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-22 | Submittal Number: 10 28 00-4.0 From: KIM DOWALIBY Final Due Date: 04/21/21 Subject: TOILET BATH AND LAUNDRY ACCESSORIES - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR TOILET AND BATH ACCESSORIES TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES Status: OPEN | Info Exchange
| 16157 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 10 28 00-4.0 From: KIM DOWALIBY Final Due Date: 04/21/21 Subject: TOILET BATH AND LAUNDRY ACCESSORIES - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR TOILET AND BATH ACCESSORIES TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES Status: OPEN | Info Exchange
| 16560 | Responded and Closed | Approved as Noted | 2021-04-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED 1. APPROVED, SUBMIT IN FINAL O/M MANUALS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 10 28 00-4 TOILET BATH AND LAUNDRY ACCESSORIES - Maintenance Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 10 28 00-4 TOILET BATH AND LAUNDRY ACCESSORIES - Maintenance Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-27 |  | 10 28 00-4 TOILET BATH AND LAUNDRY ACCESSORIES - Maintenance Data_POP.pdf
10 28 00-005-00 | 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES | 10 28 00-005-00 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Premium Space & NHL Locker Room) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-09 | Responded and Closed - Approved as Noted |  | Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous), Kelsea Conkright (Populous) |  |  |  | 2020-10-23 | 2020-10-29 | 21 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-10-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08714 | Received | For Review | 2020-10-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-10-23 | Submittal Number: 10 28 00-5.0 From: DANIELLE SCOTT Final Due Date: 10/23/20 Subject: TOILET BATH AND LAUNDRY ACCESSORIES - PRODUCT DATA & TA SCHEDULE (PREMIUM SPACE & NHL LOCKER ROOM) Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. 2. INCLUDE ANCHORING AND MOUNTING REQUIREMENTS, INCLUDING REQUIREMENTS FOR CUTOUTS IN OTHER WORK AND SUBSTRATE PREPARATION. 3. INCLUDE ELECTRICAL REQUIREMENTS. TA SCHEDULE Spec Section: 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES Status: OPEN | Info Exchange
| 11506 | Forwarded | For Review | 2020-10-12 | Josh Dobken (Populous) | Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 10 28 00-5.0 From: DANIELLE SCOTT Final Due Date: 10/23/20 Subject: TOILET BATH AND LAUNDRY ACCESSORIES - PRODUCT DATA & TA SCHEDULE (PREMIUM SPACE & NHL LOCKER ROOM) Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. 2. INCLUDE ANCHORING AND MOUNTING REQUIREMENTS, INCLUDING REQUIREMENTS FOR CUTOUTS IN OTHER WORK AND SUBSTRATE PREPARATION. 3. INCLUDE ELECTRICAL REQUIREMENTS. TA SCHEDULE Spec Section: 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES Status: OPEN | Info Exchange
| 11507 | Forwarded | For Review | 2020-10-12 | Josh Dobken (Populous) | Kelsea Conkright (Populous) | 2020-10-19 | Submittal Number: 10 28 00-5.0 From: DANIELLE SCOTT Final Due Date: 10/23/20 Subject: TOILET BATH AND LAUNDRY ACCESSORIES - PRODUCT DATA & TA SCHEDULE (PREMIUM SPACE & NHL LOCKER ROOM) Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. 2. INCLUDE ANCHORING AND MOUNTING REQUIREMENTS, INCLUDING REQUIREMENTS FOR CUTOUTS IN OTHER WORK AND SUBSTRATE PREPARATION. 3. INCLUDE ELECTRICAL REQUIREMENTS. TA SCHEDULE Spec Section: 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES Status: OPEN | Info Exchange
| 12024 | Responded and Closed | Approved as Noted | 2020-10-29 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  | CONTRACTOR SHALL CONFIRM WALL CAVITY DEPTHS TO ENSURE PROPER FIT OF ALL SCHEDULED, RECESSED ACCESSORIES. CONTRACTOR SHALL COORDINATE BLOCKING REQUIREMENTS FOR INSTALLATION OF SCHEDULED ACCESSORIES. CONTRACTOR SHALL COORDINATE INSTALLATION LOCATIONS, HEIGHTS, AND CLEARANCES WITH WORK OF OTHER TRADES (MILLWORK, TOILET PARTITIONS, WALL FINISHES, PLUMBING, ETC.) TO ENSURE PROPER FIT OF ALL ACCESSORIES. CONTRACTOR TO VERIFY AND COORDINATE NUMBER AND LOCATION OF ACCESSORIES. SEE ADDITIONAL COMMENTS WITHIN SUBMITTAL. REFER TO RFI 3312 AND CCD078 FOR REVISIONS TO ACCESSORIES, RESUBMIT AS PART OF 10 28 00-001 REV 1. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-09 02:00 |  | 10 28 00-5 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Premium Space and NHL Locker Room).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-09 02:00 |  | 10 28 00-5 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Premium Space and NHL Locker Room).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-09 02:00 |  | 10 28 00-5 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Premium Space and NHL Locker Room).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-29 02:00 |  | 10 28 00-5 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data & TA Schedule (Premium Space and NHL Locker Room)_POP.pdf
10 28 00-005-01 | 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES | 10 28 00-005-01 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data TA44 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-04 | 2021-05-04 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12647 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-04 | Submittal Number: 10 28 00-5.1 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: TOILET BATH AND LAUNDRY ACCESSORIES - PRODUCT DATA TA44 Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. 2. INCLUDE ANCHORING AND MOUNTING REQUIREMENTS, INCLUDING REQUIREMENTS FOR CUTOUTS IN OTHER WORK AND SUBSTRATE PREPARATION. 3. INCLUDE ELECTRICAL REQUIREMENTS. TA SCHEDULE Spec Section: 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES Status: OPEN | Info Exchange
| 16364 | Forwarded | For Review | 2021-04-19 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-26 | Submittal Number: 10 28 00-5.1 From: KIM DOWALIBY Final Due Date: 05/03/21 Subject: TOILET BATH AND LAUNDRY ACCESSORIES - PRODUCT DATA TA44 Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES. 2. INCLUDE ANCHORING AND MOUNTING REQUIREMENTS, INCLUDING REQUIREMENTS FOR CUTOUTS IN OTHER WORK AND SUBSTRATE PREPARATION. 3. INCLUDE ELECTRICAL REQUIREMENTS. TA SCHEDULE Spec Section: 10 28 00 - TOILET, BATH, AND LAUNDRY ACCESSORIES Status: OPEN | Info Exchange
| 16716 | Responded and Closed | Approved | 2021-05-04 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-19 |  | 10 28 00-5.1 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data TA44.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-19 |  | 10 28 00-5.1 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data TA44.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-04 |  | 10 28 00-5.1 TOILET BATH AND LAUNDRY ACCESSORIES - Product Data TA44_POP.pdf
10 28 80-004-00 | 10 28 80 | 10 28 80-004-00 GLASS SHOWER DOORS - Samples for Initial Selection | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-05-19 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13144 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-02 07:00 | Submittal Number: 10 28 80-4.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: GLASS SHOWER DOORS - SAMPLES FOR INITIAL SELECTION Description: Spec Section: 10 28 80 - GLASS SHOWER DOORS Status: OPEN | Info Exchange
| 17004 | Forwarded | For Review | 2021-05-18 | Allie Zimmerman | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-25 | Submittal Number: 10 28 80-4.0 From: ALLIE ZIMMERMAN Final Due Date: 06/01/21 Subject: GLASS SHOWER DOORS - SAMPLES FOR INITIAL SELECTION Description: Spec Section: 10 28 80 - GLASS SHOWER DOORS Status: OPEN | Info Exchange
| 17056 | Responded and Closed | Approved as Noted | 2021-05-19 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | Submittal 10 28 80-4 Revision 0 GLASS SHOWER DOORS - Samples for Initial Selection_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-05-17 |  | Submittal 10 28 80-4 Revision 0 GLASS SHOWER DOORS - Samples for Initial Selection_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-19 |  | Submittal 10 28 80-4 Revision 0 GLASS SHOWER DOORS - Samples for Initial Selection_MAM Reviewed_POP.pdf
10 28 80-005-00 | 10 28 80 | 10 28 80-005-00 GLASS SHOWER DOORS - Samples for Verification | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-09 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-23 | 2021-06-09 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13466 | Received | For Review | 2021-06-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-23 | Submittal Number: 10 28 80-5.0 From: ALLIE ZIMMERMAN Final Due Date: 06/22/21 Subject: GLASS SHOWER DOORS - SAMPLES FOR VERIFICATION Description: Spec Section: 10 28 80 - GLASS SHOWER DOORS Status: OPEN | Info Exchange
| 17411 | Forwarded | For Review | 2021-06-09 | Allie Zimmerman | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-16 | Submittal Number: 10 28 80-5.0 From: ALLIE ZIMMERMAN Final Due Date: 06/22/21 Subject: GLASS SHOWER DOORS - SAMPLES FOR VERIFICATION Description: Spec Section: 10 28 80 - GLASS SHOWER DOORS Status: OPEN | Info Exchange
| 17424 | Responded and Closed | Approved | 2021-06-09 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-08 |  | Submittal 10 28 80-5 Revision 0 GLASS SHOWER DOORS - Samples for Verification_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-06-08 |  | Submittal 10 28 80-5 Revision 0 GLASS SHOWER DOORS - Samples for Verification_MAM Reviewed.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-06-09 |  | Submittal 10 28 80-5 Revision 0 GLASS SHOWER DOORS - Samples for Verification_MAM Reviewed_POP.pdf
10 43 13-001-00 | 10 43 13 - DEFIBRILLATOR CABINETS | 10 43 13-001-00 DEFIBRILLATOR CABINETS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-27 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-10 | 2020-11-10 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-11-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09023 | Received | For Review | 2020-10-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-11-10 | Submittal Number: 10 43 13-1.0 From: DANIELLE SCOTT Final Due Date: 11/09/20 Subject: DEFIBRILLATOR CABINETS - PRODUCT DATA Description: PRODUCT DATA : INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COM- PONENTS AND PROFILES, AND FINISHES CABINETS. 1. CABINETS: INCLUDE ROUGHING-IN DIMENSIONS, DETAILS SHOWING MOUNTING METHODS, RELATIONSHIPS OF BOX AND TRIM TO SURROUNDING CONSTRUCTION, DOOR HARDWARE, CABINET TYPE, TRIM STYLE, AND PANEL STYLE. Spec Section: 10 43 13 - DEFIBRILLATOR CABINETS Status: OPEN | Info Exchange
| 11904 | Forwarded | For Review | 2020-10-27 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-03 | Submittal Number: 10 43 13-1.0 From: DANIELLE SCOTT Final Due Date: 11/09/20 Subject: DEFIBRILLATOR CABINETS - PRODUCT DATA Description: PRODUCT DATA : INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COM- PONENTS AND PROFILES, AND FINISHES CABINETS. 1. CABINETS: INCLUDE ROUGHING-IN DIMENSIONS, DETAILS SHOWING MOUNTING METHODS, RELATIONSHIPS OF BOX AND TRIM TO SURROUNDING CONSTRUCTION, DOOR HARDWARE, CABINET TYPE, TRIM STYLE, AND PANEL STYLE. Spec Section: 10 43 13 - DEFIBRILLATOR CABINETS Status: OPEN | Info Exchange
| 12317 | Responded and Closed | Approved as Noted | 2020-11-10 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 10 43 13-1 DEFIBRILLATOR CABINETS - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 10 43 13-1 DEFIBRILLATOR CABINETS - Product Data.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-10 |  | 10 43 13-1 DEFIBRILLATOR CABINETS - Product Data-POP.pdf
10 43 13-002-00 | 10 43 13 - DEFIBRILLATOR CABINETS | 10 43 13-002-00 DEFIBRILLATOR CABINETS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 | 2021-04-27 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12470 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-22 | Submittal Number: 10 43 13-2.0 From: KIM DOWALIBY Final Due Date: 04/14/21 Subject: DEFIBRILLATOR CABINETS - SAMPLES Description: SAMPLES : FOR EACH TYPE OF EXPOSED CABINET FINISH REQUIRED, PREPARED ON SAMPLES OF SIZE INDI- CATED BELOW AND OF SAME THICKNESS AND MATERIAL INDICATED FOR THE WORK. IF FINISHES INVOLVE NOR- MAL COLOR AND TEXTURE VARIATIONS, INCLUDE SAMPLE SETS SHOWING THE FULL RANGE OF VARIATIONS EX- PECTED. 1. SIZE: 6-BY-6-INCH- (150-BY-150-MM-) SQUARE SAMPLES. Spec Section: 10 43 13 - DEFIBRILLATOR CABINETS Status: OPEN | Info Exchange
| 16160 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 10 43 13-2.0 From: KIM DOWALIBY Final Due Date: 04/14/21 Subject: DEFIBRILLATOR CABINETS - SAMPLES Description: SAMPLES : FOR EACH TYPE OF EXPOSED CABINET FINISH REQUIRED, PREPARED ON SAMPLES OF SIZE INDI- CATED BELOW AND OF SAME THICKNESS AND MATERIAL INDICATED FOR THE WORK. IF FINISHES INVOLVE NOR- MAL COLOR AND TEXTURE VARIATIONS, INCLUDE SAMPLE SETS SHOWING THE FULL RANGE OF VARIATIONS EX- PECTED. 1. SIZE: 6-BY-6-INCH- (150-BY-150-MM-) SQUARE SAMPLES. Spec Section: 10 43 13 - DEFIBRILLATOR CABINETS Status: OPEN | Info Exchange
| 16561 | Responded and Closed | Approved | 2021-04-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 10 43 13-2 DEFIBRILLATOR CABINETS - Samples.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 10 43 13-2 DEFIBRILLATOR CABINETS - Samples.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-27 |  | 10 43 13-2 DEFIBRILLATOR CABINETS - Samples_POP.pdf
10 44 13-001-00 | 10 44 13 - FIRE PROTECTION CABINETS | 10 44 13-001-00 FIRE PROTECTION CABINETS - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-26 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-11-09 | 2020-11-03 | 9 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-11-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08962 | Received | For Review | 2020-10-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-11-09 | Submittal Number: 10 44 13-1.0 From: DANIELLE SCOTT Final Due Date: 11/06/20 Subject: FIRE PROTECTION CABINETS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. SHOW DOOR HARDWARE, CABINET TYPE, TRIM STYLE, AND PANEL STYLE. INCLUDE ROUGHING-IN DIMENSIONS AND DETAILS SHOWING MOUNTING METHOD AND RELATIONSHIPS OF BOX AND TRIM TO SURROUNDING CONSTRUCTION. Spec Section: 10 44 13 - FIRE PROTECTION CABINETS Status: OPEN | Info Exchange
| 11833 | Forwarded | For Review | 2020-10-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-10-30 | Submittal Number: 10 44 13-1.0 From: DANIELLE SCOTT Final Due Date: 11/06/20 Subject: FIRE PROTECTION CABINETS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. SHOW DOOR HARDWARE, CABINET TYPE, TRIM STYLE, AND PANEL STYLE. INCLUDE ROUGHING-IN DIMENSIONS AND DETAILS SHOWING MOUNTING METHOD AND RELATIONSHIPS OF BOX AND TRIM TO SURROUNDING CONSTRUCTION. Spec Section: 10 44 13 - FIRE PROTECTION CABINETS Status: OPEN | Info Exchange
| 12139 | Responded and Closed | Approved | 2020-11-03 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-23 |  | 10 44 13-1 FIRE PROTECTION CABINETS - Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-23 |  | 10 44 13-1 FIRE PROTECTION CABINETS - Product Data.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-03 |  | 10 44 13-1 FIRE PROTECTION CABINETS - Product Data-POP.pdf
10 44 13-004-00 | 10 44 13 - FIRE PROTECTION CABINETS | 10 44 13-004-00 FIRE PROTECTION CABINETS - Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 | 2021-04-27 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12469 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-22 | Submittal Number: 10 44 13-4.0 From: KIM DOWALIBY Final Due Date: 04/14/21 Subject: FIRE PROTECTION CABINETS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR FIRE-PROTECTION CABINETS TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 10 44 13 - FIRE PROTECTION CABINETS Status: OPEN | Info Exchange
| 16159 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 10 44 13-4.0 From: KIM DOWALIBY Final Due Date: 04/14/21 Subject: FIRE PROTECTION CABINETS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR FIRE-PROTECTION CABINETS TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 10 44 13 - FIRE PROTECTION CABINETS Status: OPEN | Info Exchange
| 16562 | Responded and Closed | Approved as Noted | 2021-04-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED 1. APPROVED, SUBMIT IN FINAL OM MANUALS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 10 44 13-4 - FIRE PROTECTION CABINETS - Maintenance Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 10 44 13-4 - FIRE PROTECTION CABINETS - Maintenance Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-27 |  | 10 44 13-4 - FIRE PROTECTION CABINETS - Maintenance Data_POP.pdf
10 44 13-005-00 | 10 44 13 - FIRE PROTECTION CABINETS | 10 44 13-005-00 FIRE PROTECTION CABINETS - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-03-08 | 22 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11398 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-03-01 | Submittal Number: 10 44 13-5.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: FIRE PROTECTION CABINETS - SAMPLE Description: Spec Section: 10 44 13 - FIRE PROTECTION CABINETS Status: OPEN | Info Exchange
| 14765 | Forwarded | For Review | 2021-02-13 | Danielle Scott | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 10 44 13-5.0 From: DANIELLE SCOTT Final Due Date: 02/26/21 Subject: FIRE PROTECTION CABINETS - SAMPLE Description: Spec Section: 10 44 13 - FIRE PROTECTION CABINETS Status: OPEN | Info Exchange
| 15348 | Responded and Closed | Approved | 2021-03-08 | Danielle Scott | AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-12 |  | 10 44 13-5 Revision 0 FIRE PROTECTION CABINETS - Sample.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-02-12 |  | 10 44 13-5 Revision 0 FIRE PROTECTION CABINETS - Sample.pdf
| Responded and Closed |  | Danielle Scott | 1 | 2021-03-08 |  | 10 44 13-5 Revision 0 FIRE PROTECTION CABINETS - Sample_POP.pdf
10 44 13-006-00 | 10 44 13 - FIRE PROTECTION CABINETS | 10 44 13-006-00 FIRE PROTECTION CABINETS - Non-Rated Cabinets Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-13 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-27 | 2021-04-27 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12545 | Received | For Review | 2021-04-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-27 | Submittal Number: 10 44 13-6.0 From: KIM DOWALIBY Final Due Date: 04/26/21 Subject: FIRE PROTECTION CABINETS - NON-RATED CABINETS PRODUCT DATA Description: Spec Section: 10 44 13 - FIRE PROTECTION CABINETS Status: OPEN | Info Exchange
| 16245 | Forwarded | For Review | 2021-04-12 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-19 | Submittal Number: 10 44 13-6.0 From: KIM DOWALIBY Final Due Date: 04/26/21 Subject: FIRE PROTECTION CABINETS - NON-RATED CABINETS PRODUCT DATA Description: Spec Section: 10 44 13 - FIRE PROTECTION CABINETS Status: OPEN | Info Exchange
| 16563 | Responded and Closed | Approved | 2021-04-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-12 |  | 10 44 13-6 FIRE PROTECTION CABINETS - Non-Rated Cabinets Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-12 |  | 10 44 13-6 FIRE PROTECTION CABINETS - Non-Rated Cabinets Product Data.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-27 |  | 10 44 13-6 FIRE PROTECTION CABINETS - Non-Rated Cabinets Product Data_POP.pdf
10 44 13-007-00 | 10 44 13 - FIRE PROTECTION CABINETS | 10 44 13-007-00 FIRE PROTECTION CABINETS - Surface Mounted Cabinets and Wall Mounted Brackets - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-10 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-24 | 2021-05-11 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-05-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12988 | Received | For Review | 2021-05-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-24 | Submittal Number: 10 44 13-7.0 From: KIM DOWALIBY Final Due Date: 05/21/21 Subject: FIRE PROTECTION CABINETS - SURFACE MOUNTED CABINETS AND WALL MOUNTED BRACKETS - PRODUCT DATA Description: Spec Section: 10 44 13 - FIRE PROTECTION CABINETS Status: OPEN | Info Exchange
| 16811 | Forwarded | For Review | 2021-05-10 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-17 | Submittal Number: 10 44 13-7.0 From: KIM DOWALIBY Final Due Date: 05/21/21 Subject: FIRE PROTECTION CABINETS - SURFACE MOUNTED CABINETS AND WALL MOUNTED BRACKETS - PRODUCT DATA Description: Spec Section: 10 44 13 - FIRE PROTECTION CABINETS Status: OPEN | Info Exchange
| 16882 | Responded and Closed | Approved as Noted | 2021-05-11 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 10 44 13-7 - FIRE PROTECTION CABINETS - Surface Mounted Cabinets and Wall Mounted Brackets.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-10 |  | 10 44 13-7 - FIRE PROTECTION CABINETS - Surface Mounted Cabinets and Wall Mounted Brackets.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-11 |  | 10 44 13-7 - FIRE PROTECTION CABINETS - Surface Mounted Cabinets and Wall Mounted Brackets_POP.pdf
10 44 16-001-00 | 10 44 16 - FIRE EXTINGUISHERS | 10 44 16-001-00 FIRE EXTINGUISHERS - Product Data & Warranty | Closed | Architectural, Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Nick Theimer (ME Engineers) |  |  |  | 2021-04-19 | 2021-04-21 | 17 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-04-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12370 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 10 44 16-1.0 From: KIM DOWALIBY Final Due Date: 04/14/21 Subject: FIRE EXTINGUISHERS - PRODUCT DATA & WARRANTY Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE RATING AND CLASSIFICATION, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR FIRE EXTINGUISHER AND MOUNTING BRACKETS. Spec Section: 10 44 16 - FIRE EXTINGUISHERS Status: OPEN | Info Exchange
| 16026 | Forwarded | For Review | 2021-04-01 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 10 44 16-1.0 From: KIM DOWALIBY Final Due Date: 04/14/21 Subject: FIRE EXTINGUISHERS - PRODUCT DATA & WARRANTY Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE RATING AND CLASSIFICATION, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR FIRE EXTINGUISHER AND MOUNTING BRACKETS. Spec Section: 10 44 16 - FIRE EXTINGUISHERS Status: OPEN | Info Exchange
| 16063 | Forwarded | For Review | 2021-04-05 | Populous SCA_CCA | Bryan Klote (Populous); Nick Theimer (ME Engineers) | 2021-04-12 | Submittal Number: 10 44 16-1.0 From: KIM DOWALIBY Final Due Date: 04/14/21 Subject: FIRE EXTINGUISHERS - PRODUCT DATA & WARRANTY Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. INCLUDE RATING AND CLASSIFICATION, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR FIRE EXTINGUISHER AND MOUNTING BRACKETS. Spec Section: 10 44 16 - FIRE EXTINGUISHERS Status: OPEN | Info Exchange
| 16424 | Responded and Closed | Approved as Noted | 2021-04-21 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. REVISE TYPE A,B,C TO 10LB PER SPEC 10 44 16 - 1.1-A TYPE K APPROVED AS SUBMITTED 2. COORDINATE 10 44 13 CABINET SIZE WITH FIRE EXTINGUISHER SIZES | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 10 44 16-1 - Fire Extinguishers - Product Data & Warranty.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 10 44 16-1 - Fire Extinguishers - Product Data & Warranty.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-31 02:00 |  | 10 44 16-1 - Fire Extinguishers - Product Data & Warranty.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-21 |  | 10 44 16-1 - Fire Extinguishers - Product Data & Warranty_POP.pdf
10 51 13-001-00 | 10 51 13 - METAL LOCKERS | 10 51 13-001-00 METAL LOCKERS - Product Data, Warranty, Test Reports | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-20 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-04 07:00 | 2021-06-04 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13204 | Received | For Review | 2021-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-04 07:00 | Submittal Number: 10 51 13-1.0 From: KIM DOWALIBY Final Due Date: 06/03/21 Subject: METAL LOCKERS - PRODUCT DATA, WARRANTY, TEST REPORTS Description: PRODUCT DATA : FOR EACH TYPE OF METAL LOCKER. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR EACH TYPE OF METAL LOCKER AND BENCH INCLUDING MAINTENANCE DATA FOR ADJUSTING, REPAIRING, AND REPLACING LOCKER DOORS AND LATCHING MECHANISMS TO INCLUDE IN MAINTENANCE MANUALS SPECIFIED IN DIVISION 01. Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 17092 | Forwarded | For Review | 2021-05-20 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-27 | Submittal Number: 10 51 13-1.0 From: KIM DOWALIBY Final Due Date: 06/03/21 Subject: METAL LOCKERS - PRODUCT DATA, WARRANTY, TEST REPORTS Description: PRODUCT DATA : FOR EACH TYPE OF METAL LOCKER. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR EACH TYPE OF METAL LOCKER AND BENCH INCLUDING MAINTENANCE DATA FOR ADJUSTING, REPAIRING, AND REPLACING LOCKER DOORS AND LATCHING MECHANISMS TO INCLUDE IN MAINTENANCE MANUALS SPECIFIED IN DIVISION 01. Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 13409 | Review Response | Approved as Noted | 2021-06-04 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17343 | Responded and Closed | Approved as Noted | 2021-06-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-20 |  | 10 51 13-1 - METAL LOCKERS - Product Data Warranty Test Reports.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-20 |  | 10 51 13-1 - METAL LOCKERS - Product Data Warranty Test Reports.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-04 |  | 10 51 13-1 - METAL LOCKERS - Product Data Warranty Test Reports_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-20 |  | 10 51 13-1 - METAL LOCKERS - Product Data Warranty Test Reports.pdf
10 51 13-007-00 | 10 51 13 - METAL LOCKERS | 10 51 13-007-00 METAL LOCKERS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-21 | 2020-12-24 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-12-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09933 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-21 | Submittal Number: 10 51 13-7.0 From: DANIELLE SCOTT Final Due Date: 12/18/20 Subject: METAL LOCKERS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR METAL LOCKERS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. 2. SHOW LOCKER TRIM AND ACCESSORIES. 3. INCLUDE LOCKER IDENTIFICATION SYSTEM AND NUMBERING SEQUENCE. Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 13011 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-14 | Submittal Number: 10 51 13-7.0 From: DANIELLE SCOTT Final Due Date: 12/18/20 Subject: METAL LOCKERS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR METAL LOCKERS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. 2. SHOW LOCKER TRIM AND ACCESSORIES. 3. INCLUDE LOCKER IDENTIFICATION SYSTEM AND NUMBERING SEQUENCE. Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 10353 | Review Response | Approved as Noted/Resubmit | 2020-12-24 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13526 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-24 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-04 |  | 10 51 13 Metal Lockers - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-04 |  | 10 51 13 Metal Lockers - Shop Drawings.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-24 |  | 10 51 13 Metal Lockers - Shop Drawings_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-12-04 |  | 10 51 13 Metal Lockers - Shop Drawings.pdf
10 51 13-007-01 | 10 51 13 - METAL LOCKERS | 10 51 13-007-01 METAL LOCKERS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-27 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-10 | 2021-02-04 | 9 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10976 | Received | For Review | 2021-01-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-02-10 | Submittal Number: 10 51 13-7.1 From: DANIELLE SCOTT Final Due Date: 02/09/21 Subject: METAL LOCKERS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR METAL LOCKERS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. 2. SHOW LOCKER TRIM AND ACCESSORIES. 3. INCLUDE LOCKER IDENTIFICATION SYSTEM AND NUMBERING SEQUENCE. Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 14255 | Forwarded | For Review | 2021-01-26 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-02 | Submittal Number: 10 51 13-7.1 From: DANIELLE SCOTT Final Due Date: 02/09/21 Subject: METAL LOCKERS - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR METAL LOCKERS. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. 2. SHOW LOCKER TRIM AND ACCESSORIES. 3. INCLUDE LOCKER IDENTIFICATION SYSTEM AND NUMBERING SEQUENCE. Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 11219 | Review Response | Approved as Noted | 2021-02-04 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14518 | Responded and Closed | Approved as Noted | 2021-02-04 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-26 |  | 10 51 13 - Revision 1 Metal Locker Submittal 1.22.21 (002).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-26 |  | 10 51 13 - Revision 1 Metal Locker Submittal 1.22.21 (002).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-04 |  | 10 51 13 - Revision 1 Metal Locker Submittal 1.22.21_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-01-26 |  | 10 51 13 - Revision 1 Metal Locker Submittal 1.22.21 (002).pdf
10 51 13-008-00 | 10 51 13 - METAL LOCKERS | 10 51 13-008-00 METAL LOCKERS - Samples for Initial Selection | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-07 | 2020-12-09 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-12-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09607 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2020-12-07 | Submittal Number: 10 51 13-8.0 From: DANIELLE SCOTT Final Due Date: 12/03/20 Subject: METAL LOCKERS - SAMPLES FOR INITIAL SELECTION Description: COLOR CHART FOR INITIAL SELECTION PROVIDED. AFTER THE INITIAL COLOR SELECTION, OUR TRADE PARTNER WILL SEND A PHYSICAL SAMPLE(S) OF THE COLOR(S). Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 12642 | Forwarded | For Review | 2020-11-19 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-26 | Submittal Number: 10 51 13-8.0 From: DANIELLE SCOTT Final Due Date: 12/03/20 Subject: METAL LOCKERS - SAMPLES FOR INITIAL SELECTION Description: COLOR CHART FOR INITIAL SELECTION PROVIDED. AFTER THE INITIAL COLOR SELECTION, OUR TRADE PARTNER WILL SEND A PHYSICAL SAMPLE(S) OF THE COLOR(S). Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 10051 | Review Response | Approved as Noted | 2020-12-09 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13151 | Responded and Closed | Approved as Noted | 2020-12-09 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-19 |  | 10 51 13 Metal Lockers - Samples for Initial Selection.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-19 |  | 10 51 13 Metal Lockers - Samples for Initial Selection.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-09 |  | 10 51 13 Metal Lockers - Samples for Initial Selection_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-19 |  | 10 51 13 Metal Lockers - Samples for Initial Selection.pdf
10 51 13-011-00 | 10 51 13 - METAL LOCKERS | 10 51 13-011-00 METAL LOCKERS - Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-22 | 2021-04-15 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12468 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-22 | Submittal Number: 10 51 13-11.0 From: KIM DOWALIBY Final Due Date: 04/14/21 Subject: METAL LOCKERS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR ADJUSTING, REPAIRING, AND REPLACING LOCKER DOORS AND LATCHING MECHANISMS TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 16158 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-15 | Submittal Number: 10 51 13-11.0 From: KIM DOWALIBY Final Due Date: 04/14/21 Subject: METAL LOCKERS - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR ADJUSTING, REPAIRING, AND REPLACING LOCKER DOORS AND LATCHING MECHANISMS TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 12616 | Review Response | Approved as Noted | 2021-04-15 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | This submittal is approved as noted. Final approval pending submittal of O&M manuals per section 01 78 23. | Info Exchange
| 16334 | Responded and Closed | Approved as Noted | 2021-04-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: This submittal is approved as noted. Final approval pending submittal of O&M manuals per section 01 78 23. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 10 51 13 Metal Lockers - Maintenance Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 10 51 13 Metal Lockers - Maintenance Data.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-15 |  | 10 51 13 Metal Lockers - Maintenance Data_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 10 51 13 Metal Lockers - Maintenance Data.pdf
10 51 13-013-00 | 10 51 13 - METAL LOCKERS | 10 51 13-013-00 Metal Locker Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-11 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-25 | 2021-02-19 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-02-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11335 | Received | For Review | 2021-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-25 | Submittal Number: 10 51 13-13.0 From: DANIELLE SCOTT Final Due Date: 02/24/21 Subject: METAL LOCKER SAMPLE Description: Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 14694 | Forwarded | For Review | 2021-02-11 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-18 | Submittal Number: 10 51 13-13.0 From: DANIELLE SCOTT Final Due Date: 02/24/21 Subject: METAL LOCKER SAMPLE Description: Spec Section: 10 51 13 - METAL LOCKERS Status: OPEN | Info Exchange
| 11535 | Review Response | Approved | 2021-02-19 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14953 | Responded and Closed | Approved | 2021-02-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-10 |  | 10 51 13-13 Revision 0 Metal Locker Sample.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-10 |  | 10 51 13-13 Revision 0 Metal Locker Sample.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-19 |  | 10 51 13-13 Revision 0 Metal Locker Sample_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-10 |  | 10 51 13-13 Revision 0 Metal Locker Sample.pdf
11 12 43-010-00 | 11 12 43 - VEHICLE BARRIER SYSTEMS | 11 12 43-010-00 Wedge Barrier Submittal Package | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-14 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Abby Harrison (ME Engineers) |  |  |  | 2020-07-28 | 2020-08-11 | 29 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-08-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06934 | Received | For Review | 2020-07-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-07-28 | Submittal Number: 11 12 43-10.0 From: CHRISTIAN ALBERS Final Due Date: 07/27/20 Subject: WEDGE BARRIER SUBMITTAL PACKAGE Description: PLEASE SEE ATTACHED SHOP DRAWINGS AND PRODUCT DATA FOR WEDGE BARRIER SYSTEM. Spec Section: 11 12 43 - VEHICLE BARRIER SYSTEMS Status: OPEN | Info Exchange
| 09289 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-07-20 | Submittal Number: 11 12 43-10.0 From: CHRISTIAN ALBERS Final Due Date: 07/27/20 Subject: WEDGE BARRIER SUBMITTAL PACKAGE Description: PLEASE SEE ATTACHED SHOP DRAWINGS AND PRODUCT DATA FOR WEDGE BARRIER SYSTEM. Spec Section: 11 12 43 - VEHICLE BARRIER SYSTEMS Status: OPEN | Info Exchange
| 09434 | Sent | For Information Only | 2020-07-20 | Tom Usher (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory) |  | Hi Elliott - I thought you might want to take a look at the wedge barrier submittal. Upon initial review, I noticed two things... 1. There is a wall-mounted control panel in the tunnel (page 5) - and I am not sure that is where it should be located. 2. There is a traffic signal we need to locate as well. We talked about having a second one at the bottom of the tunnel (given the steep incline). I'm just familiarizing myself with page 23 which appears to describe everything we need. I'll keep reading and perhaps we can discuss later in the week. | Info Exchange
| 09478 | Forwarded | For Review | 2020-07-22 | Bryan Klote (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Abby Harrison (ME Engineers) |  | Submittal Number: 11 12 43-10.0 From: CHRISTIAN ALBERS Final Due Date: 07/27/20 Subject: WEDGE BARRIER SUBMITTAL PACKAGE Description: PLEASE SEE ATTACHED SHOP DRAWINGS AND PRODUCT DATA FOR WEDGE BARRIER SYSTEM. Spec Section: 11 12 43 - VEHICLE BARRIER SYSTEMS Status: OPEN | Info Exchange
| 07514 | Review Response | Approved as Noted | 2020-07-31 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.31 | Info Exchange
| 10006 | Responded and Closed | Approved as Noted | 2020-08-11 | Tom Usher (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.31 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 11 12 43 - 10 Wedge Barrier Submittal Package.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 11 12 43 - 10 Wedge Barrier Submittal Package.pdf
| Sent |  | Tom Usher (Populous) | 1 | 2020-07-13 |  | 11 12 43 - 10 Wedge Barrier Submittal Package.pdf
| Forwarded |  | Bryan Klote (Populous) | 1 | 2020-07-13 |  | 11 12 43 - 10 Wedge Barrier Submittal Package.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-12 02:00 |  | 11 12 43 - 10 Wedge Barrier Submittal Package.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2020-08-10 02:00 |  | 11 12 43 - 10 Wedge Barrier Submittal Package - ME Review_POP.pdf
11 12 43-011-00 | 11 12 43 - VEHICLE BARRIER SYSTEMS | 11 12 43-011-00 Bollard Product Data: Deep, Shallow, and Ultra Shallow | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-23 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-12-09 | 2020-12-09 | 17 |  | Record Copies; Transfers; Submittals | 11 12 43-011-00-01 - 11 12 43-011-00 Bollard Product Data: Deep, Shallow, and Ultra Shallow | 17 |  | 2020-12-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09658 | Received | For Review | 2020-11-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (M.A. Mortenson Company) | 2020-12-09 | Submittal Number: 11 12 43-11.0 From: CHRISTIAN ALBERS Final Due Date: 12/05/20 Subject: BOLLARD PRODUCT DATA: DEEP, SHALLOW, AND ULTRA SHALLOW Description: SEE PRODUCT DATA RECEIVED FROM PERIMETER SECURITY FOR DEEP MOUNT, SHALLOW MOUNT, AND ULTRA SHALLOW MOUNT BOLLARDS. Spec Section: 11 12 43 - VEHICLE BARRIER SYSTEMS Status: OPEN | Info Exchange
| 12709 | Forwarded | For Review | 2020-11-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-30 | Submittal Number: 11 12 43-11.0 From: CHRISTIAN ALBERS Final Due Date: 12/05/20 Subject: BOLLARD PRODUCT DATA: DEEP, SHALLOW, AND ULTRA SHALLOW Description: SEE PRODUCT DATA RECEIVED FROM PERIMETER SECURITY FOR DEEP MOUNT, SHALLOW MOUNT, AND ULTRA SHALLOW MOUNT BOLLARDS. Spec Section: 11 12 43 - VEHICLE BARRIER SYSTEMS Status: OPEN | Info Exchange
| 10072 | Review Response | Approved as Noted/Resubmit | 2020-12-09 | Tom Usher (Populous) | Shaina Burris (Populous) |  | CONFIRM OPERABLE BOLLARD KEYING REQUIREMENTS W/ OWNER. ARCHITECT UNDERSTANDS FOOTING SIZES INDICATED CAN BE ADJUSTED TO ACCOMMODATE FIELD CONDITIONS. EXPOSED BOLLARD SURFACES TO BE STAINLESS STEEL. THIS SUBMITTAL IS APPROVED AS NOTED. RESUBMIT PORTION ALLOWS US TO TRACK REMAINING ITEMS YET TO BE SUBMITTED. | Info Exchange
| 13170 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-09 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Tom Usher (Populous) Remarks: CONFIRM OPERABLE BOLLARD KEYING REQUIREMENTS W/ OWNER. ARCHITECT UNDERSTANDS FOOTING SIZES INDICATED CAN BE ADJUSTED TO ACCOMMODATE FIELD CONDITIONS. EXPOSED BOLLARD SURFACES TO BE STAINLESS STEEL. THIS SUBMITTAL IS APPROVED AS NOTED. RESUBMIT PORTION ALLOWS US TO TRACK REMAINING ITEMS YET TO BE SUBMITTED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-21 |  | 11 12 43 - 0011 - Bollard Product Data - Deep Shallow and Ultra Shallow.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-21 |  | 11 12 43 - 0011 - Bollard Product Data - Deep Shallow and Ultra Shallow.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2020-12-09 02:00 |  | 11 12 43 - 0011 - Bollard Product Data - Deep Shallow and Ultra Shallow_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-20 02:00 |  | 11 12 43 - 0011 - Bollard Product Data - Deep Shallow and Ultra Shallow.pdf
11 12 43-011-00-01 | 11 12 43 - VEHICLE BARRIER SYSTEMS | 11 12 43-011-00 Bollard Product Data: Deep, Shallow, and Ultra Shallow | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 12 43-011-00 - 11 12 43-011-00 Bollard Product Data: Deep, Shallow, and Ultra Shallow | -1 | 2020-12-23
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-20 02:00 |  | 11 12 43 - 0011 - Bollard Product Data - Deep Shallow and Ultra Shallow.pdf
11 13 16-005-00 | 11 13 16 - LOADING DOCK SEALS AND SHELTERS | 11 13 16-005-00 Dock Sealers Product Data and Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-23 | Responded and Closed - Approved |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-06 | 2020-02-13 | 22 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-02-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04024 | Received | For Review | 2020-01-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers | 2020-02-06 | Submittal Number: 11 13 16-5.0 From: CHRISTIAN ALBERS Final Due Date: 02/05/20 Subject: DOCK SEALERS PRODUCT DATA AND SHOP DRAWINGS Description: Spec Section: 11 13 16 - LOADING DOCK SEALS AND SHELTERS Status: OPEN | Info Exchange
| 05611 | Forwarded | For Review | 2020-01-22 | Shaina Burris (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-01-29 | Submittal Number: 11 13 16-5.0 From: CHRISTIAN ALBERS Final Due Date: 02/05/20 Subject: DOCK SEALERS PRODUCT DATA AND SHOP DRAWINGS Description: Spec Section: 11 13 16 - LOADING DOCK SEALS AND SHELTERS Status: OPEN | Info Exchange
| 06012 | Responded and Closed | Approved | 2020-02-13 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-22 |  | 11 13 16 - 05 - Dock Sealers Product Data and Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-22 |  | 11 13 16 - 05 - Dock Sealers Product Data and Shop Drawings.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-01-22 |  | Transmittal_Submittal - 11 13 16-005-00 (Forwarded).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-02-13 |  | 11 13 16 - 05 - Dock Sealers Product Data and Shop Drawings-POP.pdf
11 13 19-010-00 | 11 13 19 - STATIONARY LOADING DOCK EQUIPMENT | 11 13 19-010-00 Dock Leveler Product Data and Layout | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-23 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-06 | 2020-02-13 | 22 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-02-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04020 | Received | For Review | 2020-01-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers | 2020-02-06 | Submittal Number: 11 13 19-10.0 From: CHRISTIAN ALBERS Final Due Date: 02/05/20 Subject: DOCK LEVELER PRODUCT DATA AND LAYOUT Description: Spec Section: 11 13 19 - STATIONARY LOADING DOCK EQUIPMENT Status: OPEN | Info Exchange
| 05606 | Forwarded | For Review | 2020-01-22 | Shaina Burris (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-01-29 | Submittal Number: 11 13 19-10.0 From: CHRISTIAN ALBERS Final Due Date: 02/05/20 Subject: DOCK LEVELER PRODUCT DATA AND LAYOUT Description: Spec Section: 11 13 19 - STATIONARY LOADING DOCK EQUIPMENT Status: OPEN | Info Exchange
| 06011 | Responded and Closed | Approved as Noted | 2020-02-13 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE CONFIRM WARRANTY STATUS PER NOTE. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-22 |  | 11 13 19 - 10 - Dock Leveler Product Data and Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-22 |  | 11 13 19 - 10 - Dock Leveler Product Data and Shop Drawings.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-01-22 |  | Transmittal_Submittal - 11 13 19-010-00 (Forwarded).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-02-13 |  | 11 13 19 - 10 - Dock Leveler Product Data and Shop Drawings-POP.pdf
11 13 19-011-00 | 11 13 19 - STATIONARY LOADING DOCK EQUIPMENT | 11 13 19-011-00 Truck Restraints and Light Communication System Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-23 | Responded and Closed - Approved |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-02-06 | 2020-02-13 | 22 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-02-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04023 | Received | For Review | 2020-01-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers | 2020-02-06 | Submittal Number: 11 13 19-11.0 From: CHRISTIAN ALBERS Final Due Date: 02/05/20 Subject: TRUCK RESTRAINTS AND LIGHT COMMUNICATION SYSTEM PRODUCT DATA Description: Spec Section: 11 13 19 - STATIONARY LOADING DOCK EQUIPMENT Status: OPEN | Info Exchange
| 05610 | Forwarded | For Review | 2020-01-22 | Shaina Burris (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-01-29 | Submittal Number: 11 13 19-11.0 From: CHRISTIAN ALBERS Final Due Date: 02/05/20 Subject: TRUCK RESTRAINTS AND LIGHT COMMUNICATION SYSTEM PRODUCT DATA Description: Spec Section: 11 13 19 - STATIONARY LOADING DOCK EQUIPMENT Status: OPEN | Info Exchange
| 06010 | Responded and Closed | Approved | 2020-02-13 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-22 |  | 11 13 19 - 11 - Truck Restraints and Light Communication System Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-22 |  | 11 13 19 - 11 - Truck Restraints and Light Communication System Product Data.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-02-13 |  | 11 13 19 - 11 - Truck Restraints and Light Communication System Product Data-POP.pdf
11 24 29-001-00 | 11 24 29 - FACILITY FALL PROTECTION | 11 24 29-001-00 FACILITY FALL PROTECTION - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-12-03 | 2020-12-17 | 31 |  | Record Copies; Transfers; Submittals |  | 31 |  | 2020-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09502 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Koch (CAA ICON / Strategy Advisory) | 2020-12-03 | Submittal Number: 11 24 29-1.0 From: CODY KOCH Final Due Date: 12/10/20 Subject: FACILITY FALL PROTECTION - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES. 2. INCLUDE RATED CAPACITIES, OPERATING CHARACTERISTICS, AND FURNISHED SPECIALTIES AND ACCESSORIES. Spec Section: 11 24 29 - FACILITY FALL PROTECTION Status: OPEN | Info Exchange
| 12523 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-24 | Submittal Number: 11 24 29-1.0 From: CODY KOCH Final Due Date: 12/10/20 Subject: FACILITY FALL PROTECTION - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES. 2. INCLUDE RATED CAPACITIES, OPERATING CHARACTERISTICS, AND FURNISHED SPECIALTIES AND ACCESSORIES. Spec Section: 11 24 29 - FACILITY FALL PROTECTION Status: OPEN | Info Exchange
| 12898 | Forwarded | For Review | 2020-12-02 | Todd Spangler (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2020-12-03 | Submittal Number: 11 24 29-1.0 From: CODY KOCH Final Due Date: 12/10/20 Subject: FACILITY FALL PROTECTION - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES. 2. INCLUDE RATED CAPACITIES, OPERATING CHARACTERISTICS, AND FURNISHED SPECIALTIES AND ACCESSORIES. Spec Section: 11 24 29 - FACILITY FALL PROTECTION Status: OPEN | Info Exchange
| 13375 | Responded and Closed | Approved | 2020-12-17 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Koch (CAA ICON / Strategy Advisory) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | Evan- Climate Pledge Arena Product Data Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | Evan- Climate Pledge Arena Product Data Submittal.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-11-17 |  | Evan- Climate Pledge Arena Product Data Submittal.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | Evan- Climate Pledge Arena Product Data Submittal.pdf
11 24 29-002-00 | 11 24 29 - FACILITY FALL PROTECTION | 11 24 29-002-00 FACILITY FALL PROTECTION - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-12-03 | 2020-12-17 | 31 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2020-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09501 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Koch (CAA ICON / Strategy Advisory) | 2020-12-03 | Submittal Number: 11 24 29-2.0 From: CODY KOCH Final Due Date: 12/10/20 Subject: FACILITY FALL PROTECTION - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 2. INCLUDE DETAILS OF EQUIPMENT ASSEMBLIES. INDICATE DIMENSIONS, WEIGHTS, LOADS, REQUIRED CLEARANCES, METHOD OF FIELD ASSEMBLY, COMPONENTS, AND LOCATION AND SIZE OF EACH FIELD CONNECTION. Spec Section: 11 24 29 - FACILITY FALL PROTECTION Status: OPEN | Info Exchange
| 12522 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-24 | Submittal Number: 11 24 29-2.0 From: CODY KOCH Final Due Date: 12/10/20 Subject: FACILITY FALL PROTECTION - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 2. INCLUDE DETAILS OF EQUIPMENT ASSEMBLIES. INDICATE DIMENSIONS, WEIGHTS, LOADS, REQUIRED CLEARANCES, METHOD OF FIELD ASSEMBLY, COMPONENTS, AND LOCATION AND SIZE OF EACH FIELD CONNECTION. Spec Section: 11 24 29 - FACILITY FALL PROTECTION Status: OPEN | Info Exchange
| 12897 | Forwarded | For Review | 2020-12-02 | Todd Spangler (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2020-12-03 | Submittal Number: 11 24 29-2.0 From: CODY KOCH Final Due Date: 12/10/20 Subject: FACILITY FALL PROTECTION - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 2. INCLUDE DETAILS OF EQUIPMENT ASSEMBLIES. INDICATE DIMENSIONS, WEIGHTS, LOADS, REQUIRED CLEARANCES, METHOD OF FIELD ASSEMBLY, COMPONENTS, AND LOCATION AND SIZE OF EACH FIELD CONNECTION. Spec Section: 11 24 29 - FACILITY FALL PROTECTION Status: OPEN | Info Exchange
| 10181 | Review Response | Approved as Noted | 2020-12-15 | Tom Usher (Populous) | Chris Minter (Populous); Josh Dobken (Populous) |  | Fall arrest contractor to submit calcs for this system for EOR to review and approve. TT has only reviewed these drawings for locations of stanchions and loads imposed. Matt Ross (Thornton Tomasetti) All painted steel is to match the rigging grid: SW 7674 Peppercorn Tom Usher (Populous) Chris Minter is checking Milwaukee for cable clearances above rigging grid and catwalk. | Info Exchange
| 13376 | Responded and Closed | Approved as Noted | 2020-12-17 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Koch (CAA ICON / Strategy Advisory) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | Evan-Climate Pledge Arena Rigging for Review & Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | Evan-Climate Pledge Arena Rigging for Review & Approval.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2020-11-17 |  | Evan-Climate Pledge Arena Rigging for Review & Approval.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2020-11-17 |  | Evan-Climate Pledge Arena Rigging for Review & Approval.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | Evan-Climate Pledge Arena Rigging for Review & Approval.pdf
11 24 29-002-01 | 11 24 29 - FACILITY FALL PROTECTION | 11 24 29-002-01 FACILITY FALL PROTECTION - Shop Drawings | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-05 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2021-05-19 | 2021-05-18 | 14 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12950 | Received | For Review | 2021-05-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Koch (CAA ICON / Strategy Advisory) | 2021-05-19 | Submittal Number: 11 24 29-2.1 From: CODY KOCH Final Due Date: 12/10/20 Subject: FACILITY FALL PROTECTION - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 2. INCLUDE DETAILS OF EQUIPMENT ASSEMBLIES. INDICATE DIMENSIONS, WEIGHTS, LOADS, REQUIRED CLEARANCES, METHOD OF FIELD ASSEMBLY, COMPONENTS, AND LOCATION AND SIZE OF EACH FIELD CONNECTION. Spec Section: 11 24 29 - FACILITY FALL PROTECTION Status: OPEN | Info Exchange
| 16748 | Forwarded | For Review | 2021-05-05 | Cody Koch (CAA ICON / Strategy Advisory) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-12 | Submittal Number: 11 24 29-2.1 From: CODY KOCH Final Due Date: 12/10/20 Subject: FACILITY FALL PROTECTION - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 2. INCLUDE DETAILS OF EQUIPMENT ASSEMBLIES. INDICATE DIMENSIONS, WEIGHTS, LOADS, REQUIRED CLEARANCES, METHOD OF FIELD ASSEMBLY, COMPONENTS, AND LOCATION AND SIZE OF EACH FIELD CONNECTION. Spec Section: 11 24 29 - FACILITY FALL PROTECTION Status: OPEN | Info Exchange
| 16826 | Forwarded | For Review | 2021-05-10 | Cody Koch (CAA ICON / Strategy Advisory) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2021-05-17 | Submittal Number: 11 24 29-2.1 From: CODY KOCH Final Due Date: 12/10/20 Subject: FACILITY FALL PROTECTION - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND ATTACHMENT DETAILS. 2. INCLUDE DETAILS OF EQUIPMENT ASSEMBLIES. INDICATE DIMENSIONS, WEIGHTS, LOADS, REQUIRED CLEARANCES, METHOD OF FIELD ASSEMBLY, COMPONENTS, AND LOCATION AND SIZE OF EACH FIELD CONNECTION. Spec Section: 11 24 29 - FACILITY FALL PROTECTION Status: OPEN | Info Exchange
| 13154 | Review Response | Approved | 2021-05-13 | Matt Ross (Thornton Tomasetti) | Cody Koch (CAA ICON / Strategy Advisory) |  | TT has no exceptions with calcs provided. | Info Exchange
| 17025 | Responded and Closed | Approved | 2021-05-18 | Cody Koch (CAA ICON / Strategy Advisory) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-05 |  | Evan- Climate Pledge Arena Calculations.pdf
| Forwarded |  | Cody Koch (CAA ICON / Strategy Advisory) | 1 | 2021-05-05 |  | Evan- Climate Pledge Arena Calculations.pdf
| Forwarded |  | Cody Koch (CAA ICON / Strategy Advisory) | 1 | 2021-05-04 02:00 |  | Evan- Climate Pledge Arena Calculations.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-05 |  | Evan- Climate Pledge Arena Calculations.pdf
| Responded and Closed |  | Cody Koch (CAA ICON / Strategy Advisory) | 1 | 2021-05-13 |  | 11 24 29-002-01 Evan- Climate Pledge Arena Calculations_TT.pdf
| Responded and Closed |  | Cody Koch (CAA ICON / Strategy Advisory) | 1 | 2021-05-18 |  | 11 24 29-002-01 Evan- Climate Pledge Arena Calculations_TT-POP.pdf
11 40 00-001-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-001-00 Underground MEP Rough-In Drawings Package 1 | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-21 | Responded and Closed - Revise and Resubmit |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-06-05 07:00 | 2020-06-02 | 13 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-06-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05968 | Received | For Review | 2020-05-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-06-05 07:00 | Submittal Number: 11 40 00-1.0 From: JOSH BROUSSARD Final Due Date: 06/03/20 Subject: UNDERGROUND MEP ROUGH-IN DRAWINGS PACKAGE 1 Description: INCLUDED ARE UNDERGROUND ROUGH-IN DRAWINGS FOR THE TUNNEL CLUBS, THE NE AND NW GRAB-N-GO'S, THE CHAIRMAN'S CLUB, AND THE CREW KITCHEN. THESE DRAWINGS HAVE BEEN COORDINATE AND REVIEWED WITH THE MEP TRADE PARTNERS, DESIGN TEAM, AND OWNER REPRESENTATION DURING THE 05/07/20 AND 04/14/20 FOOD SERVICE COORDINATION MEETINGS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08102 | Forwarded | For Review | 2020-05-20 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-05-27 | Submittal Number: 11 40 00-1.0 From: JOSH BROUSSARD Final Due Date: 06/03/20 Subject: UNDERGROUND MEP ROUGH-IN DRAWINGS PACKAGE 1 Description: INCLUDED ARE UNDERGROUND ROUGH-IN DRAWINGS FOR THE TUNNEL CLUBS, THE NE AND NW GRAB-N-GO'S, THE CHAIRMAN'S CLUB, AND THE CREW KITCHEN. THESE DRAWINGS HAVE BEEN COORDINATE AND REVIEWED WITH THE MEP TRADE PARTNERS, DESIGN TEAM, AND OWNER REPRESENTATION DURING THE 05/07/20 AND 04/14/20 FOOD SERVICE COORDINATION MEETINGS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06144 | Review Response | Approved | 2020-05-21 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 08247 | Forwarded | For Review | 2020-05-28 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-1.0 From: JOSH BROUSSARD Final Due Date: 06/03/20 Subject: UNDERGROUND MEP ROUGH-IN DRAWINGS PACKAGE 1 Description: INCLUDED ARE UNDERGROUND ROUGH-IN DRAWINGS FOR THE TUNNEL CLUBS, THE NE AND NW GRAB-N-GO'S, THE CHAIRMAN'S CLUB, AND THE CREW KITCHEN. THESE DRAWINGS HAVE BEEN COORDINATE AND REVIEWED WITH THE MEP TRADE PARTNERS, DESIGN TEAM, AND OWNER REPRESENTATION DURING THE 05/07/20 AND 04/14/20 FOOD SERVICE COORDINATION MEETINGS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06145 | Review Response | Revise and Resubmit | 2020-06-02 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.02 | Info Exchange
| 08327 | Responded and Closed | Revise and Resubmit | 2020-06-02 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Revise and Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-20 |  | 11 40 00-1.0 Underground MEP Rough-In Drawings Package 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-20 |  | 11 40 00-1.0 Underground MEP Rough-In Drawings Package 1.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-05-20 |  | 11 40 00-1.0 Underground MEP Rough-In Drawings Package 1.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-05-20 |  | 11 40 00-1.0 Underground MEP Rough-In Drawings Package 1.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-20 |  | 11 40 00-1.0 Underground MEP Rough-In Drawings Package 1.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-06-02 |  | 11 40 00-1.0 Underground MEP Rough-In Drawings Package 1_S2O_MEE_POP.pdf
11 40 00-001-01 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-001-01 Underground MEP Rough-In Drawings Package 1 Rev 1 | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-16 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Heidi Evans (ME Engineers) |  |  |  | 2020-06-30 | 2020-06-26 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-06-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06435 | Received | For Review | 2020-06-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-06-30 | Submittal Number: 11 40 00-1.1 From: JOSH BROUSSARD Final Due Date: 06/30/20 Subject: UNDERGROUND MEP ROUGH-IN DRAWINGS PACKAGE 1 REV 1 Description: REVISIONS TO UNDERGROUND ROUGH-IN DRAWINGS FOR THE TUNNEL CLUBS, THE NE AND NW GRAB-N-GO'S, THE CHAIRMAN'S CLUB, AND THE CREW KITCHEN TO ADDRESS REV0 REVIEW COMMENTS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08675 | Forwarded | For Review | 2020-06-16 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Mark Lievens (ME Engineers); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Heidi Evans (ME Engineers) | 2020-06-23 | Submittal Number: 11 40 00-1.1 From: JOSH BROUSSARD Final Due Date: 06/30/20 Subject: UNDERGROUND MEP ROUGH-IN DRAWINGS PACKAGE 1 REV 1 Description: REVISIONS TO UNDERGROUND ROUGH-IN DRAWINGS FOR THE TUNNEL CLUBS, THE NE AND NW GRAB-N-GO'S, THE CHAIRMAN'S CLUB, AND THE CREW KITCHEN TO ADDRESS REV0 REVIEW COMMENTS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06627 | Review Response | Approved as Noted | 2020-06-20 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  | MEP to verify all underground routes are acceptable | Info Exchange
| 06629 | Review Response | Approved as Noted | 2020-06-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.23 | Info Exchange
| 08934 | Responded and Closed | Approved as Noted | 2020-06-26 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: MEP to verify all underground routes are acceptable Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-16 |  | 11 40 00-1.1 UG MEP Rough-In Drawings Package 1 Rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-16 |  | 11 40 00-1.1 UG MEP Rough-In Drawings Package 1 Rev 1.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-06-16 |  | 11 40 00-1.1 UG MEP Rough-In Drawings Package 1 Rev 1.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-06-16 |  | 11 40 00-1.1 UG MEP Rough-In Drawings Package 1 Rev 1.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-06-26 |  | 11 40 00-1.1 UG MEP Rough-In Drawings Package 1 Rev 1_S2O_ME_POP.pdf
11 40 00-002-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-002-00 Eagle Floor Trough Shop Drawings | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-27 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Dave Ferguson (ME Engineers) |  |  |  | 2020-06-10 | 2020-06-02 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-06-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06065 | Received | For Review | 2020-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-06-10 | Submittal Number: 11 40 00-2.0 From: TOM DUFON Final Due Date: 06/10/20 Subject: EAGLE FLOOR TROUGH SHOP DRAWINGS Description: THIS SUBMITTAL INCLUDES ALL FLOOR TROUGHS FOR THE PROJECT WHICH ARE ALL LOCATED IN THE MAIN KITCHEN (FS3-1.01) Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08218 | Forwarded | For Review | 2020-05-27 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-06-03 | Submittal Number: 11 40 00-2.0 From: TOM DUFON Final Due Date: 06/10/20 Subject: EAGLE FLOOR TROUGH SHOP DRAWINGS Description: THIS SUBMITTAL INCLUDES ALL FLOOR TROUGHS FOR THE PROJECT WHICH ARE ALL LOCATED IN THE MAIN KITCHEN (FS3-1.01) Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06153 | Review Response | Approved as Noted | 2020-05-28 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 08291 | Forwarded | For Review | 2020-06-01 | Kelsea Conkright (Populous) | Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-2.0 From: TOM DUFON Final Due Date: 06/10/20 Subject: EAGLE FLOOR TROUGH SHOP DRAWINGS Description: THIS SUBMITTAL INCLUDES ALL FLOOR TROUGHS FOR THE PROJECT WHICH ARE ALL LOCATED IN THE MAIN KITCHEN (FS3-1.01) Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06155 | Review Response | No Action Taken or Required | 2020-06-01 | Dave Ferguson (ME Engineers) | Kelsea Conkright (Populous) |  | Reviewed. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 1 June 2020 | Info Exchange
| 08324 | Responded and Closed | Approved as Noted | 2020-06-02 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: Reviewed. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 1 June 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-27 |  | 11 40 00-2.0 Eagle Floor Trough Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-27 |  | 11 40 00-2.0 Eagle Floor Trough Shop Drawings.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-05-27 |  | 11 40 00-2.0 Eagle Floor Trough Shop Drawings.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-05-27 |  | 11 40 00-2.0 Eagle Floor Trough Shop Drawings.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-05-27 |  | 11 40 00-2.0 Eagle Floor Trough Shop Drawings.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-06-02 |  | 11 40 00-2.0 Eagle Floor Trough Shop Drawings_S2O_MEE_POP.pdf
11 40 00-003-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-003-00 Refrigeration - ColdZone | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2020-07-02 | 2020-07-07 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-07-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06490 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 11 40 00-3.0 From: JOSH BROUSSARD Final Due Date: 07/02/20 Subject: REFRIGERATION - COLDZONE Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08742 | Forwarded | For Review | 2020-06-18 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-06-25 | Submittal Number: 11 40 00-3.0 From: JOSH BROUSSARD Final Due Date: 07/02/20 Subject: REFRIGERATION - COLDZONE Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06802 | Review Response | Approved as Noted | 2020-06-23 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 06840 | Review Response | Approved as Noted | 2020-07-07 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 09176 | Responded and Closed | Approved as Noted | 2020-07-07 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 |  | 11 40 00-3.0 ColdZone Refrigeration Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-18 |  | 11 40 00-3.0 ColdZone Refrigeration Drawings.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-06-18 |  | 11 40 00-3.0 ColdZone Refrigeration Drawings.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-07-07 |  | 11 40 00-3.0 ColdZone Refrigeration Drawings_S2O_MEE_POP.pdf
11 40 00-004-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-004-00 Walk-In Cooler - American Panel | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2020-07-02 | 2020-07-07 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-07-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06491 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 11 40 00-4.0 From: JOSH BROUSSARD Final Due Date: 07/01/20 Subject: WALK-IN COOLER - AMERICAN PANEL Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08743 | Forwarded | For Review | 2020-06-18 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-06-25 | Submittal Number: 11 40 00-4.0 From: JOSH BROUSSARD Final Due Date: 07/01/20 Subject: WALK-IN COOLER - AMERICAN PANEL Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06801 | Review Response | Approved as Noted | 2020-06-23 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 06829 | Review Response | Approved as Noted | 2020-07-07 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 09164 | Responded and Closed | Approved as Noted | 2020-07-07 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 11 40 00-4.0 American Panel Walk-In Coolers.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 11 40 00-4.0 American Panel Walk-In Coolers.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-06-17 |  | 11 40 00-4.0 American Panel Walk-In Coolers.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-07-07 |  | 11 40 00-4.0 American Panel Walk-In Coolers_S2O_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-06-17 |  | 11 40 00-4.0 American Panel Walk-In Coolers.pdf
11 40 00-005-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-005-00 Exhaust Hood & Fire Suppression Shop Drawings | Closed | Food Services, Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-14 | Responded and Closed - Approved as Noted/Resubmit |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Heidi Evans (ME Engineers) |  |  |  | 2020-08-03 07:00 | 2020-07-29 | 16 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-07-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06933 | Received | For Review | 2020-07-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-08-03 07:00 | Submittal Number: 11 40 00-5.0 From: JOSH BROUSSARD Final Due Date: 07/27/20 Subject: EXHAUST HOOD & FIRE SUPPRESSION SHOP DRAWINGS Description: CAPTIVE AIRE EXHAUST HOOD & FIRE SUPPRESSION DRAWINGS FOR APPROVAL Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09287 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Heidi Evans (ME Engineers) | 2020-07-20 | Submittal Number: 11 40 00-5.0 From: JOSH BROUSSARD Final Due Date: 07/27/20 Subject: EXHAUST HOOD & FIRE SUPPRESSION SHOP DRAWINGS Description: CAPTIVE AIRE EXHAUST HOOD & FIRE SUPPRESSION DRAWINGS FOR APPROVAL Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07171 | Review Response | Approved as Noted | 2020-07-15 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  | Mechanical engineers to verify all engineering is coordinated with their documents. | Info Exchange
| 07243 | Review Response | Approved as Noted/Resubmit | 2020-07-29 | Nick Theimer (ME Engineers) | Kelsea Conkright (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.07.29 | Info Exchange
| 09660 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Mechanical engineers to verify all engineering is coordinated with their documents. Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 11 40 00-5.0 Exhaust Hood & Fire Suppression Shop Dwgs.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 11 40 00-5.0 Exhaust Hood & Fire Suppression Shop Dwgs.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-07-13 |  | 11 40 00-5.0 Exhaust Hood & Fire Suppression Shop Dwgs.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-13 |  | 11 40 00-5.0 Exhaust Hood & Fire Suppression Shop Dwgs.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-29 |  | 11 40 00-5.0 Exhaust Hood & Fire Suppression Shop Dwgs - ME_S2O_POP.pdf
11 40 00-005-01 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-005-01 Exhaust Hood & Fire Suppression Shop Drawings R1 | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-01 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Heidi Evans (ME Engineers), Dave Ferguson (ME Engineers), Kuebler Perry (Populous) |  |  |  | 2020-10-21 | 2020-10-12 | 12 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-10-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08464 | Received | For Review | 2020-10-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-10-21 | Submittal Number: 11 40 00-5.1 From: JOSH BROUSSARD Final Due Date: 10/14/20 Subject: EXHAUST HOOD & FIRE SUPPRESSION SHOP DRAWINGS R1 Description: CAPTIVE AIRE EXHAUST HOOD & FIRE SUPPRESSION DRAWINGS FOR APPROVAL Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11205 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Heidi Evans (ME Engineers) | 2020-10-07 | Submittal Number: 11 40 00-5.1 From: JOSH BROUSSARD Final Due Date: 10/14/20 Subject: EXHAUST HOOD & FIRE SUPPRESSION SHOP DRAWINGS R1 Description: CAPTIVE AIRE EXHAUST HOOD & FIRE SUPPRESSION DRAWINGS FOR APPROVAL Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08543 | Review Response | Approved as Noted | 2020-10-05 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  | ME to review to verify CFM & SP info. | Info Exchange
| 11301 | Forwarded | For Review | 2020-10-05 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Kuebler Perry (Populous) | 2020-10-12 | Submittal Number: 11 40 00-5.1 From: JOSH BROUSSARD Final Due Date: 10/14/20 Subject: EXHAUST HOOD & FIRE SUPPRESSION SHOP DRAWINGS R1 Description: CAPTIVE AIRE EXHAUST HOOD & FIRE SUPPRESSION DRAWINGS FOR APPROVAL Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08722 | Review Response | Approved as Noted | 2020-10-06 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.10.06 | Info Exchange
| 11524 | Responded and Closed | Approved as Noted | 2020-10-12 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: ME to review to verify CFM & SP info. Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 11 40 00-5.1 Exhaust Hood & Fire Suppression Shop Dwgs R1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 11 40 00-5.1 Exhaust Hood & Fire Suppression Shop Dwgs R1.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-09-29 02:00 |  | 11 40 00-5.1 Exhaust Hood & Fire Suppression Shop Dwgs R1.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-29 02:00 |  | 11 40 00-5.1 Exhaust Hood & Fire Suppression Shop Dwgs R1.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-29 |  | 11 40 00-5.1 Exhaust Hood & Fire Suppression Shop Dwgs R1.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-12 |  | 11 40 00-5.1 Exhaust Hood & Fire Suppression Shop Dwgs_S2O_ME_POP.pdf
11 40 00-006-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-006-00 Custom Stainless Steel Fabrication Shop Drawings | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-14 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2020-07-28 | 2020-07-28 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06957 | Received | For Review | 2020-07-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-28 | Submittal Number: 11 40 00-6.0 From: JOSH BROUSSARD Final Due Date: 07/28/20 Subject: CUSTOM STAINLESS STEEL FABRICATION SHOP DRAWINGS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09324 | Forwarded | For Review | 2020-07-14 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-07-21 | Submittal Number: 11 40 00-6.0 From: JOSH BROUSSARD Final Due Date: 07/28/20 Subject: CUSTOM STAINLESS STEEL FABRICATION SHOP DRAWINGS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06995 | Review Response | Approved as Noted | 2020-07-16 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 07213 | Review Response | Approved as Noted | 2020-07-28 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 09620 | Responded and Closed | Approved as Noted | 2020-07-28 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| 09851 | Sent | For Information Only | 2020-08-05 | Josh Dobken (Populous) | Josh Broussard (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-14 |  | 11 40 00-6.0 Custom SS Fabrication Shop Dwgs.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-14 |  | 11 40 00-6.0 Custom SS Fabrication Shop Dwgs.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-07-16 |  | 200716 S2O Resp 11 40 00-6.0 Custom SS Fabrication Shop Dwgs.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-07-28 |  | 11 40 00-6.0 Custom SS Fabrication Shop Dwgs_S2O_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-07-14 |  | 11 40 00-6.0 Custom SS Fabrication Shop Dwgs.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-07-13 02:00 |  | 11 40 00-6.0 Custom SS Fabrication Shop Dwgs.pdf
11 40 00-006-01 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-006-01 Custom Stainless Steel Fabrication Shop Drawings Rev 1 | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2020-10-12 | 2020-09-29 | 2 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08353 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 11 40 00-6.1 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: CUSTOM STAINLESS STEEL FABRICATION SHOP DRAWINGS REV 1 Description: THIS SUBMITTAL PACKAGE INCLUDES THE ITEMS FOR FS3-3.04 THAT WERE MISSING IN THE ORIGINAL SUBMITTAL, THE REVISED WARE WASHER VENT DUCT TO MATCH THE HOBART SPECIFICATIONS, AND ADDED UPPER CONCOURSE BEVERAGE STATION CHASE WAYS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11066 | Forwarded | For Review | 2020-09-25 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-10-02 | Submittal Number: 11 40 00-6.1 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: CUSTOM STAINLESS STEEL FABRICATION SHOP DRAWINGS REV 1 Description: THIS SUBMITTAL PACKAGE INCLUDES THE ITEMS FOR FS3-3.04 THAT WERE MISSING IN THE ORIGINAL SUBMITTAL, THE REVISED WARE WASHER VENT DUCT TO MATCH THE HOBART SPECIFICATIONS, AND ADDED UPPER CONCOURSE BEVERAGE STATION CHASE WAYS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08402 | Review Response | Approved as Noted | 2020-09-28 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 11137 | Responded and Closed | Approved as Noted | 2020-09-29 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 11 40 00-6.1 Custom SS Fabrication Shop Dwgs R1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 11 40 00-6.1 Custom SS Fabrication Shop Dwgs R1.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-09-25 |  | 11 40 00-6.1 Custom SS Fabrication Shop Dwgs R1.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-09-29 |  | 11 40 00-6.1 Custom SS Fabrication Shop Dwgs R1_S2O_POP.pdf
11 40 00-007-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-007-00 Food Shields - BSI | Closed | Food Services, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-18 | Responded and Closed - Revise and Resubmit |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Kuebler Perry (Populous) |  |  |  | 2020-10-02 | 2020-09-29 | 12 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08202 | Received | For Review | 2020-09-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-10-02 | Submittal Number: 11 40 00-7.0 From: JOSH BROUSSARD Final Due Date: 09/25/20 Subject: FOOD SHIELDS - BSI Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10887 | Forwarded | For Review | 2020-09-18 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-09-25 | Submittal Number: 11 40 00-7.0 From: JOSH BROUSSARD Final Due Date: 09/25/20 Subject: FOOD SHIELDS - BSI Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10968 | Forwarded | For Review | 2020-09-22 | Josh Dobken (Populous) | Kuebler Perry (Populous) | 2020-09-29 | Submittal Number: 11 40 00-7.0 From: JOSH BROUSSARD Final Due Date: 09/25/20 Subject: FOOD SHIELDS - BSI Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08320 | Review Response | Revise and Resubmit | 2020-09-24 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  | Populous to advise on post finish choices | Info Exchange
| 11172 | Responded and Closed | Revise and Resubmit | 2020-09-29 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Peg Galie (S2O Consultants, Inc.) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-18 |  | 11 40 00-7.0 - BSI Food Shield Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-18 |  | 11 40 00-7.0 - BSI Food Shield Shop Drawings.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-17 02:00 |  | 11 40 00-7.0 - BSI Food Shield Shop Drawings.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-09-18 |  | 11 40 00-7.0 - BSI Food Shield Shop Drawings.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-09-29 |  | 11 40 00-7.0 - BSI Food Shield Shop Drawings_S2O_POP.pdf
11 40 00-007-01 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-007-01 BSI Food Shield Shop Drawings - Rev 1 | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2020-11-16 | 2020-11-13 | 12 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-11-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09139 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-11-16 | Submittal Number: 11 40 00-7.1 From: JOSH BROUSSARD Final Due Date: 11/13/20 Subject: BSI FOOD SHIELD SHOP DRAWINGS - REV 1 Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12061 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-11-09 | Submittal Number: 11 40 00-7.1 From: JOSH BROUSSARD Final Due Date: 11/13/20 Subject: BSI FOOD SHIELD SHOP DRAWINGS - REV 1 Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09422 | Review Response | Approved as Noted | 2020-11-10 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 12431 | Responded and Closed | Approved as Noted | 2020-11-13 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-31 |  | 11 40 00-7.1 - BSI Food Shield Shop Drawings Rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-31 |  | 11 40 00-7.1 - BSI Food Shield Shop Drawings Rev 1.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-10-31 |  | 11 40 00-7.1 - BSI Food Shield Shop Drawings Rev 1.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-13 |  | 11 40 00-7.1 - BSI Food Shield Shop Drawings Rev 1_S2O_POP.pdf
11 40 00-008-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-008-00: FOOD SERVICE EQUIPMENT - Beverage Conduit Product Data | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-25 | Responded and Closed - Approved |  | Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2019-10-10 | 2019-09-30 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-09-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02533 | Received | For Review | 2019-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC) | 2019-10-10 | Submittal Number: 11 40 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 11/05/19 Subject: FOOD SERVICE EQUIPMENT - BEVERAGE CONDUIT PRODUCT DATA Description: PRODUCT DATA FOR BEVERAGE CONDUIT PER SPECIFICATIONS 11 40 00 Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 03819 | Forwarded | For Review | 2019-09-26 | . (Seattle Arena Company, LLC) | Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2019-10-03 | Submittal Number: 11 40 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 11/05/19 Subject: FOOD SERVICE EQUIPMENT - BEVERAGE CONDUIT PRODUCT DATA Description: PRODUCT DATA FOR BEVERAGE CONDUIT PER SPECIFICATIONS 11 40 00 Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 02596 | Review Response | Approved | 2019-09-27 | Peg Galie (S2O Consultants, Inc.) | . (Seattle Arena Company, LLC) |  |  | Info Exchange
| 03886 | Responded and Closed | Approved | 2019-09-30 | . (Seattle Arena Company, LLC) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Peg Galie (S2O Consultants, Inc.) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-25 02:00 |  | 11 40 00-8.0 - Food Service Equipment Beverage Conduit Product Data - MAM.pdf
| Forwarded |  | . (Seattle Arena Company, LLC) | 1 | 2019-09-25 02:00 |  | 11 40 00-8.0 - Food Service Equipment Beverage Conduit Product Data - MAM.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2019-09-25 |  | 11 40 00-8.0 - Food Service Equipment Beverage Conduit Product Data - MAM.pdf
| Responded and Closed |  | . (Seattle Arena Company, LLC) | 1 | 2019-09-30 |  | 190926 S2O Resp 11 40 00-8.0 - Food Service Equipment Beverage Conduit - S2O_POP.pdf
11 40 00-009-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-009-00 UnderSlab Beverage Conduit | Closed | Food Services, Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-23 | Responded and Closed - Approved |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Heidi Evans (ME Engineers), Bryan Klote (Populous), Kelsea Conkright (Populous) |  |  |  | 2020-07-08 07:00 | 2020-07-07 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06553 | Received | For Review | 2020-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-08 07:00 | Submittal Number: 11 40 00-9.0 From: GRETCHEN TOSHACH Final Due Date: 06/12/20 Subject: UNDERSLAB BEVERAGE CONDUIT Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08821 | Forwarded | For Review | 2020-06-22 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Heidi Evans (ME Engineers) | 2020-06-29 | Submittal Number: 11 40 00-9.0 From: GRETCHEN TOSHACH Final Due Date: 06/12/20 Subject: UNDERSLAB BEVERAGE CONDUIT Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06658 | Review Response | Approved | 2020-06-23 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 08970 | Forwarded | For Review | 2020-06-29 | Josh Dobken (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) | 2020-07-06 | Submittal Number: 11 40 00-9.0 From: GRETCHEN TOSHACH Final Due Date: 06/12/20 Subject: UNDERSLAB BEVERAGE CONDUIT Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06837 | Review Response | No Action Taken or Required | 2020-06-30 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | See attached. David J. Ferguson, P.E. ME Engineers, Inc. 30 June 2020 | Info Exchange
| 09174 | Responded and Closed | Approved | 2020-07-07 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: See attached. David J. Ferguson, P.E. ME Engineers, Inc. 30 June 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-22 |  | 11 40 00-1.0 UG Bev Conduit PVC - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-22 |  | 11 40 00-1.0 UG Bev Conduit PVC - MAM.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-06-21 02:00 |  | 11 40 00-1.0 UG Bev Conduit PVC - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-21 02:00 |  | 11 40 00-1.0 UG Bev Conduit PVC - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-06-21 |  | 11 40 00-1.0 UG Bev Conduit PVC - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-07 |  | 11 40 00-009-00 UG Bev Conduit PVC - MAM_S2O_ME_POP.pdf
11 40 00-010-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-010-00 Flight Type Dishwasher Shop Drawing | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-07-21 | 2020-07-21 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06797 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 11 40 00-10.0 From: JOSH BROUSSARD Final Due Date: 07/20/20 Subject: FLIGHT TYPE DISHWASHER SHOP DRAWING Description: THIS SUBMITTAL INCLUDES THE SHOP DRAWING FOR THE FLIGHT TYPE DISHWASHER (ITEM #17.019) IN MAIN KITCHEN FS3-1.01. SEE EAGLE CUSTOM FAB SHOP DRAWINGS FOR DUCT RISER, ITEM #21.701. SEE FS3-1.01 BUY OUT BOOK FOR ITEM #17.019B - BOOSTER HEATER. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09132 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-07-13 | Submittal Number: 11 40 00-10.0 From: JOSH BROUSSARD Final Due Date: 07/20/20 Subject: FLIGHT TYPE DISHWASHER SHOP DRAWING Description: THIS SUBMITTAL INCLUDES THE SHOP DRAWING FOR THE FLIGHT TYPE DISHWASHER (ITEM #17.019) IN MAIN KITCHEN FS3-1.01. SEE EAGLE CUSTOM FAB SHOP DRAWINGS FOR DUCT RISER, ITEM #21.701. SEE FS3-1.01 BUY OUT BOOK FOR ITEM #17.019B - BOOSTER HEATER. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07046 | Review Response | Approved as Noted | 2020-07-07 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 09292 | Forwarded | For Review | 2020-07-13 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-10.0 From: JOSH BROUSSARD Final Due Date: 07/20/20 Subject: FLIGHT TYPE DISHWASHER SHOP DRAWING Description: THIS SUBMITTAL INCLUDES THE SHOP DRAWING FOR THE FLIGHT TYPE DISHWASHER (ITEM #17.019) IN MAIN KITCHEN FS3-1.01. SEE EAGLE CUSTOM FAB SHOP DRAWINGS FOR DUCT RISER, ITEM #21.701. SEE FS3-1.01 BUY OUT BOOK FOR ITEM #17.019B - BOOSTER HEATER. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07047 | Review Response | Approved as Noted | 2020-07-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.17 | Info Exchange
| 09460 | Responded and Closed | Approved as Noted | 2020-07-21 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 11 40 00-10.0 Flight Type Dishwasher Shop Drawing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 11 40 00-10.0 Flight Type Dishwasher Shop Drawing.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-07-06 |  | 11 40 00-10.0 Flight Type Dishwasher Shop Drawing.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-07-06 |  | 11 40 00-10.0 Flight Type Dishwasher Shop Drawing.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-06 |  | 11 40 00-10.0 Flight Type Dishwasher Shop Drawing.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-07-21 |  | 11 40 00-010-00 - Hobart - Flight Type Drawing - Submittal - S20_ME_POP Review.pdf
11 40 00-011-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-011-00 Under Bar Equipment - Krowne | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Revise and Resubmit |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2020-12-03 08:00 | 2020-12-02 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09478 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 11 40 00-11.0 From: JOSH BROUSSARD Final Due Date: 11/30/20 Subject: UNDER BAR EQUIPMENT - KROWNE Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12496 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-11-24 | Submittal Number: 11 40 00-11.0 From: JOSH BROUSSARD Final Due Date: 11/30/20 Subject: UNDER BAR EQUIPMENT - KROWNE Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09816 | Review Response | Approved as Noted/Resubmit | 2020-11-20 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 09824 | Review Response | Revise and Resubmit | 2020-12-02 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12905 | Responded and Closed | Revise and Resubmit | 2020-12-02 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 11 40 00-11.0 - Krowne Under Bar Equip.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 11 40 00-11.0 - Krowne Under Bar Equip.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-11-16 |  | 11 40 00-11.0 - Krowne Under Bar Equip.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-02 |  | 11 40 00-11.0 - Krowne Under Bar Equip_S2O_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-16 |  | 11 40 00-11.0 - Krowne Under Bar Equip.pdf
11 40 00-011-01 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-011-01 Under Bar Equipment - Krowne Rev 1 | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-21 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2021-01-13 | 2020-12-30 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-12-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10286 | Received | For Review | 2020-12-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2021-01-13 | Submittal Number: 11 40 00-11.1 From: JOSH BROUSSARD Final Due Date: 01/04/21 Subject: UNDER BAR EQUIPMENT - KROWNE REV 1 Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13443 | Forwarded | For Review | 2020-12-21 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-12-28 | Submittal Number: 11 40 00-11.1 From: JOSH BROUSSARD Final Due Date: 01/04/21 Subject: UNDER BAR EQUIPMENT - KROWNE REV 1 Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10364 | Review Response | Approved as Noted | 2020-12-22 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  | Please see PDF with comments added. | Info Exchange
| 10365 | Review Response | Approved as Noted | 2020-12-30 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13543 | Responded and Closed | Approved as Noted | 2020-12-30 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Please see PDF with comments added. Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-21 |  | 11 40 00-11.1 - Krowne Under Bar Equip Rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-21 |  | 11 40 00-11.1 - Krowne Under Bar Equip Rev 1.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-12-21 |  | 11 40 00-11.1 - Krowne Under Bar Equip Rev 1.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-22 |  | 11 40 00-11.1 - Krowne Under Bar Equip Rev 1_S2O_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-21 |  | 11 40 00-11.1 - Krowne Under Bar Equip Rev 1.pdf
11 40 00-012-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-012-00 Underground MEP Rough-In Drawings Package 2 | Closed | Food Services, Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-19 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Kelsea Conkright (Populous), Dave Ferguson (ME Engineers) |  |  |  | 2020-07-06 07:00 | 2020-07-07 | 19 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-07-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06515 | Received | For Review | 2020-06-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-06 07:00 | Submittal Number: 11 40 00-12.0 From: JOSH BROUSSARD Final Due Date: 07/08/20 Subject: UNDERGROUND MEP ROUGH-IN DRAWINGS PACKAGE 2 Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08769 | Forwarded | For Review | 2020-06-19 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Mark Lievens (ME Engineers); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-26 | Submittal Number: 11 40 00-12.0 From: JOSH BROUSSARD Final Due Date: 07/08/20 Subject: UNDERGROUND MEP ROUGH-IN DRAWINGS PACKAGE 2 Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06659 | Review Response | Approved as Noted | 2020-06-23 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 08968 | Forwarded | For Review | 2020-06-29 | Josh Dobken (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Dave Ferguson (ME Engineers) | 2020-07-06 | Submittal Number: 11 40 00-12.0 From: JOSH BROUSSARD Final Due Date: 07/08/20 Subject: UNDERGROUND MEP ROUGH-IN DRAWINGS PACKAGE 2 Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08971 | Forwarded | For Review | 2020-06-29 | Josh Dobken (Populous) | Nick Theimer (ME Engineers) | 2020-07-06 | Submittal Number: 11 40 00-12.0 From: JOSH BROUSSARD Final Due Date: 07/08/20 Subject: UNDERGROUND MEP ROUGH-IN DRAWINGS PACKAGE 2 Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 06830 | Review Response | Approved as Noted | 2020-06-30 | Dave Ferguson (ME Engineers) | Josh Dobken (Populous) |  | Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 30 June 2020 | Info Exchange
| 09170 | Responded and Closed | Approved as Noted | 2020-07-07 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Dave Ferguson (ME Engineers) Remarks: Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 30 June 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-18 |  | 11 40 00-12.0 UG MEP Rough-In Drawings Package 2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-18 |  | 11 40 00-12.0 UG MEP Rough-In Drawings Package 2.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-06-17 02:00 |  | 11 40 00-12.0 UG MEP Rough-In Drawings Package 2.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-17 02:00 |  | 11 40 00-12.0 UG MEP Rough-In Drawings Package 2.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-17 02:00 |  | 11 40 00-12.0 UG MEP Rough-In Drawings Package 2.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-06-17 |  | 11 40 00-12.0 UG MEP Rough-In Drawings Package 2.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-07-07 |  | 11 40 00-12.0 UG MEP Rough-In Drawings Package 2_S2O_ME_POP.pdf
11 40 00-013-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-013-00 Main Con Quad D Install Plans & Equip Schedule | Closed | Food Services, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-07-20 | 2020-07-20 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06782 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 11 40 00-13.0 From: JOSH BROUSSARD Final Due Date: 07/20/20 Subject: MAIN CON QUAD D INSTALL PLANS & EQUIP SCHEDULE Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09117 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-07-13 | Submittal Number: 11 40 00-13.0 From: JOSH BROUSSARD Final Due Date: 07/20/20 Subject: MAIN CON QUAD D INSTALL PLANS & EQUIP SCHEDULE Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07044 | Review Response | Approved as Noted | 2020-07-07 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 09290 | Forwarded | For Review | 2020-07-13 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-13.0 From: JOSH BROUSSARD Final Due Date: 07/20/20 Subject: MAIN CON QUAD D INSTALL PLANS & EQUIP SCHEDULE Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07045 | Review Response | Approved as Noted | 2020-07-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.20 | Info Exchange
| 09435 | Responded and Closed | Approved as Noted | 2020-07-20 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 11 40 00-13.0 Main Con Quad D Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 11 40 00-13.0 Main Con Quad D Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-07-06 |  | 11 40 00-13.0 Main Con Quad D Install Plans & Equip Schedules.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-07-06 |  | 11 40 00-13.0 Main Con Quad D Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-06 |  | 11 40 00-13.0 Main Con Quad D Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-07-20 |  | 11 40 00-13.0 Main Con Quad D Install Plans & Equip Schedules - S20_ME_POP Review.pdf
11 40 00-014-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-014-00 Upper Con Quad D Install Plans & Equip Schedules | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-02 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-07-16 | 2020-07-20 | 19 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06770 | Received | For Review | 2020-07-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-16 | Submittal Number: 11 40 00-14.0 From: JOSH BROUSSARD Final Due Date: 07/16/20 Subject: UPPER CON QUAD D INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-5.01 AND FS3-5.07. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063, RFI 2711, AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09098 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-07-13 | Submittal Number: 11 40 00-14.0 From: JOSH BROUSSARD Final Due Date: 07/16/20 Subject: UPPER CON QUAD D INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-5.01 AND FS3-5.07. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063, RFI 2711, AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07038 | Review Response | Approved as Noted | 2020-07-06 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  | Approved as noted | Info Exchange
| 09288 | Forwarded | For Review | 2020-07-13 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-14.0 From: JOSH BROUSSARD Final Due Date: 07/16/20 Subject: UPPER CON QUAD D INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-5.01 AND FS3-5.07. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063, RFI 2711, AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07040 | Review Response | Approved as Noted | 2020-07-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.20 | Info Exchange
| 09432 | Responded and Closed | Approved as Noted | 2020-07-20 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Approved as noted Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-02 |  | 11 40 00-14.0 Upper Con Quad D Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-02 |  | 11 40 00-14.0 Upper Con Quad D Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-07-02 |  | 11 40 00-14.0 Upper Con Quad D Install Plans & Equip Schedules.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-07-02 |  | 11 40 00-14.0 Upper Con Quad D Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-02 |  | 11 40 00-14.0 Upper Con Quad D Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-07-20 |  | 11 40 00-14.0 Upper Con Quad D Install Plans & Equip Schedules - S20_ME_POP Review.pdf
11 40 00-015-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-015-00 Main Con Area C Equipment Plans and Schedule | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-20 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-03 | 2020-07-29 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07026 | Received | For Review | 2020-07-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-08-03 | Submittal Number: 11 40 00-15.0 From: JOSH BROUSSARD Final Due Date: 08/03/20 Subject: MAIN CON AREA C EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-3.11, FS3-3.12, AND FS3-3.13. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063, RFI 2719, AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09409 | Forwarded | For Review | 2020-07-20 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-07-27 | Submittal Number: 11 40 00-15.0 From: JOSH BROUSSARD Final Due Date: 08/03/20 Subject: MAIN CON AREA C EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-3.11, FS3-3.12, AND FS3-3.13. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063, RFI 2719, AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07230 | Review Response | Approved as Noted | 2020-07-22 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  | See our comments on the attached PDF. | Info Exchange
| 09601 | Forwarded | For Review | 2020-07-28 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-03 | Submittal Number: 11 40 00-15.0 From: JOSH BROUSSARD Final Due Date: 08/03/20 Subject: MAIN CON AREA C EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-3.11, FS3-3.12, AND FS3-3.13. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063, RFI 2719, AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07231 | Review Response | Approved as Noted | 2020-07-28 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.28 | Info Exchange
| 09659 | Responded and Closed | Approved as Noted | 2020-07-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: See our comments on the attached PDF. Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-20 |  | 11 40 00-15.0 Main Con Area C Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-20 |  | 11 40 00-15.0 Main Con Area C Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-07-20 |  | 11 40 00-15.0 Main Con Area C Install Plans & Equip Schedules.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-07-19 02:00 |  | 11 40 00-15.0 Main Con Area C Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-19 |  | 11 40 00-15.0 Main Con Area C Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-29 |  | 11 40 00-15.0 Main Con Area C Install Plans & Equip Schedules - S2O_ME_POP.pdf
11 40 00-016-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-016-00 Main Con Area A North Equipment Plans and Schedule | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-20 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-03 | 2020-07-29 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07027 | Received | For Review | 2020-07-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-08-03 | Submittal Number: 11 40 00-16.0 From: JOSH BROUSSARD Final Due Date: 08/03/20 Subject: MAIN CON AREA A NORTH EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-3.01 AND FS3-3.02. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063, RFI 2951, AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09412 | Forwarded | For Review | 2020-07-20 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-07-27 | Submittal Number: 11 40 00-16.0 From: JOSH BROUSSARD Final Due Date: 08/03/20 Subject: MAIN CON AREA A NORTH EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-3.01 AND FS3-3.02. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063, RFI 2951, AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07227 | Review Response | Approved as Noted | 2020-07-22 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  | See our comments on the attached PDF. | Info Exchange
| 09602 | Forwarded | For Review | 2020-07-28 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-03 | Submittal Number: 11 40 00-16.0 From: JOSH BROUSSARD Final Due Date: 08/03/20 Subject: MAIN CON AREA A NORTH EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-3.01 AND FS3-3.02. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063, RFI 2951, AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07228 | Review Response | Approved as Noted | 2020-07-28 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.28 | Info Exchange
| 09644 | Responded and Closed | Approved as Noted | 2020-07-29 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: See our comments on the attached PDF. Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-20 |  | 11 40 00-16.0 Main Con Area A North Equip Plans & Schedule.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-20 |  | 11 40 00-16.0 Main Con Area A North Equip Plans & Schedule.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-07-20 |  | 11 40 00-16.0 Main Con Area A North Equip Plans & Schedule.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-07-19 02:00 |  | 11 40 00-16.0 Main Con Area A North Equip Plans & Schedule.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-19 |  | 11 40 00-16.0 Main Con Area A North Equip Plans & Schedule.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-07-29 |  | 11 40 00-16.0 Main Con Area A North Equip Plans & Schedule - S2O_ME_POP.pdf
11 40 00-017-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-017-00 Upper Con Area A Equipment Plans and Schedule | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-28 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Heidi Evans (ME Engineers) |  |  |  | 2020-08-11 | 2020-08-10 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-08-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07177 | Received | For Review | 2020-07-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-08-11 | Submittal Number: 11 40 00-17.0 From: JOSH BROUSSARD Final Due Date: 08/11/20 Subject: UPPER CON AREA A EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-5.02 AND FS3-5.03. ALL INFORMATION HAS BEEN UPDATED THROUGH RFI 2919, CCD 066, AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09579 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Heidi Evans (ME Engineers) | 2020-08-04 | Submittal Number: 11 40 00-17.0 From: JOSH BROUSSARD Final Due Date: 08/11/20 Subject: UPPER CON AREA A EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-5.02 AND FS3-5.03. ALL INFORMATION HAS BEEN UPDATED THROUGH RFI 2919, CCD 066, AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07400 | Review Response | Approved as Noted | 2020-07-29 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 07488 | Review Response | Approved | 2020-08-10 | Nick Theimer (ME Engineers) | Kelsea Conkright (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.08.10 | Info Exchange
| 07489 | Review Response | Approved as Noted | 2020-08-10 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 09975 | Responded and Closed | Approved as Noted | 2020-08-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.08.10 Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-28 |  | 11 40 00-17.0 Upper Con Area A Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-28 |  | 11 40 00-17.0 Upper Con Area A Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-07-28 |  | 11 40 00-17.0 Upper Con Area A Install Plans & Equip Schedules.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-28 |  | 11 40 00-17.0 Upper Con Area A Install Plans & Equip Schedules.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-08-10 |  | 11 40 00-17.0 Upper Con Area A Install Plans & Equip Schedules_S2O_ME_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-28 |  | 11 40 00-17.0 Upper Con Area A Install Plans & Equip Schedules.pdf
11 40 00-018-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-018-00 Main Con Area B North Equipment Plans and Schedule | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-28 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Heidi Evans (ME Engineers) |  |  |  | 2020-08-11 | 2020-08-10 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-08-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07185 | Received | For Review | 2020-07-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-08-11 | Submittal Number: 11 40 00-18.0 From: JOSH BROUSSARD Final Due Date: 08/11/20 Subject: MAIN CON AREA B NORTH EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-3.09 AND FS3-3.10. ALL INFORMATION HAS BEEN UPDATED THROUGH RFI 2997 AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09589 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Heidi Evans (ME Engineers) | 2020-08-04 | Submittal Number: 11 40 00-18.0 From: JOSH BROUSSARD Final Due Date: 08/11/20 Subject: MAIN CON AREA B NORTH EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-3.09 AND FS3-3.10. ALL INFORMATION HAS BEEN UPDATED THROUGH RFI 2997 AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07401 | Review Response | Approved as Noted | 2020-07-29 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 07491 | Review Response | Approved as Noted | 2020-08-10 | Nick Theimer (ME Engineers) | Kelsea Conkright (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.08.10 | Info Exchange
| 07492 | Review Response | Approved as Noted | 2020-08-10 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 09977 | Responded and Closed | Approved as Noted | 2020-08-10 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.08.10 Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-28 |  | 11 40 00-18.0 Main Con Area B North Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-28 |  | 11 40 00-18.0 Main Con Area B North Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-07-28 |  | 11 40 00-18.0 Main Con Area B North Install Plans & Equip Schedules.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-28 |  | 11 40 00-18.0 Main Con Area B North Install Plans & Equip Schedules.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-08-10 |  | 11 40 00-18.0 Main Con Area B North Install Plans & Equip Schedules_S2O_ME_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-07-28 |  | 11 40 00-18.0 Main Con Area B North Install Plans & Equip Schedules.pdf
11 40 00-019-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-019-00 Suite Level Area C North Equipment Plans and Schedule | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-14 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers) |  |  |  | 2020-08-28 | 2020-08-28 | 15 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07541 | Received | For Review | 2020-08-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-08-28 | Submittal Number: 11 40 00-19.0 From: JOSH BROUSSARD Final Due Date: 08/27/20 Subject: SUITE LEVEL AREA C NORTH EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-4.06, FS3-4.07, AND FS3-4.08. ALL INFORMATION HAS BEEN UPDATED THROUGH RFI CCD 069 AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10041 | Forwarded | For Review | 2020-08-14 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-08-21 | Submittal Number: 11 40 00-19.0 From: JOSH BROUSSARD Final Due Date: 08/27/20 Subject: SUITE LEVEL AREA C NORTH EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-4.06, FS3-4.07, AND FS3-4.08. ALL INFORMATION HAS BEEN UPDATED THROUGH RFI CCD 069 AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07816 | Review Response | Approved as Noted | 2020-08-14 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 10269 | Forwarded | For Review | 2020-08-24 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers) | 2020-08-28 | Submittal Number: 11 40 00-19.0 From: JOSH BROUSSARD Final Due Date: 08/27/20 Subject: SUITE LEVEL AREA C NORTH EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-4.06, FS3-4.07, AND FS3-4.08. ALL INFORMATION HAS BEEN UPDATED THROUGH RFI CCD 069 AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07817 | Review Response | Approved as Noted | 2020-08-26 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached ME submittal review. Thank you, Mark Lievens ME Engineers 2020.08.26 | Info Exchange
| 10406 | Responded and Closed | Approved as Noted | 2020-08-28 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached ME submittal review. Thank you, Mark Lievens ME Engineers 2020.08.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-13 |  | 11 40 00-19.0 Suite Level Area C North Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-13 |  | 11 40 00-19.0 Suite Level Area C North Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-08-13 |  | 11 40 00-19.0 Suite Level Area C North Install Plans & Equip Schedules.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-08-12 02:00 |  | 11 40 00-19.0 Suite Level Area C North Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-12 |  | 11 40 00-19.0 Suite Level Area C North Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-08-28 |  | 11 40 00-19.0 Suite Level Area C North Install Plans & Equip Schedules_S2O_MEE_POP.pdf
11 40 00-020-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-020-00 Walk-In Freezer Thermal Break Materials | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-27 | Responded and Closed - Revise and Resubmit |  | Amber Kennedy (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-11-10 | 2020-10-30 | 4 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-10-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09027 | Received | For Review | 2020-10-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-11-10 | Submittal Number: 11 40 00-20.0 From: JOSH BROUSSARD Final Due Date: 11/10/20 Subject: WALK-IN FREEZER THERMAL BREAK MATERIALS Description: THIS SUBMITTAL INCLUDES PRODUCT DATA FOR THE MATERIALS TO BE PROVIDED BY FOOD SERVICE FOR THE WALK-IN FREEZER SLAB DEPRESSIONS PER THE DETAIL ON FS3-1.02S AND RFI 4029 (INCLUDING BREAKER STRIP, VAPOR BARRIER AND INSULATION). NOTE THAT THE DOW FREEZERMATE INSULATION PRODUCT SHOWN IN THE DETAIL IS NOT AVAILABLE SO THE SUBMITTAL INCLUDES AMERICAN PANEL'S RECOMMENDED INSULATION FOR THIS APPLICATION. THE FELT SHEET SHOWN ON THE DETAIL IS NOT INCLUDED AS IT WAS REMOVED IN RFI 4029. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11908 | Forwarded | For Review | 2020-10-27 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Mark Lievens (ME Engineers); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-03 | Submittal Number: 11 40 00-20.0 From: JOSH BROUSSARD Final Due Date: 11/10/20 Subject: WALK-IN FREEZER THERMAL BREAK MATERIALS Description: THIS SUBMITTAL INCLUDES PRODUCT DATA FOR THE MATERIALS TO BE PROVIDED BY FOOD SERVICE FOR THE WALK-IN FREEZER SLAB DEPRESSIONS PER THE DETAIL ON FS3-1.02S AND RFI 4029 (INCLUDING BREAKER STRIP, VAPOR BARRIER AND INSULATION). NOTE THAT THE DOW FREEZERMATE INSULATION PRODUCT SHOWN IN THE DETAIL IS NOT AVAILABLE SO THE SUBMITTAL INCLUDES AMERICAN PANEL'S RECOMMENDED INSULATION FOR THIS APPLICATION. THE FELT SHEET SHOWN ON THE DETAIL IS NOT INCLUDED AS IT WAS REMOVED IN RFI 4029. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09112 | Review Response | Approved as Noted | 2020-10-28 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  | Structural Engineer to confirm compressive strength of 20 PSI is acceptable. 40 PSI is basis of design. | Info Exchange
| 09113 | Review Response | Revise and Resubmit | 2020-10-28 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  | 40 PSI is basis of design. Insulation must meet R-Value of 28 to meet basis of design. | Info Exchange
| 12026 | Forwarded | For Review | 2020-10-30 | Kelsea Conkright (Populous) | Matt Ross (Thornton Tomasetti) |  | Submittal Number: 11 40 00-20.0 From: JOSH BROUSSARD Final Due Date: 11/10/20 Subject: WALK-IN FREEZER THERMAL BREAK MATERIALS Description: THIS SUBMITTAL INCLUDES PRODUCT DATA FOR THE MATERIALS TO BE PROVIDED BY FOOD SERVICE FOR THE WALK-IN FREEZER SLAB DEPRESSIONS PER THE DETAIL ON FS3-1.02S AND RFI 4029 (INCLUDING BREAKER STRIP, VAPOR BARRIER AND INSULATION). NOTE THAT THE DOW FREEZERMATE INSULATION PRODUCT SHOWN IN THE DETAIL IS NOT AVAILABLE SO THE SUBMITTAL INCLUDES AMERICAN PANEL'S RECOMMENDED INSULATION FOR THIS APPLICATION. THE FELT SHEET SHOWN ON THE DETAIL IS NOT INCLUDED AS IT WAS REMOVED IN RFI 4029. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12039 | Responded and Closed | Revise and Resubmit | 2020-10-30 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Peg Galie (S2O Consultants, Inc.) Remarks: 40 PSI is basis of design. Insulation must meet R-Value of 28 to meet basis of design. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 11 40 00-20.0 Walk-In Freezer Thermal Break Materials.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 11 40 00-20.0 Walk-In Freezer Thermal Break Materials.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-10-27 |  | 11 40 00-20.0 Walk-In Freezer Thermal Break Materials.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-10-30 |  | 11 40 00-20.0 Walk-In Freezer Thermal Break Materials_S2O_POP.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-10-27 |  | 11 40 00-20.0 Walk-In Freezer Thermal Break Materials.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-27 |  | 11 40 00-20.0 Walk-In Freezer Thermal Break Materials.pdf
11 40 00-020-01 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-020-01 Walk-In Freezer Thermal Break Materials Rev 1 | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-16 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2020-11-30 | 2020-11-16 | 1 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-11-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09431 | Received | For Review | 2020-11-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-11-30 | Submittal Number: 11 40 00-20.1 From: JOSH BROUSSARD Final Due Date: 11/27/20 Subject: WALK-IN FREEZER THERMAL BREAK MATERIALS REV 1 Description: THIS REVISION CLARIFIES THAT 3 LAYERS OF THE SUBMITTED INSULATION WILL BE PROVIDED WHICH MEETS AN R-VALUE GREATER THAN 28. PLEASE CONFIRM THAT THE 20 PSI COMPRESSIVE STRENGTH IS ACCEPTABLE PER AMERICAN PANEL RECOMMENDATION. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12438 | Forwarded | For Review | 2020-11-13 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-11-20 | Submittal Number: 11 40 00-20.1 From: JOSH BROUSSARD Final Due Date: 11/27/20 Subject: WALK-IN FREEZER THERMAL BREAK MATERIALS REV 1 Description: THIS REVISION CLARIFIES THAT 3 LAYERS OF THE SUBMITTED INSULATION WILL BE PROVIDED WHICH MEETS AN R-VALUE GREATER THAN 28. PLEASE CONFIRM THAT THE 20 PSI COMPRESSIVE STRENGTH IS ACCEPTABLE PER AMERICAN PANEL RECOMMENDATION. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09450 | Review Response | Approved as Noted | 2020-11-16 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 12460 | Responded and Closed | Approved as Noted | 2020-11-16 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-13 |  | 11 40 00-20.1 Walk-In Freezer Thermal Break Materials R1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-13 |  | 11 40 00-20.1 Walk-In Freezer Thermal Break Materials R1.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-11-13 |  | 11 40 00-20.1 Walk-In Freezer Thermal Break Materials R1.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-16 |  | 11 40 00-20.1 Walk-In Freezer Thermal Break Materials R1_S2O_POP.pdf
11 40 00-021-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-021-00 Event Level Area D Equipment Plans and Schedule | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-17 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers) |  |  |  | 2020-08-31 | 2020-08-28 | 12 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07580 | Received | For Review | 2020-08-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-08-31 | Submittal Number: 11 40 00-21.0 From: JOSH BROUSSARD Final Due Date: 08/31/20 Subject: EVENT LEVEL AREA D EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-1.05 AND FS3-1.06. ALL INFORMATION HAS BEEN UPDATED WITH ALL FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10088 | Forwarded | For Review | 2020-08-17 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-08-24 | Submittal Number: 11 40 00-21.0 From: JOSH BROUSSARD Final Due Date: 08/31/20 Subject: EVENT LEVEL AREA D EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-1.05 AND FS3-1.06. ALL INFORMATION HAS BEEN UPDATED WITH ALL FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07826 | Review Response | Approved as Noted | 2020-08-19 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 10270 | Forwarded | For Review | 2020-08-24 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers) | 2020-08-31 | Submittal Number: 11 40 00-21.0 From: JOSH BROUSSARD Final Due Date: 08/31/20 Subject: EVENT LEVEL AREA D EQUIPMENT PLANS AND SCHEDULE Description: THIS SUBMITTAL INCLUDES DRAWINGS AND SCHEDULES FOR FOOD SERVICE AREAS FS3-1.05 AND FS3-1.06. ALL INFORMATION HAS BEEN UPDATED WITH ALL FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07827 | Review Response | Approved | 2020-08-26 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached ME submittal review. Thank you, Mark Lievens ME Engineers 2020.08.26 | Info Exchange
| 10407 | Responded and Closed | Approved as Noted | 2020-08-28 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached ME submittal review. Thank you, Mark Lievens ME Engineers 2020.08.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-17 |  | 11 40 00-21.0 Event Level Area D Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-17 |  | 11 40 00-21.0 Event Level Area D Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-08-17 |  | 11 40 00-21.0 Event Level Area D Install Plans & Equip Schedules.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-08-16 02:00 |  | 11 40 00-21.0 Event Level Area D Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-16 |  | 11 40 00-21.0 Event Level Area D Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-08-28 |  | 11 40 00-21.0 Event Level Area D Install Plans & Equip Schedules_S2O_MEE_POP.pdf
11 40 00-022-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-022-00 Suite Level Area C Install Plans & Equipment Schedules | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-18 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-09-01 | 2020-08-28 | 11 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07595 | Received | For Review | 2020-08-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-09-01 | Submittal Number: 11 40 00-22.0 From: JOSH BROUSSARD Final Due Date: 08/31/20 Subject: SUITE LEVEL AREA C INSTALL PLANS & EQUIPMENT SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-4.09, FS3-4.10, AND FS3-4.11. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063 REVISIONS, RFI 3109 AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10111 | Forwarded | For Review | 2020-08-18 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-08-25 | Submittal Number: 11 40 00-22.0 From: JOSH BROUSSARD Final Due Date: 08/31/20 Subject: SUITE LEVEL AREA C INSTALL PLANS & EQUIPMENT SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-4.09, FS3-4.10, AND FS3-4.11. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063 REVISIONS, RFI 3109 AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07828 | Review Response | Approved as Noted | 2020-08-19 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 10316 | Forwarded | For Review | 2020-08-25 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-22.0 From: JOSH BROUSSARD Final Due Date: 08/31/20 Subject: SUITE LEVEL AREA C INSTALL PLANS & EQUIPMENT SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-4.09, FS3-4.10, AND FS3-4.11. ALL INFORMATION HAS BEEN UPDATED THROUGH CCD 063 REVISIONS, RFI 3109 AND FOOD SERVICE COORDINATION MARK-UPS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 07829 | Review Response | Approved as Noted | 2020-08-27 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.08.26 | Info Exchange
| 07830 | Review Response | Approved as Noted | 2020-08-27 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | ****CORRECTION**** Please use this attached submittal file for the submittal response. I just uploading the incorrect submittal file (11 40 00-019) a few mins ago. Sorry for the confusion. Thanks, Mark Lievens ME Engineers 2020.08.26 | Info Exchange
| 10408 | Responded and Closed | Approved as Noted | 2020-08-28 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.08.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-17 |  | 11 40 00-22.0 Suite Level Area C Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-17 |  | 11 40 00-22.0 Suite Level Area C Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-08-17 |  | 11 40 00-22.0 Suite Level Area C Install Plans & Equip Schedules.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-08-17 |  | 11 40 00-22.0 Suite Level Area C Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-17 |  | 11 40 00-22.0 Suite Level Area C Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-17 |  | 11 40 00-22.0 Suite Level Area C Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-08-28 |  | 11 40 00-22.0 Suite Level Area C Install Plans & Equip Schedules_S2O_MEE_POP.pdf
11 40 00-023-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-023-00 Main Con Area A South Install Plans & Equip Schedules | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-01 | Responded and Closed - Approved as Noted/Resubmit |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-10-15 | 2020-10-20 | 20 |  | Record Copies; Transfers; Submittals | 11 40 00-023-00-01 - 11 40 00-023-00 Main Con Area A South Install Plans & Equip Schedules | 21 |  | 2020-10-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08463 | Received | For Review | 2020-10-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-10-15 | Submittal Number: 11 40 00-23.0 From: JOSH BROUSSARD Final Due Date: 10/14/20 Subject: MAIN CON AREA A SOUTH INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-3.03, FS3-3.04, AND FS3-3.05. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11204 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-10-07 | Submittal Number: 11 40 00-23.0 From: JOSH BROUSSARD Final Due Date: 10/14/20 Subject: MAIN CON AREA A SOUTH INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-3.03, FS3-3.04, AND FS3-3.05. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08671 | Review Response | Approved as Noted | 2020-10-05 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 11453 | Forwarded | For Review | 2020-10-08 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-23.0 From: JOSH BROUSSARD Final Due Date: 10/14/20 Subject: MAIN CON AREA A SOUTH INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-3.03, FS3-3.04, AND FS3-3.05. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08890 | Review Response | Approved as Noted/Resubmit | 2020-10-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.20 | Info Exchange
| 11746 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-20 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 11 40 00-23.0 Main Con Area A South Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 11 40 00-23.0 Main Con Area A South Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-09-30 |  | 11 40 00-23.0 Main Con Area A South Install Plans & Equip Schedules.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-09-30 |  | 11 40 00-23.0 Main Con Area A South Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-30 |  | 11 40 00-23.0 Main Con Area A South Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-20 |  | 11 40 00-23.0 Main Con Area A South Install Plans & Equip Schedules_S2O_MEE_POP.pdf
11 40 00-023-00-01 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-023-00 Main Con Area A South Install Plans & Equip Schedules | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 40 00-023-00 - 11 40 00-023-00 Main Con Area A South Install Plans & Equip Schedules | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-20 |  | 11 40 00-23.0 Main Con Area A South Install Plans & Equip Schedules_S2O_MEE_POP.pdf
11 40 00-024-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-024-00 Perlick Custom Beer Dispenser | Closed | Food Services, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Kuebler Perry (Populous) |  |  |  | 2020-10-09 | 2020-09-29 | 5 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08348 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-10-09 | Submittal Number: 11 40 00-24.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: PERLICK CUSTOM BEER DISPENSER Description: SEE ATTACHED FOR PERLICK CUSTOM BEER DISPENSERS AT CRAFT BEER BARS FS3-3.11 AND FS3-3.17. INCLUDES ITEM #'S 2.122, 2.212, 2.206L, AND 2.206L. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11061 | Forwarded | For Review | 2020-09-25 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-10-02 | Submittal Number: 11 40 00-24.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: PERLICK CUSTOM BEER DISPENSER Description: SEE ATTACHED FOR PERLICK CUSTOM BEER DISPENSERS AT CRAFT BEER BARS FS3-3.11 AND FS3-3.17. INCLUDES ITEM #'S 2.122, 2.212, 2.206L, AND 2.206L. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08400 | Review Response | Approved as Noted | 2020-09-28 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  | Architect to verify finish | Info Exchange
| 11101 | Forwarded | For Review | 2020-09-28 | Josh Dobken (Populous) | Kuebler Perry (Populous) | 2020-10-05 | Submittal Number: 11 40 00-24.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: PERLICK CUSTOM BEER DISPENSER Description: SEE ATTACHED FOR PERLICK CUSTOM BEER DISPENSERS AT CRAFT BEER BARS FS3-3.11 AND FS3-3.17. INCLUDES ITEM #'S 2.122, 2.212, 2.206L, AND 2.206L. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11162 | Responded and Closed | Approved as Noted | 2020-09-29 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 11 40 00-24.0 - Perlick Custom Beer Dispensers.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 11 40 00-24.0 - Perlick Custom Beer Dispensers.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-09-25 |  | 11 40 00-24.0 - Perlick Custom Beer Dispensers.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-24 02:00 |  | 11 40 00-24.0 - Perlick Custom Beer Dispensers.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-09-29 |  | 11 40 00-24.0 - Perlick Custom Beer Dispensers_S2O_POP.pdf
11 40 00-024-01 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-024-01 Perlick Custom Beer Dispenser Rev 1 | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-02 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2021-02-16 | 2021-02-04 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11110 | Received | For Review | 2021-02-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (Mortenson Construction) | 2021-02-16 | Submittal Number: 11 40 00-24.1 From: JOSH BROUSSARD Final Due Date: 02/15/21 Subject: PERLICK CUSTOM BEER DISPENSER REV 1 Description: SEE ATTACHED FOR THE REVISION TO THE PERLICK CUSTOM BEER DISPENSERS (ITEM # 2.122) AT CRAFT BEER BARS FS3-3.11 AND FS3-3.17. THIS REVISION IS REFLECTIVE OF THE DIRECTION TO REDUCE THE OVERALL DEPTH OF THE DISPENSER FROM 16" TO 12" IN ORDER TO FIT ON THE COUNTERS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 14421 | Forwarded | For Review | 2021-02-01 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2021-02-08 | Submittal Number: 11 40 00-24.1 From: JOSH BROUSSARD Final Due Date: 02/15/21 Subject: PERLICK CUSTOM BEER DISPENSER REV 1 Description: SEE ATTACHED FOR THE REVISION TO THE PERLICK CUSTOM BEER DISPENSERS (ITEM # 2.122) AT CRAFT BEER BARS FS3-3.11 AND FS3-3.17. THIS REVISION IS REFLECTIVE OF THE DIRECTION TO REDUCE THE OVERALL DEPTH OF THE DISPENSER FROM 16" TO 12" IN ORDER TO FIT ON THE COUNTERS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11223 | Review Response | Approved as Noted | 2021-02-02 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 14524 | Responded and Closed | Approved as Noted | 2021-02-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-01 |  | 11 40 00-24.1 - Perlick Custom Beer Dispensers R1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-01 |  | 11 40 00-24.1 - Perlick Custom Beer Dispensers R1.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-02-01 |  | 11 40 00-24.1 - Perlick Custom Beer Dispensers R1.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-04 |  | 210202 S2O Resp 11 40 00-24.1 - Perlick Custom Beer Dispensers R1_POP.pdf
11 40 00-025-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-025-00 Event Level Area A/E Install Plans & Equip Schedules | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-10-12 | 2020-10-08 | 11 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08357 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 11 40 00-25.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: EVENT LEVEL AREA A/E INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-1.01 AND FS3-1.02. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11071 | Forwarded | For Review | 2020-09-25 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-10-02 | Submittal Number: 11 40 00-25.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: EVENT LEVEL AREA A/E INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-1.01 AND FS3-1.02. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08381 | Review Response | Approved as Noted | 2020-09-28 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 11109 | Forwarded | For Review | 2020-09-28 | Shaina Burris (Populous) | Peg Galie (S2O Consultants, Inc.) |  | Submittal Number: 11 40 00-25.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: EVENT LEVEL AREA A/E INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-1.01 AND FS3-1.02. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11113 | Forwarded | For Review | 2020-09-28 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-25.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: EVENT LEVEL AREA A/E INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-1.01 AND FS3-1.02. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08665 | Review Response | Approved as Noted | 2020-09-28 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 08666 | Review Response | Approved as Noted | 2020-10-07 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.07 | Info Exchange
| 11450 | Responded and Closed | Approved as Noted | 2020-10-08 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.07 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 11 40 00-25.0 Event Level Area E Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 11 40 00-25.0 Event Level Area E Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-09-25 |  | 11 40 00-25.0 Event Level Area E Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 11 40 00-25.0 Event Level Area E Install Plans & Equip Schedules.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-09-25 |  | 11 40 00-25.0 Event Level Area E Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-09-25 |  | 11 40 00-25.0 Event Level Area E Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-25 |  | 11 40 00-25.0 Event Level Area E Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-08 |  | 11 40 00-25.0 Event Level Area E Install Plans & Equip Schedules_S2O_MEE_POP.pdf
11 40 00-026-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-026-00 Suite Level Area A Install Plans & Equip Schedules | Closed | Food Services, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-15 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-10-29 | 2020-10-22 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-10-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08800 | Received | For Review | 2020-10-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-10-29 | Submittal Number: 11 40 00-26.0 From: JOSH BROUSSARD Final Due Date: 10/29/20 Subject: SUITE LEVEL AREA A INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-4.01 AND FS3-4.03 CURRENT THROUGH CCD 075. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11633 | Forwarded | For Review | 2020-10-15 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Mark Lievens (ME Engineers); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-22 | Submittal Number: 11 40 00-26.0 From: JOSH BROUSSARD Final Due Date: 10/29/20 Subject: SUITE LEVEL AREA A INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-4.01 AND FS3-4.03 CURRENT THROUGH CCD 075. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08893 | Review Response | Approved as Noted | 2020-10-19 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 11750 | Forwarded | For Review | 2020-10-21 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-26.0 From: JOSH BROUSSARD Final Due Date: 10/29/20 Subject: SUITE LEVEL AREA A INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-4.01 AND FS3-4.03 CURRENT THROUGH CCD 075. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08910 | Review Response | Approved as Noted | 2020-10-21 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.21 | Info Exchange
| 11797 | Responded and Closed | Approved as Noted | 2020-10-22 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-15 |  | 11 40 00-26.0 Suite Level Area A Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-15 |  | 11 40 00-26.0 Suite Level Area A Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-10-15 |  | 11 40 00-26.0 Suite Level Area A Install Plans & Equip Schedules.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-10-15 |  | 11 40 00-26.0 Suite Level Area A Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-15 |  | 11 40 00-26.0 Suite Level Area A Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-22 |  | 11 40 00-26.0 Suite Level Area A Install Plans & Equip Schedules_S2O_MEE_POP.pdf
11 40 00-027-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-027-00 Upper Con Area C Install Plans & Equip Schedules | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-10-12 | 2020-10-10 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08358 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 11 40 00-27.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: UPPER CON AREA C INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-5.05 AND FS3-5.06. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11072 | Forwarded | For Review | 2020-09-25 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-10-02 | Submittal Number: 11 40 00-27.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: UPPER CON AREA C INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-5.05 AND FS3-5.06. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08663 | Review Response | Approved as Noted | 2020-09-28 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 11112 | Forwarded | For Review | 2020-09-28 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-27.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: UPPER CON AREA C INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-5.05 AND FS3-5.06. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08664 | Review Response | Approved as Noted | 2020-10-07 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.07 | Info Exchange
| 11447 | Responded and Closed | Approved as Noted | 2020-10-08 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.07 | Info Exchange
| 11487 | Reopened | Additional Information | 2020-10-10 19:48 | Kelsea Conkright (Populous)
| 11488 | Responded and Closed | Approved as Noted | 2020-10-10 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.07 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 11 40 00-27.0 Upper Con Area C Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 11 40 00-27.0 Upper Con Area C Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-09-25 |  | 11 40 00-27.0 Upper Con Area C Install Plans & Equip Schedules.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-09-25 |  | 11 40 00-27.0 Upper Con Area C Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-25 |  | 11 40 00-27.0 Upper Con Area C Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-08 |  | 11 40 00-27.0 Upper Con Area C Install Plans & Equip Schedules_S2O_MEE_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-08 |  | 11 40 00-27.0 Upper Con Area C Install Plans & Equip Schedules_S2O_MEE_POP.pdf
11 40 00-028-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-028-00 Upper Con Area B Install Plans & Equip Schedules | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-02 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-10-16 | 2020-10-20 | 19 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-10-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08494 | Received | For Review | 2020-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-10-16 | Submittal Number: 11 40 00-28.0 From: JOSH BROUSSARD Final Due Date: 10/15/20 Subject: UPPER CON AREA B INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREA FS3-5.04. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11239 | Forwarded | For Review | 2020-10-01 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-10-08 | Submittal Number: 11 40 00-28.0 From: JOSH BROUSSARD Final Due Date: 10/15/20 Subject: UPPER CON AREA B INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREA FS3-5.04. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08674 | Review Response | Approved as Noted | 2020-10-05 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 11456 | Forwarded | For Review | 2020-10-08 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-28.0 From: JOSH BROUSSARD Final Due Date: 10/15/20 Subject: UPPER CON AREA B INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREA FS3-5.04. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08892 | Review Response | Approved | 2020-10-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.20 | Info Exchange
| 11749 | Responded and Closed | Approved as Noted | 2020-10-20 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 11 40 00-28.0 Upper Con Area B Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-01 |  | 11 40 00-28.0 Upper Con Area B Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-10-01 |  | 11 40 00-28.0 Upper Con Area B Install Plans & Equip Schedules.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-10-01 |  | 11 40 00-28.0 Upper Con Area B Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-01 |  | 11 40 00-28.0 Upper Con Area B Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-20 |  | 11 40 00-28.0 Upper Con Area B Install Plans & Equip Schedules_S2O_MEE_POP.pdf
11 40 00-029-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-029-00 Event Level Area B & C Install Plans & Equip Schedules | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-10-12 | 2020-10-08 | 11 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08356 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 11 40 00-29.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: EVENT LEVEL AREA B & C INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-1.03 AND FS3-1.04. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11070 | Forwarded | For Review | 2020-09-25 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-10-02 | Submittal Number: 11 40 00-29.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: EVENT LEVEL AREA B & C INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-1.03 AND FS3-1.04. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08661 | Review Response | Approved as Noted | 2020-09-28 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 11111 | Forwarded | For Review | 2020-09-28 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-29.0 From: JOSH BROUSSARD Final Due Date: 10/09/20 Subject: EVENT LEVEL AREA B & C INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-1.03 AND FS3-1.04. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08662 | Review Response | Approved as Noted | 2020-10-07 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.10.07 | Info Exchange
| 11445 | Responded and Closed | Approved as Noted | 2020-10-08 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.10.07 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 11 40 00-29.0 Event Level Area B & C Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 11 40 00-29.0 Event Level Area B & C Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-09-25 |  | 11 40 00-29.0 Event Level Area B & C Install Plans & Equip Schedules.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-09-25 |  | 11 40 00-29.0 Event Level Area B & C Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-25 |  | 11 40 00-29.0 Event Level Area B & C Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-08 |  | 11 40 00-29.0 Event Level Area B & C Install Plans & Equip Schedules_S2O_MEE_POP.pdf
11 40 00-031-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-031-00 Main Con Area B South Install Plans & Equip Schedules | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-16 | 2020-11-13 | 12 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-11-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09138 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-11-16 | Submittal Number: 11 40 00-31.0 From: JOSH BROUSSARD Final Due Date: 11/16/20 Subject: MAIN CON AREA B SOUTH INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-3.06, FS3-3.07, AND FS3-3.08. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12060 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Mark Lievens (ME Engineers); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-09 | Submittal Number: 11 40 00-31.0 From: JOSH BROUSSARD Final Due Date: 11/16/20 Subject: MAIN CON AREA B SOUTH INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-3.06, FS3-3.07, AND FS3-3.08. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09409 | Review Response | Approved as Noted | 2020-11-06 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  | POP to advise on heat lamp shroud finish. | Info Exchange
| 09410 | Review Response | Approved as Noted | 2020-11-12 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.12 | Info Exchange
| 12424 | Responded and Closed | Approved as Noted | 2020-11-13 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: POP to advise on heat lamp shroud finish. Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.12 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | 11 40 00-31.0 Main Con Area B South Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | 11 40 00-31.0 Main Con Area B South Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-11-02 |  | 11 40 00-31.0 Main Con Area B South Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-02 |  | 11 40 00-31.0 Main Con Area B South Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-13 |  | 11 40 00-31.0 Main Con Area B South Install Plans & Equip Schedules_ME_S2O_POP.pdf
11 40 00-032-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-032-00 Suite Level Area B Install Plans & Equip Schedules | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-01 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-10-15 | 2020-10-21 | 21 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-10-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08470 | Received | For Review | 2020-10-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-10-15 | Submittal Number: 11 40 00-32.0 From: JOSH BROUSSARD Final Due Date: 10/14/20 Subject: SUITE LEVEL AREA B INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-4.02 AND FS3-4.04. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11213 | Forwarded | For Review | 2020-10-01 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-10-08 | Submittal Number: 11 40 00-32.0 From: JOSH BROUSSARD Final Due Date: 10/14/20 Subject: SUITE LEVEL AREA B INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-4.02 AND FS3-4.04. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08672 | Review Response | Approved as Noted | 2020-10-05 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 11454 | Forwarded | For Review | 2020-10-08 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-32.0 From: JOSH BROUSSARD Final Due Date: 10/14/20 Subject: SUITE LEVEL AREA B INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-4.02 AND FS3-4.04. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 08891 | Review Response | Approved | 2020-10-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.20 | Info Exchange
| 11753 | Responded and Closed | Approved as Noted | 2020-10-21 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 11 40 00-32.0 Suite Level Area B Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 11 40 00-32.0 Suite Level Area B Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-09-30 |  | 11 40 00-32.0 Suite Level Area B Install Plans & Equip Schedules.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-09-30 |  | 11 40 00-32.0 Suite Level Area B Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-30 |  | 11 40 00-32.0 Suite Level Area B Install Plans & Equip Schedules.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-20 |  | 11 40 00-32.0 Suite Level Area B Install Plans & Equip Schedules_S2O_MEE_POP.pdf
11 40 00-032-01 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-032-01 FS3-4.04 Install Plans & Equip Schedules Rev 1 | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-01 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Heidi Evans (ME Engineers) |  |  |  | 2020-12-15 | 2020-12-03 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09770 | Received | For Review | 2020-12-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-12-15 | Submittal Number: 11 40 00-32.1 From: JOSH BROUSSARD Final Due Date: 12/14/20 Subject: FS3-4.04 INSTALL PLANS & EQUIP SCHEDULES REV 1 Description: THIS SUBMITTAL INCLUDES UPDATED INFORMATION FOR ITEM 17.014 AND 17.014B REFLECTIVE OF CHANGING SUPPLIERS FROM CHAMPION TO HOBART AT PANTRY 04.14.08. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12851 | Forwarded | For Review | 2020-12-01 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Mark Lievens (ME Engineers); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Heidi Evans (ME Engineers) | 2020-12-08 | Submittal Number: 11 40 00-32.1 From: JOSH BROUSSARD Final Due Date: 12/14/20 Subject: FS3-4.04 INSTALL PLANS & EQUIP SCHEDULES REV 1 Description: THIS SUBMITTAL INCLUDES UPDATED INFORMATION FOR ITEM 17.014 AND 17.014B REFLECTIVE OF CHANGING SUPPLIERS FROM CHAMPION TO HOBART AT PANTRY 04.14.08. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09844 | Review Response | Approved as Noted | 2020-12-02 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 12926 | Forwarded | For Review | 2020-12-02 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers) |  | Submittal Number: 11 40 00-32.1 From: JOSH BROUSSARD Final Due Date: 12/14/20 Subject: FS3-4.04 INSTALL PLANS & EQUIP SCHEDULES REV 1 Description: THIS SUBMITTAL INCLUDES UPDATED INFORMATION FOR ITEM 17.014 AND 17.014B REFLECTIVE OF CHANGING SUPPLIERS FROM CHAMPION TO HOBART AT PANTRY 04.14.08. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09880 | Review Response | Approved as Noted | 2020-12-03 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12963 | Responded and Closed | Approved as Noted | 2020-12-03 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-30 |  | 11 40 00-32.1 FS3-4.04 Install Plans & Equip Schedule Rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-30 |  | 11 40 00-32.1 FS3-4.04 Install Plans & Equip Schedule Rev 1.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-11-30 |  | 11 40 00-32.1 FS3-4.04 Install Plans & Equip Schedule Rev 1.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-11-30 |  | 11 40 00-32.1 FS3-4.04 Install Plans & Equip Schedule Rev 1.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-03 |  | 11 40 00-32.1 FS3-4.04 Install Plans & Equip Schedule Rev 1_S2O_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-30 |  | 11 40 00-32.1 FS3-4.04 Install Plans & Equip Schedule Rev 1.pdf
11 40 00-033-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-033-00 Space Needle Area A/B Install Plans & Equip Schedules | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-16 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-12-02 08:00 | 2020-12-02 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09436 | Received | For Review | 2020-11-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-12-02 08:00 | Submittal Number: 11 40 00-33.0 From: JOSH BROUSSARD Final Due Date: 11/27/20 Subject: SPACE NEEDLE AREA A/B INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-5.50.01 AND FS3-5.50.02. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12443 | Forwarded | For Review | 2020-11-16 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-11-23 | Submittal Number: 11 40 00-33.0 From: JOSH BROUSSARD Final Due Date: 11/27/20 Subject: SPACE NEEDLE AREA A/B INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-5.50.01 AND FS3-5.50.02. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09831 | Review Response | Approved as Noted | 2020-11-17 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 12578 | Forwarded | For Review | 2020-11-18 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-33.0 From: JOSH BROUSSARD Final Due Date: 11/27/20 Subject: SPACE NEEDLE AREA A/B INSTALL PLANS & EQUIP SCHEDULES Description: THIS SUBMITTAL INCLUDES DRAWINGS, SCHEDULES, AND BUY OUT BOOKS FOR FOOD SERVICE AREAS FS3-5.50.01 AND FS3-5.50.02. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09832 | Review Response | Approved as Noted | 2020-11-30 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.30 | Info Exchange
| 09835 | Review Response | Approved as Noted | 2020-12-02 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12919 | Responded and Closed | Approved as Noted | 2020-12-02 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.30 Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-13 |  | 11 40 00-31.0 Space Needle Club Install Plans & Equip Schedules.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-13 |  | 11 40 00-31.0 Space Needle Club Install Plans & Equip Schedules.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-11-13 |  | 11 40 00-31.0 Space Needle Club Install Plans & Equip Schedules.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-11-13 |  | 11 40 00-31.0 Space Needle Club Install Plans & Equip Schedules.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-13 |  | 11 40 00-31.0 Space Needle Club Install Plans & Equip Schedules.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-02 |  | 11 40 00-31.0 Space Needle Club Install Plans & Equip Schedules_S2O_ME_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-13 |  | 11 40 00-31.0 Space Needle Club Install Plans & Equip Schedules.pdf
11 40 00-034-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-034-00 Hood Support Materials | Closed | Food Services, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-22 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Matthew Farber (Thornton Tomasetti), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-14 | 2021-01-06 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-01-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10311 | Received | For Review | 2020-12-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2021-01-14 | Submittal Number: 11 40 00-34.0 From: JOSH BROUSSARD Final Due Date: 01/05/21 Subject: HOOD SUPPORT MATERIALS Description: THE ATTACHED SUBMITTAL INCLUDES ENGINEERING AND CONNECTION DETAILS TO THE BUILDING STRUCTURE FOR THE HOODS IN THE MAIN KITCHEN ON THE EVENT LEVEL. LOADING OF HOODS ON THE BUILDING STRUCTURE TO BE REVIEWED BY THORNTON TOMASETTI FOR VERIFICATION THAT THE STRUCTURE CAN ACCOMMODATE THE REACTIONS FROM THE CONNECTIONS SPECIFIED IN THE SUBMITTAL. PRODUCT DATA FOR INSTALLATION COMPONENTS NOT PROVIDED BY ISAT TO BE PROVIDED IN A SEPARATE SUBMITTAL. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13470 | Forwarded | For Review | 2020-12-22 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Matthew Farber (Thornton Tomasetti); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasett... | 2020-12-29 | Submittal Number: 11 40 00-34.0 From: JOSH BROUSSARD Final Due Date: 01/05/21 Subject: HOOD SUPPORT MATERIALS Description: THE ATTACHED SUBMITTAL INCLUDES ENGINEERING AND CONNECTION DETAILS TO THE BUILDING STRUCTURE FOR THE HOODS IN THE MAIN KITCHEN ON THE EVENT LEVEL. LOADING OF HOODS ON THE BUILDING STRUCTURE TO BE REVIEWED BY THORNTON TOMASETTI FOR VERIFICATION THAT THE STRUCTURE CAN ACCOMMODATE THE REACTIONS FROM THE CONNECTIONS SPECIFIED IN THE SUBMITTAL. PRODUCT DATA FOR INSTALLATION COMPONENTS NOT PROVIDED BY ISAT TO BE PROVIDED IN A SEPARATE SUBMITTAL. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10366 | Review Response | No Action Taken or Required | 2020-12-22 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  | Reviewed. | Info Exchange
| 13544 | Responded and Closed | No Action Taken or Required | 2020-12-30 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Peg Galie (S2O Consultants, Inc.) Remarks: Reviewed. | Info Exchange
| 13545 | Reopened | Additional Information | 2020-12-30 17:45 | Kelsea Conkright (Populous)
| 13546 | Forwarded | For Review | 2020-12-30 | Kelsea Conkright (Populous) | Matt Ross (Thornton Tomasetti) |  | Submittal Number: 11 40 00-34.0 From: JOSH BROUSSARD Final Due Date: 01/05/21 Subject: HOOD SUPPORT MATERIALS Description: THE ATTACHED SUBMITTAL INCLUDES ENGINEERING AND CONNECTION DETAILS TO THE BUILDING STRUCTURE FOR THE HOODS IN THE MAIN KITCHEN ON THE EVENT LEVEL. LOADING OF HOODS ON THE BUILDING STRUCTURE TO BE REVIEWED BY THORNTON TOMASETTI FOR VERIFICATION THAT THE STRUCTURE CAN ACCOMMODATE THE REACTIONS FROM THE CONNECTIONS SPECIFIED IN THE SUBMITTAL. PRODUCT DATA FOR INSTALLATION COMPONENTS NOT PROVIDED BY ISAT TO BE PROVIDED IN A SEPARATE SUBMITTAL. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10482 | Review Response | Approved as Noted | 2021-01-06 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 13682 | Responded and Closed | Approved as Noted | 2021-01-06 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Peg Galie (S2O Consultants, Inc.) Remarks: Reviewed. Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-22 |  | 11 40 00-34.0 Kitchen Hood Seismic Bracing & Anchorage Design.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-22 |  | 11 40 00-34.0 Kitchen Hood Seismic Bracing & Anchorage Design.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-12-30 |  | 11 40 00-34.0 Kitchen Hood Seismic Bracing & Anchorage Design_S2O_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-12-22 |  | 11 40 00-34.0 Kitchen Hood Seismic Bracing & Anchorage Design.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-12-30 |  | 11 40 00-34.0 Kitchen Hood Seismic Bracing & Anchorage Design_S2O_POP.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-30 |  | 11 40 00-34.0 Kitchen Hood Seismic Bracing & Anchorage Design_S2O_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-06 |  | 11 40 00-34.0 Kitchen Hood Seismic Bracing & Anchorage Design_S2O_POP_TT.pdf
11 40 00-035-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-035-00 Item 21.909 Fire Extinguishing System | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-27 | Responded and Closed - Approved as Noted/Resubmit |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Heidi Evans (ME Engineers) |  |  |  | 2020-11-10 | 2020-11-02 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-11-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09022 | Received | For Review | 2020-10-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-11-10 | Submittal Number: 11 40 00-35.0 From: JOSH BROUSSARD Final Due Date: 11/10/20 Subject: ITEM 21.909 FIRE EXTINGUISHING SYSTEM Description: THIS SUBMITTAL INCLUDE THE DATA SHEETS AND O&M MANUAL FOR FOOD SERVICE ITEM 21.909 (ANSUL FIRE EXTINGUISHING SYSTEM). Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 11903 | Forwarded | For Review | 2020-10-27 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Heidi Evans (ME Engineers) | 2020-11-03 | Submittal Number: 11 40 00-35.0 From: JOSH BROUSSARD Final Due Date: 11/10/20 Subject: ITEM 21.909 FIRE EXTINGUISHING SYSTEM Description: THIS SUBMITTAL INCLUDE THE DATA SHEETS AND O&M MANUAL FOR FOOD SERVICE ITEM 21.909 (ANSUL FIRE EXTINGUISHING SYSTEM). Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09177 | Review Response | Approved | 2020-10-28 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 09178 | Review Response | Approved as Noted/Resubmit | 2020-11-02 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.11.02 | Info Exchange
| 12109 | Responded and Closed | Approved as Noted | 2020-11-02 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.11.02 | Info Exchange
| 12110 | Reopened | Additional Information | 2020-11-02 17:41 | Kelsea Conkright (Populous)
| 12112 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-02 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.11.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 11 40 00-35.0 Item 21.909 Fire Extinguishing System.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 11 40 00-35.0 Item 21.909 Fire Extinguishing System.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-10-27 |  | 11 40 00-35.0 Item 21.909 Fire Extinguishing System.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-02 |  | 11 40 00-35.0 Item 21.909 Fire Extinguishing System_ME.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-02 |  | 11 40 00-35.0 Item 21.909 Fire Extinguishing System_S2O_ME_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-02 |  | 11 40 00-35.0 Item 21.909 Fire Extinguishing System_S2O_ME_POP.pdf
11 40 00-035-01 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-035-01 Item 21.909 Fire Extinguishing System | Closed | Food Services, Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-10 | Responded and Closed - Approved as Noted/Resubmit |  | Amber Kennedy (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-04 08:00 | 2020-12-29 | 20 |  | Record Copies; Transfers; Submittals | 11 40 00-035-01-01 - 11 40 00-035-01 Item 21.909 Fire Extinguishing System | 14 |  | 2020-12-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10078 | Received | For Review | 2020-12-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Josh Broussard (M.A. Mortenson Company) | 2021-01-04 08:00 | Submittal Number: 11 40 00-35.1 From: JOSH BROUSSARD Final Due Date: 12/23/20 Subject: ITEM 21.909 FIRE EXTINGUISHING SYSTEM Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13174 | Forwarded | For Review | 2020-12-10 | Josh Broussard (M.A. Mortenson Company) | Amber Kennedy (S2O Consultants, Inc.); Mark Lievens (ME Engineers); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-17 | Submittal Number: 11 40 00-35.1 From: JOSH BROUSSARD Final Due Date: 12/23/20 Subject: ITEM 21.909 FIRE EXTINGUISHING SYSTEM Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10337 | Review Response | Approved | 2020-12-11 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 13504 | Forwarded | For Review | 2020-12-23 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers) |  | Submittal Number: 11 40 00-35.1 From: JOSH BROUSSARD Final Due Date: 12/23/20 Subject: ITEM 21.909 FIRE EXTINGUISHING SYSTEM Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10358 | Review Response | Approved as Noted/Resubmit | 2020-12-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.12.23 | Info Exchange
| 13534 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.12.23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-09 |  | 11 40 00-35.1 Item 21.909 Fire Extinguishing System R1.pdf
| Forwarded |  | Josh Broussard (Mortenson Construction) | 1 | 2020-12-09 |  | 11 40 00-35.1 Item 21.909 Fire Extinguishing System R1.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-12-09 |  | 11 40 00-35.1 Item 21.909 Fire Extinguishing System R1.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-12-09 |  | 11 40 00-35.1 Item 21.909 Fire Extinguishing System R1.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-12-09 |  | 11 40 00-35.1 Item 21.909 Fire Extinguishing System R1.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-29 |  | 11 40 00-35.1 Item 21.909 Fire Extinguishing System R1_S2O_ME_POP.pdf
11 40 00-035-01-01 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-035-01 Item 21.909 Fire Extinguishing System | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 40 00-035-01 - 11 40 00-035-01 Item 21.909 Fire Extinguishing System | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-29 |  | 11 40 00-35.1 Item 21.909 Fire Extinguishing System R1_S2O_ME_POP.pdf
11 40 00-036-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-036-00 Interlake Pallet Rack Product Data | Closed | Architectural, Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-21 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Kuebler Perry (Populous) |  |  |  | 2021-01-13 | 2020-12-30 | 10 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-12-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10257 | Received | For Review | 2020-12-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Josh Broussard (M.A. Mortenson Company) | 2021-01-13 | Submittal Number: 11 40 00-36.0 From: JOSH BROUSSARD Final Due Date: 12/31/20 Subject: INTERLAKE PALLET RACK PRODUCT DATA Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13412 | Forwarded | For Review | 2020-12-18 | Josh Broussard (M.A. Mortenson Company) | Kelsea Conkright (Populous); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.); Kuebler Perry (Populous) | 2020-12-25 | Submittal Number: 11 40 00-36.0 From: JOSH BROUSSARD Final Due Date: 12/31/20 Subject: INTERLAKE PALLET RACK PRODUCT DATA Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10315 | Review Response | Rejected | 2020-12-21 | Peg Galie (S2O Consultants, Inc.) | Josh Broussard (M.A. Mortenson Company) |  | No attachments provide. Please provide the data sheets for review. | Info Exchange
| 13480 | Forwarded | For Review | 2020-12-22 | Josh Broussard (M.A. Mortenson Company) | Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-12-29 | Submittal Number: 11 40 00-36.0 From: JOSH BROUSSARD Final Due Date: 12/31/20 Subject: INTERLAKE PALLET RACK PRODUCT DATA Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10363 | Review Response | Approved as Noted | 2020-12-22 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 13542 | Responded and Closed | Approved as Noted | 2020-12-30 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-18 02:00 |  | 11 40 00-36.0 Interlake Pallet Rack Product Data.pdf
| Forwarded |  | Josh Broussard (Mortenson Construction) | 1 | 2020-12-18 02:00 |  | 11 40 00-36.0 Interlake Pallet Rack Product Data.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-12-18 02:00 |  | 11 40 00-36.0 Interlake Pallet Rack Product Data.pdf
| Forwarded |  | Josh Broussard (Mortenson Construction) | 1 | 2020-12-22 02:00 |  | Copy of 11 40 00-36.0 Interlake Pallet Rack Product Data.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-12-22 |  | Copy of 11 40 00-36.0 Interlake Pallet Rack Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-30 |  | 11 40 00-36.0 Interlake Pallet Rack Product Data_S2O_POP.pdf
11 40 00-037-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-037-00 CCD 075 Food Service Revisions | Closed | Food Services, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-12-03 08:00 | 2020-12-09 | 23 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-12-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09479 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 11 40 00-37.0 From: JOSH BROUSSARD Final Due Date: 12/01/20 Subject: CCD 075 FOOD SERVICE REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12497 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-11-24 | Submittal Number: 11 40 00-37.0 From: JOSH BROUSSARD Final Due Date: 12/01/20 Subject: CCD 075 FOOD SERVICE REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09820 | Review Response | Approved as Noted | 2020-11-19 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  | Make corrections noted | Info Exchange
| 09825 | Review Response | Approved as Noted | 2020-12-02 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12975 | Forwarded | For Review | 2020-12-03 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-37.0 From: JOSH BROUSSARD Final Due Date: 12/01/20 Subject: CCD 075 FOOD SERVICE REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10048 | Review Response | Approved as Noted | 2020-12-08 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.12.08 | Info Exchange
| 13149 | Responded and Closed | Approved as Noted | 2020-12-09 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Make corrections noted Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.12.08 Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | 11 40 00-37.0 CCD 075 Food Service Revisions.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | 11 40 00-37.0 CCD 075 Food Service Revisions.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-11-17 |  | 11 40 00-37.0 CCD 075 Food Service Revisions.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-02 |  | 11 40 00-37.0 CCD 075 Food Service Revisions_S2O_POP.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-11-17 |  | 11 40 00-37.0 CCD 075 Food Service Revisions.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-17 |  | 11 40 00-37.0 CCD 075 Food Service Revisions.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-12-09 |  | 11 40 00-37.0 CCD 075 Food Service Revisions_S2O_POP_ME.pdf
11 40 00-038-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-038-00 CCD 077 Food Service Revisions | Closed | Food Services, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-23 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-12-09 | 2020-12-09 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-12-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09685 | Received | For Review | 2020-11-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-09 | Submittal Number: 11 40 00-38.0 From: JOSH BROUSSARD Final Due Date: 12/07/20 Subject: CCD 077 FOOD SERVICE REVISIONS Description: THIS SUBMITTAL INCLUDES REVISIONS TO FS3-3.05, FS3-3.13, FS3-3.15, FS3-4.07, AND FS3-4.10 PER CCD 077. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12739 | Forwarded | For Review | 2020-11-23 | Populous SCA_CCA | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-11-30 | Submittal Number: 11 40 00-38.0 From: JOSH BROUSSARD Final Due Date: 12/07/20 Subject: CCD 077 FOOD SERVICE REVISIONS Description: THIS SUBMITTAL INCLUDES REVISIONS TO FS3-3.05, FS3-3.13, FS3-3.15, FS3-4.07, AND FS3-4.10 PER CCD 077. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 09846 | Review Response | Approved as Noted | 2020-11-30 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 12928 | Forwarded | For Review | 2020-12-02 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-38.0 From: JOSH BROUSSARD Final Due Date: 12/07/20 Subject: CCD 077 FOOD SERVICE REVISIONS Description: THIS SUBMITTAL INCLUDES REVISIONS TO FS3-3.05, FS3-3.13, FS3-3.15, FS3-4.07, AND FS3-4.10 PER CCD 077. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10052 | Review Response | Approved as Noted | 2020-12-09 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Mark Lievens ME Engineers 2020.12.09 | Info Exchange
| 13155 | Responded and Closed | Approved as Noted | 2020-12-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2020.12.09 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-23 |  | 11 40 00-38.0 CCD 077 Food Service Revisions.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-23 |  | 11 40 00-38.0 CCD 077 Food Service Revisions.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-11-23 |  | 11 40 00-38.0 CCD 077 Food Service Revisions.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-02 |  | 11 40 00-38.0 CCD 077 Food Service Revisions_S2O.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-12-02 |  | 11 40 00-38.0 CCD 077 Food Service Revisions_S2O.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-09 |  | 11 40 00-38.0 CCD 077 Food Service Revisions_S2O-ME-POP.pdf
11 40 00-039-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-039-00 CCD 079 Food Service Revisions | Closed | Food Services, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-15 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2021-01-07 | 2021-01-08 | 25 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10157 | Received | For Review | 2020-12-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2021-01-07 | Submittal Number: 11 40 00-39.0 From: JOSH BROUSSARD Final Due Date: 12/28/20 Subject: CCD 079 FOOD SERVICE REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13290 | Forwarded | For Review | 2020-12-15 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-12-22 | Submittal Number: 11 40 00-39.0 From: JOSH BROUSSARD Final Due Date: 12/28/20Status: OPEN Subject: CCD 079 FOOD SERVICE REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT | Info Exchange
| 10362 | Review Response | Approved as Noted | 2020-12-15 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 13539 | Forwarded | For Review | 2020-12-30 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-39.0 From: JOSH BROUSSARD Final Due Date: 12/28/20Status: OPEN Subject: CCD 079 FOOD SERVICE REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT | Info Exchange
| 10537 | Review Response | Approved | 2021-01-07 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.01.07 | Info Exchange
| 13737 | Responded and Closed | Approved as Noted | 2021-01-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.01.07 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-14 |  | 11 40 00-39.0 CCD 079 Food Service Revisions.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-14 |  | 11 40 00-39.0 CCD 079 Food Service Revisions.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-12-14 |  | 11 40 00-39.0 CCD 079 Food Service Revisions.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2020-12-14 |  | 11 40 00-39.0 CCD 079 Food Service Revisions.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-12-14 |  | 11 40 00-39.0 CCD 079 Food Service Revisions.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-08 |  | 11 40 00-39.0 CCD 079 Food Service Revisions_S2O_ME_POP.pdf
11 40 00-040-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-040-00 CCD 084 Food Service Equipment Revisions | Closed | Food Services, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers) |  |  |  | 2021-01-21 | 2021-01-11 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10518 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (Mortenson Construction) | 2021-01-21 | Submittal Number: 11 40 00-40.0 From: JOSH BROUSSARD Final Due Date: 01/21/21 Subject: CCD 084 FOOD SERVICE EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13722 | Forwarded | For Review | 2021-01-07 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2021-01-14 | Submittal Number: 11 40 00-40.0 From: JOSH BROUSSARD Final Due Date: 01/21/21 Subject: CCD 084 FOOD SERVICE EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10539 | Review Response | Approved as Noted | 2021-01-08 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 13739 | Forwarded | For Review | 2021-01-08 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers) |  | Submittal Number: 11 40 00-40.0 From: JOSH BROUSSARD Final Due Date: 01/21/21 Subject: CCD 084 FOOD SERVICE EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10610 | Review Response | Approved as Noted | 2021-01-11 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.01.11 | Info Exchange
| 13823 | Responded and Closed | Approved as Noted | 2021-01-11 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.01.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-07 |  | 11 40 00-40.0 CCD 084 Food Service Revisions.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-07 |  | 11 40 00-40.0 CCD 084 Food Service Revisions.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-01-07 |  | 11 40 00-40.0 CCD 084 Food Service Revisions.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-01-07 |  | 11 40 00-40.0 CCD 084 Food Service Revisions.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-01-07 |  | 11 40 00-40.0 CCD 084 Food Service Revisions.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-01-11 |  | 11 40 00-40.0 CCD 084 Food Service Revisions_S2O_ME_POP.pdf
11 40 00-042-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-042-00 Food Service Wire Shelves - Metro | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-19 | Responded and Closed - Approved |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2021-02-02 | 2021-01-20 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10768 | Received | For Review | 2021-01-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (Mortenson Construction) | 2021-02-02 | Submittal Number: 11 40 00-42.0 From: JOSH BROUSSARD Final Due Date: 02/02/21 Subject: FOOD SERVICE WIRE SHELVES - METRO Description: THIS SUBMITTAL PROVIDES CORRECTIONS FOR WIRE SHELVING ITEMS THAT WERE REJECTED ON PREVIOUS SUBMITTAL PACKAGES - PROVIDING THE APPROVED ALTERNATE METRO PRODUCTS IN LIEU OF EAGLE. THIS INCLUDES ITEM #’S 13.133, 13.134, 13.135, 13.143, 13.144, 13.145. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 14003 | Forwarded | For Review | 2021-01-19 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2021-01-26 | Submittal Number: 11 40 00-42.0 From: JOSH BROUSSARD Final Due Date: 02/02/21 Subject: FOOD SERVICE WIRE SHELVES - METRO Description: THIS SUBMITTAL PROVIDES CORRECTIONS FOR WIRE SHELVING ITEMS THAT WERE REJECTED ON PREVIOUS SUBMITTAL PACKAGES - PROVIDING THE APPROVED ALTERNATE METRO PRODUCTS IN LIEU OF EAGLE. THIS INCLUDES ITEM #’S 13.133, 13.134, 13.135, 13.143, 13.144, 13.145. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 10810 | Review Response | Approved | 2021-01-19 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  |  | Info Exchange
| 14059 | Responded and Closed | Approved | 2021-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Josh Broussard (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Peg Galie (S2O Consultants, Inc.) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-19 |  | 11 40 00-42.0 Metro Food Service Wire Shelves.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-19 |  | 11 40 00-42.0 Metro Food Service Wire Shelves.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-01-18 02:00 |  | 11 40 00-42.0 Metro Food Service Wire Shelves.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-20 02:00 |  | 210119 S2O Resp 11 40 00-42.0 Metro Food Service Wire Shelves_pop.pdf
11 40 00-043-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-043-00 CCD 086 & 088 Food Service Equipment Revisions | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-08 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2021-03-22 | 2021-03-24 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11840 | Received | For Review | 2021-03-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (Mortenson Construction) | 2021-03-22 | Submittal Number: 11 40 00-43.0 From: JOSH BROUSSARD Final Due Date: 03/22/21 Subject: CCD 086 & 088 FOOD SERVICE EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 15351 | Forwarded | For Review | 2021-03-08 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2021-03-15 | Submittal Number: 11 40 00-43.0 From: JOSH BROUSSARD Final Due Date: 03/22/21 Subject: CCD 086 & 088 FOOD SERVICE EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12222 | Review Response | Approved as Noted | 2021-03-10 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 15566 | Forwarded | For Review | 2021-03-15 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-43.0 From: JOSH BROUSSARD Final Due Date: 03/22/21 Subject: CCD 086 & 088 FOOD SERVICE EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12223 | Review Response | Approved as Noted | 2021-03-24 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.03.24 | Info Exchange
| 15812 | Responded and Closed | Approved as Noted | 2021-03-24 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.03.24 Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-08 |  | 11 40 00-43.0 CCD 86_88 Equip Revs.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-08 |  | 11 40 00-43.0 CCD 86_88 Equip Revs.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-03-08 |  | 11 40 00-43.0 CCD 86_88 Equip Revs.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-03-08 |  | 11 40 00-43.0 CCD 86_88 Equip Revs.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-03-08 |  | 11 40 00-43.0 CCD 86_88 Equip Revs.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-24 |  | 11 40 00-43.0 CCD 86_88 Equip Revs - S2O_ME_POP.pdf
11 40 00-044-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-044-00 FS3-4.11 Custom Stainless Counter Per CCD 088 | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2021-04-22 | 2021-04-26 | 19 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12471 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Josh Broussard (Mortenson Construction) | 2021-04-22 | Submittal Number: 11 40 00-44.0 From: JOSH BROUSSARD Final Due Date: 04/09/21 Subject: FS3-4.11 CUSTOM STAINLESS COUNTER PER CCD 088 Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 16161 | Forwarded | For Review | 2021-04-08 | Josh Broussard (Mortenson Construction) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2021-04-15 | Submittal Number: 11 40 00-44.0 From: JOSH BROUSSARD Final Due Date: 04/09/21 Subject: FS3-4.11 CUSTOM STAINLESS COUNTER PER CCD 088 Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 12682 | Review Response | Approved as Noted | 2021-04-08 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  | Populous to review to confirm pass through openings at front counter | Info Exchange
| 16502 | Responded and Closed | Approved as Noted | 2021-04-26 | Chad Francis (Populous) | Josh Broussard (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 11 40 00-44.0 - FS3-4.11 Custom Stainless Counter Per CCD 088.pdf
| Forwarded |  | Josh Broussard (Mortenson Construction) | 1 | 2021-04-08 |  | 11 40 00-44.0 - FS3-4.11 Custom Stainless Counter Per CCD 088.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-04-08 |  | 11 40 00-44.0 - FS3-4.11 Custom Stainless Counter Per CCD 088.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-26 |  | 210408 S2O Resp 40 00-44.0 - FS3-4.11 Custom Stainless Counter Per CCD 088_POP.pdf
11 40 00-045-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-045-00 CCD 091 & CCD 094 Equipment Revisions | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-23 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2021-05-07 | 2021-05-14 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-05-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12725 | Received | For Review | 2021-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-07 | Submittal Number: 11 40 00-45.0 From: JOSH BROUSSARD Final Due Date: 05/06/21 Subject: CCD 091 & CCD 094 EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 16451 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2021-04-29 | Submittal Number: 11 40 00-45.0 From: JOSH BROUSSARD Final Due Date: 05/06/21 Subject: CCD 091 & CCD 094 EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13104 | Review Response | Approved as Noted | 2021-04-26 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  | Please see comments on PDF | Info Exchange
| 16564 | Forwarded | For Review | 2021-04-27 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) |  | Submittal Number: 11 40 00-45.0 From: JOSH BROUSSARD Final Due Date: 05/06/21 Subject: CCD 091 & CCD 094 EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13105 | Review Response | Approved as Noted | 2021-05-13 | Mark Lievens (ME Engineers) | Kelsea Conkright (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.05.13 | Info Exchange
| 16950 | Responded and Closed | Approved as Noted | 2021-05-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Please see comments on PDF Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.05.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-22 |  | 11 40 00-45.0 - CCD 091 & 094 Epuipment Revs.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-22 |  | 11 40 00-45.0 - CCD 091 & 094 Epuipment Revs.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-04-22 |  | 11 40 00-45.0 - CCD 091 & 094 Epuipment Revs.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-22 |  | 11 40 00-45.0 - CCD 091 & 094 Epuipment Revs.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-22 |  | 11 40 00-45.0 - CCD 091 & 094 Epuipment Revs.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-14 |  | 210426 S2O Resp 11 40 00-45.0 - CCD 091 & 094 Epuipment Revs - ME Review_POP.pdf
11 40 00-046-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-046-00 CCD 099 & 101 Equipment Revisions | Closed | Food Services, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-27 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-11 | 2021-06-07 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13295 | Received | For Review | 2021-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-11 | Submittal Number: 11 40 00-46.0 From: JOSH BROUSSARD Final Due Date: 06/09/21 Subject: CCD 099 & 101 EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 17195 | Forwarded | For Review | 2021-05-27 | Populous SCA_CCA | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2021-06-03 | Submittal Number: 11 40 00-46.0 From: JOSH BROUSSARD Final Due Date: 06/09/21 Subject: CCD 099 & 101 EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13410 | Review Response | Approved as Noted | 2021-06-01 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 17256 | Forwarded | For Review | 2021-06-01 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-08 | Submittal Number: 11 40 00-46.0 From: JOSH BROUSSARD Final Due Date: 06/09/21 Subject: CCD 099 & 101 EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13411 | Review Response | Approved | 2021-06-04 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.06.04 | Info Exchange
| 13412 | Review Response | Approved as Noted | 2021-06-07 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17345 | Responded and Closed | Approved as Noted | 2021-06-07 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.06.04 Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-26 |  | 11 40 00-46.0 - CCD 099 & 101 Epuipment Revs.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-26 |  | 11 40 00-46.0 - CCD 099 & 101 Epuipment Revs.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-05-26 |  | 11 40 00-46.0 - CCD 099 & 101 Epuipment Revs.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-25 02:00 |  | 11 40 00-46.0 - CCD 099 & 101 Epuipment Revs.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-05-25 |  | 11 40 00-46.0 - CCD 099 & 101 Epuipment Revs.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-07 |  | 11 40 00-46.0 - CCD 099 & 101 Epuipment Revs_S2O_ME_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-07 |  | 11 40 00-46.0 - CCD 099 & 101 Epuipment Revs_S2O_ME_POP.pdf
11 40 00-047-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-047-00 FOOD SERVICE EQUIPMENT - Manufacturers List | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-10 | Responded and Closed - No Action Taken or Required |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2021-05-24 | 2021-05-12 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13020 | Received | For Review | 2021-05-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-24 | Submittal Number: 11 40 00-47.0 From: JOSH BROUSSARD Final Due Date: 05/24/21 Subject: FOOD SERVICE EQUIPMENT - MANUFACTURERS LIST Description: MANUFACTURERS' LIST : SUBMIT IN WRITINGA LIST OF ALL MANUFACTURERS' REPRESENTATIVES OF THE FOODSERVICE EQUIPMENT, SUCH AS CONVECTION OVENS, RANGES, ETC., AND THEIR AUTHORIZED SERVICE AGENCIES' ADDRESSES AND TELEPHONE NUMBERS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 16848 | Forwarded | For Review | 2021-05-10 | Populous SCA_CCA | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2021-05-17 | Submittal Number: 11 40 00-47.0 From: JOSH BROUSSARD Final Due Date: 05/24/21 Subject: FOOD SERVICE EQUIPMENT - MANUFACTURERS LIST Description: MANUFACTURERS' LIST : SUBMIT IN WRITINGA LIST OF ALL MANUFACTURERS' REPRESENTATIVES OF THE FOODSERVICE EQUIPMENT, SUCH AS CONVECTION OVENS, RANGES, ETC., AND THEIR AUTHORIZED SERVICE AGENCIES' ADDRESSES AND TELEPHONE NUMBERS. Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13085 | Review Response | Approved | 2021-05-11 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  | Reviewed fro information | Info Exchange
| 16922 | Responded and Closed | No Action Taken or Required | 2021-05-12 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Peg Galie (S2O Consultants, Inc.) Remarks: Reviewed for information | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 11 40 00-47.0 Manufacturers Represntative List.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-10 |  | 11 40 00-47.0 Manufacturers Represntative List.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-05-10 |  | 11 40 00-47.0 Manufacturers Represntative List.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-12 |  | 210511 S2O Resp 11 40 00-47.0 Manufacturers Represntative List_POP.pdf
11 40 00-049-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-049-00 GUARANTIES AND WARRANTIES | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-27 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Mark Lievens (ME Engineers), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2021-09-10 | 2021-09-01 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14527 | Received | For Review | 2021-08-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-10 | Submittal Number: 11 40 00-49.0 From: JOSH BROUSSARD Final Due Date: 09/10/21 Subject: GUARANTIES AND WARRANTIES Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 18728 | Forwarded | For Review | 2021-08-30 | Populous SCA_CCA | Kelsea Conkright (Populous); Mark Lievens (ME Engineers); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.) | 2021-09-06 | Submittal Number: 11 40 00-49.0 From: JOSH BROUSSARD Final Due Date: 09/10/21 Subject: GUARANTIES AND WARRANTIES Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 14540 | Review Response | Approved | 2021-08-31 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 18745 | Responded and Closed | Approved | 2021-09-01 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Peg Galie (S2O Consultants, Inc.) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-27 02:00 |  | 11 40 00-49.0 Stafford-Smith Draft Warranty Letters.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-27 02:00 |  | 11 40 00-49.0 Stafford-Smith Draft Warranty Letters.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-08-27 |  | 11 40 00-49.0 Stafford-Smith Draft Warranty Letters.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-01 |  | 210831 S2O Resp 11 40 00-49.0 Stafford-Smith Draft Warranty Letters_POP.pdf
11 40 00-055-00 | 11 40 00 - FOOD SERVICE EQUIPMENT | 11 40 00-055-00 CCD 105 & CCD 107 Equipment Revisions | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-08 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-22 | 2021-07-15 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13839 | Received | For Review | 2021-07-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (Mortenson Construction) | 2021-07-22 | Submittal Number: 11 40 00-55.0 From: JOSH BROUSSARD Final Due Date: 07/22/21 Subject: CCD 105 & CCD 107 EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 17914 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2021-07-15 | Submittal Number: 11 40 00-55.0 From: JOSH BROUSSARD Final Due Date: 07/22/21 Subject: CCD 105 & CCD 107 EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13947 | Review Response | Approved | 2021-07-08 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  |  | Info Exchange
| 17948 | Forwarded | For Review | 2021-07-08 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-15 | Submittal Number: 11 40 00-55.0 From: JOSH BROUSSARD Final Due Date: 07/22/21 Subject: CCD 105 & CCD 107 EQUIPMENT REVISIONS Description: Spec Section: 11 40 00 - FOOD SERVICE EQUIPMENT Status: OPEN | Info Exchange
| 13948 | Review Response | Approved as Noted | 2021-07-15 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.15 | Info Exchange
| 13949 | Review Response | Approved as Noted | 2021-07-15 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18051 | Responded and Closed | Approved as Noted | 2021-07-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.15 Response (Approved) from: Peg Galie (S2O Consultants, Inc.) Remarks: Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-08 |  | 11 40 00-55.0 - CCD 105 & 107 Epuipment Revs.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-08 |  | 11 40 00-55.0 - CCD 105 & 107 Epuipment Revs.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-07-08 |  | 11 40 00-55.0 - CCD 105 & 107 Epuipment Revs.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-07-07 02:00 |  | 11 40 00-55.0 - CCD 105 & 107 Epuipment Revs.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-07 |  | 11 40 00-55.0 - CCD 105 & 107 Epuipment Revs.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-07-15 |  | 11 40 00-55.0 - CCD 105 & 107 Epuipment Revs_S2O_ME_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-08 |  | 11 40 00-55.0 - CCD 105 & 107 Epuipment Revs.pdf
11 61 43-003-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-003-00 Arena Curtains - Samples & Product Data (Packages 1, 2, 3, and 4) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-18 | 2021-02-09 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11189 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-18 | Submittal Number: 11 61 43-3.0 From: DOMINGO SAMPAYO Final Due Date: 02/16/21 Subject: AREAN CURTAINS - SAMPLES & PRODUCT DATA (PACKAGES 1, 2, 3, AND 4) Description: SAMPLES SUBMITTED: DUTCH VELOUR 22 OZ UPGRADE AND ALTERNATIVE TO 15/16OZ DUTCH VELOUR 22OZ WITH LINER ********** PACKAGE 1: ARENA BLACKOUT - DUTCH VELOUR 22OZ (NO LINER NEEDED AS HEAVIER FABRIC) PACKAGE 2: NORTH ACOUSTIC – DUTCH VELOUR 22OZ PLUS LINER (SEE SAMPLE WITH LINER) PACKAGE 3: UPPER BOWL (NEW DESIGN/CHANGE) - DUTCH VELOUR 22OZ (SUGGEST NO LINER NEEDED AS HEAVIER FABRIC) PACKAGE 4: HALF HOUSE- DUTCH VELOUR 22OZ (NO LINER NEEDED AS HEAVIER FABRIC) Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14495 | Forwarded | For Review | 2021-02-04 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-11 | Submittal Number: 11 61 43-3.0 From: DOMINGO SAMPAYO Final Due Date: 02/16/21 Subject: AREAN CURTAINS - SAMPLES & PRODUCT DATA (PACKAGES 1, 2, 3, AND 4) Description: SAMPLES SUBMITTED: DUTCH VELOUR 22 OZ UPGRADE AND ALTERNATIVE TO 15/16OZ DUTCH VELOUR 22OZ WITH LINER ********** PACKAGE 1: ARENA BLACKOUT - DUTCH VELOUR 22OZ (NO LINER NEEDED AS HEAVIER FABRIC) PACKAGE 2: NORTH ACOUSTIC – DUTCH VELOUR 22OZ PLUS LINER (SEE SAMPLE WITH LINER) PACKAGE 3: UPPER BOWL (NEW DESIGN/CHANGE) - DUTCH VELOUR 22OZ (SUGGEST NO LINER NEEDED AS HEAVIER FABRIC) PACKAGE 4: HALF HOUSE- DUTCH VELOUR 22OZ (NO LINER NEEDED AS HEAVIER FABRIC) Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14639 | Responded and Closed | Approved as Noted | 2021-02-09 | Populous SCA_CCA | Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-03 |  | 11 61 43-3 Areana Curtains - Samples & Product Data (Packages 1 2 3 and 4).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-03 |  | 11 61 43-3 Areana Curtains - Samples & Product Data (Packages 1 2 3 and 4).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-09 |  | 11 61 43-3 Areana Curtains - Samples & Product Data (Packages 1 2 3 and 4)_POP.pdf
11 61 43-009-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-009-00 Package 1 - Arena Blackout | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-19 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-02 | 2021-02-05 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-02-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10769 | Received | For Review | 2021-01-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-02-02 | Submittal Number: 11 61 43-9.0 From: DOMINGO SAMPAYO Final Due Date: 01/22/21 Subject: PACKAGE 1 - ARENA BLACKOUT Description: PACKAGE 1 - ARENA BLACKOUT INCLUDES: EVENT LEVEL MAIN CONCOURSE SUITE LEVEL NORTH SIDE & MOUNT BAKER CLUB UPPER CONCOURSE SPACE NEEDLE CLUB BRIDGE LEVEL ***PRODUCT DATA & SHOP DRAWINGS INCLUDED ON THIS SUBMITTAL*** Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14005 | Forwarded | For Review | 2021-01-19 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-26 | Submittal Number: 11 61 43-9.0 From: DOMINGO SAMPAYO Final Due Date: 01/22/21 Subject: PACKAGE 1 - ARENA BLACKOUT Description: PACKAGE 1 - ARENA BLACKOUT INCLUDES: EVENT LEVEL MAIN CONCOURSE SUITE LEVEL NORTH SIDE & MOUNT BAKER CLUB UPPER CONCOURSE SPACE NEEDLE CLUB BRIDGE LEVEL ***PRODUCT DATA & SHOP DRAWINGS INCLUDED ON THIS SUBMITTAL*** Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 11230 | Review Response | Revise and Resubmit | 2021-02-05 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14536 | Responded and Closed | Revise and Resubmit | 2021-02-05 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-15 |  | 11 61 43-9 Package 1 - Arena Blackout.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-15 |  | 11 61 43-9 Package 1 - Arena Blackout.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-02-05 |  | 11 61 43-9 Package 1 - Arena Blackout_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-01-15 |  | 11 61 43-9 Package 1 - Arena Blackout.pdf
11 61 43-009-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-009-01 Package 1 - Arena Blackout | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-20 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12392 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 11 61 43-9.1 From: DOMINGO SAMPAYO Final Due Date: 04/12/21 Subject: PACKAGE 1 - ARENA BLACKOUT Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 16051 | Forwarded | For Review | 2021-04-05 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-12 | Submittal Number: 11 61 43-9.1 From: DOMINGO SAMPAYO Final Due Date: 04/12/21 Subject: PACKAGE 1 - ARENA BLACKOUT Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 12656 | Review Response | Revise and Resubmit | 2021-04-20 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16376 | Responded and Closed | Revise and Resubmit | 2021-04-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 11 61 43-009-1 Package 1 - Arena Blackout.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 11 61 43-009-1 Package 1 - Arena Blackout.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-20 |  | 11 61 43-009-1 Package 1 - Arena Blackout_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 11 61 43-009-1 Package 1 - Arena Blackout.pdf
11 61 43-009-02 | 11 61 43 - ARENA CURTAINS | 11 61 43-009-02 Package 1 - Arena Blackout | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-14 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-28 | 2021-06-28 | 15 |  | Record Copies; Transfers; Submittals | 11 61 43-009-02-01 - 11 61 43-009-02 Package 1 - Arena Blackout | 15 |  | 2021-06-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13512 | Received | For Review | 2021-06-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-06-28 | Submittal Number: 11 61 43-9.2 From: DOMINGO SAMPAYO Final Due Date: 06/14/21 Subject: PACKAGE 1 - ARENA BLACKOUT Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 17476 | Forwarded | For Review | 2021-06-14 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-21 | Submittal Number: 11 61 43-9.2 From: DOMINGO SAMPAYO Final Due Date: 06/14/21 Subject: PACKAGE 1 - ARENA BLACKOUT Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 13683 | Review Response | Approved as Noted/Resubmit | 2021-06-28 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17719 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-28 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-11 |  | 11 61 43-9 R2 Package 1 - Arena Blackout.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-11 |  | 11 61 43-9 R2 Package 1 - Arena Blackout.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-28 |  | 11 61 43-9 R2 Package 1 - Arena Blackout_FULL FILE_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-06-11 |  | 11 61 43-9 R2 Package 1 - Arena Blackout.pdf
11 61 43-009-02-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-009-02 Package 1 - Arena Blackout | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 61 43-009-02 - 11 61 43-009-02 Package 1 - Arena Blackout | -1 | 2021-07-12
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-11 |  | 11 61 43-9 R2 Package 1 - Arena Blackout.pdf
11 61 43-009-03 | 11 61 43 - ARENA CURTAINS | 11 61 43-009-03 Package 1 - Arena Blackout - FOR CITY SUBMISSION | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-16 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-30 | 2021-07-19 | 4 |  | Record Copies; Transfers; Submittals | 11 61 43-009-03-01 - 11 61 43-009-03 Package 1 - Arena Blackout - FOR CITY SUBMISSION | 4 |  | 2021-07-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13979 | Received | For Review | 2021-07-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-30 | Submittal Number: 11 61 43-9.3 From: JES PELKEY Final Due Date: 07/30/21 Subject: PACKAGE 1 - ARENA BLACKOUT - FOR CITY SUBMISSION Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 18081 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-23 | Submittal Number: 11 61 43-9.3 From: JES PELKEY Final Due Date: 07/30/21 Subject: PACKAGE 1 - ARENA BLACKOUT - FOR CITY SUBMISSION Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14008 | Review Response | Approved as Noted/Resubmit | 2021-07-19 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18121 | Responded and Closed | Approved as Noted/Resubmit | 2021-07-19 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-16 |  | 11 61 43-9.3 - Package 1 - Arena Blackout - FOR CITY SUBMISSION.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | 11 61 43-9.3 - Package 1 - Arena Blackout - FOR CITY SUBMISSION.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-07-19 |  | SCA - Curtains - Package 1 Submital v5_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-07-16 |  | 11 61 43-9.3 - Package 1 - Arena Blackout - FOR CITY SUBMISSION.pdf
11 61 43-009-03-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-009-03 Package 1 - Arena Blackout - FOR CITY SUBMISSION | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 61 43-009-03 - 11 61 43-009-03 Package 1 - Arena Blackout - FOR CITY SUBMISSION | -1 | 2021-08-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-16 |  | 11 61 43-9.3 - Package 1 - Arena Blackout - FOR CITY SUBMISSION.pdf
11 61 43-009-04 | 11 61 43 - ARENA CURTAINS | 11 61 43-009-04 Package 1 - Arena Blackout - FOR CITY SUBMISSION | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-09 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-23 | 2021-08-12 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-08-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14260 | Received | For Review | 2021-08-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-08-23 | Submittal Number: 11 61 43-9.4 From: JES PELKEY Final Due Date: 08/20/21 Subject: PACKAGE 1 - ARENA BLACKOUT - FOR CITY SUBMISSION Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 18422 | Forwarded | For Review | 2021-08-09 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-16 | Submittal Number: 11 61 43-9.4 From: JES PELKEY Final Due Date: 08/20/21 Subject: PACKAGE 1 - ARENA BLACKOUT - FOR CITY SUBMISSION Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14345 | Review Response | Approved | 2021-08-12 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18516 | Responded and Closed | Approved | 2021-08-12 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-06 |  | 11 61 43-9.4 - Package 1 - Arena Blackout - FOR CITY SUBMISSION.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-06 |  | 11 61 43-9.4 - Package 1 - Arena Blackout - FOR CITY SUBMISSION.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-08-12 |  | 11 61 43-9.4 - Package 1 - Arena Blackout - FOR CITY SUBMISSION_revised_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-08-06 |  | 11 61 43-9.4 - Package 1 - Arena Blackout - FOR CITY SUBMISSION.pdf
11 61 43-009-05 | 11 61 43 - ARENA CURTAINS | 11 61 43-009-05 Package 1 - Arena Blackout - FOR CITY RESUBMISSION | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-29 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2021-10-13 | 2021-09-29 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14749 | Received | For Review | 2021-09-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-10-13 | Submittal Number: 11 61 43-9.5 From: JES PELKEY Final Due Date: 09/28/21 Subject: PACKAGE 1 - ARENA BLACKOUT - FOR CITY RESUBMISSION Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 19016 | Forwarded | For Review | 2021-09-29 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-10-06 | Submittal Number: 11 61 43-9.5 From: JES PELKEY Final Due Date: 09/28/21 Subject: PACKAGE 1 - ARENA BLACKOUT - FOR CITY RESUBMISSION Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 19017 | Forwarded | For Review | 2021-09-29 | Kelsea Conkright (Populous) | Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) |  | Submittal Number: 11 61 43-9.5 From: JES PELKEY Final Due Date: 09/28/21 Subject: PACKAGE 1 - ARENA BLACKOUT - FOR CITY RESUBMISSION Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14756 | Review Response | Approved as Noted | 2021-09-29 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See comments in attached submittal. No resubmit required. | Info Exchange
| 14757 | Review Response | Approved as Noted | 2021-09-29 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 19025 | Responded and Closed | Approved as Noted | 2021-09-29 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments in attached submittal. No resubmit required. Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-28 |  | 11 61 43-9.5 - Package 1 - Arena Blackout - FOR CITY RESUBMISSION Final.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-28 |  | 11 61 43-9.5 - Package 1 - Arena Blackout - FOR CITY RESUBMISSION Final.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-09-28 |  | 11 61 43-9.5 - Package 1 - Arena Blackout - FOR CITY RESUBMISSION Final.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-09-28 |  | 11 61 43-9.5 - Package 1 - Arena Blackout - FOR CITY RESUBMISSION Final.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-09-29 |  | 11 61 43-9.5 - Package 1 - Arena Blackout - FOR CITY RESUBMISSION Final_TT_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-09-28 |  | 11 61 43-9.5 - Package 1 - Arena Blackout - FOR CITY RESUBMISSION Final.pdf
11 61 43-012-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-012-00 Package 6 - Space Needle Club Decorative Curtain | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-27 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-11 | 2021-05-09 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-05-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12807 | Received | For Review | 2021-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-11 | Submittal Number: 11 61 43-12.0 From: DOMINGO SAMPAYO Final Due Date: 07/05/21 Subject: PACKAGE 6 - SPACE NEEDLE CLUB DECORATIVE CURTAIN Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 16554 | Forwarded | For Review | 2021-04-27 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-04 | Submittal Number: 11 61 43-12.0 From: DOMINGO SAMPAYO Final Due Date: 07/05/21 Subject: PACKAGE 6 - SPACE NEEDLE CLUB DECORATIVE CURTAIN Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 12985 | Review Response | Revise and Resubmit | 2021-05-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16809 | Responded and Closed | Revise and Resubmit | 2021-05-09 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-27 |  | 11 61 43-12 Package 6 - Space Needle Club Decorative Curtain.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-27 |  | 11 61 43-12 Package 6 - Space Needle Club Decorative Curtain.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-09 |  | 11 61 43-12 Package 6 - Space Needle Club Decorative Curtain_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-27 |  | 11 61 43-12 Package 6 - Space Needle Club Decorative Curtain.pdf
11 61 43-012-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-012-01 Package 6 - Space Needle Club Decorative Curtain | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-25 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-12 07:00 | 2021-07-15 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13654 | Received | For Review | 2021-06-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-12 07:00 | Submittal Number: 11 61 43-12.1 From: DOMINGO SAMPAYO Final Due Date: 06/23/21 Subject: PACKAGE 6 - SPACE NEEDLE CLUB DECORATIVE CURTAIN Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 17679 | Forwarded | For Review | 2021-06-25 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-02 | Submittal Number: 11 61 43-12.1 From: DOMINGO SAMPAYO Final Due Date: 06/23/21 Subject: PACKAGE 6 - SPACE NEEDLE CLUB DECORATIVE CURTAIN Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 17778 | Forwarded | For Review | 2021-06-30 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-07 | Submittal Number: 11 61 43-12.1 From: DOMINGO SAMPAYO Final Due Date: 06/23/21 Subject: PACKAGE 6 - SPACE NEEDLE CLUB DECORATIVE CURTAIN Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 13945 | Review Response | Approved as Noted | 2021-07-15 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18050 | Responded and Closed | Approved as Noted | 2021-07-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-25 |  | SCA - Curtains - Package 6 Submittal v2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-25 |  | SCA - Curtains - Package 6 Submittal v2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-25 |  | SCA - Curtains - Package 6 Submittal v2.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-15 |  | 11 61 43-12.1 Space Needle Curtain SD-MAM_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-25 |  | SCA - Curtains - Package 6 Submittal v2.pdf
11 61 43-013-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-013-00 Smartstage Curtain Performance Specifications | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Not Required For Review |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Kelsea Conkright (Populous), Geoff Cheong, Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2021-01-27 08:00 | 2021-01-21 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-01-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10632 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2021-01-27 08:00 | Submittal Number: 11 61 43-13.0 From: DOMINGO SAMPAYO Final Due Date: 01/27/21 Subject: SMARTSTAGE CURTAIN PERFORMANCE SPECIFICATIONS Description: ALL THE SIX (6) PACKAGES SPECIFICATIONS TO BE INCLUDED IN THIS SUBMITTAL. Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 13840 | Forwarded | For Review | 2021-01-12 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2021-01-19 | Submittal Number: 11 61 43-13.0 From: DOMINGO SAMPAYO Final Due Date: 01/27/21 Subject: SMARTSTAGE CURTAIN PERFORMANCE SPECIFICATIONS Description: ALL THE SIX (6) PACKAGES SPECIFICATIONS TO BE INCLUDED IN THIS SUBMITTAL. Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 10805 | Review Response | Not Required For Review | 2021-01-12 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  | This is outside the foodservice scope. Please forward to the appropriate party. | Info Exchange
| 14054 | Forwarded | For Review | 2021-01-20 | Josh Dobken (Populous) | Kelsea Conkright (Populous); Geoff Cheong; Tom Usher (Populous); Chris Minter (Populous) | 2021-01-27 | Submittal Number: 11 61 43-13.0 From: DOMINGO SAMPAYO Final Due Date: 01/27/21 Subject: SMARTSTAGE CURTAIN PERFORMANCE SPECIFICATIONS Description: ALL THE SIX (6) PACKAGES SPECIFICATIONS TO BE INCLUDED IN THIS SUBMITTAL. Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 10881 | Review Response | Not Required For Review | 2021-01-21 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Specifications not required for Review by design team. | Info Exchange
| 14121 | Responded and Closed | Not Required For Review | 2021-01-21 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Not Required For Review) from: Kelsea Conkright (Populous) Remarks: Specifications not required for Review by design team. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 11 61 43-13.0 Smartstage Curtain Performance Specifications (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 11 61 43-13.0 Smartstage Curtain Performance Specifications (MAM Review).pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-01-11 02:00 |  | 11 61 43-13.0 Smartstage Curtain Performance Specifications (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-11 02:00 |  | 11 61 43-13.0 Smartstage Curtain Performance Specifications (MAM Review).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-21 |  | 11 61 43-13.0 Smartstage Curtain Performance Specifications (MAM Review)_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-01-12 |  | 11 61 43-13.0 Smartstage Curtain Performance Specifications (MAM Review).pdf
11 61 43-013-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-013-01 Smartstage Curtain Performance Specifications | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-10 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-24 | 2021-05-18 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12992 | Received | For Review | 2021-05-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-24 | Submittal Number: 11 61 43-13.1 From: DOMINGO SAMPAYO Final Due Date: 05/21/21 Subject: SMARTSTAGE CURTAIN PERFORMANCE SPECIFICATIONS Description: ALL THE SIX (6) PACKAGES SPECIFICATIONS TO BE INCLUDED IN THIS SUBMITTAL. Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 16815 | Forwarded | For Review | 2021-05-10 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-17 | Submittal Number: 11 61 43-13.1 From: DOMINGO SAMPAYO Final Due Date: 05/21/21 Subject: SMARTSTAGE CURTAIN PERFORMANCE SPECIFICATIONS Description: ALL THE SIX (6) PACKAGES SPECIFICATIONS TO BE INCLUDED IN THIS SUBMITTAL. Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 17029 | Responded and Closed | Approved | 2021-05-18 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 11 61 43-13 R1 Smartstage Curtain Performance Specifications.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-10 |  | 11 61 43-13 R1 Smartstage Curtain Performance Specifications.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-18 |  | 11 61 43-13 R1 Smartstage Curtain Performance Specifications-POP.pdf
11 61 43-014-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-014-00: Package 2 - North Acoustic Curtains (PLATES ONLY) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-18 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Chris Minter (Populous) |  |  |  | 2021-03-04 | 2021-03-01 | 12 |  | Record Copies; Transfers; Submittals | 11 61 43-014-00-01 - 11 61 43-014-00: Package 2 - North Acoustic Curtains (PLATES ONLY) | 11 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11533 | Received | For Review | 2021-02-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-04 | Submittal Number: 11 61 43-14.0 From: DOMINGO SAMPAYO Final Due Date: 03/22/21 Subject: PACKAGE 2 - NORTH ACOUSTIC CURTAINS (PLATES ONLY) Description: ***NEED PRODUCT DATA AND LOAD INFORMATION*** Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14948 | Forwarded | For Review | 2021-02-19 | Populous SCA_CCA | Kelsea Conkright (Populous); Chris Minter (Populous) | 2021-02-26 | Submittal Number: 11 61 43-14.0 From: DOMINGO SAMPAYO Final Due Date: 03/22/21 Subject: PACKAGE 2 - NORTH ACOUSTIC CURTAINS (PLATES ONLY) Description: ***NEED PRODUCT DATA AND LOAD INFORMATION*** Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 15164 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-01 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-18 02:00 |  | 11 61 43-14 Pkg2 - N Acoustic Curtains (PLATES).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-18 02:00 |  | 11 61 43-14 Pkg2 - N Acoustic Curtains (PLATES).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-01 |  | 11 61 43-14 Pkg2 - N Acoustic Curtains (PLATES)_POP.pdf
11 61 43-014-00-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-014-00: Package 2 - North Acoustic Curtains (PLATES ONLY) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 61 43-014-00 - 11 61 43-014-00: Package 2 - North Acoustic Curtains (PLATES ONLY) | -1 | 2021-03-15
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-01 |  | 11 61 43-14 Pkg2 - N Acoustic Curtains (PLATES)_POP.pdf
11 61 43-015-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-015-00 Arena Curtains - Samples & Product Data (Package 5 - North Wall Motorized Blackout Roller Shades & Package 6 - Space Needle Decorative Curtains) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-08 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-22 | 2021-03-15 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11842 | Received | For Review | 2021-03-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-03-22 | Submittal Number: 11 61 43-15.0 From: DOMINGO SAMPAYO Final Due Date: 04/08/21 Subject: ARENA CURTAINS - SAMPLES & PRODUCT DATA (PACKAGE 5 - NORTH WALL MOTORIZED BLACKOUT ROLLER SHADES & PACKAGE 6 - SPACE NEEDLE DECORATIVE CURTAINS) Description: SAMPLES SUBMITTED: PACKAGE 5 - NORTH WALL MOTORIZED BLACKOUT ROLLER SHADES - SAMPLE 3,4 & 5 ARE THE SAME, DUPLICATES – CURTAINS PACKAGE 6 - SPACE NEEDLE DECORATIVE CURTAINS - SAMPLE 1 & 2 ARE THE SAME, DUPLICATES – CURTAINS – NOTE: SMARTSTAGE IS ALSO LOOKING FOR ALTERNATIVE, NOT 100% SATISFIED WITH THE BACKING. WEBBING FOR ALL DRAPES: SAMPLE 6 – PACKAGE 1,2,3,4 & 6. Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 15352 | Forwarded | For Review | 2021-03-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-15 | Submittal Number: 11 61 43-15.0 From: DOMINGO SAMPAYO Final Due Date: 04/08/21 Subject: ARENA CURTAINS - SAMPLES & PRODUCT DATA (PACKAGE 5 - NORTH WALL MOTORIZED BLACKOUT ROLLER SHADES & PACKAGE 6 - SPACE NEEDLE DECORATIVE CURTAINS) Description: SAMPLES SUBMITTED: PACKAGE 5 - NORTH WALL MOTORIZED BLACKOUT ROLLER SHADES - SAMPLE 3,4 & 5 ARE THE SAME, DUPLICATES – CURTAINS PACKAGE 6 - SPACE NEEDLE DECORATIVE CURTAINS - SAMPLE 1 & 2 ARE THE SAME, DUPLICATES – CURTAINS – NOTE: SMARTSTAGE IS ALSO LOOKING FOR ALTERNATIVE, NOT 100% SATISFIED WITH THE BACKING. WEBBING FOR ALL DRAPES: SAMPLE 6 – PACKAGE 1,2,3,4 & 6. Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 12025 | Review Response | Approved as Noted/Resubmit | 2021-03-15 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15565 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-15 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-08 |  | 11 61 43-15 Arena Curtains - Samples & Product Data (Package 5 - North Wall Motorized Blackout Roller Shades & Package 6 - Space Needle Decorative Curtains).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-08 |  | 11 61 43-15 Arena Curtains - Samples & Product Data (Package 5 - North Wall Motorized Blackout Roller Shades & Package 6 - Space Needle Decorative Curtains).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-15 |  | 11 61 43-15 Arena Curtains - Samples & Product Data (Package 5 & Package 6)_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-03-08 |  | 11 61 43-15 Arena Curtains - Samples & Product Data (Package 5 - North Wall Motorized Blackout Roller Shades & Package 6 - Space Needle Decorative Curtains).pdf
11 61 43-015-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-015-01 Arena Curtains - Samples & Product Data (Package 5 - North Wall Motorized Blackout Roller Shades & Package 6 - Space Needle Decorative Curtains) | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-13 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12393 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 11 61 43-15.1 From: DOMINGO SAMPAYO Final Due Date: 04/16/21 Subject: ARENA CURTAINS - SAMPLES & PRODUCT DATA (PACKAGE 5 - NORTH WALL MOTORIZED BLACKOUT ROLLER SHADES & PACKAGE 6 - SPACE NEEDLE DECORATIVE CURTAINS) Description: SAMPLES: PACKAGE 5 - NORTH WALL MOTORIZED BLACKOUT ROLLER SHADES - SAMPLE 3,4 & 5 ARE THE SAME, DUPLICATES – CURTAINS - BEING SUBMITTED ON THIS REVISION 1 PACKAGE 6 - SPACE NEEDLE DECORATIVE CURTAINS - SAMPLE 1 & 2 ARE THE SAME, DUPLICATES – CURTAINS – NOTE: SMARTSTAGE IS ALSO LOOKING FOR ALTERNATIVE, NOT 100% SATISFIED WITH THE BACKING. - APPROVED AS NOTED ON ORIGINAL SUBMITTAL (SEE ATTACHED) WEBBING FOR ALL DRAPES: SAMPLE 6 – PACKAGE 1,2,3,4 & 6. - APPROVED AS NOTED ON ORIGINAL SUBMITTAL (SEE ATTACHED) ***ROCKWELL TO APPROVED ALL THE SAMPLES*** Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 16052 | Forwarded | For Review | 2021-04-05 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-12 | Submittal Number: 11 61 43-15.1 From: DOMINGO SAMPAYO Final Due Date: 04/16/21 Subject: ARENA CURTAINS - SAMPLES & PRODUCT DATA (PACKAGE 5 - NORTH WALL MOTORIZED BLACKOUT ROLLER SHADES & PACKAGE 6 - SPACE NEEDLE DECORATIVE CURTAINS) Description: SAMPLES: PACKAGE 5 - NORTH WALL MOTORIZED BLACKOUT ROLLER SHADES - SAMPLE 3,4 & 5 ARE THE SAME, DUPLICATES – CURTAINS - BEING SUBMITTED ON THIS REVISION 1 PACKAGE 6 - SPACE NEEDLE DECORATIVE CURTAINS - SAMPLE 1 & 2 ARE THE SAME, DUPLICATES – CURTAINS – NOTE: SMARTSTAGE IS ALSO LOOKING FOR ALTERNATIVE, NOT 100% SATISFIED WITH THE BACKING. - APPROVED AS NOTED ON ORIGINAL SUBMITTAL (SEE ATTACHED) WEBBING FOR ALL DRAPES: SAMPLE 6 – PACKAGE 1,2,3,4 & 6. - APPROVED AS NOTED ON ORIGINAL SUBMITTAL (SEE ATTACHED) ***ROCKWELL TO APPROVED ALL THE SAMPLES*** Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 12565 | Review Response | Approved | 2021-04-13 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16273 | Responded and Closed | Approved | 2021-04-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 11 61 43-15-1 Arena Curtains - Samples & Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 11 61 43-15-1 Arena Curtains - Samples & Product Data.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-13 |  | 11 61 43-15-1 Arena Curtains - Samples & Product Data_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 11 61 43-15-1 Arena Curtains - Samples & Product Data.pdf
11 61 43-016-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-016-00 ARENA CURTAINS - Control Panel Locations - Shop Drawings FOR RECORD | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-05-18 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13153 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-06-02 07:00 | Submittal Number: 11 61 43-16.0 From: KIM DOWALIBY Final Due Date: 06/01/21 Subject: ARENA CURTAINS - CONTROL PANEL LOCATIONS - SHOP DRAWINGS FOR RECORD Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 17018 | Forwarded | For Review | 2021-05-18 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-25 | Submittal Number: 11 61 43-16.0 From: KIM DOWALIBY Final Due Date: 06/01/21 Subject: ARENA CURTAINS - CONTROL PANEL LOCATIONS - SHOP DRAWINGS FOR RECORD Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 17031 | Responded and Closed | Approved | 2021-05-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-18 |  | 11 61 43-16 - ARENA CURTAINS - Control Panel Locations - Shop Drawings FOR RECORD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-18 |  | 11 61 43-16 - ARENA CURTAINS - Control Panel Locations - Shop Drawings FOR RECORD.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-05-18 |  | 11 61 43-16 - ARENA CURTAINS - Control Panel Locations - Shop Drawings FOR RECORD-POP.pdf
11 61 43-017-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-017-00 Clerestory Curtains - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-30 | Responded and Closed - Rejected |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Mark Lievens (ME Engineers) |  |  |  | 2021-08-13 | 2021-08-10 | 12 |  | Record Copies; Transfers; Submittals | 11 61 43-017-00-01 - 11 61 43-017-00 Clerestory Curtains - Shop Drawings | 13 |  | 2021-08-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14166 | Received | For Review | 2021-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-08-13 | Submittal Number: 11 61 43-17.0 From: KIM DOWALIBY Final Due Date: 08/12/21 Subject: CLERESTORY CURTAINS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 18313 | Forwarded | For Review | 2021-07-29 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-05 | Submittal Number: 11 61 43-17.0 From: KIM DOWALIBY Final Due Date: 08/12/21 Subject: CLERESTORY CURTAINS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 18335 | Forwarded | For Review | 2021-08-02 | Kuebler Perry (Populous) | Mark Lievens (ME Engineers) |  | Submittal Number: 11 61 43-17.0 From: KIM DOWALIBY Final Due Date: 08/12/21 Subject: CLERESTORY CURTAINS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14296 | Review Response | Rejected | 2021-08-10 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Per coordination with Mortenson on 8/3, revised shop drawings to be sent to Design Team. | Info Exchange
| 18461 | Responded and Closed | Rejected | 2021-08-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Kelsea Conkright (Populous) Remarks: Per coordination with Mortenson on 8/3, revised shop drawings to be sent to Design Team. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-29 |  | 11 61 43-17 - Clerestory Curtains - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-29 |  | 11 61 43-17 - Clerestory Curtains - Shop Drawings.pdf
| Forwarded |  | Kuebler Perry (Populous) | 1 | 2021-07-29 |  | 11 61 43-17 - Clerestory Curtains - Shop Drawings.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-07-29 |  | 11 61 43-17 - Clerestory Curtains - Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-29 |  | 11 61 43-17 - Clerestory Curtains - Shop Drawings.pdf
11 61 43-017-00-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-017-00 Clerestory Curtains - Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 61 43-017-00 - 11 61 43-017-00 Clerestory Curtains - Shop Drawings | -1 | 2021-08-24
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-29 |  | 11 61 43-17 - Clerestory Curtains - Shop Drawings.pdf
11 61 43-017-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-017-01 Clerestory Curtains - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-12 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-26 | 2021-08-18 | 7 |  | Record Copies; Transfers; Submittals | 11 61 43-017-01-01 - 11 61 43-017-01 Clerestory Curtains - Shop Drawings | 7 |  | 2021-08-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14335 | Received | For Review | 2021-08-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-08-26 | Submittal Number: 11 61 43-17.1 From: KIM DOWALIBY Final Due Date: 08/25/21 Subject: CLERESTORY CURTAINS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 18504 | Forwarded | For Review | 2021-08-12 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-19 | Submittal Number: 11 61 43-17.1 From: KIM DOWALIBY Final Due Date: 08/25/21 Subject: CLERESTORY CURTAINS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14397 | Review Response | Approved as Noted/Resubmit | 2021-08-18 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18579 | Responded and Closed | Approved as Noted/Resubmit | 2021-08-18 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-11 |  | 11 61 43-17.1 Clerestory Curtains SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-11 |  | 11 61 43-17.1 Clerestory Curtains SD-MAM.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-08-18 |  | 11 61 43-17.1 Clerestory Curtains SD-MAM_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-08-11 |  | 11 61 43-17.1 Clerestory Curtains SD-MAM.pdf
11 61 43-017-01-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-017-01 Clerestory Curtains - Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 61 43-017-01 - 11 61 43-017-01 Clerestory Curtains - Shop Drawings | -1 | 2021-09-01
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-11 |  | 11 61 43-17.1 Clerestory Curtains SD-MAM.pdf
11 61 43-017-03 | 11 61 43 - ARENA CURTAINS | 11 61 43-017-03 Clerestory Curtains - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-13 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2021-09-27 | 2021-09-17 | 5 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-09-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14623 | Received | For Review | 2021-09-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-09-27 | Submittal Number: 11 61 43-17.3 From: KIM DOWALIBY Final Due Date: 09/24/21 Subject: CLERESTORY CURTAINS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 18862 | Forwarded | For Review | 2021-09-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-20 | Submittal Number: 11 61 43-17.3 From: KIM DOWALIBY Final Due Date: 09/24/21 Subject: CLERESTORY CURTAINS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14651 | Review Response | Approved as Noted | 2021-09-14 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18890 | Forwarded | For Review | 2021-09-14 | Kelsea Conkright (Populous) | Matt Ross (Thornton Tomasetti) |  | Submittal Number: 11 61 43-17.3 From: KIM DOWALIBY Final Due Date: 09/24/21 Subject: CLERESTORY CURTAINS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 18898 | Forwarded | For Review | 2021-09-15 | Kelsea Conkright (Populous) | Franz Kogler (Thornton Tomasetti) |  | Submittal Number: 11 61 43-17.3 From: KIM DOWALIBY Final Due Date: 09/24/21 Subject: CLERESTORY CURTAINS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14666 | Review Response | Approved as Noted | 2021-09-17 | Franz Kogler (Thornton Tomasetti) | Kelsea Conkright (Populous) |  | See attached submittal for review comments. | Info Exchange
| 18912 | Responded and Closed | Approved as Noted | 2021-09-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-10 |  | 11 61 43-17.3 Clerestory Curtains SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-10 |  | 11 61 43-17.3 Clerestory Curtains SD-MAM.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-09-14 |  | 11 61 43-17.3 Clerestory Curtains SD-MAM.pdf_POP.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-09-10 |  | 11 61 43-17.3 Clerestory Curtains SD-MAM.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-09-10 |  | 11 61 43-17.3 Clerestory Curtains SD-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-09-10 |  | 11 61 43-17.3 Clerestory Curtains SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-10 |  | 11 61 43-17.3 Clerestory Curtains SD-MAM.pdf
11 61 43-018-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-018-00 Ticket Office Manual Window Shades | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-25 | Responded and Closed - Not Required For Review |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-09 | 2021-06-30 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-06-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13655 | Received | For Review | 2021-06-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-09 | Submittal Number: 11 61 43-18.0 From: DOMINGO SAMPAYO Final Due Date: 07/14/21 Subject: TICKET OFFICE MANUAL WINDOW SHADES Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 17680 | Forwarded | For Review | 2021-06-25 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-02 | Submittal Number: 11 61 43-18.0 From: DOMINGO SAMPAYO Final Due Date: 07/14/21 Subject: TICKET OFFICE MANUAL WINDOW SHADES Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 17779 | Responded and Closed | Not Required For Review | 2021-06-30 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please note that submittal #11 61 43-18.0 is void. This submittal was pushed through in Procore into Populous’s court without Mortenson’s review or stamp. It also was submitted under the wrong spec section. The ticket office roller window shade has since been marked up by Mortenson, stamped, and submitted under submittal #12 21 24-11.0. Please make sure that this is the submittal that the design team reviews. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-25 |  | Submittals - SCA -Ticket Office v1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-25 |  | Submittals - SCA -Ticket Office v1.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-30 |  | FW_ Submittal 11 61 43-18_0 - VOID.msg
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-25 |  | Submittals - SCA -Ticket Office v1.pdf
11 61 43-019-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-019-00 Metropolitan Curtains - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-01 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-16 07:00 | 2021-07-08 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13751 | Received | For Review | 2021-07-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-16 07:00 | Submittal Number: 11 61 43-19.0 From: JES PELKEY Final Due Date: 07/15/21 Subject: METROPOLITAN CURTAINS - SAMPLE Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 17800 | Forwarded | For Review | 2021-07-01 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-08 | Submittal Number: 11 61 43-19.0 From: JES PELKEY Final Due Date: 07/15/21 Subject: METROPOLITAN CURTAINS - SAMPLE Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 17931 | Responded and Closed | Approved | 2021-07-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Kim Dowaliby |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-01 |  | 11 61 43-19.0 Metro Club Curtain Sample-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-01 |  | 11 61 43-19.0 Metro Club Curtain Sample-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-07-08 02:00 |  | 11 61 43-19.0 Metro Club Curtain Sample-MAM_pop.pdf
11 61 43-020-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-020-00 Metro Club Curtain Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-01 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-16 07:00 | 2021-07-13 | 13 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13745 | Received | For Review | 2021-07-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-16 07:00 | Submittal Number: 11 61 43-20.0 From: JES PELKEY Final Due Date: 07/13/21 Subject: METRO CLUB CURTAIN SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 17791 | Forwarded | For Review | 2021-06-30 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-07 | Submittal Number: 11 61 43-20.0 From: JES PELKEY Final Due Date: 07/13/21 Subject: METRO CLUB CURTAIN SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 13906 | Review Response | Revise and Resubmit | 2021-07-13 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18007 | Responded and Closed | Revise and Resubmit | 2021-07-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-30 |  | 11 61 43-20.0 Metro Club Curtain SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-30 |  | 11 61 43-20.0 Metro Club Curtain SD-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-13 |  | 11 61 43-20.0 Metro Club Curtain SD-MAM_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-30 |  | 11 61 43-20.0 Metro Club Curtain SD-MAM.pdf
11 61 43-020-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-020-01 Metro Club Curtain Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-31 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Kuebler Perry (Populous), Chris Minter (Populous) |  |  |  | 2021-09-14 | 2021-09-14 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14548 | Received | For Review | 2021-08-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction) | 2021-09-14 | Submittal Number: 11 61 43-20.1 From: JES PELKEY Final Due Date: 09/13/21 Subject: METRO CLUB CURTAIN SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 18758 | Forwarded | For Review | 2021-09-01 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Kuebler Perry (Populous); Chris Minter (Populous) | 2021-09-08 | Submittal Number: 11 61 43-20.1 From: JES PELKEY Final Due Date: 09/13/21 Subject: METRO CLUB CURTAIN SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14650 | Review Response | Approved as Noted | 2021-09-14 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18889 | Responded and Closed | Approved as Noted | 2021-09-14 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| 19032 | Sent | For Information Only | 2021-09-30 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: Kim, Please see attached for the submittal previously returned on 9/14. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-30 02:00 |  | 11 61 43-20.1 Metro Club Curtain Shop Drawings & PD.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-30 02:00 |  | 11 61 43-20.1 Metro Club Curtain Shop Drawings & PD.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-09-14 |  | 11 61 43-20.1 Metro Club Curtain Shop Drawings & PD.pdf_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-08-30 |  | 11 61 43-20.1 Metro Club Curtain Shop Drawings & PD.pdf
| Sent |  | Kelsea Conkright (Populous) | 1 | 2021-08-30 |  | 11 61 43-20.1 Metro Club Curtain Shop Drawings & PD.pdf
11 61 43-021-00 | 11 61 43 - ARENA CURTAINS | 11 61 43-021-00 Clerestory Curtain Valence Truss - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-13 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2021-09-27 | 2021-09-20 | 8 |  | Record Copies; Transfers; Submittals | 11 61 43-021-00-01 - 11 61 43-021-00 Clerestory Curtain Valence Truss - Shop Drawings | 10 |  | 2021-09-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14624 | Received | For Review | 2021-09-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-09-27 | Submittal Number: 11 61 43-21.0 From: KIM DOWALIBY Final Due Date: 09/24/21 Subject: CLERESTORY CURTAIN VALENCE TRUSS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 18863 | Forwarded | For Review | 2021-09-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-20 | Submittal Number: 11 61 43-21.0 From: KIM DOWALIBY Final Due Date: 09/24/21 Subject: CLERESTORY CURTAIN VALENCE TRUSS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 18902 | Forwarded | For Review | 2021-09-16 | Kuebler Perry (Populous) | Matt Ross (Thornton Tomasetti) |  | Submittal Number: 11 61 43-21.0 From: KIM DOWALIBY Final Due Date: 09/24/21 Subject: CLERESTORY CURTAIN VALENCE TRUSS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 18913 | Forwarded | For Review | 2021-09-17 | Kelsea Conkright (Populous) | Franz Kogler (Thornton Tomasetti) |  | Submittal Number: 11 61 43-21.0 From: KIM DOWALIBY Final Due Date: 09/24/21 Subject: CLERESTORY CURTAIN VALENCE TRUSS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14668 | Review Response | Approved as Noted/Resubmit | 2021-09-17 | Franz Kogler (Thornton Tomasetti) | Kelsea Conkright (Populous) |  | See comments in attached submittal. | Info Exchange
| 14672 | Review Response | Approved as Noted/Resubmit | 2021-09-20 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18922 | Responded and Closed | Approved as Noted/Resubmit | 2021-09-20 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments in attached submittal. Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-10 |  | 11 61 43-21 - Clerestory Curtain Valence Truss - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-10 |  | 11 61 43-21 - Clerestory Curtain Valence Truss - Shop Drawings.pdf
| Forwarded |  | Kuebler Perry (Populous) | 1 | 2021-09-10 |  | 11 61 43-21 - Clerestory Curtain Valence Truss - Shop Drawings.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-09-10 |  | 11 61 43-21 - Clerestory Curtain Valence Truss - Shop Drawings.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-09-10 |  | 11 61 43-21 - Clerestory Curtain Valence Truss - Shop Drawings.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-09-20 |  | 11 61 43-21 - Clerestory Curtain Valence Truss - Shop Drawings_TTReview_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-09-10 |  | 11 61 43-21 - Clerestory Curtain Valence Truss - Shop Drawings.pdf
11 61 43-021-00-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-021-00 Clerestory Curtain Valence Truss - Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 61 43-021-00 - 11 61 43-021-00 Clerestory Curtain Valence Truss - Shop Drawings | -1 | 2021-10-04
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-10 |  | 11 61 43-21 - Clerestory Curtain Valence Truss - Shop Drawings.pdf
11 61 43-021-01 | 11 61 43 - ARENA CURTAINS | 11 61 43-021-01 Clerestory Curtain Valence Truss - Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-29 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-10-13 | 2021-09-29 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14745 | Received | For Review | 2021-09-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-10-13 | Submittal Number: 11 61 43-21.1 From: KIM DOWALIBY Final Due Date: 10/12/21 Subject: CLERESTORY CURTAIN VALENCE TRUSS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 19013 | Forwarded | For Review | 2021-09-28 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-10-05 | Submittal Number: 11 61 43-21.1 From: KIM DOWALIBY Final Due Date: 10/12/21 Subject: CLERESTORY CURTAIN VALENCE TRUSS - SHOP DRAWINGS Description: Spec Section: 11 61 43 - ARENA CURTAINS Status: OPEN | Info Exchange
| 14758 | Review Response | Approved as Noted | 2021-09-29 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See comments in attached submittal. This submittal appears to be duplicated in portions of submittal 11 61 43-9.5. Supplier to coordinate structural requirements provided by engineers of delegated systems. | Info Exchange
| 14759 | Review Response | Approved as Noted | 2021-09-29 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 19026 | Responded and Closed | Approved as Noted | 2021-09-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments in attached submittal. This submittal appears to be duplicated in portions of submittal 11 61 43-9.5. Supplier to coordinate structural requirements provided by engineers of delegated systems. Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-28 |  | 11 61 43-21.1 - Clerestory Curtain Valence Truss - Shop Drawings Rev 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-28 |  | 11 61 43-21.1 - Clerestory Curtain Valence Truss - Shop Drawings Rev 1.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-09-28 |  | 11 61 43-21.1 - Clerestory Curtain Valence Truss - Shop Drawings Rev 1.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-09-29 |  | 11 61 43-21.1 - Clerestory Curtain Valence Truss - Shop Drawings Rev 1_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-28 |  | 11 61 43-21.1 - Clerestory Curtain Valence Truss - Shop Drawings Rev 1.pdf
11 61 44-009-01 | 11 61 44 - HALF-HOUSE CURTAINS | 11 61 44-009-01 Package 4 - Half House Curtains | Closed | Structural, Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-24 | Closed - Void |  | Matthew Farber (Thornton Tomasetti), Brian Elwell (Idibri), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-07 |  | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12201 | Received | For Review | 2021-03-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-07 | Submittal Number: 11 61 44-9.1 From: DOMINGO SAMPAYO Final Due Date: 04/06/21 Subject: PACKAGE 4 - HALF HOUSE CURTAINS Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 15787 | Forwarded | For Review | 2021-03-24 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian Elwell (Idibri); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton... | 2021-03-31 | Submittal Number: 11 61 44-9.1 From: DOMINGO SAMPAYO Final Due Date: 04/06/21 Subject: PACKAGE 4 - HALF HOUSE CURTAINS Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 15887 | Closed | Void | 2021-03-25 | Josh Dobken (Populous) |  |  | SUBMITTAL CANCELLED AND VOIDED BY CONTRACTOR (EMAIL FROM KIM DOWALIBY ON 3/25/2021). NO REVIEW REQUIRED.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-23 |  | 11 61 44-9 Rev1 Package 4 - Half House Curtains.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-23 |  | 11 61 44-9 Rev1 Package 4 - Half House Curtains.pdf
11 61 44-009-02 | 11 61 44 - HALF-HOUSE CURTAINS | 11 61 44-009-02 Package 4 - Up Stage Curtains | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-04 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian Elwell (Idibri), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Kelsea Conkright (Populous), Todd Spangler (Populous), Chris Minter (Populous) |  |  |  | 2021-05-18 | 2021-05-18 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12924 | Received | For Review | 2021-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-18 | Submittal Number: 11 61 44-9.2 From: KIM DOWALIBY Final Due Date: 05/17/21 Subject: PACKAGE 4 - UP STAGE CURTAINS Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 16706 | Forwarded | For Review | 2021-05-04 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian Elwell (Idibri); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton... | 2021-05-11 | Submittal Number: 11 61 44-9.2 From: KIM DOWALIBY Final Due Date: 05/17/21 Subject: PACKAGE 4 - UP STAGE CURTAINS Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 16825 | Forwarded | For Review | 2021-05-10 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Chris Minter (Populous) | 2021-05-17 | Submittal Number: 11 61 44-9.2 From: KIM DOWALIBY Final Due Date: 05/17/21 Subject: PACKAGE 4 - UP STAGE CURTAINS Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 13157 | Review Response | Approved as Noted | 2021-05-12 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Idibri reviewed for acoustics and sound system integration only. | Info Exchange
| 13159 | Review Response | Approved as Noted | 2021-05-17 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Exceptions noted, resubmit not required. See attached submittal. TT-FK ¦ 2021-05-17 | Info Exchange
| 17028 | Responded and Closed | Approved as Noted | 2021-05-18 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-03 |  | 11 61 44-9.2 - Package 4 Up Stage Curtains - Shop Drawings Rev 2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-03 |  | 11 61 44-9.2 - Package 4 Up Stage Curtains - Shop Drawings Rev 2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-02 02:00 |  | 11 61 44-9.2 - Package 4 Up Stage Curtains - Shop Drawings Rev 2.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-05-03 |  | 11 61 44-9.2 - Package 4 Up Stage Curtains - Shop Drawings Rev 2.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-05-03 |  | 11 61 44-9.2 - Package 4 Up Stage Curtains - Shop Drawings Rev 2.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-12 |  | 11 61 44-9.2 - Package 4 Up Stage Curtains - Shop Drawings Rev 2 i!i Notes.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-17 |  | 11 61 44-9.2 - Package 4 Up Stage Curtains - Shop Drawings Rev 2_TT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-18 |  | 11 61 44-9.2 - Package 4 Up Stage Curtains - Shop Drawings Rev 2 i!i Notes-POP.pdf
11 61 44-009-03 | 11 61 44 - HALF-HOUSE CURTAINS | 11 61 44-009-03 Package 4 - Up Stage Curtains - FINAL FOR RECORD | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-09 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2021-08-23 | 2021-08-26 | 18 |  | Record Copies; Transfers; Submittals | 11 61 44-009-03-01 - 11 61 44-009-03 Package 4 - Up Stage Curtains - FINAL FOR RECORD | 18 |  | 2021-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14261 | Received | For Review | 2021-08-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-08-23 | Submittal Number: 11 61 44-9.3 From: KIM DOWALIBY Final Due Date: 08/20/21 Subject: PACKAGE 4 - UP STAGE CURTAINS - FINAL FOR RECORD Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 18423 | Forwarded | For Review | 2021-08-09 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-16 | Submittal Number: 11 61 44-9.3 From: KIM DOWALIBY Final Due Date: 08/20/21 Subject: PACKAGE 4 - UP STAGE CURTAINS - FINAL FOR RECORD Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 14424 | Review Response | Approved as Noted/Resubmit | 2021-08-19 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18618 | Responded and Closed | Approved as Noted/Resubmit | 2021-08-19 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| 18674 | Reopened | Additional Information | 2021-08-26 11:39 | Kelsea Conkright (Populous)
| 18675 | Forwarded | For Review | 2021-08-26 | Kelsea Conkright (Populous) | Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) |  | Submittal Number: 11 61 44-9.3 From: KIM DOWALIBY Final Due Date: 08/20/21 Subject: PACKAGE 4 - UP STAGE CURTAINS - FINAL FOR RECORD Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 14498 | Review Response | Approved as Noted | 2021-08-26 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Received for record. See TT's comments in previous return of this submittal. Refer to Submittal package 11 61 44-9.2 - Package 4 Up Stage Curtains - Shop Drawings Rev 2, returned on 05/17/2021. | Info Exchange
| 14501 | Review Response | Approved as Noted | 2021-08-26 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18695 | Responded and Closed | Approved as Noted | 2021-08-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: Received for record. See TT's comments in previous return of this submittal. Refer to Submittal package 11 61 44-9.2 - Package 4 Up Stage Curtains - Shop Drawings Rev 2, returned on 05/17/2021. Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-06 |  | 11 61 44-9.3 - Package 4 Up Stage Curtains - Shop Drawings FINAL FOR RECORD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-06 |  | 11 61 44-9.3 - Package 4 Up Stage Curtains - Shop Drawings FINAL FOR RECORD.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-08-19 |  | 11 61 44-9.3 - Package 4 Up Stage Curtains - Shop Drawings FINAL FOR RECORD_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-08-06 |  | 11 61 44-9.3 - Package 4 Up Stage Curtains - Shop Drawings FINAL FOR RECORD.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-08-06 |  | 11 61 44-9.3 - Package 4 Up Stage Curtains - Shop Drawings FINAL FOR RECORD.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-08-06 |  | 11 61 44-9.3 - Package 4 Up Stage Curtains - Shop Drawings FINAL FOR RECORD.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-08-26 |  | 11 61 44-9.3 - Package 4 Up Stage Curtains - Shop Drawings FINAL FOR RECORD_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-06 |  | 11 61 44-9.3 - Package 4 Up Stage Curtains - Shop Drawings FINAL FOR RECORD.pdf
11 61 44-009-03-01 | 11 61 44 - HALF-HOUSE CURTAINS | 11 61 44-009-03 Package 4 - Up Stage Curtains - FINAL FOR RECORD | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 61 44-009-03 - 11 61 44-009-03 Package 4 - Up Stage Curtains - FINAL FOR RECORD | -1 | 2021-09-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-06 |  | 11 61 44-9.3 - Package 4 Up Stage Curtains - Shop Drawings FINAL FOR RECORD.pdf
11 61 44-010-00 | 11 61 44 - HALF-HOUSE CURTAINS | 11 61 44-010-00 Package 2 - North Acoustic Curtains | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian Elwell (Idibri), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-01-27 08:00 | 2021-02-02 | 22 |  | Record Copies; Transfers; Submittals | 11 61 44-010-00-01 - 11 61 44-010-00 Package 2 - North Acoustic Curtains | 17 |  | 2021-02-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10633 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-27 08:00 | Submittal Number: 11 61 44-10.0 From: DOMINGO SAMPAYO Final Due Date: 01/27/21 Subject: PACKAGE 2 - NORTH ACOUSTIC CURTAINS Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 13841 | Forwarded | For Review | 2021-01-12 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-19 | Submittal Number: 11 61 44-10.0 From: DOMINGO SAMPAYO Final Due Date: 01/27/21 Subject: PACKAGE 2 - NORTH ACOUSTIC CURTAINS Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 14246 | Forwarded | For Review | 2021-01-26 | Populous SCA_CCA | Brian Elwell (Idibri); Matt Ross (Thornton Tomasetti) |  | Submittal Number: 11 61 44-10.0 From: DOMINGO SAMPAYO Final Due Date: 01/27/21 Subject: PACKAGE 2 - NORTH ACOUSTIC CURTAINS Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 11130 | Review Response | Rejected | 2021-01-27 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  | See comments on submittal SDK ¦ TT ¦ 01/27/2021 | Info Exchange
| 11131 | Review Response | Approved as Noted | 2021-01-28 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Letter of transmittal said this included product data. There were no cutsheets attached, so we assume this is covered in another submittal. | Info Exchange
| 14442 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-02 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Letter of transmittal said this included product data. There were no cutsheets attached, so we assume this is covered in another submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 11 61 44-10.0 North Acoustic Curtain (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-12 |  | 11 61 44-10.0 North Acoustic Curtain (MAM Review).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-12 |  | 11 61 44-10.0 North Acoustic Curtain (MAM Review).pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2021-01-27 |  | 11 61 44-10.0 North Acoustic Curtain_TT REVIEW.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-01-12 |  | 11 61 44-10.0 North Acoustic Curtain (MAM Review).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-02 |  | 11 61 44-10.0 North Acoustic Curtain - MAM__IDIBRI_POP.pdf
11 61 44-010-00-01 | 11 61 44 - HALF-HOUSE CURTAINS | 11 61 44-010-00 Package 2 - North Acoustic Curtains | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 61 44-010-00 - 11 61 44-010-00 Package 2 - North Acoustic Curtains | -1 | 2021-02-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | 11 61 44-10.0 North Acoustic Curtain - MAM__IDIBRI_POP.pdf
11 61 44-010-01 | 11 61 44 - HALF-HOUSE CURTAINS | 11 61 44-010-01 Package 2 - North Acoustic Curtains | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-22 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian Elwell (Idibri), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-06 | 2021-05-04 | 13 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12718 | Received | For Review | 2021-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-06 | Submittal Number: 11 61 44-10.1 From: DOMINGO SAMPAYO Final Due Date: 05/05/21 Subject: PACKAGE 2 - NORTH ACOUSTIC CURTAINS Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 16441 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian Elwell (Idibri); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton... | 2021-04-29 | Submittal Number: 11 61 44-10.1 From: DOMINGO SAMPAYO Final Due Date: 05/05/21 Subject: PACKAGE 2 - NORTH ACOUSTIC CURTAINS Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 12920 | Review Response | Approved as Noted | 2021-04-27 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See attached. | Info Exchange
| 12921 | Review Response | No Action Taken or Required | 2021-04-29 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Nothing to review related to acoustics. | Info Exchange
| 16702 | Responded and Closed | Approved as Noted | 2021-05-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attached. Response (No Action Taken or Required) from: Brian Elwell (Idibri) Remarks: Nothing to review related to acoustics. | Info Exchange
| 16765 | Sent | For Information Only | 2021-05-05 | Populous SCA_CCA | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attached. Response (No Action Taken or Required) from: Brian Elwell (Idibri) Remarks: Nothing to review related to acoustics. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-22 |  | 11 61 44-10 Rev1 Package 2 - North Acoustic Curtains.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-22 |  | 11 61 44-10 Rev1 Package 2 - North Acoustic Curtains.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-04-22 |  | 11 61 44-10 Rev1 Package 2 - North Acoustic Curtains.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-04-22 |  | 11 61 44-10 Rev1 Package 2 - North Acoustic Curtains.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-04 |  | 11 61 44-10 Rev1 Package 2 - North Acoustic Curtains_TT_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-04-21 02:00 |  | 11 61 44-10 Rev1 Package 2 - North Acoustic Curtains.pdf
11 61 44-011-00 | 11 61 44 - HALF-HOUSE CURTAINS | 11 61 44-011-00 Package 2 - North Acoustic Curtains (Plates, Anchor Bolts, Locations and Elevations) - PARTIAL | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-09 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Kelsea Conkright (Populous), Chris Minter (Populous) |  |  |  | 2021-03-23 | 2021-03-16 | 8 |  | Record Copies; Transfers; Submittals | 11 61 44-011-00-01 - 11 61 44-011-00 Package 2 - North Acoustic Curtains (Plates, Anchor Bolts, Locations and Elevations) - PARTIAL | 8 |  | 2021-03-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11873 | Received | For Review | 2021-03-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-03-23 | Submittal Number: 11 61 44-11.0 From: DOMINGO SAMPAYO Final Due Date: 03/12/21 Subject: PACKAGE 2 - NORTH ACOUSTIC CURTAINS (PLATES, ANCHOR BOLTS, LOCATIONS AND ELEVATIONS) - PARTIAL Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 15389 | Forwarded | For Review | 2021-03-09 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-16 | Submittal Number: 11 61 44-11.0 From: DOMINGO SAMPAYO Final Due Date: 03/12/21 Subject: PACKAGE 2 - NORTH ACOUSTIC CURTAINS (PLATES, ANCHOR BOLTS, LOCATIONS AND ELEVATIONS) - PARTIAL Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 15455 | Forwarded | For Review | 2021-03-10 | Josh Dobken (Populous) | Kelsea Conkright (Populous); Chris Minter (Populous) | 2021-03-17 | Submittal Number: 11 61 44-11.0 From: DOMINGO SAMPAYO Final Due Date: 03/12/21 Subject: PACKAGE 2 - NORTH ACOUSTIC CURTAINS (PLATES, ANCHOR BOLTS, LOCATIONS AND ELEVATIONS) - PARTIAL Description: Spec Section: 11 61 44 - HALF HOUSE CURTAINS Status: OPEN | Info Exchange
| 12053 | Review Response | Approved as Noted/Resubmit | 2021-03-11 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Per general note SU-5, this system is a delegated design item that is required to be engineered, signed and sealed by a licensed engineer. TT limited its review of this submittal to: - magnitude and location of loads imposed on base structure - post-installed anchor type & approval All other items are not reviewed. Populous to review geometry and finishes. FK ¦ TT ¦ 3/11/2021 | Info Exchange
| 12060 | Review Response | Approved as Noted/Resubmit | 2021-03-16 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Populous limited its review of this submittal to the following -- 1. Dimensions of bottom hem of curtain off the precast 2. Mount plate color | Info Exchange
| 15616 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-16 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Franz Kogler (Thornton Tomasetti) Remarks: Per general note SU-5, this system is a delegated design item that is required to be engineered, signed and sealed by a licensed engineer. TT limited its review of this submittal to: - magnitude and location of loads imposed on base structure - post-installed anchor type & approval All other items are not reviewed. Populous to review geometry and finishes. FK ¦ TT ¦ 3/11/2021 Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: Populous limited its review of this submittal to the following -- 1. Dimensions of bottom hem of curtain off the precast 2. Mount plate color | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-08 |  | 11 61 44-11 Package 2 - North Acoustic Curtains (Plates Anchor Bolts Locations and Elevations) - PARTIAL.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-08 |  | 11 61 44-11 Package 2 - North Acoustic Curtains (Plates Anchor Bolts Locations and Elevations) - PARTIAL.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-07 02:00 |  | 11 61 44-11 Package 2 - North Acoustic Curtains (Plates Anchor Bolts Locations and Elevations) - PARTIAL.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-03-08 |  | 11 61 44-11 Package 2 - North Acoustic Curtains (Plates Anchor Bolts Locations and Elevations) - PARTIAL.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-16 |  | 11 61 44-11 Package 2 - North Acoustic Curtains - PARTIAL_TTFK_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-03-08 |  | 11 61 44-11 Package 2 - North Acoustic Curtains (Plates Anchor Bolts Locations and Elevations) - PARTIAL.pdf
11 61 44-011-00-01 | 11 61 44 - HALF-HOUSE CURTAINS | 11 61 44-011-00 Package 2 - North Acoustic Curtains (Plates, Anchor Bolts, Locations and Elevations) - PARTIAL | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 61 44-011-00 - 11 61 44-011-00 Package 2 - North Acoustic Curtains (Plates, Anchor Bolts, Locations and Elevations) - PARTIAL | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-08 |  | 11 61 44-11 Package 2 - North Acoustic Curtains (Plates Anchor Bolts Locations and Elevations) - PARTIAL.pdf
11 61 45-005-00 | 11 61 45 - UPPER BOWL MASKING SYSTEM | 11 61 45-005-00 Upper Bowl Masking System/Half House/Arena Curtains - Qualification Data | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-05 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Kelsea Conkright (Populous), Todd Spangler (Populous), Chris Minter (Populous) |  |  |  | 2021-05-19 | 2021-05-18 | 14 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12945 | Received | For Review | 2021-05-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-19 | Submittal Number: 11 61 45-5.0 From: DOMINGO SAMPAYO Final Due Date: 05/18/21 Subject: UPPER BOWL MASKING SYSTEM/HALF HOUSE/ARENA CURTAINS - QUALIFICATION DATA Description: QUALIFICATION DATA: FOR INSTALLER AND PROFESSIONAL ENGINEER. INCLUDE LISTS OF COMPLETED PROJECTS WITH PROJECT NAMES AND ADDRESSES, NAMES AND ADDRESSES OF ARCHITECTS AND OWNERS, AND OTHER INFORMATION SPECIFIED. Spec Section: 11 61 45 - UPPER BOWL MASKING SYSTEM Status: OPEN | Info Exchange
| 16743 | Forwarded | For Review | 2021-05-05 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-12 | Submittal Number: 11 61 45-5.0 From: DOMINGO SAMPAYO Final Due Date: 05/18/21 Subject: UPPER BOWL MASKING SYSTEM/HALF HOUSE/ARENA CURTAINS - QUALIFICATION DATA Description: QUALIFICATION DATA: FOR INSTALLER AND PROFESSIONAL ENGINEER. INCLUDE LISTS OF COMPLETED PROJECTS WITH PROJECT NAMES AND ADDRESSES, NAMES AND ADDRESSES OF ARCHITECTS AND OWNERS, AND OTHER INFORMATION SPECIFIED. Spec Section: 11 61 45 - UPPER BOWL MASKING SYSTEM Status: OPEN | Info Exchange
| 16827 | Forwarded | For Review | 2021-05-10 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Chris Minter (Populous) | 2021-05-17 | Submittal Number: 11 61 45-5.0 From: DOMINGO SAMPAYO Final Due Date: 05/18/21 Subject: UPPER BOWL MASKING SYSTEM/HALF HOUSE/ARENA CURTAINS - QUALIFICATION DATA Description: QUALIFICATION DATA: FOR INSTALLER AND PROFESSIONAL ENGINEER. INCLUDE LISTS OF COMPLETED PROJECTS WITH PROJECT NAMES AND ADDRESSES, NAMES AND ADDRESSES OF ARCHITECTS AND OWNERS, AND OTHER INFORMATION SPECIFIED. Spec Section: 11 61 45 - UPPER BOWL MASKING SYSTEM Status: OPEN | Info Exchange
| 13158 | Review Response | No Action Taken or Required | 2021-05-13 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Retained for Record. Arch to review. | Info Exchange
| 17030 | Responded and Closed | Approved | 2021-05-18 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-05 |  | 11 61 45-5 Upper Bowl Masking System-Half House-Arena Curtains - Qualification Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-05 |  | 11 61 45-5 Upper Bowl Masking System-Half House-Arena Curtains - Qualification Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-04 02:00 |  | 11 61 45-5 Upper Bowl Masking System-Half House-Arena Curtains - Qualification Data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-05 |  | 11 61 45-5 Upper Bowl Masking System-Half House-Arena Curtains - Qualification Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-18 |  | 11 61 45-5 Upper Bowl Masking System-Half House-Arena Curtains - Qualification Data-POP.pdf
11 61 45-009-01 | 11 61 45 - UPPER BOWL MASKING SYSTEM | 11 61 45-009-01 Package 3 - Upper Bowl Masking System | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti) |  |  |  | 2021-03-29 | 2021-04-06 | 23 |  | Record Copies; Transfers; Submittals | 11 61 45-009-01-01 - 11 61 45-009-01 Package 3 - Upper Bowl Masking System | 23 |  | 2021-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11988 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-03-29 | Submittal Number: 11 61 45-9.1 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: PACKAGE 3 - UPPER BOWL MASKING SYSTEM Description: Spec Section: 11 61 45 - UPPER BOWL MASKING SYSTEM Status: OPEN | Info Exchange
| 15528 | Forwarded | For Review | 2021-03-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-22 | Submittal Number: 11 61 45-9.1 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: PACKAGE 3 - UPPER BOWL MASKING SYSTEM Description: Spec Section: 11 61 45 - UPPER BOWL MASKING SYSTEM Status: OPEN | Info Exchange
| 16105 | Forwarded | For Review | 2021-04-06 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) | 2021-03-29 | Submittal Number: 11 61 45-9.1 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: PACKAGE 3 - UPPER BOWL MASKING SYSTEM Description: Spec Section: 11 61 45 - UPPER BOWL MASKING SYSTEM Status: OPEN | Info Exchange
| 12435 | Review Response | Revise and Resubmit | 2021-04-06 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | Per general note SU-5, this system is a delegated design item that is required to be designed/engineered, signed and sealed by a licensed engineer. TT limited its review of this submittal to magnitude and location of loads imposed on base structure. All other items are not reviewed. FK ¦ TT ¦ 3/30/2021 | Info Exchange
| 16112 | Forwarded | For Review | 2021-04-06 | Josh Dobken (Populous) | Kelsea Conkright (Populous); Chris Minter (Populous) | 2021-03-29 | Submittal Number: 11 61 45-9.1 From: DOMINGO SAMPAYO Final Due Date: 03/29/21 Subject: PACKAGE 3 - UPPER BOWL MASKING SYSTEM Description: Spec Section: 11 61 45 - UPPER BOWL MASKING SYSTEM Status: OPEN | Info Exchange
| 12439 | Review Response | Revise and Resubmit | 2021-04-06 | Chris Minter (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16117 | Responded and Closed | Revise and Resubmit | 2021-04-06 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Franz Kogler (Thornton Tomasetti) Remarks: Per general note SU-5, this system is a delegated design item that is required to be designed/engineered, signed and sealed by a licensed engineer. TT limited its review of this submittal to magnitude and location of loads imposed on base structure. All other items are not reviewed. FK ¦ TT ¦ 3/30/2021 Response (Revise and Resubmit) from: Chris Minter (Populous) Remarks: | Info Exchange
| 16123 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-06 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-14 |  | 11 61 45-9.1 Upper Bowl Masking SD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-14 |  | 11 61 45-9.1 Upper Bowl Masking SD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-13 02:00 |  | 11 61 45-9.1 Upper Bowl Masking SD-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-04-06 02:00 |  | 11 61 45-9.1 Upper Bowl Masking SD-MAM-POP_TTReview.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-13 02:00 |  | 11 61 45-9.1 Upper Bowl Masking SD-MAM.pdf
| Review Response |  | Chris Minter (Populous) | 1 | 2021-04-06 |  | 11 61 45-9.1 Upper Bowl Masking SD-MAM-POP_TTReview.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-14 |  | 11 61 45-9.1 Upper Bowl Masking SD-MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-14 |  | 11 61 45-9.1 Upper Bowl Masking SD-MAM.pdf
11 61 45-009-01-01 | 11 61 45 - UPPER BOWL MASKING SYSTEM | 11 61 45-009-01 Package 3 - Upper Bowl Masking System | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 11 61 45-009-01 - 11 61 45-009-01 Package 3 - Upper Bowl Masking System | -1 | 2021-04-20
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-14 |  | 11 61 45-9.1 Upper Bowl Masking SD-MAM.pdf
11 61 45-009-02 | 11 61 45 - UPPER BOWL MASKING SYSTEM | 11 61 45-009-02 Package 3 - Upper Bowl Masking System | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-23 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Kelsea Conkright (Populous), Chris Minter (Populous) |  |  |  | 2021-05-07 | 2021-05-06 | 14 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12726 | Received | For Review | 2021-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-07 | Submittal Number: 11 61 45-9.2 From: KIM DOWALIBY Final Due Date: 05/06/21 Subject: PACKAGE 3 - UPPER BOWL MASKING SYSTEM Description: Spec Section: 11 61 45 - UPPER BOWL MASKING SYSTEM Status: OPEN | Info Exchange
| 16452 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-29 | Submittal Number: 11 61 45-9.2 From: KIM DOWALIBY Final Due Date: 05/06/21 Subject: PACKAGE 3 - UPPER BOWL MASKING SYSTEM Description: Spec Section: 11 61 45 - UPPER BOWL MASKING SYSTEM Status: OPEN | Info Exchange
| 12967 | Review Response | Approved as Noted | 2021-04-27 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See attached submittal for review comments. | Info Exchange
| 16713 | Forwarded | For Review | 2021-05-04 | Populous SCA_CCA | Kelsea Conkright (Populous); Chris Minter (Populous) | 2021-05-07 | Submittal Number: 11 61 45-9.2 From: KIM DOWALIBY Final Due Date: 05/06/21 Subject: PACKAGE 3 - UPPER BOWL MASKING SYSTEM Description: Spec Section: 11 61 45 - UPPER BOWL MASKING SYSTEM Status: OPEN | Info Exchange
| 16778 | Responded and Closed | Approved as Noted | 2021-05-06 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-22 |  | 11 61 45-9.2 - Package 3 - Upper Bowl Masking - Shop Drawings Rev 2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-22 |  | 11 61 45-9.2 - Package 3 - Upper Bowl Masking - Shop Drawings Rev 2.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-04-21 02:00 |  | 11 61 45-9.2 - Package 3 - Upper Bowl Masking - Shop Drawings Rev 2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-21 02:00 |  | 11 61 45-9.2 - Package 3 - Upper Bowl Masking - Shop Drawings Rev 2.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-27 |  | 11 61 45-9.2 - Package 3 - Upper Bowl Masking - Shop Drawings Rev 2_TTReview.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-06 |  | 11 61 45-9.2 - Package 3 - Upper Bowl Masking - Shop Drawings Rev 2_TTReview-POP.pdf
12 21 24-009-00 | 12 21 24 | 12 21 24-009-00 Package 5 - North Wall Window Shade System | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-26 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-09 | 2021-01-26 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10968 | Received | For Review | 2021-01-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-09 | Submittal Number: 12 21 24-9.0 From: DOMINGO SAMPAYO Final Due Date: 02/08/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 14243 | Forwarded | For Review | 2021-01-26 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-02 | Submittal Number: 12 21 24-9.0 From: DOMINGO SAMPAYO Final Due Date: 02/08/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 14254 | Responded and Closed | Revise and Resubmit | 2021-01-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-26 |  | 12 21 24-9 Package 5 - North Wall Window Shade System.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-26 |  | 12 21 24-9 Package 5 - North Wall Window Shade System.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-26 |  | 12 21 24-9 Package 5 - North Wall Window Shade System_POP.pdf
12 21 24-009-01 | 12 21 24 | 12 21 24-009-01 Package 5 - North Wall Window Shade System | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-18 | 2021-02-10 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-02-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11190 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2021-02-18 | Submittal Number: 12 21 24-9.1 From: DOMINGO SAMPAYO Final Due Date: 02/17/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 14496 | Forwarded | For Review | 2021-02-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-11 | Submittal Number: 12 21 24-9.1 From: DOMINGO SAMPAYO Final Due Date: 02/17/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 14664 | Responded and Closed | Revise and Resubmit | 2021-02-10 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-03 |  | 12 21 24-9 R1 Package 5 - North Wall Window Shade System.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-03 |  | 12 21 24-9 R1 Package 5 - North Wall Window Shade System.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-02-10 |  | 12 21 24-009-01 Package 5 - North Wall Window Shade System_TT_POP.pdf
12 21 24-009-02 | 12 21 24 | 12 21 24-009-02 Package 5 - North Wall Window Shade System | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2021-04-01 | 2021-04-01 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-04-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12099 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-01 | Submittal Number: 12 21 24-9.2 From: DOMINGO SAMPAYO Final Due Date: 03/30/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 15658 | Forwarded | For Review | 2021-03-18 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-25 | Submittal Number: 12 21 24-9.2 From: DOMINGO SAMPAYO Final Due Date: 03/30/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 15846 | Forwarded | For Review | 2021-03-26 | Populous SCA_CCA | Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) |  | Submittal Number: 12 21 24-9.2 From: DOMINGO SAMPAYO Final Due Date: 03/30/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Email
| 15994 | Responded and Closed | Revise and Resubmit | 2021-04-01 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR COMMENTS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-18 |  | 12 21 24-9 Rev2 Package 5 - North Wall Window Shade System.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-18 |  | 12 21 24-9 Rev2 Package 5 - North Wall Window Shade System.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-18 |  | 12 21 24-9 Rev2 Package 5 - North Wall Window Shade System.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 12 21 24-9 Rev2 Package 5 - North Wall Window Shade System_POP.pdf
12 21 24-009-03 | 12 21 24 | 12 21 24-009-03 Package 5 - North Wall Window Shade System | Closed | Architectural, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-04 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Mark Lievens (ME Engineers), Franz Kogler (Thornton Tomasetti) |  |  |  | 2021-06-18 | 2021-06-18 | 15 |  | Record Copies; Transfers; Submittals | 12 21 24-009-03-01 - 12 21 24-009-03 Package 5 - North Wall Window Shade System | 15 |  | 2021-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13392 | Received | For Review | 2021-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-18 | Submittal Number: 12 21 24-9.3 From: DOMINGO SAMPAYO Final Due Date: 06/14/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 17320 | Forwarded | For Review | 2021-06-04 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-11 | Submittal Number: 12 21 24-9.3 From: DOMINGO SAMPAYO Final Due Date: 06/14/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 17416 | Forwarded | For Review | 2021-06-09 | Populous SCA_CCA | Mark Lievens (ME Engineers) |  | Submittal Number: 12 21 24-9.3 From: DOMINGO SAMPAYO Final Due Date: 06/14/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 17447 | Forwarded | For Review | 2021-06-11 | Populous SCA_CCA | Franz Kogler (Thornton Tomasetti) |  | Submittal Number: 12 21 24-9.3 From: DOMINGO SAMPAYO Final Due Date: 06/14/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 13567 | Review Response | Approved as Noted | 2021-06-18 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.06.18 | Info Exchange
| 13568 | Review Response | Approved as Noted/Resubmit | 2021-06-18 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17567 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-18 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.06.18 Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-04 |  | 12 21 24-009-3 Package 5 - North Wall Window Shade System.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-04 |  | 12 21 24-009-3 Package 5 - North Wall Window Shade System.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-04 |  | 12 21 24-009-3 Package 5 - North Wall Window Shade System.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-09 |  | Transmittal_Submittal - 12 21 24-009-03 (Forwarded)_1.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-06-04 |  | 12 21 24-009-3 Package 5 - North Wall Window Shade System.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-18 |  | 12 21 24-009-3 Package 5 - North Wall Window Shade System_POP_ME.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-18 |  | 12 21 24-009-3 Package 5 - North Wall Window Shade System_POP_ME.pdf
12 21 24-009-03-01 | 12 21 24 | 12 21 24-009-03 Package 5 - North Wall Window Shade System | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 12 21 24-009-03 - 12 21 24-009-03 Package 5 - North Wall Window Shade System | -1 | 2021-07-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-18 |  | 12 21 24-009-3 Package 5 - North Wall Window Shade System_POP_ME.pdf
12 21 24-009-04 | 12 21 24 | 12 21 24-009-04 Package 5 - North Wall Window Shade System | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-29 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-12 | 2021-08-16 | 19 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-08-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14157 | Received | For Review | 2021-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-08-12 | Submittal Number: 12 21 24-9.4 From: JES PELKEY Final Due Date: 08/11/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 18299 | Forwarded | For Review | 2021-07-29 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-05 | Submittal Number: 12 21 24-9.4 From: JES PELKEY Final Due Date: 08/11/21 Subject: PACKAGE 5 - NORTH WALL WINDOW SHADE SYSTEM Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 14374 | Review Response | Approved as Noted | 2021-08-12 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see attached submittal review. Mark Lievens ME Engineers 2021.08.12 | Info Exchange
| 18549 | Responded and Closed | Approved | 2021-08-16 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-28 |  | 12 21 24-9.4 - Package 5 - North Wall Window Shade System Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-28 |  | 12 21 24-9.4 - Package 5 - North Wall Window Shade System Shop Drawings.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-28 |  | 12 21 24-9.4 - Package 5 - North Wall Window Shade System Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-08-16 |  | 12 21 24-9.4 - Package 5 - North Wall Window Shade System Shop Drawings - ME_POP.pdf
12 21 24-010-00 | 12 21 24 | 12 21 24-010-00 Ticket Office Roller Window Shade Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-30 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Kelsea Conkright (Populous), Kuebler Perry (Populous) |  |  |  | 2021-07-15 07:00 | 2021-07-08 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13719 | Received | For Review | 2021-06-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-15 07:00 | Submittal Number: 12 21 24-10.0 From: JES PELKEY Final Due Date: 07/13/21 Subject: TICKET OFFICE ROLLER WINDOW SHADE SAMPLES Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 17762 | Forwarded | For Review | 2021-06-30 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-07 | Submittal Number: 12 21 24-10.0 From: JES PELKEY Final Due Date: 07/13/21 Subject: TICKET OFFICE ROLLER WINDOW SHADE SAMPLES Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 17863 | Forwarded | For Review | 2021-07-06 | Populous SCA_CCA | Kelsea Conkright (Populous); Kuebler Perry (Populous) | 2021-07-13 | Submittal Number: 12 21 24-10.0 From: JES PELKEY Final Due Date: 07/13/21 Subject: TICKET OFFICE ROLLER WINDOW SHADE SAMPLES Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 17930 | Responded and Closed | Approved as Noted | 2021-07-08 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-29 |  | 12 21 24-10.0 Ticket Office Window Shade Samples-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-29 |  | 12 21 24-10.0 Ticket Office Window Shade Samples-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-28 02:00 |  | 12 21 24-10.0 Ticket Office Window Shade Samples-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-08 02:00 |  | 12 21 24-10.0 Ticket Office Window Shade Samples-MAM_pop.pdf
12 21 24-011-00 | 12 21 24 | 12 21 24-011-00 Ticket Office Roller Window Shade Shop Drawing and Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-30 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Kelsea Conkright (Populous), Kuebler Perry (Populous) |  |  |  | 2021-07-15 07:00 | 2021-07-12 | 13 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13720 | Received | For Review | 2021-06-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-15 07:00 | Submittal Number: 12 21 24-11.0 From: JES PELKEY Final Due Date: 07/13/21 Subject: TICKET OFFICE ROLLER WINDOW SHADE SHOP DRAWING AND PRODUCT DATA Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 17763 | Forwarded | For Review | 2021-06-30 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-07 | Submittal Number: 12 21 24-11.0 From: JES PELKEY Final Due Date: 07/13/21 Subject: TICKET OFFICE ROLLER WINDOW SHADE SHOP DRAWING AND PRODUCT DATA Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 13774 | Review Response | Not Required For Review | 2021-07-01 | Mark Lievens (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | Manual shades not required for electrical review. Mark Lievens ME Engineers 2021.07.01 | Info Exchange
| 17864 | Forwarded | For Review | 2021-07-06 | Populous SCA_CCA | Kelsea Conkright (Populous); Kuebler Perry (Populous) | 2021-07-13 | Submittal Number: 12 21 24-11.0 From: JES PELKEY Final Due Date: 07/13/21 Subject: TICKET OFFICE ROLLER WINDOW SHADE SHOP DRAWING AND PRODUCT DATA Description: Spec Section: 12 21 24 - ROLLER WINDOW SHADES Status: OPEN | Info Exchange
| 17979 | Responded and Closed | Approved as Noted | 2021-07-12 | Chad Francis (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-29 |  | 12 21 24-11.0 Ticket Office Window Shade SD and PD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-29 |  | 12 21 24-11.0 Ticket Office Window Shade SD and PD-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-06-29 |  | 12 21 24-11.0 Ticket Office Window Shade SD and PD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-28 02:00 |  | 12 21 24-11.0 Ticket Office Window Shade SD and PD-MAM.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-12 |  | 12 21 24-11.0 Ticket Office Window Shade SD and PD-MAM_POP.pdf
12 22 00-008-00 | 12 22 00 - CURTAINS AND DRAPES | 12 22 00-008-00 Chairman Club Curtain Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-30 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-15 07:00 | 2021-07-08 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13721 | Received | For Review | 2021-06-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-15 07:00 | Submittal Number: 12 22 00-8.0 From: JES PELKEY Final Due Date: 07/16/21 Subject: CHAIRMAN CLUB CURTAIN SAMPLE Description: Spec Section: 12 22 00 - CURTAINS AND DRAPES Status: OPEN | Info Exchange
| 17764 | Forwarded | For Review | 2021-06-30 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-07 | Submittal Number: 12 22 00-8.0 From: JES PELKEY Final Due Date: 07/16/21 Subject: CHAIRMAN CLUB CURTAIN SAMPLE Description: Spec Section: 12 22 00 - CURTAINS AND DRAPES Status: OPEN | Info Exchange
| 17920 | Responded and Closed | Approved | 2021-07-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-29 |  | 12 22 00-8.0 Chairman Club Curtain Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-29 |  | 12 22 00-8.0 Chairman Club Curtain Sample.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-07-08 02:00 |  | 12 22 00-8.0 Chairman Club Curtain Sample_POP.pdf
12 22 00-009-00 | 12 22 00 - CURTAINS AND DRAPES | 12 22 00-009-00 Chairman Club Curtain Shop Drawings and Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-08 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-22 | 2021-07-13 | 6 |  | Record Copies; Transfers; Submittals | 12 22 00-009-00-01 - 12 22 00-009-00 Chairman Club Curtain Shop Drawings and Product Data | 6 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13840 | Received | For Review | 2021-07-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-22 | Submittal Number: 12 22 00-9.0 From: JES PELKEY Final Due Date: 07/20/21 Subject: CHAIRMAN CLUB CURTAIN SHOP DRAWINGS AND PRODUCT DATA Description: Spec Section: 12 22 00 - CURTAINS AND DRAPES Status: OPEN | Info Exchange
| 17915 | Forwarded | For Review | 2021-07-08 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-15 | Submittal Number: 12 22 00-9.0 From: JES PELKEY Final Due Date: 07/20/21 Subject: CHAIRMAN CLUB CURTAIN SHOP DRAWINGS AND PRODUCT DATA Description: Spec Section: 12 22 00 - CURTAINS AND DRAPES Status: OPEN | Info Exchange
| 13919 | Review Response | Revise and Resubmit | 2021-07-13 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 18021 | Responded and Closed | Revise and Resubmit | 2021-07-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-07 |  | 12 22 00-9.0 Chairman Club Curtain SD&PD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-07 |  | 12 22 00-9.0 Chairman Club Curtain SD&PD-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-13 |  | 12 22 00-9.0 Chairman Club Curtain SD&PD-MAM_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-07 |  | 12 22 00-9.0 Chairman Club Curtain SD&PD-MAM.pdf
12 22 00-009-00-01 | 12 22 00 - CURTAINS AND DRAPES | 12 22 00-009-00 Chairman Club Curtain Shop Drawings and Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 12 22 00-009-00 - 12 22 00-009-00 Chairman Club Curtain Shop Drawings and Product Data | -1 | 2021-07-27
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-07 |  | 12 22 00-9.0 Chairman Club Curtain SD&PD-MAM.pdf
12 22 00-009-01 | 12 22 00 - CURTAINS AND DRAPES | 12 22 00-009-01 Chairman Club Curtain Shop Drawings and Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-27 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-10 | 2021-08-09 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14123 | Received | For Review | 2021-07-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Jes Pelkey (Mortenson Construction); Kim Dowaliby | 2021-08-10 | Submittal Number: 12 22 00-9.1 From: JES PELKEY Final Due Date: 08/04/21 Subject: CHAIRMAN CLUB CURTAIN SHOP DRAWINGS AND PRODUCT DATA Description: Spec Section: 12 22 00 - CURTAINS AND DRAPES Status: OPEN | Info Exchange
| 18254 | Forwarded | For Review | 2021-07-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-03 | Submittal Number: 12 22 00-9.1 From: JES PELKEY Final Due Date: 08/04/21 Subject: CHAIRMAN CLUB CURTAIN SHOP DRAWINGS AND PRODUCT DATA Description: Spec Section: 12 22 00 - CURTAINS AND DRAPES Status: OPEN | Info Exchange
| 14284 | Review Response | Approved as Noted | 2021-08-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18448 | Responded and Closed | Approved as Noted | 2021-08-09 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-26 |  | 12 22 00-9.1 Chairman Club Curtain SD&PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-26 |  | 12 22 00-9.1 Chairman Club Curtain SD&PD-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-09 |  | 12 22 00-9.1 Chairman Club Curtain SD&PD-MAM_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-26 |  | 12 22 00-9.1 Chairman Club Curtain SD&PD-MAM.pdf
12 22 00-010-00 | 12 22 00 - CURTAINS AND DRAPES | 12 22 00-010-00 Space Needle Club Decorative Curtain - Sample | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-29 | 2021-07-22 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-07-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13953 | Received | For Review | 2021-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Kim Dowaliby | 2021-07-29 | Submittal Number: 12 22 00-10.0 From: KIM DOWALIBY Final Due Date: 07/28/21 Subject: SPACE NEEDLE CLUB DECORATIVE CURTAIN - SAMPLE Description: Spec Section: 12 22 00 - CURTAINS AND DRAPES Status: OPEN | Info Exchange
| 18056 | Forwarded | For Review | 2021-07-15 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-22 | Submittal Number: 12 22 00-10.0 From: KIM DOWALIBY Final Due Date: 07/28/21 Subject: SPACE NEEDLE CLUB DECORATIVE CURTAIN - SAMPLE Description: Spec Section: 12 22 00 - CURTAINS AND DRAPES Status: OPEN | Info Exchange
| 14067 | Review Response | Approved as Noted | 2021-07-22 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18190 | Responded and Closed | Approved as Noted | 2021-07-22 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-14 |  | 12 22 00-10 Space Needle Club Decorative Curtain Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-14 |  | 12 22 00-10 Space Needle Club Decorative Curtain Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-22 |  | 12 22 00-10 Space Needle Club Decorative Curtain _POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-14 |  | 12 22 00-10 Space Needle Club Decorative Curtain Sample.pdf
12 36 23.13-001-00 | 12 36 23-13 - PLASTIC-LAMINATE-CLAD COUNTERTOPS | 12 36 23.13-001-00 P-L Countertop Shop Drawings Package 1 - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-10 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-24 | 2020-06-18 | 9 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06316 | Received | For Review | 2020-06-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-06-24 | Submittal Number: 12 36 23.13-1.0 From: JOSH BROUSSARD Final Due Date: 06/23/20 Subject: P-L COUNTERTOP SHOP DRAWINGS PACKAGE 1 - BASE BUILDING Description: SHOP DRAWINGS FOR PLASTIC LAMINATED COUNTER TOPS ON EVENT LEVEL. NOTE THAT PLASTIC LAMINATED COUNTER TOPS THAT ARE INTEGRAL TO CASEWORK ARE SUBMITTED UNDER THE APPLICABLE CASEWORK SPEC SECTION AS PART OF THE CASEWORK SHOP DRAWINGS. Spec Section: 12 36 23.13 - PLASTIC LAMINATE CLAD COUNTERTOPS Status: OPEN | Info Exchange
| 08520 | Forwarded | For Review | 2020-06-09 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-06-16 | Submittal Number: 12 36 23.13-1.0 From: JOSH BROUSSARD Final Due Date: 06/23/20 Subject: P-L COUNTERTOP SHOP DRAWINGS PACKAGE 1 - BASE BUILDING Description: SHOP DRAWINGS FOR PLASTIC LAMINATED COUNTER TOPS ON EVENT LEVEL. NOTE THAT PLASTIC LAMINATED COUNTER TOPS THAT ARE INTEGRAL TO CASEWORK ARE SUBMITTED UNDER THE APPLICABLE CASEWORK SPEC SECTION AS PART OF THE CASEWORK SHOP DRAWINGS. Spec Section: 12 36 23.13 - PLASTIC LAMINATE CLAD COUNTERTOPS Status: OPEN | Info Exchange
| 06505 | Review Response | Revise and Resubmit | 2020-06-18 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  |  | Mail
| 08760 | Responded and Closed | Revise and Resubmit | 2020-06-18 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-09 |  | 12 36 23.13-1.0 P-L Countertop Shop Drawings Package 1 - Base Building.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-09 |  | 12 36 23.13-1.0 P-L Countertop Shop Drawings Package 1 - Base Building(1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-09 |  | 12 36 23.13-1.0 P-L Countertop Shop Drawings Package 1 - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-09 |  | 12 36 23.13-1.0 P-L Countertop Shop Drawings Package 1 - Base Building(1).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-06-18 |  | 12 36 23.13-1.0 P-L Countertop Shop Drawings Package 1 - Base Building_POP_FINAL.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-06-09 |  | 12 36 23.13-1.0 P-L Countertop Shop Drawings Package 1 - Base Building.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-06-09 |  | 12 36 23.13-1.0 P-L Countertop Shop Drawings Package 1 - Base Building(1).pdf
12 36 23.13-001-01 | 12 36 23-13 - PLASTIC-LAMINATE-CLAD COUNTERTOPS | 12 36 23.13-001-01 P-L Countertop Shop Drawings Event Level - Base Building Rev 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-20 | 2020-07-07 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-07-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06771 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 12 36 23.13-1.1 From: JOSH BROUSSARD Final Due Date: 07/17/20 Subject: P-L COUNTERTOP SHOP DRAWINGS EVENT LEVEL - BASE BUILDING REV 1 Description: REVISION 1 FOR SHOP DRAWINGS FOR PLASTIC LAMINATED COUNTER TOPS ON EVENT LEVEL. NOTE THAT PLASTIC LAMINATED COUNTER TOPS THAT ARE INTEGRAL TO CASEWORK ARE SUBMITTED UNDER THE APPLICABLE CASEWORK SPEC SECTION AS PART OF THE CASEWORK SHOP DRAWINGS. Spec Section: 12 36 23.13 - PLASTIC LAMINATE CLAD COUNTERTOPS Status: OPEN | Info Exchange
| 09099 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-07-13 | Submittal Number: 12 36 23.13-1.1 From: JOSH BROUSSARD Final Due Date: 07/17/20 Subject: P-L COUNTERTOP SHOP DRAWINGS EVENT LEVEL - BASE BUILDING REV 1 Description: REVISION 1 FOR SHOP DRAWINGS FOR PLASTIC LAMINATED COUNTER TOPS ON EVENT LEVEL. NOTE THAT PLASTIC LAMINATED COUNTER TOPS THAT ARE INTEGRAL TO CASEWORK ARE SUBMITTED UNDER THE APPLICABLE CASEWORK SPEC SECTION AS PART OF THE CASEWORK SHOP DRAWINGS. Spec Section: 12 36 23.13 - PLASTIC LAMINATE CLAD COUNTERTOPS Status: OPEN | Info Exchange
| 06819 | Review Response | Approved as Noted | 2020-07-07 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to shop-drawing markup. | Mail
| 09154 | Responded and Closed | Approved as Noted | 2020-07-07 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to shop drawings markup. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-03 |  | 12 36 23.13-1.1 P-L Countertop Shop Dwgs Event Lvl - Base Bldg R1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-03 |  | 12 36 23.13-1.1 P-L Countertop Shop Dwgs Event Lvl - Base Bldg R1.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-07-07 |  | 12 36 23.13-1.1 P-L Countertop Shop Dwgs Event Lvl - Base Bldg R1_POP_Final.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-03 |  | 12 36 23.13-1.1 P-L Countertop Shop Dwgs Event Lvl - Base Bldg R1.pdf
12 36 23.13-002-00 | 12 36 23-13 - PLASTIC-LAMINATE-CLAD COUNTERTOPS | 12 36 23.13-002-00 Bridge Level Press Counter & Shelf Shop Drawings - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-20 | 2020-07-20 | 15 |  | Record Copies; Transfers; Submittals | 12 36 23.13-002-00-01 - 12 36 23.13-002-00 Bridge Level Press Counter & Shelf Shop Drawings - Base Building | 15 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06772 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 12 36 23.13-2.0 From: JOSH BROUSSARD Final Due Date: 07/17/20 Subject: BRIDGE LEVEL PRESS COUNTER & SHELF SHOP DRAWINGS - BASE BUILDING Description: Spec Section: 12 36 23.13 - PLASTIC LAMINATE CLAD COUNTERTOPS Status: OPEN | Info Exchange
| 09100 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-07-13 | Submittal Number: 12 36 23.13-2.0 From: JOSH BROUSSARD Final Due Date: 07/17/20 Subject: BRIDGE LEVEL PRESS COUNTER & SHELF SHOP DRAWINGS - BASE BUILDING Description: Spec Section: 12 36 23.13 - PLASTIC LAMINATE CLAD COUNTERTOPS Status: OPEN | Info Exchange
| 07032 | Review Response | Revise and Resubmit | 2020-07-20 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | See comments noted on submittal. | Info Exchange
| 09420 | Responded and Closed | Revise and Resubmit | 2020-07-20 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: See comments noted on submittal. | Info Exchange
| 10057 | Sent | For Information Only | 2020-08-14 | Josh Dobken (Populous) | Josh Broussard (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) |  | Responded and Closed (Revise and Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: See comments noted on submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-03 |  | 12 36 23.13-2.0 Bridge Lvl Press Counter & Shelf Shop Dwgs - Base Bldg.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-03 |  | 12 36 23.13-2.0 Bridge Lvl Press Counter & Shelf Shop Dwgs - Base Bldg.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-07-20 |  | 12 36 23.13-2.0 Bridge Lvl Press Counter & Shelf Shop Dwgs - Base Bldg_FINAL.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-07-03 |  | 12 36 23.13-2.0 Bridge Lvl Press Counter & Shelf Shop Dwgs - Base Bldg.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-07-02 02:00 |  | 12 36 23.13-2.0 Bridge Lvl Press Counter & Shelf Shop Dwgs - Base Bldg.pdf
12 36 23.13-002-00-01 | 12 36 23-13 - PLASTIC-LAMINATE-CLAD COUNTERTOPS | 12 36 23.13-002-00 Bridge Level Press Counter & Shelf Shop Drawings - Base Building | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 12 36 23.13-002-00 - 12 36 23.13-002-00 Bridge Level Press Counter & Shelf Shop Drawings - Base Building | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-03 |  | 12 36 23.13-2.0 Bridge Lvl Press Counter & Shelf Shop Dwgs - Base Bldg.pdf
12 36 23.13-002-01 | 12 36 23.13 | 12 36 23.13-002-01 Bridge Level Press Counter & Shelf Shop Drawings - Base Building Rev 1 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-22 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-06 | 2020-09-30 | 9 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-09-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08245 | Received | For Review | 2020-09-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-06 | Submittal Number: 12 36 23.13-2.1 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: BRIDGE LEVEL PRESS COUNTER & SHELF SHOP DRAWINGS - BASE BUILDING REV 1 Description: Spec Section: 12 36 23.13 - PLASTIC LAMINATE CLAD COUNTERTOPS Status: OPEN | Info Exchange
| 10949 | Forwarded | For Review | 2020-09-21 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-28 | Submittal Number: 12 36 23.13-2.1 From: MIKE SOLFELT Final Due Date: 09/11/20 Subject: BRIDGE LEVEL PRESS COUNTER & SHELF SHOP DRAWINGS - BASE BUILDING REV 1 Description: Spec Section: 12 36 23.13 - PLASTIC LAMINATE CLAD COUNTERTOPS Status: OPEN | Info Exchange
| 08456 | Review Response | Approved as Noted | 2020-09-30 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 11197 | Responded and Closed | Approved as Noted | 2020-09-30 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 12 36 23.13-2.1 Bridge Lvl Press Counter & Shelf Shop Dwgs - Base Bldg.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-21 |  | 12 36 23.13-2.1 Bridge Lvl Press Counter & Shelf Shop Dwgs - Base Bldg.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-09-30 |  | 12 36 23.13-2.1 Bridge Lvl Press Counter & Shelf Shop Dwgs - Base Bldg_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-09-21 |  | 12 36 23.13-2.1 Bridge Lvl Press Counter & Shelf Shop Dwgs - Base Bldg.pdf
12 36 23.13-003-00 | 12 36 23.13 | 12 36 23.13-003-00 Cash Counting Room | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-29 | 2021-03-17 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11996 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-29 | Submittal Number: 12 36 23.13-3.0 From: MIKE SOLFELT Final Due Date: 03/25/21 Subject: CASH COUNTING ROOM Description: Spec Section: 12 36 23.13 - PLASTIC LAMINATE CLAD COUNTERTOPS Status: OPEN | Info Exchange
| 15536 | Forwarded | For Review | 2021-03-15 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-22 | Submittal Number: 12 36 23.13-3.0 From: MIKE SOLFELT Final Due Date: 03/25/21 Subject: CASH COUNTING ROOM Description: Spec Section: 12 36 23.13 - PLASTIC LAMINATE CLAD COUNTERTOPS Status: OPEN | Info Exchange
| 12087 | Review Response | Approved as Noted | 2021-03-17 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15645 | Responded and Closed | Approved as Noted | 2021-03-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-15 |  | 12 36 23.13-3 Cash Counting Room.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-15 |  | 12 36 23.13-3 Cash Counting Room.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-17 |  | 12 36 23.13-3 Cash Counting Room_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-15 |  | 12 36 23.13-3 Cash Counting Room.pdf
12 36 61-001-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-001-00 Stone Countertop Shop Drawings Package 1 - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-05 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Kuebler Perry (Populous), Josh Dobken (Populous) |  |  |  | 2020-06-19 | 2020-06-18 | 14 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06252 | Received | For Review | 2020-06-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (M.A. Mortenson Company) | 2020-06-19 | Submittal Number: 12 36 61-1.0 From: JOSH BROUSSARD Final Due Date: 06/19/20 Subject: STONE COUNTERTOP SHOP DRAWINGS PACKAGE 1 - BASE BUILDING Description: SHOP DRAWINGS FOR SSM10 STONE LEDGES IN THE BASE BUILDING AREAS. Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 08437 | Forwarded | For Review | 2020-06-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) | 2020-06-15 | Submittal Number: 12 36 61-1.0 From: JOSH BROUSSARD Final Due Date: 06/19/20 Subject: STONE COUNTERTOP SHOP DRAWINGS PACKAGE 1 - BASE BUILDING Description: SHOP DRAWINGS FOR SSM10 STONE LEDGES IN THE BASE BUILDING AREAS. Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 06498 | Review Response | Approved as Noted | 2020-06-18 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  |  | Mail
| 08752 | Responded and Closed | Approved as Noted | 2020-06-18 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 12 36 61-1.0 Stone Countertop Shop Drawings Package 1 - Base Building.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 12 36 61-1.0 Stone Countertop Shop Drawings Package 1 - Base Building(1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 12 36 61-1.0 Stone Countertop Shop Drawings Package 1 - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 12 36 61-1.0 Stone Countertop Shop Drawings Package 1 - Base Building(1).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-06-18 |  | 12 36 61-1.0 Stone Countertop Shop Drawings Package 1 - Base Building_POP FINAL.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-06-05 |  | 12 36 61-1.0 Stone Countertop Shop Drawings Package 1 - Base Building.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-06-05 |  | 12 36 61-1.0 Stone Countertop Shop Drawings Package 1 - Base Building(1).pdf
12 36 61-002-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-002-00 Stone Drink Rails Shop Drawings - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-28 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-11 | 2020-08-14 | 18 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-08-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07168 | Received | For Review | 2020-07-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-08-11 | Submittal Number: 12 36 61-2.0 From: JOSH BROUSSARD Final Due Date: 07/27/20 Subject: STONE DRINK RAILS SHOP DRAWINGS - BASE BUILDING Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 09564 | Forwarded | For Review | 2020-07-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-03 | Submittal Number: 12 36 61-2.0 From: JOSH BROUSSARD Final Due Date: 07/27/20 Subject: STONE DRINK RAILS SHOP DRAWINGS - BASE BUILDING Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 07452 | Review Response | Approved as Noted | 2020-08-06 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached review. | Info Exchange
| 09920 | Closed | Void | 2020-08-06 | Kuebler Perry (Populous)
| 10058 | Reopened | Additional Information | 2020-08-14 15:02 | Josh Dobken (Populous) |  |  | Was voided in error. Reopening to re-send to contractor.
| 10059 | Responded and Closed | Approved as Noted | 2020-08-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Josh Broussard (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Kuebler Perry (Populous) Remarks: Refer to attached review. | Info Exchange
| 10130 | Sent | For Information Only | 2020-08-18 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company); Ryan Crookston (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted) to: Danny Keim (M.A. Mortenson Company); Josh Broussard (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) Remarks: Response (Approved as Noted) from: Kuebler Perry (Populous) Remarks: Refer to attached review. | Info Exchange
| 10323 | Sent | For Information Only | 2020-08-26 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company) |  | Sent to: Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (M.A. Mortenson Company); Ryan Crookston (M.A. Mortenson Company) Remarks: Responded and Closed (Approved as Noted) to: Danny Keim (M.A. Mortenson Company); Josh Broussard (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) Remarks: Response (Approved as Noted) from: Kuebler Perry (Populous) Remarks: Refer to attached review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-27 |  | 12 36 61 - 002 Drink Rails.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-27 |  | 12 36 61 - 002 Drink Rails.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-06 |  | 12 36 61 - 002 Drink Rails_POP Final.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-26 02:00 |  | 12 36 61 - 002 Drink Rails.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-07-26 02:00 |  | 12 36 61 - 002 Drink Rails.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-07-26 02:00 |  | 12 36 61 - 002 Drink Rails.pdf
12 36 61-004-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-004-00 SSM50 Countertop Shop Drawings - Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-28 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-11 | 2020-08-06 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07173 | Received | For Review | 2020-07-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-08-11 | Submittal Number: 12 36 61-4.0 From: JOSH BROUSSARD Final Due Date: 07/27/20 Subject: SSM50 COUNTERTOP SHOP DRAWINGS - BASE BUILDING Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 09574 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-04 | Submittal Number: 12 36 61-4.0 From: JOSH BROUSSARD Final Due Date: 07/27/20 Subject: SSM50 COUNTERTOP SHOP DRAWINGS - BASE BUILDING Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 07449 | Review Response | Approved as Noted | 2020-08-06 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached review. | Info Exchange
| 09917 | Responded and Closed | Approved as Noted | 2020-08-06 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-27 |  | 12 36 61 - 004 SSM50 Countertop Shop Drawings - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-27 |  | 12 36 61 - 004 SSM50 Countertop Shop Drawings - Base Building.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-06 |  | 12 36 61 - 004 SSM50 Countertop Shop Drawings - Base Building_POP Final.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-07-27 |  | 12 36 61 - 004 SSM50 Countertop Shop Drawings - Base Building.pdf
12 36 61-006-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-006-00 SSM10 Bench Ledge Shop Drawings- Base Building | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-14 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-08-28 | 2020-08-28 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07575 | Received | For Review | 2020-08-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-08-28 | Submittal Number: 12 36 61-6.0 From: JOSH BROUSSARD Final Due Date: 08/07/20 Subject: SSM10 BENCH LEDGE SHOP DRAWINGS- BASE BUILDING Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 10081 | Forwarded | For Review | 2020-08-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-24 | Submittal Number: 12 36 61-6.0 From: JOSH BROUSSARD Final Due Date: 08/07/20 Subject: SSM10 BENCH LEDGE SHOP DRAWINGS- BASE BUILDING Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 07822 | Review Response | Approved as Noted | 2020-08-28 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached review. | Info Exchange
| 10399 | Responded and Closed | Approved as Noted | 2020-08-28 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-14 |  | 123661-006 SSM10 Bench Ledge Shop Drawings - Base Building.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-14 |  | 123661-006 SSM10 Bench Ledge Shop Drawings - Base Building.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-28 |  | 123661-006 SSM10 Bench Ledge Shop Drawings - Base Building_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-14 |  | 123661-006 SSM10 Bench Ledge Shop Drawings - Base Building.pdf
12 36 61-012-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-012-00 SIMULATED STONE COUNTERTOPS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-17 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-10-01 | 2020-09-29 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08165 | Received | For Review | 2020-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-01 | Submittal Number: 12 36 61-12.0 From: MIKE SOLFELT Final Due Date: 09/23/20 Subject: SIMULATED STONE COUNTERTOPS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS. SAMPLES ARE NOT REQUIRED IF BASIS-OF- DESIGN PRODUCT IS SUBMITTED. 1. COUNTERTOP MATERIAL, 12 INCHES SQUARE, SUBMIT PHOTOGRAPHS IN ADVANCE OF FULL SIZE SAMPLES, REPRESENTING MATERIALS TRUE COLOR AND OTHER CHARACTERISTICS. 2. ONE FULL-SIZE SOLID-SURFACE-MATERIAL COUNTERTOP, WITH FRONT EDGE AND SPLASH, 8 BY 10 INCHES, OF CONSTRUCTION AND IN CONFIGURATION SPECIFIED. 3. ONE FULL-SIZE QUARTZ AGGLOMERATE COUNTERTOP, WITH FRONT EDGE AND SPLASH, 8 BY 10 INCHES, OF CONSTRUCTION AND IN CONFIGURATION SPECIFIED. Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 10839 | Forwarded | For Review | 2020-09-17 | Populous SCA_CCA | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-24 | Submittal Number: 12 36 61-12.0 From: MIKE SOLFELT Final Due Date: 09/23/20 Subject: SIMULATED STONE COUNTERTOPS - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR THE FOLLOWING PRODUCTS. SAMPLES ARE NOT REQUIRED IF BASIS-OF- DESIGN PRODUCT IS SUBMITTED. 1. COUNTERTOP MATERIAL, 12 INCHES SQUARE, SUBMIT PHOTOGRAPHS IN ADVANCE OF FULL SIZE SAMPLES, REPRESENTING MATERIALS TRUE COLOR AND OTHER CHARACTERISTICS. 2. ONE FULL-SIZE SOLID-SURFACE-MATERIAL COUNTERTOP, WITH FRONT EDGE AND SPLASH, 8 BY 10 INCHES, OF CONSTRUCTION AND IN CONFIGURATION SPECIFIED. 3. ONE FULL-SIZE QUARTZ AGGLOMERATE COUNTERTOP, WITH FRONT EDGE AND SPLASH, 8 BY 10 INCHES, OF CONSTRUCTION AND IN CONFIGURATION SPECIFIED. Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 08408 | Review Response | Approved | 2020-09-29 | Kuebler Perry (Populous) | Populous SCA_CCA |  | See attached submittal review. | Info Exchange
| 11144 | Responded and Closed | Approved | 2020-09-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-17 |  | 12 36 61-012 Simulated Stone Sample.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-17 |  | 12 36 61-012 Simulated Stone Sample.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-29 |  | 12 36 61-012 Simulated Stone Sample_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-17 |  | 12 36 61-012 Simulated Stone Sample.pdf
12 36 61-013-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-013-00 ST11, ST17, ST13, ST12, SSM44 Stone Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2020-10-14 | 2020-10-06 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08452 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (M.A. Mortenson Company) | 2020-10-14 | Submittal Number: 12 36 61-13.0 From: MIKE SOLFELT Final Due Date: 10/09/20 Subject: ST11, ST17, ST13, ST12, SSM44 STONE SAMPLES Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 11193 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2020-10-07 | Submittal Number: 12 36 61-13.0 From: MIKE SOLFELT Final Due Date: 10/09/20 Subject: ST11, ST17, ST13, ST12, SSM44 STONE SAMPLES Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 08616 | Review Response | Approved | 2020-10-06 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11386 | Responded and Closed | Approved | 2020-10-06 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 123661-013 ST11 ST17 ST13 ST12 SSM44 Stone Samples.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 123661-013 ST11 ST17 ST13 ST12 SSM44 Stone Samples.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-06 |  | 123661-013 ST11 ST17 ST13 ST12 SSM44 Stone Samples POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-09-30 |  | 123661-013 ST11 ST17 ST13 ST12 SSM44 Stone Samples.pdf
12 36 61-014-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-014-00 Premium Countertops Samples - Cambria | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-02-08 | 2021-02-05 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-02-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10939 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-02-08 | Submittal Number: 12 36 61-14.0 From: MIKE SOLFELT Final Due Date: 02/08/21 Subject: PREMIUM COUNTERTOPS SAMPLES - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 14202 | Forwarded | For Review | 2021-01-25 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-01 | Submittal Number: 12 36 61-14.0 From: MIKE SOLFELT Final Due Date: 02/08/21 Subject: PREMIUM COUNTERTOPS SAMPLES - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 11227 | Review Response | Approved as Noted | 2021-02-05 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached sample review. Confirm selections with Rockwell before proceeding. | Info Exchange
| 14532 | Responded and Closed | Approved as Noted | 2021-02-05 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached sample review. Confirm selections with Rockwell before proceeding. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 123661-014 Premium Coutnertop Samples - Camrbia.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-25 |  | 123661-014 Premium Coutnertop Samples - Camrbia.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-05 |  | 123661-014 Premium Coutnertop Samples - Camrbia_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-25 |  | 123661-014 Premium Coutnertop Samples - Camrbia.pdf
12 36 61-015-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-015-00 Chairman's Club Countertops - Cambria | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-05 | 2021-04-21 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-04-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12706 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-05-05 | Submittal Number: 12 36 61-15.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: CHAIRMAN'S CLUB COUNTERTOPS - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 16423 | Forwarded | For Review | 2021-04-21 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-28 | Submittal Number: 12 36 61-15.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: CHAIRMAN'S CLUB COUNTERTOPS - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 16428 | Responded and Closed | Approved as Noted | 2021-04-21 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | 1. FIELD VERIFY ALL DIMENSIONS 2. SHOP DRAWINGS SUBMITTED ARE FROM THE DD SET, CM TO COORDINATE WITH CURRENT CD SET 3. CM TO COORDINATE FINAL ROCKWELL GROUP COMMENTS COUNTERTOP MATERIAL IS NOT NOTED, CONFIRM ST03 CAMBRIA SUTHERLAND PER AGREEMENT 4. COORDINATE ALL PLUMBING TEMPLATES WITH PLUMBING DRAWINGS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-21 |  | 123661-015 Chairmans Club Restroom Countertops - Cambria.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-21 |  | 123661-015 Chairmans Club Restroom Countertops - Cambria.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-21 |  | 123661-015 Chairmans Club Restroom Countertops - Cambria_POP.pdf
12 36 61-016-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-016-00 Main Concourse Club Countertops - East/ West - Cambria | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-20 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12396 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-04-19 | Submittal Number: 12 36 61-16.0 From: MIKE SOLFELT Final Due Date: 04/19/21 Subject: MAIN CONCOURSE CLUB COUNTERTOPS - EAST/ WEST - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 16067 | Forwarded | For Review | 2021-04-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-12 | Submittal Number: 12 36 61-16.0 From: MIKE SOLFELT Final Due Date: 04/19/21 Subject: MAIN CONCOURSE CLUB COUNTERTOPS - EAST/ WEST - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 16379 | Responded and Closed | Approved as Noted | 2021-04-20 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 123661-016 Main Concourse Club Countertops - Cambria.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-05 |  | 123661-016 Main Concourse Club Countertops - Cambria.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-20 |  | 123661-016 Main Concourse Club Countertops - Cambria_POP.pdf
12 36 61-016-01 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-016-01 Main Concourse Club Countertops - East/ West - Cambria | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-02 07:00 | 2021-05-27 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-05-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13146 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-06-02 07:00 | Submittal Number: 12 36 61-16.1 From: MIKE SOLFELT Final Due Date: 04/19/21 Subject: MAIN CONCOURSE CLUB COUNTERTOPS - EAST/ WEST - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 17005 | Forwarded | For Review | 2021-05-18 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 12 36 61-16.1 From: MIKE SOLFELT Final Due Date: 04/19/21 Subject: MAIN CONCOURSE CLUB COUNTERTOPS - EAST/ WEST - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 17188 | Responded and Closed | Approved as Noted | 2021-05-27 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | 123661-016 Main Concourse Club Countertops - Cambria rev1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-17 |  | 123661-016 Main Concourse Club Countertops - Cambria rev1.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-05-27 |  | 123661-016 Main Concourse Club Countertops - Cambria rev1_POP.pdf
12 36 61-017-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-017-00 Mount Baker Club Countertops - Cambria | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-05 | 2021-04-21 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-04-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12707 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-05-05 | Submittal Number: 12 36 61-17.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: MOUNT BAKER CLUB COUNTERTOPS - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 16425 | Forwarded | For Review | 2021-04-21 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-28 | Submittal Number: 12 36 61-17.0 From: MIKE SOLFELT Final Due Date: 05/05/21 Subject: MOUNT BAKER CLUB COUNTERTOPS - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 16427 | Responded and Closed | Approved as Noted | 2021-04-21 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | PLEASE SEE ATTACHED FOR ALL COMMENTS 1. FIELD VERIFY ALL DIMENSIONS 2. SHOP DRAWINGS SUBMITTED ARE FROM THE DD SET, CM TO COORDINATE WITH CURRENT CD SET 3. CM TO COORDINATE FINAL ROCKWELL GROUP COMMENTS 4. COORDINATE ALL EQUIPMENT TEMPLATES WITH FOOD SERVICE DRAWINGS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-21 |  | 123661-017 Mount Baker Club Countertops - Cambria.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-21 |  | 123661-017 Mount Baker Club Countertops - Cambria.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-21 |  | 123661-017 Mount Baker Club Countertops - Cambria_POP.pdf
12 36 61-018-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-018-00 Suite Level Restrooms Countertops - Cambria | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-31 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-14 | 2021-04-16 | 17 |  | Record Copies; Transfers; Submittals | 12 36 61-018-00-01 - 12 36 61-018-00 Suite Level Restrooms Countertops - Cambria | 2 |  | 2021-04-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12615 | Received | For Review | 2021-03-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-14 | Submittal Number: 12 36 61-18.0 From: MIKE SOLFELT Final Due Date: 04/14/21 Subject: Suite Level Restrooms Countertops - Cambria Description: Spec Section: Status: OPEN | Email
| 16332 | Forwarded | For Review | 2021-04-15 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-14 | Submittal Number: 12 36 61-18.0 From: MIKE SOLFELT Final Due Date: 04/14/21 Subject: Suite Level Restrooms Countertops - Cambria Description: Spec Section: Status: OPEN | Info Exchange
| 16338 | Responded and Closed | Revise and Resubmit | 2021-04-16 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | 1. FIELD VERIFY ALL DIMENSIONS 2. COORDINATE SINK/FAUCET TEMPLATE WITH PLUMBING DRAWINGS 3. DRAWINGS SUBMITTED ARE FROM THE 100% DD SET. CM TO RESUBMIT WITH CURRENT CD DRAWINGS WHICH INDICATES ST13 REFER TO CURRENT FINISH LEGEND. CAMBRIA SUTHERLAND IS NOT LISTED FOR ST13 4. CM TO COORDINATE ROCKWELL GROUP COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-15 |  | 123661-018 Suite Level Restrooms Countertops - Cambria.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-15 |  | 123661-018 Suite Level Restrooms Countertops - Cambria.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-16 |  | 123661-018 Suite Level Restrooms Countertops - Cambria_POP.pdf
12 36 61-018-00-01 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-018-00 Suite Level Restrooms Countertops - Cambria | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 12 36 61-018-00 - 12 36 61-018-00 Suite Level Restrooms Countertops - Cambria | -1 | 2021-04-30
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-16 |  | 123661-018 Suite Level Restrooms Countertops - Cambria_POP.pdf
12 36 61-019-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-019-00 Space Needle Club Restroom Countertops - Cambria | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-21 | 17 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-04-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12356 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-04-19 | Submittal Number: 12 36 61-19.0 From: MIKE SOLFELT Final Due Date: 04/14/21 Subject: SPACE NEEDLE CLUB RESTROOM COUNTERTOPS - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 16013 | Forwarded | For Review | 2021-04-01 | Mike Solfelt (Mortenson Construction) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 12 36 61-19.0 From: MIKE SOLFELT Final Due Date: 04/14/21 Subject: SPACE NEEDLE CLUB RESTROOM COUNTERTOPS - CAMBRIA Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 16426 | Responded and Closed | Approved as Noted | 2021-04-21 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mike Solfelt (Mortenson Construction) |  | 1. FIELD VERIFY ALL DIMENSIONS 2. SHOP DRAWINGS SUBMITTED ARE FROM THE DD SET, CM TO COORDINATE WITH CURRENT CD SET 3. CM TO COORDINATE FINAL ROCKWELL GROUP COMMENTS 4. COORDINATE SINK/FAUCET TEMPLATE WITH PLUMBING DRAWINGS 5. COORDINATE SINK SPACING WITH ENLARGED PLANS 1, 2/A3-05.5-2 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 123661-019 Space Needle Level Restrooms Countertops - Cambria.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-04-01 |  | 123661-019 Space Needle Level Restrooms Countertops - Cambria.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-04-21 |  | 123661-019 Space Needle Level Restrooms Countertops - Cambria_POP.pdf
12 36 61-020-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-020-00 SSM32 and SSM33 Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-12 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-26 | 2021-06-03 | 53 |  | Record Copies; Transfers; Submittals |  | 53 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12535 | Received | For Review | 2021-04-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Mike Solfelt (Mortenson Construction) | 2021-04-26 | Submittal Number: 12 36 61-20.0 From: JOSH BROUSSARD Final Due Date: 04/26/21 Subject: SSM32 AND SSM33 SAMPLES Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 16237 | Forwarded | For Review | 2021-04-12 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-19 | Submittal Number: 12 36 61-20.0 From: JOSH BROUSSARD Final Due Date: 04/26/21 Subject: SSM32 AND SSM33 SAMPLES Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 12830 | Review Response | Approved as Noted/Resubmit | 2021-04-28 | Kuebler Perry (Populous) | Kuebler Perry (Populous) |  | Refer to attached submittal response. | Info Exchange
| 16606 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-28 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| 13372 | Review Response | Approved | 2021-06-03 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17300 | Responded and Closed | Approved | 2021-06-03 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-12 |  | 12 36 61-20.0 SSM32 and SSM33.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-12 |  | 12 36 61-20.0 SSM32 and SSM33.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-28 |  | 12 36 61-20.0 SSM32 and SSM33_POP.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-06-03 |  | 12 36 61-20.0 SSM32 and SSM33_POP_Rev 1.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-04-12 |  | 12 36 61-20.0 SSM32 and SSM33.pdf
12 36 61-022-00 | 12 36 61 - SIMULATED STONE COUNTERTOPS | 12 36 61-022-00 SSM33 Cambria Hadley | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-01 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-15 | 2021-06-07 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13334 | Received | For Review | 2021-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-15 | Submittal Number: 12 36 61-22.0 From: MIKE SOLFELT Final Due Date: 06/08/21 Subject: SSM33 CAMBRIA HADLEY Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 17253 | Forwarded | For Review | 2021-06-01 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 12 36 61-22.0 From: MIKE SOLFELT Final Due Date: 06/08/21 Subject: SSM33 CAMBRIA HADLEY Description: Spec Section: 12 36 61 - SIMULATED STONE COUNTERTOPS Status: OPEN | Info Exchange
| 13423 | Review Response | Approved | 2021-06-07 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17363 | Responded and Closed | Approved | 2021-06-07 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-01 |  | 123661-020 Cambria Hadley.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-01 |  | 123661-020 Cambria Hadley.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-07 |  | 123661-020 Cambria Hadley_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-01 |  | 123661-020 Cambria Hadley.pdf
12 48 13-001-00 | 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES | 12 48 13-001-00 ENTRANCE FLOOR MATS AND FRAMES - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-23 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-06 | 2021-03-29 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12176 | Received | For Review | 2021-03-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-06 | Submittal Number: 12 48 13-1.0 From: DANIELLE SCOTT Final Due Date: 04/05/21 Subject: ENTRANCE FLOOR MATS AND FRAMES - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR FLOOR MATS AND FRAMES. Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 15760 | Forwarded | For Review | 2021-03-23 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-30 | Submittal Number: 12 48 13-1.0 From: DANIELLE SCOTT Final Due Date: 04/05/21 Subject: ENTRANCE FLOOR MATS AND FRAMES - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT. 1. INCLUDE CONSTRUCTION DETAILS, MATERIAL DESCRIPTIONS, DIMENSIONS OF INDIVIDUAL COMPONENTS AND PROFILES, AND FINISHES FOR FLOOR MATS AND FRAMES. Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 15905 | Responded and Closed | Approved | 2021-03-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-22 |  | 12 48 13-1 Revision 0 ENTRANCE FLOOR MATS AND FRAMES - Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-22 |  | 12 48 13-1 Revision 0 ENTRANCE FLOOR MATS AND FRAMES - Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-29 |  | 12 48 13-1 Revision 0 ENTRANCE FLOOR MATS AND FRAMES - Product Data_POP.pdf
12 48 13-002-00 | 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES | 12 48 13-002-00 ENTRANCE FLOOR MATS AND FRAMES - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-22 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-06 07:00 | 2021-04-01 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-04-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12167 | Received | For Review | 2021-03-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Danielle Scott | 2021-04-06 07:00 | Submittal Number: 12 48 13-2.0 From: DANIELLE SCOTT Final Due Date: 04/05/21 Subject: ENTRANCE FLOOR MATS AND FRAMES - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. ITEMS PENETRATING FLOOR MATS AND FRAMES, INCLUDING DOOR CONTROL DEVICES. 2. DIVISIONS BETWEEN MAT SECTIONS. 3. PERIMETER FLOOR MOLDINGS. 4. CUSTOM GRAPHICS: SCALE DRAWING INDICATING COLORS. Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 15751 | Forwarded | For Review | 2021-03-22 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-29 | Submittal Number: 12 48 13-2.0 From: DANIELLE SCOTT Final Due Date: 04/05/21 Subject: ENTRANCE FLOOR MATS AND FRAMES - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. ITEMS PENETRATING FLOOR MATS AND FRAMES, INCLUDING DOOR CONTROL DEVICES. 2. DIVISIONS BETWEEN MAT SECTIONS. 3. PERIMETER FLOOR MOLDINGS. 4. CUSTOM GRAPHICS: SCALE DRAWING INDICATING COLORS. Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 15997 | Responded and Closed | Approved as Noted | 2021-04-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Danielle Scott |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-22 |  | 12 48 13-2 Revision 0 ENTRANCE FLOOR MATS AND FRAMES - Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-22 |  | 12 48 13-2 Revision 0 ENTRANCE FLOOR MATS AND FRAMES - Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-04-01 |  | 12 48 13-2 Revision 0 ENTRANCE FLOOR MATS AND FRAMES - Shop Drawings_POP.pdf
12 48 13-002-01 | 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES | 12 48 13-002-01 ENTRANCE FLOOR MATS AND FRAMES - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-03 07:00 | 2021-05-24 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-05-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13180 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-03 07:00 | Submittal Number: 12 48 13-2.1 From: KIM DOWALIBY Final Due Date: 06/02/21 Subject: ENTRANCE FLOOR MATS AND FRAMES - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. ITEMS PENETRATING FLOOR MATS AND FRAMES, INCLUDING DOOR CONTROL DEVICES. 2. DIVISIONS BETWEEN MAT SECTIONS. 3. PERIMETER FLOOR MOLDINGS. 4. CUSTOM GRAPHICS: SCALE DRAWING INDICATING COLORS. Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 17068 | Forwarded | For Review | 2021-05-19 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-26 | Submittal Number: 12 48 13-2.1 From: KIM DOWALIBY Final Due Date: 06/02/21 Subject: ENTRANCE FLOOR MATS AND FRAMES - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. ITEMS PENETRATING FLOOR MATS AND FRAMES, INCLUDING DOOR CONTROL DEVICES. 2. DIVISIONS BETWEEN MAT SECTIONS. 3. PERIMETER FLOOR MOLDINGS. 4. CUSTOM GRAPHICS: SCALE DRAWING INDICATING COLORS. Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 17127 | Responded and Closed | Approved | 2021-05-24 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-19 |  | 12 48 13-2 Revision 1 ENTRANCE FLOOR MATS AND FRAMES - Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-19 |  | 12 48 13-2 Revision 1 ENTRANCE FLOOR MATS AND FRAMES - Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-24 |  | 12 48 13-2 Revision 1 ENTRANCE FLOOR MATS AND FRAMES_POP.pdf
12 48 13-003-00 | 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES | 12 48 13-003-00 ENTRANCE FLOOR MATS AND FRAMES - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-23 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-06 | 2021-03-29 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12177 | Received | For Review | 2021-03-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Danielle Scott | 2021-04-06 | Submittal Number: 12 48 13-3.0 From: DANIELLE SCOTT Final Due Date: 04/05/21 Subject: ENTRANCE FLOOR MATS AND FRAMES - SAMPLES Description: SAMPLES : FOR THE FOLLOWING PRODUCTS, IN MANUFACTURER'S STANDARD SIZES: 1. TREAD RAIL: SAMPLE OF EACH TYPE AND COLOR. 2. FRAME MEMBERS: SAMPLE OF EACH TYPE AND COLOR. Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 15761 | Forwarded | For Review | 2021-03-23 | Danielle Scott | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-30 | Submittal Number: 12 48 13-3.0 From: DANIELLE SCOTT Final Due Date: 04/05/21 Subject: ENTRANCE FLOOR MATS AND FRAMES - SAMPLES Description: SAMPLES : FOR THE FOLLOWING PRODUCTS, IN MANUFACTURER'S STANDARD SIZES: 1. TREAD RAIL: SAMPLE OF EACH TYPE AND COLOR. 2. FRAME MEMBERS: SAMPLE OF EACH TYPE AND COLOR. Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 15906 | Responded and Closed | Approved | 2021-03-29 | Danielle Scott | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-22 |  | 12 48 13-3 Revision 0 ENTRANCE FLOOR MATS AND FRAMES - Samples.pdf
| Forwarded |  | Danielle Scott | 1 | 2021-03-22 |  | 12 48 13-3 Revision 0 ENTRANCE FLOOR MATS AND FRAMES - Samples.pdf
| Responded and Closed |  | Danielle Scott | 1 | 2021-03-29 |  | 12 48 13-3 Revision 0 ENTRANCE FLOOR MATS AND FRAMES - Samples_POP.pdf
12 48 13-004-00 | 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES | 12 48 13-004-00 ENTRANCE FLOOR MATS AND FRAMES - Maintenance Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-22 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-05 | 2021-03-29 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12168 | Received | For Review | 2021-03-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-05 | Submittal Number: 12 48 13-4.0 From: DANIELLE SCOTT Final Due Date: 04/05/21 Subject: ENTRANCE FLOOR MATS AND FRAMES - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR FLOOR MATS AND FRAMES TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 15752 | Forwarded | For Review | 2021-03-22 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-29 | Submittal Number: 12 48 13-4.0 From: DANIELLE SCOTT Final Due Date: 04/05/21 Subject: ENTRANCE FLOOR MATS AND FRAMES - MAINTENANCE DATA Description: MAINTENANCE DATA : FOR FLOOR MATS AND FRAMES TO INCLUDE IN MAINTENANCE MANUALS. Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 15908 | Responded and Closed | Approved | 2021-03-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-22 |  | 12 48 13-4 ENTRANCE FLOOR MATS AND FRAMES - Maintenance Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-22 |  | 12 48 13-4 ENTRANCE FLOOR MATS AND FRAMES - Maintenance Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-29 |  | 12 48 13-4 ENTRANCE FLOOR MATS AND FRAMES - Maintenance Data_POP.pdf
12 48 13-005-00 | 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES | 12 48 13-005-00 Entry Grate Floor Leveling Compound - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-24 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-07 | 2021-09-13 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-09-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14443 | Received | No Action Required | 2021-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-07 | Submittal Number: 12 48 13-5.0 From: LUCAS TRADAL Final Due Date: 09/06/21 Subject: ENTRY GRATE FLOOR LEVELING COMPOUND - PRODUCT DATA Description: Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 18642 | Forwarded | For Review | 2021-08-24 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-31 | Submittal Number: 12 48 13-5.0 From: LUCAS TRADAL Final Due Date: 09/06/21 Subject: ENTRY GRATE FLOOR LEVELING COMPOUND - PRODUCT DATA Description: Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 18878 | Responded and Closed | Approved | 2021-09-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-24 |  | 12 48 13-5 Revision 0 ENTRANCE FLOOR MATS AND FRAMES.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-24 |  | 12 48 13-5 Revision 0 ENTRANCE FLOOR MATS AND FRAMES.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-13 |  | 12 48 13-5 Revision 0 ENTRANCE FLOOR MATS AND FRAMES_POP.pdf
12 48 13-006-00 | 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES | 12 48 13-006-00 Entry Grate Perimeter Sealant - Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-26 | Responded and Closed - Approved |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2021-09-09 | 2021-09-08 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14505 | Received | For Review | 2021-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-09 | Submittal Number: 12 48 13-6.0 From: LUCAS TRADAL Final Due Date: 09/08/21 Subject: ENTRY GRATE PERIMETER SEALANT - PRODUCT DATA Description: Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 18701 | Forwarded | For Review | 2021-08-26 | Populous SCA_CCA | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2021-09-02 | Submittal Number: 12 48 13-6.0 From: LUCAS TRADAL Final Due Date: 09/08/21 Subject: ENTRY GRATE PERIMETER SEALANT - PRODUCT DATA Description: Spec Section: 12 48 13 - ENTRANCE FLOOR MATS AND FRAMES Status: OPEN | Info Exchange
| 18811 | Responded and Closed | Approved | 2021-09-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-25 02:00 |  | 12 48 13-6 Revision 0 ENTRANCE FLOOR MATS AND FRAMES - Entry Grate Perimeter Sealant Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-25 02:00 |  | 12 48 13-6 Revision 0 ENTRANCE FLOOR MATS AND FRAMES - Entry Grate Perimeter Sealant Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-08 |  | 12 48 13-6 Revision 0 ENTRANCE FLOOR MATS AND FRAMES_POP.pdf
12 63 26-001-00 | 12 63 26 - ARENA SEATS | 12 63 26-001-00 Fixed Seating Fabric Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-13 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-27 | 2020-07-30 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-07-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06925 | Received | For Review | 2020-07-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-07-27 | Submittal Number: 12 63 26-1.0 From: NATE WEINGART Final Due Date: 07/24/20 Subject: FIXED SEATING FABRIC SAMPLES Description: Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 09268 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2020-07-20 | Submittal Number: 12 63 26-1.0 From: NATE WEINGART Final Due Date: 07/24/20 Subject: FIXED SEATING FABRIC SAMPLES Description: Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 09694 | Responded and Closed | Approved as Noted | 2020-07-30 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 126326-1.0 Fixed Seating Fabric Samples (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 126326-1.0 Fixed Seating Fabric Samples (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-07-30 |  | 126326-1.0 Fixed Seating Fabric Samples (MAM Review)-POP.pdf
12 63 26-002-00 | 12 63 26 - ARENA SEATS | 12 63 26-002-00 Fixed Seating Initial Layouts | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-13 | Responded and Closed - Rejected |  | Todd Spangler (Populous), Josh Dobken (Populous) |  |  |  | 2020-07-27 | 2020-07-30 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-07-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06924 | Received | For Review | 2020-07-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-07-27 | Submittal Number: 12 63 26-2.0 From: NATE WEINGART Final Due Date: 07/24/20 Subject: FIXED SEATING INITIAL LAYOUTS Description: Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 09267 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2020-07-20 | Submittal Number: 12 63 26-2.0 From: NATE WEINGART Final Due Date: 07/24/20 Subject: FIXED SEATING INITIAL LAYOUTS Description: Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 09695 | Responded and Closed | Rejected | 2020-07-30 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 126326-2.0 Fixed Seating Initial Layouts (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 126326-2.0 Fixed Seating Initial Layouts (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-07-30 |  | 126326-2.0 Fixed Seating Initial Layouts (MAM Review)-POP.pdf
12 63 26-002-01 | 12 63 26 - ARENA SEATS | 12 63 26-002-01 Fixed Seating Initial Layout Resubmittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-31 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-14 | 2020-08-11 | 12 |  | Record Copies; Transfers; Submittals | 12 63 26-002-01-01 - 12 63 26-002-01 Fixed Seating Initial Layout Resubmittal | 12 |  | 2020-08-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07296 | Received | For Review | 2020-07-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-08-14 | Submittal Number: 12 63 26-2.1 From: NATE WEINGART Final Due Date: 08/14/20 Subject: FIXED SEATING INITIAL LAYOUT RESUBMITTAL Description: Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 09717 | Forwarded | For Review | 2020-07-31 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-07 | Submittal Number: 12 63 26-2.1 From: NATE WEINGART Final Due Date: 08/14/20 Subject: FIXED SEATING INITIAL LAYOUT RESUBMITTAL Description: Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 10003 | Responded and Closed | Revise and Resubmit | 2020-08-11 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-31 |  | 126326-2.1 Fixed Seating Initial Layout Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-31 |  | 126326-2.1 Fixed Seating Initial Layout Resubmittal (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-08-11 |  | 126326-2.1 Fixed Seating Initial Layout Resubmittal (MAM Review)-POP.pdf
12 63 26-002-01-01 | 12 63 26 - ARENA SEATS | 12 63 26-002-01 Fixed Seating Initial Layout Resubmittal | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 12 63 26-002-01 - 12 63 26-002-01 Fixed Seating Initial Layout Resubmittal | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-11 |  | 126326-2.1 Fixed Seating Initial Layout Resubmittal (MAM Review)-POP.pdf
12 63 26-003-00 | 12 63 26 - ARENA SEATS | 12 63 26-003-00 ARENA SEATS - Upper Bowl and Suite Layout and Manifests | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-28 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-14 07:00 | 2020-09-18 | 22 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-09-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07806 | Received | For Review | 2020-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (M.A. Mortenson Company) | 2020-09-14 07:00 | Submittal Number: 12 63 26-3.0 From: TYLER KREN Final Due Date: 09/11/20 Subject: ARENA SEATS - UPPER BOWL AND SUITE LAYOUT AND MANIFESTS Description: SHOP DRAWINGS AND MANIFESTS FOR THE UPPER BOWL AND SUITE SECTIONS Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 10384 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-03 | Submittal Number: 12 63 26-3.0 From: TYLER KREN Final Due Date: 09/11/20 Subject: ARENA SEATS - UPPER BOWL AND SUITE LAYOUT AND MANIFESTS Description: SHOP DRAWINGS AND MANIFESTS FOR THE UPPER BOWL AND SUITE SECTIONS Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 10895 | Responded and Closed | Approved as Noted | 2020-09-18 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 12 63 26 - 3 Arena Seats - Upper Bowl and Suite Layout And Manifests.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-27 |  | 12 63 26 - 3 Arena Seats - Upper Bowl and Suite Layout And Manifests.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-09-18 |  | 12 63 26 - 3 Arena Seats - Upper Bowl and Suite Layout And Manifests-POP.pdf
12 63 26-004-00 | 12 63 26 - ARENA SEATS | 12 63 26-004-00 ARENA SEATS - Shop Drawings - Lower + Upper Bowl + Manifest | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-18 | 2021-01-14 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10385 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (M.A. Mortenson Company) | 2021-01-18 | Submittal Number: 12 63 26-4.0 From: TYLER KREN Final Due Date: 01/12/21 Subject: ARENA SEATS - SHOP DRAWINGS - LOWER + UPPER BOWL + MANIFEST Description: SHOP DRAWINGS: PROVIDE THE FOLLOWING DRAWINGS A. COMPLETE SEATING BOWL WITH TREAD AND RISER MOUNTING DETAILS AND AISLE LOCATIONS 1) SHOW JOINTS BETWEEN PRECAST TREADS AND RISERS AND ATTACHMENTS. 2) SHOW LOCATIONS OF WHEELCHAIR COMPANION SEATING. 3) SHOW EASY ACCESS CHAIRS. B. END STANDARD DESIGN WITH LOGO. C. HINGED ARMREST FOR EASY-ACCESS CHAIR END STANDARDS. D. LOW RISER HEIGHT MOUNTING BRACKET, IF REQUIRED. E. SEAT AND BACK DESIGN. F. SEAT ASSEMBLY. G. SEAT AND ROW IDENTIFICATION GRAPHICS. H. SEAT ATTACHMENT AT UNIQUE CONDITIONS SUCH AS ANGLED CORNERS AND WHERE CHAIRS SPAN ACROSSA CONTROL OR EXPANSION JOINT. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 13569 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-11 | Submittal Number: 12 63 26-4.0 From: TYLER KREN Final Due Date: 01/12/21 Subject: ARENA SEATS - SHOP DRAWINGS - LOWER + UPPER BOWL + MANIFEST Description: SHOP DRAWINGS: PROVIDE THE FOLLOWING DRAWINGS A. COMPLETE SEATING BOWL WITH TREAD AND RISER MOUNTING DETAILS AND AISLE LOCATIONS 1) SHOW JOINTS BETWEEN PRECAST TREADS AND RISERS AND ATTACHMENTS. 2) SHOW LOCATIONS OF WHEELCHAIR COMPANION SEATING. 3) SHOW EASY ACCESS CHAIRS. B. END STANDARD DESIGN WITH LOGO. C. HINGED ARMREST FOR EASY-ACCESS CHAIR END STANDARDS. D. LOW RISER HEIGHT MOUNTING BRACKET, IF REQUIRED. E. SEAT AND BACK DESIGN. F. SEAT ASSEMBLY. G. SEAT AND ROW IDENTIFICATION GRAPHICS. H. SEAT ATTACHMENT AT UNIQUE CONDITIONS SUCH AS ANGLED CORNERS AND WHERE CHAIRS SPAN ACROSSA CONTROL OR EXPANSION JOINT. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 13945 | Responded and Closed | Revise and Resubmit | 2021-01-14 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-29 |  | 126326-4 Arena Seats - Lower Upper Bowl SDs Manifest.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-29 |  | 126326-4 Arena Seats - Lower Upper Bowl SDs Manifest.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-01-14 |  | 126326-4 Arena Seats - Lower Upper Bowl SDs Manifest-POP.pdf
12 63 26-004-01 | 12 63 26 - ARENA SEATS | 12 63 26-004-01 ARENA SEATS - Shop Drawings + Manifest | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-01 | 2021-03-03 | 17 |  | Record Copies; Transfers; Submittals | 12 63 26-004-01-01 - 12 63 26-004-01 ARENA SEATS - Shop Drawings + Manifest | 17 |  | 2021-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11411 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyler Kren (Mortenson Construction) | 2021-03-01 | Submittal Number: 12 63 26-4.1 From: TYLER KREN Final Due Date: 03/01/21 Subject: ARENA SEATS - SHOP DRAWINGS + MANIFEST Description: SHOP DRAWINGS SHOWING LOCATIONS, MEASUREMENTS AND QUANTITIES OF THE CAMATIC FIXED SEATS ON UPPER BOWL, LOWER BOWL AND SUITE LEVEL. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 14778 | Forwarded | For Review | 2021-02-15 | Tyler Kren (Mortenson Construction) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-22 | Submittal Number: 12 63 26-4.1 From: TYLER KREN Final Due Date: 03/01/21 Subject: ARENA SEATS - SHOP DRAWINGS + MANIFEST Description: SHOP DRAWINGS SHOWING LOCATIONS, MEASUREMENTS AND QUANTITIES OF THE CAMATIC FIXED SEATS ON UPPER BOWL, LOWER BOWL AND SUITE LEVEL. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 15256 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-03 | Tyler Kren (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See comments on pdf. Additionally, for all seats that are numbered ( 1 ) that are not located on an aisle, start that seat numbering at 3. Additionally, provide a manifest showing locations of the easy arm chairs. -CLM | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 12 63 26-4.1 Arena Fixed Seating SDs.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-02-15 |  | 12 63 26-4.1 Arena Fixed Seating SDs.pdf
| Responded and Closed |  | Tyler Kren (Mortenson Construction) | 1 | 2021-03-03 |  | 12 63 26-4.1 Arena Fixed Seating SDs-POP.pdf
12 63 26-004-01-01 | 12 63 26 - ARENA SEATS | 12 63 26-004-01 ARENA SEATS - Shop Drawings + Manifest | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 12 63 26-004-01 - 12 63 26-004-01 ARENA SEATS - Shop Drawings + Manifest | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-03 |  | 12 63 26-4.1 Arena Fixed Seating SDs-POP.pdf
12 63 26-004-02 | 12 63 26 - ARENA SEATS | 12 63 26-004-02 ARENA SEATS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-26 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-12 07:00 | 2021-04-26 | 32 |  | Record Copies; Transfers; Submittals |  | 32 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12248 | Received | For Review | 2021-03-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyler Kren (Mortenson Construction) | 2021-04-12 07:00 | Submittal Number: 12 63 26-4.2 From: TYLER KREN Final Due Date: 04/08/21 Subject: ARENA SEATS - SHOP DRAWINGS Description: SHOP DRAWINGS SHOWING LOCATIONS, MEASUREMENTS AND QUANTITIES OF THE CAMATIC FIXED SEATS ON UPPER BOWL, LOWER BOWL AND SUITE LEVEL. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 15848 | Forwarded | For Review | 2021-03-26 | Tyler Kren (Mortenson Construction) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-02 | Submittal Number: 12 63 26-4.2 From: TYLER KREN Final Due Date: 04/08/21 Subject: ARENA SEATS - SHOP DRAWINGS Description: SHOP DRAWINGS SHOWING LOCATIONS, MEASUREMENTS AND QUANTITIES OF THE CAMATIC FIXED SEATS ON UPPER BOWL, LOWER BOWL AND SUITE LEVEL. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 16524 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-26 | Tyler Kren (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-25 |  | 12 63 26 4.2 - Arena Seats Shop Drawings.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-03-25 |  | 12 63 26 4.2 - Arena Seats Shop Drawings.pdf
| Responded and Closed |  | Tyler Kren (Mortenson Construction) | 1 | 2021-04-26 |  | 12 63 26 4.2 - Arena Seats Shop Drawings-POP.pdf
12 63 26-004-03 | 12 63 26 - ARENA SEATS | 12 63 26-004-03 ARENA SEATS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-21 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-07 07:00 | 2021-05-27 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-05-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13220 | Received | For Review | 2021-05-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyler Kren (Mortenson Construction) | 2021-06-07 07:00 | Submittal Number: 12 63 26-4.3 From: TYLER KREN Final Due Date: 06/03/21 Subject: ARENA SEATS - SHOP DRAWINGS Description: SHOP DRAWINGS REVISION WITH UPDATED SEAT COUNTS. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 17110 | Forwarded | For Review | 2021-05-21 | Tyler Kren (Mortenson Construction) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-28 | Submittal Number: 12 63 26-4.3 From: TYLER KREN Final Due Date: 06/03/21 Subject: ARENA SEATS - SHOP DRAWINGS Description: SHOP DRAWINGS REVISION WITH UPDATED SEAT COUNTS. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 17203 | Responded and Closed | Approved | 2021-05-27 | Tyler Kren (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 17403 | Sent | For Information Only | 2021-06-08 | Tyler Kren (Mortenson Construction) | Tyler Kren (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 17404 | Sent | For Information Only | 2021-06-08 | Populous SCA_CCA | Brooke Burcham (Mortenson Construction); Tyler Kren (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-20 |  | 126326-4.3 Arena Seats SDs.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-20 |  | 126326-4.3 Arena Seats SDs.pdf
| Responded and Closed |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-27 |  | 126326-4.3 Arena Seats SDs-POP.pdf
| Sent |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-20 |  | 126326-4.3 Arena Seats SDs.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-05-19 02:00 |  | 126326-4.3 Arena Seats SDs.pdf
12 63 26-007-00 | 12 63 26 - ARENA SEATS | 12 63 26-007-00 ARENA SEATS - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-18 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Geoff Cheong, Chris Minter (Populous) |  |  |  | 2021-01-12 | 2021-01-14 | 28 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2021-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10255 | Received | For Review | 2020-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (M.A. Mortenson Company) | 2021-01-12 | Submittal Number: 12 63 26-7.0 From: TYLER KREN Final Due Date: 01/04/21 Subject: ARENA SEATS - SAMPLES Description: SUBMIT ONE ASSEMBLED ARENA CHAIR IN SELECTED COLOR, ONE CHAIR ONA TUBULAR STEEL ASSEM- BLY, AND ONE EASY ACCESS CHAIR. A. APPROVED CHAIR SAMPLES MAY BE USED AS PART OF THE WORK. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 13410 | Forwarded | For Review | 2020-12-18 | Josh Dobken (Populous) | Todd Spangler (Populous); Geoff Cheong; Chris Minter (Populous) | 2020-12-25 | Submittal Number: 12 63 26-7.0 From: TYLER KREN Final Due Date: 01/04/21 Subject: ARENA SEATS - SAMPLES Description: SUBMIT ONE ASSEMBLED ARENA CHAIR IN SELECTED COLOR, ONE CHAIR ONA TUBULAR STEEL ASSEM- BLY, AND ONE EASY ACCESS CHAIR. A. APPROVED CHAIR SAMPLES MAY BE USED AS PART OF THE WORK. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 13947 | Responded and Closed | Approved as Noted | 2021-01-14 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-18 02:00 |  | 12 63 26 -7 - Sample Forte Highback.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-12-18 02:00 |  | 12 63 26 -7 - Sample Forte Highback.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-01-14 |  | 12 63 26 -7 - Sample Forte Highback-POP.pdf
12 63 26-010-00 | 12 63 26 - ARENA SEATS | 12 63 26-010-00 NHL Home locker room seating layout | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Rejected |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-04-19 | 2021-04-14 | 10 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-04-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12357 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-04-19 | Submittal Number: 12 63 26-10.0 From: TYLER KREN Final Due Date: 04/14/21 Subject: NHL HOME LOCKER ROOM SEATING LAYOUT Description: Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 16014 | Forwarded | For Review | 2021-04-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 12 63 26-10.0 From: TYLER KREN Final Due Date: 04/14/21 Subject: NHL HOME LOCKER ROOM SEATING LAYOUT Description: Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 12595 | Review Response | Rejected | 2021-04-14 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Resubmit with corrected seat quantities. | Info Exchange
| 16312 | Responded and Closed | Rejected | 2021-04-14 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Kelsea Conkright (Populous) Remarks: Resubmit with corrected seat quantities. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 12 63 26 - 10 NHL Locker room Layout.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-01 |  | 12 63 26 - 10 NHL Locker room Layout.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-14 |  | 12 63 26 - 10 NHL Locker room Layout_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-04-01 |  | 12 63 26 - 10 NHL Locker room Layout.pdf
12 63 26-010-01 | 12 63 26 - ARENA SEATS | 12 63 26-010-01 NHL Home locker room seating layout | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-10 | 2021-05-07 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-05-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12766 | Received | For Review | 2021-04-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyler Kren (Mortenson Construction) | 2021-05-10 | Submittal Number: 12 63 26-10.1 From: TYLER KREN Final Due Date: 05/10/21 Subject: NHL HOME LOCKER ROOM SEATING LAYOUT Description: UPDATED WITH CORRECT LAYOUT/SEAT COUNT. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 16501 | Forwarded | For Review | 2021-04-26 | Tyler Kren (Mortenson Construction) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-03 | Submittal Number: 12 63 26-10.1 From: TYLER KREN Final Due Date: 05/10/21 Subject: NHL HOME LOCKER ROOM SEATING LAYOUT Description: UPDATED WITH CORRECT LAYOUT/SEAT COUNT. Spec Section: 12 63 26 - ARENA SEATS Status: OPEN | Info Exchange
| 12981 | Review Response | Approved as Noted | 2021-05-07 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16803 | Responded and Closed | Approved as Noted | 2021-05-07 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-26 |  | 126326-10-NHL home locker room seating layout.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-04-26 |  | 126326-10-NHL home locker room seating layout.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-05-07 |  | 126326-10-NHL home locker room seating layout_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-26 |  | 126326-10-NHL home locker room seating layout.pdf
12 66 13-001-00 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-001-00 Multipurpose Seating Samples - Vinyl | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-22 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Josh Dobken (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2020-07-27 07:00 | 2020-07-30 | 70 |  | Record Copies; Transfers; Submittals |  | 70 |  | 2020-07-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05989 | Received | For Review | 2020-05-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-07-27 07:00 | Submittal Number: 12 66 13-1.0 From: NATE WEINGART Final Due Date: 06/05/20 Subject: MULTIPURPOSE SEATING SAMPLES - VINYL Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 08126 | Forwarded | For Review | 2020-05-22 | Shaina Burris (Populous) | Todd Spangler (Populous); Josh Dobken (Populous) | 2020-05-29 | Submittal Number: 12 66 13-1.0 From: NATE WEINGART Final Due Date: 06/05/20 Subject: MULTIPURPOSE SEATING SAMPLES - VINYL Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 08139 | Forwarded | For Review | 2020-05-22 | Josh Dobken (Populous) | Tom Usher (Populous); Chris Minter (Populous) | 2020-05-29 | Submittal Number: 12 66 13-1.0 From: NATE WEINGART Final Due Date: 06/05/20 Subject: MULTIPURPOSE SEATING SAMPLES - VINYL Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 09680 | Responded and Closed | Approved as Noted | 2020-07-30 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-21 |  | 126613-1.0 Multipurpose Seating Samples - Vinyl (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-21 |  | 126613-1.0 Multipurpose Seating Samples - Vinyl (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-20 02:00 |  | 126613-1.0 Multipurpose Seating Samples - Vinyl (MAM Review).pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-05-21 |  | 126613-1.0 Multipurpose Seating Samples - Vinyl (MAM Review).pdf
12 66 13-003-00 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-003-00 Multipurpose Seating Shop Drawings - East & West | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-09 | 2020-08-26 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07756 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (M.A. Mortenson Company) | 2020-09-09 | Submittal Number: 12 66 13-3.0 From: NATE WEINGART Final Due Date: 09/09/20 Subject: MULTIPURPOSE SEATING SHOP DRAWINGS - EAST & WEST Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 10327 | Forwarded | For Review | 2020-08-26 | Shaina Burris (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-02 | Submittal Number: 12 66 13-3.0 From: NATE WEINGART Final Due Date: 09/09/20 Subject: MULTIPURPOSE SEATING SHOP DRAWINGS - EAST & WEST Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 10354 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-26 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 12 66 13-3 Multipupose Seating SD E&W.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-26 |  | 12 66 13-3 Multipupose Seating SD E&W.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-08-26 |  | 12 66 13-3 Multipupose Seating SD E&W-POP.pdf
12 66 13-003-01 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-003-01 Multipurpose Seating Shop Drawings - East & West | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-11 | Responded and Closed - Approved |  | Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-25 | 2020-09-10 | -1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08037 | Received | For Review | 2020-09-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-25 | Submittal Number: 12 66 13-3.1 From: NATE WEINGART Final Due Date: 09/24/20 Subject: MULTIPURPOSE SEATING SHOP DRAWINGS - EAST & WEST Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 10691 | Forwarded | For Review | 2020-09-10 | Populous SCA_CCA | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-09-17 | Submittal Number: 12 66 13-3.1 From: NATE WEINGART Final Due Date: 09/24/20 Subject: MULTIPURPOSE SEATING SHOP DRAWINGS - EAST & WEST Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 10697 | Responded and Closed | Approved | 2020-09-10 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-10 |  | 12 66 13 3.1 Multipupose Seating SD E&W.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-10 |  | 12 66 13 3.1 Multipupose Seating SD E&W.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-10 |  | 12 66 13 3.1 Multipupose Seating SD E&W-POP.pdf
12 66 13-003-02 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-003-02 Multipurpose Seating - East & West - Response to City Structural Correction Notice | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-28 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-17 | 2020-11-16 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-11-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09058 | Received | For Review | 2020-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-11-17 | Submittal Number: 12 66 13-3.2 From: NATE WEINGART Final Due Date: 11/11/20 Subject: MULTIPURPOSE SEATING - EAST & WEST - RESPONSE TO CITY STRUCTURAL CORRECTION NOTICE Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 11946 | Forwarded | For Review | 2020-10-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-11-04 | Submittal Number: 12 66 13-3.2 From: NATE WEINGART Final Due Date: 11/11/20 Subject: MULTIPURPOSE SEATING - EAST & WEST - RESPONSE TO CITY STRUCTURAL CORRECTION NOTICE Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 12291 | Forwarded | For Review | 2020-11-09 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Chris Minter (Populous); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Tho... | 2020-11-16 | Submittal Number: 12 66 13-3.2 From: NATE WEINGART Final Due Date: 11/11/20 Subject: MULTIPURPOSE SEATING - EAST & WEST - RESPONSE TO CITY STRUCTURAL CORRECTION NOTICE Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 12447 | Responded and Closed | Approved | 2020-11-16 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-28 |  | 12 66 13-3.2 East & West - Response to City Structural Correction Notice (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-28 |  | 12 66 13-3.2 East & West - Response to City Structural Correction Notice (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-27 02:00 |  | 12 66 13-3.2 East & West - Response to City Structural Correction Notice (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-16 |  | 12 66 13-3.2 East & West - Response to City Structural Correction Notice (MAM Review)-POP.pdf
12 66 13-003-03 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-003-03 Multipurpose Seating - East & West - Response to City Structural Correction Notice #2 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-16 | Responded and Closed - Not Required For Review |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2020-12-02 08:00 | 2020-11-17 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-11-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09438 | Received | For Review | 2020-11-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-12-02 08:00 | Submittal Number: 12 66 13-3.3 From: NATE WEINGART Final Due Date: 11/27/20 Subject: MULTIPURPOSE SEATING - EAST & WEST - RESPONSE TO CITY STRUCTURAL CORRECTION NOTICE #2 Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 12446 | Forwarded | For Review | 2020-11-16 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2020-11-23 | Submittal Number: 12 66 13-3.3 From: NATE WEINGART Final Due Date: 11/27/20 Subject: MULTIPURPOSE SEATING - EAST & WEST - RESPONSE TO CITY STRUCTURAL CORRECTION NOTICE #2 Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 12517 | Responded and Closed | Not Required For Review | 2020-11-17 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 12 66 13-3.3 East & West - Correction Notice Response #2 (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 12 66 13-3.3 East & West - Correction Notice Response #2 (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-11-17 |  | 12 66 13-3.3 East & West - Correction Notice Response #2 (MAM Review)-POP.pdf
12 66 13-004-00 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-004-00 Multipurpose Seating - Railing Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-29 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-08-12 | 2020-08-26 | 29 |  | Record Copies; Transfers; Submittals |  | 30 |  | 2020-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07214 | Received | For Review | 2020-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-08-12 | Submittal Number: 12 66 13-4.0 From: NATE WEINGART Final Due Date: 08/12/20 Subject: MULTIPURPOSE SEATING - RAILING SAMPLES Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 09622 | Forwarded | For Review | 2020-07-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-08-04 | Submittal Number: 12 66 13-4.0 From: NATE WEINGART Final Due Date: 08/12/20 Subject: MULTIPURPOSE SEATING - RAILING SAMPLES Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 10355 | Responded and Closed | Approved | 2020-08-26 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-28 |  | 126613-4.0 Multipurpose Seating - Railing Samples (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-28 |  | 126613-4.0 Multipurpose Seating - Railing Samples (MAM Review).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-08-26 |  | 126613-4.0 Multipurpose Seating - Railing Samples (MAM Review)-POP.pdf
12 66 13-005-00 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-005-00 Multipurpose Seating Shop Drawings - North & South | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-15 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-01-29 | 2021-01-15 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-01-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10719 | Received | For Review | 2021-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2021-01-29 | Submittal Number: 12 66 13-5.0 From: NATE WEINGART Final Due Date: 01/15/21 Subject: MULTIPURPOSE SEATING SHOP DRAWINGS - NORTH & SOUTH Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 13944 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-21 | Submittal Number: 12 66 13-5.0 From: NATE WEINGART Final Due Date: 01/15/21 Subject: MULTIPURPOSE SEATING SHOP DRAWINGS - NORTH & SOUTH Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 13975 | Responded and Closed | Approved | 2021-01-15 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | 12 66 13-5.0 Multipurpose Seating Shop Drawings - North & South (MAM Review).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | PACKAGE 2_NORTH SOUTH_CALCULATIONS.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | 12 66 13-5.0 Multipurpose Seating Shop Drawings - North & South (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | PACKAGE 2_NORTH SOUTH_CALCULATIONS.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-01-15 |  | 12 66 13-5.0 Multipurpose Seating Shop Drawings - North & South (MAM Review)-POP.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-01-14 |  | PACKAGE 2_NORTH SOUTH_CALCULATIONS-POP.pdf
12 66 13-005-01 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-005-01 Multipurpose Seating Shop Drawings - North & South - City Response | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-17 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-03-31 | 2021-03-17 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12074 | Received | For Review | 2021-03-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-03-31 | Submittal Number: 12 66 13-5.1 From: TYLER KREN Final Due Date: 03/31/21 Subject: MULTIPURPOSE SEATING SHOP DRAWINGS - NORTH & SOUTH - CITY RESPONSE Description: RESPONSE TO CITY COMMENTS FOR N/S SUBMISSION Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 15628 | Forwarded | For Review | 2021-03-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-03-24 | Submittal Number: 12 66 13-5.1 From: TYLER KREN Final Due Date: 03/31/21 Subject: MULTIPURPOSE SEATING SHOP DRAWINGS - NORTH & SOUTH - CITY RESPONSE Description: RESPONSE TO CITY COMMENTS FOR N/S SUBMISSION Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 15646 | Responded and Closed | Approved as Noted | 2021-03-17 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-16 |  | 12 66 13 -5.1 Multipurpose Seat Shop Drawings - North & South (MAM Review).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-16 |  | PACKAGE 2_NORTH SOUTH_CALCULATIONS_REV1.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-16 |  | PACKAGE 2_NORTH SOUTH_DRAWINGS_REV1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-16 |  | 12 66 13 -5.1 Multipurpose Seat Shop Drawings - North & South (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-16 |  | PACKAGE 2_NORTH SOUTH_CALCULATIONS_REV1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-16 |  | PACKAGE 2_NORTH SOUTH_DRAWINGS_REV1.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-17 |  | 12 66 13 -5.1 Multipurpose Seat Shop Drawings - North & South (MAM Review)-POP.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-16 |  | PACKAGE 2_NORTH SOUTH_CALCULATIONS_REV1.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-16 |  | PACKAGE 2_NORTH SOUTH_DRAWINGS_REV1.pdf
12 66 13-005-02 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-005-02 Multipurpose Seating Shop Drawings - North & South - City Response | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-26 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-06-10 07:00 | 2021-05-28 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-05-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13285 | Received | For Review | 2021-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyler Kren (Mortenson Construction) | 2021-06-10 07:00 | Submittal Number: 12 66 13-5.2 From: TYLER KREN Final Due Date: 06/09/21 Subject: MULTIPURPOSE SEATING SHOP DRAWINGS - NORTH & SOUTH - CITY RESPONSE Description: RESPONSE TO CITY COMMENTS FOR N/S SUBMISSION Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 17187 | Forwarded | For Review | 2021-05-26 | Tyler Kren (Mortenson Construction) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-02 | Submittal Number: 12 66 13-5.2 From: TYLER KREN Final Due Date: 06/09/21 Subject: MULTIPURPOSE SEATING SHOP DRAWINGS - NORTH & SOUTH - CITY RESPONSE Description: RESPONSE TO CITY COMMENTS FOR N/S SUBMISSION Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 17214 | Responded and Closed | Approved | 2021-05-28 | Tyler Kren (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-26 |  | 126613-5.2 N.S Retractable City Resubmission SDs.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-26 |  | 126613-5.2 N.S Retractable City Resubmission SDs.pdf
| Responded and Closed |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-28 |  | 126613-5.2 N.S Retractable City Resubmission SDs-POP.pdf
12 66 13-012-00 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-012-00 Multipurpose Seating- Spanner Deck Detail | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-06 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-20 | 2021-08-19 | 45 |  | Record Copies; Transfers; Submittals |  | 45 |  | 2021-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13780 | Received | For Review | 2021-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-07-20 | Submittal Number: 12 66 13-12.0 From: TYLER KREN Final Due Date: 07/19/21 Subject: MULTIPURPOSE SEATING- SPANNER DECK DETAIL Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 17835 | Forwarded | For Review | 2021-07-06 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-13 | Submittal Number: 12 66 13-12.0 From: TYLER KREN Final Due Date: 07/19/21 Subject: MULTIPURPOSE SEATING- SPANNER DECK DETAIL Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 18606 | Responded and Closed | Approved | 2021-08-19 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-04 |  | 126613-12 SEDA Spanner Deck Detail.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-04 |  | 126613-12 SEDA Spanner Deck Detail.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-08-19 |  | 126613-12 SEDA Spanner Deck Detail-POP.pdf
12 66 13-013-00 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-013-00 Multipurpose Seating- Infill Platform Detail -SE | Open - Overdue | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-13 | Forwarded - For Review |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) | 2021-09-20 | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  | 2021-09-27 |  | 25 |  | Record Copies; Transfers; Submittals |  | 25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14634 | Received | For Review | 2021-09-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-09-27 | Submittal Number: 12 66 13-13.0 From: TYLER KREN Final Due Date: 09/27/21 Subject: MULTIPURPOSE SEATING- INFILL PLATFORM DETAIL -SE Description: SUBMITTAL FOR THE SPANNER DECK PLATFORM THAT IS TO BE INCLUDED ON THE SOUTH END BY S10. Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 18876 | Forwarded | For Review | 2021-09-13 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-20 | Submittal Number: 12 66 13-13.0 From: TYLER KREN Final Due Date: 09/27/21 Subject: MULTIPURPOSE SEATING- INFILL PLATFORM DETAIL -SE Description: SUBMITTAL FOR THE SPANNER DECK PLATFORM THAT IS TO BE INCLUDED ON THE SOUTH END BY S10. Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-13 |  | 126613-13 SEDA infill platform SE Corner.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-13 |  | 126613-13 SEDA infill platform SE Corner.pdf
12 66 13-013-01 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-013-01 Multipurpose Seating- Infill Platform Detail -SE | Open | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-10-06 | Forwarded - For Review |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) | 2021-10-12 | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  | 2021-10-20 |  | 2 |  | Record Copies; Transfers; Submittals |  | 3
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14783 | Received | For Review | 2021-10-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-10-20 | Submittal Number: 12 66 13-13.1 From: TYLER KREN Final Due Date: 10/19/21 Subject: MULTIPURPOSE SEATING- INFILL PLATFORM DETAIL -SE Description: SUBMITTAL FOR THE SPANNER DECK PLATFORM THAT IS TO BE INCLUDED ON THE SOUTH END BY S10. Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 19055 | Forwarded | For Review | 2021-10-05 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-10-12 | Submittal Number: 12 66 13-13.1 From: TYLER KREN Final Due Date: 10/19/21 Subject: MULTIPURPOSE SEATING- INFILL PLATFORM DETAIL -SE Description: SUBMITTAL FOR THE SPANNER DECK PLATFORM THAT IS TO BE INCLUDED ON THE SOUTH END BY S10. Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-10-05 |  | 126613-13.1 - S10 portable platform.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-10-05 |  | 126613-13.1 - S10 portable platform.pdf
12 66 13-014-00 | 12 66 13 - MULTIPURPOSE SEATING | 12 66 13-014-00 SEDA - Gap between stationary dual risers and precast fix | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-03 | Responded and Closed - No Action Taken or Required |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-17 | 2021-09-23 | 52 |  | Record Copies; Transfers; Submittals |  | 53 |  | 2021-09-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14195 | Received | For Review | 2021-08-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-08-17 | Submittal Number: 12 66 13-14.0 From: TYLER KREN Final Due Date: 08/16/21 Subject: SEDA - GAP BETWEEN STATIONARY DUAL RISERS AND PRECAST FIX Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 18349 | Forwarded | For Review | 2021-08-02 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-09 | Submittal Number: 12 66 13-14.0 From: TYLER KREN Final Due Date: 08/16/21 Subject: SEDA - GAP BETWEEN STATIONARY DUAL RISERS AND PRECAST FIX Description: Spec Section: 12 66 13 - MULTIPURPOSE SEATING Status: OPEN | Info Exchange
| 18951 | Responded and Closed | No Action Taken or Required | 2021-09-23 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Tyler Kren (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Received for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-02 |  | 12 66 13-14 Gap between stationary dual risers and precast fix.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-02 |  | 12 66 13-14 Gap between stationary dual risers and precast fix.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-09-23 02:00 |  | 12 66 13-14 Gap between stationary dual risers and precast fix_pop.pdf
12 66 23-001-00 | 12 66 23 - PORTABLE PLATFORMS | 12 66 23-001-00 PORTABLE PLATFORMS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-12 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-05-26 | 2021-05-18 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-05-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13062 | Received | For Review | 2021-05-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyler Kren (Mortenson Construction) | 2021-05-26 | Submittal Number: 12 66 23-1.0 From: TYLER KREN Final Due Date: 05/25/21 Subject: PORTABLE PLATFORMS - SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING LAYOUT OF PORTABLE PLATFORMS WITH SEATING HEIGHTS AND LAYOUTS, ROW SPACING AND RISE, AISLE WIDTHS AND LOCATIONS, OVERALL DIMENSIONS FOR INSTALLED AND STORED UNITS, CONNECTIONS AND RELATIONSHIP TO ADJOINING WORK, ACCESSORIES, TYPES OF MATERIALS, AND FINISHES. Spec Section: 12 66 23 - PORTABLE PLATFORMS Status: OPEN | Info Exchange
| 16898 | Forwarded | For Review | 2021-05-12 | Tyler Kren (Mortenson Construction) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-05-19 | Submittal Number: 12 66 23-1.0 From: TYLER KREN Final Due Date: 05/25/21 Subject: PORTABLE PLATFORMS - SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING LAYOUT OF PORTABLE PLATFORMS WITH SEATING HEIGHTS AND LAYOUTS, ROW SPACING AND RISE, AISLE WIDTHS AND LOCATIONS, OVERALL DIMENSIONS FOR INSTALLED AND STORED UNITS, CONNECTIONS AND RELATIONSHIP TO ADJOINING WORK, ACCESSORIES, TYPES OF MATERIALS, AND FINISHES. Spec Section: 12 66 23 - PORTABLE PLATFORMS Status: OPEN | Info Exchange
| 17017 | Responded and Closed | Approved as Noted | 2021-05-18 | Tyler Kren (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | Section 126623.1 - Portable Platforms.pdf
| Forwarded |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-11 |  | Section 126623.1 - Portable Platforms.pdf
| Responded and Closed |  | Tyler Kren (Mortenson Construction) | 1 | 2021-05-18 |  | Section 126623.1 - Portable Platforms-POP.pdf
12 66 23-001-01 | 12 66 23 - PORTABLE PLATFORMS | 12 66 23-001-01 PORTABLE PLATFORMS - Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-28 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-12 | 2021-06-29 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-06-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13680 | Received | For Review | 2021-06-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-07-12 | Submittal Number: 12 66 23-1.1 From: TYLER KREN Final Due Date: 07/12/21 Subject: PORTABLE PLATFORMS - SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING LAYOUT OF PORTABLE PLATFORMS WITH SEATING HEIGHTS AND LAYOUTS, ROW SPACING AND RISE, AISLE WIDTHS AND LOCATIONS, OVERALL DIMENSIONS FOR INSTALLED AND STORED UNITS, CONNECTIONS AND RELATIONSHIP TO ADJOINING WORK, ACCESSORIES, TYPES OF MATERIALS, AND FINISHES. Spec Section: 12 66 23 - PORTABLE PLATFORMS Status: OPEN | Info Exchange
| 17715 | Forwarded | For Review | 2021-06-28 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-05 | Submittal Number: 12 66 23-1.1 From: TYLER KREN Final Due Date: 07/12/21 Subject: PORTABLE PLATFORMS - SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING LAYOUT OF PORTABLE PLATFORMS WITH SEATING HEIGHTS AND LAYOUTS, ROW SPACING AND RISE, AISLE WIDTHS AND LOCATIONS, OVERALL DIMENSIONS FOR INSTALLED AND STORED UNITS, CONNECTIONS AND RELATIONSHIP TO ADJOINING WORK, ACCESSORIES, TYPES OF MATERIALS, AND FINISHES. Spec Section: 12 66 23 - PORTABLE PLATFORMS Status: OPEN | Info Exchange
| 17749 | Responded and Closed | Approved | 2021-06-29 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-28 |  | 126623-1.1 Portable platforms SDs.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-28 |  | Seda - Climate Pledge Arena - 56456 - Calc_rev0_STAMPED.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-28 |  | 126623-1.1 Portable platforms SDs.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-28 |  | Seda - Climate Pledge Arena - 56456 - Calc_rev0_STAMPED.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-06-29 |  | 126623-1.1 Portable platforms SDs-POP.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-06-28 |  | Seda - Climate Pledge Arena - 56456 - Calc_rev0_STAMPED.pdf
12 66 23-001-02 | 12 66 23 - PORTABLE PLATFORMS | 12 66 23-001-02 PORTABLE PLATFORMS - Shop Drawings - Ramps | Open - Overdue | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-08 | Forwarded - For Review |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) | 2021-09-15 | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  | 2021-09-22 |  | 30 |  | Record Copies; Transfers; Submittals |  | 30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14597 | Received | For Review | 2021-09-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyler Kren (Mortenson Construction) | 2021-09-22 | Submittal Number: 12 66 23-1.2 From: TYLER KREN Final Due Date: 09/22/21 Subject: PORTABLE PLATFORMS - SHOP DRAWINGS - RAMPS Description: SHOP DRAWINGS FOR THE RAMPS Spec Section: 12 66 23 - PORTABLE PLATFORMS Status: OPEN | Info Exchange
| 18817 | Forwarded | For Review | 2021-09-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-15 | Submittal Number: 12 66 23-1.2 From: TYLER KREN Final Due Date: 09/22/21 Subject: PORTABLE PLATFORMS - SHOP DRAWINGS - RAMPS Description: SHOP DRAWINGS FOR THE RAMPS Spec Section: 12 66 23 - PORTABLE PLATFORMS Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-08 |  | 12 66 23 -1.2 Portable Platform - Ramp Submittal.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-08 |  | 56456-SUBMITTAL REV A - AS BUILT_STAMPED.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-08 |  | 12 66 23 -1.2 Portable Platform - Ramp Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-08 |  | 56456-SUBMITTAL REV A - AS BUILT_STAMPED.pdf
12 93 00-006-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-006-00 SITE FURNISHINGS - Vine Trellis Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-22 | 2021-02-19 | 12 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-02-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11277 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-02-22 | Submittal Number: 12 93 00-6.0 From: CHRISTIAN GENEROSA Final Due Date: 03/03/21 Subject: SITE FURNISHINGS - VINE TRELLIS SHOP DRAWINGS Description: VINE TRELLIS SHOP DRAWINGS: - A. PROVIDE DETAILS OF CONSTRUCTION AND INSTALLATION. INCLUDE MATERIALS, DIMENSIONS, AND METHODS OF JOINING, FASTENING, AND ANCHORING. B. OBTAIN APPROVAL FOR MINOR VARIATIONS IN DETAIL FOR THE PURPOSE OF IMPROVING FABRICATION AND INSTALLATION PROCEDURES, BUT NOT AFFECTING GENERAL DESIGN FOR STRUCTURAL STABILITY OR SIZE. C. INCLUDE SHOP DRAWINGS FOR ALL CANDIDATES SUBMITTED FOR EQUIVALENCY STATUS TO SPECIFIED PRODUCTS. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14609 | Forwarded | For Review | 2021-02-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-15 | Submittal Number: 12 93 00-6.0 From: CHRISTIAN GENEROSA Final Due Date: 03/03/21 Subject: SITE FURNISHINGS - VINE TRELLIS SHOP DRAWINGS Description: VINE TRELLIS SHOP DRAWINGS: - A. PROVIDE DETAILS OF CONSTRUCTION AND INSTALLATION. INCLUDE MATERIALS, DIMENSIONS, AND METHODS OF JOINING, FASTENING, AND ANCHORING. B. OBTAIN APPROVAL FOR MINOR VARIATIONS IN DETAIL FOR THE PURPOSE OF IMPROVING FABRICATION AND INSTALLATION PROCEDURES, BUT NOT AFFECTING GENERAL DESIGN FOR STRUCTURAL STABILITY OR SIZE. C. INCLUDE SHOP DRAWINGS FOR ALL CANDIDATES SUBMITTED FOR EQUIVALENCY STATUS TO SPECIFIED PRODUCTS. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14826 | Forwarded | For Review | 2021-02-15 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-22 | Submittal Number: 12 93 00-6.0 From: CHRISTIAN GENEROSA Final Due Date: 03/03/21 Subject: SITE FURNISHINGS - VINE TRELLIS SHOP DRAWINGS Description: VINE TRELLIS SHOP DRAWINGS: - A. PROVIDE DETAILS OF CONSTRUCTION AND INSTALLATION. INCLUDE MATERIALS, DIMENSIONS, AND METHODS OF JOINING, FASTENING, AND ANCHORING. B. OBTAIN APPROVAL FOR MINOR VARIATIONS IN DETAIL FOR THE PURPOSE OF IMPROVING FABRICATION AND INSTALLATION PROCEDURES, BUT NOT AFFECTING GENERAL DESIGN FOR STRUCTURAL STABILITY OR SIZE. C. INCLUDE SHOP DRAWINGS FOR ALL CANDIDATES SUBMITTED FOR EQUIVALENCY STATUS TO SPECIFIED PRODUCTS. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 11558 | Review Response | Approved | 2021-02-16 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  |  | Info Exchange
| 14978 | Responded and Closed | Approved | 2021-02-19 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-08 |  | 2021-02-08 129300-0006-00 Green Screen Wall Shop Drawings and Product Literature_ MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-08 |  | 2021-02-08 129300-0006-00 Green Screen Wall Shop Drawings and Product Literature_ MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-07 02:00 |  | 2021-02-08 129300-0006-00 Green Screen Wall Shop Drawings and Product Literature_ MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-02-07 02:00 |  | 2021-02-08 129300-0006-00 Green Screen Wall Shop Drawings and Product Literature_ MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-19 02:00 |  | 129300-006-00 Green Screen Wall PD_ MAM - SWIFT_POP.pdf
12 93 00-009-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-009-00 Steel Planter Walls - Shop Drawings | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-17 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-03 | 2021-02-24 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11511 | Received | For Review | 2021-02-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-03 | Submittal Number: 12 93 00-9.0 From: CHRISTIAN GENEROSA Final Due Date: 02/16/21 Subject: STEEL PLANTER WALLS - SHOP DRAWINGS Description: SUBMIT LITERATURE IDENTIFYING ALL MATERIALS INCLUDED IN THE FINISHED PRODUCT PRIOR TO FABRICATION C. STEEL PLANTER WALL SHOP DRAWINGS: PROVIDE DETAILS OF CONSTRUCTION AND INSTALLATION INCLUDING MATERIALS, DIMENSIONS, METHODS OF JOINING, FASTENINGS, AND ANCHORING FOR ALL FABRICATED ITEMS. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14905 | Forwarded | For Review | 2021-02-17 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-24 | Submittal Number: 12 93 00-9.0 From: CHRISTIAN GENEROSA Final Due Date: 02/16/21 Subject: STEEL PLANTER WALLS - SHOP DRAWINGS Description: SUBMIT LITERATURE IDENTIFYING ALL MATERIALS INCLUDED IN THE FINISHED PRODUCT PRIOR TO FABRICATION C. STEEL PLANTER WALL SHOP DRAWINGS: PROVIDE DETAILS OF CONSTRUCTION AND INSTALLATION INCLUDING MATERIALS, DIMENSIONS, METHODS OF JOINING, FASTENINGS, AND ANCHORING FOR ALL FABRICATED ITEMS. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 11631 | Review Response | Approved as Noted | 2021-02-24 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | See notes. Provide swatches for final color approval. | Info Exchange
| 15079 | Responded and Closed | Approved as Noted | 2021-02-24 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See notes. Provide swatches for final color approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-17 |  | 2021-02-1 129300-0009-00 Steel Planter Wall Shop Drawings_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-17 |  | 2021-02-1 129300-0009-00 Steel Planter Wall Shop Drawings_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-02-16 02:00 |  | 2021-02-1 129300-0009-00 Steel Planter Wall Shop Drawings_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-24 02:00 |  | 129300-009-00 Steel Planter Wall Shop Drawings_MAM - SWIFT_POP.pdf
12 93 00-011-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-011-00 Skate Deterrents - Shop Drawings | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-21 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-01-13 | 2021-01-11 | 22 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10287 | Received | For Review | 2020-12-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-01-13 | Submittal Number: 12 93 00-11.0 From: CHRISTIAN GENEROSA Final Due Date: 01/05/21 Subject: SKATE DETERRENTS - SHOP DRAWINGS Description: SHOP DRAWINGS: PROVIDE DETAILS OF CONSTRUCTION AND INSTALLATION INCLUDING MATERIALS, DIMENSIONS, METHODS OF JOINING, FASTENINGS AND ANCHORING FOR ALL FABRICATED ITEMS: A. OBTAIN APPROVAL FOR MINOR VARIATIONS IN DETAIL FOR THE PURPOSE OF IMPROVING FABRICATIONAND INSTALLATION PROCEDURES, BUT NOT AFFECTING GENERAL DESIGN FOR STRUCTURAL STABILITY OR SIZE. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 13444 | Forwarded | For Review | 2020-12-21 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Submittal Number: 12 93 00-11.0 From: CHRISTIAN GENEROSA Final Due Date: 01/05/21 Subject: SKATE DETERRENTS - SHOP DRAWINGS Description: SHOP DRAWINGS: PROVIDE DETAILS OF CONSTRUCTION AND INSTALLATION INCLUDING MATERIALS, DIMENSIONS, METHODS OF JOINING, FASTENINGS AND ANCHORING FOR ALL FABRICATED ITEMS: A. OBTAIN APPROVAL FOR MINOR VARIATIONS IN DETAIL FOR THE PURPOSE OF IMPROVING FABRICATIONAND INSTALLATION PROCEDURES, BUT NOT AFFECTING GENERAL DESIGN FOR STRUCTURAL STABILITY OR SIZE. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 13456 | Forwarded | For Review | 2020-12-22 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-12-29 | Submittal Number: 12 93 00-11.0 From: CHRISTIAN GENEROSA Final Due Date: 01/05/21 Subject: SKATE DETERRENTS - SHOP DRAWINGS Description: SHOP DRAWINGS: PROVIDE DETAILS OF CONSTRUCTION AND INSTALLATION INCLUDING MATERIALS, DIMENSIONS, METHODS OF JOINING, FASTENINGS AND ANCHORING FOR ALL FABRICATED ITEMS: A. OBTAIN APPROVAL FOR MINOR VARIATIONS IN DETAIL FOR THE PURPOSE OF IMPROVING FABRICATIONAND INSTALLATION PROCEDURES, BUT NOT AFFECTING GENERAL DESIGN FOR STRUCTURAL STABILITY OR SIZE. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 10605 | Review Response | Approved as Noted | 2021-01-06 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 13812 | Responded and Closed | Approved as Noted | 2021-01-11 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-21 |  | 2020-12-21 SKATE DETERRENTS Shop Drawings_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-21 |  | 2020-12-21 SKATE DETERRENTS Shop Drawings_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-21 |  | 2020-12-21 SKATE DETERRENTS Shop Drawings_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-12-21 |  | 2020-12-21 SKATE DETERRENTS Shop Drawings_MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-01-11 |  | 2020-12-21 SKATE DETERRENTS Shop Drawings_SWIFT_POP.pdf
12 93 00-012-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-012-00 Precast Bench Mix Design, LEED Product Data - French Grey | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-19 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-02 | 2021-02-04 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10770 | Received | For Review | 2021-01-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-02-02 | Submittal Number: 12 93 00-12.0 From: CHRISTIAN GENEROSA Final Due Date: 01/29/21 Subject: PRECAST BENCH MIX DESIGN, LEED PRODUCT DATA - FRENCH GREY Description: Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14006 | Forwarded | For Review | 2021-01-19 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-26 | Submittal Number: 12 93 00-12.0 From: CHRISTIAN GENEROSA Final Due Date: 01/29/21 Subject: PRECAST BENCH MIX DESIGN, LEED PRODUCT DATA - FRENCH GREY Description: Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14190 | Forwarded | For Review | 2021-01-25 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-02-01 | Submittal Number: 12 93 00-12.0 From: CHRISTIAN GENEROSA Final Due Date: 01/29/21 Subject: PRECAST BENCH MIX DESIGN, LEED PRODUCT DATA - FRENCH GREY Description: Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14216 | Forwarded | For Review | 2021-01-25 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-01 | Submittal Number: 12 93 00-12.0 From: CHRISTIAN GENEROSA Final Due Date: 01/29/21 Subject: PRECAST BENCH MIX DESIGN, LEED PRODUCT DATA - FRENCH GREY Description: Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 11222 | Review Response | Approved | 2021-02-03 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 14523 | Responded and Closed | Approved | 2021-02-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-16 |  | 2021-01-16 Precast Bench Mix Design LEED Product Data_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-16 |  | 2021-01-16 Precast Bench Mix Design LEED Product Data_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-15 02:00 |  | 2021-01-16 Precast Bench Mix Design LEED Product Data_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-15 02:00 |  | 2021-01-16 Precast Bench Mix Design LEED Product Data_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-01-15 |  | 2021-01-16 Precast Bench Mix Design LEED Product Data_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-04 |  | 2021-01-16 Precast Bench Mix Design LEED Product Data_MAM - SWIFT_pop.pdf
12 93 00-013-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-013-00 Skate Deterrent Sample | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-08 | 2021-02-08 | 15 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-02-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10943 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-02-08 | Submittal Number: 12 93 00-13.0 From: CHRISTIAN GENEROSA Final Due Date: 02/08/21 Subject: SKATE DETERRENT SAMPLE Description: SKATE DETERRENTS: ONE (1) FABRICATED UNIT WITH FINISHED EDGES. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14207 | Forwarded | For Review | 2021-01-25 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-01 | Submittal Number: 12 93 00-13.0 From: CHRISTIAN GENEROSA Final Due Date: 02/08/21 Subject: SKATE DETERRENT SAMPLE Description: SKATE DETERRENTS: ONE (1) FABRICATED UNIT WITH FINISHED EDGES. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14217 | Forwarded | For Review | 2021-01-25 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-01 | Submittal Number: 12 93 00-13.0 From: CHRISTIAN GENEROSA Final Due Date: 02/08/21 Subject: SKATE DETERRENT SAMPLE Description: SKATE DETERRENTS: ONE (1) FABRICATED UNIT WITH FINISHED EDGES. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 11274 | Review Response | Approved | 2021-02-01 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  |  | Info Exchange
| 14607 | Responded and Closed | Approved | 2021-02-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 21-01-25 12 93 00-013-0 Skate Deterrent Sample_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-25 |  | 21-01-25 12 93 00-013-0 Skate Deterrent Sample_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-24 02:00 |  | 21-01-25 12 93 00-013-0 Skate Deterrent Sample_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-01-24 02:00 |  | 21-01-25 12 93 00-013-0 Skate Deterrent Sample_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-08 02:00 |  | 21-01-25 12 93 00-013-0 Skate Deterrent Sample_MAM - SWIFT_POP.pdf
12 93 00-014-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-014-00 Custom Wood Bench Tops Shop Drawings | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-18 | 2021-02-15 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11191 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-02-18 | Submittal Number: 12 93 00-14.0 From: CHRISTIAN GENEROSA Final Due Date: 02/18/21 Subject: CUSTOM WOOD BENCH TOPS SHOP DRAWINGS Description: CUSTOM WOOD BENCH TOPS FOR THE PRECAST BENCHES. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14497 | Forwarded | For Review | 2021-02-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-11 | Submittal Number: 12 93 00-14.0 From: CHRISTIAN GENEROSA Final Due Date: 02/18/21 Subject: CUSTOM WOOD BENCH TOPS SHOP DRAWINGS Description: CUSTOM WOOD BENCH TOPS FOR THE PRECAST BENCHES. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14619 | Forwarded | For Review | 2021-02-08 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-15 | Submittal Number: 12 93 00-14.0 From: CHRISTIAN GENEROSA Final Due Date: 02/18/21 Subject: CUSTOM WOOD BENCH TOPS SHOP DRAWINGS Description: CUSTOM WOOD BENCH TOPS FOR THE PRECAST BENCHES. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 11441 | Review Response | Approved as Noted/Resubmit | 2021-02-15 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | Wood dimensions illustrated do not match specified product. please revise and resubmit. | Info Exchange
| 14822 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted/Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Wood dimensions illustrated do not match specified product. please revise and resubmit. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-03 |  | 2021-02-1 129300-0014-00 Custom Wood Benches Shop Drawings_ MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-03 |  | 2021-02-1 129300-0014-00 Custom Wood Benches Shop Drawings_ MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-02 02:00 |  | 2021-02-1 129300-0014-00 Custom Wood Benches Shop Drawings_ MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-02-02 02:00 |  | 2021-02-1 129300-0014-00 Custom Wood Benches Shop Drawings_ MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-15 02:00 |  | 2021-02-1 129300-0014-00 Custom Wood Benches Shop Drawings_ MAM - SWIFT_pop.pdf
12 93 00-014-01 | 12 93 00 - SITE FURNISHINGS | 12 93 00-014-01 Custom Wood Bench Tops Shop Drawings | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-28 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-06-14 07:00 | 2021-06-15 | 19 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13323 | Received | For Review | 2021-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-14 07:00 | Submittal Number: 12 93 00-14.1 From: MICHAEL HENNESSY Final Due Date: 06/11/21 Subject: CUSTOM WOOD BENCH TOPS SHOP DRAWINGS Description: CUSTOM WOOD BENCH TOPS FOR THE PRECAST BENCHES. SUBMITTAL REVISION REFLECTS CHANGES REQUESTED BY MAM ON 2/19/2021. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 17236 | Forwarded | For Review | 2021-06-01 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-08 | Submittal Number: 12 93 00-14.1 From: MICHAEL HENNESSY Final Due Date: 06/11/21 Subject: CUSTOM WOOD BENCH TOPS SHOP DRAWINGS Description: CUSTOM WOOD BENCH TOPS FOR THE PRECAST BENCHES. SUBMITTAL REVISION REFLECTS CHANGES REQUESTED BY MAM ON 2/19/2021. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 17393 | Forwarded | For Review | 2021-06-08 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-14 | Submittal Number: 12 93 00-14.1 From: MICHAEL HENNESSY Final Due Date: 06/11/21 Subject: CUSTOM WOOD BENCH TOPS SHOP DRAWINGS Description: CUSTOM WOOD BENCH TOPS FOR THE PRECAST BENCHES. SUBMITTAL REVISION REFLECTS CHANGES REQUESTED BY MAM ON 2/19/2021. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 13544 | Review Response | Approved | 2021-06-15 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 17524 | Responded and Closed | Approved | 2021-06-15 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-28 |  | 2021-05-28 129300-0014-01 Custom Wood Benches Shop Drawings_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-28 |  | 2021-05-28 129300-0014-01 Custom Wood Benches Shop Drawings_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-27 02:00 |  | 2021-05-28 129300-0014-01 Custom Wood Benches Shop Drawings_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-27 02:00 |  | 2021-05-28 129300-0014-01 Custom Wood Benches Shop Drawings_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-15 02:00 |  | 12 93 00-014-01 Custom Wood Benches Shop Drawings_MAM - SWIFT_POP.pdf
12 93 00-015-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-015-00 Precast Benches Shop Drawings | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-18 | 2021-02-19 | 16 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-02-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11192 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-02-18 | Submittal Number: 12 93 00-15.0 From: CHRISTIAN GENEROSA Final Due Date: 02/18/21 Subject: PRECAST BENCHES SHOP DRAWINGS Description: 12 93 00 PRECAST BENCHES SHOP DRAWINGS. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14498 | Forwarded | For Review | 2021-02-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-02-11 | Submittal Number: 12 93 00-15.0 From: CHRISTIAN GENEROSA Final Due Date: 02/18/21 Subject: PRECAST BENCHES SHOP DRAWINGS Description: 12 93 00 PRECAST BENCHES SHOP DRAWINGS. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14618 | Forwarded | For Review | 2021-02-08 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-15 | Submittal Number: 12 93 00-15.0 From: CHRISTIAN GENEROSA Final Due Date: 02/18/21 Subject: PRECAST BENCHES SHOP DRAWINGS Description: 12 93 00 PRECAST BENCHES SHOP DRAWINGS. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 11444 | Review Response | Approved as Noted/Resubmit | 2021-02-15 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | See comments. Large bench is not current design, see attached for correct. | Info Exchange
| 14825 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted/Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See comments. Large bench is not current design, see attached for correct. | Info Exchange
| 14936 | Reopened | Additional Information | 2021-02-19 10:39 | Bryan Klote (Populous) |  |  | changed disposition
| 14937 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-19 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Approved as Noted/Resubmit - confirm that the holes for the large bench are being properly coordinated with wood top. BK/Populous 02.19.2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-04 |  | 129300-0015-00 Precast Benches Shop Drawings_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-04 |  | 129300-0015-00 Precast Benches Shop Drawings_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-03 02:00 |  | 129300-0015-00 Precast Benches Shop Drawings_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-02-03 02:00 |  | 129300-0015-00 Precast Benches Shop Drawings_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-15 02:00 |  | 129300-0015-00 Precast Benches Shop Drawings_MAM - SWIFT_POP.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-19 |  | 129300-0015-00 Precast Benches Shop Drawings - SWIFT_POP-R1.pdf
12 93 00-015-02 | 12 93 00 - SITE FURNISHINGS | 12 93 00-015-02 Precast Benches Shop Drawings | Closed | Architectural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-09 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-23 | 2021-03-10 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11874 | Received | For Review | 2021-03-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Generosa | 2021-03-23 | Submittal Number: 12 93 00-15.2 From: CHRISTIAN GENEROSA Final Due Date: 03/22/21 Subject: PRECAST BENCHES SHOP DRAWINGS Description: 12 93 00 PRECAST BENCHES SHOP DRAWINGS. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 15390 | Forwarded | For Review | 2021-03-09 | Christian Generosa | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-16 | Submittal Number: 12 93 00-15.2 From: CHRISTIAN GENEROSA Final Due Date: 03/22/21 Subject: PRECAST BENCHES SHOP DRAWINGS Description: 12 93 00 PRECAST BENCHES SHOP DRAWINGS. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 11918 | Review Response | Approved as Noted | 2021-03-09 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Christian Generosa |  |  | Info Exchange
| 15443 | Responded and Closed | Approved as Noted | 2021-03-10 | Christian Generosa | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-08 |  | 129300-0015-02 Precast Benches Shop Drawings_MAM.pdf
| Forwarded |  | Christian Generosa | 1 | 2021-03-08 |  | 129300-0015-02 Precast Benches Shop Drawings_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-08 |  | 129300-0015-02 Precast Benches Shop Drawings_MAM.pdf
| Responded and Closed |  | Christian Generosa | 1 | 2021-03-10 |  | 129300-0015-02 Precast Benches Shop Drawings_MAM - SWIFT_POP.pdf
12 93 00-016-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-016-00 SITE FURNISHINGS - Vine Trellis LEED Product Data | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-02 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-16 | 2021-03-16 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-03-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11739 | Received | For Review | 2021-03-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-16 | Submittal Number: 12 93 00-16.0 From: CHRISTIAN GENEROSA Final Due Date: 03/15/21 Subject: SITE FURNISHINGS - VINE TRELLIS LEED PRODUCT DATA Description: LEED V4 CHART AND PRODUCT DATA Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 15211 | Forwarded | For Review | 2021-03-02 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-09 | Submittal Number: 12 93 00-16.0 From: CHRISTIAN GENEROSA Final Due Date: 03/15/21 Subject: SITE FURNISHINGS - VINE TRELLIS LEED PRODUCT DATA Description: LEED V4 CHART AND PRODUCT DATA Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 12055 | Review Response | Approved | 2021-03-10 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 15611 | Responded and Closed | Approved | 2021-03-16 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-01 |  | 2021-03-01 129300-0016-00 Vine Trellis LEED PD_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-01 |  | 2021-03-01 129300-0016-00 Vine Trellis LEED PD_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-02-28 02:00 |  | 2021-03-01 129300-0016-00 Vine Trellis LEED PD_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-16 02:00 |  | 2021-03-01 129300-0016-00 Vine Trellis LEED PD_MAM_POP.pdf
12 93 00-017-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-017-00 Amphitheater Wood Top Seating Shop Drawings | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved as Noted/Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-29 | 2021-03-24 | 10 |  | Record Copies; Transfers; Submittals | 12 93 00-017-00-01 - 12 93 00-017-00 Amphitheater Wood Top Seating Shop Drawings | 10 |  | 2021-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11989 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-29 | Submittal Number: 12 93 00-17.0 From: CHRISTIAN GENEROSA Final Due Date: 03/29/21 Subject: AMPHITHEATER WOOD TOP SEATING SHOP DRAWINGS Description: WOOD AMPHITHEATER SEATING TOPS PRODUCT DATA. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 15529 | Forwarded | For Review | 2021-03-15 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-22 | Submittal Number: 12 93 00-17.0 From: CHRISTIAN GENEROSA Final Due Date: 03/29/21 Subject: AMPHITHEATER WOOD TOP SEATING SHOP DRAWINGS Description: WOOD AMPHITHEATER SEATING TOPS PRODUCT DATA. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 12230 | Review Response | Approved as Noted/Resubmit | 2021-03-24 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | 1. Submit sample of milled 2x4 wood for final approval of finish and edge treatment. 2. As drawn there is no clear detailing of end condition of board lengths. See attached drawing providing clarification of assumed wood seat assembly. Assumption is 8' standard assembly length. 3. Please provide higher resolution for resubmittal, some linework is not legible at this resolution. | Info Exchange
| 15820 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted/Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: 1. Submit sample of milled 2x4 wood for final approval of finish and edge treatment. 2. As drawn there is no clear detailing of end condition of board lengths. See attached drawing providing clarification of assumed wood seat assembly. Assumption is 8' standard assembly length. 3. Please provide higher resolution for resubmittal, some linework is not legible at this resolution. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-14 |  | 2021-03-14 129300-0017-00 Amphitheater Woodtop SD_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-14 |  | 2021-03-14 129300-0017-00 Amphitheater Woodtop SD_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-13 02:00 |  | 2021-03-14 129300-0017-00 Amphitheater Woodtop SD_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-24 02:00 |  | 129300-017-00 Amphitheater Woodtop SD_MAM - SWIFT_POP.pdf
12 93 00-017-00-01 | 12 93 00 - SITE FURNISHINGS | 12 93 00-017-00 Amphitheater Wood Top Seating Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 12 93 00-017-00 - 12 93 00-017-00 Amphitheater Wood Top Seating Shop Drawings | -1 | 2021-04-07
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-24 02:00 |  | 129300-017-00 Amphitheater Woodtop SD_MAM - SWIFT_POP.pdf
12 93 00-017-01 | 12 93 00 - SITE FURNISHINGS | 12 93 00-017-01 Amphitheater Wood Top Seating Shop Drawings | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-02 | Responded and Closed - Approved as Noted/Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-08-16 | 2021-08-09 | 8 |  | Record Copies; Transfers; Submittals | 12 93 00-017-01-01 - 12 93 00-017-01 Amphitheater Wood Top Seating Shop Drawings | 3 |  | 2021-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14171 | Received | For Review | 2021-08-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-08-16 | Submittal Number: 12 93 00-17.1 From: CHRISTIAN GENEROSA Final Due Date: 08/16/21 Subject: AMPHITHEATER WOOD TOP SEATING SHOP DRAWINGS Description: WOOD AMPHITHEATER SEATING TOPS PRODUCT DATA. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 18322 | Forwarded | For Review | 2021-08-02 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-09 | Submittal Number: 12 93 00-17.1 From: CHRISTIAN GENEROSA Final Due Date: 08/16/21 Subject: AMPHITHEATER WOOD TOP SEATING SHOP DRAWINGS Description: WOOD AMPHITHEATER SEATING TOPS PRODUCT DATA. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14274 | Review Response | Approved as Noted/Resubmit | 2021-08-04 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Changes from last submittal have not been incorporated. Revise to address previous comments. See additional clarifications in attached mark up. | Info Exchange
| 18436 | Responded and Closed | Approved as Noted/Resubmit | 2021-08-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted/Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Changes from last submittal have not been incorporated. Revise to address previous comments. See additional clarifications in attached mark up. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-30 |  | 2021-07-30 129300-0017-01 Amphitheater Woodtop SD_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-30 |  | 2021-07-30 129300-0017-01 Amphitheater Woodtop SD_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-07-29 02:00 |  | 2021-07-30 129300-0017-01 Amphitheater Woodtop SD_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-08-09 02:00 |  | 129300-017-01 Amphitheater Woodtop SD_MAM - SWIFT_POP.pdf
12 93 00-017-01-01 | 12 93 00 - SITE FURNISHINGS | 12 93 00-017-01 Amphitheater Wood Top Seating Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 12 93 00-017-01 - 12 93 00-017-01 Amphitheater Wood Top Seating Shop Drawings | -1 | 2021-08-23
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-09 02:00 |  | 129300-017-01 Amphitheater Woodtop SD_MAM - SWIFT_POP.pdf
12 93 00-017-02 | 12 93 00 - SITE FURNISHINGS | 12 93 00-017-02 Amphitheater Wood Top Seating Shop Drawings | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-30 | Responded and Closed - Approved as Noted/Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Shawn Stankewich (Swift and Company Landscape Arch) |  |  |  | 2021-09-13 | 2021-09-09 | 11 |  | Record Copies; Transfers; Submittals | 12 93 00-017-02-01 - 12 93 00-017-02 Amphitheater Wood Top Seating Shop Drawings | 11 |  | 2021-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14526 | Received | For Review | 2021-08-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-13 | Submittal Number: 12 93 00-17.2 From: CHRISTIAN GENEROSA Final Due Date: 09/13/21 Subject: AMPHITHEATER WOOD TOP SEATING SHOP DRAWINGS Description: WOOD AMPHITHEATER SEATING TOPS PRODUCT DATA. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 18727 | Forwarded | For Review | 2021-08-30 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-09-06 | Submittal Number: 12 93 00-17.2 From: CHRISTIAN GENEROSA Final Due Date: 09/13/21 Subject: AMPHITHEATER WOOD TOP SEATING SHOP DRAWINGS Description: WOOD AMPHITHEATER SEATING TOPS PRODUCT DATA. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 18825 | Forwarded | For Review | 2021-09-08 | Populous SCA_CCA | Shawn Stankewich (Swift and Company Landscape Arch) |  | Submittal Number: 12 93 00-17.2 From: CHRISTIAN GENEROSA Final Due Date: 09/13/21 Subject: AMPHITHEATER WOOD TOP SEATING SHOP DRAWINGS Description: WOOD AMPHITHEATER SEATING TOPS PRODUCT DATA. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 18828 | Responded and Closed | Approved as Noted/Resubmit | 2021-09-09 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa; Colin.Saiz@mortenson.com |  | See attached review from Swift | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-30 02:00 |  | 129300-0017-02 Amphitheater Wood Top Seating SD.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-30 02:00 |  | 129300-0017-02 Amphitheater Wood Top Seating SD.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-30 |  | 129300-0017-02 Amphitheater Wood Top Seating SD.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-09 02:00 |  | 129300-0017-02 Amphitheater Wood Top Seating SD - SWIFT_POP.pdf
12 93 00-017-02-01 | 12 93 00 - SITE FURNISHINGS | 12 93 00-017-02 Amphitheater Wood Top Seating Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 12 93 00-017-02 - 12 93 00-017-02 Amphitheater Wood Top Seating Shop Drawings | -1 | 2021-09-23
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-09 02:00 |  | 129300-0017-02 Amphitheater Wood Top Seating SD - SWIFT_POP.pdf
12 93 00-018-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-018-00 Vine Trellis (Green Screen) Samples | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-04-01 | 2021-03-29 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12098 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-01 | Submittal Number: 12 93 00-18.0 From: CHRISTIAN GENEROSA Final Due Date: 04/01/21 Subject: VINE TRELLIS (GREEN SCREEN) SAMPLES Description: SAMPLES OF ALL SPECIFIED MATERIALS, FASTENERS, AND FINISHES. PRODUCT SAMPLE OF GREEN SCREEN VINE TRELLIS WALL. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 15657 | Forwarded | For Review | 2021-03-18 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-25 | Submittal Number: 12 93 00-18.0 From: CHRISTIAN GENEROSA Final Due Date: 04/01/21 Subject: VINE TRELLIS (GREEN SCREEN) SAMPLES Description: SAMPLES OF ALL SPECIFIED MATERIALS, FASTENERS, AND FINISHES. PRODUCT SAMPLE OF GREEN SCREEN VINE TRELLIS WALL. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 12298 | Review Response | Approved as Noted | 2021-03-29 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 15928 | Responded and Closed | Approved as Noted | 2021-03-29 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-18 |  | 2021-03-18 Vine Trellis (Green Screen) Samples_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-18 |  | 2021-03-18 Vine Trellis (Green Screen) Samples_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-17 02:00 |  | 2021-03-18 Vine Trellis (Green Screen) Samples_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-29 02:00 |  | 12 93 00-018-00 Vine Trellis Samples_MAM_ SWIFT_POP.pdf
12 93 00-019-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-019-00 Vine Trellis - Green Screen Shop Drawings | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-10 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-05-24 | 2021-06-07 | 29 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12993 | Received | For Review | 2021-05-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-24 | Submittal Number: 12 93 00-19.0 From: CHRISTIAN GENEROSA Final Due Date: 05/24/21 Subject: VINE TRELLIS - GREEN SCREEN SHOP DRAWINGS Description: VINE TRELLIS SHOP DRAWINGS Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 16816 | Forwarded | For Review | 2021-05-10 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-05-17 | Submittal Number: 12 93 00-19.0 From: CHRISTIAN GENEROSA Final Due Date: 05/24/21 Subject: VINE TRELLIS - GREEN SCREEN SHOP DRAWINGS Description: VINE TRELLIS SHOP DRAWINGS Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 13437 | Review Response | Approved as Noted | 2021-06-04 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 17377 | Responded and Closed | Approved as Noted | 2021-06-07 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 2021-05-08 129300-0019-00 Vine Trellis Green Screen SD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-10 |  | 2021-05-08 129300-0019-00 Vine Trellis Green Screen SD_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-09 02:00 |  | 2021-05-08 129300-0019-00 Vine Trellis Green Screen SD_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-07 02:00 |  | 12 93 00-019-00 Vine Trellis Green Screen SD_MAM - SWIFT_POP.pdf
12 93 00-019-01 | 12 93 00 - SITE FURNISHINGS | 12 93 00-019-01 Vine Trellis - Green Screen Shop Drawings | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-02 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-08-16 | 2021-08-09 | 8 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14172 | Received | For Review | 2021-08-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-08-16 | Submittal Number: 12 93 00-19.1 From: CHRISTIAN GENEROSA Final Due Date: 08/16/21 Subject: VINE TRELLIS - GREEN SCREEN SHOP DRAWINGS Description: VINE TRELLIS SHOP DRAWINGS Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 18323 | Forwarded | For Review | 2021-08-02 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-09 | Submittal Number: 12 93 00-19.1 From: CHRISTIAN GENEROSA Final Due Date: 08/16/21 Subject: VINE TRELLIS - GREEN SCREEN SHOP DRAWINGS Description: VINE TRELLIS SHOP DRAWINGS Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14275 | Review Response | Approved as Noted | 2021-08-05 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | No notchout at garage entry screen. Rain sensor will mount on standoff bracket. Review for notchout at garage entry greenscreen only (sheet gs.7). No other content reviewed. Previous submittal was returned as "approved as noted." Refer to previous submittal for comments. | Info Exchange
| 18437 | Responded and Closed | Approved as Noted | 2021-08-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: No notchout at garage entry screen. Rain sensor will mount on standoff bracket. Review for notchout at garage entry greenscreen only (sheet gs.7). No other content reviewed. Previous submittal was returned as "approved as noted." Refer to previous submittal for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-01 |  | 12 93 00-0019-01 Vine Trellis Green Screen SD_MAM Revisions.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-01 |  | 12 93 00-0019-01 Vine Trellis Green Screen SD_MAM Revisions.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-07-31 02:00 |  | 12 93 00-0019-01 Vine Trellis Green Screen SD_MAM Revisions.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-08-09 02:00 |  | 12 93 00-0019-01 Vine Trellis Green Screen SD_MAM Revisions - SWIFT_POP.pdf
12 93 00-020-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-020-00 Steel Planter Wall and Wood Tops for Bench Seating LEED Product Data | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-26 | Responded and Closed - Revise and Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-06-10 07:00 | 2021-07-02 | 38 |  | Record Copies; Transfers; Submittals | 12 93 00-020-00-01 - 12 93 00-020-00 Steel Planter Wall and Wood Tops for Bench Seating LEED Product Data | 37 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13274 | Received | For Review | 2021-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-10 07:00 | Submittal Number: 12 93 00-20.0 From: CHRISTIAN GENEROSA Final Due Date: 06/09/21 Subject: STEEL PLANTER WALL AND WOOD TOPS FOR BENCH SEATING LEED PRODUCT DATA Description: LEEDV4 FORM SUBMITTAL FOR BOTH THE STEEL PLANTER WALLS AND WOOD TOPS FOR THE BENCH SEATING. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 17179 | Forwarded | For Review | 2021-05-26 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-02 | Submittal Number: 12 93 00-20.0 From: CHRISTIAN GENEROSA Final Due Date: 06/09/21 Subject: STEEL PLANTER WALL AND WOOD TOPS FOR BENCH SEATING LEED PRODUCT DATA Description: LEEDV4 FORM SUBMITTAL FOR BOTH THE STEEL PLANTER WALLS AND WOOD TOPS FOR THE BENCH SEATING. Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 13770 | Review Response | Revise and Resubmit | 2021-07-01 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | See comments in pdf. | Info Exchange
| 17821 | Responded and Closed | Revise and Resubmit | 2021-07-02 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Revise and Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See comments in pdf. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-26 |  | 2021-05-26 129300-0020-00 Steel Planter and Wood Top LEEDv4_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-26 |  | 2021-05-26 129300-0020-00 Steel Planter and Wood Top LEEDv4_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-26 |  | 2021-05-26 129300-0020-00 Steel Planter and Wood Top LEEDv4_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-02 |  | 2021-05-26 129300-0020-00 Steel Planter and Wood Top LEEDv4_MAM-SWIFT_POP.pdf
12 93 00-020-00-01 | 12 93 00 - SITE FURNISHINGS | 12 93 00-020-00 Steel Planter Wall and Wood Tops for Bench Seating LEED Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 12 93 00-020-00 - 12 93 00-020-00 Steel Planter Wall and Wood Tops for Bench Seating LEED Product Data | -1 | 2021-07-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-02 |  | 2021-05-26 129300-0020-00 Steel Planter and Wood Top LEEDv4_MAM-SWIFT_POP.pdf
12 93 00-021-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-021-00 Steel Planter Wall PPG Product Data and Color Sample | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-09 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-08-23 | 2021-08-19 | 11 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14262 | Received | For Review | 2021-08-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-08-23 | Submittal Number: 12 93 00-21.0 From: CHRISTIAN GENEROSA Final Due Date: 08/23/21 Subject: STEEL PLANTER WALL PPG PRODUCT DATA AND COLOR SAMPLE Description: Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 18424 | Forwarded | For Review | 2021-08-09 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-16 | Submittal Number: 12 93 00-21.0 From: CHRISTIAN GENEROSA Final Due Date: 08/23/21 Subject: STEEL PLANTER WALL PPG PRODUCT DATA AND COLOR SAMPLE Description: Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14408 | Review Response | Approved | 2021-08-18 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 18598 | Responded and Closed | Approved | 2021-08-19 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-09 |  | 12 93 00-0021-00 Steel Planter Wall Product Data and Color Sample_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-09 |  | 12 93 00-0021-00 Steel Planter Wall Product Data and Color Sample_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-08-09 |  | 12 93 00-0021-00 Steel Planter Wall Product Data and Color Sample_MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-08-19 |  | 12 93 00-0021-00 Steel Planter Wall Product Data and Color Sample_MAM - SWIFT_POP.pdf
12 93 00-022-00 | 12 93 00 - SITE FURNISHINGS | 12 93 00-022-00 Trench Grate at Soil Cells (Product Data) | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-16 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-08-30 | 2021-08-26 | 11 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14385 | Received | For Review | 2021-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-08-30 | Submittal Number: 12 93 00-22.0 From: JAMIE ELROD Final Due Date: 08/30/21 Subject: TRENCH GRATE AT SOIL CELLS (PRODUCT DATA) Description: Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 18561 | Forwarded | For Review | 2021-08-16 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-23 | Submittal Number: 12 93 00-22.0 From: JAMIE ELROD Final Due Date: 08/30/21 Subject: TRENCH GRATE AT SOIL CELLS (PRODUCT DATA) Description: Spec Section: 12 93 00 - SITE FURNISHINGS Status: OPEN | Info Exchange
| 14499 | Review Response | Approved as Noted | 2021-08-25 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 18693 | Responded and Closed | Approved as Noted | 2021-08-26 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-16 |  | 12 93 00-0022-00 Trench Grate at Soil Cells_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-16 |  | 12 93 00-0022-00 Trench Grate at Soil Cells_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-08-15 02:00 |  | 12 93 00-0022-00 Trench Grate at Soil Cells_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-26 02:00 |  | 12 93 00-0022-00 Trench Grate at Soil Cells_MAM - SWIFT_POP.pdf
12 93 13-001-00 | 12 93 13 | 12 93 13-001-00 Bicycle Rack Product Data, Installation Instructions | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-14 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-01-06 | 2020-12-27 | 14 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-12-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10124 | Received | For Review | 2020-12-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-01-06 | Submittal Number: 12 93 13-1.0 From: CHRISTIAN GENEROSA Final Due Date: 12/28/20 Subject: BICYCLE RACK PRODUCT DATA, INSTALLATION INSTRUCTIONS Description: ALL SPECIFICATION REQUIREMENTS SHOWN ON DRAWINGS ONLY: (DRAWING LEGEND #19) 4/L8-002 BIKE RACK, MODEL "TOFINO" CANE DETECTABLE (2) BIKE, STAINLESS STEEL BEAD BLAST, SURFACE, MOUNTING RAILS, AND MOUNTING HARDWARE. Spec Section: 12 93 13 - BICYCLE RACKS Status: OPEN | Info Exchange
| 13233 | Forwarded | For Review | 2020-12-14 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-12-21 | Submittal Number: 12 93 13-1.0 From: CHRISTIAN GENEROSA Final Due Date: 12/28/20 Subject: BICYCLE RACK PRODUCT DATA, INSTALLATION INSTRUCTIONS Description: ALL SPECIFICATION REQUIREMENTS SHOWN ON DRAWINGS ONLY: (DRAWING LEGEND #19) 4/L8-002 BIKE RACK, MODEL "TOFINO" CANE DETECTABLE (2) BIKE, STAINLESS STEEL BEAD BLAST, SURFACE, MOUNTING RAILS, AND MOUNTING HARDWARE. Spec Section: 12 93 13 - BICYCLE RACKS Status: OPEN | Info Exchange
| 13319 | Forwarded | For Review | 2020-12-15 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-12-22 | Submittal Number: 12 93 13-1.0 From: CHRISTIAN GENEROSA Final Due Date: 12/28/20 Subject: BICYCLE RACK PRODUCT DATA, INSTALLATION INSTRUCTIONS Description: ALL SPECIFICATION REQUIREMENTS SHOWN ON DRAWINGS ONLY: (DRAWING LEGEND #19) 4/L8-002 BIKE RACK, MODEL "TOFINO" CANE DETECTABLE (2) BIKE, STAINLESS STEEL BEAD BLAST, SURFACE, MOUNTING RAILS, AND MOUNTING HARDWARE. Spec Section: 12 93 13 - BICYCLE RACKS Status: OPEN | Info Exchange
| 10357 | Review Response | Approved | 2020-12-22 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  |  | Info Exchange
| 13530 | Responded and Closed | Approved | 2020-12-27 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-12 |  | 129313 Bike Rack Product Data Installation Instructions_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-12 |  | 129313 Bike Rack Product Data Installation Instructions_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-12-11 02:00 |  | 129313 Bike Rack Product Data Installation Instructions_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-12-11 |  | 129313 Bike Rack Product Data Installation Instructions_MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-12-27 |  | 129313 Bike Rack Product Data Installation Instructions_MAM - SWIFT_POP.pdf
12 93 13-002-00 | 12 93 13 | 12 93 13-002-00 Bicycle Rack LEED Product Data | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-15 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-01 08:00 | 2021-02-04 | 21 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10726 | Received | For Review | 2021-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-02-01 08:00 | Submittal Number: 12 93 13-2.0 From: CHRISTIAN GENEROSA Final Due Date: 01/29/21 Subject: BICYCLE RACK LEED PRODUCT DATA Description: ALL SPECIFICATION REQUIREMENTS SHOWN ON DRAWINGS ONLY: (DRAWING LEGEND #19) 4/L8-002 BIKE RACK, MODEL "TOFINO" CANE DETECTABLE (2) BIKE, STAINLESS STEEL BEAD BLAST, SURFACE, MOUNTING RAILS, AND MOUNTING HARDWARE. LEED PRODUCT DATA SUBMITTAL FORM Spec Section: 12 93 13 - BICYCLE RACKS Status: OPEN | Info Exchange
| 13955 | Forwarded | For Review | 2021-01-15 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-01-22 | Submittal Number: 12 93 13-2.0 From: CHRISTIAN GENEROSA Final Due Date: 01/29/21 Subject: BICYCLE RACK LEED PRODUCT DATA Description: ALL SPECIFICATION REQUIREMENTS SHOWN ON DRAWINGS ONLY: (DRAWING LEGEND #19) 4/L8-002 BIKE RACK, MODEL "TOFINO" CANE DETECTABLE (2) BIKE, STAINLESS STEEL BEAD BLAST, SURFACE, MOUNTING RAILS, AND MOUNTING HARDWARE. LEED PRODUCT DATA SUBMITTAL FORM Spec Section: 12 93 13 - BICYCLE RACKS Status: OPEN | Info Exchange
| 14215 | Forwarded | For Review | 2021-01-25 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-01 | Submittal Number: 12 93 13-2.0 From: CHRISTIAN GENEROSA Final Due Date: 01/29/21 Subject: BICYCLE RACK LEED PRODUCT DATA Description: ALL SPECIFICATION REQUIREMENTS SHOWN ON DRAWINGS ONLY: (DRAWING LEGEND #19) 4/L8-002 BIKE RACK, MODEL "TOFINO" CANE DETECTABLE (2) BIKE, STAINLESS STEEL BEAD BLAST, SURFACE, MOUNTING RAILS, AND MOUNTING HARDWARE. LEED PRODUCT DATA SUBMITTAL FORM Spec Section: 12 93 13 - BICYCLE RACKS Status: OPEN | Info Exchange
| 11221 | Review Response | Approved | 2021-02-03 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 14521 | Responded and Closed | Approved | 2021-02-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | Sportworks - Div 01 81 13 LEEDv4 Product Submittal Form_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | Sportworks - Div 01 81 13 LEEDv4 Product Submittal Form_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-13 02:00 |  | Sportworks - Div 01 81 13 LEEDv4 Product Submittal Form_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-01-13 |  | Sportworks - Div 01 81 13 LEEDv4 Product Submittal Form_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-14 |  | Sportworks - Div 01 81 13 LEEDv4 Product Submittal Form_MAM.pdf
13 10 00-001-00 | 13 10 00 | 13 10 00-001-00 Bollard Shop Drawings | Closed | Structural, Architectural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-27 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-10 | 2021-02-09 | 14 |  | Record Copies; Transfers; Submittals | 13 10 00-001-00-01 - 13 10 00-001-00 Bollard Shop Drawings | 7 |  | 2021-02-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10991 | Received | For Review | 2021-01-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Albers (Mortenson Construction) | 2021-02-10 | Submittal Number: 13 10 00-1.0 From: CHRISTIAN ALBERS Final Due Date: 02/09/21 Subject: BOLLARD SHOP DRAWINGS Description: DESIGN TEAM PLEASE ADVISE ON CLASHES CALLED OUT WITHIN THE DRAWINGS. THESE SHOP DRAWINGS INCLUDE ALL BOLLARDS EXCEPT GARAGE ENTRY BOLLARDS AS THAT IS CURRENTLY BEING COORDINATED. Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 14300 | Forwarded | For Review | 2021-01-27 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2021-02-03 | Submittal Number: 13 10 00-1.0 From: CHRISTIAN ALBERS Final Due Date: 02/09/21 Subject: BOLLARD SHOP DRAWINGS Description: DESIGN TEAM PLEASE ADVISE ON CLASHES CALLED OUT WITHIN THE DRAWINGS. THESE SHOP DRAWINGS INCLUDE ALL BOLLARDS EXCEPT GARAGE ENTRY BOLLARDS AS THAT IS CURRENTLY BEING COORDINATED. Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 11283 | Review Response | Revise and Resubmit | 2021-02-02 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 14453 | Forwarded | For Review | 2021-02-02 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-09 | Submittal Number: 13 10 00-1.0 From: CHRISTIAN ALBERS Final Due Date: 02/09/21 Subject: BOLLARD SHOP DRAWINGS Description: DESIGN TEAM PLEASE ADVISE ON CLASHES CALLED OUT WITHIN THE DRAWINGS. THESE SHOP DRAWINGS INCLUDE ALL BOLLARDS EXCEPT GARAGE ENTRY BOLLARDS AS THAT IS CURRENTLY BEING COORDINATED. Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 14627 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-09 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-26 |  | 13 10 00 - 0001 - Bollard Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-26 |  | 13 10 00 - 0001 - Bollard Shop Drawings.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-26 |  | 13 10 00 - 0001 - Bollard Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-26 |  | 13 10 00 - 0001 - Bollard Shop Drawings.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-02-09 |  | 13 10 00 - 0001 - Bollard Shop Drawings_TT Review_Swift_POP.pdf
13 10 00-001-00-01 | 13 10 00 | 13 10 00-001-00 Bollard Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 13 10 00-001-00 - 13 10 00-001-00 Bollard Shop Drawings | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-09 |  | 13 10 00 - 0001 - Bollard Shop Drawings_TT Review_Swift_POP.pdf
13 10 00-002-00 | 13 10 00 | 13 10 00-002-00 Retractable Garage Entry Bollard Shop Drawings | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-04 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-03-18 | 2021-03-18 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11794 | Received | For Review | 2021-03-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-18 | Submittal Number: 13 10 00-2.0 From: CHRISTIAN ALBERS Final Due Date: 03/18/21 Subject: RETRACTABLE GARAGE ENTRY BOLLARD SHOP DRAWINGS Description: SEE ATTACHED RETRACTABLE BOLLARD SHOP DRAWINGS AND PRODUCT DATA FOR THE GARAGE ENTRY BOLLARDS. Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 15281 | Forwarded | For Review | 2021-03-04 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok... | 2021-03-11 | Submittal Number: 13 10 00-2.0 From: CHRISTIAN ALBERS Final Due Date: 03/18/21 Subject: RETRACTABLE GARAGE ENTRY BOLLARD SHOP DRAWINGS Description: SEE ATTACHED RETRACTABLE BOLLARD SHOP DRAWINGS AND PRODUCT DATA FOR THE GARAGE ENTRY BOLLARDS. Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 11931 | Review Response | Not Required For Review | 2021-03-10 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | Landscape plans to be updated to reflect garage bollard location within ROW. | Info Exchange
| 15458 | Forwarded | For Review | 2021-03-10 | Populous SCA_CCA | Matt Ross (Thornton Tomasetti); Ross Cussen | 2021-03-17 | Submittal Number: 13 10 00-2.0 From: CHRISTIAN ALBERS Final Due Date: 03/18/21 Subject: RETRACTABLE GARAGE ENTRY BOLLARD SHOP DRAWINGS Description: SEE ATTACHED RETRACTABLE BOLLARD SHOP DRAWINGS AND PRODUCT DATA FOR THE GARAGE ENTRY BOLLARDS. Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 12090 | Review Response | Approved as Noted | 2021-03-18 | Matt Ross (Thornton Tomasetti) | Tom Usher (Populous); Populous SCA_CCA |  |  | Info Exchange
| 12089 | Review Response | Approved as Noted | 2021-03-18 | Tom Usher (Populous) | Tom Usher (Populous) |  | Pending response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: See attached submittal for comments | Info Exchange
| 15663 | Responded and Closed | Approved as Noted | 2021-03-18 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-04 |  | 13 10 00-002 -Retractable Garage Entry Bollard Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-04 |  | 13 10 00-002 -Retractable Garage Entry Bollard Shop Drawings.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-04 |  | 13 10 00-002 -Retractable Garage Entry Bollard Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-04 |  | 13 10 00-002 -Retractable Garage Entry Bollard Shop Drawings.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-04 |  | 13 10 00-002 -Retractable Garage Entry Bollard Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-18 |  | 13 10 00-002 -Retractable Garage Entry Bollard Shop Drawings_TT Review_POP.pdf
13 10 00-003-00 | 13 10 00 | 13 10 00-003-00 Bollard Elevations | Closed | Structural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-15 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen, Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-06-29 | 2021-07-01 | 17 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-07-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13520 | Received | For Review | 2021-06-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-06-29 | Submittal Number: 13 10 00-3.0 From: CHRISTIAN ALBERS Final Due Date: 06/28/21 Subject: BOLLARD ELEVATIONS Description: SEE ATTACHED DOCUMENTS DETAILING THE TOP OF FINISH SLAB (FS) AT EACH BOLLARD LOCATION, PLANNED HEIGHT OF BOLLARD IS TO BE 48" ABOVE FS. PLEASE CONFIRM THE FS ELEVATIONS AT EACH BOLLARD ARE CORRECT. Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 17489 | Forwarded | For Review | 2021-06-14 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-06-21 | Submittal Number: 13 10 00-3.0 From: CHRISTIAN ALBERS Final Due Date: 06/28/21 Subject: BOLLARD ELEVATIONS Description: SEE ATTACHED DOCUMENTS DETAILING THE TOP OF FINISH SLAB (FS) AT EACH BOLLARD LOCATION, PLANNED HEIGHT OF BOLLARD IS TO BE 48" ABOVE FS. PLEASE CONFIRM THE FS ELEVATIONS AT EACH BOLLARD ARE CORRECT. Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 17525 | Forwarded | For Review | 2021-06-15 | Christian Albers (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-22 | Submittal Number: 13 10 00-3.0 From: CHRISTIAN ALBERS Final Due Date: 06/28/21 Subject: BOLLARD ELEVATIONS Description: SEE ATTACHED DOCUMENTS DETAILING THE TOP OF FINISH SLAB (FS) AT EACH BOLLARD LOCATION, PLANNED HEIGHT OF BOLLARD IS TO BE 48" ABOVE FS. PLEASE CONFIRM THE FS ELEVATIONS AT EACH BOLLARD ARE CORRECT. Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 17812 | Responded and Closed | Approved as Noted | 2021-07-01 | Christian Albers (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-14 |  | 13 10 00 - 03 - Bollard Elevations.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-14 |  | 13 10 00 - 03 - Bollard Elevations.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-13 02:00 |  | 13 10 00 - 03 - Bollard Elevations.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-07-01 |  | 13 10 00 - 03 - Bollard Elevations-POP.pdf
13 10 00-004-00 | 13 10 00 | 13 10 00-004-00 North Courtyard/Breezeway Bollard Layout | Closed | Landscape, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-23 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-07-07 | 2021-06-29 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-06-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13619 | Received | For Review | 2021-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-07-07 | Submittal Number: 13 10 00-4.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: NORTH COURTYARD/BREEZEWAY BOLLARD LAYOUT Description: Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 17634 | Forwarded | For Review | 2021-06-23 | Christian Albers (Mortenson Construction) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-06-30 | Submittal Number: 13 10 00-4.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: NORTH COURTYARD/BREEZEWAY BOLLARD LAYOUT Description: Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 17655 | Forwarded | For Review | 2021-06-24 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Tom Usher (Populous); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-07-01 | Submittal Number: 13 10 00-4.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: NORTH COURTYARD/BREEZEWAY BOLLARD LAYOUT Description: Spec Section: 13 10 00 - VEHICULAR BARRIERS Status: OPEN | Info Exchange
| 17755 | Responded and Closed | Approved as Noted | 2021-06-29 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-22 |  | 13 10 00 - 04 - North Courtyard Breezeway Bollard Layout.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-22 |  | 13 10 00 - 04 - North Courtyard Breezeway Bollard Layout.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-21 02:00 |  | 13 10 00 - 04 - North Courtyard Breezeway Bollard Layout.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-29 02:00 |  | 13 10 00 - 04 - North Courtyard Breezeway Bollard Layout_POP in progress - SWIFT_POP.pdf
13 10 61-001-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-001-00 ICE RINK REFRIGERATION AND PIPING - Qualification Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-03 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-17 | 2021-06-07 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13363 | Received | For Review | 2021-06-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-06-17 | Submittal Number: 13 10 61-1.0 From: TYRONE THORNTON Final Due Date: 06/16/21 Subject: ICE RINK REFRIGERATION AND PIPING - QUALIFICATION DATA Description: REFRIGERATION INSTALLER SHALL HAVE INSTALLEDA MINIMUM OF 5 ARTIFICIAL ICE RINKS OF 10,000 SEATS OR GREATER USING GLYCOL WITHIN PREVIOUS 10 YEARS TO BE ELIGIBLE TO SUBMITA BID ON THIS WORK. THE REFRIGERATION INSTALLER SHALL HAVE ADEQUATE PERSONNEL AND EQUIPMENT, AND SHALL BE APPROVED BY THE ARCHITECT AND ENGINEER. THE REFRIGERATION INSTALLER SHALL BE ABLE TO SATISFACTORILY SERVICE THE EQUIPMENT AFTER INSTALLATION, AND SHALL PROVIDE 24 HOUR SERVICE FOR 1 YEAR AFTER ACCEPTANCE OF SYSTEM BY OWNER. THE REFRIGERATION INSTALLER SHALL EMPLOY ONLY SKILLED WELDERS, EACH HOLDINGA CURRENTLY ACTIVE CERTIFICATE, DATED WITHIN 12 MONTHS, FROMA RECOGNIZED TESTING ASSOCIATION, INDICATING SATISFACTORY WELDING TEST RESULTS PER THE AMERICAN WELDING OR ASME BOILER AND UNFIRED PRESSURE VESSEL CODE, SECTION IX, WELDING QUALIFICATIONS. RETEST IS REQUIRED IF WELDER HAS NOT PERFORMED WELDING FORA PERIOD OF 90 DAYS. THE REFRIGERATION INSTALLER SHALL EMPLOY LICENSED ELECTRICIANS FOR ELECTRICAL EQUIPMENT INSTALLATION AND POWER WIRING. THE REFRIGERATION INSTALLER SHALL PROVIDE ALL PRODUCT DATA, SHOP DRAWINGS, DESIGNS, DAILY LOGS, RECORD DOCUMENTS AND WARRANTIES. THE REFRIGERATION INSTALLER SHALL FURNISH, INSTALL AND DESIGNA COMPLETE SYSTEM INCLUDING ALL ENGINEERING, SHOP DRAWINGS, SUBMITTALS AND DESIGN WORK, CALCULATIONS, ETC. ALL WORK (E.G. SHOP DRAWINGS, ENGINEERING, CALCULATIONS, DESIGN WORK, ETC.) TO THE EXTENT REQUIRED BY APPLICABLE LAW, SHALL BEAR THE SEAL OF AN ENGINEER PROPERLY REGISTERED IN THE STATE OF WASHINGTON. THE REFRIGERATION INSTALLER SHALL PERFORM ALL WORK TO OBTAIN APPROVAL AND PERMITS OF THE ICE FLOOR SYSTEM DESIGN AND INSTALLED WORK FROM THE LOCAL AND STATE GOVERNING AUTHORITIES AND SHALL ABIDE BY ALL CODE REQUIREMENTS. THE REFRIGERATION INSTALLER SHALL INCLUDE COSTS TO PAY FOR PERMITS AS NECESSARY. CIMCO REFRIGERATION, PACE REFRIGERATION (FORMERLY COMMERCIAL REFRIGERATION) AND ICE BUILDERS ARE APPROVED TO PROVIDE PROPOSALS FOR THIS PROJECT. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 17292 | Forwarded | For Review | 2021-06-02 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-09 | Submittal Number: 13 10 61-1.0 From: TYRONE THORNTON Final Due Date: 06/16/21 Subject: ICE RINK REFRIGERATION AND PIPING - QUALIFICATION DATA Description: REFRIGERATION INSTALLER SHALL HAVE INSTALLEDA MINIMUM OF 5 ARTIFICIAL ICE RINKS OF 10,000 SEATS OR GREATER USING GLYCOL WITHIN PREVIOUS 10 YEARS TO BE ELIGIBLE TO SUBMITA BID ON THIS WORK. THE REFRIGERATION INSTALLER SHALL HAVE ADEQUATE PERSONNEL AND EQUIPMENT, AND SHALL BE APPROVED BY THE ARCHITECT AND ENGINEER. THE REFRIGERATION INSTALLER SHALL BE ABLE TO SATISFACTORILY SERVICE THE EQUIPMENT AFTER INSTALLATION, AND SHALL PROVIDE 24 HOUR SERVICE FOR 1 YEAR AFTER ACCEPTANCE OF SYSTEM BY OWNER. THE REFRIGERATION INSTALLER SHALL EMPLOY ONLY SKILLED WELDERS, EACH HOLDINGA CURRENTLY ACTIVE CERTIFICATE, DATED WITHIN 12 MONTHS, FROMA RECOGNIZED TESTING ASSOCIATION, INDICATING SATISFACTORY WELDING TEST RESULTS PER THE AMERICAN WELDING OR ASME BOILER AND UNFIRED PRESSURE VESSEL CODE, SECTION IX, WELDING QUALIFICATIONS. RETEST IS REQUIRED IF WELDER HAS NOT PERFORMED WELDING FORA PERIOD OF 90 DAYS. THE REFRIGERATION INSTALLER SHALL EMPLOY LICENSED ELECTRICIANS FOR ELECTRICAL EQUIPMENT INSTALLATION AND POWER WIRING. THE REFRIGERATION INSTALLER SHALL PROVIDE ALL PRODUCT DATA, SHOP DRAWINGS, DESIGNS, DAILY LOGS, RECORD DOCUMENTS AND WARRANTIES. THE REFRIGERATION INSTALLER SHALL FURNISH, INSTALL AND DESIGNA COMPLETE SYSTEM INCLUDING ALL ENGINEERING, SHOP DRAWINGS, SUBMITTALS AND DESIGN WORK, CALCULATIONS, ETC. ALL WORK (E.G. SHOP DRAWINGS, ENGINEERING, CALCULATIONS, DESIGN WORK, ETC.) TO THE EXTENT REQUIRED BY APPLICABLE LAW, SHALL BEAR THE SEAL OF AN ENGINEER PROPERLY REGISTERED IN THE STATE OF WASHINGTON. THE REFRIGERATION INSTALLER SHALL PERFORM ALL WORK TO OBTAIN APPROVAL AND PERMITS OF THE ICE FLOOR SYSTEM DESIGN AND INSTALLED WORK FROM THE LOCAL AND STATE GOVERNING AUTHORITIES AND SHALL ABIDE BY ALL CODE REQUIREMENTS. THE REFRIGERATION INSTALLER SHALL INCLUDE COSTS TO PAY FOR PERMITS AS NECESSARY. CIMCO REFRIGERATION, PACE REFRIGERATION (FORMERLY COMMERCIAL REFRIGERATION) AND ICE BUILDERS ARE APPROVED TO PROVIDE PROPOSALS FOR THIS PROJECT. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 13447 | Review Response | Approved | 2021-06-03 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.06.03 | Info Exchange
| 17385 | Responded and Closed | Approved | 2021-06-07 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.06.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-02 |  | 13 10 61 - Ice Builders Qualifications_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-02 |  | 13 10 61 - Ice Builders Qualifications_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-06-01 02:00 |  | 13 10 61 - Ice Builders Qualifications_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-07 02:00 |  | 13 10 61 - Ice Builders Qualifications_ME_POP.pdf
13 10 61-002-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-002-00 ICE RINK REFRIGERATION AND PIPING - Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-05 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-03 | 2020-04-09 | 36 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-04-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04671 | Received | For Review | 2020-03-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-03 | Submittal Number: 13 10 61-2.0 From: JES PELKEY Final Due Date: 04/07/20 Subject: ICE RINK REFRIGERATION AND PIPING - SHOP DRAWINGS Description: PROVIDE 6 COPIES OF SHOP DRAWINGS FOR THE ENTIRE ICE SYSTEM. SHOP DRAWINGS SHALL INCLUDE ALL EQUIPMENT SPECIFICATIONS, ICE FLOOR LAYOUT, PIPING LAYOUT, PIPING SCHEMATIC FLOW DIAGRAMS, MOTOR CONTROL CENTERS, ELECTRICAL POWER DIAGRAMS, CONTROL DIAGRAMS AND WIRING AND DETAILS OF CONSTRUCTION. COMPLETE SHOP DRAWINGS SHALL BE PROVIDED. NO PART OF ICE SYSTEM WILL BE RELEASED FOR CONSTRUCTION UNTIL ENTIRE SUBMITTAL IS ACCEPTED BY ENGINEER. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06776 | Forwarded | For Review | 2020-03-20 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-27 | Submittal Number: 13 10 61-2.0 From: JES PELKEY Final Due Date: 04/07/20 Subject: ICE RINK REFRIGERATION AND PIPING - SHOP DRAWINGS Description: PROVIDE 6 COPIES OF SHOP DRAWINGS FOR THE ENTIRE ICE SYSTEM. SHOP DRAWINGS SHALL INCLUDE ALL EQUIPMENT SPECIFICATIONS, ICE FLOOR LAYOUT, PIPING LAYOUT, PIPING SCHEMATIC FLOW DIAGRAMS, MOTOR CONTROL CENTERS, ELECTRICAL POWER DIAGRAMS, CONTROL DIAGRAMS AND WIRING AND DETAILS OF CONSTRUCTION. COMPLETE SHOP DRAWINGS SHALL BE PROVIDED. NO PART OF ICE SYSTEM WILL BE RELEASED FOR CONSTRUCTION UNTIL ENTIRE SUBMITTAL IS ACCEPTED BY ENGINEER. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 05279 | Review Response | Approved as Noted | 2020-04-09 | Nick Theimer (ME Engineers) | Tom Usher (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.04.09 | Info Exchange
| 07181 | Responded and Closed | Approved as Noted | 2020-04-09 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.04.09 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-05 |  | 13 10 61-2.0 - UG Piping Shop Drawings - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-20 02:00 |  | 13 10 61-2.0 - UG Piping Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-20 02:00 |  | 13 10 61-2.0 - UG Piping Shop Drawings - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-09 02:00 |  | 13 10 61-2.0 - UG Piping Shop Drawings_ME_pop.pdf
13 10 61-003-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-003-00 ICE RINK REFRIGERATION AND PIPING - Warranty | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-01 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-15 | 2021-06-11 | 11 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-06-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13335 | Received | For Review | 2021-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-06-15 | Submittal Number: 13 10 61-3.0 From: TYRONE THORNTON Final Due Date: 06/15/21 Subject: ICE RINK REFRIGERATION AND PIPING - WARRANTY Description: THE CONTRACTOR SHALL WARRANTY ALL PARTS AND LABOR OF THE ICE RINK SYSTEM FORA PERIOD AFTER THE ACCEPTANCE OF THE OWNER AND WHEN THEY HAVE ASSUMED OPERATION OF THE FACILITY. WARRANTY ON EQUIPMENT SHALL BE IN EFFECT FOR THE DURATION OF THE TIME OFFERED BY THE MANUFACTURER OF THE EQUIPMENT. THE CHILLER PACKAGE SHALL HAVE FULL 2 YEAR WARRANTY. THE CONCRETE FLOOR SHALL HAVEA WARRANTY FOR 2 YEARS. THE REFRIGERATION AND RINK PIPING INSTALLER GUARANTEES THAT HE SHALL REPAIR, REPLACE, AND INSTALL ANY OR ALL PARTS, MATERIALS, OR WORKMANSHIP FOUND TO BE DEFECTIVE OR LACKING IN SPECIFIED CAPACITY AS STIPULATED IN FOREGOING SPECIFICATIONS AND/OR SHOWN ON DRAWINGS. GUARANTEE INCLUDES NECESSARY LABOR, AS WELL AS MATERIAL AND REFRIGERANT REQUIRED FOR REPAIR, REPLACEMENT, AND/OR 24 HOUR PER DAY SERVICE FOR A YEAR REFERRED TO ABOVE Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 17254 | Forwarded | For Review | 2021-06-01 | Tyrone Thornton (Mortenson Construction) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-08 | Submittal Number: 13 10 61-3.0 From: TYRONE THORNTON Final Due Date: 06/15/21 Subject: ICE RINK REFRIGERATION AND PIPING - WARRANTY Description: THE CONTRACTOR SHALL WARRANTY ALL PARTS AND LABOR OF THE ICE RINK SYSTEM FORA PERIOD AFTER THE ACCEPTANCE OF THE OWNER AND WHEN THEY HAVE ASSUMED OPERATION OF THE FACILITY. WARRANTY ON EQUIPMENT SHALL BE IN EFFECT FOR THE DURATION OF THE TIME OFFERED BY THE MANUFACTURER OF THE EQUIPMENT. THE CHILLER PACKAGE SHALL HAVE FULL 2 YEAR WARRANTY. THE CONCRETE FLOOR SHALL HAVEA WARRANTY FOR 2 YEARS. THE REFRIGERATION AND RINK PIPING INSTALLER GUARANTEES THAT HE SHALL REPAIR, REPLACE, AND INSTALL ANY OR ALL PARTS, MATERIALS, OR WORKMANSHIP FOUND TO BE DEFECTIVE OR LACKING IN SPECIFIED CAPACITY AS STIPULATED IN FOREGOING SPECIFICATIONS AND/OR SHOWN ON DRAWINGS. GUARANTEE INCLUDES NECESSARY LABOR, AS WELL AS MATERIAL AND REFRIGERANT REQUIRED FOR REPAIR, REPLACEMENT, AND/OR 24 HOUR PER DAY SERVICE FOR A YEAR REFERRED TO ABOVE Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 13446 | Review Response | Approved as Noted/Resubmit | 2021-06-03 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.06.03 | Info Exchange
| 17384 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-07 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.06.03 | Info Exchange
| 17454 | Reopened | Additional Information | 2021-06-11 09:18 | Josh Dobken (Populous) |  |  | Revision to design team response.
| 17456 | Responded and Closed | Approved | 2021-06-11 | Tyrone Thornton (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) |  | Reopened (Additional Information) by: Josh Dobken Remarks: Revision to design team response. Revised to approved per MEE response. | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-01 |  | 13 10 61-3 Ice Rink Refrigeration & Piping Warranty_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-06-01 |  | 13 10 61-3 Ice Rink Refrigeration & Piping Warranty_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-31 02:00 |  | 13 10 61-3 Ice Rink Refrigeration & Piping Warranty_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-07 02:00 |  | 13 10 61-3 Ice Rink Refrigeration & Piping Warranty_ME_POP.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-06-11 02:00 |  | 13 10 61-3 Ice Rink Refrigeration & Piping Warranty_ME_POPv2.pdf
13 10 61-004-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-004-00 UG Pipe Fittings - Sub Floor | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-11 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-25 | 2020-03-17 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04762 | Received | For Review | 2020-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-25 | Submittal Number: 13 10 61-4.0 From: GRETCHEN TOSHACH Final Due Date: 03/24/20 Subject: UG PIPE FITTINGS - SUB FLOOR Description: UG PIPE FITTINGS - SUB FLOOR Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06532 | Forwarded | For Review | 2020-03-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-18 | Submittal Number: 13 10 61-4.0 From: GRETCHEN TOSHACH Final Due Date: 03/24/20 Subject: UG PIPE FITTINGS - SUB FLOOR Description: UG PIPE FITTINGS - SUB FLOOR Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 04899 | Review Response | Approved | 2020-03-17 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.17 | Info Exchange
| 06691 | Responded and Closed | Approved | 2020-03-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 13 10 61-4.0 - UG Pipe and Fittings Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-11 |  | 13 10 61-4.0 - UG Pipe and Fittings Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-10 02:00 |  | 13 10 61-4.0 - UG Pipe and Fittings Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-17 02:00 |  | 13 10 61-4.0 - UG Pipe and Fittings Product Data_ME_POP.pdf
13 10 61-005-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-005-00 UG Conduit | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-05 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-19 | 2020-03-17 | 13 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04672 | Received | For Review | 2020-03-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-19 | Submittal Number: 13 10 61-5.0 From: GRETCHEN TOSHACH Final Due Date: 04/07/20 Subject: UG CONDUIT Description: UNDERGROUND CONDUIT Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06427 | Forwarded | For Review | 2020-03-05 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-12 | Submittal Number: 13 10 61-5.0 From: GRETCHEN TOSHACH Final Due Date: 04/07/20 Subject: UG CONDUIT Description: UNDERGROUND CONDUIT Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 04898 | Review Response | Approved | 2020-03-14 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.14 | Info Exchange
| 06690 | Responded and Closed | Approved | 2020-03-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-05 |  | 13 10 61-5.0 Buried Conduit Product Data - MAM[1].pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-05 |  | 13 10 61-5.0 Buried Conduit Product Data - MAM[1].pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-04 02:00 |  | 13 10 61-5.0 Buried Conduit Product Data - MAM[1].pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-17 02:00 |  | 13 10 61-5.0 Buried Conduit Product Data - MAM-ME_POP.pdf
13 10 61-006-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-006-00 Rink Floor UG Pipe and Fittings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-17 | 2020-03-23 | 21 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04595 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 13 10 61-6.0 From: GRETCHEN TOSHACH Final Due Date: 04/07/20 Subject: RINK FLOOR UG PIPE AND FITTINGS Description: RINK FLOOR UNDERGROUND PIPE AND PIPE FITTINGS Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06333 | Forwarded | For Review | 2020-03-03 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-03-10 | Submittal Number: 13 10 61-6.0 From: GRETCHEN TOSHACH Final Due Date: 04/07/20 Subject: RINK FLOOR UG PIPE AND FITTINGS Description: RINK FLOOR UNDERGROUND PIPE AND PIPE FITTINGS Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06649 | Forwarded | For Review | 2020-03-16 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-17 | Submittal Number: 13 10 61-6.0 From: GRETCHEN TOSHACH Final Due Date: 04/07/20 Subject: RINK FLOOR UG PIPE AND FITTINGS Description: RINK FLOOR UNDERGROUND PIPE AND PIPE FITTINGS Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Email
| 04969 | Review Response | Approved | 2020-03-20 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.19 | Info Exchange
| 06774 | Forwarded | For Review | 2020-03-20 | Josh Dobken (Populous) | Bryan Klote (Populous) | 2020-03-17 | Submittal Number: 13 10 61-6.0 From: GRETCHEN TOSHACH Final Due Date: 04/07/20 Subject: RINK FLOOR UG PIPE AND FITTINGS Description: RINK FLOOR UNDERGROUND PIPE AND PIPE FITTINGS Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06812 | Responded and Closed | Approved | 2020-03-23 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 13 10 61-6.0 RINK FLOOR UG PIPE AND FITTINGS - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 13 10 61-6.0 RINK FLOOR UG PIPE AND FITTINGS - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-01 02:00 |  | 13 10 61-6.0 RINK FLOOR UG PIPE AND FITTINGS - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-19 02:00 |  | 13 10 61-6.0 RINK FLOOR UG PIPE AND FITTINGS_ME.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-01 02:00 |  | 13 10 61-6.0 RINK FLOOR UG PIPE AND FITTINGS - MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-03-02 |  | 13 10 61-6.0 RINK FLOOR UG PIPE AND FITTINGS - MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-03-19 |  | 13 10 61-6.0 RINK FLOOR UG PIPE AND FITTINGS_ME.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-03-23 |  | 13 10 61-6.0 RINK FLOOR UG PIPE AND FITTINGS_ME-POP.pdf
13 10 61-007-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-007-00 Refrigeration System Fluids | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-12 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-26 | 2020-05-14 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-05-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05799 | Received | For Review | 2020-05-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-26 | Submittal Number: 13 10 61-7.0 From: GRETCHEN TOSHACH Final Due Date: 06/09/20 Subject: REFRIGERATION SYSTEM FLUIDS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 07862 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 13 10 61-7.0 From: GRETCHEN TOSHACH Final Due Date: 06/09/20 Subject: REFRIGERATION SYSTEM FLUIDS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 05871 | Review Response | Approved | 2020-05-12 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.12 | Info Exchange
| 07967 | Responded and Closed | Approved | 2020-05-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.12 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 13 10 61-7.0 - Refrigeration System Fluids - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 13 10 61-7.0 - Refrigeration System Fluids - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 13 10 61-7.0 - Refrigeration System Fluids - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-14 02:00 |  | 13 10 61-7.0 - Refrigeration System Fluids_ME_POP.pdf
13 10 61-008-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-008-00 Safety | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-26 07:00 | 2020-05-19 | 9 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05800 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 13 10 61-8.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: SAFETY Description: PRODUCT DATA Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 07863 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-18 | Submittal Number: 13 10 61-8.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: SAFETY Description: PRODUCT DATA Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 07873 | Forwarded | For Review | 2020-05-11 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 13 10 61-8.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: SAFETY Description: PRODUCT DATA Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06123 | Review Response | Approved | 2020-05-14 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.05.14 | Info Exchange
| 08061 | Responded and Closed | Approved | 2020-05-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 13 10 61-8.0 - Signage - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 13 10 61-8.0 - Signage - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-10 02:00 |  | 13 10 61-8.0 - Signage - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 13 10 61-8.0 - Signage - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-19 |  | 13 10 61-8.0 - Signage_ME_POP.pdf
13 10 61-009-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-009-00 Refrigeration Equipment | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-23 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-08 07:00 | 2020-07-06 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06567 | Received | For Review | 2020-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-08 07:00 | Submittal Number: 13 10 61-9.0 From: GRETCHEN TOSHACH Final Due Date: 06/23/20 Subject: REFRIGERATION EQUIPMENT Description: EVAPORATOR AND SURGE DRUM ( SHELL AND TUBE) CONDENSER (SHELL AND TUBE) INTERMEDIATE CONDENSER (PLATE AND FRAME) HIGH PRESSURE AMMONIA RECEIVER RECIPROCATING COMPRESSORS OIL SEPARATORS OIL POT AMMONIA DISPERSION TANK ICE RINK FLOOR PUMPS SUB FLOOR PUMPS CONDENSER PUMPS BRINE HEATER (DEBONDING) COMPRESSION TANK ACCESSORIES Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 08842 | Forwarded | For Review | 2020-06-23 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-30 | Submittal Number: 13 10 61-9.0 From: GRETCHEN TOSHACH Final Due Date: 06/23/20 Subject: REFRIGERATION EQUIPMENT Description: EVAPORATOR AND SURGE DRUM ( SHELL AND TUBE) CONDENSER (SHELL AND TUBE) INTERMEDIATE CONDENSER (PLATE AND FRAME) HIGH PRESSURE AMMONIA RECEIVER RECIPROCATING COMPRESSORS OIL SEPARATORS OIL POT AMMONIA DISPERSION TANK ICE RINK FLOOR PUMPS SUB FLOOR PUMPS CONDENSER PUMPS BRINE HEATER (DEBONDING) COMPRESSION TANK ACCESSORIES Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06790 | Review Response | Approved as Noted/Resubmit | 2020-07-02 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.07.02 | Info Exchange
| 09126 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-06 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-23 |  | 13 10 61-9.0 - Ice Refrigeration Equip - MAM[1].pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-23 |  | 13 10 61-9.0 - Ice Refrigeration Equip - MAM[1].pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-23 |  | 13 10 61-9.0 - Ice Refrigeration Equip - MAM[1].pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-06 |  | 13 10 61-9.0 - Ice Refrigeration Equip_ME_POP.pdf
13 10 61-009-01 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-009-01 Refrigeration Equipment | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-03 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-17 | 2021-06-21 | 19 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-06-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13364 | Received | For Review | 2021-06-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-17 | Submittal Number: 13 10 61-9.1 From: GRETCHEN TOSHACH Final Due Date: 06/16/21 Subject: REFRIGERATION EQUIPMENT Description: EVAPORATOR AND SURGE DRUM ( SHELL AND TUBE) CONDENSER (SHELL AND TUBE) INTERMEDIATE CONDENSER (PLATE AND FRAME) HIGH PRESSURE AMMONIA RECEIVER RECIPROCATING COMPRESSORS OIL SEPARATORS OIL POT AMMONIA DISPERSION TANK ICE RINK FLOOR PUMPS SUB FLOOR PUMPS CONDENSER PUMPS BRINE HEATER (DEBONDING) COMPRESSION TANK ACCESSORIES Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 17293 | Forwarded | For Review | 2021-06-02 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-09 | Submittal Number: 13 10 61-9.1 From: GRETCHEN TOSHACH Final Due Date: 06/16/21 Subject: REFRIGERATION EQUIPMENT Description: EVAPORATOR AND SURGE DRUM ( SHELL AND TUBE) CONDENSER (SHELL AND TUBE) INTERMEDIATE CONDENSER (PLATE AND FRAME) HIGH PRESSURE AMMONIA RECEIVER RECIPROCATING COMPRESSORS OIL SEPARATORS OIL POT AMMONIA DISPERSION TANK ICE RINK FLOOR PUMPS SUB FLOOR PUMPS CONDENSER PUMPS BRINE HEATER (DEBONDING) COMPRESSION TANK ACCESSORIES Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 13583 | Review Response | Approved as Noted | 2021-06-18 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.06.18 | Info Exchange
| 17584 | Responded and Closed | Approved as Noted | 2021-06-21 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.06.18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-02 |  | 131061-9.1 - Refrigeration Equipment - Rev 1_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-02 |  | 131061-9.1 - Refrigeration Equipment - Rev 1_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-06-02 |  | 131061-9.1 - Refrigeration Equipment - Rev 1_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-21 |  | 131061-9.1 - Refrigeration Equipment - Rev 1_ME_POP.pdf
13 10 61-010-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-010-00 Ammonia Valves and Piping | Closed | Architectural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-02 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-16 | 2020-06-18 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06150 | Received | For Review | 2020-06-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-16 | Submittal Number: 13 10 61-10.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: AMMONIA VALVES AND PIPING Description: PIPING AND FITTINGS, VALVE TAGS, PIPE HANGERS, PIPE AND EQUIPMENT MARKERS, PRESSURE RELIEFS, REFRIGERANT STRAINERS, HAND EXPANSION VALVES, CHECK VALVES, REFRIGERANT SOLENOID VALVES, PRESSURE REGULATING VALVE, REPLACEABLE FILTER DRYERS, FLOAT SWITCH, AUTOMATIC EXPANSION VALVE ASSEMBLY, ADJUSTABLE LEVEL CONTROLLER, PRESSURE GAUGES (AMMONIA AND OIL) Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 08318 | Forwarded | For Review | 2020-06-02 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-06-09 | Submittal Number: 13 10 61-10.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: AMMONIA VALVES AND PIPING Description: PIPING AND FITTINGS, VALVE TAGS, PIPE HANGERS, PIPE AND EQUIPMENT MARKERS, PRESSURE RELIEFS, REFRIGERANT STRAINERS, HAND EXPANSION VALVES, CHECK VALVES, REFRIGERANT SOLENOID VALVES, PRESSURE REGULATING VALVE, REPLACEABLE FILTER DRYERS, FLOAT SWITCH, AUTOMATIC EXPANSION VALVE ASSEMBLY, ADJUSTABLE LEVEL CONTROLLER, PRESSURE GAUGES (AMMONIA AND OIL) Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 08610 | Forwarded | For Review | 2020-06-15 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-16 | Submittal Number: 13 10 61-10.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: AMMONIA VALVES AND PIPING Description: PIPING AND FITTINGS, VALVE TAGS, PIPE HANGERS, PIPE AND EQUIPMENT MARKERS, PRESSURE RELIEFS, REFRIGERANT STRAINERS, HAND EXPANSION VALVES, CHECK VALVES, REFRIGERANT SOLENOID VALVES, PRESSURE REGULATING VALVE, REPLACEABLE FILTER DRYERS, FLOAT SWITCH, AUTOMATIC EXPANSION VALVE ASSEMBLY, ADJUSTABLE LEVEL CONTROLLER, PRESSURE GAUGES (AMMONIA AND OIL) Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06479 | Review Response | Approved as Noted | 2020-06-18 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.06.18 | Info Exchange
| 08730 | Responded and Closed | Approved as Noted | 2020-06-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.06.18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-02 |  | 13 10 61-10.0 Ammoniva Valves and Piping - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-02 |  | 13 10 61-10.0 Ammoniva Valves and Piping - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-01 02:00 |  | 13 10 61-10.0 Ammoniva Valves and Piping - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-01 02:00 |  | 13 10 61-10.0 Ammoniva Valves and Piping - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-18 02:00 |  | 13 10 61-10.0 Ammoniva Valves and Piping_ME_pop.pdf
13 10 61-011-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-011-00 Glycol Valves and PIping | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-12 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-27 07:00 | 2020-05-19 | 8 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05801 | Received | For Review | 2020-05-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-27 07:00 | Submittal Number: 13 10 61-11.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: GLYCOL VALVES AND PIPING Description: GLYCOL: FLEXIBLE CONNECTORS, 2-WAY MOTORIZED BUTTERFLY VALVE, 3-WAY MOTORIZED BUTTERFLY VALVE, BALL VALVES, CHECK VALVES, BUTTERFLY VALVES, COMPRESSION TANK AND SIGHT GLASS ASSEMBLY, PIPING AND FITTINGS (CONDENSER, SUB FLOOR, & OIL COOLING), VALVE TAGS, PIPE HANGERS AND SUPPORTS, PIPE AND EQUIPMENT MARKERS, THERMOMETERS, PRESSURE GAUGES, TRIPLE DUTY VALVES, SUCTION GUIDES, BALANCING VALVES, AUTO AIR VENTS, Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 07864 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 13 10 61-11.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: GLYCOL VALVES AND PIPING Description: GLYCOL: FLEXIBLE CONNECTORS, 2-WAY MOTORIZED BUTTERFLY VALVE, 3-WAY MOTORIZED BUTTERFLY VALVE, BALL VALVES, CHECK VALVES, BUTTERFLY VALVES, COMPRESSION TANK AND SIGHT GLASS ASSEMBLY, PIPING AND FITTINGS (CONDENSER, SUB FLOOR, & OIL COOLING), VALVE TAGS, PIPE HANGERS AND SUPPORTS, PIPE AND EQUIPMENT MARKERS, THERMOMETERS, PRESSURE GAUGES, TRIPLE DUTY VALVES, SUCTION GUIDES, BALANCING VALVES, AUTO AIR VENTS, Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06124 | Review Response | Approved as Noted/Resubmit | 2020-05-14 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Resubmit items as noted. | Info Exchange
| 08060 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Resubmit items as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 13 10 61-11.0 - Glycol Valves and Piping - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 13 10 61-11.0 - Glycol Valves and Piping - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 13 10 61-11.0 - Glycol Valves and Piping - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-19 |  | 13 10 61-11.0 - Glycol Valves and Piping_ME_POP.pdf
13 10 61-011-01 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-011-01 Glycol Valves and PIping | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-24 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-09 07:00 | 2020-07-06 | 13 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06579 | Received | For Review | 2020-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-09 07:00 | Submittal Number: 13 10 61-11.1 From: GRETCHEN TOSHACH Final Due Date: 07/07/20 Subject: GLYCOL VALVES AND PIPING Description: GLYCOL: FLEXIBLE CONNECTORS, 2-WAY MOTORIZED BUTTERFLY VALVE, 3-WAY MOTORIZED BUTTERFLY VALVE, BALL VALVES, CHECK VALVES, BUTTERFLY VALVES, COMPRESSION TANK AND SIGHT GLASS ASSEMBLY, PIPING AND FITTINGS (CONDENSER, SUB FLOOR, & OIL COOLING), VALVE TAGS, PIPE HANGERS AND SUPPORTS, PIPE AND EQUIPMENT MARKERS, THERMOMETERS, PRESSURE GAUGES, TRIPLE DUTY VALVES, SUCTION GUIDES, BALANCING VALVES, AUTO AIR VENTS, Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 08860 | Forwarded | For Review | 2020-06-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-01 | Submittal Number: 13 10 61-11.1 From: GRETCHEN TOSHACH Final Due Date: 07/07/20 Subject: GLYCOL VALVES AND PIPING Description: GLYCOL: FLEXIBLE CONNECTORS, 2-WAY MOTORIZED BUTTERFLY VALVE, 3-WAY MOTORIZED BUTTERFLY VALVE, BALL VALVES, CHECK VALVES, BUTTERFLY VALVES, COMPRESSION TANK AND SIGHT GLASS ASSEMBLY, PIPING AND FITTINGS (CONDENSER, SUB FLOOR, & OIL COOLING), VALVE TAGS, PIPE HANGERS AND SUPPORTS, PIPE AND EQUIPMENT MARKERS, THERMOMETERS, PRESSURE GAUGES, TRIPLE DUTY VALVES, SUCTION GUIDES, BALANCING VALVES, AUTO AIR VENTS, Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06792 | Review Response | Approved | 2020-07-01 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.07.01 | Info Exchange
| 09127 | Responded and Closed | Approved | 2020-07-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-23 |  | 13 10 61-11.1 - Glycol Valves and Piping - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-23 |  | 13 10 61-11.1 - Glycol Valves and Piping - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-23 |  | 13 10 61-11.1 - Glycol Valves and Piping - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-06 |  | 13 10 61-11.1 - Glycol Valves and Piping_ME_POP.pdf
13 10 61-012-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-012-00 Electrical and Controls | Closed | Mechanical, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-03 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-17 | 2021-06-21 | 19 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-06-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13368 | Received | For Review | 2021-06-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-17 | Submittal Number: 13 10 61-12.0 From: JES PELKEY Final Due Date: 06/02/21 Subject: ELECTRICAL AND CONTROLS Description: MOTOR CONTROL CENTER - PANEL AND LAYOUT, PDB - REGULAR POWER, PDB - EMERGENCY POWER, CIRCUIT BREAKERS, STARTERS, PRESSURE TRANSDUCERS, RINK FLOOR TEMPERATURE SENSORS, NTC TEMPERATURE SENSORS, FLOW SENSORS, HIGH PRESSURE CUT-OUTS, CONTROLS PROGRAM Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 17297 | Forwarded | For Review | 2021-06-03 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-10 | Submittal Number: 13 10 61-12.0 From: JES PELKEY Final Due Date: 06/02/21 Subject: ELECTRICAL AND CONTROLS Description: MOTOR CONTROL CENTER - PANEL AND LAYOUT, PDB - REGULAR POWER, PDB - EMERGENCY POWER, CIRCUIT BREAKERS, STARTERS, PRESSURE TRANSDUCERS, RINK FLOOR TEMPERATURE SENSORS, NTC TEMPERATURE SENSORS, FLOW SENSORS, HIGH PRESSURE CUT-OUTS, CONTROLS PROGRAM Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 13582 | Review Response | Approved as Noted | 2021-06-18 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.06.18 | Info Exchange
| 17583 | Responded and Closed | Approved as Noted | 2021-06-21 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.06.18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-03 |  | 131061-12.0 - ELECTRICAL AND CONTROLS_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-03 |  | 131061-12.0 - ELECTRICAL AND CONTROLS_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-06-03 |  | 131061-12.0 - ELECTRICAL AND CONTROLS_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-21 |  | 131061-12.0 - ELECTRICAL AND CONTROLS_ME_POP.pdf
13 10 61-013-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-013-00 Equipment and Piping Insulation | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-19 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-06 07:00 | 2020-07-01 | 13 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-07-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06520 | Received | For Review | 2020-06-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-06 07:00 | Submittal Number: 13 10 61-13.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: EQUIPMENT AND PIPING INSULATION Description: INSULATION FOR PIPING AND EQUIPMENT Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 08775 | Forwarded | For Review | 2020-06-19 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-26 | Submittal Number: 13 10 61-13.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: EQUIPMENT AND PIPING INSULATION Description: INSULATION FOR PIPING AND EQUIPMENT Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06867 | Review Response | Approved | 2020-06-30 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.06.30 | Info Exchange
| 09038 | Responded and Closed | Approved as Noted | 2020-07-01 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.06.30 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-19 |  | 13 10 61-13.0 - EQUIPMENT AND PIPING INSULATION - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-19 |  | 13 10 61-13.0 - EQUIPMENT AND PIPING INSULATION - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-18 02:00 |  | 13 10 61-13.0 - EQUIPMENT AND PIPING INSULATION - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-01 |  | 13 10 61-13.0 - EQUIPMENT AND PIPING INSULATION_ME_POP.pdf
13 10 61-014-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-014-00 Refrigeration Gas Monitoring System | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-26 07:00 | 2020-05-19 | 9 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05802 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 13 10 61-14.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: REFRIGERATION GAS MONITORING SYSTEM Description: REFRIGERATION GAS MONITORING SYSTEM Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 07866 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 13 10 61-14.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: REFRIGERATION GAS MONITORING SYSTEM Description: REFRIGERATION GAS MONITORING SYSTEM Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06125 | Review Response | Approved | 2020-05-14 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.14 | Info Exchange
| 08059 | Responded and Closed | Approved | 2020-05-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 13 10 61-14.0 Refrigeration Gas Monitoring - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 13 10 61-14.0 Refrigeration Gas Monitoring - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 13 10 61-14.0 Refrigeration Gas Monitoring - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-19 |  | 13 10 61-14.0 Refrigeration Gas Monitoring_ME_POP.pdf
13 10 61-015-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-015-00 Snow Melt Coil | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-03 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-17 | 2021-06-03 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13369 | Received | For Review | 2021-06-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-06-17 | Submittal Number: 13 10 61-15.0 From: GRETCHEN TOSHACH Final Due Date: 06/16/21 Subject: SNOW MELT COIL Description: SNOW MELT COIL Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 17298 | Forwarded | For Review | 2021-06-03 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-10 | Submittal Number: 13 10 61-15.0 From: GRETCHEN TOSHACH Final Due Date: 06/16/21 Subject: SNOW MELT COIL Description: SNOW MELT COIL Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 13390 | Review Response | Approved as Noted | 2021-06-03 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.06.03 | Info Exchange
| 17318 | Responded and Closed | Approved as Noted | 2021-06-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.06.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-02 |  | 13 10 61 - SNOW MELT COIL (DRAWING PIPE AND FITTINGS)_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-02 |  | 13 10 61 - SNOW MELT COIL (DRAWING PIPE AND FITTINGS)_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-06-01 02:00 |  | 13 10 61 - SNOW MELT COIL (DRAWING PIPE AND FITTINGS)_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-03 02:00 |  | 13 10 61 - SNOW MELT COIL (DRAWING PIPE AND FITTINGS)_ME_POP.pdf
13 10 61-017-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-017-00 Ammonia Piping and Fittings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-12 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-26 | 2020-08-18 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-08-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07525 | Received | For Review | 2020-08-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-26 | Submittal Number: 13 10 61-17.0 From: GRETCHEN TOSHACH Final Due Date: 08/26/20 Subject: AMMONIA PIPING AND FITTINGS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 10020 | Forwarded | For Review | 2020-08-12 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-19 | Submittal Number: 13 10 61-17.0 From: GRETCHEN TOSHACH Final Due Date: 08/26/20 Subject: AMMONIA PIPING AND FITTINGS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 07600 | Review Response | Revise and Resubmit | 2020-08-17 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.08.17 | Info Exchange
| 10118 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-18 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.08.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-12 |  | 13 10 61-17.0 - AMMONIA PIPING AND FITTINGS - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-12 |  | 13 10 61-17.0 - AMMONIA PIPING AND FITTINGS - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-08-11 02:00 |  | 13 10 61-17.0 - AMMONIA PIPING AND FITTINGS - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-18 02:00 |  | 13 10 61-17.0 - AMMONIA PIPING AND FITTINGS_ME_pop.pdf
13 10 61-017-01 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-017-01 Ammonia Piping and Fittings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-01 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-15 | 2021-06-03 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13336 | Received | For Review | 2021-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-06-15 | Submittal Number: 13 10 61-17.1 From: TYRONE THORNTON Final Due Date: 06/15/21 Subject: AMMONIA PIPING AND FITTINGS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 17255 | Forwarded | For Review | 2021-06-01 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-08 | Submittal Number: 13 10 61-17.1 From: TYRONE THORNTON Final Due Date: 06/15/21 Subject: AMMONIA PIPING AND FITTINGS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 13383 | Review Response | Approved | 2021-06-03 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.06.03 | Info Exchange
| 17313 | Responded and Closed | Approved | 2021-06-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.06.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-01 |  | 131061-17.1 - AMMONIA PIPING AND FITTINGS_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-01 |  | 131061-17.1 - AMMONIA PIPING AND FITTINGS_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-31 02:00 |  | 131061-17.1 - AMMONIA PIPING AND FITTINGS_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-03 02:00 |  | 13 10 61-17.1 - AMMONIA PIPING AND FITTINGS_ME_POP.pdf
13 10 61-018-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-018-00 Glycol Valves and Fittings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-19 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-06 07:00 | 2020-07-01 | 13 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-07-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06519 | Received | For Review | 2020-06-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-06 07:00 | Submittal Number: 13 10 61-18.0 From: GRETCHEN TOSHACH Final Due Date: 07/08/20 Subject: GLYCOL VALVES AND FITTINGS Description: ADDITIONAL GLYCOL VALVES AND FITTINGS Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 08774 | Forwarded | For Review | 2020-06-19 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-26 | Submittal Number: 13 10 61-18.0 From: GRETCHEN TOSHACH Final Due Date: 07/08/20 Subject: GLYCOL VALVES AND FITTINGS Description: ADDITIONAL GLYCOL VALVES AND FITTINGS Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 06866 | Review Response | Approved as Noted | 2020-06-30 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.06.30 | Info Exchange
| 09037 | Responded and Closed | Approved as Noted | 2020-07-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.06.30 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-19 |  | 13 10 61-18.0 - GLYCOL VALVES AND FITTINGS - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-19 |  | 13 10 61-18.0 - GLYCOL VALVES AND FITTINGS - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-18 02:00 |  | 13 10 61-18.0 - GLYCOL VALVES AND FITTINGS - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-01 |  | 13 10 61-18.0 - GLYCOL VALVES AND FITTINGS_ME_POP.pdf
13 10 61-019-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-019-00 R-09 - Secondary Ammonia Vent Piping Plan | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-06 | 2020-08-06 | 15 |  | Record Copies; Transfers; Submittals | 13 10 61-019-01 - 13 10 61-019-00 R-09 - Secondary Ammonia Vent Piping Plan | 2 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07114 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 13 10 61-19.0 From: CARTER TWOMBLY Final Due Date: 07/24/20 Subject: R-09 - SECONDARY AMMONIA VENT PIPING PLAN Description: SEE SECONDARY AMMONIA VENT PIPING PLAN. THE VENT PIPE HAS BEEN ROUTED DIFFERENT AS A RESULT FROM CHANGES IN ELEVATION FROM THE PARKING GARAGE ABOVE AND LIMIT SPACE IN THE CHILLER ROOM. PLEASE REVIEW DRAWING AND ADVISE IF THIS IS AN ACCEPTABLE ROUTE. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 09503 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-30 | Submittal Number: 13 10 61-19.0 From: CARTER TWOMBLY Final Due Date: 07/24/20 Subject: R-09 - SECONDARY AMMONIA VENT PIPING PLAN Description: SEE SECONDARY AMMONIA VENT PIPING PLAN. THE VENT PIPE HAS BEEN ROUTED DIFFERENT AS A RESULT FROM CHANGES IN ELEVATION FROM THE PARKING GARAGE ABOVE AND LIMIT SPACE IN THE CHILLER ROOM. PLEASE REVIEW DRAWING AND ADVISE IF THIS IS AN ACCEPTABLE ROUTE. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 07440 | Review Response | Approved as Noted | 2020-07-24 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Submit items noted. Nick Theimer ME Engineers 2020.07.24 | Info Exchange
| 09910 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Submit items noted. Nick Theimer ME Engineers 2020.07.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 13 10 61-19.0 - R-09 VENT- MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | 13 10 61-19.0 - R-09 VENT- MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-22 02:00 |  | 13 10 61-19.0 - R-09 VENT- MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-06 02:00 |  | 13 10 61-19.0 - R-09 VENT_ME_pop.pdf
13 10 61-019-01 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-019-00 R-09 - Secondary Ammonia Vent Piping Plan | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 13 10 61-019-00 - 13 10 61-019-00 R-09 - Secondary Ammonia Vent Piping Plan | -1 | 2020-08-20
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 02:00 |  | 13 10 61-19.0 - R-09 VENT_ME_pop.pdf
13 10 61-020-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-020-00 Full Ice Set | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-07 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-21 | 2020-08-17 | 11 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-08-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07467 | Received | For Review | 2020-08-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-08-21 | Submittal Number: 13 10 61-20.0 From: GRETCHEN TOSHACH Final Due Date: 09/04/20 Subject: FULL ICE SET Description: ICE SET DRAWINGS STAMPED. FOR RECORD UPLOAD. COMBINED DOCUMENTS SENT TO DESIGN TEAM FOR PERMIT. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 09946 | Forwarded | For Review | 2020-08-10 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-17 | Submittal Number: 13 10 61-20.0 From: GRETCHEN TOSHACH Final Due Date: 09/04/20 Subject: FULL ICE SET Description: ICE SET DRAWINGS STAMPED. FOR RECORD UPLOAD. COMBINED DOCUMENTS SENT TO DESIGN TEAM FOR PERMIT. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 07589 | Review Response | No Action Taken or Required | 2020-08-14 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. For information and record only. Nick Theimer ME Engineers 2020.08.14 | Info Exchange
| 10103 | Responded and Closed | No Action Taken or Required | 2020-08-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: See attached for review. For information and record only. Nick Theimer ME Engineers 2020.08.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-07 |  | Ammonia Dispersion Tanks - Fabrication Drawing.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-07 |  | Equipment Containing Ammonia.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-07 |  | SEATTLE - ICE SYSTEM - FULL SET - ss.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-07 |  | Ammonia Dispersion Tanks - Fabrication Drawing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-07 |  | Equipment Containing Ammonia.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-07 |  | SEATTLE - ICE SYSTEM - FULL SET - ss.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-08-06 02:00 |  | Ammonia Dispersion Tanks - Fabrication Drawing.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-08-06 02:00 |  | Equipment Containing Ammonia.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-08-06 02:00 |  | SEATTLE - ICE SYSTEM - FULL SET - ss.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-17 02:00 |  | 13 10 61-020-00 - CPA Record Set Ice_ME_pop.pdf
13 10 61-020-01 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-020-01 Ice Rink Slab Shop Drawing Revision | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-26 | Closed - Void |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-05-10 |  | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12776 | Received | For Review | 2021-04-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-05-10 | Submittal Number: 13 10 61-20.1 From: TYRONE THORNTON Final Due Date: 05/10/21 Subject: 13 10 61 - ICE RINK SLAB SHOP DRAWING REVISION Description: DIMENSION REVISIONS TO R-05, 06, AND 07 ONLY. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 16513 | Forwarded | For Review | 2021-04-26 | Tyrone Thornton (Mortenson Construction) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-03 | Submittal Number: 13 10 61-20.1 From: TYRONE THORNTON Final Due Date: 05/10/21 Subject: 13 10 61 - ICE RINK SLAB SHOP DRAWING REVISION Description: DIMENSION REVISIONS TO R-05, 06, AND 07 ONLY. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 16577 | Closed | Void | 2021-04-27 | Josh Dobken (Populous) |  |  | Voided per discussion during document control on 4/27.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-26 |  | 13 10 61-020 CPA Ice Slab Shop Drawings_Revised.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-04-26 |  | 13 10 61-020 CPA Ice Slab Shop Drawings_Revised.pdf
13 10 61-021-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-021-00 Ice Rink Floor Insert Plan & Details | Closed | Mechanical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-04 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2021-03-18 | 2021-04-06 | 34 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11785 | Received | For Review | 2021-03-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-03-18 | Submittal Number: 13 10 61-21.0 From: TYRONE THORNTON Final Due Date: 03/17/21 Subject: 13 10 61 - ICE RINK FLOOR INSERT PLAN & DETAILS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 15273 | Forwarded | For Review | 2021-03-04 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-11 | Submittal Number: 13 10 61-21.0 From: TYRONE THORNTON Final Due Date: 03/17/21 Subject: 13 10 61 - ICE RINK FLOOR INSERT PLAN & DETAILS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 12453 | Review Response | Approved | 2021-03-08 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.03.08 | Info Exchange
| 15413 | Forwarded | For Review | 2021-03-09 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2021-03-16 | Submittal Number: 13 10 61-21.0 From: TYRONE THORNTON Final Due Date: 03/17/21 Subject: 13 10 61 - ICE RINK FLOOR INSERT PLAN & DETAILS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 16124 | Responded and Closed | Approved | 2021-04-06 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 16590 | Sent | For Information Only | 2021-04-27 | Josh Dobken (Populous) | Domingo Sampayo (Mortenson Construction); Tyrone Thornton (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Responded and Closed (Approved) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.03.08 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-03 |  | 13 10 61 - ICE RINK FLOOR INSERT PLAN AND DETAILS_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-03 |  | 13 10 61 - ICE RINK FLOOR INSERT PLAN AND DETAILS_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-03-02 02:00 |  | 13 10 61 - ICE RINK FLOOR INSERT PLAN AND DETAILS_MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-02 02:00 |  | 13 10 61 - ICE RINK FLOOR INSERT PLAN AND DETAILS_MAM Review.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-08 |  | 13 10 61 - ICE RINK FLOOR INSERT PLAN AND DETAILS_ME.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-04-06 |  | 13 10 61 - ICE RINK FLOOR INSERT PLAN AND DETAILS_ME-POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-03-02 02:00 |  | 13 10 61 - ICE RINK FLOOR INSERT PLAN AND DETAILS_MAM Review.pdf
13 10 61-022-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-022-00 Engineered Seismic Pipe Hangers | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-04 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2021-03-18 | 2021-03-23 | 20 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11786 | Received | For Review | 2021-03-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-03-18 | Submittal Number: 13 10 61-22.0 From: TYRONE THORNTON Final Due Date: 03/17/21 Subject: 13 10 61 - ENGINEERED SEISMIC PIPE HANGERS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 15274 | Forwarded | For Review | 2021-03-04 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-11 | Submittal Number: 13 10 61-22.0 From: TYRONE THORNTON Final Due Date: 03/17/21 Subject: 13 10 61 - ENGINEERED SEISMIC PIPE HANGERS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 11862 | Review Response | Approved as Noted | 2021-03-08 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.03.08 | Info Exchange
| 15381 | Forwarded | For Review | 2021-03-09 | Bryan Klote (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) |  | Submittal Number: 13 10 61-22.0 From: TYRONE THORNTON Final Due Date: 03/17/21 Subject: 13 10 61 - ENGINEERED SEISMIC PIPE HANGERS Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 12192 | Review Response | Approved as Noted | 2021-03-22 | Franz Kogler (Thornton Tomasetti) | Bryan Klote (Populous) |  | See comments in attached submittal review. | Info Exchange
| 15778 | Responded and Closed | Approved as Noted | 2021-03-23 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.03.08 Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments in attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-03 |  | 13 10 61 - Engineered Seismic Pipe Hangers_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-03 |  | 13 10 61 - Engineered Seismic Pipe Hangers_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-03-03 |  | 13 10 61 - Engineered Seismic Pipe Hangers_MAM Review.pdf
| Forwarded |  | Bryan Klote (Populous) | 1 | 2021-03-03 |  | 13 10 61 - Engineered Seismic Pipe Hangers_MAM Review.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-03-02 02:00 |  | 13 10 61 - Engineered Seismic Pipe Hangers_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-23 02:00 |  | 13 10 61 - Engineered Seismic Pipe Hangers_ME_TT REVIEW_POP.pdf
13 10 61-023-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-023-00 12" Compactable Ice Rink Slab Stone Dust | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-17 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-03-31 | 2021-03-24 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12058 | Received | For Review | 2021-03-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-03-31 | Submittal Number: 13 10 61-23.0 From: TYRONE THORNTON Final Due Date: 03/30/21 Subject: 12" COMPACTABLE ICE RINK SLAB STONE DUST Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 15614 | Forwarded | For Review | 2021-03-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-23 | Submittal Number: 13 10 61-23.0 From: TYRONE THORNTON Final Due Date: 03/30/21 Subject: 12" COMPACTABLE ICE RINK SLAB STONE DUST Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 12191 | Review Response | Approved | 2021-03-23 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.03.23 | Info Exchange
| 15777 | Forwarded | For Review | 2021-03-23 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2021-03-30 | Submittal Number: 13 10 61-23.0 From: TYRONE THORNTON Final Due Date: 03/30/21 Subject: 12" COMPACTABLE ICE RINK SLAB STONE DUST Description: Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 15809 | Responded and Closed | Approved | 2021-03-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.03.23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-16 |  | 13 10 62 - ICE RINK SUB FLOOR SAND_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-16 |  | 13 10 62 - ICE RINK SUB FLOOR SAND_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-03-15 02:00 |  | 13 10 62 - ICE RINK SUB FLOOR SAND_MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-15 02:00 |  | 13 10 62 - ICE RINK SUB FLOOR SAND_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-24 02:00 |  | 13 10 61-23.0 ICE RINK SUB FLOOR SAND_ME_POP.pdf
13 10 61-024-00 | 13 10 61 - ICE RINK REFRIGERATION AND PIPING | 13 10 61-024-00 12" Ice Rink Sand Subbase | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-24 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-04-08 07:00 | 2021-03-29 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12202 | Received | For Review | 2021-03-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-04-08 07:00 | Submittal Number: 13 10 61-24.0 From: TYRONE THORNTON Final Due Date: 04/06/21 Subject: 12" ICE RINK SAND SUBBASE Description: MIX PROVIDED BY CALPORTLAND TO IMPROVE THE CYCLE TIME ON THE MATERIAL DELIVERY. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 15788 | Forwarded | For Review | 2021-03-24 | Tyrone Thornton (Mortenson Construction) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-31 | Submittal Number: 13 10 61-24.0 From: TYRONE THORNTON Final Due Date: 04/06/21 Subject: 12" ICE RINK SAND SUBBASE Description: MIX PROVIDED BY CALPORTLAND TO IMPROVE THE CYCLE TIME ON THE MATERIAL DELIVERY. Spec Section: 13 10 61 - ICE RINK REFRIGERATION AND PIPING Status: OPEN | Info Exchange
| 12299 | Review Response | Approved | 2021-03-24 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.03.24 | Info Exchange
| 15929 | Responded and Closed | Approved | 2021-03-29 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.03.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-23 |  | 13 10 61 - CalPortland ICE SUB FLOOR SAND_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-03-23 |  | 13 10 61 - CalPortland ICE SUB FLOOR SAND_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-03-22 02:00 |  | 13 10 61 - CalPortland ICE SUB FLOOR SAND_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-29 02:00 |  | 13 10 61-024 CalPortland ICE SUB FLOOR SAND_ME_POP.pdf
13 10 62-001-00 | 13 10 62 - ICE RINK FLOOR | 13 10 62-001-00 Ice Rink Floor Materials and Piping | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-26 07:00 | 2020-05-19 | 9 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05803 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 13 10 62-1.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: ICE RINK FLOOR MATERIALS AND PIPING Description: FINK FLOOR HEADER PIPE AND FITTINGS, RINK FLOOR PIPE, PIPE CHAIRS, SUB-FLOOR UNDERGROUND PIPE AND FITTINGS, ICE RINK INSULATION, VAPOR BARRIER AND SEAM TAPE, REBAR, MESH, PERIMETER STEEL, EXPANSION JOINT MATERIAL, CONCRETE MIX, CONCRETE CURING BLANKETS, SUB FLOOR SAND, CONCRETE PATCHING MATERIAL. Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 07867 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-18 | Submittal Number: 13 10 62-1.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: ICE RINK FLOOR MATERIALS AND PIPING Description: FINK FLOOR HEADER PIPE AND FITTINGS, RINK FLOOR PIPE, PIPE CHAIRS, SUB-FLOOR UNDERGROUND PIPE AND FITTINGS, ICE RINK INSULATION, VAPOR BARRIER AND SEAM TAPE, REBAR, MESH, PERIMETER STEEL, EXPANSION JOINT MATERIAL, CONCRETE MIX, CONCRETE CURING BLANKETS, SUB FLOOR SAND, CONCRETE PATCHING MATERIAL. Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 07874 | Forwarded | For Review | 2020-05-11 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 13 10 62-1.0 From: GRETCHEN TOSHACH Final Due Date: 05/26/20 Subject: ICE RINK FLOOR MATERIALS AND PIPING Description: FINK FLOOR HEADER PIPE AND FITTINGS, RINK FLOOR PIPE, PIPE CHAIRS, SUB-FLOOR UNDERGROUND PIPE AND FITTINGS, ICE RINK INSULATION, VAPOR BARRIER AND SEAM TAPE, REBAR, MESH, PERIMETER STEEL, EXPANSION JOINT MATERIAL, CONCRETE MIX, CONCRETE CURING BLANKETS, SUB FLOOR SAND, CONCRETE PATCHING MATERIAL. Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 06126 | Review Response | Approved as Noted/Resubmit | 2020-05-15 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.15 | Info Exchange
| 08062 | Responded and Closed | Approved as Noted | 2020-05-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 13 10 62-1.0 - Ice Rink Floor Materials and Piping - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 13 10 62-1.0 - Ice Rink Floor Materials and Piping - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-10 02:00 |  | 13 10 62-1.0 - Ice Rink Floor Materials and Piping - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 13 10 62-1.0 - Ice Rink Floor Materials and Piping - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-19 |  | 13 10 62-1.0 - Ice Rink Floor Materials and Piping_ME_POP.pdf
13 10 62-001-01 | 13 10 62 - ICE RINK FLOOR | 13 10 62-001-01 Ice Rink Floor Materials and Piping | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-24 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-09 07:00 | 2020-07-06 | 13 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06580 | Received | For Review | 2020-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-09 07:00 | Submittal Number: 13 10 62-1.1 From: GRETCHEN TOSHACH Final Due Date: 07/07/20 Subject: ICE RINK FLOOR MATERIALS AND PIPING Description: RINK FLOOR HEADER PIPE AND FITTINGS Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 08862 | Forwarded | For Review | 2020-06-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-01 | Submittal Number: 13 10 62-1.1 From: GRETCHEN TOSHACH Final Due Date: 07/07/20 Subject: ICE RINK FLOOR MATERIALS AND PIPING Description: RINK FLOOR HEADER PIPE AND FITTINGS Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 06793 | Review Response | Approved | 2020-07-02 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.07.02 | Info Exchange
| 09129 | Responded and Closed | Approved | 2020-07-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-23 |  | 13 10 62-1.1 - Ice Rink Floor Materials and Piping - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-23 |  | 13 10 62-1.1 - Ice Rink Floor Materials and Piping - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-23 |  | 13 10 62-1.1 - Ice Rink Floor Materials and Piping - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-06 |  | 13 10 62-1.1 - Ice Rink Floor Materials and Piping_ME_POP.pdf
13 10 62-004-00 | 13 10 62 - ICE RINK FLOOR | 13 10 62-004-00 Ice Rink Concrete Mix Design | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-19 | Responded and Closed - Rejected |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Mike Steele (CAA ICON / Strategy Advisory), Elliott Veazey (CAA ICON / Strategy Advisory), Mike Tihista (CAA ICON / Strategy Advisory) |  |  |  | 2021-04-06 07:00 | 2021-04-05 | 18 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12241 | Received | For Review | 2021-03-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-04-06 07:00 | Submittal Number: 13 10 62-4.0 From: TYRONE THORNTON Final Due Date: 04/02/21 Subject: ICE RINK CONCRETE MIX DESIGN Description: Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 15833 | Forwarded | For Review | 2021-03-25 | Tyrone Thornton (Mortenson Construction) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-04-01 | Submittal Number: 13 10 62-4.0 From: TYRONE THORNTON Final Due Date: 04/02/21 Subject: ICE RINK CONCRETE MIX DESIGN Description: Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 15837 | Forwarded | For Review | 2021-03-25 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-26 | Submittal Number: 13 10 62-4.0 From: TYRONE THORNTON Final Due Date: 04/02/21 Subject: ICE RINK CONCRETE MIX DESIGN Description: Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Email
| 12413 | Review Response | Approved as Noted | 2021-03-29 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Owner's representative/special inspector shall review per specification. Nick Theimer ME Engineers 2021.03.29 | Info Exchange
| 15930 | Forwarded | For Review | 2021-03-29 | Josh Dobken (Populous) | Mike Steele (CAA ICON / Strategy Advisory); Elliott Veazey (CAA ICON / Strategy Advisory); Mike Tihista (CAA ICON / Strategy Advisory) | 2021-04-05 | Submittal Number: 13 10 62-4.0 From: TYRONE THORNTON Final Due Date: 04/02/21 Subject: ICE RINK CONCRETE MIX DESIGN Description: Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Email
| 12414 | Review Response | Rejected | 2021-04-01 | Sean McNeill (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 16046 | Responded and Closed | Rejected | 2021-04-05 | Tyrone Thornton (Mortenson Construction) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Sean McNeill (Thornton Tomasetti) Remarks: Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Owner's representative/special inspector shall review per specification. Nick Theimer ME Engineers 2021.03.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-24 02:00 |  | 13 10 62 - ICE RINK Concrete Mix_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-03-25 |  | 13 10 62 - ICE RINK Concrete Mix_MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-24 02:00 |  | 13 10 62 - ICE RINK Concrete Mix_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-03-24 02:00 |  | 13 10 62 - ICE RINK Concrete Mix_MAM Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-24 02:00 |  | 13 10 62 - ICE RINK Concrete Mix_MAM Review.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2021-03-24 02:00 |  | 13 10 62 - ICE RINK Concrete Mix_MAM Review.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-04-05 02:00 |  | 13 10 62 - ICE RINK Concrete Mix_MAM Review_TT_POP.pdf
13 10 62-004-01 | 13 10 62 - ICE RINK FLOOR | 13 10 62-004-01 Ice Rink Concrete Mix Design | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-05 | 2021-04-30 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-04-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12710 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-05-05 | Submittal Number: 13 10 62-4.1 From: TYRONE THORNTON Final Due Date: 05/05/21 Subject: ICE RINK CONCRETE MIX DESIGN Description: Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 16431 | Forwarded | For Review | 2021-04-21 | Tyrone Thornton (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (ME Engineers); Sean McNeill (Thornton T... | 2021-04-28 | Submittal Number: 13 10 62-4.1 From: TYRONE THORNTON Final Due Date: 05/05/21 Subject: ICE RINK CONCRETE MIX DESIGN Description: Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 12880 | Review Response | Approved | 2021-04-30 | Matt Ross (Thornton Tomasetti) | Tyrone Thornton (Mortenson Construction) |  | Please note that we have not received signed and sealed calcs for the ice slab as indicated per Spec Section 13 10 62 1.3 A. These calcs will have to be signed and sealed and reviewed and approved by TT per the specification. | Info Exchange
| 16662 | Responded and Closed | Approved as Noted | 2021-04-30 | Tyrone Thornton (Mortenson Construction) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Please note that we have not received signed and sealed calcs for the ice slab as indicated per Spec Section 13 10 62 1.3 A. These calcs will have to be signed and sealed and reviewed and approved by TT per the specification. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-21 |  | 13 10 62_Rev1 - ICE RINK Concrete Mix_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-04-21 |  | 13 10 62_Rev1 - ICE RINK Concrete Mix_MAM Review.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-30 02:00 |  | 13 10 62_Rev1 - ICE RINK Concrete Mix_MAM Review_TT.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-04-30 02:00 |  | 13 10 62_Rev1 - ICE RINK Concrete Mix_MAM Review_TT_POP.pdf
13 10 62-004-02 | 13 10 62 - ICE RINK FLOOR | 13 10 62-004-02 Ice Rink Concrete Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-06 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-05-20 | 2021-05-06 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12966 | Received | For Review | 2021-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-05-20 | Submittal Number: 13 10 62-4.2 From: TYRONE THORNTON Final Due Date: 05/06/21 Subject: ICE RINK CONCRETE MIX DESIGN Description: SUBMISSION OF THE CONCRETE CALCULATIONS ONLY. Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 16773 | Forwarded | For Review | 2021-05-06 | Tyrone Thornton (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-05-13 | Submittal Number: 13 10 62-4.2 From: TYRONE THORNTON Final Due Date: 05/06/21 Subject: ICE RINK CONCRETE MIX DESIGN Description: SUBMISSION OF THE CONCRETE CALCULATIONS ONLY. Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 16775 | Forwarded | For Review | 2021-05-06 | Tyrone Thornton (Mortenson Construction) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-13 | Submittal Number: 13 10 62-4.2 From: TYRONE THORNTON Final Due Date: 05/06/21 Subject: ICE RINK CONCRETE MIX DESIGN Description: SUBMISSION OF THE CONCRETE CALCULATIONS ONLY. Spec Section: 13 10 62 - ICE RINK FLOOR Status: OPEN | Info Exchange
| 12968 | Review Response | No Action Taken or Required | 2021-05-06 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | See attached. Reviewed for information only. Nick Theimer ME Engineers 2021.05.06 | Info Exchange
| 12969 | Review Response | Approved | 2021-05-06 | Raymond Chou (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 16785 | Responded and Closed | Approved | 2021-05-06 | Tyrone Thornton (Mortenson Construction) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: See attached. Reviewed for information only. Nick Theimer ME Engineers 2021.05.06 Response (Approved) from: Raymond Chou (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-06 |  | CPA Ice Rink Slab Calculations_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-05-06 |  | CPA Ice Rink Slab Calculations_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-05-06 |  | CPA Ice Rink Slab Calculations_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-05 02:00 |  | CPA Ice Rink Slab Calculations_MAM Review.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2021-05-06 02:00 |  | CPA Ice Rink Slab Calculations_MAM Review_TT Reviewed.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-05-06 02:00 |  | 13 10 62-4.2_CPA Ice Rink Slab Calculations_MAM Review_TT Reviewed_MEE_POP.pdf
13 10 64-001-00 | 13 10 64 - ICE CONDITIONING EQUIPMENT | 13 10 64-001-00 Jet Ice System | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-21 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-07 07:00 | 2021-06-03 | 14 |  | Record Copies; Transfers; Submittals | 13 10 64-001-00-01 - 13 10 64-001-00 Jet Ice System | 7 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13221 | Received | For Review | 2021-05-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-06-07 07:00 | Submittal Number: 13 10 64-1.0 From: TYRONE THORNTON Final Due Date: 06/03/21 Subject: JET ICE SYSTEM Description: JET ICE SYSTEM PRODUCT DATA Spec Section: 13 10 64 - ICE CONDITIONING EQUIPMENT Status: OPEN | Info Exchange
| 17111 | Forwarded | For Review | 2021-05-21 | Tyrone Thornton (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (ME Engineers); Sean McNeill (Thornton T... | 2021-05-28 | Submittal Number: 13 10 64-1.0 From: TYRONE THORNTON Final Due Date: 06/03/21 Subject: JET ICE SYSTEM Description: JET ICE SYSTEM PRODUCT DATA Spec Section: 13 10 64 - ICE CONDITIONING EQUIPMENT Status: OPEN | Info Exchange
| 13386 | Review Response | Approved as Noted/Resubmit | 2021-05-27 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.05.27 | Info Exchange
| 17315 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-03 | Tyrone Thornton (Mortenson Construction) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.05.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-20 |  | 13 10 64-1_WATER TREATMENT AND HEATING SYSTEM_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-05-20 |  | 13 10 64-1_WATER TREATMENT AND HEATING SYSTEM_MAM Review.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-19 02:00 |  | 13 10 64-1_WATER TREATMENT AND HEATING SYSTEM_MAM Review.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-06-03 02:00 |  | 13 10 64-1_WATER TREATMENT AND HEATING SYSTEM_ME_POP.pdf
13 10 64-001-00-01 | 13 10 64 - ICE CONDITIONING EQUIPMENT | 13 10 64-001-00 Jet Ice System | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 13 10 64-001-00 - 13 10 64-001-00 Jet Ice System | -1 | 2021-06-17
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-03 02:00 |  | 13 10 64-1_WATER TREATMENT AND HEATING SYSTEM_ME_POP.pdf
13 10 64-001-01 | 13 10 64 - ICE CONDITIONING EQUIPMENT | 13 10 64-001-01 Jet Ice System | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-06 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-20 | 2021-08-09 | 4 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14240 | Received | For Review | 2021-08-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-08-20 | Submittal Number: 13 10 64-1.1 From: TYRONE THORNTON Final Due Date: 08/19/21 Subject: JET ICE SYSTEM Description: JET ICE SYSTEM PRODUCT DATA Spec Section: 13 10 64 - ICE CONDITIONING EQUIPMENT Status: OPEN | Info Exchange
| 18396 | Forwarded | For Review | 2021-08-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-13 | Submittal Number: 13 10 64-1.1 From: TYRONE THORNTON Final Due Date: 08/19/21 Subject: JET ICE SYSTEM Description: JET ICE SYSTEM PRODUCT DATA Spec Section: 13 10 64 - ICE CONDITIONING EQUIPMENT Status: OPEN | Info Exchange
| 18403 | Forwarded | For Review | 2021-08-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-13 | Submittal Number: 13 10 64-1.1 From: TYRONE THORNTON Final Due Date: 08/19/21 Subject: JET ICE SYSTEM Description: JET ICE SYSTEM PRODUCT DATA Spec Section: 13 10 64 - ICE CONDITIONING EQUIPMENT Status: OPEN | Info Exchange
| 14273 | Review Response | Approved as Noted | 2021-08-06 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.08.06 | Info Exchange
| 18435 | Responded and Closed | Approved as Noted | 2021-08-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.08.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-05 |  | 13 10 64-1 Rev 1-JET ICE SYSTEM PLAN AND ELEVATION.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-05 |  | 13 10 64-1 Rev 1-JET ICE SYSTEM PLAN AND ELEVATION.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-05 |  | 13 10 64-1 Rev 1-JET ICE SYSTEM PLAN AND ELEVATION.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-08-04 02:00 |  | 13 10 64-1 Rev 1-JET ICE SYSTEM PLAN AND ELEVATION.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-08-09 02:00 |  | 13 10 64-1 Rev 1-JET ICE SYSTEM PLAN AND ELEVATION_ME_POP.pdf
13 17 23-001-00 | 13 17 23 | 13 17 23-001-00 Hydroworx | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-27 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-11 | 2020-05-12 | 16 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05546 | Received | For Review | 2020-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-11 | Submittal Number: 13 17 23-1.0 From: GRETCHEN TOSHACH Final Due Date: 05/08/20 Subject: HYDROWORX Description: POOLS SUBMITTAL PACKAGE Spec Section: 13 17 23 - THERAPEUTIC POOLS Status: OPEN | Info Exchange
| 07522 | Forwarded | For Review | 2020-04-24 | Populous SCA_CCA | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2020-05-01 | Submittal Number: 13 17 23-1.0 From: GRETCHEN TOSHACH Final Due Date: 05/08/20 Subject: HYDROWORX Description: POOLS SUBMITTAL PACKAGE Spec Section: 13 17 23 - THERAPEUTIC POOLS Status: OPEN | Info Exchange
| 07734 | Forwarded | For Review | 2020-05-04 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-11 | Submittal Number: 13 17 23-1.0 From: GRETCHEN TOSHACH Final Due Date: 05/08/20 Subject: HYDROWORX Description: POOLS SUBMITTAL PACKAGE Spec Section: 13 17 23 - THERAPEUTIC POOLS Status: OPEN | Info Exchange
| 07904 | Responded and Closed | Approved | 2020-05-12 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | 13 17 23-1.0 Hydrotherapy Pool - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-24 |  | 13 17 23-1.0 Hydrotherapy Pool - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-23 02:00 |  | 13 17 23-1.0 Hydrotherapy Pool - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-24 |  | 13 17 23-1.0 Hydrotherapy Pool - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-12 |  | 13 17 23-1.0 Hydrotherapy Pool - MAM-POP.pdf
13 17 23-002-00 | 13 17 23 | 13 17 23-002-00 Pool Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2020-09-08 07:00 | 2020-09-08 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07703 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-09-08 07:00 | Submittal Number: 13 17 23-2.0 From: GRETCHEN TOSHACH Final Due Date: 09/08/20 Subject: POOL SHOP DRAWINGS Description: POOL SHOP DRAWINGS Spec Section: 13 17 23 - THERAPEUTIC POOLS Status: OPEN | Info Exchange
| 10251 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2020-08-31 | Submittal Number: 13 17 23-2.0 From: GRETCHEN TOSHACH Final Due Date: 09/08/20 Subject: POOL SHOP DRAWINGS Description: POOL SHOP DRAWINGS Spec Section: 13 17 23 - THERAPEUTIC POOLS Status: OPEN | Info Exchange
| 10615 | Responded and Closed | Approved as Noted | 2020-09-08 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 13 17 23-2.0 Hydrotherapy Pool SD - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 13 17 23-2.0 Hydrotherapy Pool SD - MAM.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2020-09-08 |  | 13 17 23-2.0 Hydrotherapy Pool SD - MAM-POP.pdf
13 18 16-002-00 | 13 18 16 - ICE RINK DASHER SYSTEM | 13 18 16-002-00 ICE RINK DASHER SYSTEM - Shop Drawings | Closed | Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-17 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Tom Usher (Populous), Nick Theimer (ME Engineers), Chris Minter (Populous), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Mark Lievens (ME Engineers), Geoff Cheong |  |  |  | 2021-03-03 | 2021-03-10 | 22 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11516 | Received | For Review | 2021-02-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Populous SCA_CCA; Cody Stieritz | 2021-03-03 | Submittal Number: 13 18 16-2.0 From: ELLIOTT VEAZEY Final Due Date: 03/10/21 Subject: ICE RINK DASHER SYSTEM - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DASHER BOARD SYSTEM. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, ANCHOR LAYOUTS, AND ATTACHMENTS TO OTHER WORK. 1. DETAIL ASSEMBLIES AND INDICATE DIMENSIONS, COMPONENTS, AND LOCATION AND SIZE OF EACH FIELD CONNECTION. A. BOARD ASSEMBLIES. B. GLAZING ASSEMBLIES. C. PLAYER, PENALTY, AND TIMEKEEPER BOXES. 2. SHOW SIZES AND LOCATIONS OF DOORS, LIFT GATES AND REMOVABLE SECTIONS RELATIVE TO FLOOR LAYOUT. Spec Section: 13 18 16 - ICE RINK DASHER SYSTEM Status: OPEN | Info Exchange
| 14915 | Forwarded | For Review | 2021-02-17 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Tom Usher (Populous); Nick Theimer (ME Engineers); Chris Minter (Populous); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) | 2021-02-24 | Submittal Number: 13 18 16-2.0 From: ELLIOTT VEAZEY Final Due Date: 03/10/21 Subject: ICE RINK DASHER SYSTEM - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DASHER BOARD SYSTEM. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, ANCHOR LAYOUTS, AND ATTACHMENTS TO OTHER WORK. 1. DETAIL ASSEMBLIES AND INDICATE DIMENSIONS, COMPONENTS, AND LOCATION AND SIZE OF EACH FIELD CONNECTION. A. BOARD ASSEMBLIES. B. GLAZING ASSEMBLIES. C. PLAYER, PENALTY, AND TIMEKEEPER BOXES. 2. SHOW SIZES AND LOCATIONS OF DOORS, LIFT GATES AND REMOVABLE SECTIONS RELATIVE TO FLOOR LAYOUT. Spec Section: 13 18 16 - ICE RINK DASHER SYSTEM Status: OPEN | Info Exchange
| 11776 | Review Response | Approved | 2021-02-22 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | TT has no exceptions. Please provide loads imposed from hanging netting to structure to EOR for review and approval. | Info Exchange
| 15009 | Forwarded | For Review | 2021-02-22 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers) | 2021-03-01 | Submittal Number: 13 18 16-2.0 From: ELLIOTT VEAZEY Final Due Date: 03/10/21 Subject: ICE RINK DASHER SYSTEM - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DASHER BOARD SYSTEM. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, ANCHOR LAYOUTS, AND ATTACHMENTS TO OTHER WORK. 1. DETAIL ASSEMBLIES AND INDICATE DIMENSIONS, COMPONENTS, AND LOCATION AND SIZE OF EACH FIELD CONNECTION. A. BOARD ASSEMBLIES. B. GLAZING ASSEMBLIES. C. PLAYER, PENALTY, AND TIMEKEEPER BOXES. 2. SHOW SIZES AND LOCATIONS OF DOORS, LIFT GATES AND REMOVABLE SECTIONS RELATIVE TO FLOOR LAYOUT. Spec Section: 13 18 16 - ICE RINK DASHER SYSTEM Status: OPEN | Info Exchange
| 15195 | Forwarded | For Review | 2021-03-01 | Josh Dobken (Populous) | Geoff Cheong | 2021-03-03 | Submittal Number: 13 18 16-2.0 From: ELLIOTT VEAZEY Final Due Date: 03/10/21 Subject: ICE RINK DASHER SYSTEM - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DASHER BOARD SYSTEM. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, ANCHOR LAYOUTS, AND ATTACHMENTS TO OTHER WORK. 1. DETAIL ASSEMBLIES AND INDICATE DIMENSIONS, COMPONENTS, AND LOCATION AND SIZE OF EACH FIELD CONNECTION. A. BOARD ASSEMBLIES. B. GLAZING ASSEMBLIES. C. PLAYER, PENALTY, AND TIMEKEEPER BOXES. 2. SHOW SIZES AND LOCATIONS OF DOORS, LIFT GATES AND REMOVABLE SECTIONS RELATIVE TO FLOOR LAYOUT. Spec Section: 13 18 16 - ICE RINK DASHER SYSTEM Status: OPEN | Info Exchange
| 11922 | Review Response | Approved as Noted | 2021-03-02 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | Please see the attached submtital review. Mark Lievens ME Engineers 2021.03.02 | Info Exchange
| 15447 | Responded and Closed | Approved as Noted | 2021-03-10 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-17 02:00 |  | 13 18 16-002-00 Ice Rink Dasher System PD and SD.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-17 02:00 |  | 13 18 16-002-00 Ice Rink Dasher System PD and SD.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-17 |  | 13 18 16-002-00 Ice Rink Dasher System PD and SD.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-17 02:00 |  | 13 18 16-002-00 Ice Rink Dasher System PD and SD.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-17 02:00 |  | 13 18 16-002-00 Ice Rink Dasher System PD and SD.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-02-17 |  | 13 18 16-002-00 Ice Rink Dasher System PD and SD.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-02-22 |  | 13 18 16-002-00 Ice Rink Dasher System PD and SD_TT.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-02 |  | 13 18 16-002-00 Ice Rink Dasher System PD and SD_TT_ME.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-03-10 |  | 13 18 16-002-00 Ice Rink Dasher System PD and SD_TT_ME-POP.pdf
13 24 16-001-00 | 13 24 16 | 13 24 16-001-00 Sauna Submittal Package | Closed | Architectural, Electrical, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-16 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Mark Lievens (ME Engineers) |  |  |  | 2021-03-30 | 2021-04-06 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12048 | Received | For Review | 2021-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-03-30 | Submittal Number: 13 24 16-1.0 From: MIKE SOLFELT Final Due Date: 04/12/21 Subject: SAUNA SUBMITTAL PACKAGE Description: Spec Section: 13 24 16 - SAUNAS Status: OPEN | Info Exchange
| 15597 | Forwarded | For Review | 2021-03-16 | Mike Solfelt (Mortenson Construction) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-23 | Submittal Number: 13 24 16-1.0 From: MIKE SOLFELT Final Due Date: 04/12/21 Subject: SAUNA SUBMITTAL PACKAGE Description: Spec Section: 13 24 16 - SAUNAS Status: OPEN | Info Exchange
| 15814 | Forwarded | For Review | 2021-03-24 | Kelsea Conkright (Populous) | Mark Lievens (ME Engineers) |  | Submittal Number: 13 24 16-1.0 From: MIKE SOLFELT Final Due Date: 04/12/21 Subject: SAUNA SUBMITTAL PACKAGE Description: Spec Section: 13 24 16 - SAUNAS Status: OPEN | Info Exchange
| 12425 | Review Response | Approved as Noted | 2021-04-06 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.04.06 | Info Exchange
| 12426 | Review Response | Revise and Resubmit | 2021-04-06 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16102 | Responded and Closed | Revise and Resubmit | 2021-04-06 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.04.06 Response (Revise and Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-15 |  | 132416-001 Sauna Submittal Package.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-03-15 |  | 132416-001 Sauna Submittal Package.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-03-23 |  | 132416-001 Sauna Submittal Package_POP.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-03-23 |  | 132416-001 Sauna Submittal Package_POP.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-06 |  | 132416-001 Sauna Submittal Package_POP_ME.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-15 |  | 132416-001 Sauna Submittal Package.pdf
13 24 16-001-01 | 13 24 16 | 13 24 16-001-01 Sauna Submittal Package | Closed | Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-13 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-04-27 | 2021-04-27 | 15 |  | Record Copies; Transfers; Submittals | 13 24 16-001-01-01 - 13 24 16-001-01 Sauna Submittal Package | 16 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12546 | Received | For Review | 2021-04-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Mike Solfelt (Mortenson Construction) | 2021-04-27 | Submittal Number: 13 24 16-1.1 From: MIKE SOLFELT Final Due Date: 04/26/21 Subject: SAUNA SUBMITTAL PACKAGE Description: Spec Section: 13 24 16 - SAUNAS Status: OPEN | Info Exchange
| 16247 | Forwarded | For Review | 2021-04-12 | Mike Solfelt (Mortenson Construction) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-04-19 | Submittal Number: 13 24 16-1.1 From: MIKE SOLFELT Final Due Date: 04/26/21 Subject: SAUNA SUBMITTAL PACKAGE Description: Spec Section: 13 24 16 - SAUNAS Status: OPEN | Info Exchange
| 12701 | Review Response | Approved | 2021-04-21 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.04.21 | Info Exchange
| 12810 | Review Response | Approved as Noted/Resubmit | 2021-04-27 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16558 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-27 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.04.21 Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-12 |  | 132416-001.1 Sauna Submittal Package.pdf
| Forwarded |  | Mike Solfelt (Mortenson Construction) | 1 | 2021-04-12 |  | 132416-001.1 Sauna Submittal Package.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-12 |  | 132416-001.1 Sauna Submittal Package.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-04-27 |  | 132416-001.1 Sauna Submittal Package - ME Review_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-27 |  | 132416-001.1 Sauna Submittal Package - ME Review_POP.pdf
13 24 16-001-01-01 | 13 24 16 | 13 24 16-001-01 Sauna Submittal Package | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 13 24 16-001-01 - 13 24 16-001-01 Sauna Submittal Package | -1 | 2021-05-11
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-27 |  | 132416-001.1 Sauna Submittal Package - ME Review_POP.pdf
13 49 00-001-00 | 13 49 00 | 13 49 00-001-00 RADIATION PROTECTION - Glazing Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-11 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2021-06-25 | 2021-06-16 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-06-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13497 | Received | For Review | 2021-06-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Allie Zimmerman | 2021-06-25 | Submittal Number: 13 49 00-1.0 From: ALLIE ZIMMERMAN Final Due Date: 06/25/21 Subject: RADIATION PROTECTION - GLAZING PRODUCT DATA Description: Spec Section: 13 49 00 - RADIATION PROTECTION Status: OPEN | Info Exchange
| 17450 | Forwarded | For Review | 2021-06-11 | Allie Zimmerman | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2021-06-18 | Submittal Number: 13 49 00-1.0 From: ALLIE ZIMMERMAN Final Due Date: 06/25/21 Subject: RADIATION PROTECTION - GLAZING PRODUCT DATA Description: Spec Section: 13 49 00 - RADIATION PROTECTION Status: OPEN | Info Exchange
| 13551 | Review Response | Approved | 2021-06-16 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17542 | Responded and Closed | Approved | 2021-06-16 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-11 |  | Submittal 13 49 00-1 Revision 0 RADIATION PROTECTION - Glazing Product Data_MAM Reviewed.pdf
| Forwarded |  | Allie Zimmerman | 1 | 2021-06-11 |  | Submittal 13 49 00-1 Revision 0 RADIATION PROTECTION - Glazing Product Data_MAM Reviewed.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-16 |  | 13 49 00-1 RADIATION PROTECTION - Glazing Product Data_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-11 |  | Submittal 13 49 00-1 Revision 0 RADIATION PROTECTION - Glazing Product Data_MAM Reviewed.pdf
14 20 00-001-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-001-00 Elevator Product Data | Closed | Architectural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Heidi Evans (ME Engineers) |  |  |  | 2019-12-09 08:00 | 2019-11-26 | 6 |  | Record Copies; Transfers; Submittals | 14 20 00-001-01 - 14 20 00-001-00 Elevator Product Data | 6 |  | 2019-11-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03304 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-12-09 08:00 | Submittal Number: 14 20 00-1.0 From: NATE WEINGART Final Due Date: 12/06/19 Subject: ELEVATOR PRODUCT DATA Description: PRODUCT DATA : INCLUDE PRODUCT DATA FOR SAFETY FEATURES, OPERATING SYSTEM DESCRIPTIONS, SEQUENCE OF OPERATIONS, AND EQUIPMENT LISTS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04758 | Forwarded | For Review | 2019-11-21 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); H... | 2019-11-27 | Submittal Number: 14 20 00-1.0 From: NATE WEINGART Final Due Date: 12/06/19 Subject: ELEVATOR PRODUCT DATA Description: PRODUCT DATA : INCLUDE PRODUCT DATA FOR SAFETY FEATURES, OPERATING SYSTEM DESCRIPTIONS, SEQUENCE OF OPERATIONS, AND EQUIPMENT LISTS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03323 | Review Response | Approved | 2019-11-21 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  | The approved elevator product data submittal is attached. Populous needs to select the freight door color finish from the last page. The standard is gray. Scott Shepler Principal Fortune Shepler Saling (720) 438.1540 www.fs2ec.com | Info Exchange
| 04833 | Forwarded | For Review | 2019-11-26 | Todd Spangler (Populous) | Tom Usher (Populous) | 2019-11-26 | Submittal Number: 14 20 00-1.0 From: NATE WEINGART Final Due Date: 12/06/19 Subject: ELEVATOR PRODUCT DATA Description: PRODUCT DATA : INCLUDE PRODUCT DATA FOR SAFETY FEATURES, OPERATING SYSTEM DESCRIPTIONS, SEQUENCE OF OPERATIONS, AND EQUIPMENT LISTS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04836 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for comments. To complete submittal requirements per spec. submit finish sample.s | Info Exchange
| 03389 | Review Response | Approved as Noted | 2019-11-26 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2019.11.26 | Info Exchange
| 04855 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2019.11.26 Response (Approved) from: Scott Shepler (Fortune Shepler Saling FS2EC) Remarks: The approved elevator product data submittal is attached. Populous needs to select the freight door color finish from the last page. The standard is gray. Scott Shepler Principal Fortune Shepler Saling (720) 438.1540 www.fs2ec.com Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) Remarks: See attached for comments. To complete submittal requirements per spec. submit finish sample.s | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-20 |  | 142000-1.0 Elevator Product Data (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-20 |  | 142000-1.0 Elevator Product Data (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2019-11-21 02:00 |  | 142000-1.0 Elevator Product Data (MAM Review) FS2 Review.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-11-20 |  | 142000-1.0 Elevator Product Data (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-11-26 |  | 142000-1.0 Elevator Product Data (MAM Review) FS2_POP.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-11-19 02:00 |  | 142000-1.0 Elevator Product Data (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-26 02:00 |  | 142000-1.0 Elevator Product Data (MAM Review) FS2_POP_ME.pdf
14 20 00-001-01 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-001-00 Elevator Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 14 20 00-001-00 - 14 20 00-001-00 Elevator Product Data | -1 | 2019-12-10
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-26 02:00 |  | 142000-1.0 Elevator Product Data (MAM Review) FS2_POP_ME.pdf
14 20 00-002-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-002-00 Elevator Shop Drawings - D1 Passenger | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-27 | Responded and Closed - Revise and Resubmit |  | Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Mark Lievens (ME Engineers), Bryan Klote (Populous), Greg Briggs (Thornton Tomasetti), Todd Spangler (Populous), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-10-11 | 2019-10-11 | 15 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-10-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02575 | Received | For Review | 2019-09-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-10-11 | Submittal Number: 14 20 00-2.0 From: JES PELKEY Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - D1 PASSENGER Description: SHOP DRAWINGS : - 1. PROVIDE ELECTRONIC COPIES OF SHOP DRAWINGS SHOWING SCALED HOISTWAY, MACHINE ROOM, ENTRANCES, CABS AND FIXTURE PLANS, ELEVATIONS, SECTIONS AND DETAILS. INCLUDE DETAILS IN 2D CADD FORMAT. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03863 | Forwarded | For Review | 2019-09-30 | Shaina Burris (Populous) | Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous) | 2019-10-07 | Submittal Number: 14 20 00-2.0 From: JES PELKEY Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - D1 PASSENGER Description: SHOP DRAWINGS : - 1. PROVIDE ELECTRONIC COPIES OF SHOP DRAWINGS SHOWING SCALED HOISTWAY, MACHINE ROOM, ENTRANCES, CABS AND FIXTURE PLANS, ELEVATIONS, SECTIONS AND DETAILS. INCLUDE DETAILS IN 2D CADD FORMAT. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03907 | Forwarded | For Review | 2019-10-01 | Todd Spangler (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) |  | Submittal Number: 14 20 00-2.0 From: JES PELKEY Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - D1 PASSENGER Description: SHOP DRAWINGS : - 1. PROVIDE ELECTRONIC COPIES OF SHOP DRAWINGS SHOWING SCALED HOISTWAY, MACHINE ROOM, ENTRANCES, CABS AND FIXTURE PLANS, ELEVATIONS, SECTIONS AND DETAILS. INCLUDE DETAILS IN 2D CADD FORMAT. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03913 | Forwarded | For Review | 2019-10-01 | Todd Spangler (Populous) | Mark Lievens (ME Engineers) |  | Submittal Number: 14 20 00-2.0 From: JES PELKEY Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - D1 PASSENGER Description: SHOP DRAWINGS : - 1. PROVIDE ELECTRONIC COPIES OF SHOP DRAWINGS SHOWING SCALED HOISTWAY, MACHINE ROOM, ENTRANCES, CABS AND FIXTURE PLANS, ELEVATIONS, SECTIONS AND DETAILS. INCLUDE DETAILS IN 2D CADD FORMAT. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 02670 | Review Response | Approved as Noted | 2019-10-04 | Scott Shepler (Fortune Shepler Saling FS2EC) | Josh Dobken (Populous) |  | Attached please find the AAN Elevator D1 Shop Drawings. Please note: 1. TT/ME will need to provide comments on their respective reviews. 2. Populous will need to: · Designate the floor labeling. tke shows numerical labels for the levels - 1, 2, 3, etc. · Designate the entrance wall thickness and material type. · Confirm if the shown horizontal hall lanterns mounted above the entrances are desired or if they are to be changed to vertical lanterns mounted adjacent the entrance. · Review the contractor questions in the green boxes. | Info Exchange
| 03988 | Forwarded | For Review | 2019-10-04 | Josh Dobken (Populous) | Bryan Klote (Populous); Greg Briggs (Thornton Tomasetti); Todd Spangler (Populous); Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Tom Usher (Populous); Nick Theimer (ME Engineers); Chris Minter (Populous); Brian MacRae (Thornton Tom... | 2019-10-11 | Submittal Number: 14 20 00-2.0 From: JES PELKEY Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - D1 PASSENGER Description: SHOP DRAWINGS : - 1. PROVIDE ELECTRONIC COPIES OF SHOP DRAWINGS SHOWING SCALED HOISTWAY, MACHINE ROOM, ENTRANCES, CABS AND FIXTURE PLANS, ELEVATIONS, SECTIONS AND DETAILS. INCLUDE DETAILS IN 2D CADD FORMAT. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN Review Response Date: 10/4/2019 Due Back: -- From: Scott Shepler (Fortune Shepler Saling FS2EC) Recipients: Josh Dobken (Populous) Remarks: Attached please find the AAN Elevator D1 Shop Drawings. Please note: 1. TT/ME will need to provide comments on their respective reviews. 2. Populous will need to: · Designate the floor labeling. tke shows numerical labels for the levels - 1, 2, 3, etc. · Designate the entrance wall thickness and material type. · Confirm if the shown horizontal hall lanterns mounted above the entrances are desired or if they are to be changed to vertical lanterns mounted adjacent the entrance. · Review the contractor questions in the green boxes. | Info Exchange
| 02714 | Review Response | Revise and Resubmit | 2019-10-09 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.10.09 | Info Exchange
| 04080 | Responded and Closed | Revise and Resubmit | 2019-10-11 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-27 |  | 142000-2.0 Elevator Shop Drawings - D1 Passenger (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-27 |  | 142000-2.0 Elevator Shop Drawings - D1 Passenger (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-09-27 |  | 142000-2.0 Elevator Shop Drawings - D1 Passenger (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-09-27 |  | 142000-2.0 Elevator Shop Drawings - D1 Passenger (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2019-10-04 02:00 |  | 142000-2.0 Elevator Shop Drawings - D1 Passenger (MAM Review)_FS2 Review.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-26 02:00 |  | 142000-2.0 Elevator Shop Drawings - D1 Passenger (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-09-26 |  | 142000-2.0 Elevator Shop Drawings - D1 Passenger (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-11 |  | 142000-2.0 Elevator Shop Drawings - D1 Passenger_MAM_FS2_ME_TT_POP.pdf
14 20 00-002-01 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-002-01 Elevator Resubmittal - D1 Passenger | Closed | Architectural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-06 | Sent and Closed - For Construction |  | Mark Lievens (ME Engineers), Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-01-20 | 2020-01-28 | 25 |  | Record Copies; Transfers; Submittals |  | 25 |  | 2020-01-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03807 | Received | For Review | 2020-01-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-01-20 | Submittal Number: 14 20 00-2.1 From: NATE WEINGART Final Due Date: 01/17/20 Subject: ELEVATOR RESUBMITTAL - D1 PASSENGER Description: SHOP DRAWINGS : - 1. PROVIDE ELECTRONIC COPIES OF SHOP DRAWINGS SHOWING SCALED HOISTWAY, MACHINE ROOM, ENTRANCES, CABS AND FIXTURE PLANS, ELEVATIONS, SECTIONS AND DETAILS. INCLUDE DETAILS IN 2D CADD FORMAT. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 05347 | Forwarded | For Review | 2020-01-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti) | 2020-01-13 | Submittal Number: 14 20 00-2.1 From: NATE WEINGART Final Due Date: 01/17/20 Subject: ELEVATOR RESUBMITTAL - D1 PASSENGER Description: SHOP DRAWINGS : - 1. PROVIDE ELECTRONIC COPIES OF SHOP DRAWINGS SHOWING SCALED HOISTWAY, MACHINE ROOM, ENTRANCES, CABS AND FIXTURE PLANS, ELEVATIONS, SECTIONS AND DETAILS. INCLUDE DETAILS IN 2D CADD FORMAT. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03844 | Review Response | Approved | 2020-01-07 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. | Info Exchange
| 04054 | Review Response | Approved as Noted | 2020-01-24 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.01.24 | Info Exchange
| 04078 | Review Response | Approved as Noted | 2020-01-16 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  | Attached is the reviewed submittal. ME & TT will have to review/comment on the respective loads. Note the contractor questioned the elevator labeling. I assume these were reviewed with the Fire Chief during the life safety review, however, we defer to POP if the labeling is to be changed. tke advised that they can only provide horizontal hall lanterns. If POP wants the vertical lanterns, I included a picture on the fixture drawings from their catalog that shows vertical lanterns. Otherwise, confirm if POP is ok with their proposed horizontal lantern. Please let me know of any questions. | Info Exchange
| 05682 | Responded and Closed | Approved as Noted | 2020-01-28 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| 04150 | Review Response | Approved as Noted | 2020-01-30 | Scott Shepler (Fortune Shepler Saling FS2EC) | Todd Spangler (Populous); Josh Dobken (Populous) |  | Attached please find the referenced revised submittal that eliminates the fireman's phone jacks in the car operating panels and fire command panel. The Seattle Building Code Chapter 30 - Elevators includes the phone jacks with an exception for omission upon election by the Fire Department. George Goodall of the Seattle Fire Department has confirmed in his January 27 email that the Department uses radio communication and does not use the Fireman's phone jacks. Therefore, the jacks are to be removed from the elevator car operating panel. | Email
| 05753 | Sent and Closed | For Construction | 2020-01-30 | Josh Dobken (Populous) | Nate Weingart (Mortenson Construction) |  | Nate, See updated response from FS2. This supersedes their previous review. Please let me know if you have any questions. Thanks, Josh Dobken DESIGNER I POPULOUS 4800 Main Street ¦ Suite 300 Kansas City, Missouri 64112 ¦ USA Main: +1 816 221 1500 ¦ Fax: +1 816 329 4299 Direct: +1 816 329 4423 ¦ Mobile: +1 908 433 7880 josh.dobken@populous.com www.populous.com Response (Approved as Noted) from: Scott Shepler (Fortune Shepler Saling FS2EC) Remarks: Attached please find the referenced revised submittal that eliminates the fireman's phone jacks in the car operating panels and fire command panel. The Seattle Building Code Chapter 30 - Elevators includes the phone jacks with an exception for omission upon election by the Fire Department. George Goodall of the Seattle Fire Department has confirmed in his January 27 email that the Department uses radio communication and does not use the Fireman's phone jacks. Therefore, the jacks are to be removed from the elevator car operating panel. | Info Exchange
| 05758 | Sent | For Construction | 2020-01-30 | Josh Dobken (Populous) | Nate Weingart (Mortenson Construction) |  | Nate, Seems like there was an error in the last transmission of this submittal to you. See attached with corrections made. This supersedes their previous review. Please let me know if you have any questions. Thanks, Josh Dobken DESIGNER I POPULOUS 4800 Main Street ¦ Suite 300 Kansas City, Missouri 64112 ¦ USA Main: +1 816 221 1500 ¦ Fax: +1 816 329 4299 Direct: +1 816 329 4423 ¦ Mobile: +1 908 433 7880 josh.dobken@populous.com www.populous.com Response (Approved as Noted) from: Scott Shepler (Fortune Shepler Saling FS2EC) Remarks: Attached please find the referenced revised submittal that eliminates the fireman's phone jacks in the car operating panels and fire command panel. The Seattle Building Code Chapter 30 - Elevators includes the phone jacks with an exception for omission upon election by the Fire Department. George Goodall of the Seattle Fire Department has confirmed in his January 27 email that the Department uses radio communication and does not use the Fireman's phone jacks. Therefore, the jacks are to be removed from the elevator car operating panel. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-06 |  | 142000-2.1 Elevator D1 Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-06 |  | 142000-2.1 Elevator D1 Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-05 02:00 |  | 142000-2.1 Elevator D1 Resubmittal (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-06 |  | 142000-2.1 Elevator D1 Resubmittal (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-01-27 02:00 |  | 142000-2.1 Elevator D1 Resubmittal (MAM Review)_FS2.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-28 |  | 142000-2.1 Elevator D1 Resubmittal (MAM Review)_TT_FS2_MEE_POP.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-01-30 02:00 |  | 142000-2.1 Elevator D1 Resubmittal (MAM Review)_FS2 R1.pdf
| Sent and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-05 02:00 |  | 142000-2.1 Elevator D1 Resubmittal (MAM Review).pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-01-30 02:00 |  | 142000-2.1 Elevator D1 Resubmittal (MAM Review)_FS2 R1.pdf
14 20 00-002-02 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-002-02 Elevator D1 Passenger Engineered Drawings - Submitting for Permit | Closed | Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-15 | Responded and Closed - Approved |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-01-07 | 2020-12-18 | 4 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-12-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10176 | Received | For Review | 2020-12-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-07 | Submittal Number: 14 20 00-2.2 From: JES PELKEY Final Due Date: 12/29/20 Subject: ELEVATOR D1 PASSENGER ENGINEERED DRAWINGS - SUBMITTING FOR PERMIT Description: SHOP DRAWINGS : - 1. PROVIDE ELECTRONIC COPIES OF SHOP DRAWINGS SHOWING SCALED HOISTWAY, MACHINE ROOM, ENTRANCES, CABS AND FIXTURE PLANS, ELEVATIONS, SECTIONS AND DETAILS. INCLUDE DETAILS IN 2D CADD FORMAT. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 13312 | Forwarded | For Review | 2020-12-15 | Populous SCA_CCA | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2020-12-22 | Submittal Number: 14 20 00-2.2 From: JES PELKEY Final Due Date: 12/29/20 Subject: ELEVATOR D1 PASSENGER ENGINEERED DRAWINGS - SUBMITTING FOR PERMIT Description: SHOP DRAWINGS : - 1. PROVIDE ELECTRONIC COPIES OF SHOP DRAWINGS SHOWING SCALED HOISTWAY, MACHINE ROOM, ENTRANCES, CABS AND FIXTURE PLANS, ELEVATIONS, SECTIONS AND DETAILS. INCLUDE DETAILS IN 2D CADD FORMAT. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 10247 | Review Response | Approved | 2020-12-15 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 13397 | Responded and Closed | Approved | 2020-12-18 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-15 |  | 142000-2.2 Elevator D1 Stamped Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-15 |  | 142000-2.2 Elevator D1 Stamped Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-15 |  | 142000-2.2 Elevator D1 Stamped Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-18 |  | 142000-2.2 Elevator D1 Stamped Drawings-MAM_TT_POP.pdf
14 20 00-003-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-003-00 Elevator Shop Drawings - Quad C | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-30 | Responded and Closed - Revise and Resubmit |  | Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Mark Lievens (ME Engineers) |  |  |  | 2019-10-18 | 2019-10-18 | 19 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2019-10-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02577 | Received | For Review | 2019-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-10-18 | Submittal Number: 14 20 00-3.0 From: NATE WEINGART Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - QUAD C Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03864 | Forwarded | For Review | 2019-09-30 | Shaina Burris (Populous) | Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous) | 2019-10-07 | Submittal Number: 14 20 00-3.0 From: NATE WEINGART Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - QUAD C Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03906 | Forwarded | For Review | 2019-10-01 | Todd Spangler (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) |  | Submittal Number: 14 20 00-3.0 From: NATE WEINGART Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - QUAD C Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03912 | Forwarded | For Review | 2019-10-01 | Todd Spangler (Populous) | Mark Lievens (ME Engineers) |  | Submittal Number: 14 20 00-3.0 From: NATE WEINGART Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - QUAD C Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 02755 | Review Response | Revise and Resubmit | 2019-10-14 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens 2019.10.14 | Info Exchange
| 02793 | Review Response | Revise and Resubmit | 2019-10-16 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  |  | Info Exchange
| 02808 | Review Response | Revise and Resubmit | 2019-10-16 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  | Attached please find the R&R Elevator C1 shop drawing. Please note: · I have assumed A2-5.5C is correct vs 2/A7-06-3 & 5/A7-06-4 which show a stop at the SN Club. · tke needs to update the levels served & where the fire recall switch is located. · POP to designate the floor levels & review the clear overhead. Our VT09 detail 5 showed the 14'-4" clear to the underside of the hoisting beam; 1/A7-06-3 shows 14'-4" T.O. Hoisting Beam. | Info Exchange
| 04198 | Responded and Closed | Revise and Resubmit | 2019-10-18 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for design team review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-27 |  | 142000-3.0 Elevator Shop Drawings - Quad C (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-27 |  | 142000-3.0 Elevator Shop Drawings - Quad C (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-09-27 |  | 142000-3.0 Elevator Shop Drawings - Quad C (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-09-27 |  | 142000-3.0 Elevator Shop Drawings - Quad C (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-09-26 02:00 |  | 142000-3.0 Elevator Shop Drawings - Quad C (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-27 |  | 142000-3.0 Elevator Shop Drawings - Quad C (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2019-10-16 02:00 |  | 142000-3.0 Elevator Shop Drawings - Quad C (MAM Review)_FS2.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-16 |  | SSK-0087 Elevator Sill at SPS.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-18 |  | 142000-3.0 Elevator Shop Drawings - Quad C_MAM_FS2_TT_MEE_POP.pdf
14 20 00-003-01 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-003-01 Elevator Resubmittal - C1 & C2 | Closed | Architectural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-13 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-01-27 | 2020-01-30 | 18 |  | Record Copies; Transfers; Submittals | 14 20 00-003-02 - 14 20 00-003-02 Elevator Resubmittal - C1 & C2 | 18 |  | 2020-01-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03899 | Received | For Review | 2020-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-01-27 | Submittal Number: 14 20 00-3.1 From: NATE WEINGART Final Due Date: 01/24/20 Subject: ELEVATOR RESUBMITTAL - C1 & C2 Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 05456 | Forwarded | For Review | 2020-01-13 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti) | 2020-01-20 | Submittal Number: 14 20 00-3.1 From: NATE WEINGART Final Due Date: 01/24/20 Subject: ELEVATOR RESUBMITTAL - C1 & C2 Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04067 | Review Response | Approved as Noted | 2020-01-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please address and clarify comments related to rail bracket forces on pages 7 and 26 of the submittal. For updated detail for Sill to SPS panels, please provide TT with proposed detail concept sketch for TT to provide revised detail. For all requests addressed to TT, please issue RFIs for TT to address. | Info Exchange
| 04070 | Review Response | Approved as Noted | 2020-01-27 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  | Attached please find the approved as noted C1 & C2 drawings. Please note: 1. tke continues to show C1 serving 100, 400, 500, 550, 600. Per attached stop matrix, this elevator is to serves 100, 300, 400, 600. 2. tke cannot provide a vertical hall lantern. They either provide a horizontal lantern or offer to provide a car direction sign that travels with the elevator mounted in the car jamb. Either fixture meets code; if POP elects for the car direction sign because horizontal lanterns are not desired then tke should have a $ deduct to offer up. Please let me know if you would like to discuss this review. Scott Shepler Principal | Info Exchange
| 04125 | Review Response | Approved as Noted/Resubmit | 2020-01-29 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.29 | Info Exchange
| 05732 | Sent | For Information Only | 2020-01-29 | Josh Dobken (Populous) | Nate Weingart (Mortenson Construction) |  | Nate, see attached bootleg of TT's review of the C1 and C2 elevator resubmittal. Let me know if you have questions, Josh Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Please address and clarify comments related to rail bracket forces on pages 7 and 26 of the submittal. For updated detail for Sill to SPS panels, please provide TT with proposed detail concept sketch for TT to provide revised detail. For all requests addressed to TT, please issue RFIs for TT to address. | Info Exchange
| 04149 | Review Response | Approved as Noted | 2020-01-30 | Scott Shepler (Fortune Shepler Saling FS2EC) | Todd Spangler (Populous); Josh Dobken (Populous) |  | Attached please find the referenced revised submittal that eliminates the fireman's phone jacks in the car operating panels and fire command panel. The Seattle Building Code Chapter 30 - Elevators includes the phone jacks with an exception for omission upon election by the Fire Department. George Goodall of the Seattle Fire Department has confirmed in his January 27 email that the Department uses radio communication and does not use the Fireman's phone jacks. Therefore, the jacks are to be removed from the elevator car operating panel. | Email
| 05755 | Responded and Closed | Approved as Noted/Resubmit | 2020-01-30 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for review and comments. Resubmit control button panels only with correct numbering. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-13 |  | 142000-3.1 Elevator C1 & C2 Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-13 |  | 142000-3.1 Elevator C1 & C2 Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-12 02:00 |  | 142000-3.1 Elevator C1 & C2 Resubmittal (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-01-27 02:00 |  | 142000-3.1 Elevator C1 & C2 Resubmittal (MAM Review)_FS2.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-01-27 02:00 |  | SCA - ELEVATOR STOPS Populous Update 10162019.xlsx
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-12 02:00 |  | 142000-3.1 Elevator C1 & C2 Resubmittal (MAM Review).pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-01-12 02:00 |  | 142000-3.1 Elevator C1 & C2 Resubmittal (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-01-30 02:00 |  | 142000-3.1 Elevator C1 & C2 Resubmittal (MAM Review)_FS2 R1.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-30 |  | 142000-3.1 Elevator C1 & C2 Resubmittal (MAM Review)_TT_FS2_ME_POP.pdf
14 20 00-003-02 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-003-02 Elevator Resubmittal - C1 & C2 | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 14 20 00-003-01 - 14 20 00-003-01 Elevator Resubmittal - C1 & C2 | -1 | 2020-02-13
14 20 00-004-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-004-00 Elevator Shop Drawings - Quad B | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-30 | Responded and Closed - Revise and Resubmit |  | Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Mark Lievens (ME Engineers) |  |  |  | 2019-10-18 | 2019-10-18 | 19 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2019-10-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02578 | Received | For Review | 2019-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-10-18 | Submittal Number: 14 20 00-4.0 From: NATE WEINGART Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - QUAD B Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03865 | Forwarded | For Review | 2019-09-30 | Shaina Burris (Populous) | Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous) | 2019-10-07 | Submittal Number: 14 20 00-4.0 From: NATE WEINGART Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - QUAD B Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03905 | Forwarded | For Review | 2019-10-01 | Todd Spangler (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) |  | Submittal Number: 14 20 00-4.0 From: NATE WEINGART Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - QUAD B Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03911 | Forwarded | For Review | 2019-10-01 | Todd Spangler (Populous) | Mark Lievens (ME Engineers) |  | Submittal Number: 14 20 00-4.0 From: NATE WEINGART Final Due Date: 10/18/19 Subject: ELEVATOR SHOP DRAWINGS - QUAD B Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 02756 | Review Response | Revise and Resubmit | 2019-10-14 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.10.14 | Info Exchange
| 02807 | Review Response | Revise and Resubmit | 2019-10-16 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  |  | Info Exchange
| 02809 | Review Response | Revise and Resubmit | 2019-10-15 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  | Quad B elevator R&R shop drawings are attached. Items for Populous review are noted. Please confirm B1 landings served - A2-2B does not show a stop at Mezzanine level, A7-06-1 and A7-06-3 show a stop at Mezz. | Info Exchange
| 02818 | Review Response | Revise and Resubmit | 2019-10-17 | Scott Shepler (Fortune Shepler Saling FS2EC) | Josh Dobken (Populous) |  | Attached are updated review comments for B1, B2-B3, B4 based on the stop matrix provided. In tke's bid they clarified that they were providing tall cabs in order to accommodate the cab weight allowances that were spec'd for artist finishes. It looks like that is resulting in an overhead issue for B4. I think the artist allowance is no longer needed. Therefore the cab height can be reduced to the standard 8'. As such, it seems like the rest of the elevators in this zone should also be reduced to standard cab height; I have noted this for POP review/comment. | Info Exchange
| 04197 | Responded and Closed | Revise and Resubmit | 2019-10-18 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for design team review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-27 |  | 142000-4.0 Elevator Shop Drawings - Quad B (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-27 |  | 142000-4.0 Elevator Shop Drawings - Quad B (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-09-27 |  | 142000-4.0 Elevator Shop Drawings - Quad B (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-09-27 |  | 142000-4.0 Elevator Shop Drawings - Quad B (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-09-26 02:00 |  | 142000-4.0 Elevator Shop Drawings - Quad B (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-26 02:00 |  | 142000-4.0 Elevator Shop Drawings - Quad B (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2019-10-16 02:00 |  | 142000-4.0 Elevator Shop Drawings - Quad B (MAM Review)_FS2.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2019-10-17 02:00 |  | Copy of 142000-4.0 Elevator Shop Drawings - Quad B (MAM Review)_FS2.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-16 |  | SSK-0087 Elevator Sill at SPS.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-18 |  | 142000-4.0 Elevator Shop Drawings - Quad B (MAM Review)_FS2_ME_TT_POP.pdf
14 20 00-004-01 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-004-01 Elevator B1 B2-B3 B4 Resubmittal | Closed | Architectural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-02-24 | 2020-02-27 | 18 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04274 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-02-24 | Submittal Number: 14 20 00-4.1 From: NATE WEINGART Final Due Date: 02/21/20 Subject: ELEVATOR B1 B2-B3 B4 RESUBMITTAL Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 05915 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti) | 2020-02-17 | Submittal Number: 14 20 00-4.1 From: NATE WEINGART Final Due Date: 02/21/20 Subject: ELEVATOR B1 B2-B3 B4 RESUBMITTAL Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04311 | Review Response | Approved as Noted | 2020-02-11 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.02.11 | Info Exchange
| 04313 | Review Response | Approved as Noted | 2020-02-10 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  | Attached are the subjected approved as noted shop drawings. | Email
| 04553 | Review Response | Approved as Noted | 2020-02-24 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 06270 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-27 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-10 |  | 142000-4.1 Elevator B1 B2-B3 B4 Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 142000-4.1 Elevator B1 B2-B3 B4 Resubmittal (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-09 02:00 |  | 142000-4.1 Elevator B1 B2-B3 B4 Resubmittal (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-02-11 02:00 |  | 142000-4.1 Elevator B1 B2-B3 B4 Resubmittal (MAM Review)_FS2 Review.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-10 |  | 142000-4.1 Elevator B1 B2-B3 B4 Resubmittal (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-27 |  | 142000-4.1 Elevator B1 B2-B3 B4 Resubmittal_MAM_TT_FS2_ME_POP.pdf
14 20 00-004-02 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-004-02 Elevator B1 B2-B3 Stamped Drawings to Pull Permit | Closed | Vertical Transportation, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-22 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-01-14 | 2021-01-11 | 21 |  | Record Copies; Transfers; Submittals | 14 20 00-004-02-01 - 14 20 00-004-02 Elevator B1 B2-B3 Stamped Drawings to Pull Permit | 17 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10302 | Received | For Review | 2020-12-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-14 | Submittal Number: 14 20 00-4.2 From: JES PELKEY Final Due Date: 01/06/21 Subject: ELEVATOR B1 B2-B3 STAMPED DRAWINGS TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 13462 | Forwarded | For Review | 2020-12-22 | Populous SCA_CCA | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2020-12-29 | Submittal Number: 14 20 00-4.2 From: JES PELKEY Final Due Date: 01/06/21 Subject: ELEVATOR B1 B2-B3 STAMPED DRAWINGS TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 10577 | Review Response | Approved | 2021-01-04 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 10578 | Review Response | Approved as Noted | 2021-01-07 | Scott Shepler (Fortune Shepler Saling FS2EC) | Populous SCA_CCA |  | P6-P7 car operating button layout and cab height requires correction. | Info Exchange
| 13786 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-11 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-21 |  | 14 20 00-4.2 Elevator B1 B2-B3 Drawings for Permit-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-21 |  | 14 20 00-4.2 Elevator B1 B2-B3 Drawings for Permit-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-21 |  | 14 20 00-4.2 Elevator B1 B2-B3 Drawings for Permit-MAM.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-12-21 |  | 14 20 00-4.2 Elevator B1 B2-B3 Drawings for Permit-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-11 |  | 14 20 00-4.2 Elevator B1 B2-B3 Drawings for Permit-MAM_TT_FS2_POP.pdf
14 20 00-004-02-01 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-004-02 Elevator B1 B2-B3 Stamped Drawings to Pull Permit | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 14 20 00-004-02 - 14 20 00-004-02 Elevator B1 B2-B3 Stamped Drawings to Pull Permit | -1 | 2021-01-25
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 14 20 00-4.2 Elevator B1 B2-B3 Drawings for Permit-MAM_TT_FS2_POP.pdf
14 20 00-005-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-005-00 Elevator Shop Drawings - A1, A2-A3, A5 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-01 | Responded and Closed - Approved as Noted |  | Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Matt Ross (Thornton Tomasetti) |  |  |  | 2019-10-22 | 2019-10-23 | 23 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2019-10-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02614 | Received | For Review | 2019-10-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-10-22 | Submittal Number: 14 20 00-5.0 From: NATE WEINGART Final Due Date: 10/22/19 Subject: ELEVATOR SHOP DRAWINGS - A1, A2-A3, A5 Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03916 | Forwarded | For Review | 2019-10-02 | Shaina Burris (Populous) | Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous) | 2019-10-09 | Submittal Number: 14 20 00-5.0 From: NATE WEINGART Final Due Date: 10/22/19 Subject: ELEVATOR SHOP DRAWINGS - A1, A2-A3, A5 Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04079 | Forwarded | For Review | 2019-10-11 | Todd Spangler (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Matt Ross (Thornton Tomasetti) |  | Submittal Number: 14 20 00-5.0 From: NATE WEINGART Final Due Date: 10/22/19 Subject: ELEVATOR SHOP DRAWINGS - A1, A2-A3, A5 Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 02774 | Review Response | Revise and Resubmit | 2019-10-14 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.10.14 | Info Exchange
| 02816 | Review Response | Revise and Resubmit | 2019-10-17 | Scott Shepler (Fortune Shepler Saling FS2EC) | Populous SCA_CCA |  | Attached are R&R shop drawings for elevators A1, A2-3, A5. We designed the A5 hoistway depth 10'-7" based on tke's Synergy product. Since the design was completed, tke replaced this product & bid their Evolution 200 elevator that requires a 10'-8 1/2" hoistway depth. Populous will need to decide if the additional 1 1/2" can be accommodated or if tke needs to provide their legacy product to fit in the available space. Also, we need to decide if A1 is going to be grouped with A2-A3 with A2-A3 entrances added at Mezz, or if A1 is to operate separate from A2-A3. I noted on the drawing for POP to designate this. | Info Exchange
| 02886 | Review Response | Revise and Resubmit | 2019-10-22 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | See attached | Info Exchange
| 04271 | Responded and Closed | Approved as Noted | 2019-10-23 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-01 |  | 142000-5.0 Elevator Shop Drawings - A1 A2-A3 A5 (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-01 |  | 142000-5.0 Elevator Shop Drawings - A1 A2-A3 A5 (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-10-01 |  | 142000-5.0 Elevator Shop Drawings - A1 A2-A3 A5 (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-09-30 02:00 |  | 142000-5.0 Elevator Shop Drawings - A1 A2-A3 A5 (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2019-10-17 02:00 |  | 142000-5.0 Elevator Shop Drawings - A1 A2-A3 A5 (MAM Review)_FS2.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-09-30 02:00 |  | 142000-5.0 Elevator Shop Drawings - A1 A2-A3 A5 (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-23 |  | 142000-5.0 Elevator Shop Drawings - A1 A2-A3 A5_MAM _FS2_MEE_TT_POP.pdf
14 20 00-005-01 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-005-01 Elevator Resubmittal - A1 A2-A3 A5 | Closed | Architectural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-20 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-03 | 2020-02-06 | 18 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-02-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03980 | Received | For Review | 2020-01-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-02-03 | Submittal Number: 14 20 00-5.1 From: NATE WEINGART Final Due Date: 01/31/20 Subject: ELEVATOR RESUBMITTAL - A1 A2-A3 A5 Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 05552 | Forwarded | For Review | 2020-01-20 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti) | 2020-01-27 | Submittal Number: 14 20 00-5.1 From: NATE WEINGART Final Due Date: 01/31/20 Subject: ELEVATOR RESUBMITTAL - A1 A2-A3 A5 Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04068 | Review Response | Approved as Noted | 2020-01-27 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | MAM to submit RFIs for all framing revision and new detail requests for TT to review. For sill detail to SPS at Press Level, please provide proposed connection concept sketch for TT to review and revise detail. | Info Exchange
| 04126 | Review Response | Approved as Noted/Resubmit | 2020-01-29 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.29 | Info Exchange
| 05836 | Forwarded | For Review | 2020-02-05 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-03 | Submittal Number: 14 20 00-5.1 From: NATE WEINGART Final Due Date: 01/31/20 Subject: ELEVATOR RESUBMITTAL - A1 A2-A3 A5 Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Email
| 05851 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-06 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-19 |  | 142000-5.1 Elevator A1 A2-A3 A5 Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-19 |  | 142000-5.1 Elevator A1 A2-A3 A5 Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-18 02:00 |  | 142000-5.1 Elevator A1 A2-A3 A5 Resubmittal (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-18 02:00 |  | 142000-5.1 Elevator A1 A2-A3 A5 Resubmittal (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-18 02:00 |  | 142000-5.1 Elevator A1 A2-A3 A5 Resubmittal (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-06 |  | 142000-5.1 Elevator A1 A2-A3 A5 Resubmittal (MAM Review)_TT_FS2_ME_POP.pdf
14 20 00-005-02 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-005-02 Elevator A1-A3 Stamped Drawings to Pull Permit | Closed | Vertical Transportation, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-22 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-01-14 | 2021-01-11 | 21 |  | Record Copies; Transfers; Submittals | 14 20 00-005-02-01 - 14 20 00-005-02 Elevator A1-A3 Stamped Drawings to Pull Permit | 17 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10303 | Received | For Review | 2020-12-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-14 | Submittal Number: 14 20 00-5.2 From: NATE WEINGART Final Due Date: 01/06/21 Subject: ELEVATOR A1-A3 STAMPED DRAWINGS TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 13463 | Forwarded | For Review | 2020-12-22 | Populous SCA_CCA | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2020-12-29 | Submittal Number: 14 20 00-5.2 From: NATE WEINGART Final Due Date: 01/06/21 Subject: ELEVATOR A1-A3 STAMPED DRAWINGS TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 10572 | Review Response | Approved as Noted | 2021-01-05 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 10573 | Review Response | Approved | 2021-01-07 | Scott Shepler (Fortune Shepler Saling FS2EC) | Populous SCA_CCA |  |  | Info Exchange
| 13781 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-11 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-21 |  | 14 20 00-5.2 Elevators A1-A3 Drawnigs for Permit-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-21 |  | 14 20 00-5.2 Elevators A1-A3 Drawnigs for Permit-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-21 |  | 14 20 00-5.2 Elevators A1-A3 Drawnigs for Permit-MAM.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-12-21 |  | 14 20 00-5.2 Elevators A1-A3 Drawnigs for Permit-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-11 |  | 14 20 00-5.2 Elevators A1-A3 Drawnigs for Permit-MAM_TT_FS2_POP.pdf
14 20 00-005-02-01 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-005-02 Elevator A1-A3 Stamped Drawings to Pull Permit | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 14 20 00-005-02 - 14 20 00-005-02 Elevator A1-A3 Stamped Drawings to Pull Permit | -1 | 2021-01-25
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 14 20 00-5.2 Elevators A1-A3 Drawnigs for Permit-MAM_TT_FS2_POP.pdf
14 20 00-006-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-006-00 Elevator Shop Drawings - Area E | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-08 | Responded and Closed - Revise and Resubmit |  | Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Matt Ross (Thornton Tomasetti) |  |  |  | 2019-10-29 | 2019-10-28 | 21 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2019-10-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02692 | Received | For Review | 2019-10-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-10-29 | Submittal Number: 14 20 00-6.0 From: NATE WEINGART Final Due Date: 10/29/19 Subject: ELEVATOR SHOP DRAWINGS - AREA E Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04024 | Forwarded | For Review | 2019-10-08 | Shaina Burris (Populous) | Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous) | 2019-10-15 | Submittal Number: 14 20 00-6.0 From: NATE WEINGART Final Due Date: 10/29/19 Subject: ELEVATOR SHOP DRAWINGS - AREA E Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04078 | Forwarded | For Review | 2019-10-11 | Todd Spangler (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Matt Ross (Thornton Tomasetti) |  | Submittal Number: 14 20 00-6.0 From: NATE WEINGART Final Due Date: 10/29/19 Subject: ELEVATOR SHOP DRAWINGS - AREA E Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 02872 | Review Response | Revise and Resubmit | 2019-10-21 | Scott Shepler (Fortune Shepler Saling FS2EC) | Josh Dobken (Populous) |  | Attached are Area E shop drawings. | Info Exchange
| 02910 | Review Response | Revise and Resubmit | 2019-10-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.10.23 | Info Exchange
| 02935 | Review Response | Revise and Resubmit | 2019-10-25 | Matt Ross (Thornton Tomasetti) | Todd Spangler (Populous) |  | Elevator E1 layout differs from drawings and will clash with steel in SE Snorkel. Please revise. | Info Exchange
| 04313 | Responded and Closed | Revise and Resubmit | 2019-10-28 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-07 |  | 142000-6.0 Elevator Shop Drawings - Area E (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-07 |  | 142000-6.0 Elevator Shop Drawings - Area E (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-10-07 |  | 142000-6.0 Elevator Shop Drawings - Area E (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2019-10-21 02:00 |  | 142000-6.0 Elevator Shop Drawings - Area E (MAM Review)_FS2.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-10-06 02:00 |  | 142000-6.0 Elevator Shop Drawings - Area E (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-06 02:00 |  | 142000-6.0 Elevator Shop Drawings - Area E (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-28 |  | 142000-6.0 Elevator Shop Drawings - Area E (MAM Review)_FS2_ME_TT_POP.pdf
14 20 00-006-01 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-006-01 Elevator Resubmittal - E1-E3 | Closed | Architectural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-27 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-02-10 | 2020-02-18 | 23 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-02-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04058 | Received | For Review | 2020-01-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-02-10 | Submittal Number: 14 20 00-6.1 From: NATE WEINGART Final Due Date: 02/07/20 Subject: ELEVATOR RESUBMITTAL - E1-E3 Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 05651 | Forwarded | For Review | 2020-01-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti) | 2020-02-03 | Submittal Number: 14 20 00-6.1 From: NATE WEINGART Final Due Date: 02/07/20 Subject: ELEVATOR RESUBMITTAL - E1-E3 Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04127 | Review Response | Approved as Noted/Resubmit | 2020-01-29 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.29 | Info Exchange
| 04315 | Review Response | Approved as Noted | 2020-02-10 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 04324 | Review Response | Approved as Noted | 2020-02-11 | Scott Shepler (Fortune Shepler Saling FS2EC) | Todd Spangler (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Attached is the approved as noted elevators E1, E2-E3 shop drawing. Please look at the hoistway width for E2-E3. TK is showing 19'-10" required for the cwt safeties. The VT drawings had 19'-9", however we had a 5" divider beam, not the 6" provided. The SGA permit plans were showing 18'-8". | Info Exchange
| 06060 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-18 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-27 |  | 142000-6.1 Elevator E1 E2-3 Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-27 |  | 142000-6.1 Elevator E1 E2-3 Resubmittal (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-26 02:00 |  | 142000-6.1 Elevator E1 E2-3 Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-26 02:00 |  | 142000-6.1 Elevator E1 E2-3 Resubmittal (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-02-11 02:00 |  | 142000-6.1 Elevator E1 E2-3 Resubmittal (MAM Review)_FS2.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-18 |  | 142000-6.1 Elevator E1 E2-3 Resubmittal (MAM Review)_TT_FS2_ME_POP.pdf
14 20 00-006-02 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-006-02 Elevator Resubmittal - E1-E3 Shop Drawings - To Pull Permit | Closed | Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-03-02 | 2021-03-08 | 21 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11450 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-02 | Submittal Number: 14 20 00-6.2 From: JES PELKEY Final Due Date: 03/01/21 Subject: ELEVATOR RESUBMITTAL - E1-E3 SHOP DRAWINGS - TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 14832 | Forwarded | For Review | 2021-02-16 | Populous SCA_CCA | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2021-02-23 | Submittal Number: 14 20 00-6.2 From: JES PELKEY Final Due Date: 03/01/21 Subject: ELEVATOR RESUBMITTAL - E1-E3 SHOP DRAWINGS - TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 11677 | Review Response | Approved as Noted | 2021-02-23 | Scott Shepler (Fortune Shepler Saling FS2EC) | Populous SCA_CCA |  | Approved as noted drawings attached. Looks like two floor heights were transposed on P12, otherwise no other comments. | Info Exchange
| 11679 | Review Response | Approved as Noted | 2021-02-25 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 15343 | Responded and Closed | Approved as Noted | 2021-03-08 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 142000-6.2 Elevators E1 E2 E3 SD - For Permit-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-15 |  | 142000-6.2 Elevators E1 E2 E3 SD - For Permit-MAM.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2021-02-15 |  | 142000-6.2 Elevators E1 E2 E3 SD - For Permit-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-15 |  | 142000-6.2 Elevators E1 E2 E3 SD - For Permit-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-08 |  | 142000-6.2 Elevators E1 E2 E3 SD - For Permit-MAM_TT_POP.pdf
14 20 00-007-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-007-00 Elevator Shop Drawings - A6 Geared Freight | Closed | Architectural, Structural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-12 | Responded and Closed - Revise and Resubmit |  | Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Mark Lievens (ME Engineers), Jackie Lybarger (ME Engineers) |  |  |  | 2019-11-26 | 2019-11-27 | 16 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-11-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03172 | Received | For Review | 2019-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-11-26 | Submittal Number: 14 20 00-7.0 From: NATE WEINGART Final Due Date: 11/26/19 Subject: ELEVATOR SHOP DRAWINGS - A6 GEARED FREIGHT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04590 | Forwarded | For Review | 2019-11-12 | Shaina Burris (Populous) | Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous) | 2019-11-19 | Submittal Number: 14 20 00-7.0 From: NATE WEINGART Final Due Date: 11/26/19 Subject: ELEVATOR SHOP DRAWINGS - A6 GEARED FREIGHT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04591 | Forwarded | For Review | 2019-11-12 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-19 | Submittal Number: 14 20 00-7.0 From: NATE WEINGART Final Due Date: 11/26/19 Subject: ELEVATOR SHOP DRAWINGS - A6 GEARED FREIGHT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04672 | Forwarded | For Review | 2019-11-18 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-25 | Submittal Number: 14 20 00-7.0 From: NATE WEINGART Final Due Date: 11/26/19 Subject: ELEVATOR SHOP DRAWINGS - A6 GEARED FREIGHT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04681 | Forwarded | For Review | 2019-11-18 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Jackie Lybarger (ME Engineers) | 2019-11-25 | Submittal Number: 14 20 00-7.0 From: NATE WEINGART Final Due Date: 11/26/19 Subject: ELEVATOR SHOP DRAWINGS - A6 GEARED FREIGHT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 03291 | Review Response | Revise and Resubmit | 2019-11-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.11.20 | Info Exchange
| 03321 | Review Response | Approved as Noted | 2019-11-21 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | See TT comments for information required to complete structural design of hoistway steel. | Info Exchange
| 04851 | Forwarded | For Review | 2019-11-26 | Todd Spangler (Populous) | Chris Minter (Populous) | 2019-11-27 | Submittal Number: 14 20 00-7.0 From: NATE WEINGART Final Due Date: 11/26/19 Subject: ELEVATOR SHOP DRAWINGS - A6 GEARED FREIGHT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04866 | Responded and Closed | Revise and Resubmit | 2019-11-27 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-12 |  | 142000-7.0 Elevator Shop Drawings - A6 Geared Freight (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-12 |  | 142000-7.0 Elevator Shop Drawings - A6 Geared Freight (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-12 |  | 142000-7.0 Elevator Shop Drawings - A6 Geared Freight (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-11 02:00 |  | 142000-7.0 Elevator Shop Drawings - A6 Geared Freight (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-11 02:00 |  | 142000-7.0 Elevator Shop Drawings - A6 Geared Freight (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-11-11 02:00 |  | 142000-7.0 Elevator Shop Drawings - A6 Geared Freight (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-11 02:00 |  | 142000-7.0 Elevator Shop Drawings - A6 Geared Freight (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-11-26 |  | 142000-7.0 Elevator Shop Drawings - A6 Geared Freight MAM_FS2_MEE_TT_POP.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2019-11-27 |  | 142000-7.0 Elevator Shop Drawings - A6 Geared Freight MAM_FS2_MEE_TT_POP2.pdf
14 20 00-007-01 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-007-01 Elevator A6 Resubmittal | Closed | Architectural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-16 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-01-30 | 2020-01-31 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-01-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03929 | Received | For Review | 2020-01-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-01-30 | Submittal Number: 14 20 00-7.1 From: NATE WEINGART Final Due Date: 01/30/20 Subject: ELEVATOR A6 RESUBMITTAL Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 05496 | Forwarded | For Review | 2020-01-15 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti) | 2020-01-22 | Submittal Number: 14 20 00-7.1 From: NATE WEINGART Final Due Date: 01/30/20 Subject: ELEVATOR A6 RESUBMITTAL Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 04098 | Review Response | Approved as Noted | 2020-01-27 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 04128 | Review Response | Revise and Resubmit | 2020-01-29 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.29 | Info Exchange
| 04151 | Review Response | Approved as Noted | 2020-01-30 | Scott Shepler (Fortune Shepler Saling FS2EC) | Todd Spangler (Populous); Josh Dobken (Populous) |  | Attached please find our review of the Elevator A6 resubmittal. tke made revisions to the overhead steel beam elevations that resulted in a cab height reduction from 9' to 8'-10 1/2". We assume this was the result of the TT review comments regarding support steel locations. The 1 1/2" reduction is acceptable to us; we modified the entrance to also be 8'-10 1/2" high to match the cab height. Please advise of any questions. | Email
| 05786 | Responded and Closed | Approved as Noted/Resubmit | 2020-01-31 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached fro review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-15 |  | 142000-7.1 Elevator A6 Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-15 |  | 142000-7.1 Elevator A6 Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-14 02:00 |  | 142000-7.1 Elevator A6 Resubmittal (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-14 02:00 |  | 142000-7.1 Elevator A6 Resubmittal (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-01-30 02:00 |  | 142000-7.1 Elevator A6 Resubmittal (MAM Review)_FS2.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-31 |  | 142000-7.1 Elevator A6 Resubmittal (MAM Review)_TT_FS2_ME_POP.pdf
14 20 00-007-02 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-007-02 Elevator A6 Resubmittal - Engineered Stamped Drawings | Closed | Vertical Transportation, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-19 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-07 | 2020-12-07 | 19 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09611 | Received | For Review | 2020-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-07 | Submittal Number: 14 20 00-7.2 From: NATE WEINGART Final Due Date: 12/03/20 Subject: ELEVATOR A6 RESUBMITTAL - ENGINEERED STAMPED DRAWINGS Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 12646 | Forwarded | For Review | 2020-11-19 | Populous SCA_CCA | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Brian MacRae (Thornton Tomasetti);... | 2020-11-26 | Submittal Number: 14 20 00-7.2 From: NATE WEINGART Final Due Date: 12/03/20 Subject: ELEVATOR A6 RESUBMITTAL - ENGINEERED STAMPED DRAWINGS Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 09930 | Review Response | Approved | 2020-11-23 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 09931 | Review Response | Approved as Noted | 2020-12-03 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.12.03 | Info Exchange
| 13015 | Responded and Closed | Approved as Noted | 2020-12-07 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | I kept ME review separate because they have a comment. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-19 |  | 142000-7.2 Elevator A6 (F1) SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-19 |  | 142000-7.2 Elevator A6 (F1) SD-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-19 |  | 142000-7.2 Elevator A6 (F1) SD-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-19 |  | 142000-7.2 Elevator A6 (F1) SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-07 |  | 142000-7.2 Elevator A6 (F1) SD-MAM_TT_ME_POP.pdf
14 20 00-008-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-008-00 Elevator Finish Samples | Closed | Architectural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Approved |  | Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-01-10 | 2020-01-10 | 24 | General | Record Copies; Transfers; Submittals |  | 24 |  | 2020-01-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03681 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-01-10 | Submittal Number: 14 20 00-8.0 From: NATE WEINGART Final Due Date: 01/03/20 Subject: ELEVATOR FINISH SAMPLES Description: FINISH SAMPLES 1. UNLESS STIPULATED ELSEWHERE IN THE GENERAL AND SUPPLEMENTARY CONDITIONS, INCLUDE THE FOLLOWING: A. MINIMUM OF SIX (6) 4 INCH SQUARE SAMPLES OF EXPOSED MATERIAL, INCLUDING METAL FINISHES, CAB INTERIOR PANELS AND SILL FINISHES. B. SUBMIT SAMPLES OF ALL FIXTURES INCLUDING ONE OF EACH TYPE OF DESTINATION DISPATCHING FIXTURE, HALL LANTERN, HALL PUSHBUTTON STATION, AND CAR AND HALL BRAILLE PLATES. 2. SAMPLES SHALL BE LABELED WITH PROJECT NAME AND DESCRIPTION OF SAMPLE. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 05201 | Forwarded | For Review | 2019-12-18 | Shaina Burris (Populous) | Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-12-25 | Submittal Number: 14 20 00-8.0 From: NATE WEINGART Final Due Date: 01/03/20 Subject: ELEVATOR FINISH SAMPLES Description: FINISH SAMPLES 1. UNLESS STIPULATED ELSEWHERE IN THE GENERAL AND SUPPLEMENTARY CONDITIONS, INCLUDE THE FOLLOWING: A. MINIMUM OF SIX (6) 4 INCH SQUARE SAMPLES OF EXPOSED MATERIAL, INCLUDING METAL FINISHES, CAB INTERIOR PANELS AND SILL FINISHES. B. SUBMIT SAMPLES OF ALL FIXTURES INCLUDING ONE OF EACH TYPE OF DESTINATION DISPATCHING FIXTURE, HALL LANTERN, HALL PUSHBUTTON STATION, AND CAR AND HALL BRAILLE PLATES. 2. SAMPLES SHALL BE LABELED WITH PROJECT NAME AND DESCRIPTION OF SAMPLE. Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 05432 | Responded and Closed | Approved | 2020-01-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 142000-8.0 Elevator Finish Samples (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-18 |  | 142000-8.0 Elevator Finish Samples (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-10 02:00 |  | 142000-8.0 Elevator Finish Samples (MAM Review)_pop.pdf
14 20 00-009-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-009-00 Elevator Fire Command Panel | Closed | Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-05 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-05-19 | 2020-06-22 | 49 |  | Record Copies; Transfers; Submittals |  | 46 |  | 2020-06-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05727 | Received | For Review | 2020-05-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-05-19 | Submittal Number: 14 20 00-9.0 From: NATE WEINGART Final Due Date: 05/19/20 Subject: ELEVATOR FIRE COMMAND PANEL Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 07772 | Forwarded | For Review | 2020-05-05 | Shaina Burris (Populous) | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2020-05-12 | Submittal Number: 14 20 00-9.0 From: NATE WEINGART Final Due Date: 05/19/20 Subject: ELEVATOR FIRE COMMAND PANEL Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 06545 | Review Response | Approved as Noted | 2020-06-19 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.06.19 | Info Exchange
| 08811 | Responded and Closed | Approved as Noted | 2020-06-22 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.06.19 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | 142000-9.0 Elevator Fire Command Panel (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-05 |  | 142000-9.0 Elevator Fire Command Panel (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-04 02:00 |  | 142000-9.0 Elevator Fire Command Panel (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-22 02:00 |  | 142000-9.0 Elevator Fire Command Panel (MAM Review)_ME_fs2_pop.pdf
14 20 00-010-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-010-00 Elevator Closeout Submittals | Closed | Vertical Transportation, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-30 | Sent and Closed - For Construction |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-08-13 |  | 27 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2021-08-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14164 | Received | For Review | 2021-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-08-13 | Submittal Number: 14 20 00-10.0 From: TYRONE THORNTON Final Due Date: 08/12/21 Subject: ELEVATOR CLOSEOUT SUBMITTALS Description: OPERATIONS AND MAINTENANCE DATA FINAL ACCEPTANCE CERTIFICATES & OPERATING CERTIFICATES WARRANTY KEYS CONTINUING MAINTENANCE PROPOSAL Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 18311 | Forwarded | For Review | 2021-07-29 | Shaina Burris (Populous) | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2021-08-05 | Submittal Number: 14 20 00-10.0 From: TYRONE THORNTON Final Due Date: 08/12/21 Subject: ELEVATOR CLOSEOUT SUBMITTALS Description: OPERATIONS AND MAINTENANCE DATA FINAL ACCEPTANCE CERTIFICATES & OPERATING CERTIFICATES WARRANTY KEYS CONTINUING MAINTENANCE PROPOSAL Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 14494 | Review Response | Revise and Resubmit | 2021-08-24 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  | The warranty and maintenance agreement are not in line with the specifications and TKE bid. Please revise these portions only of the submittal and resubmit. | Info Exchange
| 14466 | Review Response | Approved as Noted/Resubmit | 2021-08-25 | Scott Shepler (Fortune Shepler Saling FS2EC) | Tom Usher (Populous) |  | Pending response (Revise and Resubmit) from: Scott Shepler (Fortune Shepler Saling FS2EC) Remarks: The warranty and maintenance agreement are not in line with the specifications and TKE bid. Please revise these portions only of the submittal and resubmit. | Info Exchange
| 18660 | Sent and Closed | For Construction | 2021-08-25 | Tom Usher (Populous) | Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Scott Shepler (Fortune Shepler Saling FS2EC) Remarks: The warranty and maintenance agreement are not in line with the specifications and TKE bid. Please revise these portions only of the submittal and resubmit. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-29 |  | 14 20 00-10.0 - Elevator Closeout Submittals.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-29 |  | 14 20 00-10.0 - Elevator Closeout Submittals.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2021-07-28 02:00 |  | 14 20 00-10.0 - Elevator Closeout Submittals.pdf
| Sent and Closed |  | Tom Usher (Populous) | 1 | 2021-07-29 |  | 14 20 00-10.0 - Elevator Closeout Submittals.pdf
14 20 00-011-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-011-00 Elevator P9 (C1) Stamped Drawings to Pull Permit | Closed | Vertical Transportation, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted/Resubmit |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-01-18 | 2021-01-11 | 8 |  | Record Copies; Transfers; Submittals | 14 20 00-011-00-01 - 14 20 00-011-00 Elevator P9 (C1) Stamped Drawings to Pull Permit | 4 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10384 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2021-01-18 | Submittal Number: 14 20 00-11.0 From: JES PELKEY Final Due Date: 01/13/21 Subject: ELEVATOR P9 (C1) STAMPED DRAWINGS TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 13568 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2021-01-11 | Submittal Number: 14 20 00-11.0 From: JES PELKEY Final Due Date: 01/13/21 Subject: ELEVATOR P9 (C1) STAMPED DRAWINGS TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 10569 | Review Response | Approved as Noted | 2021-01-05 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has not reviewed anything related to elevator P11 within this submittal and has only reviewed information pertaining to elevator P9. | Info Exchange
| 10570 | Review Response | Approved as Noted | 2021-01-07 | Scott Shepler (Fortune Shepler Saling FS2EC) | Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) |  | Reviewed P9 only per transmittal. | Info Exchange
| 13778 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-11 | Todd Spangler (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-29 |  | 14 20 00-11.0 Elevator P9 (C1) Stamped Drawings to Pull Permit (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-29 |  | 14 20 00-11.0 Elevator P9 (C1) Stamped Drawings to Pull Permit (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-29 |  | 14 20 00-11.0 Elevator P9 (C1) Stamped Drawings to Pull Permit (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-12-29 |  | 14 20 00-11.0 Elevator P9 (C1) Stamped Drawings to Pull Permit (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-01-11 |  | 14 20 00-11.0 Elevator P9 (C1) Stamped Drawings to Pull Permit (MAM Review)_TT_FS2_POP.pdf
14 20 00-011-00-01 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-011-00 Elevator P9 (C1) Stamped Drawings to Pull Permit | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 14 20 00-011-00 - 14 20 00-011-00 Elevator P9 (C1) Stamped Drawings to Pull Permit | -1 | 2021-01-25
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 14 20 00-11.0 Elevator P9 (C1) Stamped Drawings to Pull Permit (MAM Review)_TT_FS2_POP.pdf
14 20 00-012-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-012-00 Elevator P4 (A5) Engineered Drawings to be Submitted for Permit | Closed | Vertical Transportation, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-14 | Responded and Closed - Approved |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-01-06 | 2020-12-15 | 2 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10113 | Received | For Review | 2020-12-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-06 | Submittal Number: 14 20 00-12.0 From: JES PELKEY Final Due Date: 12/29/20 Subject: ELEVATOR P4 (A5) ENGINEERED DRAWINGS TO BE SUBMITTED FOR PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 13222 | Forwarded | For Review | 2020-12-11 | Populous SCA_CCA | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2020-12-18 | Submittal Number: 14 20 00-12.0 From: JES PELKEY Final Due Date: 12/29/20 Subject: ELEVATOR P4 (A5) ENGINEERED DRAWINGS TO BE SUBMITTED FOR PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 10179 | Review Response | Approved | 2020-12-15 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 13315 | Responded and Closed | Approved | 2020-12-15 | Populous SCA_CCA | Jes Pelkey (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | TT has no exceptions. POP has no exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-11 |  | 05 12 00-12.0 A5 Elevator SD for Permit-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-11 |  | 05 12 00-12.0 A5 Elevator SD for Permit-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-11 |  | 05 12 00-12.0 A5 Elevator SD for Permit-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-15 |  | 14 20 00-12.0 A5 Elevator SD for Permit-MAM_TT_POP.pdf
14 20 00-013-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-013-00 Elevator P10 (C4) Stamped Drawings to Pull Permit | Closed | Vertical Transportation, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-22 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-01-14 | 2021-01-11 | 21 |  | Record Copies; Transfers; Markups; Submittals |  | 17 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10291 | Received | For Review | 2020-12-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-14 | Submittal Number: 14 20 00-13.0 From: JES PELKEY Final Due Date: 01/06/21 Subject: ELEVATOR P10 (C4) STAMPED DRAWINGS TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 13451 | Forwarded | For Review | 2020-12-21 | Populous SCA_CCA | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2020-12-28 | Submittal Number: 14 20 00-13.0 From: JES PELKEY Final Due Date: 01/06/21 Subject: ELEVATOR P10 (C4) STAMPED DRAWINGS TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 10567 | Review Response | Approved as Noted | 2021-01-05 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 10568 | Review Response | Approved as Noted | 2021-01-06 | Scott Shepler (Fortune Shepler Saling FS2EC) | Populous SCA_CCA |  |  | Info Exchange
| 13776 | Responded and Closed | Approved as Noted | 2021-01-11 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. Clacs do not match. A final fully approved stamp cannot be provided at this time. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-21 |  | 14 20 00-13.0 Elevator C2 Stamped Drawings for Permit-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-21 |  | 14 20 00-13.0 Elevator C2 Stamped Drawings for Permit-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-21 |  | 14 20 00-13.0 Elevator C2 Stamped Drawings for Permit-MAM.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-12-21 |  | 14 20 00-13.0 Elevator C2 Stamped Drawings for Permit-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-11 |  | 14 20 00-13.0 Elevator C2 Stamped Drawings for Permit-MAM_TT_FS2_POP.pdf
14 20 00-014-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-014-00 Elevator P8 (B4) Shop Drawings - To Pull Permit | Closed | Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-03-02 | 2021-03-08 | 21 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11451 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-02 | Submittal Number: 14 20 00-14.0 From: JES PELKEY Final Due Date: 03/02/21 Subject: ELEVATOR P8 (B4) SHOP DRAWINGS - TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 14833 | Forwarded | For Review | 2021-02-16 | Populous SCA_CCA | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2021-02-23 | Submittal Number: 14 20 00-14.0 From: JES PELKEY Final Due Date: 03/02/21 Subject: ELEVATOR P8 (B4) SHOP DRAWINGS - TO PULL PERMIT Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 11836 | Review Response | Approved | 2021-02-16 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 11837 | Review Response | Approved | 2021-02-23 | Scott Shepler (Fortune Shepler Saling FS2EC) | Populous SCA_CCA |  |  | Info Exchange
| 15344 | Responded and Closed | Approved | 2021-03-08 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 14 20 00-14.0 Elevator P8 (B4) SD for Permit-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-15 |  | 14 20 00-14.0 Elevator P8 (B4) SD for Permit-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-15 |  | 14 20 00-14.0 Elevator P8 (B4) SD for Permit-MAM.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2021-02-15 |  | 14 20 00-14.0 Elevator P8 (B4) SD for Permit-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-08 |  | 14 20 00-14.0 Elevator P8 (B4) SD for Permit-MAM_TT_POP.pdf
14 20 00-015-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-015-00 Elevator Knox Box Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-24 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Tom Usher (Populous) |  |  |  | 2021-03-10 | 2021-02-24 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11618 | Received | For Review | 2021-02-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-03-10 | Submittal Number: 14 20 00-15.0 From: TYRONE THORNTON Final Due Date: 03/09/21 Subject: 14 20 00 - ELEVATOR KNOX BOX PRODUCT DATA Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 15057 | Forwarded | For Review | 2021-02-24 | Tyrone Thornton (Mortenson Construction) | Todd Spangler (Populous); Tom Usher (Populous) | 2021-03-03 | Submittal Number: 14 20 00-15.0 From: TYRONE THORNTON Final Due Date: 03/09/21 Subject: 14 20 00 - ELEVATOR KNOX BOX PRODUCT DATA Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 15074 | Responded and Closed | Approved as Noted | 2021-02-24 | Tyrone Thornton (Mortenson Construction) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-23 02:00 |  | 14 20 00 - Elevator Knox Box - Product Data.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-02-23 02:00 |  | 14 20 00 - Elevator Knox Box - Product Data.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-02-24 02:00 |  | 14 20 00-015-00 - Elevator Knox Box - Product Data_MAM_POP.pdf
14 20 00-016-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-016-00 Elevator Control Panels - Updated | Closed | Architectural, Vertical Transportation, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-26 | Responded and Closed - Approved as Noted |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC) |  |  |  | 2021-03-12 | 2021-03-04 | 7 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-03-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11688 | Received | For Review | 2021-02-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-12 | Submittal Number: 14 20 00-16.0 From: JES PELKEY Final Due Date: 03/11/21 Subject: ELEVATOR CONTROL PANELS - UPDATED Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 15145 | Forwarded | For Review | 2021-03-01 | Populous SCA_CCA | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC) | 2021-03-08 | Submittal Number: 14 20 00-16.0 From: JES PELKEY Final Due Date: 03/11/21 Subject: ELEVATOR CONTROL PANELS - UPDATED Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 11782 | Review Response | Approved as Noted | 2021-03-03 | Scott Shepler (Fortune Shepler Saling FS2EC) | Populous SCA_CCA |  |  | Info Exchange
| 15284 | Responded and Closed | Approved as Noted | 2021-03-04 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-26 02:00 |  | 14 20 00-16.0 Elevator Control Panel SD-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-26 02:00 |  | 14 20 00-16.0 Elevator Control Panel SD-MAM.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2021-02-26 |  | 14 20 00-16.0 Elevator Control Panel SD-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-04 |  | 14 20 00-16.0 Elevator Control Panel SD-MAM_FS2_POP.pdf
14 20 00-017-00 | 14 20 00 - TRACTION ELEVATORS | 14 20 00-017-00 Elevator Knox Box 1400 Series Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-04 | Review Response - Approved |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-03-18 | 2021-03-08 | 5 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11787 | Received | For Review | 2021-03-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Tyrone Thornton (Mortenson Construction) | 2021-03-18 | Submittal Number: 14 20 00-17.0 From: TYRONE THORNTON Final Due Date: 03/17/21 Subject: 14 20 00 - ELEVATOR KNOX BOX 1400 SERIES PRODUCT DATA Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 15275 | Forwarded | For Review | 2021-03-04 | Tyrone Thornton (Mortenson Construction) | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2021-03-11 | Submittal Number: 14 20 00-17.0 From: TYRONE THORNTON Final Due Date: 03/17/21 Subject: 14 20 00 - ELEVATOR KNOX BOX 1400 SERIES PRODUCT DATA Description: Spec Section: 14 20 00 - TRACTION ELEVATORS Status: OPEN | Info Exchange
| 15345 | Responded and Closed | Approved as Noted | 2021-03-08 | Tyrone Thornton (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 11924 | Review Response | Approved | 2021-03-10 | Scott Shepler (Fortune Shepler Saling FS2EC) | Tyrone Thornton (Mortenson Construction) |  | POP to designate color selection. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-03 |  | 14 20 00 - Elevator Knox Box 1400 Product Data_MAM Review.pdf
| Forwarded |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-03-03 |  | 14 20 00 - Elevator Knox Box 1400 Product Data_MAM Review.pdf
| Responded and Closed |  | Tyrone Thornton (Mortenson Construction) | 1 | 2021-03-08 |  | 14 20 00 - Elevator Knox Box 1400 Product Data_MAM_POP.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2021-03-02 02:00 |  | 14 20 00 - Elevator Knox Box 1400 Product Data_MAM Review.pdf
14 30 00-001-00 | 14 30 00 - ESCALATORS | 14 30 00-001-00 Escalator Product Data | Closed | Architectural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-12-09 08:00 | 2019-11-26 | 6 |  | Record Copies; Transfers; Submittals | 14 30 00-001-01 - 14 30 00-001-00 Escalator Product Data | 6 |  | 2019-11-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03311 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-12-09 08:00 | Submittal Number: 14 30 00-1.0 From: NATE WEINGART Final Due Date: 12/06/19 Subject: ESCALATOR PRODUCT DATA Description: PRODUCT DATA : INCLUDE PRODUCT DATA FOR SAFETY FEATURES, OPERATING SYSTEM DESCRIPTIONS, SEQUENCE OF OPERATIONS, AND EQUIPMENT LISTS. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 04765 | Forwarded | For Review | 2019-11-21 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti) | 2019-11-27 | Submittal Number: 14 30 00-1.0 From: NATE WEINGART Final Due Date: 12/06/19 Subject: ESCALATOR PRODUCT DATA Description: PRODUCT DATA : INCLUDE PRODUCT DATA FOR SAFETY FEATURES, OPERATING SYSTEM DESCRIPTIONS, SEQUENCE OF OPERATIONS, AND EQUIPMENT LISTS. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 04769 | Forwarded | For Review | 2019-11-21 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2019-11-28 | Submittal Number: 14 30 00-1.0 From: NATE WEINGART Final Due Date: 12/06/19 Subject: ESCALATOR PRODUCT DATA Description: PRODUCT DATA : INCLUDE PRODUCT DATA FOR SAFETY FEATURES, OPERATING SYSTEM DESCRIPTIONS, SEQUENCE OF OPERATIONS, AND EQUIPMENT LISTS. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 03324 | Review Response | Approved | 2019-11-21 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  | Approved Escalator Product Data for Seattle Center is attached. Scott Shepler Principal Fortune Shepler Saling (720) 438.1540 www.fs2ec.com | Info Exchange
| 04835 | Forwarded | For Review | 2019-11-26 | Todd Spangler (Populous) | Tom Usher (Populous) | 2019-11-26 | Submittal Number: 14 30 00-1.0 From: NATE WEINGART Final Due Date: 12/06/19 Subject: ESCALATOR PRODUCT DATA Description: PRODUCT DATA : INCLUDE PRODUCT DATA FOR SAFETY FEATURES, OPERATING SYSTEM DESCRIPTIONS, SEQUENCE OF OPERATIONS, AND EQUIPMENT LISTS. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 04840 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-26 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for review and comments. Submit required finish samples per spec. | Info Exchange
| 03390 | Review Response | Approved as Noted | 2019-11-26 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2019.11.26 | Info Exchange
| 04856 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2019.11.26 Response (Approved) from: Scott Shepler (Fortune Shepler Saling FS2EC) Remarks: Approved Escalator Product Data for Seattle Center is attached. Scott Shepler Principal Fortune Shepler Saling (720) 438.1540 www.fs2ec.com Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) Remarks: See attached for review and comments. Submit required finish samples per spec. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-21 |  | 143000-1.0 Escalator Product Data (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-21 |  | 143000-1.0 Escalator Product Data (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-20 02:00 |  | 143000-1.0 Escalator Product Data (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2019-11-21 02:00 |  | 143000-1.0 Escalator Product Data (MAM Review) FS2 Review.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-11-21 |  | 143000-1.0 Escalator Product Data (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-11-26 |  | 143000-1.0 Escalator Product Data (MAM Review) FS2 POP.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-11-20 02:00 |  | 143000-1.0 Escalator Product Data (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-26 02:00 |  | 143000-1.0 Escalator Product Data (MAM Review) FS2 POP_ME.pdf
14 30 00-001-01 | 14 30 00 - ESCALATORS | 14 30 00-001-00 Escalator Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 14 30 00-001-00 - 14 30 00-001-00 Escalator Product Data | -1 | 2019-12-10
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-26 02:00 |  | 143000-1.0 Escalator Product Data (MAM Review) FS2 POP_ME.pdf
14 30 00-002-00 | 14 30 00 - ESCALATORS | 14 30 00-002-00 Escalator Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-30 | Responded and Closed - Revise and Resubmit |  | Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Mark Lievens (ME Engineers) |  |  |  | 2019-10-14 | 2019-10-09 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-10-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02579 | Received | For Review | 2019-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-10-14 | Submittal Number: 14 30 00-2.0 From: JES PELKEY Final Due Date: 10/11/19 Subject: ESCALATOR SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. UNLESS STIPULATED ELSEWHERE IN THE GENERAL AND SUPPLEMENTARY CONDITIONS, PROVIDE ELECTRONIC SCALED SHOP DRAWINGS IN 2D CADD OF PLANS, ELEVATIONS, SECTIONS AND DETAILS INDICATING WELLWAYS, ENCLOSURES, GUARDS, AND LOCATION OF EQUIPMENT. INCLUDE DETAILS OF AREAS WHERE ESCALATOR EQUIPMENT JOINS OTHER FINISH WORK. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 03866 | Forwarded | For Review | 2019-09-30 | Shaina Burris (Populous) | Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous) |  | Submittal Number: 14 30 00-2.0 From: JES PELKEY Final Due Date: 10/11/19 Subject: ESCALATOR SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. UNLESS STIPULATED ELSEWHERE IN THE GENERAL AND SUPPLEMENTARY CONDITIONS, PROVIDE ELECTRONIC SCALED SHOP DRAWINGS IN 2D CADD OF PLANS, ELEVATIONS, SECTIONS AND DETAILS INDICATING WELLWAYS, ENCLOSURES, GUARDS, AND LOCATION OF EQUIPMENT. INCLUDE DETAILS OF AREAS WHERE ESCALATOR EQUIPMENT JOINS OTHER FINISH WORK. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 03904 | Forwarded | For Review | 2019-10-01 | Todd Spangler (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) |  | Submittal Number: 14 30 00-2.0 From: JES PELKEY Final Due Date: 10/11/19 Subject: ESCALATOR SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. UNLESS STIPULATED ELSEWHERE IN THE GENERAL AND SUPPLEMENTARY CONDITIONS, PROVIDE ELECTRONIC SCALED SHOP DRAWINGS IN 2D CADD OF PLANS, ELEVATIONS, SECTIONS AND DETAILS INDICATING WELLWAYS, ENCLOSURES, GUARDS, AND LOCATION OF EQUIPMENT. INCLUDE DETAILS OF AREAS WHERE ESCALATOR EQUIPMENT JOINS OTHER FINISH WORK. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 03910 | Forwarded | For Review | 2019-10-01 | Todd Spangler (Populous) | Mark Lievens (ME Engineers) |  | Submittal Number: 14 30 00-2.0 From: JES PELKEY Final Due Date: 10/11/19 Subject: ESCALATOR SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. UNLESS STIPULATED ELSEWHERE IN THE GENERAL AND SUPPLEMENTARY CONDITIONS, PROVIDE ELECTRONIC SCALED SHOP DRAWINGS IN 2D CADD OF PLANS, ELEVATIONS, SECTIONS AND DETAILS INDICATING WELLWAYS, ENCLOSURES, GUARDS, AND LOCATION OF EQUIPMENT. INCLUDE DETAILS OF AREAS WHERE ESCALATOR EQUIPMENT JOINS OTHER FINISH WORK. A. INCLUDE REACTIONS, HEAT EMISSIONS, AND LOCATION OF OPERATING DEVICES ON LAYOUTS. 2. POWER CONFIRMATION SHEETS: INCLUDE HP (KW), CODE LETTER, ACCELERATING CURRENT, FULL-LOAD RUNNING CURRENT, DEMAND FACTOR AND REGENERATIVE LOADS FOR APPLICABLE MOTORS AND POWER CONVERSION UNITS. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 02706 | Review Response | Revise and Resubmit | 2019-10-08 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.10.08 | Info Exchange
| 04047 | Responded and Closed | Revise and Resubmit | 2019-10-09 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-27 |  | 143000-2.0 Escalator Shop Drawings (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-27 |  | 143000-2.0 Escalator Shop Drawings (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-09-27 |  | 143000-2.0 Escalator Shop Drawings (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-09-27 |  | 143000-2.0 Escalator Shop Drawings (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-09-26 02:00 |  | 143000-2.0 Escalator Shop Drawings (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-09 |  | 143000-2.0 Escalator Shop Drawings (MAM Review)_FS2 Review_POP_ME_TT REVIEW.pdf
14 30 00-002-01 | 14 30 00 - ESCALATORS | 14 30 00-002-01 Escalator Shop Drawing Resubmittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-31 | Responded and Closed - Approved as Noted/Resubmit |  | Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Mark Lievens (ME Engineers), Matt Ross (Thornton Tomasetti) |  |  |  | 2019-11-14 | 2019-11-12 | 13 |  | Record Copies; Transfers; Submittals | 14 30 00-002-02 - 14 30 00-002-02 Escalator SD Resubmittal for Record | 13 |  | 2019-11-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02984 | Received | For Review | 2019-10-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-11-14 | Submittal Number: 14 30 00-2.1 From: NATE WEINGART Final Due Date: 11/14/19 Subject: ESCALATOR SHOP DRAWING RESUBMITTAL Description: Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 04369 | Forwarded | For Review | 2019-10-30 | Shaina Burris (Populous) | Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous) | 2019-11-06 | Submittal Number: 14 30 00-2.1 From: NATE WEINGART Final Due Date: 11/14/19 Subject: ESCALATOR SHOP DRAWING RESUBMITTAL Description: Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 04386 | Forwarded | For Review | 2019-10-31 | Todd Spangler (Populous) | Mark Lievens (ME Engineers); Matt Ross (Thornton Tomasetti) | 2019-11-06 | Submittal Number: 14 30 00-2.1 From: NATE WEINGART Final Due Date: 11/14/19 Subject: ESCALATOR SHOP DRAWING RESUBMITTAL Description: Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 03129 | Review Response | Approved as Noted | 2019-11-08 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | See TT comments in markup. | Info Exchange
| 03140 | Review Response | Approved as Noted | 2019-11-06 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  | Escalator shops are attached returned AAN. Scott Shepler Principal Fortune Shepler Saling (720) 438.1540 www.fs2ec.com | Info Exchange
| 03162 | Review Response | Approved as Noted | 2019-11-11 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens 2019.11.11 ME Engineers | Info Exchange
| 04582 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-12 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached for review and comments. Resubmit for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-30 |  | 143000-2.1 Escalator Shop Drawing Resubmittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-30 |  | 143000-2.1 Escalator Shop Drawing Resubmittal (MAM Review).pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2019-10-30 |  | 143000-2.1 Escalator Shop Drawing Resubmittal (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-30 |  | 143000-2.1 Escalator Shop Drawing Resubmittal (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2019-11-08 02:00 |  | 143000-2.1 Escalator Shop Drawing Resubmittal (MAM Review)_FS2.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-10-30 |  | 143000-2.1 Escalator Shop Drawing Resubmittal (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-11-12 |  | 143000-2.1 Escalator Shop Drawing Resubmittal_MAM_FS2_ME_TT_POP.pdf
14 30 00-002-02 | 14 30 00 - ESCALATORS | 14 30 00-002-02 Escalator SD Resubmittal for Record | Closed | Architectural, Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-05 | Responded and Closed - No Action Taken or Required |  | Todd Spangler (Populous), Tom Usher (Populous), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC) |  |  |  | 2019-12-19 | 2019-12-16 | 12 |  | Record Copies; Transfers; Submittals | 14 30 00-002-01 - 14 30 00-002-01 Escalator Shop Drawing Resubmittal | 8 | 2019-11-26 | 2019-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03517 | Received | For Review | 2019-12-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2019-12-19 | Submittal Number: 14 30 00-2.2 From: NATE WEINGART Final Due Date: 12/19/19 Subject: ESCALATORS - RESUBMITTAL FOR RECORD Description: Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 05024 | Forwarded | For Review | 2019-12-09 | Josh Dobken (Populous) | Todd Spangler (Populous); Tom Usher (Populous); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC) | 2019-12-16 | Submittal Number: 14 30 00-2.2 From: NATE WEINGART Final Due Date: 12/19/19 Subject: ESCALATORS - RESUBMITTAL FOR RECORD Description: Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 05168 | Responded and Closed | No Action Taken or Required | 2019-12-16 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | Received for record only | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-04 02:00 |  | 143000-2.2 Escalators - Resubmittal for Record (MAM Review).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-04 02:00 |  | 143000-2.2 Escalators - Resubmittal for Record (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-04 02:00 |  | 143000-2.2 Escalators - Resubmittal for Record (MAM Review).pdf
14 30 00-002-03 | 14 30 00 - ESCALATORS | 14 30 00-002-03 Escalator Shop Drawings Stamped by Local Engineer | Closed | Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-21 | Review Response - Approved |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-03-06 | 2020-02-27 | 7 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04438 | Received | For Review | 2020-02-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-03-06 | Submittal Number: 14 30 00-2.3 From: NATE WEINGART Final Due Date: 03/06/20 Subject: ESCALATOR SHOP DRAWINGS STAMPED BY LOCAL ENGINEER Description: Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 06126 | Forwarded | For Review | 2020-02-21 | Shaina Burris (Populous) | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2020-02-28 | Submittal Number: 14 30 00-2.3 From: NATE WEINGART Final Due Date: 03/06/20 Subject: ESCALATOR SHOP DRAWINGS STAMPED BY LOCAL ENGINEER Description: Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 04552 | Review Response | Approved | 2020-02-27 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. | Info Exchange
| 06266 | Responded and Closed | Approved as Noted | 2020-02-27 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | See attached for review and comments. | Info Exchange
| 04643 | Review Response | Approved | 2020-03-03 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  | Approved Escalator shops with local engineers stamp. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-20 |  | 143000-2.3 Escalator Shop Drawings Stamped by Local Engineer (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-20 |  | 143000-2.3 Escalator Shop Drawings Stamped by Local Engineer (MAM Review).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-20 |  | 143000-2.3 Escalator Shop Drawings Stamped by Local Engineer (MAM Review).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-02-27 |  | 143000-2.3 Escalator Shop Drawings Stamped_MAM_TT_POP.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-02-19 02:00 |  | 143000-2.3 Escalator Shop Drawings Stamped by Local Engineer (MAM Review).pdf
14 30 00-002-04 | 14 30 00 - ESCALATORS | 14 30 00-002-04 Escalators - Shop Drawings for Post-Permit Submittal | Closed | Vertical Transportation | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-18 | Responded and Closed - Approved |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-06-02 07:00 | 2020-06-04 | 18 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05907 | Received | For Review | 2020-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (M.A. Mortenson Company) | 2020-06-02 07:00 | Submittal Number: 14 30 00-2.4 From: NATE WEINGART Final Due Date: 05/29/20 Subject: ESCALATORS - SHOP DRAWINGS FOR POST-PERMIT SUBMITTAL Description: Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 08012 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2020-05-25 | Submittal Number: 14 30 00-2.4 From: NATE WEINGART Final Due Date: 05/29/20 Subject: ESCALATORS - SHOP DRAWINGS FOR POST-PERMIT SUBMITTAL Description: Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 06213 | Review Response | Approved | 2020-05-20 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  |  | Info Exchange
| 06214 | Review Response | Approved | 2020-06-01 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.01 | Info Exchange
| 06215 | Review Response | Approved | 2020-06-01 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. | Info Exchange
| 08393 | Responded and Closed | Approved | 2020-06-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company) |  | Response (Approved) from: Scott Shepler (Fortune Shepler Saling FS2EC) Remarks: Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.01 Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 143000-2.4 Escalators - Shop Drawings for Post-Permit Submittal (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 143000-2.4 Escalators - Shop Drawings for Post-Permit Submittal (MAM Review).pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2020-05-17 02:00 |  | 143000-2.4 Escalators - Shop Drawings for Post-Permit Submittal (MAM Review).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-06-02 02:00 |  | 143000-2.4 Escalators - Shop Drawings for Post-Permit Submittal (MAM Review)-ME.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-17 02:00 |  | 143000-2.4 Escalators - Shop Drawings for Post-Permit Submittal (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-04 02:00 |  | 143000-2.4 Escalators - Shop Drawings for Post-Permit Submittal (MAM Review)-FS2_ME_TT_POP.pdf
14 30 00-003-00 | 14 30 00 - ESCALATORS | 14 30 00-003-00 Escalator Finish Sample | Closed | Vertical Transportation, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Approved |  | Tom Usher (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2020-01-10 | 2020-01-10 | 24 | General | Record Copies; Transfers; Submittals |  | 24 |  | 2020-01-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03682 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Nate Weingart (Mortenson Construction) | 2020-01-10 | Submittal Number: 14 30 00-3.0 From: NATE WEINGART Final Due Date: 01/03/20 Subject: ESCALATOR FINISH SAMPLE Description: FINISH SAMPLES 1. UNLESS STIPULATED ELSEWHERE IN THE GENERAL AND SUPPLEMENTARY CONDITIONS, INCLUDEA MINIMUM OF SIX (6): A. 4 INCH SQUARE SAMPLES OF EXPOSED FINISH MATERIAL. B. 6 INCH LENGTH OF HANDRAIL. 2. SAMPLES SHALL BE LABELED WITH PROJECT NAME AND DESCRIPTION OF SAMPLE. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 05202 | Forwarded | For Review | 2019-12-18 | Shaina Burris (Populous) | Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-12-25 | Submittal Number: 14 30 00-3.0 From: NATE WEINGART Final Due Date: 01/03/20 Subject: ESCALATOR FINISH SAMPLE Description: FINISH SAMPLES 1. UNLESS STIPULATED ELSEWHERE IN THE GENERAL AND SUPPLEMENTARY CONDITIONS, INCLUDEA MINIMUM OF SIX (6): A. 4 INCH SQUARE SAMPLES OF EXPOSED FINISH MATERIAL. B. 6 INCH LENGTH OF HANDRAIL. 2. SAMPLES SHALL BE LABELED WITH PROJECT NAME AND DESCRIPTION OF SAMPLE. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 05433 | Responded and Closed | Approved | 2020-01-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (Mortenson Construction) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 143000-3.0 Escalator Finish Sample (MAM Review).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-18 |  | 143000-3.0 Escalator Finish Sample (MAM Review).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-10 02:00 |  | 143000-3.0 Escalator Finish Sample (MAM Review)_POP.pdf
14 30 00-004-00 | 14 30 00 - ESCALATORS | 14 30 00-004-00 Escalator Closeout Submittals | Closed | Vertical Transportation, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-21 | Sent and Closed - For Construction |  | Todd Spangler (Populous), Mark Lievens (ME Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Darci Mills (Fortune Shepler Saling FS2EC), Scott Shepler (Fortune Shepler Saling FS2EC), Chris Minter (Populous), Josh Dobken (Populous), Matt Ross (Thornton Tomasetti), Chad Francis (Populous) |  |  |  | 2021-08-04 |  | 36 |  | Record Copies; Transfers; Submittals |  | 36 |  | 2021-08-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14039 | Received | For Review | 2021-07-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2021-08-04 | Submittal Number: 14 30 00-4.0 From: TYRONE THORNTON Final Due Date: 08/04/21 Subject: ESCALATOR CLOSEOUT SUBMITTALS Description: OPERATIONS AND MAINTENANCE DATA: INCLUDE OPERATIONS, LUBRICATION SCHEDULES AND RECOMMENDED LUBRICANTS, MAINTENANCE ROUTINES, AND PARTS MANUALS IN BOTH HARD COPY AND ELECTRONIC VERSION. A. INCLUDE STRAIGHT-LINE, INDEXED, WIRING DIAGRAMS OF INSTALLED ESCALATOR CIRCUITS. B. INCLUDE ANY SPECIAL DIAGNOSTIC TOOLS REQUIRED FOR MAINTENANCE. DISREGARD TK SUBMISSION. DOCUMENTS TRANSMITTED VIA EMAIL. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 18162 | Forwarded | For Review | 2021-07-21 | Shaina Burris (Populous) | Todd Spangler (Populous); Mark Lievens (ME Engineers); Tom Usher (Populous); Nick Theimer (ME Engineers); Darci Mills (Fortune Shepler Saling FS2EC); Scott Shepler (Fortune Shepler Saling FS2EC); Chris Minter (Populous); Josh Dobken (Populous); Matt Ro... | 2021-07-28 | Submittal Number: 14 30 00-4.0 From: TYRONE THORNTON Final Due Date: 08/04/21 Subject: ESCALATOR CLOSEOUT SUBMITTALS Description: OPERATIONS AND MAINTENANCE DATA: INCLUDE OPERATIONS, LUBRICATION SCHEDULES AND RECOMMENDED LUBRICANTS, MAINTENANCE ROUTINES, AND PARTS MANUALS IN BOTH HARD COPY AND ELECTRONIC VERSION. A. INCLUDE STRAIGHT-LINE, INDEXED, WIRING DIAGRAMS OF INSTALLED ESCALATOR CIRCUITS. B. INCLUDE ANY SPECIAL DIAGNOSTIC TOOLS REQUIRED FOR MAINTENANCE. DISREGARD TK SUBMISSION. DOCUMENTS TRANSMITTED VIA EMAIL. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 18647 | Forwarded | For Review | 2021-08-24 | Shaina Burris (Populous) | Scott Shepler (Fortune Shepler Saling FS2EC) |  | Submittal Number: 14 30 00-4.0 From: TYRONE THORNTON Final Due Date: 08/04/21 Subject: ESCALATOR CLOSEOUT SUBMITTALS Description: OPERATIONS AND MAINTENANCE DATA: INCLUDE OPERATIONS, LUBRICATION SCHEDULES AND RECOMMENDED LUBRICANTS, MAINTENANCE ROUTINES, AND PARTS MANUALS IN BOTH HARD COPY AND ELECTRONIC VERSION. A. INCLUDE STRAIGHT-LINE, INDEXED, WIRING DIAGRAMS OF INSTALLED ESCALATOR CIRCUITS. B. INCLUDE ANY SPECIAL DIAGNOSTIC TOOLS REQUIRED FOR MAINTENANCE. DISREGARD TK SUBMISSION. DOCUMENTS TRANSMITTED VIA EMAIL. Spec Section: 14 30 00 - ESCALATORS Status: OPEN | Info Exchange
| 14493 | Review Response | Revise and Resubmit | 2021-08-24 | Scott Shepler (Fortune Shepler Saling FS2EC) | Shaina Burris (Populous) |  | Revise and resubmit page 1888 only - Warranty to be revised to include overtime callbacks per specifications and TKE bid. | Info Exchange
| 14465 | Review Response | Approved as Noted/Resubmit | 2021-08-25 | Scott Shepler (Fortune Shepler Saling FS2EC) | Tom Usher (Populous) |  | Pending response (Revise and Resubmit) from: Scott Shepler (Fortune Shepler Saling FS2EC) Remarks: Revise and resubmit page 1888 only - Warranty to be revised to include overtime callbacks per specifications and TKE bid. | Info Exchange
| 18659 | Sent and Closed | For Construction | 2021-08-25 | Tom Usher (Populous) | Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Scott Shepler (Fortune Shepler Saling FS2EC) Remarks: Revise and resubmit page 1888 only - Warranty to be revised to include overtime callbacks per specifications and TKE bid. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-21 |  | 14 30 00-4.0 - Escalator Closeout Submittals.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-21 |  | 14 30 00-4.0 - Escalator Closeout Submittals.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-21 |  | 14 30 00-4.0 - Escalator Closeout Submittals.pdf
| Review Response |  | Scott Shepler (Fortune Shepler Saling FS2EC) | 1 | 2021-07-20 02:00 |  | 14 30 00-4.0 - Escalator Closeout Submittals.pdf
| Sent and Closed |  | Tom Usher (Populous) | 1 | 2021-07-21 |  | 14 30 00-4.0 - Escalator Closeout Submittals.pdf
21 13 00-001-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-001-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - Upper Bowl Shop Drawings | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-29 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-11-12 | 2019-11-04 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-11-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02956 | Received | For Review | 2019-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2019-11-12 | Submittal Number: 21 13 00-1.0 From: SIMRAN GEORGE Final Due Date: 11/11/19 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - UPPER BOWL SHOP DRAWINGS Description: SUBMIT PLANS AND HYDRAULIC CALCULATIONS SIGNED AND SEALED BY THE PROFESSIONAL ENGINEER SUPERVISING THE DESIGN OF THE FIRE SPRINKLER SYSTEM, AND ONE (1) SET OF REPRODUCIBLE OF THE COMPLETE SHOP DRAWINGS OF THE SPRINKLER SYSTEM TO THE REGULATORY AGENCIES HAVING JURISDICTION. AFTER APPROVALS ARE OBTAINED, SUBMIT THE DRAWINGS AND HYDRAULIC CALCULATIONS TO THE ARCHITECT FOR REVIEW. WRITTEN APPROVAL OF THE ARCHITECT MUST BE OBTAINED BEFORE PURCHASING OR INSTALLING ANY EQUIPMENT. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 04334 | Forwarded | For Review | 2019-10-29 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-05 | Submittal Number: 21 13 00-1.0 From: SIMRAN GEORGE Final Due Date: 11/11/19 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - UPPER BOWL SHOP DRAWINGS Description: SUBMIT PLANS AND HYDRAULIC CALCULATIONS SIGNED AND SEALED BY THE PROFESSIONAL ENGINEER SUPERVISING THE DESIGN OF THE FIRE SPRINKLER SYSTEM, AND ONE (1) SET OF REPRODUCIBLE OF THE COMPLETE SHOP DRAWINGS OF THE SPRINKLER SYSTEM TO THE REGULATORY AGENCIES HAVING JURISDICTION. AFTER APPROVALS ARE OBTAINED, SUBMIT THE DRAWINGS AND HYDRAULIC CALCULATIONS TO THE ARCHITECT FOR REVIEW. WRITTEN APPROVAL OF THE ARCHITECT MUST BE OBTAINED BEFORE PURCHASING OR INSTALLING ANY EQUIPMENT. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 03029 | Review Response | Approved | 2019-11-04 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 4 November 2019 | Info Exchange
| 04418 | Responded and Closed | Approved | 2019-11-04 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 4 November 2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-28 |  | 21 13 00-1.0 Fire Suppresion Sprinkler Systems - Upper Bowl Sprinkler Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-28 |  | 21 13 00-1.0 Fire Suppresion Sprinkler Systems - Upper Bowl Sprinkler Shop Drawings-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-11-04 02:00 |  | 21 13 00-1.0 Fire Suppresion Sprinkler Systems - Upper Bowl Sprinkler Shop Drawings_MEE Review_4 Nov 19.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-04 02:00 |  | 21 13 00-1.0 Fire Suppresion Sprinkler Systems - Upper Bowl Sprinkler Shop Drawings_MEE Review_4 Nov 19_POP.pdf
21 13 00-002-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-002-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - Manufacturers Instructions | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Ben Muscente (Howe Engineers, Inc.), Andrew Newman (Howe Engineers, Inc.) |  |  |  | 2019-12-09 08:00 | 2019-11-25 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-11-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03297 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2019-12-09 08:00 | Submittal Number: 21 13 00-2.0 From: SIMRAN GEORGE Final Due Date: 12/04/19 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - MANUFACTURERS INSTRUCTIONS Description: SUBMIT THE FOLLOWING FOR REVIEW TO THE ARCHITECT PRIOR TO THE START OF INSTALLATION: 1. MATERIAL AND EQUIPMENT INFORMATION SHALL INCLUDE CATALOG CUTS AND TECHNICAL DATA FOR EACH SYSTEM COMPONENT OR DEVICE. THIS SHALL INCLUDE, BUT NOT BE LIMITED TO PIPING, FITTINGS, GLOBE AND ANGLE VALVES, O.S.&Y VALVES, BUTTERFLY VALVES, CHECK VALVES, AUTOMATIC SPRINKLER HEADS, ESCUTCHEONS, HANGERS, FLOW SWITCHES, TAMPER SWITCHES, ALARM VALVES, TRIM AND REQUIRED ACCESSORIES, DRY PIPE VALVES, TRIM AND REQUIRED ACCESSORIES AND AIR COMPRESSOR. 2. A COMPLETE SCHEDULE OF THE MATERIAL AND EQUIPMENT PROPOSED FOR THIS INSTALLATION. INCLUDE CATALOG CUTS, DIAGRAMS, DRAWINGS, AND SUCH OTHER DESCRIPTIVE DATA AS MAY BE REQUIRED TO CLEARLY SHOW WHAT, WHERE, AND HOW THE COMPONENT IS INTENDED TO BE INSTALLED. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 04746 | Forwarded | For Review | 2019-11-20 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-27 | Submittal Number: 21 13 00-2.0 From: SIMRAN GEORGE Final Due Date: 12/04/19 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - MANUFACTURERS INSTRUCTIONS Description: SUBMIT THE FOLLOWING FOR REVIEW TO THE ARCHITECT PRIOR TO THE START OF INSTALLATION: 1. MATERIAL AND EQUIPMENT INFORMATION SHALL INCLUDE CATALOG CUTS AND TECHNICAL DATA FOR EACH SYSTEM COMPONENT OR DEVICE. THIS SHALL INCLUDE, BUT NOT BE LIMITED TO PIPING, FITTINGS, GLOBE AND ANGLE VALVES, O.S.&Y VALVES, BUTTERFLY VALVES, CHECK VALVES, AUTOMATIC SPRINKLER HEADS, ESCUTCHEONS, HANGERS, FLOW SWITCHES, TAMPER SWITCHES, ALARM VALVES, TRIM AND REQUIRED ACCESSORIES, DRY PIPE VALVES, TRIM AND REQUIRED ACCESSORIES AND AIR COMPRESSOR. 2. A COMPLETE SCHEDULE OF THE MATERIAL AND EQUIPMENT PROPOSED FOR THIS INSTALLATION. INCLUDE CATALOG CUTS, DIAGRAMS, DRAWINGS, AND SUCH OTHER DESCRIPTIVE DATA AS MAY BE REQUIRED TO CLEARLY SHOW WHAT, WHERE, AND HOW THE COMPONENT IS INTENDED TO BE INSTALLED. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 04752 | Forwarded | For Review | 2019-11-20 | Josh Dobken (Populous) | Ben Muscente (Howe Engineers, Inc.); Andrew Newman (Howe Engineers, Inc.) | 2019-11-27 | Submittal Number: 21 13 00-2.0 From: SIMRAN GEORGE Final Due Date: 12/04/19 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - MANUFACTURERS INSTRUCTIONS Description: SUBMIT THE FOLLOWING FOR REVIEW TO THE ARCHITECT PRIOR TO THE START OF INSTALLATION: 1. MATERIAL AND EQUIPMENT INFORMATION SHALL INCLUDE CATALOG CUTS AND TECHNICAL DATA FOR EACH SYSTEM COMPONENT OR DEVICE. THIS SHALL INCLUDE, BUT NOT BE LIMITED TO PIPING, FITTINGS, GLOBE AND ANGLE VALVES, O.S.&Y VALVES, BUTTERFLY VALVES, CHECK VALVES, AUTOMATIC SPRINKLER HEADS, ESCUTCHEONS, HANGERS, FLOW SWITCHES, TAMPER SWITCHES, ALARM VALVES, TRIM AND REQUIRED ACCESSORIES, DRY PIPE VALVES, TRIM AND REQUIRED ACCESSORIES AND AIR COMPRESSOR. 2. A COMPLETE SCHEDULE OF THE MATERIAL AND EQUIPMENT PROPOSED FOR THIS INSTALLATION. INCLUDE CATALOG CUTS, DIAGRAMS, DRAWINGS, AND SUCH OTHER DESCRIPTIVE DATA AS MAY BE REQUIRED TO CLEARLY SHOW WHAT, WHERE, AND HOW THE COMPONENT IS INTENDED TO BE INSTALLED. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 03376 | Review Response | Approved | 2019-11-21 | Dave Ferguson (ME Engineers) | Josh Dobken (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 21 November 2019 | Info Exchange
| 04776 | Responded and Closed | Approved | 2019-11-25 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 21 November 2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-20 |  | 21 13 00-1.0 Fire Suppresion Sprinkler Systems - Upper Bowl Sprinkler Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-20 |  | 21 13 00-1.0 Fire Suppresion Sprinkler Systems - Upper Bowl Sprinkler Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-19 02:00 |  | 21 13 00-1.0 Fire Suppresion Sprinkler Systems - Upper Bowl Sprinkler Product Data-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-11-21 02:00 |  | 21 13 00-2.0 Fire Suppresion Sprinkler Systems - Upper Bowl Sprinkler Product Data_MEE Review_21 Nov 19.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-25 02:00 |  | 21 13 00-2.0 Fire Suppresion Sprinkler Systems - Upper Bowl Sprinkler Product Data_MEE Review_21 Nov 19_POP.pdf
21 13 00-003-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-003-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - Shell and Core Shop Drawings | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-12 | 2020-08-31 | 40 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-08-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07120 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-08-12 | Submittal Number: 21 13 00-3.0 From: SIMRAN GEORGE Final Due Date: 08/11/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - SHELL AND CORE SHOP DRAWINGS Description: SUBMIT PLANS AND HYDRAULIC CALCULATIONS SIGNED AND SEALED BY THE PROFESSIONAL ENGINEER SUPERVISING THE DESIGN OF THE FIRE SPRINKLER SYSTEM, AND ONE (1) SET OF REPRODUCIBLE OF THE COMPLETE SHOP DRAWINGS OF THE SPRINKLER SYSTEM TO THE REGULATORY AGENCIES HAVING JURISDICTION. AFTER APPROVALS ARE OBTAINED, SUBMIT THE DRAWINGS AND HYDRAULIC CALCULATIONS TO THE ARCHITECT FOR REVIEW. WRITTEN APPROVAL OF THE ARCHITECT MUST BE OBTAINED BEFORE PURCHASING OR INSTALLING ANY EQUIPMENT. PREPARE SHOP DRAWINGS SHOWING LAYOUT OF FIRE PROTECTION SYSTEM. USE MINIMUM SCALE OF 1/8 = 1-0 FOR FLOOR PLANS. DRAWINGS SHALL COORDINATE WITH ALL BUILDING STRUCTURAL FEATURES AND COMPONENTS AND SHOW ROUTING OF PIPING TO CLEAR SAME. DRAWINGS SHALL BE ACCURATELY DIMENSIONED TO SHOW PROPOSED LOCATION OF ALL FIRE PROTECTION SYSTEM COMPONENTS. SYSTEM DESIGN SHALL BE COMPLETELY COORDINATED WITH THE ARCHITECTURAL, STRUCTURAL, MECHANICAL, AND ELECTRICAL FEATURES OF THE BUILDING. THE DRAWINGS SHALL SHOW ALL DETAILS REQUIRED BY NFPA 13 - SPRINKLER SYSTEM, INSTALLATION FOR WORKING DRAWINGS. IN ALL AREAS WITH SUSPENDED CEILINGS, REFLECTED CEILING PLANS SHALL BE PREPARED SHOWING THE LOCATION OF SPRINKLERS, LIGHTS, DIFFUSERS, GRILLES, ETC. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 09511 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-30 | Submittal Number: 21 13 00-3.0 From: SIMRAN GEORGE Final Due Date: 08/11/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - SHELL AND CORE SHOP DRAWINGS Description: SUBMIT PLANS AND HYDRAULIC CALCULATIONS SIGNED AND SEALED BY THE PROFESSIONAL ENGINEER SUPERVISING THE DESIGN OF THE FIRE SPRINKLER SYSTEM, AND ONE (1) SET OF REPRODUCIBLE OF THE COMPLETE SHOP DRAWINGS OF THE SPRINKLER SYSTEM TO THE REGULATORY AGENCIES HAVING JURISDICTION. AFTER APPROVALS ARE OBTAINED, SUBMIT THE DRAWINGS AND HYDRAULIC CALCULATIONS TO THE ARCHITECT FOR REVIEW. WRITTEN APPROVAL OF THE ARCHITECT MUST BE OBTAINED BEFORE PURCHASING OR INSTALLING ANY EQUIPMENT. PREPARE SHOP DRAWINGS SHOWING LAYOUT OF FIRE PROTECTION SYSTEM. USE MINIMUM SCALE OF 1/8 = 1-0 FOR FLOOR PLANS. DRAWINGS SHALL COORDINATE WITH ALL BUILDING STRUCTURAL FEATURES AND COMPONENTS AND SHOW ROUTING OF PIPING TO CLEAR SAME. DRAWINGS SHALL BE ACCURATELY DIMENSIONED TO SHOW PROPOSED LOCATION OF ALL FIRE PROTECTION SYSTEM COMPONENTS. SYSTEM DESIGN SHALL BE COMPLETELY COORDINATED WITH THE ARCHITECTURAL, STRUCTURAL, MECHANICAL, AND ELECTRICAL FEATURES OF THE BUILDING. THE DRAWINGS SHALL SHOW ALL DETAILS REQUIRED BY NFPA 13 - SPRINKLER SYSTEM, INSTALLATION FOR WORKING DRAWINGS. IN ALL AREAS WITH SUSPENDED CEILINGS, REFLECTED CEILING PLANS SHALL BE PREPARED SHOWING THE LOCATION OF SPRINKLERS, LIGHTS, DIFFUSERS, GRILLES, ETC. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 07847 | Review Response | Approved | 2020-07-24 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 24 July 2020 | Info Exchange
| 10432 | Responded and Closed | Approved as Noted | 2020-08-31 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 21 13 00-3.0 Fire Suppresion Sprinkler Systems - Shell and Core Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | 21 13 00-3.0 Fire Suppresion Sprinkler Systems - Shell and Core Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-07-23 |  | 21 13 00-3.0 Fire Suppresion Sprinkler Systems - Shell and Core Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-08-31 |  | 21 13 00-3.0 Fire Suppresion Sprinkler Systems - Shell and Core Shop Drawings_ME_POP.pdf
21 13 00-006-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-006-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - Product Data | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-07 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-21 | 2020-01-10 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-01-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03815 | Received | For Review | 2020-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2020-01-21 | Submittal Number: 21 13 00-6.0 From: SIMRAN GEORGE Final Due Date: 01/21/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - PRODUCT DATA Description: SUBMIT THE FOLLOWING FOR THE ENTIRETY OF THE BUILDING FOR REVIEW TO THE ARCHITECT PRIOR TO THE START OF INSTALLATION: 1. MATERIAL AND EQUIPMENT INFORMATION SHALL INCLUDE CATALOG CUTS AND TECHNICAL DATA FOR EACH SYSTEM COMPONENT OR DEVICE. THIS SHALL INCLUDE, BUT NOT BE LIMITED TO PIPING, FITTINGS, GLOBE AND ANGLE VALVES, O.S.&Y VALVES, BUTTERFLY VALVES, CHECK VALVES, AUTOMATIC SPRINKLER HEADS, ESCUTCHEONS, HANGERS, FLOW SWITCHES, TAMPER SWITCHES, ALARM VALVES, TRIM AND REQUIRED ACCESSORIES, DRY PIPE VALVES, TRIM AND REQUIRED ACCESSORIES AND AIR COMPRESSOR. 2. A COMPLETE SCHEDULE OF THE MATERIAL AND EQUIPMENT PROPOSED FOR THIS INSTALLATION. INCLUDE CATALOG CUTS, DIAGRAMS, DRAWINGS, AND SUCH OTHER DESCRIPTIVE DATA AS MAY BE REQUIRED TO CLEARLY SHOW WHAT, WHERE, AND HOW THE COMPONENT IS INTENDED TO BE INSTALLED. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 05356 | Forwarded | For Review | 2020-01-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-14 | Submittal Number: 21 13 00-6.0 From: SIMRAN GEORGE Final Due Date: 01/21/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - PRODUCT DATA Description: SUBMIT THE FOLLOWING FOR THE ENTIRETY OF THE BUILDING FOR REVIEW TO THE ARCHITECT PRIOR TO THE START OF INSTALLATION: 1. MATERIAL AND EQUIPMENT INFORMATION SHALL INCLUDE CATALOG CUTS AND TECHNICAL DATA FOR EACH SYSTEM COMPONENT OR DEVICE. THIS SHALL INCLUDE, BUT NOT BE LIMITED TO PIPING, FITTINGS, GLOBE AND ANGLE VALVES, O.S.&Y VALVES, BUTTERFLY VALVES, CHECK VALVES, AUTOMATIC SPRINKLER HEADS, ESCUTCHEONS, HANGERS, FLOW SWITCHES, TAMPER SWITCHES, ALARM VALVES, TRIM AND REQUIRED ACCESSORIES, DRY PIPE VALVES, TRIM AND REQUIRED ACCESSORIES AND AIR COMPRESSOR. 2. A COMPLETE SCHEDULE OF THE MATERIAL AND EQUIPMENT PROPOSED FOR THIS INSTALLATION. INCLUDE CATALOG CUTS, DIAGRAMS, DRAWINGS, AND SUCH OTHER DESCRIPTIVE DATA AS MAY BE REQUIRED TO CLEARLY SHOW WHAT, WHERE, AND HOW THE COMPONENT IS INTENDED TO BE INSTALLED. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 03874 | Review Response | Approved | 2020-01-10 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 10 January 2020 | Info Exchange
| 05426 | Responded and Closed | Approved | 2020-01-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 10 January 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-06 |  | 21 13 00-6.0 Fire Suppresion Sprinkler Systems - Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-06 |  | 21 13 00-6.0 Fire Suppresion Sprinkler Systems - Product Data-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-01-10 02:00 |  | 21 13 00-6.0 Fire Suppresion Sprinkler Systems - Product Data_MEE Review_10 Jan 20.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-10 02:00 |  | 21 13 00-6.0 Fire Suppresion Sprinkler Systems - Product Data_MEE Review_10 Jan 20_POP.pdf
21 13 00-007-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-007-00 FIRE SUPPRESSION SPRINKLER SYSTEMS Pendant Heads - Manufacturers Instructions | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-31 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-14 | 2020-02-03 | 4 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-02-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04159 | Received | For Review | 2020-01-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2020-02-14 | Submittal Number: 21 13 00-7.0 From: SIMRAN GEORGE Final Due Date: 02/14/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS PENDANT HEADS - MANUFACTURERS INSTRUCTIONS Description: PRODUCT DATA FOR PENDANT TYPE HEADS Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 05765 | Forwarded | For Review | 2020-01-31 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-07 | Submittal Number: 21 13 00-7.0 From: SIMRAN GEORGE Final Due Date: 02/14/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS PENDANT HEADS - MANUFACTURERS INSTRUCTIONS Description: PRODUCT DATA FOR PENDANT TYPE HEADS Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 04179 | Review Response | Approved | 2020-01-31 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 31 January 2020 | Info Exchange
| 05792 | Responded and Closed | Approved | 2020-02-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 31 January 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-30 |  | 21 13 00-7.0 Fire Suppresion Sprinkler Systems Pendant Heads- Manufacturers Instructions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-30 |  | 21 13 00-7.0 Fire Suppresion Sprinkler Systems Pendant Heads- Manufacturers Instructions-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-01-31 02:00 |  | 21 13 00-7.0 Fire Suppresion Sprinkler Systems Pendant Heads- Manufacturers Instructions_MEE Review_31 Jan 20.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-03 02:00 |  | 21 13 00-7.0 Fire Suppresion Sprinkler Systems Pendant Heads- Manufacturers Instructions_MEE Review_31 Jan 20_POP.pdf
21 13 00-008-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-008-00 Tunnel Hanger Calculations | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Rejected |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-03-17 | 2020-03-04 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-03-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04596 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 21 13 00-8.0 From: SIMRAN GEORGE Final Due Date: 03/13/20 Subject: TUNNEL HANGER CALCULATIONS Description: PLEASE SUBMIT HANGER LOADS AND ATTACHMENT DETAILS FOR THE SPRINKLER SYSTEM IN THE TUNNEL. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 06334 | Forwarded | For Review | 2020-03-03 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-10 | Submittal Number: 21 13 00-8.0 From: SIMRAN GEORGE Final Due Date: 03/13/20 Subject: TUNNEL HANGER CALCULATIONS Description: PLEASE SUBMIT HANGER LOADS AND ATTACHMENT DETAILS FOR THE SPRINKLER SYSTEM IN THE TUNNEL. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 04615 | Review Response | Approved | 2020-03-03 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 3 March 2020 | Info Exchange
| 06352 | Forwarded | For Review | 2020-03-03 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-03-10 | Submittal Number: 21 13 00-8.0 From: SIMRAN GEORGE Final Due Date: 03/13/20 Subject: TUNNEL HANGER CALCULATIONS Description: PLEASE SUBMIT HANGER LOADS AND ATTACHMENT DETAILS FOR THE SPRINKLER SYSTEM IN THE TUNNEL. Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 04642 | Review Response | Rejected | 2020-03-03 | Andy Tatkowski (Thornton Tomasetti) | Josh Dobken (Populous) |  | Provide PE stamp in accordance with Note SU-5 on S0-01 and address overall comments. ART ¦ TT ¦ 3/3/2020 | Info Exchange
| 06382 | Responded and Closed | Rejected | 2020-03-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Rejected) from: Andy Tatkowski (Thornton Tomasetti) Remarks: Provide PE stamp in accordance with Note SU-5 on S0-01 and address overall comments. ART ¦ TT ¦ 3/3/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 21 13 00-8.0 Fire Suppresion Sprinkler Systems - Tunnel Hanger Calculations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 21 13 00-8.0 Fire Suppresion Sprinkler Systems - Tunnel Hanger Calculations-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-03-03 02:00 |  | 21 13 00-8.0 Fire Suppresion Sprinkler Systems - Tunnel Hanger Calculations_MEE Review_3 Mar 20.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-01 02:00 |  | 21 13 00-8.0 Fire Suppresion Sprinkler Systems - Tunnel Hanger Calculations-MAM.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-03-01 02:00 |  | 21 13 00-8.0 Fire Suppresion Sprinkler Systems - Tunnel Hanger Calculations-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-04 02:00 |  | 21 13 00-8.0 Fire Suppresion Sprinkler Systems - Tunnel Hanger Calculations_MEE Review_3 Mar 20_TT_POP.pdf
21 13 00-009-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-009-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - Event Level Shop Drawings | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-21 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-06 | 2020-03-02 | 11 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04442 | Received | For Review | 2020-02-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-03-06 | Submittal Number: 21 13 00-9.0 From: SIMRAN GEORGE Final Due Date: 03/06/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - EVENT LEVEL SHOP DRAWINGS Description: EVENT LEVEL SHOP DRAWINGS Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 06131 | Forwarded | For Review | 2020-02-21 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-28 | Submittal Number: 21 13 00-9.0 From: SIMRAN GEORGE Final Due Date: 03/06/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - EVENT LEVEL SHOP DRAWINGS Description: EVENT LEVEL SHOP DRAWINGS Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 04582 | Review Response | Approved | 2020-02-25 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc 25 February 2020 | Info Exchange
| 06319 | Responded and Closed | Approved | 2020-03-02 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc 25 February 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-21 |  | 21 13 00-9.0 Fire Suppresion Sprinkler Systems - Event Level Sprinkler Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-21 |  | 21 13 00-9.0 Fire Suppresion Sprinkler Systems - Event Level Sprinkler Shop Drawings-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-02-25 02:00 |  | 21 13 00-9.0 Fire Suppresion Sprinkler Systems - Event Level Sprinkler Shop Drawings_MEE Review_25 Feb 20.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-02 02:00 |  | 21 13 00-9.0 Fire Suppresion Sprinkler Systems - Event Level Sprinkler Shop Drawings_MEE Review_25 Feb 20_POP.pdf
21 13 00-010-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-010-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - Mech Mezz C and D Shop Drawings | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-27 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-12 | 2020-03-02 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04533 | Received | For Review | 2020-02-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-03-12 | Submittal Number: 21 13 00-10.0 From: SIMRAN GEORGE Final Due Date: 03/12/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - MECH MEZZ C AND D SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 06240 | Forwarded | For Review | 2020-02-27 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-05 | Submittal Number: 21 13 00-10.0 From: SIMRAN GEORGE Final Due Date: 03/12/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - MECH MEZZ C AND D SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 04584 | Review Response | Approved | 2020-02-27 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 27 February 2020 | Info Exchange
| 06320 | Responded and Closed | Approved | 2020-03-02 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 27 February 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-26 |  | 21 13 00-10.0 Fire Suppresion Sprinkler Systems - Mech Mezz C and D Sprinkler Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-26 |  | 21 13 00-10.0 Fire Suppresion Sprinkler Systems - Mech Mezz C and D Sprinkler Shop Drawings-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-02-27 02:00 |  | 21 13 00-10.0 Fire Suppresion Sprinkler Systems - Mech Mezz C and D Sprinkler Shop Drawings_MEE Review_27 Feb 20.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-02 02:00 |  | 21 13 00-10.0 Fire Suppresion Sprinkler Systems - Mech Mezz C and D Sprinkler Shop Drawings_MEE Review_27 Feb 20_POP.pdf
21 13 00-012-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-012-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - Mech Mezz A,B,E,F Shop Drawings | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-31 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-15 07:00 | 2020-04-21 | 22 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-04-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05147 | Received | For Review | 2020-03-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-04-15 07:00 | Submittal Number: 21 13 00-12.0 From: SIMRAN GEORGE Final Due Date: 04/14/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - MECH MEZZ A,B,E,F SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 06980 | Forwarded | For Review | 2020-03-31 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-07 | Submittal Number: 21 13 00-12.0 From: SIMRAN GEORGE Final Due Date: 04/14/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - MECH MEZZ A,B,E,F SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 05474 | Review Response | Approved | 2020-04-20 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exception Taken. See attached. David J. Ferguson, P.E. ME Engineers Inc. 20 April 2020 | Info Exchange
| 07432 | Responded and Closed | Approved | 2020-04-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exception Taken. See attached. David J. Ferguson, P.E. ME Engineers Inc. 20 April 2020 | Info Exchange
| 07442 | Sent | For Information Only | 2020-04-21 | Josh Dobken (Populous) | Simran George (M.A. Mortenson Company) |  | Responded and Closed (Approved) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) Remarks: Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exception Taken. See attached. David J. Ferguson, P.E. ME Engineers Inc. 20 April 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-31 |  | 21 13 00-12.0 Fire Suppresion Sprinkler Systems - Mech Mezz ABEF Sprinkler Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-31 |  | 21 13 00-12.0 Fire Suppresion Sprinkler Systems - Mech Mezz ABEF Sprinkler Shop Drawings-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-04-20 02:00 |  | 21 13 00-12.0 Fire Suppresion Sprinkler Systems - Mech Mezz ABEF Sprinkler Shop Drawings_MEE Review_20 Apr 20.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-21 02:00 |  | 21 13 00-12.0 Fire Suppresion Sprinkler Systems - Mech Mezz ABEF Sprinkler Shop Drawings_MEE Review_20 Apr 20_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-03-30 02:00 |  | 21 13 00-12.0 Fire Suppresion Sprinkler Systems - Mech Mezz ABEF Sprinkler Shop Drawings-MAM.pdf
21 13 00-013-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-013-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - Main Concourse Shop Drawings | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-19 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-03 07:00 | 2020-05-26 | 8 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05930 | Received | For Review | 2020-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-06-03 07:00 | Submittal Number: 21 13 00-13.0 From: SIMRAN GEORGE Final Due Date: 06/02/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - MAIN CONCOURSE SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08047 | Forwarded | For Review | 2020-05-19 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-26 | Submittal Number: 21 13 00-13.0 From: SIMRAN GEORGE Final Due Date: 06/02/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - MAIN CONCOURSE SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 06014 | Review Response | Approved | 2020-05-19 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 19 May 2020 | Info Exchange
| 08157 | Responded and Closed | Approved | 2020-05-26 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 19 May 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 |  | 21 13 00-13.0 Fire Suppresion Sprinkler Systems - Main Concourse Sprinkler Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-19 |  | 21 13 00-13.0 Fire Suppresion Sprinkler Systems - Main Concourse Sprinkler Shop Drawings-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-05-18 02:00 |  | 21 13 00-13.0 Fire Suppresion Sprinkler Systems - Main Concourse Sprinkler Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-26 02:00 |  | 21 13 00-13.0 Fire Suppresion Sprinkler Systems - Main Concourse Sprinkler Shop Drawings_MEE Review_19 May 20_POP.pdf
21 13 00-014-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-014-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - Suite Level Shop Drawings | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-19 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-03 07:00 | 2020-05-26 | 8 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05934 | Received | For Review | 2020-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-06-03 07:00 | Submittal Number: 21 13 00-14.0 From: SIMRAN GEORGE Final Due Date: 06/02/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - SUITE LEVEL SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08053 | Forwarded | For Review | 2020-05-19 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-26 | Submittal Number: 21 13 00-14.0 From: SIMRAN GEORGE Final Due Date: 06/02/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - SUITE LEVEL SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 06015 | Review Response | Approved | 2020-05-19 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 19 May 2020 | Info Exchange
| 08158 | Responded and Closed | Approved | 2020-05-26 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 19 May 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 |  | 21 13 00-14.0 Fire Suppresion Sprinkler Systems - Suite Sprinkler Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-19 |  | 21 13 00-14.0 Fire Suppresion Sprinkler Systems - Suite Sprinkler Shop Drawings-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-05-18 02:00 |  | 21 13 00-14.0 Fire Suppresion Sprinkler Systems - Suite Sprinkler Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-26 02:00 |  | 21 13 00-14.0 Fire Suppresion Sprinkler Systems - Suite Sprinkler Shop Drawings-MEE Review_19 May 20_POP.pdf
21 13 00-015-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-015-00 Arena Hanger Calculations | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti) |  |  |  | 2020-09-10 07:00 | 2020-09-08 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07760 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-10 07:00 | Submittal Number: 21 13 00-15.0 From: SIMRAN GEORGE Final Due Date: 09/09/20 Subject: ARENA HANGER CALCULATIONS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10331 | Forwarded | For Review | 2020-08-26 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-02 | Submittal Number: 21 13 00-15.0 From: SIMRAN GEORGE Final Due Date: 09/09/20 Subject: ARENA HANGER CALCULATIONS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 07970 | Review Response | Approved | 2020-08-27 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 27 August 2020 | Info Exchange
| 10442 | Forwarded | For Review | 2020-08-31 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) | 2020-09-07 | Submittal Number: 21 13 00-15.0 From: SIMRAN GEORGE Final Due Date: 09/09/20 Subject: ARENA HANGER CALCULATIONS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08062 | Review Response | Approved as Noted | 2020-09-08 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 10598 | Responded and Closed | Approved as Noted | 2020-09-08 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Pending response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 21 13 00-15.0 Fire Suppresion Sprinkler Systems - Arena Hanger Calculations - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-26 |  | 21 13 00-15.0 Fire Suppresion Sprinkler Systems - Arena Hanger Calculations - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-08-26 |  | 21 13 00-15.0 Fire Suppresion Sprinkler Systems - Arena Hanger Calculations - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-25 02:00 |  | 21 13 00-15.0 Fire Suppresion Sprinkler Systems - Arena Hanger Calculations - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-25 02:00 |  | 21 13 00-15.0 Fire Suppresion Sprinkler Systems - Arena Hanger Calculations - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-08 |  | 21 13 00-15.0 Fire Suppresion Sprinkler Systems - Arena Hanger Calculations_ME_TT_POP.pdf
21 13 00-024-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-024-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - Atrium Glazing Sprinkler System | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-14 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-28 | 2020-09-15 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08068 | Received | For Review | 2020-09-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-09-28 | Submittal Number: 21 13 00-24.0 From: SIMRAN GEORGE Final Due Date: 09/28/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - ATRIUM GLAZING SPRINKLER SYSTEM Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10734 | Forwarded | For Review | 2020-09-14 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-21 | Submittal Number: 21 13 00-24.0 From: SIMRAN GEORGE Final Due Date: 09/28/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - ATRIUM GLAZING SPRINKLER SYSTEM Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08129 | Review Response | Approved | 2020-09-14 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 14 September 2020 | Info Exchange
| 10803 | Responded and Closed | Approved as Noted | 2020-09-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | See attached for comments. Skylight contractor to review details, and clacs. and approve. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-11 |  | 21 13 00-24.0 Fire Suppresion Sprinkler Systems - Atrium Glazing Sprinkler System- MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-11 |  | 21 13 00-24.0 Fire Suppresion Sprinkler Systems - Atrium Glazing Sprinkler System- MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-11 |  | 21 13 00-24.0 Fire Suppresion Sprinkler Systems - Atrium Glazing Sprinkler System- MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-09-15 |  | 21 13 00-24.0 Fire Suppresion Sprinkler Systems - Atrium Glazing Sprinkler System_MEE_POP.pdf
21 13 00-025-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-025-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - Caddy Loop Hanger Product Data | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-13 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-27 | 2020-08-25 | 13 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-08-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07528 | Received | For Review | 2020-08-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-08-27 | Submittal Number: 21 13 00-25.0 From: SIMRAN GEORGE Final Due Date: 08/27/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - CADDY LOOP HANGER PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10024 | Forwarded | For Review | 2020-08-13 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-20 | Submittal Number: 21 13 00-25.0 From: SIMRAN GEORGE Final Due Date: 08/27/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - CADDY LOOP HANGER PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 07742 | Review Response | Approved | 2020-08-13 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 13 August 2020 | Info Exchange
| 10308 | Responded and Closed | Approved | 2020-08-25 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-12 |  | 21 13 00-25.0 Fire Suppresion Sprinkler Systems - Caddy Loop Hanger Product Data- MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-12 |  | 21 13 00-25.0 Fire Suppresion Sprinkler Systems - Caddy Loop Hanger Product Data- MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-08-12 |  | 21 13 00-25.0 Fire Suppresion Sprinkler Systems - Caddy Loop Hanger Product Data- MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-08-25 |  | 21 13 00-25.0 Fire Suppresion Sprinkler Systems - Caddy Loop Hanger Product Data_ME_POP.pdf
21 13 00-026-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-026-00 200 Mechanical Mezzanine CCD 052, 054, 055 Shop Drawings | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-21 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-04 | 2020-08-31 | 11 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-08-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07654 | Received | For Review | 2020-08-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-09-04 | Submittal Number: 21 13 00-26.0 From: SIMRAN GEORGE Final Due Date: 09/18/20 Subject: 200 MECHANICAL MEZZANINE CCD 052, 054, 055 SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10197 | Forwarded | For Review | 2020-08-20 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-27 | Submittal Number: 21 13 00-26.0 From: SIMRAN GEORGE Final Due Date: 09/18/20 Subject: 200 MECHANICAL MEZZANINE CCD 052, 054, 055 SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 07850 | Review Response | Approved | 2020-08-21 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 21 August 2020 | Info Exchange
| 10435 | Responded and Closed | Approved as Noted | 2020-08-31 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 21 13 00-26.0 Fire Suppresion Sprinkler Systems - 200 Mechanical Mezzanine CCD 052 054 055 Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-20 |  | 21 13 00-26.0 Fire Suppresion Sprinkler Systems - 200 Mechanical Mezzanine CCD 052 054 055 Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-08-20 |  | 21 13 00-26.0 Fire Suppresion Sprinkler Systems - 200 Mechanical Mezzanine CCD 052 054 055 Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-08-31 |  | 21 13 00-26.0 Fire Suppresion Sprinkler Systems - 200 Mech Mezz Shop Drawings_ME_POP.pdf
21 13 00-027-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-027-00 500 Upper Concourse CCD 052, 054, 055 Shop Drawings | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-04 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-21 | 2020-09-21 | 18 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07956 | Received | For Review | 2020-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-09-21 | Submittal Number: 21 13 00-27.0 From: SIMRAN GEORGE Final Due Date: 09/17/20 Subject: 500 UPPER CONCOURSE CCD 052, 054, 055 SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10580 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-15 | Submittal Number: 21 13 00-27.0 From: SIMRAN GEORGE Final Due Date: 09/17/20 Subject: 500 UPPER CONCOURSE CCD 052, 054, 055 SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08228 | Review Response | Approved | 2020-09-08 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 8 September 2020 | Info Exchange
| 10926 | Responded and Closed | Approved as Noted | 2020-09-21 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-03 |  | 21 13 00-27.0 Fire Suppresion Sprinkler Systems - 500 Upper Concourse CCD 052 054 055 Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-03 |  | 21 13 00-27.0 Fire Suppresion Sprinkler Systems - 500 Upper Concourse CCD 052 054 055 Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-03 |  | 21 13 00-27.0 Fire Suppresion Sprinkler Systems - 500 Upper Concourse CCD 052 054 055 Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-03 |  | 21 13 00-27.0 Fire Suppresion Sprinkler Systems - 500 Upper Concourse CCD 052 054 055 Shop Drawings - MAM.pdf
21 13 00-028-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-028-00 FIRE SUPPRESSION SPRINKLER SYSTEMS - AHJ REVIEWED Shell and Core Shop Drawings For Record | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-26 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-10 07:00 | 2020-09-14 | 20 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07769 | Received | For Review | 2020-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-09-10 07:00 | Submittal Number: 21 13 00-28.0 From: SIMRAN GEORGE Final Due Date: 10/05/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - AHJ REVIEWED SHELL AND CORE SHOP DRAWINGS FOR RECORD Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10341 | Forwarded | For Review | 2020-08-26 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-02 | Submittal Number: 21 13 00-28.0 From: SIMRAN GEORGE Final Due Date: 10/05/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - AHJ REVIEWED SHELL AND CORE SHOP DRAWINGS FOR RECORD Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10571 | Forwarded | For Review | 2020-09-08 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) | 2020-09-10 | Submittal Number: 21 13 00-28.0 From: SIMRAN GEORGE Final Due Date: 10/05/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - AHJ REVIEWED SHELL AND CORE SHOP DRAWINGS FOR RECORD Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08078 | Review Response | No Action Taken or Required | 2020-09-08 | Dave Ferguson (ME Engineers) | Josh Dobken (Populous) |  | Reviewed. No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 8 September 2020 | Info Exchange
| 10745 | Responded and Closed | No Action Taken or Required | 2020-09-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Received for record | Info Exchange
| 11600 | Sent | For Information Only | 2020-10-14 | Josh Dobken (Populous) | Simran George (M.A. Mortenson Company) |  | Response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: Reviewed. No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 8 September 2020 Responded and Closed (No Action Taken or Required) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) Remarks: Received for record | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 21 13 00-28.0 Fire Suppresion Sprinkler Systems - AHJ REVIEWED Shell and Core Shop Drawings For Record - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-26 |  | 21 13 00-28.0 Fire Suppresion Sprinkler Systems - AHJ REVIEWED Shell and Core Shop Drawings For Record - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-08-25 02:00 |  | 21 13 00-28.0 Fire Suppresion Sprinkler Systems - AHJ REVIEWED Shell and Core Shop Drawings For Record - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-08-25 02:00 |  | 21 13 00-28.0 Fire Suppresion Sprinkler Systems - AHJ REVIEWED Shell and Core Shop Drawings For Record - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-14 02:00 |  | 21 13 00-28.0 Fire Suppresion Sprinkler Systems - AHJ REVIEWED Shell and Core Shop Drawings For Record_MEE Review_8 Sep 20_pop.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-08-25 02:00 |  | 21 13 00-28.0 Fire Suppresion Sprinkler Systems - AHJ REVIEWED Shell and Core Shop Drawings For Record - MAM.pdf
21 13 00-029-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-029-00 100 Event Level CCD 052, 054, 055 Shop Drawings - Area A and D | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-03 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-18 | 2020-09-18 | 16 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07955 | Received | For Review | 2020-09-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-09-18 | Submittal Number: 21 13 00-29.0 From: SIMRAN GEORGE Final Due Date: 09/17/20 Subject: 100 EVENT LEVEL CCD 052, 054, 055 SHOP DRAWINGS - AREA A AND D Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10579 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-15 | Submittal Number: 21 13 00-29.0 From: SIMRAN GEORGE Final Due Date: 09/17/20 Subject: 100 EVENT LEVEL CCD 052, 054, 055 SHOP DRAWINGS - AREA A AND D Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08206 | Review Response | Approved | 2020-09-08 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 8 September 2020 | Info Exchange
| 10894 | Responded and Closed | Approved | 2020-09-18 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 8 September 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-02 |  | 21 13 00-29.0 Fire Suppresion Sprinkler Systems - 100 Event Level CCD 052 054 055 Shop Drawings-Area A and D- MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-02 |  | 21 13 00-29.0 Fire Suppresion Sprinkler Systems - 100 Event Level CCD 052 054 055 Shop Drawings-Area A and D- MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-02 |  | 21 13 00-29.0 Fire Suppresion Sprinkler Systems - 100 Event Level CCD 052 054 055 Shop Drawings-Area A and D- MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-18 |  | 21 13 00-29.0 Fire Suppresion Sprinkler Systems-100 Event Level-ME_POP.pdf
21 13 00-030-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-030-00 Fire Suppression Sprinkler Systems - 300 Main Con CCD 052, 054, 055 Shop Drawings | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-21 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-05 | 2020-09-29 | 9 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08225 | Received | For Review | 2020-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-05 | Submittal Number: 21 13 00-30.0 From: SIMRAN GEORGE Final Due Date: 10/05/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - 300 MAIN CON CCD 052, 054, 055 SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10922 | Forwarded | For Review | 2020-09-21 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-28 | Submittal Number: 21 13 00-30.0 From: SIMRAN GEORGE Final Due Date: 10/05/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - 300 MAIN CON CCD 052, 054, 055 SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08401 | Review Response | Approved | 2020-09-22 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 22 September 2020 | Info Exchange
| 11135 | Responded and Closed | Approved | 2020-09-29 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 22 September 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 21 13 00-30.0 Fire Suppression Sprinkler Systems - 300 Main Con CCD 052 054 055 Shop Drawings- MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-21 |  | 21 13 00-30.0 Fire Suppression Sprinkler Systems - 300 Main Con CCD 052 054 055 Shop Drawings- MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-21 |  | 21 13 00-30.0 Fire Suppression Sprinkler Systems - 300 Main Con CCD 052 054 055 Shop Drawings- MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-29 |  | 21 13 00-30.0 Fire Suppression Sprinkler - 300 Main Con Shop Drawings_ME_POP.pdf
21 13 00-031-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-031-00 Fire Suppression Sprinkler Systems - Fire Hose Valve Product Data | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-04 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-21 | 2020-09-21 | 18 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07954 | Received | For Review | 2020-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-09-21 | Submittal Number: 21 13 00-31.0 From: SIMRAN GEORGE Final Due Date: 10/15/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - FIRE HOSE VALVE PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10578 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-15 | Submittal Number: 21 13 00-31.0 From: SIMRAN GEORGE Final Due Date: 10/15/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEMS - FIRE HOSE VALVE PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08229 | Review Response | Approved | 2020-09-08 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 8 September 2020 | Info Exchange
| 10927 | Responded and Closed | Approved | 2020-09-21 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 8 September 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-04 |  | 21 13 00-31.0 Fire Suppresion Sprinkler Systems - Fire Hose Valve Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-04 |  | 21 13 00-31.0 Fire Suppresion Sprinkler Systems - Fire Hose Valve Product Data - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-04 |  | 21 13 00-31.0 Fire Suppresion Sprinkler Systems - Fire Hose Valve Product Data - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-21 |  | 21 13 00-31.0 Fire Suppresion Sprinkler Systems - Fire Hose Valve PD - ME_POP.pdf
21 13 00-032-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-032-00 100 Event Level CCD 052, 054, 055 Shop Drawings - Quads B, C, and F | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-17 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-01 | 2020-09-21 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08167 | Received | For Review | 2020-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-10-01 | Submittal Number: 21 13 00-32.0 From: SIMRAN GEORGE Final Due Date: 10/01/20 Subject: 100 EVENT LEVEL CCD 052, 054, 055 SHOP DRAWINGS - QUADS B, C, AND F Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10842 | Forwarded | For Review | 2020-09-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-24 | Submittal Number: 21 13 00-32.0 From: SIMRAN GEORGE Final Due Date: 10/01/20 Subject: 100 EVENT LEVEL CCD 052, 054, 055 SHOP DRAWINGS - QUADS B, C, AND F Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08233 | Review Response | Approved | 2020-09-17 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 September 2020 | Info Exchange
| 10932 | Responded and Closed | Approved as Noted | 2020-09-21 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-17 |  | 21 13 00-32.0 100 Event Level CCD 052 054 055 Shop Drawings - Quads B C and F- MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-17 |  | 21 13 00-32.0 100 Event Level CCD 052 054 055 Shop Drawings - Quads B C and F- MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-17 |  | 21 13 00-32.0 100 Event Level CCD 052 054 055 Shop Drawings - Quads B C and F- MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-21 |  | 21 13 00-32.0 100 Event Level CCD Shop Drawings - Quads B C and F_ME_POP.pdf
21 13 00-033-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-033-00 400 Suite Level CCD 052, 054, 055 Shop Drawings | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-21 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-05 | 2020-09-29 | 9 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08226 | Received | For Review | 2020-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-10-05 | Submittal Number: 21 13 00-33.0 From: SIMRAN GEORGE Final Due Date: 10/08/20 Subject: 400 SUITE LEVEL CCD 052, 054, 055 SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10923 | Forwarded | For Review | 2020-09-21 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-28 | Submittal Number: 21 13 00-33.0 From: SIMRAN GEORGE Final Due Date: 10/08/20 Subject: 400 SUITE LEVEL CCD 052, 054, 055 SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08397 | Review Response | Approved | 2020-09-22 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 22 September 2020 | Info Exchange
| 11132 | Responded and Closed | Approved | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 22 September 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 21 13 00-33.0 400 Suite Level CCD 052 054 055 Shop Drawings- MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-21 |  | 21 13 00-33.0 400 Suite Level CCD 052 054 055 Shop Drawings- MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-21 |  | 21 13 00-33.0 400 Suite Level CCD 052 054 055 Shop Drawings- MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 21 13 00-33.0 400 Suite Level CCD 052 054 055 Shop Drawings_ME_POP.pdf
21 13 00-034-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-034-00 Additional Deferred Space Specific Materials | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-17 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-01 | 2020-09-21 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08168 | Received | For Review | 2020-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-01 | Submittal Number: 21 13 00-34.0 From: SIMRAN GEORGE Final Due Date: 10/01/20 Subject: ADDITIONAL DEFERRED SPACE SPECIFIC MATERIALS Description: 300 AND 400 LEVEL SPECIFIC DEFERRED SPACE FIRE PROTECTION MATERIALS Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10843 | Forwarded | For Review | 2020-09-17 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-24 | Submittal Number: 21 13 00-34.0 From: SIMRAN GEORGE Final Due Date: 10/01/20 Subject: ADDITIONAL DEFERRED SPACE SPECIFIC MATERIALS Description: 300 AND 400 LEVEL SPECIFIC DEFERRED SPACE FIRE PROTECTION MATERIALS Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08231 | Review Response | Approved | 2020-09-17 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 September 2020 | Info Exchange
| 10929 | Responded and Closed | Approved | 2020-09-21 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 September 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-17 |  | 21 13 00-34.0 Additional Deferred SPace Specific Materials- MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-17 |  | 21 13 00-34.0 Additional Deferred SPace Specific Materials- MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-17 |  | 21 13 00-34.0 Additional Deferred SPace Specific Materials- MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-21 |  | 21 13 00-34.0 Additional Deferred SPace Specific Materials_ME_POP.pdf
21 13 00-035-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-035-00 Couplings Product Data | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-25 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-09 | 2020-10-08 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08331 | Received | For Review | 2020-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-10-09 | Submittal Number: 21 13 00-35.0 From: SIMRAN GEORGE Final Due Date: 11/05/20 Subject: COUPLINGS PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 11040 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-01 | Submittal Number: 21 13 00-35.0 From: SIMRAN GEORGE Final Due Date: 11/05/20 Subject: COUPLINGS PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 08669 | Review Response | Approved | 2020-10-06 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exception Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 6 October 2020 | Info Exchange
| 11451 | Responded and Closed | Approved | 2020-10-08 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exception Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 6 October 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 21 13 00-35.0 Couplings Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 21 13 00-35.0 Couplings Product Data - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-24 |  | 21 13 00-35.0 Couplings Product Data - MAM.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-10-08 |  | 21 13 00-35.0 Couplings Product Data_MEE_POP.pdf
21 13 00-036-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-036-00 Access Doors | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-12 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-30 08:00 | 2020-12-01 | 20 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09391 | Received | For Review | 2020-11-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-11-30 08:00 | Submittal Number: 21 13 00-36.0 From: SIMRAN GEORGE Final Due Date: 12/04/20 Subject: ACCESS DOORS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 12395 | Forwarded | For Review | 2020-11-12 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-19 | Submittal Number: 21 13 00-36.0 From: SIMRAN GEORGE Final Due Date: 12/04/20 Subject: ACCESS DOORS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 09774 | Review Response | Approved | 2020-11-12 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 12 November 2020 | Info Exchange
| 12856 | Responded and Closed | Approved | 2020-12-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-11 |  | 21 13 00-36.0 Access Doors Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-11 |  | 21 13 00-36.0 Access Doors Product Data - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-11-11 |  | 21 13 00-36.0 Access Doors Product Data - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-01 |  | 21 13 00-36.0 Access Doors Product Data_ME_POP.pdf
21 13 00-037-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-037-00 1870 Series Fire Hose Valve Cabinet Product Data | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-30 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-13 | 2020-11-11 | 13 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09119 | Received | For Review | 2020-10-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-11-13 | Submittal Number: 21 13 00-37.0 From: SIMRAN GEORGE Final Due Date: 12/08/20 Subject: 1870 SERIES FIRE HOSE VALVE CABINET PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 12032 | Forwarded | For Review | 2020-10-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-06 | Submittal Number: 21 13 00-37.0 From: SIMRAN GEORGE Final Due Date: 12/08/20 Subject: 1870 SERIES FIRE HOSE VALVE CABINET PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 09379 | Review Response | Approved | 2020-10-30 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 30 October 2020 | Info Exchange
| 12378 | Responded and Closed | Approved | 2020-11-11 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 30 October 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-29 |  | 21 13 00-37.0 1870 Series Fire Hose Valve Cabinet Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-29 |  | 21 13 00-37.0 1870 Series Fire Hose Valve Cabinet Product Data - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-10-29 |  | 21 13 00-37.0 1870 Series Fire Hose Valve Cabinet Product Data - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-11-11 |  | 21 13 00-37.0 1870 Series Fire Hose Valve Cabinet Product Data_ME_POP.pdf
21 13 00-038-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-038-00 Access Doors - Shop Drawings | Closed | Fire Protection, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-30 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-14 | 2020-12-10 | 11 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09755 | Received | For Review | 2020-11-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-12-14 | Submittal Number: 21 13 00-38.0 From: SIMRAN GEORGE Final Due Date: 12/24/20 Subject: ACCESS DOORS - SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 12823 | Forwarded | For Review | 2020-11-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-07 | Submittal Number: 21 13 00-38.0 From: SIMRAN GEORGE Final Due Date: 12/24/20 Subject: ACCESS DOORS - SHOP DRAWINGS Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 09777 | Review Response | Approved | 2020-11-30 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. Architect to review locations for approval. David J. Ferguson, P.E. ME Engineers, Inc. 30 November 2020 | Info Exchange
| 12859 | Responded and Closed | Approved | 2020-12-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. Architect to review locations for approval. David J. Ferguson, P.E. ME Engineers, Inc. 30 November 2020 | Info Exchange
| 13177 | Reopened | Additional Information | 2020-12-10 09:11 | Bryan Klote (Populous) |  |  | added comments at (3) locations
| 13178 | Responded and Closed | Approved as Noted | 2020-12-10 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | re-opened to add (3) additional comments. BK/Populous 12.10.2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-27 |  | 21 13 00-38.0 Access Doors Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-27 |  | 21 13 00-38.0 Access Doors Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-11-27 |  | 21 13 00-38.0 Access Doors Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-01 |  | 21 13 00-38.0 Access Doors Shop Drawings_ME_POP.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-10 |  | 21 13 00-38.0 Access Doors Shop Drawings_ME_POPr1.pdf
21 13 00-039-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-039-00 Fire Suppression Sprinkler System - Shop Drawing Update December 2020 For Record | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - No Action Taken or Required |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-18 | 2021-01-05 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10383 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2021-01-18 | Submittal Number: 21 13 00-39.0 From: SIMRAN GEORGE Final Due Date: 12/18/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEM - SHOP DRAWING UPDATE DECEMBER 2020 FOR RECORD Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 13567 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-11 | Submittal Number: 21 13 00-39.0 From: SIMRAN GEORGE Final Due Date: 12/18/20 Subject: FIRE SUPPRESSION SPRINKLER SYSTEM - SHOP DRAWING UPDATE DECEMBER 2020 FOR RECORD Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 10452 | Review Response | No Action Taken or Required | 2021-01-04 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. Submittal provided for record. David J. Ferguson, P.E. ME Engineers, Inc. 4 January 2021 | Info Exchange
| 13648 | Responded and Closed | No Action Taken or Required | 2021-01-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. Submittal provided for record. David J. Ferguson, P.E. ME Engineers, Inc. 4 January 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-29 |  | 21 13 00-39.0 Fire SUppression SPrinkler System - Shop Drawing Update December 2020 For Record - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-29 |  | 21 13 00-39.0 Fire SUppression SPrinkler System - Shop Drawing Update December 2020 For Record - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-12-28 02:00 |  | 21 13 00-39.0 Fire SUppression SPrinkler System - Shop Drawing Update December 2020 For Record - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-05 02:00 |  | 21 13 00-39.0 Fire SUppression SPrinkler System - Shop Drawing Update December 2020 For Record_MEE Review_4 Jan 21_pop.pdf
21 13 00-040-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-040-00 Additional Deferred Space Specific Materials - 100 Event Level | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-16 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-02 08:00 | 2020-12-01 | 16 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09437 | Received | For Review | 2020-11-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-12-02 08:00 | Submittal Number: 21 13 00-40.0 From: SIMRAN GEORGE Final Due Date: 11/30/20 Subject: ADDITIONAL DEFERRED SPACE SPECIFIC MATERIALS - 100 EVENT LEVEL Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 12444 | Forwarded | For Review | 2020-11-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-23 | Submittal Number: 21 13 00-40.0 From: SIMRAN GEORGE Final Due Date: 11/30/20 Subject: ADDITIONAL DEFERRED SPACE SPECIFIC MATERIALS - 100 EVENT LEVEL Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 09775 | Review Response | Approved | 2020-11-16 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 16 November 2020 | Info Exchange
| 12857 | Responded and Closed | Approved | 2020-12-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-15 |  | 21 13 00-40.0 Additional Deferred Space Specific Materials- 100 Event Level Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-15 |  | 21 13 00-40.0 Additional Deferred Space Specific Materials- 100 Event Level Product Data - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-11-15 |  | 21 13 00-40.0 Additional Deferred Space Specific Materials- 100 Event Level Product Data - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-01 |  | 21 13 00-40.0 Additional Deferred Space Specific Materials_ME_POP.pdf
21 13 00-041-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-041-00 Wire Guards Product Data | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-09 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-23 | 2021-03-01 | 21 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11293 | Received | For Review | 2021-02-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2021-02-23 | Submittal Number: 21 13 00-41.0 From: SIMRAN GEORGE Final Due Date: 03/19/21 Subject: WIRE GUARDS PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 14641 | Forwarded | For Review | 2021-02-09 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-16 | Submittal Number: 21 13 00-41.0 From: SIMRAN GEORGE Final Due Date: 03/19/21 Subject: WIRE GUARDS PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 11702 | Review Response | Approved as Noted | 2021-02-10 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached. Populous to review/comment on selected color. David J. Ferguson, P.E. ME Engineers, Inc. 10 February 2021 | Info Exchange
| 15146 | Responded and Closed | Approved as Noted | 2021-03-01 | Tom Usher (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Pending response (Approved as Noted) from: Dave Ferguson (ME Engineers) Remarks: See attached. Populous to review/comment on selected color. Populous prefers chrome-plated (given likely locations in concourses and clubs). David J. Ferguson, P.E. ME Engineers, Inc. 10 February 2021 Populous prefers chrome-plated (given likely locations in concourses and clubs). Tom Usher | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-09 |  | 21 13 00-41.0 Fire Suppression Sprinkler System - Wire Guards Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-09 |  | 21 13 00-41.0 Fire Suppression Sprinkler System - Wire Guards Product Data - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-02-08 02:00 |  | 21 13 00-41.0 Fire Suppression Sprinkler System - Wire Guards Product Data - MAM.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2021-03-01 |  | 21 13 00-41.0 Fire Suppression Sprinkler System - Wire Guards Product Data_MEE Review_10 Feb 21_POP.pdf
21 13 00-042-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-042-00 Pre-Action Nitrogen Generator - Product Data | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-10 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-24 | 2021-03-01 | 20 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11312 | Received | For Review | 2021-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2021-02-24 | Submittal Number: 21 13 00-42.0 From: SIMRAN GEORGE Final Due Date: 03/22/21 Subject: PRE-ACTION NITROGEN GENERATOR - PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 14663 | Forwarded | For Review | 2021-02-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-17 | Submittal Number: 21 13 00-42.0 From: SIMRAN GEORGE Final Due Date: 03/22/21 Subject: PRE-ACTION NITROGEN GENERATOR - PRODUCT DATA Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 11694 | Review Response | Approved | 2021-02-10 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 10 February 2021 | Info Exchange
| 15165 | Responded and Closed | Approved | 2021-03-01 | Tom Usher (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 10 February 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-09 |  | 21 13 00-42.0 Fire Suppression Sprinkler System - Pre-Action Nitrogen Generator Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-09 |  | 21 13 00-42.0 Fire Suppression Sprinkler System - Pre-Action Nitrogen Generator Product Data - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-02-09 |  | 21 13 00-42.0 Fire Suppression Sprinkler System - Pre-Action Nitrogen Generator Product Data - MAM.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2021-03-01 |  | 21 13 00-42.0 Fire Suppression - Pre-Action Nitro Gen PD_MEE_POP.pdf
21 13 00-043-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-043-00 1st Ave. N. Garage Fire Protection Package | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-08 | Responded and Closed - No Action Taken or Required |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-09-22 | 2021-09-07 | -1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-09-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14587 | Received | For Review | 2021-09-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-09-22 | Submittal Number: 21 13 00-43.0 From: ALLIE ZIMMERMAN Final Due Date: 09/21/21 Subject: 1ST AVE. N. GARAGE FIRE PROTECTION PACKAGE Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 18806 | Forwarded | For Review | 2021-09-07 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-09-14 | Submittal Number: 21 13 00-43.0 From: ALLIE ZIMMERMAN Final Due Date: 09/21/21 Subject: 1ST AVE. N. GARAGE FIRE PROTECTION PACKAGE Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 14589 | Review Response | No Action Taken or Required | 2021-09-07 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Reviewed. See attached David J. Ferguson, P.E. ME Engineers, Inc. 7 September 2021 | Info Exchange
| 14588 | Review Response | No Action Taken or Required | 2021-09-07 | Dave Ferguson (ME Engineers) | Tom Usher (Populous) |  | Pending response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: Reviewed. See attached David J. Ferguson, P.E. ME Engineers, Inc. 7 September 2021 | Info Exchange
| 18807 | Responded and Closed | No Action Taken or Required | 2021-09-07 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-07 |  | Submittal 21 13 00-43 Revision 0 1st Ave. N. Garage Fire Protection Package_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-07 |  | Submittal 21 13 00-43 Revision 0 1st Ave. N. Garage Fire Protection Package_MAM Reviewed.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-09-07 |  | Submittal 21 13 00-43 Revision 0 1st Ave. N. Garage Fire Protection Package_MAM Reviewed.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-09-07 |  | 21 13 00-43 Revision 0 1st Ave. N. Garage Fire Protection Package_MEE Review_7 Sep 21_POP.pdf
21 13 00-043-01 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-043-01 1st Ave. N. Garage Fire Protection Package | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-20 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-10-04 | 2021-09-21 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14671 | Received | For Review | 2021-09-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-10-04 | Submittal Number: 21 13 00-43.1 From: ALLIE ZIMMERMAN Final Due Date: 10/01/21 Subject: 1ST AVE. N. GARAGE FIRE PROTECTION PACKAGE Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 18920 | Forwarded | For Review | 2021-09-20 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-09-27 | Submittal Number: 21 13 00-43.1 From: ALLIE ZIMMERMAN Final Due Date: 10/01/21 Subject: 1ST AVE. N. GARAGE FIRE PROTECTION PACKAGE Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 14680 | Review Response | No Action Taken or Required | 2021-09-20 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | Reviewed. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 20 September 2021 | Info Exchange
| 18932 | Responded and Closed | No Action Taken or Required | 2021-09-21 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: Reviewed. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 20 September 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-17 |  | Submittal 21 13 00-43 Revision 1 1st Ave. N. Garage Fire Protection Package_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-17 |  | Submittal 21 13 00-43 Revision 1 1st Ave. N. Garage Fire Protection Package_MAM Reviewed.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-09-17 |  | Submittal 21 13 00-43 Revision 1 1st Ave. N. Garage Fire Protection Package_MAM Reviewed.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-09-21 |  | Submittal 21 13 00-43 Revision 1 1st Ave. N. Garage FP PKG_ME_POP.pdf
21 13 00-044-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 13 00-044-00 Fire Pump Final Flow Test Sign Off - For Record | Closed | Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-13 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-09-27 | 2021-09-13 | 1 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-09-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14625 | Received | For Review | 2021-09-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2021-09-27 | Submittal Number: 21 13 00-44.0 From: SIMRAN GEORGE Final Due Date: 10/22/21 Subject: FIRE PUMP FINAL FLOW TEST SIGN OFF - FOR RECORD Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 18864 | Forwarded | For Review | 2021-09-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-09-20 | Submittal Number: 21 13 00-44.0 From: SIMRAN GEORGE Final Due Date: 10/22/21 Subject: FIRE PUMP FINAL FLOW TEST SIGN OFF - FOR RECORD Description: Spec Section: 21 13 00 - FIRE-SUPPRESSION SPRINKLER SYSTEMS Status: OPEN | Info Exchange
| 14627 | Review Response | No Action Taken or Required | 2021-09-13 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Reviewed. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 13 September 2021 | Info Exchange
| 18866 | Responded and Closed | No Action Taken or Required | 2021-09-13 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: Reviewed. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 13 September 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-10 |  | 21 13 00-44.0 Fire Suppression Sprinkler System - Fire Pump Final Flow Test Sign Off - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-10 |  | 21 13 00-44.0 Fire Suppression Sprinkler System - Fire Pump Final Flow Test Sign Off - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-09-10 |  | 21 13 00-44.0 Fire Suppression Sprinkler System - Fire Pump Final Flow Test Sign Off - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-09-13 |  | 21 13 00-44.0 Fire Suppression Sprinkler System - Fire Pump Final Flow Test Sign Off_ME_POP.pdf
21 22 00-002-00 | 21 22 00 - CLEAN AGENT FIRE EXTINGUISHING SYSTEMS | 21 22 00-002-00 DAS FM-200 Product Data | Closed | Technology, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-18 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Michael Mazzocchi (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2021-03-04 | 2021-03-09 | 20 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11574 | Received | For Review | 2021-02-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-04 | Submittal Number: 21 22 00-2.0 From: COLIN SAIZ Final Due Date: 03/05/21 Subject: DAS FM-200 PRODUCT DATA Description: Spec Section: 21 22 00 - CLEAN-AGENT FIRE-EXTINGUISHING SYSTEMS Status: OPEN | Info Exchange
| 14996 | Forwarded | For Review | 2021-02-22 | Populous SCA_CCA | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Michael Mazzocchi (ME Engineers) | 2021-03-01 | Submittal Number: 21 22 00-2.0 From: COLIN SAIZ Final Due Date: 03/05/21 Subject: DAS FM-200 PRODUCT DATA Description: Spec Section: 21 22 00 - CLEAN-AGENT FIRE-EXTINGUISHING SYSTEMS Status: OPEN | Info Exchange
| 15196 | Forwarded | For Review | 2021-03-01 | Populous SCA_CCA | Dave Ferguson (ME Engineers) | 2021-03-04 | Submittal Number: 21 22 00-2.0 From: COLIN SAIZ Final Due Date: 03/05/21 Subject: DAS FM-200 PRODUCT DATA Description: Spec Section: 21 22 00 - CLEAN-AGENT FIRE-EXTINGUISHING SYSTEMS Status: OPEN | Info Exchange
| 11859 | Review Response | Approved as Noted | 2021-03-03 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 3 March 2021 | Info Exchange
| 15379 | Responded and Closed | Approved as Noted | 2021-03-09 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz; Colin.Saiz@mortenson.com |  | Response (Approved as Noted) from: Dave Ferguson (ME Engineers) Remarks: Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 3 March 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-18 02:00 |  | 20-1101 Submittal - 02 - Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-18 02:00 |  | 20-1101 Submittal - 02 - Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-18 02:00 |  | 20-1101 Submittal - 02 - Product Data.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-02-18 |  | 20-1101 Submittal - 02 - Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-09 |  | 21 22 00-002-00 DAS FM-200 Product Data_ME_POP.pdf
21 22 00-003-00 | 21 13 00 - FIRE SUPPRESSION SPRINKLER SYSTEMS | 21 22 00-003-00 DAS FM-200 Shop Drawings | Closed | Technology, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-18 | Responded and Closed - Approved |  | Bryan Klote (Populous), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Michael Mazzocchi (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2021-03-04 | 2021-03-09 | 20 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11577 | Received | For Review | 2021-02-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Stieritz | 2021-03-04 | Submittal Number: 21 22 00-3.0 From: COLIN SAIZ Final Due Date: 03/05/21 Subject: DAS FM-200 SHOP DRAWINGS Description: Spec Section: 21 22 00 - CLEAN-AGENT FIRE-EXTINGUISHING SYSTEMS Status: OPEN | Info Exchange
| 14997 | Forwarded | For Review | 2021-02-22 | Cody Stieritz | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Michael Mazzocchi (ME Engineers) | 2021-03-01 | Submittal Number: 21 22 00-3.0 From: COLIN SAIZ Final Due Date: 03/05/21 Subject: DAS FM-200 SHOP DRAWINGS Description: Spec Section: 21 22 00 - CLEAN-AGENT FIRE-EXTINGUISHING SYSTEMS Status: OPEN | Info Exchange
| 15198 | Forwarded | For Review | 2021-03-01 | Cody Stieritz | Dave Ferguson (ME Engineers) | 2021-03-04 | Submittal Number: 21 22 00-3.0 From: COLIN SAIZ Final Due Date: 03/05/21 Subject: DAS FM-200 SHOP DRAWINGS Description: Spec Section: 21 22 00 - CLEAN-AGENT FIRE-EXTINGUISHING SYSTEMS Status: OPEN | Info Exchange
| 11858 | Review Response | Approved | 2021-03-03 | Dave Ferguson (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 3 March 2021 | Info Exchange
| 15378 | Responded and Closed | Approved | 2021-03-09 | Cody Stieritz | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz; Colin.Saiz@mortenson.com |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 3 March 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-18 02:00 |  | 20-1101 Submittal - 01 - Shop Drawings.pdf
| Forwarded |  | Cody Stieritz | 1 | 2021-02-18 02:00 |  | 20-1101 Submittal - 01 - Shop Drawings.pdf
| Forwarded |  | Cody Stieritz | 1 | 2021-02-18 02:00 |  | 20-1101 Submittal - 01 - Shop Drawings.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-02-18 |  | 20-1101 Submittal - 01 - Shop Drawings.pdf
| Responded and Closed |  | Cody Stieritz | 1 | 2021-03-09 |  | 21 22 00-003-00 DAS FM-200 Shop Drawings_ME_POP.pdf
21 22 00-003-01 | 21 22 00 - CLEAN AGENT FIRE EXTINGUISHING SYSTEMS | 21 22 00-003-01 DAS FM-200 Shop Drawings | Closed | Fire Alarm | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-21 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-10-05 | 2021-09-21 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14673 | Received | For Review | 2021-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Stieritz | 2021-10-05 | Submittal Number: 21 22 00-3.1 From: COLIN SAIZ Final Due Date: 10/06/21 Subject: DAS FM-200 SHOP DRAWINGS Description: Spec Section: 21 22 00 - CLEAN-AGENT FIRE-EXTINGUISHING SYSTEMS Status: OPEN | Info Exchange
| 18923 | Forwarded | For Review | 2021-09-20 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-09-27 | Submittal Number: 21 22 00-3.1 From: COLIN SAIZ Final Due Date: 10/06/21 Subject: DAS FM-200 SHOP DRAWINGS Description: Spec Section: 21 22 00 - CLEAN-AGENT FIRE-EXTINGUISHING SYSTEMS Status: OPEN | Info Exchange
| 14682 | Review Response | Approved | 2021-09-21 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 21 September 2021 | Info Exchange
| 18933 | Responded and Closed | Approved | 2021-09-21 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 21 September 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-20 |  | 212200-003-1 DAS FM-200 Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-20 |  | 212200-003-1 DAS FM-200 Shop Drawings.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-09-20 |  | 212200-003-1 DAS FM-200 Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-21 |  | 212200-003-1 DAS FM-200 Shop Drawings_ME_POP.pdf
22 05 00-001-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-001-00 Under-Ground Plumbing - Shop Drawings | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-25 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-11-08 | 2019-11-04 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-11-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02917 | Received | For Review | 2019-10-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-11-08 | Submittal Number: 22 05 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 11/06/19 Subject: UNDER-GROUND PLUMBING - SHOP DRAWINGS Description: UNDERGROUND SHOP DRAWINGS Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 04288 | Forwarded | For Review | 2019-10-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-01 | Submittal Number: 22 05 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 11/06/19 Subject: UNDER-GROUND PLUMBING - SHOP DRAWINGS Description: UNDERGROUND SHOP DRAWINGS Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 03030 | Review Response | Approved | 2019-11-04 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 4 November 2019 | Info Exchange
| 04419 | Responded and Closed | Approved | 2019-11-04 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 4 November 2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-24 |  | 22 05 00-1.0 SDP-201 UG WV Plbg Plans - Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-24 |  | 22 05 00-1.0 SDP-201 UG WV Plbg Plans - Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-11-04 02:00 |  | 22 05 00-1.0 SDP-201 UG WV Plbg Plans - Shop Drawings_MEE Review_4 Nov 19.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-04 02:00 |  | 22 05 00-1.0 SDP-201 UG WV Plbg Plans - Shop Drawings_MEE Review_4 Nov 19_POP.pdf
22 05 00-002-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-002-00 Event Level Plumbing Shop Drawings | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-03 | 2020-03-06 | 18 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-03-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04385 | Received | For Review | 2020-02-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-03 | Submittal Number: 22 05 00-2.0 From: GRETCHEN TOSHACH Final Due Date: 03/17/20 Subject: EVENT LEVEL PLUMBING SHOP DRAWINGS Description: EVENT LEVEL PLUMBING SHOP DRAWINGS. GRAVITY AND DOMESTIC. Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 06058 | Forwarded | For Review | 2020-02-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-25 | Submittal Number: 22 05 00-2.0 From: GRETCHEN TOSHACH Final Due Date: 03/17/20 Subject: EVENT LEVEL PLUMBING SHOP DRAWINGS Description: EVENT LEVEL PLUMBING SHOP DRAWINGS. GRAVITY AND DOMESTIC. Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 04749 | Review Response | Approved as Noted | 2020-02-25 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Make Corrections Noted (as noted in blue text). See attached David J. Ferguson, P.E. ME Engineers, Inc. 25 February 2020 | Info Exchange
| 06450 | Responded and Closed | Approved as Noted | 2020-03-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Pending response (Approved as Noted) from: Dave Ferguson (ME Engineers) Remarks: Make Corrections Noted (as noted in blue text). See attached David J. Ferguson, P.E. ME Engineers, Inc. 25 February 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | 22 05 00-2.0 - Plumbing Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-17 |  | 22 05 00-2.0 - Plumbing Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-02-25 02:00 |  | 22 05 00-2.0 - Plumbing Shop Drawings_MEE Review_25 Feb 20.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-03-06 |  | 22 05 00-2.0 - Plumbing Shop Drawings_MEE_POP Review_25 Feb 20.pdf
22 05 00-003-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-003-00 Tunnel Sump Lids | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-30 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-10 | 2020-03-31 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-03-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05101 | Received | For Review | 2020-03-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-10 | Submittal Number: 22 05 00-3.0 From: GRETCHEN TOSHACH Final Due Date: 04/17/20 Subject: TUNNEL SUMP LIDS Description: LIDS FOR TUNNEL SUMP VAULTS Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 06929 | Forwarded | For Review | 2020-03-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-06 | Submittal Number: 22 05 00-3.0 From: GRETCHEN TOSHACH Final Due Date: 04/17/20 Subject: TUNNEL SUMP LIDS Description: LIDS FOR TUNNEL SUMP VAULTS Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 05148 | Review Response | Approved | 2020-03-30 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 30 March 2020 | Info Exchange
| 06985 | Responded and Closed | Approved | 2020-03-31 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 30 March 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-27 |  | 22 05 00-3.0 SP-4 SP-6 Tunnel Sump Lids Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-27 |  | 22 05 00-3.0 SP-4 SP-6 Tunnel Sump Lids Product Data - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-03-30 |  | 22 05 00-3.0 SP-4 SP-6 Tunnel Sump Lids Product Data_MEE Review_30 Mar 20.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-03-31 |  | 22 05 00-3.0 SP-4 SP-6 Tunnel Sump Lids Product Data_ME_POP.pdf
22 05 00-004-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-004-00 200 Mech-pipe Shop Drawings | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-31 | Responded and Closed - Rejected |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-14 | 2020-04-01 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-04-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05149 | Received | For Review | 2020-03-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-14 | Submittal Number: 22 05 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 04/14/20 Subject: 200 MECH-PIPE SHOP DRAWINGS Description: SHOP DRAWINGS FOR MEHCANICAL PIPING 200 LEVEL MEZZANINE Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 06982 | Forwarded | For Review | 2020-03-31 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-07 | Submittal Number: 22 05 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 04/14/20 Subject: 200 MECH-PIPE SHOP DRAWINGS Description: SHOP DRAWINGS FOR MEHCANICAL PIPING 200 LEVEL MEZZANINE Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 05173 | Review Response | Rejected | 2020-04-01 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Submit as a Division 23 submittal. These are not Division 22 piping systems. See attached David J. Ferguson, P.E. ME Engineers, Inc. 1 April 2020 | Info Exchange
| 07014 | Responded and Closed | Rejected | 2020-04-01 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Rejected) from: Dave Ferguson (ME Engineers) Remarks: Submit as a Division 23 submittal. These are not Division 22 piping systems. See attached David J. Ferguson, P.E. ME Engineers, Inc. 1 April 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-31 |  | 03-13-20 Lvl200 Quad A-B-E-F Piping Submittal-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-31 |  | 03-13-20 Lvl200 Quad A-B-E-F Piping Submittal-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-04-01 02:00 |  | 22 05 00-4.0 - Lvl200 Quad A-B-E-F Piping Submittal_MEE Review_1 Apr 20.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-01 02:00 |  | 22 05 00-4.0 - Lvl200 Quad A-B-E-F Piping Submittal_MEE Review_1 Apr 20_POP.pdf
22 05 00-005-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-005-00 200 Bev Conduit - Shop Drawings | Closed | Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-31 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2020-04-15 | 2020-04-21 | 22 |  | Record Copies; Transfers; Submittals | 22 05 00-005-01 - 22 05 00-005-00 200 Bev Conduit - Shop Drawings | 22 |  | 2020-04-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05150 | Received | For Review | 2020-03-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-15 | Submittal Number: 22 05 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 04/14/20 Subject: 200 BEV CONDUIT - SHOP DRAWINGS Description: BEVERAGE CONDUIT FOR 200 LEVEL Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 06983 | Forwarded | For Review | 2020-03-31 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-07 | Submittal Number: 22 05 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 04/14/20 Subject: 200 BEV CONDUIT - SHOP DRAWINGS Description: BEVERAGE CONDUIT FOR 200 LEVEL Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 05174 | Review Response | No Action Taken or Required | 2020-04-01 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Reviewed only. Beverage conduit is not part of Division 22 scope of work. Food Service consultant to review and comment. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 1 April 2020 | Info Exchange
| 07015 | Forwarded | For Review | 2020-04-01 | Josh Dobken (Populous) | Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-04-08 | Submittal Number: 22 05 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 04/14/20 Subject: 200 BEV CONDUIT - SHOP DRAWINGS Description: BEVERAGE CONDUIT FOR 200 LEVEL Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 05482 | Review Response | Revise and Resubmit | 2020-04-21 | Peg Galie (S2O Consultants, Inc.) | Josh Dobken (Populous) |  |  | Email
| 07435 | Responded and Closed | Revise and Resubmit | 2020-04-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Peg Galie (S2O Consultants, Inc.) Remarks: See attached submittal. Please revise and resubmit to reflect design changes in CCD 052. | Info Exchange
| 09186 | Sent | For Information Only | 2020-07-07 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Nate Weingart (M.A. Mortenson Company); Ryan Crookston (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Revise and Resubmit) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Revise and Resubmit) from: Peg Galie (S2O Consultants, Inc.) Remarks: See attached submittal. Please revise and resubmit to reflect design changes in CCD 052. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-31 |  | 22 05 00-5.0 200 Bev Conduit Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-31 |  | 22 05 00-5.0 200 Bev Conduit Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-04-01 02:00 |  | 22 05 00-5.0 200 Bev Conduit Shop Drawings_MEE Review_1 Apr 20.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-30 02:00 |  | 22 05 00-5.0 200 Bev Conduit Shop Drawings - MAM.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-04-21 02:00 |  | 200405 S2O Reps 22 05 00-5.0 200 Bev Conduit Shop Drawings_MEE Review_1 Apr 20.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-30 02:00 |  | 22 05 00-5.0 200 Bev Conduit Shop Drawings - MAM.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-04-21 02:00 |  | 200405 S2O Reps 22 05 00-5.0 200 Bev Conduit Shop Drawings_MEE Review_1 Apr 20_POP.pdf
22 05 00-005-01 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-005-00 200 Bev Conduit - Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 22 05 00-005-00 - 22 05 00-005-00 200 Bev Conduit - Shop Drawings | -1 | 2020-05-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-30 02:00 |  | 22 05 00-5.0 200 Bev Conduit Shop Drawings - MAM.pdf
22 05 00-006-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-006-00 200 Plumbing Shop Drawings | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-01 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-15 | 2020-04-06 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05167 | Received | For Review | 2020-04-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-15 | Submittal Number: 22 05 00-6.0 From: GRETCHEN TOSHACH Final Due Date: 04/14/20 Subject: 200 PLUMBING SHOP DRAWINGS Description: 200 LEVEL PLUMBING SHOP DRAWINGS, INCLUDES CO2 Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 07002 | Forwarded | For Review | 2020-04-01 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-08 | Submittal Number: 22 05 00-6.0 From: GRETCHEN TOSHACH Final Due Date: 04/14/20 Subject: 200 PLUMBING SHOP DRAWINGS Description: 200 LEVEL PLUMBING SHOP DRAWINGS, INCLUDES CO2 Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 05217 | Review Response | Approved | 2020-04-02 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 2 April 2020 | Info Exchange
| 07098 | Responded and Closed | Approved | 2020-04-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 2 April 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-01 |  | 22 05 00-6.0 200 Plumbing Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-01 |  | 22 05 00-6.0 200 Plumbing Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-04-02 02:00 |  | 22 05 00-6.0 200 Plumbing Shop Drawings_MEE Review_2 Apr 20.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-06 02:00 |  | 22 05 00-6.0 200 Plumbing Shop Drawings_MEE Review_2 Apr 20_POP.pdf
22 05 00-007-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-007-00 300 Main Concourse Plumbing Shop Drawings | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-23 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-08 07:00 | 2020-06-30 | 8 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-06-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06572 | Received | For Review | 2020-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-08 07:00 | Submittal Number: 22 05 00-7.0 From: GRETCHEN TOSHACH Final Due Date: 05/06/20 Subject: 300 MAIN CONCOURSE PLUMBING SHOP DRAWINGS Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 08849 | Forwarded | For Review | 2020-06-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-30 | Submittal Number: 22 05 00-7.0 From: GRETCHEN TOSHACH Final Due Date: 05/06/20 Subject: 300 MAIN CONCOURSE PLUMBING SHOP DRAWINGS Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 06845 | Review Response | Approved | 2020-06-23 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached David J. Ferguson, P.E. ME Engineers, Inc. 23 June 2020 | Info Exchange
| 09032 | Responded and Closed | Approved | 2020-06-30 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-23 |  | 22 05 00-7.0 300 Plumbing shops ABCDEF - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-23 |  | 22 05 00-7.0 300 Plumbing shops ABCDEF - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-06-22 02:00 |  | 22 05 00-7.0 300 Plumbing shops ABCDEF - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-30 |  | 22 05 00-7.0 300 Plumbing shops ABCDEF - ME_POP.pdf
22 05 00-008-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-008-00 400 Suite Level Piping Shop Drawings - Area D + C | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-24 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-09 07:00 | 2020-06-30 | 7 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-06-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06573 | Received | For Review | 2020-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-09 07:00 | Submittal Number: 22 05 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 05/06/20 Subject: 400 SUITE LEVEL PIPING SHOP DRAWINGS - AREA D + C Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 08850 | Forwarded | For Review | 2020-06-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-30 | Submittal Number: 22 05 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 05/06/20 Subject: 400 SUITE LEVEL PIPING SHOP DRAWINGS - AREA D + C Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 06846 | Review Response | Approved | 2020-06-23 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached. David J. Ferguson, P.E. ME Engineers, Inc. 23 June 2020 | Info Exchange
| 09028 | Responded and Closed | Approved | 2020-06-30 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-23 |  | 22 05 008.0 400 Plumbing Shops - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-23 |  | 22 05 008.0 400 Plumbing Shops - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-06-22 02:00 |  | 22 05 008.0 400 Plumbing Shops - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-30 |  | 22 05 00-8.0 400 Plumbing Shops - ME_POP.pdf
22 05 00-011-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-011-00 UG - CCD 52 Piping Shop Drawings - Quads A, B, C, E, F | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-23 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-08 07:00 | 2020-07-06 | 14 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06554 | Received | For Review | 2020-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-08 07:00 | Submittal Number: 22 05 00-11.0 From: GRETCHEN TOSHACH Final Due Date: 05/13/20 Subject: UG - CCD 52 PIPING SHOP DRAWINGS - QUADS A, B, C, E, F Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 08822 | Forwarded | For Review | 2020-06-22 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-29 | Submittal Number: 22 05 00-11.0 From: GRETCHEN TOSHACH Final Due Date: 05/13/20 Subject: UG - CCD 52 PIPING SHOP DRAWINGS - QUADS A, B, C, E, F Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 06847 | Review Response | Approved | 2020-06-23 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | See attached. David J. Ferguson, P.E. ME Engineers, Inc. 23 June 2020 | Info Exchange
| 09102 | Responded and Closed | Approved | 2020-07-06 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-22 |  | 22 05 00-11.0 UG CCD52 Areas ABCDE - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-22 |  | 22 05 00-11.0 UG CCD52 Areas ABCDE - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-06-21 02:00 |  | 22 05 00-11.0 UG CCD52 Areas ABCDE - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-06 |  | 22 05 00-11.0 UG CCD52 Areas ABCDE - ME_POP.pdf
22 05 00-015-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-015-00 South Parcel/Tunnel Piping Shop Drawings | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-21 | 2021-01-11 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10506 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-21 | Submittal Number: 22 05 00-15.0 From: GRETCHEN TOSHACH Final Due Date: 01/21/21 Subject: SOUTH PARCEL/TUNNEL PIPING SHOP DRAWINGS Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 13709 | Forwarded | For Review | 2021-01-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-14 | Submittal Number: 22 05 00-15.0 From: GRETCHEN TOSHACH Final Due Date: 01/21/21 Subject: SOUTH PARCEL/TUNNEL PIPING SHOP DRAWINGS Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 10611 | Review Response | Approved | 2021-01-07 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 January 2021 | Info Exchange
| 13818 | Responded and Closed | Approved | 2021-01-11 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 January 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-07 |  | 22 05 00-15.0 SP_Tunnel Plumbing Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-07 |  | 22 05 00-15.0 SP_Tunnel Plumbing Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-01-07 |  | 22 05 00-15.0 SP_Tunnel Plumbing Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-01-11 |  | 22 05 00-15.0 SP_Tunnel Plumbing Shop Drawings_ME_POP.pdf
22 05 00-025-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-025-00 100-300 Floor Sink Locations for SEOR per RFI 2418 | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-03 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-17 | 2020-06-05 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-06-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06163 | Received | For Review | 2020-06-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-17 | Submittal Number: 22 05 00-25.0 From: GRETCHEN TOSHACH Final Due Date: 07/15/20 Subject: 100-300 FLOOR SINK LOCATIONS FOR SEOR PER RFI 2418 Description: EVENT THROUGH MAIN FLOOR SINK AND AREA DRAIN LOCATION, EVENT THROUGH MAIN, SUBMITTING PER TT COMMENT ON RFI2418. REMAINING FLOORS TO FOLLOW, UNLESS NOTED OTHERWISE. Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 08337 | Forwarded | For Review | 2020-06-03 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-10 | Submittal Number: 22 05 00-25.0 From: GRETCHEN TOSHACH Final Due Date: 07/15/20 Subject: 100-300 FLOOR SINK LOCATIONS FOR SEOR PER RFI 2418 Description: EVENT THROUGH MAIN FLOOR SINK AND AREA DRAIN LOCATION, EVENT THROUGH MAIN, SUBMITTING PER TT COMMENT ON RFI2418. REMAINING FLOORS TO FOLLOW, UNLESS NOTED OTHERWISE. Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 06531 | Review Response | No Action Taken or Required | 2020-06-04 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Submittal reviewed. Contractor shall note that use of trap guards is acceptable (and preferred) in lieu of trap primers. David J. Ferguson, P.E. ME Engineers, Inc. 4 June 2020 | Info Exchange
| 08415 | Responded and Closed | No Action Taken or Required | 2020-06-05 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: Submittal reviewed. Contractor shall note that use of trap guards is acceptable (and preferred) in lieu of trap primers. David J. Ferguson, P.E. ME Engineers, Inc. 4 June 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-03 |  | 22 05 00-25.0 SCA Drain Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-03 |  | 22 05 00-25.0 SCA Drain Drawings.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-06-03 |  | 22 05 00-25.0 SCA Drain Drawings.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-03 |  | 22 05 00-25.0 SCA Drain Drawings.pdf
22 05 00-026-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-026-00 Plumbing Deferred Scope Shop Drawings | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-17 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-31 | 2020-09-01 | 16 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07581 | Received | For Review | 2020-08-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-08-31 | Submittal Number: 22 05 00-26.0 From: GRETCHEN TOSHACH Final Due Date: 08/28/20 Subject: PLUMBING DEFERRED SCOPE SHOP DRAWINGS Description: DEFERRED SCOPE SHOP DRAWINGS CCDS 52/54/58 Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 10089 | Forwarded | For Review | 2020-08-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-24 | Submittal Number: 22 05 00-26.0 From: GRETCHEN TOSHACH Final Due Date: 08/28/20 Subject: PLUMBING DEFERRED SCOPE SHOP DRAWINGS Description: DEFERRED SCOPE SHOP DRAWINGS CCDS 52/54/58 Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 07880 | Review Response | Approved | 2020-08-18 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 18 August 2020 | Info Exchange
| 10482 | Responded and Closed | Approved | 2020-09-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-17 |  | 22 05 00-26.0 PLBG Deferred Scope - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-17 |  | 22 05 00-26.0 PLBG Deferred Scope - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-08-17 |  | 22 05 00-26.0 PLBG Deferred Scope - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-01 |  | 22 05 00-26.0 PLBG Deferred Scope_ME_POP.pdf
22 05 00-027-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-027-00 400 Level - Plumbing Deferred Scope Shop Drawing | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-19 | 2020-10-19 | 15 |  | Record Copies; Transfers; Submittals | 22 05 00-027-00-01 - 22 05 00-027-00 400 Level - Plumbing Deferred Scope Shop Drawing | 1 |  | 2020-10-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08548 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 22 05 00-27.0 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: 400 LEVEL - PLUMBING DEFERRED SCOPE SHOP DRAWING Description: DEFERRED SPACE 400 LEVEL PLUMBING SHOP DRAWINGS Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 11310 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-12 | Submittal Number: 22 05 00-27.0 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: 400 LEVEL - PLUMBING DEFERRED SCOPE SHOP DRAWING Description: DEFERRED SPACE 400 LEVEL PLUMBING SHOP DRAWINGS Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 08845 | Review Response | Revise and Resubmit | 2020-10-05 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | See attached. David J. Ferguson, P.E. ME Engineers, Inc. 5 October 2020 | Info Exchange
| 11693 | Responded and Closed | Revise and Resubmit | 2020-10-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Revise and Resubmit) from: Dave Ferguson (ME Engineers) Remarks: See attached. David J. Ferguson, P.E. ME Engineers, Inc. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 22 05 00-27.0 - 400 lvl Plumbing Deferred Shops - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 22 05 00-27.0 - 400 lvl Plumbing Deferred Shops - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-10-05 |  | 22 05 00-27.0 - 400 lvl Plumbing Deferred Shops - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-19 |  | 22 05 00-27.0 - 400 lvl Plumbing Deferred Shops_ME_POP.pdf
22 05 00-027-00-01 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-027-00 400 Level - Plumbing Deferred Scope Shop Drawing | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 22 05 00-027-00 - 22 05 00-027-00 400 Level - Plumbing Deferred Scope Shop Drawing | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-19 |  | 22 05 00-27.0 - 400 lvl Plumbing Deferred Shops_ME_POP.pdf
22 05 00-029-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-029-00 DW Shop Drawing Updates | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-21 | 2021-01-11 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10507 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-21 | Submittal Number: 22 05 00-29.0 From: GRETCHEN TOSHACH Final Due Date: 01/21/21 Subject: DW SHOP DRAWING UPDATES Description: DOMESTIC WATER SHOP DRAWING UPDATES Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 13710 | Forwarded | For Review | 2021-01-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-14 | Submittal Number: 22 05 00-29.0 From: GRETCHEN TOSHACH Final Due Date: 01/21/21 Subject: DW SHOP DRAWING UPDATES Description: DOMESTIC WATER SHOP DRAWING UPDATES Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 10609 | Review Response | Approved | 2021-01-07 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc 7 January 2021 | Info Exchange
| 13816 | Responded and Closed | Approved | 2021-01-11 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc 7 January 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-07 |  | 22 05 00-29.0 Dom Water CCD Update - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-07 |  | 22 05 00-29.0 Dom Water CCD Update - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-01-07 |  | 22 05 00-29.0 Dom Water CCD Update - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-01-11 |  | 22 05 00-29.0 Dom Water CCD Update_ME_POP.pdf
22 05 00-030-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-030-00 W&V & Bev Con Shop Drawing Update | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-26 08:00 | 2021-02-01 | 22 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10595 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-26 08:00 | Submittal Number: 22 05 00-30.0 From: GRETCHEN TOSHACH Final Due Date: 01/22/21 Subject: W&V & BEV CON SHOP DRAWING UPDATE Description: GRAVITY LINES, WASTE AND VENT, AND BEVERAGE CONDUIT SHOP DRAWING UPDATE Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 13800 | Forwarded | For Review | 2021-01-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-18 | Submittal Number: 22 05 00-30.0 From: GRETCHEN TOSHACH Final Due Date: 01/22/21 Subject: W&V & BEV CON SHOP DRAWING UPDATE Description: GRAVITY LINES, WASTE AND VENT, AND BEVERAGE CONDUIT SHOP DRAWING UPDATE Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 11094 | Review Response | Approved | 2021-01-11 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 11 January 2021 | Info Exchange
| 14392 | Responded and Closed | Approved as Noted | 2021-02-01 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | 22 05 00-30.0 WV_BC Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-08 |  | 22 05 00-30.0 WV_BC Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-01-08 |  | 22 05 00-30.0 WV_BC Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-01 |  | 22 05 00-30.0 WV_BC Shop Drawings_ME_POP.pdf
22 05 00-031-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-031-00 Rain to Rink System - CCD080 | Closed | Civil, Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2021-01-18 | 2021-01-11 | 8 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10382 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2021-01-18 | Submittal Number: 22 05 00-31.0 From: GRETCHEN TOSHACH Final Due Date: 01/14/21 Subject: RAIN TO RINK SYSTEM - CCD080 Description: EXCLUDING STORAGE TANK, SUBMITTED IN SEPARATE SUBMITTAL. Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 13565 | Forwarded | For Review | 2021-01-04 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-01-11 | Submittal Number: 22 05 00-31.0 From: GRETCHEN TOSHACH Final Due Date: 01/14/21 Subject: RAIN TO RINK SYSTEM - CCD080 Description: EXCLUDING STORAGE TANK, SUBMITTED IN SEPARATE SUBMITTAL. Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 13643 | Forwarded | For Review | 2021-01-05 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers) | 2021-01-12 | Submittal Number: 22 05 00-31.0 From: GRETCHEN TOSHACH Final Due Date: 01/14/21 Subject: RAIN TO RINK SYSTEM - CCD080 Description: EXCLUDING STORAGE TANK, SUBMITTED IN SEPARATE SUBMITTAL. Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 10618 | Review Response | No Action Taken or Required | 2021-01-05 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | Reviewed only to coordinate interface to ME Engineers' scope of work. David J. Ferguson, P.E. ME Engineers, Inc. 5 January 2021 | Info Exchange
| 13826 | Responded and Closed | Approved as Noted | 2021-01-11 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: Reviewed only to coordinate interface to ME Engineers' scope of work. David J. Ferguson, P.E. ME Engineers, Inc. 5 January 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-31 |  | 22 05 00-31.0 - Rain To Rink - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-31 |  | 22 05 00-31.0 - Rain To Rink - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-12-30 02:00 |  | 22 05 00-31.0 - Rain To Rink - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-12-30 |  | 22 05 00-31.0 - Rain To Rink - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-01-11 |  | 22 05 00-31.0 - Rain To Rink_ME_POP.pdf
22 05 00-032-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-032-00 Rain to Rink System - CCD080 Underground Tank + Vortex Filter | Closed | Plumbing, Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-01-18 | 2021-01-11 | 8 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10381 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (M.A. Mortenson Company) | 2021-01-18 | Submittal Number: 22 05 00-32.0 From: GRETCHEN TOSHACH Final Due Date: 01/14/21 Subject: RAIN TO RINK SYSTEM - CCD080 UNDERGROUND TANK + VORTEX FILTER Description: RAIN TO RINK SYSTEM - CCD080 UNDERGROUND TANK + VORTEX FILTER ONLY. REMAINING PACKAGE SUBMITTED IN 22 05 00-31.0 Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 13564 | Forwarded | For Review | 2021-01-04 | Gretchen Toshach (M.A. Mortenson Company) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-11 | Submittal Number: 22 05 00-32.0 From: GRETCHEN TOSHACH Final Due Date: 01/14/21Status: OPEN Subject: RAIN TO RINK SYSTEM - CCD080 UNDERGROUND TANK + VORTEX FILTER Description: RAIN TO RINK SYSTEM - CCD080 UNDERGROUND TANK + VORTEX FILTER ONLY. REMAINING PACKAGE SUBMITTED IN 22 05 00-31.0 Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | Info Exchange
| 13566 | Forwarded | For Review | 2021-01-04 | Gretchen Toshach (M.A. Mortenson Company) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-01-11 | Submittal Number: 22 05 00-32.0 From: GRETCHEN TOSHACH Final Due Date: 01/14/21Status: OPEN Subject: RAIN TO RINK SYSTEM - CCD080 UNDERGROUND TANK + VORTEX FILTER Description: RAIN TO RINK SYSTEM - CCD080 UNDERGROUND TANK + VORTEX FILTER ONLY. REMAINING PACKAGE SUBMITTED IN 22 05 00-31.0 Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | Info Exchange
| 10617 | Review Response | Approved as Noted | 2021-01-05 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 13825 | Responded and Closed | Approved as Noted | 2021-01-11 | Gretchen Toshach (Mortenson Construction) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-31 |  | 22 05 00-32.0 - Rain To Rink Tank and Vortex Filter - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2020-12-31 |  | 22 05 00-32.0 - Rain To Rink Tank and Vortex Filter - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2020-12-31 |  | 22 05 00-32.0 - Rain To Rink Tank and Vortex Filter - MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-12-31 |  | 22 05 00-32.0 - Rain To Rink Tank and Vortex Filter - MAM.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-01-11 |  | 22 05 00-32.0 - Rain To Rink Tank and Vortex Filter - DCI_POP.pdf
22 05 00-033-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-033-00 WV to Cooling Towers | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-02 07:00 | 2021-05-25 | 8 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-05-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13147 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-02 07:00 | Submittal Number: 22 05 00-33.0 From: GRETCHEN TOSHACH Final Due Date: 05/25/21 Subject: WV TO COOLING TOWERS Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 17006 | Forwarded | For Review | 2021-05-18 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-25 | Submittal Number: 22 05 00-33.0 From: GRETCHEN TOSHACH Final Due Date: 05/25/21 Subject: WV TO COOLING TOWERS Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 13260 | Review Response | Approved as Noted | 2021-05-18 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 18 May 2021 | Info Exchange
| 17158 | Responded and Closed | Approved as Noted | 2021-05-25 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Dave Ferguson (ME Engineers) Remarks: Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | 22 05 00-33.0 S Parcel Garage Routing WV - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-17 |  | 22 05 00-33.0 S Parcel Garage Routing WV - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-05-17 |  | 22 05 00-33.0 S Parcel Garage Routing WV - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-25 |  | 22 05 00-33.0 S Parcel Garage Routing WV_ME_POP.pdf
22 05 00-034-00 | 22 05 00 - COMMON WORK RESULTS FOR PLUMBING | 22 05 00-034-00 June 2021 Plumbing Shop Drawing Updates-For Record | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-18 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-02 | 2021-06-21 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-06-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13576 | Received | For Review | 2021-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (Mortenson Construction) | 2021-07-02 | Submittal Number: 22 05 00-34.0 From: JACK JOHNSON Final Due Date: 07/09/21 Subject: JUNE 2021 PLUMBING SHOP DRAWING UPDATES-FOR RECORD Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 17577 | Forwarded | For Review | 2021-06-18 | Gretchen Toshach (Mortenson Construction) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-25 | Submittal Number: 22 05 00-34.0 From: JACK JOHNSON Final Due Date: 07/09/21 Subject: JUNE 2021 PLUMBING SHOP DRAWING UPDATES-FOR RECORD Description: Spec Section: 22 05 00 - COMMON WORK RESULTS FOR PLUMBING Status: OPEN | Info Exchange
| 13586 | Review Response | No Action Taken or Required | 2021-06-21 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 21 June 2021 | Info Exchange
| 17587 | Responded and Closed | No Action Taken or Required | 2021-06-21 | Gretchen Toshach (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); jack.a.johnson@mortenson.com |  | Response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 21 June 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-18 |  | 220500-SDP-34 June 2021 Plg Record Update Submittal.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-06-18 |  | 220500-SDP-34 June 2021 Plg Record Update Submittal.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-06-18 |  | 220500-SDP-34 June 2021 Plg Record Update Submittal.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-06-21 |  | 22 05 00-034-0 June 2021 Plg Record Update Submittal_ME_POP.pdf
22 05 50-008-00 | 22 05 50 - PLUMBING SEISMIC RESTRAINTS | 22 05 50-008-00 100 Plumbing Seismic Restraints Calculations | Closed | Plumbing, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-02 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-16 | 2020-06-22 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-06-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06151 | Received | For Review | 2020-06-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-16 | Submittal Number: 22 05 50-8.0 From: GRETCHEN TOSHACH Final Due Date: 04/30/20 Subject: 100 PLUMBING SEISMIC RESTRAINTS CALCULATIONS Description: SEIMSIC RESTRAINT CALCULATIONS FOR PLUMBING EVENT LEVEL Spec Section: 22 05 50 - PLUMBING SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08319 | Forwarded | For Review | 2020-06-02 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-09 | Submittal Number: 22 05 50-8.0 From: GRETCHEN TOSHACH Final Due Date: 04/30/20 Subject: 100 PLUMBING SEISMIC RESTRAINTS CALCULATIONS Description: SEIMSIC RESTRAINT CALCULATIONS FOR PLUMBING EVENT LEVEL Spec Section: 22 05 50 - PLUMBING SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06239 | Review Response | No Action Taken or Required | 2020-06-03 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Reviewed. See attached David J. Ferguson, P.E. ME Engineers, Inc. 3 June 2020 | Info Exchange
| 08423 | Forwarded | For Review | 2020-06-05 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael C... | 2020-06-12 | Submittal Number: 22 05 50-8.0 From: GRETCHEN TOSHACH Final Due Date: 04/30/20 Subject: 100 PLUMBING SEISMIC RESTRAINTS CALCULATIONS Description: SEIMSIC RESTRAINT CALCULATIONS FOR PLUMBING EVENT LEVEL Spec Section: 22 05 50 - PLUMBING SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06546 | Review Response | Approved as Noted/Resubmit | 2020-06-22 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | Exceptions noted, see attached submittal. | Info Exchange
| 08812 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-22 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Franz Kogler (Thornton Tomasetti) Remarks: Exceptions noted, see attached submittal. Response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: Reviewed. See attached David J. Ferguson, P.E. ME Engineers, Inc. 3 June 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-02 |  | 22 055 00-8.0 100 Plbg Seismic Restraints - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-02 |  | 22 055 00-8.0 100 Plbg Seismic Restraints - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-06-01 02:00 |  | 22 055 00-8.0 100 Plbg Seismic Restraints - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-01 02:00 |  | 22 055 00-8.0 100 Plbg Seismic Restraints - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-06-22 02:00 |  | 22 055 00-8.0 100 Plbg Seismic Restraints_MEE Review_TTReview.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-22 02:00 |  | 22 055 00-8.0 100 Plbg Seismic Restraints_MEE Review_TTReview_pop.pdf
22 05 50-008-01 | 22 05 50 - PLUMBING SEISMIC RESTRAINTS | 22 05 50-008-01 100 Plumbing Seismic Restraints Calculations | Closed | Plumbing, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-20 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-04 07:00 | 2021-06-08 | 20 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-06-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13206 | Received | For Review | 2021-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-04 07:00 | Submittal Number: 22 05 50-8.1 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: 100 PLUMBING SEISMIC RESTRAINTS CALCULATIONS Description: SEIMSIC RESTRAINT CALCULATIONS FOR PLUMBING EVENT LEVEL Spec Section: 22 05 50 - PLUMBING SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 17094 | Forwarded | For Review | 2021-05-20 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (ME Engine... | 2021-05-27 | Submittal Number: 22 05 50-8.1 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: 100 PLUMBING SEISMIC RESTRAINTS CALCULATIONS Description: SEIMSIC RESTRAINT CALCULATIONS FOR PLUMBING EVENT LEVEL Spec Section: 22 05 50 - PLUMBING SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13457 | Review Response | Approved | 2021-05-20 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 20 May 2021 | Info Exchange
| 13458 | Review Response | Approved as Noted | 2021-05-28 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Exceptions Noted, see attached. | Info Exchange
| 17401 | Responded and Closed | Approved as Noted | 2021-06-08 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-19 |  | 22 05 50-8.1 100 P Seismic Restraints - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-19 |  | 22 05 50-8.1 100 P Seismic Restraints - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-05-19 |  | 22 05 50-8.1 100 P Seismic Restraints - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-05-19 |  | 22 05 50-8.1 100 P Seismic Restraints - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-28 |  | 22 05 50-8.1 100 P Seismic Restraints - MAM_TTReview.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-08 |  | 22 05 50-8.1 100 P Seismic Restraints - MAM_TTReview-POP.pdf
22 05 50-009-00 | 22 05 50 - PLUMBING SEISMIC RESTRAINTS | 22 05 50-009-00 Level 200 Mech Mezz Plumbing Seismic Restraints Calculations | Closed | Plumbing, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-02 | 2020-07-01 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-07-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06473 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 22 05 50-9.0 From: SIMRAN GEORGE Final Due Date: 06/30/20 Subject: LEVEL 200 MECH MEZZ PLUMBING SEISMIC RESTRAINTS CALCULATIONS Description: Spec Section: 22 05 50 - PLUMBING SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08723 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-24 | Submittal Number: 22 05 50-9.0 From: SIMRAN GEORGE Final Due Date: 06/30/20 Subject: LEVEL 200 MECH MEZZ PLUMBING SEISMIC RESTRAINTS CALCULATIONS Description: Spec Section: 22 05 50 - PLUMBING SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06868 | Review Response | No Action Taken or Required | 2020-06-17 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Reviewed. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 June 2020 | Info Exchange
| 08740 | Forwarded | For Review | 2020-06-18 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael C... | 2020-06-25 | Submittal Number: 22 05 50-9.0 From: SIMRAN GEORGE Final Due Date: 06/30/20 Subject: LEVEL 200 MECH MEZZ PLUMBING SEISMIC RESTRAINTS CALCULATIONS Description: Spec Section: 22 05 50 - PLUMBING SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06869 | Review Response | Approved as Noted | 2020-06-29 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | TT has exceptions as noted. Resubmit is only required if new seismic restraints are added. Note: submittal has only been reviewed for seismic loads imposed. All gravity loads from MEP are to be submitted in separate submittal. Provide ISAT calcs for record for all seismic restraint systems being used on project. | Info Exchange
| 09040 | Responded and Closed | Approved as Noted | 2020-07-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (No Action Taken or Required) from: Dave Ferguson (ME Engineers) Remarks: Reviewed. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 June 2020 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: TT has exceptions as noted. Resubmit is only required if new seismic restraints are added. Note: submittal has only been reviewed for seismic loads imposed. All gravity loads from MEP are to be submitted in separate submittal. Provide ISAT calcs for record for all seismic restraint systems being used on project. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 22 05 50-9.0 Mezz Plbg Seis Restraints - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 22 05 50-9.0 Mezz Plbg Seis Restraints - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-06-16 02:00 |  | 22 05 50-9.0 Mezz Plbg Seis Restraints - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-16 02:00 |  | 22 05 50-9.0 Mezz Plbg Seis Restraints - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-16 02:00 |  | 22 05 50-9.0 Mezz Plbg Seis Restraints - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-01 |  | 22 05 50-9.0 Mezz Plbg Seis Restraints - ME_TT_POP.pdf
22 10 00-001-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-001-00 PLUMBING PIPING - Manufacturers Instructions | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-09 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-07-23 | 2019-07-10 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-07-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01702 | Received | For Review | 2019-07-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-23 | Submittal Number: 22 10 00-1.0 From: PATRICK KLEIN Final Due Date: 07/22/19 Subject: PLUMBING PIPING - MANUFACTURERS INSTRUCTIONS Description: SUBMIT MANUFACTURERS DATA ON THE FOLLOWING : - 1. PRESSURE REDUCING VALVES. 2. BACKFLOW PREVENTERS. 3. WATER HAMMER ARRESTERS. 4. PIPING PRODUCTS, FITTING AND CONNECTION METHODS. 5. ROOF DRAINS, FLOOR DRAINS, FLOOR SINKS, CLEANOUTS AND AREA DRAINS. 6. DOWNSPOUT NOZZLES. 7. MANHOLE FRAMES AND COVERS. 8. BACKWATER VALVES. 9. CATCH-BASINS AND COVERS. 10. WATER METER AND METER PIT. 11. TRAP PRIMERS 12. TRAP GUARDS 13. THERMOSTATIC MIXING VALVES Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 02797 | Forwarded | For Review | 2019-07-09 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2019-07-16 | Submittal Number: 22 10 00-1.0 From: PATRICK KLEIN Final Due Date: 07/22/19 Subject: PLUMBING PIPING - MANUFACTURERS INSTRUCTIONS Description: SUBMIT MANUFACTURERS DATA ON THE FOLLOWING : - 1. PRESSURE REDUCING VALVES. 2. BACKFLOW PREVENTERS. 3. WATER HAMMER ARRESTERS. 4. PIPING PRODUCTS, FITTING AND CONNECTION METHODS. 5. ROOF DRAINS, FLOOR DRAINS, FLOOR SINKS, CLEANOUTS AND AREA DRAINS. 6. DOWNSPOUT NOZZLES. 7. MANHOLE FRAMES AND COVERS. 8. BACKWATER VALVES. 9. CATCH-BASINS AND COVERS. 10. WATER METER AND METER PIT. 11. TRAP PRIMERS 12. TRAP GUARDS 13. THERMOSTATIC MIXING VALVES Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 01729 | Review Response | Approved as Noted | 2019-07-09 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 9 July 2019 | Info Exchange
| 02832 | Responded and Closed | Approved as Noted | 2019-07-10 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Dave Ferguson (ME Engineers) Remarks: Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 9 July 2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-08 |  | 22 10 00-1.0 Manufacturer's Instructions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-09 |  | 22 10 00-1.0 Manufacturer's Instructions-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-07-09 |  | 22 10 00-1.0 Plumbing Piping_MEE Review_9 Jul 19.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2019-07-10 |  | 22 10 00-1.0 Manufacturer's Instructions-MAM_ME Response_POP.pdf
22 10 00-001-01 | 22 10 00 - PLUMBING PIPING | 22 10 00-001-01 PLUMBING PIPING - Manufacturers Instructions | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-21 | 2020-07-20 | 14 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06807 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 22 10 00-1.1 From: PATRICK KLEIN Final Due Date: 07/20/20 Subject: PLUMBING PIPING - MANUFACTURERS INSTRUCTIONS Description: SUBMIT MANUFACTURERS DATA ON THE FOLLOWING : - 1. PRESSURE REDUCING VALVES. 2. BACKFLOW PREVENTERS. 3. WATER HAMMER ARRESTERS. 4. PIPING PRODUCTS, FITTING AND CONNECTION METHODS. 5. ROOF DRAINS, FLOOR DRAINS, FLOOR SINKS, CLEANOUTS AND AREA DRAINS. 6. DOWNSPOUT NOZZLES. 7. MANHOLE FRAMES AND COVERS. 8. BACKWATER VALVES. 9. CATCH-BASINS AND COVERS. 10. WATER METER AND METER PIT. 11. TRAP PRIMERS 12. TRAP GUARDS 13. THERMOSTATIC MIXING VALVES Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 09141 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 22 10 00-1.1 From: PATRICK KLEIN Final Due Date: 07/20/20 Subject: PLUMBING PIPING - MANUFACTURERS INSTRUCTIONS Description: SUBMIT MANUFACTURERS DATA ON THE FOLLOWING : - 1. PRESSURE REDUCING VALVES. 2. BACKFLOW PREVENTERS. 3. WATER HAMMER ARRESTERS. 4. PIPING PRODUCTS, FITTING AND CONNECTION METHODS. 5. ROOF DRAINS, FLOOR DRAINS, FLOOR SINKS, CLEANOUTS AND AREA DRAINS. 6. DOWNSPOUT NOZZLES. 7. MANHOLE FRAMES AND COVERS. 8. BACKWATER VALVES. 9. CATCH-BASINS AND COVERS. 10. WATER METER AND METER PIT. 11. TRAP PRIMERS 12. TRAP GUARDS 13. THERMOSTATIC MIXING VALVES Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 07039 | Review Response | Approved | 2020-07-07 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 July 2020 | Info Exchange
| 09424 | Responded and Closed | Approved | 2020-07-20 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: See attached. David J. Ferguson, P.E. ME Engineers, Inc. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 22 10 00-1.1 Plbg Piping - MAM[1].pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 22 10 00-1.1 Plbg Piping - MAM[1].pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-07-06 |  | 22 10 00-1.1 Plbg Piping - MAM[1].pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-20 |  | 22 10 00-1.1 Plbg Piping_ME_POP.pdf
22 10 00-003-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-003-00 Vent Piping Under Roof | Closed | Plumbing, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-20 | 2020-02-25 | 20 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-02-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04240 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2020-02-20 | Submittal Number: 22 10 00-3.0 From: GRETCHEN TOSHACH Final Due Date: 03/18/20 Subject: VENT PIPING UNDER ROOF Description: SHOP DRAWINGS FOR UNDER ROOF PLUMBING VENT PIPING Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 05869 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-13 | Submittal Number: 22 10 00-3.0 From: GRETCHEN TOSHACH Final Due Date: 03/18/20 Subject: VENT PIPING UNDER ROOF Description: SHOP DRAWINGS FOR UNDER ROOF PLUMBING VENT PIPING Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 04793 | Review Response | Approved | 2020-02-07 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 7 February 2020 | Info Exchange
| 06197 | Responded and Closed | Approved as Noted | 2020-02-25 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 22 10 00-3.0 Vent Under Roof Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | 22 10 00-3.0 Vent Under Roof Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-02-07 |  | 22 10 00-3.0 Vent Under Roof Shop Drawings_MEE Review_6 Feb 20.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-02-25 |  | 22 10 00-3.0 Vent Under Roof Shop Drawings_MEE-POP_6 Feb 20.pdf
22 10 00-004-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-004-00 Plumbing Piping | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-06 | 2020-08-06 | 15 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07115 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 22 10 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 08/05/20 Subject: PLUMBING PIPING Description: PLUMBING PIPING Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 09504 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-30 | Submittal Number: 22 10 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 08/05/20 Subject: PLUMBING PIPING Description: PLUMBING PIPING Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 07450 | Review Response | Approved | 2020-07-23 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | See attached David J. Ferguson, P.E. ME Engineers, Inc. 23 July 2020 | Info Exchange
| 09918 | Responded and Closed | Approved | 2020-08-06 | Bryan Klote (Populous) | Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: See attached David J. Ferguson, P.E. ME Engineers, Inc. 23 July 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 22 10 00-4.0 Plbg Piping - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | 22 10 00-4.0 Plbg Piping - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-07-23 |  | 22 10 00-4.0 Plbg Piping - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-08-06 |  | 22 10 00-4.0 Plbg Piping_MEE_POP.pdf
22 10 00-005-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-005-00 300 Bev Con Shop Drawings | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2020-07-21 | 2020-07-13 | 7 |  | Record Copies; Transfers; Submittals | 22 10 00-005-00-01 - 22 10 00-005-00 300 Bev Con Shop Drawings | 2 |  | 2020-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06831 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 22 10 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: 300 BEV CON SHOP DRAWINGS Description: BEVERAGE CONDUIT SHOP DRAWINGS. MAIN CON Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 09165 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 22 10 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: 300 BEV CON SHOP DRAWINGS Description: BEVERAGE CONDUIT SHOP DRAWINGS. MAIN CON Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 09172 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2020-07-14 | Submittal Number: 22 10 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: 300 BEV CON SHOP DRAWINGS Description: BEVERAGE CONDUIT SHOP DRAWINGS. MAIN CON Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 06936 | Review Response | No Action Taken or Required | 2020-07-07 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 July 2020 | Info Exchange
| 06939 | Review Response | Revise and Resubmit | 2020-07-08 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  | Update to reflect current FS drawings. | Info Exchange
| 09297 | Responded and Closed | Revise and Resubmit | 2020-07-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Peg Galie (S2O Consultants, Inc.) Remarks: Update to reflect current FS drawings. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-07 |  | 22 10 00-5.0 300 Bev Con - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 22 10 00-5.0 300 Bev Con - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 22 10 00-5.0 300 Bev Con - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-07-06 02:00 |  | 22 10 00-5.0 300 Bev Con - MAM.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-07-06 02:00 |  | 22 10 00-5.0 300 Bev Con - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-13 02:00 |  | 200708 S2O Resp 22 10 00-5.0 300 Bev Con - MAM_ME_POP.pdf
22 10 00-005-00-01 | 22 10 00 - PLUMBING PIPING | 22 10 00-005-00 300 Bev Con Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 22 10 00-005-00 - 22 10 00-005-00 300 Bev Con Shop Drawings | -1 | 2020-07-27
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 02:00 |  | 200708 S2O Resp 22 10 00-5.0 300 Bev Con - MAM_ME_POP.pdf
22 10 00-006-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-006-00 400 Bev Con Shop Drawings | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Revise and Resubmit |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Heidi Evans (ME Engineers) |  |  |  | 2020-07-21 | 2020-07-13 | 7 |  | Record Copies; Transfers; Submittals | 22 10 00-006-00-01 - 22 10 00-006-00 400 Bev Con Shop Drawings | 2 |  | 2020-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06832 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 22 10 00-6.0 From: GRETCHEN TOSHACH Final Due Date: 07/14/20 Subject: 400 BEV CON SHOP DRAWINGS Description: 400 LEVEL BEVERAGE CONDUIT SHOP DRAWINGS Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 09171 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Heidi Evans (ME Engineers) |  | Submittal Number: 22 10 00-6.0 From: GRETCHEN TOSHACH Final Due Date: 07/14/20 Subject: 400 BEV CON SHOP DRAWINGS Description: 400 LEVEL BEVERAGE CONDUIT SHOP DRAWINGS Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 06937 | Review Response | No Action Taken or Required | 2020-07-07 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached. No plumbing scope indicated. David J. Ferguson, P.E. ME Engineers, Inc. 7 July 2020 | Info Exchange
| 06938 | Review Response | Revise and Resubmit | 2020-07-08 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  | Please update to reflect most recent documents. | Info Exchange
| 09296 | Responded and Closed | Revise and Resubmit | 2020-07-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Peg Galie (S2O Consultants, Inc.) Remarks: Please update to reflect most recent documents. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-07 |  | 22 10 00-6.0 400 Bev Con - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 22 10 00-6.0 400 Bev Con - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-07-06 02:00 |  | 22 10 00-6.0 400 Bev Con - MAM.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-07-06 02:00 |  | 22 10 00-6.0 400 Bev Con - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-13 02:00 |  | 200708 S2O Resp 22 10 00-6.0 400 Bev Con - MAM_ME_POP.pdf
22 10 00-006-00-01 | 22 10 00 - PLUMBING PIPING | 22 10 00-006-00 400 Bev Con Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 22 10 00-006-00 - 22 10 00-006-00 400 Bev Con Shop Drawings | -1 | 2020-07-27
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 02:00 |  | 200708 S2O Resp 22 10 00-6.0 400 Bev Con - MAM_ME_POP.pdf
22 10 00-007-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-007-00 CCD 066 AD-3 Area Drain | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-08 07:00 | 2020-09-01 | 9 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07700 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-09-08 07:00 | Submittal Number: 22 10 00-7.0 From: GRETCHEN TOSHACH Final Due Date: 09/30/20 Subject: CCD 066 AD-3 AREA DRAIN Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 10249 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-31 | Submittal Number: 22 10 00-7.0 From: GRETCHEN TOSHACH Final Due Date: 09/30/20 Subject: CCD 066 AD-3 AREA DRAIN Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 07881 | Review Response | Approved | 2020-08-26 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 26 August 2020 | Info Exchange
| 10483 | Responded and Closed | Approved | 2020-09-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 26 August 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 22 10 00-7.0 AD-3 CCD-066 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 22 10 00-7.0 AD-3 CCD-066 - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-08-24 |  | 22 10 00-7.0 AD-3 CCD-066 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-01 |  | 22 10 00-7.0 AD-3 CCD-066_ME_POP.pdf
22 10 00-008-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-008-00 HoldRite Fitting Restraints | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-07 | 2020-09-29 | 7 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08289 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 22 10 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 10/09/20 Subject: HOLDRITE FITTING RESTRAINTS Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 10995 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-30 | Submittal Number: 22 10 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 10/09/20 Subject: HOLDRITE FITTING RESTRAINTS Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 08410 | Review Response | Approved | 2020-09-23 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 23 September 2020 | Info Exchange
| 11147 | Responded and Closed | Approved | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 23 September 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 22 10 00-8.0 Holdrite Restraints - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 22 10 00-8.0 Holdrite Restraints - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-23 |  | 22 10 00-8.0 Holdrite Restraints - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 22 10 00-8.0 Holdrite Restraints_ME_POP.pdf
22 10 00-009-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-009-00 Valve Access Cover | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-07 | 2020-09-29 | 7 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08290 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 22 10 00-9.0 From: GRETCHEN TOSHACH Final Due Date: 10/02/20 Subject: VALVE ACCESS COVER Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 10996 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-30 | Submittal Number: 22 10 00-9.0 From: GRETCHEN TOSHACH Final Due Date: 10/02/20 Subject: VALVE ACCESS COVER Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 08404 | Review Response | Approved | 2020-09-23 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 23 September 2020 | Info Exchange
| 11138 | Responded and Closed | Approved | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 23 September 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 22 10 00-9.0 SOG Valve Access - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 22 10 00-9.0 SOG Valve Access - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-23 |  | 22 10 00-9.0 SOG Valve Access - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 22 10 00-9.0 SOG Valve Access_ME_POP.pdf
22 10 00-010-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-010-00 Plumbing Carrier Shop Drawings | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-03 08:00 | 2020-12-03 | 17 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09477 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 22 10 00-10.0 From: GRETCHEN TOSHACH Final Due Date: 11/30/20 Subject: PLUMBING CARRIER SHOP DRAWINGS Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 12495 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-24 | Submittal Number: 22 10 00-10.0 From: GRETCHEN TOSHACH Final Due Date: 11/30/20 Subject: PLUMBING CARRIER SHOP DRAWINGS Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 09863 | Review Response | Approved | 2020-11-17 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 November 2020 | Info Exchange
| 12946 | Responded and Closed | Approved | 2020-12-03 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 22 10 00-10.0 Plbg Carrier Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 22 10 00-10.0 Plbg Carrier Shop Drawings - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-11-16 |  | 22 10 00-10.0 Plbg Carrier Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-03 |  | 22 10 00-10.0 Plbg Carrier Shop Drawings_ME_POP.pdf
22 10 00-011-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-011-00 PRV Stations | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-03 08:00 | 2020-12-03 | 17 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09476 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 22 10 00-11.0 From: GRETCHEN TOSHACH Final Due Date: 11/30/20 Subject: PRV STATIONS Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 12494 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-24 | Submittal Number: 22 10 00-11.0 From: GRETCHEN TOSHACH Final Due Date: 11/30/20 Subject: PRV STATIONS Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 09861 | Review Response | Approved | 2020-11-17 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 November 2020 | Info Exchange
| 12944 | Responded and Closed | Approved | 2020-12-03 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 22 10 00-11.0 PRV Stations - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 22 10 00-11.0 PRV Stations - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-11-16 |  | 22 10 00-11.0 PRV Stations - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-03 |  | 22 10 00-11.0 PRV Stations_ME_POP.pdf
22 10 00-012-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-012-00 Plumbing Piping - Grease Trap | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-25 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-11 | 2020-12-03 | 9 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09738 | Received | For Review | 2020-11-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-11 | Submittal Number: 22 10 00-12.0 From: GRETCHEN TOSHACH Final Due Date: 12/18/20 Subject: PLUMBING PIPING - GREASE TRAP Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 12806 | Forwarded | For Review | 2020-11-25 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-02 | Submittal Number: 22 10 00-12.0 From: GRETCHEN TOSHACH Final Due Date: 12/18/20 Subject: PLUMBING PIPING - GREASE TRAP Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 09865 | Review Response | Approved | 2020-11-25 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 25 November 2020 | Info Exchange
| 12949 | Responded and Closed | Approved | 2020-12-03 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 25 November 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-24 |  | 22 10 00-12.0 Grease Trap - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-24 |  | 22 10 00-12.0 Grease Trap - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-11-24 |  | 22 10 00-12.0 Grease Trap - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-03 |  | 22 10 00-12.0 Grease Trap_ME_POP.pdf
22 10 00-013-00 | 22 10 00 - PLUMBING PIPING | 22 10 00-013-00 Food Service Equip Backflow Preventers | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-04-01 | 2021-03-30 | 13 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12100 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-01 | Submittal Number: 22 10 00-13.0 From: JOSH BROUSSARD Final Due Date: 04/01/21 Subject: FOOD SERVICE EQUIP BACKFLOW PREVENTERS Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 15659 | Forwarded | For Review | 2021-03-18 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-25 | Submittal Number: 22 10 00-13.0 From: JOSH BROUSSARD Final Due Date: 04/01/21 Subject: FOOD SERVICE EQUIP BACKFLOW PREVENTERS Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 12301 | Review Response | Approved | 2021-03-25 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 25 March 2021 | Info Exchange
| 15907 | Responded and Closed | Approved | 2021-03-30 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Josh Broussard (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 25 March 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-18 |  | 22 10 00-13.0 - Food Service Equip Backflow Preventers.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-18 |  | 22 10 00-13.0 - Food Service Equip Backflow Preventers.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-03-18 |  | 22 10 00-13.0 - Food Service Equip Backflow Preventers.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-30 |  | 22 10 00-13.0 - Food Service Equip Backflow Preventers_ME_POP.pdf
22 10 00-013-01 | 22 10 00 - PLUMBING PIPING | 22 10 00-013-01 Food Service Equip Backflow Preventers Spec Revisions | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-25 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-09 07:00 | 2021-05-28 | 4 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-05-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13252 | Received | For Review | 2021-05-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-09 07:00 | Submittal Number: 22 10 00-13.1 From: JOSH BROUSSARD Final Due Date: 06/08/21 Subject: FOOD SERVICE EQUIP BACKFLOW PREVENTERS SPEC REVISIONS Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 17148 | Forwarded | For Review | 2021-05-25 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-01 | Submittal Number: 22 10 00-13.1 From: JOSH BROUSSARD Final Due Date: 06/08/21 Subject: FOOD SERVICE EQUIP BACKFLOW PREVENTERS SPEC REVISIONS Description: Spec Section: 22 10 00 - PLUMBING PIPING Status: OPEN | Info Exchange
| 13303 | Review Response | Approved | 2021-05-25 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 25 May 2021 | Info Exchange
| 17212 | Responded and Closed | Approved | 2021-05-28 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 25 May 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-25 |  | 22 10 00-13.1 - Food Service Equip Backflow Preventer Spec Revisions.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-25 |  | 22 10 00-13.1 - Food Service Equip Backflow Preventer Spec Revisions.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-05-25 |  | 22 10 00-13.1 - Food Service Equip Backflow Preventer Spec Revisions.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-28 |  | 22 10 00-13.1 - Food Service Equip Backflow Preventer Spec Revisions_MEE_POP.pdf
22 11 13-004-00 | 22 11 13 - WATER DISTRIBUTION PIPING | 22 11 13-004-00 Water Service Package | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-12 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-08-26 | 2019-08-28 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2019-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02030 | Received | For Review | 2019-08-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-26 | Submittal Number: 22 11 13-4.0 From: DOMINGO SAMPAYO Final Due Date: 08/16/19 Subject: WATER SERVICE PACKAGE Description: 1. 6” & 8” DI PIPE 2. 6” & 8” FITTINGS 3. 6”,8”, AND 12” GATE VALVES 4. VALVE BOXES 5. JOINING MATERIALS 6. FIRE HYDRANT 7. FIRE DEPARTMENT CONNECTION 8. WATER LINE BEDDING Spec Section: 22 11 13 - WATER DISTRIBUTION PIPING Status: OPEN | Info Exchange
| 03194 | Forwarded | For Review | 2019-08-12 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-19 | Submittal Number: 22 11 13-4.0 From: DOMINGO SAMPAYO Final Due Date: 08/16/19 Subject: WATER SERVICE PACKAGE Description: 1. 6” & 8” DI PIPE 2. 6” & 8” FITTINGS 3. 6”,8”, AND 12” GATE VALVES 4. VALVE BOXES 5. JOINING MATERIALS 6. FIRE HYDRANT 7. FIRE DEPARTMENT CONNECTION 8. WATER LINE BEDDING Spec Section: 22 11 13 - WATER DISTRIBUTION PIPING Status: OPEN | Info Exchange
| 03219 | Forwarded | For Review | 2019-08-13 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-08-20 | Submittal Number: 22 11 13-4.0 From: DOMINGO SAMPAYO Final Due Date: 08/16/19 Subject: WATER SERVICE PACKAGE Description: 1. 6” & 8” DI PIPE 2. 6” & 8” FITTINGS 3. 6”,8”, AND 12” GATE VALVES 4. VALVE BOXES 5. JOINING MATERIALS 6. FIRE HYDRANT 7. FIRE DEPARTMENT CONNECTION 8. WATER LINE BEDDING Spec Section: 22 11 13 - WATER DISTRIBUTION PIPING Status: OPEN | Info Exchange
| 02230 | Review Response | Approved as Noted | 2019-08-28 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached review of the water service package materials submittal. - J. Grant, DCI Engineers | Info Exchange
| 03449 | Responded and Closed | Approved as Noted | 2019-08-28 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached review of the water service package materials submittal. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-10 |  | 22 11 13-4 Water Service Package.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-10 |  | 22 11 13-4 Water Service Package.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-10 |  | 22 11 13-4 Water Service Package.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2019-08-09 02:00 |  | 22 11 13-4 Water Service Package.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-28 02:00 |  | 22 11 13-4 Water Service Package_DCI Review_POP.pdf
22 11 23-002-00 | 22 11 23 - DOMESTIC WATER BOOSTER | 22 11 23-002-00 DOMESTIC WATER BOOSTER - General | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-15 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-29 | 2019-08-20 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02071 | Received | For Review | 2019-08-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-29 | Submittal Number: 22 11 23-2.0 From: PATRICK KLEIN Final Due Date: 08/28/19 Subject: DOMESTIC WATER BOOSTER - GENERAL Description: 1. THE SUBMITTAL DATA FOR THE PUMPING SYSTEM SHALL BE INCLUDED IN BOTH ELECTRONIC AND HARD- COPY FORMAT. Spec Section: 22 11 23 - DOMESTIC WATERBOOSTER Status: OPEN | Info Exchange
| 03244 | Forwarded | For Review | 2019-08-15 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-22 | Submittal Number: 22 11 23-2.0 From: PATRICK KLEIN Final Due Date: 08/28/19 Subject: DOMESTIC WATER BOOSTER - GENERAL Description: 1. THE SUBMITTAL DATA FOR THE PUMPING SYSTEM SHALL BE INCLUDED IN BOTH ELECTRONIC AND HARD- COPY FORMAT. Spec Section: 22 11 23 - DOMESTIC WATERBOOSTER Status: OPEN | Info Exchange
| 02157 | Review Response | Approved | 2019-08-16 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc 16 August 2019 | Info Exchange
| 03337 | Responded and Closed | Approved | 2019-08-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc 16 August 2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-15 |  | 22 11 23-2.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-15 |  | 22 11 23-2.0 Product Data-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-08-16 02:00 |  | 22 11 23-2.0 Product Data_MEE Review_16 Aug 19.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-14 02:00 |  | 22 11 23-2.0 Product Data-MAM.pdf
22 13 13-001-00 | 22 13 13 - SANITARY SEWERS | 22 13 13-001-00 Sewer Utilities ( 8” Sewer Pipe and Fittings & Clean Outs) | Closed | Utilities | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-29 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-09-13 07:00 | 2019-09-06 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-09-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02241 | Received | For Review | 2019-08-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-13 07:00 | Submittal Number: 22 13 13-1.0 From: JUAN BOLANOS Final Due Date: 09/09/19 Subject: SEWER UTILITIES ( 8” SEWER PIPE AND FITTINGS & CLEAN OUTS) Description: INCLUDED WITH THIS SUBMITTAL: 1. 8” SEWER PIPE AND FITTINGS 2. CLEAN OUTS Spec Section: 22 13 13 - SANITARY SEWERS Status: OPEN | Info Exchange
| 03459 | Forwarded | For Review | 2019-08-29 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-09-05 | Submittal Number: 22 13 13-1.0 From: JUAN BOLANOS Final Due Date: 09/09/19 Subject: SEWER UTILITIES ( 8” SEWER PIPE AND FITTINGS & CLEAN OUTS) Description: INCLUDED WITH THIS SUBMITTAL: 1. 8” SEWER PIPE AND FITTINGS 2. CLEAN OUTS Spec Section: 22 13 13 - SANITARY SEWERS Status: OPEN | Info Exchange
| 02331 | Review Response | Approved | 2019-09-06 | Darren Simpson (DCI Engineers) | Shaina Burris (Populous) |  |  | Info Exchange
| 03568 | Responded and Closed | Approved | 2019-09-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-29 |  | 190203 SCA -221313 Sewer Utilities.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-29 |  | Sewer Utilities ( 8_ Sewer Pipe and Fittings & Clean Outs).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-29 |  | 22 13 13-001-00 Sewer Utilities ( 8_ Sewer Pipe and Fittings & Clean Outs).pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-08-28 02:00 |  | 22 13 13-001-00 Sewer Utilities ( 8_ Sewer Pipe and Fittings & Clean Outs).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-06 02:00 |  | 22 13 13-001-00 Sewer Utilities ( 8_ Sewer Pipe and Fittings & Clean Outs)_DCI_POP.pdf
22 13 13-002-00 | 22 13 13 - SANITARY SEWERS | 22 13 13-002-00 10' DI SS pipe & SSMH | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-28 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-05-12 | 2021-05-06 | 9 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12826 | Received | For Review | 2021-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-12 | Submittal Number: 22 13 13-2.0 From: JUAN BOLANOS Final Due Date: 05/12/21 Subject: 10' DI SS PIPE & SSMH Description: CCD 94 EXTENDED THE WEST SEWER LINE WHICH CREATED THE FOLLOWING SUBMITTALS: 1. 10' DI CLASS 50 2. SSMH#1 3. SSMH#3 Spec Section: 22 13 13 - SANITARY SEWERS Status: OPEN | Info Exchange
| 16602 | Forwarded | For Review | 2021-04-28 | Populous SCA_CCA | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-05-05 | Submittal Number: 22 13 13-2.0 From: JUAN BOLANOS Final Due Date: 05/12/21 Subject: 10' DI SS PIPE & SSMH Description: CCD 94 EXTENDED THE WEST SEWER LINE WHICH CREATED THE FOLLOWING SUBMITTALS: 1. 10' DI CLASS 50 2. SSMH#1 3. SSMH#3 Spec Section: 22 13 13 - SANITARY SEWERS Status: OPEN | Info Exchange
| 12955 | Review Response | Approved as Noted | 2021-04-29 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached submittal review. The invert at the building plumbing POC has been raised, which affects the inverts of the downstream manholes. A draft copy of the plan revision, to be issued in a future CCD, is attached to the submittal review. - J. Grant, DCI Engineers | Info Exchange
| 16696 | Forwarded | For Review | 2021-05-04 | Populous SCA_CCA | Jarrett Grant (DCI Engineers) | 2021-05-11 | Submittal Number: 22 13 13-2.0 From: JUAN BOLANOS Final Due Date: 05/12/21 Subject: 10' DI SS PIPE & SSMH Description: CCD 94 EXTENDED THE WEST SEWER LINE WHICH CREATED THE FOLLOWING SUBMITTALS: 1. 10' DI CLASS 50 2. SSMH#1 3. SSMH#3 Spec Section: 22 13 13 - SANITARY SEWERS Status: OPEN | Info Exchange
| 16759 | Forwarded | For Review | 2021-05-05 | Populous SCA_CCA | Jarrett Grant (DCI Engineers) | 2021-05-12 | Submittal Number: 22 13 13-2.0 From: JUAN BOLANOS Final Due Date: 05/12/21 Subject: 10' DI SS PIPE & SSMH Description: CCD 94 EXTENDED THE WEST SEWER LINE WHICH CREATED THE FOLLOWING SUBMITTALS: 1. 10' DI CLASS 50 2. SSMH#1 3. SSMH#3 Spec Section: 22 13 13 - SANITARY SEWERS Status: OPEN | Info Exchange
| 12970 | Review Response | Approved as Noted | 2021-05-05 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached materials submittal review. Revise MHs per markups and attached plan revision issued under CCD 099. - J. Grant, DCI Engineers | Info Exchange
| 16786 | Responded and Closed | Approved as Noted | 2021-05-06 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached materials submittal review. Revise MHs per markups and attached plan revision issued under CCD 099. - J. Grant, DCI Engineers | Info Exchange
| 17059 | Sent | For Information Only | 2021-05-19 | Populous SCA_CCA | Brooke Burcham (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Responded and Closed (Approved as Noted) to: Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa Remarks: Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached materials submittal review. Revise MHs per markups and attached plan revision issued under CCD 099. - J. Grant, DCI Engineers | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-28 |  | 2021-040-21 221313-0002-00 DI SS Pipe & SSMH PD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-28 |  | 2021-040-21 221313-0002-00 DI SS Pipe & SSMH PD_MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-04-27 02:00 |  | 2021-040-21 221313-0002-00 DI SS Pipe & SSMH PD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-27 02:00 |  | 2021-040-21 221313-0002-00 DI SS Pipe & SSMH PD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-27 02:00 |  | 2021-040-21 221313-0002-00 DI SS Pipe & SSMH PD_MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-04-27 02:00 |  | 2021-040-21 221313-0002-00 DI SS Pipe & SSMH PD_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-06 02:00 |  | 22 13 13-002-00 DI SS Pipe & SSMH PD_MAM_DCI_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-04-27 02:00 |  | 2021-040-21 221313-0002-00 DI SS Pipe & SSMH PD_MAM.pdf
22 15 00-001-00 | 22 15 00 | 22 15 00-001-00 SEDA Compressed Air Equipment for Retractables | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-05-04 | 2021-04-27 | 8 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12679 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-04 | Submittal Number: 22 15 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 04/16/21 Subject: SEDA COMPRESSED AIR EQUIPMENT FOR RETRACTABLES Description: Spec Section: 22 15 00 - COMPRESSED-AIR SYSTEM Status: OPEN | Info Exchange
| 16397 | Forwarded | For Review | 2021-04-20 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-04-27 | Submittal Number: 22 15 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 04/16/21 Subject: SEDA COMPRESSED AIR EQUIPMENT FOR RETRACTABLES Description: Spec Section: 22 15 00 - COMPRESSED-AIR SYSTEM Status: OPEN | Info Exchange
| 12822 | Review Response | Approved | 2021-04-21 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.04.21 | Info Exchange
| 16599 | Responded and Closed | Approved | 2021-04-27 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.04.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-20 |  | 22 15 00-1.0 Air Compressor for SEDA - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-20 |  | 22 15 00-1.0 Air Compressor for SEDA - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-04-19 02:00 |  | 22 15 00-1.0 Air Compressor for SEDA - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-27 02:00 |  | 22 15 00-1.0 Air Compressor for SEDA_ME_POP.pdf
22 15 00-002-00 | 22 15 00 | 22 15 00-002-00 Compressed Air System Accessories | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-21 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-04 | 2021-07-27 | 7 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-07-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14040 | Received | For Review | 2021-07-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-08-04 | Submittal Number: 22 15 00-2.0 From: GRETCHEN TOSHACH Final Due Date: 08/04/21 Subject: COMPRESSED AIR SYSTEM ACCESSORIES Description: Spec Section: 22 15 00 - COMPRESSED-AIR SYSTEM Status: OPEN | Info Exchange
| 18164 | Forwarded | For Review | 2021-07-21 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-28 | Submittal Number: 22 15 00-2.0 From: GRETCHEN TOSHACH Final Due Date: 08/04/21 Subject: COMPRESSED AIR SYSTEM ACCESSORIES Description: Spec Section: 22 15 00 - COMPRESSED-AIR SYSTEM Status: OPEN | Info Exchange
| 14143 | Review Response | Approved | 2021-07-21 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 21 July 2021 | Info Exchange
| 18278 | Responded and Closed | Approved | 2021-07-27 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 21 July 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-21 |  | 22.1500.2 Compressed Air Products Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-21 |  | 22.1500.2 Compressed Air Products Submittal.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-07-21 |  | 22.1500.2 Compressed Air Products Submittal.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-07-27 |  | 22.1500.2 Compressed Air Products Submittal_ME_POP.pdf
22 21 23-001-00 | 22 21 23 - NATURAL GAS SYSTEMS | 22 21 23-001-00 NATURAL GAS SYSTEMS - Product Data | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-10 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-07-24 | 2019-07-11 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-07-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01723 | Received | For Review | 2019-07-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-24 | Submittal Number: 22 21 23-1.0 From: PATRICK KLEIN Final Due Date: 07/23/19 Subject: NATURAL GAS SYSTEMS - PRODUCT DATA Description: MANUFACTURERS PRODUCT DATA : SUBMIT FOR: 1. GAS COCKS. 2. GAS METER. 3. EMERGENCY SHUT-OFF VALVES AND RELAYS. 4. PRESSURE REDUCING VALVES. Spec Section: 22 21 23 - NATURAL GAS SYSTEMS Status: OPEN | Info Exchange
| 02824 | Forwarded | For Review | 2019-07-10 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2019-07-17 | Submittal Number: 22 21 23-1.0 From: PATRICK KLEIN Final Due Date: 07/23/19 Subject: NATURAL GAS SYSTEMS - PRODUCT DATA Description: MANUFACTURERS PRODUCT DATA : SUBMIT FOR: 1. GAS COCKS. 2. GAS METER. 3. EMERGENCY SHUT-OFF VALVES AND RELAYS. 4. PRESSURE REDUCING VALVES. Spec Section: 22 21 23 - NATURAL GAS SYSTEMS Status: OPEN | Info Exchange
| 01750 | Review Response | Approved | 2019-07-11 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 11 July 2019 | Info Exchange
| 02857 | Responded and Closed | Approved | 2019-07-11 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 11 July 2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-09 |  | 22 21 23-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-10 |  | 22 21 23-1.0 Product Data-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-07-11 |  | 22 21 23-1.0 Product Data_MEE Review_11 Jul 19.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-11 |  | 22 21 23-1.0 Product Data_MEE Review_POP.pdf
22 30 00-001-00 | 22 30 00 - PLUMBING EQUIPMENT | 22 30 00-001-00 PLUMBING EQUIPMENT - Product Data | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-29 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-09-13 07:00 | 2019-09-03 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2019-09-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02237 | Received | For Review | 2019-08-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-13 07:00 | Submittal Number: 22 30 00-1.0 From: PATRICK KLEIN Final Due Date: 09/11/19 Subject: PLUMBING EQUIPMENT - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR THE FOLLOWING : - 1. DOMESTIC WATER HEATERS. 2. DOMESTIC HOT WATER STORAGE TANKS. 3. PUMPS. 4. SUMP BASINS. 5. STARTUP REPORT FOR GAS FIRED HEATERS. 6. WARRANTY AND SERVICE POLICIES. Spec Section: 22 30 00 - PLUMBING EQUIPMENT Status: OPEN | Info Exchange
| 03455 | Forwarded | For Review | 2019-08-29 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2019-09-05 | Submittal Number: 22 30 00-1.0 From: PATRICK KLEIN Final Due Date: 09/11/19 Subject: PLUMBING EQUIPMENT - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR THE FOLLOWING : - 1. DOMESTIC WATER HEATERS. 2. DOMESTIC HOT WATER STORAGE TANKS. 3. PUMPS. 4. SUMP BASINS. 5. STARTUP REPORT FOR GAS FIRED HEATERS. 6. WARRANTY AND SERVICE POLICIES. Spec Section: 22 30 00 - PLUMBING EQUIPMENT Status: OPEN | Info Exchange
| 02283 | Review Response | Approved as Noted | 2019-09-03 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached for comments on individual pieces of submitted equipment. David J. Ferguson, P.E. ME Engineers, Inc. 3 September 2019 | Info Exchange
| 03509 | Responded and Closed | Approved as Noted/Resubmit | 2019-09-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Dave Ferguson (ME Engineers) Remarks: See attached for comments on individual pieces of submitted equipment. David J. Ferguson, P.E. ME Engineers, Inc. 3 September 2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-28 |  | 22 30 00-1.0 Plumbing Equipment_MAM.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-28 |  | 22_3000.0_PlbgEquip_submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-28 |  | 22 30 00-1.0 Plumbing Equipment_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-28 |  | 22_3000.0_PlbgEquip_submittal.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-09-03 02:00 |  | 22 30 00-1.0 Plumbing Equipment_MEE Review_3 Sep 19.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-03 02:00 |  | 22 30 00-1.0 Plumbing Equipment_MEE Review_3 Sep 19_POP.pdf
22 30 00-001-01 | 22 30 00 - PLUMBING EQUIPMENT | 22 30 00-001-01 PLUMBING EQUIPMENT - Product Data | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-27 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2019-10-11 | 2019-10-01 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-10-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02580 | Received | For Review | 2019-09-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC); Simran George (Mortenson Construction) | 2019-10-11 | Submittal Number: 22 30 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 10/11/19 Subject: PLUMBING EQUIPMENT - PRODUCT DATA Description: RESUBMIT MANUFACTURERS PRODUCT DATA FOR THE FOLLOWING : EWH-CONC-2 Spec Section: 22 30 00 - PLUMBING EQUIPMENT Status: OPEN | Info Exchange
| 03867 | Forwarded | For Review | 2019-09-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-07 | Submittal Number: 22 30 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 10/11/19 Subject: PLUMBING EQUIPMENT - PRODUCT DATA Description: RESUBMIT MANUFACTURERS PRODUCT DATA FOR THE FOLLOWING : EWH-CONC-2 Spec Section: 22 30 00 - PLUMBING EQUIPMENT Status: OPEN | Info Exchange
| 03868 | Forwarded | For Review | 2019-09-30 | Shaina Burris (Populous) | Dave Ferguson (ME Engineers) |  | Submittal Number: 22 30 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 10/11/19 Subject: PLUMBING EQUIPMENT - PRODUCT DATA Description: RESUBMIT MANUFACTURERS PRODUCT DATA FOR THE FOLLOWING : EWH-CONC-2 Spec Section: 22 30 00 - PLUMBING EQUIPMENT Status: OPEN | Info Exchange
| 02611 | Review Response | Approved | 2019-09-30 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 30 September 2019 | Info Exchange
| 03909 | Responded and Closed | Approved | 2019-10-01 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 30 September 2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-27 |  | 223000-1.1 Plumbing Equipment Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-27 |  | 223000-1.1 Plumbing Equipment Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-27 |  | 223000-1.1 Plumbing Equipment Product Data-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-09-30 |  | 223000-1.1 Plumbing Equipment Product Data-MEE Review_30 Sep 19.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-01 |  | 223000-1.1 Plumbing Equipment Product Data-MEE Review_POP.pdf
22 30 00-003-00 | 22 30 00 - PLUMBING EQUIPMENT | 22 30 00-003-00 PLUMBING EQUIPMENT - SP-7 Product Data | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-28 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-11 | 2020-06-05 | 9 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-06-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06078 | Received | For Review | 2020-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-11 | Submittal Number: 22 30 00-3.0 From: SIMRAN GEORGE Final Due Date: 06/12/20 Subject: PLUMBING EQUIPMENT - SP-7 PRODUCT DATA Description: Spec Section: 22 30 00 - PLUMBING EQUIPMENT Status: OPEN | Info Exchange
| 08231 | Forwarded | For Review | 2020-05-28 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-04 | Submittal Number: 22 30 00-3.0 From: SIMRAN GEORGE Final Due Date: 06/12/20 Subject: PLUMBING EQUIPMENT - SP-7 PRODUCT DATA Description: Spec Section: 22 30 00 - PLUMBING EQUIPMENT Status: OPEN | Info Exchange
| 06874 | Review Response | Approved as Noted/Resubmit | 2020-05-29 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 29 May 2020 | Info Exchange
| 08406 | Responded and Closed | Approved as Noted | 2020-06-05 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Pending response (Approved as Noted/Resubmit) from: Dave Ferguson (ME Engineers) Remarks: Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 29 May 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-27 |  | 22 30 00-2.0 SP-7_SumpPump - MAM[1].pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-27 |  | 22 30 00-3.0 SP-7_SumpPump - MAM[1].pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-05-26 02:00 |  | 22 30 00-3.0 SP-7_SumpPump - MAM[1].pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-05 |  | 22 30 00-3.0 SP-7_SumpPump_MEE_POP.pdf
22 30 00-004-00 | 22 30 00 - PLUMBING EQUIPMENT | 22 30 00-004-00 Electric Water Heaters CCD 064 | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-06 | 2020-07-28 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07116 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 22 30 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 08/11/20 Subject: ELECTRIC WATER HEATERS CCD 064 Description: Spec Section: 22 30 00 - PLUMBING EQUIPMENT Status: OPEN | Info Exchange
| 09505 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-30 | Submittal Number: 22 30 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 08/11/20 Subject: ELECTRIC WATER HEATERS CCD 064 Description: Spec Section: 22 30 00 - PLUMBING EQUIPMENT Status: OPEN | Info Exchange
| 07221 | Review Response | Approved as Noted | 2020-07-24 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached. David J. Ferguson, P.E. ME Engineers, Inc. 24 July 2020 | Info Exchange
| 09634 | Responded and Closed | Approved as Noted | 2020-07-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Dave Ferguson (ME Engineers) Remarks: See attached. David J. Ferguson, P.E. ME Engineers, Inc. 24 July 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 22 30 00-4.0 Elec Water Htrs CCD-064 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | 22 30 00-4.0 Elec Water Htrs CCD-064 - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-07-22 02:00 |  | 22 30 00-4.0 Elec Water Htrs CCD-064 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-28 02:00 |  | 22 30 00-4.0 Elec Water Htrs CCD-064_MEE Review_24 Jul 20_pop.pdf
22 30 00-004-01 | 22 30 00 - PLUMBING EQUIPMENT | 22 30 00-004-01 Electric Water Heaters CCD 064 | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-24 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-08 | 2020-09-29 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08311 | Received | For Review | 2020-09-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-08 | Submittal Number: 22 30 00-4.1 From: GRETCHEN TOSHACH Final Due Date: 10/07/20 Subject: ELECTRIC WATER HEATERS CCD 064 Description: Spec Section: 22 30 00 - PLUMBING EQUIPMENT Status: OPEN | Info Exchange
| 11018 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-01 | Submittal Number: 22 30 00-4.1 From: GRETCHEN TOSHACH Final Due Date: 10/07/20 Subject: ELECTRIC WATER HEATERS CCD 064 Description: Spec Section: 22 30 00 - PLUMBING EQUIPMENT Status: OPEN | Info Exchange
| 08411 | Review Response | Approved | 2020-09-24 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 24 September 2020 | Info Exchange
| 11149 | Responded and Closed | Approved | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 24 September 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 22 30 00-4.1 Elec Water Htrs CCD-064 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 22 30 00-4.1 Elec Water Htrs CCD-064 - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-24 |  | 22 30 00-4.1 Elec Water Htrs CCD-064 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 22 30 00-4.1 Elec Water Htrs CCD-064_ME_POP.pdf
22 40 00-001-00 | 22 40 00 - PLUMBING FIXTURES | 22 40 00-001-00 PLUMBING FIXTURES PD | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-15 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous) |  |  |  | 2019-08-02 | 2019-08-07 | 24 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2019-08-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01781 | Received | For Review | 2019-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-02 | Submittal Number: 22 40 00-1.0 From: PATRICK KLEIN Final Due Date: 07/29/19 Subject: PLUMBING FIXTURES - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR PLUMBING FIXTURES AND ACCESSORIES, IN ACCORDANCE WITH DIVISION 1. Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 02906 | Forwarded | For Review | 2019-07-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2019-07-23 | Submittal Number: 22 40 00-1.0 From: PATRICK KLEIN Final Due Date: 07/29/19 Subject: PLUMBING FIXTURES - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR PLUMBING FIXTURES AND ACCESSORIES, IN ACCORDANCE WITH DIVISION 1. Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 01907 | Review Response | Approved as Noted/Resubmit | 2019-07-29 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached cover sheet for comments on individual fixtures. Populous - Please note a few items (highlighted in yellow) that require architectural review/approval. David J. Ferguson, P.E. 29 July 2019 | Info Exchange
| 03050 | Forwarded | For Review | 2019-07-29 | Josh Dobken (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous) | 2019-07-29 | Submittal Number: 22 40 00-1.0 From: PATRICK KLEIN Final Due Date: 07/29/19 Subject: PLUMBING FIXTURES - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR PLUMBING FIXTURES AND ACCESSORIES, IN ACCORDANCE WITH DIVISION 1. Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Email
| 01996 | Review Response | Approved as Noted/Resubmit | 2019-08-05 | Kuebler Perry (Populous) | Josh Dobken (Populous) |  | - Refer to engineer's comments - Refer to engineering pages 2 and 3 for architect's notes - Resubmit L-6 faucet and sing with a better match to specified product's aesthetic | Info Exchange
| 03149 | Responded and Closed | Approved as Noted/Resubmit | 2019-08-07 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Dave Ferguson (ME Engineers) Remarks: See attached cover sheet for comments on individual fixtures. Populous - Please note a few items (highlighted in yellow) that require architectural review/approval. David J. Ferguson, P.E. 29 July 2019 Response (Approved as Noted/Resubmit) from: Kuebler Perry (Populous) Remarks: - Refer to engineer's comments - Refer to engineering pages 2 and 3 for architect's notes - Resubmit L-6 faucet and sing with a better match to specified product's aesthetic | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-15 |  | 22 40 00-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-16 |  | 22 40 00-1.0 Plumbing Product Data-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-07-29 02:00 |  | 22 40 00-1.0 Plumbing Product Data_MEE Review_29 Jul 19.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-07-14 02:00 |  | 22 40 00-1.0 Product Data-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2019-08-05 02:00 |  | 22 40 00-1.0 Plumbing Product Data_MEE Review_29 Jul 19 POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-14 02:00 |  | 22 40 00-1.0 Product Data-MAM.pdf
22 40 00-001-01 | 22 40 00 - PLUMBING FIXTURES | 22 40 00-001-01 PLUMBING FIXTURES - Product Data | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-29 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Tom Usher (Populous), Kuebler Perry (Populous) |  |  |  | 2019-09-13 07:00 | 2019-09-09 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02240 | Received | For Review | 2019-08-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-13 07:00 | Submittal Number: 22 40 00-1.1 From: PATRICK KLEIN Final Due Date: 09/11/19 Subject: PLUMBING FIXTURES - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR PLUMBING FIXTURES AND ACCESSORIES, IN ACCORDANCE WITH DIVISION 1. Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 03458 | Forwarded | For Review | 2019-08-29 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2019-09-05 | Submittal Number: 22 40 00-1.1 From: PATRICK KLEIN Final Due Date: 09/11/19 Subject: PLUMBING FIXTURES - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR PLUMBING FIXTURES AND ACCESSORIES, IN ACCORDANCE WITH DIVISION 1. Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 02315 | Review Response | Approved as Noted | 2019-09-04 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached. Populous: please note your approval is requested on a few items for finish or shape. I've highlighted them on my cover sheet. David J. Ferguson, P.E. ME Engineers, Inc. 4 September 2019 | Info Exchange
| 03546 | Forwarded | For Review | 2019-09-05 | Josh Dobken (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous) | 2019-09-12 | Submittal Number: 22 40 00-1.1 From: PATRICK KLEIN Final Due Date: 09/11/19 Subject: PLUMBING FIXTURES - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR PLUMBING FIXTURES AND ACCESSORIES, IN ACCORDANCE WITH DIVISION 1. Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Email
| 02361 | Review Response | Approved as Noted | 2019-09-09 | Kuebler Perry (Populous) | Josh Dobken (Populous) |  | See attached. No exceptions taken | Info Exchange
| 03599 | Responded and Closed | Approved as Noted | 2019-09-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Kuebler Perry (Populous) Remarks: See attached. No exceptions taken | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-29 |  | 22 40 00-1.1 Product Data-MAM.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-29 |  | 22 4000.1 Plbg Fixtures submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-29 |  | 22 40 00-1.1 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-29 |  | 22 4000.1 Plbg Fixtures submittal.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-09-04 02:00 |  | 22 40 00-1.1 Plumbing Product Data-RESUBMIT_MEE Review_4 Sep 19.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-08-28 02:00 |  | 22 40 00-1.1 Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-08-28 02:00 |  | 22 4000.1 Plbg Fixtures submittal.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2019-09-09 02:00 |  | 22 40 00-1.1 Plumbing Product Data-MEE Review_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-28 02:00 |  | 22 40 00-1.1 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-28 02:00 |  | 22 4000.1 Plbg Fixtures submittal.pdf
22 40 00-001-02 | 22 40 00 - PLUMBING FIXTURES | 22 40 00-001-02 SH-3 Revision | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-21 | 2021-01-11 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10508 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-21 | Submittal Number: 22 40 00-1.2 From: GRETCHEN TOSHACH Final Due Date: 01/21/21 Subject: SH-3 REVISION Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 13711 | Forwarded | For Review | 2021-01-07 | Populous SCA_CCA | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-14 | Submittal Number: 22 40 00-1.2 From: GRETCHEN TOSHACH Final Due Date: 01/21/21 Subject: SH-3 REVISION Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 10612 | Review Response | Approved as Noted | 2021-01-07 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 January 2021 | Info Exchange
| 13819 | Responded and Closed | Approved as Noted | 2021-01-11 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved as Noted) from: Dave Ferguson (ME Engineers) Remarks: Make Corrections Noted. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 January 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-07 |  | 22 40 00-1.2 SH-3 Shower Rev - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-07 |  | 22 40 00-1.2 SH-3 Shower Rev - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-01-07 |  | 22 40 00-1.2 SH-3 Shower Rev - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-11 |  | 22 40 00-1.2 SH-3 Shower Rev_ME_POP.pdf
22 40 00-004-00 | 22 40 00 - PLUMBING FIXTURES | 22 40 00-004-00 PLUMBING FIXTURES - CCD 054 | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-25 | 2020-05-12 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05804 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-25 | Submittal Number: 22 40 00-4.0 From: SIMRAN GEORGE Final Due Date: 06/12/20 Subject: PLUMBING FIXTURES - CCD 054 Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 07868 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 22 40 00-4.0 From: SIMRAN GEORGE Final Due Date: 06/12/20 Subject: PLUMBING FIXTURES - CCD 054 Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 05833 | Review Response | Revise and Resubmit | 2020-05-12 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Revise and Resubmit: S-6 Faucet No Exceptions Taken: All others David J. Ferguson, P.E. ME Engineers, Inc. 12 May 2020 | Info Exchange
| 07915 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Dave Ferguson (ME Engineers) Remarks: Revise and Resubmit: S-6 Faucet No Exceptions Taken: All others David J. Ferguson, P.E. ME Engineers, Inc. 12 May 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 22 40 00-4.0 Plbg Fixtures-CCD-054 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 22 40 00-4.0 Plbg Fixtures-CCD-054 - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-05-10 02:00 |  | 22 40 00-4.0 Plbg Fixtures-CCD-054 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-12 02:00 |  | 22 40 00-4.0 Plbg Fixtures-CCD-054_MEE Review_12 May 20_POP.pdf
22 40 00-004-01 | 22 40 00 - PLUMBING FIXTURES | 22 40 00-004-01 PLUMBING FIXTURES - CCD 054 | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-02 | 2020-06-24 | 7 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06467 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 22 40 00-4.1 From: SIMRAN GEORGE Final Due Date: 07/01/20 Subject: PLUMBING FIXTURES - CCD 054 Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 08717 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-24 | Submittal Number: 22 40 00-4.1 From: SIMRAN GEORGE Final Due Date: 07/01/20 Subject: PLUMBING FIXTURES - CCD 054 Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 06591 | Review Response | Approved | 2020-06-17 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 June 2020 | Info Exchange
| 08881 | Responded and Closed | Approved | 2020-06-24 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 June 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 22 40 00-4.1 S-6 Faucet - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 22 40 00-4.1 S-6 Faucet - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-06-16 02:00 |  | 22 40 00-4.1 S-6 Faucet - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-24 |  | 22 40 00-4.1 S-6 Faucet - ME_POP.pdf
22 40 00-005-00 | 22 40 00 - PLUMBING FIXTURES | 22 40 00-005-00 Fixtures in Hydrotherapy Areas | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-02 | 2020-06-26 | 9 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-06-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06468 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 22 40 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 06/26/20 Subject: FIXTURES IN HYDROTHERAPY AREAS Description: PLUMBING FIXTURES AROUND HYDROTHERAPY DRAINS PRODUCT DATA Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 08718 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-24 | Submittal Number: 22 40 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 06/26/20 Subject: FIXTURES IN HYDROTHERAPY AREAS Description: PLUMBING FIXTURES AROUND HYDROTHERAPY DRAINS PRODUCT DATA Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 06588 | Review Response | Approved | 2020-06-17 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 June 2020 | Info Exchange
| 06624 | Review Response | Approved as Noted | 2020-06-26 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | See attached. | Info Exchange
| 08933 | Responded and Closed | Approved as Noted | 2020-06-26 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 June 2020 Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 22 40 00-5.0 Hydrotherapy Area Fixtures - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 22 40 00-5.0 Hydrotherapy Area Fixtures - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-06-17 |  | 22 40 00-5.0 Hydrotherapy Area Fixtures - MAM.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-06-26 |  | 22 40 00-5.0 Hydrotherapy Area Fixtures - MEE_POP.pdf
22 40 00-006-00 | 22 40 00 - PLUMBING FIXTURES | 22 40 00-006-00 CCD063 Waterless Urinals | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-21 | 2020-07-08 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06835 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 22 40 00-6.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: CCD063 WATERLESS URINALS Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 09168 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 22 40 00-6.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: CCD063 WATERLESS URINALS Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 06856 | Review Response | Approved | 2020-07-07 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 July 2020 | Info Exchange
| 09199 | Responded and Closed | Approved | 2020-07-08 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 July 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-07 |  | 22 40 00-6.0 UR-3-4 Waterless Urinals - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 22 40 00-6.0 UR-3-4 Waterless Urinals - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-07-07 |  | 22 40 00-6.0 UR-3-4 Waterless Urinals - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-08 |  | 22 40 00-6.0 UR-3-4 Waterless Urinals_ME_POP.pdf
22 40 00-008-00 | 22 40 00 - PLUMBING FIXTURES | 22 40 00-008-00 CCD 066/067 Fixture S-2, S-4, WH-3 and EEWS-1 Changes | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-08 07:00 | 2020-09-01 | 9 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07701 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-09-08 07:00 | Submittal Number: 22 40 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 09/30/20 Subject: CCD 066/067 FIXTURE S-2, S-4, WH-3 AND EEWS-1 CHANGES Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 10250 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-31 | Submittal Number: 22 40 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 09/30/20 Subject: CCD 066/067 FIXTURE S-2, S-4, WH-3 AND EEWS-1 CHANGES Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 07882 | Review Response | Approved | 2020-08-26 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 26 August 2020 | Info Exchange
| 10484 | Responded and Closed | Approved | 2020-09-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 26 August 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 22 40 00-8.0 S-2-4 EEWS-1WH-3 CCD Changes - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 22 40 00-8.0 S-2-4 EEWS-1WH-3 CCD Changes - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-08-24 |  | 22 40 00-8.0 S-2-4 EEWS-1WH-3 CCD Changes - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-01 |  | 22 40 00-8.0 S-2-4 EEWS-1WH-3 CCD Changes_ME_POP.pdf
22 40 00-008-01 | 22 40 00 - PLUMBING FIXTURES | 22 40 00-008-01 EEWS Valve | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-17 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-01 | 2020-09-21 | 5 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08171 | Received | For Review | 2020-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-01 | Submittal Number: 22 40 00-8.1 From: GRETCHEN TOSHACH Final Due Date: 09/25/20 Subject: EEWS VALVE Description: VALVE FOR EMERGENCY EYE WASH STATION Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 10850 | Forwarded | For Review | 2020-09-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-24 | Submittal Number: 22 40 00-8.1 From: GRETCHEN TOSHACH Final Due Date: 09/25/20 Subject: EEWS VALVE Description: VALVE FOR EMERGENCY EYE WASH STATION Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 08234 | Review Response | Approved | 2020-09-17 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 September 2020 | Info Exchange
| 10933 | Responded and Closed | Approved | 2020-09-21 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 17 September 2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-17 |  | 22 40 00-8.1 EEWS Valve - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-17 |  | 22 40 00-8.1 EEWS Valve - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-09-17 |  | 22 40 00-8.1 EEWS Valve - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-21 |  | 22 40 00-8.1 EEWS Valve_ME_POP.pdf
22 40 00-009-00 | 22 40 00 - PLUMBING FIXTURES | 22 40 00-009-00 Plumbing Fixtures - Floor Sinks | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-19 | 2020-10-06 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08550 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 22 40 00-9.0 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: PLUMBING FIXTURES - FLOOR SINKS Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 11312 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-12 | Submittal Number: 22 40 00-9.0 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: PLUMBING FIXTURES - FLOOR SINKS Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 08604 | Review Response | Approved | 2020-10-05 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 5 October 2020 | Info Exchange
| 11373 | Responded and Closed | Approved | 2020-10-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 22 40 00-9.0 - Alt Floor Sinks - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 22 40 00-9.0 - Alt Floor Sinks - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-10-05 |  | 22 40 00-9.0 - Alt Floor Sinks - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-06 |  | 22 40 00-9.0 - Alt Floor Sinks_ME_POP.pdf
22 40 00-010-00 | 22 40 00 - PLUMBING FIXTURES | 22 40 00-010-00 Plumbing Fixtures - Scheir Grease Interceptor | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-25 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-04-09 07:00 | 2021-03-30 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12242 | Received | For Review | 2021-03-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2021-04-09 07:00 | Submittal Number: 22 40 00-10.0 From: SIMRAN GEORGE Final Due Date: 04/14/21 Subject: PLUMBING FIXTURES - SCHEIR GREASE INTERCEPTOR Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 15834 | Forwarded | For Review | 2021-03-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-04-01 | Submittal Number: 22 40 00-10.0 From: SIMRAN GEORGE Final Due Date: 04/14/21 Subject: PLUMBING FIXTURES - SCHEIR GREASE INTERCEPTOR Description: Spec Section: 22 40 00 - PLUMBING FIXTURES Status: OPEN | Info Exchange
| 12302 | Review Response | Approved | 2021-03-26 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 26 March 2021 | Info Exchange
| 15933 | Responded and Closed | Approved | 2021-03-30 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached David J. Ferguson, P.E. ME Engineers, Inc. 26 March 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-25 |  | 22 40 00-10.0 Scheir Grease Interceptor Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-25 |  | 22 40 00-10.0 Scheir Grease Interceptor Product Data-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-03-25 |  | 22 40 00-10.0 Scheir Grease Interceptor Product Data-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-03-30 |  | 22 40 00-10.0 Scheir Grease Interceptor Product Data_ME_POP.pdf
22 63 17-001-00 | 22 63 17 - CARBON-DIOXIDE SYSTEMS | 22 63 17-001-00 CARBON-DIOXIDE SYSTEMS - Product Data | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-26 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-10 | 2019-09-30 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-09-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02535 | Received | For Review | 2019-09-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC) | 2019-10-10 | Submittal Number: 22 63 17-1.0 From: GRETCHEN TOSHACH Final Due Date: 06/11/19 Subject: CARBON-DIOXIDE SYSTEMS - PRODUCT DATA Description: SHOP DRAWINGS : - 1. PROVIDEA SCHEDULE OF ALL PIPING MATERIALS, VALVES, FITTINGS, ETC., FOR APPROVAL COMPLETE WITH ALL PERTINENT DATA SUCH AS MANUFACTURER CATALOG NUMBER, PRESSURE, ETC. SUBMIT CUTS OF VALVES AND PIPING SPECIALTIES. 2. THE RESPONSIBILITY FOR PIPE ROUTING, DESIGN, SIZING AND LAYOUT DRAWINGS IS BY THE DESIGN BUILDER. PROVIDE DESIGN AND SHOP DRAWINGS INDICATING ALL PIPING, FITTINGS, VALVES, AND OTHER COMPONENTS REQUIRED FORA COMPLETE AND OPERABLE SYSTEM. Spec Section: 22 63 17 - CARBON DIOXIDE SYSTEMS Status: OPEN | Info Exchange
| 03821 | Forwarded | For Review | 2019-09-26 | . (Seattle Arena Company, LLC) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-03 | Submittal Number: 22 63 17-1.0 From: GRETCHEN TOSHACH Final Due Date: 06/11/19 Subject: CARBON-DIOXIDE SYSTEMS - PRODUCT DATA Description: SHOP DRAWINGS : - 1. PROVIDEA SCHEDULE OF ALL PIPING MATERIALS, VALVES, FITTINGS, ETC., FOR APPROVAL COMPLETE WITH ALL PERTINENT DATA SUCH AS MANUFACTURER CATALOG NUMBER, PRESSURE, ETC. SUBMIT CUTS OF VALVES AND PIPING SPECIALTIES. 2. THE RESPONSIBILITY FOR PIPE ROUTING, DESIGN, SIZING AND LAYOUT DRAWINGS IS BY THE DESIGN BUILDER. PROVIDE DESIGN AND SHOP DRAWINGS INDICATING ALL PIPING, FITTINGS, VALVES, AND OTHER COMPONENTS REQUIRED FORA COMPLETE AND OPERABLE SYSTEM. Spec Section: 22 63 17 - CARBON DIOXIDE SYSTEMS Status: OPEN | Info Exchange
| 02597 | Review Response | Approved | 2019-09-27 | Dave Ferguson (ME Engineers) | . (Seattle Arena Company, LLC) |  | No Exception Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 27 September 2019 | Info Exchange
| 03887 | Responded and Closed | Approved | 2019-09-30 | . (Seattle Arena Company, LLC) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exception Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 27 September 2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-25 02:00 |  | 22 63 17-1 Carbon Dioxide Systems - Product Data - MAM.pdf
| Forwarded |  | . (Seattle Arena Company, LLC) | 1 | 2019-09-25 02:00 |  | 22 63 17-1 Carbon Dioxide Systems - Product Data - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-09-27 |  | 22 63 17-1 Carbon Dioxide Systems - Product Data_MEE Review_27 Sep 19.pdf
| Responded and Closed |  | . (Seattle Arena Company, LLC) | 1 | 2019-09-30 |  | 22 63 17-1 Carbon Dioxide Systems - Product Data_MEE Review_27 Sep 19_POP.pdf
22 63 17-003-00 | 22 63 17 - CARBON-DIOXIDE SYSTEMS | 22 63 17-003-00 CO2 Control Valves | Closed | Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-30 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-14 | 2021-07-02 | 3 |  | Record Copies; Transfers; Submittals | 22 63 17-003-00-01 - 22 63 17-003-00 CO2 Control Valves | 2 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13718 | Received | For Review | 2021-06-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-07-14 | Submittal Number: 22 63 17-3.0 From: GRETCHEN TOSHACH Final Due Date: 06/11/21 Subject: CO2 CONTROL VALVES Description: Spec Section: 22 63 17 - CARBON DIOXIDE SYSTEMS Status: OPEN | Info Exchange
| 17759 | Forwarded | For Review | 2021-06-29 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-06 | Submittal Number: 22 63 17-3.0 From: GRETCHEN TOSHACH Final Due Date: 06/11/21 Subject: CO2 CONTROL VALVES Description: Spec Section: 22 63 17 - CARBON DIOXIDE SYSTEMS Status: OPEN | Info Exchange
| 13764 | Review Response | Revise and Resubmit | 2021-06-30 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer / Dave Ferguson ME Engineers 2021.06.30 | Info Exchange
| 17816 | Responded and Closed | Revise and Resubmit | 2021-07-02 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer / Dave Ferguson ME Engineers 2021.06.30 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-29 |  | 22 63 17-1 CO2 Control Valves - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-29 |  | 22 63 17-1 CO2 Control Valves - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-06-29 |  | 22 63 17-1 CO2 Control Valves - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-07-02 |  | 22 63 17-003-00 CO2 Control Valves_ME_POP.pdf
22 63 17-003-00-01 | 22 63 17 - CARBON-DIOXIDE SYSTEMS | 22 63 17-003-00 CO2 Control Valves | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 22 63 17-003-00 - 22 63 17-003-00 CO2 Control Valves | -1 | 2021-07-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-02 |  | 22 63 17-003-00 CO2 Control Valves_ME_POP.pdf
23 05 01 26 25 01-010-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01 26 25 01-010-00 MEP Slab Penetrations - D1 Mechanical Mezzanine For Record | Closed | Mechanical, Electrical, Architectural, Plumbing, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-12 | Responded and Closed - No Action Taken or Required |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Greg Briggs (Thornton Tomasetti), Todd Spangler (Populous), Matthew Farber (Thornton Tomasetti), Tom Usher (Populous), Dave Ferguson (ME Engineers), Chris Minter (Populous), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-26 | 2020-06-24 | 13 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06374 | Received | For Review | 2020-06-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-06-26 | Submittal Number: 23 05 01/26 25 01-10.0 From: SIMRAN GEORGE Final Due Date: 07/10/20 Subject: MEP SLAB PENETRATIONS - D1 MECHANICAL MEZZANINE FOR RECORD Description: FOR RECORD SUBMITTAL OF MOST CURRENT MEP PENETRATIONS PLANNED FOR D1 MECHANICAL MEZZANINE SLAB ON METAL DECK Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 08592 | Forwarded | For Review | 2020-06-12 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-19 | Submittal Number: 23 05 01/26 25 01-10.0 From: SIMRAN GEORGE Final Due Date: 07/10/20 Subject: MEP SLAB PENETRATIONS - D1 MECHANICAL MEZZANINE FOR RECORD Description: FOR RECORD SUBMITTAL OF MOST CURRENT MEP PENETRATIONS PLANNED FOR D1 MECHANICAL MEZZANINE SLAB ON METAL DECK Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 08647 | Forwarded | For Review | 2020-06-15 | Josh Dobken (Populous) | Bryan Klote (Populous); Greg Briggs (Thornton Tomasetti); Todd Spangler (Populous); Matthew Farber (Thornton Tomasetti); Tom Usher (Populous); Dave Ferguson (ME Engineers); Chris Minter (Populous); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton... |  | Submittal Number: 23 05 01/26 25 01-10.0 From: SIMRAN GEORGE Final Due Date: 07/10/20 Subject: MEP SLAB PENETRATIONS - D1 MECHANICAL MEZZANINE FOR RECORD Description: FOR RECORD SUBMITTAL OF MOST CURRENT MEP PENETRATIONS PLANNED FOR D1 MECHANICAL MEZZANINE SLAB ON METAL DECK Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 06711 | Review Response | Not Required For Review | 2020-06-16 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Retained for Record only. | Info Exchange
| 06712 | Review Response | No Action Taken or Required | 2020-06-19 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | For record only. Nick Theimer ME Engineers 2020.06.19 | Info Exchange
| 08870 | Responded and Closed | No Action Taken or Required | 2020-06-24 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-12 |  | 23 05 01-26 25 01-10.0 MEP Slab Penetrations D1 Mechanical Mezzanine For Record - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-12 |  | 23 05 01-26 25 01-10.0 MEP Slab Penetrations D1 Mechanical Mezzanine For Record - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-11 02:00 |  | 23 05 01-26 25 01-10.0 MEP Slab Penetrations D1 Mechanical Mezzanine For Record - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-11 02:00 |  | 23 05 01-26 25 01-10.0 MEP Slab Penetrations D1 Mechanical Mezzanine For Record - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-11 02:00 |  | 23 05 01-26 25 01-10.0 MEP Slab Penetrations D1 Mechanical Mezzanine For Record - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-24 |  | 23 05 01-26 25 01-10.0 MEP Slab Penetrations D1 Mechanical Mezzanine For Record_ME_POP.pdf
23 05 01 26 25 01-014-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01 26 25 01-014-00 MEP Slab Penetrations Quad C For Record | Closed | Mechanical, Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-02 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2020-10-16 | 2020-10-28 | 27 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-10-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08506 | Received | For Review | 2020-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ella Pilgrim (M.A. Mortenson Company); Simran George (M.A. Mortenson Company) | 2020-10-16 | Submittal Number: 23 05 01/26 25 01-14.0 From: SIMRAN GEORGE Final Due Date: 10/29/20 Subject: MEP SLAB PENETRATIONS QUAD C FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 11252 | Forwarded | For Review | 2020-10-01 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-08 | Submittal Number: 23 05 01/26 25 01-14.0 From: SIMRAN GEORGE Final Due Date: 10/29/20 Subject: MEP SLAB PENETRATIONS QUAD C FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 08848 | Review Response | No Action Taken or Required | 2020-10-06 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | Reviewed for record only. Nick Theimer ME Engineers 2020.10.06 | Info Exchange
| 11665 | Forwarded | For Review | 2020-10-16 | Bryan Klote (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) |  | Submittal Number: 23 05 01/26 25 01-14.0 From: SIMRAN GEORGE Final Due Date: 10/29/20 Subject: MEP SLAB PENETRATIONS QUAD C FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 09075 | Review Response | Approved as Noted | 2020-10-21 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Shift openings as noted in submittal review. | Info Exchange
| 11981 | Responded and Closed | Approved as Noted | 2020-10-28 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for record only. Nick Theimer ME Engineers 2020.10.06 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Shift openings as noted in submittal review. | Info Exchange
| 12341 | Sent | For Information Only | 2020-11-10 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for record only. Nick Theimer ME Engineers 2020.10.06 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Shift openings as noted in submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 23 05 01-26 25 01-14.0 MEP Slab Penetrations Quad C For Record-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-01 |  | 23 05 01-26 25 01-14.0 MEP Slab Penetrations Quad C For Record-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-10-01 |  | 23 05 01-26 25 01-14.0 MEP Slab Penetrations Quad C For Record-MAM.pdf
| Forwarded |  | Bryan Klote (Populous) | 1 | 2020-10-01 |  | 23 05 01-26 25 01-14.0 MEP Slab Penetrations Quad C For Record-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-01 |  | 23 05 01-26 25 01-14.0 MEP Slab Penetrations Quad C For Record-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-21 |  | 23 05 01-26 25 01-14.0 MEP Slab Penetrations Quad C For Record-ME_TT_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-09-30 02:00 |  | 23 05 01-26 25 01-14.0 MEP Slab Penetrations Quad C For Record-MAM.pdf
23 05 01 26 25 01-015-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01 26 25 01-015-00 MEP Slab Penetrations Quad A For Record | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-06 | Responded and Closed - No Action Taken or Required |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-20 | 2020-10-19 | 14 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-10-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08595 | Received | For Review | 2020-10-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ella Pilgrim (M.A. Mortenson Company); Simran George (M.A. Mortenson Company) | 2020-10-20 | Submittal Number: 23 05 01/26 25 01-15.0 From: SIMRAN GEORGE Final Due Date: 10/19/20 Subject: MEP SLAB PENETRATIONS QUAD A FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 11358 | Forwarded | For Review | 2020-10-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornt... | 2020-10-13 | Submittal Number: 23 05 01/26 25 01-15.0 From: SIMRAN GEORGE Final Due Date: 10/19/20 Subject: MEP SLAB PENETRATIONS QUAD A FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 08847 | Review Response | No Action Taken or Required | 2020-10-06 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | Reviewed for record only. Nick Theimer ME Engineers 2020.10.06 | Info Exchange
| 08983 | Review Response | Approved | 2020-10-14 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Confirm there are no clashes of openings with structural steel members. | Info Exchange
| 11695 | Responded and Closed | No Action Taken or Required | 2020-10-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for record only. Nick Theimer ME Engineers 2020.10.06 Pending response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Confirm there are no clashes of openings with structural steel members. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 23 05 01-26 25 01-15.0 MEP Slab Penetrations Quad A For Record-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 23 05 01-26 25 01-15.0 MEP Slab Penetrations Quad A For Record-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-10-05 |  | 23 05 01-26 25 01-15.0 MEP Slab Penetrations Quad A For Record-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-04 02:00 |  | 23 05 01-26 25 01-15.0 MEP Slab Penetrations Quad A For Record-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-19 |  | 23 05 01-26 25 01-15.0 MEP Slab Penetrations Quad A For Record-MAM_TT_ME_POP.pdf
23 05 01 26 25 01-016-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01 26 25 01-016-00 MEP RCP Plans - Main Concourse Mockup Bathrooms 03.35.02 and 03.35.03 | Closed | Mechanical, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-30 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-13 | 2020-11-11 | 13 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09127 | Received | For Review | 2020-10-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-11-13 | Submittal Number: 23 05 01/26 25 01-16.0 From: SIMRAN GEORGE Final Due Date: 11/13/20 Subject: MEP RCP PLANS - MAIN CONCOURSE MOCKUP BATHROOMS 03.35.02 AND 03.35.03 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 12042 | Forwarded | For Review | 2020-10-30 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-06 | Submittal Number: 23 05 01/26 25 01-16.0 From: SIMRAN GEORGE Final Due Date: 11/13/20 Subject: MEP RCP PLANS - MAIN CONCOURSE MOCKUP BATHROOMS 03.35.02 AND 03.35.03 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 09376 | Review Response | Approved | 2020-11-01 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.01 | Info Exchange
| 12375 | Responded and Closed | Approved as Noted | 2020-11-11 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-30 |  | 23 05 01-26 25 01-16.0 MEP RCP Plans-Main Concourse Mockup Bathrooms 03.35.02 and 03.35.03-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-30 |  | 23 05 01-26 25 01-16.0 MEP RCP Plans-Main Concourse Mockup Bathrooms 03.35.02 and 03.35.03-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-30 |  | 23 05 01-26 25 01-16.0 MEP RCP Plans-Main Concourse Mockup Bathrooms 03.35.02 and 03.35.03-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-11-11 |  | 23 05 01-26 25 01-16.0 MEP RCP Plans-Main Concourse Mockup Bathrooms-MAM-ME_POP.pdf
23 05 01 26 25 01-019-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01 26 25 01-019-00 MECHANICAL AND ELECTRICAL COORDINATION - Premium Space Electrical Penetrations | Closed | Mechanical, Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-29 08:00 | 2021-02-01 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10701 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-01-29 08:00 | Submittal Number: 23 05 01/26 25 01-19.0 From: PATRICK KLEIN Final Due Date: 01/27/21 Subject: MECHANICAL AND ELECTRICAL COORDINATION - PREMIUM SPACE ELECTRICAL PENETRATIONS Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 13922 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-21 | Submittal Number: 23 05 01/26 25 01-19.0 From: PATRICK KLEIN Final Due Date: 01/27/21 Subject: MECHANICAL AND ELECTRICAL COORDINATION - PREMIUM SPACE ELECTRICAL PENETRATIONS Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 14240 | Forwarded | For Review | 2021-01-26 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2021-01-29 | Submittal Number: 23 05 01/26 25 01-19.0 From: PATRICK KLEIN Final Due Date: 01/27/21 Subject: MECHANICAL AND ELECTRICAL COORDINATION - PREMIUM SPACE ELECTRICAL PENETRATIONS Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 11097 | Review Response | Approved as Noted | 2021-01-26 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. TT/Populous shall confirm penetrations are acceptable. Thank you, Mark Lievens ME Engineers 2021.01.26 | Info Exchange
| 11881 | Review Response | Approved | 2021-02-01 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Contractor to coordinate core locations with as-built locations tof structural members to avoid clashes. Contractor to scan for rebar to avoid cutting slab bars prior to coring. | Info Exchange
| 14396 | Responded and Closed | Approved as Noted | 2021-02-01 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.01.26 Pending response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Contractor to coordinate core locations with as-built locations tof structural members to avoid clashes. Contractor to scan for rebar to avoid cutting slab bars prior to coring. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 23 05 01-26 05 01-19.0 Premium Space Electrical Cores-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 23 05 01-26 05 01-19.0 Premium Space Electrical Cores-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-12 02:00 |  | 23 05 01-26 05 01-19.0 Premium Space Electrical Cores-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-01-13 |  | 23 05 01-26 05 01-19.0 Premium Space Electrical Cores-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-12 02:00 |  | 23 05 01-26 05 01-19.0 Premium Space Electrical Cores-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-01 |  | 23 05 01-26 05 01-19.0 Premium Space Electrical Cores-ME_TT_POP.pdf
23 05 01 26 25 01-020-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01 26 25 01-020-00 Ticket Shaft Shops | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-20 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-04 07:00 | 2021-05-25 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-05-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13207 | Received | For Review | 2021-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (Mortenson Construction) | 2021-06-04 07:00 | Submittal Number: 23 05 01/26 25 01-20.0 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: TICKET SHAFT SHOPS Description: SHOP DRAWINGS Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 17095 | Forwarded | For Review | 2021-05-20 | Gretchen Toshach (Mortenson Construction) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-27 | Submittal Number: 23 05 01/26 25 01-20.0 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: TICKET SHAFT SHOPS Description: SHOP DRAWINGS Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 13259 | Review Response | Approved | 2021-05-21 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.05.21 | Info Exchange
| 17156 | Responded and Closed | Approved | 2021-05-25 | Gretchen Toshach (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.05.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-19 |  | 23 05 01-20.0 Ticket Shaft Shops - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-05-19 |  | 23 05 01-20.0 Ticket Shaft Shops - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-18 02:00 |  | 23 05 01-20.0 Ticket Shaft Shops - MAM.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-05-25 02:00 |  | 23 05 01-20.0 Ticket Shaft Shops_ME_POP.pdf
23 05 01 26 25 01-021-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01 26 25 01-021-00 Coordinated MEP RCP Drawings For Record | Closed | Mechanical, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - No Action Taken or Required |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Brian Elwell (Idibri), Kuebler Perry (Populous), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-05-17 | 2021-05-24 | 22 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-05-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12927 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2021-05-17 | Submittal Number: 23 05 01/26 25 01-21.0 From: SIMRAN GEORGE Final Due Date: 05/31/21 Subject: COORDINATED MEP RCP DRAWINGS FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 16708 | Forwarded | For Review | 2021-05-04 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-11 | Submittal Number: 23 05 01/26 25 01-21.0 From: SIMRAN GEORGE Final Due Date: 05/31/21 Subject: COORDINATED MEP RCP DRAWINGS FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 16878 | Forwarded | For Review | 2021-05-11 | Josh Dobken (Populous) | Bryan Klote (Populous); Brian Elwell (Idibri); Kuebler Perry (Populous); Michael Mazzocchi (ME Engineers) | 2021-05-17 | Submittal Number: 23 05 01/26 25 01-21.0 From: SIMRAN GEORGE Final Due Date: 05/31/21 Subject: COORDINATED MEP RCP DRAWINGS FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 13231 | Review Response | No Action Taken or Required | 2021-05-24 | Kuebler Perry (Populous) | Josh Dobken (Populous) |  |  | Info Exchange
| 17118 | Responded and Closed | No Action Taken or Required | 2021-05-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-03 |  | 23 05 01-26 05 01-21.0 Coordinated MEP RCP Drawings for Record-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-03 |  | 23 05 01-26 05 01-21.0 Coordinated MEP RCP Drawings for Record-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-05-02 02:00 |  | 23 05 01-26 05 01-21.0 Coordinated MEP RCP Drawings for Record-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-05-02 |  | 23 05 01-26 05 01-21.0 Coordinated MEP RCP Drawings for Record-MAM.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-05-03 |  | 23 05 01-26 05 01-21.0 Coordinated MEP RCP Drawings for Record-MAM.pdf
23 05 01/26 25 01-001-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-001-00 MEP Slab Penetrations Package 1 | Closed | Mechanical, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-08 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-22 | 2019-09-03 | 27 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2019-09-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02010 | Received | For Review | 2019-08-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2019-08-22 |  | Email
| 03165 | Forwarded | For Review | 2019-08-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-15 |  | Info Exchange
| 03166 | Forwarded | For Review | 2019-08-08 | Shaina Burris (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous) | 2019-08-15 |  | Info Exchange
| 03319 | Forwarded | For Review | 2019-08-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-22 |  | Email
| 03320 | Forwarded | For Review | 2019-08-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-22 |  | Info Exchange
| 02190 | Review Response | Approved as Noted | 2019-08-22 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.08.22 | Info Exchange
| 02281 | Review Response | No Action Taken or Required | 2019-08-30 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | No Exceptions from TT. Received for Record. | Info Exchange
| 03505 | Responded and Closed | Approved as Noted | 2019-09-03 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.08.22 Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: No Exceptions from TT. Received for Record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-08 |  | 23 05 01-26 25 01-001-00 MEP Slab Penetrations Package 1-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-08 |  | 23 05 01-26 25 01-001-00 MEP Slab Penetrations Package 1-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-07 02:00 |  | 23 05 01-26 25 01-001-00 MEP Slab Penetrations Package 1-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-07 02:00 |  | 23 05 01-26 25 01-001-00 MEP Slab Penetrations Package 1-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-07 02:00 |  | 23 05 01-26 25 01-001-00 MEP Slab Penetrations Package 1-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-07 02:00 |  | 23 05 01-26 25 01-001-00 MEP Slab Penetrations Package 1-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-08-07 02:00 |  | 23 05 01-26 25 01-001-00 MEP Slab Penetrations Package 1-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-03 02:00 |  | 23 05 01-26 25 01-001-00 MEP Slab Penetrations Package 1-ME_TT_POP.pdf
23 05 01/26 25 01-002-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-002-00 MEP Slab Penetrations Package 2 | Closed | Mechanical, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-21 | Review Response - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2019-11-04 | 2019-11-08 | 19 |  | Record Copies; Transfers; Submittals |  | 171 |  | 2019-11-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02846 | Received | For Review | 2019-10-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2019-11-04 | Submittal Number: 23 05 01/26 25 01-2.0 From: SIMRAN GEORGE Final Due Date: 11/01/19 Subject: MEP SLAB PENETRATIONS PACKAGE 2 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 04204 | Forwarded | For Review | 2019-10-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-25 | Submittal Number: 23 05 01/26 25 01-2.0 From: SIMRAN GEORGE Final Due Date: 11/01/19 Subject: MEP SLAB PENETRATIONS PACKAGE 2 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 04252 | Forwarded | For Review | 2019-10-22 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) | 2019-10-29 | Submittal Number: 23 05 01/26 25 01-2.0 From: SIMRAN GEORGE Final Due Date: 11/01/19 Subject: MEP SLAB PENETRATIONS PACKAGE 2 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 03060 | Review Response | Approved as Noted | 2019-11-05 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | See TT comments for exceptions noted related to slab penetration locations. | Info Exchange
| 04468 | Forwarded | For Review | 2019-11-05 | Bryan Klote (Populous) | Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2019-11-04 | Harry, can you please review this penetration submittal? We apologize for not getting it sent to you earlier. Most of the pages won't impact you, as they are on the mezzanine level or the parking garage. However, it does cover some of the main concourse concessions. Thanks, Bryan Klote Submittal Number: 23 05 01/26 25 01-2.0 From: SIMRAN GEORGE Final Due Date: 11/01/19 Subject: MEP SLAB PENETRATIONS PACKAGE 2 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 03099 | Review Response | Approved as Noted | 2019-11-06 | Peg Galie (S2O Consultants, Inc.) | Bryan Klote (Populous) |  |  | Info Exchange
| 03111 | Review Response | Approved as Noted | 2019-11-06 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See comments in package. Nick Theimer ME Engineers 2019.11.06 | Info Exchange
| 04549 | Responded and Closed | Approved as Noted | 2019-11-08 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See comments in package. Response (Approved as Noted) from: Peg Galie (S2O Consultants, Inc.) Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: See TT comments for exceptions noted related to slab penetration locations. Response (Approved as Noted) from: bryan klote (populous) Remarks: See comments in package. | Info Exchange
| 05874 | Review Response | Revise and Resubmit | 2020-04-05 | Peg Galie (S2O Consultants, Inc.) | Bryan Klote (Populous) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-18 |  | 23 05 01-26 25 01-2.0 MEP Slab Penetrations Package 2 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-18 |  | 23 05 01-26 25 01-2.0 MEP Slab Penetrations Package 2 - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-10-17 02:00 |  | 23 05 01-26 25 01-2.0 MEP Slab Penetrations Package 2 - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-17 02:00 |  | 23 05 01-26 25 01-2.0 MEP Slab Penetrations Package 2 - MAM.pdf
| Forwarded |  | Bryan Klote (Populous) | 1 | 2019-10-18 |  | 23 05 01-26 25 01-2.0 MEP Slab Penetrations Package 2 - MAM.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2019-10-17 02:00 |  | 23 05 01-26 25 01-2.0 MEP Slab Penetrations Package 2 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-10-17 02:00 |  | 23 05 01-26 25 01-2.0 MEP Slab Penetrations Package 2 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2019-11-08 |  | 23 05 01-26 25 01-2.0 MEP Slab Penetrations Package 2 - MAM_S2O_TT_ME_POP.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2019-10-17 02:00 |  | 23 05 01-26 25 01-2.0 MEP Slab Penetrations Package 2 - MAM.pdf
23 05 01/26 25 01-003-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-003-00 MEP Slab Penetrations Package 3 | Closed | Mechanical, Electrical, Architectural, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-05 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.), Matt Ross (Thornton Tomasetti), Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2019-11-19 | 2019-12-13 | 39 |  | Record Copies; Transfers; Submittals |  | 37 |  | 2019-12-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03042 | Received | For Review | 2019-11-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2019-11-19 | Submittal Number: 23 05 01/26 25 01-3.0 From: SIMRAN GEORGE Final Due Date: 11/26/19 Subject: MEP SLAB PENETRATIONS PACKAGE 3 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 04432 | Forwarded | For Review | 2019-11-04 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-11 | Submittal Number: 23 05 01/26 25 01-3.0 From: SIMRAN GEORGE Final Due Date: 11/26/19 Subject: MEP SLAB PENETRATIONS PACKAGE 3 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 04853 | Forwarded | For Review | 2019-11-26 | Bryan Klote (Populous) | Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.); Matt Ross (Thornton Tomasetti) |  | Submittal Number: 23 05 01/26 25 01-3.0 From: SIMRAN GEORGE Final Due Date: 11/26/19 Subject: MEP SLAB PENETRATIONS PACKAGE 3 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 03406 | Review Response | Approved | 2019-11-27 | Peg Galie (S2O Consultants, Inc.) | Bryan Klote (Populous) |  |  | Info Exchange
| 03409 | Review Response | Approved as Noted | 2019-11-27 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | See attached for comments. No cover page provided as comments are within package. Please note that a good chunk of these spaces are part of deferred scope that is currently being designed. Nick Theimer ME Engineers 2019.11.27 | Info Exchange
| 04879 | Forwarded | For Review | 2019-11-27 | Josh Dobken (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2019-11-19 | Submittal Number: 23 05 01/26 25 01-3.0 From: SIMRAN GEORGE Final Due Date: 11/26/19 Subject: MEP SLAB PENETRATIONS PACKAGE 3 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 03584 | Review Response | Approved as Noted | 2019-12-10 | Matt Ross (Thornton Tomasetti) | Bryan Klote (Populous) |  | See TT comments in the attached markup | Info Exchange
| 05110 | Responded and Closed | Approved as Noted | 2019-12-13 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | See attached markups for comments. Bryan Klote/Populous 12.13.2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-04 |  | 23 05 01-26 25 01-3.0 MEP Slab Penetrations Package 3 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-04 |  | 23 05 01-26 25 01-3.0 MEP Slab Penetrations Package 3 - MAM.pdf
| Forwarded |  | Bryan Klote (Populous) | 1 | 2019-11-04 |  | 23 05 01-26 25 01-3.0 MEP Slab Penetrations Package 3 - MAM.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2019-11-03 01:00 |  | 23 05 01-26 25 01-3.0 MEP Slab Penetrations Package 3 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-03 01:00 |  | 23 05 01-26 25 01-3.0 MEP Slab Penetrations Package 3 - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-03 01:00 |  | 23 05 01-26 25 01-3.0 MEP Slab Penetrations Package 3 - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-03 01:00 |  | 23 05 01-26 25 01-3.0 MEP Slab Penetrations Package 3 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2019-12-13 |  | 23 05 01-26 25 01-3.0 MEP Slab Penetrations Package 3 - MAM_TT-S2O-ME-POP.pdf
23 05 01/26 25 01-004-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-004-00 MEP Slab Penetrations Package 4 | Closed | Mechanical, Electrical, Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-04 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Tom Usher (Populous), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Chris Minter (Populous), Matt Ross (Thornton Tomasetti), Heidi Evans (ME Engineers), Peg Galie (S2O Consultants, Inc.), Harry Schildkraut (S2O Consultants, Inc.) |  |  |  | 2019-12-18 | 2020-01-08 | 36 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03522 | Received | For Review | 2019-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-12-18 | Submittal Number: 23 05 01/26 25 01-4.0 From: PATRICK KLEIN Final Due Date: 12/17/19 Subject: MEP SLAB PENETRATIONS PACKAGE 4 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 04988 | Forwarded | For Review | 2019-12-05 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Tom Usher (Populous); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Chris Minter (Populous); Matt Ross (Thornton Tomasett... | 2019-12-12 | Submittal Number: 23 05 01/26 25 01-4.0 From: PATRICK KLEIN Final Due Date: 12/17/19 Subject: MEP SLAB PENETRATIONS PACKAGE 4 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 05091 | Forwarded | For Review | 2019-12-12 | Josh Dobken (Populous) | Peg Galie (S2O Consultants, Inc.); Harry Schildkraut (S2O Consultants, Inc.) | 2019-12-18 | Submittal Number: 23 05 01/26 25 01-4.0 From: PATRICK KLEIN Final Due Date: 12/17/19 Subject: MEP SLAB PENETRATIONS PACKAGE 4 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 03628 | Review Response | Approved as Noted | 2019-12-13 | Peg Galie (S2O Consultants, Inc.) | Josh Dobken (Populous) |  |  | Info Exchange
| 03713 | Review Response | Approved as Noted | 2019-12-20 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. No cover page provided, refer to comments in package. Nick Theimer ME Engineers 2019.12.19 | Info Exchange
| 03720 | Review Response | Approved as Noted/Resubmit | 2019-12-20 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Please resubmit slab penetrations at ticket office for redesign per CCD-040. | Info Exchange
| 05371 | Responded and Closed | Approved as Noted | 2020-01-07 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  |  | Info Exchange
| 05389 | Reopened | Additional Information | 2020-01-08 16:05 | Bryan Klote (Populous) |  |  | Attachment didn't send.
| 05390 | Responded and Closed | Approved as Noted | 2020-01-08 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | See attached. Bryan Klote/Populous | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-04 02:00 |  | 23 05 01-26 25 01-4.0 MEP Slab Penetrations Package 4 - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-04 02:00 |  | 23 05 01-26 25 01-4.0 MEP Slab Penetrations Package 4 - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-04 02:00 |  | 23 05 01-26 25 01-4.0 MEP Slab Penetrations Package 4 - MAM.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2019-12-04 02:00 |  | 23 05 01-26 25 01-4.0 MEP Slab Penetrations Package 4 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-12-04 02:00 |  | 23 05 01-26 25 01-4.0 MEP Slab Penetrations Package 4 - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-04 02:00 |  | 23 05 01-26 25 01-4.0 MEP Slab Penetrations Package 4 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-01-07 |  | 23 05 01-26 25 01-4.0 MEP Slab Penetrations Package 4 - MAM_TT REVIEW_ME_s2o_POP.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-01-07 |  | 23 05 01-26 25 01-4.0 MEP Slab Penetrations Package 4 - MAM_TT REVIEW_ME_s2o_POP.pdf
23 05 01/26 25 01-005-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-005-00 MEP Slab Penetrations Package 5 | Closed | Electrical, Architectural, Food Services, Mechanical, Plumbing, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-16 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-30 | 2020-02-03 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-02-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03935 | Received | For Review | 2020-01-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-30 | Submittal Number: 23 05 01/26 25 01-5.0 From: PATRICK KLEIN Final Due Date: 01/30/20 Subject: MEP SLAB PENETRATIONS PACKAGE 5 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 05501 | Forwarded | For Review | 2020-01-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-23 | Submittal Number: 23 05 01/26 25 01-5.0 From: PATRICK KLEIN Final Due Date: 01/30/20 Subject: MEP SLAB PENETRATIONS PACKAGE 5 Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 05803 | Responded and Closed | Approved as Noted | 2020-02-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-16 |  | 23 05 01-26 25 01-5.0 MEP Slab Penetrations Package 5 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-16 |  | 23 05 01-26 25 01-5.0 MEP Slab Penetrations Package 5 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-03 02:00 |  | 23 05 01-26 25 01-5.0 MEP Slab Penetrations Package 5 - MAM_TT_ME_S2O_POP.pdf
23 05 01/26 25 01-006-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-006-00 MEP RCP Plans - Event Level | Closed | Mechanical, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-27 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-12 | 2020-03-20 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-03-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04534 | Received | For Review | 2020-02-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-03-12 | Submittal Number: 23 05 01/26 25 01-6.0 From: SIMRAN GEORGE Final Due Date: 03/12/20 Subject: MEP RCP PLANS - EVENT LEVEL Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 06241 | Forwarded | For Review | 2020-02-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-05 | Submittal Number: 23 05 01/26 25 01-6.0 From: SIMRAN GEORGE Final Due Date: 03/12/20 Subject: MEP RCP PLANS - EVENT LEVEL Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 06770 | Responded and Closed | Revise and Resubmit | 2020-03-20 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-26 |  | 23 05 01-26 25 01-6.0 MEP RCP Plans-Event Level-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-26 |  | 23 05 01-26 25 01-6.0 MEP RCP Plans-Event Level-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-03-20 |  | 23 05 01-26 25 01-6.0 MEP RCP Plans-Event Level-MAM_ME_POP.pdf
23 05 01/26 25 01-006-01 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-006-01 MEP RCP Plans - Event Level | Closed | Mechanical, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-08 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-23 | 2020-04-27 | 20 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05250 | Received | For Review | 2020-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) | 2020-04-23 | Submittal Number: 23 05 01/26 25 01-6.1 From: SIMRAN GEORGE Final Due Date: 04/21/20 Subject: MEP RCP PLANS - EVENT LEVEL Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 07142 | Forwarded | For Review | 2020-04-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-15 | Submittal Number: 23 05 01/26 25 01-6.1 From: SIMRAN GEORGE Final Due Date: 04/21/20 Subject: MEP RCP PLANS - EVENT LEVEL Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 05569 | Review Response | Approved as Noted | 2020-04-22 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.22 | Info Exchange
| 07548 | Responded and Closed | Approved as Noted | 2020-04-27 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-07 |  | 23 05 01-26 25 01-6.1 MEP RCP Plans-Event Level-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-07 |  | 23 05 01-26 25 01-6.1 MEP RCP Plans-Event Level-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-06 02:00 |  | 23 05 01-26 25 01-6.1 MEP RCP Plans-Event Level-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-27 02:00 |  | 23 05 01-26 25 01-6.1 MEP RCP Plans-Event Level-MAM-ME_POP.pdf
23 05 01/26 25 01-007-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-007-00 MEP RCP Plans - Mechanical Mezzanine | Closed | Mechanical, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-22 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-06 | 2020-05-06 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05486 | Received | For Review | 2020-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-05-06 | Submittal Number: 23 05 01/26 25 01-7.0 From: SIMRAN GEORGE Final Due Date: 05/05/20 Subject: MEP RCP PLANS - MECHANICAL MEZZANINE Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 07440 | Forwarded | For Review | 2020-04-21 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-28 | Submittal Number: 23 05 01/26 25 01-7.0 From: SIMRAN GEORGE Final Due Date: 05/05/20 Subject: MEP RCP PLANS - MECHANICAL MEZZANINE Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 05768 | Review Response | Approved as Noted | 2020-05-01 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.05.01 | Info Exchange
| 07800 | Responded and Closed | Approved as Noted | 2020-05-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.05.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-21 |  | 23 05 01-26 25 01-7.0 MEP RCP Plans-Mechanical Mezzanine-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-21 |  | 23 05 01-26 25 01-7.0 MEP RCP Plans-Mechanical Mezzanine-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-20 02:00 |  | 23 05 01-26 25 01-7.0 MEP RCP Plans-Mechanical Mezzanine-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-05 |  | 23 05 01-26 25 01-7.0 MEP RCP Plans-Mechanical Mezzanine-MAM-ME_POP.pdf
23 05 01/26 25 01-008-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-008-00 MEP RCP Plans - Suite Level | Closed | Mechanical, Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-30 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-14 | 2020-06-15 | 47 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05642 | Received | For Review | 2020-04-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-05-14 | Submittal Number: 23 05 01/26 25 01-8.0 From: SIMRAN GEORGE Final Due Date: 05/14/20 Subject: MEP RCP PLANS - SUITE LEVEL Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 07638 | Forwarded | For Review | 2020-04-30 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-07 | Submittal Number: 23 05 01/26 25 01-8.0 From: SIMRAN GEORGE Final Due Date: 05/14/20 Subject: MEP RCP PLANS - SUITE LEVEL Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 06406 | Review Response | Approved as Noted | 2020-05-15 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.15 | Info Exchange
| 08609 | Responded and Closed | Approved as Noted | 2020-06-15 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-29 |  | 23 05 01-26 25 01-8.0 MEP RCP Plans-Suite Level-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-29 |  | 23 05 01-26 25 01-8.0 MEP RCP Plans-Suite Level-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-29 |  | 23 05 01-26 25 01-8.0 MEP RCP Plans-Suite Level-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-15 |  | 23 05 01-26 25 01-8.0 MEP RCP Plans-Suite Level-MAM-ME_POP.pdf
23 05 01/26 25 01-009-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-9.0 MEP RCP Plans - Main Concourse Level | Closed | Mechanical, Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Dave Ferguson (ME Engineers) |  |  |  | 2020-05-26 | 2020-06-15 | 36 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05778 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-05-26 | Submittal Number: 23 05 01/26 25 01-9.0 From: SIMRAN GEORGE Final Due Date: 05/20/20 Subject: MEP RCP PLANS - MAIN CONCOURSE LEVEL Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 07835 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 23 05 01/26 25 01-9.0 From: SIMRAN GEORGE Final Due Date: 05/20/20 Subject: MEP RCP PLANS - MAIN CONCOURSE LEVEL Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 08016 | Forwarded | For Review | 2020-05-18 | Josh Dobken (Populous) | Dave Ferguson (ME Engineers) | 2020-05-25 | Submittal Number: 23 05 01/26 25 01-9.0 From: SIMRAN GEORGE Final Due Date: 05/20/20 Subject: MEP RCP PLANS - MAIN CONCOURSE LEVEL Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 06407 | Review Response | Approved as Noted | 2020-05-26 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.26 | Info Exchange
| 08611 | Responded and Closed | Approved as Noted | 2020-06-15 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 23 05 01-26 25 01-9.0 MEP RCP Plans-Main Concourse Level-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 23 05 01-26 25 01-9.0 MEP RCP Plans-Main Concourse Level-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-10 02:00 |  | 23 05 01-26 25 01-9.0 MEP RCP Plans-Main Concourse Level-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-11 |  | 23 05 01-26 25 01-9.0 MEP RCP Plans-Main Concourse Level-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-15 |  | 23 05 01-26 25 01-9.0 MEP RCP Plans-Main Concourse Level-MAM-ME_POP.pdf
23 05 01/26 25 01-011-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-011-00 MEP Slab on Metal Deck Penetrations Quad D - Mech Mezz, Main Con, Upper Con - For Record | Closed | Electrical, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-11 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-08-25 | 2020-08-28 | 18 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07495 | Received | For Review | 2020-08-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-08-25 | Submittal Number: 23 05 01/26 25 01-11.0 From: SIMRAN GEORGE Final Due Date: 08/25/20 Subject: MEP SLAB ON METAL DECK PENETRATIONS QUAD D - MECH MEZZ, MAIN CON, UPPER CON - FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 09980 | Forwarded | For Review | 2020-08-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-17 | Submittal Number: 23 05 01/26 25 01-11.0 From: SIMRAN GEORGE Final Due Date: 08/25/20 Subject: MEP SLAB ON METAL DECK PENETRATIONS QUAD D - MECH MEZZ, MAIN CON, UPPER CON - FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 07739 | Review Response | No Action Taken or Required | 2020-08-14 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | Reviewed for record only. Nick Theimer ME Engineers 2020.08.14 | Info Exchange
| 10119 | Forwarded | For Review | 2020-08-18 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2020-08-25 | Submittal Number: 23 05 01/26 25 01-11.0 From: SIMRAN GEORGE Final Due Date: 08/25/20 Subject: MEP SLAB ON METAL DECK PENETRATIONS QUAD D - MECH MEZZ, MAIN CON, UPPER CON - FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 10304 | Responded and Closed | No Action Taken or Required | 2020-08-25 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for record only. Nick Theimer ME Engineers 2020.08.14 | Info Exchange
| 10345 | Reopened | Additional Information | 2020-08-26 12:53 | Josh Dobken (Populous) |  |  | Reopened for TT to provide comments.
| 07836 | Review Response | Approved as Noted | 2020-08-28 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 10419 | Responded and Closed | Approved as Noted | 2020-08-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: REFER TO TT COMMENTS IN SUBMITTAL. VERIFY NO OPENINGS CLASH WITH STEEL. SHIFT OPENINGS AS NOTED TO AVOID CLASHES. PROVIDE SLAB SUPPORT AROUND OPENINGS AND CLUSTERS OF OPENINGS PER DETAIL 1/S5-22, TYP. SUBMITTAL DOES NOT NEED TO BE RESUBMIT UNLESS ADDITIONAL OPENINGS ARE PROVIDED OR CURRENT OPENINGS ARE SHIFTED OTHER THAN AS NOTED. Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for record only. Nick Theimer ME Engineers 2020.08.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-10 |  | 23 05 01-26 25 01-11.0 MEP Slab Penetrations Quad D For Record-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-10 |  | 23 05 01-26 25 01-11.0 MEP Slab Penetrations Quad D For Record-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-08-09 02:00 |  | 23 05 01-26 25 01-11.0 MEP Slab Penetrations Quad D For Record-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-08-09 02:00 |  | 23 05 01-26 25 01-11.0 MEP Slab Penetrations Quad D For Record-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-25 02:00 |  | 23 05 01-26 25 01-11.0 MEP Slab Penetrations Quad D For Record_ME_pop.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-09 02:00 |  | 23 05 01-26 25 01-11.0 MEP Slab Penetrations Quad D For Record-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-28 02:00 |  | 23 05 01-26 25 01-11.0 MEP Slab Penetrations Quad D For Record_ME_TT REVIEW_POP.pdf
23 05 01/26 25 01-012-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-012-00 East Main Concourse Club Electrical Slab Penetration and Hanger Package | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-04 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2020-09-21 | 2020-09-25 | 22 |  | Record Copies; Transfers; Submittals | 23 05 01/26 25 01-012-01 - 23 05 01/26 25 01-012-00 East Main Concourse Club Electrical Slab Penetration and Hanger Package | 16 |  | 2020-09-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07953 | Received | For Review | 2020-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-09-21 | Submittal Number: 23 05 01/26 25 01-12.0 From: PATRICK KLEIN Final Due Date: 09/21/20 Subject: EAST MAIN CONCOURSE CLUB ELECTRICAL SLAB PENETRATION AND HANGER PACKAGE Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 10577 | Forwarded | For Review | 2020-09-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-15 | Submittal Number: 23 05 01/26 25 01-12.0 From: PATRICK KLEIN Final Due Date: 09/21/20 Subject: EAST MAIN CONCOURSE CLUB ELECTRICAL SLAB PENETRATION AND HANGER PACKAGE Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 08232 | Review Response | Approved as Noted | 2020-09-16 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. This shall be sent to TT for review. Thank you, Mark Lievens ME Engineers 2020.09.16 | Info Exchange
| 10930 | Forwarded | For Review | 2020-09-21 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) | 2020-09-21 | Submittal Number: 23 05 01/26 25 01-12.0 From: PATRICK KLEIN Final Due Date: 09/21/20 Subject: EAST MAIN CONCOURSE CLUB ELECTRICAL SLAB PENETRATION AND HANGER PACKAGE Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 08343 | Review Response | Revise and Resubmit | 2020-09-23 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Provide Loads imposed and calcs for all hangers for EOR to review. | Info Exchange
| 11055 | Responded and Closed | Revise and Resubmit | 2020-09-25 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. This shall be sent to TT for review. Thank you, Mark Lievens ME Engineers 2020.09.16 Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Provide Loads imposed and calcs for all hangers for EOR to review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-04 |  | 23 05 01-26 25 01-12.0 East MC Club Elec Slab Pen and Hanger Package-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-04 |  | 23 05 01-26 25 01-12.0 East MC Club Elec Slab Pen and Hanger Package-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-03 02:00 |  | 23 05 01-26 25 01-12.0 East MC Club Elec Slab Pen and Hanger Package-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-03 02:00 |  | 23 05 01-26 25 01-12.0 East MC Club Elec Slab Pen and Hanger Package-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-03 02:00 |  | 23 05 01-26 25 01-12.0 East MC Club Elec Slab Pen and Hanger Package-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-25 02:00 |  | 23 05 01-26 25 01-12.0 East MC Club Elec Slab Pen and Hanger Package-MAM-ME_TT REVIEW_pop.pdf
23 05 01/26 25 01-012-01 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-012-00 East Main Concourse Club Electrical Slab Penetration and Hanger Package | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 23 05 01/26 25 01-012-00 - 23 05 01/26 25 01-012-00 East Main Concourse Club Electrical Slab Penetration and Hanger Package | -1 | 2020-10-09
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 02:00 |  | 23 05 01-26 25 01-12.0 East MC Club Elec Slab Pen and Hanger Package-MAM-ME_TT REVIEW_pop.pdf
23 05 01/26 25 01-013-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-013-00 MEP Slab on Metal Deck Penetrations Quad D - Suite Level - For Record | Closed | Mechanical, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-16 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-09-30 | 2020-09-25 | 10 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-09-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08152 | Received | For Review | 2020-09-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-30 | Submittal Number: 23 05 01/26 25 01-13.0 From: SIMRAN GEORGE Final Due Date: 09/30/20 Subject: MEP SLAB ON METAL DECK PENETRATIONS QUAD D - SUITE LEVEL - FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 10825 | Forwarded | For Review | 2020-09-16 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-23 | Submittal Number: 23 05 01/26 25 01-13.0 From: SIMRAN GEORGE Final Due Date: 09/30/20 Subject: MEP SLAB ON METAL DECK PENETRATIONS QUAD D - SUITE LEVEL - FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 08253 | Review Response | No Action Taken or Required | 2020-09-21 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | Reviewed for record only. Nick Theimer ME Engineers 2020.09.21 | Info Exchange
| 10959 | Forwarded | For Review | 2020-09-22 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) |  | Submittal Number: 23 05 01/26 25 01-13.0 From: SIMRAN GEORGE Final Due Date: 09/30/20 Subject: MEP SLAB ON METAL DECK PENETRATIONS QUAD D - SUITE LEVEL - FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 08344 | Review Response | Approved as Noted | 2020-09-23 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | There is one cluster of sleeves in this submittal that requires steel to support deck per 1/S5-22 unless sleeves are spaced out to avoid the cluster clasification per 1/S5-22. | Info Exchange
| 11057 | Responded and Closed | Approved as Noted | 2020-09-25 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for record only. Nick Theimer ME Engineers 2020.09.21 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: There is one cluster of sleeves in this submittal that requires steel to support deck per 1/S5-22 unless sleeves are spaced out to avoid the cluster clasification per 1/S5-22. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-16 |  | 23 05 01-26 25 01-13.0 MEP Slab on Metal Deck Penetrations Quad D-Suite Level-For Record - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-16 |  | 23 05 01-26 25 01-13.0 MEP Slab on Metal Deck Penetrations Quad D-Suite Level-For Record - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-16 |  | 23 05 01-26 25 01-13.0 MEP Slab on Metal Deck Penetrations Quad D-Suite Level-For Record - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-16 |  | 23 05 01-26 25 01-13.0 MEP Slab on Metal Deck Penetrations Quad D-Suite Level-For Record - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-15 02:00 |  | 23 05 01-26 25 01-13.0 MEP Slab on Metal Deck Penetrations Quad D-Suite Level-For Record - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-25 02:00 |  | 23 05 01-26 25 01-13.0 MEP Slab on Metal Deck Penetrations Quad D-Suite Level-For Record - MAM_ME_TT REVIEW_pop.pdf
23 05 01/26 25 01-017-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-017-00 MEP Slab Penetrations Quads B, E, and F For Record | Closed | Mechanical, Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-21 | 2021-01-04 | 29 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-01-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09932 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-12-21 | Submittal Number: 23 05 01/26 25 01-17.0 From: SIMRAN GEORGE Final Due Date: 12/21/20 Subject: MEP SLAB PENETRATIONS QUADS B, E, AND F FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 13010 | Forwarded | For Review | 2020-12-07 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornt... | 2020-12-14 | Submittal Number: 23 05 01/26 25 01-17.0 From: SIMRAN GEORGE Final Due Date: 12/21/20 Subject: MEP SLAB PENETRATIONS QUADS B, E, AND F FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 10418 | Review Response | No Action Taken or Required | 2020-12-07 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal that we have received for record. Thank you, Mark Lievens ME Engineers 2020.12.07 | Info Exchange
| 10839 | Review Response | Approved as Noted | 2020-12-18 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 13597 | Responded and Closed | Approved as Noted | 2021-01-04 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-05 |  | 23 05 01-26 25 01-17.0 MEP Slab Penetrations Quads B E and F For Record-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-05 |  | 23 05 01-26 25 01-17.0 MEP Slab Penetrations Quads B E and F For Record-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-12-05 |  | 23 05 01-26 25 01-17.0 MEP Slab Penetrations Quads B E and F For Record-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-12-04 02:00 |  | 23 05 01-26 25 01-17.0 MEP Slab Penetrations Quads B E and F For Record-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-01-04 |  | 23 05 01-26 25 01-17.0 MEP Slab Penetrations Quads B E and F For Record-ME_TT_POP.pdf
23 05 01/26 25 01-018-00 | 23 05 01 - MECHANICAL AND ELECTRICAL COORDINATION | 23 05 01/26 25 01-018-00 MEP Slab Penetrations Space Needle For Record | Closed | Mechanical, Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-25 | 2021-01-12 | 2 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-01-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10561 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Simran George (Mortenson Construction) | 2021-01-25 | Submittal Number: 23 05 01/26 25 01-18.0 From: SIMRAN GEORGE Final Due Date: 01/22/21 Subject: MEP SLAB PENETRATIONS SPACE NEEDLE FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 13760 | Forwarded | For Review | 2021-01-08 | Simran George (Mortenson Construction) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornt... | 2021-01-15 | Submittal Number: 23 05 01/26 25 01-18.0 From: SIMRAN GEORGE Final Due Date: 01/22/21 Subject: MEP SLAB PENETRATIONS SPACE NEEDLE FOR RECORD Description: Spec Section: 23 05 01/26 25 01 - MECHANICAL AND ELECTRICAL COORDINATION Status: OPEN | Info Exchange
| 10648 | Review Response | Approved as Noted | 2021-01-11 | Matt Ross (Thornton Tomasetti) | Simran George (Mortenson Construction) |  |  | Info Exchange
| 10649 | Review Response | No Action Taken or Required | 2021-01-11 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Submitted for record only. Nick Theimer ME Engineers 2021.01.11 | Info Exchange
| 13859 | Responded and Closed | Approved as Noted | 2021-01-12 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Submitted for record only. Nick Theimer ME Engineers 2021.01.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | 23 05 01-26 25 01-18.0 MEP Slab Penetrations Space Needle For Record-MAM.pdf
| Forwarded |  | Simran George (Mortenson Construction) | 1 | 2021-01-08 |  | 23 05 01-26 25 01-18.0 MEP Slab Penetrations Space Needle For Record-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-07 02:00 |  | 23 05 01-26 25 01-18.0 MEP Slab Penetrations Space Needle For Record-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-07 02:00 |  | 23 05 01-26 25 01-18.0 MEP Slab Penetrations Space Needle For Record-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-12 02:00 |  | 23 05 01-26 25 01-18.0 MEP Slab Penetrations Space Needle For Record-MAM_Combined_pop.pdf
23 05 02-004-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-004-00 Event Level Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-18 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-03 | 2020-03-10 | 22 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04386 | Received | For Review | 2020-02-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-03 | Submittal Number: 23 05 02-4.0 From: GRETCHEN TOSHACH Final Due Date: 03/17/20 Subject: EVENT LEVEL SHOP DRAWINGS Description: EVENT LEVEL SHOP DRAWINGS FOR MECHANICAL SHEET METAL AND PIPING Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06059 | Forwarded | For Review | 2020-02-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-25 | Submittal Number: 23 05 02-4.0 From: GRETCHEN TOSHACH Final Due Date: 03/17/20 Subject: EVENT LEVEL SHOP DRAWINGS Description: EVENT LEVEL SHOP DRAWINGS FOR MECHANICAL SHEET METAL AND PIPING Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 04739 | Review Response | Approved as Noted/Resubmit | 2020-03-04 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Resubmittal requested is for formal documentation. Nick Theimer ME Engineers 2020.03.04 | Info Exchange
| 06511 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-10 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Resubmittal requested is for formal documentation. Nick Theimer ME Engineers 2020.03.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-17 |  | 23 05 02-4.0 - 100 Mech Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-17 |  | 23 05 02-4.0 - 100 Mech Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-02-16 02:00 |  | 23 05 02-4.0 - 100 Mech Shop Drawings - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-10 02:00 |  | 23 05 02-4.0 - 100 Mech Shop Drawings_ME_POP.pdf
23 05 02-004-01 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-004-01 Event Level Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-09 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-23 | 2020-11-21 | 13 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-11-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09297 | Received | For Review | 2020-11-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-11-23 | Submittal Number: 23 05 02-4.1 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: EVENT LEVEL SHOP DRAWINGS Description: RESUBMITTAL FOR FORMAL DOCUMENTATION Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 12268 | Forwarded | For Review | 2020-11-09 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-16 | Submittal Number: 23 05 02-4.1 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: EVENT LEVEL SHOP DRAWINGS Description: RESUBMITTAL FOR FORMAL DOCUMENTATION Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09655 | Review Response | Approved as Noted | 2020-11-12 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.11.12 | Info Exchange
| 12706 | Responded and Closed | Approved as Noted | 2020-11-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.11.12 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 23 05 02-4.1 Event Lvl HVAC Revs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 23 05 02-4.1 Event Lvl HVAC Revs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-05 02:00 |  | 23 05 02-4.1 Event Lvl HVAC Revs - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-21 02:00 |  | 23 05 02-4.1 Event Lvl HVAC Revs_ME_pop.pdf
23 05 02-005-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-005-00 Hydronic Riser | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-06 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-20 | 2020-03-25 | 20 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-03-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04680 | Received | For Review | 2020-03-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-20 | Submittal Number: 23 05 02-5.0 From: GRETCHEN TOSHACH Final Due Date: 03/19/20 Subject: HYDRONIC RISER Description: MECHANICAL PIPING HYDRONIC RISER SHOP DRAWINGS Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06438 | Forwarded | For Review | 2020-03-05 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-12 | Submittal Number: 23 05 02-5.0 From: GRETCHEN TOSHACH Final Due Date: 03/19/20 Subject: HYDRONIC RISER Description: MECHANICAL PIPING HYDRONIC RISER SHOP DRAWINGS Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05050 | Review Response | No Action Taken or Required | 2020-03-13 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Reviewed for general conformance with the design intent. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| 06872 | Responded and Closed | No Action Taken or Required | 2020-03-25 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for general conformance with the design intent. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-05 |  | 23 05 02-5.0 Hyrdonic Risers Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-05 |  | 23 05 02-5.0 Hyrdonic Risers Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-04 02:00 |  | 23 05 02-5.0 Hyrdonic Risers Shop Drawings - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-25 02:00 |  | 23 05 02-5.0 Hyrdonic Risers Shop Drawings_ME_pop.pdf
23 05 02-006-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-006-00 200 Sheet Metal Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-31 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-15 | 2020-04-15 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05151 | Received | For Review | 2020-03-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-15 | Submittal Number: 23 05 02-6.0 From: GRETCHEN TOSHACH Final Due Date: 04/14/20 Subject: 200 SHEET METAL SHOP DRAWINGS Description: 200 LEVEL MECHANICAL SHEET METAL SHOP DRAWINGS Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06984 | Forwarded | For Review | 2020-03-31 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-07 | Submittal Number: 23 05 02-6.0 From: GRETCHEN TOSHACH Final Due Date: 04/14/20 Subject: 200 SHEET METAL SHOP DRAWINGS Description: 200 LEVEL MECHANICAL SHEET METAL SHOP DRAWINGS Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05476 | Review Response | Approved as Noted | 2020-04-14 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.04.14 | Info Exchange
| 07298 | Responded and Closed | Approved as Noted | 2020-04-15 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Pending response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.04.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-31 |  | 23 05 02-6.0 200 Sheetmetal Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-31 |  | 23 05 02-6.0 200 Sheetmetal Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-30 02:00 |  | 23 05 02-6.0 200 Sheetmetal Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-04-15 |  | 23 05 02-6.0 200 Sheetmetal Shop Drawings_ME_POP.pdf
23 05 02-007-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-007-00 200 Mech-pipe Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-02 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-20 07:00 | 2020-04-15 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05179 | Received | For Review | 2020-04-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-20 07:00 | Submittal Number: 23 05 02-7.0 From: GRETCHEN TOSHACH Final Due Date: 04/14/20 Subject: 200 MECH-PIPE SHOP DRAWINGS Description: SHOP DRAWINGS FOR MEHCANICAL PIPING 200 LEVEL MEZZANINE Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07025 | Forwarded | For Review | 2020-04-02 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-09 | Submittal Number: 23 05 02-7.0 From: GRETCHEN TOSHACH Final Due Date: 04/14/20 Subject: 200 MECH-PIPE SHOP DRAWINGS Description: SHOP DRAWINGS FOR MEHCANICAL PIPING 200 LEVEL MEZZANINE Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05477 | Review Response | Approved as Noted | 2020-04-14 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.04.14 | Info Exchange
| 07297 | Responded and Closed | Approved as Noted | 2020-04-15 | Bryan Klote (Populous) | Nick Theimer (ME Engineers); Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.04.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-02 |  | 23 05 02-7.0 200 M-Pipe Shop Drawings -MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-02 |  | 23 05 02-7.0 200 M-Pipe Shop Drawings -MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-01 02:00 |  | 23 05 02-7.0 200 M-Pipe Shop Drawings -MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-04-15 |  | 23 05 02-7.0 200 M-Pipe Shop Drawings_ME_POP.pdf
23 05 02-008-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-008-00 400 Suite Level Sheet Metal Shop Drawings - Area D+C | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-22 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-06 | 2020-05-06 | 15 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05504 | Received | For Review | 2020-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-06 | Submittal Number: 23 05 02-8.0 From: GRETCHEN TOSHACH Final Due Date: 05/06/20 Subject: 400 SUITE LEVEL SHEET METAL SHOP DRAWINGS - AREA D+C Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07462 | Forwarded | For Review | 2020-04-22 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-29 | Submittal Number: 23 05 02-8.0 From: GRETCHEN TOSHACH Final Due Date: 05/06/20 Subject: 400 SUITE LEVEL SHEET METAL SHOP DRAWINGS - AREA D+C Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05764 | Review Response | No Action Taken or Required | 2020-04-28 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.04.28 | Info Exchange
| 07803 | Responded and Closed | Approved as Noted | 2020-05-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 23 05 02-8.0 400 Ste Lvl SM Areas_D-C Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 23 05 02-8.0 400 Ste Lvl SM Areas_D-C Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-21 02:00 |  | 23 05 02-8.0 400 Ste Lvl SM Areas_D-C Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-06 |  | 23 05 02-8.0 400 Ste Lvl SM Areas_D-C Shop Drawings_ME_POP.pdf
23 05 02-010-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-010-00 400 Suite Level Mech Piping Shop Drawings - Area D + C | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-23 | Review Response - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-07 | 2020-05-06 | 14 |  | Record Copies; Transfers; Submittals |  | 43 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05509 | Received | For Review | 2020-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-07 | Submittal Number: 23 05 02-10.0 From: GRETCHEN TOSHACH Final Due Date: 05/06/20 Subject: 400 SUITE LEVEL MECH PIPING SHOP DRAWINGS - AREA D + C Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07468 | Forwarded | For Review | 2020-04-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-30 | Submittal Number: 23 05 02-10.0 From: GRETCHEN TOSHACH Final Due Date: 05/06/20 Subject: 400 SUITE LEVEL MECH PIPING SHOP DRAWINGS - AREA D + C Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05873 | Review Response | No Action Taken or Required | 2020-04-28 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.04.28 | Info Exchange
| 07801 | Responded and Closed | No Action Taken or Required | 2020-05-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| 06197 | Review Response | Approved | 2020-06-04 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | Review disposition has been updated. Attaching the new submittal cover sheets. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 23 05 02-10.0 400 Ste Lvl Mech Pipe AreaD_C Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 23 05 02-10.0 400 Ste Lvl Mech Pipe AreaD_C Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-21 02:00 |  | 23 05 02-10.0 400 Ste Lvl Mech Pipe AreaD_C Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-06 |  | 23 05 02-10.0 400 Ste Lvl Mech Pipe AreaD_C Shop Drawings_ME_POP.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-04 02:00 |  | 23 05 02-10.0 400 Ste Lvl Mech Pipe AreaD_C Shop Drawings_ME_UPDATED.pdf
23 05 02-022-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-022-00 300 Main Con Sheet Metal Shop Drawings - Area D+C | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-23 | Review Response - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-07 | 2020-05-06 | 14 |  | Record Copies; Transfers; Submittals |  | 43 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05510 | Received | For Review | 2020-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-07 | Submittal Number: 23 05 02-22.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 300 MAIN CON SHEET METAL SHOP DRAWINGS - AREA D+C Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07469 | Forwarded | For Review | 2020-04-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-30 | Submittal Number: 23 05 02-22.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 300 MAIN CON SHEET METAL SHOP DRAWINGS - AREA D+C Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05765 | Review Response | No Action Taken or Required | 2020-05-05 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.05 | Info Exchange
| 07805 | Responded and Closed | Approved as Noted | 2020-05-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| 06194 | Review Response | Approved as Noted | 2020-06-04 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 23 05 22-22.0 300 LVL SM Areas_D-C Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 23 05 22-22.0 300 LVL SM Areas_D-C Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-21 02:00 |  | 23 05 22-22.0 300 LVL SM Areas_D-C Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-06 |  | 23 05 22-22.0 300 LVL SM Areas_D-C Shop Drawings_ME_POP.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-04 02:00 |  | 23 05 22-22.0 300 LVL SM Areas_D-C Shop Drawings_ME_UPDATED.pdf
23 05 02-023-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-023-00 300 Main Con Mech Piping Shop Drawings - Area D+C | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-23 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-07 | 2020-05-06 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05511 | Received | For Review | 2020-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-07 | Submittal Number: 23 05 02-23.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 300 MAIN CON MECH PIPING SHOP DRAWINGS - AREA D+C Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07470 | Forwarded | For Review | 2020-04-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-30 | Submittal Number: 23 05 02-23.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 300 MAIN CON MECH PIPING SHOP DRAWINGS - AREA D+C Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05766 | Review Response | No Action Taken or Required | 2020-05-05 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.05 | Info Exchange
| 07809 | Responded and Closed | Approved as Noted | 2020-05-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 23 05 02-23.0 300 Main Con AreaD_C Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 23 05 02-23.0 300 Main Con AreaD_C Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-21 02:00 |  | 23 05 02-23.0 300 Main Con AreaD_C Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-06 |  | 23 05 02-23.0 300 Main Con AreaD_C Shop Drawings_ME_POP.pdf
23 05 02-024-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-024-00 300 Main Con Sheet Metal Shop Drawings - Area A,B,E,F | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-26 07:00 | 2020-05-19 | 9 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05779 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 23 05 02-24.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 300 MAIN CON SHEET METAL SHOP DRAWINGS - AREA A,B,E,F Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07836 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 23 05 02-24.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 300 MAIN CON SHEET METAL SHOP DRAWINGS - AREA A,B,E,F Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06127 | Review Response | Approved as Noted | 2020-05-15 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.15 | Info Exchange
| 08057 | Responded and Closed | Approved as Noted | 2020-05-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 23 05 02-24.0 300ABEF SM Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 23 05 02-24.0 300ABEF SM Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 23 05 02-24.0 300ABEF SM Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-19 |  | 23 05 02-24.0 300ABEF SM Shop Drawings_ME_POP.pdf
23 05 02-025-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-025-00 300 Main Con Mech Piping Shop Drawings - Area A,B,E,F | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-26 07:00 | 2020-05-19 | 9 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05780 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 23 05 02-25.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 300 MAIN CON MECH PIPING SHOP DRAWINGS - AREA A,B,E,F Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07837 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 23 05 02-25.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 300 MAIN CON MECH PIPING SHOP DRAWINGS - AREA A,B,E,F Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06128 | Review Response | Approved as Noted | 2020-05-15 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.15 | Info Exchange
| 08055 | Responded and Closed | Approved as Noted | 2020-05-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Pending response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 23 05 02-24.0 300ABEF MP Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 23 05 02-24.0 300ABEF MP Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 23 05 02-24.0 300ABEF MP Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-19 |  | 23 05 02-25.0 300ABEF MP Shop Drawings_ME_POP.pdf
23 05 02-026-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-026-00 400 Suite Level Mech Piping Shop Drawings - Area A,B,E,F | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-23 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-07 | 2020-05-12 | 20 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05512 | Received | For Review | 2020-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-07 | Submittal Number: 23 05 02-26.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 400 SUITE LEVEL MECH PIPING SHOP DRAWINGS - AREA A,B,E,F Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07471 | Forwarded | For Review | 2020-04-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-30 | Submittal Number: 23 05 02-26.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 400 SUITE LEVEL MECH PIPING SHOP DRAWINGS - AREA A,B,E,F Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05831 | Review Response | Approved as Noted | 2020-05-11 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.11 | Info Exchange
| 07912 | Responded and Closed | Approved as Noted | 2020-05-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 23 05 02-26.0 400 Ste Lvl MP Areas ABEF Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 23 05 02-26.0 400 Ste Lvl MP Areas ABEF Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-21 02:00 |  | 23 05 02-26.0 400 Ste Lvl MP Areas ABEF Shop Drawings - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-12 02:00 |  | 23 05 02-26.0 400 Ste Lvl MP Areas ABEF Shop Drawings_ME_POP.pdf
23 05 02-027-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-027-00 400 Suite Level Sheet Metal Shop Drawings - Area A,B,E,F | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-23 | Review Response - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-07 | 2020-05-06 | 14 |  | Record Copies; Transfers; Submittals |  | 43 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05513 | Received | For Review | 2020-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-07 | Submittal Number: 23 05 02-27.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 400 SUITE LEVEL SHEET METAL SHOP DRAWINGS - AREA A,B,E,F Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07472 | Forwarded | For Review | 2020-04-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-30 | Submittal Number: 23 05 02-27.0 From: GRETCHEN TOSHACH Final Due Date: 05/21/20 Subject: 400 SUITE LEVEL SHEET METAL SHOP DRAWINGS - AREA A,B,E,F Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05767 | Review Response | No Action Taken or Required | 2020-05-04 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.04 | Info Exchange
| 07811 | Responded and Closed | Approved as Noted | 2020-05-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| 06196 | Review Response | Approved as Noted | 2020-06-04 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | Review disposition has been updated. Attaching the new submittal cover sheets. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 23 05 02-27.0 400 Ste Lvl SM Areas ABEF Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 23 05 02-27.0 400 Ste Lvl SM Areas ABEF Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-21 02:00 |  | 23 05 02-27.0 400 Ste Lvl SM Areas ABEF Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-06 |  | 23 05 02-27.0 400 Ste Lvl SM Areas ABEF Shop Drawings_ME_POP.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-04 02:00 |  | 23 05 02-27.0 400 Ste Lvl SM Areas ABEF Shop Drawings_ME_UPDATED.pdf
23 05 02-032-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-032-00 550 Space Needle Sheet Metal Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-23 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-08 07:00 | 2020-07-06 | 14 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06555 | Received | For Review | 2020-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-08 07:00 | Submittal Number: 23 05 02-32.0 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: 550 SPACE NEEDLE SHEET METAL SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 08823 | Forwarded | For Review | 2020-06-22 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-29 | Submittal Number: 23 05 02-32.0 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: 550 SPACE NEEDLE SHEET METAL SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06871 | Review Response | Approved as Noted/Resubmit | 2020-06-30 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.06.30 | Info Exchange
| 09105 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-22 |  | 23 05 02-32.0 - 550 SM Shop Drawings- MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-22 |  | 23 05 02-32.0 - 550 SM Shop Drawings- MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-21 02:00 |  | 23 05 02-32.0 - 550 SM Shop Drawings- MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-06 |  | 23 05 02-32.0 - 550 SM Shop Drawings_ME_POP.pdf
23 05 02-032-01 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-032-01 550 Space Needle Sheet Metal Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-03 08:00 | 2020-11-20 | 4 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09475 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 23 05 02-32.1 From: GRETCHEN TOSHACH Final Due Date: 11/30/20 Subject: 550 SPACE NEEDLE SHEET METAL SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 12493 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-24 | Submittal Number: 23 05 02-32.1 From: GRETCHEN TOSHACH Final Due Date: 11/30/20 Subject: 550 SPACE NEEDLE SHEET METAL SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09645 | Review Response | Approved as Noted | 2020-11-18 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.11.18 | Info Exchange
| 12693 | Responded and Closed | Approved as Noted | 2020-11-20 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.11.18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 23 05 02-32.1 Space Needle SM Shops - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 23 05 02-32.1 Space Needle SM Shops - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-21 02:00 |  | 23 05 02-32.1 Space Needle SM Shops_ME.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-20 02:00 |  | 23 05 02-32.1 Space Needle SM Shops_ME_POP.pdf
23 05 02-032-02 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-032-02 550 Space Needle Sheet Metal Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-05 | 2021-02-02 | 12 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-02-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10898 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-05 | Submittal Number: 23 05 02-32.2 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: 550 SPACE NEEDLE SHEET METAL SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 14152 | Forwarded | For Review | 2021-01-22 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-29 | Submittal Number: 23 05 02-32.2 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: 550 SPACE NEEDLE SHEET METAL SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11125 | Review Response | Approved | 2021-01-26 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.01.26 | Info Exchange
| 14436 | Responded and Closed | Approved | 2021-02-02 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.01.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-22 |  | 23 05 02-32.2 550 SM Shop Dwgs - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-22 |  | 23 05 02-32.2 550 SM Shop Dwgs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-22 |  | 23 05 02-32.2 550 SM Shop Dwgs - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-02 |  | 23 05 02-32.2 550 SM Shop Dwgs_ME_POP.pdf
23 05 02-033-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-033-00 550 Space Needle Mech Piping Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-05 | 2021-02-02 | 12 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-02-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10899 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-02-05 | Submittal Number: 23 05 02-33.0 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: 550 SPACE NEEDLE MECH PIPING SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 14153 | Forwarded | For Review | 2021-01-22 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-29 | Submittal Number: 23 05 02-33.0 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: 550 SPACE NEEDLE MECH PIPING SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11122 | Review Response | Approved as Noted | 2021-01-26 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.01.26 | Info Exchange
| 14432 | Responded and Closed | Approved as Noted | 2021-02-02 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.01.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-22 |  | 23 05 02-33.0 550 MP Shop Drwgs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-22 |  | 23 05 02-33.0 550 MP Shop Drwgs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-22 |  | 23 05 02-33.0 550 MP Shop Drwgs - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-02 |  | 23 05 02-33.0 550 MP Shop Drwgs_ME_POP.pdf
23 05 02-034-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-034-00 700 Catwalk Sheet Metal Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-05 | 2021-02-02 | 12 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-02-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10905 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-02-05 | Submittal Number: 23 05 02-34.0 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: 700 CATWALK SHEET METAL SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 14159 | Forwarded | For Review | 2021-01-22 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-29 | Submittal Number: 23 05 02-34.0 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: 700 CATWALK SHEET METAL SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11120 | Review Response | Approved | 2021-01-27 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.01.27 | Info Exchange
| 14431 | Responded and Closed | Approved | 2021-02-02 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.01.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-22 |  | 23 05 02-34.0 700 SM Catwalk Roof Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-22 |  | 23 05 02-34.0 700 SM Catwalk Roof Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-22 |  | 23 05 02-34.0 700 SM Catwalk Roof Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-02 |  | 23 05 02-34.0 700 SM Catwalk Roof Shop Drawings_ME_POP.pdf
23 05 02-038-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-038-00 Sheetmetal Riser Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-17 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-01 | 2020-07-06 | 20 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06460 | Received | For Review | 2020-06-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-01 | Submittal Number: 23 05 02-38.0 From: GRETCHEN TOSHACH Final Due Date: 07/10/20 Subject: SHEETMETAL RISER SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 08709 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-24 | Submittal Number: 23 05 02-38.0 From: GRETCHEN TOSHACH Final Due Date: 07/10/20 Subject: SHEETMETAL RISER SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06870 | Review Response | Revise and Resubmit | 2020-06-29 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.06.29 | Info Exchange
| 09104 | Responded and Closed | Revise and Resubmit | 2020-07-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 23 05 02-38.0 SheetMetal Risers Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 23 05 02-38.0 SheetMetal Risers Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-16 02:00 |  | 23 05 02-38.0 SheetMetal Risers Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-06 |  | 23 05 02-38.0 SheetMetal Risers Shop Drawings_ME_POP.pdf
23 05 02-038-01 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-038-01 Sheetmetal Riser Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-03 08:00 | 2020-12-01 | 15 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09474 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 23 05 02-38.1 From: GRETCHEN TOSHACH Final Due Date: 11/30/20 Subject: SHEETMETAL RISER SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 12492 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-24 | Submittal Number: 23 05 02-38.1 From: GRETCHEN TOSHACH Final Due Date: 11/30/20 Subject: SHEETMETAL RISER SHOP DRAWINGS Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09776 | Review Response | Approved | 2020-11-18 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.11.18 | Info Exchange
| 12858 | Responded and Closed | Approved | 2020-12-01 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.11.18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 23 05 02-38.1 - NW SM Risers - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 23 05 02-38.1 - NW SM Risers - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-15 02:00 |  | 23 05 02-38.1 - NW SM Risers - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-01 02:00 |  | 23 05 02-38.1 - NW SM Risers_ME_pop.pdf
23 05 02-039-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-039-00 South Parcel - Makeup Water for Cooling Tower | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-10 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-24 | 2020-07-20 | 11 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06895 | Received | For Review | 2020-07-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-24 | Submittal Number: 23 05 02-39.0 From: GRETCHEN TOSHACH Final Due Date: 07/24/20 Subject: SOUTH PARCEL - MAKEUP WATER FOR COOLING TOWER Description: MAKEUP WATER LINE FOR THE COOLING TOWER AT THE BRESSI GARAGE Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09236 | Forwarded | For Review | 2020-07-10 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-17 | Submittal Number: 23 05 02-39.0 From: GRETCHEN TOSHACH Final Due Date: 07/24/20 Subject: SOUTH PARCEL - MAKEUP WATER FOR COOLING TOWER Description: MAKEUP WATER LINE FOR THE COOLING TOWER AT THE BRESSI GARAGE Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07041 | Review Response | Approved | 2020-07-14 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| 09425 | Responded and Closed | Approved | 2020-07-20 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-09 |  | 23 05 02-39.0 - SP CT MU Water - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-09 |  | 23 05 02-39.0 - SP CT MU Water - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-09 |  | 23 05 02-39.0 - SP CT MU Water - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-20 |  | 23 05 02-39.0 - SP CT MU Water_ME_POP.pdf
23 05 02-040-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-040-00 Sheet Metal Deferred Scope Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-17 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-31 | 2020-09-01 | 16 |  | Record Copies; Transfers; Submittals | 23 05 02-040-00-01 - 23 05 02-040-00 Sheet Metal Deferred Scope Shop Drawings | 12 |  | 2020-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07582 | Received | For Review | 2020-08-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-08-31 | Submittal Number: 23 05 02-40.0 From: GRETCHEN TOSHACH Final Due Date: 08/28/20 Subject: SHEET METAL DEFERRED SCOPE SHOP DRAWINGS Description: SHEET METAL DEFERRED SCOPE SHOP DRAWINGS CCDS 52/54/58 Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10090 | Forwarded | For Review | 2020-08-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-24 | Submittal Number: 23 05 02-40.0 From: GRETCHEN TOSHACH Final Due Date: 08/28/20 Subject: SHEET METAL DEFERRED SCOPE SHOP DRAWINGS Description: SHEET METAL DEFERRED SCOPE SHOP DRAWINGS CCDS 52/54/58 Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07884 | Review Response | Revise and Resubmit | 2020-08-28 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.08.28 | Info Exchange
| 10486 | Responded and Closed | Revise and Resubmit | 2020-09-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.08.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-17 |  | 23 05 02-40.0 HVAC Deferred Scope - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-17 |  | 23 05 02-40.0 HVAC Deferred Scope - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-08-17 |  | 23 05 02-40.0 HVAC Deferred Scope - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-01 |  | 23 05 02-40.0 HVAC Deferred Scope_ME_POP.pdf
23 05 02-040-00-01 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-040-00 Sheet Metal Deferred Scope Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 23 05 02-040-00 - 23 05 02-040-00 Sheet Metal Deferred Scope Shop Drawings | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-01 |  | 23 05 02-40.0 HVAC Deferred Scope_ME_POP.pdf
23 05 02-041-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-041-00 Mech Piping Deferred Scope Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-17 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-31 | 2020-09-01 | 16 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07576 | Received | For Review | 2020-08-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-08-31 | Submittal Number: 23 05 02-41.0 From: GRETCHEN TOSHACH Final Due Date: 08/28/20 Subject: MECH PIPING DEFERRED SCOPE SHOP DRAWINGS Description: MECH PIPING DEFERRED SCOPE SHOP DRAWINGS CCDS 52/54/58 Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10082 | Forwarded | For Review | 2020-08-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-24 | Submittal Number: 23 05 02-41.0 From: GRETCHEN TOSHACH Final Due Date: 08/28/20 Subject: MECH PIPING DEFERRED SCOPE SHOP DRAWINGS Description: MECH PIPING DEFERRED SCOPE SHOP DRAWINGS CCDS 52/54/58 Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07883 | Review Response | Approved as Noted | 2020-08-26 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.08.26 | Info Exchange
| 10485 | Responded and Closed | Approved as Noted | 2020-09-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.08.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-17 |  | 2020.08.17 - MP Deferred Scope Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-17 |  | 2020.08.17 - MP Deferred Scope Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-08-17 |  | 2020.08.17 - MP Deferred Scope Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-01 |  | 2020.08.17 - MP Deferred Scope Shop Drawings_ME_POP.pdf
23 05 02-050-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-050-00 SM Shop Drawing Update | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-05 | 2021-02-02 | 12 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-02-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10906 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-02-05 | Submittal Number: 23 05 02-50.0 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: SM SHOP DRAWING UPDATE Description: SHOP DRAWING UPDATE Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 14160 | Forwarded | For Review | 2021-01-22 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-29 | Submittal Number: 23 05 02-50.0 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: SM SHOP DRAWING UPDATE Description: SHOP DRAWING UPDATE Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11116 | Review Response | No Action Taken or Required | 2021-01-27 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | Reviewed for record only. Nick Theimer ME Engineers 2021.01.27 | Info Exchange
| 14427 | Responded and Closed | No Action Taken or Required | 2021-02-02 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for record only. Nick Theimer ME Engineers 2021.01.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-22 |  | 23 05 02-50 SM Shop Drawing Update for Record - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-22 |  | 23 05 02-50 SM Shop Drawing Update for Record - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-22 |  | 23 05 02-50 SM Shop Drawing Update for Record - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-02 |  | 23 05 02-50 SM Shop Drawing Update for Record_ME_POP.pdf
23 05 02-051-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-051-00 MP Shop Drawing Update | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-05 | 2021-02-01 | 11 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10907 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-05 | Submittal Number: 23 05 02-51.0 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: MP SHOP DRAWING UPDATE Description: MP SHOP DRAWING UPDATE Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 14161 | Forwarded | For Review | 2021-01-22 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-29 | Submittal Number: 23 05 02-51.0 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: MP SHOP DRAWING UPDATE Description: MP SHOP DRAWING UPDATE Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11085 | Review Response | No Action Taken or Required | 2021-01-27 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | Reviewed for record only. Nick Theimer ME Engineers 2021.01.27 | Info Exchange
| 14383 | Responded and Closed | No Action Taken or Required | 2021-02-01 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for record only. Nick Theimer ME Engineers 2021.01.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-22 |  | 23 05 02-51.0 MP Shop Drawing Update for Record - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-22 |  | 23 05 02-51.0 MP Shop Drawing Update for Record - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-22 |  | 23 05 02-51.0 MP Shop Drawing Update for Record - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-01 |  | 23 05 02-51.0 MP Shop Drawing Update for Record_ME_POP.pdf
23 05 02-052-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-052-00 June 2021 Mechanical Piping Shop Drawing Updates-For Record | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-18 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-02 | 2021-06-28 | 11 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-06-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13577 | Received | For Review | 2021-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-07-02 | Submittal Number: 23 05 02-52.0 From: JACK JOHNSON Final Due Date: 07/09/21 Subject: JUNE 2021 MECHANICAL PIPING SHOP DRAWING UPDATES-FOR RECORD Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 17578 | Forwarded | For Review | 2021-06-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-25 | Submittal Number: 23 05 02-52.0 From: JACK JOHNSON Final Due Date: 07/09/21 Subject: JUNE 2021 MECHANICAL PIPING SHOP DRAWING UPDATES-FOR RECORD Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 13692 | Review Response | No Action Taken or Required | 2021-06-24 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | Reviewed for record only. Nick Theimer ME Engineers 2021.06.24 | Info Exchange
| 17729 | Responded and Closed | No Action Taken or Required | 2021-06-28 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for record only. Nick Theimer ME Engineers 2021.06.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-18 |  | 23.0502-SDF-52 June 2021 Record Update Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-18 |  | 23.0502-SDF-52 June 2021 Record Update Submittal.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-06-17 02:00 |  | 23.0502-SDF-52 June 2021 Record Update Submittal.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-28 02:00 |  | 23.0502-SDF-52 June 2021 Record Update Submittal_ME_POP.pdf
23 05 02-053-00 | 23 05 02 - BASIC MECHANICAL REQUIREMENTS | 23 05 02-053-00 June 2021 Sheet Metal Shop Drawing Updates-For Record | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-18 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-02 | 2021-06-28 | 11 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-06-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13578 | Received | For Review | 2021-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-07-02 | Submittal Number: 23 05 02-53.0 From: JACK JOHNSON Final Due Date: 07/09/21 Subject: JUNE 2021 SHEET METAL SHOP DRAWING UPDATES-FOR RECORD Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 17579 | Forwarded | For Review | 2021-06-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-25 | Submittal Number: 23 05 02-53.0 From: JACK JOHNSON Final Due Date: 07/09/21 Subject: JUNE 2021 SHEET METAL SHOP DRAWING UPDATES-FOR RECORD Description: Spec Section: 23 05 02 - BASIC MECHANICAL REQUIREMENTS Status: OPEN | Info Exchange
| 13693 | Review Response | No Action Taken or Required | 2021-06-24 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | Reviewed for record only. Nick Theimer ME Engineers 2021.06.24 | Info Exchange
| 17730 | Responded and Closed | No Action Taken or Required | 2021-06-28 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for record only. Nick Theimer ME Engineers 2021.06.24 | Info Exchange
| 18030 | Sent | For Information Only | 2021-07-14 | Populous SCA_CCA | Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Responded and Closed (No Action Taken or Required) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Reviewed for record only. Nick Theimer ME Engineers 2021.06.24 | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-18 |  | 23.0502-SDH-53 June 2021 Record Updates Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-18 |  | 23.0502-SDH-53 June 2021 Record Updates Submittal.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-06-17 02:00 |  | 23.0502-SDH-53 June 2021 Record Updates Submittal.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-17 02:00 |  | 23.0502-SDH-53 June 2021 Record Updates Submittal.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-07-14 02:00 |  | Pages from 23.0502-SDH-53 June 2021 Record Updates Submittal_ME_POP.pdf
23 05 03-001-00 | 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS | 23 05 03-001-00 BASIC MECHANICAL MATERIALS AND METHODS - Manufacturers Instructions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-29 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Rick Lewis (Studio 08 Consultants), Linda Scott (Studio 08 Consultants), Tom Welsh (Studio 08 Consultants) |  |  |  | 2019-08-12 | 2019-08-12 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-08-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01896 | Received | For Review | 2019-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-12 | Submittal Number: 23 05 03-1.0 From: PATRICK KLEIN Final Due Date: 08/12/19 Subject: BASIC MECHANICAL MATERIALS AND METHODS - MANUFACTURERS INSTRUCTIONS Description: MANUFACTURERS DATA - SUBMIT MANUFACTURERS DATA FOR : - 1. ACCESS PANELS. 2. FIRE STOPPING MATERIALS. A. APPLICATION DATA - SUBMIT APPLICATION DATA FOR FIRESTOPPING MATERIALS SHOWING UL REQUIRED INSTALLATION DETAILS FOR EVERY COMBINATION OF PIPE MATERIAL, PENETRATED STRUCTURE, OPENING SIZE AND REQUIRED FIRE RATING WITHIN THE SCOPE OF THIS PROJECT. APPLICATION DATA DRAWINGS SHALL INCLUDE UL SYSTEM NUMBER. 3. HEAT TRACE. A. SUBMIT SHOP DRAWINGS FOR REVIEW PRIOR TO INSTALLATION. SHOP DRAWINGS SHALL SHOW THE OVERALL SYSTEM, COMPONENT PRODUCT DATA, EACH CONTROL LOCATION, CABLE LENGTHS, ELECTRICAL CONNECTION REQUIREMENTS, AND ELECTRICAL FEED POINTS. PROVIDEA SUMMARY SHEET OF THE ENTIRE SYSTEM WITH CAPACITY DATA FOR EACH CABLE LENGTH. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 03037 | Forwarded | For Review | 2019-07-29 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-05 | Submittal Number: 23 05 03-1.0 From: PATRICK KLEIN Final Due Date: 08/12/19 Subject: BASIC MECHANICAL MATERIALS AND METHODS - MANUFACTURERS INSTRUCTIONS Description: MANUFACTURERS DATA - SUBMIT MANUFACTURERS DATA FOR : - 1. ACCESS PANELS. 2. FIRE STOPPING MATERIALS. A. APPLICATION DATA - SUBMIT APPLICATION DATA FOR FIRESTOPPING MATERIALS SHOWING UL REQUIRED INSTALLATION DETAILS FOR EVERY COMBINATION OF PIPE MATERIAL, PENETRATED STRUCTURE, OPENING SIZE AND REQUIRED FIRE RATING WITHIN THE SCOPE OF THIS PROJECT. APPLICATION DATA DRAWINGS SHALL INCLUDE UL SYSTEM NUMBER. 3. HEAT TRACE. A. SUBMIT SHOP DRAWINGS FOR REVIEW PRIOR TO INSTALLATION. SHOP DRAWINGS SHALL SHOW THE OVERALL SYSTEM, COMPONENT PRODUCT DATA, EACH CONTROL LOCATION, CABLE LENGTHS, ELECTRICAL CONNECTION REQUIREMENTS, AND ELECTRICAL FEED POINTS. PROVIDEA SUMMARY SHEET OF THE ENTIRE SYSTEM WITH CAPACITY DATA FOR EACH CABLE LENGTH. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 01959 | Review Response | Revise and Resubmit | 2019-08-01 | Nick Theimer (ME Engineers) | Populous SCA_CCA; Shaina Burris (Populous) |  | Please see attached for ME Review of 23 05 03-001-00. Populous to review access doors prior to returning to contractor. Nick Theimer ME Engineers 2019.08.01 | Info Exchange
| 03104 | Forwarded | For Review | 2019-08-01 | Shaina Burris (Populous) | Rick Lewis (Studio 08 Consultants); Linda Scott (Studio 08 Consultants); Tom Welsh (Studio 08 Consultants) | 2019-08-08 | Submittal Number: 23 05 03-1.0 From: PATRICK KLEIN Final Due Date: 08/12/19 Subject: BASIC MECHANICAL MATERIALS AND METHODS - MANUFACTURERS INSTRUCTIONS Description: MANUFACTURERS DATA - SUBMIT MANUFACTURERS DATA FOR : - 1. ACCESS PANELS. 2. FIRE STOPPING MATERIALS. A. APPLICATION DATA - SUBMIT APPLICATION DATA FOR FIRESTOPPING MATERIALS SHOWING UL REQUIRED INSTALLATION DETAILS FOR EVERY COMBINATION OF PIPE MATERIAL, PENETRATED STRUCTURE, OPENING SIZE AND REQUIRED FIRE RATING WITHIN THE SCOPE OF THIS PROJECT. APPLICATION DATA DRAWINGS SHALL INCLUDE UL SYSTEM NUMBER. 3. HEAT TRACE. A. SUBMIT SHOP DRAWINGS FOR REVIEW PRIOR TO INSTALLATION. SHOP DRAWINGS SHALL SHOW THE OVERALL SYSTEM, COMPONENT PRODUCT DATA, EACH CONTROL LOCATION, CABLE LENGTHS, ELECTRICAL CONNECTION REQUIREMENTS, AND ELECTRICAL FEED POINTS. PROVIDEA SUMMARY SHEET OF THE ENTIRE SYSTEM WITH CAPACITY DATA FOR EACH CABLE LENGTH. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 02039 | Review Response | Approved as Noted | 2019-08-12 | Josh Dobken (Populous) | Josh Dobken (Populous) |  | Approved as noted. Please provide stainless steel access doors with no. 4 finish in wet areas. -jhd | Info Exchange
| 03206 | Responded and Closed | Approved as Noted | 2019-08-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: Please see attached for ME Review of 23 05 03-001-00. Populous to review access doors prior to returning to contractor. Nick Theimer ME Engineers 2019.08.01 Response (Approved as Noted) from: Josh Dobken (Populous) Remarks: Approved as noted. Please provide stainless steel access doors with no. 4 finish in wet areas. -jhd | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-29 |  | 23 05 03-1.0 Manufacturer's Instructions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-29 |  | 23 05 03-1.0 Manufacturer's Instructions-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-29 |  | 23 05 03-1.0 Manufacturer's Instructions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-29 |  | 23 05 03-1.0 Manufacturer's Instructions-MAM.pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2019-08-12 02:00 |  | 23 05 03-1.0 Manufacturer's Instructions_ME_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-12 02:00 |  | 23 05 03-1.0 Manufacturer's Instructions_ME_POP.pdf
23 05 03-001-01 | 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS | 23 05 03-001-01 BASIC MECHANICAL MATERIALS AND METHODS - Manufacturers Instructions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-22 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-08 07:00 | 2020-06-04 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05990 | Received | For Review | 2020-05-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-08 07:00 | Submittal Number: 23 05 03-1.1 From: GRETCHEN TOSHACH Final Due Date: 08/12/19 Subject: BASIC MECHANICAL MATERIALS AND METHODS - MANUFACTURERS INSTRUCTIONS Description: MANUFACTURERS DATA - SUBMIT MANUFACTURERS DATA FOR : - 1. ACCESS PANELS. 2. FIRE STOPPING MATERIALS. A. APPLICATION DATA - SUBMIT APPLICATION DATA FOR FIRESTOPPING MATERIALS SHOWING UL REQUIRED INSTALLATION DETAILS FOR EVERY COMBINATION OF PIPE MATERIAL, PENETRATED STRUCTURE, OPENING SIZE AND REQUIRED FIRE RATING WITHIN THE SCOPE OF THIS PROJECT. APPLICATION DATA DRAWINGS SHALL INCLUDE UL SYSTEM NUMBER. 3. HEAT TRACE. A. SUBMIT SHOP DRAWINGS FOR REVIEW PRIOR TO INSTALLATION. SHOP DRAWINGS SHALL SHOW THE OVERALL SYSTEM, COMPONENT PRODUCT DATA, EACH CONTROL LOCATION, CABLE LENGTHS, ELECTRICAL CONNECTION REQUIREMENTS, AND ELECTRICAL FEED POINTS. PROVIDEA SUMMARY SHEET OF THE ENTIRE SYSTEM WITH CAPACITY DATA FOR EACH CABLE LENGTH. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 08127 | Forwarded | For Review | 2020-05-22 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-29 | Submittal Number: 23 05 03-1.1 From: GRETCHEN TOSHACH Final Due Date: 08/12/19 Subject: BASIC MECHANICAL MATERIALS AND METHODS - MANUFACTURERS INSTRUCTIONS Description: MANUFACTURERS DATA - SUBMIT MANUFACTURERS DATA FOR : - 1. ACCESS PANELS. 2. FIRE STOPPING MATERIALS. A. APPLICATION DATA - SUBMIT APPLICATION DATA FOR FIRESTOPPING MATERIALS SHOWING UL REQUIRED INSTALLATION DETAILS FOR EVERY COMBINATION OF PIPE MATERIAL, PENETRATED STRUCTURE, OPENING SIZE AND REQUIRED FIRE RATING WITHIN THE SCOPE OF THIS PROJECT. APPLICATION DATA DRAWINGS SHALL INCLUDE UL SYSTEM NUMBER. 3. HEAT TRACE. A. SUBMIT SHOP DRAWINGS FOR REVIEW PRIOR TO INSTALLATION. SHOP DRAWINGS SHALL SHOW THE OVERALL SYSTEM, COMPONENT PRODUCT DATA, EACH CONTROL LOCATION, CABLE LENGTHS, ELECTRICAL CONNECTION REQUIREMENTS, AND ELECTRICAL FEED POINTS. PROVIDEA SUMMARY SHEET OF THE ENTIRE SYSTEM WITH CAPACITY DATA FOR EACH CABLE LENGTH. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 06209 | Review Response | Approved as Noted | 2020-06-03 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Submit items as noted in separate submittal package. Nick Theimer / Mark Lievens ME Engineers 2020.06.03 | Info Exchange
| 08389 | Responded and Closed | Approved as Noted | 2020-06-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Submit items as noted in separate submittal package. Nick Theimer / Mark Lievens ME Engineers 2020.06.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-21 |  | 23 05 03-1.1 Heat Trace MP-PL - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-21 |  | 23 05 03-1.1 Heat Trace MP-PL - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-20 02:00 |  | 23 05 03-1.1 Heat Trace MP-PL - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-04 02:00 |  | 23 05 03-1.1 Heat Trace MP-PL_ME_POP.pdf
23 05 03-001-02 | 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS | 23 05 03-001-02 BASIC MECHANICAL MATERIALS AND METHODS - Manufacturers Instructions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-21 | 2020-07-20 | 14 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06808 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 23 05 03-1.2 From: GRETCHEN TOSHACH Final Due Date: 07/20/20 Subject: BASIC MECHANICAL MATERIALS AND METHODS - MANUFACTURERS INSTRUCTIONS Description: MANUFACTURERS DATA - SUBMIT MANUFACTURERS DATA FOR : - 1. ACCESS PANELS. 2. FIRE STOPPING MATERIALS. A. APPLICATION DATA - SUBMIT APPLICATION DATA FOR FIRESTOPPING MATERIALS SHOWING UL REQUIRED INSTALLATION DETAILS FOR EVERY COMBINATION OF PIPE MATERIAL, PENETRATED STRUCTURE, OPENING SIZE AND REQUIRED FIRE RATING WITHIN THE SCOPE OF THIS PROJECT. APPLICATION DATA DRAWINGS SHALL INCLUDE UL SYSTEM NUMBER. 3. HEAT TRACE. A. SUBMIT SHOP DRAWINGS FOR REVIEW PRIOR TO INSTALLATION. SHOP DRAWINGS SHALL SHOW THE OVERALL SYSTEM, COMPONENT PRODUCT DATA, EACH CONTROL LOCATION, CABLE LENGTHS, ELECTRICAL CONNECTION REQUIREMENTS, AND ELECTRICAL FEED POINTS. PROVIDEA SUMMARY SHEET OF THE ENTIRE SYSTEM WITH CAPACITY DATA FOR EACH CABLE LENGTH. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 09142 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 23 05 03-1.2 From: GRETCHEN TOSHACH Final Due Date: 07/20/20 Subject: BASIC MECHANICAL MATERIALS AND METHODS - MANUFACTURERS INSTRUCTIONS Description: MANUFACTURERS DATA - SUBMIT MANUFACTURERS DATA FOR : - 1. ACCESS PANELS. 2. FIRE STOPPING MATERIALS. A. APPLICATION DATA - SUBMIT APPLICATION DATA FOR FIRESTOPPING MATERIALS SHOWING UL REQUIRED INSTALLATION DETAILS FOR EVERY COMBINATION OF PIPE MATERIAL, PENETRATED STRUCTURE, OPENING SIZE AND REQUIRED FIRE RATING WITHIN THE SCOPE OF THIS PROJECT. APPLICATION DATA DRAWINGS SHALL INCLUDE UL SYSTEM NUMBER. 3. HEAT TRACE. A. SUBMIT SHOP DRAWINGS FOR REVIEW PRIOR TO INSTALLATION. SHOP DRAWINGS SHALL SHOW THE OVERALL SYSTEM, COMPONENT PRODUCT DATA, EACH CONTROL LOCATION, CABLE LENGTHS, ELECTRICAL CONNECTION REQUIREMENTS, AND ELECTRICAL FEED POINTS. PROVIDEA SUMMARY SHEET OF THE ENTIRE SYSTEM WITH CAPACITY DATA FOR EACH CABLE LENGTH. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 07042 | Review Response | Approved as Noted | 2020-07-15 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.07.15 | Info Exchange
| 09426 | Responded and Closed | Approved as Noted | 2020-07-20 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 23 0503.1R1 Heat Trace - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 23 0503.1R1 Heat Trace - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-06 |  | 23 0503.1R1 Heat Trace - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-20 |  | 23 05 03-1.1R1 Heat Trace MP-PL_ME_POP.pdf
23 05 03-003-00 | 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS | 23 05 03-003-00 Duct Caulking/Adhesive | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-18 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-02 | 2020-06-24 | 7 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06470 | Received | For Review | 2020-06-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-02 | Submittal Number: 23 05 03-3.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: DUCT CAULKING/ADHESIVE Description: Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 08720 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-24 | Submittal Number: 23 05 03-3.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: DUCT CAULKING/ADHESIVE Description: Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 06710 | Review Response | Approved | 2020-06-19 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.06.19 | Info Exchange
| 08871 | Responded and Closed | Approved | 2020-06-24 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.06.19 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 23 05 03-3.0 Duct Sealing Material - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 23 05 03-3.0 Duct Sealing Material - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-16 02:00 |  | 23 05 03-3.0 Duct Sealing Material - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-24 |  | 23 05 03-3.0 Duct Sealing Material_ME_POP.pdf
23 05 03-004-00 | 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS | 23 05 03-004-00 Duct Sealant | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-19 | 2020-10-05 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08551 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 23 05 03-4.0 From: GRETCHEN TOSHACH Final Due Date: 11/12/20 Subject: DUCT SEALANT Description: Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 11314 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-12 | Submittal Number: 23 05 03-4.0 From: GRETCHEN TOSHACH Final Due Date: 11/12/20 Subject: DUCT SEALANT Description: Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 08579 | Review Response | Approved | 2020-10-05 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.10.05 | Info Exchange
| 11340 | Responded and Closed | Approved | 2020-10-05 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 23 05 03-4.0 Duct Sealant - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 23 05 03-4.0 Duct Sealant - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-10-05 |  | 23 05 03-4.0 Duct Sealant - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-05 |  | 23 05 03-4.0 Duct Sealant_ME_POP.pdf
23 05 03-005-00 | 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS | 23 05 03-005-00 DAHU 2F.01 Trolley Design | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-30 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-14 | 2020-12-08 | 9 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-12-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09754 | Received | For Review | 2020-11-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (M.A. Mortenson Company) | 2020-12-14 | Submittal Number: 23 05 03-5.0 From: GRETCHEN TOSHACH Final Due Date: 12/11/20 Subject: DAHU 2F.01 TROLLEY DESIGN Description: SUBMITTING FOR STRUCTURAL REVIEW AND CONFIRMATION LOADS AND PLAN IS ACCEPTABLE. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 12821 | Forwarded | For Review | 2020-11-30 | Gretchen Toshach (M.A. Mortenson Company) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-07 | Submittal Number: 23 05 03-5.0 From: GRETCHEN TOSHACH Final Due Date: 12/11/20 Subject: DAHU 2F.01 TROLLEY DESIGN Description: SUBMITTING FOR STRUCTURAL REVIEW AND CONFIRMATION LOADS AND PLAN IS ACCEPTABLE. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 12846 | Forwarded | For Review | 2020-11-30 | Gretchen Toshach (M.A. Mortenson Company) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-12-07 | Submittal Number: 23 05 03-5.0 From: GRETCHEN TOSHACH Final Due Date: 12/11/20 Subject: DAHU 2F.01 TROLLEY DESIGN Description: SUBMITTING FOR STRUCTURAL REVIEW AND CONFIRMATION LOADS AND PLAN IS ACCEPTABLE. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 10002 | Review Response | Approved | 2020-12-01 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.12.01 | Info Exchange
| 10066 | Review Response | Revise and Resubmit | 2020-12-07 | Matt Ross (Thornton Tomasetti) | Gretchen Toshach (M.A. Mortenson Company) |  | Proposed system is not structurally acceptable. Contractor's engineer to provide engineered supplemental framing to resolve trolley system loads imposed directly to steel at Main Concourse. Calcs and details to be submitted to EOR for review and approval. | Info Exchange
| 13090 | Responded and Closed | Revise and Resubmit | 2020-12-08 | Gretchen Toshach (M.A. Mortenson Company) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Proposed system is not structurally acceptable. Contractor's engineer to provide engineered supplemental framing to resolve trolley system loads imposed directly to steel at Main Concourse. Calcs and details to be submitted to EOR for review and approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-25 |  | 23 05 03-5.0 - Detail for Steel Beam Trolley System - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2020-11-25 |  | 23 05 03-5.0 - Detail for Steel Beam Trolley System - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2020-11-25 |  | 23 05 03-5.0 - Detail for Steel Beam Trolley System - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-25 |  | 23 05 03-5.0 - Detail for Steel Beam Trolley System - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-25 |  | 23 05 03-5.0 - Detail for Steel Beam Trolley System - MAM.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2020-12-08 |  | 23 05 03-5.0 - Detail for Steel Beam Trolley System - TT_ME_POP.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2020-12-07 |  | CPA - Structural Calcualtions and Detail for Steel Beam Trolley System - ENW 11-13-20_TT.pdf
23 05 03-005-01 | 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS | 23 05 03-005-01 DAHU 2F.01 Trolley Design | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-18 | 2021-01-12 | 9 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-01-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10380 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (M.A. Mortenson Company) | 2021-01-18 | Submittal Number: 23 05 03-5.1 From: GRETCHEN TOSHACH Final Due Date: 01/13/21 Subject: DAHU 2F.01 TROLLEY DESIGN Description: SUBMITTING FOR STRUCTURAL REVIEW AND CONFIRMATION LOADS AND PLAN IS ACCEPTABLE. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 13563 | Forwarded | For Review | 2021-01-04 | Gretchen Toshach (M.A. Mortenson Company) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-11 | Submittal Number: 23 05 03-5.1 From: GRETCHEN TOSHACH Final Due Date: 01/13/21 Subject: DAHU 2F.01 TROLLEY DESIGN Description: SUBMITTING FOR STRUCTURAL REVIEW AND CONFIRMATION LOADS AND PLAN IS ACCEPTABLE. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 10656 | Review Response | Approved | 2021-01-04 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.01.04 | Info Exchange
| 13642 | Forwarded | For Review | 2021-01-05 | Gretchen Toshach (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2021-01-12 | Submittal Number: 23 05 03-5.1 From: GRETCHEN TOSHACH Final Due Date: 01/13/21 Subject: DAHU 2F.01 TROLLEY DESIGN Description: SUBMITTING FOR STRUCTURAL REVIEW AND CONFIRMATION LOADS AND PLAN IS ACCEPTABLE. Spec Section: 23 05 03 - BASIC MECHANICAL MATERIALS AND METHODS Status: OPEN | Info Exchange
| 10657 | Review Response | Approved as Noted | 2021-01-06 | Matt Ross (Thornton Tomasetti) | Gretchen Toshach (Mortenson Construction) |  |  | Info Exchange
| 13872 | Responded and Closed | Approved as Noted | 2021-01-12 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.01.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-31 |  | 23 05 03-5.1 DAHU 2F.01Trolley System Install - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2020-12-31 |  | 23 05 03-5.1 DAHU 2F.01Trolley System Install - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-12-30 02:00 |  | 23 05 03-5.1 DAHU 2F.01Trolley System Install - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2020-12-30 02:00 |  | 23 05 03-5.1 DAHU 2F.01Trolley System Install - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-30 02:00 |  | 23 05 03-5.1 DAHU 2F.01Trolley System Install - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-12 02:00 |  | 23 05 03-5.1 DAHU 2F.01Trolley System Install_ME_TT_pop.pdf
23 05 21-001-00 | 23 05 21 - PIPE AND PIPE FITTINGS | 23 05 21-001-00 Pipe Fittings Product Data | Closed | Mechanical | Patrick Klein (Mortenson Construction) | 2019-06-24 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-07-08 | 2019-06-25 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01608 | Received | For Review | 2019-06-24 | Patrick Klein (Mortenson Construction) | Populous SCA_CCA | 2019-07-08 |  | Email
| 02656 | Forwarded | For Review | 2019-06-24 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-07-01 |  | Info Exchange
| 01622 | Review Response | Rejected | 2019-06-25 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | Please see attached for review of Submittal 23 05 21-001-00. Note this package is rejected, but that a resubmittal is not required for the approved or approved as noted products. | Info Exchange
| 02680 | Responded and Closed | Approved as Noted | 2019-06-25 | Populous SCA_CCA | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction) |  | Response (Rejected) from: Nick Theimer (ME Engineers) Remarks: Please see attached for review of Submittal 23 05 21-001-00. Note this package is rejected, but that a resubmittal is not required for the approved or approved as noted products. POP - package is approved as noted, refer to M-E comments for rejected portion. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Patrick Klein (Mortenson Construction) | 1 | 2019-06-24 |  | 23 05 21-001-00 Pipe Fittings Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-24 |  | 23 05 21-001-00 Pipe Fittings Product Data.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-06-25 |  | 23 05 21-001-00 Pipe Fittings Product Data_ME.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-06-25 |  | 23 05 21-001-00 Pipe Fittings Product Data_ME_POP.pdf
23 05 21-003-00 | 23 05 21 - PIPE AND PIPE FITTINGS | 23 05 21-003-00 PIPE AND PIPE FITTINGS - Certificates | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-09 08:00 | 2019-12-09 | 19 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-12-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03316 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-09 08:00 | Submittal Number: 23 05 21-3.0 From: PATRICK KLEIN Final Due Date: 12/06/19 Subject: PIPE AND PIPE FITTINGS - CERTIFICATES Description: WELDER CERTIFICATES: 1. SUBMIT ONE COPY OF CERTIFICATE TO ARCHTITECT/ENGINEER. 2. MAINTAIN ONE COPY ON PROJECT SITE. Spec Section: 23 05 21 - PIPE AND PIPE FITTINGS Status: OPEN | Info Exchange
| 04770 | Forwarded | For Review | 2019-11-21 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-27 | Submittal Number: 23 05 21-3.0 From: PATRICK KLEIN Final Due Date: 12/06/19 Subject: PIPE AND PIPE FITTINGS - CERTIFICATES Description: WELDER CERTIFICATES: 1. SUBMIT ONE COPY OF CERTIFICATE TO ARCHTITECT/ENGINEER. 2. MAINTAIN ONE COPY ON PROJECT SITE. Spec Section: 23 05 21 - PIPE AND PIPE FITTINGS Status: OPEN | Info Exchange
| 03547 | Review Response | Approved | 2019-12-06 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| 05017 | Responded and Closed | Approved | 2019-12-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-21 |  | 23 05 21-3.0 Welding CertIficates -MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-21 |  | 23 05 21-3.0 Welding CertIficates -MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-12-09 02:00 |  | 23 05 21-3.0 Welding CertIficates_ME.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 23 05 21-3.0 Welding CertIficates_ME_POP.pdf
23 05 21-004-00 | 23 05 21 - PIPE AND PIPE FITTINGS | 23 05 21-004-00: Shop Welding Certificates | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-09 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-23 | 2019-12-10 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03554 | Received | For Review | 2019-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-23 | Submittal Number: 23 05 21-4.0 From: GRETCHEN TOSHACH Final Due Date: 01/16/20 Subject: SHOP WELDING CERTIFICATES Description: HERMANSON SHOP WELDER CERTIFICATES Spec Section: 23 05 21 - PIPE AND PIPE FITTINGS Status: OPEN | Info Exchange
| 05023 | Forwarded | For Review | 2019-12-09 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-16 | Submittal Number: 23 05 21-4.0 From: GRETCHEN TOSHACH Final Due Date: 01/16/20 Subject: SHOP WELDING CERTIFICATES Description: HERMANSON SHOP WELDER CERTIFICATES Spec Section: 23 05 21 - PIPE AND PIPE FITTINGS Status: OPEN | Info Exchange
| 03570 | Review Response | Approved | 2019-12-09 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.09 | Info Exchange
| 05047 | Responded and Closed | Approved | 2019-12-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.09 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-09 02:00 |  | 23 05 21-4.0 Shop Welding Certs - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 23 05 21-4.0 Shop Welding Certs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-12-09 02:00 |  | 23 05 21-4.0 Shop Welding Certs - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-10 02:00 |  | 23 05 21-4.0 Shop Welding Certs_ME_POP.pdf
23 05 22-001-00 | 23 05 22 - PIPING ACCESSORIES | 23 05 22-001-00 Manufacturer's Instructions- | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-10 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Josh Dobken (Populous) |  |  |  | 2019-07-24 | 2019-08-15 | 37 |  | Record Copies; Transfers; Submittals |  | 38 |  | 2019-08-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01717 | Received | For Review | 2019-07-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2019-07-24 |  | Email
| 02818 | Forwarded | For Review | 2019-07-09 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-07-16 |  | Info Exchange
| 01778 | Review Response | Revise and Resubmit | 2019-07-15 | Nick Theimer (ME Engineers) | Shaina Burris (Populous) |  | Please see attached for review of Submittal 23 05 22-001-00. Please note that not all items are required to be resubmitted, refer to disposition sheets for further details. | Info Exchange
| 02903 | Forwarded | For Review | 2019-07-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Josh Dobken (Populous) | 2019-07-22 |  | Info Exchange
| 02084 | Review Response | Approved as Noted/Resubmit | 2019-08-15 | Bryan Klote (Populous) | Shaina Burris (Populous) |  | This is an incomplete submittal - missing are: - [LEED] Laboratory tests reports for sealants - 07 84 13, 1.3B.2 - Product Schedules - 07 84 13, 1.3C - Qualification Data for installer 07 84 13, 1.4A - Product Test Reports 07 84 13, 1.4B Similar items missing from 07 84 43 | Info Exchange
| 03256 | Responded and Closed | Approved as Noted/Resubmit | 2019-08-15 | Shaina Burris (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | ME/Nick Theimer: Please see attached for review of Submittal 23 05 22-001-00. Please note that not all items are required to be resubmitted, refer to disposition sheets for further details. Pop/Bryan Klote: This is an incomplete submittal - missing are: - [LEED] Laboratory tests reports for sealants - 07 84 13, 1.3B.2 - Product Schedules - 07 84 13, 1.3C - Qualification Data for installer 07 84 13, 1.4A - Product Test Reports 07 84 13, 1.4B | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-09 |  | 23 05 22-001-00 Manufacturer's Instructions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-09 |  | 23 05 22-001-00 Manufacturer's Instructions-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-15 |  | 23 05 22-001-00 Manufacturer's Instructions-MAM_ME.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-09 |  | 23 05 22-001-00 Manufacturer's Instructions-MAM.pdf
| Review Response |  | Bryan Klote (Populous) | 1 | 2019-08-15 |  | 23 05 22-001-00 Manufacturer's Instructions-MAM_ME_POP.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2019-07-09 |  | 23 05 22-001-00 Manufacturer's Instructions-MAM.pdf
23 05 22-001-01 | 23 05 22 - PIPING ACCESSORIES | 23 05 22-001-01 PIPING ACCESSORIES - Manufacturers Instructions | Closed | Mechanical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-09 08:00 | 2019-12-13 | 23 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2019-12-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03295 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-09 08:00 | Submittal Number: 23 05 22-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/08/19 Subject: PIPING ACCESSORIES - MANUFACTURERS INSTRUCTIONS Description: PLEASE RESUBMIT ON THE FOLLOWING: FLEXIBLE PIPE CONNECTIONS - METRAFLEX DOUBLESPHERE IN LIEU OF LOCATIONS WHERE METRA-MINI WERE SUBMITTED STEEL PIPE SLEEVES IRON PIPE SLEEVES SHEET METAL PIPE SLEEVES LEED LAB TEST REPORTS FOR SEALANTS PRODUCT SCHEDULES SPECIFYING LOCATIONS OF FIRE STOPPING DETAILS/ASSEMBLIES QUALIFICATION DATA FOR INSTALLER OF FIRESTOPPING PRODUCT TEST REPORTS FOR FIRESTOPPING Spec Section: 23 05 22 - PIPING ACCESSORIES Status: OPEN | Info Exchange
| 04744 | Forwarded | For Review | 2019-11-20 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-27 | Submittal Number: 23 05 22-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/08/19 Subject: PIPING ACCESSORIES - MANUFACTURERS INSTRUCTIONS Description: PLEASE RESUBMIT ON THE FOLLOWING: FLEXIBLE PIPE CONNECTIONS - METRAFLEX DOUBLESPHERE IN LIEU OF LOCATIONS WHERE METRA-MINI WERE SUBMITTED STEEL PIPE SLEEVES IRON PIPE SLEEVES SHEET METAL PIPE SLEEVES LEED LAB TEST REPORTS FOR SEALANTS PRODUCT SCHEDULES SPECIFYING LOCATIONS OF FIRE STOPPING DETAILS/ASSEMBLIES QUALIFICATION DATA FOR INSTALLER OF FIRESTOPPING PRODUCT TEST REPORTS FOR FIRESTOPPING Spec Section: 23 05 22 - PIPING ACCESSORIES Status: OPEN | Info Exchange
| 03548 | Review Response | Approved as Noted | 2019-12-06 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| 05128 | Responded and Closed | Approved as Noted | 2019-12-13 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-20 |  | 23 05 22-1.1 Pipe-Pipe Fitting Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-20 |  | 23 05 22-1.1 Pipe-Pipe Fitting Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-19 02:00 |  | 23 05 22-1.1 Pipe-Pipe Fitting Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-13 02:00 |  | 23 05 22-1.1 Pipe-Pipe Fitting Product Data_ME_POP.pdf
23 05 22-001-02 | 23 05 22 - PIPING ACCESSORIES | 23 05 22-001-02 PIPING ACCESSORIES - Manufacturers Instructions | Closed | Mechanical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-27 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-10 | 2020-06-15 | 20 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06064 | Received | For Review | 2020-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-10 | Submittal Number: 23 05 22-1.2 From: GRETCHEN TOSHACH Final Due Date: 12/09/19 Subject: PIPING ACCESSORIES - MANUFACTURERS INSTRUCTIONS Description: PLEASE RESUBMIT ON THE FOLLOWING: PRODUCT SCHEDULES SPECIFYING LOCATIONS OF FIRE STOPPING DETAILS/ASSEMBLIES QUALIFICATION DATA FOR INSTALLER OF FIRESTOPPING PRODUCT TEST REPORTS FOR FIRESTOPPING Spec Section: 23 05 22 - PIPING ACCESSORIES Status: OPEN | Info Exchange
| 08217 | Forwarded | For Review | 2020-05-27 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-03 | Submittal Number: 23 05 22-1.2 From: GRETCHEN TOSHACH Final Due Date: 12/09/19 Subject: PIPING ACCESSORIES - MANUFACTURERS INSTRUCTIONS Description: PLEASE RESUBMIT ON THE FOLLOWING: PRODUCT SCHEDULES SPECIFYING LOCATIONS OF FIRE STOPPING DETAILS/ASSEMBLIES QUALIFICATION DATA FOR INSTALLER OF FIRESTOPPING PRODUCT TEST REPORTS FOR FIRESTOPPING Spec Section: 23 05 22 - PIPING ACCESSORIES Status: OPEN | Info Exchange
| 06397 | Review Response | Approved | 2020-06-03 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Architect to review for F and T ratings. Nick Theimer ME Engineers 2020.06.03 | Info Exchange
| 08707 | Responded and Closed | Approved as Noted | 2020-06-15 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Architect to review for F and T ratings. Nick Theimer ME Engineers 2020.06.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-27 |  | 23 05 22-1.2 Firestop_HILTI - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-27 |  | 23 05 22-1.2 Firestop_HILTI - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-26 02:00 |  | 23 05 22-1.2 Firestop_HILTI - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-15 02:00 |  | 23 05 22-1.2 Firestop_HILTI_ME_POP.pdf
23 05 22-001-03 | 23 05 22 - PIPING ACCESSORIES | 23 05 22-001-03 PIPING ACCESSORIES - Victaulic Style 077 Flexible Couplings - Manufacturers Instructions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-09 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-03-23 | 2021-03-09 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11875 | Received | For Review | 2021-03-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-03-23 | Submittal Number: 23 05 22-1.3 From: GRETCHEN TOSHACH Final Due Date: 03/22/21 Subject: PIPING ACCESSORIES - VICTAULIC STYLE 077 FLEXIBLE COUPLINGS - MANUFACTURERS INSTRUCTIONS Description: PLEASE RESUBMIT ON THE FOLLOWING: VICTAULIC STYLE 077 FLEXIBLE COUPLINGS. Spec Section: 23 05 22 - PIPING ACCESSORIES Status: OPEN | Info Exchange
| 15391 | Forwarded | For Review | 2021-03-09 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-16 | Submittal Number: 23 05 22-1.3 From: GRETCHEN TOSHACH Final Due Date: 03/22/21 Subject: PIPING ACCESSORIES - VICTAULIC STYLE 077 FLEXIBLE COUPLINGS - MANUFACTURERS INSTRUCTIONS Description: PLEASE RESUBMIT ON THE FOLLOWING: VICTAULIC STYLE 077 FLEXIBLE COUPLINGS. Spec Section: 23 05 22 - PIPING ACCESSORIES Status: OPEN | Info Exchange
| 11893 | Review Response | Approved | 2021-03-09 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.03.09 | Info Exchange
| 15412 | Responded and Closed | Approved | 2021-03-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.03.09 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-08 |  | 23 05 22-1.3 Victaulic 077 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-08 |  | 23 05 22-1.3 Victaulic 077 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-03-07 02:00 |  | 23 05 22-1.3 Victaulic 077 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-09 02:00 |  | 23 05 22-1.3 Victaulic 077_ME_POP.pdf
23 05 22-003-00 | 23 05 22 - PIPING ACCESSORIES | 23 05 22-003-00 Underground CDWS/R Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-27 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-11 | 2019-12-10 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03405 | Received | For Review | 2019-11-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-11 | Submittal Number: 23 05 22-3.0 From: GRETCHEN TOSHACH Final Due Date: 12/13/19 Subject: UNDERGROUND CDWS/R PRODUCT DATA Description: PRODUCT DATA FOR HVAC PIPING SLEEVES AND LINK SEALS THAT WILL BE USED FOR THE UNDERGROUND CONDENSER WATER SUPPLY AND RETURN Spec Section: 23 05 22 - PIPING ACCESSORIES Status: OPEN | Info Exchange
| 04872 | Forwarded | For Review | 2019-11-27 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-04 | Submittal Number: 23 05 22-3.0 From: GRETCHEN TOSHACH Final Due Date: 12/13/19 Subject: UNDERGROUND CDWS/R PRODUCT DATA Description: PRODUCT DATA FOR HVAC PIPING SLEEVES AND LINK SEALS THAT WILL BE USED FOR THE UNDERGROUND CONDENSER WATER SUPPLY AND RETURN Spec Section: 23 05 22 - PIPING ACCESSORIES Status: OPEN | Info Exchange
| 03569 | Review Response | Approved as Noted | 2019-12-09 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.09 | Info Exchange
| 05046 | Responded and Closed | Approved as Noted | 2019-12-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.09 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-27 |  | 23 05 22 -3.0 UG CDWS_R Sleeves Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-27 |  | 23 05 22 -3.0 UG CDWS_R Sleeves Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-26 02:00 |  | 23 05 22 -3.0 UG CDWS_R Sleeves Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-10 02:00 |  | 23 05 22 -3.0 UG CDWS_R Sleeves Product Data_ME_POP.pdf
23 05 23-001-00 | 23 05 23 - VALVES | 23 05 23-001-00 VALVES - Manufacturers Instructions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-09 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-07-23 | 2019-07-23 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-07-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01703 | Received | For Review | 2019-07-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-23 | Submittal Number: 23 05 23-1.0 From: PATRICK KLEIN Final Due Date: 07/22/19 Subject: VALVES - MANUFACTURERS INSTRUCTIONS Description: MANUFACTURERS DATA : SUBMIT MANUFACTURERS PRODUCT DATA INCLUDING: 1. DIMENSIONS 2. SIZES 3. END CONNECTIONS 4. WEIGHTS 5. INSTALLATION INSTRUCTIONS 6. INSTRUCTIONS ON REPACKING AND REPAIRING VALVES. 7. RANGE OF FLOW AND FULL OPEN (PERMANENT) PRESSURE LOSS FOR BALANCING VALVES AND PLUG VALVES. 8. DIFFERENTIAL PRESSURE TABLES FOR FLOW MEASUREMENT AT VENTURI TYPE BALANCING VALVES. Spec Section: 23 05 23 - VALVES Status: OPEN | Info Exchange
| 02798 | Forwarded | For Review | 2019-07-09 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-07-16 | Submittal Number: 23 05 23-1.0 From: PATRICK KLEIN Final Due Date: 07/22/19 Subject: VALVES - MANUFACTURERS INSTRUCTIONS Description: MANUFACTURERS DATA : SUBMIT MANUFACTURERS PRODUCT DATA INCLUDING: 1. DIMENSIONS 2. SIZES 3. END CONNECTIONS 4. WEIGHTS 5. INSTALLATION INSTRUCTIONS 6. INSTRUCTIONS ON REPACKING AND REPAIRING VALVES. 7. RANGE OF FLOW AND FULL OPEN (PERMANENT) PRESSURE LOSS FOR BALANCING VALVES AND PLUG VALVES. 8. DIFFERENTIAL PRESSURE TABLES FOR FLOW MEASUREMENT AT VENTURI TYPE BALANCING VALVES. Spec Section: 23 05 23 - VALVES Status: OPEN | Info Exchange
| 01850 | Review Response | Approved as Noted | 2019-07-22 | Nick Theimer (ME Engineers) | Shaina Burris (Populous) |  | Please see attached for review of Submittal 23 05 23-001. | Info Exchange
| 02978 | Responded and Closed | Approved as Noted | 2019-07-23 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: Please see attached for review of Submittal 23 05 23-001. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-08 |  | 23 05 23-1.0 Manufacturer's Instructions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-09 |  | 23 05 23-1.0 Manufacturer's Instructions-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-22 02:00 |  | 23 05 23-1.0 - Valves - Manufacturer's Instructions-MAM_ME.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-23 02:00 |  | 23 05 23-1.0 - Valves - Manufacturer's Instructions-MAM_ME_POP.pdf
23 05 23-003-00 | 23 05 23 - VALVES | 23 05 23-003-00 Hydronic Piping Valves | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-30 | 2020-03-30 | 15 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-03-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04865 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 23 05 23-3.0 From: GRETCHEN TOSHACH Final Due Date: 04/13/20 Subject: HYDRONIC PIPING VALVES Description: VALVES FOR HYDRONIC MECHANICAL PIPING Spec Section: 23 05 23 - VALVES Status: OPEN | Info Exchange
| 06645 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-23 | Submittal Number: 23 05 23-3.0 From: GRETCHEN TOSHACH Final Due Date: 04/13/20 Subject: HYDRONIC PIPING VALVES Description: VALVES FOR HYDRONIC MECHANICAL PIPING Spec Section: 23 05 23 - VALVES Status: OPEN | Info Exchange
| 05122 | Review Response | Approved as Noted | 2020-03-19 | Nick Theimer (ME Engineers) | Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.19 | Info Exchange
| 06957 | Responded and Closed | Approved as Noted | 2020-03-30 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.19 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 23 05 23-3.0 Hydronic Pipe Valves Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 23 05 23-3.0 Hydronic Pipe Valves Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-15 02:00 |  | 23 05 23-3.0 Hydronic Pipe Valves Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-30 02:00 |  | 23 05 23-3.0 Hydronic Pipe Valves Product Data_ME_POP.pdf
23 05 23-004-00 | 23 05 23 - VALVES | 23 05 23-004-00 DAHU Control Valves | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-21 | 2020-07-20 | 14 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06820 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 23 05 23-4.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: DAHU CONTROL VALVES Description: DAHU VALVES Spec Section: 23 05 23 - VALVES Status: OPEN | Info Exchange
| 09155 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 23 05 23-4.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: DAHU CONTROL VALVES Description: DAHU VALVES Spec Section: 23 05 23 - VALVES Status: OPEN | Info Exchange
| 07043 | Review Response | Approved | 2020-07-15 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.07.15 | Info Exchange
| 09427 | Responded and Closed | Approved | 2020-07-20 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-07 |  | 23 05 23-4.0 DAHU Control Valve - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 23 05 23-4.0 DAHU Control Valve - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-07 |  | 23 05 23-4.0 DAHU Control Valve - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-20 |  | 23 05 23-4.0 DAHU Control Valve_ME_POP.pdf
23 05 23-005-00 | 23 05 23 - VALVES | 23 05 23-005-00 Pressure Reducing Valve for HHW, CHW, and CDW | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-20 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-04 07:00 | 2021-05-25 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-05-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13208 | Received | For Review | 2021-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-04 07:00 | Submittal Number: 23 05 23-5.0 From: GRETCHEN TOSHACH Final Due Date: 06/21/21 Subject: PRESSURE REDUCING VALVE FOR HHW, CHW, AND CDW Description: Spec Section: 23 05 23 - VALVES Status: OPEN | Info Exchange
| 17097 | Forwarded | For Review | 2021-05-20 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-27 | Submittal Number: 23 05 23-5.0 From: GRETCHEN TOSHACH Final Due Date: 06/21/21 Subject: PRESSURE REDUCING VALVE FOR HHW, CHW, AND CDW Description: Spec Section: 23 05 23 - VALVES Status: OPEN | Info Exchange
| 13258 | Review Response | Approved | 2021-05-21 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.05.21 | Info Exchange
| 17155 | Responded and Closed | Approved | 2021-05-25 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.05.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-19 |  | 23 05 23-5.0 PRV MP - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-19 |  | 23 05 23-5.0 PRV MP - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-18 02:00 |  | 23 05 23-5.0 PRV MP - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-25 02:00 |  | 23 05 23-5.0 PRV MP_ME_POP.pdf
23 05 29-001-00 | 23 05 29 - PIPE SUPPORTS AND ANCHORS | 23 05 29-001-00 Pipe Supports and Anchors PD | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-15 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-02 | 2019-08-09 | 26 |  | Record Copies; Transfers; Submittals | 23 05 29-001-01 - 23 05 29-001-01 Pipe Supports and Anchors PD | 25 |  | 2019-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01763 | Received | For Review | 2019-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-02 | Submittal Number: 23 05 29-1.0 From: PATRICK KLEIN Final Due Date: 07/26/19 Subject: PIPE SUPPORTS AND ANCHORS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA ON THE FOLLOWING : - 1. HANGERS OTHER THAN CLEVIS TYPE. 2. ANCHORS. Spec Section: 23 05 29 - PIPE SUPPORTS AND ANCHORS Status: OPEN | Info Exchange
| 02883 | Forwarded | For Review | 2019-07-15 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-07-22 | Submittal Number: 23 05 29-1.0 From: PATRICK KLEIN Final Due Date: 07/26/19 Subject: PIPE SUPPORTS AND ANCHORS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA ON THE FOLLOWING : - 1. HANGERS OTHER THAN CLEVIS TYPE. 2. ANCHORS. Spec Section: 23 05 29 - PIPE SUPPORTS AND ANCHORS Status: OPEN | Info Exchange
| 02023 | Review Response | Revise and Resubmit | 2019-08-08 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Take note of Dura Blok review requirements. Nick Theimer ME Engineers 2019.08.08 | Info Exchange
| 03188 | Responded and Closed | Approved as Noted/Resubmit | 2019-08-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Take note of Dura Blok review requirements. Nick Theimer ME Engineers 2019.08.08 Reference matrix for approved items. Resubmit specific items as indicated. JHD | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-12 |  | 23 05 29-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-15 |  | 23 05 29-1.0 Pipe Supports and Anchors PD Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-14 02:00 |  | 23 05 29-1.0 Pipe Supports and Anchors PD Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-09 02:00 |  | 23 05 29-1.0 Pipe Supports and Anchors PD Product Data-ME_POP.pdf
23 05 29-001-01 | 23 05 29 - PIPE SUPPORTS AND ANCHORS | 23 05 29-001-01 Pipe Supports and Anchors PD | Expected - Overdue | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [7 empty] | 2019-08-23 |  | -1 |  | Submittals | 23 05 29-001-00 - 23 05 29-001-00 Pipe Supports and Anchors PD | -1 | 2019-08-23
23 05 29-004-00 | 23 05 29 - PIPE SUPPORTS AND ANCHORS | 23 05 29-004-00 M-Pipe Pipe Supports | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-30 | 2020-03-30 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-03-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04858 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 23 05 29-4.0 From: GRETCHEN TOSHACH Final Due Date: 04/13/20 Subject: M-PIPE PIPE SUPPORTS Description: PIPE SUPPORTS FOR MECHANICAL PIPING Spec Section: 23 05 29 - PIPE SUPPORTS AND ANCHORS Status: OPEN | Info Exchange
| 06635 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-23 | Submittal Number: 23 05 29-4.0 From: GRETCHEN TOSHACH Final Due Date: 04/13/20 Subject: M-PIPE PIPE SUPPORTS Description: PIPE SUPPORTS FOR MECHANICAL PIPING Spec Section: 23 05 29 - PIPE SUPPORTS AND ANCHORS Status: OPEN | Info Exchange
| 05123 | Review Response | Approved | 2020-03-24 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.24 | Info Exchange
| 06954 | Responded and Closed | Approved | 2020-03-30 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 23 05 29-4.0 Pipe Supports and Anchors Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 23 05 29-4.0 Pipe Supports and Anchors Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-16 |  | 23 05 29-4.0 Pipe Supports and Anchors Product Data - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-03-30 |  | 23 05 29-4.0 Pipe Supports and Anchors Product Data_ME_POP.pdf
23 05 29-005-00 | 23 05 29 - PIPE SUPPORTS AND ANCHORS | 23 05 29-005-00 PIPE SUPPORTS AND ANCHORS- Additional Hanger Anchors | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-27 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-10 | 2020-06-18 | 23 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06060 | Received | For Review | 2020-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-10 | Submittal Number: 23 05 29-5.0 From: GRETCHEN TOSHACH Final Due Date: 06/23/20 Subject: PIPE SUPPORTS AND ANCHORS- ADDITIONAL HANGER ANCHORS Description: Spec Section: 23 05 29 - PIPE SUPPORTS AND ANCHORS Status: OPEN | Info Exchange
| 08211 | Forwarded | For Review | 2020-05-27 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-03 | Submittal Number: 23 05 29-5.0 From: GRETCHEN TOSHACH Final Due Date: 06/23/20 Subject: PIPE SUPPORTS AND ANCHORS- ADDITIONAL HANGER ANCHORS Description: Spec Section: 23 05 29 - PIPE SUPPORTS AND ANCHORS Status: OPEN | Info Exchange
| 06399 | Review Response | Approved | 2020-06-03 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.06.03 | Info Exchange
| 08576 | Forwarded | For Review | 2020-06-11 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael C... | 2020-06-10 | Submittal Number: 23 05 29-5.0 From: GRETCHEN TOSHACH Final Due Date: 06/23/20 Subject: PIPE SUPPORTS AND ANCHORS- ADDITIONAL HANGER ANCHORS Description: Spec Section: 23 05 29 - PIPE SUPPORTS AND ANCHORS Status: OPEN | Info Exchange
| 06480 | Review Response | Approved | 2020-06-17 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 08731 | Responded and Closed | Approved | 2020-06-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.06.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-27 |  | 23 05 29-5.0 Addl Hanger Anchors - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-27 |  | 23 05 29-5.0 Addl Hanger Anchors - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-26 02:00 |  | 23 05 29-5.0 Addl Hanger Anchors - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-26 02:00 |  | 23 05 29-5.0 Addl Hanger Anchors - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-26 02:00 |  | 23 05 29-5.0 Addl Hanger Anchors - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-18 02:00 |  | 23 05 29-5.0 Addl Hanger Anchors_ME_TT REVIEW_pop.pdf
23 05 29-006-00 | 23 05 29 - PIPE SUPPORTS AND ANCHORS | 23 05 29-006-00 Pipe Supports/Anchors | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-19 | 2020-10-11 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-10-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08561 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 23 05 29-6.0 From: GRETCHEN TOSHACH Final Due Date: 10/09/20 Subject: PIPE SUPPORTS/ANCHORS Description: Spec Section: 23 05 29 - PIPE SUPPORTS AND ANCHORS Status: OPEN | Info Exchange
| 11321 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-10-12 | Submittal Number: 23 05 29-6.0 From: GRETCHEN TOSHACH Final Due Date: 10/09/20 Subject: PIPE SUPPORTS/ANCHORS Description: Spec Section: 23 05 29 - PIPE SUPPORTS AND ANCHORS Status: OPEN | Info Exchange
| 08575 | Review Response | Approved | 2020-10-05 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 08703 | Review Response | Approved | 2020-10-06 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.10.06 | Info Exchange
| 11494 | Responded and Closed | Approved | 2020-10-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.06 | Info Exchange
| 11969 | Sent | For Information Only | 2020-10-28 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.06 | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 23 05 29-6.0Pipe Hangers - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 23 05 29-6.0Pipe Hangers - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-05 |  | 23 05 29-6.0Pipe Hangers - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-10-04 02:00 |  | 23 05 29-6.0Pipe Hangers - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-11 02:00 |  | 23 05 29-6.0Pipe Hangers - MAM_TT_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-10-04 02:00 |  | 23 05 29-6.0Pipe Hangers - MAM.pdf
23 05 29-007-00 | 23 05 29 - PIPE SUPPORTS AND ANCHORS | 23 05 29-007-00 Atrium Duct Anchors | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-09 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-23 | 2020-12-17 | 9 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10041 | Received | For Review | 2020-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-23 | Submittal Number: 23 05 29-7.0 From: GRETCHEN TOSHACH Final Due Date: 12/23/20 Subject: ATRIUM DUCT ANCHORS Description: Spec Section: 23 05 29 - PIPE SUPPORTS AND ANCHORS Status: OPEN | Info Exchange
| 13139 | Forwarded | For Review | 2020-12-09 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-12-16 | Submittal Number: 23 05 29-7.0 From: GRETCHEN TOSHACH Final Due Date: 12/23/20 Subject: ATRIUM DUCT ANCHORS Description: Spec Section: 23 05 29 - PIPE SUPPORTS AND ANCHORS Status: OPEN | Info Exchange
| 10212 | Review Response | Approved | 2020-12-11 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Structural engineer to review Nick Theimer ME Engineers 2020.12.11 | Info Exchange
| 10835 | Review Response | Approved | 2020-12-15 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. Loads imposed on structural framing to be provided to EOR for review and approval in separate submittal. | Info Exchange
| 13355 | Responded and Closed | Approved | 2020-12-17 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.12.11 Pending response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. Loads imposed on structural framing to be provided to EOR for review and approval in separate submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-09 |  | 23 05 29-7.4 Atrium Duct Anchors - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-09 |  | 23 05 29-7.4 Atrium Duct Anchors - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-12-09 |  | 23 05 29-7.4 Atrium Duct Anchors - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-12-08 02:00 |  | 23 05 29-7.4 Atrium Duct Anchors - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-17 |  | 23 05 29-7.4 Atrium Duct Anchors - TT_ME_POP.pdf
23 05 30-001-00 | 23 05 30 - ELECTRONIC SPEED CONTROLLERS | 23 05 30-001-00 ELECTRONIC SPEED CONTROLLERS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-16 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-30 | 2019-08-30 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-08-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02093 | Received | For Review | 2019-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction) | 2019-08-30 | Submittal Number: 23 05 30-1.0 From: PATRICK KLEIN Final Due Date: 08/29/19 Subject: ELECTRONIC SPEED CONTROLLERS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR EACH UNIT. INCLUDE : - 1. CAPACITY: A. HORSEPOWER B. KVA C. AMPS 2. WIRING DIAGRAMS: A. INCLUDE DIAGRAMS FOR BASIC UNIT AND FOR ALL REQUIRED ACCESSORIES. 3. DIMENSIONS. 4. INSTALLATION INSTRUCTIONS. 5. DESCRIPTION OF DIAGNOSTIC SYSTEM. 6. OPTIONS PROVIDED. 7. TIME-CURRENT CURVES FOR VFD CIRCUIT. Spec Section: 23 05 30 - ELECTRONIC SPEED CONTROLLERS Status: OPEN | Info Exchange
| 03266 | Forwarded | For Review | 2019-08-16 | Patrick Klein (Mortenson Construction) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-23 | Submittal Number: 23 05 30-1.0 From: PATRICK KLEIN Final Due Date: 08/29/19 Subject: ELECTRONIC SPEED CONTROLLERS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR EACH UNIT. INCLUDE : - 1. CAPACITY: A. HORSEPOWER B. KVA C. AMPS 2. WIRING DIAGRAMS: A. INCLUDE DIAGRAMS FOR BASIC UNIT AND FOR ALL REQUIRED ACCESSORIES. 3. DIMENSIONS. 4. INSTALLATION INSTRUCTIONS. 5. DESCRIPTION OF DIAGNOSTIC SYSTEM. 6. OPTIONS PROVIDED. 7. TIME-CURRENT CURVES FOR VFD CIRCUIT. Spec Section: 23 05 30 - ELECTRONIC SPEED CONTROLLERS Status: OPEN | Info Exchange
| 02272 | Review Response | Revise and Resubmit | 2019-08-30 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Revise and resubmit. Nick Theimer ME Engineers 2019.08.30 | Info Exchange
| 03495 | Responded and Closed | Approved as Noted/Resubmit | 2019-08-30 | Patrick Klein (Mortenson Construction) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Revise and resubmit items as indicated. Nick Theimer ME Engineers 2019.08.30 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-15 |  | 23 05 30-1.0 Variable Frequency Drives-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2019-08-15 |  | 23 05 30-1.0 Variable Frequency Drives-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-14 02:00 |  | 23 05 30-1.0 Variable Frequency Drives-MAM.pdf
| Responded and Closed |  | Patrick Klein (Mortenson Construction) | 1 | 2019-08-30 02:00 |  | 23 05 30-1.0 Variable Frequency Drives-ME_POP.pdf
23 05 30-001-01 | 23 05 30 - ELECTRONIC SPEED CONTROLLERS | 23 05 30-001-01 ELECTRONIC SPEED CONTROLLERS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-27 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-11 | 2019-10-02 | 6 |  | Record Copies; Transfers; Submittals | 23 05 30-001-02 - 23 05 30-001-01 ELECTRONIC SPEED CONTROLLERS - Product Data | 3 |  | 2019-10-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02581 | Received | For Review | 2019-09-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC); Gretchen Toshach (Mortenson Construction) | 2019-10-11 | Submittal Number: 23 05 30-1.1 From: GRETCHEN TOSHACH Final Due Date: 10/09/19 Subject: ELECTRONIC SPEED CONTROLLERS - PRODUCT DATA Description: RESUBMIT MANUFACTURERS PRODUCT DATA FOR: CWP-1E.01-.04, EF-1F.03, EF-2C.01-.02, EF-2D.01, SPF-2A.01, 2B.01, 2C.01, 2D.01, SEF-2A.01, 2B.01, 2C.01, 2D.01, SEF-6A.01-.04, SEF-6B.01-.04, SEF-1A-D Spec Section: 23 05 30 - ELECTRONIC SPEED CONTROLLERS Status: OPEN | Info Exchange
| 03869 | Forwarded | For Review | 2019-09-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-07 | Submittal Number: 23 05 30-1.1 From: GRETCHEN TOSHACH Final Due Date: 10/09/19 Subject: ELECTRONIC SPEED CONTROLLERS - PRODUCT DATA Description: RESUBMIT MANUFACTURERS PRODUCT DATA FOR: CWP-1E.01-.04, EF-1F.03, EF-2C.01-.02, EF-2D.01, SPF-2A.01, 2B.01, 2C.01, 2D.01, SEF-2A.01, 2B.01, 2C.01, 2D.01, SEF-6A.01-.04, SEF-6B.01-.04, SEF-1A-D Spec Section: 23 05 30 - ELECTRONIC SPEED CONTROLLERS Status: OPEN | Info Exchange
| 02638 | Review Response | Approved as Noted/Resubmit | 2019-10-02 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Refer to disposition comments. Submit harmonic analysis. Nick Theimer ME Engineers 2019.10.02 | Info Exchange
| 03947 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-02 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Refer to disposition comments. Submit harmonic analysis. Nick Theimer ME Engineers 2019.10.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-27 |  | 23 05 30-1.1 Variable Frequency Drives_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-27 |  | 23 05 30-1.1 Variable Frequency Drives_MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-09-26 02:00 |  | 23 05 30-1.1 Variable Frequency Drives_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-02 02:00 |  | 23 05 30-1.1 Variable Frequency Drives-ME_POP.pdf
23 05 30-001-02 | 23 05 30 - ELECTRONIC SPEED CONTROLLERS | 23 05 30-001-01 ELECTRONIC SPEED CONTROLLERS - Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 23 05 30-001-01 - 23 05 30-001-01 ELECTRONIC SPEED CONTROLLERS - Product Data | -1 | 2019-10-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-02 02:00 |  | 23 05 30-1.1 Variable Frequency Drives-ME_POP.pdf
23 05 30-003-00 | 23 05 30 - ELECTRONIC SPEED CONTROLLERS | 23 05 30-003-00 CCD-041 VFD for EF 1F.7 Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-17 | 2020-03-13 | 11 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-03-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04583 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 23 05 30-3.0 From: GRETCHEN TOSHACH Final Due Date: 03/06/20 Subject: CCD-041 VFD FOR EF 1F.7 PRODUCT DATA Description: VFD FOR EF 1F.7 PRODUCT DATA AS ISSUED IN CCD 041 Spec Section: 23 05 30 - ELECTRONIC SPEED CONTROLLERS Status: OPEN | Info Exchange
| 06318 | Forwarded | For Review | 2020-03-02 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-09 | Submittal Number: 23 05 30-3.0 From: GRETCHEN TOSHACH Final Due Date: 03/06/20 Subject: CCD-041 VFD FOR EF 1F.7 PRODUCT DATA Description: VFD FOR EF 1F.7 PRODUCT DATA AS ISSUED IN CCD 041 Spec Section: 23 05 30 - ELECTRONIC SPEED CONTROLLERS Status: OPEN | Info Exchange
| 04821 | Review Response | Approved as Noted | 2020-03-13 | Nick Theimer (ME Engineers) | Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| 06599 | Responded and Closed | Approved as Noted | 2020-03-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 23 05 30-3.0 VFD-EF-1F.07 CCD041 Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 23 05 30-3.0 VFD-EF-1F.07 CCD041 Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-01 02:00 |  | 23 05 30-3.0 VFD-EF-1F.07 CCD041 Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-13 02:00 |  | 23 05 30-3.0 VFD-EF-1F.07 CCD041 Product Data_ME_POP.pdf
23 05 48-001-00 | 23 05 48 - VIBRATION CONTROL | 23 05 48-001-00 VIBRATION CONTROL - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-30 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-13 | 2019-08-09 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01904 | Received | For Review | 2019-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-13 | Submittal Number: 23 05 48-1.0 From: PATRICK KLEIN Final Due Date: 08/12/19 Subject: VIBRATION CONTROL - PRODUCT DATA Description: PRIOR TO ORDERING ANY PRODUCTS, SUBMIT SHOP DRAWINGS OR THE ITEMS LISTED BELOW. THE SHOP DRAWINGS MUST BE COMPLETE WHEN SUBMITTED AND MUST BE PRESENTED INA CLEAR, EASILY UNDERSTOOD FORM. INCOMPLETE OR UNCLEAR PRESENTATION OF SHOP DRAWINGS MAY BE REASON FOR REJECTION OF THE SUBMITTAL. 1. A COMPLETE DESCRIPTION OF PRODUCTS TO BE SUPPLIED, INCLUDING PRODUCT DATA, DIMENSIONS, SPECIFICATIONS, AND INSTALLATION INSTRUCTIONS. 2. DETAILED SELECTION DATA FOR EACH VIBRATION ISOLATOR SUPPORTING EQUIPMENT, INCLUDING: A. THE EQUIPMENT IDENTIFICATION MARK; B. A CUT SHEET OF THE ISOLATED EQUIPMENT SHOWING EQUIPMENT SUPPORT POINTS AND OPERATING WEIGHT AT EACH POINT. C. THE ISOLATOR TYPE; D. THE ACTUAL LOAD; E. THE STATIC DEFLECTION EXPECTED UNDER THE ACTUAL LOAD; F. SPECIFIED MINIMUM STATIC DEFLECTION; G. THE ADDITIONAL DEFLECTION-TO-SOLID UNDER LOAD; H. THE RATIO OF SPRING HEIGHT UNDER LOAD TO SPRING DIAMETER. 3. STEEL RAILS, STEEL BASE FRAMES, AND CONCRETE INERTIA BASES SHOWING ALL STEEL WORK, REINFORCING, VIBRATION ISOLATOR MOUNTING ATTACHMENT METHOD, AND LOCATION OF EQUIPMENT ATTACHMENT BOLTS. 4. SPECIAL DETAILS NECESSARY TO CONVEY COMPLETE UNDERSTANDING OF THE WORK TO BE PERFORMED. Spec Section: 23 05 48 - VIBRATION CONTROL Status: OPEN | Info Exchange
| 03047 | Forwarded | For Review | 2019-07-29 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-05 | Submittal Number: 23 05 48-1.0 From: PATRICK KLEIN Final Due Date: 08/12/19 Subject: VIBRATION CONTROL - PRODUCT DATA Description: PRIOR TO ORDERING ANY PRODUCTS, SUBMIT SHOP DRAWINGS OR THE ITEMS LISTED BELOW. THE SHOP DRAWINGS MUST BE COMPLETE WHEN SUBMITTED AND MUST BE PRESENTED INA CLEAR, EASILY UNDERSTOOD FORM. INCOMPLETE OR UNCLEAR PRESENTATION OF SHOP DRAWINGS MAY BE REASON FOR REJECTION OF THE SUBMITTAL. 1. A COMPLETE DESCRIPTION OF PRODUCTS TO BE SUPPLIED, INCLUDING PRODUCT DATA, DIMENSIONS, SPECIFICATIONS, AND INSTALLATION INSTRUCTIONS. 2. DETAILED SELECTION DATA FOR EACH VIBRATION ISOLATOR SUPPORTING EQUIPMENT, INCLUDING: A. THE EQUIPMENT IDENTIFICATION MARK; B. A CUT SHEET OF THE ISOLATED EQUIPMENT SHOWING EQUIPMENT SUPPORT POINTS AND OPERATING WEIGHT AT EACH POINT. C. THE ISOLATOR TYPE; D. THE ACTUAL LOAD; E. THE STATIC DEFLECTION EXPECTED UNDER THE ACTUAL LOAD; F. SPECIFIED MINIMUM STATIC DEFLECTION; G. THE ADDITIONAL DEFLECTION-TO-SOLID UNDER LOAD; H. THE RATIO OF SPRING HEIGHT UNDER LOAD TO SPRING DIAMETER. 3. STEEL RAILS, STEEL BASE FRAMES, AND CONCRETE INERTIA BASES SHOWING ALL STEEL WORK, REINFORCING, VIBRATION ISOLATOR MOUNTING ATTACHMENT METHOD, AND LOCATION OF EQUIPMENT ATTACHMENT BOLTS. 4. SPECIAL DETAILS NECESSARY TO CONVEY COMPLETE UNDERSTANDING OF THE WORK TO BE PERFORMED. Spec Section: 23 05 48 - VIBRATION CONTROL Status: OPEN | Info Exchange
| 02024 | Review Response | Approved as Noted | 2019-08-08 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | Please see attached for review. Nick Theimer ME Engineers 2019.08.08 | Info Exchange
| 03189 | Responded and Closed | Approved as Noted | 2019-08-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: Please see attached for review. Nick Theimer ME Engineers 2019.08.08 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-29 |  | 23 05 48-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-29 |  | 23 05 48-1.0 Vibration Control Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-28 02:00 |  | 23 05 48-1.0 Vibration Control Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-09 02:00 |  | 23 05 48-1.0 Vibration Control Product Data-ME-POP.pdf
23 05 48-002-00 | 23 05 48 - VIBRATION CONTROL | 23 05 48-002-00 Mechanical Room Vibration Isolation | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-27 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-10 | 2020-06-04 | 9 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06061 | Received | For Review | 2020-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-10 | Submittal Number: 23 05 48-2.0 From: GRETCHEN TOSHACH Final Due Date: 06/30/20 Subject: MECHANICAL ROOM VIBRATION ISOLATION Description: Spec Section: 23 05 48 - VIBRATION CONTROL Status: OPEN | Info Exchange
| 08212 | Forwarded | For Review | 2020-05-27 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-03 | Submittal Number: 23 05 48-2.0 From: GRETCHEN TOSHACH Final Due Date: 06/30/20 Subject: MECHANICAL ROOM VIBRATION ISOLATION Description: Spec Section: 23 05 48 - VIBRATION CONTROL Status: OPEN | Info Exchange
| 06208 | Review Response | Approved | 2020-06-03 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.06.03 | Info Exchange
| 08388 | Responded and Closed | Approved | 2020-06-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.06.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-27 |  | 23 05 48-2.0 Mech Rm Pipe Vib Control - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-27 |  | 23 05 48-2.0 Mech Rm Pipe Vib Control - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-26 02:00 |  | 23 05 48-2.0 Mech Rm Pipe Vib Control - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-04 02:00 |  | 23 05 48-2.0 Mech Rm Pipe Vib Control_ME_POP.pdf
23 05 49-001-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-001-00 SEISMIC RESTRAINTS - General | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-29 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-12 | 2019-08-20 | 23 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2019-08-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01897 | Received | For Review | 2019-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-12 | Submittal Number: 23 05 49-1.0 From: PATRICK KLEIN Final Due Date: 08/12/19 Subject: SEISMIC RESTRAINTS - GENERAL Description: SUBMITTED SYSTEMS SHALL BE PER MASON INDUSTRIES, ISAT, OR B-LINE/TOLCO. CONTRACTOR SHALL IDENTIFY AND CONVEY EACH DECK CONDITION TO WHICH SEISMIC ATTACHMENTS WILL BE MADE. INFORMATION SHALL INCLUDE TYPE AND SIZE OF STEEL MEMBER AND ANY POINT LOAD LIMITATIONS OR RESTRICTIONS. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 03038 | Forwarded | For Review | 2019-07-29 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-05 | Submittal Number: 23 05 49-1.0 From: PATRICK KLEIN Final Due Date: 08/12/19 Subject: SEISMIC RESTRAINTS - GENERAL Description: SUBMITTED SYSTEMS SHALL BE PER MASON INDUSTRIES, ISAT, OR B-LINE/TOLCO. CONTRACTOR SHALL IDENTIFY AND CONVEY EACH DECK CONDITION TO WHICH SEISMIC ATTACHMENTS WILL BE MADE. INFORMATION SHALL INCLUDE TYPE AND SIZE OF STEEL MEMBER AND ANY POINT LOAD LIMITATIONS OR RESTRICTIONS. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 02156 | Review Response | Approved | 2019-08-16 | Nick Theimer (ME Engineers) | Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2109.08.16 | Info Exchange
| 03336 | Responded and Closed | Approved | 2019-08-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2109.08.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-29 |  | 23 05 49-1.0 ISAT Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-29 |  | 23 05 49-1.0 ISAT Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-28 02:00 |  | 23 05 49-1.0 ISAT Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-20 02:00 |  | 23 05 49-1.0 ISAT Product Data-ME_POP.pdf
23 05 49-007-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-007-00 23 05 49 Seismic Restraints Bowl Duct | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-22 | Closed - Void |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-06 |  | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-11-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03334 | Received | For Review | 2019-11-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-06 | Submittal Number: 23 05 49-7.0 From: GRETCHEN TOSHACH Final Due Date: 12/11/19 Subject: 23 05 49 SEISMIC RESTRAINTS BOWL DUCT Description: PROVIDE BOWL DUCT SEISMIC DESIGN FORCE CALCULATIONS PER ASCE 7-10, FORMULA 13.3-1 STAMPED BY A CIVIL OR STRUCTURAL ENGINEER LICENSED TO PRACTICE IN THE STATE OF CALIFORNIA. CALCULATIONS SHALL UTILIZE CORRECT SEISMIC COEFFICIENTS PER ASCE 7-10, TABLE 13.6-1 FOR THE COMPONENT AND INSTALLATION CONDITION. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 04786 | Forwarded | For Review | 2019-11-22 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-02 | Submittal Number: 23 05 49-7.0 From: GRETCHEN TOSHACH Final Due Date: 12/11/19 Subject: 23 05 49 SEISMIC RESTRAINTS BOWL DUCT Description: PROVIDE BOWL DUCT SEISMIC DESIGN FORCE CALCULATIONS PER ASCE 7-10, FORMULA 13.3-1 STAMPED BY A CIVIL OR STRUCTURAL ENGINEER LICENSED TO PRACTICE IN THE STATE OF CALIFORNIA. CALCULATIONS SHALL UTILIZE CORRECT SEISMIC COEFFICIENTS PER ASCE 7-10, TABLE 13.6-1 FOR THE COMPONENT AND INSTALLATION CONDITION. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 04795 | Closed | Void | 2019-11-22 | Josh Dobken (Populous) |  |  | Item has been voided per Mortenson request.
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-21 |  | 23 05 49-7.0 Seismic Bowl Duct Calculations - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-21 |  | 23 05 49-7.0 Seismic Bowl Duct Calculations - MAM.pdf
23 05 49-007-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-007-01 23 05 49 Seismic Restraints Bowl Duct | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-25 | Responded and Closed - Rejected |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-09 | 2019-12-20 | 26 |  | Record Copies; Transfers; Submittals |  | 25 |  | 2019-12-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03363 | Received | For Review | 2019-11-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-09 | Submittal Number: 23 05 49-7.1 From: GRETCHEN TOSHACH Final Due Date: 12/11/19 Subject: 23 05 49 SEISMIC RESTRAINTS BOWL DUCT Description: PROVIDE BOWL DUCT SEISMIC DESIGN FORCE CALCULATIONS PER ASCE 7-10, FORMULA 13.3-1 STAMPED BY A CIVIL OR STRUCTURAL ENGINEER LICENSED TO PRACTICE IN THE STATE OF CALIFORNIA. CALCULATIONS SHALL UTILIZE CORRECT SEISMIC COEFFICIENTS PER ASCE 7-10, TABLE 13.6-1 FOR THE COMPONENT AND INSTALLATION CONDITION. PREVIOUS REVISION VOIDED IN ORDER TO INCLUDE ADDITIONAL CALCULATIONS TO THE PACKAGE. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 04816 | Forwarded | For Review | 2019-11-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-02 | Submittal Number: 23 05 49-7.1 From: GRETCHEN TOSHACH Final Due Date: 12/11/19 Subject: 23 05 49 SEISMIC RESTRAINTS BOWL DUCT Description: PROVIDE BOWL DUCT SEISMIC DESIGN FORCE CALCULATIONS PER ASCE 7-10, FORMULA 13.3-1 STAMPED BY A CIVIL OR STRUCTURAL ENGINEER LICENSED TO PRACTICE IN THE STATE OF CALIFORNIA. CALCULATIONS SHALL UTILIZE CORRECT SEISMIC COEFFICIENTS PER ASCE 7-10, TABLE 13.6-1 FOR THE COMPONENT AND INSTALLATION CONDITION. PREVIOUS REVISION VOIDED IN ORDER TO INCLUDE ADDITIONAL CALCULATIONS TO THE PACKAGE. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 03549 | Review Response | Approved as Noted | 2019-12-06 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. This submittal requires structural review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| 05018 | Forwarded | For Review | 2019-12-09 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth K... | 2019-12-12 | Submittal Number: 23 05 49-7.1 From: GRETCHEN TOSHACH Final Due Date: 12/11/19 Subject: 23 05 49 SEISMIC RESTRAINTS BOWL DUCT Description: PROVIDE BOWL DUCT SEISMIC DESIGN FORCE CALCULATIONS PER ASCE 7-10, FORMULA 13.3-1 STAMPED BY A CIVIL OR STRUCTURAL ENGINEER LICENSED TO PRACTICE IN THE STATE OF CALIFORNIA. CALCULATIONS SHALL UTILIZE CORRECT SEISMIC COEFFICIENTS PER ASCE 7-10, TABLE 13.6-1 FOR THE COMPONENT AND INSTALLATION CONDITION. PREVIOUS REVISION VOIDED IN ORDER TO INCLUDE ADDITIONAL CALCULATIONS TO THE PACKAGE. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 03725 | Review Response | Rejected | 2019-12-19 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached submittal for TT's comments. TT has provided comments on the temporary hoist beam as a courtesy. However, such a review is formally outside TT's scope, but MAM may choose to engage TT as a Construction Engineering service in a similar manner as for assessing the hung scaffolding. | Info Exchange
| 05255 | Responded and Closed | Rejected | 2019-12-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Reference TT comments in submittal package for specific items to address. Mortenson to provide contractor review and stamp on sheet in resubmittal. Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. This submittal requires structural review. Nick Theimer ME Engineers 2019.12.06 Response (Rejected) from: Franz Kogler (Thornton Tomasetti) Remarks: See attached submittal for TT's comments. TT has provided comments on the temporary hoist beam as a courtesy. However, such a review is formally outside TT's scope, but MAM may choose to engage TT as a Construction Engineering service in a similar manner as for assessing the hung scaffolding. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-25 |  | 23 05 49-7.1 Seismic Bowl Duct Calculations - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-25 |  | 23 05 49-7.1 Seismic Bowl Duct Calculations - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-24 02:00 |  | 23 05 49-7.1 Seismic Bowl Duct Calculations - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-24 02:00 |  | 23 05 49-7.1 Seismic Bowl Duct Calculations - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-11-24 02:00 |  | 23 05 49-7.1 Seismic Bowl Duct Calculations - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-24 02:00 |  | 23 05 49-7.1 Seismic Bowl Duct Calculations - MAM.pdf
23 05 49-007-02 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-007-02 23 05 49 Seismic Restraints Bowl Duct | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-14 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-02-28 | 2020-03-05 | 21 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-03-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04351 | Received | For Review | 2020-02-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-02-28 | Submittal Number: 23 05 49-7.2 From: GRETCHEN TOSHACH Final Due Date: 01/31/20 Subject: 23 05 49 SEISMIC RESTRAINTS BOWL DUCT Description: PROVIDE BOWL DUCT SEISMIC DESIGN FORCE CALCULATIONS PER ASCE 7-10, FORMULA 13.3-1 STAMPED BY A CIVIL OR STRUCTURAL ENGINEER LICENSED TO PRACTICE IN THE STATE OF CALIFORNIA. CALCULATIONS SHALL UTILIZE CORRECT SEISMIC COEFFICIENTS PER ASCE 7-10, TABLE 13.6-1 FOR THE COMPONENT AND INSTALLATION CONDITION. PREVIOUS REVISION VOIDED IN ORDER TO INCLUDE ADDITIONAL CALCULATIONS TO THE PACKAGE. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06022 | Forwarded | For Review | 2020-02-14 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-21 | Submittal Number: 23 05 49-7.2 From: GRETCHEN TOSHACH Final Due Date: 01/31/20 Subject: 23 05 49 SEISMIC RESTRAINTS BOWL DUCT Description: PROVIDE BOWL DUCT SEISMIC DESIGN FORCE CALCULATIONS PER ASCE 7-10, FORMULA 13.3-1 STAMPED BY A CIVIL OR STRUCTURAL ENGINEER LICENSED TO PRACTICE IN THE STATE OF CALIFORNIA. CALCULATIONS SHALL UTILIZE CORRECT SEISMIC COEFFICIENTS PER ASCE 7-10, TABLE 13.6-1 FOR THE COMPONENT AND INSTALLATION CONDITION. PREVIOUS REVISION VOIDED IN ORDER TO INCLUDE ADDITIONAL CALCULATIONS TO THE PACKAGE. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06028 | Forwarded | For Review | 2020-02-17 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-24 | Submittal Number: 23 05 49-7.2 From: GRETCHEN TOSHACH Final Due Date: 01/31/20 Subject: 23 05 49 SEISMIC RESTRAINTS BOWL DUCT Description: PROVIDE BOWL DUCT SEISMIC DESIGN FORCE CALCULATIONS PER ASCE 7-10, FORMULA 13.3-1 STAMPED BY A CIVIL OR STRUCTURAL ENGINEER LICENSED TO PRACTICE IN THE STATE OF CALIFORNIA. CALCULATIONS SHALL UTILIZE CORRECT SEISMIC COEFFICIENTS PER ASCE 7-10, TABLE 13.6-1 FOR THE COMPONENT AND INSTALLATION CONDITION. PREVIOUS REVISION VOIDED IN ORDER TO INCLUDE ADDITIONAL CALCULATIONS TO THE PACKAGE. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 04431 | Review Response | Approved | 2020-02-18 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.02.18 | Info Exchange
| 04673 | Review Response | Approved as Noted/Resubmit | 2020-03-04 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See comments in attached submittal. TT-FK | Info Exchange
| 06428 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-05 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: Structural engineer to review. Nick Theimer ME Engineers 2020.02.18 Response (Approved as Noted/Resubmit) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments in attached submittal. TT-FK | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-13 |  | 23 05 49-7.2 Seismic_Bowl Duct Calculations - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-13 |  | 23 05 49-7.2 Seismic_Bowl Duct Calculations - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-13 |  | 23 05 49-7.2 Seismic_Bowl Duct Calculations - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-02-12 02:00 |  | 23 05 49-7.2 Seismic_Bowl Duct Calculations - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-02-12 02:00 |  | 23 05 49-7.2 Seismic_Bowl Duct Calculations - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-05 02:00 |  | 23 05 49-7.2 Seismic_Bowl Duct Calculations - MAM_TTReview_POP.pdf
23 05 49-007-03 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-007-03 23 05 49 Seismic Restraints Bowl Duct | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-30 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-14 | 2020-04-16 | 18 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-04-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05102 | Received | For Review | 2020-03-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-14 | Submittal Number: 23 05 49-7.3 From: GRETCHEN TOSHACH Final Due Date: 04/10/20 Subject: 23 05 49 SEISMIC RESTRAINTS BOWL DUCT Description: PROVIDE BOWL DUCT SEISMIC DESIGN FORCE CALCULATIONS PER ASCE 7-10, FORMULA 13.3-1 STAMPED BY A CIVIL OR STRUCTURAL ENGINEER LICENSED TO PRACTICE IN THE STATE OF CALIFORNIA. CALCULATIONS SHALL UTILIZE CORRECT SEISMIC COEFFICIENTS PER ASCE 7-10, TABLE 13.6-1 FOR THE COMPONENT AND INSTALLATION CONDITION. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06930 | Forwarded | For Review | 2020-03-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-06 | Submittal Number: 23 05 49-7.3 From: GRETCHEN TOSHACH Final Due Date: 04/10/20 Subject: 23 05 49 SEISMIC RESTRAINTS BOWL DUCT Description: PROVIDE BOWL DUCT SEISMIC DESIGN FORCE CALCULATIONS PER ASCE 7-10, FORMULA 13.3-1 STAMPED BY A CIVIL OR STRUCTURAL ENGINEER LICENSED TO PRACTICE IN THE STATE OF CALIFORNIA. CALCULATIONS SHALL UTILIZE CORRECT SEISMIC COEFFICIENTS PER ASCE 7-10, TABLE 13.6-1 FOR THE COMPONENT AND INSTALLATION CONDITION. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 05112 | Review Response | No Action Taken or Required | 2020-03-30 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.03.30 | Info Exchange
| 06940 | Forwarded | For Review | 2020-03-30 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-04-06 | Submittal Number: 23 05 49-7.3 From: GRETCHEN TOSHACH Final Due Date: 04/10/20 Subject: 23 05 49 SEISMIC RESTRAINTS BOWL DUCT Description: PROVIDE BOWL DUCT SEISMIC DESIGN FORCE CALCULATIONS PER ASCE 7-10, FORMULA 13.3-1 STAMPED BY A CIVIL OR STRUCTURAL ENGINEER LICENSED TO PRACTICE IN THE STATE OF CALIFORNIA. CALCULATIONS SHALL UTILIZE CORRECT SEISMIC COEFFICIENTS PER ASCE 7-10, TABLE 13.6-1 FOR THE COMPONENT AND INSTALLATION CONDITION. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 05399 | Review Response | Approved as Noted | 2020-04-15 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | See comments in attached submittal. | Info Exchange
| 07331 | Responded and Closed | Approved as Noted | 2020-04-16 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Structural engineer to review. Nick Theimer ME Engineers 2020.03.30 Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments in attached submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-27 |  | 23 05 49-7.3 Seismic_Bowl Duct Calculations - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-27 |  | 23 05 49-7.3 Seismic_Bowl Duct Calculations - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-26 02:00 |  | 23 05 49-7.3 Seismic_Bowl Duct Calculations - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-26 02:00 |  | 23 05 49-7.3 Seismic_Bowl Duct Calculations - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-03-26 02:00 |  | 23 05 49-7.3 Seismic_Bowl Duct Calculations - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-16 02:00 |  | 23 05 49-7.3 Seismic_Bowl Duct Calculations_ME_TT_POP Review.pdf
23 05 49-008-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-008-00 Cooling Tower Seismic Calculation and Vibration Isolation Submittal | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-20 | Responded and Closed - Rejected |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-03 | 2020-02-05 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-02-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03986 | Received | For Review | 2020-01-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2020-02-03 | Submittal Number: 23 05 49-8.0 From: GRETCHEN TOSHACH Final Due Date: 01/30/20 Subject: COOLING TOWER SEISMIC CALCULATION AND VIBRATION ISOLATION SUBMITTAL Description: SEISMIC CALCULATIONS AND ISOLATION VIBRATION FOR COOLING TOWERS Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 05564 | Forwarded | For Review | 2020-01-20 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-27 | Submittal Number: 23 05 49-8.0 From: GRETCHEN TOSHACH Final Due Date: 01/30/20 Subject: COOLING TOWER SEISMIC CALCULATION AND VIBRATION ISOLATION SUBMITTAL Description: SEISMIC CALCULATIONS AND ISOLATION VIBRATION FOR COOLING TOWERS Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 05638 | Forwarded | For Review | 2020-01-24 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... |  | Submittal Number: 23 05 49-8.0 From: GRETCHEN TOSHACH Final Due Date: 01/30/20 Subject: COOLING TOWER SEISMIC CALCULATION AND VIBRATION ISOLATION SUBMITTAL Description: SEISMIC CALCULATIONS AND ISOLATION VIBRATION FOR COOLING TOWERS Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 04190 | Review Response | Not Required For Review | 2020-02-03 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | See attached for note for structural engineer to review. Nick Theimer ME Engineers 2020.02.03 | Info Exchange
| 04212 | Review Response | Rejected | 2020-02-05 | Andy Tatkowski (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached. ART ¦ TT ¦ 2/5/2020 | Info Exchange
| 05835 | Responded and Closed | Rejected | 2020-02-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | See comments provided by Structural Engineer and resubmit accordingly. Response (Not Required For Review) from: Nick Theimer (ME Engineers) Remarks: See attached for note for structural engineer to review. Nick Theimer ME Engineers 2020.02.03 Response (Rejected) from: Andy Tatkowski (Thornton Tomasetti) Remarks: See attached. ART ¦ TT ¦ 2/5/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-20 |  | 23 05 49-8.0 CT Seismic Calcs - MAM[1].pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-20 |  | 23 05 49-8.0 CT Seismic Calcs - MAM[1].pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-20 |  | 23 05 49-8.0 CT Seismic Calcs - MAM[1].pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-01-19 02:00 |  | 23 05 49-8.0 CT Seismic Calcs - MAM[1].pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-02-05 02:00 |  | 23 05 49-8.0 CT Seismic Calcs - MAM_TT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-05 02:00 |  | 23 05 49-8.0 CT Seismic Calcs - MAM_TT_ME_POP.pdf
23 05 49-008-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-008-01 Cooling Tower Seismic Calculation and Vibration Isolation Submittal | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-18 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-03-03 | 2020-03-03 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04387 | Received | For Review | 2020-02-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-03 | Submittal Number: 23 05 49-8.1 From: GRETCHEN TOSHACH Final Due Date: 01/30/20 Subject: COOLING TOWER SEISMIC CALCULATION AND VIBRATION ISOLATION SUBMITTAL Description: SEISMIC CALCULATIONS AND ISOLATION VIBRATION FOR COOLING TOWERS Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06061 | Forwarded | For Review | 2020-02-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-25 | Submittal Number: 23 05 49-8.1 From: GRETCHEN TOSHACH Final Due Date: 01/30/20 Subject: COOLING TOWER SEISMIC CALCULATION AND VIBRATION ISOLATION SUBMITTAL Description: SEISMIC CALCULATIONS AND ISOLATION VIBRATION FOR COOLING TOWERS Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 04432 | Review Response | Not Required For Review | 2020-02-18 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.02.18 | Info Exchange
| 06065 | Forwarded | For Review | 2020-02-18 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-02-25 | Submittal Number: 23 05 49-8.1 From: GRETCHEN TOSHACH Final Due Date: 01/30/20 Subject: COOLING TOWER SEISMIC CALCULATION AND VIBRATION ISOLATION SUBMITTAL Description: SEISMIC CALCULATIONS AND ISOLATION VIBRATION FOR COOLING TOWERS Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 04560 | Review Response | Approved | 2020-02-28 | Andy Tatkowski (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached. ART ¦ TT ¦ 2/28/2020 | Info Exchange
| 06361 | Responded and Closed | Approved | 2020-03-03 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Andy Tatkowski (Thornton Tomasetti) Remarks: See attached. ART ¦ TT ¦ 2/28/2020 Response (Not Required For Review) from: Nick Theimer (ME Engineers) Remarks: Structural engineer to review. Nick Theimer ME Engineers 2020.02.18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-18 |  | 23 05 49-8.1 Cooling Tower Seismic Calcs.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-18 |  | 23 05 49-8.1 Cooling Tower Seismic Calcs.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-02-17 02:00 |  | 23 05 49-8.1 Cooling Tower Seismic Calcs.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-17 02:00 |  | 23 05 49-8.1 Cooling Tower Seismic Calcs.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-02-17 |  | 23 05 49-8.1 Cooling Tower Seismic Calcs.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-03 02:00 |  | 23 05 49-8.1 CT Seismic Calcs_ME_TT_POP.pdf
23 05 49-009-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-009-00 SCA - South Parcel Piping Seismic Calculations | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-17 | 2020-03-13 | 11 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-03-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04585 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 23 05 49-9.0 From: GRETCHEN TOSHACH Final Due Date: 04/08/20 Subject: SCA - SOUTH PARCEL PIPING SEISMIC CALCULATIONS Description: SEISMIC CALCULATIONS FOR THE SOUTH PARCEL MECHANICAL PIPING Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06321 | Forwarded | For Review | 2020-03-02 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-09 | Submittal Number: 23 05 49-9.0 From: GRETCHEN TOSHACH Final Due Date: 04/08/20 Subject: SCA - SOUTH PARCEL PIPING SEISMIC CALCULATIONS Description: SEISMIC CALCULATIONS FOR THE SOUTH PARCEL MECHANICAL PIPING Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06325 | Forwarded | For Review | 2020-03-02 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-09 | Submittal Number: 23 05 49-9.0 From: GRETCHEN TOSHACH Final Due Date: 04/08/20 Subject: SCA - SOUTH PARCEL PIPING SEISMIC CALCULATIONS Description: SEISMIC CALCULATIONS FOR THE SOUTH PARCEL MECHANICAL PIPING Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 04822 | Review Response | Approved as Noted/Resubmit | 2020-03-10 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | PROVIDE LOADS IMPOSED ON W12X26 AND W16X26 FOR TT REVIEW. GEOMETRY IS DIFFERENT FOR THIS CASE THAN THE TYPICAL CALC SHOWN ON PAGE 24. KB TT 3/10/2020 | Info Exchange
| 04824 | Review Response | No Action Taken or Required | 2020-03-13 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| 06601 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Samar Kenkre (Thornton Tomasetti) Remarks: PROVIDE LOADS IMPOSED ON W12X26 AND W16X26 FOR TT REVIEW. GEOMETRY IS DIFFERENT FOR THIS CASE THAN THE TYPICAL CALC SHOWN ON PAGE 24. KB TT 3/10/2020 Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: Structural engineer to review. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 23 05 49-9.0 S Parcel Seismic Calcs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 23 05 49-9.0 S Parcel Seismic Calcs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 23 05 49-9.0 S Parcel Seismic Calcs - MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-03-01 02:00 |  | 23 05 49-9.0 S Parcel Seismic Calcs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-01 02:00 |  | 23 05 49-9.0 S Parcel Seismic Calcs - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-13 02:00 |  | 23 05 49-9.0 S Parcel Seismic Calcs - MAM_TT_ME_POP.pdf
23 05 49-009-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-009-01 SCA - South Parcel Piping Seismic Calculations | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-30 | Responded and Closed - Rejected |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-14 | 2020-04-16 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-04-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05103 | Received | For Review | 2020-03-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-14 | Submittal Number: 23 05 49-9.1 From: GRETCHEN TOSHACH Final Due Date: 04/10/20 Subject: SCA - SOUTH PARCEL PIPING SEISMIC CALCULATIONS Description: SEISMIC CALCULATIONS FOR THE SOUTH PARCEL MECHANICAL PIPING - COMMENT ON PREVIOUS SUBMITTAL REQUESTED LOADS IMPOSED ON PAGE 33 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06931 | Forwarded | For Review | 2020-03-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-06 | Submittal Number: 23 05 49-9.1 From: GRETCHEN TOSHACH Final Due Date: 04/10/20 Subject: SCA - SOUTH PARCEL PIPING SEISMIC CALCULATIONS Description: SEISMIC CALCULATIONS FOR THE SOUTH PARCEL MECHANICAL PIPING - COMMENT ON PREVIOUS SUBMITTAL REQUESTED LOADS IMPOSED ON PAGE 33 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 05113 | Review Response | No Action Taken or Required | 2020-03-30 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.03.30 | Info Exchange
| 06941 | Forwarded | For Review | 2020-03-30 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-04-06 | Submittal Number: 23 05 49-9.1 From: GRETCHEN TOSHACH Final Due Date: 04/10/20 Subject: SCA - SOUTH PARCEL PIPING SEISMIC CALCULATIONS Description: SEISMIC CALCULATIONS FOR THE SOUTH PARCEL MECHANICAL PIPING - COMMENT ON PREVIOUS SUBMITTAL REQUESTED LOADS IMPOSED ON PAGE 33 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 05232 | Review Response | Not Required For Review | 2020-04-07 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.04.07 | Info Exchange
| 07121 | Forwarded | For Review | 2020-04-07 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean Mc... | 2020-04-13 | Submittal Number: 23 05 49-9.1 From: GRETCHEN TOSHACH Final Due Date: 04/10/20 Subject: SCA - SOUTH PARCEL PIPING SEISMIC CALCULATIONS Description: SEISMIC CALCULATIONS FOR THE SOUTH PARCEL MECHANICAL PIPING - COMMENT ON PREVIOUS SUBMITTAL REQUESTED LOADS IMPOSED ON PAGE 33 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 05400 | Review Response | Rejected | 2020-04-16 | Andy Tatkowski (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached. | Info Exchange
| 07332 | Responded and Closed | Rejected | 2020-04-16 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Not Required For Review) from: Nick Theimer (ME Engineers) Remarks: Structural engineer to review. Nick Theimer ME Engineers 2020.04.07 Response (Rejected) from: Andy Tatkowski (Thornton Tomasetti) Remarks: See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-27 |  | 23 05 49-9.1 S. Parcel Seismic Calcs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-27 |  | 23 05 49-9.1 S. Parcel Seismic Calcs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-26 02:00 |  | 23 05 49-9.1 S. Parcel Seismic Calcs - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-26 02:00 |  | 23 05 49-9.1 S. Parcel Seismic Calcs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-07 02:00 |  | 23 05 49-9.1 S. Parcel Seismic Calcs_ME.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-26 02:00 |  | 23 05 49-9.1 S. Parcel Seismic Calcs - MAM.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-04-17 02:00 |  | 23 05 49-9.1 S. Parcel Seismic Calcs - MAM_TT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-16 02:00 |  | 23 05 49-9.1 S. Parcel Seismic Calcs - MAM_TT_POP.pdf
23 05 49-009-02 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-009-02 SCA - South Parcel Piping Seismic Calculations | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-26 07:00 | 2020-05-22 | 12 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-05-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05805 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 23 05 49-9.2 From: GRETCHEN TOSHACH Final Due Date: 05/14/20 Subject: SCA - SOUTH PARCEL PIPING SEISMIC CALCULATIONS Description: SEISMIC CALCULATIONS FOR THE SOUTH PARCEL MECHANICAL PIPING - COMMENT ON PREVIOUS SUBMITTAL REQUESTED LOADS IMPOSED ON PAGE 33 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07869 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 23 05 49-9.2 From: GRETCHEN TOSHACH Final Due Date: 05/14/20 Subject: SCA - SOUTH PARCEL PIPING SEISMIC CALCULATIONS Description: SEISMIC CALCULATIONS FOR THE SOUTH PARCEL MECHANICAL PIPING - COMMENT ON PREVIOUS SUBMITTAL REQUESTED LOADS IMPOSED ON PAGE 33 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07881 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-18 | Submittal Number: 23 05 49-9.2 From: GRETCHEN TOSHACH Final Due Date: 05/14/20 Subject: SCA - SOUTH PARCEL PIPING SEISMIC CALCULATIONS Description: SEISMIC CALCULATIONS FOR THE SOUTH PARCEL MECHANICAL PIPING - COMMENT ON PREVIOUS SUBMITTAL REQUESTED LOADS IMPOSED ON PAGE 33 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 05996 | Review Response | No Action Taken or Required | 2020-05-19 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.05.19 | Info Exchange
| 05997 | Review Response | Approved as Noted | 2020-05-20 | Andy Tatkowski (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached. ART ¦ TT ¦ 5/20/2020 | Info Exchange
| 08134 | Responded and Closed | Approved as Noted | 2020-05-22 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.05.19 Response (Approved as Noted) from: Andy Tatkowski (Thornton Tomasetti) Remarks: See attached. ART ¦ TT ¦ 5/20/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 23 05 49-9.2 S Parcel Seismic Calcs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 23 05 49-9.2 S Parcel Seismic Calcs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 23 05 49-9.2 S Parcel Seismic Calcs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 23 05 49-9.2 S Parcel Seismic Calcs - MAM.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-05-20 02:00 |  | 23 05 49-9.2 S Parcel Seismic Calcs - MAM_TT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-22 02:00 |  | 23 05 49-9.2 S Parcel Seismic Calcs - MAM_TT_POP.pdf
23 05 49-010-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-010-00 100 Duct and M-Pipe Seismic Restraints | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-01 | 2020-06-01 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-06-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05806 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-01 | Submittal Number: 23 05 49-10.0 From: GRETCHEN TOSHACH Final Due Date: 04/30/20 Subject: 100 DUCT AND M-PIPE SEISMIC RESTRAINTS Description: SHEET METAL AND MECHANICAL PIPING SEISMIC CALCULATIONS FOR EVENT LEVEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07870 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 23 05 49-10.0 From: GRETCHEN TOSHACH Final Due Date: 04/30/20 Subject: 100 DUCT AND M-PIPE SEISMIC RESTRAINTS Description: SHEET METAL AND MECHANICAL PIPING SEISMIC CALCULATIONS FOR EVENT LEVEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07880 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-18 | Submittal Number: 23 05 49-10.0 From: GRETCHEN TOSHACH Final Due Date: 04/30/20 Subject: 100 DUCT AND M-PIPE SEISMIC RESTRAINTS Description: SHEET METAL AND MECHANICAL PIPING SEISMIC CALCULATIONS FOR EVENT LEVEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06136 | Review Response | Revise and Resubmit | 2020-05-28 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Refer to marked up submittal for comments and missing items. | Info Exchange
| 06137 | Review Response | Approved as Noted | 2020-06-01 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2020.06.01 | Info Exchange
| 08300 | Responded and Closed | Revise and Resubmit | 2020-06-01 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Refer to marked up submittal for comments and missing items. Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2020.06.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 23 05 49-10.0 100 Event Lvl Mech Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 23 05 49-10.0 100 Event Lvl Mech Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 23 05 49-10.0 100 Event Lvl Mech Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-10 02:00 |  | 23 05 49-10.0 100 Event Lvl Mech Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 23 05 49-10.0 100 Event Lvl Mech Seismic - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-01 02:00 |  | 23 05 49-10.0 100 Event Lvl Mech Seismic - MAM_TTReview_POP.pdf
23 05 49-010-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-010-01 100 Duct and M-Pipe Seismic Restraints | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-12 | 2020-10-12 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08374 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 23 05 49-10.1 From: GRETCHEN TOSHACH Final Due Date: 07/22/20 Subject: 100 DUCT AND M-PIPE SEISMIC RESTRAINTS Description: SHEET METAL AND MECHANICAL PIPING SEISMIC CALCULATIONS FOR EVENT LEVEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11094 | Forwarded | For Review | 2020-09-28 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-10-05 | Submittal Number: 23 05 49-10.1 From: GRETCHEN TOSHACH Final Due Date: 07/22/20 Subject: 100 DUCT AND M-PIPE SEISMIC RESTRAINTS Description: SHEET METAL AND MECHANICAL PIPING SEISMIC CALCULATIONS FOR EVENT LEVEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08412 | Review Response | Approved | 2020-09-28 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Structural engineer to review. Submit ductwork in separate submittal. Nick Theimer ME Engineers 2020.09.28 | Info Exchange
| 08724 | Review Response | Approved as Noted | 2020-10-12 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Refer to TT comments within submittal. Hermanson to address total MEP hung load per pdf page 16 comment. | Info Exchange
| 11526 | Responded and Closed | Approved as Noted | 2020-10-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Submit ductwork in separate submittal. Nick Theimer ME Engineers 2020.09.28 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Refer to TT comments within submittal. Hermanson to address total MEP hung load per pdf page 16 comment. | Info Exchange
| 11971 | Sent | For Information Only | 2020-10-28 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Submit ductwork in separate submittal. Nick Theimer ME Engineers 2020.09.28 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Refer to TT comments within submittal. Hermanson to address total MEP hung load per pdf page 16 comment. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-28 |  | 23 05 49-10.1 100 Event Lvl Mech Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-28 |  | 23 05 49-10.1 100 Event Lvl Mech Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-28 |  | 23 05 49-10.1 100 Event Lvl Mech Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-27 02:00 |  | 23 05 49-10.1 100 Event Lvl Mech Seismic - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-12 02:00 |  | 23 05 49-10.1 100 Event Lvl Mech Seismic - MAM_TT REVIEW_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-09-27 02:00 |  | 23 05 49-10.1 100 Event Lvl Mech Seismic - MAM.pdf
23 05 49-010-02 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-010-02 100 Duct and M-Pipe Seismic Restraints | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-05 | 2021-02-11 | 21 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10902 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-02-05 | Submittal Number: 23 05 49-10.2 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: 100 DUCT AND M-PIPE SEISMIC RESTRAINTS Description: SHEET METAL AND MECHANICAL PIPING SEISMIC CALCULATIONS FOR EVENT LEVEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 14156 | Forwarded | For Review | 2021-01-22 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2021-01-29 | Submittal Number: 23 05 49-10.2 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: 100 DUCT AND M-PIPE SEISMIC RESTRAINTS Description: SHEET METAL AND MECHANICAL PIPING SEISMIC CALCULATIONS FOR EVENT LEVEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11363 | Review Response | Approved | 2021-01-26 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.01.26 | Info Exchange
| 11364 | Review Response | Revise and Resubmit | 2021-02-08 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See comments on attachment. | Info Exchange
| 14722 | Responded and Closed | Revise and Resubmit | 2021-02-11 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.01.26 Response (Revise and Resubmit) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments on attachment. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-22 |  | 23 05 49-10.2 100 HVAC Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-22 |  | 23 05 49-10.2 100 HVAC Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-22 |  | 23 05 49-10.2 100 HVAC Seismic - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-01-22 |  | 23 05 49-10.2 100 HVAC Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-11 |  | 23 05 49-10.2 100 HVAC Seismic - ME_TT_POP.pdf
23 05 49-010-03 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-010-03 100 Duct and M-Pipe Seismic Restraints | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-20 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-04 07:00 | 2021-06-03 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13209 | Received | For Review | 2021-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-04 07:00 | Submittal Number: 23 05 49-10.3 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: 100 DUCT AND M-PIPE SEISMIC RESTRAINTS Description: SHEET METAL AND MECHANICAL PIPING SEISMIC CALCULATIONS FOR EVENT LEVEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 17098 | Forwarded | For Review | 2021-05-20 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (ME Engineers); Sean McNeill (Thornton T... | 2021-05-27 | Submittal Number: 23 05 49-10.3 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: 100 DUCT AND M-PIPE SEISMIC RESTRAINTS Description: SHEET METAL AND MECHANICAL PIPING SEISMIC CALCULATIONS FOR EVENT LEVEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13387 | Review Response | Approved | 2021-05-21 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers | Info Exchange
| 13389 | Review Response | Approved as Noted | 2021-05-28 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | No exceptions, see attached. | Info Exchange
| 17317 | Responded and Closed | Approved as Noted | 2021-06-03 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: No exceptions, see attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-19 |  | 23 05 49-10.3 100 SM MP Seismic - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-19 |  | 23 05 49-10.3 100 SM MP Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-18 02:00 |  | 23 05 49-10.3 100 SM MP Seismic - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-05-18 02:00 |  | 23 05 49-10.3 100 SM MP Seismic - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-03 02:00 |  | 23 05 49-10.3 100 SM MP Seismic - MAM_TT_ME_POP.pdf
23 05 49-011-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-011-00 Equipment Seismic Vibration Isolation | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-27 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-16 | 2020-06-15 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06057 | Received | For Review | 2020-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-16 | Submittal Number: 23 05 49-11.0 From: GRETCHEN TOSHACH Final Due Date: 06/22/20 Subject: EQUIPMENT SEISMIC VIBRATION ISOLATION Description: EQUIPMENT INCLUDED: AC 4F.01, DHC-2B.01, AS-1E.01,2,3 HX-1E.01, 02, 03 CH-1E.01, 02,03 ET-1E.01,02,03,04 AC-3F.01 H-1C.01 CU-3F.01, 4F.01, 4F.02 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08208 | Forwarded | For Review | 2020-05-27 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-03 | Submittal Number: 23 05 49-11.0 From: GRETCHEN TOSHACH Final Due Date: 06/22/20 Subject: EQUIPMENT SEISMIC VIBRATION ISOLATION Description: EQUIPMENT INCLUDED: AC 4F.01, DHC-2B.01, AS-1E.01,2,3 HX-1E.01, 02, 03 CH-1E.01, 02,03 ET-1E.01,02,03,04 AC-3F.01 H-1C.01 CU-3F.01, 4F.01, 4F.02 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06212 | Review Response | Approved | 2020-06-03 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2020.06.03 | Info Exchange
| 08392 | Forwarded | For Review | 2020-06-04 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean Mc... | 2020-06-10 | Submittal Number: 23 05 49-11.0 From: GRETCHEN TOSHACH Final Due Date: 06/22/20 Subject: EQUIPMENT SEISMIC VIBRATION ISOLATION Description: EQUIPMENT INCLUDED: AC 4F.01, DHC-2B.01, AS-1E.01,2,3 HX-1E.01, 02, 03 CH-1E.01, 02,03 ET-1E.01,02,03,04 AC-3F.01 H-1C.01 CU-3F.01, 4F.01, 4F.02 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06401 | Review Response | Approved as Noted | 2020-06-15 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Exceptions Noted. Do not need to resubmit. | Info Exchange
| 08618 | Responded and Closed | Approved as Noted | 2020-06-15 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Exceptions Noted. Do not need to resubmit. Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2020.06.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-27 |  | 23 05 49-11.0 Seis_VibIso Wet Side Equip - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-27 |  | 23 05 49-11.0 Seis_VibIso Wet Side Equip - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-26 02:00 |  | 23 05 49-11.0 Seis_VibIso Wet Side Equip - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-26 02:00 |  | 23 05 49-11.0 Seis_VibIso Wet Side Equip - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-26 02:00 |  | 23 05 49-11.0 Seis_VibIso Wet Side Equip - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-15 02:00 |  | 23 05 49-11.0 Seis_VibIso Wet Side Equip_ME_TT REVIEW_POP.pdf
23 05 49-011-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-011-01 Equipment Seismic Vibration Isolation | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-14 | 2020-10-11 | 12 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-10-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08438 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-14 | Submittal Number: 23 05 49-11.1 From: GRETCHEN TOSHACH Final Due Date: 10/14/20 Subject: EQUIPMENT SEISMIC VIBRATION ISOLATION Description: EQUIPMENT INCLUDED: AC 4F.01, DHC-2B.01, AS-1E.01,2,3 HX-1E.01, 02, 03 CH-1E.01, 02,03 ET-1E.01,02,03,04 AC-3F.01 H-1C.01 CU-3F.01, 4F.01, 4F.02 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11179 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-10-07 | Submittal Number: 23 05 49-11.1 From: GRETCHEN TOSHACH Final Due Date: 10/14/20 Subject: EQUIPMENT SEISMIC VIBRATION ISOLATION Description: EQUIPMENT INCLUDED: AC 4F.01, DHC-2B.01, AS-1E.01,2,3 HX-1E.01, 02, 03 CH-1E.01, 02,03 ET-1E.01,02,03,04 AC-3F.01 H-1C.01 CU-3F.01, 4F.01, 4F.02 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08555 | Review Response | Approved | 2020-10-01 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.10.01 | Info Exchange
| 08701 | Review Response | Approved as Noted | 2020-10-09 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Please address previous comment from Rev 0. Do not need to resubmit. | Info Exchange
| 11492 | Responded and Closed | Approved as Noted | 2020-10-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.10.01 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Please address previous comment from Rev 0. Do not need to resubmit. | Info Exchange
| 11973 | Sent | For Information Only | 2020-10-28 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.10.01 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Please address previous comment from Rev 0. Do not need to resubmit. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 23 05 49-11.1 Seis_VibIso Wet Side Equip - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 23 05 49-11.1 Seis_VibIso Wet Side Equip - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-30 |  | 23 05 49-11.1 Seis_VibIso Wet Side Equip - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-29 02:00 |  | 23 05 49-11.1 Seis_VibIso Wet Side Equip - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-11 02:00 |  | 23 05 49-11.1 Seis_VibIso Wet Side Equip - MAM_TT REVIEW_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-09-29 02:00 |  | 23 05 49-11.1 Seis_VibIso Wet Side Equip - MAM.pdf
23 05 49-012-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-012-00 Seismic Vibration Isolation Calculations | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-26 07:00 | 2020-06-03 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05807 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 23 05 49-12.0 From: GRETCHEN TOSHACH Final Due Date: 05/22/20 Subject: SEISMIC VIBRATION ISOLATION CALCULATIONS Description: EQUIPMENT LIST INCLUDED: CWP-1E.01, 02,03,04 HWP-1E.01,02,03 HX-1E.02,03 CH-1E.01,02,03 ET-1E.01,02,03,04 AC-3F.01 H-1C.01 CE-3F.01, 4F.01, 4F.02 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07871 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 23 05 49-12.0 From: GRETCHEN TOSHACH Final Due Date: 05/22/20 Subject: SEISMIC VIBRATION ISOLATION CALCULATIONS Description: EQUIPMENT LIST INCLUDED: CWP-1E.01, 02,03,04 HWP-1E.01,02,03 HX-1E.02,03 CH-1E.01,02,03 ET-1E.01,02,03,04 AC-3F.01 H-1C.01 CE-3F.01, 4F.01, 4F.02 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07879 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-18 | Submittal Number: 23 05 49-12.0 From: GRETCHEN TOSHACH Final Due Date: 05/22/20 Subject: SEISMIC VIBRATION ISOLATION CALCULATIONS Description: EQUIPMENT LIST INCLUDED: CWP-1E.01, 02,03,04 HWP-1E.01,02,03 HX-1E.02,03 CH-1E.01,02,03 ET-1E.01,02,03,04 AC-3F.01 H-1C.01 CE-3F.01, 4F.01, 4F.02 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06040 | Review Response | Approved as Noted | 2020-05-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2020.05.22 | Info Exchange
| 06041 | Review Response | Approved as Noted | 2020-05-26 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Provide Locations of equipment to review loads imposed for record. | Info Exchange
| 08187 | Responded and Closed | Approved as Noted | 2020-05-26 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2020.05.22 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Provide Locations of equipment to review loads imposed for record. | Info Exchange
| 08325 | Reopened | Additional Information | 2020-06-02 14:28 | Josh Dobken (Populous) |  |  | Reopened for revised response from TT.
| 08332 | Forwarded | For Review | 2020-06-02 | Josh Dobken (Populous) | Matt Ross (Thornton Tomasetti) | 2020-05-26 | Submittal Number: 23 05 49-12.0 From: GRETCHEN TOSHACH Final Due Date: 05/22/20 Subject: SEISMIC VIBRATION ISOLATION CALCULATIONS Description: EQUIPMENT LIST INCLUDED: CWP-1E.01, 02,03,04 HWP-1E.01,02,03 HX-1E.02,03 CH-1E.01,02,03 ET-1E.01,02,03,04 AC-3F.01 H-1C.01 CE-3F.01, 4F.01, 4F.02 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06166 | Review Response | Approved | 2020-06-03 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 08339 | Responded and Closed | Approved | 2020-06-03 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | See revised response from TT. ME comments remain the same. Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Reopened (Additional Information) by: Josh Dobken Remarks: Reopened for revised response from TT. Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Provide Locations of equipment to review loads imposed for record. Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2020.05.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 23 05 49-12.0 Seis_VibIso Wet Side Equip 2 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 23 05 49-12.0 Seis_VibIso Wet Side Equip 2 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 23 05 49-12.0 Seis_VibIso Wet Side Equip 2 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 23 05 49-12.0 Seis_VibIso Wet Side Equip 2 - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-10 02:00 |  | 23 05 49-12.0 Seis_VibIso Wet Side Equip 2 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-26 02:00 |  | 23 05 49-12.0 Seis_VibIso Wet Side Equip 2 - MAM_TT REVIEW_POP.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-10 02:00 |  | 23 05 49-12.0 Seis_VibIso Wet Side Equip 2 - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-10 02:00 |  | 23 05 49-12.0 Seis_VibIso Wet Side Equip 2 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-22 02:00 |  | 23 05 49-12.0 Seis_VibIso Wet Side Equip 2_ME.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-03 02:00 |  | 23 05 49-12.0 Seis_VibIso Wet Side Equip 2 - MAM_TT REVIEW_revised_POP.pdf
23 05 49-012-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-012-01 Seismic Vibration Isolation Calculations | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-14 | 2020-10-11 | 12 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-10-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08454 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-14 | Submittal Number: 23 05 49-12.1 From: GRETCHEN TOSHACH Final Due Date: 10/14/20 Subject: SEISMIC VIBRATION ISOLATION CALCULATIONS Description: EQUIPMENT LIST INCLUDED: CWP-1E.01, 02,03,04 HWP-1E.01,02,03 HX-1E.02,03 CH-1E.01,02,03 ET-1E.01,02,03,04 AC-3F.01 H-1C.01 CE-3F.01, 4F.01, 4F.02 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11195 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-10-07 | Submittal Number: 23 05 49-12.1 From: GRETCHEN TOSHACH Final Due Date: 10/14/20 Subject: SEISMIC VIBRATION ISOLATION CALCULATIONS Description: EQUIPMENT LIST INCLUDED: CWP-1E.01, 02,03,04 HWP-1E.01,02,03 HX-1E.02,03 CH-1E.01,02,03 ET-1E.01,02,03,04 AC-3F.01 H-1C.01 CE-3F.01, 4F.01, 4F.02 Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08554 | Review Response | Approved | 2020-10-01 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.10.01 | Info Exchange
| 08702 | Review Response | Approved | 2020-10-09 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 11493 | Responded and Closed | Approved | 2020-10-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.10.01 Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| 11972 | Sent | For Information Only | 2020-10-28 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.10.01 Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 23 05 49-12.1 Seis_VibIso Wet Side Equip 2 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 23 05 49-12.1 Seis_VibIso Wet Side Equip 2 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-30 |  | 23 05 49-12.1 Seis_VibIso Wet Side Equip 2 - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-29 02:00 |  | 23 05 49-12.1 Seis_VibIso Wet Side Equip 2 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-11 02:00 |  | 23 05 49-12.1 Seis_VibIso Wet Side Equip 2 - MAM_TT REVIEW_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-09-29 02:00 |  | 23 05 49-12.1 Seis_VibIso Wet Side Equip 2 - MAM.pdf
23 05 49-013-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-013-00 Seismic Restraints - Exhaust Fans and PCUs | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-26 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-09 | 2020-06-15 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06023 | Received | For Review | 2020-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-09 | Submittal Number: 23 05 49-13.0 From: SIMRAN GEORGE Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - EXHAUST FANS AND PCUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08167 | Forwarded | For Review | 2020-05-26 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-02 | Submittal Number: 23 05 49-13.0 From: SIMRAN GEORGE Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - EXHAUST FANS AND PCUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06238 | Review Response | Revise and Resubmit | 2020-06-04 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2020.06.04 | Info Exchange
| 08383 | Forwarded | For Review | 2020-06-04 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean Mc... | 2020-06-09 | Submittal Number: 23 05 49-13.0 From: SIMRAN GEORGE Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - EXHAUST FANS AND PCUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06413 | Review Response | Approved as Noted | 2020-06-15 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Exceptions noted. Do not need to resubmit. | Info Exchange
| 08639 | Responded and Closed | Revise and Resubmit | 2020-06-15 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Resubmit per ME comments. -jhd/POP Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Exceptions noted. Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2020.06.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-26 |  | 23 05 49-13.0 Seis_VibIso PCUs_EFs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-26 |  | 23 05 49-13.0 Seis_VibIso PCUs_EFs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-25 02:00 |  | 23 05 49-13.0 Seis_VibIso PCUs_EFs - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-25 02:00 |  | 23 05 49-13.0 Seis_VibIso PCUs_EFs - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-25 02:00 |  | 23 05 49-13.0 Seis_VibIso PCUs_EFs - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-15 02:00 |  | 23 05 49-13.0 Seis_VibIso PCUs_EFs_ME_TT REVIEW_pop.pdf
23 05 49-013-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-013-01 Seismic Restraints - Exhaust Fans and PCUs | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Brian Elwell (Idibri), Raymond Chou (Thornton Tomasetti) |  |  |  | 2020-12-03 | 2020-12-01 | 15 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09500 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-03 | Submittal Number: 23 05 49-13.1 From: GRETCHEN TOSHACH Final Due Date: 12/01/20 Subject: SEISMIC RESTRAINTS - EXHAUST FANS AND PCUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 12521 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... |  | Submittal Number: 23 05 49-13.1 From: GRETCHEN TOSHACH Final Due Date: 12/01/20 Subject: SEISMIC RESTRAINTS - EXHAUST FANS AND PCUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09559 | Review Response | Approved | 2020-11-18 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.11.18 | Info Exchange
| 12582 | Forwarded | For Review | 2020-11-18 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian Elwell (Idibri); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thor... | 2020-11-25 | Submittal Number: 23 05 49-13.1 From: GRETCHEN TOSHACH Final Due Date: 12/01/20 Subject: SEISMIC RESTRAINTS - EXHAUST FANS AND PCUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09778 | Review Response | No Action Taken or Required | 2020-11-19 | Brian Elwell (Idibri) | Josh Dobken (Populous) |  | Per Josh, this was sent to Idibri accidentally. | Info Exchange
| 09779 | Review Response | Approved as Noted | 2020-11-24 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 12860 | Responded and Closed | Approved as Noted | 2020-12-01 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.11.18 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | 23 05 49-13.1 Seis_VibIso PCUs_EFs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-17 |  | 23 05 49-13.1 Seis_VibIso PCUs_EFs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-19 02:00 |  | 23 05 49-13.1 Seis_VibIso PCUs_EFs_ME.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-11-16 02:00 |  | 23 05 49-13.1 Seis_VibIso PCUs_EFs - MAM.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-11-16 02:00 |  | 23 05 49-13.1 Seis_VibIso PCUs_EFs - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-16 02:00 |  | 23 05 49-13.1 Seis_VibIso PCUs_EFs - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-01 02:00 |  | 23 05 49-13.1 Seis_VibIso PCUs_EFs - MAM_TT_ME_POP.pdf
23 05 49-014-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-014-00 Seismic Restraints - Electric Unit Heaters and Air Curtains | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-21 | 2020-07-21 | 15 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06809 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 23 05 49-14.0 From: SIMRAN GEORGE Final Due Date: 07/20/20 Subject: SEISMIC RESTRAINTS - ELECTRIC UNIT HEATERS AND AIR CURTAINS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09143 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 23 05 49-14.0 From: SIMRAN GEORGE Final Due Date: 07/20/20 Subject: SEISMIC RESTRAINTS - ELECTRIC UNIT HEATERS AND AIR CURTAINS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09275 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-20 | Submittal Number: 23 05 49-14.0 From: SIMRAN GEORGE Final Due Date: 07/20/20 Subject: SEISMIC RESTRAINTS - ELECTRIC UNIT HEATERS AND AIR CURTAINS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07054 | Review Response | Revise and Resubmit | 2020-07-14 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Revise calcs for Seismic Design Category D as noted in General Notes. | Info Exchange
| 07081 | Review Response | Approved | 2020-07-14 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| 09442 | Responded and Closed | Revise and Resubmit | 2020-07-21 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Revise calcs for Seismic Design Category D as noted in General Notes. Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 23 05 49-14.0 AUH and AC Seim Restr and Vib Iso - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 23 05 49-14.0 AUH and AC Seim Restr and Vib Iso - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 23 05 49-14.0 AUH and AC Seim Restr and Vib Iso - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-06 |  | 23 05 49-14.0 AUH and AC Seim Restr and Vib Iso - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-05 02:00 |  | 23 05 49-14.0 AUH and AC Seim Restr and Vib Iso - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-21 |  | 23 05 49-14.0 AUH and AC Seim Restr and Vib Iso - TT_ME_POP.pdf
23 05 49-014-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-014-01 Seismic Restraints - Electric Unit Heaters and Air Curtains | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-16 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Matt Ross (Thornton Tomasetti), Heidi Evans (ME Engineers) |  |  |  | 2020-09-30 | 2020-09-25 | 10 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-09-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08210 | Received | For Review | 2020-09-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-30 |  | Email
| 10900 | Forwarded | For Review | 2020-09-18 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Matt Ross (Thornton Tomasetti); Heidi Evans (ME Engineers) | 2020-09-25 |  | Info Exchange
| 08254 | Review Response | Approved | 2020-09-21 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.09.21 | Info Exchange
| 08346 | Review Response | Approved | 2020-09-24 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 11058 | Responded and Closed | Approved | 2020-09-25 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.09.21 Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| 11761 | Sent | For Information Only | 2020-10-21 | Populous SCA_CCA | Tyrone Thornton (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.09.21 Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-18 02:00 |  | 23 05 4914.1 Seis_VibIso Htrs_AirCurtains - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-18 02:00 |  | 23 05 4914.1 Seis_VibIso Htrs_AirCurtains - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-18 |  | 23 05 4914.1 Seis_VibIso Htrs_AirCurtains - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-18 02:00 |  | 23 05 4914.1 Seis_VibIso Htrs_AirCurtains - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-25 02:00 |  | 23 05 49-14.1 AUH and AC Seim Restr and Vib Iso_combined.pdf
| Sent |  | Populous SCA_CCA | 1 | 2020-09-18 02:00 |  | 23 05 4914.1 Seis_VibIso Htrs_AirCurtains - MAM.pdf
23 05 49-015-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-015-00 Seismic Restraints - FCUs, VAVs, and EAVs | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-27 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-10 | 2020-06-15 | 20 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06022 | Received | For Review | 2020-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-10 | Submittal Number: 23 05 49-15.0 From: SIMRAN GEORGE Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - FCUS, VAVS, AND EAVS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08166 | Forwarded | For Review | 2020-05-26 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-02 | Submittal Number: 23 05 49-15.0 From: SIMRAN GEORGE Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - FCUS, VAVS, AND EAVS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06211 | Review Response | Approved | 2020-06-04 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.06.04 | Info Exchange
| 08391 | Forwarded | For Review | 2020-06-04 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean Mc... | 2020-06-10 | Submittal Number: 23 05 49-15.0 From: SIMRAN GEORGE Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - FCUS, VAVS, AND EAVS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06412 | Review Response | Revise and Resubmit | 2020-06-15 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Revise calcs assuming Seismic Design Category D as noted in general notes. | Info Exchange
| 08638 | Responded and Closed | Revise and Resubmit | 2020-06-15 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Revise calcs assuming Seismic Design Category D as noted in general notes. Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.06.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-26 |  | 23 05 49-15.0 Seis_VibIso FCUVAVEAV - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-26 |  | 23 05 49-15.0 Seis_VibIso FCUVAVEAV - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-25 02:00 |  | 23 05 49-15.0 Seis_VibIso FCUVAVEAV - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-25 02:00 |  | 23 05 49-15.0 Seis_VibIso FCUVAVEAV - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-25 02:00 |  | 23 05 49-15.0 Seis_VibIso FCUVAVEAV - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-15 02:00 |  | 23 05 49-15.0 Seis_VibIso FCUVAVEAV_ME_TT REVIEW_POP.pdf
23 05 49-015-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-015-01 Seismic Restraints - FCUs, VAVs, and EAVs | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-21 | 2020-07-21 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06821 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 23 05 49-15.1 From: GRETCHEN TOSHACH Final Due Date: 07/22/20 Subject: SEISMIC RESTRAINTS - FCUS, VAVS, AND EAVS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09156 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 23 05 49-15.1 From: GRETCHEN TOSHACH Final Due Date: 07/22/20 Subject: SEISMIC RESTRAINTS - FCUS, VAVS, AND EAVS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09274 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-20 | Submittal Number: 23 05 49-15.1 From: GRETCHEN TOSHACH Final Due Date: 07/22/20 Subject: SEISMIC RESTRAINTS - FCUS, VAVS, AND EAVS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07053 | Review Response | Approved | 2020-07-14 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 07082 | Review Response | Approved | 2020-07-15 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.07.15 | Info Exchange
| 09441 | Responded and Closed | Approved | 2020-07-21 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-07 |  | 23 05 49 15.1 Seis VibIso FCUVAVEAV - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 23 05 49 15.1 Seis VibIso FCUVAVEAV - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 23 05 49 15.1 Seis VibIso FCUVAVEAV - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-07 |  | 23 05 49 15.1 Seis VibIso FCUVAVEAV - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-06 02:00 |  | 23 05 49 15.1 Seis VibIso FCUVAVEAV - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-21 |  | 23 05 49 15.1 Seis VibIso FCUVAVEAV - TT_ME_POP.pdf
23 05 49-016-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-016-00 Seismic Restraints - AHUs/DAHUs/ERVs/MAUs | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-26 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-15 | 2020-06-15 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06024 | Received | For Review | 2020-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-15 | Submittal Number: 23 05 49-16.0 From: SIMRAN GEORGE Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - AHUS/DAHUS/ERVS/MAUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08168 | Forwarded | For Review | 2020-05-26 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-02 | Submittal Number: 23 05 49-16.0 From: SIMRAN GEORGE Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - AHUS/DAHUS/ERVS/MAUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06205 | Review Response | Revise and Resubmit | 2020-06-04 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.06.04 | Info Exchange
| 08386 | Forwarded | For Review | 2020-06-04 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean Mc... | 2020-06-09 | Submittal Number: 23 05 49-16.0 From: SIMRAN GEORGE Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - AHUS/DAHUS/ERVS/MAUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06400 | Review Response | Approved as Noted/Resubmit | 2020-06-15 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 08617 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-15 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.06.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-26 |  | 23 05 49-16.0 Seis_VibIso AHUs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-26 |  | 23 05 49-16.0 Seis_VibIso AHUs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-25 02:00 |  | 23 05 49-16.0 Seis_VibIso AHUs - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-25 02:00 |  | 23 05 49-16.0 Seis_VibIso AHUs - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-25 02:00 |  | 23 05 49-16.0 Seis_VibIso AHUs - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-15 02:00 |  | 23 05 49-16.0 Seis_VibIso AHUs_ME_TT REVIEW_POP.pdf
23 05 49-016-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-016-01 Seismic Restraints - AHUs/DAHUs/ERVs/MAUs | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-21 | 2020-07-21 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06822 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 23 05 49-16.1 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: SEISMIC RESTRAINTS - AHUS/DAHUS/ERVS/MAUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09157 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 23 05 49-16.1 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: SEISMIC RESTRAINTS - AHUS/DAHUS/ERVS/MAUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09273 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-20 | Submittal Number: 23 05 49-16.1 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: SEISMIC RESTRAINTS - AHUS/DAHUS/ERVS/MAUS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07051 | Review Response | Approved | 2020-07-14 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 07083 | Review Response | Approved as Noted | 2020-07-15 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.07.15 | Info Exchange
| 09439 | Responded and Closed | Approved as Noted | 2020-07-21 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-07 |  | 23 05 49-16.1 Seis VibIso AHUs DAHU ERV MAU - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 23 05 49-16.1 Seis VibIso AHUs DAHU ERV MAU - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 23 05 49-16.1 Seis VibIso AHUs DAHU ERV MAU - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-07 |  | 23 05 49-16.1 Seis VibIso AHUs DAHU ERV MAU - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-06 02:00 |  | 23 05 49-16.1 Seis VibIso AHUs DAHU ERV MAU - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-21 |  | 23 05 49-16.1 Seis VibIso AHUs DAHU ERV MAU - MAM_TT_ME_POP.pdf
23 05 49-016-02 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-016-02 Seismic Restraints - AHUs/DAHUs/ERVs/MAUs | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-11 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-25 | 2020-09-21 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08045 | Received | For Review | 2020-09-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-09-25 | Submittal Number: 23 05 49-16.2 From: GRETCHEN TOSHACH Final Due Date: 09/18/20 Subject: SEISMIC RESTRAINTS - AHUS/DAHUS/ERVS/MAUS Description: THIS HAS THE UNITS WITH THE SUSPENDED FRAMES, ERV CHANGE TO REFLECT SCREWS VS WELDS FOR THE CLIPS AND THE DAHU THAT IS WELDING TO STEEL. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 10710 | Forwarded | For Review | 2020-09-11 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-09-18 | Submittal Number: 23 05 49-16.2 From: GRETCHEN TOSHACH Final Due Date: 09/18/20 Subject: SEISMIC RESTRAINTS - AHUS/DAHUS/ERVS/MAUS Description: THIS HAS THE UNITS WITH THE SUSPENDED FRAMES, ERV CHANGE TO REFLECT SCREWS VS WELDS FOR THE CLIPS AND THE DAHU THAT IS WELDING TO STEEL. Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08218 | Review Response | Approved | 2020-09-15 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.09.15 | Info Exchange
| 08219 | Review Response | Approved as Noted | 2020-09-18 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 10909 | Responded and Closed | Approved as Noted | 2020-09-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.09.15 Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-11 |  | 23 05 49-16.2 Seis_VibIso AHUs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-11 |  | 23 05 49-16.2 Seis_VibIso AHUs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-10 02:00 |  | 23 05 49-16.2 Seis_VibIso AHUs - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-09-10 02:00 |  | 23 05 49-16.2 Seis_VibIso AHUs - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-21 02:00 |  | 23 05 49-16.2 Seis_VibIso AHUs - MAM_TT-REVIEW_POP.pdf
23 05 49-016-03 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-016-03 Seismic Restraints - CRAC units | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-22 08:00 | 2021-01-20 | 14 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10509 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (Mortenson Construction) | 2021-01-22 08:00 | Submittal Number: 23 05 49-16.3 From: GRETCHEN TOSHACH Final Due Date: 01/20/21 Subject: SEISMIC RESTRAINTS - CRAC UNITS Description: UPDATED CRAC UNITS ONLY - SUBMITTING WITHOUT HOUSEKEEPING PADS Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13712 | Forwarded | For Review | 2021-01-07 | Gretchen Toshach (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2021-01-14 | Submittal Number: 23 05 49-16.3 From: GRETCHEN TOSHACH Final Due Date: 01/20/21 Subject: SEISMIC RESTRAINTS - CRAC UNITS Description: UPDATED CRAC UNITS ONLY - SUBMITTING WITHOUT HOUSEKEEPING PADS Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 10829 | Review Response | Approved | 2021-01-07 | Matt Ross (Thornton Tomasetti) | Gretchen Toshach (Mortenson Construction) |  | TT has no exceptions. | Info Exchange
| 10830 | Review Response | Approved as Noted | 2021-01-07 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.01.07 | Info Exchange
| 14077 | Responded and Closed | Approved as Noted | 2021-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.01.07 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-06 |  | 23 05 49-16.3 CRAC Units Seis_VibIso - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-01-06 |  | 23 05 49-16.3 CRAC Units Seis_VibIso - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-05 02:00 |  | 23 05 49-16.3 CRAC Units Seis_VibIso - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-05 02:00 |  | 23 05 49-16.3 CRAC Units Seis_VibIso - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-20 02:00 |  | 23 05 49-16.3 CRAC Units Seis_VibIso_ME_TT_POP.pdf
23 05 49-017-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-017-00 Seismic Restraints - WSHPs | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-26 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-09 | 2020-06-15 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06025 | Received | For Review | 2020-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-09 | Submittal Number: 23 05 49-17.0 From: GRETCHEN TOSHACH Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - WSHPS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08169 | Forwarded | For Review | 2020-05-26 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-02 | Submittal Number: 23 05 49-17.0 From: GRETCHEN TOSHACH Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - WSHPS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06207 | Review Response | Approved | 2020-06-04 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2020.06.04 | Info Exchange
| 08387 | Forwarded | For Review | 2020-06-04 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean Mc... | 2020-06-09 | Submittal Number: 23 05 49-17.0 From: GRETCHEN TOSHACH Final Due Date: 06/25/20 Subject: SEISMIC RESTRAINTS - WSHPS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06402 | Review Response | Approved as Noted | 2020-06-15 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Exceptions noted. Do not need to resubmit. | Info Exchange
| 08619 | Responded and Closed | Approved as Noted | 2020-06-15 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Exceptions noted. Do not need to resubmit. Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2020.06.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-26 |  | 23 05 49-17.0 Seis_VibIso WSHPs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-26 |  | 23 05 49-17.0 Seis_VibIso WSHPs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-25 02:00 |  | 23 05 49-17.0 Seis_VibIso WSHPs - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-25 02:00 |  | 23 05 49-17.0 Seis_VibIso WSHPs - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-25 02:00 |  | 23 05 49-17.0 Seis_VibIso WSHPs - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-15 02:00 |  | 23 05 49-17.0 Seis_VibIso WSHPs_ME_TT REVIEW_pop.pdf
23 05 49-018-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-018-00 Seismic Restraints - Riser Supports Ductwork | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-17 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-01 | 2020-06-18 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06459 | Received | For Review | 2020-06-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-01 | Submittal Number: 23 05 49-18.0 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: SEISMIC RESTRAINTS - RISER SUPPORTS DUCTWORK Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08708 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-24 | Submittal Number: 23 05 49-18.0 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: SEISMIC RESTRAINTS - RISER SUPPORTS DUCTWORK Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08726 | Forwarded | For Review | 2020-06-17 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2020-06-24 | Submittal Number: 23 05 49-18.0 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: SEISMIC RESTRAINTS - RISER SUPPORTS DUCTWORK Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06492 | Review Response | Revise and Resubmit | 2020-06-18 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Refer to comments in submittal. Missing calcs. | Info Exchange
| 08744 | Responded and Closed | Revise and Resubmit | 2020-06-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Refer to comments in submittal. Missing calcs. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 23 05 49-18.0 SM Riser NWE Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 23 05 49-18.0 SM Riser NWE Seismic - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-16 02:00 |  | 23 05 49-18.0 SM Riser NWE Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-16 02:00 |  | 23 05 49-18.0 SM Riser NWE Seismic - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-18 02:00 |  | 23 05 49-18.0 SM Riser NWE Seismic - MAM_TT REVIEW_POP.pdf
23 05 49-018-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-018-01 Seismic Restraints - Riser Supports Ductwork | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-21 | 2020-07-21 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06798 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 23 05 49-18.1 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: SEISMIC RESTRAINTS - RISER SUPPORTS DUCTWORK Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09133 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-13 | Submittal Number: 23 05 49-18.1 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: SEISMIC RESTRAINTS - RISER SUPPORTS DUCTWORK Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09272 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-20 | Submittal Number: 23 05 49-18.1 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: SEISMIC RESTRAINTS - RISER SUPPORTS DUCTWORK Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07049 | Review Response | Approved as Noted | 2020-07-14 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 07084 | Review Response | Approved as Noted | 2020-07-14 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| 09437 | Responded and Closed | Approved as Noted | 2020-07-21 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Pending response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 23 05 49-18.1 SM Riser NWE Seismic MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 23 05 49-18.1 SM Riser NWE Seismic MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 23 05 49-18.1 SM Riser NWE Seismic MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-06 |  | 23 05 49-18.1 SM Riser NWE Seismic MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-05 02:00 |  | 23 05 49-18.1 SM Riser NWE Seismic MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-21 |  | 23 05 49-18.1 SM Riser NWE Seismic MAM_TT_ME_POP.pdf
23 05 49-018-02 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-018-02 Seismic Restraints - Riser Supports Ductwork | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-22 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-05 | 2021-02-02 | 12 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-02-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10908 | Received | For Review | 2021-01-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-02-05 | Submittal Number: 23 05 49-18.2 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: SEISMIC RESTRAINTS - RISER SUPPORTS DUCTWORK Description: RESUBMIT TO ADDRESS MEENGINEERS COMMENT Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 14162 | Forwarded | For Review | 2021-01-22 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2021-01-29 | Submittal Number: 23 05 49-18.2 From: GRETCHEN TOSHACH Final Due Date: 02/05/21 Subject: SEISMIC RESTRAINTS - RISER SUPPORTS DUCTWORK Description: RESUBMIT TO ADDRESS MEENGINEERS COMMENT Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11127 | Review Response | Approved | 2021-01-26 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.01.26 | Info Exchange
| 11151 | Review Response | Approved as Noted | 2021-02-01 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Confirm previous comments have been addressed. | Info Exchange
| 14438 | Responded and Closed | Approved as Noted | 2021-02-02 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.01.26 Pending response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Confirm previous comments have been addressed. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-22 |  | 23 05 49-18.2 SW Shaft Risers Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-22 |  | 23 05 49-18.2 SW Shaft Risers Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-22 |  | 23 05 49-18.2 SW Shaft Risers Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-21 02:00 |  | 23 05 49-18.2 SW Shaft Risers Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-02 |  | 23 05 49-18.2 SW Shaft Risers Seismic - ME_TT_POP.pdf
23 05 49-018-03 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-018-03 Seismic Restraints - Riser Supports Ductwork | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-20 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-04 07:00 | 2021-05-25 | 6 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-05-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13210 | Received | For Review | 2021-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (Mortenson Construction) | 2021-06-04 07:00 | Submittal Number: 23 05 49-18.3 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: SEISMIC RESTRAINTS - RISER SUPPORTS DUCTWORK Description: RESUBMIT TO ADDRESS MEENGINEERS COMMENT Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 17099 | Forwarded | For Review | 2021-05-20 | Gretchen Toshach (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (ME Engineers); Sean McNeill (Thornton T... | 2021-05-27 | Submittal Number: 23 05 49-18.3 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: SEISMIC RESTRAINTS - RISER SUPPORTS DUCTWORK Description: RESUBMIT TO ADDRESS MEENGINEERS COMMENT Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13263 | Review Response | Approved | 2021-05-21 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.05.21 | Info Exchange
| 13264 | Review Response | Approved | 2021-05-24 | Matt Ross (Thornton Tomasetti) | Gretchen Toshach (Mortenson Construction) |  | TT has no exceptions. | Info Exchange
| 17160 | Responded and Closed | Approved | 2021-05-25 | Gretchen Toshach (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-19 |  | 23 05 49-18.3 SW Shaft Risers Seismic - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-05-19 |  | 23 05 49-18.3 SW Shaft Risers Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-19 |  | 23 05 49-18.3 SW Shaft Risers Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-19 |  | 23 05 49-18.3 SW Shaft Risers Seismic - MAM.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-05-25 |  | 23 05 49-18.3 SW Shaft Risers Seismic - MAM_TT_POP.pdf
23 05 49-019-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-019-00 Seismic Restraints - 200 Mech Mezz Ductwork | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-17 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-01 | 2020-06-29 | 13 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-06-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06455 | Received | For Review | 2020-06-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-01 | Submittal Number: 23 05 49-19.0 From: GRETCHEN TOSHACH Final Due Date: 07/10/20 Subject: SEISMIC RESTRAINTS - 200 MECH MEZZ DUCTWORK Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08705 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-24 | Submittal Number: 23 05 49-19.0 From: GRETCHEN TOSHACH Final Due Date: 07/10/20 Subject: SEISMIC RESTRAINTS - 200 MECH MEZZ DUCTWORK Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08727 | Forwarded | For Review | 2020-06-17 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2020-06-24 | Submittal Number: 23 05 49-19.0 From: GRETCHEN TOSHACH Final Due Date: 07/10/20 Subject: SEISMIC RESTRAINTS - 200 MECH MEZZ DUCTWORK Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06660 | Review Response | Approved | 2020-06-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Structural engineer to review, Nick Theimer ME Engineers 2020.06.22 | Info Exchange
| 06661 | Review Response | Approved as Noted | 2020-06-26 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 08963 | Responded and Closed | Approved as Noted | 2020-06-29 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review, Nick Theimer ME Engineers 2020.06.22 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 23 05 49-19.0 Mezz Lvl Duct HVAC Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 23 05 49-19.0 Mezz Lvl Duct HVAC Seismic - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-16 02:00 |  | 23 05 49-19.0 Mezz Lvl Duct HVAC Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-16 02:00 |  | 23 05 49-19.0 Mezz Lvl Duct HVAC Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-16 02:00 |  | 23 05 49-19.0 Mezz Lvl Duct HVAC Seismic - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-29 02:00 |  | 23 05 49-19.0 Mezz Lvl Duct HVAC Seismic - MAM_TT REVIEW_ME_POP.pdf
23 05 49-020-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-020-00 Mechanical Room Support Steel | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-17 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-01 | 2020-07-06 | 20 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06461 | Received | For Review | 2020-06-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-01 | Submittal Number: 23 05 49-20.0 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: MECHANICAL ROOM SUPPORT STEEL Description: MECHANICAL ROOM SUPPORT STEEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08710 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (T... | 2020-06-24 | Submittal Number: 23 05 49-20.0 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: MECHANICAL ROOM SUPPORT STEEL Description: MECHANICAL ROOM SUPPORT STEEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06655 | Review Response | Approved | 2020-06-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.06.22 | Info Exchange
| 06777 | Review Response | Revise and Resubmit | 2020-07-02 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | Per conversation with Gretchen at MAM, we have stamped this Revise and Resubmit. MAM will provide additional information needed for review of loads imposed. See comments on submittal. SDK ¦ TT ¦ 7/2/2020 | Info Exchange
| 09112 | Responded and Closed | Revise and Resubmit | 2020-07-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.06.22 Response (Revise and Resubmit) from: Samar Kenkre (Thornton Tomasetti) Remarks: Per conversation with Gretchen at MAM, we have stamped this Revise and Resubmit. MAM will provide additional information needed for review of loads imposed. See comments on submittal. SDK ¦ TT ¦ 7/2/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 23 05 49-20 Suppl Steel MechRm - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 23 05 49-20 Suppl Steel MechRm - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-16 02:00 |  | 23 05 49-20 Suppl Steel MechRm - MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-06-16 02:00 |  | 23 05 49-20 Suppl Steel MechRm - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-06 02:00 |  | 23 05 49-20 Suppl Steel MechRm - MAM_TT Review_POP.pdf
23 05 49-020-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-020-01 Mechanical Room Support Steel | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-30 | Responded and Closed - Rejected |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-14 | 2020-11-02 | 34 |  | Record Copies; Transfers; Submittals |  | 30 |  | 2020-11-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08455 | Received | For Review | 2020-09-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-14 | Submittal Number: 23 05 49-20.1 From: GRETCHEN TOSHACH Final Due Date: 10/14/20 Subject: MECHANICAL ROOM SUPPORT STEEL Description: MECHANICAL ROOM SUPPORT STEEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11196 | Forwarded | For Review | 2020-09-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-10-07 | Submittal Number: 23 05 49-20.1 From: GRETCHEN TOSHACH Final Due Date: 10/14/20 Subject: MECHANICAL ROOM SUPPORT STEEL Description: MECHANICAL ROOM SUPPORT STEEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08553 | Review Response | Approved | 2020-10-01 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.10.01 | Info Exchange
| 09170 | Review Response | Rejected | 2020-10-29 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | As discussed with MAM/ISAT, we will expect to receive a revised submittal with the following information: 1) Connection details to primary structure (steel beams and deck). Connections should not impose any torsion on beams. 2) Unfactored horizontal and vertical reactions imposed on primary structure due to support steel or rods/braces directly. These loads should be mapped on the structural drawings. SDK ¦ TT ¦ 10/29/2020 | Info Exchange
| 12116 | Responded and Closed | Rejected | 2020-11-02 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.10.01 Response (Rejected) from: Samar Kenkre (Thornton Tomasetti) Remarks: As discussed with MAM/ISAT, we will expect to receive a revised submittal with the following information: 1) Connection details to primary structure (steel beams and deck). Connections should not impose any torsion on beams. 2) Unfactored horizontal and vertical reactions imposed on primary structure due to support steel or rods/braces directly. These loads should be mapped on the structural drawings. SDK ¦ TT ¦ 10/29/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-30 |  | 23 05 49-20.1 Supp Steel Mech - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-30 |  | 23 05 49-20.1 Supp Steel Mech - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-30 |  | 23 05 49-20.1 Supp Steel Mech - MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-11-02 02:00 |  | 23 05 49-020-01 - Support Steel Mech_TT Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-02 02:00 |  | 23 05 49-020-01 - Support Steel Mech_TT Review (002)_me_pop.pdf
23 05 49-020-02 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-020-02 Mechanical Room Support Steel | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-03 08:00 | 2020-12-08 | 22 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-12-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09473 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 23 05 49-20.2 From: GRETCHEN TOSHACH Final Due Date: 11/30/20 Subject: MECHANICAL ROOM SUPPORT STEEL Description: MECHANICAL CHILLER ROOM SUPPORT STEEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 12491 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-11-24 | Submittal Number: 23 05 49-20.2 From: GRETCHEN TOSHACH Final Due Date: 11/30/20 Subject: MECHANICAL ROOM SUPPORT STEEL Description: MECHANICAL CHILLER ROOM SUPPORT STEEL Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09999 | Review Response | Approved | 2020-11-18 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.11.18 | Info Exchange
| 10068 | Review Response | Approved as Noted | 2020-12-04 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 13087 | Responded and Closed | Approved as Noted | 2020-12-08 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 23 05 49-20.2 Suppl Steel Mech Rm - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 23 05 49-20.2 Suppl Steel Mech Rm - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-16 |  | 23 05 49-20.2 Suppl Steel Mech Rm - MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-11-16 |  | 23 05 49-20.2 Suppl Steel Mech Rm - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-08 |  | 23 05 49-20.2 Suppl Steel Mech Rm - MAM_TT_ME_POP.pdf
23 05 49-021-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-021-00 Mezzanine HVAC Piping Seismic | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-17 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-01 | 2020-07-06 | 20 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06462 | Received | For Review | 2020-06-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-01 | Submittal Number: 23 05 49-21.0 From: GRETCHEN TOSHACH Final Due Date: 07/24/20 Subject: MEZZANINE HVAC PIPING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08711 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-24 | Submittal Number: 23 05 49-21.0 From: GRETCHEN TOSHACH Final Due Date: 07/24/20 Subject: MEZZANINE HVAC PIPING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08728 | Forwarded | For Review | 2020-06-17 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2020-06-24 | Submittal Number: 23 05 49-21.0 From: GRETCHEN TOSHACH Final Due Date: 07/24/20 Subject: MEZZANINE HVAC PIPING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 06775 | Review Response | Approved as Noted | 2020-06-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.06.22 | Info Exchange
| 06776 | Review Response | Revise and Resubmit | 2020-07-01 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Calcs missing for trapeze assemblies to concrete slab/steel members, ISAT details, and specific trapeze assemblies as noted. This submittal has only been reviewed for seismic loading. Gravity loads imposed to be submitted to SEOR for review and approval in separate submittal. Note, some of the rod total vertical loads are too high for concentrated superimposed loads. Contractor to coordinate loads imposed from all trades to ensure allowable loads per structural drawings are not exceeded per general note CD-10. | Info Exchange
| 09111 | Responded and Closed | Revise and Resubmit | 2020-07-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.06.22 Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Calcs missing for trapeze assemblies to concrete slab/steel members, ISAT details, and specific trapeze assemblies as noted. This submittal has only been reviewed for seismic loading. Gravity loads imposed to be submitted to SEOR for review and approval in separate submittal. Note, some of the rod total vertical loads are too high for concentrated superimposed loads. Contractor to coordinate loads imposed from all trades to ensure allowable loads per structural drawings are not exceeded per general note CD-10. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 23 05 49-21.0 Mezz MPipe Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 23 05 49-21.0 Mezz MPipe Seismic - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-16 02:00 |  | 23 05 49-21.0 Mezz MPipe Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-16 02:00 |  | 23 05 49-21.0 Mezz MPipe Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-06-16 02:00 |  | 23 05 49-21.0 Mezz MPipe Seismic - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-06 02:00 |  | 23 05 49-21.0 Mezz MPipe Seismic_ME_TT_POP.pdf
23 05 49-021-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-021-01 Mezzanine HVAC Piping Seismic | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-08 07:00 | 2020-09-08 | 16 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07718 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-09-08 07:00 | Submittal Number: 23 05 49-21.1 From: GRETCHEN TOSHACH Final Due Date: 07/31/20 Subject: MEZZANINE HVAC PIPING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 10267 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-08-31 | Submittal Number: 23 05 49-21.1 From: GRETCHEN TOSHACH Final Due Date: 07/31/20 Subject: MEZZANINE HVAC PIPING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07773 | Review Response | Approved as Noted | 2020-08-26 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.08.26 | Info Exchange
| 10347 | Forwarded | For Review | 2020-08-26 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2020-09-02 | Submittal Number: 23 05 49-21.1 From: GRETCHEN TOSHACH Final Due Date: 07/31/20 Subject: MEZZANINE HVAC PIPING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07968 | Review Response | Approved as Noted | 2020-09-04 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Do not need to resubmit unless TT's assumptions are not correct. | Info Exchange
| 10594 | Responded and Closed | Approved as Noted | 2020-09-08 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Do not need to resubmit unless TT's assumptions are not correct. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 23 05 49-21.1 Mezz MPipe Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 23 05 49-21.1 Mezz MPipe Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-08-23 02:00 |  | 23 05 49-21.1 Mezz MPipe Seismic - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-08-23 02:00 |  | 23 05 49-21.1 Mezz MPipe Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-23 |  | 23 05 49-21.1 Mezz MPipe Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-08 |  | 23 05 49-21.1 Mezz MPipe Seismic - ME_TT_POP.pdf
23 05 49-022-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-022-00 Seismic Restraints - 300 Main Concourse Mechanical Piping | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-06 | 2020-08-06 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07117 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 23 05 49-22.0 From: GRETCHEN TOSHACH Final Due Date: 08/05/20 Subject: SEISMIC RESTRAINTS - 300 MAIN CONCOURSE MECHANICAL PIPING Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09508 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-30 | Submittal Number: 23 05 49-22.0 From: GRETCHEN TOSHACH Final Due Date: 08/05/20 Subject: SEISMIC RESTRAINTS - 300 MAIN CONCOURSE MECHANICAL PIPING Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07200 | Review Response | Approved | 2020-07-24 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.07.24 | Info Exchange
| 09603 | Forwarded | For Review | 2020-07-28 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McN... | 2020-08-04 | Submittal Number: 23 05 49-22.0 From: GRETCHEN TOSHACH Final Due Date: 08/05/20 Subject: SEISMIC RESTRAINTS - 300 MAIN CONCOURSE MECHANICAL PIPING Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07437 | Review Response | Approved | 2020-08-03 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | No seismic restraint loads imposed to review. TT has no exceptions. Gravity loads imposed to be submitted to TT for review in separate submittal. | Info Exchange
| 09906 | Responded and Closed | Approved | 2020-08-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: No seismic restraint loads imposed to review. TT has no exceptions. Gravity loads imposed to be submitted to TT for review in separate submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 23 05 49-22 300 M-Pipe Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | 23 05 49-22 300 M-Pipe Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-22 02:00 |  | 23 05 49-22 300 M-Pipe Seismic - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-22 02:00 |  | 23 05 49-22 300 M-Pipe Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-22 |  | 23 05 49-22 300 M-Pipe Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-23 |  | 23 05 49-22 300 M-Pipe Seismic - MAM.pdf
23 05 49-023-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-023-00 Seismic Restraints - HVAC Piping Riser Shafts | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-06 | 2020-08-11 | 20 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-08-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07118 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 23 05 49-23.0 From: GRETCHEN TOSHACH Final Due Date: 08/05/20 Subject: SEISMIC RESTRAINTS - HVAC PIPING RISER SHAFTS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09509 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-30 | Submittal Number: 23 05 49-23.0 From: GRETCHEN TOSHACH Final Due Date: 08/05/20 Subject: SEISMIC RESTRAINTS - HVAC PIPING RISER SHAFTS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07202 | Review Response | Approved | 2020-07-24 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.07.24 | Info Exchange
| 09604 | Forwarded | For Review | 2020-07-28 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2020-08-04 | Submittal Number: 23 05 49-23.0 From: GRETCHEN TOSHACH Final Due Date: 08/05/20 Subject: SEISMIC RESTRAINTS - HVAC PIPING RISER SHAFTS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 07522 | Review Response | Approved as Noted/Resubmit | 2020-08-07 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Refer to comments within submittal. Please resubmit items that have been requested. All other items are approved as noted. | Info Exchange
| 10016 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Refer to comments within submittal. Please resubmit items that have been requested. All other items are approved as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 23 05 49-23.0 HVAC Pipe Shaft Risers Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | 23 05 49-23.0 HVAC Pipe Shaft Risers Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-22 02:00 |  | 23 05 49-23.0 HVAC Pipe Shaft Risers Seismic - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-07-22 02:00 |  | 23 05 49-23.0 HVAC Pipe Shaft Risers Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-22 02:00 |  | 23 05 49-23.0 HVAC Pipe Shaft Risers Seismic - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-11 02:00 |  | 23 05 49-23.0 HVAC Pipe Shaft Risers Seismic_ME_TT_POP.pdf
23 05 49-023-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-023-01 Seismic Restraints - HVAC Piping Riser Shafts | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-11 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-25 | 2020-09-21 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08056 | Received | For Review | 2020-09-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-09-25 | Submittal Number: 23 05 49-23.1 From: GRETCHEN TOSHACH Final Due Date: 09/18/20 Subject: SEISMIC RESTRAINTS - HVAC PIPING RISER SHAFTS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 10719 | Forwarded | For Review | 2020-09-11 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-09-18 | Submittal Number: 23 05 49-23.1 From: GRETCHEN TOSHACH Final Due Date: 09/18/20 Subject: SEISMIC RESTRAINTS - HVAC PIPING RISER SHAFTS Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 08220 | Review Response | Approved | 2020-09-15 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.09.15 | Info Exchange
| 08222 | Review Response | Approved as Noted | 2020-09-18 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 10911 | Responded and Closed | Approved as Noted | 2020-09-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2020.09.15 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-11 |  | 23 05 49-23.1 Pipe Shaft Risers Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-11 |  | 23 05 49-23.1 Pipe Shaft Risers Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-10 02:00 |  | 23 05 49-23.1 Pipe Shaft Risers Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-10 02:00 |  | 23 05 49-23.1 Pipe Shaft Risers Seismic - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-21 02:00 |  | 23 05 49-23.1 Pipe Shaft Risers Seismic - MAM_TT REVIEW_POP.pdf
23 05 49-024-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-024-00 Seismic Restraints - 400 Suite Level Mechanical Piping | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-09 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-23 | 2020-11-11 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09295 | Received | For Review | 2020-11-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-11-23 | Submittal Number: 23 05 49-24.0 From: GRETCHEN TOSHACH Final Due Date: 12/11/20 Subject: SEISMIC RESTRAINTS - 400 SUITE LEVEL MECHANICAL PIPING Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 12265 | Forwarded | For Review | 2020-11-09 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-11-16 | Submittal Number: 23 05 49-24.0 From: GRETCHEN TOSHACH Final Due Date: 12/11/20 Subject: SEISMIC RESTRAINTS - 400 SUITE LEVEL MECHANICAL PIPING Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09381 | Review Response | Approved as Noted | 2020-11-10 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | See typical comments on transmittal page of submittal. | Info Exchange
| 09467 | Review Response | Approved | 2020-11-11 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.11.11 | Info Exchange
| 12379 | Responded and Closed | Approved as Noted | 2020-11-11 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: See typical comments on transmittal page of submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 23 05 49-24.0 400 M-Pipe Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 23 05 49-24.0 400 M-Pipe Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-06 |  | 23 05 49-24.0 400 M-Pipe Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-05 02:00 |  | 23 05 49-24.0 400 M-Pipe Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-11-11 |  | 23 05 49-24.0 400 M-Pipe Seismic - MAM_TT_ME_POP.pdf
23 05 49-025-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-025-00 Beverage Conduit Suspended Seismic | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-09 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-11-23 | 2020-11-11 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09294 | Received | For Review | 2020-11-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-11-23 | Submittal Number: 23 05 49-25.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: BEVERAGE CONDUIT SUSPENDED SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 12262 | Forwarded | For Review | 2020-11-09 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2020-11-16 | Submittal Number: 23 05 49-25.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: BEVERAGE CONDUIT SUSPENDED SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 09383 | Review Response | Approved as Noted | 2020-11-10 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Note all loads imposed from systems attached to base structure are to be communicated with EOR for review and approval. All loads imposed to be coordinated to note exceed design loads per contract drawings per General Note CD-10. Loads imposed are not to generate horizontal shear or torsion in base structure and contractor to provide supplemental bracing to resolve these forces per General Note CD-16. | Info Exchange
| 12382 | Responded and Closed | Approved as Noted | 2020-11-11 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Note all loads imposed from systems attached to base structure are to be communicated with EOR for review and approval. All loads imposed to be coordinated to note exceed design loads per contract drawings per General Note CD-10. Loads imposed are not to generate horizontal shear or torsion in base structure and contractor to provide supplemental bracing to resolve these forces per General Note CD-16. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 23 05 49-25.0 Bev Con Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 23 05 49-25.0 Bev Con Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-06 |  | 23 05 49-25.0 Bev Con Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-11-11 |  | 23 05 49-25.0 Bev Con Seismic - MAM_TT_POP.pdf
23 05 49-026-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-026-00 300 Main Con Duct Seismic | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved as Noted/Resubmit |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-29 08:00 | 2021-02-01 | 19 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10702 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-29 08:00 | Submittal Number: 23 05 49-26.0 From: GRETCHEN TOSHACH Final Due Date: 01/27/21 Subject: 300 MAIN CON DUCT SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13923 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2021-01-21 | Submittal Number: 23 05 49-26.0 From: GRETCHEN TOSHACH Final Due Date: 01/27/21 Subject: 300 MAIN CON DUCT SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11107 | Review Response | Approved | 2021-01-15 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.01.15 | Info Exchange
| 11150 | Review Response | Revise and Resubmit | 2021-01-22 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Refer to comments within submittal. There are several ducts that do not have bracing or support information. Confirm that all required seismic restraints are listed in submittal. All gravity loads imposed from ducts to be provided to EOR for review and approval (may be in separate submittal). Approved as noted if no other restraints are required. Revise and resubmit otherwise showing all restraints and attachment points for ducts. | Info Exchange
| 14409 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-01 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.01.15 Pending response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Refer to comments within submittal. There are several ducts that do not have bracing or support information. Confirm that all required seismic restraints are listed in submittal. All gravity loads imposed from ducts to be provided to EOR for review and approval (may be in separate submittal). Approved as noted if no other restraints are required. Revise and resubmit otherwise showing all restraints and attachment points for ducts. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 23 05 49-26.0 300 Duct Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 23 05 49-26.0 300 Duct Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-13 |  | 23 05 49-26.0 300 Duct Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-12 02:00 |  | 23 05 49-26.0 300 Duct Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-01 |  | 23 05 49-26.0 300 Duct Seismic - ME_TT_POP.pdf
23 05 49-026-01 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-026-01 300 Main Con Duct Seismic | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-20 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-04 07:00 | 2021-05-25 | 6 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-05-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13211 | Received | For Review | 2021-05-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (Mortenson Construction) | 2021-06-04 07:00 | Submittal Number: 23 05 49-26.1 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: 300 MAIN CON DUCT SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 17100 | Forwarded | For Review | 2021-05-20 | Gretchen Toshach (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (ME Engineers); Sean McNeill (Thornton T... | 2021-05-27 | Submittal Number: 23 05 49-26.1 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: 300 MAIN CON DUCT SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13261 | Review Response | Approved | 2021-05-21 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Stuctural engineer to review. Nick Theimer ME Engineers 2021.05.21 | Info Exchange
| 13262 | Review Response | Approved | 2021-05-24 | Matt Ross (Thornton Tomasetti) | Gretchen Toshach (Mortenson Construction) |  | Contractor to confirm separate submittals showing complete seismic bracing as indicated within have been sent to EOR for review and approval. | Info Exchange
| 17159 | Responded and Closed | Approved | 2021-05-25 | Gretchen Toshach (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Contractor to confirm separate submittals showing complete seismic bracing as indicated within have been sent to EOR for review and approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-19 |  | 23 05 49-26.1 300 SM Seismic - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-05-19 |  | 23 05 49-26.1 300 SM Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-19 |  | 23 05 49-26.1 300 SM Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-19 |  | 23 05 49-26.1 300 SM Seismic - MAM.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-05-25 |  | 23 05 49-26.1 300 SM Seismic - MAM_TT_POP.pdf
23 05 49-027-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-027-00 400 Suite Duct Seismic | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-29 08:00 | 2021-02-01 | 19 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10687 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-29 08:00 | Submittal Number: 23 05 49-27.0 From: GRETCHEN TOSHACH Final Due Date: 01/27/21 Subject: 400 SUITE DUCT SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13908 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2021-01-20 | Submittal Number: 23 05 49-27.0 From: GRETCHEN TOSHACH Final Due Date: 01/27/21 Subject: 400 SUITE DUCT SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11106 | Review Response | Approved | 2021-01-15 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See atached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.01.15 | Info Exchange
| 11149 | Review Response | Revise and Resubmit | 2021-01-22 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Refer to comments within submittal. There are several ducts that do not have bracing or support information. Confirm that all required seismic restraints are listed in submittal. All gravity loads imposed from ducts to be provided to EOR for review and approval (may be in separate submittal). Approved as noted if no other restraints are required. Revise and resubmit otherwise showing all restraints and attachment points for ducts. | Info Exchange
| 14408 | Responded and Closed | Approved as Noted | 2021-02-01 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See atached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.01.15 Pending response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Refer to comments within submittal. There are several ducts that do not have bracing or support information. Confirm that all required seismic restraints are listed in submittal. All gravity loads imposed from ducts to be provided to EOR for review and approval (may be in separate submittal). Approved as noted if no other restraints are required. Revise and resubmit otherwise showing all restraints and attachment points for ducts. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 23 05 49-27.0 400 Duct Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 23 05 49-27.0 400 Duct Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-13 |  | 23 05 49-27.0 400 Duct Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-12 02:00 |  | 23 05 49-27.0 400 Duct Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-01 |  | 23 05 49-27.0 400 Duct Seismic - ME_TT_POP.pdf
23 05 49-028-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-028-00 500 Upper Con Duct Seismic | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-29 08:00 | 2021-02-01 | 19 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10688 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-29 08:00 | Submittal Number: 23 05 49-28.0 From: GRETCHEN TOSHACH Final Due Date: 01/27/21 Subject: 500 UPPER CON DUCT SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13909 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2021-01-20 | Submittal Number: 23 05 49-28.0 From: GRETCHEN TOSHACH Final Due Date: 01/27/21 Subject: 500 UPPER CON DUCT SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11105 | Review Response | Approved | 2021-01-15 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.01.15 | Info Exchange
| 11148 | Review Response | Approved | 2021-01-22 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions as there are no seismic loads imposed to review. However, all gravity loads imposed from all ducts on base structure are to be submitted to EOR for review and approval. | Info Exchange
| 14407 | Responded and Closed | Approved | 2021-02-01 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.01.15 Pending response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions as there are no seismic loads imposed to review. However, all gravity loads imposed from all ducts on base structure are to be submitted to EOR for review and approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 23 05 49-28.0 500 Duct Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 23 05 49-28.0 500 Duct Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-13 |  | 23 05 49-28.0 500 Duct Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-12 02:00 |  | 23 05 49-28.0 500 Duct Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-01 |  | 23 05 49-28.0 500 Duct Seismic - ME_TT_POP.pdf
23 05 49-029-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-029-00 550 Space Needle Duct Seismic | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-29 08:00 | 2021-02-01 | 19 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10684 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-29 08:00 | Submittal Number: 23 05 49-29.0 From: GRETCHEN TOSHACH Final Due Date: 01/27/21 Subject: 550 SPACE NEEDLE DUCT SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13904 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2021-01-20 | Submittal Number: 23 05 49-29.0 From: GRETCHEN TOSHACH Final Due Date: 01/27/21 Subject: 550 SPACE NEEDLE DUCT SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11104 | Review Response | Approved | 2021-01-15 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Strucutral engineer to review. Nick Theimer ME Engineers 2021.01.15 | Info Exchange
| 11147 | Review Response | Approved as Noted | 2021-01-22 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Coordinate all attachments to precast with precast mfr, typ. Refer to typical comments regarding duct support struts and beam clamp details. No connections are to be made to horizontal bracing members. Clarify attachment plan for ducts on North side at Area C&D cores. There is no slab above. | Info Exchange
| 14405 | Responded and Closed | Approved as Noted | 2021-02-01 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.01.15 Pending response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Coordinate all attachments to precast with precast mfr, typ. Refer to typical comments regarding duct support struts and beam clamp details. No connections are to be made to horizontal bracing members. Clarify attachment plan for ducts on North side at Area C&D cores. There is no slab above. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 23 05 49-29.0 550 Duct Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 23 05 49-29.0 550 Duct Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-13 |  | 23 05 49-29.0 550 Duct Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-12 02:00 |  | 23 05 49-29.0 550 Duct Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-01 |  | 23 05 49-29.0 550 Duct Seismic - ME_TT_POP.pdf
23 05 49-030-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-030-00 200 Plumbing Seismic | Closed | Plumbing, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-26 08:00 | 2021-02-01 | 22 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10598 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-26 08:00 | Submittal Number: 23 05 49-30.0 From: GRETCHEN TOSHACH Final Due Date: 01/22/21 Subject: 200 PLUMBING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13803 | Forwarded | For Review | 2021-01-11 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thorn... | 2021-01-18 | Submittal Number: 23 05 49-30.0 From: GRETCHEN TOSHACH Final Due Date: 01/22/21 Subject: 200 PLUMBING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11103 | Review Response | Approved | 2021-01-11 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 11 January 2021 | Info Exchange
| 11146 | Review Response | Approved as Noted | 2021-01-22 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attachment for comments and notes. | Info Exchange
| 14404 | Responded and Closed | Approved as Noted | 2021-02-01 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 11 January 2021 Pending response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attachment for comments and notes. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | 23 05 49-30.0 200 Level Plbg Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-08 |  | 23 05 49-30.0 200 Level Plbg Seismic - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-01-08 |  | 23 05 49-30.0 200 Level Plbg Seismic - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-01-07 02:00 |  | 23 05 49-30.0 200 Level Plbg Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-01 |  | 23 05 49-30.0 200 Level Plbg Seismic - ME_TT_POP.pdf
23 05 49-031-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-031-00 300 Plumbing Seismic | Closed | Plumbing, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-26 08:00 | 2021-02-01 | 22 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10562 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-26 08:00 | Submittal Number: 23 05 49-31.0 From: GRETCHEN TOSHACH Final Due Date: 01/22/21 Subject: 300 PLUMBING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13762 | Forwarded | For Review | 2021-01-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thorn... |  | Submittal Number: 23 05 49-31.0 From: GRETCHEN TOSHACH Final Due Date: 01/22/21 Subject: 300 PLUMBING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13764 | Forwarded | For Review | 2021-01-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thorn... | 2021-01-15 | Submittal Number: 23 05 49-31.0 From: GRETCHEN TOSHACH Final Due Date: 01/22/21 Subject: 300 PLUMBING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11102 | Review Response | Approved | 2021-01-10 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 10 January 2021 | Info Exchange
| 11145 | Review Response | Approved as Noted | 2021-01-25 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attachments for review comments. | Info Exchange
| 14401 | Responded and Closed | Approved as Noted | 2021-02-01 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 10 January 2021 Pending response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attachments for review comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-08 |  | 23 05 49-31.0 300 Level Plbg Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-08 |  | 23 05 49-31.0 300 Level Plbg Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-08 |  | 23 05 49-31.0 300 Level Plbg Seismic - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-01-08 |  | 23 05 49-31.0 300 Level Plbg Seismic - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-01-07 02:00 |  | 23 05 49-31.0 300 Level Plbg Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-01 |  | 23 05 49-31.0 300 Level Plbg Seismic - ME_TT_POP.pdf
23 05 49-032-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-032-00 400 Plumbing Seismic | Closed | Structural, Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-06 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-21 08:00 | 2021-02-01 | 27 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10510 | Received | For Review | 2021-01-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-21 08:00 | Submittal Number: 23 05 49-32.0 From: GRETCHEN TOSHACH Final Due Date: 01/20/21 Subject: 400 PLUMBING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13713 | Forwarded | For Review | 2021-01-07 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thorn... | 2021-01-14 | Submittal Number: 23 05 49-32.0 From: GRETCHEN TOSHACH Final Due Date: 01/20/21 Subject: 400 PLUMBING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11100 | Review Response | Approved | 2021-01-07 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 January 2021 | Info Exchange
| 11144 | Review Response | Approved as Noted | 2021-01-25 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attachment for marked comments. | Info Exchange
| 14399 | Responded and Closed | Approved as Noted | 2021-02-01 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 January 2021 Pending response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attachment for marked comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-06 |  | 23 05 49-32.0 400 Level Plbg Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-06 |  | 23 05 49-32.0 400 Level Plbg Seismic - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-01-06 |  | 23 05 49-32.0 400 Level Plbg Seismic - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-01-05 02:00 |  | 23 05 49-32.0 400 Level Plbg Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-01 |  | 23 05 49-32.0 400 Level Plbg Seismic - ME_TT_POP.pdf
23 05 49-033-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-033-00 500 Plumbing Seismic | Closed | Structural, Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-22 08:00 | 2021-02-01 | 26 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10511 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-22 08:00 | Submittal Number: 23 05 49-33.0 From: GRETCHEN TOSHACH Final Due Date: 01/20/21 Subject: 500 PLUMBING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13714 | Forwarded | For Review | 2021-01-07 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thorn... | 2021-01-14 | Submittal Number: 23 05 49-33.0 From: GRETCHEN TOSHACH Final Due Date: 01/20/21 Subject: 500 PLUMBING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 11098 | Review Response | Approved | 2021-01-07 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 January 2021 | Info Exchange
| 11143 | Review Response | Approved as Noted | 2021-01-25 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attachment for review comments. | Info Exchange
| 14397 | Responded and Closed | Approved as Noted | 2021-02-01 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 7 January 2021 Pending response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attachment for review comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-06 |  | 23 05 49-33.0 500 Level Plbg Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-06 |  | 23 05 49-33.0 500 Level Plbg Seismic - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-01-06 |  | 23 05 49-33.0 500 Level Plbg Seismic - MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-01-05 02:00 |  | 23 05 49-33.0 500 Level Plbg Seismic - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-01 |  | 23 05 49-33.0 500 Level Plbg Seismic - ME_TT_POP.pdf
23 05 49-034-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-034-00 550 Space Needle Mechanical Piping Seismic | Closed | Structural, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-05 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-20 08:00 | 2021-01-20 | 16 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10460 | Received | For Review | 2021-01-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (Mortenson Construction) | 2021-01-20 08:00 | Submittal Number: 23 05 49-34.0 From: GRETCHEN TOSHACH Final Due Date: 01/19/21 Subject: 550 SPACE NEEDLE MECHANICAL PIPING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13656 | Forwarded | For Review | 2021-01-05 | Gretchen Toshach (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (... | 2021-01-12 | Submittal Number: 23 05 49-34.0 From: GRETCHEN TOSHACH Final Due Date: 01/19/21 Subject: 550 SPACE NEEDLE MECHANICAL PIPING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 10812 | Review Response | Approved | 2021-01-05 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 20201.01.05 | Info Exchange
| 10813 | Review Response | Approved as Noted | 2021-01-08 | Matt Ross (Thornton Tomasetti) | Bryan Klote (Populous); Gretchen Toshach (Mortenson Construction) |  | TT has no exceptions from a seismic restraints standpoint. However, all gravity loads and attachments points to base structure are to be provided to TT for review and approval. Typical at all runs. | Info Exchange
| 10814 | Review Response | Approved as Noted | 2021-01-08 | Matt Ross (Thornton Tomasetti) | Bryan Klote (Populous); Gretchen Toshach (Mortenson Construction) |  | TT has no exceptions from a seismic restraints standpoint. However, all gravity loads and attachments points to base structure are to be provided to TT for review and approval. Typical at all runs. | Info Exchange
| 14061 | Responded and Closed | Approved as Noted | 2021-01-20 | Gretchen Toshach (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions from a seismic restraints standpoint. However, all gravity loads and attachments points to base structure are to be provided to TT for review and approval. Typical at all runs. Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 20201.01.05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-05 |  | 23 05 49-34. 550 M-Pipe Seismic - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-01-05 |  | 23 05 49-34. 550 M-Pipe Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-04 02:00 |  | 23 05 49-34. 550 M-Pipe Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-04 02:00 |  | 23 05 49-34. 550 M-Pipe Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-04 02:00 |  | 23 05 49-34. 550 M-Pipe Seismic - MAM.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-01-20 02:00 |  | 23 05 49-34. 550 M-Pipe Seismic - MAM_TT_ME_POP.pdf
23 05 49-035-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-035-00 550 Plumbing Seismic | Closed | Structural, Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-05 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-20 08:00 | 2021-01-24 | 20 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-01-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10459 | Received | For Review | 2021-01-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (Mortenson Construction) | 2021-01-20 08:00 | Submittal Number: 23 05 49-35.0 From: GRETCHEN TOSHACH Final Due Date: 01/19/21 Subject: 550 PLUMBING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 13655 | Forwarded | For Review | 2021-01-05 | Gretchen Toshach (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thorn... | 2021-01-12 | Submittal Number: 23 05 49-35.0 From: GRETCHEN TOSHACH Final Due Date: 01/19/21 Subject: 550 PLUMBING SEISMIC Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 10811 | Review Response | Approved | 2021-01-05 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 5 January 2021 | Info Exchange
| 10921 | Review Response | Approved as Noted | 2021-01-08 | Matt Ross (Thornton Tomasetti) | Bryan Klote (Populous); Gretchen Toshach (Mortenson Construction) |  | Clarify attachments at this level as there is no slab above. Attachments to SPS and Precast stadia are to be reviewed and approved by the respective system engineers. | Info Exchange
| 14179 | Responded and Closed | Approved as Noted | 2021-01-24 | Gretchen Toshach (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Clarify attachments at this level as there is no slab above. Attachments to SPS and Precast stadia are to be reviewed and approved by the respective system engineers. Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 5 January 2021 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-05 |  | 23 05 49-35.0 550 Level Plbg Seismic - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-01-05 |  | 23 05 49-35.0 550 Level Plbg Seismic - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-01-04 02:00 |  | 23 05 49-35.0 550 Level Plbg Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-04 02:00 |  | 23 05 49-35.0 550 Level Plbg Seismic - MAM.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-01-24 02:00 |  | 23 05 49-35.0 550 Level Plbg Seismic - MAM_TT_MEE_POP.pdf
23 05 49-037-00 | 23 05 49 - SEISMIC RESTRAINTS | 23 05 49-037-00 Seismic for Fans from CCD086 | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-23 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-07 07:00 | 2021-04-05 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12178 | Received | For Review | 2021-03-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-04-07 07:00 | Submittal Number: 23 05 49-37.0 From: GRETCHEN TOSHACH Final Due Date: 04/06/21 Subject: SEISMIC FOR FANS FROM CCD086 Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 15762 | Forwarded | For Review | 2021-03-23 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (ME Engineers); Sean McNeill (Thornton T... | 2021-03-30 | Submittal Number: 23 05 49-37.0 From: GRETCHEN TOSHACH Final Due Date: 04/06/21 Subject: SEISMIC FOR FANS FROM CCD086 Description: Spec Section: 23 05 49 - SEISMIC RESTRAINTS Status: OPEN | Info Exchange
| 12303 | Review Response | Approved | 2021-03-23 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.03.23 | Info Exchange
| 12415 | Review Response | Approved as Noted | 2021-04-01 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 16087 | Responded and Closed | Approved as Noted | 2021-04-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.03.23 Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-23 |  | 23 05 49-37.0 CCD-086 Fan Adds Seismic - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-23 |  | 23 05 49-37.0 CCD-086 Fan Adds Seismic - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-03-23 |  | 23 05 49-37.0 CCD-086 Fan Adds Seismic - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-22 02:00 |  | 23 05 49-37.0 CCD-086 Fan Adds Seismic - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-04-05 02:00 |  | 23 05 49-37.0 CCD-086 Fan Adds Seismic - MAM_TT_ME_POP.pdf
23 05 53-001-00 | 23 05 53 - MECHANICAL IDENTIFICATION | 23 05 53-001-00 MECHANICAL IDENTIFICATION - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-31 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-14 | 2019-08-09 | 10 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01921 | Received | For Review | 2019-07-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-14 | Submittal Number: 23 05 53-1.0 From: PATRICK KLEIN Final Due Date: 08/13/19 Subject: MECHANICAL IDENTIFICATION - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA ON THE FOLLOWING : - 1. PLASTIC PIPE MARKERS AND METHOD OF APPLICATION. 2. ENGRAVED PLASTIC LAMINATE SIGN. Spec Section: 23 05 53 - MECHANICAL IDENTIFICATION Status: OPEN | Info Exchange
| 03067 | Forwarded | For Review | 2019-07-31 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-07 | Submittal Number: 23 05 53-1.0 From: PATRICK KLEIN Final Due Date: 08/13/19 Subject: MECHANICAL IDENTIFICATION - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA ON THE FOLLOWING : - 1. PLASTIC PIPE MARKERS AND METHOD OF APPLICATION. 2. ENGRAVED PLASTIC LAMINATE SIGN. Spec Section: 23 05 53 - MECHANICAL IDENTIFICATION Status: OPEN | Info Exchange
| 02025 | Review Response | Approved as Noted | 2019-08-07 | Nick Theimer (ME Engineers) | Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.08.07 | Info Exchange
| 03190 | Responded and Closed | Approved as Noted | 2019-08-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.08.07 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-30 |  | 23 05 53-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-30 |  | 23 05 53-1.0 Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-29 02:00 |  | 23 05 53-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-09 02:00 |  | 23 05 53-1.0 Product Data-ME-POP.pdf
23 07 00-001-00 | 23 07 00 - MECHANICAL INSULATION | 23 07 00-001-00 Mechanical Insulation PD | Closed | Mechanical | Patrick Klein (Mortenson Construction) | 2019-06-19 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-07-03 | 2019-06-28 | 10 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-06-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01597 | Received | For Review | 2019-06-19 | Patrick Klein (Mortenson Construction) | Populous SCA_CCA | 2019-07-03 |  | Email
| 02637 | Forwarded | For Review | 2019-06-21 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-06-28 |  | Info Exchange
| 01653 | Review Response | Approved as Noted | 2019-06-28 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | Please see attached for review of Submittal 230700-0001-00. | Info Exchange
| 02721 | Responded and Closed | Approved as Noted | 2019-06-28 | Populous SCA_CCA | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: Please see attached for review of Submittal 230700-0001-00. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Patrick Klein (Mortenson Construction) | 1 | 2019-06-21 |  | 23 07 00-001-00 Mechanical Insulation PD.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-21 |  | 23 07 00-001-00 Mechanical Insulation PD.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-06-28 |  | 23 07 00-001-00 Mechanical Insulation PD_ME.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-06-28 |  | 23 07 00-001-00 Mechanical Insulation PD_ME_POP.pdf
23 07 00-001-01 | 23 07 00 - MECHANICAL INSULATION | 23 07 00-001-01 MECHANICAL INSULATION - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-06 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-20 | 2020-03-17 | 12 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04679 | Received | For Review | 2020-03-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-20 | Submittal Number: 23 07 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 10/31/19 Subject: MECHANICAL INSULATION - PRODUCT DATA Description: SUBMIT INSULATION MATRIX Spec Section: 23 07 00 - MECHANICAL INSULATION Status: OPEN | Info Exchange
| 06437 | Forwarded | For Review | 2020-03-05 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-12 | Submittal Number: 23 07 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 10/31/19 Subject: MECHANICAL INSULATION - PRODUCT DATA Description: SUBMIT INSULATION MATRIX Spec Section: 23 07 00 - MECHANICAL INSULATION Status: OPEN | Info Exchange
| 04900 | Review Response | Approved | 2020-03-17 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.17 | Info Exchange
| 06693 | Responded and Closed | Approved | 2020-03-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-05 |  | 23 0700-1.1 Mech Insul Matrix - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-05 |  | 23 0700-1.1 Mech Insul Matrix - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-04 02:00 |  | 23 0700-1.1 Mech Insul Matrix - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-17 02:00 |  | 23 0700-1.1 Mech Insul Matrix_ME_POP.pdf
23 07 00-001-02 | 23 07 00 - MECHANICAL INSULATION | 23 07 00-001-02 MECHANICAL INSULATION - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-21 | 2020-07-20 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06823 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 23 07 00-1.2 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: MECHANICAL INSULATION - PRODUCT DATA Description: SUBMIT INSULATION MATRIX Spec Section: 23 07 00 - MECHANICAL INSULATION Status: OPEN | Info Exchange
| 09158 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 23 07 00-1.2 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: MECHANICAL INSULATION - PRODUCT DATA Description: SUBMIT INSULATION MATRIX Spec Section: 23 07 00 - MECHANICAL INSULATION Status: OPEN | Info Exchange
| 07034 | Review Response | Approved as Noted | 2020-07-16 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.07.16 | Info Exchange
| 09419 | Responded and Closed | Approved as Noted | 2020-07-20 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-07 |  | 23 07 00-1.2 Mech Insul Matrix - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 23 07 00-1.2 Mech Insul Matrix - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-07 |  | 23 07 00-1.2 Mech Insul Matrix - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-20 |  | 23 07 00-1.2 Mech Insul Matrix_ME_POP.pdf
23 07 00-001-03 | 23 07 00 - MECHANICAL INSULATION | 23 07 00-001-03 MECHANICAL INSULATION - Insulation Matrix | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-24 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-08 | 2020-09-29 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08310 | Received | For Review | 2020-09-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-08 | Submittal Number: 23 07 00-1.3 From: GRETCHEN TOSHACH Final Due Date: 10/07/20 Subject: MECHANICAL INSULATION - INSULATION MATRIX Description: Spec Section: 23 07 00 - MECHANICAL INSULATION Status: OPEN | Info Exchange
| 11017 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-01 | Submittal Number: 23 07 00-1.3 From: GRETCHEN TOSHACH Final Due Date: 10/07/20 Subject: MECHANICAL INSULATION - INSULATION MATRIX Description: Spec Section: 23 07 00 - MECHANICAL INSULATION Status: OPEN | Info Exchange
| 08414 | Review Response | Approved | 2020-09-24 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| 11150 | Responded and Closed | Approved | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 23 07 00-1.3 Mech Insul_Matrix - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 23 07 00-1.3 Mech Insul_Matrix - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-24 |  | 23 07 00-1.3 Mech Insul_Matrix - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 23 07 00-1.3 Mech Insul Matrix_ME_POP.pdf
23 07 00-001-04 | 23 07 00 - MECHANICAL INSULATION | 23 07 00-001-04 JM Micro-Lok HP ULTRA pipe insulation - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-17 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-03-31 | 2021-03-24 | 8 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12083 | Received | For Review | 2021-03-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-03-31 | Submittal Number: 23 07 00-1.4 From: GRETCHEN TOSHACH Final Due Date: 04/02/21 Subject: JM MICRO-LOK HP ULTRA PIPE INSULATION - PRODUCT DATA Description: Spec Section: 23 07 00 - MECHANICAL INSULATION Status: OPEN | Info Exchange
| 15640 | Forwarded | For Review | 2021-03-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-24 | Submittal Number: 23 07 00-1.4 From: GRETCHEN TOSHACH Final Due Date: 04/02/21 Subject: JM MICRO-LOK HP ULTRA PIPE INSULATION - PRODUCT DATA Description: Spec Section: 23 07 00 - MECHANICAL INSULATION Status: OPEN | Info Exchange
| 12232 | Review Response | Approved | 2021-03-22 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.03.22 | Info Exchange
| 15822 | Responded and Closed | Approved | 2021-03-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.03.22 | Info Exchange
| 16738 | Sent | For Information Only | 2021-05-04 | Josh Dobken (Populous) | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Responded and Closed (Approved) to: Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.03.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-17 |  | 23 07 00-1.4 Mech Insulation ULTRA - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-17 |  | 23 07 00-1.4 Mech Insulation ULTRA - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-03-16 02:00 |  | 23 07 00-1.4 Mech Insulation ULTRA - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-24 02:00 |  | 23 07 00-1.4 Mech Insulation ULTRA_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-03-16 02:00 |  | 23 07 00-1.4 Mech Insulation ULTRA - MAM.pdf
23 07 00-002-00 | 23 07 00 - MECHANICAL INSULATION | 23 07 00-002-00 MECHANICAL INSULATION - LEED Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-16 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-30 | 2019-08-30 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-08-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02094 | Received | For Review | 2019-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-30 | Submittal Number: 23 07 00-2.0 From: PATRICK KLEIN Final Due Date: 08/29/19 Subject: MECHANICAL INSULATION - LEED DATA Description: SEALERS, MASTICS AND ADHESIVES. 1. FITTING COVERS. 2. MANUFACTURERS INSTALLATION DETAILS FOR FIRE RATED DUCT WRAP. 3. LOW-EMITTING ADHESIVES AND SEALANTS EQC4.1 REQUIREMENTS FOR LEED SUBMITTALS. Spec Section: 23 07 00 - MECHANICAL INSULATION Status: OPEN | Info Exchange
| 03267 | Forwarded | For Review | 2019-08-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-23 | Submittal Number: 23 07 00-2.0 From: PATRICK KLEIN Final Due Date: 08/29/19 Subject: MECHANICAL INSULATION - LEED DATA Description: SEALERS, MASTICS AND ADHESIVES. 1. FITTING COVERS. 2. MANUFACTURERS INSTALLATION DETAILS FOR FIRE RATED DUCT WRAP. 3. LOW-EMITTING ADHESIVES AND SEALANTS EQC4.1 REQUIREMENTS FOR LEED SUBMITTALS. Spec Section: 23 07 00 - MECHANICAL INSULATION Status: OPEN | Info Exchange
| 02270 | Review Response | No Action Taken or Required | 2019-08-29 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.08.29 | Info Exchange
| 03492 | Responded and Closed | No Action Taken or Required | 2019-08-30 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Brooke Burcham (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.08.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-15 |  | 23 07 00-2.0 Mech Insulation LEED-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-15 |  | 23 07 00-2.0 Mech Insulation LEED-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-14 02:00 |  | 23 07 00-2.0 Mech Insulation LEED-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-30 02:00 |  | 23 07 00-2.0 Mech Insulation LEED-ME_POP.pdf
23 09 00-001-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-001-00 BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - General | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-21 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-11 | 2020-05-04 | 14 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05484 | Received | For Review | 2020-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-11 | Submittal Number: 23 09 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 06/11/19 Subject: BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - GENERAL Description: 1. COMPLETE SEQUENCE OF OPERATION.- Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 07438 | Forwarded | For Review | 2020-04-21 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-28 | Submittal Number: 23 09 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 06/11/19 Subject: BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - GENERAL Description: 1. COMPLETE SEQUENCE OF OPERATION.- Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 05710 | Review Response | Revise and Resubmit | 2020-05-01 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.01 | Info Exchange
| 07740 | Responded and Closed | Revise and Resubmit | 2020-05-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-21 |  | 23 09 00-1.0 BAS Package - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-21 |  | 23 09 00-1.0 BAS Package - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-20 02:00 |  | 23 09 00-1.0 BAS Package - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-04 02:00 |  | 23 09 00-1.0 BAS Package_ME_POP.pdf
23 09 00-001-01 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-001-01 BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - General | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-17 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-31 | 2020-08-03 | 18 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-08-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07016 | Received | For Review | 2020-07-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-31 | Submittal Number: 23 09 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 06/11/20 Subject: BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - GENERAL Description: 1. COMPLETE SEQUENCE OF OPERATION.- Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 09398 | Forwarded | For Review | 2020-07-20 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-27 | Submittal Number: 23 09 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 06/11/20 Subject: BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - GENERAL Description: 1. COMPLETE SEQUENCE OF OPERATION.- Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 07316 | Review Response | Approved as Noted/Resubmit | 2020-07-29 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Submit specified items in separate submittal package. Nick Theimer ME Engineers 2020.07.29 | Info Exchange
| 09755 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-03 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Submit specified items in separate submittal package. Nick Theimer ME Engineers 2020.07.29 | Info Exchange
| 09858 | Sent | For Information Only | 2020-08-05 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted/Resubmit) to: Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Submit specified items in separate submittal package. Nick Theimer ME Engineers 2020.07.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-17 |  | 23 09 00-1.1 Controls - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-17 |  | 23 09 00-1.1 Controls - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-17 |  | 23 09 00-1.1 Controls - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-08-03 |  | 23 09 00-1.1 Controls_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-07-16 02:00 |  | 23 09 00-1.1 Controls - MAM.pdf
23 09 00-001-02 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-001-02 BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - General | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-06 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-20 | 2020-11-18 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-11-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09277 | Received | For Review | 2020-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-11-20 | Submittal Number: 23 09 00-1.2 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - GENERAL Description: 1. COMPLETE SEQUENCE OF OPERATION.- Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 12233 | Forwarded | For Review | 2020-11-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-13 | Submittal Number: 23 09 00-1.2 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - GENERAL Description: 1. COMPLETE SEQUENCE OF OPERATION.- Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 09558 | Review Response | Approved | 2020-11-18 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.11.18 | Info Exchange
| 12581 | Responded and Closed | Approved | 2020-11-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.11.18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 23 09 00-1.2 Controls Submittal - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 23 09 00-1.2 Controls Submittal - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-18 02:00 |  | 23 09 00-1.2 Controls Submittal_ME.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-18 02:00 |  | 23 09 00-1.2 Controls Submittal_ME_POP.pdf
23 09 00-010-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-010-00 Valve Schedule | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-30 | 2020-03-25 | 10 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-03-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04846 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 23 09 00-10.0 From: GRETCHEN TOSHACH Final Due Date: 04/06/20 Subject: VALVE SCHEDULE Description: SIEMENS VALVE SCHEDULE Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 06623 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-23 | Submittal Number: 23 09 00-10.0 From: GRETCHEN TOSHACH Final Due Date: 04/06/20 Subject: VALVE SCHEDULE Description: SIEMENS VALVE SCHEDULE Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 05039 | Review Response | Approved as Noted | 2020-03-20 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.20 | Info Exchange
| 06861 | Responded and Closed | Approved as Noted | 2020-03-25 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 23 09 00-10.0 Valve Schedule - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 23 09 00-10.0 Valve Schedule - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-15 02:00 |  | 23 09 00-10.0 Valve Schedule - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-25 02:00 |  | 23 09 00-10.0 Valve Schedule_ME_POP.pdf
23 09 00-012-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-012-00 BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - CCD 063 and 064 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-25 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-09 07:00 | 2020-09-01 | 8 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07738 | Received | For Review | 2020-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-09-09 07:00 | Submittal Number: 23 09 00-12.0 From: GRETCHEN TOSHACH Final Due Date: 09/10/20 Subject: BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - CCD 063 AND 064 Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 10302 | Forwarded | For Review | 2020-08-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-01 | Submittal Number: 23 09 00-12.0 From: GRETCHEN TOSHACH Final Due Date: 09/10/20 Subject: BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - CCD 063 AND 064 Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 07885 | Review Response | Approved as Noted | 2020-08-27 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.08.27 | Info Exchange
| 10487 | Responded and Closed | Approved as Noted | 2020-09-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.08.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-25 |  | 23 09 00-12.0 Controls_CCD-063_064 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-25 |  | 23 09 00-12.0 Controls_CCD-063_064 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-08-25 |  | 23 09 00-12.0 Controls_CCD-063_064 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-01 |  | 23 09 00-12.0 Controls_CCD-063_064_ME_POP.pdf
23 09 00-013-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-013-00 BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - Metering | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-12 | 2020-09-29 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08378 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 23 09 00-13.0 From: GRETCHEN TOSHACH Final Due Date: 09/10/20 Subject: BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - METERING Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 11103 | Forwarded | For Review | 2020-09-28 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-05 | Submittal Number: 23 09 00-13.0 From: GRETCHEN TOSHACH Final Due Date: 09/10/20 Subject: BUILDING AUTOMATION AND AUTOMATIC TEMPERATURE - METERING Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 08423 | Review Response | Approved as Noted | 2020-09-28 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.09.28 | Info Exchange
| 11160 | Responded and Closed | Approved as Noted | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.09.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-28 |  | 23 09 00-13.0 ME Comments_Superheat - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-28 |  | 23 09 00-13.0 ME Comments_Superheat - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-28 |  | 23 09 00-13.0 ME Comments_Superheat - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 23 09 00-13.0 ME Comments_Superheat_ME_POP.pdf
23 09 00-014-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-014-00 Electric Boiler and Metering | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-19 | 2020-10-19 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-10-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08560 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 23 09 00-14.0 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: ELECTRIC BOILER AND METERING Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 11319 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-12 | Submittal Number: 23 09 00-14.0 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: ELECTRIC BOILER AND METERING Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 08846 | Review Response | Approved as Noted | 2020-10-16 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.10.15 | Info Exchange
| 11694 | Responded and Closed | Approved as Noted | 2020-10-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 23 09 00-14.0 Elec Boilers_Metering - MAM[1].pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 23 09 00-14.0 Elec Boilers_Metering - MAM[1].pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-10-05 |  | 23 09 00-14.0 Elec Boilers_Metering - MAM[1].pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-19 |  | 23 09 00-14.0 Elec Boilers_Metering_ME_POP.pdf
23 09 00-015-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-015-00 Controls – Analox Food Service CO2 Sensor PD | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-09 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-23 | 2020-12-15 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10040 | Received | For Review | 2020-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-23 | Submittal Number: 23 09 00-15.0 From: GRETCHEN TOSHACH Final Due Date: 12/23/20 Subject: CONTROLS – ANALOX FOOD SERVICE CO2 SENSOR PD Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 13138 | Forwarded | For Review | 2020-12-09 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-16 | Submittal Number: 23 09 00-15.0 From: GRETCHEN TOSHACH Final Due Date: 12/23/20 Subject: CONTROLS – ANALOX FOOD SERVICE CO2 SENSOR PD Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 10161 | Review Response | Approved | 2020-12-14 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.12.14 | Info Exchange
| 13295 | Responded and Closed | Approved | 2020-12-15 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.12.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-09 |  | 23 09 00-15.0 Controls CO2 Sensors - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-09 |  | 23 09 00-15.0 Controls CO2 Sensors - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-12-09 |  | 23 09 00-15.0 Controls CO2 Sensors - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-15 |  | 23 09 00-15.0 Controls CO2 Sensors_ME_POP.pdf
23 09 00-016-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-016-00 Controls – Base Control Submittal revised through CCD-73 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-09 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-23 | 2020-12-14 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-12-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10039 | Received | For Review | 2020-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (M.A. Mortenson Company) | 2020-12-23 | Submittal Number: 23 09 00-16.0 From: GRETCHEN TOSHACH Final Due Date: 12/22/20 Subject: CONTROLS – BASE CONTROL SUBMITTAL REVISED THROUGH CCD-73 Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 13137 | Forwarded | For Review | 2020-12-09 | Gretchen Toshach (M.A. Mortenson Company) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-16 | Submittal Number: 23 09 00-16.0 From: GRETCHEN TOSHACH Final Due Date: 12/22/20 Subject: CONTROLS – BASE CONTROL SUBMITTAL REVISED THROUGH CCD-73 Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 10145 | Review Response | Approved as Noted | 2020-12-14 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.12.14 | Info Exchange
| 13268 | Responded and Closed | Approved as Noted | 2020-12-14 | Gretchen Toshach (M.A. Mortenson Company) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.12.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-08 |  | 23 09 00-16.0 Controls_CCD-073 - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2020-12-08 |  | 23 09 00-16.0 Controls_CCD-073 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-12-08 |  | 23 09 00-16.0 Controls_CCD-073 - MAM.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2020-12-14 |  | 23 09 00-16.0 Controls_CCD-073_ME_POP.pdf
23 09 00-016-01 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-016-01 Controls – Base Control Submittal revised through CCD-73 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-25 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-09 07:00 | 2021-06-03 | 10 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13253 | Received | For Review | 2021-05-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-09 07:00 | Submittal Number: 23 09 00-16.1 From: GRETCHEN TOSHACH Final Due Date: 06/08/21 Subject: CONTROLS – BASE CONTROL SUBMITTAL REVISED THROUGH CCD-73 Description: REVISIONS TO BACKBONE Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 17149 | Forwarded | For Review | 2021-05-25 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-01 | Submittal Number: 23 09 00-16.1 From: GRETCHEN TOSHACH Final Due Date: 06/08/21 Subject: CONTROLS – BASE CONTROL SUBMITTAL REVISED THROUGH CCD-73 Description: REVISIONS TO BACKBONE Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 13391 | Review Response | Approved | 2021-05-25 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.05.25 | Info Exchange
| 17319 | Responded and Closed | Approved | 2021-06-03 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.05.25 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-25 |  | 23 09 00-16.1 Base Controls CCD-073 - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-25 |  | 23 09 00-16.1 Base Controls CCD-073 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-24 02:00 |  | 23 09 00-16.1 Base Controls CCD-073 - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-03 02:00 |  | 23 09 00-16.1 Base Controls CCD-073_ME_POP.pdf
23 09 00-017-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-017-00 Controls Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-03-02 | 2021-02-24 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11452 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-03-02 | Submittal Number: 23 09 00-17.0 From: GRETCHEN TOSHACH Final Due Date: 03/01/21 Subject: CONTROLS SHOP DRAWINGS Description: SEIMENS CONTROLS SHOP DRAWINGS Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 14834 | Forwarded | For Review | 2021-02-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-23 | Submittal Number: 23 09 00-17.0 From: GRETCHEN TOSHACH Final Due Date: 03/01/21 Subject: CONTROLS SHOP DRAWINGS Description: SEIMENS CONTROLS SHOP DRAWINGS Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 11630 | Review Response | Approved as Noted | 2021-02-24 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.02.24 | Info Exchange
| 15077 | Responded and Closed | Approved as Noted | 2021-02-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.02.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 23 09 00-17.0 Controls Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-15 |  | 23 09 00-17.0 Controls Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-02-14 02:00 |  | 23 09 00-17.0 Controls Shop Drawings - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-24 02:00 |  | 23 09 00-17.0 Controls Shop Drawings_ME_POP.pdf
23 09 00-018-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-018-00 BAS Graphics Package | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-02 07:00 | 2021-05-24 | 7 |  | Record Copies; Transfers; Submittals | 23 09 00-018-00-01 - 23 09 00-018-00 BAS Graphics Package | 4 |  | 2021-05-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13128 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-02 07:00 | Submittal Number: 23 09 00-18.0 From: GRETCHEN TOSHACH Final Due Date: 05/28/21 Subject: BAS GRAPHICS PACKAGE Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 16987 | Forwarded | For Review | 2021-05-17 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-24 | Submittal Number: 23 09 00-18.0 From: GRETCHEN TOSHACH Final Due Date: 05/28/21 Subject: BAS GRAPHICS PACKAGE Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 13250 | Review Response | Approved as Noted/Resubmit | 2021-05-20 | Nick Theimer (ME Engineers) | Kuebler Perry (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.05.20 | Info Exchange
| 17146 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-24 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.05.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | 23 09 00-18.0 BAS Graphics - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-17 |  | 23 09 00-18.0 BAS Graphics - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-16 02:00 |  | 23 09 00-18.0 BAS Graphics - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-24 02:00 |  | 23 09 00-18.0 BAS Graphics_ME_POP.pdf
23 09 00-018-00-01 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-018-00 BAS Graphics Package | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 23 09 00-018-00 - 23 09 00-018-00 BAS Graphics Package | -1 | 2021-06-07
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-24 02:00 |  | 23 09 00-18.0 BAS Graphics_ME_POP.pdf
23 09 00-019-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-019-00 Controls Update per CCD 84, 86 and misc RFIs | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-03 07:00 | 2021-06-01 | 14 |  | Record Copies; Transfers; Submittals | 23 09 00-019-00-01 - 23 09 00-019-00 Controls Update per CCD 84, 86 and misc RFIs | 7 |  | 2021-06-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13184 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-03 07:00 | Submittal Number: 23 09 00-19.0 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: CONTROLS UPDATE PER CCD 84, 86 AND MISC RFIS Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 17074 | Forwarded | For Review | 2021-05-19 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-26 | Submittal Number: 23 09 00-19.0 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: CONTROLS UPDATE PER CCD 84, 86 AND MISC RFIS Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 13350 | Review Response | Approved as Noted/Resubmit | 2021-05-25 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.05.25 | Info Exchange
| 17274 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-01 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.05.25 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-19 |  | 23 09 00-19.0 Controls CCD-8486_Misc Changes - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-19 |  | 23 09 00-19.0 Controls CCD-8486_Misc Changes - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-18 02:00 |  | 23 09 00-19.0 Controls CCD-8486_Misc Changes - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-01 02:00 |  | 23 09 00-19.0 Controls CCD-8486_Misc Changes_ME_POP.pdf
23 09 00-019-00-01 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-019-00 Controls Update per CCD 84, 86 and misc RFIs | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 23 09 00-019-00 - 23 09 00-019-00 Controls Update per CCD 84, 86 and misc RFIs | -1 | 2021-06-15
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-01 02:00 |  | 23 09 00-19.0 Controls CCD-8486_Misc Changes_ME_POP.pdf
23 09 00-020-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | 23 09 00-020-00 Controls Compliance Matrix | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-02 07:00 | 2021-06-01 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-06-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13123 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (Mortenson Construction) | 2021-06-02 07:00 | Submittal Number: 23 09 00-20.0 From: GRETCHEN TOSHACH Final Due Date: 05/28/21 Subject: CONTROLS COMPLIANCE MATRIX Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 16983 | Forwarded | For Review | 2021-05-17 | Gretchen Toshach (Mortenson Construction) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-24 | Submittal Number: 23 09 00-20.0 From: GRETCHEN TOSHACH Final Due Date: 05/28/21 Subject: CONTROLS COMPLIANCE MATRIX Description: Spec Section: 23 09 00 - BUILDING AUTOMATION AND AUTOMATICTEMERATURE CONTROL SYSTEMS Status: OPEN | Info Exchange
| 13343 | Review Response | Approved | 2021-05-27 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.05.27 | Info Exchange
| 17265 | Responded and Closed | Approved | 2021-06-01 | Gretchen Toshach (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.05.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | 23 09 00-20.0 Controls Compliance Matrix - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-05-17 |  | 23 09 00-20.0 Controls Compliance Matrix - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-16 02:00 |  | 23 09 00-20.0 Controls Compliance Matrix - MAM.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-06-01 02:00 |  | 23 09 00-20.0 Controls Compliance Matrix_ME_POP.pdf
23 21 13-002-00 | 23 21 13 - HYDRONIC PIPING | 23 21 13-002-00 Hydronic Piping Product Data | Closed | Mechanical | Patrick Klein (Mortenson Construction) | 2019-06-13 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Jeff Sawarynski (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-06-27 | 2019-06-25 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-06-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01506 | Received | For Review | 2019-06-13 | Patrick Klein (Mortenson Construction) | SCA_CCA@populous.com | 2019-06-27 |  | Email
| 02526 | Forwarded | For Review | 2019-06-13 | SCA_CCA@populous.com | Nick Theimer (ME Engineers); Jeff Sawarynski (ME Engineers); Heidi Evans (ME Engineers) | 2019-06-20 |  | Info Exchange
| 01621 | Review Response | Approved as Noted | 2019-06-25 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 02679 | Responded and Closed | Approved as Noted | 2019-06-25 | Populous SCA_CCA | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Patrick Klein (Mortenson Construction) | 1 | 2019-06-13 |  | 23 21 13-002-00 Hydronic Piping Product Data - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-13 |  | 23 21 13-002-00 Hydronic Piping Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-06-25 |  | 23 21 13-002-00 Hydronic Piping Product Data - MAM_ME.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-06-25 |  | 23 21 13-002-00 Hydronic Piping Product Data - MAM_ME_POP.pdf
23 21 13-003-00 | 23 21 13 - HYDRONIC PIPING | 23 21 13-003-00 UG Condenser Water Piping CCD 026 - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-20 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-06 | 2019-12-06 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2019-12-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03279 | Received | For Review | 2019-11-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-06 | Submittal Number: 23 21 13-3.0 From: GRETCHEN TOSHACH Final Due Date: 12/30/19 Subject: UG CONDENSER WATER PIPING CCD 026 - PRODUCT DATA Description: SUBMIT MANUFACTURER PRODUCT DATA PER SPECIFICATIONS FOR UNDERGROUND CONDENSER WATER PIPING AS UPDATED IN RFI 1466 AND ISSUED IN CCD-026. Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 04727 | Forwarded | For Review | 2019-11-20 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-27 | Submittal Number: 23 21 13-3.0 From: GRETCHEN TOSHACH Final Due Date: 12/30/19 Subject: UG CONDENSER WATER PIPING CCD 026 - PRODUCT DATA Description: SUBMIT MANUFACTURER PRODUCT DATA PER SPECIFICATIONS FOR UNDERGROUND CONDENSER WATER PIPING AS UPDATED IN RFI 1466 AND ISSUED IN CCD-026. Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 03533 | Review Response | Approved | 2019-12-06 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| 05003 | Responded and Closed | Approved | 2019-12-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-20 |  | 23 21 13-3.0 UG Cond Piping CCD026 Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-20 |  | 23 21 13-3.0 UG Cond Piping CCD026 Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-19 02:00 |  | 23 21 13-3.0 UG Cond Piping CCD026 Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-06 02:00 |  | 23 21 13-3.0 UG Cond Piping CCD026 Product Data_ME_POP.pdf
23 21 13-004-00 | 23 21 13 - HYDRONIC PIPING | 23 21 13-004-00 Tunnel CDWS/R | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-04 | Responded and Closed - Rejected |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-18 | 2019-12-23 | 20 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2019-12-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03464 | Received | For Review | 2019-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-18 | Submittal Number: 23 21 13-4.0 From: GRETCHEN TOSHACH Final Due Date: 12/17/19 Subject: TUNNEL CDWS/R Description: Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 04939 | Forwarded | For Review | 2019-12-03 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-10 | Submittal Number: 23 21 13-4.0 From: GRETCHEN TOSHACH Final Due Date: 12/17/19 Subject: TUNNEL CDWS/R Description: Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 03568 | Review Response | Approved as Noted | 2019-12-09 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. TT or appropriate structural engineer for tunnel should review pipe hanger loading points through tunnel. Nick Theimer ME Engineers 2019.12.09 | Info Exchange
| 05045 | Forwarded | For Review | 2019-12-10 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth K... | 2019-12-17 | Submittal Number: 23 21 13-4.0 From: GRETCHEN TOSHACH Final Due Date: 12/17/19 Subject: TUNNEL CDWS/R Description: Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 03739 | Review Response | Rejected | 2019-12-23 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  | Provide signed and sealed submittal package. Also provide calculation package along with this submittal. SDK ¦ TT ¦ 12/23/2019 | Info Exchange
| 05272 | Responded and Closed | Rejected | 2019-12-23 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Rejected on the basis of TT's comments provided in submittal. Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. TT or appropriate structural engineer for tunnel should review pipe hanger loading points through tunnel. Nick Theimer ME Engineers 2019.12.09 Response (Rejected) from: Samar Kenkre (Thornton Tomasetti) Remarks: Provide signed and sealed submittal package. Also provide calculation package along with this submittal. SDK ¦ TT ¦ 12/23/2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-03 |  | 23 21 13-4.0 CDWS_R Tunnel Pipe Shop Drawing - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-03 |  | 23 21 13-4.0 CDWS_R Tunnel Pipe Shop Drawing - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-12-02 02:00 |  | 23 21 13-4.0 CDWS_R Tunnel Pipe Shop Drawing - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-02 02:00 |  | 23 21 13-4.0 CDWS_R Tunnel Pipe Shop Drawing - MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-12-02 02:00 |  | 23 21 13-4.0 CDWS_R Tunnel Pipe Shop Drawing - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-02 02:00 |  | 23 21 13-4.0 CDWS_R Tunnel Pipe Shop Drawing - MAM.pdf
23 21 13-004-01 | 23 21 13 - HYDRONIC PIPING | 23 21 13-004-01 Tunnel CDWS/R | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-28 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Matt Ross (Thornton Tomasetti), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-11 | 2020-02-05 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-02-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04088 | Received | For Review | 2020-01-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2020-02-11 | Submittal Number: 23 21 13-4.1 From: GRETCHEN TOSHACH Final Due Date: 02/10/20 Subject: TUNNEL CDWS/R Description: SUBMIT AS SPECIFIED Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 05681 | Forwarded | For Review | 2020-01-28 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-04 | Submittal Number: 23 21 13-4.1 From: GRETCHEN TOSHACH Final Due Date: 02/10/20 Subject: TUNNEL CDWS/R Description: SUBMIT AS SPECIFIED Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 04099 | Review Response | Approved as Noted/Resubmit | 2020-01-28 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for ME Engineers review. The tunnel structural engineer needs to review this as well. Nick Theimer ME Engineers 2020.01.28 | Info Exchange
| 05693 | Forwarded | For Review | 2020-01-28 | Josh Dobken (Populous) | Matt Ross (Thornton Tomasetti) | 2020-02-04 | Submittal Number: 23 21 13-4.1 From: GRETCHEN TOSHACH Final Due Date: 02/10/20 Subject: TUNNEL CDWS/R Description: SUBMIT AS SPECIFIED Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Email
| 05705 | Forwarded | For Review | 2020-01-28 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-02-04 | Submittal Number: 23 21 13-4.1 From: GRETCHEN TOSHACH Final Due Date: 02/10/20 Subject: TUNNEL CDWS/R Description: SUBMIT AS SPECIFIED Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 04211 | Review Response | Approved as Noted | 2020-02-05 | Andy Tatkowski (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached. ART ¦ TT ¦ 2/5/2020 | Info Exchange
| 05834 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for ME Engineers review. The tunnel structural engineer needs to review this as well. Nick Theimer ME Engineers 2020.01.28 Response (Approved as Noted) from: Andy Tatkowski (Thornton Tomasetti) Remarks: See attached. ART ¦ TT ¦ 2/5/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-27 |  | 23 21 13-4.1 CDWSR Tunnel Pipe-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-27 |  | 23 21 13-4.1 CDWSR Tunnel Pipe-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-01-26 02:00 |  | 23 21 13-4.1 CDWSR Tunnel Pipe-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-26 02:00 |  | 23 21 13-4.1 CDWSR Tunnel Pipe-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-26 02:00 |  | 23 21 13-4.1 CDWSR Tunnel Pipe-MAM.pdf
| Review Response |  | Andy Tatkowski (Thornton Tomasetti) | 1 | 2020-01-26 02:00 |  | 23 21 13-4.1 CDWSR Tunnel Pipe-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-05 02:00 |  | 23 21 13-4.1 CDWS_R Tunnel Pipe Shop Drawing_ME_TT_POP.pdf
23 21 13-004-02 | 23 21 13 - HYDRONIC PIPING | 23 21 13-004-02 Tunnel CDWS/R | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-17 | 2020-03-25 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-03-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04589 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 23 21 13-4.2 From: GRETCHEN TOSHACH Final Due Date: 03/11/20 Subject: TUNNEL CDWS/R Description: COMMENT RESPONSES Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 06327 | Forwarded | For Review | 2020-03-02 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-09 | Submittal Number: 23 21 13-4.2 From: GRETCHEN TOSHACH Final Due Date: 03/11/20 Subject: TUNNEL CDWS/R Description: COMMENT RESPONSES Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 04825 | Review Response | Approved as Noted | 2020-03-13 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineer 2020.03.13 | Info Exchange
| 06602 | Forwarded | For Review | 2020-03-13 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-03-17 | Submittal Number: 23 21 13-4.2 From: GRETCHEN TOSHACH Final Due Date: 03/11/20 Subject: TUNNEL CDWS/R Description: COMMENT RESPONSES Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 05038 | Review Response | Approved as Noted | 2020-03-24 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | Only the loads imposed on the tunnel structure have been reviewed. All other information is not reviewed, retained for record. Provide loads imposed and attachment calculations as req'd per General Notes & Specifications for the areas outside the tunnel (as marked on drawings HPI-12 and HPI-13, this submittal). TT-FK ¦ 2020-03-24 | Info Exchange
| 06860 | Responded and Closed | Approved as Noted | 2020-03-25 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Structural engineer to review. Nick Theimer ME Engineer 2020.03.13 Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: Only the loads imposed on the tunnel structure have been reviewed. All other information is not reviewed, retained for record. Provide loads imposed and attachment calculations as req'd per General Notes & Specifications for the areas outside the tunnel (as marked on drawings HPI-12 and HPI-13, this submittal). TT-FK ¦ 2020-03-24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 23 21 13-4.2 CDWSR Tunnel Pipe-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 23 21 13-4.2 CDWSR Tunnel Pipe-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-01 02:00 |  | 23 21 13-4.2 CDWSR Tunnel Pipe-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-01 02:00 |  | 23 21 13-4.2 CDWSR Tunnel Pipe-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-03-01 02:00 |  | 23 21 13-4.2 CDWSR Tunnel Pipe-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-25 02:00 |  | 23 21 13-4.2 CDWS_R Tunnel Pipe Shop Drawing_ME_TT_POP.pdf
23 21 13-006-00 | 23 21 13 - HYDRONIC PIPING | 23 21 13-006-00 Cooling Tower & South Parcel Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-03-03 | 2020-03-02 | 14 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04388 | Received | For Review | 2020-02-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-03 | Submittal Number: 23 21 13-6.0 From: GRETCHEN TOSHACH Final Due Date: 02/26/20 Subject: COOLING TOWER & SOUTH PARCEL SHOP DRAWINGS Description: SHOP DRAWINGS FOR THE SOUTH PARCEL & COOLING TOWER PIPING DRAWINGS. SEISMIC CALCULATIONS TO FOLLOW IN SEPARATE SUBMITTAL UPON LAYOUT APPROVAL. Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 06062 | Forwarded | For Review | 2020-02-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-25 | Submittal Number: 23 21 13-6.0 From: GRETCHEN TOSHACH Final Due Date: 02/26/20 Subject: COOLING TOWER & SOUTH PARCEL SHOP DRAWINGS Description: SHOP DRAWINGS FOR THE SOUTH PARCEL & COOLING TOWER PIPING DRAWINGS. SEISMIC CALCULATIONS TO FOLLOW IN SEPARATE SUBMITTAL UPON LAYOUT APPROVAL. Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 06064 | Forwarded | For Review | 2020-02-18 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-02-25 | Submittal Number: 23 21 13-6.0 From: GRETCHEN TOSHACH Final Due Date: 02/26/20 Subject: COOLING TOWER & SOUTH PARCEL SHOP DRAWINGS Description: SHOP DRAWINGS FOR THE SOUTH PARCEL & COOLING TOWER PIPING DRAWINGS. SEISMIC CALCULATIONS TO FOLLOW IN SEPARATE SUBMITTAL UPON LAYOUT APPROVAL. Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 06068 | Forwarded | For Review | 2020-02-18 | Josh Dobken (Populous) | Matt Ross (Thornton Tomasetti) | 2020-02-25 | Submittal Number: 23 21 13-6.0 From: GRETCHEN TOSHACH Final Due Date: 02/26/20 Subject: COOLING TOWER & SOUTH PARCEL SHOP DRAWINGS Description: SHOP DRAWINGS FOR THE SOUTH PARCEL & COOLING TOWER PIPING DRAWINGS. SEISMIC CALCULATIONS TO FOLLOW IN SEPARATE SUBMITTAL UPON LAYOUT APPROVAL. Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 06280 | Forwarded | For Review | 2020-02-28 | Josh Dobken (Populous) | Andy Tatkowski (Thornton Tomasetti) | 2020-03-03 | Submittal Number: 23 21 13-6.0 From: GRETCHEN TOSHACH Final Due Date: 02/26/20 Subject: COOLING TOWER & SOUTH PARCEL SHOP DRAWINGS Description: SHOP DRAWINGS FOR THE SOUTH PARCEL & COOLING TOWER PIPING DRAWINGS. SEISMIC CALCULATIONS TO FOLLOW IN SEPARATE SUBMITTAL UPON LAYOUT APPROVAL. Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 04578 | Review Response | Approved as Noted | 2020-02-28 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.02.28 | Info Exchange
| 06314 | Responded and Closed | Approved as Noted | 2020-03-02 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.02.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-18 |  | 23 21 13-6.0 CT & SP Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-18 |  | 23 21 13-6.0 CT & SP Shop Drawings - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-17 02:00 |  | 23 21 13-6.0 CT & SP Shop Drawings - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-17 02:00 |  | 23 21 13-6.0 CT & SP Shop Drawings - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-17 02:00 |  | 23 21 13-6.0 CT & SP Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-02-17 02:00 |  | 23 21 13-6.0 CT & SP Shop Drawings - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-02 02:00 |  | 23 21 13-6.0 CT & SP Shop Drawings_ME_POP.pdf
23 21 13-007-00 | 23 21 13 - HYDRONIC PIPING | 23 21 13-007-00 Hydronic Piping Accessories | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-30 | 2020-03-30 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-03-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04842 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 23 21 13-7.0 From: GRETCHEN TOSHACH Final Due Date: 04/13/20 Subject: HYDRONIC PIPING ACCESSORIES Description: STRAINER AND AIR VENT FOR MECHANICAL PIPING Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 06619 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-23 | Submittal Number: 23 21 13-7.0 From: GRETCHEN TOSHACH Final Due Date: 04/13/20 Subject: HYDRONIC PIPING ACCESSORIES Description: STRAINER AND AIR VENT FOR MECHANICAL PIPING Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 05124 | Review Response | Approved | 2020-03-24 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.24 | Info Exchange
| 06955 | Responded and Closed | Approved | 2020-03-30 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 23 21 13-7.0 Hydronic Accessories Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 23 21 13-7.0 Hydronic Accessories Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-16 |  | 23 21 13-7.0 Hydronic Accessories Product Data - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-03-30 |  | 23 21 13-7.0 Hydronic Accessories Product Data_ME_POP.pdf
23 21 13-008-00 | 23 21 13 - HYDRONIC PIPING | 23 21 13-008-00 Coil Connection kits | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-30 | 2020-03-30 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-03-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04843 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 23 21 13-8.0 From: GRETCHEN TOSHACH Final Due Date: 03/30/20 Subject: COIL CONNECTION KITS Description: COIL CONNECTION KITS FOR HYDRONIC HOSE KITS FOR WSHPS, VAVS, AND FCUS Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 06620 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-23 | Submittal Number: 23 21 13-8.0 From: GRETCHEN TOSHACH Final Due Date: 03/30/20 Subject: COIL CONNECTION KITS Description: COIL CONNECTION KITS FOR HYDRONIC HOSE KITS FOR WSHPS, VAVS, AND FCUS Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 05125 | Review Response | Approved as Noted | 2020-03-27 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.27 | Info Exchange
| 06956 | Responded and Closed | Approved as Noted | 2020-03-30 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 23 21 13-8.0 Coil Conn Kits WSHP FCU VAV Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 23 21 13-8.0 Coil Conn Kits WSHP FCU VAV Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-16 |  | 23 21 13-8.0 Coil Conn Kits WSHP FCU VAV Product Data - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-03-30 |  | 23 21 13-8.0 Coil Conn Kits WSHP FCU VAV Product Data_ME_POP.pdf
23 21 13-009-00 | 23 21 13 - HYDRONIC PIPING | 23 21 13-009-00 Hydronic Pipe | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-26 07:00 | 2020-05-26 | 16 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05781 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 23 21 13-9.0 From: GRETCHEN TOSHACH Final Due Date: 05/08/20 Subject: HYDRONIC PIPE Description: PRODUCT DATA FOR HYDRONIC PIPE Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 07838 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 23 21 13-9.0 From: GRETCHEN TOSHACH Final Due Date: 05/08/20 Subject: HYDRONIC PIPE Description: PRODUCT DATA FOR HYDRONIC PIPE Spec Section: 23 21 13 - HYDRONIC PIPING Status: OPEN | Info Exchange
| 06045 | Review Response | Approved | 2020-05-15 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.15 | Info Exchange
| 08189 | Responded and Closed | Approved | 2020-05-26 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 23 21 13-9.0 Hydronic Pipe -MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 23 21 13-9.0 Hydronic Pipe -MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 23 21 13-9.0 Hydronic Pipe -MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-26 02:00 |  | 23 21 13-9.0 Hydronic Pipe_ME_POP.pdf
23 21 23-001-00 | 23 21 23 - HVAC PUMPS | 23 21 23-001-00: HVAC PUMPS - Product Data | Closed | Mechanical | Patrick Klein (Mortenson Construction) | 2019-05-29 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-06-12 | 2019-06-10 | 13 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-06-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01422 | Received | For Review | 2019-05-29 | Patrick Klein (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-12 | Manufacturers Product Data : Submit manufacturers product data on pumps. 1. Include pump curve and mark rating point. Also include single pump operating point fora parallel pump application. 2. Show maximum allowable operating temperature and pressure. 3. Note in red any deviations from specified construction. 4. Show impeller diameter indicate maximum impeller diameter for pump volute provided and indicate if impeller is machined down. MAM reviewed A/E please review and approve | Info Exchange
| 02424 | Forwarded | For Review | 2019-06-03 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-06-10 | Manufacturers Product Data : Submit manufacturers product data on pumps. 1. Include pump curve and mark rating point. Also include single pump operating point fora parallel pump application. 2. Show maximum allowable operating temperature and pressure. 3. Note in red any deviations from specified construction. 4. Show impeller diameter indicate maximum impeller diameter for pump volute provided and indicate if impeller is machined down. MAM reviewed A/E please review and approve | Info Exchange
| 01483 | Review Response | Approved as Noted | 2019-06-10 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | Please see attached for review of Submittal 23 21 23 -1.0 | Info Exchange
| 02494 | Responded and Closed | Approved as Noted | 2019-06-10 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: Please see attached for review of Submittal 23 21 23 -1.0 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Patrick Klein (Mortenson Construction) | 1 | 2019-06-03 |  | 23 21 23-001-00 HVAC Pumps Product Data.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-03 |  | 23 21 23-001-00 HVAC Pumps Product Data.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-06-10 |  | 23 21 23-001-00 HVAC Pumps Product Data_ME_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-03 |  | 23 21 23-001-00 HVAC Pumps Product Data.pdf
23 21 23-002-00 | 23 21 23 - HVAC PUMPS | 23 21 23-002-00 HVAC PUMPS - CCD 021 Pump Revisions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-28 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-09-11 | 2019-08-29 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-08-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02220 | Received | For Review | 2019-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-11 | Submittal Number: 23 21 23-2.0 From: PATRICK KLEIN Final Due Date: 09/10/19 Subject: HVAC PUMPS - CCD 021 PUMP REVISIONS Description: Spec Section: 23 21 23 - HVAC PUMPS Status: OPEN | Info Exchange
| 03431 | Forwarded | For Review | 2019-08-28 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-09-04 | Submittal Number: 23 21 23-2.0 From: PATRICK KLEIN Final Due Date: 09/10/19 Subject: HVAC PUMPS - CCD 021 PUMP REVISIONS Description: Spec Section: 23 21 23 - HVAC PUMPS Status: OPEN | Info Exchange
| 02245 | Review Response | Approved as Noted | 2019-08-28 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.08.28 | Info Exchange
| 03465 | Responded and Closed | Approved as Noted | 2019-08-29 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.08.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-27 |  | 23 21 23-2.0 CCD 021 Revisions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-27 |  | 23 21 23-2.0 CCD 021 Revisions-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-26 02:00 |  | 23 21 23-2.0 CCD 021 Revisions-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-29 02:00 |  | 23 21 23-2.0 CCD 021 Revisions-ME_POP.pdf
23 23 00-001-00 | 23 23 00 - REFRIGERANT PIPING | 23 23 00-001-00 REFRIGERANT PIPING - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-30 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-14 | 2020-12-03 | 4 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09766 | Received | For Review | 2020-11-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) | 2020-12-14 | Submittal Number: 23 23 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 12/14/20 Subject: REFRIGERANT PIPING - PRODUCT DATA Description: Spec Section: 23 23 00 - REFRIGERANT PIPING Status: OPEN | Info Exchange
| 12836 | Forwarded | For Review | 2020-11-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-07 | Submittal Number: 23 23 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 12/14/20 Subject: REFRIGERANT PIPING - PRODUCT DATA Description: Spec Section: 23 23 00 - REFRIGERANT PIPING Status: OPEN | Info Exchange
| 09868 | Review Response | Approved as Noted/Resubmit | 2020-12-02 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.12.02 | Info Exchange
| 12951 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-03 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.12.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-30 |  | 23 23 00-1.0 Refrig Piping fittings valves - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-30 |  | 23 23 00-1.0 Refrig Piping fittings valves - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-30 |  | 23 23 00-1.0 Refrig Piping fittings valves - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-03 |  | 23 23 00-1.0 Refrig Piping fittings valves_ME_POP.pdf
23 23 00-001-01 | 23 23 00 - REFRIGERANT PIPING | 23 23 00-001-01 REFRIGERANT PIPING - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-05 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-19 | 2021-01-11 | 7 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10451 | Received | For Review | 2021-01-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-19 | Submittal Number: 23 23 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 01/19/21 Subject: REFRIGERANT PIPING - PRODUCT DATA Description: Spec Section: 23 23 00 - REFRIGERANT PIPING Status: OPEN | Info Exchange
| 13646 | Forwarded | For Review | 2021-01-05 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-12 | Submittal Number: 23 23 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 01/19/21 Subject: REFRIGERANT PIPING - PRODUCT DATA Description: Spec Section: 23 23 00 - REFRIGERANT PIPING Status: OPEN | Info Exchange
| 10613 | Review Response | Approved as Noted | 2021-01-05 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.01.05 | Info Exchange
| 13820 | Responded and Closed | Approved as Noted | 2021-01-11 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.01.05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-05 |  | 23 23 00-1.1 Refrig Piping - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-05 |  | 23 23 00-1.1 Refrig Piping - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-05 |  | 23 23 00-1.1 Refrig Piping - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-11 |  | 23 23 00-1.1 Refrig Piping_ME_POP.pdf
23 23 00-002-00 | 23 23 00 - REFRIGERANT PIPING | 23 23 00-002-00 Food Service Refrigeration Piping Materials | Closed | Mechanical, Food Services | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-11 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Heidi Evans (ME Engineers) |  |  |  | 2021-02-25 | 2021-02-17 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11336 | Received | For Review | 2021-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (Mortenson Construction) | 2021-02-25 | Submittal Number: 23 23 00-2.0 From: JOSH BROUSSARD Final Due Date: 02/25/21 Subject: FOOD SERVICE REFRIGERATION PIPING MATERIALS Description: SUBMITTAL INCLUDES THE FOLLOWING: ARMAFLEX INUSLATION COPPER TUBING BRAZING FILLER MATERIAL CUSH-A-THERM INSULATION CLAMP STRUT CHANNEL THREADED ROD DROP-IN ANCHOR DROP-IN ANCHOR EVALUATION REPORT Spec Section: 23 23 00 - REFRIGERANT PIPING Status: OPEN | Info Exchange
| 14695 | Forwarded | For Review | 2021-02-11 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Heidi Evans (ME Engineers) | 2021-02-18 | Submittal Number: 23 23 00-2.0 From: JOSH BROUSSARD Final Due Date: 02/25/21 Subject: FOOD SERVICE REFRIGERATION PIPING MATERIALS Description: SUBMITTAL INCLUDES THE FOLLOWING: ARMAFLEX INUSLATION COPPER TUBING BRAZING FILLER MATERIAL CUSH-A-THERM INSULATION CLAMP STRUT CHANNEL THREADED ROD DROP-IN ANCHOR DROP-IN ANCHOR EVALUATION REPORT Spec Section: 23 23 00 - REFRIGERANT PIPING Status: OPEN | Info Exchange
| 11501 | Review Response | Not Required For Review | 2021-02-11 | Peg Galie (S2O Consultants, Inc.) | Populous SCA_CCA |  | Outside foodservice scope | Info Exchange
| 11502 | Review Response | Approved as Noted | 2021-02-16 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.02.16 | Info Exchange
| 14899 | Responded and Closed | Approved as Noted | 2021-02-17 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.02.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-11 |  | 23 23 00-2.0 Food Service Refrigeration Piping Materials.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-11 |  | 23 23 00-2.0 Food Service Refrigeration Piping Materials.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2021-02-11 |  | 23 23 00-2.0 Food Service Refrigeration Piping Materials.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-02-11 |  | 23 23 00-2.0 Food Service Refrigeration Piping Materials.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-02-17 |  | 23 23 00-2.0 Food Service Refrigeration Piping Materials_ME_POP.pdf
23 25 13-001-00 | 23 25 13 - HVAC SYSTEM CHEMICAL TREATMENT | 23 25 13-001-00 HVAC SYSTEM CHEMICAL TREATMENT - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-21 | 2020-07-21 | 15 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06824 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 23 25 13-1.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: HVAC SYSTEM CHEMICAL TREATMENT - PRODUCT DATA Description: PROVIDE PRODUCT DATA FOR EACH PIECE OF EQUIPMENT INSTALLED THE SYSTEM AND FOR EACH CHEMICAL USED. Spec Section: 23 25 13 - HVAC SYSTEM CHEMICAL TREATMENT Status: OPEN | Info Exchange
| 09159 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 23 25 13-1.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: HVAC SYSTEM CHEMICAL TREATMENT - PRODUCT DATA Description: PROVIDE PRODUCT DATA FOR EACH PIECE OF EQUIPMENT INSTALLED THE SYSTEM AND FOR EACH CHEMICAL USED. Spec Section: 23 25 13 - HVAC SYSTEM CHEMICAL TREATMENT Status: OPEN | Info Exchange
| 07060 | Review Response | Approved as Noted | 2020-07-16 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.07.16 | Info Exchange
| 09449 | Responded and Closed | Approved as Noted | 2020-07-21 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-07 |  | 23 25 13-1.0 HVAC Chemical Treatment - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 23 25 13-1.0 HVAC Chemical Treatment - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-07 |  | 23 25 13-1.0 HVAC Chemical Treatment - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-21 |  | 23 25 13-1.0 HVAC Chemical Treatment_ME_POP.pdf
23 25 15-001-00 | 23 25 15 - CENTRIFUGAL SEPARATOR | 23 25 15-001-00 CENTRIFUGAL SEPARATOR - General | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-17 | 2020-03-10 | 8 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04581 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 23 25 15-1.0 From: PATRICK KLEIN Final Due Date: 09/06/19 Subject: CENTRIFUGAL SEPARATOR - GENERAL Description: 1. DESCRIPTION OF SYSTEM OPERATION.- Spec Section: 23 25 15 - CENTRIFUGAL SEPARATOR Status: OPEN | Info Exchange
| 06317 | Forwarded | For Review | 2020-03-02 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-09 | Submittal Number: 23 25 15-1.0 From: PATRICK KLEIN Final Due Date: 09/06/19 Subject: CENTRIFUGAL SEPARATOR - GENERAL Description: 1. DESCRIPTION OF SYSTEM OPERATION.- Spec Section: 23 25 15 - CENTRIFUGAL SEPARATOR Status: OPEN | Info Exchange
| 04740 | Review Response | Approved as Noted | 2020-03-06 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.06 | Info Exchange
| 06512 | Responded and Closed | Approved as Noted | 2020-03-10 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 23 25 15-1.0 Centrifugal Separator and Pump House Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 23 25 15-1.0 Centrifugal Separator and Pump House Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-01 02:00 |  | 23 25 15-1.0 Centrifugal Separator and Pump House Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-10 02:00 |  | 23 25 15-1.0 Centrifugal Separator and Pump House Product Data_ME_POP.pdf
23 25 16-001-00 | 23 25 16 - CONDENSER WATER TREATING SYSTEM | 23 25 16-001-00 CONDENSER WATER TREATING SYSTEM - Manufacturers Instructions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-04 | 2019-12-09 | 22 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2019-12-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03239 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-04 | Submittal Number: 23 25 16-1.0 From: GRETCHEN TOSHACH Final Due Date: 10/21/19 Subject: CONDENSER WATER TREATING SYSTEM - MANUFACTURERS INSTRUCTIONS Description: 1. MANUFACTURERS DATA ON MATERIALS AND EQUIPMENT.- Spec Section: 23 25 16 - CONDENSER WATER TREATING SYSTEM (NON-CHEMICAL) Status: OPEN | Info Exchange
| 04678 | Forwarded | For Review | 2019-11-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-25 | Submittal Number: 23 25 16-1.0 From: GRETCHEN TOSHACH Final Due Date: 10/21/19 Subject: CONDENSER WATER TREATING SYSTEM - MANUFACTURERS INSTRUCTIONS Description: 1. MANUFACTURERS DATA ON MATERIALS AND EQUIPMENT.- Spec Section: 23 25 16 - CONDENSER WATER TREATING SYSTEM (NON-CHEMICAL) Status: OPEN | Info Exchange
| 03551 | Review Response | Approved | 2019-12-06 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| 05020 | Responded and Closed | Approved | 2019-12-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-18 |  | 23 25 16-1.0 Cond Water Treatment Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-18 |  | 23 25 16-1.0 Cond Water Treatment Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-17 02:00 |  | 23 25 16-1.0 Cond Water Treatment Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 23 25 16-1.0 Cond Water Treatment Product Data_ME_POP.pdf
23 26 00-001-00 | 23 26 00 - ENERGY AND WATER METERING DEVICES | 23 26 00-001-00 Flow Meter Schedule and Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-17 | 2020-03-18 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04597 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 23 26 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 04/06/20 Subject: FLOW METER SCHEDULE AND PRODUCT DATA Description: FLOW METER SCHEDULE AND PRODUCT DATA Spec Section: 23 26 00 - ENERGY AND WATER METERING DEVICES Status: OPEN | Info Exchange
| 06335 | Forwarded | For Review | 2020-03-03 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-10 | Submittal Number: 23 26 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 04/06/20 Subject: FLOW METER SCHEDULE AND PRODUCT DATA Description: FLOW METER SCHEDULE AND PRODUCT DATA Spec Section: 23 26 00 - ENERGY AND WATER METERING DEVICES Status: OPEN | Info Exchange
| 04918 | Review Response | Approved as Noted | 2020-03-17 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.17 | Info Exchange
| 06714 | Responded and Closed | Approved as Noted | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 23 26 00-1.0 Flow Meter Schedule and Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 23 26 00-1.0 Flow Meter Schedule and Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-01 02:00 |  | 23 26 00-1.0 Flow Meter Schedule and Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-18 02:00 |  | 23 26 00-1.0 Flow Meter Schedule and Product Data_ME_POP.pdf
23 26 00-002-00 | 23 26 00 - ENERGY AND WATER METERING DEVICES | 23 26 00-002-00 Domestic Water Meters | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-30 | 2020-03-30 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-03-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04844 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 23 26 00-2.0 From: GRETCHEN TOSHACH Final Due Date: 04/06/20 Subject: DOMESTIC WATER METERS Description: Spec Section: 23 26 00 - ENERGY AND WATER METERING DEVICES Status: OPEN | Info Exchange
| 06621 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-23 | Submittal Number: 23 26 00-2.0 From: GRETCHEN TOSHACH Final Due Date: 04/06/20 Subject: DOMESTIC WATER METERS Description: Spec Section: 23 26 00 - ENERGY AND WATER METERING DEVICES Status: OPEN | Info Exchange
| 05126 | Review Response | Approved as Noted | 2020-03-24 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.24 | Info Exchange
| 06958 | Responded and Closed | Approved as Noted | 2020-03-30 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 23 26 00-2.0 Domestic Water Meters Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 23 26 00-2.0 Domestic Water Meters Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-16 |  | 23 26 00-2.0 Domestic Water Meters Product Data - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-03-30 |  | 23 26 00-2.0 Domestic Water Meters Product Data_ME_POP.pdf
23 26 00-003-00 | 23 26 00 - ENERGY AND WATER METERING DEVICES | 23 26 00-003-00 Additional Building Water Meter | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-18 | 2021-02-15 | 12 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11193 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction) | 2021-02-18 | Submittal Number: 23 26 00-3.0 From: SIMRAN GEORGE Final Due Date: 02/17/21 Subject: ADDITIONAL BUILDING WATER METER Description: Spec Section: 23 26 00 - ENERGY AND WATER METERING DEVICES Status: OPEN | Info Exchange
| 14499 | Forwarded | For Review | 2021-02-04 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-11 | Submittal Number: 23 26 00-3.0 From: SIMRAN GEORGE Final Due Date: 02/17/21 Subject: ADDITIONAL BUILDING WATER METER Description: Spec Section: 23 26 00 - ENERGY AND WATER METERING DEVICES Status: OPEN | Info Exchange
| 11442 | Review Response | Approved | 2021-02-04 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.02.04 | Info Exchange
| 14823 | Responded and Closed | Approved | 2021-02-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.02.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-03 |  | 23 26 00-3.0 Additional Building Water Meter Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-03 |  | 23 26 00-3.0 Additional Building Water Meter Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-02-02 02:00 |  | 23 26 00-3.0 Additional Building Water Meter Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-15 02:00 |  | 23 26 00-3.0 Additional Building Water Meter Product Data_ME_POP.pdf
23 26 00-004-00 | 23 26 00 - ENERGY AND WATER METERING DEVICES | 23 26 00-004-00 Sewer Submeter - Neptune MACH 10 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-03 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-05-17 | 2021-05-06 | 4 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12926 | Received | For Review | 2021-05-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-17 | Submittal Number: 23 26 00-4.0 From: SIMRAN GEORGE Final Due Date: 05/19/21 Subject: SEWER SUBMETER - NEPTUNE MACH 10 Description: Spec Section: 23 26 00 - ENERGY AND WATER METERING DEVICES Status: OPEN | Info Exchange
| 16707 | Forwarded | For Review | 2021-05-04 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-11 | Submittal Number: 23 26 00-4.0 From: SIMRAN GEORGE Final Due Date: 05/19/21 Subject: SEWER SUBMETER - NEPTUNE MACH 10 Description: Spec Section: 23 26 00 - ENERGY AND WATER METERING DEVICES Status: OPEN | Info Exchange
| 12972 | Review Response | Approved | 2021-05-04 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.05.04 | Info Exchange
| 16791 | Responded and Closed | Approved | 2021-05-06 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.05.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-03 |  | 23 26 00-4.0 Sewer Submeter - Neptune Mach 10 - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-03 |  | 23 26 00-4.0 Sewer Submeter - Neptune Mach 10 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-02 02:00 |  | 23 26 00-4.0 Sewer Submeter - Neptune Mach 10 - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-06 02:00 |  | 23 26 00-4.0 Sewer Submeter - Neptune Mach 10_ME_POP.pdf
23 31 13-003-00 | 23 31 13 - DUCTWORK | 23 31 13-003-00: DUCTWORK - Product Data | Closed | Mechanical | Patrick Klein (Mortenson Construction) | 2019-06-06 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-06-20 | 2019-06-20 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-06-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01466 | Received | For Review | 2019-06-06 | Patrick Klein (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-20 | Product Data : Submit manufacturers product data on the following: 1. Duct lining. 2. Duct lining adhesive. MAM Reviewed. A/E please review, provide comment, and approve. | Info Exchange
| 02473 | Forwarded | For Review | 2019-06-07 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-06-14 | Product Data : Submit manufacturers product data on the following: 1. Duct lining. 2. Duct lining adhesive. MAM Reviewed. A/E please review, provide comment, and approve. | Info Exchange
| 01589 | Review Response | Revise and Resubmit | 2019-06-20 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | Please find attached review of Submittal 23 31 13 -003-00. | Info Exchange
| 02630 | Responded and Closed | Approved as Noted/Resubmit | 2019-06-20 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: Please find attached review of Submittal 23 31 13 -003-00. POP comments - revise and resubmit specific items per consultant's comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Patrick Klein (Mortenson Construction) | 1 | 2019-06-07 |  | 23 31 13-3.0 Ductwork Product Data - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-07 |  | 23 31 13-3.0 Ductwork Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-06-20 |  | 23 31 13-3.0 Ductwork Product Data - MAM_ME.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-20 |  | 23 31 13-3.0 Ductwork Product Data - MAM_ME_POP.pdf
23 31 13-003-01 | 23 31 13 - DUCTWORK | 23 31 13-003-01 DUCTWORK - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-01 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-07-16 | 2019-07-08 | 8 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2019-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01666 | Received | For Review | 2019-07-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-16 | Submittal Number: 23 31 13-3.1 From: PATRICK KLEIN Final Due Date: 07/15/19 Subject: DUCTWORK - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA ON THE FOLLOWING: 1. DUCT LINING. 2. DUCT LINING ADHESIVE. Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 02738 | Forwarded | For Review | 2019-07-02 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) |  | Submittal Number: 23 31 13-3.1 From: PATRICK KLEIN Final Due Date: 07/15/19 Subject: DUCTWORK - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA ON THE FOLLOWING: 1. DUCT LINING. 2. DUCT LINING ADHESIVE. Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 01694 | Review Response | Approved | 2019-07-07 | Nick Theimer (ME Engineers) | Shaina Burris (Populous) |  | Please see attached for review of Submittal 23 31 13-003-01. | Info Exchange
| 02780 | Responded and Closed | Approved as Noted/Resubmit | 2019-07-08 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: Please see attached for review of Submittal 23 31 13-003-01. POP - please submit missing items as indicated | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-01 |  | 23 31 13-3.1 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-02 |  | 23 31 13-3.1 Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-07 |  | 23 31 13-3.1 Product Data-MAM_ME.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-08 |  | 23 31 13-3.1 Product Data-MAM_ME_POP.pdf
23 31 13-003-02 | 23 31 13 - DUCTWORK | 23 31 13-003-02 DUCTWORK - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-30 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-14 | 2020-04-14 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-04-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05104 | Received | For Review | 2020-03-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-14 | Submittal Number: 23 31 13-3.2 From: PATRICK KLEIN Final Due Date: 04/10/20 Subject: DUCTWORK - PRODUCT DATA Description: SUBMIT PRODUCT DATA ON DISHWASHER EXHAUST DUCT, VAPOR LADEN DUCT (SHOWER AND LOCKER ROOM EXHAUST), GREASE LADEN DUCT, CONTRACTOR FABRICATED CASINGS AND PLENUMS, AND FACTORY FABRICATED PLENUMS OMITTED FROM PREVIOUS SUBMITTAL Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 06932 | Forwarded | For Review | 2020-03-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-06 | Submittal Number: 23 31 13-3.2 From: PATRICK KLEIN Final Due Date: 04/10/20 Subject: DUCTWORK - PRODUCT DATA Description: SUBMIT PRODUCT DATA ON DISHWASHER EXHAUST DUCT, VAPOR LADEN DUCT (SHOWER AND LOCKER ROOM EXHAUST), GREASE LADEN DUCT, CONTRACTOR FABRICATED CASINGS AND PLENUMS, AND FACTORY FABRICATED PLENUMS OMITTED FROM PREVIOUS SUBMITTAL Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 05339 | Review Response | Approved as Noted | 2020-04-13 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.04.13 | Info Exchange
| 07261 | Responded and Closed | Approved as Noted | 2020-04-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.04.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-27 |  | 23 31 13-3.2 Ductwork Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-27 |  | 23 31 13-3.2 Ductwork Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-26 02:00 |  | 23 31 13-3.2 Ductwork Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-14 02:00 |  | 23 31 13-3.2 Ductwork Product Data_ME_POP.pdf
23 31 13-004-00 | 23 31 13 - DUCTWORK | 23 31 13-004-00 Bowl Ductwork - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-21 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-11-04 | 2019-11-04 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-11-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02847 | Received | For Review | 2019-10-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-11-04 | Submittal Number: 23 31 13-4.0 From: GRETCHEN TOSHACH Final Due Date: 11/08/19 Subject: BOWL DUCTWORK - PRODUCT DATA Description: PRODUCT DATA FOR BOWL DUCT. THIS K-27 PRODUCT WAS NOT INCLUDED WITH THE PREVIOUS DUCTWORK SUBMITTAL. Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 04205 | Forwarded | For Review | 2019-10-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-25 | Submittal Number: 23 31 13-4.0 From: GRETCHEN TOSHACH Final Due Date: 11/08/19 Subject: BOWL DUCTWORK - PRODUCT DATA Description: PRODUCT DATA FOR BOWL DUCT. THIS K-27 PRODUCT WAS NOT INCLUDED WITH THE PREVIOUS DUCTWORK SUBMITTAL. Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 03031 | Review Response | Approved | 2019-11-01 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.11.01 | Info Exchange
| 04420 | Responded and Closed | Approved | 2019-11-04 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.11.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-18 |  | 23 31 13-4.0 Bowl Ductwork submittal-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-18 |  | 23 31 13-4.0 Bowl Ductwork submittal-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-10-17 02:00 |  | 23 31 13-4.0 Bowl Ductwork submittal-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-04 02:00 |  | 23 31 13-4.0 Bowl Ductwork submittal-ME_POP.pdf
23 31 13-005-00 | 23 31 13 - DUCTWORK | 23 31 13-005-00 Catwalk Ductwork Sheet Metal - Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-09 08:00 | 2019-12-06 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-12-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03317 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) | 2019-12-09 08:00 | Submittal Number: 23 31 13-5.0 From: SIMRAN GEORGE Final Due Date: 12/13/19 Subject: CATWALK DUCTWORK SHEET METAL - SHOP DRAWINGS Description: Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 04771 | Forwarded | For Review | 2019-11-21 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-27 | Submittal Number: 23 31 13-5.0 From: SIMRAN GEORGE Final Due Date: 12/13/19 Subject: CATWALK DUCTWORK SHEET METAL - SHOP DRAWINGS Description: Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 03536 | Review Response | Approved as Noted | 2019-12-06 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| 05006 | Responded and Closed | Approved as Noted | 2019-12-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-21 |  | 23 31 13-5.0 Catwalk Ductwork Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-21 |  | 23 31 13-5.0 Catwalk Ductwork Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-20 02:00 |  | 23 31 13-5.0 Catwalk Ductwork Shop Drawings - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-06 02:00 |  | 23 31 13-5.0 Catwalk Ductwork Shop Drawings_ME_POP.pdf
23 31 13-005-01 | 23 31 13 - DUCTWORK | 23 31 13-005-01 Catwalk Ductwork Sheet Metal - Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-06 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-20 | 2020-01-10 | 5 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-01-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03801 | Received | For Review | 2020-01-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2020-01-20 | Submittal Number: 23 31 13-5.1 From: SIMRAN GEORGE Final Due Date: 01/22/20 Subject: CATWALK DUCTWORK SHEET METAL - SHOP DRAWINGS Description: RESPONSES TO PREVIOUS COMMENTS ADDRESSED. Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 05339 | Forwarded | For Review | 2020-01-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-13 | Submittal Number: 23 31 13-5.1 From: SIMRAN GEORGE Final Due Date: 01/22/20 Subject: CATWALK DUCTWORK SHEET METAL - SHOP DRAWINGS Description: RESPONSES TO PREVIOUS COMMENTS ADDRESSED. Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 03875 | Review Response | Approved as Noted | 2020-01-09 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.01.09 | Info Exchange
| 05427 | Responded and Closed | Approved as Noted | 2020-01-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.01.09 | Info Exchange
| 05451 | Sent | For Information Only | 2020-01-13 | Josh Dobken (Populous) | Simran George (Mortenson Construction) |  | Responded and Closed (Approved as Noted) to: Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) Remarks: Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.01.09 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-06 |  | 23 31 13-5.1 Catwalk Ductwork Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-06 |  | 23 31 13-5.1 Catwalk Ductwork Shop Drawings - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-01-05 02:00 |  | 23 31 13-5.1 Catwalk Ductwork Shop Drawings - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-05 02:00 |  | 23 31 13-5.1 Catwalk Ductwork Shop Drawings - MAM.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-01-10 02:00 |  | 23 31 13-5.1 Catwalk Ductwork Shop Drawings_ME_POP.pdf
23 31 13-006-00 | 23 31 13 - DUCTWORK | 23 31 13-006-00 Factory Fabricated Plenums | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-23 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-07 | 2020-04-28 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05500 | Received | For Review | 2020-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-07 | Submittal Number: 23 31 13-6.0 From: GRETCHEN TOSHACH Final Due Date: 04/29/20 Subject: FACTORY FABRICATED PLENUMS Description: FACTORY FABRICATED PLENUMS Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 07458 | Forwarded | For Review | 2020-04-22 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-29 | Submittal Number: 23 31 13-6.0 From: GRETCHEN TOSHACH Final Due Date: 04/29/20 Subject: FACTORY FABRICATED PLENUMS Description: FACTORY FABRICATED PLENUMS Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 05604 | Review Response | Approved as Noted/Resubmit | 2020-04-27 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.4.27 | Info Exchange
| 07596 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.4.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 23 31 13-6.0 Semco Factory Plenums - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 23 31 13-6.0 Semco Factory Plenums - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-21 02:00 |  | 23 31 13-6.0 Semco Factory Plenums - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-28 02:00 |  | 23 31 13-6.0 Semco Factory Plenums_ME_POP.pdf
23 31 13-006-01 | 23 31 13 - DUCTWORK | 23 31 13-006-01 Factory Fabricated Plenums | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-08 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-22 | 2020-12-14 | 7 |  | Record Copies; Transfers; Submittals | 23 31 13-006-01-01 - 23 31 13-006-01 Factory Fabricated Plenums | 4 |  | 2020-12-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10007 | Received | For Review | 2020-12-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-22 | Submittal Number: 23 31 13-6.1 From: GRETCHEN TOSHACH Final Due Date: 12/22/20 Subject: FACTORY FABRICATED PLENUMS Description: FACTORY FABRICATED PLENUMS ADDITIONAL PRODUCT DATA AND EXACT SHOP DRAWING LOCATIONS, PER SUBMITTAL REVIEW COMMENTS. Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 13095 | Forwarded | For Review | 2020-12-08 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-15 | Submittal Number: 23 31 13-6.1 From: GRETCHEN TOSHACH Final Due Date: 12/22/20 Subject: FACTORY FABRICATED PLENUMS Description: FACTORY FABRICATED PLENUMS ADDITIONAL PRODUCT DATA AND EXACT SHOP DRAWING LOCATIONS, PER SUBMITTAL REVIEW COMMENTS. Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 10146 | Review Response | Approved as Noted/Resubmit | 2020-12-11 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.12.11 | Info Exchange
| 13269 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-14 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.12.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-08 |  | 23 31 13-6.1 Factory Plenums Locations - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-08 |  | 23 31 13-6.1 Factory Plenums Locations - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-12-08 |  | 23 31 13-6.1 Factory Plenums Locations - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-14 |  | 23 31 13-6.1 Semco Factory Plenums_ME_POP.pdf
23 31 13-006-01-01 | 23 31 13 - DUCTWORK | 23 31 13-006-01 Factory Fabricated Plenums | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 23 31 13-006-01 - 23 31 13-006-01 Factory Fabricated Plenums | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-14 |  | 23 31 13-6.1 Semco Factory Plenums_ME_POP.pdf
23 31 13-007-00 | 23 31 13 - DUCTWORK | 23 31 13-007-00 Semco - Fire Rated Barrier Ductwork | Closed | Mechanical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Todd Spangler (Populous) |  |  |  | 2020-10-07 | 2020-10-02 | 10 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-10-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08291 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 23 31 13-7.0 From: GRETCHEN TOSHACH Final Due Date: 10/02/20 Subject: SEMCO - FIRE RATED BARRIER DUCTWORK Description: Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 10997 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-30 | Submittal Number: 23 31 13-7.0 From: GRETCHEN TOSHACH Final Due Date: 10/02/20 Subject: SEMCO - FIRE RATED BARRIER DUCTWORK Description: Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 08515 | Review Response | Approved | 2020-09-28 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Architect to comment on any additional insulation required to provide meet the exterior envelope inuslation requirements. Nick Theimer ME Engineers 2020.09.28 | Info Exchange
| 11143 | Forwarded | For Review | 2020-09-29 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2020-10-06 | Submittal Number: 23 31 13-7.0 From: GRETCHEN TOSHACH Final Due Date: 10/02/20 Subject: SEMCO - FIRE RATED BARRIER DUCTWORK Description: Spec Section: 23 31 13 - DUCTWORK Status: OPEN | Info Exchange
| 11266 | Responded and Closed | Approved as Noted | 2020-10-02 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.09.28 Response (Approved as Noted) from: Bryan Klote (Populous) Remarks: Further discussion/coordination required on insulation requirements. BK/Populous 2020.10.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 23 31 13-7.0 Semco Fire Rated Barrier Ductwork - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 23 31 13-7.0 Semco Fire Rated Barrier Ductwork - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-23 |  | 23 31 13-7.0 Semco Fire Rated Barrier Ductwork - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-22 02:00 |  | 23 31 13-7.0 Semco Fire Rated Barrier Ductwork - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-02 |  | 23 31 13-7.0 Semco Fire Rated Barrier Ductwork_ME_POP.pdf
23 33 00-001-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-001-00 DUCTWORK ACCESSORIES - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-16 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-30 | 2019-09-05 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2019-09-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02099 | Received | For Review | 2019-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-30 | Submittal Number: 23 33 00-1.0 From: PATRICK KLEIN Final Due Date: 08/30/19 Subject: DUCTWORK ACCESSORIES - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA ON THE FOLLOWING: 1. FLEXIBLE DUCT 2. CEILING DAMPERS 3. FIRE DAMPERS 4. SMOKE DAMPERS 5. LOUVERS 6. LOUVERED PENTHOUSES 7. ROOF-MOUNTED INTAKES 8. ROOF-MOUNTED RELIEFS 9. GRAVITY RELIEF DAMPERS 10. SOUND ATTENUATORS Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 03275 | Forwarded | For Review | 2019-08-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-23 | Submittal Number: 23 33 00-1.0 From: PATRICK KLEIN Final Due Date: 08/30/19 Subject: DUCTWORK ACCESSORIES - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA ON THE FOLLOWING: 1. FLEXIBLE DUCT 2. CEILING DAMPERS 3. FIRE DAMPERS 4. SMOKE DAMPERS 5. LOUVERS 6. LOUVERED PENTHOUSES 7. ROOF-MOUNTED INTAKES 8. ROOF-MOUNTED RELIEFS 9. GRAVITY RELIEF DAMPERS 10. SOUND ATTENUATORS Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 02312 | Review Response | Revise and Resubmit | 2019-09-05 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Revise and resubmit per disposition comments. Nick Theimer ME Engineers 2019.09.05 | Info Exchange
| 03543 | Responded and Closed | Approved as Noted/Resubmit | 2019-09-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Revise and resubmit per disposition comments. Nick Theimer ME Engineers 2019.09.05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-16 |  | 23 33 00-1.0 Ductwork Accessories Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-16 |  | 23 33 00-1.0 Ductwork Accessories Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-15 02:00 |  | 23 33 00-1.0 Ductwork Accessories Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-05 02:00 |  | 23 33 00-1.0 Ductwork Accessories Product Data - ME_POP.pdf
23 33 00-001-01 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-001-01 DUCTWORK ACCESSORIES - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-25 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-11-08 | 2019-11-04 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-11-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02918 | Received | For Review | 2019-10-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-11-08 | Submittal Number: 23 33 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/07/19 Subject: DUCTWORK ACCESSORIES - PRODUCT DATA Description: REVISE AND RESUBMIT PRODUCT DATA FOR SOUND ATTENUATORS AND SMOKE DAMPERS. IF NEEDED, REVISE AND RESUBMIT MANUFACTURERS PRODUCT DATA ON THE FOLLOWING: 1. FIRE DAMPERS 2. FIRE SMOKE DAMPERS. Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 04289 | Forwarded | For Review | 2019-10-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-01 | Submittal Number: 23 33 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/07/19 Subject: DUCTWORK ACCESSORIES - PRODUCT DATA Description: REVISE AND RESUBMIT PRODUCT DATA FOR SOUND ATTENUATORS AND SMOKE DAMPERS. IF NEEDED, REVISE AND RESUBMIT MANUFACTURERS PRODUCT DATA ON THE FOLLOWING: 1. FIRE DAMPERS 2. FIRE SMOKE DAMPERS. Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 03032 | Review Response | Approved as Noted | 2019-11-01 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.11.01 | Info Exchange
| 04421 | Responded and Closed | Approved as Noted | 2019-11-04 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.11.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-24 |  | 23 33 00-1.1 Ductwork Accessories Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-24 |  | 23 33 00-1.1 Ductwork Accessories Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-10-23 02:00 |  | 23 33 00-1.1 Ductwork Accessories Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-04 02:00 |  | 23 33 00-1.1 Ductwork Accessories Product Data - ME_POP.pdf
23 33 00-002-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-002-00 Bowl Duct Hangers | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-10 | 2019-12-19 | 2 | General | Record Copies; Transfers; Submittals |  | 2 |  | 2019-12-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03677 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2020-01-10 | Submittal Number: 23 33 00-2.0 From: GRETCHEN TOSHACH Final Due Date: 12/24/19 Subject: BOWL DUCT HANGERS Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 05197 | Forwarded | For Review | 2019-12-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-25 | Submittal Number: 23 33 00-2.0 From: GRETCHEN TOSHACH Final Due Date: 12/24/19 Subject: BOWL DUCT HANGERS Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 03710 | Review Response | Approved as Noted | 2019-12-19 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.19 | Info Exchange
| 05240 | Responded and Closed | Approved as Noted | 2019-12-19 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.19 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 23 33 00-2.0 Bowl Duct Hangers - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-18 |  | 23 33 00-2.0 Bowl Duct Hangers - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-12-17 02:00 |  | 23 33 00-2.0 Bowl Duct Hangers - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-19 02:00 |  | 23 33 00-2.0 Bowl Duct Hangers_ME_POP.pdf
23 33 00-003-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-003-00 Return Air Flex Duct | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-25 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-10 | 2020-03-02 | 7 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04486 | Received | For Review | 2020-02-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-10 | Submittal Number: 23 33 00-3.0 From: GRETCHEN TOSHACH Final Due Date: 03/31/20 Subject: RETURN AIR FLEX DUCT Description: PRODUCT DATA FOR RETURN AIR FLEX DUCT Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 06180 | Forwarded | For Review | 2020-02-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-03 | Submittal Number: 23 33 00-3.0 From: GRETCHEN TOSHACH Final Due Date: 03/31/20 Subject: RETURN AIR FLEX DUCT Description: PRODUCT DATA FOR RETURN AIR FLEX DUCT Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 04587 | Review Response | Approved | 2020-02-28 | Nick Theimer (ME Engineers) | Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.02.28 | Info Exchange
| 06324 | Responded and Closed | Approved | 2020-03-02 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.02.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-25 |  | 23 33 00-3.0 Return Air Flex Duct - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-25 |  | 23 33 00-3.0 Return Air Flex Duct - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-02-24 02:00 |  | 23 33 00-3.0 Return Air Flex Duct - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-02 02:00 |  | 23 33 00-3.0 Return Air Flex Duct_ME_POP.pdf
23 33 00-004-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-004-00 Duct Hangers | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-30 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-14 07:00 | 2020-04-14 | 16 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-04-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05094 | Received | For Review | 2020-03-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-14 07:00 | Submittal Number: 23 33 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 04/10/20 Subject: DUCT HANGERS Description: HANGERS FOR ALL DUCTWORK. PREVIOUSLY SUBMITTED HANGERS FOR BOWLDUCT ONLY Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 06922 | Forwarded | For Review | 2020-03-27 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-03 | Submittal Number: 23 33 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 04/10/20 Subject: DUCT HANGERS Description: HANGERS FOR ALL DUCTWORK. PREVIOUSLY SUBMITTED HANGERS FOR BOWLDUCT ONLY Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 05340 | Review Response | Approved | 2020-04-13 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.04.13 | Info Exchange
| 07262 | Responded and Closed | Approved | 2020-04-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.04.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-27 |  | 23 33 00-4.0 Duct Hangers Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-27 |  | 23 33 00-4.0 Duct Hangers Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-26 02:00 |  | 23 33 00-4.0 Duct Hangers Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-14 02:00 |  | 23 33 00-4.0 Duct Hangers Product Data_ME_POP.pdf
23 33 00-005-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-005-00 Remote Dampers Battery | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-17 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-01 | 2020-06-24 | 8 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06463 | Received | For Review | 2020-06-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-01 | Submittal Number: 23 33 00-5.0 From: SIMRAN GEORGE Final Due Date: 07/01/20 Subject: REMOTE DAMPERS BATTERY Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 08712 | Forwarded | For Review | 2020-06-17 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-24 | Submittal Number: 23 33 00-5.0 From: SIMRAN GEORGE Final Due Date: 07/01/20 Subject: REMOTE DAMPERS BATTERY Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 06709 | Review Response | Approved | 2020-06-22 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.06.22 | Info Exchange
| 08872 | Responded and Closed | Approved | 2020-06-24 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.06.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 23 33 00-5.0 Remote Battery Dampers - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-17 |  | 23 33 00-5.0 Remote Battery Dampers - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-16 02:00 |  | 23 33 00-5.0 Remote Battery Dampers - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-24 |  | 23 33 00-5.0 Remote Battery Dampers_ME_POP.pdf
23 33 00-006-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-006-00 Stainless Dampers | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-21 | 2020-08-11 | 5 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-08-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07453 | Received | For Review | 2020-08-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-08-21 | Submittal Number: 23 33 00-6.0 From: GRETCHEN TOSHACH Final Due Date: 08/20/20 Subject: STAINLESS DAMPERS Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 09921 | Forwarded | For Review | 2020-08-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-14 | Submittal Number: 23 33 00-6.0 From: GRETCHEN TOSHACH Final Due Date: 08/20/20 Subject: STAINLESS DAMPERS Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 07513 | Review Response | Approved as Noted | 2020-08-10 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.08.10 | Info Exchange
| 10002 | Responded and Closed | Approved as Noted | 2020-08-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.08.10 | Info Exchange
| 10060 | Sent | For Information Only | 2020-08-14 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.08.10 | Info Exchange
| 10324 | Sent | For Information Only | 2020-08-26 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Sent to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) Remarks: Responded and Closed (Approved as Noted) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.08.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | 23 33 00-6.0 Stainless Steel Dampers - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-06 |  | 23 33 00-6.0 Stainless Steel Dampers - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-08-05 02:00 |  | 23 33 00-6.0 Stainless Steel Dampers - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-11 02:00 |  | 23 33 00-6.0 Stainless Steel Dampers_ME_pop.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-08-05 02:00 |  | 23 33 00-6.0 Stainless Steel Dampers - MAM.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-08-05 02:00 |  | 23 33 00-6.0 Stainless Steel Dampers - MAM.pdf
23 33 00-006-01 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-006-01 Stainless Dampers | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-19 | 2020-10-13 | 9 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08559 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 23 33 00-6.1 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: STAINLESS DAMPERS Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 11318 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-12 | Submittal Number: 23 33 00-6.1 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: STAINLESS DAMPERS Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 08764 | Review Response | Approved | 2020-10-06 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.10.06 | Info Exchange
| 11590 | Responded and Closed | Approved | 2020-10-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.06 | Info Exchange
| 11975 | Sent | For Information Only | 2020-10-28 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 23 33 00-6.1 Stainless Dampers Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 23 33 00-6.1 Stainless Dampers Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-10-04 02:00 |  | 23 33 00-6.1 Stainless Dampers Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-13 02:00 |  | 23 33 00-6.1 Stainless Steel Dampers_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-10-04 02:00 |  | 23 33 00-6.1 Stainless Dampers Product Data - MAM.pdf
23 33 00-007-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-007-00 Damper Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-21 | 2020-07-21 | 15 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06810 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 23 33 00-7.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: DAMPER PRODUCT DATA Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 09144 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 23 33 00-7.0 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: DAMPER PRODUCT DATA Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 07061 | Review Response | Approved | 2020-07-14 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| 09450 | Responded and Closed | Approved as Noted | 2020-07-21 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 23 33 00-7.0 Dampers - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 23 33 00-7.0 Dampers - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-06 |  | 23 33 00-7.0 Dampers - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-21 |  | 23 33 00-7.0 Dampers_ME_POP.pdf
23 33 00-007-01 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-007-01 Damper Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-27 08:00 | 2021-01-20 | 9 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10654 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-27 08:00 | Submittal Number: 23 33 00-7.1 From: GRETCHEN TOSHACH Final Due Date: 01/26/21 Subject: DAMPER PRODUCT DATA Description: SUBMIT LOCATION OF WALL PLATES FOR APPROVAL Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 13864 | Forwarded | For Review | 2021-01-12 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-19 | Submittal Number: 23 33 00-7.1 From: GRETCHEN TOSHACH Final Due Date: 01/26/21 Subject: DAMPER PRODUCT DATA Description: SUBMIT LOCATION OF WALL PLATES FOR APPROVAL Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 10808 | Review Response | Approved as Noted | 2021-01-13 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.01.13 | Info Exchange
| 14057 | Responded and Closed | Approved as Noted | 2021-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.01.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 23 33 00-7.1 Remote Damper Balance - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 23 33 00-7.1 Remote Damper Balance - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-11 02:00 |  | 23 33 00-7.1 Remote Damper Balance - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-20 02:00 |  | 23 33 00-7.1 Remote Damper Balance_ME_pop.pdf
23 33 00-008-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-008-00 Damper Alternate Actuator | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-24 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-08 | 2020-09-29 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08307 | Received | For Review | 2020-09-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-08 | Submittal Number: 23 33 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 10/07/20 Subject: DAMPER ALTERNATE ACTUATOR Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 11014 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-01 | Submittal Number: 23 33 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 10/07/20 Subject: DAMPER ALTERNATE ACTUATOR Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 08426 | Review Response | Approved as Noted | 2020-09-24 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| 11163 | Responded and Closed | Approved as Noted | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 23 33 00-8.0 Damper Alt Actuator - MAM (1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 23 33 00-8.0 Damper Alt Actuator - MAM (1).pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-23 |  | 23 33 00-8.0 Damper Alt Actuator - MAM (1).pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 23 33 00-8.0 Damper Alt Actuator_ME_POP.pdf
23 33 00-009-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-009-00 Control Dampers | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-24 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-08 | 2020-09-29 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08309 | Received | For Review | 2020-09-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-08 | Submittal Number: 23 33 00-9.0 From: GRETCHEN TOSHACH Final Due Date: 10/07/20 Subject: CONTROL DAMPERS Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 11016 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) |  | Submittal Number: 23 33 00-9.0 From: GRETCHEN TOSHACH Final Due Date: 10/07/20 Subject: CONTROL DAMPERS Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 08425 | Review Response | Approved | 2020-09-24 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| 11161 | Responded and Closed | Approved | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 23 3300.9 Control Damper Sumbittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 23 33 00-9.0 Control Damper Sumbittal.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-23 |  | 23 33 00-9.0 Control Damper Sumbittal.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 23 33 00-9.0 Control Damper Sumbittal_ME_POP.pdf
23 33 00-010-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-010-00 Various Accessories | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-19 | 2020-10-13 | 9 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08558 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 23 33 00-10.0 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: VARIOUS ACCESSORIES Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 11317 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-12 | Submittal Number: 23 33 00-10.0 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: VARIOUS ACCESSORIES Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 08765 | Review Response | Approved as Noted | 2020-10-09 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.10.09 | Info Exchange
| 11591 | Responded and Closed | Approved as Noted | 2020-10-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.09 | Info Exchange
| 11974 | Sent | For Information Only | 2020-10-28 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.09 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 23 33 00-10.0 Various Accessories - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 23 33 00-10.0 Various Accessories - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-10-04 02:00 |  | 23 33 00-10.0 Various Accessories - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-13 02:00 |  | 23 33 00-10.0 Various Accessories_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-10-04 02:00 |  | 23 33 00-10.0 Various Accessories - MAM.pdf
23 33 00-011-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-011-00 Stainless Steel CB Dampers | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-27 08:00 | 2021-01-20 | 9 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10655 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-01-27 08:00 | Submittal Number: 23 33 00-11.0 From: GRETCHEN TOSHACH Final Due Date: 01/26/21 Subject: STAINLESS STEEL CB DAMPERS Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 13865 | Forwarded | For Review | 2021-01-12 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-19 | Submittal Number: 23 33 00-11.0 From: GRETCHEN TOSHACH Final Due Date: 01/26/21 Subject: STAINLESS STEEL CB DAMPERS Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 10833 | Review Response | Approved | 2021-01-12 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.01.12 | Info Exchange
| 14080 | Responded and Closed | Approved | 2021-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.01.12 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 23 33 00-110 SS CB Dampers - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 23 33 00-110 SS CB Dampers - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-11 02:00 |  | 23 33 00-110 SS CB Dampers - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-20 02:00 |  | 23 33 00-011-0 SS CB Dampers_ME_POP.pdf
23 33 00-012-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-012-00 Duct Accessories - Spiral Liner and Remote DAHU Filter | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-03-02 | 2021-02-24 | 9 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11453 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-02 | Submittal Number: 23 33 00-12.0 From: GRETCHEN TOSHACH Final Due Date: 03/01/21 Subject: DUCT ACCESSORIES - SPIRAL LINER AND REMOTE DAHU FILTER Description: DUCT ACCESSORIES - SPIRAL LINER AND REMOTE DAHU FILTER Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 14835 | Forwarded | For Review | 2021-02-16 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-23 | Submittal Number: 23 33 00-12.0 From: GRETCHEN TOSHACH Final Due Date: 03/01/21 Subject: DUCT ACCESSORIES - SPIRAL LINER AND REMOTE DAHU FILTER Description: DUCT ACCESSORIES - SPIRAL LINER AND REMOTE DAHU FILTER Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 11628 | Review Response | Approved as Noted/Resubmit | 2021-02-16 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.02.16 | Info Exchange
| 15075 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-24 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.02.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 23 33 00-12.0 Spiral Line_Remote DAHU Filter - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-15 |  | 23 33 00-12.0 Spiral Line_Remote DAHU Filter - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-02-14 02:00 |  | 23 33 00-12.0 Spiral Line_Remote DAHU Filter - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-24 02:00 |  | 23 33 00-12.0 Spiral Line_Remote DAHU Filter_ME_POP.pdf
23 33 00-012-01 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-012-01 Duct Accessories - Spiral Liner and Remote DAHU Filter | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-03 07:00 | 2021-05-25 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-05-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13185 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-03 07:00 | Submittal Number: 23 33 00-12.1 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: DUCT ACCESSORIES - SPIRAL LINER AND REMOTE DAHU FILTER Description: DUCT ACCESSORIES - SPIRAL LINER AND REMOTE DAHU FILTER Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 17075 | Forwarded | For Review | 2021-05-19 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-26 | Submittal Number: 23 33 00-12.1 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: DUCT ACCESSORIES - SPIRAL LINER AND REMOTE DAHU FILTER Description: DUCT ACCESSORIES - SPIRAL LINER AND REMOTE DAHU FILTER Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 13257 | Review Response | Approved | 2021-05-20 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Note the title of the submittal includes "remote DAHU filter" but that was not submitted. Nick Theimer ME Engineers 2021.05.20 | Info Exchange
| 17154 | Responded and Closed | Approved | 2021-05-25 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Note the title of the submittal includes "remote DAHU filter" but that was not submitted. Nick Theimer ME Engineers 2021.05.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-19 |  | 23 33 00-12.1 Johns Manville Spiral Liner - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-19 |  | 23 33 00-12.1 Johns Manville Spiral Liner - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-18 02:00 |  | 23 33 00-12.1 Johns Manville Spiral Liner - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-25 02:00 |  | 23 33 00-12.1 Johns Manville Spiral Liner_ME_POP.pdf
23 33 00-013-00 | 23 33 00 - DUCTWORK ACCESSORIES | 23 33 00-013-00 Damper Indicator Switches | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-03 07:00 | 2021-05-25 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-05-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13186 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-03 07:00 | Submittal Number: 23 33 00-13.0 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: DAMPER INDICATOR SWITCHES Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 17076 | Forwarded | For Review | 2021-05-19 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-26 | Submittal Number: 23 33 00-13.0 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: DAMPER INDICATOR SWITCHES Description: Spec Section: 23 33 00 - DUCTWORK ACCESSORIES Status: OPEN | Info Exchange
| 13265 | Review Response | Approved | 2021-05-25 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.05.25 | Info Exchange
| 17161 | Responded and Closed | Approved | 2021-05-25 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.05.25 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-19 |  | 23 33 00-13.0 Indicator Switch - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-19 |  | 23 33 00-13.0 Indicator Switch - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-19 |  | 23 33 00-13.0 Indicator Switch - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-25 |  | 23 33 00-13.0 Indicator Switch_ME_POP.pdf
23 34 00-001-00 | 23 34 00 - FANS | 23 34 00-001-00 Fans Product Data | Closed | Mechanical | Patrick Klein (Mortenson Construction) | 2019-06-20 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-07-11 | 2019-07-08 | 19 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01583 | Received | For Review | 2019-06-20 | Patrick Klein (Mortenson Construction) | Populous SCA_CCA | 2019-07-11 |  | Email
| 02622 | Forwarded | For Review | 2019-06-20 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-06-27 |  | Info Exchange
| 01695 | Review Response | Revise and Resubmit | 2019-07-03 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | Please see attached for review of Submittal 23 34 00-001-00. | Info Exchange
| 02779 | Responded and Closed | Revise and Resubmit | 2019-07-08 | Populous SCA_CCA | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: Please see attached for review of Submittal 23 34 00-001-00. POP - see noted items required for resubmission | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Patrick Klein (Mortenson Construction) | 1 | 2019-06-20 |  | 23 34 00-001-00 Fans Product Data-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-20 |  | 23 34 00-001-00 Fans Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-07 |  | 23 34 00-001-00 Fans Product Data-MAM_ME.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-07-08 |  | 23 34 00-001-00 Fans Product Data-MAM_ME_POP.pdf
23 34 00-001-01 | 23 34 00 - FANS | 23 34 00-001-01 FANS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-16 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-30 | 2019-08-26 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02100 | Received | For Review | 2019-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-30 | Submittal Number: 23 34 00-1.1 From: PATRICK KLEIN Final Due Date: 08/30/19 Subject: FANS - PRODUCT DATA Description: MANUFACTURERS DATA : SUBMIT MANUFACTURERS PRODUCT DATA INCLUDING: 1. PERFORMANCE 2. SIZE 3. TYPE 4. OPTIONS PROVIDED 5. FAN CURVES 6. INDICATE COMPLIANCE WITH SECTION 1.1 WHERE APPLICABLE. Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 03277 | Forwarded | For Review | 2019-08-19 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-26 | Submittal Number: 23 34 00-1.1 From: PATRICK KLEIN Final Due Date: 08/30/19 Subject: FANS - PRODUCT DATA Description: MANUFACTURERS DATA : SUBMIT MANUFACTURERS PRODUCT DATA INCLUDING: 1. PERFORMANCE 2. SIZE 3. TYPE 4. OPTIONS PROVIDED 5. FAN CURVES 6. INDICATE COMPLIANCE WITH SECTION 1.1 WHERE APPLICABLE. Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 02198 | Review Response | Approved as Noted | 2019-08-26 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached review. Nick Theimer ME Engineers 2019.08.26 | Info Exchange
| 03403 | Responded and Closed | Approved as Noted | 2019-08-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached review. Nick Theimer ME Engineers 2019.08.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-16 |  | 23 34 00-1.1 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-16 |  | 23 34 00-1.1 Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-15 02:00 |  | 23 34 00-1.1 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-26 02:00 |  | 23 34 00-001-01 Fans Product Data-MAM_ME_POP.pdf
23 34 00-001-02 | 23 34 00 - FANS | 23 34 00-001-2 Fans Product Data | Closed | Mechanical | Gretchen Toshach (Mortenson Construction) | 2019-12-19 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-13 | 2019-12-19 | 1 | General | Record Copies; Transfers; Submittals |  | 2 |  | 2019-12-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03694 | Received | For Review | 2019-12-19 | Gretchen Toshach (Mortenson Construction) | Josh Dobken (Populous) | 2020-01-13 |  | Email
| 05215 | Forwarded | For Review | 2019-12-18 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-02 |  | Info Exchange
| 03711 | Review Response | Approved as Noted | 2019-12-19 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.19 | Info Exchange
| 05241 | Responded and Closed | Approved as Noted | 2019-12-19 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.19 | Info Exchange
| 05407 | Sent | For Information Only | 2020-01-09 | Josh Dobken (Populous) | Ryan Crookston (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Responded and Closed (Approved as Noted) to: Danny Keim (Mortenson Construction); Gretchen Toshach (Mortenson Construction) Remarks: Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.19 | Info Exchange
| 05561 | Sent | For Information Only | 2020-01-20 | Josh Dobken (Populous) | Ryan Crookston (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Sent to: Ryan Crookston (Mortenson Construction); Gretchen Toshach (Mortenson Construction) Remarks: Responded and Closed (Approved as Noted) to: Danny Keim (Mortenson Construction); Gretchen Toshach (Mortenson Construction) Remarks: Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.19 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Gretchen Toshach (Mortenson Construction) | 1 | 2019-12-18 02:00 |  | 23 34 00-1.2 Fans Product Data - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-18 02:00 |  | 23 34 00-1.2 Fans Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-12-18 02:00 |  | 23 34 00-1.2 Fans Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-19 02:00 |  | 23 34 00-1.2 Fans Product Data_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2019-12-18 02:00 |  | 23 34 00-1.2 Fans Product Data - MAM.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2019-12-18 02:00 |  | 23 34 00-1.2 Fans Product Data - MAM.pdf
23 34 00-001-03 | 23 34 00 - FANS | 23 34 00-001-03 FANS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-30 | 2020-03-31 | 16 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-03-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04845 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 23 34 00-1.3 From: GRETCHEN TOSHACH Final Due Date: 03/30/20 Subject: FANS - PRODUCT DATA Description: SUBMIT BALANCE OF FANS FOR THE FOLLOWING PER PREVIOUS SUBMITTALS: EF-1A.01 EF-1E.01 THROUGH 1E.05 SF-1E.01 THROUGH 1E.05 EF-1B.03 EF-1F.03 DF-7A.01 THROUGH 7D.01 Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 06622 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-23 | Submittal Number: 23 34 00-1.3 From: GRETCHEN TOSHACH Final Due Date: 03/30/20 Subject: FANS - PRODUCT DATA Description: SUBMIT BALANCE OF FANS FOR THE FOLLOWING PER PREVIOUS SUBMITTALS: EF-1A.01 EF-1E.01 THROUGH 1E.05 SF-1E.01 THROUGH 1E.05 EF-1B.03 EF-1F.03 DF-7A.01 THROUGH 7D.01 Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 05139 | Review Response | Approved as Noted | 2020-03-27 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.27 | Info Exchange
| 06972 | Responded and Closed | Approved as Noted | 2020-03-31 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 23 34 00-1.3 Enervex Fans Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 23 34 00-1.3 Enervex Fans Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-15 02:00 |  | 23 34 00-1.3 Enervex Fans Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-31 02:00 |  | 23 34 00-1.3 Enervex Fans Product Data_ME_POP.pdf
23 34 00-003-00 | 23 34 00 - FANS | 23 34 00-003-00 DESTRATIFICATION FANS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2019-12-04 08:00 | 2019-12-04 | 17 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2019-12-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03219 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) | 2019-12-04 08:00 | Submittal Number: 23 34 00-3.0 From: SIMRAN GEORGE Final Due Date: 11/29/19 Subject: DESTRATIFICATION FANS - PRODUCT DATA Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 04658 | Forwarded | For Review | 2019-11-15 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-22 | Submittal Number: 23 34 00-3.0 From: SIMRAN GEORGE Final Due Date: 11/29/19 Subject: DESTRATIFICATION FANS - PRODUCT DATA Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 03292 | Review Response | Approved as Noted | 2019-11-20 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Architect to confirm color comments. Nick Theimer ME Engineers 2019.11.20 | Info Exchange
| 04741 | Forwarded | For Review | 2019-11-20 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2019-11-27 | Submittal Number: 23 34 00-3.0 From: SIMRAN GEORGE Final Due Date: 11/29/19 Subject: DESTRATIFICATION FANS - PRODUCT DATA Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 04967 | Responded and Closed | Approved as Noted | 2019-12-04 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | See attached for review. Architect to confirm color comments. Nick Theimer ME Engineers 2019.11.20 Note the color change - yellow to silver (fan will be all silver). Bryan Klote/Populous - 12.04.2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-15 |  | 23 34 00-3.0 Destratification Fans - Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-15 |  | 23 34 00-3.0 Destratification Fans - Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-14 02:00 |  | 23 34 00-3.0 Destratification Fans - Product Data - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-14 02:00 |  | 23 34 00-3.0 Destratification Fans - Product Data - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2019-12-04 |  | 23 34 00-3.0 Destratification Fans - Product Data_ME-POP.pdf
23 34 00-004-00 | 23 34 00 - FANS | 23 34 00-004-00 Laundry Exhaust Fan - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-19 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-02 | 2020-03-31 | 13 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-03-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04948 | Received | For Review | 2020-03-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-02 | Submittal Number: 23 34 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 03/09/20 Subject: LAUNDRY EXHAUST FAN - PRODUCT DATA Description: LAUNDRY EXHAUST FAN - RESUBMITTING WITH LOCAL CODE UL LISTED FAN. Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 06745 | Forwarded | For Review | 2020-03-19 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-26 | Submittal Number: 23 34 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 03/09/20 Subject: LAUNDRY EXHAUST FAN - PRODUCT DATA Description: LAUNDRY EXHAUST FAN - RESUBMITTING WITH LOCAL CODE UL LISTED FAN. Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 05140 | Review Response | Approved | 2020-03-27 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.27 | Info Exchange
| 06973 | Responded and Closed | Approved | 2020-03-31 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-18 |  | 23 34 00-4.0 EF-1B.03 Fan - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-18 |  | 23 34 00-4.0 EF-1B.03 Fan - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-17 02:00 |  | 23 34 00-4.0 EF-1B.03 Fan - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-31 02:00 |  | 23 34 00-4.0 EF-1B.03 Fan_ME_POP.pdf
23 34 00-005-00 | 23 34 00 - FANS | 23 34 00-005-00 CCD-041 EF 1F.07 - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-17 | 2020-03-13 | 11 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-03-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04598 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 23 34 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 03/06/20 Subject: CCD-041 EF 1F.07 - PRODUCT DATA Description: PRODUCT DATA FOR EXHAUST FAN EF 1F.07 AS ISSUED IN CCD 041 Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 06336 | Forwarded | For Review | 2020-03-03 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-10 | Submittal Number: 23 34 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 03/06/20 Subject: CCD-041 EF 1F.07 - PRODUCT DATA Description: PRODUCT DATA FOR EXHAUST FAN EF 1F.07 AS ISSUED IN CCD 041 Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 04826 | Review Response | Approved | 2020-03-13 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| 06603 | Responded and Closed | Approved | 2020-03-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 23 34 00-5.0 EF-1F.07 Fan Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 23 34 00-5.0 EF-1F.07 Fan Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-01 02:00 |  | 23 34 00-5.0 EF-1F.07 Fan Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-13 02:00 |  | 23 34 00-5.0 EF-1F.07 Fan Product Data_ME_POP.pdf
23 34 00-006-00 | 23 34 00 - FANS | 23 34 00-006-00 BAF Fan Mount | Closed | Mechanical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-03-17 | 2020-03-18 | 16 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04599 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 23 34 00-6.0 From: GRETCHEN TOSHACH Final Due Date: 03/31/20 Subject: BAF FAN MOUNT Description: DESTRATIFICATION FAN MOUNT FOR RECORD. REQUIRE MODIFICATIONS FROM MANUFACTURER RECOMMENDATIONS FOR FAN MOUNT SUBMITTED FOR RECORD. Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 06337 | Forwarded | For Review | 2020-03-03 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-10 | Submittal Number: 23 34 00-6.0 From: GRETCHEN TOSHACH Final Due Date: 03/31/20 Subject: BAF FAN MOUNT Description: DESTRATIFICATION FAN MOUNT FOR RECORD. REQUIRE MODIFICATIONS FROM MANUFACTURER RECOMMENDATIONS FOR FAN MOUNT SUBMITTED FOR RECORD. Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 04827 | Review Response | Not Required For Review | 2020-03-13 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | Structural engineer to review. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| 06604 | Forwarded | For Review | 2020-03-13 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-03-17 | Submittal Number: 23 34 00-6.0 From: GRETCHEN TOSHACH Final Due Date: 03/31/20 Subject: BAF FAN MOUNT Description: DESTRATIFICATION FAN MOUNT FOR RECORD. REQUIRE MODIFICATIONS FROM MANUFACTURER RECOMMENDATIONS FOR FAN MOUNT SUBMITTED FOR RECORD. Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 04919 | Review Response | Approved | 2020-03-16 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | No exceptions. | Info Exchange
| 06716 | Responded and Closed | Approved | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: No exceptions. Response (Not Required For Review) from: Nick Theimer (ME Engineers) Remarks: Structural engineer to review. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| 06786 | Sent | For Construction | 2020-03-23 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: No exceptions. Response (Not Required For Review) from: Nick Theimer (ME Engineers) Remarks: Structural engineer to review. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 23 34 00-6.0 BAF Fan Mounting Calcs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 23 34 00-6.0 BAF Fan Mounting Calcs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-01 02:00 |  | 23 34 00-6.0 BAF Fan Mounting Calcs - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-01 02:00 |  | 23 34 00-6.0 BAF Fan Mounting Calcs - MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-03-01 02:00 |  | 23 34 00-6.0 BAF Fan Mounting Calcs - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-01 02:00 |  | 23 34 00-6.0 BAF Fan Mounting Calcs - MAM.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-03-18 02:00 |  | 23 34 00-6.0 BAF Fan Mounting Calcs_ME_TT_POP.pdf
23 34 00-007-00 | 23 34 00 - FANS | 23 34 00-007-00 CCD-042 - EF 4F.01 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-16 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-30 | 2020-03-31 | 16 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-03-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04847 | Received | For Review | 2020-03-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-30 | Submittal Number: 23 34 00-7.0 From: GRETCHEN TOSHACH Final Due Date: 03/27/20 Subject: CCD-042 - EF 4F.01 Description: PRODUCT DATA PER FAN SUBMITTED FOR CCD-042 EF 4F.01 Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 06624 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-23 | Submittal Number: 23 34 00-7.0 From: GRETCHEN TOSHACH Final Due Date: 03/27/20 Subject: CCD-042 - EF 4F.01 Description: PRODUCT DATA PER FAN SUBMITTED FOR CCD-042 EF 4F.01 Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 05138 | Review Response | Approved | 2020-03-24 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.24 | Info Exchange
| 06971 | Responded and Closed | Approved | 2020-03-31 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-16 |  | 23 34 00-7.0 EF-4F.01 CCD-042 Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-16 |  | 23 34 00-7.0 EF-4F.01 CCD-042 Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-15 02:00 |  | 23 34 00-7.0 EF-4F.01 CCD-042 Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-31 02:00 |  | 23 34 00-7.0 EF-4F.01 CCD-042 Product Data_ME_POP.pdf
23 34 00-008-00 | 23 34 00 - FANS | 23 34 00-008-00 FANS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-26 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-09 | 2020-06-12 | 18 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-06-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06026 | Received | For Review | 2020-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-09 | Submittal Number: 23 34 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 06/17/20 Subject: FANS - PRODUCT DATA Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 08170 | Forwarded | For Review | 2020-05-26 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-02 | Submittal Number: 23 34 00-8.0 From: GRETCHEN TOSHACH Final Due Date: 06/17/20 Subject: FANS - PRODUCT DATA Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 06379 | Review Response | Approved as Noted | 2020-06-05 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.06.05 | Info Exchange
| 08596 | Responded and Closed | Approved as Noted | 2020-06-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.06.05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-26 |  | 23 34 00-8.0 Fans CCD-525455 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-26 |  | 23 34 00-8.0 Fans CCD-525455 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-25 02:00 |  | 23 34 00-8.0 Fans CCD-525455 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-12 02:00 |  | 23 34 00-8.0 Fans CCD-525455_ME_pop.pdf
23 34 00-009-00 | 23 34 00 - FANS | 23 34 00-009-00 Laundry Exhaust Fans | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-17 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-01 | 2020-06-24 | 8 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06464 | Received | For Review | 2020-06-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-01 | Submittal Number: 23 34 00-9.0 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: LAUNDRY EXHAUST FANS Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 08713 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-24 | Submittal Number: 23 34 00-9.0 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: LAUNDRY EXHAUST FANS Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 06708 | Review Response | Approved as Noted/Resubmit | 2020-06-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Units shall be revised to CCD 064. Nick Theimer ME Engineers 2020.06.22 | Info Exchange
| 08873 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-24 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Units shall be revised to CCD 064. Nick Theimer ME Engineers 2020.06.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 23 34 00-9.0 Laundry Exhaust Fans base & deferred - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 23 34 00-9.0 Laundry Exhaust Fans base & deferred - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-16 02:00 |  | 23 34 00-9.0 Laundry Exhaust Fans base & deferred - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-17 |  | 23 34 00-9.0 Laundry Exhaust Fans base & deferred - MAM.pdf
23 34 00-009-01 | 23 34 00 - FANS | 23 34 00-009-01 Laundry Exhaust Fans | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-07 | 2020-09-29 | 7 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08292 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 23 34 00-9.1 From: GRETCHEN TOSHACH Final Due Date: 10/02/20 Subject: LAUNDRY EXHAUST FANS Description: UPDATED LAUNDRY EXHAUST FANS PER CCD 064 - SUSTAINABILITY INITIATIVES FROM GAS TO ELECTRIC. Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 10998 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-30 | Submittal Number: 23 34 00-9.1 From: GRETCHEN TOSHACH Final Due Date: 10/02/20 Subject: LAUNDRY EXHAUST FANS Description: UPDATED LAUNDRY EXHAUST FANS PER CCD 064 - SUSTAINABILITY INITIATIVES FROM GAS TO ELECTRIC. Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 08419 | Review Response | Approved | 2020-09-28 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.09.28 | Info Exchange
| 11156 | Responded and Closed | Approved | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.09.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 23 34 00-9.1 Laundry Fans EF-1A.011D.01 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 23 34 00-9.1 Laundry Fans EF-1A.011D.01 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-23 |  | 23 34 00-9.1 Laundry Fans EF-1A.011D.01 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 23 34 00-9.1 Laundry Fans EF-1A.011D.01_ME_POP.pdf
23 34 00-010-00 | 23 34 00 - FANS | 23 34 00-010-00 CCD-062 Laundry Fan EF-1B.01 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-08 | 2021-02-02 | 9 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-02-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10941 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-08 | Submittal Number: 23 34 00-10.0 From: GRETCHEN TOSHACH Final Due Date: 08/21/20 Subject: CCD-062 LAUNDRY FAN EF-1B.01 Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 14204 | Forwarded | For Review | 2021-01-25 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-01 | Submittal Number: 23 34 00-10.0 From: GRETCHEN TOSHACH Final Due Date: 08/21/20 Subject: CCD-062 LAUNDRY FAN EF-1B.01 Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 11128 | Review Response | Approved | 2021-01-26 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.01.26 | Info Exchange
| 14439 | Responded and Closed | Approved | 2021-02-02 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.01.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-25 |  | 23 34 00-10.0 EF-1B.01 CCD-062 - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-25 |  | 23 34 00-10.0 EF-1B.01 CCD-062 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-25 |  | 23 34 00-10.0 EF-1B.01 CCD-062 - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-02 |  | 23 34 00-10.0 EF-1B.01 CCD-062_ME_POP.pdf
23 34 00-011-00 | 23 34 00 - FANS | 23 34 00-011-00 CCD 065 Transfer Fan | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-24 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-08 | 2020-09-29 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08308 | Received | For Review | 2020-09-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-08 | Submittal Number: 23 34 00-11.0 From: GRETCHEN TOSHACH Final Due Date: 10/07/20 Subject: CCD 065 TRANSFER FAN Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 11015 | Forwarded | For Review | 2020-09-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-01 | Submittal Number: 23 34 00-11.0 From: GRETCHEN TOSHACH Final Due Date: 10/07/20 Subject: CCD 065 TRANSFER FAN Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 08420 | Review Response | Approved as Noted | 2020-09-24 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| 11157 | Responded and Closed | Approved as Noted | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-24 |  | 23 34 00-110 TF-1E.01 CCD-065 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-24 |  | 23 34 00-11.0 TF-1E.01 CCD-065 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-24 |  | 23 34 00-11.0 TF-1E.01 CCD-065 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 23 34 00-11.0 TF-1E.01 CCD-065_ME_POP.pdf
23 34 00-012-00 | 23 34 00 - FANS | 23 34 00-012-00 CCD 071 Cupula Fans | Closed | Mechanical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-06 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Geoff Cheong |  |  |  | 2020-11-20 | 2020-11-24 | 19 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-11-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09269 | Received | For Review | 2020-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-11-20 | Submittal Number: 23 34 00-12.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: CCD 071 CUPULA FANS Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 12221 | Forwarded | For Review | 2020-11-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-13 | Submittal Number: 23 34 00-12.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: CCD 071 CUPULA FANS Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 09728 | Review Response | Approved as Noted | 2020-11-12 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Geoff Cheong; Josh Dobken (Populous) |  | See attahced for review. ARCHITECT TO COMMENT ON FAN COLOR SELECTION PRIOR TO RETURNING SUBMITTAL. Nick Theimer ME Engineers 2020.11.12 | Info Exchange
| 12703 | Forwarded | For Review | 2020-11-21 | Josh Dobken (Populous) | Bryan Klote (Populous); Geoff Cheong | 2020-11-20 | Submittal Number: 23 34 00-12.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: CCD 071 CUPULA FANS Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 12795 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-24 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attahced for review. Nick Theimer ME Engineers 2020.11.12 submit curb adapter BK/Populous 11.24.2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 23 3 400-12.0 SEF Cupula Fans CCD071 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 23 3 400-12.0 SEF Cupula Fans CCD071 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-06 |  | 23 3 400-12.0 SEF Cupula Fans CCD071 - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-11-05 02:00 |  | 23 3 400-12.0 SEF Cupula Fans CCD071 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-11-24 |  | 23 34 00-12.0 SEF Cupula Fans CCD071_ME_POP.pdf
23 34 00-012-01 | 23 34 00 - FANS | 23 34 00-012-01 CCD 071 Cupula Fans | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-11 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-03-25 | 2021-03-24 | 14 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11949 | Received | For Review | 2021-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-03-25 | Submittal Number: 23 34 00-12.1 From: GRETCHEN TOSHACH Final Due Date: 03/25/21 Subject: CCD 071 CUPULA FANS Description: CURB ADAPTOR Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 15472 | Forwarded | For Review | 2021-03-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-18 | Submittal Number: 23 34 00-12.1 From: GRETCHEN TOSHACH Final Due Date: 03/25/21 Subject: CCD 071 CUPULA FANS Description: CURB ADAPTOR Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 15495 | Forwarded | For Review | 2021-03-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-18 | Submittal Number: 23 34 00-12.1 From: GRETCHEN TOSHACH Final Due Date: 03/25/21 Subject: CCD 071 CUPULA FANS Description: CURB ADAPTOR Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 12228 | Review Response | Approved as Noted | 2021-03-22 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.03.22 | Info Exchange
| 15818 | Responded and Closed | Approved as Noted | 2021-03-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.03.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-11 |  | 23 34 00-12. Cupula Fan Curb Adaptor - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-11 |  | 23 34 00-12. Cupula Fan Curb Adaptor - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-11 |  | 23 34 00-12. Cupula Fan Curb Adaptor - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-03-10 02:00 |  | 23 34 00-12. Cupula Fan Curb Adaptor - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-24 02:00 |  | 23 34 00-012-01 Cupula Fan Curb Adaptor_ME_POP.pdf
23 34 00-013-00 | 23 34 00 - FANS | 23 34 00-013-00 CCD 078/79 Fans | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-25 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-11 | 2020-12-03 | 9 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09737 | Received | For Review | 2020-11-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-11 | Submittal Number: 23 34 00-13.0 From: GRETCHEN TOSHACH Final Due Date: 01/05/21 Subject: CCD 078/79 FANS Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 12805 | Forwarded | For Review | 2020-11-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-02 | Submittal Number: 23 34 00-13.0 From: GRETCHEN TOSHACH Final Due Date: 01/05/21 Subject: CCD 078/79 FANS Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 09869 | Review Response | Approved | 2020-12-01 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.12.01 | Info Exchange
| 12952 | Responded and Closed | Approved | 2020-12-03 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.12.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-24 |  | 23 34 00-13.0 CCD-078-079 Fans - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-24 |  | 23 34 00-13.0 CCD-078-079 Fans - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-24 |  | 23 34 00-13.0 CCD-078-079 Fans - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-03 |  | 23 34 00-13.0 CCD-078-079 Fans_ME_POP.pdf
23 34 00-014-00 | 23 34 00 - FANS | 23 34 00-014-00 CCD 086 Transfer Fans | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-03-02 | 2021-02-24 | 9 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11454 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-03-02 | Submittal Number: 23 34 00-14.0 From: GRETCHEN TOSHACH Final Due Date: 03/01/21 Subject: CCD 086 TRANSFER FANS Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 14836 | Forwarded | For Review | 2021-02-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-23 | Submittal Number: 23 34 00-14.0 From: GRETCHEN TOSHACH Final Due Date: 03/01/21 Subject: CCD 086 TRANSFER FANS Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 11629 | Review Response | Approved | 2021-02-16 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.02.16 | Info Exchange
| 15076 | Responded and Closed | Approved | 2021-02-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.02.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 23 34 00-14.0 JWO CCD-086 Fans - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-15 |  | 23 34 00-14.0 JWO CCD-086 Fans - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-02-14 02:00 |  | 23 34 00-14.0 JWO CCD-086 Fans - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-24 02:00 |  | 23 34 00-14.0 JWO CCD-086 Fans_ME_POP.pdf
23 34 00-015-00 | 23 34 00 - FANS | 23 34 00-015-00 Cupula Fans VFD (CCD 071) + Nema 3R VFDs | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-17 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-03-31 | 2021-03-29 | 13 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12075 | Received | For Review | 2021-03-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-03-31 | Submittal Number: 23 34 00-15.0 From: GRETCHEN TOSHACH Final Due Date: 03/19/21 Subject: CUPULA FANS VFD (CCD 071) + NEMA 3R VFDS Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 15629 | Forwarded | For Review | 2021-03-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-24 | Submittal Number: 23 34 00-15.0 From: GRETCHEN TOSHACH Final Due Date: 03/19/21 Subject: CUPULA FANS VFD (CCD 071) + NEMA 3R VFDS Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 12297 | Review Response | Approved | 2021-03-23 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.03.23 | Info Exchange
| 15927 | Responded and Closed | Approved | 2021-03-29 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.03.23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-17 |  | 23 34 00-15.0 Cupola Fan VFDs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-17 |  | 23 34 00-15.0 Cupola Fan VFDs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-03-16 02:00 |  | 23 34 00-15.0 Cupola Fan VFDs - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-29 02:00 |  | 23 34 00-15.0 Cupola Fan VFDs - MAM_ME_POP.pdf
23 34 00-016-00 | 23 34 00 - FANS | 23 34 00-016-00 CCD 091 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-19 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-03 07:00 | 2021-05-25 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-05-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13181 | Received | For Review | 2021-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-03 07:00 | Submittal Number: 23 34 00-16.0 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: CCD 091 Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 17069 | Forwarded | For Review | 2021-05-19 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-26 | Submittal Number: 23 34 00-16.0 From: GRETCHEN TOSHACH Final Due Date: 06/02/21 Subject: CCD 091 Description: Spec Section: 23 34 00 - FANS Status: OPEN | Info Exchange
| 13256 | Review Response | Approved | 2021-05-20 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.05.21 | Info Exchange
| 17153 | Responded and Closed | Approved | 2021-05-25 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.05.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-19 |  | 23 34 00-16.0 CCD-091 Transfer Fans - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-19 |  | 23 34 00-16.0 CCD-091 Transfer Fans - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-18 02:00 |  | 23 34 00-16.0 CCD-091 Transfer Fans - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-25 02:00 |  | 23 34 00-16.0 CCD-091 Transfer Fans_ME_POP.pdf
23 36 00-001-00 | 23 36 00 - AIR TERMINAL UNITS | 23 36 00-001-00 AIR TERMINAL UNITS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-27 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-11 | 2019-10-15 | 19 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-10-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02582 | Received | For Review | 2019-09-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC); Gretchen Toshach (Mortenson Construction) | 2019-10-11 | Submittal Number: 23 36 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 10/09/19 Subject: AIR TERMINAL UNITS - PRODUCT DATA Description: SUBMIT SHOP DRAWINGS AND PRODUCT DATA SHEETS INDICATING CONFIGURATION, GENERAL ASSEMBLY, AND MATERIALS USED IN FABRICATION. Spec Section: 23 36 00 - AIR TERMINAL UNITS Status: OPEN | Info Exchange
| 03870 | Forwarded | For Review | 2019-09-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-07 | Submittal Number: 23 36 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 10/09/19 Subject: AIR TERMINAL UNITS - PRODUCT DATA Description: SUBMIT SHOP DRAWINGS AND PRODUCT DATA SHEETS INDICATING CONFIGURATION, GENERAL ASSEMBLY, AND MATERIALS USED IN FABRICATION. Spec Section: 23 36 00 - AIR TERMINAL UNITS Status: OPEN | Info Exchange
| 02775 | Review Response | Approved as Noted/Resubmit | 2019-10-14 | Nick Theimer (ME Engineers) | Kelsea Conkright (Populous); Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.10.14 | Info Exchange
| 04120 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-26 |  | 23 36 00-1.0 Air Terminal Units Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-26 |  | 23 36 00-1.0 Air Terminal Units Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-09-25 02:00 |  | 23 36 00-1.0 Air Terminal Units Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-15 02:00 |  | 23 36 00-1.0 Air Terminal Units Product Data - ME_POP.pdf
23 36 00-001-01 | 23 36 00 - AIR TERMINAL UNITS | 23 36 00-001-01 AIR TERMINAL UNITS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-09 08:00 | 2019-12-10 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2019-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03318 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-09 08:00 | Submittal Number: 23 36 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/15/19 Subject: AIR TERMINAL UNITS - PRODUCT DATA Description: SUBMIT SHOP DRAWINGS AND PRODUCT DATA SHEETS INDICATING CONFIGURATION, GENERAL ASSEMBLY, AND MATERIALS USED IN FABRICATION. Spec Section: 23 36 00 - AIR TERMINAL UNITS Status: OPEN | Info Exchange
| 04772 | Forwarded | For Review | 2019-11-21 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-27 | Submittal Number: 23 36 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/15/19 Subject: AIR TERMINAL UNITS - PRODUCT DATA Description: SUBMIT SHOP DRAWINGS AND PRODUCT DATA SHEETS INDICATING CONFIGURATION, GENERAL ASSEMBLY, AND MATERIALS USED IN FABRICATION. Spec Section: 23 36 00 - AIR TERMINAL UNITS Status: OPEN | Info Exchange
| 03582 | Review Response | Approved as Noted | 2019-12-10 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.10 | Info Exchange
| 05062 | Responded and Closed | Approved as Noted | 2019-12-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-21 |  | 23 36 00-1.1 VAVs and EAVs Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-21 |  | 23 36 00-1.1 VAVs and EAVs Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-20 02:00 |  | 23 36 00-1.1 VAVs and EAVs Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-10 02:00 |  | 23 36 00-1.1 VAVs and EAVs Product Data_ME_POP.pdf
23 36 00-004-00 | 23 36 00 - AIR TERMINAL UNITS | 23 36 00-004-00 AIR TERMINAL UNITS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-26 07:00 | 2020-06-04 | 25 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05782 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-26 07:00 | Submittal Number: 23 36 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 06/17/20 Subject: AIR TERMINAL UNITS - PRODUCT DATA Description: Spec Section: 23 36 00 - AIR TERMINAL UNITS Status: OPEN | Info Exchange
| 07839 | Forwarded | For Review | 2020-05-11 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 23 36 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 06/17/20 Subject: AIR TERMINAL UNITS - PRODUCT DATA Description: Spec Section: 23 36 00 - AIR TERMINAL UNITS Status: OPEN | Info Exchange
| 06199 | Review Response | Approved as Noted/Resubmit | 2020-06-02 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.06.02 | Info Exchange
| 08377 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-04 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.06.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 23 36 00-4.0 VAVs-CCD-052_055 -MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-11 |  | 23 36 00-4.0 VAVs-CCD-052_055 -MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 23 36 00-4.0 VAVs-CCD-052_055 -MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-04 02:00 |  | 23 36 00-4.0 VAVs-CCD-052_055_ME_POP.pdf
23 36 00-004-01 | 23 36 00 - AIR TERMINAL UNITS | 23 36 00-004-01 AIR TERMINAL UNITS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-21 | 2020-07-13 | 7 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06799 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 23 36 00-4.1 From: GRETCHEN TOSHACH Final Due Date: 07/13/20 Subject: AIR TERMINAL UNITS - PRODUCT DATA Description: RESUBMIT VAVS AS SPECIFIED IN PREVIOUS SUBMITTAL REVISION COMMENTS Spec Section: 23 36 00 - AIR TERMINAL UNITS Status: OPEN | Info Exchange
| 09134 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-13 | Submittal Number: 23 36 00-4.1 From: GRETCHEN TOSHACH Final Due Date: 07/13/20 Subject: AIR TERMINAL UNITS - PRODUCT DATA Description: RESUBMIT VAVS AS SPECIFIED IN PREVIOUS SUBMITTAL REVISION COMMENTS Spec Section: 23 36 00 - AIR TERMINAL UNITS Status: OPEN | Info Exchange
| 06930 | Review Response | Approved as Noted | 2020-07-09 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.07.09 | Info Exchange
| 09281 | Responded and Closed | Approved as Noted | 2020-07-13 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.09 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 23 36 00-4.1 VAVs-CCD-052_055 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 23 36 00-4.1 VAVs-CCD-052_055 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-06 |  | 23 36 00-4.1 VAVs-CCD-052_055 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-13 |  | 23 36 00-4.1 VAVs-CCD-052_055_ME_POP.pdf
23 36 00-005-00 | 23 36 00 - AIR TERMINAL UNITS | 23 36 00-005-00 CCD 071 WNBA Terminal units | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-06 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-20 | 2020-11-16 | 11 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-11-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09268 | Received | For Review | 2020-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-11-20 | Submittal Number: 23 36 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: CCD 071 WNBA TERMINAL UNITS Description: Spec Section: 23 36 00 - AIR TERMINAL UNITS Status: OPEN | Info Exchange
| 12220 | Forwarded | For Review | 2020-11-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-13 | Submittal Number: 23 36 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: CCD 071 WNBA TERMINAL UNITS Description: Spec Section: 23 36 00 - AIR TERMINAL UNITS Status: OPEN | Info Exchange
| 09451 | Review Response | Approved as Noted | 2020-11-11 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.11.11 | Info Exchange
| 12461 | Responded and Closed | Approved as Noted | 2020-11-16 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.11.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 23 36 00-5.0 WNBA Terminal Units CCD-073 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 23 36 00-5.0 WNBA Terminal Units CCD-073 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-06 |  | 23 36 00-5.0 WNBA Terminal Units CCD-073 - MAM.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-11-16 |  | 23 36 00-5.0 WNBA Terminal Units CCD-073_ME_POP.pdf
23 37 00-001-00 | 23 37 00 - AIR INLETS AND OUTLETS | 23 37 00-001-00 AIR INLETS AND OUTLETS - General | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-25 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Kuebler Perry (Populous) |  |  |  | 2020-03-10 | 2020-03-19 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-03-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04487 | Received | For Review | 2020-02-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-10 | Submittal Number: 23 37 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 10/09/19 Subject: AIR INLETS AND OUTLETS - GENERAL Description: SUBMIT CATALOG DATA INCLUDING THROW, SOUND, PRESSURE DROP AND PHYSICAL DIMENSIONS. Spec Section: 23 37 00 - AIR INLETS AND OUTLETS Status: OPEN | Info Exchange
| 06181 | Forwarded | For Review | 2020-02-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-03 | Submittal Number: 23 37 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 10/09/19 Subject: AIR INLETS AND OUTLETS - GENERAL Description: SUBMIT CATALOG DATA INCLUDING THROW, SOUND, PRESSURE DROP AND PHYSICAL DIMENSIONS. Spec Section: 23 37 00 - AIR INLETS AND OUTLETS Status: OPEN | Info Exchange
| 04922 | Review Response | Approved as Noted | 2020-03-17 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Shaina Burris (Populous) |  | See attached for review. Architect to comment on colors required for special color ceilings. Color options have been requested in the submittal and has been noted to be provided in separate submittal for GRDs noted. Nick Theimer ME Engineers 2020.03.17 | Info Exchange
| 06719 | Forwarded | For Review | 2020-03-18 | Josh Dobken (Populous) | Kuebler Perry (Populous) | 2020-03-10 | Submittal Number: 23 37 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 10/09/19 Subject: AIR INLETS AND OUTLETS - GENERAL Description: SUBMIT CATALOG DATA INCLUDING THROW, SOUND, PRESSURE DROP AND PHYSICAL DIMENSIONS. Spec Section: 23 37 00 - AIR INLETS AND OUTLETS Status: OPEN | Email
| 04957 | Review Response | Approved as Noted/Resubmit | 2020-03-19 | Kuebler Perry (Populous) | Josh Dobken (Populous) |  | See attached submittal. | Info Exchange
| 06757 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-19 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Kuebler Perry (Populous) Remarks: See attached submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-24 |  | 23 3700-1.0 Air Inlets Outls Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-24 |  | 23 3700-1.0 Air Inlets Outls Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-02-23 02:00 |  | 23 3700-1.0 Air Inlets Outls Product Data - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-23 02:00 |  | 23 3700-1.0 Air Inlets Outls Product Data - MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-03-19 02:00 |  | 23 3700-1.0 Air Inlets Outlets Product Data_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-19 02:00 |  | 23 3700-1.0 Air Inlets Outlets Product Data_POP.pdf
23 37 00-001-01 | 23 37 00 - AIR INLETS AND OUTLETS | 23 37 00-001-01 AIR INLETS AND OUTLETS - General | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-20 | 2020-07-22 | 17 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-07-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06783 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 23 37 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 07/20/20 Subject: AIR INLETS AND OUTLETS - GENERAL Description: REVISE AND RESUBMIT ITEMS ONLY - DEFERRED SPACES Spec Section: 23 37 00 - AIR INLETS AND OUTLETS Status: OPEN | Info Exchange
| 09118 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-13 | Submittal Number: 23 37 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 07/20/20 Subject: AIR INLETS AND OUTLETS - GENERAL Description: REVISE AND RESUBMIT ITEMS ONLY - DEFERRED SPACES Spec Section: 23 37 00 - AIR INLETS AND OUTLETS Status: OPEN | Info Exchange
| 07096 | Review Response | Approved as Noted/Resubmit | 2020-07-16 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Architect to comment on colors (as noted in separate email). Nick Theimer ME Engineers 2020.07.16 See attached markup. K. Perry Populous 20200722 | Info Exchange
| 09481 | Responded and Closed | Approved as Noted/Resubmit | 2020-07-22 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.16 Response (Approved as Noted/Resubmit) from: Kuebler Perry (Populous) See attached markup. K. Perry Populous 2020.07.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 23 37 00-1.1 GRDs Deferred Scope - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 23 37 00-1.1 GRDs Deferred Scope - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-16 |  | 23 37 00-1.1 GRDs Deferred Scope_ME.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-22 |  | 23 37 00-1.1 GRDs Deferred Scope_POP.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-22 |  | 23 37 00-1.1 GRDs Deferred Scope_ME_POP.pdf
23 37 00-001-02 | 23 37 00 - AIR INLETS AND OUTLETS | 23 37 00-001-02 AIR INLETS AND OUTLETS - General | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-20 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-05-04 | 2021-04-27 | 8 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12680 | Received | For Review | 2021-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-04 | Submittal Number: 23 37 00-1.2 From: GRETCHEN TOSHACH Final Due Date: 05/04/21 Subject: AIR INLETS AND OUTLETS - GENERAL Description: REVISE AND RESUBMIT ITEMS ONLY Spec Section: 23 37 00 - AIR INLETS AND OUTLETS Status: OPEN | Info Exchange
| 16398 | Forwarded | For Review | 2021-04-20 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-04-27 | Submittal Number: 23 37 00-1.2 From: GRETCHEN TOSHACH Final Due Date: 05/04/21 Subject: AIR INLETS AND OUTLETS - GENERAL Description: REVISE AND RESUBMIT ITEMS ONLY Spec Section: 23 37 00 - AIR INLETS AND OUTLETS Status: OPEN | Info Exchange
| 12821 | Review Response | Approved as Noted | 2021-04-21 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.04.21 | Info Exchange
| 16598 | Responded and Closed | Approved as Noted | 2021-04-27 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.04.21 | Info Exchange
| 16767 | Sent | For Information Only | 2021-05-05 | Populous SCA_CCA | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Responded and Closed (Approved as Noted) to: Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) Remarks: Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.04.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-20 |  | 23 37 00-1.2 GRDs Deferred Scope - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-20 |  | 23 37 00-1.2 GRDs Deferred Scope - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-04-19 02:00 |  | 23 37 00-1.2 GRDs Deferred Scope - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-27 02:00 |  | 23 37 00-1.2 GRDs Deferred Scope_ME_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-04-19 02:00 |  | 23 37 00-1.2 GRDs Deferred Scope - MAM.pdf
23 40 00-001-00 | 23 40 00 - AIR CLEANING | 23 40 00-001-00 AIR CLEANING - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-03 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-17 | 2020-03-18 | 16 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04600 | Received | For Review | 2020-03-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-17 | Submittal Number: 23 40 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 03/20/20 Subject: AIR CLEANING - PRODUCT DATA Description: BIPOLAR IONIZATION APPROVED PRODUCT IN LIEU OF CATALYTIC UV FILTERS IN AHUS, DAHUS, AND ERVS. SUBMIT MANUFACTURERS PRODUCT DATA INCLUDING : - 1. MEDIA: A. DESCRIPTION B. EFFICIENCY C. TEST METHOD 2. ENCLOSURE 3. SUPPORT REQUIREMENTS 4. WEIGHT 5. ELECTRICAL DATA 6. DRAWINGS SHOWING DIMENSIONS Spec Section: 23 40 00 - AIR CLEANING Status: OPEN | Info Exchange
| 06338 | Forwarded | For Review | 2020-03-03 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-10 | Submittal Number: 23 40 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 03/20/20 Subject: AIR CLEANING - PRODUCT DATA Description: BIPOLAR IONIZATION APPROVED PRODUCT IN LIEU OF CATALYTIC UV FILTERS IN AHUS, DAHUS, AND ERVS. SUBMIT MANUFACTURERS PRODUCT DATA INCLUDING : - 1. MEDIA: A. DESCRIPTION B. EFFICIENCY C. TEST METHOD 2. ENCLOSURE 3. SUPPORT REQUIREMENTS 4. WEIGHT 5. ELECTRICAL DATA 6. DRAWINGS SHOWING DIMENSIONS Spec Section: 23 40 00 - AIR CLEANING Status: OPEN | Info Exchange
| 04921 | Review Response | Approved | 2020-03-16 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.16 | Info Exchange
| 06718 | Responded and Closed | Approved | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-02 |  | 23 40 00-1.0 Air Cleaning Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-02 |  | 23 40 00-1.0 Air Cleaning Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-01 02:00 |  | 23 40 00-1.0 Air Cleaning Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-18 02:00 |  | 23 40 00-1.0 Air Cleaning Product Data_ME_POP.pdf
23 40 00-002-00 | 23 40 00 - AIR CLEANING | 23 40 00-002-00 Air Cleaning - Shop Drawings | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-23 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-07 | 2020-05-04 | 12 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05517 | Received | For Review | 2020-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-07 | Submittal Number: 23 40 00-2.0 From: GRETCHEN TOSHACH Final Due Date: 05/07/20 Subject: AIR CLEANING - SHOP DRAWINGS Description: BIPOLAR IONIZATION SHOP DRAWINGS FOR EACH AHU, DAHU, AND ERV Spec Section: 23 40 00 - AIR CLEANING Status: OPEN | Info Exchange
| 07476 | Forwarded | For Review | 2020-04-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-30 | Submittal Number: 23 40 00-2.0 From: GRETCHEN TOSHACH Final Due Date: 05/07/20 Subject: AIR CLEANING - SHOP DRAWINGS Description: BIPOLAR IONIZATION SHOP DRAWINGS FOR EACH AHU, DAHU, AND ERV Spec Section: 23 40 00 - AIR CLEANING Status: OPEN | Info Exchange
| 05709 | Review Response | Approved as Noted | 2020-04-27 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.04.27 | Info Exchange
| 07739 | Responded and Closed | Approved as Noted | 2020-05-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.04.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-23 |  | 23 40 00-2.0 Air Cleaning Shop Drawing - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-23 |  | 23 40 00-2.0 Air Cleaning Shop Drawing - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-22 02:00 |  | 23 40 00-2.0 Air Cleaning Shop Drawing - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-04 02:00 |  | 23 40 00-2.0 Air Cleaning Shop Drawing_ME_POP.pdf
23 40 00-003-00 | 23 40 00 - AIR CLEANING | 23 40 00-003-00 Air Cleaning Shop Drawings - MAU and Suite Level | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-06 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-20 | 2020-11-21 | 16 |  | Record Copies; Transfers; Submittals | 23 40 00-003-01 - 23 40 00-003-00 Air Cleaning Shop Drawings - MAU and Suite Level | 6 |  | 2020-11-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09267 | Received | For Review | 2020-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-11-20 | Submittal Number: 23 40 00-3.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: AIR CLEANING SHOP DRAWINGS - MAU AND SUITE LEVEL Description: Spec Section: 23 40 00 - AIR CLEANING Status: OPEN | Info Exchange
| 12219 | Forwarded | For Review | 2020-11-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-13 | Submittal Number: 23 40 00-3.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: AIR CLEANING SHOP DRAWINGS - MAU AND SUITE LEVEL Description: Spec Section: 23 40 00 - AIR CLEANING Status: OPEN | Info Exchange
| 09653 | Review Response | Approved as Noted/Resubmit | 2020-11-11 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Resubmit. Nick Theimer ME Engineers 2020.11.11 | Info Exchange
| 12704 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Resubmit. Nick Theimer ME Engineers 2020.11.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 23 40 00-3.0 - Air Cleaning Atomos Air - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 23 40 00-3.0 - Air Cleaning Atomos Air - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-05 02:00 |  | 23 40 00-3.0 - Air Cleaning Atomos Air - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-21 02:00 |  | 23 40 00-3.0 - Air Cleaning Atomos Air_ME_pop.pdf
23 40 00-003-01 | 23 40 00 - AIR CLEANING | 23 40 00-003-00 Air Cleaning Shop Drawings - MAU and Suite Level | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 23 40 00-003-00 - 23 40 00-003-00 Air Cleaning Shop Drawings - MAU and Suite Level | -1 | 2020-12-07
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-21 02:00 |  | 23 40 00-3.0 - Air Cleaning Atomos Air_ME_pop.pdf
23 51 00-001-00 | 23 51 00 - FLUE SYSTEMS | 23 51 00-001-00 FLUE SYSTEMS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-30 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-14 07:00 | 2020-04-14 | 16 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-04-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05095 | Received | For Review | 2020-03-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-04-14 07:00 | Submittal Number: 23 51 00-1.0 From: PATRICK KLEIN Final Due Date: 04/10/20 Subject: FLUE SYSTEMS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA ON : - 1. DOUBLE WALL VENT PIPE SPECIFICATIONS. 2. ENGINEERED, FACTORY PROVIDED DRAWING OF INTENDED DESIGN AND ROUTING INCLUDING ALL COMPONENTS AND SIZES. A. SUBMIT PRESSURE DROP CALCULATION. Spec Section: 23 51 00 - FLUE SYSTEMS Status: OPEN | Info Exchange
| 06923 | Forwarded | For Review | 2020-03-27 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-03 | Submittal Number: 23 51 00-1.0 From: PATRICK KLEIN Final Due Date: 04/10/20 Subject: FLUE SYSTEMS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA ON : - 1. DOUBLE WALL VENT PIPE SPECIFICATIONS. 2. ENGINEERED, FACTORY PROVIDED DRAWING OF INTENDED DESIGN AND ROUTING INCLUDING ALL COMPONENTS AND SIZES. A. SUBMIT PRESSURE DROP CALCULATION. Spec Section: 23 51 00 - FLUE SYSTEMS Status: OPEN | Info Exchange
| 05341 | Review Response | Approved | 2020-04-13 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.04.13 | Info Exchange
| 07263 | Responded and Closed | Approved | 2020-04-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.04.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-27 |  | 23 51 00-1.0 Flue Systems Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-27 |  | 23 51 00-1.0 Flue Systems Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-26 02:00 |  | 23 51 00-1.0 Flue Systems Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-14 02:00 |  | 23 51 00-1.0 Flue Systems Product Data_ME_POP.pdf
23 52 00-002-00 | 23 52 00 - BOILERS | 23 52 00-002-00 BOILERS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-29 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-09-19 | 2019-09-20 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2019-09-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02238 | Received | For Review | 2019-08-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-19 | Submittal Number: 23 52 00-2.0 From: PATRICK KLEIN Final Due Date: 09/11/19 Subject: BOILERS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA. Spec Section: 23 52 00 - BOILERS Status: OPEN | Info Exchange
| 03456 | Forwarded | For Review | 2019-08-29 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-09-05 | Submittal Number: 23 52 00-2.0 From: PATRICK KLEIN Final Due Date: 09/11/19 Subject: BOILERS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA. Spec Section: 23 52 00 - BOILERS Status: OPEN | Info Exchange
| 02476 | Review Response | Approved as Noted | 2019-09-20 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.09.20 | Info Exchange
| 03750 | Responded and Closed | Approved as Noted | 2019-09-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.09.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-28 |  | 23 52 00-2.0 Product Data-MAM.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-28 |  | 23 5200.0 Boilers submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-28 |  | 23 52 00-2.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-28 |  | 23 5200.0 Boilers submittal.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-27 02:00 |  | 23 52 00-2.0 Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-27 02:00 |  | 23 5200.0 Boilers submittal.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-20 02:00 |  | 23 52 00-2.0 Product Data_ME_POP.pdf
23 52 00-005-00 | 23 52 00 - BOILERS | 23 52 00-005-00 Electric Boilers CCD 064 | Closed | Mechanical, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-17 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-31 | 2020-07-28 | 12 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07017 | Received | For Review | 2020-07-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-31 | Submittal Number: 23 52 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 08/11/20 Subject: ELECTRIC BOILERS CCD 064 Description: Spec Section: 23 52 00 - BOILERS Status: OPEN | Info Exchange
| 09399 | Forwarded | For Review | 2020-07-20 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-27 | Submittal Number: 23 52 00-5.0 From: GRETCHEN TOSHACH Final Due Date: 08/11/20 Subject: ELECTRIC BOILERS CCD 064 Description: Spec Section: 23 52 00 - BOILERS Status: OPEN | Info Exchange
| 07218 | Review Response | Approved as Noted | 2020-07-24 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.07.24 | Info Exchange
| 09631 | Responded and Closed | Approved as Noted | 2020-07-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-17 |  | 23 52 00-5.0 Electric Boilers CCD064 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-17 |  | 23 52 00-5.0 Electric Boilers CCD064 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-16 02:00 |  | 23 52 00-5.0 Electric Boilers CCD064 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-28 02:00 |  | 23 52 00-5.0 Electric Boilers CCD064_ME_pop.pdf
23 57 00-002-00 | 23 57 00 - HEAT EXCHANGERS | 23 57 00-002-00 Heat Exchangers Product Data | Closed | Mechanical | Patrick Klein (Mortenson Construction) | 2019-06-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), James Stieg (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-07-02 | 2019-06-27 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-06-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01554 | Received | For Review | 2019-06-18 | Patrick Klein (Mortenson Construction) | Populous SCA_CCA | 2019-07-02 |  | Email
| 02582 | Forwarded | For Review | 2019-06-18 | Populous SCA_CCA | Nick Theimer (ME Engineers); James Stieg (ME Engineers); Heidi Evans (ME Engineers) | 2019-06-25 |  | Info Exchange
| 01620 | Review Response | Approved as Noted | 2019-06-25 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 02678 | Forwarded | For Review | 2019-06-25 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-02 |  | Email
| 01634 | Review Response | Approved | 2019-06-27 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | The weight of the heat exchanger is acceptable for us since it is sitting on slab on grade. | Info Exchange
| 02699 | Responded and Closed | Approved as Noted | 2019-06-27 | Populous SCA_CCA | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: The weight of the heat exchanger is acceptable for us since it is sitting on slab on grade. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Patrick Klein (Mortenson Construction) | 1 | 2019-06-18 |  | 23 57 00-002-00 Heat Exchangers Product Data-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-18 |  | 23 57 00-002-00 Heat Exchangers Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-06-25 |  | 23 57 00-002-00 Heat Exchangers Product Data-MAM_ME.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-18 |  | 23 57 00-002-00 Heat Exchangers Product Data-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-06-27 |  | 23 57 00-002-00 Heat Exchangers Product Data-MAM_ME_POP.pdf
23 57 00-003-00 | 23 57 00 - HEAT EXCHANGERS | 23 57 00-003-00 HEAT EXCHANGERS - CCD 021 Heat Exchanger Revisions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-28 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-09-12 | 2019-09-03 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-09-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02221 | Received | For Review | 2019-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-12 | Submittal Number: 23 57 00-3.0 From: PATRICK KLEIN Final Due Date: 09/10/19 Subject: HEAT EXCHANGERS - CCD 021 HEAT EXCHANGER REVISIONS Description: Spec Section: 23 57 00 - HEAT EXCHANGERS Status: OPEN | Info Exchange
| 03432 | Forwarded | For Review | 2019-08-28 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-09-04 | Submittal Number: 23 57 00-3.0 From: PATRICK KLEIN Final Due Date: 09/10/19 Subject: HEAT EXCHANGERS - CCD 021 HEAT EXCHANGER REVISIONS Description: Spec Section: 23 57 00 - HEAT EXCHANGERS Status: OPEN | Info Exchange
| 02263 | Review Response | Approved | 2019-08-29 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Please note this requires a structural review as weights are more than design. Nick Theimer ME Engineers 2019.08.29. | Info Exchange
| 03484 | Forwarded | For Review | 2019-08-29 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Mich... | 2019-09-05 | Submittal Number: 23 57 00-3.0 From: PATRICK KLEIN Final Due Date: 09/10/19 Subject: HEAT EXCHANGERS - CCD 021 HEAT EXCHANGER REVISIONS Description: Spec Section: 23 57 00 - HEAT EXCHANGERS Status: OPEN | Email
| 03506 | Responded and Closed | Approved | 2019-09-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.08.29. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-27 |  | 23 57 00-3.0 CCD 021 Heat Exchanger Revisions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-27 |  | 23 57 00-3.0 CCD 021 Heat Exchanger Revisions-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-26 02:00 |  | 23 57 00-3.0 CCD 021 Heat Exchanger Revisions-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-08-26 02:00 |  | 23 57 00-3.0 CCD 021 Heat Exchanger Revisions-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-03 02:00 |  | 23 57 00-3.0 CCD 021 Heat Exchanger Revisions-ME_POP.pdf
23 57 00-004-00 | 23 57 00 - HEAT EXCHANGERS | 23 57 00-004-00 Ice Plant Heat Exchangers | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-01 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-15 | 2020-10-11 | 11 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-10-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08481 | Received | For Review | 2020-10-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-15 | Submittal Number: 23 57 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 10/15/20 Subject: ICE PLANT HEAT EXCHANGERS Description: RESUBMITTING FOR RECORD FOR COORDINATION WITH ICE BUILDERS ADJUSTED FLOWS Spec Section: 23 57 00 - HEAT EXCHANGERS Status: OPEN | Info Exchange
| 11226 | Forwarded | For Review | 2020-10-01 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-08 | Submittal Number: 23 57 00-4.0 From: GRETCHEN TOSHACH Final Due Date: 10/15/20 Subject: ICE PLANT HEAT EXCHANGERS Description: RESUBMITTING FOR RECORD FOR COORDINATION WITH ICE BUILDERS ADJUSTED FLOWS Spec Section: 23 57 00 - HEAT EXCHANGERS Status: OPEN | Info Exchange
| 08704 | Review Response | Approved as Noted/Resubmit | 2020-10-09 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.10.09 | Info Exchange
| 11495 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.09 | Info Exchange
| 11976 | Sent | For Information Only | 2020-10-28 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted/Resubmit) to: Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.09 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-01 |  | 23 57 00-4.0 HX-1E.04 -1E.05 RFI-2749 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-01 |  | 23 57 00-4.0 HX-1E.04 -1E.05 RFI-2749 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-30 02:00 |  | 23 57 00-4.0 HX-1E.04 -1E.05 RFI-2749 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-11 02:00 |  | 23 57 00-4.0 HX-1E.04 -1E.05 RFI-2749_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-09-30 02:00 |  | 23 57 00-4.0 HX-1E.04 -1E.05 RFI-2749 - MAM.pdf
23 57 00-004-01 | 23 57 00 - HEAT EXCHANGERS | 23 57 00-004-01 Ice Plant Heat Exchangers | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-25 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-11 | 2020-12-03 | 9 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09736 | Received | For Review | 2020-11-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-11 | Submittal Number: 23 57 00-4.1 From: GRETCHEN TOSHACH Final Due Date: 12/08/20 Subject: ICE PLANT HEAT EXCHANGERS Description: RESUBMITTING FOR RECORD FOR COORDINATION WITH ICE BUILDERS ADJUSTED FLOWS Spec Section: 23 57 00 - HEAT EXCHANGERS Status: OPEN | Info Exchange
| 12804 | Forwarded | For Review | 2020-11-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-02 | Submittal Number: 23 57 00-4.1 From: GRETCHEN TOSHACH Final Due Date: 12/08/20 Subject: ICE PLANT HEAT EXCHANGERS Description: RESUBMITTING FOR RECORD FOR COORDINATION WITH ICE BUILDERS ADJUSTED FLOWS Spec Section: 23 57 00 - HEAT EXCHANGERS Status: OPEN | Info Exchange
| 09870 | Review Response | Approved | 2020-12-01 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.12.01 | Info Exchange
| 12953 | Responded and Closed | Approved | 2020-12-03 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.12.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-24 |  | 23 57 00-4.1 HX-1E.04 -1E.05 RFI-2749 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-24 |  | 23 57 00-4.1 HX-1E.04 -1E.05 RFI-2749 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-24 |  | 23 57 00-4.1 HX-1E.04 -1E.05 RFI-2749 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-03 |  | 23 57 00-4.1 HX-1E.04 -1E.05 RFI-2749_ME_POP.pdf
23 64 16-002-00 | 23 64 16 - CENTRIFUGAL WATER CHILLERS | 23 64 16-002-00 CENTRIFUGAL WATER CHILLERS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-15 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-29 | 2019-08-26 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02072 | Received | For Review | 2019-08-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-29 | Submittal Number: 23 64 16-2.0 From: PATRICK KLEIN Final Due Date: 08/28/19 Subject: CENTRIFUGAL WATER CHILLERS - PRODUCT DATA Description: SUBMIT PRODUCT DATA INDICATING RATED CAPACITIES, WEIGHTS, SPECIALTIES AND ACCESSORIES, ELECTRICAL REQUIREMENTS AND WIRING DIAGRAMS. Spec Section: 23 64 16 - CENTRIFUGAL WATER CHILLERS Status: OPEN | Info Exchange
| 03245 | Forwarded | For Review | 2019-08-15 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-22 | Submittal Number: 23 64 16-2.0 From: PATRICK KLEIN Final Due Date: 08/28/19 Subject: CENTRIFUGAL WATER CHILLERS - PRODUCT DATA Description: SUBMIT PRODUCT DATA INDICATING RATED CAPACITIES, WEIGHTS, SPECIALTIES AND ACCESSORIES, ELECTRICAL REQUIREMENTS AND WIRING DIAGRAMS. Spec Section: 23 64 16 - CENTRIFUGAL WATER CHILLERS Status: OPEN | Info Exchange
| 02199 | Review Response | Approved as Noted/Resubmit | 2019-08-26 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Contractor to comment on differences between factory tests being conducted. Nick Theimer ME Engineers 2019.08.26 | Info Exchange
| 03404 | Responded and Closed | Approved as Noted/Resubmit | 2019-08-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Contractor to comment on differences between factory tests being conducted. Nick Theimer ME Engineers 2019.08.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-14 |  | 23 64 16-2.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-14 |  | 23 64 16-2.0 Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-13 02:00 |  | 23 64 16-2.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-26 02:00 |  | 23 64 16-2.0 Chiller Product Data-ME_POP.pdf
23 64 16-002-01 | 23 64 16 - CENTRIFUGAL WATER CHILLERS | 23 64 16-002-01 CENTRIFUGAL WATER CHILLERS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-08 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-22 | 2020-12-14 | 7 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-12-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10001 | Received | For Review | 2020-12-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-22 | Submittal Number: 23 64 16-2.1 From: PATRICK KLEIN Final Due Date: 12/21/20 Subject: CENTRIFUGAL WATER CHILLERS - PRODUCT DATA Description: SUBMIT CERTIFIED TEST REPORTS OF ALL DATA TO THE ENGINEER OF RECORD PRIOR TO INSTALLATION OF CHILLERS Spec Section: 23 64 16 - CENTRIFUGAL WATER CHILLERS Status: OPEN | Info Exchange
| 13089 | Forwarded | For Review | 2020-12-08 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-15 | Submittal Number: 23 64 16-2.1 From: PATRICK KLEIN Final Due Date: 12/21/20 Subject: CENTRIFUGAL WATER CHILLERS - PRODUCT DATA Description: SUBMIT CERTIFIED TEST REPORTS OF ALL DATA TO THE ENGINEER OF RECORD PRIOR TO INSTALLATION OF CHILLERS Spec Section: 23 64 16 - CENTRIFUGAL WATER CHILLERS Status: OPEN | Info Exchange
| 10147 | Review Response | Approved | 2020-12-11 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.12.11 | Info Exchange
| 13270 | Responded and Closed | Approved | 2020-12-14 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.12.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 23 64 16-2.1 Chiller Test Reports - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-07 |  | 23 64 16-2.1 Chiller Test Reports - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-12-07 |  | 23 64 16-2.1 Chiller Test Reports - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-14 |  | 23 64 16-2.1 Chiller Test Reports_ME_POP.pdf
23 65 00-001-00 | 23 65 00 - COOLING TOWERS | 23 65 00-001-00 COOLING TOWERS - Manufacturers Instructions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-01 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-16 | 2019-10-18 | 18 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2019-10-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02615 | Received | For Review | 2019-10-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-10-16 | Submittal Number: 23 65 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 10/16/19 Subject: COOLING TOWERS - MANUFACTURERS INSTRUCTIONS Description: SUBMIT MANUFACTURERS DATA INCLUDING : - 1. OVERALL DIMENSIONS. 2. OPERATING WEIGHTS. 3. SUPPORT LOADING POINTS AND LOADS. 4. FAN CFM AND BRAKE HORSEPOWER. 5. MOTOR DATA. 6. SIZES AND LOCATIONS OF CONNECTIONS. 7. INSTALLATION INSTRUCTIONS. 8. MAINTENANCE MANUALS. 9. SOUND POWER LEVELS. Spec Section: 23 65 00 - COOLING TOWERS Status: OPEN | Info Exchange
| 03917 | Forwarded | For Review | 2019-10-02 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) |  | Submittal Number: 23 65 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 10/16/19 Subject: COOLING TOWERS - MANUFACTURERS INSTRUCTIONS Description: SUBMIT MANUFACTURERS DATA INCLUDING : - 1. OVERALL DIMENSIONS. 2. OPERATING WEIGHTS. 3. SUPPORT LOADING POINTS AND LOADS. 4. FAN CFM AND BRAKE HORSEPOWER. 5. MOTOR DATA. 6. SIZES AND LOCATIONS OF CONNECTIONS. 7. INSTALLATION INSTRUCTIONS. 8. MAINTENANCE MANUALS. 9. SOUND POWER LEVELS. Spec Section: 23 65 00 - COOLING TOWERS Status: OPEN | Info Exchange
| 02838 | Review Response | Revise and Resubmit | 2019-10-18 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.10.18 | Info Exchange
| 04186 | Responded and Closed | Revise and Resubmit | 2019-10-18 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.10.18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-30 |  | 23 65 00-1.0 Cooling Towers Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-30 |  | 23 65 00-1.0 Cooling Towers Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-09-29 02:00 |  | 23 65 00-1.0 Cooling Towers Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-18 02:00 |  | 23 65 00-1.0 Cooling Towers Product Data_ME_POP.pdf
23 65 00-001-01 | 23 65 00 - COOLING TOWERS | 23 65 00-001-01 COOLING TOWERS - Manufacturers Instructions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-04 08:00 | 2019-11-25 | 8 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2019-11-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03229 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-04 08:00 | Submittal Number: 23 65 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/29/19 Subject: COOLING TOWERS - MANUFACTURERS INSTRUCTIONS Description: REVISED PER MEE SUBMITTAL COMMENTS. Spec Section: 23 65 00 - COOLING TOWERS Status: OPEN | Info Exchange
| 04668 | Forwarded | For Review | 2019-11-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-25 | Submittal Number: 23 65 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/29/19 Subject: COOLING TOWERS - MANUFACTURERS INSTRUCTIONS Description: REVISED PER MEE SUBMITTAL COMMENTS. Spec Section: 23 65 00 - COOLING TOWERS Status: OPEN | Info Exchange
| 03362 | Review Response | Approved as Noted | 2019-11-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.11.22 | Info Exchange
| 04818 | Responded and Closed | Approved as Noted | 2019-11-25 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.11.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-15 |  | 23 65 00-1.1 Cooling Towers Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-15 |  | 23 65 00-1.1 Cooling Towers Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-14 02:00 |  | 23 65 00-1.1 Cooling Towers Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-25 02:00 |  | 23 65 00-1.1 Cooling Towers Product Data_ME_POP.pdf
23 73 13-002-00 | 23 73 13 - AIR HANDLING UNITS WITH COIL | 23 73 13-002-00 AIR HANDLING UNITS WITH COIL - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-29 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-09-19 | 2019-09-24 | 27 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2019-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02239 | Received | For Review | 2019-08-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-19 | Submittal Number: 23 73 13-2.0 From: PATRICK KLEIN Final Due Date: 09/11/19 Subject: AIR HANDLING UNITS WITH COIL - PRODUCT DATA Description: PRODUCT DATA SHALL INDICATE DIMENSIONS, WEIGHTS, CAPACITIES, FAN PERFORMANCE, MOTOR ELECTRICAL CHARACTERISTICS, AND FINISHES OF MATERIALS. Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 03457 | Forwarded | For Review | 2019-08-29 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-09-05 | Submittal Number: 23 73 13-2.0 From: PATRICK KLEIN Final Due Date: 09/11/19 Subject: AIR HANDLING UNITS WITH COIL - PRODUCT DATA Description: PRODUCT DATA SHALL INDICATE DIMENSIONS, WEIGHTS, CAPACITIES, FAN PERFORMANCE, MOTOR ELECTRICAL CHARACTERISTICS, AND FINISHES OF MATERIALS. Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 02501 | Review Response | Revise and Resubmit | 2019-09-24 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2019.09.24 | Info Exchange
| 03776 | Responded and Closed | Revise and Resubmit | 2019-09-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.09.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-29 |  | 23 73 13-2.0 Product Data-MAM.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-29 |  | 23 7313.0 AHU's submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-29 |  | 23 73 13-2.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-29 |  | 23 7313.0 AHU's submittal.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-28 02:00 |  | 23 73 13-2.0 Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-28 02:00 |  | 23 7313.0 AHU's submittal.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-24 02:00 |  | 23 73 13-2.0 Product Data_ME_POP.pdf
23 73 13-002-01 | 23 73 13 - AIR HANDLING UNITS WITH COIL | 23 73 13-002-01 AIR HANDLING UNITS WITH COIL - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-04 08:00 | 2019-11-25 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-11-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03238 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) | 2019-12-04 08:00 | Submittal Number: 23 73 13-2.1 From: GRETCHEN TOSHACH Final Due Date: 11/29/19 Subject: AIR HANDLING UNITS WITH COIL - PRODUCT DATA Description: PRODUCT DATA SHALL INDICATE DIMENSIONS, WEIGHTS, CAPACITIES, FAN PERFORMANCE, MOTOR ELECTRICAL CHARACTERISTICS, AND FINISHES OF MATERIALS. Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 04677 | Forwarded | For Review | 2019-11-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-25 | Submittal Number: 23 73 13-2.1 From: GRETCHEN TOSHACH Final Due Date: 11/29/19 Subject: AIR HANDLING UNITS WITH COIL - PRODUCT DATA Description: PRODUCT DATA SHALL INDICATE DIMENSIONS, WEIGHTS, CAPACITIES, FAN PERFORMANCE, MOTOR ELECTRICAL CHARACTERISTICS, AND FINISHES OF MATERIALS. Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 03360 | Review Response | Revise and Resubmit | 2019-11-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Refer to disposition comments. Nick Theimer ME Engineers 2019.11.22 | Info Exchange
| 04826 | Forwarded | For Review | 2019-11-25 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-02 | Submittal Number: 23 73 13-2.1 From: GRETCHEN TOSHACH Final Due Date: 11/29/19 Subject: AIR HANDLING UNITS WITH COIL - PRODUCT DATA Description: PRODUCT DATA SHALL INDICATE DIMENSIONS, WEIGHTS, CAPACITIES, FAN PERFORMANCE, MOTOR ELECTRICAL CHARACTERISTICS, AND FINISHES OF MATERIALS. Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 03372 | Review Response | Revise and Resubmit | 2019-11-25 | Nick Theimer (ME Engineers) | Josh Dobken (Populous) |  | See attached for updated file. Nick Theimer ME Engineers 2019.11.25 | Info Exchange
| 04828 | Responded and Closed | Revise and Resubmit | 2019-11-25 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Refer to disposition comments. Nick Theimer ME Engineers 2019.11.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-18 |  | 23 73 13-32.1 AHU Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-18 |  | 23 73 13-32.1 AHU Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-17 02:00 |  | 23 73 13-32.1 AHU Product Data - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-17 02:00 |  | 23 73 13-32.1 AHU Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-17 02:00 |  | 23 73 13-32.1 AHU Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-25 02:00 |  | 23 73 13-02.1 AHU Product Data_ME_POP.pdf
23 73 13-002-02 | 23 73 13 - AIR HANDLING UNITS WITH COIL | 23 73 13-002-02 AIR HANDLING UNITS WITH COIL - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-16 | 2019-12-23 | 6 | General | Record Copies; Transfers; Submittals |  | 5 |  | 2019-12-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03678 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2020-01-16 | Submittal Number: 23 73 13-2.2 From: GRETCHEN TOSHACH Final Due Date: 12/27/19 Subject: AIR HANDLING UNITS WITH COIL - PRODUCT DATA Description: PRODUCT DATA SHALL INDICATE DIMENSIONS, WEIGHTS, CAPACITIES, FAN PERFORMANCE, MOTOR ELECTRICAL CHARACTERISTICS, AND FINISHES OF MATERIALS. ADDRESS SUBMITTAL REVISION COMMENTS, COMMENTS REQUIRING RESUBMITTAL FOR BOWL AHUS (2A.01, 2B.01, 2C.01, 2D.01), EAST ICE SUITES (AHU 2A.02), WEST ICE SUITES (AHU 2C.02) Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 05198 | Forwarded | For Review | 2019-12-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-25 | Submittal Number: 23 73 13-2.2 From: GRETCHEN TOSHACH Final Due Date: 12/27/19 Subject: AIR HANDLING UNITS WITH COIL - PRODUCT DATA Description: PRODUCT DATA SHALL INDICATE DIMENSIONS, WEIGHTS, CAPACITIES, FAN PERFORMANCE, MOTOR ELECTRICAL CHARACTERISTICS, AND FINISHES OF MATERIALS. ADDRESS SUBMITTAL REVISION COMMENTS, COMMENTS REQUIRING RESUBMITTAL FOR BOWL AHUS (2A.01, 2B.01, 2C.01, 2D.01), EAST ICE SUITES (AHU 2A.02), WEST ICE SUITES (AHU 2C.02) Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 03735 | Review Response | Approved as Noted | 2019-12-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.22 | Info Exchange
| 05265 | Responded and Closed | Approved as Noted | 2019-12-23 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 23 73 13-2.1 MAU_ AHU's Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-18 |  | 23 73 13-2.1 MAU_ AHU's Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-12-17 02:00 |  | 23 73 13-2.1 MAU_ AHU's Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-23 02:00 |  | 23 73 13-2.2 MAU_ AHU's Product Data_ME_POP.pdf
23 73 13-003-00 | 23 73 13 - AIR HANDLING UNITS WITH COIL | 23 73 13-003-00 AIR HANDLING UNITS WITH COIL - Energy Recovery Ventilation Unit Package | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-06 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-09-20 | 2019-09-24 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2019-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02318 | Received | For Review | 2019-09-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-20 | Submittal Number: 23 73 13-3.0 From: PATRICK KLEIN Final Due Date: 09/19/19 Subject: AIR HANDLING UNITS WITH COIL - ENERGY RECOVERY VENTILATION UNIT PACKAGE Description: SUBMIT PRODUCT DATA OF FILTER SIZES AND QUANTITIES, FILTER PERFORMANCE, AND FILTER FRAMES. SUBMIT ERV UNITS Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 03550 | Forwarded | For Review | 2019-09-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-09-13 | Submittal Number: 23 73 13-3.0 From: PATRICK KLEIN Final Due Date: 09/19/19 Subject: AIR HANDLING UNITS WITH COIL - ENERGY RECOVERY VENTILATION UNIT PACKAGE Description: SUBMIT PRODUCT DATA OF FILTER SIZES AND QUANTITIES, FILTER PERFORMANCE, AND FILTER FRAMES. SUBMIT ERV UNITS Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 02502 | Review Response | Approved as Noted/Resubmit | 2019-09-24 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2019.09.24 | Info Exchange
| 03777 | Responded and Closed | Approved as Noted/Resubmit | 2019-09-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.09.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-05 |  | 23 73 13-3.0 Energy Recovery Ventilation Unit Package-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-05 |  | 23 73 13-3.0 Energy Recovery Ventilation Unit Package-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-09-04 02:00 |  | 23 73 13-3.0 Energy Recovery Ventilation Unit Package-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-24 02:00 |  | 23 73 13-3.0 Energy Recovery Ventilation Unit Package_ME_POP.pdf
23 73 13-003-01 | 23 73 13 - AIR HANDLING UNITS WITH COIL | 23 73 13-003-01 AIR HANDLING UNITS WITH COIL - Energy Recovery Ventilation Unit Package | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-04 08:00 | 2019-11-25 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-11-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03234 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-04 08:00 | Submittal Number: 23 73 13-3.1 From: GRETCHEN TOSHACH Final Due Date: 10/25/19 Subject: AIR HANDLING UNITS WITH COIL - ENERGY RECOVERY VENTILATION UNIT PACKAGE Description: SUBMIT PRODUCT DATA OF FILTER SIZES AND QUANTITIES, FILTER PERFORMANCE, AND FILTER FRAMES. SUBMIT ERV UNITS SUBMIT RE-SUBMITTAL ITEMS ONLY. Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 04673 | Forwarded | For Review | 2019-11-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-25 | Submittal Number: 23 73 13-3.1 From: GRETCHEN TOSHACH Final Due Date: 10/25/19 Subject: AIR HANDLING UNITS WITH COIL - ENERGY RECOVERY VENTILATION UNIT PACKAGE Description: SUBMIT PRODUCT DATA OF FILTER SIZES AND QUANTITIES, FILTER PERFORMANCE, AND FILTER FRAMES. SUBMIT ERV UNITS SUBMIT RE-SUBMITTAL ITEMS ONLY. Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 03373 | Review Response | Approved as Noted | 2019-11-25 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.11.25 | Info Exchange
| 04829 | Responded and Closed | Approved as Noted | 2019-11-25 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.11.25 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-18 |  | 23 73 13-3.1 Energy Recovery Ventilation unit Package - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-18 |  | 23 73 13-3.1 Energy Recovery Ventilation unit Package - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-17 02:00 |  | 23 73 13-3.1 Energy Recovery Ventilation unit Package - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-25 02:00 |  | 23 73 13-3.1 Energy Recovery Ventilation Unit Package_ME_POP.pdf
23 73 13-003-02 | 23 73 13 - AIR HANDLING UNITS WITH COIL | 23 73 13-003-02 AIR HANDLING UNITS WITH COIL - Energy Recovery Ventilation Unit Package | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-16 | 2019-12-23 | 6 | General | Record Copies; Transfers; Submittals |  | 5 |  | 2019-12-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03679 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-01-16 | Submittal Number: 23 73 13-3.2 From: GRETCHEN TOSHACH Final Due Date: 12/26/19 Subject: AIR HANDLING UNITS WITH COIL - ENERGY RECOVERY VENTILATION UNIT PACKAGE Description: RESUBMIT ERV 2B.02 FOR APPROVAL. Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 05199 | Forwarded | For Review | 2019-12-18 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-25 | Submittal Number: 23 73 13-3.2 From: GRETCHEN TOSHACH Final Due Date: 12/26/19 Subject: AIR HANDLING UNITS WITH COIL - ENERGY RECOVERY VENTILATION UNIT PACKAGE Description: RESUBMIT ERV 2B.02 FOR APPROVAL. Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 03734 | Review Response | Approved as Noted | 2019-12-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2019.12.22 | Info Exchange
| 05264 | Responded and Closed | Approved as Noted | 2019-12-23 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 23 73 13-3.2 Energy Recovery Ventilation unit Package - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-18 |  | 23 73 13-3.2 Energy Recovery Ventilation unit Package - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-12-17 02:00 |  | 23 73 13-3.2 Energy Recovery Ventilation unit Package - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-23 02:00 |  | 23 73 13-3.2 Energy Recovery Ventilation Unit Package_ME_POP.pdf
23 73 13-008-00 | 23 73 13 - AIR HANDLING UNITS WITH COIL | 23 73 13-008-00 AHUs CCD-064 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-23 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-06 | 2020-07-28 | 6 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07119 | Received | For Review | 2020-07-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-08-06 | Submittal Number: 23 73 13-8.0 From: GRETCHEN TOSHACH Final Due Date: 08/05/20 Subject: AHUS CCD-064 Description: Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 09510 | Forwarded | For Review | 2020-07-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-30 | Submittal Number: 23 73 13-8.0 From: GRETCHEN TOSHACH Final Due Date: 08/05/20 Subject: AHUS CCD-064 Description: Spec Section: 23 73 13 - AIR HANDLING UNITS WITH COIL Status: OPEN | Info Exchange
| 07222 | Review Response | Approved as Noted | 2020-07-27 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.07.27 | Info Exchange
| 09635 | Responded and Closed | Approved as Noted | 2020-07-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-23 |  | 23 73 13-8.0 AHU_MAU CCD-064 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-23 |  | 23 73 13-8.0 AHU_MAU CCD-064 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-22 02:00 |  | 23 73 13-8.0 AHU_MAU CCD-064 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-28 02:00 |  | 23 73 13-8.0 AHU_MAU CCD-064_ME_pop.pdf
23 73 25-001-00 | 23 73 25 - DESICCANT AIR HANDLING UNITS WITH COILS | 23 73 25-001-00 DESICCANT AIR HANDLING UNITS WITH COILS - Schedules | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-11 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-25 | 2019-11-01 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2019-11-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02734 | Received | For Review | 2019-10-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-10-25 | Submittal Number: 23 73 25-1.0 From: GRETCHEN TOSHACH Final Due Date: 11/08/19 Subject: DESICCANT AIR HANDLING UNITS WITH COILS - SCHEDULES Description: EQUIPMENT SCHEDULE CONTAINING DEHUMIDIFICATION, FAN MOTOR DATA, GAS REQUIREMENT, ELECTRICAL POWER REQUIREMENT AND FILTRATION SCHEDULE. Spec Section: 23 73 25 - DESICCANT AIR HANDLING UNITS WITH COILS Status: OPEN | Info Exchange
| 04070 | Forwarded | For Review | 2019-10-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-18 | Submittal Number: 23 73 25-1.0 From: GRETCHEN TOSHACH Final Due Date: 11/08/19 Subject: DESICCANT AIR HANDLING UNITS WITH COILS - SCHEDULES Description: EQUIPMENT SCHEDULE CONTAINING DEHUMIDIFICATION, FAN MOTOR DATA, GAS REQUIREMENT, ELECTRICAL POWER REQUIREMENT AND FILTRATION SCHEDULE. Spec Section: 23 73 25 - DESICCANT AIR HANDLING UNITS WITH COILS Status: OPEN | Info Exchange
| 03013 | Review Response | Approved as Noted | 2019-11-01 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.11.01 | Info Exchange
| 04403 | Responded and Closed | Approved as Noted | 2019-11-01 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.11.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-11 |  | 23 73 25-1.0 Desiccant AHU's Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-11 |  | 23 73 25-1.0 Desiccant AHU's Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-10-10 02:00 |  | 23 73 25-1.0 Desiccant AHU's Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-01 02:00 |  | 23 73 25-1.0 Desiccant AHU's Product Data_ME_POP.pdf
23 73 25-001-01 | 23 73 25 - DESICCANT AIR HANDLING UNITS WITH COILS | 23 73 25-001-01 DESICCANT AIR HANDLING UNITS WITH COILS - Schedules | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-10 | 2019-12-23 | 6 | General | Record Copies; Transfers; Submittals |  | 5 |  | 2019-12-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03680 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-01-10 | Submittal Number: 23 73 25-1.1 From: GRETCHEN TOSHACH Final Due Date: 12/06/19 Subject: DESICCANT AIR HANDLING UNITS WITH COILS - SCHEDULES Description: EQUIPMENT SCHEDULE CONTAINING DEHUMIDIFICATION, FAN MOTOR DATA, GAS REQUIREMENT, ELECTRICAL POWER REQUIREMENT AND FILTRATION SCHEDULE. Spec Section: 23 73 25 - DESICCANT AIR HANDLING UNITS WITH COILS Status: OPEN | Info Exchange
| 05200 | Forwarded | For Review | 2019-12-18 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-25 | Submittal Number: 23 73 25-1.1 From: GRETCHEN TOSHACH Final Due Date: 12/06/19 Subject: DESICCANT AIR HANDLING UNITS WITH COILS - SCHEDULES Description: EQUIPMENT SCHEDULE CONTAINING DEHUMIDIFICATION, FAN MOTOR DATA, GAS REQUIREMENT, ELECTRICAL POWER REQUIREMENT AND FILTRATION SCHEDULE. Spec Section: 23 73 25 - DESICCANT AIR HANDLING UNITS WITH COILS Status: OPEN | Info Exchange
| 03736 | Review Response | No Action Taken or Required | 2019-12-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Submitted for information only. Nick Theimer ME Engineers 2019.12.22 | Info Exchange
| 05267 | Responded and Closed | No Action Taken or Required | 2019-12-23 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (No Action Taken or Required) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Submitted for information only. Nick Theimer ME Engineers 2019.12.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 23 73 25-1.1 Desiccant AHU's Product Data - MAM[1].pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-18 |  | 23 73 25-1.1 Desiccant AHU's Product Data - MAM[1].pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-12-17 02:00 |  | 23 73 25-1.1 Desiccant AHU's Product Data - MAM[1].pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-17 02:00 |  | 23 73 25-1.1 Desiccant AHU's Product Data - MAM[1].pdf
23 73 25-004-00 | 23 73 25 - DESICCANT AIR HANDLING UNITS WITH COILS | 23 73 25-004-00 DESICCANT AIR HANDLING UNITS WITH COILS - General | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-05 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-19 | 2021-01-11 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-01-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10458 | Received | For Review | 2021-01-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Gretchen Toshach (Mortenson Construction) | 2021-01-19 | Submittal Number: 23 73 25-4.0 From: GRETCHEN TOSHACH Final Due Date: 07/26/21 Subject: DESICCANT AIR HANDLING UNITS WITH COILS - GENERAL Description: CONTROL DIAGRAMS AND PARTS LISTS SHOWING ALL ELECTRICAL CIRCUITS, COMPONENTS RATING AND ANY APPLICABLE SETPOINTS. Spec Section: 23 73 25 - DESICCANT AIR HANDLING UNITS WITH COILS Status: OPEN | Info Exchange
| 13654 | Forwarded | For Review | 2021-01-05 | Gretchen Toshach (Mortenson Construction) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-12 | Submittal Number: 23 73 25-4.0 From: GRETCHEN TOSHACH Final Due Date: 07/26/21 Subject: DESICCANT AIR HANDLING UNITS WITH COILS - GENERAL Description: CONTROL DIAGRAMS AND PARTS LISTS SHOWING ALL ELECTRICAL CIRCUITS, COMPONENTS RATING AND ANY APPLICABLE SETPOINTS. Spec Section: 23 73 25 - DESICCANT AIR HANDLING UNITS WITH COILS Status: OPEN | Info Exchange
| 10614 | Review Response | Approved | 2021-01-06 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.01.06 | Info Exchange
| 13821 | Responded and Closed | Approved | 2021-01-11 | Gretchen Toshach (Mortenson Construction) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.01.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-05 |  | 23 73 25-4.0 DAHU-XX.XX Wiring Diagrams - MAM.pdf
| Forwarded |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-01-05 |  | 23 73 25-4.0 DAHU-XX.XX Wiring Diagrams - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-01-05 |  | 23 73 25-4.0 DAHU-XX.XX Wiring Diagrams - MAM.pdf
| Responded and Closed |  | Gretchen Toshach (Mortenson Construction) | 1 | 2021-01-11 |  | 23 73 25-4.0 DAHU-XX.XX Wiring Diagrams_ME_POP.pdf
23 81 19-003-00 | 23 81 19 - AIR CONDITIONING UNITS - HEAT PUMPS | 23 81 19-003-00 AIR CONDITIONING UNITS HEAT PUMPS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-31 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-20 | 2019-08-28 | 29 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2019-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01922 | Received | For Review | 2019-07-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-20 | Submittal Number: 23 81 19-3.0 From: PATRICK KLEIN Final Due Date: 08/13/19 Subject: AIR CONDITIONING UNITS/HEAT PUMPS - PRODUCT DATA Description: SUBMIT PRODUCT DATA OF FILTER SIZES AND QUANTITIES, FILTER PERFORMANCE, AND FILTER FRAMES. Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 03068 | Forwarded | For Review | 2019-07-31 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-07 | Submittal Number: 23 81 19-3.0 From: PATRICK KLEIN Final Due Date: 08/13/19 Subject: AIR CONDITIONING UNITS/HEAT PUMPS - PRODUCT DATA Description: SUBMIT PRODUCT DATA OF FILTER SIZES AND QUANTITIES, FILTER PERFORMANCE, AND FILTER FRAMES. Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 02188 | Review Response | Approved as Noted | 2019-08-26 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.08.26 | Info Exchange
| 03392 | Responded and Closed | Approved as Noted | 2019-08-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.08.26 | Info Exchange
| 03443 | Reopened | Additional Information | 2019-08-28 15:10 | Josh Dobken (Populous) |  |  | VSV heat pump cooling discharge temperature review updated. Revised submittal to be attached.
| 03444 | Responded and Closed | Approved as Noted | 2019-08-28 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Reopened (Additional Information) by: Josh Dobken Remarks: VSV heat pump cooling discharge temperature review updated. Revised submittal attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-30 |  | 23 81 19-3.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-31 |  | 23 81 19-3.0 AC Units Heat Pumps Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-30 02:00 |  | 23 81 19-3.0 AC Units Heat Pumps Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-26 02:00 |  | 23 81 19-3.0 AC Units Heat Pumps Product Data-ME_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-28 02:00 |  | 23 81 19-3.0 AC Units Heat Pumps Product Data-ME revised_POP.pdf
23 81 19-003-01 | 23 81 19 - AIR CONDITIONING UNITS - HEAT PUMPS | 23 81 19-003-01 AIR CONDITIONING UNITS/HEAT PUMPS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-15 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-03 | 2019-11-22 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-11-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03217 | Received | For Review | 2019-11-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) | 2019-12-03 | Submittal Number: 23 81 19-3.1 From: GRETCHEN TOSHACH Final Due Date: 01/27/20 Subject: AIR CONDITIONING UNITS/HEAT PUMPS - PRODUCT DATA Description: SUBMITTAL HELD FOR PUMPS TO BE SUBMITTED AS A PART OF THE DEFERRED SPACES. Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 04654 | Forwarded | For Review | 2019-11-15 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-22 | Submittal Number: 23 81 19-3.1 From: GRETCHEN TOSHACH Final Due Date: 01/27/20 Subject: AIR CONDITIONING UNITS/HEAT PUMPS - PRODUCT DATA Description: SUBMITTAL HELD FOR PUMPS TO BE SUBMITTED AS A PART OF THE DEFERRED SPACES. Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 03343 | Review Response | Approved as Noted | 2019-11-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.11.22 | Info Exchange
| 04797 | Responded and Closed | Approved as Noted | 2019-11-22 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.11.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-15 |  | 23 81 19-3.1 Air Conditioning Units - Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-15 |  | 23 81 19-3.1 Air Conditioning Units - Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-14 02:00 |  | 23 81 19-3.1 Air Conditioning Units - Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-22 02:00 |  | 23 81 19-3.1 AC Units Heat Pumps Product Data-ME_POP.pdf
23 81 19-008-00 | 23 81 19 - AIR CONDITIONING UNITS - HEAT PUMPS | 23 81 19-008-00 CCD-041 WSHP 1C.07 Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-25 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-10 | 2020-03-02 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04488 | Received | For Review | 2020-02-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-10 | Submittal Number: 23 81 19-8.0 From: GRETCHEN TOSHACH Final Due Date: 03/06/20 Subject: CCD-041 WSHP 1C.07 PRODUCT DATA Description: PRODUCT DATA FOR WSHP 1C.07 AS ISSUED IN CCD 041 Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 06182 | Forwarded | For Review | 2020-02-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-03 | Submittal Number: 23 81 19-8.0 From: GRETCHEN TOSHACH Final Due Date: 03/06/20 Subject: CCD-041 WSHP 1C.07 PRODUCT DATA Description: PRODUCT DATA FOR WSHP 1C.07 AS ISSUED IN CCD 041 Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 04588 | Review Response | Approved as Noted | 2020-03-02 | Nick Theimer (ME Engineers) | Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.02 | Info Exchange
| 06326 | Responded and Closed | Approved as Noted | 2020-03-02 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.03.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-24 |  | 23 81 19-8.0 WSHP-1C.07 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-24 |  | 23 81 19-8.0 WSHP-1C.07 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-02-23 02:00 |  | 23 81 19-8.0 WSHP-1C.07 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-02 02:00 |  | 23 81 19-8.0 WSHP-1C.07_ME_POP.pdf
23 81 19-009-00 | 23 81 19 - AIR CONDITIONING UNITS - HEAT PUMPS | 23 81 19-009-00 WSHPs Revisions 4B.04, 3C.03, 3D.02 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-24 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-08 | 2020-05-04 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05542 | Received | For Review | 2020-04-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-08 | Submittal Number: 23 81 19-9.0 From: GRETCHEN TOSHACH Final Due Date: 05/08/20 Subject: WSHPS REVISIONS 4B.04, 3C.03, 3D.02 Description: WSHPS AS REVISED IN: 4B.04 REVISED IN RFI 2244 3C.03 REVISED IN CCD-052 3D.02 REVISED IN CCD-052 Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 07515 | Forwarded | For Review | 2020-04-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-01 | Submittal Number: 23 81 19-9.0 From: GRETCHEN TOSHACH Final Due Date: 05/08/20 Subject: WSHPS REVISIONS 4B.04, 3C.03, 3D.02 Description: WSHPS AS REVISED IN: 4B.04 REVISED IN RFI 2244 3C.03 REVISED IN CCD-052 3D.02 REVISED IN CCD-052 Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 05711 | Review Response | Approved as Noted | 2020-05-01 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.01 | Info Exchange
| 07741 | Responded and Closed | Approved as Noted | 2020-05-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | 23 81 19-9.0 WSHP-XX.XX CCD-052 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-24 |  | 23 81 19-9.0 WSHP-XX.XX CCD-052 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-23 02:00 |  | 23 81 19-9.0 WSHP-XX.XX CCD-052 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-04 02:00 |  | 23 81 19-9.0 WSHP-XX.XX CCD-052_ME_POP.pdf
23 81 19-010-00 | 23 81 19 - AIR CONDITIONING UNITS - HEAT PUMPS | 23 81 19-010-00 WSHPs - CCD 52 Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-22 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-06 | 2020-05-04 | 13 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05505 | Received | For Review | 2020-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-06 | Submittal Number: 23 81 19-10.0 From: GRETCHEN TOSHACH Final Due Date: 05/07/20 Subject: WSHPS - CCD 52 PRODUCT DATA Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 07463 | Forwarded | For Review | 2020-04-22 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-29 | Submittal Number: 23 81 19-10.0 From: GRETCHEN TOSHACH Final Due Date: 05/07/20 Subject: WSHPS - CCD 52 PRODUCT DATA Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 05708 | Review Response | Approved | 2020-05-01 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.01 | Info Exchange
| 07738 | Responded and Closed | Approved | 2020-05-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 23 81 19-10.0 WSHP CCD-052 Deferred - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 23 81 19-10.0 WSHP CCD-052 Deferred - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-21 02:00 |  | 23 81 19-10.0 WSHP CCD-052 Deferred - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-04 02:00 |  | 23 81 19-10.0 WSHP CCD-052 Deferred_ME_POP.pdf
23 81 19-011-00 | 23 81 19 - AIR CONDITIONING UNITS - HEAT PUMPS | 23 81 19-011-00 WSHPs - CCD54, 55, 58 Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-27 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-10 | 2020-06-12 | 17 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-06-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06056 | Received | For Review | 2020-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-06-10 | Submittal Number: 23 81 19-11.0 From: GRETCHEN TOSHACH Final Due Date: 06/24/20 Subject: WSHPS - CCD54, 55, 58 PRODUCT DATA Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 08206 | Forwarded | For Review | 2020-05-27 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-03 | Submittal Number: 23 81 19-11.0 From: GRETCHEN TOSHACH Final Due Date: 06/24/20 Subject: WSHPS - CCD54, 55, 58 PRODUCT DATA Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 06380 | Review Response | Revise and Resubmit | 2020-06-10 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.06.10 | Info Exchange
| 08597 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.06.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-27 |  | 23 81 19-11.0 WSHP-XX CCD-54-55-58 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-27 |  | 23 81 19-11.0 WSHP-XX CCD-54-55-58 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-26 02:00 |  | 23 81 19-11.0 WSHP-XX CCD-54-55-58 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-12 02:00 |  | 23 81 19-11.0 WSHP-XX CCD-54-55-58_ME_pop.pdf
23 81 19-011-01 | 23 81 19 - AIR CONDITIONING UNITS - HEAT PUMPS | 23 81 19-011-01 WSHPs - CCD54, 55, 58 Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-20 | 2020-07-21 | 16 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06784 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 23 81 19-11.1 From: GRETCHEN TOSHACH Final Due Date: 07/13/20 Subject: WSHPS - CCD54, 55, 58 PRODUCT DATA Description: RESUBMIT WSHP AS SPECIFIED IN REVIEW COMMENTS OF PREVIOUS SUBMITTAL VERSION. Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 09119 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-13 | Submittal Number: 23 81 19-11.1 From: GRETCHEN TOSHACH Final Due Date: 07/13/20 Subject: WSHPS - CCD54, 55, 58 PRODUCT DATA Description: RESUBMIT WSHP AS SPECIFIED IN REVIEW COMMENTS OF PREVIOUS SUBMITTAL VERSION. Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 07062 | Review Response | Approved as Noted | 2020-07-14 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| 09451 | Responded and Closed | Approved as Noted | 2020-07-21 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 23 81 19-11.1 WSHP 2A.13 CCD.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 23 81 19-11.1 WSHP 2A.13 CCD.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-06 |  | 23 81 19-11.1 WSHP 2A.13 CCD.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-21 |  | 23 81 19-11.1 WSHP-XX CCD-54-55-58_ME_POP.pdf
23 81 19-012-00 | 23 81 19 - AIR CONDITIONING UNITS - HEAT PUMPS | 23 81 19-012-00 WSHPs - 3C.01, 3D.01, 3A.05 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-17 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-01 | 2020-06-24 | 8 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06465 | Received | For Review | 2020-06-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-01 | Submittal Number: 23 81 19-12.0 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: WSHPS - 3C.01, 3D.01, 3A.05 Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 08714 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-24 | Submittal Number: 23 81 19-12.0 From: GRETCHEN TOSHACH Final Due Date: 07/01/20 Subject: WSHPS - 3C.01, 3D.01, 3A.05 Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 06707 | Review Response | Approved as Noted | 2020-06-22 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review Nick Theimer ME Engineers 2020.06.22 | Info Exchange
| 08879 | Responded and Closed | Approved as Noted | 2020-06-24 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review Nick Theimer ME Engineers 2020.06.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 23 81 19-12.0 WSHP-3A.053C.013D.01 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 23 81 19-12.0 WSHP-3A.053C.013D.01 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-06-16 02:00 |  | 23 81 19-12.0 WSHP-3A.053C.013D.01 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-24 |  | 23 81 19-12.0 WSHP-3A.053C.013D.01_ME_POP.pdf
23 81 19-013-00 | 23 81 19 - AIR CONDITIONING UNITS - HEAT PUMPS | 23 81 19-013-00 Condensate Pumps for WSHPs | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-07 | 2020-09-29 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08300 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 23 81 19-13.0 From: GRETCHEN TOSHACH Final Due Date: 10/14/20 Subject: CONDENSATE PUMPS FOR WSHPS Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 11004 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-30 | Submittal Number: 23 81 19-13.0 From: GRETCHEN TOSHACH Final Due Date: 10/14/20 Subject: CONDENSATE PUMPS FOR WSHPS Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 08416 | Review Response | Revise and Resubmit | 2020-09-24 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| 11153 | Responded and Closed | Revise and Resubmit | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 23 82 19-8.0 FCU Condensate Pumps - MAM.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 23 81 19-13.0 FCU Condensate Pumps - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 23 81 19-13.0 FCU Condensate Pumps - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-23 |  | 23 81 19-13.0 FCU Condensate Pumps - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 23 81 19-13.0 FCU Condensate Pumps_ME_POP.pdf
23 81 19-013-01 | 23 81 19 - AIR CONDITIONING UNITS - HEAT PUMPS | 23 81 19-013-01 Condensate Pumps for WSHPs | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-19 | 2020-10-05 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08557 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 23 81 19-13.1 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: CONDENSATE PUMPS FOR WSHPS Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 11316 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-12 | Submittal Number: 23 81 19-13.1 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: CONDENSATE PUMPS FOR WSHPS Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 08576 | Review Response | Approved | 2020-10-05 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.10.05 | Info Exchange
| 11337 | Responded and Closed | Approved | 2020-10-05 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 23 81 19-13.1 WSHP Condensate Pumps - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 23 81 19-13.1 WSHP Condensate Pumps - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-10-05 |  | 23 81 19-13.1 WSHP Condensate Pumps - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-05 |  | 23 81 19-13.1 WSHP Condensate Pumps_ME_POP.pdf
23 81 19-014-00 | 23 81 19 - AIR CONDITIONING UNITS - HEAT PUMPS | 23 81 19-014-00 WSHP 3B.06 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-28 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-12 | 2020-09-29 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08367 | Received | For Review | 2020-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-12 | Submittal Number: 23 81 19-14.0 From: GRETCHEN TOSHACH Final Due Date: 10/09/20 Subject: WSHP 3B.06 Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 11080 | Forwarded | For Review | 2020-09-28 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-05 | Submittal Number: 23 81 19-14.0 From: GRETCHEN TOSHACH Final Due Date: 10/09/20 Subject: WSHP 3B.06 Description: Spec Section: 23 81 19 - AIR-CONDITIONING UNITS/HEAT PUMPS Status: OPEN | Info Exchange
| 08417 | Review Response | Approved as Noted | 2020-09-28 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for reveiw. Nick Theimer ME Engineers 2020.09.28 | Info Exchange
| 11154 | Responded and Closed | Approved as Noted | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for reveiw. Nick Theimer ME Engineers 2020.09.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-25 |  | 23 81 19-14.0 WSHP-3B.06 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-25 |  | 23 81 19-14.0 WSHP-3B.06 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-25 |  | 23 81 19-14.0 WSHP-3B.06 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 23 81 19-14.0 WSHP-3B.06_ME_POP.pdf
23 81 23-001-00 | 23 81 23 - ELECTRONIC ROOM AIR CONDITIONING UNIT | 23 81 23-001-00 ELECTRONIC ROOM AIR CONDITIONING UNIT - Manufacturers Instructions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-30 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-13 | 2019-08-28 | 30 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2019-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01908 | Received | For Review | 2019-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-13 | Submittal Number: 23 81 23-1.0 From: PATRICK KLEIN Final Due Date: 08/12/19 Subject: ELECTRONIC ROOM AIR CONDITIONING UNIT - MANUFACTURERS INSTRUCTIONS Description: SUBMIT MANUFACTURERS DATA, INCLUDING : - 1. CAPACITY. 2. DRAWINGS SHOWING OVERALL DIMENSIONS OF COMPLETE ASSEMBLY. 3. OPERATING WEIGHTS. 4. EQUIPMENT SUPPORT REQUIREMENTS. 5. SIZES AND LOCATIONS OF CONNECTIONS. 6. ACCESSORIES. 7. AUXILIARY SUPPORT REQUIREMENTS. Spec Section: 23 81 23 - ELECTRONIC ROOM AIR CONDITIONING UNIT Status: OPEN | Info Exchange
| 03051 | Forwarded | For Review | 2019-07-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-06 | Submittal Number: 23 81 23-1.0 From: PATRICK KLEIN Final Due Date: 08/12/19 Subject: ELECTRONIC ROOM AIR CONDITIONING UNIT - MANUFACTURERS INSTRUCTIONS Description: SUBMIT MANUFACTURERS DATA, INCLUDING : - 1. CAPACITY. 2. DRAWINGS SHOWING OVERALL DIMENSIONS OF COMPLETE ASSEMBLY. 3. OPERATING WEIGHTS. 4. EQUIPMENT SUPPORT REQUIREMENTS. 5. SIZES AND LOCATIONS OF CONNECTIONS. 6. ACCESSORIES. 7. AUXILIARY SUPPORT REQUIREMENTS. Spec Section: 23 81 23 - ELECTRONIC ROOM AIR CONDITIONING UNIT Status: OPEN | Info Exchange
| 02167 | Review Response | Approved as Noted | 2019-08-21 | Nick Theimer (ME Engineers) | Tom Usher (Populous); Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.08.21 | Info Exchange
| 03364 | Responded and Closed | Approved as Noted | 2019-08-21 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.08.21 | Info Exchange
| 03445 | Reopened | Additional Information | 2019-08-28 16:43 | Josh Dobken (Populous) |  |  | Reopened to update CRAC submittal based on discussion with M-E, Hermanson and MAM. See attached submittal
| 03446 | Responded and Closed | Approved as Noted | 2019-08-28 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Reopened (Additional Information) by: Josh Dobken Remarks: Reopened to update CRAC submittal based on discussion with M-E, Hermanson and MAM. See attached submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-29 |  | 23 81 23-1.0 Manufacturer's Instructions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-29 |  | 23 81 23-1.0 Manufacturer's Instructions-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-28 02:00 |  | 23 81 23-1.0 Manufacturer's Instructions-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-21 02:00 |  | 23 81 23-1.0 Manufacturer's Instructions-ME_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-28 02:00 |  | 23 81 23-1.0 Manufacturer's Instructions-ME revised_POP.pdf
23 81 26-001-00 | 23 81 26 - SPLIT SYSTEM AIR CONDITIONERS | 23 81 26-001-00 SPLIT SYSTEM AIR CONDITIONERS - Performance Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-17 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-07-31 | 2019-08-01 | 16 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-08-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01793 | Received | For Review | 2019-07-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-07-31 | Submittal Number: 23 81 26-1.0 From: PATRICK KLEIN Final Due Date: 07/30/19 Subject: SPLIT SYSTEM AIR CONDITIONERS - PERFORMANCE DATA Description: DESCRIPTIVE DATA: A. PERFORMANCE DATA. B. PUBLISHED SOUND POWER LEVELS BASED ON ACTUAL TEST DATA. C. FINISHES. D. PIPING ARRANGEMENT. E. ACCESSORIES. F. CONDENSING UNIT AND FAN COIL UNIT OPERATING WEIGHTS. Spec Section: 23 81 26 - SPLIT-SYSTEM AIR CONDITIONERS Status: OPEN | Info Exchange
| 02919 | Forwarded | For Review | 2019-07-17 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-07-24 | Submittal Number: 23 81 26-1.0 From: PATRICK KLEIN Final Due Date: 07/30/19 Subject: SPLIT SYSTEM AIR CONDITIONERS - PERFORMANCE DATA Description: DESCRIPTIVE DATA: A. PERFORMANCE DATA. B. PUBLISHED SOUND POWER LEVELS BASED ON ACTUAL TEST DATA. C. FINISHES. D. PIPING ARRANGEMENT. E. ACCESSORIES. F. CONDENSING UNIT AND FAN COIL UNIT OPERATING WEIGHTS. Spec Section: 23 81 26 - SPLIT-SYSTEM AIR CONDITIONERS Status: OPEN | Info Exchange
| 01945 | Review Response | Approved as Noted | 2019-07-30 | Nick Theimer (ME Engineers) | Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.07.30 | Info Exchange
| 03092 | Responded and Closed | Approved as Noted | 2019-08-01 | Todd Spangler (Populous) | Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review. Nick Theimer ME Engineers 2019.07.30 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-16 |  | 23 81 26-1.0 Performance Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-17 |  | 23 81 26-1.0 Performance Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-17 |  | 23 81 26-1.0 Performance Data-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-07-16 |  | 23 81 26-1.0 Performance Data-MAM.pdf
23 81 26-001-01 | 23 81 26 - SPLIT SYSTEM AIR CONDITIONERS | 23 81 26-001-01 SPLIT SYSTEM AIR CONDITIONERS - Performance Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-11 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-25 | 2019-10-18 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-10-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02735 | Received | For Review | 2019-10-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-10-25 | Submittal Number: 23 81 26-1.1 From: GRETCHEN TOSHACH Final Due Date: 10/09/19 Subject: SPLIT SYSTEM AIR CONDITIONERS - PERFORMANCE DATA Description: DESCRIPTIVE DATA: A. PERFORMANCE DATA. B. PUBLISHED SOUND POWER LEVELS BASED ON ACTUAL TEST DATA. C. FINISHES. D. PIPING ARRANGEMENT. E. ACCESSORIES. F. CONDENSING UNIT AND FAN COIL UNIT OPERATING WEIGHTS. Spec Section: 23 81 26 - SPLIT-SYSTEM AIR CONDITIONERS Status: OPEN | Info Exchange
| 04071 | Forwarded | For Review | 2019-10-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-18 | Submittal Number: 23 81 26-1.1 From: GRETCHEN TOSHACH Final Due Date: 10/09/19 Subject: SPLIT SYSTEM AIR CONDITIONERS - PERFORMANCE DATA Description: DESCRIPTIVE DATA: A. PERFORMANCE DATA. B. PUBLISHED SOUND POWER LEVELS BASED ON ACTUAL TEST DATA. C. FINISHES. D. PIPING ARRANGEMENT. E. ACCESSORIES. F. CONDENSING UNIT AND FAN COIL UNIT OPERATING WEIGHTS. Spec Section: 23 81 26 - SPLIT-SYSTEM AIR CONDITIONERS Status: OPEN | Info Exchange
| 02837 | Review Response | Approved | 2019-10-18 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.10.18 | Info Exchange
| 04185 | Responded and Closed | Approved | 2019-10-18 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.10.18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-11 |  | 23 81 26.-.1 AC_CU-4F.02_Split Syst CCD 012 Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-11 |  | 23 81 26.-.1 AC_CU-4F.02_Split Syst CCD 012 Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-10-10 02:00 |  | 23 81 26.-.1 AC_CU-4F.02_Split Syst CCD 012 Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-18 02:00 |  | 23 81 26.-.1 AC_CU-4F.02_Split Syst CCD 012 Product Data _ME_POP.pdf
23 81 26-004-00 | 23 81 26 - SPLIT SYSTEM AIR CONDITIONERS | 23 81 26-004-00 AC 5F.01 / CU 4F.03 - CCD 042 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-11 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-25 | 2020-03-18 | 8 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04765 | Received | For Review | 2020-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-25 | Submittal Number: 23 81 26-4.0 From: GRETCHEN TOSHACH Final Due Date: 04/13/20 Subject: AC 5F.01 / CU 4F.03 - CCD 042 Description: AIRCONDITIONING SPLIT UNIT AC 5F.01 / CU 4F.03 PER CCD 042 Spec Section: 23 81 26 - SPLIT-SYSTEM AIR CONDITIONERS Status: OPEN | Info Exchange
| 06539 | Forwarded | For Review | 2020-03-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-18 | Submittal Number: 23 81 26-4.0 From: GRETCHEN TOSHACH Final Due Date: 04/13/20 Subject: AC 5F.01 / CU 4F.03 - CCD 042 Description: AIRCONDITIONING SPLIT UNIT AC 5F.01 / CU 4F.03 PER CCD 042 Spec Section: 23 81 26 - SPLIT-SYSTEM AIR CONDITIONERS Status: OPEN | Info Exchange
| 04841 | Review Response | Revise and Resubmit | 2020-03-13 | Nick Theimer (ME Engineers) | Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.03.13 | Info Exchange
| 06618 | Forwarded | For Review | 2020-03-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers) |  | Submittal Number: 23 81 26-4.0 From: GRETCHEN TOSHACH Final Due Date: 04/13/20 Subject: AC 5F.01 / CU 4F.03 - CCD 042 Description: AIRCONDITIONING SPLIT UNIT AC 5F.01 / CU 4F.03 PER CCD 042 Spec Section: 23 81 26 - SPLIT-SYSTEM AIR CONDITIONERS Status: OPEN | Info Exchange
| 04928 | Review Response | Approved as Noted | 2020-03-16 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for updated review. Nick Theimer ME Engineers 2020.03.16 | Info Exchange
| 06724 | Responded and Closed | Approved as Noted | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for updated review. Nick Theimer ME Engineers 2020.03.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 23 81 26-4.0 Split Syst CCD-042 Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-11 |  | 23 81 26-4.0 Split Syst CCD-042 Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-11 |  | 23 81 26-4.0 Split Syst CCD-042 Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-11 |  | 23 81 26-4.0 Split Syst CCD-042 Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-03-10 02:00 |  | 23 81 26-4.0 Split Syst CCD-042 Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-18 02:00 |  | 23 81 26-4.0 Split Syst CCD-042 Product Data_ME_POP.pdf
23 81 26-005-00 | 23 81 26 - SPLIT SYSTEM AIR CONDITIONERS | 23 81 26-005-00 Split System Air Conditioners CCD 64 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-20 | 2020-07-21 | 16 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06785 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 23 81 26-5.0 From: GRETCHEN TOSHACH Final Due Date: 08/11/20 Subject: SPLIT SYSTEM AIR CONDITIONERS CCD 64 Description: Spec Section: 23 81 26 - SPLIT-SYSTEM AIR CONDITIONERS Status: OPEN | Info Exchange
| 09120 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-13 | Submittal Number: 23 81 26-5.0 From: GRETCHEN TOSHACH Final Due Date: 08/11/20 Subject: SPLIT SYSTEM AIR CONDITIONERS CCD 64 Description: Spec Section: 23 81 26 - SPLIT-SYSTEM AIR CONDITIONERS Status: OPEN | Info Exchange
| 07069 | Review Response | Approved | 2020-07-14 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| 09459 | Responded and Closed | Approved | 2020-07-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 23 81 26-5.0 AC-2E.01 CCD-064 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 23 81 26-5.0 AC-2E.01 CCD-064 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-05 02:00 |  | 23 81 26-5.0 AC-2E.01 CCD-064 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-21 02:00 |  | 23 81 26-5.0 AC-2E.01 CCD-064_ME_pop.pdf
23 82 16-001-00 | 23 82 16 - AIR COILS | 23 82 16-001-00 AIR COILS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-31 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-14 | 2019-08-09 | 10 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01923 | Received | For Review | 2019-07-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-14 | Submittal Number: 23 82 16-1.0 From: PATRICK KLEIN Final Due Date: 08/13/19 Subject: AIR COILS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA INCLUDING : - 1. PERFORMANCE DATA. 2. ACCESSORIES DESCRIPTION 3. OPERATING WEIGHT. 4. DRAWINGS SHOWING: A. DIMENSIONS. B. SIZES AND LOCATIONS OF CONNECTIONS. 5. SUPPORT REQUIREMENT. Spec Section: 23 82 16 - AIR COILS Status: OPEN | Info Exchange
| 03069 | Forwarded | For Review | 2019-07-31 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-07 | Submittal Number: 23 82 16-1.0 From: PATRICK KLEIN Final Due Date: 08/13/19 Subject: AIR COILS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA INCLUDING : - 1. PERFORMANCE DATA. 2. ACCESSORIES DESCRIPTION 3. OPERATING WEIGHT. 4. DRAWINGS SHOWING: A. DIMENSIONS. B. SIZES AND LOCATIONS OF CONNECTIONS. 5. SUPPORT REQUIREMENT. Spec Section: 23 82 16 - AIR COILS Status: OPEN | Info Exchange
| 02018 | Review Response | Approved as Noted | 2019-08-07 | Nick Theimer (ME Engineers) | Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.08.07 | Info Exchange
| 03191 | Responded and Closed | Approved as Noted | 2019-08-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.08.07 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-30 |  | 23 82 16-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-31 |  | 23 82 16-1.0 Air Coils Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-31 |  | 23 82 16-1.0 Air Coils Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-09 02:00 |  | 23 82 16-1.0 Air Coils Product Data_ME_POP.pdf
23 82 19-003-00 | 23 82 19 - FAN COIL UNITS | 23 82 19-003-00 FAN COIL UNIT - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-15 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-29 | 2019-08-26 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02073 | Received | For Review | 2019-08-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-08-29 | Submittal Number: 23 82 19-3.0 From: PATRICK KLEIN Final Due Date: 08/28/19 Subject: FAN COIL UNIT - PRODUCT DATA Description: SUBMIT PRODUCT DATA OF FILTER SIZES AND QUANTITIES, FILTER PERFORMANCE, AND FILTER FRAMES. Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 03246 | Forwarded | For Review | 2019-08-15 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-22 | Submittal Number: 23 82 19-3.0 From: PATRICK KLEIN Final Due Date: 08/28/19 Subject: FAN COIL UNIT - PRODUCT DATA Description: SUBMIT PRODUCT DATA OF FILTER SIZES AND QUANTITIES, FILTER PERFORMANCE, AND FILTER FRAMES. Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 02196 | Review Response | Approved as Noted | 2019-08-26 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2019.08.26 | Info Exchange
| 03401 | Responded and Closed | Approved as Noted | 2019-08-26 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.08.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-14 |  | 23 82 19-3.0 Product Data-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-08-14 |  | 23 82 19-3.0 Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-13 02:00 |  | 23 82 19-3.0 Product Data-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-08-26 02:00 |  | 23 82 19-3.0 Fan Coil Product Data-ME_POP.pdf
23 82 19-003-01 | 23 82 19 - FAN COIL UNITS | 23 82 19-003-01 FAN COIL UNIT - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-25 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-10 | 2019-10-02 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-10-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02534 | Received | For Review | 2019-09-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | . (Seattle Arena Company, LLC) | 2019-10-10 | Submittal Number: 23 82 19-3.1 From: GRETCHEN TOSHACH Final Due Date: 01/31/20 Subject: FAN COIL UNIT - PRODUCT DATA Description: FAN COIL UNITS FOR DEFERRED SPACES TO BE SUBMITTED UNDER THIS SUBMITTAL Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 03820 | Forwarded | For Review | 2019-09-26 | . (Seattle Arena Company, LLC) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-03 | Submittal Number: 23 82 19-3.1 From: GRETCHEN TOSHACH Final Due Date: 01/31/20 Subject: FAN COIL UNIT - PRODUCT DATA Description: FAN COIL UNITS FOR DEFERRED SPACES TO BE SUBMITTED UNDER THIS SUBMITTAL Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 02637 | Review Response | Approved as Noted | 2019-10-02 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2019.10.02 | Info Exchange
| 03946 | Responded and Closed | Approved as Noted | 2019-10-02 | . (Seattle Arena Company, LLC) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.10.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-25 02:00 |  | 23 82 19-1.1 Fan Coil Unit Product Data - MAM.pdf
| Forwarded |  | . (Seattle Arena Company, LLC) | 1 | 2019-09-25 02:00 |  | 23 82 19-1.1 Fan Coil Unit Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-09-25 02:00 |  | 23 82 19-1.1 Fan Coil Unit Product Data - MAM.pdf
| Responded and Closed |  | . (Seattle Arena Company, LLC) | 1 | 2019-10-02 02:00 |  | 23 82 19-3.1 Product Data-ME_POP.pdf
23 82 19-006-00 | 23 82 19 - FAN COIL UNITS | 23 82 19-006-00 FAN COIL UNIT- CCD 52 Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-21 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-05 | 2020-05-04 | 14 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05485 | Received | For Review | 2020-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Chris Minter (Populous); Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-05 | Submittal Number: 23 82 19-6.0 From: GRETCHEN TOSHACH Final Due Date: 05/07/20 Subject: FAN COIL UNIT- CCD 52 PRODUCT DATA Description: Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 07439 | Forwarded | For Review | 2020-04-21 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-28 | Submittal Number: 23 82 19-6.0 From: GRETCHEN TOSHACH Final Due Date: 05/07/20 Subject: FAN COIL UNIT- CCD 52 PRODUCT DATA Description: Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 05707 | Review Response | Approved | 2020-05-01 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.01 | Info Exchange
| 07737 | Responded and Closed | Approved | 2020-05-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-21 |  | 23 82 19-6.0 FCU-XX-XX CCD-052 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-21 |  | 23 82 19-6.0 FCU-XX-XX CCD-052 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-04-20 02:00 |  | 23 82 19-6.0 FCU-XX-XX CCD-052 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-04 02:00 |  | 23 82 19-6.0 FCU-XX-XX CCD-052_ME_POP.pdf
23 82 19-007-00 | 23 82 19 - FAN COIL UNITS | 23 82 19-007-00 FAN COIL UNIT - CCD 055 Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-11 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-26 07:00 | 2020-05-19 | 9 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05783 | Received | For Review | 2020-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-26 07:00 | Submittal Number: 23 82 19-7.0 From: SIMRAN GEORGE Final Due Date: 06/03/20 Subject: FAN COIL UNIT - CCD 055 PRODUCT DATA Description: Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 07840 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 23 82 19-7.0 From: SIMRAN GEORGE Final Due Date: 06/03/20 Subject: FAN COIL UNIT - CCD 055 PRODUCT DATA Description: Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 05941 | Review Response | Approved | 2020-05-14 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.05.14 | Info Exchange
| 08070 | Responded and Closed | Approved | 2020-05-19 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.05.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 23 82 19-7.0 FCUs CCD055 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 23 82 19-7.0 FCUs CCD055 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-05-10 02:00 |  | 23 82 19-7.0 FCUs CCD055 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-19 02:00 |  | 23 82 19-7.0 FCUs CCD055_ME_POP.pdf
23 82 19-008-00 | 23 82 19 - FAN COIL UNITS | 23 82 19-008-00 Condensate Pumps for FCUs | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-07 | 2020-09-29 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08293 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 23 82 19-8.0 From: GRETCHEN TOSHACH Final Due Date: 10/14/20 Subject: CONDENSATE PUMPS FOR FCUS Description: Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 10999 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-30 | Submittal Number: 23 82 19-8.0 From: GRETCHEN TOSHACH Final Due Date: 10/14/20 Subject: CONDENSATE PUMPS FOR FCUS Description: Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 08415 | Review Response | Revise and Resubmit | 2020-09-24 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| 11152 | Responded and Closed | Revise and Resubmit | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.09.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 23 82 19-8.0 FCU Condensate Pumps - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 23 82 19-8.0 FCU Condensate Pumps - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-23 |  | 23 82 19-8.0 FCU Condensate Pumps - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 23 82 19-8.0 FCU Condensate Pumps_ME_POP.pdf
23 82 19-008-01 | 23 82 19 - FAN COIL UNITS | 23 82 19-008-01 Condensate Pumps for FCUs | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-19 | 2020-10-05 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08563 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 23 82 19-8.1 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: CONDENSATE PUMPS FOR FCUS Description: Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 11323 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-12 | Submittal Number: 23 82 19-8.1 From: GRETCHEN TOSHACH Final Due Date: 10/19/20 Subject: CONDENSATE PUMPS FOR FCUS Description: Spec Section: 23 82 19 - FAN COIL UNITS Status: OPEN | Info Exchange
| 08578 | Review Response | Approved | 2020-10-05 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.10.05 | Info Exchange
| 11339 | Responded and Closed | Approved | 2020-10-05 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.10.05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 23 82 19-8.1 FCU Condensate Pumps - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 23 82 19-8.1 FCU Condensate Pumps - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-10-05 |  | 23 82 19-8.1 FCU Condensate Pumps - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-05 |  | 23 82 19-8.1 FCU Condensate Pumps_ME_POP.pdf
23 82 25-001-00 | 23 82 25 - KITCHEN EXHAUST SYSTEM | 23 82 25-001-00 KITCHEN EXHAUST SYSTEM - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-24 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  |  | 2019-09-24 | 63 |  | Record Copies; Transfers; Submittals |  | 63 |  | 2019-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01859 | Received | For Review | 2019-07-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) |  | Submittal Number: 23 82 25-1.0 From: PATRICK KLEIN Final Due Date: 08/07/19 Subject: KITCHEN EXHAUST SYSTEM - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR EACH UNIT. INCLUDE : - 1. CAPACITY: A. HORSEPOWER. B. AMPS. C. STATIC PRESSURE. D. AIRFLOW (CFM). E. FAN CURVES. 2. WIRING DIAGRAMS. 3. DIMENSIONS. 4. WEIGHTS. 5. INSTALLATION INSTRUCTIONS. 6. OPTIONS PROVIDED. 7. OTHER ITEMS AS NECESSARY TO COMMUNICATE PERFORMANCE OF ITEMS PROVIDED. Spec Section: 23 82 25 - KITCHEN EXHAUST SYSTEM Status: OPEN | Info Exchange
| 02991 | Forwarded | For Review | 2019-07-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-07-31 | Submittal Number: 23 82 25-1.0 From: PATRICK KLEIN Final Due Date: 08/07/19 Subject: KITCHEN EXHAUST SYSTEM - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR EACH UNIT. INCLUDE : - 1. CAPACITY: A. HORSEPOWER. B. AMPS. C. STATIC PRESSURE. D. AIRFLOW (CFM). E. FAN CURVES. 2. WIRING DIAGRAMS. 3. DIMENSIONS. 4. WEIGHTS. 5. INSTALLATION INSTRUCTIONS. 6. OPTIONS PROVIDED. 7. OTHER ITEMS AS NECESSARY TO COMMUNICATE PERFORMANCE OF ITEMS PROVIDED. Spec Section: 23 82 25 - KITCHEN EXHAUST SYSTEM Status: OPEN | Info Exchange
| 02495 | Review Response | Revise and Resubmit | 2019-09-24 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | Revise and resubmit per updated information provided in CCD 027. Nick Theimer ME Engineers 2019.09.24 | Info Exchange
| 03771 | Responded and Closed | Revise and Resubmit | 2019-09-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: Revise and resubmit per updated information provided in CCD 027. Nick Theimer ME Engineers 2019.09.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-24 |  | 23 82 25-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-24 |  | 23 82 25-1.0 Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-07-23 02:00 |  | 23 82 25-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-24 02:00 |  | 23 82 25-1.0 Product Data_ME_POP.pdf
23 82 25-001-01 | 23 82 25 - KITCHEN EXHAUST SYSTEM | 23 82 25-001-01 KITCHEN EXHAUST SYSTEM CCD 027 - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-04 08:00 | 2019-12-09 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2019-12-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03225 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-12-04 08:00 | Submittal Number: 23 82 25-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/29/19 Subject: KITCHEN EXHAUST SYSTEM CCD 027 - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR EACH UNIT. INCLUDE : - 1. CAPACITY: A. HORSEPOWER. B. AMPS. C. STATIC PRESSURE. D. AIRFLOW (CFM). E. FAN CURVES. 2. WIRING DIAGRAMS. 3. DIMENSIONS. 4. WEIGHTS. 5. INSTALLATION INSTRUCTIONS. 6. OPTIONS PROVIDED. 7. OTHER ITEMS AS NECESSARY TO COMMUNICATE PERFORMANCE OF ITEMS PROVIDED. PER CCD 027 Spec Section: 23 82 25 - KITCHEN EXHAUST SYSTEM Status: OPEN | Info Exchange
| 04663 | Forwarded | For Review | 2019-11-15 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-22 | Submittal Number: 23 82 25-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/29/19 Subject: KITCHEN EXHAUST SYSTEM CCD 027 - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA FOR EACH UNIT. INCLUDE : - 1. CAPACITY: A. HORSEPOWER. B. AMPS. C. STATIC PRESSURE. D. AIRFLOW (CFM). E. FAN CURVES. 2. WIRING DIAGRAMS. 3. DIMENSIONS. 4. WEIGHTS. 5. INSTALLATION INSTRUCTIONS. 6. OPTIONS PROVIDED. 7. OTHER ITEMS AS NECESSARY TO COMMUNICATE PERFORMANCE OF ITEMS PROVIDED. PER CCD 027 Spec Section: 23 82 25 - KITCHEN EXHAUST SYSTEM Status: OPEN | Info Exchange
| 03550 | Review Response | Approved as Noted | 2019-12-06 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| 05019 | Responded and Closed | Approved as Noted | 2019-12-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.12.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-15 |  | 23 82 25-1.1 Kitchen Exh System CCD 027 - Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-15 |  | 23 82 25-1.1 Kitchen Exh System CCD 027 - Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-11-14 02:00 |  | 23 82 25-1.1 Kitchen Exh System CCD 027 - Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 23 82 25-1.1 Kitchen Exh System CCD 027 - Product Data_ME_POP.pdf
23 82 25-003-00 | 23 82 25 - KITCHEN EXHAUST SYSTEM | 23 82 25-003-00 KITCHEN EXHAUST SYSTEMS PCUs CCD 064 - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-20 | 2020-07-21 | 16 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06786 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 23 82 25-3.0 From: GRETCHEN TOSHACH Final Due Date: 07/20/20 Subject: KITCHEN EXHAUST SYSTEMS PCUS CCD 064 - PRODUCT DATA Description: Spec Section: 23 82 25 - KITCHEN EXHAUST SYSTEM Status: OPEN | Info Exchange
| 09121 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-13 | Submittal Number: 23 82 25-3.0 From: GRETCHEN TOSHACH Final Due Date: 07/20/20 Subject: KITCHEN EXHAUST SYSTEMS PCUS CCD 064 - PRODUCT DATA Description: Spec Section: 23 82 25 - KITCHEN EXHAUST SYSTEM Status: OPEN | Info Exchange
| 07070 | Review Response | Approved as Noted | 2020-07-15 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2020.07.15 | Info Exchange
| 09461 | Responded and Closed | Approved as Noted | 2020-07-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-06 |  | 23 82 25-3.0 PCU CCD-64 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-06 |  | 23 82 25-3.0 PCU CCD-64 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-05 02:00 |  | 23 82 25-3.0 PCU CCD-64 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-21 02:00 |  | 23 82 25-3.0 PCU CCD-64_ME_pop.pdf
23 82 39-001-00 | 23 82 39 - HEATING TERMINAL UNITS | 23 82 39-001-00 HEATING TERMINAL UNITS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-15 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-08-29 | 2019-08-30 | 16 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-08-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02074 | Received | For Review | 2019-08-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-29 | Submittal Number: 23 82 39-1.0 From: PATRICK KLEIN Final Due Date: 08/28/19 Subject: HEATING TERMINAL UNITS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA : - 1. PERFORMANCE DATA. 2. DRAWINGS. A. DIMENSIONS B. SUPPORT REQUIREMENTS C. SIZE AND LOCATION OF CONNECTIONS 3. ENCLOSURE GAUGES. 4. ACCESSORIES. 5. PARTS LISTS. 6. ADDITIONAL SUBMITTAL REQUIREMENTS FOR FAN COIL UNITS, CABINET HEATERS AND UNIT HEATERS: A. WIRING DIAGRAMS. B. INSTALLATION, OPERATING AND MAINTENANCE INSTRUCTIONS. Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 03247 | Forwarded | For Review | 2019-08-15 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-22 | Submittal Number: 23 82 39-1.0 From: PATRICK KLEIN Final Due Date: 08/28/19 Subject: HEATING TERMINAL UNITS - PRODUCT DATA Description: SUBMIT MANUFACTURERS PRODUCT DATA : - 1. PERFORMANCE DATA. 2. DRAWINGS. A. DIMENSIONS B. SUPPORT REQUIREMENTS C. SIZE AND LOCATION OF CONNECTIONS 3. ENCLOSURE GAUGES. 4. ACCESSORIES. 5. PARTS LISTS. 6. ADDITIONAL SUBMITTAL REQUIREMENTS FOR FAN COIL UNITS, CABINET HEATERS AND UNIT HEATERS: A. WIRING DIAGRAMS. B. INSTALLATION, OPERATING AND MAINTENANCE INSTRUCTIONS. Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 02187 | Review Response | Approved as Noted/Resubmit | 2019-08-26 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Architect to comment on color selection of units as outlined in review. Nick Theimer ME Engineers 2019.08.26 | Info Exchange
| 03493 | Responded and Closed | Approved as Noted/Resubmit | 2019-08-30 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Architect to comment on color selection of units as outlined in review. Nick Theimer ME Engineers 2019.08.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-15 |  | 23 82 39-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-15 |  | 23 82 39-1.0 Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-14 02:00 |  | 23 82 39-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-30 02:00 |  | 23 82 39-1.0 Product Data-ME_POP.pdf
23 82 39-001-01 | 23 82 39 - HEATING TERMINAL UNITS | 23 82 39-001-01 HEATING TERMINAL UNITS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-25 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-11-08 | 2019-11-15 | 22 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2019-11-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02919 | Received | For Review | 2019-10-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2019-11-08 | Submittal Number: 23 82 39-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/07/19 Subject: HEATING TERMINAL UNITS - PRODUCT DATA Description: PLEASE RESUBMIT ON AIRCE 5A.01 THROUGH 5D.03 Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 04290 | Forwarded | For Review | 2019-10-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-01 | Submittal Number: 23 82 39-1.1 From: GRETCHEN TOSHACH Final Due Date: 11/07/19 Subject: HEATING TERMINAL UNITS - PRODUCT DATA Description: PLEASE RESUBMIT ON AIRCE 5A.01 THROUGH 5D.03 Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 03220 | Review Response | Approved as Noted/Resubmit | 2019-11-14 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Nick Theimer ME Engineers 2019.11.14 | Info Exchange
| 04659 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.11.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-24 |  | 23 82 39-1.1 Heating Terminal Units Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-24 |  | 23 82 39-1.1 Heating Terminal Units Product Data - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-10-23 02:00 |  | 23 82 39-1.1 Heating Terminal Units Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-15 02:00 |  | 23 82 39-1.1 Heating Terminal Units Product Data - ME_POP.pdf
23 82 39-001-02 | 23 82 39 - HEATING TERMINAL UNITS | 23 82 39-001-02 HEATING TERMINAL UNITS - Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-21 | 2020-07-22 | 16 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-07-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06836 | Received | For Review | 2020-07-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-21 | Submittal Number: 23 82 39-1.2 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: HEATING TERMINAL UNITS - PRODUCT DATA Description: RESUBMIT BASEBOARD RADIATORS (JAGA/MICL) PRODUCT TO BE FLOOR MOUNTED PER SUBMITTAL COMMENTS. PROVIDE GRILLE SELECTIONS FOR ARCHITECT FINAL APPROVAL. Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 09169 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 23 82 39-1.2 From: GRETCHEN TOSHACH Final Due Date: 07/21/20 Subject: HEATING TERMINAL UNITS - PRODUCT DATA Description: RESUBMIT BASEBOARD RADIATORS (JAGA/MICL) PRODUCT TO BE FLOOR MOUNTED PER SUBMITTAL COMMENTS. PROVIDE GRILLE SELECTIONS FOR ARCHITECT FINAL APPROVAL. Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 07098 | Review Response | Approved as Noted | 2020-07-14 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Architect to confirm color in white. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| 09483 | Responded and Closed | Approved as Noted | 2020-07-22 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-07 |  | 23 82 39-1.2 Jaga Air Curtain Rev CCD 62-63.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 23 82 39-1.2 Jaga Air Curtain Rev CCD 62-63.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-07 |  | 23 82 39-1.2 Jaga Air Curtain Rev CCD 62-63.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-22 |  | 23 82 39-1.2 Jaga Air Curtain Rev CCD 62-63_ME_POP.pdf
23 82 39-001-03 | 23 82 39 - HEATING TERMINAL UNITS | 23 82 39-001-03 HEATING TERMINAL UNITS - Jaga Radiator Shop Drawings and Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-07 | 2020-09-29 | 7 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08294 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 23 82 39-1.3 From: GRETCHEN TOSHACH Final Due Date: 08/13/21 Subject: HEATING TERMINAL UNITS - JAGA RADIATOR SHOP DRAWINGS AND PRODUCT DATA Description: RESUBMITPER SUBMITTAL COMMENTS. Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 11000 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-30 | Submittal Number: 23 82 39-1.3 From: GRETCHEN TOSHACH Final Due Date: 08/13/21 Subject: HEATING TERMINAL UNITS - JAGA RADIATOR SHOP DRAWINGS AND PRODUCT DATA Description: RESUBMITPER SUBMITTAL COMMENTS. Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 08427 | Review Response | Approved as Noted | 2020-09-23 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.09.23 | Info Exchange
| 11164 | Responded and Closed | Approved as Noted | 2020-09-29 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.09.23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 23 82 39-1.3 Jaga Air Curtain_Shop Drwgs - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 23 82 39-1.3 Jaga Air Curtain_Shop Drwgs - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-09-23 |  | 23 82 39-1.3 Jaga Air Curtain_Shop Drwgs - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-29 |  | 23 82 39-1.3 Jaga Air Curtain_Shop Drwgs_ME_POP.pdf
23 82 39-002-00 | 23 82 39 - HEATING TERMINAL UNITS | 23 82 39-002-00 ECUH CCD062 | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-08 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-22 | 2020-07-22 | 15 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-07-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06834 | Received | For Review | 2020-07-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-22 | Submittal Number: 23 82 39-2.0 From: GRETCHEN TOSHACH Final Due Date: 07/24/20 Subject: ECUH CCD062 Description: REVISED ECUH PER CCD062 Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 09167 | Forwarded | For Review | 2020-07-07 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-14 | Submittal Number: 23 82 39-2.0 From: GRETCHEN TOSHACH Final Due Date: 07/24/20 Subject: ECUH CCD062 Description: REVISED ECUH PER CCD062 Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 07097 | Review Response | Approved as Noted | 2020-07-16 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Architect to comment on color. Nick Theimer ME Engineers 2020.07.16 | Info Exchange
| 09482 | Responded and Closed | Approved as Noted | 2020-07-22 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.07.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-07 |  | 23 82 39-2.0 ECUHs CCD063 - MAM[1].pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-07 |  | 23 82 39-2.0 ECUHs CCD063 - MAM[1].pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-07-07 |  | 23 82 39-2.0 ECUHs CCD063 - MAM[1].pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-22 |  | 23 82 39-2.0 ECUHs CCD063_ME_POP.pdf
23 82 39-003-00 | 23 82 39 - HEATING TERMINAL UNITS | 23 82 39-003-00 Electric Unit Heaters | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-06 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-10 08:00 | 2020-12-03 | 28 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09266 | Received | For Review | 2020-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-12-10 08:00 | Submittal Number: 23 82 39-3.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: ELECTRIC UNIT HEATERS Description: Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 12218 | Forwarded | For Review | 2020-11-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-13 | Submittal Number: 23 82 39-3.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: ELECTRIC UNIT HEATERS Description: Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 09654 | Review Response | Revise and Resubmit | 2020-11-11 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Submittal incomplete. | Info Exchange
| 12705 | Responded and Closed | Rejected | 2020-11-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Submittal incomplete. | Info Exchange
| 12980 | Reopened | Additional Information | 2020-12-03 14:52 | Josh Dobken (Populous) |  |  | Reopening submittal based on error in materials submitted. Email attached with submittal was received on 11/24. Due date for submittal revised to 12/10.
| 12981 | Forwarded | For Review | 2020-12-03 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-10 | Submittal Number: 23 82 39-3.0 From: GRETCHEN TOSHACH Final Due Date: 11/20/20 Subject: ELECTRIC UNIT HEATERS Description: Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 09898 | Review Response | Approved | 2020-12-03 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2020.12.03 | Info Exchange
| 12984 | Responded and Closed | Approved | 2020-12-03 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.12.03 | Info Exchange
| 13665 | Sent | For Information Only | 2021-01-05 | Josh Dobken (Populous) | Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2020.12.03 | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 23 82 39-3.0 EUH-4F-014F-024F-03 - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 23 82 39-3.0 EUH-4F-014F-024F-03 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-05 02:00 |  | 23 82 39-3.0 EUH-4F-014F-024F-03 - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-21 02:00 |  | 23 82 39-3.0 EUH-4F-014F-024F-03_ME_pop.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-11-05 02:00 |  | 23 82 39-3.0 EUH-4F-014F-024F-03 - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2020-11-05 |  | 23 82 39-3.0 EUH-4F-014F-024F-03 - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-03 |  | 23 82 39-3.0 EUH-4F-014F-024F-03_r_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-11-05 02:00 |  | 23 82 39-3.0 EUH-4F-014F-024F-03 - MAM.pdf
23 82 39-004-00 | 23 82 39 - HEATING TERMINAL UNITS | 23 82 39-004-00 CUH-1B.03 and CUH-1B.04 Product Data | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-04 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-18 | 2021-06-07 | 4 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13384 | Received | For Review | 2021-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2021-06-18 | Submittal Number: 23 82 39-4.0 From: SIMRAN GEORGE Final Due Date: 07/07/21 Subject: CUH-1B.03 AND CUH-1B.04 PRODUCT DATA Description: Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 17312 | Forwarded | For Review | 2021-06-03 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-10 | Submittal Number: 23 82 39-4.0 From: SIMRAN GEORGE Final Due Date: 07/07/21 Subject: CUH-1B.03 AND CUH-1B.04 PRODUCT DATA Description: Spec Section: 23 82 39 - HEATING TERMINAL UNITS Status: OPEN | Info Exchange
| 13445 | Review Response | Approved | 2021-06-03 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.06.03 | Info Exchange
| 17383 | Responded and Closed | Approved | 2021-06-07 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.06.03 | Info Exchange
| 18152 | Sent | For Information Only | 2021-07-21 | Josh Dobken (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Responded and Closed (Approved) to: Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) Remarks: Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.06.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-03 |  | 23 82 39-4.0 CUH-1B.03 and CUH-1B.04 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-03 |  | 23 82 39-4.0 CUH-1B.03 and CUH-1B.04 Product Data-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-06-02 02:00 |  | 23 82 39-4.0 CUH-1B.03 and CUH-1B.04 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-07 02:00 |  | 23 82 39-4.0 CUH-1B.03 and CUH-1B.04 Product Data_ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-06-02 02:00 |  | 23 82 39-4.0 CUH-1B.03 and CUH-1B.04 Product Data-MAM.pdf
23 84 13-001-00 | 23 84 13 - HUMIDIFIERS | 23 84 13-001-00 HUMIDIFIERS - Manufacturers Instructions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-20 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-09-04 | 2019-09-04 | 16 |  | Record Copies; Transfers; Submittals | 23 84 13-001-01 - 23 84 13-001-01 HUMIDIFIERS - Manufacturers Instructions | 16 |  | 2019-09-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02136 | Received | For Review | 2019-08-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-04 | Submittal Number: 23 84 13-1.0 From: PATRICK KLEIN Final Due Date: 09/02/19 Subject: HUMIDIFIERS - MANUFACTURERS INSTRUCTIONS Description: SUBMIT MANUFACTURERS DATA, INCLUDING : - 1. DRAWINGS SHOWING OVERALL DIMENSIONS OF COMPLETE ASSEMBLY. 2. OPERATING WEIGHTS. 3. EQUIPMENT SUPPORT REQUIREMENTS. 4. SIZES AND LOCATIONS OF CONNECTIONS. 5. ACCESSORIES. 6. AUXILIARY SUPPORT REQUIREMENTS. Spec Section: 23 84 13 - HUMIDIFIERS Status: OPEN | Info Exchange
| 03314 | Forwarded | For Review | 2019-08-20 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-27 | Submittal Number: 23 84 13-1.0 From: PATRICK KLEIN Final Due Date: 09/02/19 Subject: HUMIDIFIERS - MANUFACTURERS INSTRUCTIONS Description: SUBMIT MANUFACTURERS DATA, INCLUDING : - 1. DRAWINGS SHOWING OVERALL DIMENSIONS OF COMPLETE ASSEMBLY. 2. OPERATING WEIGHTS. 3. EQUIPMENT SUPPORT REQUIREMENTS. 4. SIZES AND LOCATIONS OF CONNECTIONS. 5. ACCESSORIES. 6. AUXILIARY SUPPORT REQUIREMENTS. Spec Section: 23 84 13 - HUMIDIFIERS Status: OPEN | Info Exchange
| 02296 | Review Response | Approved as Noted/Resubmit | 2019-09-04 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA; Shaina Burris (Populous) |  | See attached for review. Values listed as "0" need to be updated. Nick Theimer ME Engineers 2019.09.04 | Info Exchange
| 03521 | Responded and Closed | Approved as Noted/Resubmit | 2019-09-04 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Values listed as "0" need to be updated. Nick Theimer ME Engineers 2019.09.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-19 |  | 23 84 13-1.0 Humidifiers Manufacturer's Instructions - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-19 |  | 23 84 13-1.0 Humidifiers Manufacturer's Instructions - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-08-18 02:00 |  | 23 84 13-1.0 Humidifiers Manufacturer's Instructions - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-04 02:00 |  | 23 84 13-1.0 Humidifiers Manufacturer's Instructions - ME_POP.pdf
23 84 13-001-01 | 23 84 13 - HUMIDIFIERS | 23 84 13-001-01 HUMIDIFIERS - Manufacturers Instructions | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-24 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-08 | 2019-09-25 | 2 |  | Record Copies; Transfers; Submittals | 23 84 13-001-00 - 23 84 13-001-00 HUMIDIFIERS - Manufacturers Instructions | 1 | 2019-09-18 | 2019-09-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02518 | Received | For Review | 2019-09-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-10-08 | Submittal Number: 23 84 13-1.1 From: GRETCHEN TOSHACH Final Due Date: 10/09/19 Subject: HUMIDIFIERS - MANUFACTURERS INSTRUCTIONS Description: - MC TO UPDATE AND RESUBMIT VALUES LISTED AS "0" ON THE "ZONE LIST" PAGE. - PROVIDE 20A FUSES IN LIEU OF SCHEDULED 15A FUSES AT LOCAL DISCONNECT. Spec Section: 23 84 13 - HUMIDIFIERS Status: OPEN | Info Exchange
| 03797 | Forwarded | For Review | 2019-09-25 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-02 | Submittal Number: 23 84 13-1.1 From: GRETCHEN TOSHACH Final Due Date: 10/09/19 Subject: HUMIDIFIERS - MANUFACTURERS INSTRUCTIONS Description: - MC TO UPDATE AND RESUBMIT VALUES LISTED AS "0" ON THE "ZONE LIST" PAGE. - PROVIDE 20A FUSES IN LIEU OF SCHEDULED 15A FUSES AT LOCAL DISCONNECT. Spec Section: 23 84 13 - HUMIDIFIERS Status: OPEN | Info Exchange
| 02529 | Review Response | Approved as Noted | 2019-09-25 | Nick Theimer (ME Engineers) | Josh Dobken (Populous); Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2019.09.25 | Info Exchange
| 03811 | Responded and Closed | Approved as Noted | 2019-09-25 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2019.09.25 | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-24 02:00 |  | 23 84 13-1.1 Humidifiers Manufacturer's Instructions - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-24 02:00 |  | 23 84 13-1.1 Humidifiers Manufacturer's Instructions - MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2019-09-24 02:00 |  | 23 84 13-1.1 Humidifiers Manufacturer's Instructions - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-25 02:00 |  | 23 84 13-1.1 Humidifiers Manufacturer's Instructions - ME_POP.pdf
26 05 02-001-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-001-00 ELECTRICAL REQUIREMENTS - Event and Riser Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-25 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-09 | 2020-04-13 | 20 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05043 | Received | For Review | 2020-03-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-09 | Submittal Number: 26 05 02-1.0 From: PATRICK KLEIN Final Due Date: 04/08/20 Subject: ELECTRICAL REQUIREMENTS - EVENT AND RISER SHOP DRAWINGS Description: PREPARE COORDINATION DRAWINGS IN ACCORDANCE WITH DIVISION 1 SUBMITTALS TOA SCALE OF = 1-0 OR LARGER; DETAILING MAJOR ELEMENTS, COMPONENTS, AND SYSTEMS OF ELECTRICAL EQUIPMENT (I.E., ALL TRANSFORMER VAULTS, SWITCHGEAR ROOMS, GENERATOR ROOMS, ELECTRICAL ROOMS AND TECHNOLOGY ROOMS) AND MATERIALS IN RELATIONSHIP WITH OTHER SYSTEMS, INSTALLATIONS, AND BUILDING COMPONENTS. WHERE EQUIPMENT IS LOCATED OUTDOORS, PREPARE SHOP DRAWINGS INDICATING ELECTRICAL EQUIPMENT LOCATIONS AND EXTERIOR ELEMENTS IN THE EQUIPMENT AREAS. INDICATE LOCATIONS WHERE SPACE IS LIMITED FOR INSTALLATION AND ACCESS AND WHERE SEQUENCING AND COORDINATION OF INSTALLATIONS ARE IMPORTANT TO THE EFFICIENT FLOW OF THE WORK, INCLUDING (BUT NOT NECESSARILY LIMITED TO) THE FOLLOWING: 1. INDICATE THE PROPOSED LOCATIONS OF MAJOR RACEWAY SYSTEMS, AND MATERIALS. INCLUDE THE FOLLOWING: A. EXTERIOR WALL AND FOUNDATION PENETRATIONS. B. FIRE-RATED WALL AND FLOOR PENETRATIONS. C. SUPPORT DETAILS. D. SIZES AND LOCATION OF REQUIRED CONCRETE PADS AND BASES. 2. INDICATE SCHEDULING, SEQUENCING, MOVEMENT, AND POSITIONING OF LARGE EQUIPMENT INTO THE BUILDING DURING CONSTRUCTION. 3. PREPARE FLOOR PLANS, ELEVATIONS, AND DETAILS TO INDICATE PENETRATIONS IN FLOORS, WALLS, AND CEILINGS AND THEIR RELATIONSHIP TO OTHER PENETRATIONS AND INSTALLATION. 4. ELECTRICAL AND TRANSFORMER VAULT ROOMS INDICATING CONDUIT STUB-UP LOCATIONS. 5. MEDIUM-VOLTAGE, NORMAL AND EMERGENCY UNDERGROUND CONDUIT AND DUCT BANK ROUTING. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06865 | Forwarded | For Review | 2020-03-25 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-01 | Submittal Number: 26 05 02-1.0 From: PATRICK KLEIN Final Due Date: 04/08/20 Subject: ELECTRICAL REQUIREMENTS - EVENT AND RISER SHOP DRAWINGS Description: PREPARE COORDINATION DRAWINGS IN ACCORDANCE WITH DIVISION 1 SUBMITTALS TOA SCALE OF = 1-0 OR LARGER; DETAILING MAJOR ELEMENTS, COMPONENTS, AND SYSTEMS OF ELECTRICAL EQUIPMENT (I.E., ALL TRANSFORMER VAULTS, SWITCHGEAR ROOMS, GENERATOR ROOMS, ELECTRICAL ROOMS AND TECHNOLOGY ROOMS) AND MATERIALS IN RELATIONSHIP WITH OTHER SYSTEMS, INSTALLATIONS, AND BUILDING COMPONENTS. WHERE EQUIPMENT IS LOCATED OUTDOORS, PREPARE SHOP DRAWINGS INDICATING ELECTRICAL EQUIPMENT LOCATIONS AND EXTERIOR ELEMENTS IN THE EQUIPMENT AREAS. INDICATE LOCATIONS WHERE SPACE IS LIMITED FOR INSTALLATION AND ACCESS AND WHERE SEQUENCING AND COORDINATION OF INSTALLATIONS ARE IMPORTANT TO THE EFFICIENT FLOW OF THE WORK, INCLUDING (BUT NOT NECESSARILY LIMITED TO) THE FOLLOWING: 1. INDICATE THE PROPOSED LOCATIONS OF MAJOR RACEWAY SYSTEMS, AND MATERIALS. INCLUDE THE FOLLOWING: A. EXTERIOR WALL AND FOUNDATION PENETRATIONS. B. FIRE-RATED WALL AND FLOOR PENETRATIONS. C. SUPPORT DETAILS. D. SIZES AND LOCATION OF REQUIRED CONCRETE PADS AND BASES. 2. INDICATE SCHEDULING, SEQUENCING, MOVEMENT, AND POSITIONING OF LARGE EQUIPMENT INTO THE BUILDING DURING CONSTRUCTION. 3. PREPARE FLOOR PLANS, ELEVATIONS, AND DETAILS TO INDICATE PENETRATIONS IN FLOORS, WALLS, AND CEILINGS AND THEIR RELATIONSHIP TO OTHER PENETRATIONS AND INSTALLATION. 4. ELECTRICAL AND TRANSFORMER VAULT ROOMS INDICATING CONDUIT STUB-UP LOCATIONS. 5. MEDIUM-VOLTAGE, NORMAL AND EMERGENCY UNDERGROUND CONDUIT AND DUCT BANK ROUTING. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05313 | Review Response | Approved as Noted | 2020-04-11 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.11 | Info Exchange
| 07226 | Responded and Closed | Approved as Noted | 2020-04-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-25 |  | 26 05 02-1.0 Event and Riser Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-25 |  | 26 05 02-1.0 Event and Riser Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-24 02:00 |  | 26 05 02-1.0 Event and Riser Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-13 02:00 |  | 26 05 02-1.0 Event and Riser Shop Drawings-MAM - ME_POP.pdf
26 05 02-003-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-003-00 ELECTRICAL REQUIREMENTS - General | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-28 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-09-12 07:00 | 2019-09-12 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-09-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02222 | Received | For Review | 2019-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-09-12 07:00 | Submittal Number: 26 05 02-3.0 From: PATRICK KLEIN Final Due Date: 09/10/19 Subject: ELECTRICAL REQUIREMENTS - GENERAL Description: 1. AFTER RECEIPT OF NOTICE TO PROCEED, THE CONTRACTOR SHALL SUBMIT TO THE ARCHITECTA TYPED LIST- OF SUBMITTALS AND THE SCHEDULED DATE OF SUBMISSION. LIST SHALL INCLUDE SUBMITTAL NUMBER, SECTION NUMBER AND SCHEDULED DATE OF SUBMISSION. SUBMITTALS SHALL BE GROUPED AND SUBMITTED IN NO MORE THAN TEN COMPLETE PACKAGES. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 03433 | Forwarded | For Review | 2019-08-28 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-09-04 | Submittal Number: 26 05 02-3.0 From: PATRICK KLEIN Final Due Date: 09/10/19 Subject: ELECTRICAL REQUIREMENTS - GENERAL Description: 1. AFTER RECEIPT OF NOTICE TO PROCEED, THE CONTRACTOR SHALL SUBMIT TO THE ARCHITECTA TYPED LIST- OF SUBMITTALS AND THE SCHEDULED DATE OF SUBMISSION. LIST SHALL INCLUDE SUBMITTAL NUMBER, SECTION NUMBER AND SCHEDULED DATE OF SUBMISSION. SUBMITTALS SHALL BE GROUPED AND SUBMITTED IN NO MORE THAN TEN COMPLETE PACKAGES. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 02392 | Review Response | Approved | 2019-09-11 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2019.09.11 | Info Exchange
| 03640 | Responded and Closed | Approved as Noted | 2019-09-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2019.09.11 See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-27 |  | 07.17.19 Submittal dates.xlsx
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-27 |  | 26 05 02-3.0 Submission Schedule-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-27 |  | 07.17.19 Submittal dates.xlsx
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-27 |  | 26 05 02-3.0 Submission Schedule-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-08-26 02:00 |  | 07.17.19 Submittal dates.xlsx
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-08-26 02:00 |  | 26 05 02-3.0 Submission Schedule-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-12 02:00 |  | 26 05 02-3.0 Submission Schedule-MAM-ME_POP.pdf
26 05 02-004-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-004-00 ELECTRICAL REQUIREMENTS - Mech Mezz Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-26 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-09 | 2020-04-13 | 19 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-04-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05052 | Received | For Review | 2020-03-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-09 | Submittal Number: 26 05 02-4.0 From: PATRICK KLEIN Final Due Date: 04/08/20 Subject: ELECTRICAL REQUIREMENTS - MECH MEZZ SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06874 | Forwarded | For Review | 2020-03-25 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-01 | Submittal Number: 26 05 02-4.0 From: PATRICK KLEIN Final Due Date: 04/08/20 Subject: ELECTRICAL REQUIREMENTS - MECH MEZZ SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05312 | Review Response | Approved as Noted | 2020-04-10 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.10 | Info Exchange
| 07225 | Responded and Closed | Approved as Noted | 2020-04-13 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-25 |  | 26 05 02-4.0 Mech Mezz Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-25 |  | 26 05 02-4.0 Mech Mezz Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-24 02:00 |  | 26 05 02-4.0 Mech Mezz Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-13 02:00 |  | 26 05 02-4.0 Mech Mezz Shop Drawings-MAM - ME_POP.pdf
26 05 02-005-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-005-00 ELECTRICAL REQUIREMENTS - Enlarged Electrical Room and Housekeeping Pad Layout Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-26 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-09 | 2020-04-15 | 21 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05044 | Received | For Review | 2020-03-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-09 | Submittal Number: 26 05 02-5.0 From: PATRICK KLEIN Final Due Date: 04/08/20 Subject: ELECTRICAL REQUIREMENTS - ENLARGED ELECTRICAL ROOM AND HOUSEKEEPING PAD LAYOUT DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06866 | Forwarded | For Review | 2020-03-25 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-01 | Submittal Number: 26 05 02-5.0 From: PATRICK KLEIN Final Due Date: 04/08/20 Subject: ELECTRICAL REQUIREMENTS - ENLARGED ELECTRICAL ROOM AND HOUSEKEEPING PAD LAYOUT DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05343 | Review Response | Approved as Noted | 2020-04-13 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.13 | Info Exchange
| 07296 | Responded and Closed | Approved as Noted | 2020-04-15 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-25 |  | 26 05 02-5.0 Enlarged Electrical Room and Housekeeping Pad Layout Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-25 |  | 26 05 02-5.0 Enlarged Electrical Room and Housekeeping Pad Layout Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-24 02:00 |  | 26 05 02-5.0 Enlarged Electrical Room and Housekeeping Pad Layout Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-04-15 |  | 26 05 02-5.0 Enlarged Electrical Room and Housekeeping Pad Layout Drawings-MAM-ME_POP.pdf
26 05 02-006-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-006-00 ELECTRICAL REQUIREMENTS - Suite Level Area C and D Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-09 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-24 07:00 | 2020-04-24 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-04-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05273 | Received | For Review | 2020-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-24 07:00 | Submittal Number: 26 05 02-6.0 From: PATRICK KLEIN Final Due Date: 04/23/20 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL AREA C AND D SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07166 | Forwarded | For Review | 2020-04-09 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-16 | Submittal Number: 26 05 02-6.0 From: PATRICK KLEIN Final Due Date: 04/23/20 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL AREA C AND D SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05543 | Review Response | Approved as Noted | 2020-04-24 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.24 | Info Exchange
| 07516 | Responded and Closed | Approved as Noted | 2020-04-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-09 |  | 26 05 02-6.0 Suite Level Area C and D Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-09 |  | 26 05 02-6.0 Suite Level Area C and D Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-08 02:00 |  | 26 05 02-6.0 Suite Level Area C and D Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-24 02:00 |  | 26 05 02-6.0 Suite Level Area C and D Shop Drawings-MAM-ME_POP.pdf
26 05 02-007-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-007-00 ELECTRICAL REQUIREMENTS - Car Charging Stations | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-20 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-04 | 2020-05-04 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05427 | Received | For Review | 2020-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-05-04 | Submittal Number: 26 05 02-7.0 From: PATRICK KLEIN Final Due Date: 05/04/20 Subject: ELECTRICAL REQUIREMENTS - CAR CHARGING STATIONS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07365 | Forwarded | For Review | 2020-04-20 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-27 | Submittal Number: 26 05 02-7.0 From: PATRICK KLEIN Final Due Date: 05/04/20 Subject: ELECTRICAL REQUIREMENTS - CAR CHARGING STATIONS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05706 | Review Response | Approved as Noted | 2020-05-01 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.01 | Info Exchange
| 07736 | Responded and Closed | Approved as Noted | 2020-05-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-20 |  | 26 05 02-7.0 Car Charging Stations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-20 |  | 26 05 02-7.0 Car Charging Stations-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-19 02:00 |  | 26 05 02-7.0 Car Charging Stations-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-04 02:00 |  | 26 05 02-7.0 Car Charging Stations-MAM-ME_POP.pdf
26 05 02-008-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-008-00 ELECTRICAL REQUIREMENTS - Event Level Point Load Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-22 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-06 | 2020-05-06 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05493 | Received | For Review | 2020-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-05-06 | Submittal Number: 26 05 02-8.0 From: PATRICK KLEIN Final Due Date: 05/05/20 Subject: ELECTRICAL REQUIREMENTS - EVENT LEVEL POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07447 | Forwarded | For Review | 2020-04-22 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-29 | Submittal Number: 26 05 02-8.0 From: PATRICK KLEIN Final Due Date: 05/05/20 Subject: ELECTRICAL REQUIREMENTS - EVENT LEVEL POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07451 | Forwarded | For Review | 2020-04-22 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean Mc... | 2020-04-29 | Submittal Number: 26 05 02-8.0 From: PATRICK KLEIN Final Due Date: 05/05/20 Subject: ELECTRICAL REQUIREMENTS - EVENT LEVEL POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05762 | Review Response | Approved as Noted | 2020-05-05 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Hangers to attach to steel framing. Any hangers hanging from metal deck must meet criteria per general note DK-3. Any hangers attaching to precast stadia must be coordinated with precast manufacturer/designer. Hangers in plenum space must be coordinate with Arch and CFMF Engineer. Contractor to coordinate total loads imposed from all trades to meet maximum MEP SDL allowances per drawings. | Info Exchange
| 07813 | Responded and Closed | Approved as Noted | 2020-05-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| 08451 | Sent | For Information Only | 2020-06-08 | Josh Dobken (Populous) | Patrick Klein (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Hangers to attach to steel framing. Any hangers hanging from metal deck must meet criteria per general note DK-3. Any hangers attaching to precast stadia must be coordinated with precast manufacturer/designer. Hangers in plenum space must be coordinate with Arch and CFMF Engineer. Contractor to coordinate total loads imposed from all trades to meet maximum MEP SDL allowances per drawings. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-21 |  | 26 05 02-8.0 Event Level Point Load Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-21 |  | 26 05 02-8.0 Event Level Point Load Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-04-20 02:00 |  | 26 05 02-8.0 Event Level Point Load Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-04-20 02:00 |  | 26 05 02-8.0 Event Level Point Load Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-06 |  | 26 05 02-8.0 Event Level Point Load Drawings-MAM_TT_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-04-20 02:00 |  | 26 05 02-8.0 Event Level Point Load Drawings-MAM.pdf
26 05 02-009-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-009-00 ELECTRICAL REQUIREMENTS - Main Concourse Area C and D Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-23 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-07 | 2020-05-06 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05514 | Received | For Review | 2020-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-05-07 | Submittal Number: 26 05 02-9.0 From: PATRICK KLEIN Final Due Date: 05/06/20 Subject: ELECTRICAL REQUIREMENTS - MAIN CONCOURSE AREA C AND D SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07473 | Forwarded | For Review | 2020-04-23 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-30 | Submittal Number: 26 05 02-9.0 From: PATRICK KLEIN Final Due Date: 05/06/20 Subject: ELECTRICAL REQUIREMENTS - MAIN CONCOURSE AREA C AND D SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05763 | Review Response | Approved as Noted | 2020-05-05 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Please confirm exposed MC cable basket tray locations shown in main concourse are acceptable to Populous. Mark Lievens ME Engineers 2020.05.05 | Info Exchange
| 07812 | Responded and Closed | Approved as Noted | 2020-05-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 |  | 26 05 02-9.0 Main Concourse Area C and D Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-22 |  | 26 05 02-9.0 Main Concourse Area C and D Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-21 02:00 |  | 26 05 02-9.0 Main Concourse Area C and D Shop Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-06 |  | 26 05 02-9.0 Main Concourse Area C and D Shop Drawings-MAM-ME_POP.pdf
26 05 02-010-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-010-00 ELECTRICAL REQUIREMENTS - Area A, B, E and F Suite Level Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-27 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-11 | 2020-05-19 | 23 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05563 | Received | For Review | 2020-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-05-11 | Submittal Number: 26 05 02-10.0 From: PATRICK KLEIN Final Due Date: 05/08/20 Subject: ELECTRICAL REQUIREMENTS - AREA A, B, E AND F SUITE LEVEL SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07541 | Forwarded | For Review | 2020-04-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-04 | Submittal Number: 26 05 02-10.0 From: PATRICK KLEIN Final Due Date: 05/08/20 Subject: ELECTRICAL REQUIREMENTS - AREA A, B, E AND F SUITE LEVEL SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06129 | Review Response | Approved as Noted | 2020-05-15 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.15 | Info Exchange
| 08054 | Responded and Closed | Approved as Noted | 2020-05-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Pending response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | 26 05 02-10.0 Area A B E and F Suite Level Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-24 |  | 26 05 02-10.0 Area A B E and F Suite Level Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-23 02:00 |  | 26 05 02-10.0 Area A B E and F Suite Level Shops-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-05-19 |  | 26 05 02-10.0 Area A B E and F Suite Level Shops-MAM-ME_POP.pdf
26 05 02-011-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-011-00 ELECTRICAL REQUIREMENTS - Existing Catwalk Shops | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-28 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-12 | 2020-05-12 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05595 | Received | For Review | 2020-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-05-12 | Submittal Number: 26 05 02-11.0 From: PATRICK KLEIN Final Due Date: 05/11/20 Subject: ELECTRICAL REQUIREMENTS - EXISTING CATWALK SHOPS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07581 | Forwarded | For Review | 2020-04-28 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-05 | Submittal Number: 26 05 02-11.0 From: PATRICK KLEIN Final Due Date: 05/11/20 Subject: ELECTRICAL REQUIREMENTS - EXISTING CATWALK SHOPS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 05840 | Review Response | Approved as Noted | 2020-05-12 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.12 | Info Exchange
| 07923 | Responded and Closed | Approved as Noted | 2020-05-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.12 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-27 |  | 26 05 02-11.0 Existing Catwalk Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-27 |  | 26 05 02-11.0 Existing Catwalk Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-26 02:00 |  | 26 05 02-11.0 Existing Catwalk Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-12 02:00 |  | 26 05 02-11.0 Existing Catwalk Shop Drawings-MAM-ME_POP.pdf
26 05 02-012-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-012-00 ELECTRICAL REQUIREMENTS - Main Concourse Areas A, B, E, and F Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-19 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-03 07:00 | 2020-06-04 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05909 | Received | For Review | 2020-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-03 07:00 | Submittal Number: 26 05 02-12.0 From: PATRICK KLEIN Final Due Date: 06/02/20 Subject: ELECTRICAL REQUIREMENTS - MAIN CONCOURSE AREAS A, B, E, AND F SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 08014 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-25 | Submittal Number: 26 05 02-12.0 From: PATRICK KLEIN Final Due Date: 06/02/20 Subject: ELECTRICAL REQUIREMENTS - MAIN CONCOURSE AREAS A, B, E, AND F SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06204 | Review Response | Approved as Noted | 2020-06-02 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.06.02 | Info Exchange
| 08384 | Responded and Closed | Approved as Noted | 2020-06-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.06.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 26 05 02-12.0 Areas A B E and F Main Concourse Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 26 05 02-12.0 Areas A B E and F Main Concourse Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-17 02:00 |  | 26 05 02-12.0 Areas A B E and F Main Concourse Shops-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-04 02:00 |  | 26 05 02-12.0 Areas A B E and F Main Concourse Shops-MAM-ME_POP.pdf
26 05 02-013-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-013-00 ELECTRICAL REQUIREMENTS - Mech Mezz Point Load Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-19 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-03 07:00 | 2020-06-04 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05910 | Received | For Review | 2020-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-03 07:00 | Submittal Number: 26 05 02-13.0 From: PATRICK KLEIN Final Due Date: 06/02/20 Subject: ELECTRICAL REQUIREMENTS - MECH MEZZ POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 08017 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-25 | Submittal Number: 26 05 02-13.0 From: PATRICK KLEIN Final Due Date: 06/02/20 Subject: ELECTRICAL REQUIREMENTS - MECH MEZZ POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 08018 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-25 | Submittal Number: 26 05 02-13.0 From: PATRICK KLEIN Final Due Date: 06/02/20 Subject: ELECTRICAL REQUIREMENTS - MECH MEZZ POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06216 | Review Response | Approved as Noted/Resubmit | 2020-06-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | A few of the runs did not have loads shown. Please resubmit with loads shown for all runs. | Info Exchange
| 08394 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: A few of the runs did not have loads shown. Please resubmit with loads shown for all runs. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 26 05 02-13.0 Mech Mezz Point Load Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 26 05 02-13.0 Mech Mezz Point Load Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 26 05 02-13.0 Mech Mezz Point Load Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-05-17 02:00 |  | 26 05 02-13.0 Mech Mezz Point Load Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-04 02:00 |  | 26 05 02-13.0 Mech Mezz Point Load Drawings-MAM_TT REVIEW_POP.pdf
26 05 02-013-01 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-013-01 ELECTRICAL REQUIREMENTS - Mech Mezz Point Load Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-21 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-04 | 2020-07-28 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07078 | Received | For Review | 2020-07-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-08-04 | Submittal Number: 26 05 02-13.1 From: PATRICK KLEIN Final Due Date: 08/04/20 Subject: ELECTRICAL REQUIREMENTS - MECH MEZZ POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09468 | Forwarded | For Review | 2020-07-21 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-28 | Submittal Number: 26 05 02-13.1 From: PATRICK KLEIN Final Due Date: 08/04/20 Subject: ELECTRICAL REQUIREMENTS - MECH MEZZ POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09469 | Forwarded | For Review | 2020-07-21 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-28 | Submittal Number: 26 05 02-13.1 From: PATRICK KLEIN Final Due Date: 08/04/20 Subject: ELECTRICAL REQUIREMENTS - MECH MEZZ POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07220 | Review Response | Approved | 2020-07-27 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Contractor to coordinate loads imposed from all trades to ensure total allowable loads imposed are not exceeded per structural drawings (General Note CD-10). | Info Exchange
| 09633 | Responded and Closed | Approved | 2020-07-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Contractor to coordinate loads imposed from all trades to ensure total allowable loads imposed are not exceeded per structural drawings (General Note CD-10). | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-21 |  | 26 05 02-13.1 Mech Mezz Point Load Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-21 |  | 26 05 02-13.1 Mech Mezz Point Load Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-21 |  | 26 05 02-13.1 Mech Mezz Point Load Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-20 02:00 |  | 26 05 02-13.1 Mech Mezz Point Load Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-28 02:00 |  | 26 05 02-13.1 Mech Mezz Point Load Drawings-MAM_TT REVIEW_pop.pdf
26 05 02-014-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-014-00 ELECTRICAL REQUIREMENTS - South Parcel Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-10 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-24 | 2020-06-26 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-06-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06325 | Received | For Review | 2020-06-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-24 | Submittal Number: 26 05 02-14.0 From: PATRICK KLEIN Final Due Date: 06/24/20 Subject: ELECTRICAL REQUIREMENTS - SOUTH PARCEL SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 08530 | Forwarded | For Review | 2020-06-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-17 | Submittal Number: 26 05 02-14.0 From: PATRICK KLEIN Final Due Date: 06/24/20 Subject: ELECTRICAL REQUIREMENTS - SOUTH PARCEL SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 06706 | Review Response | Approved as Noted | 2020-06-25 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached review. Populous - please review the access ladder shift request within the NW corner of the generator pit shown on page 3. Thank you, Mark Lievens ME Engineers 2020.06.25 | Info Exchange
| 08923 | Responded and Closed | Approved as Noted | 2020-06-26 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached review. Thank you, Mark Lievens ME Engineers 2020.06.25 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-10 |  | 26 05 02-14.0 South Parcel Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-10 |  | 26 05 02-14.0 South Parcel Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-06-09 02:00 |  | 26 05 02-14.0 South Parcel Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-26 |  | 26 05 02-14.0 South Parcel Drawings-MAM-ME_POP.pdf
26 05 02-015-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-015-00 ELECTRICAL REQUIREMENTS - Main Concourse Areas D, C, A, and E Point Load Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-13 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-27 | 2020-07-20 | 8 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06928 | Received | For Review | 2020-07-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-27 | Submittal Number: 26 05 02-15.0 From: PATRICK KLEIN Final Due Date: 07/27/20 Subject: ELECTRICAL REQUIREMENTS - MAIN CONCOURSE AREAS D, C, A, AND E POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09276 | Forwarded | For Review | 2020-07-13 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-20 | Submittal Number: 26 05 02-15.0 From: PATRICK KLEIN Final Due Date: 07/27/20 Subject: ELECTRICAL REQUIREMENTS - MAIN CONCOURSE AREAS D, C, A, AND E POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09315 | Forwarded | For Review | 2020-07-14 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-07-21 | Submittal Number: 26 05 02-15.0 From: PATRICK KLEIN Final Due Date: 07/27/20 Subject: ELECTRICAL REQUIREMENTS - MAIN CONCOURSE AREAS D, C, A, AND E POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07035 | Review Response | Approved | 2020-07-15 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 09421 | Responded and Closed | Approved | 2020-07-20 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 26 05 02-15.0 Main Concourse Areas D C A and E Point Load Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 26 05 02-15.0 Main Concourse Areas D C A and E Point Load Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 26 05 02-15.0 Main Concourse Areas D C A and E Point Load Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-13 |  | 26 05 02-15.0 Main Concourse Areas D C A and E Point Load Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-20 |  | 26 05 02-15.0 Main Concourse Areas D C A and E Point Load Drawings-MAM_TT_POP.pdf
26 05 02-016-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-016-00 ELECTRICAL REQUIREMENTS - Upper Concourse Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-30 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-13 | 2020-08-24 | 26 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07258 | Received | For Review | 2020-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-08-13 | Submittal Number: 26 05 02-16.0 From: PATRICK KLEIN Final Due Date: 08/12/20 Subject: ELECTRICAL REQUIREMENTS - UPPER CONCOURSE SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09670 | Forwarded | For Review | 2020-07-30 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-06 | Submittal Number: 26 05 02-16.0 From: PATRICK KLEIN Final Due Date: 08/12/20 Subject: ELECTRICAL REQUIREMENTS - UPPER CONCOURSE SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07696 | Review Response | Approved as Noted | 2020-08-17 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Most of the items noted in these shop drawings requiring specific Populous review I have already discussed with Bryan, Kuebler, or Kelsea but please take a quick pass through these drawings to confirm there are no lights or runs of conduit in sensitive or incorrect areas. Thank you, Mark Lievens ME Engineers 2020.08.17 | Info Exchange
| 07702 | Review Response | Approved as Noted | 2020-08-17 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please use this updated submittal review. I noticed an error in a comment that was copied around that I have now corrected. Thank you, Mark Lievens ME Engineers 2020.08.17 | Info Exchange
| 10252 | Responded and Closed | Approved as Noted | 2020-08-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Most of the items noted in these shop drawings requiring specific Populous review I have already discussed with Bryan, Kuebler, or Kelsea but please take a quick pass through these drawings to confirm there are no lights or runs of conduit in sensitive or incorrect areas. Thank you, Mark Lievens ME Engineers 2020.08.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-29 |  | 26 05 02-16.0 Upper Concourse Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-29 |  | 26 05 02-16.0 Upper Concourse Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-28 02:00 |  | 26 05 02-16.0 Upper Concourse Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-28 02:00 |  | 26 05 02-16.0 Upper Concourse Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-24 02:00 |  | 26 05 02-16.0 Upper Concourse Shop Drawings-MAM-ME-POP.pdf
26 05 02-017-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-017-00 ELECTRICAL REQUIREMENTS - Suite Level Area C and D Point Load Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-30 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-13 | 2020-08-11 | 13 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-08-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07266 | Received | For Review | 2020-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-08-13 | Submittal Number: 26 05 02-17.0 From: PATRICK KLEIN Final Due Date: 08/13/20 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL AREA C AND D POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09681 | Forwarded | For Review | 2020-07-30 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-06 | Submittal Number: 26 05 02-17.0 From: PATRICK KLEIN Final Due Date: 08/13/20 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL AREA C AND D POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09683 | Forwarded | For Review | 2020-07-30 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-06 | Submittal Number: 26 05 02-17.0 From: PATRICK KLEIN Final Due Date: 08/13/20 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL AREA C AND D POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07509 | Review Response | Approved | 2020-08-04 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions. TT has reviewed the loads imposed assuming they are unfactored Dead Loads hanging from Upper Concourse slab and steel. Per general note CD-01, contractor to coordinate loads from all trades to ensure maximum allowable loading as noted on drawings is not exceeded. | Info Exchange
| 09998 | Responded and Closed | Approved | 2020-08-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. TT has reviewed the loads imposed assuming they are unfactored Dead Loads hanging from Upper Concourse slab and steel. Per general note CD-01, contractor to coordinate loads from all trades to ensure maximum allowable loading as noted on drawings is not exceeded. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-30 |  | 26 05 02-17.0 Suite Level Area C and D Point Load Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-30 |  | 26 05 02-17.0 Suite Level Area C and D Point Load Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-30 |  | 26 05 02-17.0 Suite Level Area C and D Point Load Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-07-29 02:00 |  | 26 05 02-17.0 Suite Level Area C and D Point Load Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-11 02:00 |  | 26 05 02-17.0 Suite Level Area C and D Point Load Drawings-MAM_TT REVIEW_pop.pdf
26 05 02-018-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-018-00 ELECTRICAL REQUIREMENTS - Locker Room Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-04 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-18 | 2020-08-24 | 21 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07343 | Received | For Review | 2020-08-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-08-18 | Submittal Number: 26 05 02-18.0 From: PATRICK KLEIN Final Due Date: 08/18/20 Subject: ELECTRICAL REQUIREMENTS - LOCKER ROOM SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09791 | Forwarded | For Review | 2020-08-04 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-11 | Submittal Number: 26 05 02-18.0 From: PATRICK KLEIN Final Due Date: 08/18/20 Subject: ELECTRICAL REQUIREMENTS - LOCKER ROOM SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07697 | Review Response | Approved as Noted | 2020-08-19 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.08.19 | Info Exchange
| 10246 | Responded and Closed | Approved as Noted | 2020-08-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.08.19 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-04 |  | 26 05 02-18.0 Locker Room Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-04 |  | 26 05 02-18.0 Locker Room Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-03 02:00 |  | 26 05 02-18.0 Locker Room Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-24 02:00 |  | 26 05 02-18.0 Locker Room Shop Drawings-MAM-ME_pop.pdf
26 05 02-019-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-019-00 ELECTRICAL REQUIREMENTS - Upper Concourse Point Load Drawings | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-06 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-08-20 | 2020-08-11 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-08-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07417 | Received | For Review | 2020-08-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-20 | Submittal Number: 26 05 02-19.0 From: PATRICK KLEIN Final Due Date: 08/20/20 Subject: ELECTRICAL REQUIREMENTS - UPPER CONCOURSE POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09884 | Forwarded | For Review | 2020-08-06 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-13 | Submittal Number: 26 05 02-19.0 From: PATRICK KLEIN Final Due Date: 08/20/20 Subject: ELECTRICAL REQUIREMENTS - UPPER CONCOURSE POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09887 | Forwarded | For Review | 2020-08-06 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-13 | Submittal Number: 26 05 02-19.0 From: PATRICK KLEIN Final Due Date: 08/20/20 Subject: ELECTRICAL REQUIREMENTS - UPPER CONCOURSE POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07512 | Review Response | Approved | 2020-08-07 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions to loads imposed. Contractor to coordinate loads for all trades to confirm allowable superimposed loads shown on contract drawings are not exceeded. | Info Exchange
| 10001 | Responded and Closed | Approved | 2020-08-11 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions to loads imposed. Contractor to coordinate loads for all trades to confirm allowable superimposed loads shown on contract drawings are not exceeded. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | 26 05 02-19.0 Upper Concourse Point Load Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-06 |  | 26 05 02-19.0 Upper Concourse Point Load Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-06 |  | 26 05 02-19.0 Upper Concourse Point Load Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-05 02:00 |  | 26 05 02-19.0 Upper Concourse Point Load Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-11 02:00 |  | 26 05 02-19.0 Upper Concourse Point Load Drawings-MAM_TT REVIEW_pop.pdf
26 05 02-020-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-020-00 ELECTRICAL REQUIREMENTS - Suite Level Areas A, E and F Point Load Drawings | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-25 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2020-09-09 07:00 | 2020-09-01 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07720 | Received | For Review | 2020-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-09 07:00 | Submittal Number: 26 05 02-20.0 From: PATRICK KLEIN Final Due Date: 09/07/20 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL AREAS A, E AND F POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10273 | Forwarded | For Review | 2020-08-24 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-31 | Submittal Number: 26 05 02-20.0 From: PATRICK KLEIN Final Due Date: 09/07/20 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL AREAS A, E AND F POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10275 | Forwarded | For Review | 2020-08-24 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2020-08-31 | Submittal Number: 26 05 02-20.0 From: PATRICK KLEIN Final Due Date: 09/07/20 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL AREAS A, E AND F POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07886 | Review Response | Approved as Noted | 2020-09-01 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Per General Note CD-10, GC to coordinate loads imposed between all trades and distribute loads such that the maximum superimposed dead loads for MEP are not exceeded per the contract documents. | Info Exchange
| 10488 | Responded and Closed | Approved as Noted | 2020-09-01 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Per General Note CD-10, GC to coordinate loads imposed between all trades and distribute loads such that the maximum superimposed dead loads for MEP are not exceeded per the contract documents. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 26 05 02-20.0 Suite Level Areas A E and F Point Load Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-24 |  | 26 05 02-20.0 Suite Level Areas A E and F Point Load Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-23 02:00 |  | 26 05 02-20.0 Suite Level Areas A E and F Point Load Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-23 |  | 26 05 02-20.0 Suite Level Areas A E and F Point Load Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-01 |  | 26 05 02-20.0 Suite Level Areas A E and F Point Load Drawings-MAM_TT_POP.pdf
26 05 02-021-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-021-00 ELECTRICAL REQUIREMENTS - Suite Level Area B Point Load Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-28 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-14 07:00 | 2020-09-01 | 5 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07801 | Received | For Review | 2020-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-09-14 07:00 | Submittal Number: 26 05 02-21.0 From: PATRICK KLEIN Final Due Date: 09/11/20 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL AREA B POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10379 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-03 | Submittal Number: 26 05 02-21.0 From: PATRICK KLEIN Final Due Date: 09/11/20 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL AREA B POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10461 | Forwarded | For Review | 2020-09-01 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-09-08 | Submittal Number: 26 05 02-21.0 From: PATRICK KLEIN Final Due Date: 09/11/20 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL AREA B POINT LOAD DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 07887 | Review Response | Approved | 2020-09-01 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Per General Note CD-10, GC to coordinate loads imposed between all trades and distribute loads such that the maximum superimposed dead loads for MEP are not exceeded per the contract documents. | Info Exchange
| 10489 | Responded and Closed | Approved | 2020-09-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: Per General Note CD-10, GC to coordinate loads imposed between all trades and distribute loads such that the maximum superimposed dead loads for MEP are not exceeded per the contract documents. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 26 05 02-21.0 Suite Level Area B Point Load Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-27 |  | 26 05 02-21.0 Suite Level Area B Point Load Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-27 |  | 26 05 02-21.0 Suite Level Area B Point Load Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-27 |  | 26 05 02-21.0 Suite Level Area B Point Load Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-01 |  | 26 05 02-21.0 Suite Level Area B Point Load Drawings-MAM_TT_POP.pdf
26 05 02-022-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-022-00 East Main Concourse Club Shop Drawings | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-09 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-09-23 | 2020-09-21 | 13 |  | Record Copies; Transfers; Submittals | 26 05 02-022-00-01 - 26 05 02-022-00 East Main Concourse Club Shop Drawings | 10 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08002 | Received | For Review | 2020-09-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-23 | Submittal Number: 26 05 02-22.0 From: PATRICK KLEIN Final Due Date: 09/22/20 Subject: EAST MAIN CONCOURSE CLUB SHOP DRAWINGS Description: THE PDF CONTAIN ALL OF OUR SHOP DRAWINGS STAPLED TOGETHER. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10634 | Forwarded | For Review | 2020-09-09 | Populous SCA_CCA | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornt... | 2020-09-16 | Submittal Number: 26 05 02-22.0 From: PATRICK KLEIN Final Due Date: 09/22/20 Subject: EAST MAIN CONCOURSE CLUB SHOP DRAWINGS Description: THE PDF CONTAIN ALL OF OUR SHOP DRAWINGS STAPLED TOGETHER. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 08244 | Review Response | Approved as Noted | 2020-09-16 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.09.16 | Info Exchange
| 08246 | Review Response | Approved as Noted | 2020-09-18 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has reviewed this submittal for layout only. Loads imposed to be submitted to EOR for review in separate submittal. | Info Exchange
| 10951 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-21 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.09.16 Pending response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: TT has reviewed this submittal for layout only. Loads imposed to be submitted to EOR for review in separate submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-08 |  | 26 05 02-22.0 East Main Concourse Club Shop Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-08 |  | 26 05 02-22.0 East Main Concourse Club Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-08 |  | 26 05 02-22.0 East Main Concourse Club Shop Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-07 02:00 |  | 26 05 02-22.0 East Main Concourse Club Shop Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-21 |  | 26 05 02-22.0 East Main Concourse Club Shop Drawings-ME_TT_POP.pdf
26 05 02-022-00-01 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-022-00 East Main Concourse Club Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 05 02-022-00 - 26 05 02-022-00 East Main Concourse Club Shop Drawings | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 26 05 02-22.0 East Main Concourse Club Shop Drawings-ME_TT_POP.pdf
26 05 02-023-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-023-00 ELECTRICAL REQUIREMENTS - Chairman's Club Underground | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-08 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-22 | 2020-09-21 | 14 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07952 | Received | For Review | 2020-09-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-22 | Submittal Number: 26 05 02-23.0 From: PATRICK KLEIN Final Due Date: 09/22/20 Subject: ELECTRICAL REQUIREMENTS - CHAIRMAN'S CLUB UNDERGROUND Description: BRANCH DRAWING Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10576 | Forwarded | For Review | 2020-09-08 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-15 | Submittal Number: 26 05 02-23.0 From: PATRICK KLEIN Final Due Date: 09/22/20 Subject: ELECTRICAL REQUIREMENTS - CHAIRMAN'S CLUB UNDERGROUND Description: BRANCH DRAWING Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 08243 | Review Response | Approved as Noted | 2020-09-14 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.09.14 | Info Exchange
| 10948 | Responded and Closed | Approved as Noted | 2020-09-21 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.09.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-08 |  | 26 05 02-23.0 Chairmans Club Underground-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-08 |  | 26 05 02-23.0 Chairmans Club Underground-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-08 |  | 26 05 02-23.0 Chairmans Club Underground-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-21 |  | 26 05 02-23.0 Chairmans Club Underground-MAM-ME_POP.pdf
26 05 02-024-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-024-00 ELECTRICAL REQUIREMENTS - Catwalk Shop Drawings | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-22 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-06 | 2020-10-06 | 15 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08241 | Received | For Review | 2020-09-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-06 | Submittal Number: 26 05 02-24.0 From: PATRICK KLEIN Final Due Date: 10/05/20 Subject: ELECTRICAL REQUIREMENTS - CATWALK SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10946 | Forwarded | For Review | 2020-09-21 | Populous SCA_CCA | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornt... | 2020-09-28 | Submittal Number: 26 05 02-24.0 From: PATRICK KLEIN Final Due Date: 10/05/20 Subject: ELECTRICAL REQUIREMENTS - CATWALK SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 08617 | Review Response | Revise and Resubmit | 2020-10-06 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Contractor to provide loads imposed at all supports shown in submittal for EOR to review and approve. | Info Exchange
| 08626 | Review Response | Approved as Noted | 2020-10-06 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.06 | Info Exchange
| 11387 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-06 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Contractor to provide loads imposed at all supports shown in submittal for EOR to review and approve. Pending response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 26 05 02-24.0 Catwalk Shop Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-21 |  | 26 05 02-24.0 Catwalk Shop Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-09-21 |  | 26 05 02-24.0 Catwalk Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-20 02:00 |  | 26 05 02-24.0 Catwalk Shop Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-06 |  | 26 05 02-24.0 Catwalk Shop Drawings-MAM-ME_TT_POP.pdf
26 05 02-024-01 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-024-01 ELECTRICAL REQUIREMENTS - Catwalk Point Load Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-25 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-08 | 2021-02-11 | 18 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10925 | Received | For Review | 2021-01-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-08 | Submittal Number: 26 05 02-24.1 From: PATRICK KLEIN Final Due Date: 02/05/21 Subject: ELECTRICAL REQUIREMENTS - CATWALK POINT LOAD SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 14185 | Forwarded | For Review | 2021-01-25 | Populous SCA_CCA | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornt... | 2021-02-01 | Submittal Number: 26 05 02-24.1 From: PATRICK KLEIN Final Due Date: 02/05/21 Subject: ELECTRICAL REQUIREMENTS - CATWALK POINT LOAD SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11014 | Review Response | Not Required For Review | 2021-01-25 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please forward to TT for review. ME does not need to review this submittal. Mark Lievens ME Engineers 2021.01.25 | Info Exchange
| 11373 | Review Response | Approved as Noted/Resubmit | 2021-02-08 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See comments in attached submittal | Info Exchange
| 14729 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-11 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Not Required For Review) from: Mark Lievens (ME Engineers) Remarks: ME does not need to review this submittal. Mark Lievens ME Engineers Response (Approved as Noted/Resubmit) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments in attached submittal | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-23 |  | 26 05 02-24.1 Catwalk Point Load Shop Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-23 |  | 26 05 02-24.1 Catwalk Point Load Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-01-22 02:00 |  | 26 05 02-24.1 Catwalk Point Load Shop Drawings-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-01-23 |  | 26 05 02-24.1 Catwalk Point Load Shop Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-11 |  | 26 05 02-24.1 Catwalk Point Load Shop Drawings-TT_POP.pdf
26 05 02-024-02 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-024-02 Catwalk Point Load Shop Drawings | Closed | Structural, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-07 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-21 | 2021-04-12 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-04-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12454 | Received | For Review | 2021-04-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2021-04-21 | Submittal Number: 26 05 02-24.2 From: PATRICK KLEIN Final Due Date: 04/14/21 Subject: ELECTRICAL REQUIREMENTS - CATWALK POINT LOAD SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Email
| 16135 | Forwarded | For Review | 2021-04-07 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-04-14 | Submittal Number: 26 05 02-24.2 From: PATRICK KLEIN Final Due Date: 04/14/21 Subject: ELECTRICAL REQUIREMENTS - CATWALK POINT LOAD SHOP DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 12551 | Review Response | Approved as Noted | 2021-04-12 | Raymond Chou (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 16258 | Responded and Closed | Approved as Noted | 2021-04-12 | Shaina Burris (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Raymond Chou (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-07 |  | 26 05 02-24.2 Catwalk Point Load Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-07 |  | 26 05 02-24.2 Catwalk Point Load Shop Drawings-MAM.pdf
| Review Response |  | Raymond Chou (Thornton Tomasetti) | 1 | 2021-04-12 02:00 |  | 26 05 02-24.2 Catwalk Point Load Shop Drawings-MAM_TT REVIEWED.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-04-12 02:00 |  | 26 05 02-24.2 Catwalk Point Load Shop Drawings-MAM_TT REVIEWED_POP.pdf
26 05 02-025-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-025-00 400 Metro Floor Slab Penetrations | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-19 | 2020-10-20 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-10-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08564 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 26 05 02-25.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: 400 METRO FLOOR SLAB PENETRATIONS Description: PLEASE REVIEW THE FLOOR LIGHT PENETRATIONS SHOP DRAWINGS. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11325 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton... | 2020-10-12 | Submittal Number: 26 05 02-25.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: 400 METRO FLOOR SLAB PENETRATIONS Description: PLEASE REVIEW THE FLOOR LIGHT PENETRATIONS SHOP DRAWINGS. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 08631 | Review Response | Approved | 2020-10-05 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 08913 | Review Response | Approved | 2020-10-16 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.16 | Info Exchange
| 08888 | Review Response | Approved as Noted | 2020-10-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response and markup. | Info Exchange
| 11744 | Responded and Closed | Approved as Noted | 2020-10-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response and markup. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 26 05 02-25.0 400 Metro Club Floor Slab Penetrations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 26 05 02-25.0 400 Metro Club Floor Slab Penetrations-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-05 |  | 26 05 02-25.0 400 Metro Club Floor Slab Penetrations-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-04 02:00 |  | 26 05 02-25.0 400 Metro Club Floor Slab Penetrations-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-20 |  | 26 05 02-25.0 400 Metro Club Floor Slab Penetrations-MAM_TT_ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-05 |  | 26 05 02-25.0 400 Metro Club Floor Slab Penetrations-MAM.pdf
26 05 02-026-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-026-00 550 Space Needle Slab Penetrations | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Review Response - Approved |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-10-19 | 2020-10-08 | 4 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08565 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 26 05 02-26.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: 550 SPACE NEEDLE SLAB PENETRATIONS Description: PLEASE REVIEW THE FLOOR LIGHT PENETRATIONS SHOP DRAWINGS. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11326 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton... | 2020-10-12 | Submittal Number: 26 05 02-26.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: 550 SPACE NEEDLE SLAB PENETRATIONS Description: PLEASE REVIEW THE FLOOR LIGHT PENETRATIONS SHOP DRAWINGS. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 08630 | Review Response | Approved as Noted | 2020-10-05 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 11407 | Responded and Closed | Approved as Noted | 2020-10-08 | Todd Spangler (Populous) | Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| 08914 | Review Response | Approved | 2020-10-16 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 26 05 02-26.0 550 Space Needle Club Slab Penetrations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 26 05 02-26.0 550 Space Needle Club Slab Penetrations-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-05 |  | 26 05 02-26.0 550 Space Needle Club Slab Penetrations-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-10-08 |  | 26 05 02-26.0 550 Space Needle Club Slab Penetrations-MAM_TT_POP.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-04 02:00 |  | 26 05 02-26.0 550 Space Needle Club Slab Penetrations-MAM.pdf
26 05 02-027-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-027-00 Suite Level East Suites and East Corridor Area D Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-16 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-02 08:00 | 2020-12-11 | 26 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-12-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09452 | Received | For Review | 2020-11-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-12-02 08:00 | Submittal Number: 26 05 02-27.0 From: PATRICK KLEIN Final Due Date: 12/01/20 Subject: SUITE LEVEL EAST SUITES AND EAST CORRIDOR AREA D SHOP DRAWINGS Description: 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM 260529: HANGERS AND SUPPORTS Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 12462 | Forwarded | For Review | 2020-11-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-23 | Submittal Number: 26 05 02-27.0 From: PATRICK KLEIN Final Due Date: 12/01/20 Subject: SUITE LEVEL EAST SUITES AND EAST CORRIDOR AREA D SHOP DRAWINGS Description: 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM 260529: HANGERS AND SUPPORTS Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10112 | Review Response | Approved as Noted | 2020-12-03 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | See the attached submittal review. Populous - Please take a look at the suite downlight layout within the submittal shown on pages 13 and 14 as it differs slightly from the design documents. Let us know if you have any questions. Thank you, Mark Lievens ME Engineers 2020.12.03 | Info Exchange
| 13221 | Responded and Closed | Approved as Noted | 2020-12-11 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. COORDINATE ALL SHOPS WITH PREVIOUS SCOPES SUBMITTAL COMMENTS 2. COORDINATE REVISE FIRE ALARM LOCATIONS NOTED ON E-400D-E-CORRIDOR-FA-01 3. SEE ATTCHED FOR ADDITIONAL COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 26 05 02-27.0 Suite Level East Siotes and East Corridor Area D Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 26 05 02-27.0 Suite Level East Siotes and East Corridor Area D Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-16 |  | 26 05 02-27.0 Suite Level East Siotes and East Corridor Area D Shops-MAM.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2020-12-11 |  | 26 05 02-27.0 Suite Level East Suites and East Corridor Area D Shops-MAM-ME_POP.pdf
26 05 02-028-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-028-00 ELECTRICAL REQUIREMENTS - Event Level Premium Space Shop Drawings | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-16 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-02 08:00 | 2020-12-02 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-12-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09453 | Received | For Review | 2020-11-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-12-02 08:00 | Submittal Number: 26 05 02-28.0 From: PATRICK KLEIN Final Due Date: 12/01/20 Subject: ELECTRICAL REQUIREMENTS - EVENT LEVEL PREMIUM SPACE SHOP DRAWINGS Description: OH HANGERS SHOP DRAWINGS SUBMITTED SEPARATELY AS WE WAIT FOR POINT LOAD CALCULATIONS. 260529: HANGERS AND SUPPORTS 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 12464 | Forwarded | For Review | 2020-11-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornt... | 2020-11-23 | Submittal Number: 26 05 02-28.0 From: PATRICK KLEIN Final Due Date: 12/01/20 Subject: ELECTRICAL REQUIREMENTS - EVENT LEVEL PREMIUM SPACE SHOP DRAWINGS Description: OH HANGERS SHOP DRAWINGS SUBMITTED SEPARATELY AS WE WAIT FOR POINT LOAD CALCULATIONS. 260529: HANGERS AND SUPPORTS 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 09891 | Review Response | Approved as Noted | 2020-11-23 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no comments layout for hanging equipment. If any of this equipment is to be embedded into slab, please provide embedment locations and sizes (diamater, depth) relative to structural steel provided that has not alreadu been submitted. As noted in Submittal Transmittal, all loads imposed from this scope of work to be submitted to EOR for review and approval in separate submittal. | Info Exchange
| 09899 | Review Response | Approved as Noted | 2020-12-01 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.12.01 | Info Exchange
| 09851 | Review Response | Approved as Noted | 2020-12-02 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12932 | Responded and Closed | Approved as Noted | 2020-12-02 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 26 05 02-28.0 Event Level Premium Space Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 26 05 02-28.0 Event Level Premium Space Shops-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-11-15 02:00 |  | 26 05 02-28.0 Event Level Premium Space Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-15 02:00 |  | 26 05 02-28.0 Event Level Premium Space Shops-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-02 |  | 26 05 02-28.0 Event Level Premium Space Shops-MAM-ME-TT-POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-16 |  | 26 05 02-28.0 Event Level Premium Space Shops-MAM.pdf
26 05 02-029-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-029-00 ELECTRICAL REQUIREMENTS - Premium Space Loading and Seismic Drawings 100, 300, and 400 Levels | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-13 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-01-28 08:00 | 2021-01-20 | 8 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10668 | Received | For Review | 2021-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-01-28 08:00 | Submittal Number: 26 05 02-29.0 From: PATRICK KLEIN Final Due Date: 01/26/21 Subject: ELECTRICAL REQUIREMENTS - PREMIUM SPACE LOADING AND SEISMIC DRAWINGS 100, 300, AND 400 LEVELS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 13889 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornt... | 2021-01-20 | Submittal Number: 26 05 02-29.0 From: PATRICK KLEIN Final Due Date: 01/26/21 Subject: ELECTRICAL REQUIREMENTS - PREMIUM SPACE LOADING AND SEISMIC DRAWINGS 100, 300, AND 400 LEVELS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10818 | Review Response | Approved as Noted | 2021-01-15 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | A higher (conservative) value of SDS was used within the submittal calcs than what is shown on the structural drawings. Provide calrification on where trapeze type 3 is used, what the typical loading is, and what the spacing of supports is. | Info Exchange
| 14070 | Responded and Closed | Approved as Noted | 2021-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: A higher (conservative) value of SDS was used within the submittal calcs than what is shown on the structural drawings. Provide calrification on where trapeze type 3 is used, what the typical loading is, and what the spacing of supports is. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 26 05 02-29.0 Premium Space Loading and Seismic Drawings 100 300 and 400 Levels-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 26 05 02-29.0 Premium Space Loading and Seismic Drawings 100 300 and 400 Levels-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-11 02:00 |  | 26 05 02-29.0 Premium Space Loading and Seismic Drawings 100 300 and 400 Levels-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-20 02:00 |  | 26 05 02-29.0 Premium Space Loading and Seismic Drawings 100 300 and 400 Levels-MAM_TT_pop.pdf
26 05 02-030-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-030-00 ELECTRICAL REQUIREMENTS - West Main Concourse Club Shops | Closed | Electrical, Structural, Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-13 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Brian Elwell (Idibri) |  |  |  | 2021-01-28 08:00 | 2021-02-02 | 21 |  | Record Copies; Transfers; Submittals | 26 05 02-030-00-01 - 26 05 02-030-00 ELECTRICAL REQUIREMENTS - West Main Concourse Club Shops | 21 |  | 2021-02-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10669 | Received | For Review | 2021-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-01-28 08:00 | Submittal Number: 26 05 02-30.0 From: PATRICK KLEIN Final Due Date: 01/26/21 Subject: ELECTRICAL REQUIREMENTS - WEST MAIN CONCOURSE CLUB SHOPS Description: HANGERS SHOP DRAWINGS SUBMITTED SEPARATELY AS WE WAIT FOR POINT LOAD CALCULATIONS. 260529: HANGERS AND SUPPORTS 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 13890 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornt... | 2021-01-20 | Submittal Number: 26 05 02-30.0 From: PATRICK KLEIN Final Due Date: 01/26/21 Subject: ELECTRICAL REQUIREMENTS - WEST MAIN CONCOURSE CLUB SHOPS Description: HANGERS SHOP DRAWINGS SUBMITTED SEPARATELY AS WE WAIT FOR POINT LOAD CALCULATIONS. 260529: HANGERS AND SUPPORTS 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11137 | Review Response | Not Required For Review | 2021-01-15 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | No Review required by TT. Loads imposed have been submitted in separate submittal. | Info Exchange
| 11879 | Review Response | Approved as Noted | 2021-01-28 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Brian Elwell (Idibri); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Idibri shall review shop drawings for speaker locations and AV conduit. Mark Lievens ME Engineers 2021.01.28 | Info Exchange
| 14412 | Sent | For Information Only | 2021-02-01 | Bryan Klote (Populous) | Kelsea Conkright (Populous); Brian Elwell (Idibri); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Brian - Apologies this is overdue already, I missed that it needed to go to you. Can you expedite the review on it please? | Info Exchange
| 14419 | Forwarded | For Review | 2021-02-01 | Josh Dobken (Populous) | Brian Elwell (Idibri) | 2021-01-28 | Submittal Number: 26 05 02-30.0 From: PATRICK KLEIN Final Due Date: 01/26/21 Subject: ELECTRICAL REQUIREMENTS - WEST MAIN CONCOURSE CLUB SHOPS Description: HANGERS SHOP DRAWINGS SUBMITTED SEPARATELY AS WE WAIT FOR POINT LOAD CALCULATIONS. 260529: HANGERS AND SUPPORTS 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11880 | Review Response | Approved as Noted/Resubmit | 2021-02-02 | Brian Elwell (Idibri) | Josh Dobken (Populous) |  |  | Info Exchange
| 14448 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-02 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Pending response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Idibri shall review shop drawings for speaker locations and AV conduit. Mark Lievens ME Engineers 2021.01.28 Pending response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-12 |  | 26 05 02-30.0 West Main Concourse Club Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-12 |  | 26 05 02-30.0 West Main Concourse Club Shop Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-12 |  | 26 05 02-30.0 West Main Concourse Club Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-01-11 02:00 |  | 26 05 02-30.0 West Main Concourse Club Shop Drawings-MAM.pdf
| Sent |  | Bryan Klote (Populous) | 1 | 2021-01-12 |  | 26 05 02-30.0 West Main Concourse Club Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-11 02:00 |  | 26 05 02-30.0 West Main Concourse Club Shop Drawings-MAM.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-01-11 02:00 |  | 26 05 02-30.0 West Main Concourse Club Shop Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-02 |  | 26 05 02-30.0 West Main Concourse Club Shop Drawings-ME_Idi_POP.pdf
26 05 02-030-00-01 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-030-00 ELECTRICAL REQUIREMENTS - West Main Concourse Club Shops | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 05 02-030-00 - 26 05 02-030-00 ELECTRICAL REQUIREMENTS - West Main Concourse Club Shops | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | 26 05 02-30.0 West Main Concourse Club Shop Drawings-ME_Idi_POP.pdf
26 05 02-031-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-031-00 ELECTRICAL REQUIREMENTS - Suite Level Shop Drawings | Closed | Electrical, Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-13 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Brian Elwell (Idibri) |  |  |  | 2021-01-28 08:00 | 2021-02-11 | 30 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2021-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10678 | Received | For Review | 2021-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-01-28 08:00 | Submittal Number: 26 05 02-31.0 From: PATRICK KLEIN Final Due Date: 01/27/21 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL SHOP DRAWINGS Description: 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 13898 | Forwarded | For Review | 2021-01-13 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-20 | Submittal Number: 26 05 02-31.0 From: PATRICK KLEIN Final Due Date: 01/27/21 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL SHOP DRAWINGS Description: 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 14420 | Forwarded | For Review | 2021-02-01 | Josh Dobken (Populous) | Brian Elwell (Idibri) | 2021-01-28 | Submittal Number: 26 05 02-31.0 From: PATRICK KLEIN Final Due Date: 01/27/21 Subject: ELECTRICAL REQUIREMENTS - SUITE LEVEL SHOP DRAWINGS Description: 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11371 | Review Response | Approved as Noted | 2021-02-02 | Brian Elwell (Idibri) | Josh Dobken (Populous) |  |  | Info Exchange
| 11372 | Review Response | Approved as Noted | 2021-02-08 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.02.08 | Info Exchange
| 14728 | Responded and Closed | Approved as Noted | 2021-02-11 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.02.08 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 26 05 02-31.0 Suite Level Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 26 05 02-31.0 Suite Level Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-12 02:00 |  | 26 05 02-31.0 Suite Level Shop Drawings-MAM.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-01-12 |  | 26 05 02-31.0 Suite Level Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-01-13 |  | 26 05 02-31.0 Suite Level Shop Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-11 |  | 26 05 02-31.0 Suite Level Shop Drawings-ME_i!i_POP.pdf
26 05 02-032-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-032-00 Space Needle Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Brian Elwell (Idibri) |  |  |  | 2021-01-29 08:00 | 2021-02-11 | 29 |  | Record Copies; Transfers; Submittals | 26 05 02-032-00-01 - 26 05 02-032-00 Space Needle Shop Drawings | 26 |  | 2021-02-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10703 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-01-29 08:00 | Submittal Number: 26 05 02-32.0 From: PATRICK KLEIN Final Due Date: 01/27/21 Subject: SPACE NEEDLE SHOP DRAWINGS Description: 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM 260529: HANGERS AND SUPPORTS DRAWING AREAS: 550 LEVEL SPACE NEEDLE CLUB Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 13924 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-21 | Submittal Number: 26 05 02-32.0 From: PATRICK KLEIN Final Due Date: 01/27/21 Subject: SPACE NEEDLE SHOP DRAWINGS Description: 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM 260529: HANGERS AND SUPPORTS DRAWING AREAS: 550 LEVEL SPACE NEEDLE CLUB Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11365 | Review Response | Approved as Noted | 2021-01-28 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Brian Elwell (Idibri); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Idibri should review speaker locations shown within the submittal. Mark Lievens ME Engineers 2020.03.28 | Info Exchange
| 14414 | Sent | For Information Only | 2021-02-01 | Bryan Klote (Populous) | Brian Elwell (Idibri); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Same for this one, sorry. | Info Exchange
| 14595 | Forwarded | For Review | 2021-02-08 | Josh Dobken (Populous) | Brian Elwell (Idibri) | 2021-01-29 | Submittal Number: 26 05 02-32.0 From: PATRICK KLEIN Final Due Date: 01/27/21 Subject: SPACE NEEDLE SHOP DRAWINGS Description: 260533: RACEWAYS AND BOXES 274130: VIDEO PRODUCTION SYSTEMS 283100: ADDRESSABLE FIRE ALARM SYSTEM 260529: HANGERS AND SUPPORTS DRAWING AREAS: 550 LEVEL SPACE NEEDLE CLUB Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 11367 | Review Response | Approved as Noted/Resubmit | 2021-02-08 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 14724 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-11 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| 14929 | Sent | For Information Only | 2021-02-18 | Josh Dobken (Populous) | Domingo Sampayo (Mortenson Construction); Patrick Klein (Mortenson Construction) |  | Responded and Closed (Approved as Noted/Resubmit) to: Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) Remarks: Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | 26 05 02-32.0 Space Needle Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-13 |  | 26 05 02-32.0 Space Needle Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-01-13 |  | 26 05 02-32.0 Space Needle Shop Drawings-MAM.pdf
| Sent |  | Bryan Klote (Populous) | 1 | 2021-01-13 |  | 26 05 02-32.0 Space Needle Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-01-12 02:00 |  | 26 05 02-32.0 Space Needle Shop Drawings-MAM.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-01-12 |  | 26 05 02-32.0 Space Needle Shop Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-02-11 |  | 26 05 02-32.0 Space Needle Shop Drawings-ME-Idib_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-02-11 02:00 |  | 26 05 02-32.0 Space Needle Shop Drawings-ME-Idib_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-02-11 02:00 |  | Transmittal_Submittal - 26 05 02-032-00 (Responded and Closed).pdf
26 05 02-032-00-01 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-032-00 Space Needle Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 05 02-032-00 - 26 05 02-032-00 Space Needle Shop Drawings | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-11 |  | 26 05 02-32.0 Space Needle Shop Drawings-ME-Idib_POP.pdf
26 05 02-033-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-033-00 Space Needle Loading and Seismic Drawings | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-15 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-01 08:00 | 2021-01-20 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10724 | Received | For Review | 2021-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-02-01 08:00 | Submittal Number: 26 05 02-33.0 From: PATRICK KLEIN Final Due Date: 01/28/21 Subject: SPACE NEEDLE LOADING AND SEISMIC DRAWINGS Description: 260529: HANGERS AND SUPPORTS DRAWING AREAS: 550 LEVEL SPACE NEEDLE CLUB PLEASE FIND THE MAX POINT LOADS CALCULATION PER OUR HANGER/SUPPORT DRAWINGS. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 13952 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornt... | 2021-01-21 | Submittal Number: 26 05 02-33.0 From: PATRICK KLEIN Final Due Date: 01/28/21 Subject: SPACE NEEDLE LOADING AND SEISMIC DRAWINGS Description: 260529: HANGERS AND SUPPORTS DRAWING AREAS: 550 LEVEL SPACE NEEDLE CLUB PLEASE FIND THE MAX POINT LOADS CALCULATION PER OUR HANGER/SUPPORT DRAWINGS. Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 10831 | Review Response | Approved as Noted | 2021-01-15 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous); Shaina Burris (Populous) |  | SDS used within Submittal Calcs is conservative compared to that shown in structural drawings. | Info Exchange
| 14078 | Responded and Closed | Approved as Noted | 2021-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: SDS used within Submittal Calcs is conservative compared to that shown in structural drawings. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | 26 05 02-33.0 Space Needle Loading and Seismic Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | 26 05 02-33.0 Space Needle Loading and Seismic Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-01-13 02:00 |  | 26 05 02-33.0 Space Needle Loading and Seismic Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-20 02:00 |  | 26 05 02-33.0 Space Needle Loading and Seismic Drawings-MAM_TT_POP.pdf
26 05 02-034-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-034-00 ELECTRICAL REQUIREMENTS - Space Needle Chandelier Structural Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-04 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-18 | 2021-06-10 | 7 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-06-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13418 | Received | For Review | 2021-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction) | 2021-06-18 | Submittal Number: 26 05 02-34.0 From: PATRICK KLEIN Final Due Date: 06/18/21 Subject: ELECTRICAL REQUIREMENTS - SPACE NEEDLE CHANDELIER STRUCTURAL DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 17350 | Forwarded | For Review | 2021-06-07 | Patrick Klein (Mortenson Construction) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tom... | 2021-06-14 | Submittal Number: 26 05 02-34.0 From: PATRICK KLEIN Final Due Date: 06/18/21 Subject: ELECTRICAL REQUIREMENTS - SPACE NEEDLE CHANDELIER STRUCTURAL DRAWINGS Description: Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 13475 | Review Response | Approved as Noted | 2021-06-10 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Arch to review. Missing calcs for bottom plate. Provide additional clarity for welds in detail. Additional through-bolts added. Contractor to field verify elevation, location, slope, etc of existing steel above prior to fabrication and installation. | Info Exchange
| 17430 | Responded and Closed | Approved as Noted | 2021-06-10 | Patrick Klein (Mortenson Construction) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Missing calcs for bottom plate. Provide additional clarity for welds in detail. Additional through-bolts added. Contractor to field verify elevation, location, slope, etc of existing steel above prior to fabrication and installation. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-04 |  | 26 05 02-34.0 Space Needle Chandelier Structural Drawings-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2021-06-04 |  | 26 05 02-34.0 Space Needle Chandelier Structural Drawings-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-06-04 |  | 26 05 02-34.0 Space Needle Chandelier Structural Drawings-MAM.pdf
| Responded and Closed |  | Patrick Klein (Mortenson Construction) | 1 | 2021-06-10 |  | 26 05 02-34.0 Space Needle Chandelier Structural Drawings-MAM_TT_POP.pdf
26 05 02-035-00 | 26 05 02 - ELECTRICAL REQUIREMENTS | 26 05 02-035-00 Living Wall Electrical Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-25 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-09-08 | 2021-09-13 | 20 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-09-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14472 | Received | For Review | 2021-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Shaina Burris (Populous) | 2021-09-08 | Submittal Number: 26 05 02-35.0 From: NICK NOWOJ Final Due Date: 08/30/21 Subject: LIVING WALL ELECTRICAL SHOP DRAWINGS Description: ELECTRICAL SHOP DRAWINGS FOR LIVING WALL Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 18665 | Forwarded | For Review | 2021-08-25 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-09-01 | Submittal Number: 26 05 02-35.0 From: NICK NOWOJ Final Due Date: 08/30/21 Subject: LIVING WALL ELECTRICAL SHOP DRAWINGS Description: ELECTRICAL SHOP DRAWINGS FOR LIVING WALL Spec Section: 26 05 02 - ELECTRICAL REQUIREMENTS Status: OPEN | Info Exchange
| 14633 | Review Response | Approved as Noted | 2021-09-10 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.09.10 | Info Exchange
| 18872 | Responded and Closed | Approved as Noted | 2021-09-13 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Colin.Saiz@mortenson.com |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.09.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-25 |  | 26 05 02-35.0 Living wall electrical shop drawings.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-25 |  | 26 05 02-35.0 Living wall electrical shop drawings.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-09-13 |  | 26 05 02-35.0 Living wall electrical shop drawings - ME_POP.pdf
26 05 03-001-00 | 26 05 03 - TESTING | 26 05 03-001-00 TESTING - Qualification Data and Form Templates | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-20 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-05 | 2020-03-10 | 20 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04422 | Received | For Review | 2020-02-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-05 | Submittal Number: 26 05 03-1.0 From: PATRICK KLEIN Final Due Date: 03/05/20 Subject: TESTING - QUALIFICATION DATA AND FORM TEMPLATES Description: QUALIFICATION OF TESTING FIRM. ONE ELECTRONIC COPY OF BLANK FORMS FOR CHECKLISTS, TEST REPORTS, AND OTHER RELATED FORMS FOR ENGINEERS REVIEW AND APPROVAL. Spec Section: 26 05 03 - TESTING Status: OPEN | Info Exchange
| 06106 | Forwarded | For Review | 2020-02-20 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-27 | Submittal Number: 26 05 03-1.0 From: PATRICK KLEIN Final Due Date: 03/05/20 Subject: TESTING - QUALIFICATION DATA AND FORM TEMPLATES Description: QUALIFICATION OF TESTING FIRM. ONE ELECTRONIC COPY OF BLANK FORMS FOR CHECKLISTS, TEST REPORTS, AND OTHER RELATED FORMS FOR ENGINEERS REVIEW AND APPROVAL. Spec Section: 26 05 03 - TESTING Status: OPEN | Info Exchange
| 04741 | Review Response | Approved as Noted | 2020-03-06 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.06 | Info Exchange
| 06513 | Responded and Closed | Approved as Noted | 2020-03-10 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-20 |  | 26 05 03-1.0 Qualification Data and Form Templates-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-20 |  | 26 05 03-1.0 Qualification Data and Form Templates-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-19 02:00 |  | 26 05 03-1.0 Qualification Data and Form Templates-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-10 02:00 |  | 26 05 03-1.0 Qualification Data and Form Templates-MAM-ME_POP.pdf
26 05 03-003-00 | 26 05 03 - TESTING | 26 05 03-003-00 TESTING - Short Circuit and Coordination Study | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-17 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-31 | 2020-04-05 | 20 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04890 | Received | For Review | 2020-03-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-03-31 | Submittal Number: 26 05 03-3.0 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: TESTING - SHORT CIRCUIT AND COORDINATION STUDY Description: PROVIDE A COMPLETE SHORT-CIRCUIT STUDY, EQUIPMENT INTERRUPTING/WITHSTAND EVALUATION, AND A PROTECTIVE DEVICE COORDINATION STUDY FOR THE ELECTRICAL DISTRIBUTION SYSTEM DESCRIBED HEREIN. Spec Section: 26 05 03 - TESTING Status: OPEN | Info Exchange
| 06680 | Forwarded | For Review | 2020-03-17 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-24 | Submittal Number: 26 05 03-3.0 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: TESTING - SHORT CIRCUIT AND COORDINATION STUDY Description: PROVIDE A COMPLETE SHORT-CIRCUIT STUDY, EQUIPMENT INTERRUPTING/WITHSTAND EVALUATION, AND A PROTECTIVE DEVICE COORDINATION STUDY FOR THE ELECTRICAL DISTRIBUTION SYSTEM DESCRIBED HEREIN. Spec Section: 26 05 03 - TESTING Status: OPEN | Info Exchange
| 05216 | Review Response | Approved as Noted/Resubmit | 2020-04-04 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review for action items and individual item dispositions. Thank you, Mark Lievens ME Engineers 2020.04.04 | Info Exchange
| 07090 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-05 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review for action items and individual item dispositions. Thank you, Mark Lievens ME Engineers 2020.04.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-17 |  | 26 05 03-3.0 Short Circuit and Coordination Study-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-17 |  | 26 05 03-3.0 Short Circuit and Coordination Study-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-16 02:00 |  | 26 05 03-3.0 Short Circuit and Coordination Study-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-05 02:00 |  | 26 05 03-3.0 Short Circuit and Coordination Study-MAM-ME_POP.pdf
26 05 03-003-01 | 26 05 03 - TESTING | 26 05 03-003-01 TESTING - Short Circuit and Coordination Study | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-12 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-27 07:00 | 2020-06-04 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05809 | Received | For Review | 2020-05-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-05-27 07:00 | Submittal Number: 26 05 03-3.1 From: PATRICK KLEIN Final Due Date: 05/29/20 Subject: TESTING - SHORT CIRCUIT AND COORDINATION STUDY Description: PROVIDE A COMPLETE SHORT-CIRCUIT STUDY, EQUIPMENT INTERRUPTING/WITHSTAND EVALUATION, AND A PROTECTIVE DEVICE COORDINATION STUDY FOR THE ELECTRICAL DISTRIBUTION SYSTEM DESCRIBED HEREIN. Spec Section: 26 05 03 - TESTING Status: OPEN | Info Exchange
| 07875 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 26 05 03-3.1 From: PATRICK KLEIN Final Due Date: 05/29/20 Subject: TESTING - SHORT CIRCUIT AND COORDINATION STUDY Description: PROVIDE A COMPLETE SHORT-CIRCUIT STUDY, EQUIPMENT INTERRUPTING/WITHSTAND EVALUATION, AND A PROTECTIVE DEVICE COORDINATION STUDY FOR THE ELECTRICAL DISTRIBUTION SYSTEM DESCRIBED HEREIN. Spec Section: 26 05 03 - TESTING Status: OPEN | Info Exchange
| 06200 | Review Response | Approved as Noted/Resubmit | 2020-06-03 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.02 | Info Exchange
| 08378 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 26 05 03-3.1 Short Circuit and Coordination Study-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 26 05 03-3.1 Short Circuit and Coordination Study-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-10 02:00 |  | 26 05 03-3.1 Short Circuit and Coordination Study-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-04 02:00 |  | 26 05 03-3.1 Short Circuit and Coordination Study-MAM-ME_POP.pdf
26 05 03-003-02 | 26 05 03 - TESTING | 26 05 03-003-02 TESTING - Short Circuit and Coordination Study | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-27 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-16 | 2020-12-01 | 36 |  | Record Copies; Transfers; Submittals | 26 05 03-003-02-01 - 26 05 03-003-02 TESTING - Short Circuit and Coordination Study | 35 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09021 | Received | For Review | 2020-10-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-16 | Submittal Number: 26 05 03-3.2 From: PATRICK KLEIN Final Due Date: 11/13/20 Subject: TESTING - SHORT CIRCUIT AND COORDINATION STUDY Description: SUBMIT TABULATION OF SUGGESTED ADJUSTABLE OCPD DEVICE SETTINGS Spec Section: 26 05 03 - TESTING Status: OPEN | Info Exchange
| 11902 | Forwarded | For Review | 2020-10-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-03 | Submittal Number: 26 05 03-3.2 From: PATRICK KLEIN Final Due Date: 11/13/20 Subject: TESTING - SHORT CIRCUIT AND COORDINATION STUDY Description: SUBMIT TABULATION OF SUGGESTED ADJUSTABLE OCPD DEVICE SETTINGS Spec Section: 26 05 03 - TESTING Status: OPEN | Info Exchange
| 09773 | Review Response | Approved as Noted/Resubmit | 2020-11-30 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. The cover page and review form have been included as a seperate PDF from the submittal due to the submittal being locked by the manufacturer from adding pages to it. Let me know if you have any questions. Thank you, Mark Lievens ME Engineers 2020.11.30 | Info Exchange
| 12855 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. The cover page and review form have been included as a seperate PDF from the submittal due to the submittal being locked by the manufacturer from adding pages to it. Let me know if you have any questions. Thank you, Mark Lievens ME Engineers 2020.11.30 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 26 05 03-3.2 Short Circuit and Coordination Study-MAM.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | Sign Off Sheet.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 26 05 03-3.2 Short Circuit and Coordination Study-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | Sign Off Sheet.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-27 |  | 26 05 03-3.2 Short Circuit and Coordination Study-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-27 |  | Sign Off Sheet.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-11-30 |  | 26 05 03-3.2 Short Circuit and Coordination Study-MAM-ME_POP.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-01 |  | Cover Sheet - 26 05 03-3.2 Short Circuit and Coordination Study-MAM-ME_POP.pdf
26 05 03-003-02-01 | 26 05 03 - TESTING | 26 05 03-003-02 TESTING - Short Circuit and Coordination Study | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 05 03-003-02 - 26 05 03-003-02 TESTING - Short Circuit and Coordination Study | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-30 |  | 26 05 03-3.2 Short Circuit and Coordination Study-MAM-ME_POP.pdf
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-01 |  | Cover Sheet - 26 05 03-3.2 Short Circuit and Coordination Study-MAM-ME_POP.pdf
26 05 03-003-03 | 26 05 03 - TESTING | 26 05 03-003-03 TESTING - Arc Flash Hazard Analysis | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-27 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-10-11 | 2021-09-30 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-09-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14704 | Received | For Review | 2021-09-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-10-11 | Submittal Number: 26 05 03-3.3 From: PATRICK KLEIN Final Due Date: 10/10/21 Subject: TESTING - ARC FLASH HAZARD ANALYSIS Description: PROVIDE ARC FLASH HAZARD ANALYSIS Spec Section: 26 05 03 - TESTING Status: OPEN | Info Exchange
| 18963 | Forwarded | For Review | 2021-09-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-10-04 | Submittal Number: 26 05 03-3.3 From: PATRICK KLEIN Final Due Date: 10/10/21 Subject: TESTING - ARC FLASH HAZARD ANALYSIS Description: PROVIDE ARC FLASH HAZARD ANALYSIS Spec Section: 26 05 03 - TESTING Status: OPEN | Info Exchange
| 14764 | Review Response | Approved as Noted | 2021-09-30 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.09.30 | Info Exchange
| 19034 | Responded and Closed | Approved as Noted | 2021-09-30 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.09.30 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-26 |  | 26 05 03-3.3 Arc Flash Hazard Analysis-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-26 |  | 26 05 03-3.3 Arc Flash Hazard Analysis-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-09-26 |  | 26 05 03-3.3 Arc Flash Hazard Analysis-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-09-30 |  | 26 05 03-3.3 Arc Flash Hazard Analysis-MAM-ME_POP.pdf
26 05 06-001-00 | 26 05 06 - BASIC MATERIAL AND METHODS | 26 05 06-001-00 Artist Lounge - Recording Light | Closed | Architectural, Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-15 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-29 | 2021-07-02 | 18 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13533 | Received | For Review | 2021-06-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-29 | Submittal Number: 26 05 06-1.0 From: ELLA PILGRIM Final Due Date: 06/30/21 Subject: ARTIST LOUNGE - RECORDING LIGHT Description: SHEET NOTE E175 - MODEL 340-REC-110 OR APPROVED EQUAL Spec Section: 26 05 06 - BASIC MATERIAL AND METHODS Status: OPEN | Info Exchange
| 17512 | Forwarded | For Review | 2021-06-15 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-22 | Submittal Number: 26 05 06-1.0 From: ELLA PILGRIM Final Due Date: 06/30/21 Subject: ARTIST LOUNGE - RECORDING LIGHT Description: SHEET NOTE E175 - MODEL 340-REC-110 OR APPROVED EQUAL Spec Section: 26 05 06 - BASIC MATERIAL AND METHODS Status: OPEN | Info Exchange
| 13768 | Review Response | Approved | 2021-06-22 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Populous shall review/approve recording light type shown within the submittal. Mark Lievens ME Engineers 2021.06.22 | Info Exchange
| 17819 | Responded and Closed | Approved | 2021-07-02 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Populous shall review/approve recording light type shown within the submittal. Mark Lievens ME Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-15 |  | 26 05 06-1.0 - Artist Lounge - Recording Light.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-15 |  | 26 05 06-1.0 - Artist Lounge - Recording Light.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-06-15 |  | 26 05 06-1.0 - Artist Lounge - Recording Light.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-02 |  | 26 05 06-1.0 - Artist Lounge - Recording Light - ME_POP.pdf
26 05 06-003-00 | 26 05 06 - BASIC MATERIAL AND METHODS | 26 05 06-003-00 Access Panel Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-23 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Kelsea Conkright (Populous), Kuebler Perry (Populous) |  |  |  | 2020-12-09 | 2020-12-14 | 22 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-12-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09675 | Received | For Review | 2020-11-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-09 | Submittal Number: 26 05 06-3.0 From: ELLA PILGRIM Final Due Date: 12/10/20 Subject: ACCESS PANEL PRODUCT DATA Description: Spec Section: 26 05 06 - BASIC MATERIALS AND METHODS Status: OPEN | Info Exchange
| 12728 | Forwarded | For Review | 2020-11-23 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-30 | Submittal Number: 26 05 06-3.0 From: ELLA PILGRIM Final Due Date: 12/10/20 Subject: ACCESS PANEL PRODUCT DATA Description: Spec Section: 26 05 06 - BASIC MATERIALS AND METHODS Status: OPEN | Info Exchange
| 12778 | Forwarded | For Review | 2020-11-24 | Populous SCA_CCA | Bryan Klote (Populous); Kelsea Conkright (Populous); Kuebler Perry (Populous) | 2020-12-01 | Submittal Number: 26 05 06-3.0 From: ELLA PILGRIM Final Due Date: 12/10/20 Subject: ACCESS PANEL PRODUCT DATA Description: Spec Section: 26 05 06 - BASIC MATERIALS AND METHODS Status: OPEN | Info Exchange
| 10143 | Review Response | No Action Taken or Required | 2020-12-03 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Populous shall review Access panel product data provided. Thanks, Mark Lievens ME Engineers 2020.12.03 | Info Exchange
| 13266 | Responded and Closed | Approved | 2020-12-14 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-23 |  | 26 05 06-3.0 Basic Material and Methods - Access Panels.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-23 |  | 26 05 06-3.0 Basic Material and Methods - Access Panels.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-22 02:00 |  | 26 05 06-3.0 Basic Material and Methods - Access Panels.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-23 |  | 26 05 06-3.0 Basic Material and Methods - Access Panels.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-14 |  | 26 05 06-3.0 Basic Material and Methods - Access Panels_POP.pdf
26 05 07-001-00 | 26 05 07 - FOOD SERVICE EQUIPMENT WIRING | 26 05 07-001-00 Portable Cart Receptacle PD | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-27 | Responded and Closed - Approved as Noted |  | Amber Kennedy (S2O Consultants, Inc.), Mark Lievens (ME Engineers), Peg Galie (S2O Consultants, Inc.), Nick Theimer (ME Engineers), Harry Schildkraut (S2O Consultants, Inc.), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-11 07:00 | 2020-09-09 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07800 | Received | For Review | 2020-08-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-09-11 07:00 | Submittal Number: 26 05 07-1.0 From: ALYSSA SANDOVAL Final Due Date: 09/11/20 Subject: PORTABLE CART RECEPTACLE PD Description: Spec Section: 26 05 07 - FOOD SERVICE EQUIPMENT WIRING Status: OPEN | Info Exchange
| 10378 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Amber Kennedy (S2O Consultants, Inc.); Mark Lievens (ME Engineers); Peg Galie (S2O Consultants, Inc.); Nick Theimer (ME Engineers); Harry Schildkraut (S2O Consultants, Inc.); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-03 | Submittal Number: 26 05 07-1.0 From: ALYSSA SANDOVAL Final Due Date: 09/11/20 Subject: PORTABLE CART RECEPTACLE PD Description: Spec Section: 26 05 07 - FOOD SERVICE EQUIPMENT WIRING Status: OPEN | Info Exchange
| 08012 | Review Response | Not Required For Review | 2020-08-28 | Peg Galie (S2O Consultants, Inc.) | Shaina Burris (Populous) |  | This is outside the foodservice scope. We do not have any comments. | Info Exchange
| 08013 | Review Response | Approved as Noted | 2020-09-09 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.09.09 | Info Exchange
| 10657 | Responded and Closed | Approved as Noted | 2020-09-09 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.09.09 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 26 05 07-1.0 Portable Cart Receptacles-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-27 |  | 26 05 07-1.0 Portable Cart Receptacles-MAM.pdf
| Review Response |  | Peg Galie (S2O Consultants, Inc.) | 1 | 2020-08-27 |  | 26 05 07-1.0 Portable Cart Receptacles-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-27 |  | 26 05 07-1.0 Portable Cart Receptacles-MAM.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2020-09-09 |  | 26 05 07-1.0 Portable Cart Receptacles-MAM_ME_POP.pdf
26 05 07-001-01 | 26 05 07 - FOOD SERVICE EQUIPMENT WIRING | 26 05 07-001-01 Portable Cart Receptacle PD | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-21 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-05 | 2020-10-06 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08242 | Received | For Review | 2020-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-10-05 | Submittal Number: 26 05 07-1.1 From: PATRICK KLEIN Final Due Date: 10/05/20 Subject: PORTABLE CART RECEPTACLE PD Description: Spec Section: 26 05 07 - FOOD SERVICE EQUIPMENT WIRING Status: OPEN | Info Exchange
| 10947 | Forwarded | For Review | 2020-09-21 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-28 | Submittal Number: 26 05 07-1.1 From: PATRICK KLEIN Final Due Date: 10/05/20 Subject: PORTABLE CART RECEPTACLE PD Description: Spec Section: 26 05 07 - FOOD SERVICE EQUIPMENT WIRING Status: OPEN | Info Exchange
| 08611 | Review Response | Approved as Noted | 2020-10-06 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.06 | Info Exchange
| 11381 | Responded and Closed | Approved as Noted | 2020-10-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.06 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 26 05 07-1.1 Portable Cart Pedestal PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-21 |  | 26 05 07-1.1 Portable Cart Pedestal PD-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-21 |  | 26 05 07-1.1 Portable Cart Pedestal PD-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-06 |  | 26 05 07-1.1 Portable Cart Pedestal PD-MAM-ME_POP.pdf
26 05 07-002-00 | 26 05 07 - FOOD SERVICE EQUIPMENT WIRING | 26 05 07-002-00 FOOD SERVICE EQUIPMENT WIRING - GFCI Protection Concessions | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-08 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-22 | 2020-09-22 | 15 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-09-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07979 | Received | For Review | 2020-09-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-22 | Submittal Number: 26 05 07-2.0 From: PATRICK KLEIN Final Due Date: 09/22/20 Subject: FOOD SERVICE EQUIPMENT WIRING - GFCI PROTECTION CONCESSIONS Description: Spec Section: 26 05 07 - FOOD SERVICE EQUIPMENT WIRING Status: OPEN | Info Exchange
| 10609 | Forwarded | For Review | 2020-09-08 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-15 | Submittal Number: 26 05 07-2.0 From: PATRICK KLEIN Final Due Date: 09/22/20 Subject: FOOD SERVICE EQUIPMENT WIRING - GFCI PROTECTION CONCESSIONS Description: Spec Section: 26 05 07 - FOOD SERVICE EQUIPMENT WIRING Status: OPEN | Info Exchange
| 08252 | Review Response | Approved as Noted | 2020-09-15 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.09.15 | Info Exchange
| 10958 | Responded and Closed | Approved as Noted | 2020-09-22 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.09.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-08 |  | 26 05 07-2.0 GFCI Protection Concessions-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-08 |  | 26 05 07-2.0 GFCI Protection Concessions-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-08 |  | 26 05 07-2.0 GFCI Protection Concessions-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-22 |  | 26 05 07-2.0 GFCI Protection Concessions-MAM-ME_POP.pdf
26 05 07-003-00 | 26 05 07 - FOOD SERVICE EQUIPMENT WIRING | 26 05 07-003-00 Beer Garden Portable Cart Pedestal Finish | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chad Francis (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-02 | 2021-03-03 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11455 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction) | 2021-03-02 | Submittal Number: 26 05 07-3.0 From: PATRICK KLEIN Final Due Date: 03/01/21 Subject: BEER GARDEN PORTABLE CART PEDESTAL FINISH Description: Spec Section: 26 05 07 - FOOD SERVICE EQUIPMENT WIRING Status: OPEN | Info Exchange
| 14877 | Forwarded | For Review | 2021-02-16 | Patrick Klein (Mortenson Construction) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chad Francis (Populous) | 2021-02-23 | Submittal Number: 26 05 07-3.0 From: PATRICK KLEIN Final Due Date: 03/01/21 Subject: BEER GARDEN PORTABLE CART PEDESTAL FINISH Description: Spec Section: 26 05 07 - FOOD SERVICE EQUIPMENT WIRING Status: OPEN | Info Exchange
| 15226 | Forwarded | For Review | 2021-03-02 | Patrick Klein (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) |  | Submittal Number: 26 05 07-3.0 From: PATRICK KLEIN Final Due Date: 03/01/21 Subject: BEER GARDEN PORTABLE CART PEDESTAL FINISH Description: Spec Section: 26 05 07 - FOOD SERVICE EQUIPMENT WIRING Status: OPEN | Info Exchange
| 15255 | Responded and Closed | Approved as Noted | 2021-03-03 | Patrick Klein (Mortenson Construction) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | see attached (color approved with matte or satin finish) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 26 05 07-3.0 Beer Garden Portable Cart Pedestal Finish-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2021-02-14 02:00 |  | 26 05 07-3.0 Beer Garden Portable Cart Pedestal Finish-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2021-02-15 |  | 26 05 07-3.0 Beer Garden Portable Cart Pedestal Finish-MAM.pdf
| Responded and Closed |  | Patrick Klein (Mortenson Construction) | 1 | 2021-03-03 |  | 26 05 07-3.0 Beer Garden Portable Cart Pedestal Finish-MAM_POP.pdf
26 05 13-001-00 | 26 05 13 - MEDIUM-VOLTAGE CABLES | 26 05 13-001-00: MEDIUM VOLTAGE CABLES - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-02 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-16 | 2019-10-22 | 21 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2019-10-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02649 | Received | For Review | 2019-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-10-16 | Submittal Number: 26 05 13-1.0 From: PATRICK KLEIN Final Due Date: 10/16/19 Subject: MEDIUM VOLTAGE CABLES - PRODUCT DATA Description: 1. SUBMIT MANUFACTURERS PRODUCT DATA, FOR THE REVIEW AND APPROVAL ON MEDIUM-VOLTAGE- CABLES INCLUDING, BUT NOT LIMITED TO, THE FOLLOWING: A. PICTORIAL DIAGRAM SHOWING CONSTRUCTION OF CABLE. B. WRITTEN INDICATION THAT CABLE MEETS OR EXCEEDS THE SPECIFICATION AND ANY EXCEPTIONS TAKEN TO THE SPECIFICATION. Spec Section: 26 05 13 - MEDIUM-VOLTAGE CABLES Status: OPEN | Info Exchange
| 03963 | Forwarded | For Review | 2019-10-03 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-10 | Submittal Number: 26 05 13-1.0 From: PATRICK KLEIN Final Due Date: 10/16/19 Subject: MEDIUM VOLTAGE CABLES - PRODUCT DATA Description: 1. SUBMIT MANUFACTURERS PRODUCT DATA, FOR THE REVIEW AND APPROVAL ON MEDIUM-VOLTAGE- CABLES INCLUDING, BUT NOT LIMITED TO, THE FOLLOWING: A. PICTORIAL DIAGRAM SHOWING CONSTRUCTION OF CABLE. B. WRITTEN INDICATION THAT CABLE MEETS OR EXCEEDS THE SPECIFICATION AND ANY EXCEPTIONS TAKEN TO THE SPECIFICATION. Spec Section: 26 05 13 - MEDIUM-VOLTAGE CABLES Status: OPEN | Info Exchange
| 02892 | Review Response | Approved as Noted | 2019-10-22 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.10.22 | Info Exchange
| 04259 | Responded and Closed | Approved as Noted | 2019-10-22 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.10.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-02 02:00 |  | 26 05 13-1.0 Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-10-02 02:00 |  | 26 05 13-1.0 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-10-02 02:00 |  | 26 05 13-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-22 02:00 |  | 26 05 13-1.0 Product Data-MAM - ME_POP.pdf
26 05 13-001-01 | 26 05 13 - MEDIUM-VOLTAGE CABLES | 26 05 13-001-01: MEDIUM VOLTAGE CABLES - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-09 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-23 | 2019-12-17 | 9 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03577 | Received | For Review | 2019-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-12-23 | Submittal Number: 26 05 13-1.1 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: MEDIUM VOLTAGE CABLES - PRODUCT DATA Description: 1. SUBMIT MANUFACTURERS PRODUCT DATA, FOR THE REVIEW AND APPROVAL ON MEDIUM-VOLTAGE- CABLES INCLUDING, BUT NOT LIMITED TO, THE FOLLOWING: A. PICTORIAL DIAGRAM SHOWING CONSTRUCTION OF CABLE. B. WRITTEN INDICATION THAT CABLE MEETS OR EXCEEDS THE SPECIFICATION AND ANY EXCEPTIONS TAKEN TO THE SPECIFICATION. Spec Section: 26 05 13 - MEDIUM-VOLTAGE CABLES Status: OPEN | Info Exchange
| 05057 | Forwarded | For Review | 2019-12-10 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-17 | Submittal Number: 26 05 13-1.1 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: MEDIUM VOLTAGE CABLES - PRODUCT DATA Description: 1. SUBMIT MANUFACTURERS PRODUCT DATA, FOR THE REVIEW AND APPROVAL ON MEDIUM-VOLTAGE- CABLES INCLUDING, BUT NOT LIMITED TO, THE FOLLOWING: A. PICTORIAL DIAGRAM SHOWING CONSTRUCTION OF CABLE. B. WRITTEN INDICATION THAT CABLE MEETS OR EXCEEDS THE SPECIFICATION AND ANY EXCEPTIONS TAKEN TO THE SPECIFICATION. Spec Section: 26 05 13 - MEDIUM-VOLTAGE CABLES Status: OPEN | Info Exchange
| 03658 | Review Response | Approved as Noted/Resubmit | 2019-12-17 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2019.12.17 | Info Exchange
| 05178 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-17 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2019.12.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-09 02:00 |  | 26 05 13-1.01 Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 26 05 13-1.01 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-12-09 02:00 |  | 26 05 13-1.01 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-17 02:00 |  | 26 05 13-1.01 Product Data-MAM-ME_POP.pdf
26 05 13-001-02 | 26 05 13 - MEDIUM-VOLTAGE CABLES | 26 05 13-001-02 MEDIUM VOLTAGE CABLES - Product Data for Additional Manufacturers | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-24 | 2020-02-24 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04293 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-02-24 | Submittal Number: 26 05 13-1.2 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: MEDIUM VOLTAGE CABLES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: 1. SUBMIT MANUFACTURERS PRODUCT DATA, FOR THE REVIEW AND APPROVAL ON MEDIUM-VOLTAGE- CABLES INCLUDING, BUT NOT LIMITED TO, THE FOLLOWING: A. PICTORIAL DIAGRAM SHOWING CONSTRUCTION OF CABLE. B. WRITTEN INDICATION THAT CABLE MEETS OR EXCEEDS THE SPECIFICATION AND ANY EXCEPTIONS TAKEN TO THE SPECIFICATION. Spec Section: 26 05 13 - MEDIUM-VOLTAGE CABLES Status: OPEN | Info Exchange
| 05942 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-17 | Submittal Number: 26 05 13-1.2 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: MEDIUM VOLTAGE CABLES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: 1. SUBMIT MANUFACTURERS PRODUCT DATA, FOR THE REVIEW AND APPROVAL ON MEDIUM-VOLTAGE- CABLES INCLUDING, BUT NOT LIMITED TO, THE FOLLOWING: A. PICTORIAL DIAGRAM SHOWING CONSTRUCTION OF CABLE. B. WRITTEN INDICATION THAT CABLE MEETS OR EXCEEDS THE SPECIFICATION AND ANY EXCEPTIONS TAKEN TO THE SPECIFICATION. Spec Section: 26 05 13 - MEDIUM-VOLTAGE CABLES Status: OPEN | Info Exchange
| 04473 | Review Response | Approved as Noted | 2020-02-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| 06166 | Responded and Closed | Approved as Noted | 2020-02-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-10 |  | 26 05 13-1.2 Product Data for Additional Manufacturers-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 26 05 13-1.2 Product Data for Additional Manufacturers-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-09 02:00 |  | 26 05 13-1.2 Product Data for Additional Manufacturers-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-24 02:00 |  | 26 05 13-1.2 Product Data for Additional Manufacturers-MAM-ME_POP.pdf
26 05 19-001-00 | 26 05 19 - ELECTRICAL POWER CONDUCTORS AND CABLES | 26 05 19-001-00 ELECTRICAL POWER CONDUCTORS AND CABLES - Product Data and Pulling Tension Calculations | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-06 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-11-20 | 2019-11-20 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03078 | Received | For Review | 2019-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-11-20 | Submittal Number: 26 05 19-1.0 From: PATRICK KLEIN Final Due Date: 11/20/19 Subject: ELECTRICAL POWER CONDUCTORS AND CABLES - PRODUCT DATA AND PULLING TENSION CALCULATIONS Description: PRODUCT DATA FOR ELECTRICAL WIRES, CABLES AND CONNECTORS. SUBMIT PULLING TENSION CALCULATIONS FOR ALL UNDERGROUND FEEDERS. Spec Section: 26 05 19 - ELECTRICAL POWER CONDUCTORS AND CABLES Status: OPEN | Info Exchange
| 04477 | Forwarded | For Review | 2019-11-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-13 | Submittal Number: 26 05 19-1.0 From: PATRICK KLEIN Final Due Date: 11/20/19 Subject: ELECTRICAL POWER CONDUCTORS AND CABLES - PRODUCT DATA AND PULLING TENSION CALCULATIONS Description: PRODUCT DATA FOR ELECTRICAL WIRES, CABLES AND CONNECTORS. SUBMIT PULLING TENSION CALCULATIONS FOR ALL UNDERGROUND FEEDERS. Spec Section: 26 05 19 - ELECTRICAL POWER CONDUCTORS AND CABLES Status: OPEN | Info Exchange
| 03286 | Review Response | Approved as Noted/Resubmit | 2019-11-19 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens 2019.11.19 | Info Exchange
| 04736 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens 2019.11.19 | Info Exchange
| 04854 | Sent | For Construction | 2019-11-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Revised submittal response attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-06 |  | 26 05 19-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-06 |  | 26 05 19-1.0 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-11-05 02:00 |  | 26 05 19-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-20 02:00 |  | 26 05 19-1.0 Product Data-MAM-ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2019-11-26 02:00 |  | 26 05 19-1.0 Product Data-MAM-ME-Rev.1_POP.pdf
26 05 19-001-01 | 26 05 19 - ELECTRICAL POWER CONDUCTORS AND CABLES | 26 05 19-001-01 ELECTRICAL POWER CONDUCTORS AND CABLES - Product Data for Additional Manufacturers | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-24 | 2020-02-24 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04290 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-02-24 | Submittal Number: 26 05 19-1.1 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: ELECTRICAL POWER CONDUCTORS AND CABLES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA FOR ELECTRICAL WIRES, CABLES AND CONNECTORS. Spec Section: 26 05 19 - ELECTRICAL POWER CONDUCTORS AND CABLES Status: OPEN | Info Exchange
| 05939 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-17 | Submittal Number: 26 05 19-1.1 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: ELECTRICAL POWER CONDUCTORS AND CABLES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA FOR ELECTRICAL WIRES, CABLES AND CONNECTORS. Spec Section: 26 05 19 - ELECTRICAL POWER CONDUCTORS AND CABLES Status: OPEN | Info Exchange
| 05940 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-17 | Submittal Number: 26 05 19-1.1 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: ELECTRICAL POWER CONDUCTORS AND CABLES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA FOR ELECTRICAL WIRES, CABLES AND CONNECTORS. Spec Section: 26 05 19 - ELECTRICAL POWER CONDUCTORS AND CABLES Status: OPEN | Info Exchange
| 04474 | Review Response | Approved as Noted | 2020-02-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| 06167 | Responded and Closed | Approved as Noted | 2020-02-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-10 |  | 26 05 43-5.1 Underground Ducts, Raceways, and Manholes Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 26 05 43-5.1 Underground Ducts, Raceways, and Manholes Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 26 05 19-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-09 02:00 |  | 26 05 19-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-24 02:00 |  | 26 05 19-1.1 Product Data for Additional Manufacturers-MAM-ME_POP.pdf
26 05 19-002-00 | 26 05 19 - ELECTRICAL POWER CONDUCTORS AND CABLES | 26 05 19-002-00 ELECTRICAL POWER CONDUCTORS AND CABLES - Cord Reel PD | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-17 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-31 | 2020-08-03 | 18 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-08-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07002 | Received | For Review | 2020-07-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-31 | Submittal Number: 26 05 19-2.0 From: PATRICK KLEIN Final Due Date: 07/30/20 Subject: ELECTRICAL POWER CONDUCTORS AND CABLES - CORD REEL PD Description: Spec Section: 26 05 19 - ELECTRICAL POWER CONDUCTORS AND CABLES Status: OPEN | Info Exchange
| 09379 | Forwarded | For Review | 2020-07-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-23 | Submittal Number: 26 05 19-2.0 From: PATRICK KLEIN Final Due Date: 07/30/20 Subject: ELECTRICAL POWER CONDUCTORS AND CABLES - CORD REEL PD Description: Spec Section: 26 05 19 - ELECTRICAL POWER CONDUCTORS AND CABLES Status: OPEN | Info Exchange
| 07315 | Review Response | Approved as Noted | 2020-07-23 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Mark Lievens ME Engineers 2020.07.23 | Info Exchange
| 09754 | Responded and Closed | Approved as Noted | 2020-08-03 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-16 |  | 26 05 19-2.0 Cord Reel PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-16 |  | 26 05 19-2.0 Cord Reel PD-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-16 |  | 26 05 19-2.0 Cord Reel PD-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-08-03 |  | 26 05 19-2.0 Cord Reel PD-MAM-ME_POP.pdf
26 05 26-001-00 | 26 05 26 - GROUNDING AND BONDING | 26 05 26-001-00 GROUNDING AND BONDING - Product Data, Wiring Diagrams, and Riser Diagrams | Closed | Electrical, Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Abby Harrison (ME Engineers) |  |  |  | 2019-12-10 | 2019-12-16 | 29 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2019-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03237 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-12-10 | Submittal Number: 26 05 26-1.0 From: PATRICK KLEIN Final Due Date: 12/02/19 Subject: GROUNDING AND BONDING - PRODUCT DATA, WIRING DIAGRAMS, AND RISER DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON GROUNDING AND BONDING PRODUCTS AND ASSOCIATED ACCESSORIES. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL GROUNDING AND BONDING WORK WHICH INDICATES LAYOUT OF GROUND RODS, LOCATION OF SYSTEM GROUNDING ELECTRODE CONNECTIONS, ROUTING OF GROUNDING ELECTRODE CONDUCTORS, ALSO INCLUDE DIAGRAMS FOR CIRCUITS AND EQUIPMENT GROUNDING CONNECTIONS. SUBMIT GROUND RISER DIAGRAM FOR ENTIRE PROJECT. SHOW BUS BARS WITH TRANSFORMER GROUND ELECTRODE CONDUCTORS, ETC. Spec Section: 26 05 26 - GROUNDING AND BONDING Status: OPEN | Info Exchange
| 04675 | Forwarded | For Review | 2019-11-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-25 | Submittal Number: 26 05 26-1.0 From: PATRICK KLEIN Final Due Date: 12/02/19 Subject: GROUNDING AND BONDING - PRODUCT DATA, WIRING DIAGRAMS, AND RISER DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON GROUNDING AND BONDING PRODUCTS AND ASSOCIATED ACCESSORIES. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL GROUNDING AND BONDING WORK WHICH INDICATES LAYOUT OF GROUND RODS, LOCATION OF SYSTEM GROUNDING ELECTRODE CONNECTIONS, ROUTING OF GROUNDING ELECTRODE CONDUCTORS, ALSO INCLUDE DIAGRAMS FOR CIRCUITS AND EQUIPMENT GROUNDING CONNECTIONS. SUBMIT GROUND RISER DIAGRAM FOR ENTIRE PROJECT. SHOW BUS BARS WITH TRANSFORMER GROUND ELECTRODE CONDUCTORS, ETC. Spec Section: 26 05 26 - GROUNDING AND BONDING Status: OPEN | Info Exchange
| 03434 | Review Response | Approved as Noted/Resubmit | 2019-12-02 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.12.02 | Info Exchange
| 04906 | Forwarded | For Review | 2019-12-02 | Josh Dobken (Populous) | Abby Harrison (ME Engineers) | 2019-12-09 | Submittal Number: 26 05 26-1.0 From: PATRICK KLEIN Final Due Date: 12/02/19 Subject: GROUNDING AND BONDING - PRODUCT DATA, WIRING DIAGRAMS, AND RISER DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON GROUNDING AND BONDING PRODUCTS AND ASSOCIATED ACCESSORIES. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL GROUNDING AND BONDING WORK WHICH INDICATES LAYOUT OF GROUND RODS, LOCATION OF SYSTEM GROUNDING ELECTRODE CONNECTIONS, ROUTING OF GROUNDING ELECTRODE CONDUCTORS, ALSO INCLUDE DIAGRAMS FOR CIRCUITS AND EQUIPMENT GROUNDING CONNECTIONS. SUBMIT GROUND RISER DIAGRAM FOR ENTIRE PROJECT. SHOW BUS BARS WITH TRANSFORMER GROUND ELECTRODE CONDUCTORS, ETC. Spec Section: 26 05 26 - GROUNDING AND BONDING Status: OPEN | Info Exchange
| 03649 | Review Response | Approved as Noted/Resubmit | 2019-12-15 | Abby Harrison (ME Engineers) | Josh Dobken (Populous) |  | See attached for Technology review of submittal as well as electrical review. | Info Exchange
| 05162 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-16 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.12.02 Response (Approved as Noted/Resubmit) from: Abby Harrison (ME Engineers) Remarks: See attached for Technology review of submittal as well as electrical review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-18 |  | 26 05 26-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-18 |  | 26 05 26-1.0 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-11-17 02:00 |  | 26 05 26-1.0 Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-17 02:00 |  | 26 05 26-1.0 Product Data-MAM.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2019-11-17 02:00 |  | 26 05 26-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-16 02:00 |  | 26 05 26-1.0 Product Data-MAM-ME_POP.pdf
26 05 26-001-01 | 26 05 26 - GROUNDING AND BONDING | 26 05 26-001-01 GROUNDING AND BONDING - Product Data for Additional Manufacturers | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-24 | 2020-02-24 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04291 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-02-24 | Submittal Number: 26 05 26-1.1 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: GROUNDING AND BONDING - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON GROUNDING AND BONDING PRODUCTS AND ASSOCIATED ACCESSORIES. Spec Section: 26 05 26 - GROUNDING AND BONDING Status: OPEN | Info Exchange
| 05941 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-17 | Submittal Number: 26 05 26-1.1 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: GROUNDING AND BONDING - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON GROUNDING AND BONDING PRODUCTS AND ASSOCIATED ACCESSORIES. Spec Section: 26 05 26 - GROUNDING AND BONDING Status: OPEN | Info Exchange
| 04475 | Review Response | Approved as Noted | 2020-02-21 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| 06168 | Responded and Closed | Approved as Noted | 2020-02-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-10 |  | 26 05 26-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 26 05 26-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-09 02:00 |  | 26 05 26-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-24 02:00 |  | 26 05 26-1.1 Product Data for Additional Manufacturers-MAM-ME_POP.pdf
26 05 29-001-00 | 26 05 29 - HANGERS AND SUPPORTS | 26 05 29-001-00 HANGERS AND SUPPORTS - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-07 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-11-21 | 2019-11-20 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03110 | Received | For Review | 2019-11-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-11-21 | Submittal Number: 26 05 29-1.0 From: PATRICK KLEIN Final Due Date: 11/21/19 Subject: HANGERS AND SUPPORTS - PRODUCT DATA Description: GENERAL : SUBMIT THE FOLLOWING IN ACCORDANCE WITH CONDITIONS OF CONTRACT AND DIVISION 1 SPECIFICATION SECTIONS. PRODUCT DATA FOR EACH TYPE OF PRODUCT SPECIFIED. 1. HANGER AND SUPPORT SCHEDULE SHOWING MANUFACTURERS FIGURE NUMBER, SIZE, SPACING, FEATURES, AND APPLICATION FOR EACH REQUIRED TYPE OF HANGER, SUPPORT, SLEEVE, SEAL, AND FASTENER TO BE USED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 04513 | Forwarded | For Review | 2019-11-07 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-14 | Submittal Number: 26 05 29-1.0 From: PATRICK KLEIN Final Due Date: 11/21/19 Subject: HANGERS AND SUPPORTS - PRODUCT DATA Description: GENERAL : SUBMIT THE FOLLOWING IN ACCORDANCE WITH CONDITIONS OF CONTRACT AND DIVISION 1 SPECIFICATION SECTIONS. PRODUCT DATA FOR EACH TYPE OF PRODUCT SPECIFIED. 1. HANGER AND SUPPORT SCHEDULE SHOWING MANUFACTURERS FIGURE NUMBER, SIZE, SPACING, FEATURES, AND APPLICATION FOR EACH REQUIRED TYPE OF HANGER, SUPPORT, SLEEVE, SEAL, AND FASTENER TO BE USED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 03289 | Review Response | Approved as Noted | 2019-11-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2019.11.20 | Info Exchange
| 04740 | Responded and Closed | Approved as Noted | 2019-11-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2019.11.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-07 |  | 26 05 29-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-07 |  | 26 05 29-1.0 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-11-06 02:00 |  | 26 05 29-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-20 02:00 |  | 26 05 29-1.0 Product Data-MAM-ME Review_POP.pdf
26 05 29-001-01 | 26 05 29 - HANGERS AND SUPPORTS | 26 05 29-001-01 HANGERS AND SUPPORTS - Product Data for Additional Manufacturers | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-20 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-05 | 2020-03-04 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-03-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04423 | Received | For Review | 2020-02-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-03-05 | Submittal Number: 26 05 29-1.1 From: PATRICK KLEIN Final Due Date: 03/10/20 Subject: HANGERS AND SUPPORTS - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: GENERAL : SUBMIT THE FOLLOWING IN ACCORDANCE WITH CONDITIONS OF CONTRACT AND DIVISION 1 SPECIFICATION SECTIONS. PRODUCT DATA FOR EACH TYPE OF PRODUCT SPECIFIED. 1. HANGER AND SUPPORT SCHEDULE SHOWING MANUFACTURERS FIGURE NUMBER, SIZE, SPACING, FEATURES, AND APPLICATION FOR EACH REQUIRED TYPE OF HANGER, SUPPORT, SLEEVE, SEAL, AND FASTENER TO BE USED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 06107 | Forwarded | For Review | 2020-02-20 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-27 | Submittal Number: 26 05 29-1.1 From: PATRICK KLEIN Final Due Date: 03/10/20 Subject: HANGERS AND SUPPORTS - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: GENERAL : SUBMIT THE FOLLOWING IN ACCORDANCE WITH CONDITIONS OF CONTRACT AND DIVISION 1 SPECIFICATION SECTIONS. PRODUCT DATA FOR EACH TYPE OF PRODUCT SPECIFIED. 1. HANGER AND SUPPORT SCHEDULE SHOWING MANUFACTURERS FIGURE NUMBER, SIZE, SPACING, FEATURES, AND APPLICATION FOR EACH REQUIRED TYPE OF HANGER, SUPPORT, SLEEVE, SEAL, AND FASTENER TO BE USED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 04644 | Review Response | Approved as Noted | 2020-03-04 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.04 | Info Exchange
| 06383 | Responded and Closed | Approved as Noted | 2020-03-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-19 |  | 26 05 29-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-19 |  | 26 05 29-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-18 02:00 |  | 26 05 29-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-04 02:00 |  | 26 05 29-1.1 Product Data for Additional Manufacturers-MAM-ME_POP.pdf
26 05 29-001-02 | 26 05 29 - HANGERS AND SUPPORTS | 26 05 29-001-02 Hangers and Supports | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-15 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-29 | 2020-07-28 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06978 | Received | For Review | 2020-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-29 | Submittal Number: 26 05 29-1.2 From: ALYSSA SANDOVAL Final Due Date: 07/29/20 Subject: HANGERS AND SUPPORTS Description: Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 09344 | Forwarded | For Review | 2020-07-15 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-22 | Submittal Number: 26 05 29-1.2 From: ALYSSA SANDOVAL Final Due Date: 07/29/20 Subject: HANGERS AND SUPPORTS Description: Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 07216 | Review Response | Approved as Noted | 2020-07-27 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.27 | Info Exchange
| 09628 | Responded and Closed | Approved as Noted | 2020-07-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Ryan Crookston (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-15 |  | 26 05 29-1.2 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-15 |  | 26 05 29-1.2 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-14 02:00 |  | 26 05 29-1.2 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-28 02:00 |  | 26 05 29-1.2 Product Data-MAM-ME_pop.pdf
26 05 29-002-00 | 26 05 29 - HANGERS AND SUPPORTS | 26 05 29-002-00: HANGERS AND SUPPORTS - Shop Drawings | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-05 | Responded and Closed - Rejected |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-19 | 2019-12-23 | 19 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-12-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03518 | Received | For Review | 2019-12-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-12-19 | Submittal Number: 26 05 29-2.0 From: PATRICK KLEIN Final Due Date: 12/18/19 Subject: HANGERS AND SUPPORTS - SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING DETAILS OF FABRICATED PRODUCTS AND MATERIALS. ENGINEERED DESIGN CONSISTING OF DETAILS AND ENGINEERING ANALYSIS FOR SUPPORTS FOR THE FOLLOWINGITEMS : 1. CABLE TRAY. 2. CONDUIT (RACKED) 3. CEILING-MOUNTED BOXES, TRANSFORMERS. 4. CONDUIT - CEILING MOUNTED, CONCRETE ENCASED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 04984 | Forwarded | For Review | 2019-12-05 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-12 | Submittal Number: 26 05 29-2.0 From: PATRICK KLEIN Final Due Date: 12/18/19 Subject: HANGERS AND SUPPORTS - SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING DETAILS OF FABRICATED PRODUCTS AND MATERIALS. ENGINEERED DESIGN CONSISTING OF DETAILS AND ENGINEERING ANALYSIS FOR SUPPORTS FOR THE FOLLOWINGITEMS : 1. CABLE TRAY. 2. CONDUIT (RACKED) 3. CEILING-MOUNTED BOXES, TRANSFORMERS. 4. CONDUIT - CEILING MOUNTED, CONCRETE ENCASED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 03660 | Review Response | Approved as Noted/Resubmit | 2019-12-17 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Please note that this submittal shall be reviewed by structural before being returned to Mortenson as there is information regarding additional point loads being added to roof trusses. Mark Lievens ME Engineers 2019.12.17 | Info Exchange
| 05180 | Forwarded | For Review | 2019-12-17 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2019-12-19 | Submittal Number: 26 05 29-2.0 From: PATRICK KLEIN Final Due Date: 12/18/19 Subject: HANGERS AND SUPPORTS - SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING DETAILS OF FABRICATED PRODUCTS AND MATERIALS. ENGINEERED DESIGN CONSISTING OF DETAILS AND ENGINEERING ANALYSIS FOR SUPPORTS FOR THE FOLLOWINGITEMS : 1. CABLE TRAY. 2. CONDUIT (RACKED) 3. CEILING-MOUNTED BOXES, TRANSFORMERS. 4. CONDUIT - CEILING MOUNTED, CONCRETE ENCASED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 03737 | Review Response | Rejected | 2019-12-20 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | See summary comments on page 7 of submittal. | Info Exchange
| 05268 | Responded and Closed | Rejected | 2019-12-23 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Submittal rejected based on TT comments provided. Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Please note that this submittal shall be reviewed by structural before being returned to Mortenson as there is information regarding additional point loads being added to roof trusses. Mark Lievens ME Engineers 2019.12.17 Response (Rejected) from: Franz Kogler (Thornton Tomasetti) Remarks: See summary comments on page 7 of submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-04 02:00 |  | 26 05 29-2.0 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-04 02:00 |  | 26 05 29-2.0 Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-12-04 02:00 |  | 26 05 29-2.0 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-04 02:00 |  | 26 05 29-2.0 Shop Drawings-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-12-04 02:00 |  | 26 05 29-2.0 Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-23 02:00 |  | 26 05 29-2.0 Shop Drawings-MAM-ME_TTReview_POP.pdf
26 05 29-002-01 | 26 05 29 - HANGERS AND SUPPORTS | 26 05 29-002-01 HANGERS AND SUPPORTS - Riser Conduit Shop Drawings | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-06 | Review Response - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2020-01-20 | 2020-01-20 | 15 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03800 | Received | For Review | 2020-01-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-20 | Submittal Number: 26 05 29-2.1 From: PATRICK KLEIN Final Due Date: 01/20/20 Subject: HANGERS AND SUPPORTS - RISER CONDUIT SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING DETAILS OF FABRICATED PRODUCTS AND MATERIALS. ENGINEERED DESIGN CONSISTING OF DETAILS AND ENGINEERING ANALYSIS FOR SUPPORTS FOR THE FOLLOWINGITEMS : 1. CABLE TRAY. 2. CONDUIT (RACKED) 3. CEILING-MOUNTED BOXES, TRANSFORMERS. 4. CONDUIT - CEILING MOUNTED, CONCRETE ENCASED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 05338 | Forwarded | For Review | 2020-01-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-13 | Submittal Number: 26 05 29-2.1 From: PATRICK KLEIN Final Due Date: 01/20/20 Subject: HANGERS AND SUPPORTS - RISER CONDUIT SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING DETAILS OF FABRICATED PRODUCTS AND MATERIALS. ENGINEERED DESIGN CONSISTING OF DETAILS AND ENGINEERING ANALYSIS FOR SUPPORTS FOR THE FOLLOWINGITEMS : 1. CABLE TRAY. 2. CONDUIT (RACKED) 3. CEILING-MOUNTED BOXES, TRANSFORMERS. 4. CONDUIT - CEILING MOUNTED, CONCRETE ENCASED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 05476 | Forwarded | For Review | 2020-01-14 | Josh Dobken (Populous) | Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) | 2020-01-20 | Submittal Number: 26 05 29-2.1 From: PATRICK KLEIN Final Due Date: 01/20/20 Subject: HANGERS AND SUPPORTS - RISER CONDUIT SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING DETAILS OF FABRICATED PRODUCTS AND MATERIALS. ENGINEERED DESIGN CONSISTING OF DETAILS AND ENGINEERING ANALYSIS FOR SUPPORTS FOR THE FOLLOWINGITEMS : 1. CABLE TRAY. 2. CONDUIT (RACKED) 3. CEILING-MOUNTED BOXES, TRANSFORMERS. 4. CONDUIT - CEILING MOUNTED, CONCRETE ENCASED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 03992 | Review Response | Approved as Noted | 2020-01-20 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached submittal comments. Submit Quad A layout for review and approval. | Info Exchange
| 05571 | Responded and Closed | Approved as Noted | 2020-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attached submittal comments. Submit Quad A layout for review and approval. | Info Exchange
| 04039 | Review Response | Approved as Noted | 2020-01-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. I believe this might have already been sent back to Mortenson. If so, there's nothing further that needs to be done with this submittal as my review defers to TT's comments. Thanks, Mark Lievens ME Engineers 2020.01.23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-06 |  | 26 05 29-2.1 Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-06 |  | 26 05 29-2.1 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-05 02:00 |  | 26 05 29-2.1 Shop Drawings-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-01-21 02:00 |  | 26 05 29-2.1 Shop Drawings-MAM_TTReview.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-20 02:00 |  | 26 05 29-2.1 Shop Drawings-MAM_TTReview_POP.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-05 02:00 |  | 26 05 29-2.1 Shop Drawings-MAM.pdf
26 05 29-002-02 | 26 05 29 - HANGERS AND SUPPORTS | 26 05 29-002-02 HANGERS AND SUPPORTS - Riser Conduit Shop Drawings | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-14 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-28 | 2020-03-10 | 26 |  | Record Copies; Transfers; Submittals |  | 25 |  | 2020-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04352 | Received | For Review | 2020-02-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-02-28 | Submittal Number: 26 05 29-2.2 From: SIMRAN GEORGE Final Due Date: 03/27/20 Subject: HANGERS AND SUPPORTS - RISER CONDUIT SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING DETAILS OF FABRICATED PRODUCTS AND MATERIALS. ENGINEERED DESIGN CONSISTING OF DETAILS AND ENGINEERING ANALYSIS FOR SUPPORTS FOR THE FOLLOWINGITEMS : 1. CABLE TRAY. 2. CONDUIT (RACKED) 3. CEILING-MOUNTED BOXES, TRANSFORMERS. 4. CONDUIT - CEILING MOUNTED, CONCRETE ENCASED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 06023 | Forwarded | For Review | 2020-02-14 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-21 | Submittal Number: 26 05 29-2.2 From: SIMRAN GEORGE Final Due Date: 03/27/20 Subject: HANGERS AND SUPPORTS - RISER CONDUIT SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING DETAILS OF FABRICATED PRODUCTS AND MATERIALS. ENGINEERED DESIGN CONSISTING OF DETAILS AND ENGINEERING ANALYSIS FOR SUPPORTS FOR THE FOLLOWINGITEMS : 1. CABLE TRAY. 2. CONDUIT (RACKED) 3. CEILING-MOUNTED BOXES, TRANSFORMERS. 4. CONDUIT - CEILING MOUNTED, CONCRETE ENCASED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 04526 | Review Response | Approved as Noted | 2020-02-26 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | See the attached submittal review. Please note - this submittal shall be sent to TT for review. Thank you, Mark Lievens ME Engineers 2020.02.26 | Info Exchange
| 06231 | Forwarded | For Review | 2020-02-26 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-02-28 | Submittal Number: 26 05 29-2.2 From: SIMRAN GEORGE Final Due Date: 03/27/20 Subject: HANGERS AND SUPPORTS - RISER CONDUIT SHOP DRAWINGS Description: SHOP DRAWINGS INDICATING DETAILS OF FABRICATED PRODUCTS AND MATERIALS. ENGINEERED DESIGN CONSISTING OF DETAILS AND ENGINEERING ANALYSIS FOR SUPPORTS FOR THE FOLLOWINGITEMS : 1. CABLE TRAY. 2. CONDUIT (RACKED) 3. CEILING-MOUNTED BOXES, TRANSFORMERS. 4. CONDUIT - CEILING MOUNTED, CONCRETE ENCASED. Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Email
| 04742 | Review Response | Approved as Noted | 2020-03-09 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | See comments on Submittal. | Info Exchange
| 06514 | Responded and Closed | Approved as Noted | 2020-03-10 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: See the attached submittal review. Please note - this submittal shall be sent to TT for review. Thank you, Mark Lievens ME Engineers 2020.02.26 Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments on Submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-13 |  | 26 05 29-2.2 Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-13 |  | 26 05 29-2.2 Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-12 02:00 |  | 26 05 29-2.2 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-12 02:00 |  | 26 05 29-2.2 Shop Drawings-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-02-12 02:00 |  | 26 05 29-2.2 Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-10 02:00 |  | 26 05 29-2.2 Shop Drawings-MAM-ME_TTReview_POP.pdf
26 05 29-005-00 | 26 05 29 - HANGERS AND SUPPORTS | 26 05 29-005-00 HANGERS AND SUPPORTS - Shop Drawings Event and Mech Mezz Area D | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-17 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-31 | 2020-02-18 | 33 |  | Record Copies; Transfers; Submittals | 26 05 29-005-01 - 26 05 29-005-00 HANGERS AND SUPPORTS - Shop Drawings Event and Mech Mezz Area D | 33 |  | 2020-02-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03969 | Received | For Review | 2020-01-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-31 | Submittal Number: 26 05 29-5.0 From: PATRICK KLEIN Final Due Date: 01/31/20 Subject: HANGERS AND SUPPORTS - SHOP DRAWINGS EVENT AND MECH MEZZ AREA D Description: Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 05538 | Forwarded | For Review | 2020-01-17 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-24 | Submittal Number: 26 05 29-5.0 From: PATRICK KLEIN Final Due Date: 01/31/20 Subject: HANGERS AND SUPPORTS - SHOP DRAWINGS EVENT AND MECH MEZZ AREA D Description: Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 04178 | Review Response | Approved as Noted | 2020-01-31 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.01.31 | Info Exchange
| 05791 | Forwarded | For Review | 2020-02-03 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2020-01-31 | Submittal Number: 26 05 29-5.0 From: PATRICK KLEIN Final Due Date: 01/31/20 Subject: HANGERS AND SUPPORTS - SHOP DRAWINGS EVENT AND MECH MEZZ AREA D Description: Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Email
| 05885 | Forwarded | For Review | 2020-02-06 | Josh Dobken (Populous) | Matt Ross (Thornton Tomasetti) | 2020-01-31 | Submittal Number: 26 05 29-5.0 From: PATRICK KLEIN Final Due Date: 01/31/20 Subject: HANGERS AND SUPPORTS - SHOP DRAWINGS EVENT AND MECH MEZZ AREA D Description: Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 04393 | Review Response | Approved as Noted/Resubmit | 2020-02-18 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Provide reactions (specify factored/unfactored) at all hanger points on plan and locations of all attachment points. | Info Exchange
| 06073 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.01.31 Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Provide reactions (specify factored/unfactored) at all hanger points on plan and locations of all attachment points. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-16 |  | 26 05 29-5.0 Shop Drawings Event and Mech Mezz Area D-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-16 |  | 26 05 29-5.0 Shop Drawings Event and Mech Mezz Area D-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-15 02:00 |  | 26 05 29-5.0 Shop Drawings Event and Mech Mezz Area D-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-15 02:00 |  | 26 05 29-5.0 Shop Drawings Event and Mech Mezz Area D-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-01-15 02:00 |  | 26 05 29-5.0 Shop Drawings Event and Mech Mezz Area D-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-01-15 02:00 |  | 26 05 29-5.0 Shop Drawings Event and Mech Mezz Area D-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-18 02:00 |  | 26 05 29-5.0 Shop Drawings Event and Mech Mezz Area D-MAM-ME_TT REVIEW_POP.pdf
26 05 29-005-01 | 26 05 29 - HANGERS AND SUPPORTS | 26 05 29-005-00 HANGERS AND SUPPORTS - Shop Drawings Event and Mech Mezz Area D | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 05 29-005-00 - 26 05 29-005-00 HANGERS AND SUPPORTS - Shop Drawings Event and Mech Mezz Area D | -1 | 2020-03-03
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-18 02:00 |  | 26 05 29-5.0 Shop Drawings Event and Mech Mezz Area D-MAM-ME_TT REVIEW_POP.pdf
26 05 29-007-00 | 26 05 29 - HANGERS AND SUPPORTS | 26 05 29-007-00 HANGERS AND SUPPORTS - Atrium Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-06 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-20 | 2020-08-25 | 20 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-08-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07420 | Received | For Review | 2020-08-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-20 | Submittal Number: 26 05 29-7.0 From: PATRICK KLEIN Final Due Date: 08/20/20 Subject: HANGERS AND SUPPORTS - ATRIUM PRODUCT DATA Description: Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 09885 | Forwarded | For Review | 2020-08-06 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-13 | Submittal Number: 26 05 29-7.0 From: PATRICK KLEIN Final Due Date: 08/20/20 Subject: HANGERS AND SUPPORTS - ATRIUM PRODUCT DATA Description: Spec Section: 26 05 29 - HANGERS AND SUPPORTS Status: OPEN | Info Exchange
| 07737 | Review Response | Approved as Noted | 2020-08-18 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.08.18 | Info Exchange
| 10299 | Responded and Closed | Approved as Noted | 2020-08-25 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.08.18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | 26 05 29-7.0 Atrium Product Data-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-06 |  | 26 05 29-7.0 Atrium Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-05 02:00 |  | 26 05 29-7.0 Atrium Product Data-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-25 02:00 |  | 26 05 29-7.0 Atrium Product Data-MAM-ME_POP.pdf
26 05 33-001-00 | 26 05 33 - RACEWAYS AND BOXES | 26 05 33-001-00 RACEWAY AND BOXES - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-07 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-11-27 | 2019-11-26 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2019-11-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03107 | Received | For Review | 2019-11-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-11-27 | Submittal Number: 26 05 33-1.0 From: PATRICK KLEIN Final Due Date: 11/21/19 Subject: RACEWAY AND BOXES - PRODUCT DATA Description: PRODUCT DATA FOR THE FOLLOWING PRODUCTS : - 1. RACEWAYS AND FITTINGS. 2. WIREWAYS AND FITTINGS. 3. BOXES AND FITTINGS. INSTALLATION INSTRUCTIONS : MANUFACTURERS WRITTEN INSTALLATION INSTRUCTIONS FOR WIREWAY, SURFACE RACEWAY, AND NONMETALLIC RACEWAY PRODUCTS. Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 04510 | Forwarded | For Review | 2019-11-07 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-14 | Submittal Number: 26 05 33-1.0 From: PATRICK KLEIN Final Due Date: 11/21/19 Subject: RACEWAY AND BOXES - PRODUCT DATA Description: PRODUCT DATA FOR THE FOLLOWING PRODUCTS : - 1. RACEWAYS AND FITTINGS. 2. WIREWAYS AND FITTINGS. 3. BOXES AND FITTINGS. INSTALLATION INSTRUCTIONS : MANUFACTURERS WRITTEN INSTALLATION INSTRUCTIONS FOR WIREWAY, SURFACE RACEWAY, AND NONMETALLIC RACEWAY PRODUCTS. Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 03387 | Review Response | Approved as Noted/Resubmit | 2019-11-22 | Abby Harrison (ME Engineers) | Shaina Burris (Populous) |  | See attached for submittal reviews of 26 05 33 and 27 05 33. | Info Exchange
| 03388 | Review Response | Revise and Resubmit | 2019-11-26 | Abby Harrison (ME Engineers) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attached for ME Electrical (26 05 33) and Technology (27 05 33) submittal reviews. | Info Exchange
| 04852 | Responded and Closed | Revise and Resubmit | 2019-11-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Abby Harrison (ME Engineers) Remarks: See attached for ME Electrical (26 05 33) and Technology (27 05 33) submittal reviews. Submittal Approved as Noted for Division 26. Revise and Resubmit as indicated in Division 27. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-07 |  | 26 27 05 33-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-07 |  | 26 27 05 33-1.0 Product Data-MAM.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2019-11-22 02:00 |  | Submittal Review Form-26 05 33-1.0.doc
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2019-11-22 02:00 |  | Submittal.Review.Form-27 05 33.docx
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2019-11-26 02:00 |  | 26 27 05 33-1.0 Product Data-MAM - ME Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-26 02:00 |  | 26 27 05 33-1.0 Product Data-MAM - ME Review_POP.pdf
26 05 33-001-01 | 26 05 33 - RACEWAYS AND BOXES | 26 05 33-001-01 RACEWAY AND BOXES - Product Data for Additional Manufacturers | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-24 | 2020-02-24 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04294 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-02-24 | Submittal Number: 26 05 33-1.1 From: PATRICK KLEIN Final Due Date: 02/28/20 Subject: RACEWAY AND BOXES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA FOR THE FOLLOWING PRODUCTS : - 1. RACEWAYS AND FITTINGS. 2. WIREWAYS AND FITTINGS. 3. BOXES AND FITTINGS. INSTALLATION INSTRUCTIONS : MANUFACTURERS WRITTEN INSTALLATION INSTRUCTIONS FOR WIREWAY, SURFACE RACEWAY, AND NONMETALLIC RACEWAY PRODUCTS. Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 05944 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-17 | Submittal Number: 26 05 33-1.1 From: PATRICK KLEIN Final Due Date: 02/28/20 Subject: RACEWAY AND BOXES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA FOR THE FOLLOWING PRODUCTS : - 1. RACEWAYS AND FITTINGS. 2. WIREWAYS AND FITTINGS. 3. BOXES AND FITTINGS. INSTALLATION INSTRUCTIONS : MANUFACTURERS WRITTEN INSTALLATION INSTRUCTIONS FOR WIREWAY, SURFACE RACEWAY, AND NONMETALLIC RACEWAY PRODUCTS. Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 05945 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-17 | Submittal Number: 26 05 33-1.1 From: PATRICK KLEIN Final Due Date: 02/28/20 Subject: RACEWAY AND BOXES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA FOR THE FOLLOWING PRODUCTS : - 1. RACEWAYS AND FITTINGS. 2. WIREWAYS AND FITTINGS. 3. BOXES AND FITTINGS. INSTALLATION INSTRUCTIONS : MANUFACTURERS WRITTEN INSTALLATION INSTRUCTIONS FOR WIREWAY, SURFACE RACEWAY, AND NONMETALLIC RACEWAY PRODUCTS. Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 05992 | Forwarded | For Review | 2020-02-12 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-19 | Submittal Number: 26 05 33-1.1 From: PATRICK KLEIN Final Due Date: 02/28/20 Subject: RACEWAY AND BOXES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA FOR THE FOLLOWING PRODUCTS : - 1. RACEWAYS AND FITTINGS. 2. WIREWAYS AND FITTINGS. 3. BOXES AND FITTINGS. INSTALLATION INSTRUCTIONS : MANUFACTURERS WRITTEN INSTALLATION INSTRUCTIONS FOR WIREWAY, SURFACE RACEWAY, AND NONMETALLIC RACEWAY PRODUCTS. Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 04476 | Review Response | Approved as Noted | 2020-02-21 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| 06169 | Responded and Closed | Approved as Noted | 2020-02-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-10 |  | 26 05 33-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 26 05 33-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 26 05 33-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-09 02:00 |  | 26 05 33-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-09 02:00 |  | 26 05 33-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-24 02:00 |  | 26 05 33-1.1 Product Data for Additional Manufacturers-MAM-ME_POP.pdf
26 05 33-001-02 | 26 05 33 - RACEWAYS AND BOXES | 26 05 33-001-02 RACEWAY AND BOXES - Product Data for Additional Manufacturers | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-12 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-26 | 2020-03-18 | 7 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04775 | Received | For Review | 2020-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-03-26 | Submittal Number: 26 05 33-1.2 From: PATRICK KLEIN Final Due Date: 03/25/20 Subject: RACEWAY AND BOXES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA FOR THE FOLLOWING PRODUCTS : - 1. RACEWAYS AND FITTINGS. 2. WIREWAYS AND FITTINGS. 3. BOXES AND FITTINGS. INSTALLATION INSTRUCTIONS : MANUFACTURERS WRITTEN INSTALLATION INSTRUCTIONS FOR WIREWAY, SURFACE RACEWAY, AND NONMETALLIC RACEWAY PRODUCTS. Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 06550 | Forwarded | For Review | 2020-03-12 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-19 | Submittal Number: 26 05 33-1.2 From: PATRICK KLEIN Final Due Date: 03/25/20 Subject: RACEWAY AND BOXES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA FOR THE FOLLOWING PRODUCTS : - 1. RACEWAYS AND FITTINGS. 2. WIREWAYS AND FITTINGS. 3. BOXES AND FITTINGS. INSTALLATION INSTRUCTIONS : MANUFACTURERS WRITTEN INSTALLATION INSTRUCTIONS FOR WIREWAY, SURFACE RACEWAY, AND NONMETALLIC RACEWAY PRODUCTS. Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 04931 | Review Response | Approved as Noted | 2020-03-14 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.14 | Info Exchange
| 06727 | Responded and Closed | Approved as Noted | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 26 05 33-1.2 Product Data for Additional Manufacturers-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-11 |  | 26 05 33-1.2 Product Data for Additional Manufacturers-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-10 02:00 |  | 26 05 33-1.2 Product Data for Additional Manufacturers-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-18 02:00 |  | 26 05 33-1.2 Product Data for Additional Manufacturers-MAM-ME_POP.pdf
26 05 33-001-04 | 26 05 33 - RACEWAYS AND BOXES | 26 05 33-001-04 Raceway and Boxes | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-15 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-29 | 2020-08-06 | 23 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06979 | Received | For Review | 2020-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-29 | Submittal Number: 26 05 33-1.4 From: ALYSSA SANDOVAL Final Due Date: 07/29/20 Subject: RACEWAY AND BOXES Description: Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 09345 | Forwarded | For Review | 2020-07-15 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-22 | Submittal Number: 26 05 33-1.4 From: ALYSSA SANDOVAL Final Due Date: 07/29/20 Subject: RACEWAY AND BOXES Description: Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 07422 | Review Response | Approved as Noted | 2020-07-28 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.28 | Info Exchange
| 09895 | Responded and Closed | Approved as Noted | 2020-08-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-15 |  | 26 05 33-1.03 Accessories Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-15 |  | 26 05 33-1.03 Accessories Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-14 02:00 |  | 26 05 33-1.03 Accessories Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-06 02:00 |  | 260533-1.03 SCA Accessories Product Electrical Data_ME Review_pop.pdf
26 05 33-003-00 | 26 05 33 - RACEWAYS AND BOXES | 26 05 33-003-00 6000 Series Wiremold Product Data | Closed | Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-18 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Kuebler Perry (Populous) |  |  |  | 2020-04-01 | 2020-04-06 | 20 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-04-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04902 | Received | For Review | 2020-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-01 | Submittal Number: 26 05 33-3.0 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: 6000 SERIES WIREMOLD PRODUCT DATA Description: Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 06695 | Forwarded | For Review | 2020-03-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-25 | Submittal Number: 26 05 33-3.0 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: 6000 SERIES WIREMOLD PRODUCT DATA Description: Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 05211 | Review Response | Approved as Noted | 2020-04-03 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.03 | Info Exchange
| 07083 | Forwarded | For Review | 2020-04-03 | Josh Dobken (Populous) | Bryan Klote (Populous); Kuebler Perry (Populous) | 2020-04-01 | Submittal Number: 26 05 33-3.0 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: 6000 SERIES WIREMOLD PRODUCT DATA Description: Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Email
| 07097 | Responded and Closed | Approved as Noted | 2020-04-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-17 |  | 26 05 33-3.0 6000 Series Wiremold Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-17 |  | 26 05 33-3.0 6000 Series Wiremold Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-16 02:00 |  | 26 05 33-3.0 6000 Series Wiremold Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-16 02:00 |  | 26 05 33-3.0 6000 Series Wiremold Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-06 02:00 |  | 26 05 33-3.0 6000 Series Wiremold Product Data-MAM-ME-POP.pdf
26 05 33-004-00 | 26 05 33 - RACEWAYS AND BOXES | 26 05 33-004-00 RACEWAY AND BOXES - Riser MC Cable Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-27 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-11 | 2020-05-12 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05564 | Received | For Review | 2020-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-05-11 | Submittal Number: 26 05 33-4.0 From: PATRICK KLEIN Final Due Date: 05/08/20 Subject: RACEWAY AND BOXES - RISER MC CABLE PRODUCT DATA Description: Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 07542 | Forwarded | For Review | 2020-04-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-04 | Submittal Number: 26 05 33-4.0 From: PATRICK KLEIN Final Due Date: 05/08/20 Subject: RACEWAY AND BOXES - RISER MC CABLE PRODUCT DATA Description: Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 05830 | Review Response | Approved as Noted | 2020-05-11 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.11 | Info Exchange
| 07910 | Responded and Closed | Approved as Noted | 2020-05-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | 26 05 33-4.0 Riser MC Cable Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-24 |  | 26 05 33-4.0 Riser MC Cable Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-23 02:00 |  | 26 05 33-4.0 Riser MC Cable Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-12 02:00 |  | 26 05 33-4.0 Riser MC Cable Product Data-MAM-ME_POP.pdf
26 05 33-005-00 | 26 05 33 - RACEWAYS AND BOXES | 26 05 33-005-00 Masonry Boxes, Poke Thru Devices, and Raceway Connections | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-17 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-31 | 2020-08-03 | 18 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-08-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07003 | Received | For Review | 2020-07-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-31 | Submittal Number: 26 05 33-5.0 From: PATRICK KLEIN Final Due Date: 07/30/20 Subject: MASONRY BOXES, POKE THRU DEVICES, AND RACEWAY CONNECTIONS Description: Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 09380 | Forwarded | For Review | 2020-07-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-23 | Submittal Number: 26 05 33-5.0 From: PATRICK KLEIN Final Due Date: 07/30/20 Subject: MASONRY BOXES, POKE THRU DEVICES, AND RACEWAY CONNECTIONS Description: Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 07317 | Review Response | Approved as Noted | 2020-07-28 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.28 | Info Exchange
| 09756 | Responded and Closed | Approved as Noted | 2020-08-03 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-16 |  | 26 05 33-5.0 Masonry Boxes Poke Thru Devices and Raceway Connections-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-16 |  | 26 05 33-5.0 Masonry Boxes Poke Thru Devices and Raceway Connections-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-16 |  | 26 05 33-5.0 Masonry Boxes Poke Thru Devices and Raceway Connections-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-08-03 |  | 26 05 33-5.0 Masonry Boxes Poke Thru Devices and Raceway Connections-MAM-ME_POP.pdf
26 05 33-009-00 | 26 05 33 - RACEWAYS AND BOXES | 26 05 33-009-00 RACEWAYS AND BOXES - Floor Box | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-28 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-11 | 2020-11-09 | 13 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09057 | Received | For Review | 2020-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-11 | Submittal Number: 26 05 33-9.0 From: BINH DUONG Final Due Date: 11/10/20 Subject: RACEWAYS AND BOXES - FLOOR BOX Description: Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 11944 | Forwarded | For Review | 2020-10-28 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-04 | Submittal Number: 26 05 33-9.0 From: BINH DUONG Final Due Date: 11/10/20 Subject: RACEWAYS AND BOXES - FLOOR BOX Description: Spec Section: 26 05 33 - RACEWAY AND BOXES Status: OPEN | Info Exchange
| 09327 | Review Response | Approved | 2020-11-04 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.04 | Info Exchange
| 12308 | Responded and Closed | Approved | 2020-11-09 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Tyrone Thornton (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 26 05 33-9.0 Floor Box-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 26 05 33-9.0 Floor Box-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-26 02:00 |  | 26 05 33-9.0 Floor Box-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-09 02:00 |  | 26 05 33-9.0 Floor Box-MAM-ME_pop.pdf
26 05 43-001-00 | 26 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 26 05 43-001-00 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Product Data | Closed | Electrical, Civil, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-16 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Gareth Loveridge (Swift and Company Landscape Arch), Jarrett Grant (DCI Engineers) |  |  |  | 2019-09-06 | 2019-09-12 | 28 |  | Record Copies; Transfers; Submittals | 26 05 43-001-02 - 26 05 43-001-02 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Product Data | 19 |  | 2019-09-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02095 | Received | For Review | 2019-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-09-06 | Submittal Number: 26 05 43-1.0 From: PATRICK KLEIN Final Due Date: 08/29/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: PRODUCT DATA FOR THE FOLLOWING : ELECTRICAL AND TELECOMMUNICATION MANHOLES, DUCT SPACERS. Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 03268 | Forwarded | For Review | 2019-08-16 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-08-23 | Submittal Number: 26 05 43-1.0 From: PATRICK KLEIN Final Due Date: 08/29/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: PRODUCT DATA FOR THE FOLLOWING : ELECTRICAL AND TELECOMMUNICATION MANHOLES, DUCT SPACERS. Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 02269 | Review Response | Approved as Noted/Resubmit | 2019-08-30 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Darren Simpson (DCI Engineers); Josh Dobken (Populous); Jarrett Grant (DCI Engineers); Populous SCA_CCA |  | See the attached submittal review. Please note that a portion of this submittal requires DCI review for the SCL vaults and raceway as well as Populous/Swift's input regarding the site pull vault cover aesthetics. Thank you, Mark Lievens 2019.08.30 ME Engineers | Info Exchange
| 03491 | Forwarded | For Review | 2019-08-30 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Gareth Loveridge (Swift and Company Landscape Arch); Jarrett Grant (DCI Engineers) | 2019-09-05 | Submittal Number: 26 05 43-1.0 From: PATRICK KLEIN Final Due Date: 08/29/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: PRODUCT DATA FOR THE FOLLOWING : ELECTRICAL AND TELECOMMUNICATION MANHOLES, DUCT SPACERS. Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 02282 | Review Response | Approved as Noted | 2019-09-03 | Darren Simpson (DCI Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 03639 | Responded and Closed | Approved as Noted/Resubmit | 2019-09-12 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: See the attached submittal review. Please note that a portion of this submittal requires DCI review for the SCL vaults and raceway as well as Populous/Swift's input regarding the site pull vault cover aesthetics. Thank you, Mark Lievens 2019.08.30 ME Engineers Response (Approved as Noted) from: Darren Simpson (DCI Engineers) Remarks: Vault lids shall be non-skid in sidewalks 444-LA vault Submit Materials to SDOT - SCL From Tom Usher - Approved as noted / Resubmit No diamond plate covers, please resubmit with available non-skid manhole cover options. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-15 |  | 26 05 43-1.0 Product Data-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-08-15 |  | 26 05 43-1.0 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-08-14 02:00 |  | 26 05 43-1.0 Product Data-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-08-14 02:00 |  | 26 05 43-1.0 Product Data-MAM.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-08-14 02:00 |  | 26 05 43-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-12 02:00 |  | 26 05 43-1.0 Product Data-MAM-ME Review_DCI_POP.pdf
26 05 43-001-01 | 26 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 26 05 43-001-01 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-06 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Gareth Loveridge (Swift and Company Landscape Arch), Jarrett Grant (DCI Engineers) |  |  |  | 2019-09-20 | 2019-09-23 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2019-09-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02319 | Received | For Review | 2019-09-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; . (Seattle Arena Company, LLC) | 2019-09-20 | Submittal Number: 26 05 43-1.1 From: PATRICK KLEIN Final Due Date: 09/19/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: INCLUDE 444 VAULT PER REVISED SCL DRAWINGS Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 03551 | Forwarded | For Review | 2019-09-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-09-13 | Submittal Number: 26 05 43-1.1 From: PATRICK KLEIN Final Due Date: 09/19/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: INCLUDE 444 VAULT PER REVISED SCL DRAWINGS Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 02475 | Review Response | No Action Taken or Required | 2019-09-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please forward to DCI and Swift for review/approval. Thank you, Mark Lievens ME Engineers 2019.09.20 | Info Exchange
| 03749 | Forwarded | For Review | 2019-09-20 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Gareth Loveridge (Swift and Company Landscape Arch); Jarrett Grant (DCI Engineers) | 2019-09-20 | Submittal Number: 26 05 43-1.1 From: PATRICK KLEIN Final Due Date: 09/19/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: INCLUDE 444 VAULT PER REVISED SCL DRAWINGS Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 02484 | Review Response | Approved as Noted | 2019-09-23 | Darren Simpson (DCI Engineers) | Josh Dobken (Populous) |  | APPROVED - Note all lids within walking areas shall be non-skid. | Info Exchange
| 03760 | Responded and Closed | Approved as Noted | 2019-09-23 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Darren Simpson (DCI Engineers) Remarks: APPROVED - Note all lids within walking areas shall be non-skid. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-05 |  | 26 05 43-1.1 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-05 |  | 26 05 43-1.1 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-09-04 02:00 |  | 26 05 43-1.1 Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-04 02:00 |  | 26 05 43-1.1 Product Data-MAM.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-09-04 02:00 |  | 26 05 43-1.1 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-23 02:00 |  | 26 05 43-1.1 Product Data-MAM - ME Review_DCI_POP.pdf
26 05 43-001-02 | 26 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 26 05 43-001-02 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Product Data | Closed | Civil, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-24 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Mark Lievens (ME Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Tom Usher (Populous), Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Gareth Loveridge (Swift and Company Landscape Arch), Jarrett Grant (DCI Engineers) |  |  |  | 2019-10-09 | 2019-10-03 | 10 |  | Record Copies; Transfers; Submittals | 26 05 43-001-00 - 26 05 43-001-00 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Product Data, 26 05 43-001-03 - 26 05 43-001-03 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Product Data | 9 | 2019-09-26 | 2019-10-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02516 | Received | For Review | 2019-09-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-10-09 | Submittal Number: 26 05 43-1.2 From: PATRICK KLEIN Final Due Date: 10/09/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: INCLUDE REVISED LID COVERS PER 1.0 SUBMITTAL COMMENTS Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 03796 | Forwarded | For Review | 2019-09-25 | Josh Dobken (Populous) | Bryan Klote (Populous); Mark Lievens (ME Engineers); Rhys Van Bemmel (Swift and Company Landscape Arch); Tom Usher (Populous); Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Gareth Loveridge (Swift and Company Landscape Arch); Jarrett Gra... | 2019-10-02 | Submittal Number: 26 05 43-1.2 From: PATRICK KLEIN Final Due Date: 10/09/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: INCLUDE REVISED LID COVERS PER 1.0 SUBMITTAL COMMENTS Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 02634 | Review Response | Not Required For Review | 2019-10-02 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached review. This submittal approval is for DCI/Swift to provide. Thank you, Mark Lievens ME Engineers 2019.10.02 | Info Exchange
| 02648 | Review Response | Revise and Resubmit | 2019-10-03 | Jarrett Grant (DCI Engineers) | Josh Dobken (Populous) |  | See attached PDF for materials submittal review. | Info Exchange
| 03962 | Responded and Closed | Revise and Resubmit | 2019-10-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Jarrett Grant (DCI Engineers) Remarks: See attached PDF for materials submittal review. 712-LA vault no longer required, please submit 444-LA vault, cover types, and material/ finish options. Design team preference for covers is to use 2 round lids wherever possible as opposed to double doors. POP/jhd | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-25 02:00 |  | 26 05 43-1.2 Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-25 02:00 |  | 26 05 43-1.2 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-09-25 02:00 |  | 26 05 43-1.2 Product Data-MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2019-09-25 02:00 |  | 26 05 43-1.2 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-03 02:00 |  | 26 05 43-1.2 Product Data-MAM_DCI_POP.pdf
26 05 43-001-03 | 26 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 26 05 43-001-03 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Product Data | Closed | Civil, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-04 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Darren Simpson (DCI Engineers), Gareth Loveridge (Swift and Company Landscape Arch), Josh Dobken (Populous), Jarrett Grant (DCI Engineers) |  |  |  | 2019-10-18 | 2019-10-10 | 7 |  | Record Copies; Transfers; Submittals | 26 05 43-001-02 - 26 05 43-001-02 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Product Data | 7 | 2019-10-17 | 2019-10-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02671 | Received | For Review | 2019-10-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-10-18 | Submittal Number: 26 05 43-1.3 From: PATRICK KLEIN Final Due Date: 10/18/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: INCLUDE REVISED LID COVERS PER 1.0 SUBMITTAL COMMENTS Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 03990 | Forwarded | For Review | 2019-10-04 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Darren Simpson (DCI Engineers); Gareth Loveridge (Swift and Company Landscape Arch); Josh Dobken (Populous); Jarrett Grant (DCI Engineers) | 2019-10-11 | Submittal Number: 26 05 43-1.3 From: PATRICK KLEIN Final Due Date: 10/18/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: INCLUDE REVISED LID COVERS PER 1.0 SUBMITTAL COMMENTS Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Email
| 04057 | Responded and Closed | Approved as Noted | 2019-10-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. Non-skid Thermion TH604 coating approved. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-04 02:00 |  | 26 05 43-1.3 Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-10-04 02:00 |  | 26 05 43-1.3 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-10 02:00 |  | 26 05 43-1.3 Product Data-MAM_DCI_added pages_POP.pdf
26 05 43-003-00 | 26 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 26 05 43-003-00 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Calculations | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-15 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-29 | 2020-01-29 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-01-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03928 | Received | For Review | 2020-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-29 | Submittal Number: 26 05 43-3.0 From: PATRICK KLEIN Final Due Date: 01/29/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - CALCULATIONS Description: SUBMIT PULLING TENSION CALCULATIONS FOR ALL UNDERGROUND FEEDERS. Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 05494 | Forwarded | For Review | 2020-01-15 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-22 | Submittal Number: 26 05 43-3.0 From: PATRICK KLEIN Final Due Date: 01/29/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - CALCULATIONS Description: SUBMIT PULLING TENSION CALCULATIONS FOR ALL UNDERGROUND FEEDERS. Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 04129 | Review Response | Approved as Noted | 2020-01-29 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.29 | Info Exchange
| 05731 | Responded and Closed | Approved as Noted | 2020-01-29 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-15 |  | 26 05 43-3.0 Pulling Tension Calculations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-15 |  | 26 05 43-3.0 Pulling Tension Calculations-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-14 02:00 |  | 26 05 43-3.0 Pulling Tension Calculations-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-29 02:00 |  | 26 05 43-3.0 Pulling Tension Calculations-MAM-ME_POP.pdf
26 05 43-004-00 | 26 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 26 05 43-004-00 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Event Level Vault Covers | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-09 08:00 | 2019-11-22 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-11-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03303 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-12-09 08:00 | Submittal Number: 26 05 43-4.0 From: PATRICK KLEIN Final Due Date: 12/05/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - EVENT LEVEL VAULT COVERS Description: Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 04757 | Forwarded | For Review | 2019-11-21 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-27 | Submittal Number: 26 05 43-4.0 From: PATRICK KLEIN Final Due Date: 12/05/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - EVENT LEVEL VAULT COVERS Description: Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 03344 | Review Response | Approved as Noted | 2019-11-22 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.11.22 | Info Exchange
| 04798 | Responded and Closed | Approved as Noted | 2019-11-22 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.11.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-21 |  | 26 05 43-4.0 Event Level Vault Covers-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-21 |  | 26 05 43-4.0 Event Level Vault Covers-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-11-20 02:00 |  | 26 05 43-4.0 Event Level Vault Covers-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-22 02:00 |  | 26 05 43-4.0 Event Level Vault Covers-MAM - ME Review_POP.pdf
26 05 43-005-00 | 26 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 26 05 43-005-00: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-04 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-18 | 2019-12-17 | 14 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03514 | Received | For Review | 2019-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-12-18 | Submittal Number: 26 05 43-5.0 From: PATRICK KLEIN Final Due Date: 12/17/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHOP DRAWINGS Description: Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 04981 | Forwarded | For Review | 2019-12-05 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-12 | Submittal Number: 26 05 43-5.0 From: PATRICK KLEIN Final Due Date: 12/17/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHOP DRAWINGS Description: Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 03664 | Review Response | Approved as Noted/Resubmit | 2019-12-16 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2019.12.16 | Info Exchange
| 05184 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-17 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2019.12.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-03 02:00 |  | 26 05 43-5.0 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-03 02:00 |  | 26 05 43-5.0 Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-12-03 02:00 |  | 26 05 43-5.0 Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-17 02:00 |  | 26 05 43-5.0 Shop Drawings-MAM-ME_POP.pdf
26 05 43-005-01 | 26 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 26 05 43-005-01 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-27 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-10 | 2020-02-12 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-02-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04049 | Received | For Review | 2020-01-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-02-10 | Submittal Number: 26 05 43-5.1 From: PATRICK KLEIN Final Due Date: 02/10/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHOP DRAWINGS Description: PLEASE SUBMIT SHALLOW UNDERGROUND SHOP DRAWINGS AS WELL AS REVISION SHOWING UNDERGROUND ROUTING WITHIN NEW TRANSFORMER ROOM IN LOADING DOCK IN .1 SUBMITTAL. Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 05643 | Forwarded | For Review | 2020-01-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-03 | Submittal Number: 26 05 43-5.1 From: PATRICK KLEIN Final Due Date: 02/10/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHOP DRAWINGS Description: PLEASE SUBMIT SHALLOW UNDERGROUND SHOP DRAWINGS AS WELL AS REVISION SHOWING UNDERGROUND ROUTING WITHIN NEW TRANSFORMER ROOM IN LOADING DOCK IN .1 SUBMITTAL. Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 04341 | Review Response | Approved as Noted | 2020-02-12 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.02.12 | Info Exchange
| 06003 | Responded and Closed | Approved as Noted | 2020-02-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.02.12 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-24 |  | 26 05 43-5.1 Underground Ducts, Raceways, and Manholes Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-24 |  | 26 05 43-5.1 Underground Ducts, Raceways, and Manholes Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-23 02:00 |  | 26 05 43-5.1 Underground Ducts, Raceways, and Manholes Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-12 02:00 |  | 26 05 43-5.1 Underground Ducts, Raceways, and Manholes Shop Drawings-MAM-ME_POP.pdf
26 05 43-006-00 | 26 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 26 05 43-006-00 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Shallow Underground Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-17 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-31 | 2020-02-03 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-02-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03970 | Received | For Review | 2020-01-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-31 | Submittal Number: 26 05 43-6.0 From: PATRICK KLEIN Final Due Date: 01/31/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHALLOW UNDERGROUND SHOP DRAWINGS Description: Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 05539 | Forwarded | For Review | 2020-01-17 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-24 | Submittal Number: 26 05 43-6.0 From: PATRICK KLEIN Final Due Date: 01/31/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHALLOW UNDERGROUND SHOP DRAWINGS Description: Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 04180 | Review Response | Approved as Noted | 2020-02-03 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.03 | Info Exchange
| 05793 | Responded and Closed | Approved as Noted | 2020-02-03 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-16 |  | 26 05 43-6.0 Shallow Underground Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-16 |  | 26 05 43-6.0 Shallow Underground Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-15 02:00 |  | 26 05 43-6.0 Shallow Underground Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-03 02:00 |  | 26 05 43-6.0 Shallow Underground Shop Drawings-MAM-ME_POP.pdf
26 05 43-007-00 | 26 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 26 05 43-007-00 Duct Spacer Product Data for Additional Manufacturers | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-24 | 2020-02-24 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04295 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-02-24 | Submittal Number: 26 05 43-7.0 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: DUCT SPACER PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 05946 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-17 | Submittal Number: 26 05 43-7.0 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: DUCT SPACER PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 04477 | Review Response | Approved as Noted | 2020-02-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| 06170 | Responded and Closed | Approved as Noted | 2020-02-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-10 |  | 26 05 43-7.0 Product Data for Additional Manufacturers-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 26 05 43-7.0 Product Data for Additional Manufacturers-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-09 02:00 |  | 26 05 43-7.0 Product Data for Additional Manufacturers-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-24 02:00 |  | 26 05 43-7.0 Product Data for Additional Manufacturers-MAM-ME_POP.pdf
26 05 43-008-00 | 26 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 26 05 43-008-00 UNDERGROUND DUCTS RACEWAYS AND MANHOLES - 480V Pulling Tension Calculations | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-24 | 2020-02-24 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04297 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-02-24 | Submittal Number: 26 05 43-8.0 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: UNDERGROUND DUCTS RACEWAYS AND MANHOLES - 480V PULLING TENSION CALCULATIONS Description: SUBMIT PULLING TENSION CALCULATIONS FOR ALL UNDERGROUND FEEDERS. Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 05950 | Forwarded | For Review | 2020-02-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-18 | Submittal Number: 26 05 43-8.0 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: UNDERGROUND DUCTS RACEWAYS AND MANHOLES - 480V PULLING TENSION CALCULATIONS Description: SUBMIT PULLING TENSION CALCULATIONS FOR ALL UNDERGROUND FEEDERS. Spec Section: 26 05 43 - UNDERGROUND DUCTS AND RACEWAYS FOR ELECTRICAL SYSTEMS Status: OPEN | Info Exchange
| 04478 | Review Response | Approved as Noted | 2020-02-21 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| 06171 | Responded and Closed | Approved as Noted | 2020-02-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-11 |  | 26 05 43-8.0 480V Pulling Tension Calculations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-11 |  | 26 05 43-8.0 480V Pulling Tension Calculations-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-10 02:00 |  | 26 05 43-8.0 480V Pulling Tension Calculations-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-24 02:00 |  | 26 05 43-8.0 480V Pulling Tension Calculations-MAM-ME_POP.pdf
26 05 48-001-00 | 26 05 48 - VIBRATION AND SEISMIC CONTROLS | 26 05 48-001-00 VIBRATION AND SEISMIC CONTROLS - Manufacturers Instructions | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-15 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-29 | 2020-07-28 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06960 | Received | For Review | 2020-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-29 | Submittal Number: 26 05 48-1.0 From: PATRICK KLEIN Final Due Date: 07/28/20 Subject: VIBRATION AND SEISMIC CONTROLS - MANUFACTURERS INSTRUCTIONS Description: THE SHOP DRAWING SUBMITTAL FOR ISOLATED ELECTRICAL EQUIPMENT SHALL INCLUDE SUBMITTAL INFORMATION FOR THE ISOLATION MOUNTS. INFORMATION SUPPLIED SHALL BE AS FOLLOWS: 1. A COMPLETE DESCRIPTION OF PRODUCTS TO BE SUPPLIED INCLUDING PRODUCT DATA, DIMENSIONS, SPECIFICATIONS, AND INSTALLATION INSTRUCTIONS. 2. DETAILED SELECTION DATA FOR EACH VIBRATION ISOLATOR SUPPORTING EQUIPMENT, INCLUDING: A. THE EQUIPMENT IDENTIFICATION MARK. B. THE ISOLATOR TYPE. C. THE ACTUAL LOAD. 3. DETAILED SELECTION DATA FOR SEISMIC RESTRAINTS INCLUDING: A. SUBMIT MANUFACTURERS DATA FOR ALL MANUFACTURED RESTRAINTS. B. ALL SUBMITTALS SHALL BE STAMPED AND CERTIFIED BYA STRUCTURAL ENGINEER REGISTERED IN THE STATE OF WASHINGTON WITHA MINIMUM OF 5 YEARS EXPERIENCE IN THE DESIGN OF SEISMIC RESTRAINTS. C. SUBMIT SHOP DRAWINGS FOR ALL FABRICATED RESTRAINTS. D. SHOW RESTRAINT TYPE AND LOCATION ON THE INSTALLATION SHOP DRAWINGS. DRAWINGS TO INCLUDE: 1) ALL SEISMIC BRACE LOCATIONS. 2) ALL SEISMIC RESTRAINT CONNECTIONS TO STRUCTURE AND VERTICAL SUPPORT ANCHORAGE AT SEISMIC LOCATIONS AND ALL OTHER VERTICAL SUPPORT ANCHORAGE CONNECTIONS. INCLUDING BUT NOT LIMITED TO QUANTITY, SIZE, AND EMBEDMENT. 3) BRACE REACTION AT ALL CONNECTION POINTS TO THE STRUCTURE FOR STRUCTURAL ENGINEER OF RECORD USE IN CHECKING SUITABILITY OF THE BUILDING STRUCTURE. 4) TYPE AND SIZE OF BRACE MEMBER. 5) SUSPENDED UTILITY MAXIMUM LBS. PER LINEAR FOOT OR MAXIMUM CONDUIT SIZE AT ALL SEISMIC LOCATIONS. 6) MINIMUM ALL THREAD ROD SIZE AT ALL SEISMIC LOCATIONS. 7) SIZE ALL HORIZONTAL SUPPORT MEMBERS TAKING INTO ACCOUNT, BUT NOT LIMITED TO, DEFLECTION AND LOAD. 8) REGISTERED WASHINGTON ENGINEER STAMP AND SIGNATURE. E. SUBMIT CALCULATIONS FOR ALL SEISMIC RESTRAINT SYSTEMS THAT ARE NOT PREAPPROVED. F. JOB SITE CONDITIONS NOT COVERED BY THE MANUFACTURERS SEISMIC BRACING GUIDELINES SHALL BE ENGINEERED BY THE MANUFACTURER. Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 09328 | Forwarded | For Review | 2020-07-15 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-22 | Submittal Number: 26 05 48-1.0 From: PATRICK KLEIN Final Due Date: 07/28/20 Subject: VIBRATION AND SEISMIC CONTROLS - MANUFACTURERS INSTRUCTIONS Description: THE SHOP DRAWING SUBMITTAL FOR ISOLATED ELECTRICAL EQUIPMENT SHALL INCLUDE SUBMITTAL INFORMATION FOR THE ISOLATION MOUNTS. INFORMATION SUPPLIED SHALL BE AS FOLLOWS: 1. A COMPLETE DESCRIPTION OF PRODUCTS TO BE SUPPLIED INCLUDING PRODUCT DATA, DIMENSIONS, SPECIFICATIONS, AND INSTALLATION INSTRUCTIONS. 2. DETAILED SELECTION DATA FOR EACH VIBRATION ISOLATOR SUPPORTING EQUIPMENT, INCLUDING: A. THE EQUIPMENT IDENTIFICATION MARK. B. THE ISOLATOR TYPE. C. THE ACTUAL LOAD. 3. DETAILED SELECTION DATA FOR SEISMIC RESTRAINTS INCLUDING: A. SUBMIT MANUFACTURERS DATA FOR ALL MANUFACTURED RESTRAINTS. B. ALL SUBMITTALS SHALL BE STAMPED AND CERTIFIED BYA STRUCTURAL ENGINEER REGISTERED IN THE STATE OF WASHINGTON WITHA MINIMUM OF 5 YEARS EXPERIENCE IN THE DESIGN OF SEISMIC RESTRAINTS. C. SUBMIT SHOP DRAWINGS FOR ALL FABRICATED RESTRAINTS. D. SHOW RESTRAINT TYPE AND LOCATION ON THE INSTALLATION SHOP DRAWINGS. DRAWINGS TO INCLUDE: 1) ALL SEISMIC BRACE LOCATIONS. 2) ALL SEISMIC RESTRAINT CONNECTIONS TO STRUCTURE AND VERTICAL SUPPORT ANCHORAGE AT SEISMIC LOCATIONS AND ALL OTHER VERTICAL SUPPORT ANCHORAGE CONNECTIONS. INCLUDING BUT NOT LIMITED TO QUANTITY, SIZE, AND EMBEDMENT. 3) BRACE REACTION AT ALL CONNECTION POINTS TO THE STRUCTURE FOR STRUCTURAL ENGINEER OF RECORD USE IN CHECKING SUITABILITY OF THE BUILDING STRUCTURE. 4) TYPE AND SIZE OF BRACE MEMBER. 5) SUSPENDED UTILITY MAXIMUM LBS. PER LINEAR FOOT OR MAXIMUM CONDUIT SIZE AT ALL SEISMIC LOCATIONS. 6) MINIMUM ALL THREAD ROD SIZE AT ALL SEISMIC LOCATIONS. 7) SIZE ALL HORIZONTAL SUPPORT MEMBERS TAKING INTO ACCOUNT, BUT NOT LIMITED TO, DEFLECTION AND LOAD. 8) REGISTERED WASHINGTON ENGINEER STAMP AND SIGNATURE. E. SUBMIT CALCULATIONS FOR ALL SEISMIC RESTRAINT SYSTEMS THAT ARE NOT PREAPPROVED. F. JOB SITE CONDITIONS NOT COVERED BY THE MANUFACTURERS SEISMIC BRACING GUIDELINES SHALL BE ENGINEERED BY THE MANUFACTURER. Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 07217 | Review Response | Approved | 2020-07-27 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.27 | Info Exchange
| 09629 | Responded and Closed | Approved | 2020-07-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-14 |  | 26 05 48-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-14 |  | 26 05 48-1.0 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-13 02:00 |  | 26 05 48-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-28 02:00 |  | 26 05 48-1.0 Product Data-MAM-ME_pop.pdf
26 05 48-003-00 | 26 05 48 - VIBRATION AND SEISMIC CONTROLS | 26 05 48-003-00 VIBRATION AND SEISMIC - Gear Attachment Calculations | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-27 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2020-09-11 07:00 | 2020-09-14 | 19 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07799 | Received | For Review | 2020-08-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-09-11 07:00 | Submittal Number: 26 05 48-3.0 From: PATRICK KLEIN Final Due Date: 09/11/20 Subject: VIBRATION AND SEISMIC - GEAR ATTACHMENT CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 10377 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-03 | Submittal Number: 26 05 48-3.0 From: PATRICK KLEIN Final Due Date: 09/11/20 Subject: VIBRATION AND SEISMIC - GEAR ATTACHMENT CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 10593 | Forwarded | For Review | 2020-09-08 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) | 2020-09-11 | Submittal Number: 26 05 48-3.0 From: PATRICK KLEIN Final Due Date: 09/11/20 Subject: VIBRATION AND SEISMIC - GEAR ATTACHMENT CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 08076 | Review Response | No Action Taken or Required | 2020-09-09 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | See the attached submittal review. Please forward to TT for review. Mark Lievens ME Engineers 2020.09.09 | Info Exchange
| 08077 | Review Response | Revise and Resubmit | 2020-09-10 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Provide net T&C forces for unit CEC-701A as noted for review of slab. | Info Exchange
| 10744 | Responded and Closed | Revise and Resubmit | 2020-09-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Mark Lievens (ME Engineers) Remarks: See the attached submittal review. Please forward to TT for review. Mark Lievens ME Engineers 2020.09.09 Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Provide net T&C forces for unit CEC-701A as noted for review of slab. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 26 05 48-3.0 Gear Attachment Calculations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-27 |  | 26 05 48-3.0 Gear Attachment Calculations-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-08-26 02:00 |  | 26 05 48-3.0 Gear Attachment Calculations-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-26 02:00 |  | 26 05 48-3.0 Gear Attachment Calculations-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-08-26 02:00 |  | 26 05 48-3.0 Gear Attachment Calculations-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-14 02:00 |  | 26 05 48-3.0 Gear Attachment Calculations-MAM_ME_TT REVIEW_POP.pdf
26 05 48-003-01 | 26 05 48 - VIBRATION AND SEISMIC CONTROLS | 26 05 48-003-01 VIBRATION AND SEISMIC - Gear Attachment Calculations | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-23 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti) |  |  |  | 2020-10-07 | 2020-10-06 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-10-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08296 | Received | For Review | 2020-09-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-10-07 | Submittal Number: 26 05 48-3.1 From: PATRICK KLEIN Final Due Date: 10/06/20 Subject: VIBRATION AND SEISMIC - GEAR ATTACHMENT CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 11001 | Forwarded | For Review | 2020-09-23 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornt... | 2020-09-30 | Submittal Number: 26 05 48-3.1 From: PATRICK KLEIN Final Due Date: 10/06/20 Subject: VIBRATION AND SEISMIC - GEAR ATTACHMENT CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 08424 | Review Response | No Action Taken or Required | 2020-09-25 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please forward this submittal to TT for their review. Thank you, Mark Lievens ME Engineers 2020.09.25 | Info Exchange
| 11105 | Forwarded | For Review | 2020-09-28 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti) | 2020-10-05 | Submittal Number: 26 05 48-3.1 From: PATRICK KLEIN Final Due Date: 10/06/20 Subject: VIBRATION AND SEISMIC - GEAR ATTACHMENT CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 08618 | Review Response | Approved | 2020-10-06 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | No exceptions. TT-FK ¦ 2020-10-05 | Info Exchange
| 11388 | Responded and Closed | Approved | 2020-10-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Franz Kogler (Thornton Tomasetti) Remarks: No exceptions. TT-FK ¦ 2020-10-05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-23 |  | 26 05 48-3.1 Gear Attachment Calculations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-23 |  | 26 05 48-3.1 Gear Attachment Calculations-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-23 |  | 26 05 48-3.1 Gear Attachment Calculations-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-09-22 02:00 |  | 26 05 48-3.1 Gear Attachment Calculations-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-09-22 |  | 26 05 48-3.1 Gear Attachment Calculations-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-06 |  | 26 05 48-3.1 Gear Attachment Calculations-MAM_TT_POP.pdf
26 05 48-004-00 | 26 05 48 - VIBRATION AND SEISMIC CONTROLS | 26 05 48-004-00 VIBRATION AND SEISMIC - Area D Shop Drawings and Calculations | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-29 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti) |  |  |  | 2020-11-12 | 2020-11-09 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-11-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09095 | Received | For Review | 2020-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-12 | Submittal Number: 26 05 48-4.0 From: PATRICK KLEIN Final Due Date: 11/12/20 Subject: VIBRATION AND SEISMIC - AREA D SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 12001 | Forwarded | For Review | 2020-10-29 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-05 | Submittal Number: 26 05 48-4.0 From: PATRICK KLEIN Final Due Date: 11/12/20 Subject: VIBRATION AND SEISMIC - AREA D SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 09146 | Review Response | No Action Taken or Required | 2020-11-01 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please have this submittal sent to TT for review. Thank you, Mark Lievens ME Engineers 2020.11.01 | Info Exchange
| 12068 | Forwarded | For Review | 2020-11-02 | Bryan Klote (Populous) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti) |  | Submittal Number: 26 05 48-4.0 From: PATRICK KLEIN Final Due Date: 11/12/20 Subject: VIBRATION AND SEISMIC - AREA D SHOP DRAWINGS AND CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 09328 | Review Response | Approved | 2020-11-09 | Matt Ross (Thornton Tomasetti) | Bryan Klote (Populous) |  |  | Info Exchange
| 12309 | Responded and Closed | Approved | 2020-11-09 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-29 |  | 26 05 48-4.0 Area D Shop Drawings and Calculations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-29 |  | 26 05 48-4.0 Area D Shop Drawings and Calculations-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-29 |  | 26 05 48-4.0 Area D Shop Drawings and Calculations-MAM.pdf
| Forwarded |  | Bryan Klote (Populous) | 1 | 2020-10-29 |  | 26 05 48-4.0 Area D Shop Drawings and Calculations-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-10-28 02:00 |  | 26 05 48-4.0 Area D Shop Drawings and Calculations-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-09 02:00 |  | 26 05 48-4.0 Area D Shop Drawings and Calculations-MAM_TT REVIEW_pop.pdf
26 05 48-005-00 | 26 05 48 - VIBRATION AND SEISMIC CONTROLS | 26 05 48-005-00 VIBRATION AND SEISMIC - Generator Attachment Calculations | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-19 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-05 07:00 | 2021-04-05 | 18 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12113 | Received | For Review | 2021-03-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction) | 2021-04-05 07:00 | Submittal Number: 26 05 48-5.0 From: PATRICK KLEIN Final Due Date: 04/01/21 Subject: VIBRATION AND SEISMIC - GENERATOR ATTACHMENT CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 15679 | Forwarded | For Review | 2021-03-19 | Patrick Klein (Mortenson Construction) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-26 | Submittal Number: 26 05 48-5.0 From: PATRICK KLEIN Final Due Date: 04/01/21 Subject: VIBRATION AND SEISMIC - GENERATOR ATTACHMENT CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 15724 | Forwarded | For Review | 2021-03-22 | Patrick Klein (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-29 | Submittal Number: 26 05 48-5.0 From: PATRICK KLEIN Final Due Date: 04/01/21 Subject: VIBRATION AND SEISMIC - GENERATOR ATTACHMENT CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 12300 | Review Response | Not Required For Review | 2021-03-24 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please forward this submittal to TT for review. Thank you, Mark Lievens ME Engineers 2021.03.24 | Info Exchange
| 12399 | Review Response | Approved | 2021-03-31 | Franz Kogler (Thornton Tomasetti) | Patrick Klein (Mortenson Construction) |  | No Exceptions. See attached. | Info Exchange
| 16071 | Responded and Closed | Approved | 2021-04-05 | Patrick Klein (Mortenson Construction) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Franz Kogler (Thornton Tomasetti) Remarks: No Exceptions. See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-19 |  | 26 05 48-5.0 Generator Attachment Calculations-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2021-03-19 |  | 26 05 48-5.0 Generator Attachment Calculations-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2021-03-19 |  | 26 05 48-5.0 Generator Attachment Calculations-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-03-19 |  | 26 05 48-5.0 Generator Attachment Calculations-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-03-18 02:00 |  | 26 05 48-5.0 Generator Attachment Calculations-MAM.pdf
| Responded and Closed |  | Patrick Klein (Mortenson Construction) | 1 | 2021-04-05 02:00 |  | 26 05 48-5.0 Generator Attachment Calculations-MAM_TTReview_POP.pdf
26 05 48-006-00 | 26 05 48 - VIBRATION AND SEISMIC CONTROLS | 26 05 48-006-00 SEISMIC AND VIBRATION - Quad A, B, and C Seismic Drawings and Calculations | Closed | Structural, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-26 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-14 07:00 | 2021-05-25 | 30 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-05-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12758 | Received | For Review | 2021-04-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-05-14 07:00 | Submittal Number: 26 05 48-6.0 From: PATRICK KLEIN Final Due Date: 05/09/21 Subject: SEISMIC AND VIBRATION - QUAD A, B, AND C SEISMIC DRAWINGS AND CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 16491 | Forwarded | For Review | 2021-04-26 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tom... | 2021-05-03 | Submittal Number: 26 05 48-6.0 From: PATRICK KLEIN Final Due Date: 05/09/21 Subject: SEISMIC AND VIBRATION - QUAD A, B, AND C SEISMIC DRAWINGS AND CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 12954 | Review Response | No Action Taken or Required | 2021-04-26 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please forward to TT for review. Mark Lievens ME Engineers 2021.04.26 | Info Exchange
| 13162 | Review Response | Approved as Noted | 2021-05-10 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Refer to comments within submittal. Do not need to resubmit unless calcs, details, or layouts change. | Info Exchange
| 17157 | Responded and Closed | Approved as Noted | 2021-05-25 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: Refer to comments within submittal. Do not need to resubmit unless calcs, details, or layouts change. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-26 |  | 26 05 48-6.0 Quad A B and C Seismic Drawings and Calcs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-26 |  | 26 05 48-6.0 Quad A B and C Seismic Drawings and Calcs-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-25 02:00 |  | 26 05 48-6.0 Quad A B and C Seismic Drawings and Calcs-MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-26 |  | 26 05 48-6.0 Quad A B and C Seismic Drawings and Calcs-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-05-25 |  | 26 05 48-6.0 Quad A B and C Seismic Drawings and Calcs-MAM_TT_POP.pdf
26 05 48-007-00 | 26 05 48 - VIBRATION AND SEISMIC CONTROLS | 26 05 48-007-00 500, 550, and 600 Level Drawings and Calculations | Open - Overdue | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-27 | Forwarded - For Review |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) | 2021-10-04 | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  | 2021-10-11 |  | 11 |  | Record Copies; Transfers; Submittals |  | 11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14705 | Received | For Review | 2021-09-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-10-11 | Submittal Number: 26 05 48-7.0 From: PATRICK KLEIN Final Due Date: 10/10/21 Subject: 26 05 48-6.0 500, 550, AND 600 LEVEL DRAWINGS AND CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| 18964 | Forwarded | For Review | 2021-09-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-10-04 | Submittal Number: 26 05 48-7.0 From: PATRICK KLEIN Final Due Date: 10/10/21 Subject: 26 05 48-6.0 500, 550, AND 600 LEVEL DRAWINGS AND CALCULATIONS Description: Spec Section: 26 05 48 - VIBRATION AND SEISMIC Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-26 |  | 26 05 48-7.0 500 550 and 600 Level Drawings and Calcs-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-26 |  | 26 05 48-7.0 500 550 and 600 Level Drawings and Calcs-MAM.pdf
26 05 53-001-00 | 26 05 53 - IDENTIFICATION | 26 05 53-001-00 IDENTIFICATION - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-08 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-22 | 2020-06-24 | 17 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06253 | Received | For Review | 2020-06-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-22 | Submittal Number: 26 05 53-1.0 From: PATRICK KLEIN Final Due Date: 06/19/20 Subject: IDENTIFICATION - PRODUCT DATA Description: PRODUCT DATA FOR EACH TYPE OF PRODUCT SPECIFIED. SCHEDULE OF IDENTIFICATION NOMENCLATURE TO BE USED FOR IDENTIFICATION SIGNS AND LABELS. Spec Section: 26 05 53 - IDENTIFICATION Status: OPEN | Info Exchange
| 08438 | Forwarded | For Review | 2020-06-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-15 | Submittal Number: 26 05 53-1.0 From: PATRICK KLEIN Final Due Date: 06/19/20 Subject: IDENTIFICATION - PRODUCT DATA Description: PRODUCT DATA FOR EACH TYPE OF PRODUCT SPECIFIED. SCHEDULE OF IDENTIFICATION NOMENCLATURE TO BE USED FOR IDENTIFICATION SIGNS AND LABELS. Spec Section: 26 05 53 - IDENTIFICATION Status: OPEN | Info Exchange
| 06625 | Review Response | Approved as Noted | 2020-06-22 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.06.22 | Info Exchange
| 08876 | Responded and Closed | Approved as Noted | 2020-06-24 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.06.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 26 05 53-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 26 05 53-1.0 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-06-04 02:00 |  | 26 05 53-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-24 |  | 26 05 53-1.0 IDENTIFICATION _ME_POP.pdf
26 05 53-003-00 | 26 05 53 - IDENTIFICATION | 26 05 53-003-00 IDENTIFICATION - Samples | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-26 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-09 | 2020-06-12 | 18 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-06-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06027 | Received | For Review | 2020-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-09 | Submittal Number: 26 05 53-3.0 From: PATRICK KLEIN Final Due Date: 03/20/20 Subject: IDENTIFICATION - SAMPLES Description: SAMPLES OF ENGRAVED, PLASTIC LAMINATE TO BE USED ON SWITCHGEAR, SWITCHBOARDS, DISCONNECT SWITCHES AND PANELBOARDS. Spec Section: 26 05 53 - IDENTIFICATION Status: OPEN | Info Exchange
| 08171 | Forwarded | For Review | 2020-05-26 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-02 | Submittal Number: 26 05 53-3.0 From: PATRICK KLEIN Final Due Date: 03/20/20 Subject: IDENTIFICATION - SAMPLES Description: SAMPLES OF ENGRAVED, PLASTIC LAMINATE TO BE USED ON SWITCHGEAR, SWITCHBOARDS, DISCONNECT SWITCHES AND PANELBOARDS. Spec Section: 26 05 53 - IDENTIFICATION Status: OPEN | Info Exchange
| 06383 | Review Response | Approved as Noted | 2020-06-11 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.11 | Info Exchange
| 08600 | Responded and Closed | Approved as Noted | 2020-06-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-26 |  | 26 05 53-3.0 Samples-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-26 |  | 26 05 53-3.0 Samples-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-25 02:00 |  | 26 05 53-3.0 Samples-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-12 02:00 |  | 26 05 53-3.0 Samples-MAM-ME_POP.pdf
26 09 13-001-00 | 26 09 13 - ELECTRICAL POWER MONITORING | 26 09 13-001-00 ELECTRICAL POWER MONITORING - Product Data, Graphic Screen Shots, Wiring Diagrams, and Network Topology Diagrams | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-18 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-08 07:00 | 2020-06-12 | 26 |  | Record Copies; Transfers; Submittals |  | 25 |  | 2020-06-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05906 | Received | For Review | 2020-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-08 07:00 | Submittal Number: 26 09 13-1.0 From: PATRICK KLEIN Final Due Date: 06/05/20 Subject: ELECTRICAL POWER MONITORING - PRODUCT DATA, GRAPHIC SCREEN SHOTS, WIRING DIAGRAMS, AND NETWORK TOPOLOGY DIAGRAMS Description: 1. METERS AND METERING ENCLOSURES COMPLETE WITH PHYSICAL DIMENSIONS, SCHEMATIC WIRING- DIAGRAM, PRODUCT DATA, DATA MAPS, ETC. 2. PRODUCT DATA FOR ALL REQUIRED NETWORK DEVICES, CONDUCTORS, COMPUTERS, SOFTWARE, ETC.- 3. NETWORK TOPOLOGY DIAGRAM INCLUDING ALL DEVICES, METERS, BMCS INTERFACE LOCATION(S),- WIRING, METER ADDRESSES, ALL DEVICE PHYSICAL LOCATIONS, POWER REQUIREMENTS FOR ALL EXTERNALLY POWERED DEVICES, ETC. 4. MANUFACTURERS LITERATURE AND SPECIFICATION- 5. GRAPHIC SCREEN SHOTS REQUIRED FOR COMPUTER SOFTWARE INTERFACE- 6. COMPONENT CONNECTION WIRING DIAGRAMS- COMMUNICATIONS SYSTEM SPECIFICATION Spec Section: 26 09 13 - ELECTRICAL POWER MONITORING Status: OPEN | Info Exchange
| 08011 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-25 | Submittal Number: 26 09 13-1.0 From: PATRICK KLEIN Final Due Date: 06/05/20 Subject: ELECTRICAL POWER MONITORING - PRODUCT DATA, GRAPHIC SCREEN SHOTS, WIRING DIAGRAMS, AND NETWORK TOPOLOGY DIAGRAMS Description: 1. METERS AND METERING ENCLOSURES COMPLETE WITH PHYSICAL DIMENSIONS, SCHEMATIC WIRING- DIAGRAM, PRODUCT DATA, DATA MAPS, ETC. 2. PRODUCT DATA FOR ALL REQUIRED NETWORK DEVICES, CONDUCTORS, COMPUTERS, SOFTWARE, ETC.- 3. NETWORK TOPOLOGY DIAGRAM INCLUDING ALL DEVICES, METERS, BMCS INTERFACE LOCATION(S),- WIRING, METER ADDRESSES, ALL DEVICE PHYSICAL LOCATIONS, POWER REQUIREMENTS FOR ALL EXTERNALLY POWERED DEVICES, ETC. 4. MANUFACTURERS LITERATURE AND SPECIFICATION- 5. GRAPHIC SCREEN SHOTS REQUIRED FOR COMPUTER SOFTWARE INTERFACE- 6. COMPONENT CONNECTION WIRING DIAGRAMS- COMMUNICATIONS SYSTEM SPECIFICATION Spec Section: 26 09 13 - ELECTRICAL POWER MONITORING Status: OPEN | Info Exchange
| 06381 | Review Response | Approved as Noted | 2020-06-11 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.11 | Info Exchange
| 08598 | Responded and Closed | Approved as Noted | 2020-06-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 26 09 13-1.0 PD Graphics and Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 26 09 13-1.0 PD Graphics and Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-17 02:00 |  | 26 09 13-1.0 PD Graphics and Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-12 02:00 |  | 26 09 13-1.0 PD Graphics and Diagrams-MAM-ME_POP.pdf
26 09 43-001-00 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-001-00 NETWORK LIGHTING CONTROL - Product Data, Shop Drawings, Wiring Diagrams, Riser Diagrams, and Product Overview | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-18 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Allison Wood (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-08 | 2020-06-24 | 38 |  | Record Copies; Transfers; Submittals |  | 30 |  | 2020-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05894 | Received | For Review | 2020-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-08 | Submittal Number: 26 09 43-1.0 From: PATRICK KLEIN Final Due Date: 06/05/20 Subject: NETWORK LIGHTING CONTROL - PRODUCT DATA, SHOP DRAWINGS, WIRING DIAGRAMS, RISER DIAGRAMS, AND PRODUCT OVERVIEW Description: PRODUCT DATA : THE MANUFACTURER SHALL SUBMIT INA BILL OF MATERIAL FORM AN ITEMIZED LIST OF ALL MATERIALS BEING SUPPLIED TO MEET THE SPECIFICATIONS. SHOP DRAWINGS : MANUFACTURER SHALL SUBMIT PLAN DRAWINGS OF ALL EQUIPMENT/COMPONENTS, ONE-LINE DIAGRAM, RELAY/DIMMER PANEL SCHEDULES, OVERRIDE DIMMER/SWITCH STATION SCHEDULES, AND PLAN DRAWINGS WITH ALL DEVICE LOCATIONS, INCLUDING PHOTOCELLS, OCCUPANCY SENSORS, SWITCH PACKS, I/O MODULES, OVERRIDE DIMMER/SWITCH LOCATIONS, AND PANEL LOCATIONS. SENSOR COVERAGE AND QUANTITY SHALL BE PROVIDED AS PART OF SHOP DRAWINGS. RISER DIAGRAM : MANUFACTURER SHALL SUBMITA LINE DIAGRAM OF THE SYSTEM CONFIGURATIONS IN SUFFICIENT DETAIL TO SHOW THE RELATIVE PLACEMENT OF ALL EQUIPMENT AND INTERCONNECTION WITH EQUIPMENT SUPPLIED BY OTHER MANUFACTURERS. WIRING DIAGRAMS : MANUFACTURER SHALL SUBMIT TYPICAL WIRING DIAGRAMS FOR ALL COMPONENTS. DETAILED INTERCONNECTION DIAGRAMS ARE REQUIRED ONLY IF PROPER INTERWIRING OF COMPONENTS IS NOT CLEARLY INDICATED ON TYPICAL WIRING DIAGRAMS. PRODUCT OVERVIEW : MANUFACTURER SHALL SUBMIT DATA SHEETS ON ALL COMPONENTS OF THE SYSTEM. THESE SHALL DESCRIBE ALL HARDWARE AND SOFTWARE ITEMS PROVIDED. A DETAILED LINE BY LINE SPECIFICATION COMPLIANCE SHALL ALSO BE INCLUDED. THE SOFTWARE SHALL IDENTIFY THE PROCESS FOR PROGRAMMING REPEATING TIME SCHEDULES. Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 07994 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Allison Wood (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-25 | Submittal Number: 26 09 43-1.0 From: PATRICK KLEIN Final Due Date: 06/05/20 Subject: NETWORK LIGHTING CONTROL - PRODUCT DATA, SHOP DRAWINGS, WIRING DIAGRAMS, RISER DIAGRAMS, AND PRODUCT OVERVIEW Description: PRODUCT DATA : THE MANUFACTURER SHALL SUBMIT INA BILL OF MATERIAL FORM AN ITEMIZED LIST OF ALL MATERIALS BEING SUPPLIED TO MEET THE SPECIFICATIONS. SHOP DRAWINGS : MANUFACTURER SHALL SUBMIT PLAN DRAWINGS OF ALL EQUIPMENT/COMPONENTS, ONE-LINE DIAGRAM, RELAY/DIMMER PANEL SCHEDULES, OVERRIDE DIMMER/SWITCH STATION SCHEDULES, AND PLAN DRAWINGS WITH ALL DEVICE LOCATIONS, INCLUDING PHOTOCELLS, OCCUPANCY SENSORS, SWITCH PACKS, I/O MODULES, OVERRIDE DIMMER/SWITCH LOCATIONS, AND PANEL LOCATIONS. SENSOR COVERAGE AND QUANTITY SHALL BE PROVIDED AS PART OF SHOP DRAWINGS. RISER DIAGRAM : MANUFACTURER SHALL SUBMITA LINE DIAGRAM OF THE SYSTEM CONFIGURATIONS IN SUFFICIENT DETAIL TO SHOW THE RELATIVE PLACEMENT OF ALL EQUIPMENT AND INTERCONNECTION WITH EQUIPMENT SUPPLIED BY OTHER MANUFACTURERS. WIRING DIAGRAMS : MANUFACTURER SHALL SUBMIT TYPICAL WIRING DIAGRAMS FOR ALL COMPONENTS. DETAILED INTERCONNECTION DIAGRAMS ARE REQUIRED ONLY IF PROPER INTERWIRING OF COMPONENTS IS NOT CLEARLY INDICATED ON TYPICAL WIRING DIAGRAMS. PRODUCT OVERVIEW : MANUFACTURER SHALL SUBMIT DATA SHEETS ON ALL COMPONENTS OF THE SYSTEM. THESE SHALL DESCRIBE ALL HARDWARE AND SOFTWARE ITEMS PROVIDED. A DETAILED LINE BY LINE SPECIFICATION COMPLIANCE SHALL ALSO BE INCLUDED. THE SOFTWARE SHALL IDENTIFY THE PROCESS FOR PROGRAMMING REPEATING TIME SCHEDULES. Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 06626 | Review Response | Approved as Noted | 2020-06-16 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.16 | Info Exchange
| 08868 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-24 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | See attached, ref: pg 2-6 for more information. Bryan Klote/Populous 06.24.2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 26 09 43-1.0 PD Shops Wiring Riser Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 26 09 43-1.0 PD Shops Wiring Riser Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-17 02:00 |  | 26 09 43-1.0 PD Shops Wiring Riser Diagrams-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-24 |  | 26 09 43-1.0 PD Shops Wiring Riser Diagrams-MAM-ME_POP.pdf
26 09 43-001-01 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-001-01 NETWORK LIGHTING CONTROL - Product Data, Shop Drawings, Wiring Diagrams, Riser Diagrams, and Product Overview | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-14 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-03 | 2020-11-17 | 35 |  | Record Copies; Transfers; Submittals |  | 30 |  | 2020-11-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08771 | Received | For Review | 2020-10-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-03 | Submittal Number: 26 09 43-1.1 From: PATRICK KLEIN Final Due Date: 11/02/20 Subject: NETWORK LIGHTING CONTROL - PRODUCT DATA, SHOP DRAWINGS, WIRING DIAGRAMS, RISER DIAGRAMS, AND PRODUCT OVERVIEW Description: PRODUCT DATA : THE MANUFACTURER SHALL SUBMIT INA BILL OF MATERIAL FORM AN ITEMIZED LIST OF ALL MATERIALS BEING SUPPLIED TO MEET THE SPECIFICATIONS. SHOP DRAWINGS : MANUFACTURER SHALL SUBMIT PLAN DRAWINGS OF ALL EQUIPMENT/COMPONENTS, ONE-LINE DIAGRAM, RELAY/DIMMER PANEL SCHEDULES, OVERRIDE DIMMER/SWITCH STATION SCHEDULES, AND PLAN DRAWINGS WITH ALL DEVICE LOCATIONS, INCLUDING PHOTOCELLS, OCCUPANCY SENSORS, SWITCH PACKS, I/O MODULES, OVERRIDE DIMMER/SWITCH LOCATIONS, AND PANEL LOCATIONS. SENSOR COVERAGE AND QUANTITY SHALL BE PROVIDED AS PART OF SHOP DRAWINGS. RISER DIAGRAM : MANUFACTURER SHALL SUBMITA LINE DIAGRAM OF THE SYSTEM CONFIGURATIONS IN SUFFICIENT DETAIL TO SHOW THE RELATIVE PLACEMENT OF ALL EQUIPMENT AND INTERCONNECTION WITH EQUIPMENT SUPPLIED BY OTHER MANUFACTURERS. WIRING DIAGRAMS : MANUFACTURER SHALL SUBMIT TYPICAL WIRING DIAGRAMS FOR ALL COMPONENTS. DETAILED INTERCONNECTION DIAGRAMS ARE REQUIRED ONLY IF PROPER INTERWIRING OF COMPONENTS IS NOT CLEARLY INDICATED ON TYPICAL WIRING DIAGRAMS. PRODUCT OVERVIEW : MANUFACTURER SHALL SUBMIT DATA SHEETS ON ALL COMPONENTS OF THE SYSTEM. THESE SHALL DESCRIBE ALL HARDWARE AND SOFTWARE ITEMS PROVIDED. A DETAILED LINE BY LINE SPECIFICATION COMPLIANCE SHALL ALSO BE INCLUDED. THE SOFTWARE SHALL IDENTIFY THE PROCESS FOR PROGRAMMING REPEATING TIME SCHEDULES. Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 11598 | Forwarded | For Review | 2020-10-14 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-21 | Submittal Number: 26 09 43-1.1 From: PATRICK KLEIN Final Due Date: 11/02/20 Subject: NETWORK LIGHTING CONTROL - PRODUCT DATA, SHOP DRAWINGS, WIRING DIAGRAMS, RISER DIAGRAMS, AND PRODUCT OVERVIEW Description: PRODUCT DATA : THE MANUFACTURER SHALL SUBMIT INA BILL OF MATERIAL FORM AN ITEMIZED LIST OF ALL MATERIALS BEING SUPPLIED TO MEET THE SPECIFICATIONS. SHOP DRAWINGS : MANUFACTURER SHALL SUBMIT PLAN DRAWINGS OF ALL EQUIPMENT/COMPONENTS, ONE-LINE DIAGRAM, RELAY/DIMMER PANEL SCHEDULES, OVERRIDE DIMMER/SWITCH STATION SCHEDULES, AND PLAN DRAWINGS WITH ALL DEVICE LOCATIONS, INCLUDING PHOTOCELLS, OCCUPANCY SENSORS, SWITCH PACKS, I/O MODULES, OVERRIDE DIMMER/SWITCH LOCATIONS, AND PANEL LOCATIONS. SENSOR COVERAGE AND QUANTITY SHALL BE PROVIDED AS PART OF SHOP DRAWINGS. RISER DIAGRAM : MANUFACTURER SHALL SUBMITA LINE DIAGRAM OF THE SYSTEM CONFIGURATIONS IN SUFFICIENT DETAIL TO SHOW THE RELATIVE PLACEMENT OF ALL EQUIPMENT AND INTERCONNECTION WITH EQUIPMENT SUPPLIED BY OTHER MANUFACTURERS. WIRING DIAGRAMS : MANUFACTURER SHALL SUBMIT TYPICAL WIRING DIAGRAMS FOR ALL COMPONENTS. DETAILED INTERCONNECTION DIAGRAMS ARE REQUIRED ONLY IF PROPER INTERWIRING OF COMPONENTS IS NOT CLEARLY INDICATED ON TYPICAL WIRING DIAGRAMS. PRODUCT OVERVIEW : MANUFACTURER SHALL SUBMIT DATA SHEETS ON ALL COMPONENTS OF THE SYSTEM. THESE SHALL DESCRIBE ALL HARDWARE AND SOFTWARE ITEMS PROVIDED. A DETAILED LINE BY LINE SPECIFICATION COMPLIANCE SHALL ALSO BE INCLUDED. THE SOFTWARE SHALL IDENTIFY THE PROCESS FOR PROGRAMMING REPEATING TIME SCHEDULES. Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 09516 | Review Response | Approved as Noted/Resubmit | 2020-11-12 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.12 | Info Exchange
| 12536 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.12 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-14 |  | 26 09 43-1.1 PD Shops Wiring Riser Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-14 |  | 26 09 43-1.1 PD Shops Wiring Riser Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-13 02:00 |  | 26 09 43-1.1 PD Shops Wiring Riser Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-17 02:00 |  | 26 09 43-1.1 PD Shops Wiring Riser Diagrams-MAM-ME_pop.pdf
26 09 43-001-02 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-001-02 NETWORK LIGHTING CONTROL - Product Data, Shop Drawings, Wiring Diagrams, Riser Diagrams, and Product Overview | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-03 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-17 | 2021-03-08 | 34 |  | Record Copies; Transfers; Submittals |  | 31 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11154 | Received | For Review | 2021-02-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-17 | Submittal Number: 26 09 43-1.2 From: PATRICK KLEIN Final Due Date: 02/16/21 Subject: NETWORK LIGHTING CONTROL - PRODUCT DATA, SHOP DRAWINGS, WIRING DIAGRAMS, RISER DIAGRAMS, AND PRODUCT OVERVIEW Description: PRODUCT DATA : THE MANUFACTURER SHALL SUBMIT INA BILL OF MATERIAL FORM AN ITEMIZED LIST OF ALL MATERIALS BEING SUPPLIED TO MEET THE SPECIFICATIONS. SHOP DRAWINGS : MANUFACTURER SHALL SUBMIT PLAN DRAWINGS OF ALL EQUIPMENT/COMPONENTS, ONE-LINE DIAGRAM, RELAY/DIMMER PANEL SCHEDULES, OVERRIDE DIMMER/SWITCH STATION SCHEDULES, AND PLAN DRAWINGS WITH ALL DEVICE LOCATIONS, INCLUDING PHOTOCELLS, OCCUPANCY SENSORS, SWITCH PACKS, I/O MODULES, OVERRIDE DIMMER/SWITCH LOCATIONS, AND PANEL LOCATIONS. SENSOR COVERAGE AND QUANTITY SHALL BE PROVIDED AS PART OF SHOP DRAWINGS. RISER DIAGRAM : MANUFACTURER SHALL SUBMITA LINE DIAGRAM OF THE SYSTEM CONFIGURATIONS IN SUFFICIENT DETAIL TO SHOW THE RELATIVE PLACEMENT OF ALL EQUIPMENT AND INTERCONNECTION WITH EQUIPMENT SUPPLIED BY OTHER MANUFACTURERS. WIRING DIAGRAMS : MANUFACTURER SHALL SUBMIT TYPICAL WIRING DIAGRAMS FOR ALL COMPONENTS. DETAILED INTERCONNECTION DIAGRAMS ARE REQUIRED ONLY IF PROPER INTERWIRING OF COMPONENTS IS NOT CLEARLY INDICATED ON TYPICAL WIRING DIAGRAMS. PRODUCT OVERVIEW : MANUFACTURER SHALL SUBMIT DATA SHEETS ON ALL COMPONENTS OF THE SYSTEM. THESE SHALL DESCRIBE ALL HARDWARE AND SOFTWARE ITEMS PROVIDED. A DETAILED LINE BY LINE SPECIFICATION COMPLIANCE SHALL ALSO BE INCLUDED. THE SOFTWARE SHALL IDENTIFY THE PROCESS FOR PROGRAMMING REPEATING TIME SCHEDULES. Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 14460 | Forwarded | For Review | 2021-02-03 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-10 | Submittal Number: 26 09 43-1.2 From: PATRICK KLEIN Final Due Date: 02/16/21 Subject: NETWORK LIGHTING CONTROL - PRODUCT DATA, SHOP DRAWINGS, WIRING DIAGRAMS, RISER DIAGRAMS, AND PRODUCT OVERVIEW Description: PRODUCT DATA : THE MANUFACTURER SHALL SUBMIT INA BILL OF MATERIAL FORM AN ITEMIZED LIST OF ALL MATERIALS BEING SUPPLIED TO MEET THE SPECIFICATIONS. SHOP DRAWINGS : MANUFACTURER SHALL SUBMIT PLAN DRAWINGS OF ALL EQUIPMENT/COMPONENTS, ONE-LINE DIAGRAM, RELAY/DIMMER PANEL SCHEDULES, OVERRIDE DIMMER/SWITCH STATION SCHEDULES, AND PLAN DRAWINGS WITH ALL DEVICE LOCATIONS, INCLUDING PHOTOCELLS, OCCUPANCY SENSORS, SWITCH PACKS, I/O MODULES, OVERRIDE DIMMER/SWITCH LOCATIONS, AND PANEL LOCATIONS. SENSOR COVERAGE AND QUANTITY SHALL BE PROVIDED AS PART OF SHOP DRAWINGS. RISER DIAGRAM : MANUFACTURER SHALL SUBMITA LINE DIAGRAM OF THE SYSTEM CONFIGURATIONS IN SUFFICIENT DETAIL TO SHOW THE RELATIVE PLACEMENT OF ALL EQUIPMENT AND INTERCONNECTION WITH EQUIPMENT SUPPLIED BY OTHER MANUFACTURERS. WIRING DIAGRAMS : MANUFACTURER SHALL SUBMIT TYPICAL WIRING DIAGRAMS FOR ALL COMPONENTS. DETAILED INTERCONNECTION DIAGRAMS ARE REQUIRED ONLY IF PROPER INTERWIRING OF COMPONENTS IS NOT CLEARLY INDICATED ON TYPICAL WIRING DIAGRAMS. PRODUCT OVERVIEW : MANUFACTURER SHALL SUBMIT DATA SHEETS ON ALL COMPONENTS OF THE SYSTEM. THESE SHALL DESCRIBE ALL HARDWARE AND SOFTWARE ITEMS PROVIDED. A DETAILED LINE BY LINE SPECIFICATION COMPLIANCE SHALL ALSO BE INCLUDED. THE SOFTWARE SHALL IDENTIFY THE PROCESS FOR PROGRAMMING REPEATING TIME SCHEDULES. Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 11852 | Review Response | Approved as Noted | 2021-03-05 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.03.05 | Info Exchange
| 15366 | Responded and Closed | Approved as Noted | 2021-03-08 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.03.05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | 26 09 43-1.2 PD Shops Wiring Riser Diagrams-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-02 |  | 26 09 43-1.2 PD Shops Wiring Riser Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-02-01 02:00 |  | 26 09 43-1.2 PD Shops Wiring Riser Diagrams-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-01 02:00 |  | 26 09 43-1.2 PD Shops Wiring Riser Diagrams-MAM.pdf
26 09 43-001-03 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-001-03 NETWORK LIGHTING CONTROL - Revised Network Riser, Ports, and Emergency DMX PD | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-14 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-28 | 2021-06-28 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-06-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13513 | Received | For Review | 2021-06-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-06-28 | Submittal Number: 26 09 43-1.3 From: PATRICK KLEIN Final Due Date: 06/27/21 Subject: NETWORK LIGHTING CONTROL - REVISED NETWORK RISER, PORTS, AND EMERGENCY DMX PD Description: Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 17477 | Forwarded | For Review | 2021-06-14 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-21 | Submittal Number: 26 09 43-1.3 From: PATRICK KLEIN Final Due Date: 06/27/21 Subject: NETWORK LIGHTING CONTROL - REVISED NETWORK RISER, PORTS, AND EMERGENCY DMX PD Description: Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 13691 | Review Response | Approved as Noted | 2021-06-28 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.06.28 | Info Exchange
| 17728 | Responded and Closed | Approved as Noted | 2021-06-28 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.06.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-14 |  | 26 09 43-1.3 Revised Network Riser Ports and EDMX PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-14 |  | 26 09 43-1.3 Revised Network Riser Ports and EDMX PD-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-06-13 02:00 |  | 26 09 43-1.3 Revised Network Riser Ports and EDMX PD-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-28 02:00 |  | 26 09 43-1.3 Revised Network Riser Ports and EDMX PD-MAM-ME_POP.pdf
26 09 43-007-00 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-007-00 NETWORK LIGHTING CONTROL - Maintenance Data | Open - Overdue | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-27 | Forwarded - For Review |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) | 2021-10-04 | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  | 2021-10-11 |  | 11 |  | Record Copies; Transfers; Submittals |  | 11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14706 | Received | For Review | 2021-09-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-10-11 | Submittal Number: 26 09 43-7.0 From: PATRICK KLEIN Final Due Date: 10/10/21 Subject: NETWORK LIGHTING CONTROL - MAINTENANCE DATA Description: MAINTENANCE MANUALS : FURNISH MAINTENANCE MANUALS WHICH CONTAIN EQUIPMENT CUTS, OPERATING INSTRUCTIONS, TROUBLESHOOTING PROCEDURES, AND SPARE PARTS LIST FOR EQUIPMENT. ENSURE MANUAL INCLUDES OPERATING INSTRUCTIONS IN ADDITION TO INSTRUCTIONS FOR MAINTENANCE OF THE SYSTEMS SOFTWARE PACKAGE. Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 18965 | Forwarded | For Review | 2021-09-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-10-04 | Submittal Number: 26 09 43-7.0 From: PATRICK KLEIN Final Due Date: 10/10/21 Subject: NETWORK LIGHTING CONTROL - MAINTENANCE DATA Description: MAINTENANCE MANUALS : FURNISH MAINTENANCE MANUALS WHICH CONTAIN EQUIPMENT CUTS, OPERATING INSTRUCTIONS, TROUBLESHOOTING PROCEDURES, AND SPARE PARTS LIST FOR EQUIPMENT. ENSURE MANUAL INCLUDES OPERATING INSTRUCTIONS IN ADDITION TO INSTRUCTIONS FOR MAINTENANCE OF THE SYSTEMS SOFTWARE PACKAGE. Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-26 |  | 26 09 43-7.0 Maintenance Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-26 |  | 26 09 43-7.0 Maintenance Data-MAM.pdf
26 09 43-008-00 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-008-00 NETWORK LIGHTING CONTROL - Graphics Screens | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-03 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-17 | 2021-03-01 | 27 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11155 | Received | For Review | 2021-02-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-02-17 | Submittal Number: 26 09 43-8.0 From: PATRICK KLEIN Final Due Date: 02/16/21 Subject: NETWORK LIGHTING CONTROL - GRAPHICS SCREENS Description: GRAPHICS SCREENS : MANUFACTURER SHALL SUBMIT GRAPHIC SCREEN LAYOUTS AS PART OFA TWO STEP APPROVAL PROCESS. 1. CONTRACTOR SHALL OBTAIN AND PROVIDE THE MANUFACTURER WITH CURRENT CAD DRAWINGS / REFLECTED CEILING PLANS WITHIN 90 DAYS OF CONTRACT AWARD FOR DEVELOPMENT OF THE GRAPHIC SCREENS. 2. CONTRACTOR SHALL OBTAIN AND PROVIDE THE MANUFACTURER WITH THE LATEST ELECTRONIC CAD OR REVIT FILES FOR USE IN CREATING COLORED LIGHTING CONTROL ZONE DRAWINGS. COLORED LIGHTING CONTROL CONCEPT DRAWINGS ARE AVAILABLE FROM THE DESIGN TEAM. 3. INITIAL GRAPHICS SUBMITTAL: MANUFACTURER SHALL SUBMIT INITIAL GRAPHIC SCREEN LAYOUTS BASED ON THE REQUIREMENTS OF THIS PROJECTA MINIMUM OF SIX MONTHS PRIOR TO SUBSTANTIAL COMPLETION. SAMPLE GRAPHIC SCREENS FROM OTHER PROJECTS ARE NOT ACCEPTABLE. 4. FINAL GRAPHICS SUBMITTAL: MANUFACTURER SHALL SUBMIT FINAL GRAPHIC SCREEN LAYOUTSA MINIMUM OF 60 DAYS PRIOR TO SUBSTANTIAL COMPLETION. Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 14461 | Forwarded | For Review | 2021-02-03 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-10 | Submittal Number: 26 09 43-8.0 From: PATRICK KLEIN Final Due Date: 02/16/21 Subject: NETWORK LIGHTING CONTROL - GRAPHICS SCREENS Description: GRAPHICS SCREENS : MANUFACTURER SHALL SUBMIT GRAPHIC SCREEN LAYOUTS AS PART OFA TWO STEP APPROVAL PROCESS. 1. CONTRACTOR SHALL OBTAIN AND PROVIDE THE MANUFACTURER WITH CURRENT CAD DRAWINGS / REFLECTED CEILING PLANS WITHIN 90 DAYS OF CONTRACT AWARD FOR DEVELOPMENT OF THE GRAPHIC SCREENS. 2. CONTRACTOR SHALL OBTAIN AND PROVIDE THE MANUFACTURER WITH THE LATEST ELECTRONIC CAD OR REVIT FILES FOR USE IN CREATING COLORED LIGHTING CONTROL ZONE DRAWINGS. COLORED LIGHTING CONTROL CONCEPT DRAWINGS ARE AVAILABLE FROM THE DESIGN TEAM. 3. INITIAL GRAPHICS SUBMITTAL: MANUFACTURER SHALL SUBMIT INITIAL GRAPHIC SCREEN LAYOUTS BASED ON THE REQUIREMENTS OF THIS PROJECTA MINIMUM OF SIX MONTHS PRIOR TO SUBSTANTIAL COMPLETION. SAMPLE GRAPHIC SCREENS FROM OTHER PROJECTS ARE NOT ACCEPTABLE. 4. FINAL GRAPHICS SUBMITTAL: MANUFACTURER SHALL SUBMIT FINAL GRAPHIC SCREEN LAYOUTSA MINIMUM OF 60 DAYS PRIOR TO SUBSTANTIAL COMPLETION. Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 11728 | Review Response | Approved as Noted | 2021-02-26 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review and requested CPA logo for use within the lighting control graphics screens. Mark Lievens ME Engineers 2021.02.26 | Info Exchange
| 15200 | Responded and Closed | Approved as Noted | 2021-03-01 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review and requested CPA logo for use within the lighting control graphics screens. Mark Lievens ME Engineers 2021.02.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | 26 09 43-8.0 Graphics Screen Samples-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-02 |  | 26 09 43-8.0 Graphics Screen Samples-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-02-01 02:00 |  | 26 09 43-8.0 Graphics Screen Samples-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-26 02:00 |  | CPA_Stacked.png
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-01 02:00 |  | 26 09 43-8.0 Graphics Screen Samples-MAM-ME_POP.pdf
26 09 43-009-00 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-009-00 NETWORK LIGHTING CONTROLS - Premium Spaces PD and Shops | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-29 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-12 | 2020-11-20 | 23 |  | Record Copies; Transfers; Submittals | 26 09 43-009-01 - 26 09 43-009-00 NETWORK LIGHTING CONTROLS - Premium Spaces PD and Shops | 23 |  | 2020-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09085 | Received | For Review | 2020-10-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-12 | Submittal Number: 26 09 43-9.0 From: PATRICK KLEIN Final Due Date: 11/17/20 Subject: NETWORK LIGHTING CONTROLS - PREMIUM SPACES PD AND SHOPS Description: SPECS SECTION: DESCRIPTION 260933: CENTRAL DIMMING CONTROLS 260943: NETWORK LIGHTING CONTROL Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 11991 | Forwarded | For Review | 2020-10-29 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-05 | Submittal Number: 26 09 43-9.0 From: PATRICK KLEIN Final Due Date: 11/17/20 Subject: NETWORK LIGHTING CONTROLS - PREMIUM SPACES PD AND SHOPS Description: SPECS SECTION: DESCRIPTION 260933: CENTRAL DIMMING CONTROLS 260943: NETWORK LIGHTING CONTROL Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 09652 | Review Response | Approved as Noted/Resubmit | 2020-11-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.20 | Info Exchange
| 12702 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-20 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.20 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-28 |  | 26 09 43-9.0 Premium Spaces PD and Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-28 |  | 26 09 43-9.0 Premium Spaces PD and Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-27 02:00 |  | 26 09 43-9.0 Premium Spaces PD and Shops-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-20 02:00 |  | 26 09 43-9.0 Premium Spaces PD and Shops-MAM-ME_pop.pdf
26 09 43-009-01 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-009-00 NETWORK LIGHTING CONTROLS - Premium Spaces PD and Shops | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 09 43-009-00 - 26 09 43-009-00 NETWORK LIGHTING CONTROLS - Premium Spaces PD and Shops | -1 | 2020-12-04
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-20 02:00 |  | 26 09 43-9.0 Premium Spaces PD and Shops-MAM-ME_pop.pdf
26 09 43-011-00 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-011-00 NETWORK LIGHTING CONTROLS - PD for Finish Selection | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-03 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-17 | 2021-03-02 | 28 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2021-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11156 | Received | For Review | 2021-02-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-02-17 | Submittal Number: 26 09 43-11.0 From: PATRICK KLEIN Final Due Date: 02/16/21 Subject: NETWORK LIGHTING CONTROLS - PD FOR FINISH SELECTION Description: Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 14462 | Forwarded | For Review | 2021-02-03 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-10 | Submittal Number: 26 09 43-11.0 From: PATRICK KLEIN Final Due Date: 02/16/21 Subject: NETWORK LIGHTING CONTROLS - PD FOR FINISH SELECTION Description: Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 11778 | Review Response | Approved as Noted | 2021-02-17 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.02.17 | Info Exchange
| 11756 | Review Response | Approved as Noted | 2021-03-02 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal. Items to match receptacle covers previously selected via RFI and Submittal. | Info Exchange
| 15233 | Responded and Closed | Approved as Noted | 2021-03-02 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal. Items to match receptacle covers previously selected via RFI and Submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | 26 09 43-11.0 PD for Finish Selection-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-02 |  | 26 09 43-11.0 PD for Finish Selection-MAM.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-02-01 02:00 |  | 26 09 43-11.0 PD for Finish Selection-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-02 |  | 26 09 43-1.1 SCA Network Lighting Control Submittal Review_ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-02 |  | 26 09 43-11.0 PD for Finish Selection-MAM.pdf
26 09 43-012-00 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-012-00 NETWORK LIGHTING CONTROLS - Updated Base Scope Shop Drawings through CCD 073 | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-03 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-23 08:00 | 2021-03-08 | 34 |  | Record Copies; Transfers; Submittals |  | 34 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11157 | Received | For Review | 2021-02-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction) | 2021-02-23 08:00 | Submittal Number: 26 09 43-12.0 From: PATRICK KLEIN Final Due Date: 02/16/21 Subject: NETWORK LIGHTING CONTROLS - UPDATED BASE SCOPE SHOP DRAWINGS THROUGH CCD 073 Description: Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 14463 | Forwarded | For Review | 2021-02-03 | Patrick Klein (Mortenson Construction) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-10 | Submittal Number: 26 09 43-12.0 From: PATRICK KLEIN Final Due Date: 02/16/21 Subject: NETWORK LIGHTING CONTROLS - UPDATED BASE SCOPE SHOP DRAWINGS THROUGH CCD 073 Description: Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 11851 | Review Response | Approved as Noted | 2021-03-08 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.03.08 | Info Exchange
| 15365 | Responded and Closed | Approved as Noted | 2021-03-08 | Patrick Klein (Mortenson Construction) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.03.08 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-02 |  | 26 09 43-12.0 Shops through CCD 073-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2021-02-02 |  | 26 09 43-12.0 Shops through CCD 073-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-02-01 02:00 |  | 26 09 43-12.0 Shops through CCD 073-MAM.pdf
| Responded and Closed |  | Patrick Klein (Mortenson Construction) | 1 | 2021-03-08 02:00 |  | 26 09 43-12.0 Shops through CCD 073-MAM-ME Review_POP.pdf
26 09 43-013-00 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-013-00 Lutron One-Line Diagrams | Closed | Lighting, Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-10 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-06-24 | 2021-07-02 | 23 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13484 | Received | For Review | 2021-06-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-24 | Submittal Number: 26 09 43-13.0 From: CODY STIERITZ Final Due Date: 06/24/21 Subject: LUTRON ONE-LINE DIAGRAMS Description: Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 17437 | Forwarded | For Review | 2021-06-10 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-17 | Submittal Number: 26 09 43-13.0 From: CODY STIERITZ Final Due Date: 06/24/21 Subject: LUTRON ONE-LINE DIAGRAMS Description: Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 17717 | Forwarded | For Review | 2021-06-28 | Populous SCA_CCA | Nick Theimer (ME Engineers); Michael Mazzocchi (ME Engineers) | 2021-06-24 | Submittal Number: 26 09 43-13.0 From: CODY STIERITZ Final Due Date: 06/24/21 Subject: LUTRON ONE-LINE DIAGRAMS Description: Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 13766 | Review Response | Approved as Noted | 2021-06-29 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.06.29 | Info Exchange
| 17818 | Responded and Closed | Approved as Noted | 2021-07-02 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.06.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-10 |  | 26 09 43-13.0 Lutron One-Line Diagrams_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-10 |  | 26 09 43-13.0 Lutron One-Line Diagrams_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-09 02:00 |  | 26 09 43-13.0 Lutron One-Line Diagrams_MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-06-10 |  | 26 09 43-13.0 Lutron One-Line Diagrams_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-02 |  | 26 09 43-13.0 Lutron One-Line Diagrams_MAM_ME_POP.pdf
26 09 43-014-00 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-014-00 NETWORK LIGHTING CONTROLS - Emergency Stair Lighting Inverter PD | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-08 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-22 | 2021-07-13 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13842 | Received | For Review | 2021-07-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-07-22 | Submittal Number: 26 09 43-14.0 From: PATRICK KLEIN Final Due Date: 07/22/21 Subject: NETWORK LIGHTING CONTROLS - EMERGENCY STAIR LIGHTING INVERTER PD Description: Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 17917 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-15 | Submittal Number: 26 09 43-14.0 From: PATRICK KLEIN Final Due Date: 07/22/21 Subject: NETWORK LIGHTING CONTROLS - EMERGENCY STAIR LIGHTING INVERTER PD Description: Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 13908 | Review Response | Approved as Noted | 2021-07-13 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.07.13 | Info Exchange
| 18012 | Responded and Closed | Approved as Noted | 2021-07-13 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.07.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-08 |  | 26 09 43-14.0 Emergency Stair Lighting Inverter PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-08 |  | 26 09 43-14.0 Emergency Stair Lighting Inverter PD-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-07 02:00 |  | 26 09 43-14.0 Emergency Stair Lighting Inverter PD-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-07-13 02:00 |  | 26 09 43-14.0 Emergency Stair Lighting Inverter PD-MAM-ME_POP.pdf
26 09 43-015-00 | 26 09 43 - NETWORK LIGHTING CONTROL | 26 09 43-015-00 19155-S0045 O&M Lighting Controls | Open - Overdue | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-15 | Forwarded - For Review |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) | 2021-09-22 | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  | 2021-10-05 07:00 |  | 23 |  | Record Copies; Transfers; Submittals |  | 23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14653 | Received | For Review | 2021-09-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-10-05 07:00 | Submittal Number: 26 09 43-15.0 From: BINH DUONG Final Due Date: 09/09/21 Subject: 19155-S0045 O&M LIGHTNG CONTROLS Description: SUBMITTAL OVERVIEW: OPERATION & MAINTENANCE MANUALS PER OUR VENDOR - NORTH COAST Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 18892 | Forwarded | For Review | 2021-09-15 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-09-22 | Submittal Number: 26 09 43-15.0 From: BINH DUONG Final Due Date: 09/09/21 Subject: 19155-S0045 O&M LIGHTNG CONTROLS Description: SUBMITTAL OVERVIEW: OPERATION & MAINTENANCE MANUALS PER OUR VENDOR - NORTH COAST Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| 18893 | Forwarded | For Review | 2021-09-15 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-09-22 | Submittal Number: 26 09 43-15.0 From: BINH DUONG Final Due Date: 09/09/21 Subject: 19155-S0045 O&M LIGHTNG CONTROLS Description: SUBMITTAL OVERVIEW: OPERATION & MAINTENANCE MANUALS PER OUR VENDOR - NORTH COAST Spec Section: 26 09 43 - NETWORK LIGHTING CONTROLS Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-01 |  | 26 51 13-44.0 O&M Lighting.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-09-01 |  | 26 51 13-44.0 O&M Lighting.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-09-01 |  | 26 51 13-44.0 O&M Lighting.pdf
26 11 16-001-00 | 26 11 16 - SECONDARY UNIT SUBSTATIONS | 26 11 16-001-00 SECONDARY UNIT SUBSTATIONS - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-09 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-23 | 2019-11-05 | 28 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2019-11-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02707 | Received | For Review | 2019-10-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-10-23 | Submittal Number: 26 11 16-1.0 From: PATRICK KLEIN Final Due Date: 10/22/19 Subject: SECONDARY UNIT SUBSTATIONS - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS TECHNICAL PRODUCT DATA, INCLUDING, BUT NOT LIMITED TO, SPECIFICATIONS, SERVICE VOLTAGES, NUMBER OF PHASES, MAIN BUS CURRENT RATINGS AND INTERRUPTING CAPACITIES, FURNISHED SPECIALTIES AND ACCESSORIES FOR SECONDARY UNIT SUBSTATIONS. ALSO PROVIDE METERING EQUIPMENT TYPES AND THEIR OPERATIONAL CAPABILITIES. Spec Section: 26 11 16 - SECONDARY UNIT SUBSTATIONS Status: OPEN | Info Exchange
| 04040 | Forwarded | For Review | 2019-10-09 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-16 | Submittal Number: 26 11 16-1.0 From: PATRICK KLEIN Final Due Date: 10/22/19 Subject: SECONDARY UNIT SUBSTATIONS - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS TECHNICAL PRODUCT DATA, INCLUDING, BUT NOT LIMITED TO, SPECIFICATIONS, SERVICE VOLTAGES, NUMBER OF PHASES, MAIN BUS CURRENT RATINGS AND INTERRUPTING CAPACITIES, FURNISHED SPECIALTIES AND ACCESSORIES FOR SECONDARY UNIT SUBSTATIONS. ALSO PROVIDE METERING EQUIPMENT TYPES AND THEIR OPERATIONAL CAPABILITIES. Spec Section: 26 11 16 - SECONDARY UNIT SUBSTATIONS Status: OPEN | Info Exchange
| 03072 | Review Response | Approved as Noted/Resubmit | 2019-11-05 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2019.11.05 | Info Exchange
| 04471 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2019.11.05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-08 |  | 26 11 16-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-08 |  | 26 11 16-1.0 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-10-07 02:00 |  | 26 11 16-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-05 02:00 |  | 26 11 16-1.0 Product Data-MAM - ME Review_POP.pdf
26 11 16-001-01 | 26 11 16 - SECONDARY UNIT SUBSTATIONS | 26 11 16-001-01 SECONDARY UNIT SUBSTATIONS - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-11 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-11-25 | 2019-11-26 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-11-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03153 | Received | For Review | 2019-11-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-11-25 | Submittal Number: 26 11 16-1.1 From: PATRICK KLEIN Final Due Date: 11/24/19 Subject: SECONDARY UNIT SUBSTATIONS - PRODUCT DATA Description: SUBMIT UNIT SUBSTATION PRODUCT DATA AND SHOP DRAWINGS. PROVIDE SHOP DRAWINGS SHOWING FULL PRIMARY SWITCH, UNIT, SUBSTATIONS, AND 480V SWITCHBOARD LINEUP. Spec Section: 26 11 16 - SECONDARY UNIT SUBSTATIONS Status: OPEN | Info Exchange
| 04573 | Forwarded | For Review | 2019-11-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-18 | Submittal Number: 26 11 16-1.1 From: PATRICK KLEIN Final Due Date: 11/24/19 Subject: SECONDARY UNIT SUBSTATIONS - PRODUCT DATA Description: SUBMIT UNIT SUBSTATION PRODUCT DATA AND SHOP DRAWINGS. PROVIDE SHOP DRAWINGS SHOWING FULL PRIMARY SWITCH, UNIT, SUBSTATIONS, AND 480V SWITCHBOARD LINEUP. Spec Section: 26 11 16 - SECONDARY UNIT SUBSTATIONS Status: OPEN | Info Exchange
| 03386 | Review Response | Approved as Noted/Resubmit | 2019-11-26 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.11.26 | Info Exchange
| 04849 | Responded and Closed | Approved as Noted/Resubmit | 2019-11-26 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.11.26 Refer to disposition sheet for specified items to resubmit. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-10 |  | 26 11 16-1.1 Product Data and Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-10 |  | 26 11 16-1.1 Product Data and Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-11-09 02:00 |  | 26 11 16-1.1 Product Data and Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-26 02:00 |  | 26 11 16-1.1 Product Data and Shop Drawings-MAM-ME_POP.pdf
26 11 16-001-02 | 26 11 16 - SECONDARY UNIT SUBSTATIONS | 26 11 16-001-02 SECONDARY UNIT SUBSTATIONS - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-02 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-22 | 2020-01-08 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03750 | Received | For Review | 2020-01-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-22 | Submittal Number: 26 11 16-1.2 From: PATRICK KLEIN Final Due Date: 01/15/20 Subject: SECONDARY UNIT SUBSTATIONS - PRODUCT DATA Description: RESUBMIT SHOP DRAWINGS OF ENLARGED ELECTRICAL ROOMS AS WELL AS FULL 480V SWITCHBOARD LINEUP. Spec Section: 26 11 16 - SECONDARY UNIT SUBSTATIONS Status: OPEN | Info Exchange
| 05284 | Forwarded | For Review | 2020-01-02 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-09 | Submittal Number: 26 11 16-1.2 From: PATRICK KLEIN Final Due Date: 01/15/20 Subject: SECONDARY UNIT SUBSTATIONS - PRODUCT DATA Description: RESUBMIT SHOP DRAWINGS OF ENLARGED ELECTRICAL ROOMS AS WELL AS FULL 480V SWITCHBOARD LINEUP. Spec Section: 26 11 16 - SECONDARY UNIT SUBSTATIONS Status: OPEN | Info Exchange
| 05313 | Sent | For Information Only | 2020-01-03 | Josh Dobken (Populous) | Bryan Klote (Populous); Mark Lievens (ME Engineers) |  | Please use this updated submittal for your review, with revisions to page 63. | Info Exchange
| 03847 | Review Response | Approved as Noted | 2020-01-08 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.08 | Info Exchange
| 05394 | Responded and Closed | Approved as Noted | 2020-01-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.08 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-31 |  | 26 11 16-1.2 Product Data and Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-31 |  | 26 11 16-1.2 Product Data and Shop Drawings-MAM.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-01-03 02:00 |  | 26 11 16-1.2 Product Data and Shop Drawings-MAM_revision 1.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-12-30 02:00 |  | 26 11 16-1.2 Product Data and Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-08 02:00 |  | 26 11 16-1.2 Product Data and Shop Drawings-MAM_revision 1_ME Review_POP.pdf
26 11 16-001-04 | 26 11 16 - SECONDARY UNIT SUBSTATIONS | 26 11 16-001-04 Secondary Unit Substations | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-26 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-13 07:00 | 2020-07-06 | 11 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-07-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06643 | Received | For Review | 2020-06-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company) | 2020-07-13 07:00 | Submittal Number: 26 11 16-1.4 From: PATRICK KLEIN Final Due Date: 07/10/20 Subject: SECONDARY UNIT SUBSTATIONS Description: Spec Section: 26 11 16 - SECONDARY UNIT SUBSTATIONS Status: OPEN | Info Exchange
| 08948 | Forwarded | For Review | 2020-06-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-06 | Submittal Number: 26 11 16-1.4 From: PATRICK KLEIN Final Due Date: 07/10/20 Subject: SECONDARY UNIT SUBSTATIONS Description: Spec Section: 26 11 16 - SECONDARY UNIT SUBSTATIONS Status: OPEN | Info Exchange
| 06872 | Review Response | Approved as Noted | 2020-07-01 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. This submittal was marked as HOT by Mortenson/Cochran and needs and expedited return and review from TT prior to the holiday weekend. I'll be sending a follow up email to them clarifying the weights included within this submittal to assist with their quick review. Thank you, Mark Lievens ME Engineers 2020.07.01 | Info Exchange
| 09049 | Forwarded | For Review | 2020-07-01 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McN... | 2020-07-08 | Submittal Number: 26 11 16-1.4 From: PATRICK KLEIN Final Due Date: 07/10/20 Subject: SECONDARY UNIT SUBSTATIONS Description: Spec Section: 26 11 16 - SECONDARY UNIT SUBSTATIONS Status: OPEN | Info Exchange
| 06873 | Review Response | Approved as Noted | 2020-07-02 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | See comments in attached submittal. TT's review is partially based on information provided by ME Engineers, see attached. | Info Exchange
| 09106 | Responded and Closed | Approved as Noted | 2020-07-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments in attached submittal. TT's review is partially based on information provided by ME Engineers, see attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-26 |  | 26 11 16-1.4 Secondary Unit Substations.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-26 |  | 26 11 16-1.4 Secondary Unit Substations.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-06-25 02:00 |  | 26 11 16-1.4 Secondary Unit Substations.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-25 02:00 |  | 26 11 16-1.4 Secondary Unit Substations.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-06-25 02:00 |  | 26 11 16-1.4 Secondary Unit Substations.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-06 |  | 26 11 16-1.4 Secondary Unit Substations - ME_TT_POP.pdf
26 11 16-005-00 | 26 11 16 - SECONDARY UNIT SUBSTATIONS | 26 11 16-005-00 SECONDARY UNIT SUBSTATIONS - Factory Test Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-15 | Responded and Closed - No Action Taken or Required |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-29 | 2020-08-06 | 23 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06961 | Received | For Review | 2020-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-29 | Submittal Number: 26 11 16-5.0 From: PATRICK KLEIN Final Due Date: 07/28/20 Subject: SECONDARY UNIT SUBSTATIONS - FACTORY TEST DATA Description: FACTORY TEST DATA : PROVIDE FACTORY TEST DATA CERTIFIED BY PROFESSIONAL ENGINEER THAT SECONDARY UNIT SUBSTATION TEST RESULTS FULFILL SPECIFIED REQUIREMENTS. TEST HIGH-VOLTAGE INCOMING SECTION, TRANSFORMER SECTION, AND LOW-VOLTAGE OUTGOING SECTION IN ACCORDANCE WITH IEEE C37.20. Spec Section: 26 11 16 - SECONDARY UNIT SUBSTATIONS Status: OPEN | Info Exchange
| 09329 | Forwarded | For Review | 2020-07-15 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-22 | Submittal Number: 26 11 16-5.0 From: PATRICK KLEIN Final Due Date: 07/28/20 Subject: SECONDARY UNIT SUBSTATIONS - FACTORY TEST DATA Description: FACTORY TEST DATA : PROVIDE FACTORY TEST DATA CERTIFIED BY PROFESSIONAL ENGINEER THAT SECONDARY UNIT SUBSTATION TEST RESULTS FULFILL SPECIFIED REQUIREMENTS. TEST HIGH-VOLTAGE INCOMING SECTION, TRANSFORMER SECTION, AND LOW-VOLTAGE OUTGOING SECTION IN ACCORDANCE WITH IEEE C37.20. Spec Section: 26 11 16 - SECONDARY UNIT SUBSTATIONS Status: OPEN | Info Exchange
| 07430 | Review Response | No Action Taken or Required | 2020-07-27 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.27 | Info Exchange
| 09897 | Responded and Closed | No Action Taken or Required | 2020-08-06 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-14 |  | 26 11 16-5.0 Factory Test Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-14 |  | 26 11 16-5.0 Factory Test Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-13 02:00 |  | 26 11 16-5.0 Factory Test Data-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-06 02:00 |  | 26 11 16-5.0 Factory Test Data-MAM-ME_pop.pdf
26 13 13-001-00 | 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR | 26 13 13-001-00: MED VOLTAGE CIRCUIT BREAKER SWITCHGEAR - PD, SD, Wiring Diagrams | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-10 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-02 | 2020-01-08 | 30 | General | Record Copies; Transfers; Submittals |  | 30 |  | 2020-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03576 | Received | For Review | 2019-12-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-02 | Submittal Number: 26 13 13-1.0 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON SWITCHGEAR INCLUDING, BUT NOT LIMITED TO, SERVICE VOLTAGES, NUMBER OF PHASES, FREQUENCIES, MAIN BUS CURRENT RATINGS, AND METERING EQUIPMENT TYPES AND FUNCTIONS. SHOP DRAWINGS : SUBMIT SCALE PLAN VIEW LAYOUT DRAWINGS OF SWITCHGEAR SHOWING ACCURATELY SCALED BASIC EQUIPMENT SECTIONS, AUXILIARY COMPARTMENTS AND INTERRUPTER SECTION. IN ADDITION, SHOW FRONT VIEW FOR EACH BAY AND SPATIAL RELATIONSHIPS OF UNITS TO ASSOCIATED EQUIPMENT. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR SWITCHGEAR SHOWING CONNECTIONS TO ELECTRICAL POWER FEEDERS AND DISTRIBUTION BRANCHES. DIFFERENTIATE BETWEEN PORTIONS OF ELECTRICAL WIRING THAT ARE MANUFACTURER-INSTALLED AND PORTIONS THAT ARE FIELD-INSTALLED. CERTIFIED TRIP CURVES FOR EACH SPECIFIED PRODUCT; ALL DESIGN VERIFICATION TEST REPORTS. THESE CURVES AND EQUIPMENT SHALL BE SUBMITTED TO SEATTLE CITY LIGHT FOR REVIEW AND APPROVAL PRIOR TO FABRICATING. Spec Section: 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR Status: OPEN | Info Exchange
| 05056 | Forwarded | For Review | 2019-12-10 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-17 | Submittal Number: 26 13 13-1.0 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON SWITCHGEAR INCLUDING, BUT NOT LIMITED TO, SERVICE VOLTAGES, NUMBER OF PHASES, FREQUENCIES, MAIN BUS CURRENT RATINGS, AND METERING EQUIPMENT TYPES AND FUNCTIONS. SHOP DRAWINGS : SUBMIT SCALE PLAN VIEW LAYOUT DRAWINGS OF SWITCHGEAR SHOWING ACCURATELY SCALED BASIC EQUIPMENT SECTIONS, AUXILIARY COMPARTMENTS AND INTERRUPTER SECTION. IN ADDITION, SHOW FRONT VIEW FOR EACH BAY AND SPATIAL RELATIONSHIPS OF UNITS TO ASSOCIATED EQUIPMENT. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR SWITCHGEAR SHOWING CONNECTIONS TO ELECTRICAL POWER FEEDERS AND DISTRIBUTION BRANCHES. DIFFERENTIATE BETWEEN PORTIONS OF ELECTRICAL WIRING THAT ARE MANUFACTURER-INSTALLED AND PORTIONS THAT ARE FIELD-INSTALLED. CERTIFIED TRIP CURVES FOR EACH SPECIFIED PRODUCT; ALL DESIGN VERIFICATION TEST REPORTS. THESE CURVES AND EQUIPMENT SHALL BE SUBMITTED TO SEATTLE CITY LIGHT FOR REVIEW AND APPROVAL PRIOR TO FABRICATING. Spec Section: 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR Status: OPEN | Info Exchange
| 05102 | Forwarded | For Review | 2019-12-12 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti) | 2019-12-19 | Submittal Number: 26 13 13-1.0 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON SWITCHGEAR INCLUDING, BUT NOT LIMITED TO, SERVICE VOLTAGES, NUMBER OF PHASES, FREQUENCIES, MAIN BUS CURRENT RATINGS, AND METERING EQUIPMENT TYPES AND FUNCTIONS. SHOP DRAWINGS : SUBMIT SCALE PLAN VIEW LAYOUT DRAWINGS OF SWITCHGEAR SHOWING ACCURATELY SCALED BASIC EQUIPMENT SECTIONS, AUXILIARY COMPARTMENTS AND INTERRUPTER SECTION. IN ADDITION, SHOW FRONT VIEW FOR EACH BAY AND SPATIAL RELATIONSHIPS OF UNITS TO ASSOCIATED EQUIPMENT. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR SWITCHGEAR SHOWING CONNECTIONS TO ELECTRICAL POWER FEEDERS AND DISTRIBUTION BRANCHES. DIFFERENTIATE BETWEEN PORTIONS OF ELECTRICAL WIRING THAT ARE MANUFACTURER-INSTALLED AND PORTIONS THAT ARE FIELD-INSTALLED. CERTIFIED TRIP CURVES FOR EACH SPECIFIED PRODUCT; ALL DESIGN VERIFICATION TEST REPORTS. THESE CURVES AND EQUIPMENT SHALL BE SUBMITTED TO SEATTLE CITY LIGHT FOR REVIEW AND APPROVAL PRIOR TO FABRICATING. Spec Section: 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR Status: OPEN | Info Exchange
| 03643 | Review Response | Approved | 2019-12-13 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  | TT takes no exceptions. Please see attached TT's review of this submittal. SDK ¦ TT ¦ 12/13/2019 | Info Exchange
| 03843 | Review Response | Approved as Noted | 2020-01-08 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.08 | Info Exchange
| 05391 | Responded and Closed | Approved as Noted | 2020-01-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Samar Kenkre (Thornton Tomasetti) Remarks: TT takes no exceptions. Please see attached TT's review of this submittal. SDK ¦ TT ¦ 12/13/2019 Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.08 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-09 02:00 |  | 26 13 13-1.0 PD, Shops, and Wiring Diagrams-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 26 13 13-1.0 PD, Shops, and Wiring Diagrams-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 26 13 13-1.0 PD, Shops, and Wiring Diagrams-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-12-09 02:00 |  | 26 13 13-1.0 PD, Shops, and Wiring Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-12-09 02:00 |  | 26 13 13-1.0 PD, Shops, and Wiring Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-08 02:00 |  | 26 13 13-1.0 PD, Shops, and Wiring Diagrams-MAM-ME Review_POP.pdf
26 13 13-001-01 | 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR | 26 13 13-001-01 MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - Sustainability Revisions | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-04 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-18 | 2020-05-06 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05685 | Received | For Review | 2020-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-05-18 | Submittal Number: 26 13 13-1.1 From: PATRICK KLEIN Final Due Date: 05/15/20 Subject: MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - SUSTAINABILITY REVISIONS Description: Spec Section: 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR Status: OPEN | Info Exchange
| 07696 | Forwarded | For Review | 2020-05-04 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-11 | Submittal Number: 26 13 13-1.1 From: PATRICK KLEIN Final Due Date: 05/15/20 Subject: MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - SUSTAINABILITY REVISIONS Description: Spec Section: 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR Status: OPEN | Info Exchange
| 05753 | Review Response | Approved as Noted | 2020-05-06 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens | Info Exchange
| 07810 | Responded and Closed | Approved as Noted | 2020-05-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-01 |  | 26 13 13-1.1 Sustainability Revisions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-01 |  | 26 13 13-1.1 Sustainability Revisions-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-30 02:00 |  | 26 13 13-1.1 Sustainability Revisions-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-06 02:00 |  | 26 13 13-1.1 Sustainability Revisions-MAM-ME_POP.pdf
26 13 13-004-00 | 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR | 26 13 13-004-00 MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - Product Data and Manufacturers Instructions | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-14 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-28 | 2020-01-30 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-01-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03908 | Received | For Review | 2020-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-28 | Submittal Number: 26 13 13-4.0 From: PATRICK KLEIN Final Due Date: 01/27/20 Subject: MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - PRODUCT DATA AND MANUFACTURERS INSTRUCTIONS Description: THE MANUFACTURER SHALL FURNISHA COMPREHENSIVE INSTRUCTION MANUAL COVERING INSTALLATION OF SWITCHGEAR ASSEMBLY AND OPERATION OF VARIOUS COMPONENTS. Spec Section: 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR Status: OPEN | Info Exchange
| 05467 | Forwarded | For Review | 2020-01-14 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-21 | Submittal Number: 26 13 13-4.0 From: PATRICK KLEIN Final Due Date: 01/27/20 Subject: MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - PRODUCT DATA AND MANUFACTURERS INSTRUCTIONS Description: THE MANUFACTURER SHALL FURNISHA COMPREHENSIVE INSTRUCTION MANUAL COVERING INSTALLATION OF SWITCHGEAR ASSEMBLY AND OPERATION OF VARIOUS COMPONENTS. Spec Section: 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR Status: OPEN | Info Exchange
| 04147 | Review Response | Approved as Noted | 2020-01-29 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.01.29 | Info Exchange
| 05751 | Responded and Closed | Approved as Noted | 2020-01-30 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.01.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-13 |  | 26 13 13-4.0 PD and Manufacturers Instructions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-13 |  | 26 13 13-4.0 PD and Manufacturers Instructions-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-12 02:00 |  | 26 13 13-4.0 PD and Manufacturers Instructions-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-30 02:00 |  | 26 13 13-4.0 PD and Manufacturers Instructions-MAM-ME_POP.pdf
26 13 13-008-00 | 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR | 26 13 13-008-00 MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - Quality Control | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-19 | 2020-10-19 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-10-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08567 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 26 13 13-8.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - QUALITY CONTROL Description: SUBMIT ALL TEST RESULTS TO ENGINEER FOR APPROVAL. Spec Section: 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR Status: OPEN | Info Exchange
| 11328 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-12 | Submittal Number: 26 13 13-8.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: MEDIUM VOLTAGE CIRCUIT BREAKER SWITCHGEAR - QUALITY CONTROL Description: SUBMIT ALL TEST RESULTS TO ENGINEER FOR APPROVAL. Spec Section: 26 13 13 - MEDIUM-VOLTAGE CIRCUIT BREAKER SWITCHGEAR Status: OPEN | Info Exchange
| 08839 | Review Response | Approved | 2020-10-16 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.10.16 | Info Exchange
| 11680 | Responded and Closed | Approved | 2020-10-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.10.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 26 13 13-8.0 MV1 GDB1 and GDB2 Quality Control Reports-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 26 13 13-8.0 MV1 GDB1 and GDB2 Quality Control Reports-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-05 |  | 26 13 13-8.0 MV1 GDB1 and GDB2 Quality Control Reports-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-19 |  | 26 13 13-8.0 MV1 GDB1 and GDB2 Quality Control Reports-MAM-ME_POP.pdf
26 22 13-001-00 | 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS | 26 22 13-001-00 LOW VOLTAGE DISTRIBUTION TRANSFORMERS - General | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Allison Wood (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-20 | 2020-02-12 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2020-02-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04241 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-02-20 | Submittal Number: 26 22 13-1.0 From: PATRICK KLEIN Final Due Date: 02/21/20 Subject: LOW VOLTAGE DISTRIBUTION TRANSFORMERS - GENERAL Description: GENERAL: SUBMIT THE FOLLOWING IN ACCORDANCE WITH CONDITIONS OF CONTRACT AND DIVISION 01 SPECIFICATION SECTIONS: 1. PRODUCT DATA FOR EACH TRANSFORMER, INCLUDING DIMENSIONAL FLOOR PLANS OF ELECTRICAL ROOMS,- SECTIONS, AND ELEVATIONS SHOWING MINIMUM CLEARANCES, INSTALLED DEVICES, AND MATERIAL LISTS. 2. TRANSFORMER PHYSICAL CHARACTERISTICS, INCLUDING DIMENSIONS, WEIGHT, KVA RATING, VOLTAGE,- % IMPEDANCE, TAPS, INSULATION CLASS AND SOUND LEVELS. 3. WIRING DIAGRAMS FROM MANUFACTURER DIFFERENTIATING BETWEEN MANUFACTURER-INSTALLED AND- FIELD-INSTALLED WIRING. 4. TRANSFORMER NO-LOAD LOSSES AND EFFICIENCY RATINGS.- 5. PRODUCT CERTIFICATES, SIGNED BY MANUFACTURER OF TRANSFORMERS CERTIFYING THAT THEIR PRODUCTS- COMPLY WITH THE SPECIFIED REQUIREMENTS. Spec Section: 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS Status: OPEN | Info Exchange
| 05871 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Allison Wood (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-13 | Submittal Number: 26 22 13-1.0 From: PATRICK KLEIN Final Due Date: 02/21/20 Subject: LOW VOLTAGE DISTRIBUTION TRANSFORMERS - GENERAL Description: GENERAL: SUBMIT THE FOLLOWING IN ACCORDANCE WITH CONDITIONS OF CONTRACT AND DIVISION 01 SPECIFICATION SECTIONS: 1. PRODUCT DATA FOR EACH TRANSFORMER, INCLUDING DIMENSIONAL FLOOR PLANS OF ELECTRICAL ROOMS,- SECTIONS, AND ELEVATIONS SHOWING MINIMUM CLEARANCES, INSTALLED DEVICES, AND MATERIAL LISTS. 2. TRANSFORMER PHYSICAL CHARACTERISTICS, INCLUDING DIMENSIONS, WEIGHT, KVA RATING, VOLTAGE,- % IMPEDANCE, TAPS, INSULATION CLASS AND SOUND LEVELS. 3. WIRING DIAGRAMS FROM MANUFACTURER DIFFERENTIATING BETWEEN MANUFACTURER-INSTALLED AND- FIELD-INSTALLED WIRING. 4. TRANSFORMER NO-LOAD LOSSES AND EFFICIENCY RATINGS.- 5. PRODUCT CERTIFICATES, SIGNED BY MANUFACTURER OF TRANSFORMERS CERTIFYING THAT THEIR PRODUCTS- COMPLY WITH THE SPECIFIED REQUIREMENTS. Spec Section: 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS Status: OPEN | Info Exchange
| 04332 | Review Response | Approved as Noted/Resubmit | 2020-02-12 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.12 | Info Exchange
| 05993 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.12 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 26 22 13-1.0 PD and Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | 26 22 13-1.0 PD and Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-05 02:00 |  | 26 22 13-1.0 PD and Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-12 02:00 |  | 26 22 13-1.0 PD and Drawings-MAM-ME_POP.pdf
26 22 13-001-01 | 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS | 26 22 13-001-01 LOW VOLTAGE DISTRIBUTION TRANSFORMERS - General | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-12 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Allison Wood (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-26 | 2020-03-18 | 7 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04776 | Received | For Review | 2020-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-03-26 | Submittal Number: 26 22 13-1.1 From: PATRICK KLEIN Final Due Date: 03/25/20 Subject: LOW VOLTAGE DISTRIBUTION TRANSFORMERS - GENERAL Description: SUBMIT HMT TRANSFORMERS FOR REVIEW AND APPROVAL Spec Section: 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS Status: OPEN | Info Exchange
| 06551 | Forwarded | For Review | 2020-03-12 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Allison Wood (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-19 | Submittal Number: 26 22 13-1.1 From: PATRICK KLEIN Final Due Date: 03/25/20 Subject: LOW VOLTAGE DISTRIBUTION TRANSFORMERS - GENERAL Description: SUBMIT HMT TRANSFORMERS FOR REVIEW AND APPROVAL Spec Section: 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS Status: OPEN | Info Exchange
| 04935 | Review Response | Approved as Noted | 2020-03-15 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.15 | Info Exchange
| 06731 | Responded and Closed | Approved as Noted | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-12 |  | 26 22 13-1.1 PD and Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-12 |  | 26 22 13-1.1 PD and Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-11 02:00 |  | 26 22 13-1.1 PD and Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-18 02:00 |  | 26 22 13-1.1 PD and Drawings-MAM-ME_POP.pdf
26 22 13-011-00 | 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS | 26 22 13-011-00 CCD 046 Permanent Bressi Refeed Equipment | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-10 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-24 | 2020-03-18 | 9 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04725 | Received | For Review | 2020-03-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-03-24 | Submittal Number: 26 22 13-11.0 From: PATRICK KLEIN Final Due Date: 03/23/20 Subject: CCD 046 PERMANENT BRESSI REFEED EQUIPMENT Description: Spec Section: 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS Status: OPEN | Info Exchange
| 06492 | Forwarded | For Review | 2020-03-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-17 | Submittal Number: 26 22 13-11.0 From: PATRICK KLEIN Final Due Date: 03/23/20 Subject: CCD 046 PERMANENT BRESSI REFEED EQUIPMENT Description: Spec Section: 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS Status: OPEN | Info Exchange
| 04934 | Review Response | Approved as Noted/Resubmit | 2020-03-15 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.15 | Info Exchange
| 06730 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-09 |  | 26 22 13-11.0 CCD 046 Permanent Bressi Refeed Equipment-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-09 |  | 26 22 13-11.0 CCD 046 Permanent Bressi Refeed Equipment-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-08 03:00 |  | 26 22 13-11.0 CCD 046 Permanent Bressi Refeed Equipment-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-18 02:00 |  | 26 22 13-11.0 CCD 046 Permanent Bressi Refeed Equipment-MAM-ME_POP.pdf
26 22 13-011-01 | 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS | 26 22 13-011-01 CCD 046 Permanent Bressi Refeed Equipment | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-27 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-13 07:00 | 2020-04-17 | 22 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-04-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05074 | Received | For Review | 2020-03-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-13 07:00 | Submittal Number: 26 22 13-11.1 From: PATRICK KLEIN Final Due Date: 04/09/20 Subject: CCD 046 PERMANENT BRESSI REFEED EQUIPMENT Description: SUBMIT TENANT METERING EQUIPMENT Spec Section: 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS Status: OPEN | Info Exchange
| 06899 | Forwarded | For Review | 2020-03-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-03 | Submittal Number: 26 22 13-11.1 From: PATRICK KLEIN Final Due Date: 04/09/20 Subject: CCD 046 PERMANENT BRESSI REFEED EQUIPMENT Description: SUBMIT TENANT METERING EQUIPMENT Spec Section: 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS Status: OPEN | Info Exchange
| 05415 | Review Response | Approved as Noted | 2020-04-15 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.15 | Info Exchange
| 07353 | Responded and Closed | Approved as Noted | 2020-04-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-26 |  | 26 22 13-11.1 CCD 046 Permanent Bressi Refeed Equipment-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-26 |  | 26 22 13-11.1 CCD 046 Permanent Bressi Refeed Equipment-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-25 02:00 |  | 26 22 13-11.1 CCD 046 Permanent Bressi Refeed Equipment-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-17 02:00 |  | 26 22 13-11.1 CCD 046 Permanent Bressi Refeed Equipment-MAM-ME_POP.pdf
26 22 13-012-00 | 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS | 26 22 13-012-00 LOW VOLTAGE DISTRIBUTION TRANSFORMERS - CCD 065 Sustainability Equipment | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-14 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-07-28 | 2020-08-03 | 21 |  | Record Copies; Transfers; Submittals | 26 22 13-012-00-01 - 26 22 13-012-00 LOW VOLTAGE DISTRIBUTION TRANSFORMERS - CCD 065 Sustainability Equipment | 17 |  | 2020-08-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06947 | Received | For Review | 2020-07-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-28 | Submittal Number: 26 22 13-12.0 From: PATRICK KLEIN Final Due Date: 07/27/20 Subject: LOW VOLTAGE DISTRIBUTION TRANSFORMERS - CCD 065 SUSTAINABILITY EQUIPMENT Description: Spec Section: 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS Status: OPEN | Info Exchange
| 09305 | Forwarded | For Review | 2020-07-14 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-21 | Submittal Number: 26 22 13-12.0 From: PATRICK KLEIN Final Due Date: 07/27/20 Subject: LOW VOLTAGE DISTRIBUTION TRANSFORMERS - CCD 065 SUSTAINABILITY EQUIPMENT Description: Spec Section: 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS Status: OPEN | Info Exchange
| 07203 | Review Response | Approved as Noted/Resubmit | 2020-07-28 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. This shall be forwarded to TT for quick confirmation of equipment weights shown on page 7 within the attached PDF. This submittal is HOT so any expedited review that TT can complete would be appreciated. Thank you, Mark Lievens ME Engineers 2020.07.28 | Info Exchange
| 09606 | Forwarded | For Review | 2020-07-28 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2020-07-28 | Submittal Number: 26 22 13-12.0 From: PATRICK KLEIN Final Due Date: 07/27/20 Subject: LOW VOLTAGE DISTRIBUTION TRANSFORMERS - CCD 065 SUSTAINABILITY EQUIPMENT Description: Spec Section: 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS Status: OPEN | Info Exchange
| 07312 | Review Response | Approved as Noted | 2020-07-30 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | No exceptions. TT has reviewed this submittal solely for the loads imposed on the building structure indicated on the markup of drawing E3-10 in this submittal. Other pages have not been reviewed. | Info Exchange
| 09751 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-03 | Todd Spangler (Populous) | Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2020.07.28 No exceptions. TT has reviewed this submittal solely for the loads imposed on the building structure indicated on the markup of drawing E3-10 in this submittal. Other pages have not been reviewed. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-13 |  | 26 22 13-12.0 CCD 065 Sustainability Equipment-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-13 |  | 26 22 13-12.0 CCD 065 Sustainability Equipment-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-12 02:00 |  | 26 22 13-12.0 CCD 065 Sustainability Equipment-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-07-12 02:00 |  | 26 22 13-12.0 CCD 065 Sustainability Equipment-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-07-12 |  | 26 22 13-12.0 CCD 065 Sustainability Equipment-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-08-03 |  | 26 22 13-12.0 CCD 065 Sustainability Equipment-MAM-ME_TT_POP.pdf
26 22 13-012-00-01 | 26 22 13 - LOW-VOLTAGE DISTRIBUTION TRANSFORMERS | 26 22 13-012-00 LOW VOLTAGE DISTRIBUTION TRANSFORMERS - CCD 065 Sustainability Equipment | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 22 13-012-00 - 26 22 13-012-00 LOW VOLTAGE DISTRIBUTION TRANSFORMERS - CCD 065 Sustainability Equipment | -1 | 2020-08-17
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-03 |  | 26 22 13-12.0 CCD 065 Sustainability Equipment-MAM-ME_TT_POP.pdf
26 24 13-001-00 | 26 24 13 - DISTRIBUTION SWITCHBOARDS | 26 24 13-001-00 DISTRIBUTION SWITCHBOARDS - Product Data, Layout Drawings, and Wiring Diagrams | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-20 | 2020-02-17 | 12 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-02-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04231 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-02-20 | Submittal Number: 26 24 13-1.0 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: DISTRIBUTION SWITCHBOARDS - PRODUCT DATA, LAYOUT DRAWINGS, AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON SWITCHBOARDS AND ENCLOSURES. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR SWITCHBOARDS AND SHOWING CONNECTIONS TO ELECTRICAL POWER FEEDERS AND DISTRIBUTION BRANCHES. SUBMIT ELECTRICAL ROOM PLAN VIEW DRAWINGS AT SCALE SHOWING ALL EQUIPMENT. PROVIDE END AND FRONT ELEVATION VIEWS OF ALL SWITCHBOARDS SHOWING: DISCONNECTS AND RATINGS, BUSS WORK, CONDUIT AREAS, DIMENSIONS, CABLE TERMINALS AND CABLE SIZES, RECOMMENDED HOUSEKEEPING PAD SIZES, MOUNTING OF EQUIPMENT SUPPLIED AND NAMEPLATE SCHEDULE. THE EQUIPMENT PRODUCT DATA, ELECTRICAL ROOM LAYOUTS AND SHORT-CIRCUIT STUDY SHALL BE SUBMITTED TOGETHER IN ORDER TO PROVIDE PROPER EVALUATION. Spec Section: 26 24 13 - DISTRIBUTION SWITCHBOARDS Status: OPEN | Info Exchange
| 05860 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-13 | Submittal Number: 26 24 13-1.0 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: DISTRIBUTION SWITCHBOARDS - PRODUCT DATA, LAYOUT DRAWINGS, AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON SWITCHBOARDS AND ENCLOSURES. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR SWITCHBOARDS AND SHOWING CONNECTIONS TO ELECTRICAL POWER FEEDERS AND DISTRIBUTION BRANCHES. SUBMIT ELECTRICAL ROOM PLAN VIEW DRAWINGS AT SCALE SHOWING ALL EQUIPMENT. PROVIDE END AND FRONT ELEVATION VIEWS OF ALL SWITCHBOARDS SHOWING: DISCONNECTS AND RATINGS, BUSS WORK, CONDUIT AREAS, DIMENSIONS, CABLE TERMINALS AND CABLE SIZES, RECOMMENDED HOUSEKEEPING PAD SIZES, MOUNTING OF EQUIPMENT SUPPLIED AND NAMEPLATE SCHEDULE. THE EQUIPMENT PRODUCT DATA, ELECTRICAL ROOM LAYOUTS AND SHORT-CIRCUIT STUDY SHALL BE SUBMITTED TOGETHER IN ORDER TO PROVIDE PROPER EVALUATION. Spec Section: 26 24 13 - DISTRIBUTION SWITCHBOARDS Status: OPEN | Info Exchange
| 04375 | Review Response | Approved as Noted/Resubmit | 2020-02-14 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.14 | Info Exchange
| 06044 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 26 24 13-1.0 PD Drawings and Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | 26 24 13-1.0 PD Drawings and Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-05 02:00 |  | 26 24 13-1.0 PD Drawings and Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-17 02:00 |  | 26 24 13-1.0 PD Drawings and Diagrams-MAM-ME_POP.pdf
26 24 13-001-01 | 26 24 13 - DISTRIBUTION SWITCHBOARDS | 26 24 13-001-01 DISTRIBUTION SWITCHBOARDS - Product Data, Layout Drawings, and Wiring Diagrams | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-12 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-26 | 2020-03-27 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-03-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04778 | Received | For Review | 2020-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-03-26 | Submittal Number: 26 24 13-1.1 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: DISTRIBUTION SWITCHBOARDS - PRODUCT DATA, LAYOUT DRAWINGS, AND WIRING DIAGRAMS Description: SUBMIT REVISED SP-MS1 SWITCHBOARD Spec Section: 26 24 13 - DISTRIBUTION SWITCHBOARDS Status: OPEN | Info Exchange
| 06553 | Forwarded | For Review | 2020-03-12 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-19 | Submittal Number: 26 24 13-1.1 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: DISTRIBUTION SWITCHBOARDS - PRODUCT DATA, LAYOUT DRAWINGS, AND WIRING DIAGRAMS Description: SUBMIT REVISED SP-MS1 SWITCHBOARD Spec Section: 26 24 13 - DISTRIBUTION SWITCHBOARDS Status: OPEN | Info Exchange
| 05088 | Review Response | Approved as Noted | 2020-03-26 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.26 | Info Exchange
| 06913 | Responded and Closed | Approved as Noted | 2020-03-27 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.26 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-12 |  | 26 24 13-1.1 PD Drawings and Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-12 |  | 26 24 13-1.1 PD Drawings and Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-11 02:00 |  | 26 24 13-1.1 PD Drawings and Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-27 02:00 |  | 26 24 13-1.1 PD Drawings and Diagrams-MAM-ME_POP.pdf
26 24 13-002-00 | 26 24 13 - DISTRIBUTION SWITCHBOARDS | 26 24 13-002-00 DISTRIBUTION SWITCHBOARDS - GDB1, GDB2, and SP-MS1 | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-12 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2020-03-26 | 2020-04-09 | 29 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2020-04-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04777 | Received | For Review | 2020-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-03-26 | Submittal Number: 26 24 13-2.0 From: PATRICK KLEIN Final Due Date: 03/25/20 Subject: DISTRIBUTION SWITCHBOARDS - GDB1, GDB2, AND SP-MS1 Description: TO BE INCLUDED IN 26 24 13-1.0 Spec Section: 26 24 13 - DISTRIBUTION SWITCHBOARDS Status: OPEN | Info Exchange
| 06552 | Forwarded | For Review | 2020-03-12 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-19 | Submittal Number: 26 24 13-2.0 From: PATRICK KLEIN Final Due Date: 03/25/20 Subject: DISTRIBUTION SWITCHBOARDS - GDB1, GDB2, AND SP-MS1 Description: TO BE INCLUDED IN 26 24 13-1.0 Spec Section: 26 24 13 - DISTRIBUTION SWITCHBOARDS Status: OPEN | Info Exchange
| 05213 | Review Response | Approved as Noted/Resubmit | 2020-04-03 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.03 | Info Exchange
| 07085 | Forwarded | For Review | 2020-04-03 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) | 2020-03-26 | Submittal Number: 26 24 13-2.0 From: PATRICK KLEIN Final Due Date: 03/25/20 Subject: DISTRIBUTION SWITCHBOARDS - GDB1, GDB2, AND SP-MS1 Description: TO BE INCLUDED IN 26 24 13-1.0 Spec Section: 26 24 13 - DISTRIBUTION SWITCHBOARDS Status: OPEN | Info Exchange
| 05274 | Review Response | Approved | 2020-04-08 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 07168 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-09 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.03 Response (Approved) from: Samar Kenkre (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-12 |  | 26 24 13-2.0 GDB1, GDB2, and SP-MS1 PD, Drawings, and Wiring Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-12 |  | 26 24 13-2.0 GDB1, GDB2, and SP-MS1 PD, Drawings, and Wiring Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-11 02:00 |  | 26 24 13-2.0 GDB1, GDB2, and SP-MS1 PD, Drawings, and Wiring Diagrams-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-11 02:00 |  | 26 24 13-2.0 GDB1, GDB2, and SP-MS1 PD, Drawings, and Wiring Diagrams-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-03-11 02:00 |  | 26 24 13-2.0 GDB1, GDB2, and SP-MS1 PD, Drawings, and Wiring Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-09 02:00 |  | 26 24 13-2.0 GDB1, GDB2, and SP-MS1 PD, Drawings, and Wiring Diagrams-MAM-ME_TT_POP.pdf
26 24 13-002-01 | 26 24 13 - DISTRIBUTION SWITCHBOARDS | 26 24 13-002-01 DISTRIBUTION SWITCHBOARDS - GDB1, GDB2, and SP-MS1 | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-12 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-27 07:00 | 2020-05-19 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05810 | Received | For Review | 2020-05-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-05-27 07:00 | Submittal Number: 26 24 13-2.1 From: PATRICK KLEIN Final Due Date: 05/25/20 Subject: DISTRIBUTION SWITCHBOARDS - GDB1, GDB2, AND SP-MS1 Description: RESUBMIT SP-MS1 ACCORDINGLY PER PREVIOUS REVISION COMMENTS Spec Section: 26 24 13 - DISTRIBUTION SWITCHBOARDS Status: OPEN | Info Exchange
| 07876 | Forwarded | For Review | 2020-05-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-18 | Submittal Number: 26 24 13-2.1 From: PATRICK KLEIN Final Due Date: 05/25/20 Subject: DISTRIBUTION SWITCHBOARDS - GDB1, GDB2, AND SP-MS1 Description: RESUBMIT SP-MS1 ACCORDINGLY PER PREVIOUS REVISION COMMENTS Spec Section: 26 24 13 - DISTRIBUTION SWITCHBOARDS Status: OPEN | Info Exchange
| 05942 | Review Response | Approved as Noted | 2020-05-18 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.18 | Info Exchange
| 08071 | Responded and Closed | Approved as Noted | 2020-05-19 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-11 |  | 26 24 13-2.1 GDB1 GDB2 and SP-MS1 PD Drawings and Wiring Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-11 |  | 26 24 13-2.1 GDB1 GDB2 and SP-MS1 PD Drawings and Wiring Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-10 02:00 |  | 26 24 13-2.1 GDB1 GDB2 and SP-MS1 PD Drawings and Wiring Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-19 02:00 |  | 26 24 13-2.1 GDB1 GDB2 and SP-MS1 PD Drawings and Wiring Diagrams-MAM-ME_pop.pdf
26 24 13-005-00 | 26 24 13 - DISTRIBUTION SWITCHBOARDS | 26 24 13-005-00 DISTRIBUTION SWITCHBOARDS - Sustainability Revisions for Boilers | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-30 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-13 | 2020-08-03 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-08-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07267 | Received | For Review | 2020-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-08-13 | Submittal Number: 26 24 13-5.0 From: PATRICK KLEIN Final Due Date: 08/13/20 Subject: DISTRIBUTION SWITCHBOARDS - SUSTAINABILITY REVISIONS FOR BOILERS Description: Spec Section: 26 24 13 - DISTRIBUTION SWITCHBOARDS Status: OPEN | Info Exchange
| 09682 | Forwarded | For Review | 2020-07-30 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-06 | Submittal Number: 26 24 13-5.0 From: PATRICK KLEIN Final Due Date: 08/13/20 Subject: DISTRIBUTION SWITCHBOARDS - SUSTAINABILITY REVISIONS FOR BOILERS Description: Spec Section: 26 24 13 - DISTRIBUTION SWITCHBOARDS Status: OPEN | Info Exchange
| 07314 | Review Response | Approved as Noted | 2020-07-31 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review to be returned to Mortenson today. This is a HOT submittal. Thank you, Mark Lievens ME Engineers 2020.07.31 | Info Exchange
| 09753 | Responded and Closed | Approved as Noted | 2020-08-03 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal. Thank you, Mark Lievens ME Engineers 2020.07.31 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-30 |  | 26 24 13-5.0 Sustainability Revisions for Boilers-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-30 |  | 26 24 13-5.0 Sustainability Revisions for Boilers-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-30 |  | 26 24 13-5.0 Sustainability Revisions for Boilers-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-08-03 |  | 26 24 13-5.0 Sustainability Revisions for Boilers-MAM-ME_POP.pdf
26 24 16-001-00 | 26 24 16 - PANELBOARDS | 26 24 16-001-00 PANEL BOARDS - Catwalk Panelboard Product Data and Wiring Diagrams | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-11 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-25 | 2020-03-18 | 8 |  | Record Copies; Transfers; Submittals | 26 24 16-001-01 - 26 24 16-001-00 PANEL BOARDS - Catwalk Panelboard Product Data and Wiring Diagrams | 7 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04758 | Received | For Review | 2020-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-03-25 | Submittal Number: 26 24 16-1.0 From: PATRICK KLEIN Final Due Date: 03/13/20 Subject: PANEL BOARDS - CATWALK PANELBOARD PRODUCT DATA AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON PANELBOARDS, AND ENCLOSURES. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR PANELBOARDS SHOWING CONNECTIONS TO ELECTRICAL POWER FEEDERS AND DISTRIBUTION BRANCHES. SUBMIT ELECTRICAL ROOM PLAN VIEW DRAWINGS AT SCALE SHOWING ALL EQUIPMENT, PANELBOARDS, DISCONNECTS AND RATINGS, BUSS WORK, CONDUIT AREAS, DIMENSIONS AND MOUNTING OF EQUIPMENT SUPPLIED. Spec Section: 26 24 16 - PANELBOARDS Status: OPEN | Info Exchange
| 06528 | Forwarded | For Review | 2020-03-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-18 | Submittal Number: 26 24 16-1.0 From: PATRICK KLEIN Final Due Date: 03/13/20 Subject: PANEL BOARDS - CATWALK PANELBOARD PRODUCT DATA AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON PANELBOARDS, AND ENCLOSURES. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR PANELBOARDS SHOWING CONNECTIONS TO ELECTRICAL POWER FEEDERS AND DISTRIBUTION BRANCHES. SUBMIT ELECTRICAL ROOM PLAN VIEW DRAWINGS AT SCALE SHOWING ALL EQUIPMENT, PANELBOARDS, DISCONNECTS AND RATINGS, BUSS WORK, CONDUIT AREAS, DIMENSIONS AND MOUNTING OF EQUIPMENT SUPPLIED. Spec Section: 26 24 16 - PANELBOARDS Status: OPEN | Info Exchange
| 04936 | Review Response | Approved as Noted/Resubmit | 2020-03-17 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.17 | Info Exchange
| 06732 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-10 |  | 26 24 16-1.0 Catwalk Panelboard Product Data and Wiring Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-10 |  | 26 24 16-1.0 Catwalk Panelboard Product Data and Wiring Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-09 02:00 |  | 26 24 16-1.0 Catwalk Panelboard Product Data and Wiring Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-18 02:00 |  | 26 24 16-1.0 Catwalk Panelboard Product Data and Wiring Diagrams-MAM-ME_POP.pdf
26 24 16-001-01 | 26 24 16 - PANELBOARDS | 26 24 16-001-00 PANEL BOARDS - Catwalk Panelboard Product Data and Wiring Diagrams | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 24 16-001-00 - 26 24 16-001-00 PANEL BOARDS - Catwalk Panelboard Product Data and Wiring Diagrams | -1 | 2020-04-01
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-18 02:00 |  | 26 24 16-1.0 Catwalk Panelboard Product Data and Wiring Diagrams-MAM-ME_POP.pdf
26 24 16-004-00 | 26 24 16 - PANELBOARDS | 26 24 16-004-00 APANEL BOARDS - Panelboard Product Data and Wiring Diagrams | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-12 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-01 | 2020-04-05 | 25 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04779 | Received | For Review | 2020-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-01 | Submittal Number: 26 24 16-4.0 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: PANEL BOARDS - PANELBOARD PRODUCT DATA AND WIRING DIAGRAMS Description: Spec Section: 26 24 16 - PANELBOARDS Status: OPEN | Info Exchange
| 06554 | Forwarded | For Review | 2020-03-12 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-19 | Submittal Number: 26 24 16-4.0 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: PANEL BOARDS - PANELBOARD PRODUCT DATA AND WIRING DIAGRAMS Description: Spec Section: 26 24 16 - PANELBOARDS Status: OPEN | Info Exchange
| 05215 | Review Response | Approved as Noted/Resubmit | 2020-04-04 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review for action items and individual item dispositions. Full submittal shall be resubmitted for record only with corrections as noted alongside additional items required for review and short circuit/coordination studies. Thank you, Mark Lievens ME Engineers 2020.04.04 | Info Exchange
| 07089 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-05 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review for action items and individual item dispositions. Full submittal shall be resubmitted for record only with corrections as noted alongside additional items required for review and short circuit/coordination studies. Thank you, Mark Lievens ME Engineers 2020.04.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 26 24 16-4.0 Product Data and Wiring Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-11 |  | 26 24 16-4.0 Product Data and Wiring Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-10 02:00 |  | 26 24 16-4.0 Product Data and Wiring Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-05 02:00 |  | 26 24 16-4.0 Product Data and Wiring Diagrams-ME_POP.pdf
26 24 16-004-01 | 26 24 16 - PANELBOARDS | 26 24 16-004-01 PANEL BOARDS - Panelboard Product Data and Wiring Diagrams | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-28 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-12 | 2020-06-01 | 35 |  | Record Copies; Transfers; Submittals |  | 34 |  | 2020-06-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05605 | Received | For Review | 2020-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-05-12 | Submittal Number: 26 24 16-4.1 From: PATRICK KLEIN Final Due Date: 05/15/20 Subject: PANEL BOARDS - PANELBOARD PRODUCT DATA AND WIRING DIAGRAMS Description: RESUBMIT PANELBOARDS SLA-FR2, MCC-FR3_2, AND MCD-FR3_1 ALONG WITH FINAL COORDINATION STUDY. Spec Section: 26 24 16 - PANELBOARDS Status: OPEN | Info Exchange
| 07597 | Forwarded | For Review | 2020-04-28 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-05 | Submittal Number: 26 24 16-4.1 From: PATRICK KLEIN Final Due Date: 05/15/20 Subject: PANEL BOARDS - PANELBOARD PRODUCT DATA AND WIRING DIAGRAMS Description: RESUBMIT PANELBOARDS SLA-FR2, MCC-FR3_2, AND MCD-FR3_1 ALONG WITH FINAL COORDINATION STUDY. Spec Section: 26 24 16 - PANELBOARDS Status: OPEN | Info Exchange
| 06138 | Review Response | Approved as Noted | 2020-05-31 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.31 | Info Exchange
| 08306 | Responded and Closed | Approved as Noted | 2020-06-01 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.31 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-28 |  | 26 24 16-4.1 Product Data and Wiring Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-28 |  | 26 24 16-4.1 Product Data and Wiring Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-27 02:00 |  | 26 24 16-4.1 Product Data and Wiring Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-01 02:00 |  | 26 24 16-4.1 Product Data and Wiring Diagrams-MAM-ME_POP.pdf
26 24 16-005-01 | 26 24 16 - PANELBOARDS | 26 24 16-005-01 DAS TR Electrical Panels (CCD083) | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-04-01 | 2021-04-12 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2021-04-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12101 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-01 | Submittal Number: 26 24 16-5.1 From: COLIN SAIZ Final Due Date: 04/05/21 Subject: DAS TR ELECTRICAL PANELS (CCD083) Description: Spec Section: 26 24 16 - PANELBOARDS Status: OPEN | Info Exchange
| 15660 | Forwarded | For Review | 2021-03-18 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-25 | Submittal Number: 26 24 16-5.1 From: COLIN SAIZ Final Due Date: 04/05/21 Subject: DAS TR ELECTRICAL PANELS (CCD083) Description: Spec Section: 26 24 16 - PANELBOARDS Status: OPEN | Info Exchange
| 12550 | Review Response | Approved as Noted | 2021-04-12 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.04.12 | Info Exchange
| 16257 | Responded and Closed | Approved as Noted | 2021-04-12 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Colin.Saiz@mortenson.com |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.04.12 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-18 |  | 26 24 16-5 DAS TR Electrical Panels (CCD083).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-18 |  | 26 24 16-5 DAS TR Electrical Panels (CCD083).pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-03-17 02:00 |  | 26 24 16-5 DAS TR Electrical Panels (CCD083).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-12 02:00 |  | 26 24 16-5 DAS TR Electrical Panels (CCD083) - ME Review_POP.pdf
26 25 00-001-00 | 26 25 00 - ENCLOSED BUS ASSEMBLIES | 26 25 00-001-00 ENCLOSED BUS ASSEMBLIES - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-18 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-02 07:00 | 2020-05-26 | 9 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05895 | Received | For Review | 2020-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-02 07:00 | Submittal Number: 26 25 00-1.0 From: PATRICK KLEIN Final Due Date: 06/01/20 Subject: ENCLOSED BUS ASSEMBLIES - PRODUCT DATA Description: THE FOLLOWING SUBMITTAL DATA SHALL BE FURNISHED ACCORDING TO THE GENERAL CONDITIONS AND SECTION 26 05 02 AND SHALL INCLUDE, BUT NOT BE LIMITED TO: 1. BUSWAYS COMPLETE WITH CAPACITY DATA, BUS DATA, DIMENSIONAL DATA, SCALED SHOP DRAWINGS INDICATING BUS ROUTING, CONNECTOR DETAIL, FITTINGS, HANGARS, ETC. 2. SERVICE BUSWAYS COMPLETE WITH CAPACITY DATA, BUS DATA, DIMENSIONAL DATA, SCALED SHOP DRAWINGS INDICATING BUS ROUTING, CONNECTOR DETAIL, FITTINGS, HANGARS, ETC. SERVICE BUSWAY INCLUDING TAP BOXES PRODUCT DATA AND SHOP DRAWINGS SHALL BE SUBMITTED TO THE UTILITY COMPANY FOR APPROVAL PRIOR TO SUBMITTING TO THE ENGINEER FOR REVIEW. Spec Section: 26 25 00 - ENCLOSED BUS ASSEMBLIES Status: OPEN | Info Exchange
| 07995 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-25 | Submittal Number: 26 25 00-1.0 From: PATRICK KLEIN Final Due Date: 06/01/20 Subject: ENCLOSED BUS ASSEMBLIES - PRODUCT DATA Description: THE FOLLOWING SUBMITTAL DATA SHALL BE FURNISHED ACCORDING TO THE GENERAL CONDITIONS AND SECTION 26 05 02 AND SHALL INCLUDE, BUT NOT BE LIMITED TO: 1. BUSWAYS COMPLETE WITH CAPACITY DATA, BUS DATA, DIMENSIONAL DATA, SCALED SHOP DRAWINGS INDICATING BUS ROUTING, CONNECTOR DETAIL, FITTINGS, HANGARS, ETC. 2. SERVICE BUSWAYS COMPLETE WITH CAPACITY DATA, BUS DATA, DIMENSIONAL DATA, SCALED SHOP DRAWINGS INDICATING BUS ROUTING, CONNECTOR DETAIL, FITTINGS, HANGARS, ETC. SERVICE BUSWAY INCLUDING TAP BOXES PRODUCT DATA AND SHOP DRAWINGS SHALL BE SUBMITTED TO THE UTILITY COMPANY FOR APPROVAL PRIOR TO SUBMITTING TO THE ENGINEER FOR REVIEW. Spec Section: 26 25 00 - ENCLOSED BUS ASSEMBLIES Status: OPEN | Info Exchange
| 06047 | Review Response | Approved as Noted | 2020-05-21 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.21 | Info Exchange
| 08191 | Responded and Closed | Approved as Noted | 2020-05-26 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 26 25 00-1.0 PD and Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 26 25 00-1.0 PD and Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-17 02:00 |  | 26 25 00-1.0 PD and Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-26 02:00 |  | 26 25 00-1.0 PD and Drawings-MAM-ME_POP.pdf
26 27 26-001-00 | 26 27 26 - WIRING DEVICES | 26 27 26-001-00 WIRING DEVICES - Product Data | Closed | Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2019-12-04 08:00 | 2019-12-12 | 25 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-12-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03232 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-12-04 08:00 | Submittal Number: 26 27 26-1.0 From: PATRICK KLEIN Final Due Date: 12/02/19 Subject: WIRING DEVICES - PRODUCT DATA Description: PRODUCT DATA FOR EACH TYPE OF PRODUCT SPECIFIED. SHOP DRAWINGS / ARCHITECTURAL COORDINATION REQUIREMENTS : - 1. FLOOR BOX LOCATIONS AND TYPES INDICATED ON DRAWINGS ARE SCHEMATIC IN NATURE AND ARE NOT DIMENSIONED LOCATIONS. CONTRACTOR SHALL SUBMIT SHOP DRAWINGS AND PRODUCT DATA FOR FINAL REVIEW AND COMMENT BY THE ARCHITECT, OWNER, AND ENGINEER, TO ENSURE DESIRED AESTHETICS ARE ACHIEVED. 2. SHOP DRAWINGS SHALL INCLUDE THE FOLLOWING DETAILED INFORMATION: A. PLACEMENT: DIMENSIONED FLOOR BOX PLACEMENT SHOWN ON FLOOR PLAN WITH CURRENT FURNITURE LAYER SHOWN. B. CONDUIT: SHOW ALL CONDUIT SIZE AND ROUTING WITH LABELS FOR POWER, DATA, AV, ETC. C. COVERS: SPECIFIC LABELS OR NOTES TO INDICATE WHERE DIFFERENT COVER TYPES AND FINISH ARE TO BE USED, IF APPLICABLE. OCCUPANCY SENSORS WIRED 1. SUBMITA LIGHTING PLAN CLEARLY MARKED BY MANUFACTURER IDENTIFYING PRODUCT TYPE, LOCATIONS, ORIENTATION AND COVERAGE FOR EACH SENSOR. 2. SUBMIT ANY INTERCONNECTION DIAGRAMS PER MAJOR SUBSYSTEMS SHOWING PROPER WIRING. OCCUPANCY SENSOR WIRELESS 1. SUBMITA LIGHTING PLAN CLEARLY MARKED BY MANUFACTURER IDENTIFYING PRODUCT TYPE, LOCATIONS, ORIENTATION AND COVERAGE FOR EACH SENSOR. Spec Section: 26 27 26 - WIRING DEVICES Status: OPEN | Info Exchange
| 04669 | Forwarded | For Review | 2019-11-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-25 | Submittal Number: 26 27 26-1.0 From: PATRICK KLEIN Final Due Date: 12/02/19 Subject: WIRING DEVICES - PRODUCT DATA Description: PRODUCT DATA FOR EACH TYPE OF PRODUCT SPECIFIED. SHOP DRAWINGS / ARCHITECTURAL COORDINATION REQUIREMENTS : - 1. FLOOR BOX LOCATIONS AND TYPES INDICATED ON DRAWINGS ARE SCHEMATIC IN NATURE AND ARE NOT DIMENSIONED LOCATIONS. CONTRACTOR SHALL SUBMIT SHOP DRAWINGS AND PRODUCT DATA FOR FINAL REVIEW AND COMMENT BY THE ARCHITECT, OWNER, AND ENGINEER, TO ENSURE DESIRED AESTHETICS ARE ACHIEVED. 2. SHOP DRAWINGS SHALL INCLUDE THE FOLLOWING DETAILED INFORMATION: A. PLACEMENT: DIMENSIONED FLOOR BOX PLACEMENT SHOWN ON FLOOR PLAN WITH CURRENT FURNITURE LAYER SHOWN. B. CONDUIT: SHOW ALL CONDUIT SIZE AND ROUTING WITH LABELS FOR POWER, DATA, AV, ETC. C. COVERS: SPECIFIC LABELS OR NOTES TO INDICATE WHERE DIFFERENT COVER TYPES AND FINISH ARE TO BE USED, IF APPLICABLE. OCCUPANCY SENSORS WIRED 1. SUBMITA LIGHTING PLAN CLEARLY MARKED BY MANUFACTURER IDENTIFYING PRODUCT TYPE, LOCATIONS, ORIENTATION AND COVERAGE FOR EACH SENSOR. 2. SUBMIT ANY INTERCONNECTION DIAGRAMS PER MAJOR SUBSYSTEMS SHOWING PROPER WIRING. OCCUPANCY SENSOR WIRELESS 1. SUBMITA LIGHTING PLAN CLEARLY MARKED BY MANUFACTURER IDENTIFYING PRODUCT TYPE, LOCATIONS, ORIENTATION AND COVERAGE FOR EACH SENSOR. Spec Section: 26 27 26 - WIRING DEVICES Status: OPEN | Info Exchange
| 03418 | Review Response | Approved as Noted | 2019-12-02 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | See the attached submittal review. Please review and comment on the device colors that shall be provided for the electrical receptacles, switches, and floorboxes. Let me know if you have any questions. Thanks, Mark Lievens ME Engineers 2019.12.02 | Info Exchange
| 04889 | Forwarded | For Review | 2019-12-02 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2019-12-04 | Submittal Number: 26 27 26-1.0 From: PATRICK KLEIN Final Due Date: 12/02/19 Subject: WIRING DEVICES - PRODUCT DATA Description: PRODUCT DATA FOR EACH TYPE OF PRODUCT SPECIFIED. SHOP DRAWINGS / ARCHITECTURAL COORDINATION REQUIREMENTS : - 1. FLOOR BOX LOCATIONS AND TYPES INDICATED ON DRAWINGS ARE SCHEMATIC IN NATURE AND ARE NOT DIMENSIONED LOCATIONS. CONTRACTOR SHALL SUBMIT SHOP DRAWINGS AND PRODUCT DATA FOR FINAL REVIEW AND COMMENT BY THE ARCHITECT, OWNER, AND ENGINEER, TO ENSURE DESIRED AESTHETICS ARE ACHIEVED. 2. SHOP DRAWINGS SHALL INCLUDE THE FOLLOWING DETAILED INFORMATION: A. PLACEMENT: DIMENSIONED FLOOR BOX PLACEMENT SHOWN ON FLOOR PLAN WITH CURRENT FURNITURE LAYER SHOWN. B. CONDUIT: SHOW ALL CONDUIT SIZE AND ROUTING WITH LABELS FOR POWER, DATA, AV, ETC. C. COVERS: SPECIFIC LABELS OR NOTES TO INDICATE WHERE DIFFERENT COVER TYPES AND FINISH ARE TO BE USED, IF APPLICABLE. OCCUPANCY SENSORS WIRED 1. SUBMITA LIGHTING PLAN CLEARLY MARKED BY MANUFACTURER IDENTIFYING PRODUCT TYPE, LOCATIONS, ORIENTATION AND COVERAGE FOR EACH SENSOR. 2. SUBMIT ANY INTERCONNECTION DIAGRAMS PER MAJOR SUBSYSTEMS SHOWING PROPER WIRING. OCCUPANCY SENSOR WIRELESS 1. SUBMITA LIGHTING PLAN CLEARLY MARKED BY MANUFACTURER IDENTIFYING PRODUCT TYPE, LOCATIONS, ORIENTATION AND COVERAGE FOR EACH SENSOR. Spec Section: 26 27 26 - WIRING DEVICES Status: OPEN | Info Exchange
| 05090 | Responded and Closed | Approved as Noted | 2019-12-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: See the attached submittal review. Please review and comment on the device colors that shall be provided for the electrical receptacles, switches, and floorboxes. Let me know if you have any questions. Thanks, Mark Lievens ME Engineers 2019.12.02 Device colors have been selected, see attached submittal. -jhd/POP | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-18 |  | 26 27 26-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-18 |  | 26 27 26-1.0 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-11-17 02:00 |  | 26 27 26-1.0 Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-17 02:00 |  | 26 27 26-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-12 02:00 |  | 26 27 26-1.0 Product Data-MAM-ME-POP.pdf
26 27 26-001-01 | 26 27 26 - WIRING DEVICES | 26 27 26-001-01 WIRING DEVICES - Product Data for Additional Manufacturers | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-24 | 2020-02-24 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04296 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-02-24 | Submittal Number: 26 27 26-1.1 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: WIRING DEVICES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA FOR EACH TYPE OF PRODUCT SPECIFIED. SHOP DRAWINGS / ARCHITECTURAL COORDINATION REQUIREMENTS : - 1. FLOOR BOX LOCATIONS AND TYPES INDICATED ON DRAWINGS ARE SCHEMATIC IN NATURE AND ARE NOT DIMENSIONED LOCATIONS. CONTRACTOR SHALL SUBMIT SHOP DRAWINGS AND PRODUCT DATA FOR FINAL REVIEW AND COMMENT BY THE ARCHITECT, OWNER, AND ENGINEER, TO ENSURE DESIRED AESTHETICS ARE ACHIEVED. 2. SHOP DRAWINGS SHALL INCLUDE THE FOLLOWING DETAILED INFORMATION: A. PLACEMENT: DIMENSIONED FLOOR BOX PLACEMENT SHOWN ON FLOOR PLAN WITH CURRENT FURNITURE LAYER SHOWN. B. CONDUIT: SHOW ALL CONDUIT SIZE AND ROUTING WITH LABELS FOR POWER, DATA, AV, ETC. C. COVERS: SPECIFIC LABELS OR NOTES TO INDICATE WHERE DIFFERENT COVER TYPES AND FINISH ARE TO BE USED, IF APPLICABLE. OCCUPANCY SENSORS WIRED 1. SUBMITA LIGHTING PLAN CLEARLY MARKED BY MANUFACTURER IDENTIFYING PRODUCT TYPE, LOCATIONS, ORIENTATION AND COVERAGE FOR EACH SENSOR. 2. SUBMIT ANY INTERCONNECTION DIAGRAMS PER MAJOR SUBSYSTEMS SHOWING PROPER WIRING. OCCUPANCY SENSOR WIRELESS 1. SUBMITA LIGHTING PLAN CLEARLY MARKED BY MANUFACTURER IDENTIFYING PRODUCT TYPE, LOCATIONS, ORIENTATION AND COVERAGE FOR EACH SENSOR. Spec Section: 26 27 26 - WIRING DEVICES Status: OPEN | Info Exchange
| 05947 | Forwarded | For Review | 2020-02-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-17 | Submittal Number: 26 27 26-1.1 From: PATRICK KLEIN Final Due Date: 02/24/20 Subject: WIRING DEVICES - PRODUCT DATA FOR ADDITIONAL MANUFACTURERS Description: PRODUCT DATA FOR EACH TYPE OF PRODUCT SPECIFIED. SHOP DRAWINGS / ARCHITECTURAL COORDINATION REQUIREMENTS : - 1. FLOOR BOX LOCATIONS AND TYPES INDICATED ON DRAWINGS ARE SCHEMATIC IN NATURE AND ARE NOT DIMENSIONED LOCATIONS. CONTRACTOR SHALL SUBMIT SHOP DRAWINGS AND PRODUCT DATA FOR FINAL REVIEW AND COMMENT BY THE ARCHITECT, OWNER, AND ENGINEER, TO ENSURE DESIRED AESTHETICS ARE ACHIEVED. 2. SHOP DRAWINGS SHALL INCLUDE THE FOLLOWING DETAILED INFORMATION: A. PLACEMENT: DIMENSIONED FLOOR BOX PLACEMENT SHOWN ON FLOOR PLAN WITH CURRENT FURNITURE LAYER SHOWN. B. CONDUIT: SHOW ALL CONDUIT SIZE AND ROUTING WITH LABELS FOR POWER, DATA, AV, ETC. C. COVERS: SPECIFIC LABELS OR NOTES TO INDICATE WHERE DIFFERENT COVER TYPES AND FINISH ARE TO BE USED, IF APPLICABLE. OCCUPANCY SENSORS WIRED 1. SUBMITA LIGHTING PLAN CLEARLY MARKED BY MANUFACTURER IDENTIFYING PRODUCT TYPE, LOCATIONS, ORIENTATION AND COVERAGE FOR EACH SENSOR. 2. SUBMIT ANY INTERCONNECTION DIAGRAMS PER MAJOR SUBSYSTEMS SHOWING PROPER WIRING. OCCUPANCY SENSOR WIRELESS 1. SUBMITA LIGHTING PLAN CLEARLY MARKED BY MANUFACTURER IDENTIFYING PRODUCT TYPE, LOCATIONS, ORIENTATION AND COVERAGE FOR EACH SENSOR. Spec Section: 26 27 26 - WIRING DEVICES Status: OPEN | Info Exchange
| 04479 | Review Response | Approved as Noted | 2020-02-21 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| 06172 | Responded and Closed | Approved as Noted | 2020-02-24 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-10 |  | 26 27 26-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-10 |  | 26 27 26-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-02-09 02:00 |  | 26 27 26-1.1 Product Data for Additional Manufacturers-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-24 02:00 |  | 26 27 26-1.1 Product Data for Additional Manufacturers-MAM-ME_POP.pdf
26 27 26-001-03 | 26 27 26 - WIRING DEVICES | 26 27 26-001-03 Wiring Devices | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-20 | 2020-08-06 | 32 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06773 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 26 27 26-1.3 From: ALYSSA SANDOVAL Final Due Date: 07/17/20 Subject: WIRING DEVICES Description: Spec Section: 26 27 26 - WIRING DEVICES Status: OPEN | Info Exchange
| 09101 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-13 | Submittal Number: 26 27 26-1.3 From: ALYSSA SANDOVAL Final Due Date: 07/17/20 Subject: WIRING DEVICES Description: Spec Section: 26 27 26 - WIRING DEVICES Status: OPEN | Info Exchange
| 07444 | Review Response | Approved as Noted | 2020-07-22 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.22 | Info Exchange
| 09912 | Responded and Closed | Approved as Noted | 2020-08-06 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-02 |  | 26 27 26-1.3 - Wiring Devices.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-02 |  | 26 27 26-1.3 - Wiring Devices.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-02 |  | 26 27 26-1.3 - Wiring Devices.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-08-06 |  | 26 27 26-1.3 - Wiring Devices - ME_POP.pdf
26 28 16-001-00 | 26 28 16 - ENCLOSED SWITCHES, FUSES AND CIRCUIT BREAKERS | 26 28 16-001-00 ENCLOSED SWITCHES, FUSES, AND CIRCUIT BREAKERS - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-24 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-13 | 2020-03-10 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04471 | Received | For Review | 2020-02-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-03-13 | Submittal Number: 26 28 16-1.0 From: PATRICK KLEIN Final Due Date: 03/13/20 Subject: ENCLOSED SWITCHES, FUSES, AND CIRCUIT BREAKERS - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON CIRCUIT AND MOTOR DISCONNECT SWITCHES, AND EQUIPMENT CONNECTORS. FUSE PRODUCT DATA : FOR EACH TYPE OF FUSE INDICATED. INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS, DESCRIPTIONS OF INDIVIDUAL COMPONENTS, AND FINISHES FOR SPARE-FUSE CABINETS. INCLUDE THE FOLLOWING FOR EACH FUSE TYPE INDICATED: 1. AMBIENT TEMPERATURE ADJUSTMENT INFORMATION: IF RATINGS OF FUSES HAVE BEEN ADJUSTED TO ACCOMMODATE AMBIENT TEMPERATURES, PROVIDE LIST OF FUSES WITH ADJUSTED RATINGS. A. FOR EACH FUSE HAVING ADJUSTED RATINGS, INCLUDE LOCATION OF FUSE, ORIGINAL FUSE RATING, LOCAL AMBIENT TEMPERATURE, AND ADJUSTED FUSE RATING. B. PROVIDE MANUFACTURER'S TECHNICAL DATA ON WHICH AMBIENT TEMPERATURE ADJUSTMENT CALCULATIONS ARE BASED. 2. DIMENSIONS AND MANUFACTURER'S TECHNICAL DATA ON FEATURES, PERFORMANCE, ELECTRICAL CHARACTERISTICS, AND RATINGS. 3. CURRENT-LIMITATION CURVES FOR FUSES WITH CURRENT-LIMITING CHARACTERISTICS. 4. TIME-CURRENT COORDINATION CURVES (AVERAGE MELT) AND CURRENT-LIMITATION CURVES (INSTANTANEOUS PEAK LET-THROUGH CURRENT) FOR EACH TYPE AND RATING OF FUSE. 5. FUSE SIZES FOR ELEVATOR FEEDERS AND ELEVATOR DISCONNECT SWITCHES. Spec Section: 26 28 16 - ENCLOSED SWITCHES, FUSES AND CIRCUIT BREAKERS Status: OPEN | Info Exchange
| 06163 | Forwarded | For Review | 2020-02-24 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-02 | Submittal Number: 26 28 16-1.0 From: PATRICK KLEIN Final Due Date: 03/13/20 Subject: ENCLOSED SWITCHES, FUSES, AND CIRCUIT BREAKERS - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON CIRCUIT AND MOTOR DISCONNECT SWITCHES, AND EQUIPMENT CONNECTORS. FUSE PRODUCT DATA : FOR EACH TYPE OF FUSE INDICATED. INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS, DESCRIPTIONS OF INDIVIDUAL COMPONENTS, AND FINISHES FOR SPARE-FUSE CABINETS. INCLUDE THE FOLLOWING FOR EACH FUSE TYPE INDICATED: 1. AMBIENT TEMPERATURE ADJUSTMENT INFORMATION: IF RATINGS OF FUSES HAVE BEEN ADJUSTED TO ACCOMMODATE AMBIENT TEMPERATURES, PROVIDE LIST OF FUSES WITH ADJUSTED RATINGS. A. FOR EACH FUSE HAVING ADJUSTED RATINGS, INCLUDE LOCATION OF FUSE, ORIGINAL FUSE RATING, LOCAL AMBIENT TEMPERATURE, AND ADJUSTED FUSE RATING. B. PROVIDE MANUFACTURER'S TECHNICAL DATA ON WHICH AMBIENT TEMPERATURE ADJUSTMENT CALCULATIONS ARE BASED. 2. DIMENSIONS AND MANUFACTURER'S TECHNICAL DATA ON FEATURES, PERFORMANCE, ELECTRICAL CHARACTERISTICS, AND RATINGS. 3. CURRENT-LIMITATION CURVES FOR FUSES WITH CURRENT-LIMITING CHARACTERISTICS. 4. TIME-CURRENT COORDINATION CURVES (AVERAGE MELT) AND CURRENT-LIMITATION CURVES (INSTANTANEOUS PEAK LET-THROUGH CURRENT) FOR EACH TYPE AND RATING OF FUSE. 5. FUSE SIZES FOR ELEVATOR FEEDERS AND ELEVATOR DISCONNECT SWITCHES. Spec Section: 26 28 16 - ENCLOSED SWITCHES, FUSES AND CIRCUIT BREAKERS Status: OPEN | Info Exchange
| 04747 | Review Response | Approved as Noted/Resubmit | 2020-03-10 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.03.10 | Info Exchange
| 06519 | Responded and Closed | Approved as Noted/Resubmit | 2020-03-10 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.03.10 Resubmit items as specified in disposition sheets within submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-24 |  | 26 28 16-1.0 Product Data and Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-24 |  | 26 28 16-1.0 Product Data and Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-10 02:00 |  | 26 28 16-1.0 Product Data and Drawings-MAM-ME.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-10 02:00 |  | 26 28 16-1.0 Product Data and Drawings-MAM-ME_POP.pdf
26 28 16-001-01 | 26 28 16 - ENCLOSED SWITCHES, FUSES AND CIRCUIT BREAKERS | 26 28 16-001-01 ENCLOSED SWITCHES, FUSES, AND CIRCUIT BREAKERS - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-06 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-21 07:00 | 2020-04-17 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-04-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05218 | Received | For Review | 2020-04-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-21 07:00 | Submittal Number: 26 28 16-1.1 From: PATRICK KLEIN Final Due Date: 04/20/20 Subject: ENCLOSED SWITCHES, FUSES, AND CIRCUIT BREAKERS - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON CIRCUIT AND MOTOR DISCONNECT SWITCHES, AND EQUIPMENT CONNECTORS. FUSE PRODUCT DATA : FOR EACH TYPE OF FUSE INDICATED. INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS, DESCRIPTIONS OF INDIVIDUAL COMPONENTS, AND FINISHES FOR SPARE-FUSE CABINETS. INCLUDE THE FOLLOWING FOR EACH FUSE TYPE INDICATED: 1. AMBIENT TEMPERATURE ADJUSTMENT INFORMATION: IF RATINGS OF FUSES HAVE BEEN ADJUSTED TO ACCOMMODATE AMBIENT TEMPERATURES, PROVIDE LIST OF FUSES WITH ADJUSTED RATINGS. A. FOR EACH FUSE HAVING ADJUSTED RATINGS, INCLUDE LOCATION OF FUSE, ORIGINAL FUSE RATING, LOCAL AMBIENT TEMPERATURE, AND ADJUSTED FUSE RATING. B. PROVIDE MANUFACTURER'S TECHNICAL DATA ON WHICH AMBIENT TEMPERATURE ADJUSTMENT CALCULATIONS ARE BASED. 2. DIMENSIONS AND MANUFACTURER'S TECHNICAL DATA ON FEATURES, PERFORMANCE, ELECTRICAL CHARACTERISTICS, AND RATINGS. 3. CURRENT-LIMITATION CURVES FOR FUSES WITH CURRENT-LIMITING CHARACTERISTICS. 4. TIME-CURRENT COORDINATION CURVES (AVERAGE MELT) AND CURRENT-LIMITATION CURVES (INSTANTANEOUS PEAK LET-THROUGH CURRENT) FOR EACH TYPE AND RATING OF FUSE. 5. FUSE SIZES FOR ELEVATOR FEEDERS AND ELEVATOR DISCONNECT SWITCHES. Spec Section: 26 28 16 - ENCLOSED SWITCHES, FUSES AND CIRCUIT BREAKERS Status: OPEN | Info Exchange
| 07102 | Forwarded | For Review | 2020-04-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-13 | Submittal Number: 26 28 16-1.1 From: PATRICK KLEIN Final Due Date: 04/20/20 Subject: ENCLOSED SWITCHES, FUSES, AND CIRCUIT BREAKERS - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON CIRCUIT AND MOTOR DISCONNECT SWITCHES, AND EQUIPMENT CONNECTORS. FUSE PRODUCT DATA : FOR EACH TYPE OF FUSE INDICATED. INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS, DESCRIPTIONS OF INDIVIDUAL COMPONENTS, AND FINISHES FOR SPARE-FUSE CABINETS. INCLUDE THE FOLLOWING FOR EACH FUSE TYPE INDICATED: 1. AMBIENT TEMPERATURE ADJUSTMENT INFORMATION: IF RATINGS OF FUSES HAVE BEEN ADJUSTED TO ACCOMMODATE AMBIENT TEMPERATURES, PROVIDE LIST OF FUSES WITH ADJUSTED RATINGS. A. FOR EACH FUSE HAVING ADJUSTED RATINGS, INCLUDE LOCATION OF FUSE, ORIGINAL FUSE RATING, LOCAL AMBIENT TEMPERATURE, AND ADJUSTED FUSE RATING. B. PROVIDE MANUFACTURER'S TECHNICAL DATA ON WHICH AMBIENT TEMPERATURE ADJUSTMENT CALCULATIONS ARE BASED. 2. DIMENSIONS AND MANUFACTURER'S TECHNICAL DATA ON FEATURES, PERFORMANCE, ELECTRICAL CHARACTERISTICS, AND RATINGS. 3. CURRENT-LIMITATION CURVES FOR FUSES WITH CURRENT-LIMITING CHARACTERISTICS. 4. TIME-CURRENT COORDINATION CURVES (AVERAGE MELT) AND CURRENT-LIMITATION CURVES (INSTANTANEOUS PEAK LET-THROUGH CURRENT) FOR EACH TYPE AND RATING OF FUSE. 5. FUSE SIZES FOR ELEVATOR FEEDERS AND ELEVATOR DISCONNECT SWITCHES. Spec Section: 26 28 16 - ENCLOSED SWITCHES, FUSES AND CIRCUIT BREAKERS Status: OPEN | Info Exchange
| 05416 | Review Response | Approved as Noted | 2020-04-17 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.17 | Info Exchange
| 07354 | Responded and Closed | Approved as Noted | 2020-04-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-06 |  | 26 28 16-1.1 Product Data and Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-06 |  | 26 28 16-1.1 Product Data and Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-05 02:00 |  | 26 28 16-1.1 Product Data and Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-17 02:00 |  | 26 28 16-1.1 Product Data and Drawings-MAM-ME_POP.pdf
26 28 16-001-02 | 26 28 16 - ENCLOSED SWITCHES, FUSES AND CIRCUIT BREAKERS | 26 28 16-001-02 ENCLOSED SWITCHES, FUSES, AND CIRCUIT BREAKERS - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-17 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-31 | 2020-07-28 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06996 | Received | For Review | 2020-07-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-31 | Submittal Number: 26 28 16-1.2 From: PATRICK KLEIN Final Due Date: 07/30/20 Subject: ENCLOSED SWITCHES, FUSES, AND CIRCUIT BREAKERS - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON CIRCUIT AND MOTOR DISCONNECT SWITCHES, AND EQUIPMENT CONNECTORS. FUSE PRODUCT DATA : FOR EACH TYPE OF FUSE INDICATED. INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS, DESCRIPTIONS OF INDIVIDUAL COMPONENTS, AND FINISHES FOR SPARE-FUSE CABINETS. INCLUDE THE FOLLOWING FOR EACH FUSE TYPE INDICATED: 1. AMBIENT TEMPERATURE ADJUSTMENT INFORMATION: IF RATINGS OF FUSES HAVE BEEN ADJUSTED TO ACCOMMODATE AMBIENT TEMPERATURES, PROVIDE LIST OF FUSES WITH ADJUSTED RATINGS. A. FOR EACH FUSE HAVING ADJUSTED RATINGS, INCLUDE LOCATION OF FUSE, ORIGINAL FUSE RATING, LOCAL AMBIENT TEMPERATURE, AND ADJUSTED FUSE RATING. B. PROVIDE MANUFACTURER'S TECHNICAL DATA ON WHICH AMBIENT TEMPERATURE ADJUSTMENT CALCULATIONS ARE BASED. 2. DIMENSIONS AND MANUFACTURER'S TECHNICAL DATA ON FEATURES, PERFORMANCE, ELECTRICAL CHARACTERISTICS, AND RATINGS. 3. CURRENT-LIMITATION CURVES FOR FUSES WITH CURRENT-LIMITING CHARACTERISTICS. 4. TIME-CURRENT COORDINATION CURVES (AVERAGE MELT) AND CURRENT-LIMITATION CURVES (INSTANTANEOUS PEAK LET-THROUGH CURRENT) FOR EACH TYPE AND RATING OF FUSE. 5. FUSE SIZES FOR ELEVATOR FEEDERS AND ELEVATOR DISCONNECT SWITCHES. Spec Section: 26 28 16 - ENCLOSED SWITCHES, FUSES AND CIRCUIT BREAKERS Status: OPEN | Info Exchange
| 09372 | Forwarded | For Review | 2020-07-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-23 | Submittal Number: 26 28 16-1.2 From: PATRICK KLEIN Final Due Date: 07/30/20 Subject: ENCLOSED SWITCHES, FUSES, AND CIRCUIT BREAKERS - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON CIRCUIT AND MOTOR DISCONNECT SWITCHES, AND EQUIPMENT CONNECTORS. FUSE PRODUCT DATA : FOR EACH TYPE OF FUSE INDICATED. INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS, DESCRIPTIONS OF INDIVIDUAL COMPONENTS, AND FINISHES FOR SPARE-FUSE CABINETS. INCLUDE THE FOLLOWING FOR EACH FUSE TYPE INDICATED: 1. AMBIENT TEMPERATURE ADJUSTMENT INFORMATION: IF RATINGS OF FUSES HAVE BEEN ADJUSTED TO ACCOMMODATE AMBIENT TEMPERATURES, PROVIDE LIST OF FUSES WITH ADJUSTED RATINGS. A. FOR EACH FUSE HAVING ADJUSTED RATINGS, INCLUDE LOCATION OF FUSE, ORIGINAL FUSE RATING, LOCAL AMBIENT TEMPERATURE, AND ADJUSTED FUSE RATING. B. PROVIDE MANUFACTURER'S TECHNICAL DATA ON WHICH AMBIENT TEMPERATURE ADJUSTMENT CALCULATIONS ARE BASED. 2. DIMENSIONS AND MANUFACTURER'S TECHNICAL DATA ON FEATURES, PERFORMANCE, ELECTRICAL CHARACTERISTICS, AND RATINGS. 3. CURRENT-LIMITATION CURVES FOR FUSES WITH CURRENT-LIMITING CHARACTERISTICS. 4. TIME-CURRENT COORDINATION CURVES (AVERAGE MELT) AND CURRENT-LIMITATION CURVES (INSTANTANEOUS PEAK LET-THROUGH CURRENT) FOR EACH TYPE AND RATING OF FUSE. 5. FUSE SIZES FOR ELEVATOR FEEDERS AND ELEVATOR DISCONNECT SWITCHES. Spec Section: 26 28 16 - ENCLOSED SWITCHES, FUSES AND CIRCUIT BREAKERS Status: OPEN | Info Exchange
| 07219 | Review Response | Approved | 2020-07-27 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.27 | Info Exchange
| 09632 | Responded and Closed | Approved | 2020-07-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-16 |  | 26 28 16-1.2 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-16 |  | 26 28 16-1.2 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-15 02:00 |  | 26 28 16-1.2 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-28 02:00 |  | 26 28 16-1.2 Product Data-MAM-ME_pop.pdf
26 28 17-001-00 | 26 28 17 - COMPANY SWITCHES | 26 28 17-001-00 COMPANY SWITCHES - Product Data | Closed | Electrical, Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-18 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Brian Elwell (Idibri) |  |  |  | 2020-04-01 | 2020-04-17 | 31 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2020-04-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04903 | Received | For Review | 2020-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-01 | Submittal Number: 26 28 17-1.0 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: COMPANY SWITCHES - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON THE COMPANY SWITCHES. SWITCH PRODUCT DATA : INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS AND DESCRIPTIONS OF INDIVIDUAL COMPONENTS. WIRING DIAGRAMS SHOWING ALL INTERNAL WIRING. Spec Section: 26 28 17 - COMPANY SWITCHES Status: OPEN | Info Exchange
| 06696 | Forwarded | For Review | 2020-03-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-25 | Submittal Number: 26 28 17-1.0 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: COMPANY SWITCHES - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON THE COMPANY SWITCHES. SWITCH PRODUCT DATA : INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS AND DESCRIPTIONS OF INDIVIDUAL COMPONENTS. WIRING DIAGRAMS SHOWING ALL INTERNAL WIRING. Spec Section: 26 28 17 - COMPANY SWITCHES Status: OPEN | Info Exchange
| 05413 | Review Response | Approved as Noted/Resubmit | 2020-04-13 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Brian Elwell (Idibri); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. I apologize for not realizing this earlier, however Idibri should review the SNG pedestal signal compartment shown on page 23 of the submittal if they've confirmed in RFI 2337 that having the signal compartment incorporated into the same enclosure as the power pedestal is acceptable. If it is not acceptable to Idibri, then the equipment shall be resubmitted for review without signal compartment. Mark Lievens ME Engineers 2020.04.11 | Info Exchange
| 07278 | Forwarded | For Review and Comment | 2020-04-14 | Josh Dobken (Populous) | Brian Elwell (Idibri) | 2020-04-01 | Submittal Number: 26 28 17-1.0 From: PATRICK KLEIN Final Due Date: 03/31/20 Subject: COMPANY SWITCHES - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON THE COMPANY SWITCHES. SWITCH PRODUCT DATA : INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS AND DESCRIPTIONS OF INDIVIDUAL COMPONENTS. WIRING DIAGRAMS SHOWING ALL INTERNAL WIRING. Spec Section: 26 28 17 - COMPANY SWITCHES Status: OPEN | Info Exchange
| 07350 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-17 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. I apologize for not realizing this earlier, however Idibri should review the SNG pedestal signal compartment shown on page 23 of the submittal if they've confirmed in RFI 2337 that having the signal compartment incorporated into the same enclosure as the power pedestal is acceptable. If it is not acceptable to Idibri, then the equipment shall be resubmitted for review without signal compartment. Mark Lievens ME Engineers 2020.04.11 Refer to response to RFI 2337 (attached here) for related item requiring Idibri approval. -jhd/pop | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-17 |  | 26 28 17-1.0 Product Data and Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-17 |  | 26 28 17-1.0 Product Data and Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-16 02:00 |  | 26 28 17-1.0 Product Data and Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-16 02:00 |  | 26 28 17-1.0 Product Data and Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-17 02:00 |  | 26 28 17-1.0 Product Data and Drawings-MAM-ME_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-17 02:00 |  | Transmittal_RFI - RFI 2337 (Responded and Closed).pdf
26 28 17-001-01 | 26 28 17 - COMPANY SWITCHES | 26 28 17-001-01 COMPANY SWITCHES - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-18 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-02 07:00 | 2020-06-01 | 15 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-06-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05896 | Received | For Review | 2020-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-02 07:00 | Submittal Number: 26 28 17-1.1 From: PATRICK KLEIN Final Due Date: 06/01/20 Subject: COMPANY SWITCHES - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON THE COMPANY SWITCHES. SWITCH PRODUCT DATA : INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS AND DESCRIPTIONS OF INDIVIDUAL COMPONENTS. WIRING DIAGRAMS SHOWING ALL INTERNAL WIRING. Spec Section: 26 28 17 - COMPANY SWITCHES Status: OPEN | Info Exchange
| 07996 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-25 | Submittal Number: 26 28 17-1.1 From: PATRICK KLEIN Final Due Date: 06/01/20 Subject: COMPANY SWITCHES - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON THE COMPANY SWITCHES. SWITCH PRODUCT DATA : INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS AND DESCRIPTIONS OF INDIVIDUAL COMPONENTS. WIRING DIAGRAMS SHOWING ALL INTERNAL WIRING. Spec Section: 26 28 17 - COMPANY SWITCHES Status: OPEN | Info Exchange
| 06139 | Review Response | Approved as Noted/Resubmit | 2020-05-30 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.30 | Info Exchange
| 08307 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-01 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.30 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 26 28 17-1.1 Product Data and Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 26 28 17-1.1 Product Data and Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-17 02:00 |  | 26 28 17-1.1 Product Data and Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-01 02:00 |  | 26 28 17-1.1 Product Data and Drawings-MAM-ME_POP.pdf
26 28 17-001-02 | 26 28 17 - COMPANY SWITCHES | 26 28 17-001-02 COMPANY SWITCHES - Product Data | Closed | Electrical, Landscape, Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-06 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Brian Elwell (Idibri), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-07-20 | 2020-08-06 | 32 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06774 | Received | For Review | 2020-07-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-20 | Submittal Number: 26 28 17-1.2 From: PATRICK KLEIN Final Due Date: 07/17/20 Subject: COMPANY SWITCHES - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON THE COMPANY SWITCHES. SWITCH PRODUCT DATA : INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS AND DESCRIPTIONS OF INDIVIDUAL COMPONENTS. WIRING DIAGRAMS SHOWING ALL INTERNAL WIRING. Spec Section: 26 28 17 - COMPANY SWITCHES Status: OPEN | Info Exchange
| 09103 | Forwarded | For Review | 2020-07-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-13 | Submittal Number: 26 28 17-1.2 From: PATRICK KLEIN Final Due Date: 07/17/20 Subject: COMPANY SWITCHES - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON THE COMPANY SWITCHES. SWITCH PRODUCT DATA : INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS AND DESCRIPTIONS OF INDIVIDUAL COMPONENTS. WIRING DIAGRAMS SHOWING ALL INTERNAL WIRING. Spec Section: 26 28 17 - COMPANY SWITCHES Status: OPEN | Info Exchange
| 07416 | Review Response | Approved as Noted | 2020-07-16 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Brian Elwell (Idibri); Gareth Loveridge (Swift and Company Landscape Arch); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Brian – Can you please confirm the signal compartments on pages 13 and 14 of the attached PDF meet your design requirements for the SNG and ENG pedestals? Gareth – Can you please confirm that the bench in quad C at the Axis lounge area can accommodate the recessed site pedestal shown on page 12 of the attached PDF? Below is the location shown on the electrical drawings but I suspect this has shifted since the Axis lounge art impacts have been incorporated. Please let me know where this enclosure shall shift to. Thank you, Mark Lievens ME Engineers 2020.07.16 | Info Exchange
| 09390 | Forwarded | For Review | 2020-07-17 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Brian Elwell (Idibri); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-07-20 | Submittal Number: 26 28 17-1.2 From: PATRICK KLEIN Final Due Date: 07/17/20 Subject: COMPANY SWITCHES - PRODUCT DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON THE COMPANY SWITCHES. SWITCH PRODUCT DATA : INCLUDE CONSTRUCTION DETAILS, MATERIAL, DIMENSIONS AND DESCRIPTIONS OF INDIVIDUAL COMPONENTS. WIRING DIAGRAMS SHOWING ALL INTERNAL WIRING. Spec Section: 26 28 17 - COMPANY SWITCHES Status: OPEN | Email
| 07418 | Review Response | Revise and Resubmit | 2020-07-21 | Brian Elwell (Idibri) | Josh Dobken (Populous) |  | Idibri takes no exceptions. | Info Exchange
| 07419 | Review Response | Approved as Noted | 2020-07-29 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | We don't see any issue with this pedestal fitting, but it's within artist's scope and will need coordination. | Info Exchange
| 09888 | Responded and Closed | Approved as Noted | 2020-08-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Brian – Can you please confirm the signal compartments on pages 13 and 14 of the attached PDF meet your design requirements for the SNG and ENG pedestals? Gareth – Can you please confirm that the bench in quad C at the Axis lounge area can accommodate the recessed site pedestal shown on page 12 of the attached PDF? Below is the location shown on the electrical drawings but I suspect this has shifted since the Axis lounge art impacts have been incorporated. Please let me know where this enclosure shall shift to. Thank you, Mark Lievens ME Engineers 2020.07.16 Response (Approved) from: Brian Elwell (Idibri) Remarks: Idibri takes no exceptions. Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: We don't see any issue with this pedestal fitting, but it's within artist's scope and will need coordination. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-02 |  | 26 28 17-1.2 Company Switches.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-02 |  | 26 28 17-1.2 Company Switches.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-01 02:00 |  | 26 28 17-1.2 Company Switches.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-07-01 02:00 |  | 26 28 17-1.2 Company Switches.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-07-01 02:00 |  | 26 28 17-1.2 Company Switches.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-07-01 02:00 |  | 26 28 17-1.2 Company Switches.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-06 02:00 |  | 26 28 17-1.2 Company Switches - Combined_POP.pdf
26 28 17-004-00 | 26 28 17 - COMPANY SWITCHES | 26 28 17-004-00 COMPANY SWITCHES - Samples | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-08 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-22 | 2020-06-24 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-06-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06254 | Received | For Review | 2020-06-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-22 | Submittal Number: 26 28 17-4.0 From: PATRICK KLEIN Final Due Date: 06/19/20 Subject: COMPANY SWITCHES - SAMPLES Description: SUBMIT SAMPLE UL LISTING LABEL. Spec Section: 26 28 17 - COMPANY SWITCHES Status: OPEN | Info Exchange
| 08442 | Forwarded | For Review | 2020-06-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-15 | Submittal Number: 26 28 17-4.0 From: PATRICK KLEIN Final Due Date: 06/19/20 Subject: COMPANY SWITCHES - SAMPLES Description: SUBMIT SAMPLE UL LISTING LABEL. Spec Section: 26 28 17 - COMPANY SWITCHES Status: OPEN | Info Exchange
| 06628 | Review Response | Approved as Noted | 2020-06-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.23 | Info Exchange
| 08874 | Responded and Closed | Approved as Noted | 2020-06-24 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-05 |  | 26 28 17-4.0 UL Listing Label Sample-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-05 |  | 26 28 17-4.0 UL Listing Label Sample-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-06-04 02:00 |  | 26 28 17-4.0 UL Listing Label Sample-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-24 |  | 26 28 17-4.0 UL Listing Label Sample-MAM-ME_POP.pdf
26 32 13-001-00 | 26 32 13 - DIESEL-ENGINE DRIVEN GENERATOR SETS | 26 32 13-001-00: DIESEL ENGINE DRIVEN GENERATOR SETS - Product Data, Shop Drawings, and Wiring Diagrams | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-06 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matt Ross (Thornton Tomasetti) |  |  |  | 2019-12-20 | 2019-12-16 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03535 | Received | For Review | 2019-12-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-12-20 | Submittal Number: 26 32 13-1.0 From: PATRICK KLEIN Final Due Date: 12/20/19 Subject: DIESEL ENGINE DRIVEN GENERATOR SETS - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON DIESEL ENGINE-DRIVEN GENERATOR SETS AND COMPONENTS. INCLUDE MANUFACTURERS STANDARD PRODUCT WARRANTY, FOR DURATION OF NOT LESS THAN TWO-YEARS, FOR REPLACEMENT OF MATERIALS AND EQUIPMENT USED IN DIESEL GENERATOR SYSTEMS. SHOP DRAWINGS : THE CONTRACTOR SHALL SUBMIT COPIES OF PERTINENT DRAWINGS AND SCHEMATIC DIAGRAMS FOR APPROVAL AND SHALL INCLUDE THE FOLLOWING: 1. ENGINE GENERATOR SET INCLUDING PLANS AND ELEVATIONS OR RISER VIEWS CLEARLY INDICATING ENTRANCE POINTS FOR EACH OF THE INTERCONNECTIONS REQUIRED. 2. SLIP-OVER STEEL HOUSING SHOWING ALL PERTINENT DIMENSIONS AND DETAILS. EXHAUST SILENCER(S) WILL BE SUPPORTED ABOVE ROOF OF THE ENCLOSURE. 3. ENGINE GENERATOR/EXCITER CONTROL CUBICLE. 4. FUEL CONSUMPTION RATE CURVES AT VARIOUS LOADS, VENTILATION AND COMBUSTION CFM REQUIREMENTS. 5. EXHAUST MUFFLER AND VIBRATION ISOLATORS. 6. BATTERY CHARGER, BATTERY, AND BATTERY RACK. 7. FUEL TANK CONNECTION POINTS. 8. AUTOMATIC LOAD TRANSFER SWITCH. 9. LEGENDS FOR ALL DEVICES ON ALL DIAGRAMS. 10. A COMPLETE = 1-0 SCALED PLANS AND SECTIONS SHOWING THE EXACT GENERATOR AND TRANSFER SWITCH SYSTEM LAYOUT INCLUDING ALL COMPONENTS AND ACCESSORIES BEING PROVIDED OR REQUIRED FOR OPERATION AS SPECIFIED HEREIN COORDINATED WITH ARCHITECTURAL, STRUCTURAL AND OTHER PLANS, SHOWING OPERATIONAL AND MAINTENANCE CLEARANCE. INCLUDE IN PLACE, RECEPTACLES, LIGHTING FIXTURES, AND OTHER ITEMS PERTINENT TO THE COMPLETE INSTALLATION. 11. MAIN CIRCUIT BREAKER. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR DIESEL ENGINE-DRIVEN GENERATOR UNIT SHOWING CONNECTIONS TO ELECTRICAL POWER PANELS, FEEDERS, AUTOMATIC TRANSFER SWITCHES, AND ANCILLARY EQUIPMENT. DIFFERENTIATE BETWEEN PORTIONS OF WIRING THAT ARE MANUFACTURER INSTALLED AND PORTIONS THAT ARE FIELD-INSTALLED. CERTIFICATIONS : PROVIDE DIESEL ENGINE-DRIVE GENERATOR SETS CERTIFIED TEST RECORD OF THE FOLLOWING FINAL PRODUCTION TESTING: 1. SINGLE-STEP LOAD PICKUP. 2. TRANSIENT AND STEADY-STATE GOVERNING. 3. SAFETY SHUTDOWN DEVICE TESTING. 4. VOLTAGE REGULATION. 5. RATED POWER. 6. MAXIMUM POWER. PROVIDEA LETTER INDICATING THE MANUFACTURE HAS REVIEWED THE INSTALLATION CONDITIONS (MAINTENANCE CLEARANCES, COMBUSTION AIR INTAKE AND RADIATOR DISCHARGE CLEARANCES, ETC.) AND CONFIRM THAT THE GENERATOR CAN DELIVER THE 100% SPECIFIED RATED OUTPUT CAPACITY. NOT SUBMITTING THE LETTER WILL BE CAUSE FOR REJECTION OF THE SUBMITTAL. PROVIDE CERTIFIED TEST RECORD PRIOR TO ENGINE-DRIVEN GENERATOR SET BEING SHIPPED FROM FACTORY TO PROJECT LOCATION. Spec Section: 26 32 13 - DIESEL ENGINE DRIVEN GENERATORS SETS Status: OPEN | Info Exchange
| 05005 | Forwarded | For Review | 2019-12-06 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-13 | Submittal Number: 26 32 13-1.0 From: PATRICK KLEIN Final Due Date: 12/20/19 Subject: DIESEL ENGINE DRIVEN GENERATOR SETS - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON DIESEL ENGINE-DRIVEN GENERATOR SETS AND COMPONENTS. INCLUDE MANUFACTURERS STANDARD PRODUCT WARRANTY, FOR DURATION OF NOT LESS THAN TWO-YEARS, FOR REPLACEMENT OF MATERIALS AND EQUIPMENT USED IN DIESEL GENERATOR SYSTEMS. SHOP DRAWINGS : THE CONTRACTOR SHALL SUBMIT COPIES OF PERTINENT DRAWINGS AND SCHEMATIC DIAGRAMS FOR APPROVAL AND SHALL INCLUDE THE FOLLOWING: 1. ENGINE GENERATOR SET INCLUDING PLANS AND ELEVATIONS OR RISER VIEWS CLEARLY INDICATING ENTRANCE POINTS FOR EACH OF THE INTERCONNECTIONS REQUIRED. 2. SLIP-OVER STEEL HOUSING SHOWING ALL PERTINENT DIMENSIONS AND DETAILS. EXHAUST SILENCER(S) WILL BE SUPPORTED ABOVE ROOF OF THE ENCLOSURE. 3. ENGINE GENERATOR/EXCITER CONTROL CUBICLE. 4. FUEL CONSUMPTION RATE CURVES AT VARIOUS LOADS, VENTILATION AND COMBUSTION CFM REQUIREMENTS. 5. EXHAUST MUFFLER AND VIBRATION ISOLATORS. 6. BATTERY CHARGER, BATTERY, AND BATTERY RACK. 7. FUEL TANK CONNECTION POINTS. 8. AUTOMATIC LOAD TRANSFER SWITCH. 9. LEGENDS FOR ALL DEVICES ON ALL DIAGRAMS. 10. A COMPLETE = 1-0 SCALED PLANS AND SECTIONS SHOWING THE EXACT GENERATOR AND TRANSFER SWITCH SYSTEM LAYOUT INCLUDING ALL COMPONENTS AND ACCESSORIES BEING PROVIDED OR REQUIRED FOR OPERATION AS SPECIFIED HEREIN COORDINATED WITH ARCHITECTURAL, STRUCTURAL AND OTHER PLANS, SHOWING OPERATIONAL AND MAINTENANCE CLEARANCE. INCLUDE IN PLACE, RECEPTACLES, LIGHTING FIXTURES, AND OTHER ITEMS PERTINENT TO THE COMPLETE INSTALLATION. 11. MAIN CIRCUIT BREAKER. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR DIESEL ENGINE-DRIVEN GENERATOR UNIT SHOWING CONNECTIONS TO ELECTRICAL POWER PANELS, FEEDERS, AUTOMATIC TRANSFER SWITCHES, AND ANCILLARY EQUIPMENT. DIFFERENTIATE BETWEEN PORTIONS OF WIRING THAT ARE MANUFACTURER INSTALLED AND PORTIONS THAT ARE FIELD-INSTALLED. CERTIFICATIONS : PROVIDE DIESEL ENGINE-DRIVE GENERATOR SETS CERTIFIED TEST RECORD OF THE FOLLOWING FINAL PRODUCTION TESTING: 1. SINGLE-STEP LOAD PICKUP. 2. TRANSIENT AND STEADY-STATE GOVERNING. 3. SAFETY SHUTDOWN DEVICE TESTING. 4. VOLTAGE REGULATION. 5. RATED POWER. 6. MAXIMUM POWER. PROVIDEA LETTER INDICATING THE MANUFACTURE HAS REVIEWED THE INSTALLATION CONDITIONS (MAINTENANCE CLEARANCES, COMBUSTION AIR INTAKE AND RADIATOR DISCHARGE CLEARANCES, ETC.) AND CONFIRM THAT THE GENERATOR CAN DELIVER THE 100% SPECIFIED RATED OUTPUT CAPACITY. NOT SUBMITTING THE LETTER WILL BE CAUSE FOR REJECTION OF THE SUBMITTAL. PROVIDE CERTIFIED TEST RECORD PRIOR TO ENGINE-DRIVEN GENERATOR SET BEING SHIPPED FROM FACTORY TO PROJECT LOCATION. Spec Section: 26 32 13 - DIESEL ENGINE DRIVEN GENERATORS SETS Status: OPEN | Info Exchange
| 03633 | Review Response | Approved as Noted/Resubmit | 2019-12-13 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.12.13 | Info Exchange
| 05136 | Forwarded | For Review | 2019-12-13 | Josh Dobken (Populous) | Matt Ross (Thornton Tomasetti) | 2019-12-20 | Submittal Number: 26 32 13-1.0 From: PATRICK KLEIN Final Due Date: 12/20/19 Subject: DIESEL ENGINE DRIVEN GENERATOR SETS - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA ON DIESEL ENGINE-DRIVEN GENERATOR SETS AND COMPONENTS. INCLUDE MANUFACTURERS STANDARD PRODUCT WARRANTY, FOR DURATION OF NOT LESS THAN TWO-YEARS, FOR REPLACEMENT OF MATERIALS AND EQUIPMENT USED IN DIESEL GENERATOR SYSTEMS. SHOP DRAWINGS : THE CONTRACTOR SHALL SUBMIT COPIES OF PERTINENT DRAWINGS AND SCHEMATIC DIAGRAMS FOR APPROVAL AND SHALL INCLUDE THE FOLLOWING: 1. ENGINE GENERATOR SET INCLUDING PLANS AND ELEVATIONS OR RISER VIEWS CLEARLY INDICATING ENTRANCE POINTS FOR EACH OF THE INTERCONNECTIONS REQUIRED. 2. SLIP-OVER STEEL HOUSING SHOWING ALL PERTINENT DIMENSIONS AND DETAILS. EXHAUST SILENCER(S) WILL BE SUPPORTED ABOVE ROOF OF THE ENCLOSURE. 3. ENGINE GENERATOR/EXCITER CONTROL CUBICLE. 4. FUEL CONSUMPTION RATE CURVES AT VARIOUS LOADS, VENTILATION AND COMBUSTION CFM REQUIREMENTS. 5. EXHAUST MUFFLER AND VIBRATION ISOLATORS. 6. BATTERY CHARGER, BATTERY, AND BATTERY RACK. 7. FUEL TANK CONNECTION POINTS. 8. AUTOMATIC LOAD TRANSFER SWITCH. 9. LEGENDS FOR ALL DEVICES ON ALL DIAGRAMS. 10. A COMPLETE = 1-0 SCALED PLANS AND SECTIONS SHOWING THE EXACT GENERATOR AND TRANSFER SWITCH SYSTEM LAYOUT INCLUDING ALL COMPONENTS AND ACCESSORIES BEING PROVIDED OR REQUIRED FOR OPERATION AS SPECIFIED HEREIN COORDINATED WITH ARCHITECTURAL, STRUCTURAL AND OTHER PLANS, SHOWING OPERATIONAL AND MAINTENANCE CLEARANCE. INCLUDE IN PLACE, RECEPTACLES, LIGHTING FIXTURES, AND OTHER ITEMS PERTINENT TO THE COMPLETE INSTALLATION. 11. MAIN CIRCUIT BREAKER. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR DIESEL ENGINE-DRIVEN GENERATOR UNIT SHOWING CONNECTIONS TO ELECTRICAL POWER PANELS, FEEDERS, AUTOMATIC TRANSFER SWITCHES, AND ANCILLARY EQUIPMENT. DIFFERENTIATE BETWEEN PORTIONS OF WIRING THAT ARE MANUFACTURER INSTALLED AND PORTIONS THAT ARE FIELD-INSTALLED. CERTIFICATIONS : PROVIDE DIESEL ENGINE-DRIVE GENERATOR SETS CERTIFIED TEST RECORD OF THE FOLLOWING FINAL PRODUCTION TESTING: 1. SINGLE-STEP LOAD PICKUP. 2. TRANSIENT AND STEADY-STATE GOVERNING. 3. SAFETY SHUTDOWN DEVICE TESTING. 4. VOLTAGE REGULATION. 5. RATED POWER. 6. MAXIMUM POWER. PROVIDEA LETTER INDICATING THE MANUFACTURE HAS REVIEWED THE INSTALLATION CONDITIONS (MAINTENANCE CLEARANCES, COMBUSTION AIR INTAKE AND RADIATOR DISCHARGE CLEARANCES, ETC.) AND CONFIRM THAT THE GENERATOR CAN DELIVER THE 100% SPECIFIED RATED OUTPUT CAPACITY. NOT SUBMITTING THE LETTER WILL BE CAUSE FOR REJECTION OF THE SUBMITTAL. PROVIDE CERTIFIED TEST RECORD PRIOR TO ENGINE-DRIVEN GENERATOR SET BEING SHIPPED FROM FACTORY TO PROJECT LOCATION. Spec Section: 26 32 13 - DIESEL ENGINE DRIVEN GENERATORS SETS Status: OPEN | Info Exchange
| 03651 | Review Response | Approved as Noted/Resubmit | 2019-12-13 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  | ME Engineers have already responded/reviewed this submittal. We only wanted to make a comment on the weight provided on the summary sheet. See attached. TT's design currently does not have this additional weight of the generator taken into account. We are revisiting our design to accommodate per coordination between TT, ME and others. | Info Exchange
| 05165 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-16 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.12.13 Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: ME Engineers have already responded/reviewed this submittal. We only wanted to make a comment on the weight provided on the summary sheet. See attached. TT's design currently does not have this additional weight of the generator taken into account. We are revisiting our design to accommodate per coordination between TT, ME and others. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-06 02:00 |  | 26 32 13-1.0 Product Data, Shop Drawings, and Wiring Diagrams-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-06 02:00 |  | 26 32 13-1.0 Product Data, Shop Drawings, and Wiring Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-12-06 02:00 |  | 26 32 13-1.0 Product Data, Shop Drawings, and Wiring Diagrams-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-06 02:00 |  | 26 32 13-1.0 Product Data, Shop Drawings, and Wiring Diagrams-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-12-13 02:00 |  | 26 32 13-1.0 -TT extracted page.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-16 02:00 |  | 26 32 13-1.0 Product Data, Shop Drawings, and Wiring Diagrams-MAM-ME-TT_POP.pdf
26 32 13-001-01 | 26 32 13 - DIESEL-ENGINE DRIVEN GENERATOR SETS | 26 32 13-001-01 DIESEL ENGINE DRIVEN GENERATOR SETS - Product Data, Shop Drawings, and Wiring Diagrams | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-14 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-28 | 2020-05-04 | 21 |  | Record Copies; Transfers; Submittals | 26 32 13-001-02 - 26 32 13-001-01 DIESEL ENGINE DRIVEN GENERATOR SETS - Product Data, Shop Drawings, and Wiring Diagrams | 15 |  | 2020-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05322 | Received | For Review | 2020-04-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-28 | Submittal Number: 26 32 13-1.1 From: PATRICK KLEIN Final Due Date: 04/27/20 Subject: DIESEL ENGINE DRIVEN GENERATOR SETS - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: SUBMIT PLANS AND SECTION DRAWING SHOWING THE GENERATOR AND TRANSFER SWITCH SYSTEM LAYOUT INCLUDING ALL COMPONENTS AND ACCESSORIES.SHOW OPERATIONAL AND MAINTENANCE CLEARANCES AND INCLUDE IN PLACE RECEPTACLES, LIGHTING FIXTURES, ETC. SUBMIT 4 COPIES OF AN AGREEMENT FOR CONTINUED SERVICE AND MAINTENANCE OF DIESEL ENGINE-DRIVEN GENERATOR SETS FOR POSSIBLE OWNER ACCEPTANCE. Spec Section: 26 32 13 - DIESEL ENGINE DRIVEN GENERATORS SETS Status: OPEN | Info Exchange
| 07236 | Forwarded | For Review | 2020-04-13 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-20 | Submittal Number: 26 32 13-1.1 From: PATRICK KLEIN Final Due Date: 04/27/20 Subject: DIESEL ENGINE DRIVEN GENERATOR SETS - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: SUBMIT PLANS AND SECTION DRAWING SHOWING THE GENERATOR AND TRANSFER SWITCH SYSTEM LAYOUT INCLUDING ALL COMPONENTS AND ACCESSORIES.SHOW OPERATIONAL AND MAINTENANCE CLEARANCES AND INCLUDE IN PLACE RECEPTACLES, LIGHTING FIXTURES, ETC. SUBMIT 4 COPIES OF AN AGREEMENT FOR CONTINUED SERVICE AND MAINTENANCE OF DIESEL ENGINE-DRIVEN GENERATOR SETS FOR POSSIBLE OWNER ACCEPTANCE. Spec Section: 26 32 13 - DIESEL ENGINE DRIVEN GENERATORS SETS Status: OPEN | Info Exchange
| 05705 | Review Response | Approved as Noted/Resubmit | 2020-04-27 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.04.27 | Info Exchange
| 07735 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.04.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-13 |  | 26 32 13-1.1 PD Shops and Maintenance Agreement-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-13 |  | 26 32 13-1.1 PD Shops and Maintenance Agreement-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-12 02:00 |  | 26 32 13-1.1 PD Shops and Maintenance Agreement-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-05-04 02:00 |  | 26 32 13-1.1 PD Shops and Maintenance Agreement-MAM-ME_POP.pdf
26 32 13-001-02 | 26 32 13 - DIESEL-ENGINE DRIVEN GENERATOR SETS | 26 32 13-001-01 DIESEL ENGINE DRIVEN GENERATOR SETS - Product Data, Shop Drawings, and Wiring Diagrams | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 32 13-001-01 - 26 32 13-001-01 DIESEL ENGINE DRIVEN GENERATOR SETS - Product Data, Shop Drawings, and Wiring Diagrams | -1 | 2020-05-18
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-04 02:00 |  | 26 32 13-1.1 PD Shops and Maintenance Agreement-MAM-ME_POP.pdf
26 32 13-008-00 | 26 32 13 - DIESEL-ENGINE DRIVEN GENERATOR SETS | 26 32 13-008-00 DIESEL ENGINE DRIVEN GENERATOR SETS - Tests And Inspections | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-01 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-09-15 | 2021-09-21 | 21 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14554 | Received | For Review | 2021-09-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-15 | Submittal Number: 26 32 13-8.0 From: PATRICK KLEIN Final Due Date: 09/15/21 Subject: DIESEL ENGINE DRIVEN GENERATOR SETS - TESTS AND INSPECTIONS Description: START-UP TESTING : - 1. ENGAGE LOCAL EQUIPMENT MANUFACTURERS REPRESENTATIVE TO PERFORM START-UP AND BUILDING LOAD TESTS UPON COMPLETION OF INSTALLATION, WITH THE ARCHITECT/ENGINEER IN ATTENDANCE; PROVIDE CERTIFIED TEST RECORD. TESTS ARE TO INCLUDE THE FOLLOWING: A. CHECK FUEL, LUBRICATING OIL, AND ANTIFREEZE IN LIQUID COOLED MODELS FOR CONFORMITY TO THE MANUFACTURERS RECOMMENDATIONS UNDER ENVIRONMENTAL CONDITIONS PRESENT. B. TEST PRIOR TO CRANKING ENGINE FOR PROPER OPERATION, ACCESSORIES THAT NORMALLY FUNCTION WHILE THE SET IS INA STANDBY MODE. ACCESSORIES INCLUDE: ENGINE HEATERS, BATTERY CHARGER, GENERATOR STRIP HEATER, REMOTE ANNUNCIATOR. C. CHECK, DURING START-UP TEST MODE, FOR EXHAUST LEAKS, PATH OF EXHAUST GASES OUTSIDE THE BUILDING, COOLING AIR FLOW, MOVEMENT DURING STARTING AND STOPPING, VIBRATION DURING RUNNING, NORMAL AND EMERGENCY LINE-TO LINE VOLTAGE AND PHASE ROTATION. D. TEST, BY MEANS OF SIMULATED POWER OUTAGE, AUTOMATIC START-UP, REMOTE-AUTOMATIC STARTING, TRANSFER OF LOAD, AND AUTOMATIC SHUT-DOWN. PRIOR TO THIS TEST ADJUST FOR PROPER SYSTEM COORDINATION, TRANSFER SWITCH TIMERS. MONITOR THROUGHOUT THE TEST, ENGINE TEMPERATURE, OIL PRESSURE, BATTERY CHARGE LEVEL, GENERATOR VOLTAGE, AMPERES, AND FREQUENCY 2. PERFORM AN EIGHT-HOUR LOAD BANK TEST WITH THE FOLLOWING SEQUENCE: A. TWO HOURS START-UP 50% LOAD. B. FOUR HOURS 100% LOAD. C. TWO HOUR 50% LOAD. (TEST RESULTS SHALL BE DOCUMENTED AND GIVEN TO THE ENGINEER FOR REVIEW AND APPROVAL.) 3. UPON COMPLETION OF INSTALLATION DEMONSTRATE CAPABILITY AND COMPLIANCE OF SYSTEM WITH REQUIREMENTS. WHERE POSSIBLE, CORRECT MALFUNCTIONING UNITS AT SITE, THEN RETEST TO DEMONSTRATE COMPLIANCE; OTHERWISE, REMOVE AND REPLACE WITH NEW UNITS, AND PROCEED WITH RETESTING. INITIAL TESTING AND RETESTING TO BE AT NO COST TO OWNER. Spec Section: 26 32 13 - DIESEL ENGINE DRIVEN GENERATORS SETS Status: OPEN | Info Exchange
| 18766 | Forwarded | For Review | 2021-09-02 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-09-09 | Submittal Number: 26 32 13-8.0 From: PATRICK KLEIN Final Due Date: 09/15/21 Subject: DIESEL ENGINE DRIVEN GENERATOR SETS - TESTS AND INSPECTIONS Description: START-UP TESTING : - 1. ENGAGE LOCAL EQUIPMENT MANUFACTURERS REPRESENTATIVE TO PERFORM START-UP AND BUILDING LOAD TESTS UPON COMPLETION OF INSTALLATION, WITH THE ARCHITECT/ENGINEER IN ATTENDANCE; PROVIDE CERTIFIED TEST RECORD. TESTS ARE TO INCLUDE THE FOLLOWING: A. CHECK FUEL, LUBRICATING OIL, AND ANTIFREEZE IN LIQUID COOLED MODELS FOR CONFORMITY TO THE MANUFACTURERS RECOMMENDATIONS UNDER ENVIRONMENTAL CONDITIONS PRESENT. B. TEST PRIOR TO CRANKING ENGINE FOR PROPER OPERATION, ACCESSORIES THAT NORMALLY FUNCTION WHILE THE SET IS INA STANDBY MODE. ACCESSORIES INCLUDE: ENGINE HEATERS, BATTERY CHARGER, GENERATOR STRIP HEATER, REMOTE ANNUNCIATOR. C. CHECK, DURING START-UP TEST MODE, FOR EXHAUST LEAKS, PATH OF EXHAUST GASES OUTSIDE THE BUILDING, COOLING AIR FLOW, MOVEMENT DURING STARTING AND STOPPING, VIBRATION DURING RUNNING, NORMAL AND EMERGENCY LINE-TO LINE VOLTAGE AND PHASE ROTATION. D. TEST, BY MEANS OF SIMULATED POWER OUTAGE, AUTOMATIC START-UP, REMOTE-AUTOMATIC STARTING, TRANSFER OF LOAD, AND AUTOMATIC SHUT-DOWN. PRIOR TO THIS TEST ADJUST FOR PROPER SYSTEM COORDINATION, TRANSFER SWITCH TIMERS. MONITOR THROUGHOUT THE TEST, ENGINE TEMPERATURE, OIL PRESSURE, BATTERY CHARGE LEVEL, GENERATOR VOLTAGE, AMPERES, AND FREQUENCY 2. PERFORM AN EIGHT-HOUR LOAD BANK TEST WITH THE FOLLOWING SEQUENCE: A. TWO HOURS START-UP 50% LOAD. B. FOUR HOURS 100% LOAD. C. TWO HOUR 50% LOAD. (TEST RESULTS SHALL BE DOCUMENTED AND GIVEN TO THE ENGINEER FOR REVIEW AND APPROVAL.) 3. UPON COMPLETION OF INSTALLATION DEMONSTRATE CAPABILITY AND COMPLIANCE OF SYSTEM WITH REQUIREMENTS. WHERE POSSIBLE, CORRECT MALFUNCTIONING UNITS AT SITE, THEN RETEST TO DEMONSTRATE COMPLIANCE; OTHERWISE, REMOVE AND REPLACE WITH NEW UNITS, AND PROCEED WITH RETESTING. INITIAL TESTING AND RETESTING TO BE AT NO COST TO OWNER. Spec Section: 26 32 13 - DIESEL ENGINE DRIVEN GENERATORS SETS Status: OPEN | Info Exchange
| 14678 | Review Response | Approved as Noted | 2021-09-21 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.09.21 | Info Exchange
| 18930 | Responded and Closed | Approved as Noted | 2021-09-21 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.09.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-01 02:00 |  | 26 32 13-8.0 Diesel Engine Driven Generator Sets - Tests and Inspections.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-09-01 02:00 |  | 26 32 13-8.0 Diesel Engine Driven Generator Sets - Tests and Inspections.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-09-01 |  | 26 32 13-8.0 Diesel Engine Driven Generator Sets - Tests and Inspections.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-21 |  | 26 32 13-8.0 Diesel Engine Driven Generator Sets - ME_POP.pdf
26 33 53-001-00 | 26 33 53 - STATIC UNINTERRUPTABLE POWER SUPPLY | 26 33 53-001-00 STATIC UNINTERRUPTABLE POWER SUPPLY PD | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-11 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-09 | 2020-01-23 | 44 | General | Record Copies; Transfers; Submittals |  | 44 |  | 2020-01-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03593 | Received | For Review | 2019-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-09 | Submittal Number: 26 33 53-1.0 From: PATRICK KLEIN Final Due Date: 12/24/19 Subject: STATIC UNINTERRUPTABLE POWER SUPPLY - PRODUCT DATA, SCHEMATICS, TEST REPORTS, SPECIFICATION COMPLIANCE REVIEW, AND QUALIFICATION DATA Description: THE FOLLOWING SUBMITTAL DATA SHALL BE FURNISHED ACCORDING TO THE GENERAL CONDITIONS AND SECTION 26 05 02 AND SHALL INCLUDE, BUT NOT BE LIMITED TO: 1. UPS COMPLETE WITH PHYSICAL DIMENSIONS, ELEVATIONS, PLAN VIEWS, SCHEMATIC DIAGRAM, NAMEPLATE DATA, VOLTAGE, CURRENT AND SHORT CIRCUIT RATINGS, MATERIALS, BUS CAPACITY DATA, CONNECTOR DETAILS, FACTORY TEST REPORTS, INSTALLATION DETAILS, ETC. 2. OPERATION AND INSTALLATION MANUAL DESCRIBING SYSTEM INSTALLATION REQUIREMENTS AND SYSTEM OPERATION INCLUDING NECESSARY SAFETY REQUIREMENTS. THE UPS MANUFACTURER SHALL INCLUDEA SPECIFICATION COMPLIANCE REVIEW. THE COMPLIANCE REVIEW WILL BEA PARAGRAPH-BY-PARAGRAPH REVIEW OF THE SPECIFICATIONS WITH THE FOLLOWING DESIGNATIONS C - COMPLY, D - DEVIATE, OR N/A MARKED IN THE MARGIN BESIDE EACH PARAGRAPH. THE UPS MANUFACTURER SHALL HAVEA MINIMUM OF TEN (10) YEARS OF EXPERIENCE IN THE DESIGN, MANUFACTURE AND TESTING OF SOLID-STATE UPS. A LIST OF INSTALLED UPS OF THE SAME TYPE AS THE MANUFACTURER PROPOSES TO FURNISH FOR THIS APPLICATION SHALL BE SUPPLIED WITH THE PROPOSAL. Spec Section: 26 33 53 - STATIC UNINTERRUPTIBLE POWER SUPPLY Status: OPEN | Info Exchange
| 05074 | Forwarded | For Review | 2019-12-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-18 | Submittal Number: 26 33 53-1.0 From: PATRICK KLEIN Final Due Date: 12/24/19 Subject: STATIC UNINTERRUPTABLE POWER SUPPLY - PRODUCT DATA, SCHEMATICS, TEST REPORTS, SPECIFICATION COMPLIANCE REVIEW, AND QUALIFICATION DATA Description: THE FOLLOWING SUBMITTAL DATA SHALL BE FURNISHED ACCORDING TO THE GENERAL CONDITIONS AND SECTION 26 05 02 AND SHALL INCLUDE, BUT NOT BE LIMITED TO: 1. UPS COMPLETE WITH PHYSICAL DIMENSIONS, ELEVATIONS, PLAN VIEWS, SCHEMATIC DIAGRAM, NAMEPLATE DATA, VOLTAGE, CURRENT AND SHORT CIRCUIT RATINGS, MATERIALS, BUS CAPACITY DATA, CONNECTOR DETAILS, FACTORY TEST REPORTS, INSTALLATION DETAILS, ETC. 2. OPERATION AND INSTALLATION MANUAL DESCRIBING SYSTEM INSTALLATION REQUIREMENTS AND SYSTEM OPERATION INCLUDING NECESSARY SAFETY REQUIREMENTS. THE UPS MANUFACTURER SHALL INCLUDEA SPECIFICATION COMPLIANCE REVIEW. THE COMPLIANCE REVIEW WILL BEA PARAGRAPH-BY-PARAGRAPH REVIEW OF THE SPECIFICATIONS WITH THE FOLLOWING DESIGNATIONS C - COMPLY, D - DEVIATE, OR N/A MARKED IN THE MARGIN BESIDE EACH PARAGRAPH. THE UPS MANUFACTURER SHALL HAVEA MINIMUM OF TEN (10) YEARS OF EXPERIENCE IN THE DESIGN, MANUFACTURE AND TESTING OF SOLID-STATE UPS. A LIST OF INSTALLED UPS OF THE SAME TYPE AS THE MANUFACTURER PROPOSES TO FURNISH FOR THIS APPLICATION SHALL BE SUPPLIED WITH THE PROPOSAL. Spec Section: 26 33 53 - STATIC UNINTERRUPTIBLE POWER SUPPLY Status: OPEN | Info Exchange
| 05075 | Forwarded | For Review | 2019-12-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-18 | Submittal Number: 26 33 53-1.0 From: PATRICK KLEIN Final Due Date: 12/24/19 Subject: STATIC UNINTERRUPTABLE POWER SUPPLY - PRODUCT DATA, SCHEMATICS, TEST REPORTS, SPECIFICATION COMPLIANCE REVIEW, AND QUALIFICATION DATA Description: THE FOLLOWING SUBMITTAL DATA SHALL BE FURNISHED ACCORDING TO THE GENERAL CONDITIONS AND SECTION 26 05 02 AND SHALL INCLUDE, BUT NOT BE LIMITED TO: 1. UPS COMPLETE WITH PHYSICAL DIMENSIONS, ELEVATIONS, PLAN VIEWS, SCHEMATIC DIAGRAM, NAMEPLATE DATA, VOLTAGE, CURRENT AND SHORT CIRCUIT RATINGS, MATERIALS, BUS CAPACITY DATA, CONNECTOR DETAILS, FACTORY TEST REPORTS, INSTALLATION DETAILS, ETC. 2. OPERATION AND INSTALLATION MANUAL DESCRIBING SYSTEM INSTALLATION REQUIREMENTS AND SYSTEM OPERATION INCLUDING NECESSARY SAFETY REQUIREMENTS. THE UPS MANUFACTURER SHALL INCLUDEA SPECIFICATION COMPLIANCE REVIEW. THE COMPLIANCE REVIEW WILL BEA PARAGRAPH-BY-PARAGRAPH REVIEW OF THE SPECIFICATIONS WITH THE FOLLOWING DESIGNATIONS C - COMPLY, D - DEVIATE, OR N/A MARKED IN THE MARGIN BESIDE EACH PARAGRAPH. THE UPS MANUFACTURER SHALL HAVEA MINIMUM OF TEN (10) YEARS OF EXPERIENCE IN THE DESIGN, MANUFACTURE AND TESTING OF SOLID-STATE UPS. A LIST OF INSTALLED UPS OF THE SAME TYPE AS THE MANUFACTURER PROPOSES TO FURNISH FOR THIS APPLICATION SHALL BE SUPPLIED WITH THE PROPOSAL. Spec Section: 26 33 53 - STATIC UNINTERRUPTIBLE POWER SUPPLY Status: OPEN | Info Exchange
| 04038 | Review Response | Approved as Noted/Resubmit | 2020-01-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.22 | Info Exchange
| 05627 | Responded and Closed | Approved as Noted/Resubmit | 2020-01-23 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-10 |  | 26 33 53-1.0 PD, Shops, and Compliance Review-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-10 |  | 26 33 53-1.0 PD, Shops, and Compliance Review-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-10 |  | 26 33 53-1.0 PD, Shops, and Compliance Review-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-12-09 02:00 |  | 26 33 53-1.0 PD, Shops, and Compliance Review-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-23 02:00 |  | 26 33 53-1.0 PD, Shops, and Compliance Review-MAM-ME_POP.pdf
26 33 53-001-01 | 26 33 53 - STATIC UNINTERRUPTABLE POWER SUPPLY | 26 33 53-001-01 STATIC UNINTERRUPTABLE POWER SUPPLY - Product Data, Schematics, Test Reports, Specification Compliance Review, and Qualification Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-10 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-24 | 2020-03-18 | 9 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04726 | Received | For Review | 2020-03-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-03-24 | Submittal Number: 26 33 53-1.1 From: PATRICK KLEIN Final Due Date: 03/23/20 Subject: STATIC UNINTERRUPTABLE POWER SUPPLY - PRODUCT DATA, SCHEMATICS, TEST REPORTS, SPECIFICATION COMPLIANCE REVIEW, AND QUALIFICATION DATA Description: PROVIDE ELECTRICAL ROOM LAYOUTS AND COORDINATION STUDY. PROVIDE ADDITIONAL DOCUMENTATION AS REQUIRED PER SPECIFICATION COMPLIANCE REVIEW COMMENTS. Spec Section: 26 33 53 - STATIC UNINTERRUPTIBLE POWER SUPPLY Status: OPEN | Info Exchange
| 06493 | Forwarded | For Review | 2020-03-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-17 | Submittal Number: 26 33 53-1.1 From: PATRICK KLEIN Final Due Date: 03/23/20 Subject: STATIC UNINTERRUPTABLE POWER SUPPLY - PRODUCT DATA, SCHEMATICS, TEST REPORTS, SPECIFICATION COMPLIANCE REVIEW, AND QUALIFICATION DATA Description: PROVIDE ELECTRICAL ROOM LAYOUTS AND COORDINATION STUDY. PROVIDE ADDITIONAL DOCUMENTATION AS REQUIRED PER SPECIFICATION COMPLIANCE REVIEW COMMENTS. Spec Section: 26 33 53 - STATIC UNINTERRUPTIBLE POWER SUPPLY Status: OPEN | Info Exchange
| 04937 | Review Response | Approved as Noted | 2020-03-15 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.15 | Info Exchange
| 06733 | Responded and Closed | Approved as Noted | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.03.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-09 |  | 26 33 53-1.1 PD, Shops, and Compliance Review-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-09 |  | 26 33 53-1.1 PD, Shops, and Compliance Review-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-08 03:00 |  | 26 33 53-1.1 PD, Shops, and Compliance Review-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-18 02:00 |  | 26 33 53-1.1 PD, Shops, and Compliance Review-MAM-ME_POP.pdf
26 33 53-001-02 | 26 33 53 - STATIC UNINTERRUPTABLE POWER SUPPLY | 26 33 53-001-2 STATIC UNINTERRUPTABLE POWER SUPPLY - Communication Card Modbus Map | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-24 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-07 | 2020-04-10 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-04-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05008 | Received | For Review | 2020-03-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-07 | Submittal Number: 26 33 53-1.2 From: PATRICK KLEIN Final Due Date: 04/06/20 Subject: STATIC UNINTERRUPTABLE POWER SUPPLY - COMMUNICATION CARD MODBUS MAP Description: PROVIDE ELECTRICAL ROOM LAYOUTS AND COORDINATION STUDY. PROVIDE ADDITIONAL DOCUMENTATION AS REQUIRED PER SPECIFICATION COMPLIANCE REVIEW COMMENTS. Spec Section: 26 33 53 - STATIC UNINTERRUPTIBLE POWER SUPPLY Status: OPEN | Info Exchange
| 06821 | Forwarded | For Review | 2020-03-24 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-31 | Submittal Number: 26 33 53-1.2 From: PATRICK KLEIN Final Due Date: 04/06/20 Subject: STATIC UNINTERRUPTABLE POWER SUPPLY - COMMUNICATION CARD MODBUS MAP Description: PROVIDE ELECTRICAL ROOM LAYOUTS AND COORDINATION STUDY. PROVIDE ADDITIONAL DOCUMENTATION AS REQUIRED PER SPECIFICATION COMPLIANCE REVIEW COMMENTS. Spec Section: 26 33 53 - STATIC UNINTERRUPTIBLE POWER SUPPLY Status: OPEN | Info Exchange
| 05290 | Review Response | Approved | 2020-04-10 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.10 | Info Exchange
| 07197 | Responded and Closed | Approved | 2020-04-10 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-23 |  | 26 33 53-1.2 Communication Card Modbus Map-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-23 |  | 26 33 53-1.2 Communication Card Modbus Map-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-22 02:00 |  | 26 33 53-1.2 Communication Card Modbus Map-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-10 02:00 |  | 26 33 53-1.2 Communication Card Modbus Map-MAM-ME_POP.pdf
26 36 23-001-00 | 26 36 23 - AUTOMATIC TRANSFER SWITCHES | 26 36 23-001-00 AUTOMATIC TRANSFER SWITCHES PD, SD and Wiring Diagrams | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-11 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-03 | 2020-01-13 | 34 | General | Record Copies; Transfers; Submittals |  | 32 |  | 2020-01-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03594 | Received | For Review | 2019-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-03 | Submittal Number: 26 36 23-1.0 From: PATRICK KLEIN Final Due Date: 12/24/19 Subject: AUTOMATIC TRANSFER SWITCHES - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA AND INSTALLATION INSTRUCTIONS FOR ELECTRICAL POWER TRANSFER SWITCHES. SHOP DRAWINGS : SUBMIT =1-0 SCALE LAYOUT DRAWINGS OF ELECTRICAL GENERATOR AND TRANSFER SWITCHES SHOWING ACCURATELY SCALED EQUIPMENT LOCATIONS, HOUSEKEEPING PAD SIZE, LOCATION AND SPATIAL RELATIONSHIPS TO ASSOCIATED ELECTRICAL EQUIPMENT IN PROXIMITY. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL TRANSFER SWITCHES, AND ASSOCIATED CONTROL DEVICES SHOWING CONNECTIONS TO PRIME AND ALTERNATE POWER SOURCES, ELECTRICAL LOAD, AND EQUIPMENT COMPONENTS. DIFFERENTIATE BETWEEN PORTIONS OF WIRING THAT ARE MANUFACTURER-INSTALLED AND PORTIONS THAT ARE FIELD-INSTALLED. Spec Section: 26 36 23 - AUTOMATIC TRANSFER SWITCHES Status: OPEN | Info Exchange
| 05076 | Forwarded | For Review | 2019-12-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-18 | Submittal Number: 26 36 23-1.0 From: PATRICK KLEIN Final Due Date: 12/24/19 Subject: AUTOMATIC TRANSFER SWITCHES - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: PRODUCT DATA : SUBMIT MANUFACTURERS DATA AND INSTALLATION INSTRUCTIONS FOR ELECTRICAL POWER TRANSFER SWITCHES. SHOP DRAWINGS : SUBMIT =1-0 SCALE LAYOUT DRAWINGS OF ELECTRICAL GENERATOR AND TRANSFER SWITCHES SHOWING ACCURATELY SCALED EQUIPMENT LOCATIONS, HOUSEKEEPING PAD SIZE, LOCATION AND SPATIAL RELATIONSHIPS TO ASSOCIATED ELECTRICAL EQUIPMENT IN PROXIMITY. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL TRANSFER SWITCHES, AND ASSOCIATED CONTROL DEVICES SHOWING CONNECTIONS TO PRIME AND ALTERNATE POWER SOURCES, ELECTRICAL LOAD, AND EQUIPMENT COMPONENTS. DIFFERENTIATE BETWEEN PORTIONS OF WIRING THAT ARE MANUFACTURER-INSTALLED AND PORTIONS THAT ARE FIELD-INSTALLED. Spec Section: 26 36 23 - AUTOMATIC TRANSFER SWITCHES Status: OPEN | Info Exchange
| 03893 | Review Response | Approved as Noted | 2020-01-11 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.11 | Info Exchange
| 05449 | Responded and Closed | Approved as Noted/Resubmit | 2020-01-13 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to general comments on disposition sheets attached for items to be submitted. Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.01.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-10 |  | 26 36 23-1.0 PD, Shops, and Wiring Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-10 |  | 26 36 23-1.0 PD, Shops, and Wiring Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-12-09 02:00 |  | 26 36 23-1.0 PD, Shops, and Wiring Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-13 02:00 |  | 26 36 23-1.0 PD, Shops, and Wiring Diagrams-MAM-ME_POP.pdf
26 36 23-001-01 | 26 36 23 - AUTOMATIC TRANSFER SWITCHES | 26 36 23-001-01 AUTOMATIC TRANSFER SWITCHES - Product Data, Shop Drawings, and Wiring Diagrams | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-19 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-03 07:00 | 2020-06-01 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-06-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05912 | Received | For Review | 2020-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-03 07:00 | Submittal Number: 26 36 23-1.1 From: PATRICK KLEIN Final Due Date: 06/02/20 Subject: AUTOMATIC TRANSFER SWITCHES - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: RESUBMIT ATS WITH TAGS CALLED OUT FOR EACH Spec Section: 26 36 23 - AUTOMATIC TRANSFER SWITCHES Status: OPEN | Info Exchange
| 08021 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-25 | Submittal Number: 26 36 23-1.1 From: PATRICK KLEIN Final Due Date: 06/02/20 Subject: AUTOMATIC TRANSFER SWITCHES - PRODUCT DATA, SHOP DRAWINGS, AND WIRING DIAGRAMS Description: RESUBMIT ATS WITH TAGS CALLED OUT FOR EACH Spec Section: 26 36 23 - AUTOMATIC TRANSFER SWITCHES Status: OPEN | Info Exchange
| 06140 | Review Response | Approved as Noted | 2020-05-27 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.27 | Info Exchange
| 08308 | Responded and Closed | Approved as Noted | 2020-06-01 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.05.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 26 36 23-1.1 PD Shops and Wiring Diagrams-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 26 36 23-1.1 PD Shops and Wiring Diagrams-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-17 02:00 |  | 26 36 23-1.1 PD Shops and Wiring Diagrams-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-01 02:00 |  | 26 36 23-1.1 PD Shops and Wiring Diagrams-MAM-ME_POP.pdf
26 41 13-001-00 | 26 41 13 - LIGHTNING PROTECTION FOR STRUCTURES | 26 41 13-001-00: LIGHTNING PROTECTION FOR STRUCTURES - Product Data, Manufacturer's Instructions, Shop Drawings, and Calculations | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-27 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-13 | 2019-12-10 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03397 | Received | For Review | 2019-11-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-12-13 | Submittal Number: 26 41 13-1.0 From: PATRICK KLEIN Final Due Date: 12/10/19 Subject: LIGHTNING PROTECTION FOR STRUCTURES - PRODUCT DATA, MANUFACTURER'S INSTRUCTIONS, SHOP DRAWINGS, AND CALCULATIONS Description: SUBMIT PRODUCT DATA THAT INCLUDES ALL PERTINENT INFORMATION AND THE MATERIALS OF EACH COMPONENT, AND INCLUDE THE CURRENT UL LISTING NUMBER IN ACCORDANCE WITH ANSI/UL 96. SUBMIT MANUFACTURERS DETAILED INSTALLATION INSTRUCTIONS. SUBMIT THE INSTALLERS STATEMENT OF WORK (SOW) DETAILING THE PLAN OF INSTALLATION, FROM BEGINNING TO COMPLETION. SUBMIT THE UL DOCUMENTATION OF THE MANUFACTURERS LISTING. SUBMIT THE UL DOCUMENTATION OF THE LPS INSTALLERS LISTING. SUBMIT SHOP DRAWINGS SHOWING : - 1. LAYOUT OF ALL AIR TERMINALS, GROUNDING ELECTRODES, CONDUCTOR SIZES AND BONDING CONNECTIONS TO THE STRUCTURE AND OTHER METAL OBJECTS. 2. SHOP DRAWINGS SHALL INCLUDE SHADED AREA NOTING THE AREA OF PROTECTION FROM HIGHER ROOFS OR OTHER LPS EQUIPMENT, WHERE THAT PROTECTION HAS BEEN DESIGNED UTILIZING ZONES OF PROTECTION CALCULATIONS. THE METHOD/FORMULA AND WRITTEN CALCULATIONS FOR DETERMINING EACH AREA OF PROTECTION SHALL BE INCLUDED IN THE SUBMITTAL PACKAGE TO THE ENGINEER. IEC 62 305-2 CALCULATIONS USED TO DETERMINE THE DESIGN CRITERIA OF THE LPS. Spec Section: 26 41 13 - LIGHTNING PROTECTION FOR STRUCTURES Status: OPEN | Info Exchange
| 04863 | Forwarded | For Review | 2019-11-27 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-05 | Submittal Number: 26 41 13-1.0 From: PATRICK KLEIN Final Due Date: 12/10/19 Subject: LIGHTNING PROTECTION FOR STRUCTURES - PRODUCT DATA, MANUFACTURER'S INSTRUCTIONS, SHOP DRAWINGS, AND CALCULATIONS Description: SUBMIT PRODUCT DATA THAT INCLUDES ALL PERTINENT INFORMATION AND THE MATERIALS OF EACH COMPONENT, AND INCLUDE THE CURRENT UL LISTING NUMBER IN ACCORDANCE WITH ANSI/UL 96. SUBMIT MANUFACTURERS DETAILED INSTALLATION INSTRUCTIONS. SUBMIT THE INSTALLERS STATEMENT OF WORK (SOW) DETAILING THE PLAN OF INSTALLATION, FROM BEGINNING TO COMPLETION. SUBMIT THE UL DOCUMENTATION OF THE MANUFACTURERS LISTING. SUBMIT THE UL DOCUMENTATION OF THE LPS INSTALLERS LISTING. SUBMIT SHOP DRAWINGS SHOWING : - 1. LAYOUT OF ALL AIR TERMINALS, GROUNDING ELECTRODES, CONDUCTOR SIZES AND BONDING CONNECTIONS TO THE STRUCTURE AND OTHER METAL OBJECTS. 2. SHOP DRAWINGS SHALL INCLUDE SHADED AREA NOTING THE AREA OF PROTECTION FROM HIGHER ROOFS OR OTHER LPS EQUIPMENT, WHERE THAT PROTECTION HAS BEEN DESIGNED UTILIZING ZONES OF PROTECTION CALCULATIONS. THE METHOD/FORMULA AND WRITTEN CALCULATIONS FOR DETERMINING EACH AREA OF PROTECTION SHALL BE INCLUDED IN THE SUBMITTAL PACKAGE TO THE ENGINEER. IEC 62 305-2 CALCULATIONS USED TO DETERMINE THE DESIGN CRITERIA OF THE LPS. Spec Section: 26 41 13 - LIGHTNING PROTECTION FOR STRUCTURES Status: OPEN | Info Exchange
| 03567 | Review Response | Approved as Noted/Resubmit | 2019-12-10 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.12.10 | Info Exchange
| 05044 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2019.12.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-26 02:00 |  | 26 41 13-1.0 PD, Instructions, Shops, and Calcs-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-26 02:00 |  | 26 41 13-1.0 PD, Instructions, Shops, and Calcs-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-11-26 02:00 |  | 26 41 13-1.0 PD, Instructions, Shops, and Calcs-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-10 02:00 |  | 26 41 13-1.0 PD, Instructions, Shops, and Calcs-MAM-ME_POP.pdf
26 41 13-001-01 | 26 41 13 - LIGHTNING PROTECTION FOR STRUCTURES | 26 41 13-001-01 LIGHTNING PROTECTION FOR STRUCTURES - CCD 041 Revisions | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-22 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Allison Wood (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-06-08 07:00 | 2020-06-12 | 22 |  | Record Copies; Transfers; Submittals | 26 41 13-001-02 - 26 41 13-001-01 LIGHTNING PROTECTION FOR STRUCTURES - CCD 041 Revisions | 20 |  | 2020-06-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05991 | Received | For Review | 2020-05-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-08 07:00 | Submittal Number: 26 41 13-1.1 From: PATRICK KLEIN Final Due Date: 06/05/20 Subject: LIGHTNING PROTECTION FOR STRUCTURES - CCD 041 REVISIONS Description: SUBMIT PRODUCT DATA THAT INCLUDES ALL PERTINENT INFORMATION AND THE MATERIALS OF EACH COMPONENT, AND INCLUDE THE CURRENT UL LISTING NUMBER IN ACCORDANCE WITH ANSI/UL 96. SUBMIT MANUFACTURERS DETAILED INSTALLATION INSTRUCTIONS. SUBMIT THE INSTALLERS STATEMENT OF WORK (SOW) DETAILING THE PLAN OF INSTALLATION, FROM BEGINNING TO COMPLETION. SUBMIT THE UL DOCUMENTATION OF THE MANUFACTURERS LISTING. SUBMIT THE UL DOCUMENTATION OF THE LPS INSTALLERS LISTING. SUBMIT SHOP DRAWINGS SHOWING : - 1. LAYOUT OF ALL AIR TERMINALS, GROUNDING ELECTRODES, CONDUCTOR SIZES AND BONDING CONNECTIONS TO THE STRUCTURE AND OTHER METAL OBJECTS. 2. SHOP DRAWINGS SHALL INCLUDE SHADED AREA NOTING THE AREA OF PROTECTION FROM HIGHER ROOFS OR OTHER LPS EQUIPMENT, WHERE THAT PROTECTION HAS BEEN DESIGNED UTILIZING ZONES OF PROTECTION CALCULATIONS. THE METHOD/FORMULA AND WRITTEN CALCULATIONS FOR DETERMINING EACH AREA OF PROTECTION SHALL BE INCLUDED IN THE SUBMITTAL PACKAGE TO THE ENGINEER. IEC 62 305-2 CALCULATIONS USED TO DETERMINE THE DESIGN CRITERIA OF THE LPS. Spec Section: 26 41 13 - LIGHTNING PROTECTION FOR STRUCTURES Status: OPEN | Info Exchange
| 08128 | Forwarded | For Review | 2020-05-22 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Allison Wood (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-29 | Submittal Number: 26 41 13-1.1 From: PATRICK KLEIN Final Due Date: 06/05/20 Subject: LIGHTNING PROTECTION FOR STRUCTURES - CCD 041 REVISIONS Description: SUBMIT PRODUCT DATA THAT INCLUDES ALL PERTINENT INFORMATION AND THE MATERIALS OF EACH COMPONENT, AND INCLUDE THE CURRENT UL LISTING NUMBER IN ACCORDANCE WITH ANSI/UL 96. SUBMIT MANUFACTURERS DETAILED INSTALLATION INSTRUCTIONS. SUBMIT THE INSTALLERS STATEMENT OF WORK (SOW) DETAILING THE PLAN OF INSTALLATION, FROM BEGINNING TO COMPLETION. SUBMIT THE UL DOCUMENTATION OF THE MANUFACTURERS LISTING. SUBMIT THE UL DOCUMENTATION OF THE LPS INSTALLERS LISTING. SUBMIT SHOP DRAWINGS SHOWING : - 1. LAYOUT OF ALL AIR TERMINALS, GROUNDING ELECTRODES, CONDUCTOR SIZES AND BONDING CONNECTIONS TO THE STRUCTURE AND OTHER METAL OBJECTS. 2. SHOP DRAWINGS SHALL INCLUDE SHADED AREA NOTING THE AREA OF PROTECTION FROM HIGHER ROOFS OR OTHER LPS EQUIPMENT, WHERE THAT PROTECTION HAS BEEN DESIGNED UTILIZING ZONES OF PROTECTION CALCULATIONS. THE METHOD/FORMULA AND WRITTEN CALCULATIONS FOR DETERMINING EACH AREA OF PROTECTION SHALL BE INCLUDED IN THE SUBMITTAL PACKAGE TO THE ENGINEER. IEC 62 305-2 CALCULATIONS USED TO DETERMINE THE DESIGN CRITERIA OF THE LPS. Spec Section: 26 41 13 - LIGHTNING PROTECTION FOR STRUCTURES Status: OPEN | Info Exchange
| 06210 | Review Response | Approved as Noted | 2020-06-02 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached review. Thornton Tomasetti shall confirm loads imposed on base structure included within submittal are acceptable. Thank you, Mark Lievens ME Engineers 2020.06.02 | Info Exchange
| 08390 | Forwarded | For Review | 2020-06-04 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean Mc... | 2020-06-08 | Submittal Number: 26 41 13-1.1 From: PATRICK KLEIN Final Due Date: 06/05/20 Subject: LIGHTNING PROTECTION FOR STRUCTURES - CCD 041 REVISIONS Description: SUBMIT PRODUCT DATA THAT INCLUDES ALL PERTINENT INFORMATION AND THE MATERIALS OF EACH COMPONENT, AND INCLUDE THE CURRENT UL LISTING NUMBER IN ACCORDANCE WITH ANSI/UL 96. SUBMIT MANUFACTURERS DETAILED INSTALLATION INSTRUCTIONS. SUBMIT THE INSTALLERS STATEMENT OF WORK (SOW) DETAILING THE PLAN OF INSTALLATION, FROM BEGINNING TO COMPLETION. SUBMIT THE UL DOCUMENTATION OF THE MANUFACTURERS LISTING. SUBMIT THE UL DOCUMENTATION OF THE LPS INSTALLERS LISTING. SUBMIT SHOP DRAWINGS SHOWING : - 1. LAYOUT OF ALL AIR TERMINALS, GROUNDING ELECTRODES, CONDUCTOR SIZES AND BONDING CONNECTIONS TO THE STRUCTURE AND OTHER METAL OBJECTS. 2. SHOP DRAWINGS SHALL INCLUDE SHADED AREA NOTING THE AREA OF PROTECTION FROM HIGHER ROOFS OR OTHER LPS EQUIPMENT, WHERE THAT PROTECTION HAS BEEN DESIGNED UTILIZING ZONES OF PROTECTION CALCULATIONS. THE METHOD/FORMULA AND WRITTEN CALCULATIONS FOR DETERMINING EACH AREA OF PROTECTION SHALL BE INCLUDED IN THE SUBMITTAL PACKAGE TO THE ENGINEER. IEC 62 305-2 CALCULATIONS USED TO DETERMINE THE DESIGN CRITERIA OF THE LPS. Spec Section: 26 41 13 - LIGHTNING PROTECTION FOR STRUCTURES Status: OPEN | Info Exchange
| 06382 | Review Response | Approved as Noted/Resubmit | 2020-06-10 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attachment. | Info Exchange
| 08599 | Responded and Closed | Approved as Noted/Resubmit | 2020-06-12 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached review. Thornton Tomasetti shall confirm loads imposed on base structure included within submittal are acceptable. Thank you, Mark Lievens ME Engineers 2020.06.02 Response (Approved as Noted/Resubmit) from: Franz Kogler (Thornton Tomasetti) Remarks: See attachment. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-21 |  | 26 41 13-1.1 CCD 041 Revisions-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-21 |  | 26 41 13-1.1 CCD 041 Revisions-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-20 02:00 |  | 26 41 13-1.1 CCD 041 Revisions-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-20 02:00 |  | 26 41 13-1.1 CCD 041 Revisions-MAM.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-05-20 02:00 |  | 26 41 13-1.1 CCD 041 Revisions-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-12 02:00 |  | 26 41 13-1.1 CCD 041 Revisions-MAM-ME_TTReview_POP.pdf
26 41 13-001-02 | 26 41 13 - LIGHTNING PROTECTION FOR STRUCTURES | 26 41 13-001-01 LIGHTNING PROTECTION FOR STRUCTURES - CCD 041 Revisions | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 41 13-001-01 - 26 41 13-001-01 LIGHTNING PROTECTION FOR STRUCTURES - CCD 041 Revisions | -1 | 2020-06-26
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-12 02:00 |  | 26 41 13-1.1 CCD 041 Revisions-MAM-ME_TTReview_POP.pdf
26 41 13-010-00 | 26 41 13 - LIGHTNING PROTECTION FOR STRUCTURES | 26 41 13-010-00 LIGHTNING PROTECTION FOR STRUCTURES - Operation and Maintenance Manuals | Open - Overdue | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-27 | Forwarded - For Review |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) | 2021-10-04 | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  | 2021-10-11 |  | 11 |  | Record Copies; Transfers; Submittals |  | 11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14707 | Received | For Review | 2021-09-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-10-11 | Submittal Number: 26 41 13-10.0 From: PATRICK KLEIN Final Due Date: 10/10/20 Subject: LIGHTNING PROTECTION FOR STRUCTURES - OPERATION AND MAINTENANCE MANUALS Description: OBTAIN UL MASTER LABEL AND DELIVER THE UL MASTER LABEL DOCUMENT TO THE OWNER. THE UL MASTER LABEL IS NOW AN ELECTRONIC DOCUMENT AND IS VALID FOR ONLY 5 YEARS FROM DATE OF ISSUANCE Spec Section: 26 41 13 - LIGHTNING PROTECTION FOR STRUCTURES Status: OPEN | Info Exchange
| 18966 | Forwarded | For Review | 2021-09-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-10-04 | Submittal Number: 26 41 13-10.0 From: PATRICK KLEIN Final Due Date: 10/10/20 Subject: LIGHTNING PROTECTION FOR STRUCTURES - OPERATION AND MAINTENANCE MANUALS Description: OBTAIN UL MASTER LABEL AND DELIVER THE UL MASTER LABEL DOCUMENT TO THE OWNER. THE UL MASTER LABEL IS NOW AN ELECTRONIC DOCUMENT AND IS VALID FOR ONLY 5 YEARS FROM DATE OF ISSUANCE Spec Section: 26 41 13 - LIGHTNING PROTECTION FOR STRUCTURES Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-26 |  | 26 41 13-10.0 Operation and Maintenance Manuals-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-26 |  | 26 41 13-10.0 Operation and Maintenance Manuals-MAM.pdf
26 43 13-001-00 | 26 43 13 - SURGE PROTECTIVE DEVICE (SPD) SELENIUM ENHANCED | 26 43 13-001-00 SURGE PROTECTIVE DEVICE (SPD) (SELENIUM ENHANCED - Product Data, Test Data, and Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-13 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-01-27 | 2020-02-04 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03883 | Received | For Review | 2020-01-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-27 | Submittal Number: 26 43 13-1.0 From: PATRICK KLEIN Final Due Date: 01/24/20 Subject: SURGE PROTECTIVE DEVICE (SPD) (SELENIUM ENHANCED - PRODUCT DATA, TEST DATA, AND SHOP DRAWINGS Description: PRODUCT DATA : PROVIDE COMPLETE PRODUCT DATA DETAILING MANUFACTURERS MODEL NUMBER, SPECIFICATIONS, FEATURES AND OPTIONS. SUBSTITUTE/ALTERNATE PRODUCTS REQUIRE PRE-APPROVAL, AND SHALL ONLY BE CONSIDERED IF THE ATTACHMENT 1 SPD SUBMITTAL COMPLIANCE FORM IS FULLY COMPLETED AND SUBMITTED AT LEAST FOURTEEN (14) DAYS PRIOR TO BID DATE. TEST DATA : CERTIFIED DOCUMENTATION SHALL BE PROVIDED OF THE PRODUCTS UL 1449 THIRD EDITION CERTIFICATION, AS TESTED BY UNDERWRITERS LABORATORIES (UL). DATA SHALL INCLUDE TYPE CLASSIFICATION (TYPE 1, TYPE 2), VOLTAGE PROTECTIVE RATING (VPR), ACTUAL MCOV TEST VALUE, NOMINAL DISCHARGE CURRENT TEST (IN) RATING, AS WELL AS SURGE CURRENT FUSE TESTING, SINGLE PULSE SURGE CURRENT CAPACITY TESTING, AND MINIMUM REPETITIVE SURGE CURRENT CAPACITY TESTING. SHOP DRAWINGS : PROVIDE ELECTRICAL AND MECHANICAL DRAWINGS THAT INCLUDE DETAIL ON UNIT DIMENSIONS, WEIGHTS, FIELD CONNECTIONS AND MOUNTING PROVISIONS. Spec Section: 26 43 13 - SURGE PROTECTIVE DEVICES (SPD) (SELENIUM ENHANCED) Status: OPEN | Info Exchange
| 05440 | Forwarded | For Review | 2020-01-13 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-01-20 | Submittal Number: 26 43 13-1.0 From: PATRICK KLEIN Final Due Date: 01/24/20 Subject: SURGE PROTECTIVE DEVICE (SPD) (SELENIUM ENHANCED - PRODUCT DATA, TEST DATA, AND SHOP DRAWINGS Description: PRODUCT DATA : PROVIDE COMPLETE PRODUCT DATA DETAILING MANUFACTURERS MODEL NUMBER, SPECIFICATIONS, FEATURES AND OPTIONS. SUBSTITUTE/ALTERNATE PRODUCTS REQUIRE PRE-APPROVAL, AND SHALL ONLY BE CONSIDERED IF THE ATTACHMENT 1 SPD SUBMITTAL COMPLIANCE FORM IS FULLY COMPLETED AND SUBMITTED AT LEAST FOURTEEN (14) DAYS PRIOR TO BID DATE. TEST DATA : CERTIFIED DOCUMENTATION SHALL BE PROVIDED OF THE PRODUCTS UL 1449 THIRD EDITION CERTIFICATION, AS TESTED BY UNDERWRITERS LABORATORIES (UL). DATA SHALL INCLUDE TYPE CLASSIFICATION (TYPE 1, TYPE 2), VOLTAGE PROTECTIVE RATING (VPR), ACTUAL MCOV TEST VALUE, NOMINAL DISCHARGE CURRENT TEST (IN) RATING, AS WELL AS SURGE CURRENT FUSE TESTING, SINGLE PULSE SURGE CURRENT CAPACITY TESTING, AND MINIMUM REPETITIVE SURGE CURRENT CAPACITY TESTING. SHOP DRAWINGS : PROVIDE ELECTRICAL AND MECHANICAL DRAWINGS THAT INCLUDE DETAIL ON UNIT DIMENSIONS, WEIGHTS, FIELD CONNECTIONS AND MOUNTING PROVISIONS. Spec Section: 26 43 13 - SURGE PROTECTIVE DEVICES (SPD) (SELENIUM ENHANCED) Status: OPEN | Info Exchange
| 04201 | Review Response | Approved as Noted/Resubmit | 2020-02-04 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.04 | Info Exchange
| 05820 | Responded and Closed | Approved as Noted/Resubmit | 2020-02-04 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.02.04 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-10 |  | 26 43 13-1.0 PD, TD, and Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-10 |  | 26 43 13-1.0 PD, TD, and Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-01-09 02:00 |  | 26 43 13-1.0 PD, TD, and Shops-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-04 02:00 |  | 26 43 13-1.0 PD, TD, and Shops-MAM-ME_POP.pdf
26 43 13-001-01 | 26 43 13 - SURGE PROTECTIVE DEVICE (SPD) SELENIUM ENHANCED | 26 43 13-001-01 SURGE PROTECTIVE DEVICE (SPD) (SELENIUM ENHANCED - Product Data, Test Data, and Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-23 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-06 | 2020-04-03 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-04-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04998 | Received | For Review | 2020-03-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-06 | Submittal Number: 26 43 13-1.1 From: PATRICK KLEIN Final Due Date: 04/06/20 Subject: SURGE PROTECTIVE DEVICE (SPD) (SELENIUM ENHANCED - PRODUCT DATA, TEST DATA, AND SHOP DRAWINGS Description: PROVIDE SUBMITTAL COMPLIANCE FORM AS REQUIRED UNDER SECTION 2.6 Spec Section: 26 43 13 - SURGE PROTECTIVE DEVICES (SPD) (SELENIUM ENHANCED) Status: OPEN | Info Exchange
| 06808 | Forwarded | For Review | 2020-03-23 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-30 | Submittal Number: 26 43 13-1.1 From: PATRICK KLEIN Final Due Date: 04/06/20 Subject: SURGE PROTECTIVE DEVICE (SPD) (SELENIUM ENHANCED - PRODUCT DATA, TEST DATA, AND SHOP DRAWINGS Description: PROVIDE SUBMITTAL COMPLIANCE FORM AS REQUIRED UNDER SECTION 2.6 Spec Section: 26 43 13 - SURGE PROTECTIVE DEVICES (SPD) (SELENIUM ENHANCED) Status: OPEN | Info Exchange
| 05212 | Review Response | Approved as Noted | 2020-04-03 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.04.03 | Info Exchange
| 07084 | Responded and Closed | Approved as Noted | 2020-04-03 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.04.03 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-23 |  | 26 43 13-1.1 Submittal Compliance Form-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-23 |  | 26 43 13-1.1 Submittal Compliance Form-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-22 02:00 |  | 26 43 13-1.1 Submittal Compliance Form-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-03 02:00 |  | 26 43 13-1.1 Submittal Compliance Form-MAM-ME_POP.pdf
26 43 14-002-00 | 26 43 14 - SURGE PROTECTIVE DEVICE SPD | 26 43 14-002-00 SURGE PROTECTIVE DEVICE (SPD) - Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-14 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-28 | 2020-04-28 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05347 | Received | For Review | 2020-04-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-28 | Submittal Number: 26 43 14-2.0 From: PATRICK KLEIN Final Due Date: 04/28/20 Subject: SURGE PROTECTIVE DEVICE (SPD) - PRODUCT DATA Description: PRODUCT DATA : PROVIDE COMPLETE PRODUCT DATA DETAILING MANUFACTURERS MODEL NUMBER, SPECIFICATIONS, FEATURES AND OPTIONS. SHOP DRAWINGS : PROVIDE ELECTRICAL AND MECHANICAL DRAWINGS THAT INCLUDE DETAIL ON UNIT DIMENSIONS, WEIGHTS, FIELD CONNECTIONS AND MOUNTING PROVISIONS. TEST DATA : MANUFACTURERS SHALL SUBMIT CERTIFIED INDEPENDENT 3RD PARTY TEST DATA VERIFYING THE FOLLOWING: LIFE CYCLE TESTING, OVERCURRENT PROTECTION, UL1449 THIRD EDITION AS TESTED BY UNDERWRITERS LABORATORIES (UL), NOISE ATTENUATION AND SURGE CURRENT CAPACITY. DATA SHALL INCLUDE TYPE CLASSIFICATION (TYPE 1, TYPE 2), VOLTAGE PROTECTIVE RATING (VPR), ACTUAL MCOV TEST VALUE, NOMINAL DISCHARGE CURRENT TEST (IN) RATING. Spec Section: 26 43 14 - SURGE PROTECTION DEVICE (SPD) Status: OPEN | Info Exchange
| 07266 | Forwarded | For Review | 2020-04-14 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-21 | Submittal Number: 26 43 14-2.0 From: PATRICK KLEIN Final Due Date: 04/28/20 Subject: SURGE PROTECTIVE DEVICE (SPD) - PRODUCT DATA Description: PRODUCT DATA : PROVIDE COMPLETE PRODUCT DATA DETAILING MANUFACTURERS MODEL NUMBER, SPECIFICATIONS, FEATURES AND OPTIONS. SHOP DRAWINGS : PROVIDE ELECTRICAL AND MECHANICAL DRAWINGS THAT INCLUDE DETAIL ON UNIT DIMENSIONS, WEIGHTS, FIELD CONNECTIONS AND MOUNTING PROVISIONS. TEST DATA : MANUFACTURERS SHALL SUBMIT CERTIFIED INDEPENDENT 3RD PARTY TEST DATA VERIFYING THE FOLLOWING: LIFE CYCLE TESTING, OVERCURRENT PROTECTION, UL1449 THIRD EDITION AS TESTED BY UNDERWRITERS LABORATORIES (UL), NOISE ATTENUATION AND SURGE CURRENT CAPACITY. DATA SHALL INCLUDE TYPE CLASSIFICATION (TYPE 1, TYPE 2), VOLTAGE PROTECTIVE RATING (VPR), ACTUAL MCOV TEST VALUE, NOMINAL DISCHARGE CURRENT TEST (IN) RATING. Spec Section: 26 43 14 - SURGE PROTECTION DEVICE (SPD) Status: OPEN | Info Exchange
| 05603 | Review Response | Approved as Noted | 2020-04-27 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.27 | Info Exchange
| 07595 | Responded and Closed | Approved as Noted | 2020-04-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.27 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-14 |  | 26 43 14-2.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-14 |  | 26 43 14-2.0 Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-13 02:00 |  | 26 43 14-2.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-28 02:00 |  | 26 43 14-2.0 Product Data-MAM-ME_POP.pdf
26 51 13-001-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-001-00 LIGHTING FIXTURES - Shop Drawings | Closed | Electrical, Architectural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-08 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-22 | 2019-10-31 | 24 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-10-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02693 | Received | For Review | 2019-10-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-10-22 | Submittal Number: 26 51 13-1.0 From: PATRICK KLEIN Final Due Date: 01/25/20 Subject: LIGHTING FIXTURES - SHOP DRAWINGS Description: SHOP DRAWINGS SHALL INCLUDE BUT NOT BE LIMITED TO : - 1. FOR STANDARD CATALOG ITEMS WITH NO MODIFICATIONS, SUBMIT CATALOG CUT SHEETS PREPARED BY THE MANUFACTURER WHICH CLEARLY SHOW ALL ELEMENTS TO BE SUPPLIED AND ALL CORRESPONDING PRODUCT DATA (INCLUDING LAMPING; BALLAST MANUFACTURER AND MODEL NUMBER; VOLTAGE; ACCESSORIES OR OPTIONS AND ANY MISCELLANEOUS ITEMS DETAILED IN THE WRITTEN DESCRIPTION OF THE SPECIFICATION). IF CUT SHEET SHOWS MORE THAN ONE (1) FIXTURE TYPE, INFORMATION ON CUT SHEET WILL BE MARKED TO CLEARLY IDENTIFY WHICH COMPONENTS BELONG TO EACH SPECIFIC TYPE. 2. FOR LAMPS, SUBMIT CATALOG CUT SHEETS PREPARED BY THE MANUFACTURER WHICH CLEARLY SHOWS MANUFACTURER, CRI, CT, WATTAGE, BASE TYPE, LUMEN OUTPUT, LAMP LIFE, AND ANY OTHER PERTINENT INFORMATION. 3. FOR CUSTOM FIXTURES, MODIFIED FIXTURES OR LINEAR FIXTURES MOUNTED IN CONTINUOUS ROWS, SUBMITA REPRODUCIBLE DRAWING PREPARED BY THE MANUFACTURER SHOWING ALL DETAILS OF CONSTRUCTION, LENGTHS OF RUNS, LAMP SOURCE TYPE AND LOCATION, PENDANT LOCATIONS, POWER LOCATIONS, FINISHES AND LIST OF MATERIALS. DRAWINGS MUST BE TO SCALE. CONTRACTOR SHALL PROVIDE MANUFACTURER WITH FIELD DIMENSIONS WHERE REQUIRED. SHOULD THESE CUSTOM/MODIFIED FIXTURES BE SPECIFIC TOA MANUFACTURERS CEILING SYSTEM, PROVIDE BOTH THE FIXTURE SUBMITTAL AND THE CEILING SUBMITTAL SIMULTANEOUSLY. 4. FOR ALTERNATE PRODUCT SUBMITTED FOR REVIEW BY CONTRACTOR, THE ARCHITECT/ENGINEERS SHALL MAKE THE FINAL DETERMINATION IFA SAMPLE PRODUCT IS TO BE PROCURED BY THE CONTRACTOR FOR REVIEW. COST ASSOCIATED WITH SAMPLES FOR NON-CONFORMING SPECIFICATIONS SHALL BE BORNE BY THE CONTRACTOR. 5. FOR ALL SUBMITTALS UNDER PARAGRAPHS 1 THROUGH 3 ABOVE, MANUFACTURER SHALL PROVIDE SUBMITTALS WITHIN TWO WEEKS OF RECEIPT OF ORDER. ALL SUBMITTALS SHALL HAVE PROJECT NAME AND FIXTURE TYPE CLEARLY SHOWN. 6. THE ARCHITECT/ENGINEER SHALL MAKE THE FINAL DETERMINATION AS TO WHETHER OR NOT THE SUBMITTAL CONTAINS SUFFICIENT INFORMATION AND RESERVES THE RIGHT TO REQUESTA SHOP DRAWING IF THE FIXTURE CUT IS INSUFFICIENT. 7. MAINTENANCE DATA: SUBMIT MAINTENANCE DATA AND PARTS LIST FOR EACH LIGHTING FIXTURE, ACCESSORY AND ALSO INCLUDE TROUBLE-SHOOTING MAINTENANCE GUIDE. IN ADDITION TO THE PRODUCT DATA AND SHOP DRAWINGS, A MAINTENANCE MANUAL IN ACCORDANCE WITH GENERAL REQUIREMENTS OF DIVISION 1 SHALL BE PROVIDED. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 04025 | Forwarded | For Review | 2019-10-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-15 | Submittal Number: 26 51 13-1.0 From: PATRICK KLEIN Final Due Date: 01/25/20 Subject: LIGHTING FIXTURES - SHOP DRAWINGS Description: SHOP DRAWINGS SHALL INCLUDE BUT NOT BE LIMITED TO : - 1. FOR STANDARD CATALOG ITEMS WITH NO MODIFICATIONS, SUBMIT CATALOG CUT SHEETS PREPARED BY THE MANUFACTURER WHICH CLEARLY SHOW ALL ELEMENTS TO BE SUPPLIED AND ALL CORRESPONDING PRODUCT DATA (INCLUDING LAMPING; BALLAST MANUFACTURER AND MODEL NUMBER; VOLTAGE; ACCESSORIES OR OPTIONS AND ANY MISCELLANEOUS ITEMS DETAILED IN THE WRITTEN DESCRIPTION OF THE SPECIFICATION). IF CUT SHEET SHOWS MORE THAN ONE (1) FIXTURE TYPE, INFORMATION ON CUT SHEET WILL BE MARKED TO CLEARLY IDENTIFY WHICH COMPONENTS BELONG TO EACH SPECIFIC TYPE. 2. FOR LAMPS, SUBMIT CATALOG CUT SHEETS PREPARED BY THE MANUFACTURER WHICH CLEARLY SHOWS MANUFACTURER, CRI, CT, WATTAGE, BASE TYPE, LUMEN OUTPUT, LAMP LIFE, AND ANY OTHER PERTINENT INFORMATION. 3. FOR CUSTOM FIXTURES, MODIFIED FIXTURES OR LINEAR FIXTURES MOUNTED IN CONTINUOUS ROWS, SUBMITA REPRODUCIBLE DRAWING PREPARED BY THE MANUFACTURER SHOWING ALL DETAILS OF CONSTRUCTION, LENGTHS OF RUNS, LAMP SOURCE TYPE AND LOCATION, PENDANT LOCATIONS, POWER LOCATIONS, FINISHES AND LIST OF MATERIALS. DRAWINGS MUST BE TO SCALE. CONTRACTOR SHALL PROVIDE MANUFACTURER WITH FIELD DIMENSIONS WHERE REQUIRED. SHOULD THESE CUSTOM/MODIFIED FIXTURES BE SPECIFIC TOA MANUFACTURERS CEILING SYSTEM, PROVIDE BOTH THE FIXTURE SUBMITTAL AND THE CEILING SUBMITTAL SIMULTANEOUSLY. 4. FOR ALTERNATE PRODUCT SUBMITTED FOR REVIEW BY CONTRACTOR, THE ARCHITECT/ENGINEERS SHALL MAKE THE FINAL DETERMINATION IFA SAMPLE PRODUCT IS TO BE PROCURED BY THE CONTRACTOR FOR REVIEW. COST ASSOCIATED WITH SAMPLES FOR NON-CONFORMING SPECIFICATIONS SHALL BE BORNE BY THE CONTRACTOR. 5. FOR ALL SUBMITTALS UNDER PARAGRAPHS 1 THROUGH 3 ABOVE, MANUFACTURER SHALL PROVIDE SUBMITTALS WITHIN TWO WEEKS OF RECEIPT OF ORDER. ALL SUBMITTALS SHALL HAVE PROJECT NAME AND FIXTURE TYPE CLEARLY SHOWN. 6. THE ARCHITECT/ENGINEER SHALL MAKE THE FINAL DETERMINATION AS TO WHETHER OR NOT THE SUBMITTAL CONTAINS SUFFICIENT INFORMATION AND RESERVES THE RIGHT TO REQUESTA SHOP DRAWING IF THE FIXTURE CUT IS INSUFFICIENT. 7. MAINTENANCE DATA: SUBMIT MAINTENANCE DATA AND PARTS LIST FOR EACH LIGHTING FIXTURE, ACCESSORY AND ALSO INCLUDE TROUBLE-SHOOTING MAINTENANCE GUIDE. IN ADDITION TO THE PRODUCT DATA AND SHOP DRAWINGS, A MAINTENANCE MANUAL IN ACCORDANCE WITH GENERAL REQUIREMENTS OF DIVISION 1 SHALL BE PROVIDED. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 04026 | Forwarded | For Review | 2019-10-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-15 | Submittal Number: 26 51 13-1.0 From: PATRICK KLEIN Final Due Date: 01/25/20 Subject: LIGHTING FIXTURES - SHOP DRAWINGS Description: SHOP DRAWINGS SHALL INCLUDE BUT NOT BE LIMITED TO : - 1. FOR STANDARD CATALOG ITEMS WITH NO MODIFICATIONS, SUBMIT CATALOG CUT SHEETS PREPARED BY THE MANUFACTURER WHICH CLEARLY SHOW ALL ELEMENTS TO BE SUPPLIED AND ALL CORRESPONDING PRODUCT DATA (INCLUDING LAMPING; BALLAST MANUFACTURER AND MODEL NUMBER; VOLTAGE; ACCESSORIES OR OPTIONS AND ANY MISCELLANEOUS ITEMS DETAILED IN THE WRITTEN DESCRIPTION OF THE SPECIFICATION). IF CUT SHEET SHOWS MORE THAN ONE (1) FIXTURE TYPE, INFORMATION ON CUT SHEET WILL BE MARKED TO CLEARLY IDENTIFY WHICH COMPONENTS BELONG TO EACH SPECIFIC TYPE. 2. FOR LAMPS, SUBMIT CATALOG CUT SHEETS PREPARED BY THE MANUFACTURER WHICH CLEARLY SHOWS MANUFACTURER, CRI, CT, WATTAGE, BASE TYPE, LUMEN OUTPUT, LAMP LIFE, AND ANY OTHER PERTINENT INFORMATION. 3. FOR CUSTOM FIXTURES, MODIFIED FIXTURES OR LINEAR FIXTURES MOUNTED IN CONTINUOUS ROWS, SUBMITA REPRODUCIBLE DRAWING PREPARED BY THE MANUFACTURER SHOWING ALL DETAILS OF CONSTRUCTION, LENGTHS OF RUNS, LAMP SOURCE TYPE AND LOCATION, PENDANT LOCATIONS, POWER LOCATIONS, FINISHES AND LIST OF MATERIALS. DRAWINGS MUST BE TO SCALE. CONTRACTOR SHALL PROVIDE MANUFACTURER WITH FIELD DIMENSIONS WHERE REQUIRED. SHOULD THESE CUSTOM/MODIFIED FIXTURES BE SPECIFIC TOA MANUFACTURERS CEILING SYSTEM, PROVIDE BOTH THE FIXTURE SUBMITTAL AND THE CEILING SUBMITTAL SIMULTANEOUSLY. 4. FOR ALTERNATE PRODUCT SUBMITTED FOR REVIEW BY CONTRACTOR, THE ARCHITECT/ENGINEERS SHALL MAKE THE FINAL DETERMINATION IFA SAMPLE PRODUCT IS TO BE PROCURED BY THE CONTRACTOR FOR REVIEW. COST ASSOCIATED WITH SAMPLES FOR NON-CONFORMING SPECIFICATIONS SHALL BE BORNE BY THE CONTRACTOR. 5. FOR ALL SUBMITTALS UNDER PARAGRAPHS 1 THROUGH 3 ABOVE, MANUFACTURER SHALL PROVIDE SUBMITTALS WITHIN TWO WEEKS OF RECEIPT OF ORDER. ALL SUBMITTALS SHALL HAVE PROJECT NAME AND FIXTURE TYPE CLEARLY SHOWN. 6. THE ARCHITECT/ENGINEER SHALL MAKE THE FINAL DETERMINATION AS TO WHETHER OR NOT THE SUBMITTAL CONTAINS SUFFICIENT INFORMATION AND RESERVES THE RIGHT TO REQUESTA SHOP DRAWING IF THE FIXTURE CUT IS INSUFFICIENT. 7. MAINTENANCE DATA: SUBMIT MAINTENANCE DATA AND PARTS LIST FOR EACH LIGHTING FIXTURE, ACCESSORY AND ALSO INCLUDE TROUBLE-SHOOTING MAINTENANCE GUIDE. IN ADDITION TO THE PRODUCT DATA AND SHOP DRAWINGS, A MAINTENANCE MANUAL IN ACCORDANCE WITH GENERAL REQUIREMENTS OF DIVISION 1 SHALL BE PROVIDED. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 02802 | Review Response | Approved as Noted/Resubmit | 2019-10-16 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review form with most of the comments included in today's submittal review party. The rest of the comments are included in Mortenson's submittal notes via the bluebeam session. Let us know if there are any questions. Thanks, Mark Lievens ME Engineers 2019.10.14 | Info Exchange
| 04393 | Responded and Closed | Approved as Noted/Resubmit | 2019-10-31 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Ankur Singhal (Mortenson Construction) |  | See attached submittal. Please note that Swift has added comments to the PDF. Also see notes associated with S9 fixtures. From ME (Mark Lievens): Please see the attached submittal review form with most of the comments included in today's submittal review party. The rest of the comments are included in Mortenson's submittal notes via the bluebeam session. Let us know if there are any questions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-07 |  | 26 51 13-1.00 Lighting Fixtures - Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-07 |  | 26 51 13-1.00 Lighting Fixtures - Shop Drawings - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-07 |  | 26 51 13-1.00 Lighting Fixtures - Shop Drawings - MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-10-06 02:00 |  | 26 51 13-1.00 Lighting Fixtures - Shop Drawings - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2019-10-31 |  | 26 51 13-1.00 Lighting Fixtures - Shop Drawings - MAM - POP_SWIFT_ME.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2019-10-31 |  | 26 51 13-1.00 Lighting Fixtures -ME Submittal Review Form.pdf
26 51 13-001-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-001-01: LIGHTING FIXTURES - Shop Drawings | Closed | Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-09 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), David Schwarz (David M. Schwarz/Architectural Services, Inc.), Heidi Evans (ME Engineers), Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Kuebler Perry (Populous) |  |  |  | 2020-01-07 | 2020-01-16 | 39 | General | Record Copies; Transfers; Submittals |  | 24 |  | 2020-01-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03575 | Received | For Review | 2019-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2020-01-07 | Submittal Number: 26 51 13-1.1 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: LIGHTING FIXTURES - SHOP DRAWINGS Description: RESUBMIT ALL S9 FIXTURES AND OTHER FIXTURES PER DISCUSSION AT THE 10/16/19 SUBMITTAL PARTY. NOTE THAT SITE POLES WILL BE SILVER COLORED, SO CORRESPONDING FIXTURES SHOULD ALSO BE SILVER. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 05052 | Forwarded | For Review | 2019-12-10 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); David Schwarz (David M. Schwarz/Architectural Services, Inc.); Heidi Evans (ME Engineers) | 2019-12-17 | Submittal Number: 26 51 13-1.1 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: LIGHTING FIXTURES - SHOP DRAWINGS Description: RESUBMIT ALL S9 FIXTURES AND OTHER FIXTURES PER DISCUSSION AT THE 10/16/19 SUBMITTAL PARTY. NOTE THAT SITE POLES WILL BE SILVER COLORED, SO CORRESPONDING FIXTURES SHOULD ALSO BE SILVER. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 05172 | Forwarded | For Review | 2019-12-16 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2019-12-23 | Submittal Number: 26 51 13-1.1 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: LIGHTING FIXTURES - SHOP DRAWINGS Description: RESUBMIT ALL S9 FIXTURES AND OTHER FIXTURES PER DISCUSSION AT THE 10/16/19 SUBMITTAL PARTY. NOTE THAT SITE POLES WILL BE SILVER COLORED, SO CORRESPONDING FIXTURES SHOULD ALSO BE SILVER. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 03779 | Review Response | Approved as Noted/Resubmit | 2020-01-02 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2020.01.02 | Info Exchange
| 05317 | Forwarded | For Review | 2020-01-03 | Josh Dobken (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous) | 2020-01-07 | Submittal Number: 26 51 13-1.1 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: LIGHTING FIXTURES - SHOP DRAWINGS Description: RESUBMIT ALL S9 FIXTURES AND OTHER FIXTURES PER DISCUSSION AT THE 10/16/19 SUBMITTAL PARTY. NOTE THAT SITE POLES WILL BE SILVER COLORED, SO CORRESPONDING FIXTURES SHOULD ALSO BE SILVER. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 05517 | Responded and Closed | Approved as Noted/Resubmit | 2020-01-16 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens/Bryan Klote ME Engineers/Populous 2020.01.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-09 02:00 |  | 26 51 13-1.1 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 26 51 13-1.1 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 26 51 13-1.1 Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-12-09 02:00 |  | 26 51 13-1.1 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 26 51 13-1.1 Shop Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-01-16 |  | 26 51 13-1.1 Shop Drawings-MAM-ME_POP.pdf
26 51 13-001-02 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-001-02 LIGHTING FIXTURES - Shop Drawings | Closed | Electrical, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-12 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Allison Wood (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-03-26 | 2020-04-15 | 35 |  | Record Copies; Transfers; Submittals |  | 34 |  | 2020-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04780 | Received | For Review | 2020-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-03-26 | Submittal Number: 26 51 13-1.2 From: PATRICK KLEIN Final Due Date: 03/25/20 Subject: LIGHTING FIXTURES - SHOP DRAWINGS Description: L13C, L14A, L14B, L16, L18, D3, D7, S3, S12, S14A, S17, S18, AND S24 AT A MINIMUM WILL ALL REQUIRE RESUBMITTALS SINCE THEY DO NOT HAVE A LIGHT FIXTURE APPROVED BETWEEN THE 1.0, 1.1, AND 5.0 SUBMITTALS. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 06555 | Forwarded | For Review | 2020-03-12 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Allison Wood (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-03-19 | Submittal Number: 26 51 13-1.2 From: PATRICK KLEIN Final Due Date: 03/25/20 Subject: LIGHTING FIXTURES - SHOP DRAWINGS Description: L13C, L14A, L14B, L16, L18, D3, D7, S3, S12, S14A, S17, S18, AND S24 AT A MINIMUM WILL ALL REQUIRE RESUBMITTALS SINCE THEY DO NOT HAVE A LIGHT FIXTURE APPROVED BETWEEN THE 1.0, 1.1, AND 5.0 SUBMITTALS. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 05186 | Review Response | Approved as Noted/Resubmit | 2020-03-26 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.3.26 | Info Exchange
| 05398 | Review Response | Approved as Noted | 2020-04-14 | Gareth Loveridge (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  |  | Email
| 07330 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-15 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please resubmit per comments provided by ME. Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.3.26 Response (Approved as Noted) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-12 |  | 26 51 13-1.2 Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-12 |  | 26 51 13-1.2 Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-11 02:00 |  | 26 51 13-1.2 Shop Drawings-MAM.pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2020-04-15 02:00 |  | 26 51 13-1.2 Shop Drawings-MAM-ME_POP-SWIFT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-16 02:00 |  | 26 51 13-1.2 Shop Drawings-Final.pdf
26 51 13-001-03 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-001-03 LIGHTING FIXTURES - Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-18 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Allison Wood (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-02 07:00 | 2020-06-04 | 18 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-06-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05897 | Received | For Review | 2020-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-02 07:00 | Submittal Number: 26 51 13-1.3 From: PATRICK KLEIN Final Due Date: 06/01/20 Subject: LIGHTING FIXTURES - SHOP DRAWINGS Description: D3, S12, AND S18 AT A MINIMUM WILL ALL REQUIRE RESUBMITTALS SINCE THEY DO NOT HAVE A LIGHT FIXTURE APPROVED BETWEEN THE 1.0, 1.1, 1.2, AND 5.0 SUBMITTALS. S17 AND S24 FIXTURES ARE CURRENTLY ADD ALTERNATES AND ARE NOT WITHIN THE BASE BUILDING SCOPE OF WORK. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 07998 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Allison Wood (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-25 | Submittal Number: 26 51 13-1.3 From: PATRICK KLEIN Final Due Date: 06/01/20 Subject: LIGHTING FIXTURES - SHOP DRAWINGS Description: D3, S12, AND S18 AT A MINIMUM WILL ALL REQUIRE RESUBMITTALS SINCE THEY DO NOT HAVE A LIGHT FIXTURE APPROVED BETWEEN THE 1.0, 1.1, 1.2, AND 5.0 SUBMITTALS. S17 AND S24 FIXTURES ARE CURRENTLY ADD ALTERNATES AND ARE NOT WITHIN THE BASE BUILDING SCOPE OF WORK. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 06201 | Review Response | Approved as Noted | 2020-05-31 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal. Populous - please confirm the light fixture finishes within the submittal. Thank you, Mark Lievens ME Engineers 2020.05.31 | Info Exchange
| 08380 | Responded and Closed | Approved as Noted | 2020-06-04 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal. Populous - please confirm the light fixture finishes within the submittal. Thank you, Mark Lievens ME Engineers 2020.05.31 S18 fixtures to be black. S12 fixtures to be silver. See attached submittal. - jhd/ pop | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 26 51 13-1.3 S12 and S18 Fixtures-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 26 51 13-1.3 S12 and S18 Fixtures-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-17 02:00 |  | 26 51 13-1.3 S12 and S18 Fixtures-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-04 02:00 |  | 26 51 13-1.3 S12 and S18 Fixtures-MAM-ME_POP.pdf
26 51 13-001-04 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-001-04 LIGHTING FIXTURES - D3,D18, and L27 Light Fixture | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-27 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Nick Theimer (ME Engineers), Gareth Loveridge (Swift and Company Landscape Arch), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-11 07:00 | 2020-09-15 | 20 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-09-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07778 | Received | For Review | 2020-08-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-09-11 07:00 | Submittal Number: 26 51 13-1.4 From: PATRICK KLEIN Final Due Date: 09/10/20 Subject: LIGHTING FIXTURES - D3,D18, AND L27 LIGHT FIXTURE Description: D3 LIGHT FIXTURE Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10358 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Rhys Van Bemmel (Swift and Company Landscape Arch); Nick Theimer (ME Engineers); Gareth Loveridge (Swift and Company Landscape Arch); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-03 | Submittal Number: 26 51 13-1.4 From: PATRICK KLEIN Final Due Date: 09/10/20 Subject: LIGHTING FIXTURES - D3,D18, AND L27 LIGHT FIXTURE Description: D3 LIGHT FIXTURE Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 08123 | Review Response | Approved as Noted/Resubmit | 2020-09-14 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Populous shall confirm finish of light fixture type L27. Fixture is used within main concourse concessions' front of house feature ceilings. Thank you, Mark Lievens ME Engineers 2020.09.14 | Info Exchange
| 10790 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-15 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.09.14 | Info Exchange
| 10902 | Sent | For Information Only | 2020-09-18 | Josh Dobken (Populous) | Tyrone Thornton (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Responded and Closed (Approved as Noted/Resubmit) to: Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) Remarks: Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.09.14 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 26 51 13-1.4 D3 D18 and L27 Resubmittal-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-26 |  | 26 51 13-1.4 D3 D18 and L27 Resubmittal-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-26 |  | 26 51 13-1.4 D3 D18 and L27 Resubmittal-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-15 |  | 26 51 13-1.4 D3 D18 and L27 Resubmittal-MAM-ME_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2020-08-25 02:00 |  | 26 51 13-1.4 D3 D18 and L27 Resubmittal-MAM.pdf
26 51 13-001-05 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-001-05 LIGHTING FIXTURES - CCD Updates and S19 and D3 Resubmittal | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-22 | 2021-03-10 | 31 |  | Record Copies; Transfers; Submittals | 26 51 13-001-05-01 - 26 51 13-001-05 LIGHTING FIXTURES - CCD Updates and S19 and D3 Resubmittal | 31 |  | 2021-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11248 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-02-22 | Submittal Number: 26 51 13-1.5 From: PATRICK KLEIN Final Due Date: 02/19/21 Subject: LIGHTING FIXTURES - CCD UPDATES AND S19 AND D3 RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 14563 | Forwarded | For Review | 2021-02-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-15 | Submittal Number: 26 51 13-1.5 From: PATRICK KLEIN Final Due Date: 02/19/21 Subject: LIGHTING FIXTURES - CCD UPDATES AND S19 AND D3 RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11917 | Review Response | Approved as Noted/Resubmit | 2021-03-04 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mortenson has marked this submittal as HOT so if you could please return by end of day today, that would be much appreciated. Below are the items we're looking for input from Populous on before this is returned: 1. Type L33 Finish - White or Black. These are located at the UC concessions in Quads C&D. They are grazing the vertical soffit. 2. Type L35 Finish - Verify Black Finish. These are the suspended linears within the open office area at the mech mezz level area A. 3. Type D3 - Comments and feedback from Todd incorproated into our comments. Uplights within atrium. 4. Type S19 Finish - Verify White Finish. These are utized at the NE and NW egree stair canopies on site. The fixture is inteded to match the existing fixtures used in this canopy. 5. Type B28A Finish - White or Black Finish. These are cylinders used within the open office areas at mech mezz level area A. Thanks, Mark Lievens ME Engineers 2021.03.04 | Info Exchange
| 11907 | Review Response | Approved as Noted/Resubmit | 2021-03-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11908 | Review Response | Approved as Noted/Resubmit | 2021-03-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | See attached. | Info Exchange
| 15440 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mortenson has marked this submittal as HOT so if you could please return by end of day today, that would be much appreciated. Below are the items we're looking for input from Populous on before this is returned: 1. Type L33 Finish - White or Black. These are located at the UC concessions in Quads C&D. They are grazing the vertical soffit. 2. Type L35 Finish - Verify Black Finish. These are the suspended linears within the open office area at the mech mezz level area A. 3. Type D3 - Comments and feedback from Todd incorproated into our comments. Uplights within atrium. 4. Type S19 Finish - Verify White Finish. These are utized at the NE and NW egree stair canopies on site. The fixture is inteded to match the existing fixtures used in this canopy. 5. Type B28A Finish - White or Black Finish. These are cylinders used within the open office areas at mech mezz level area A. Thanks, Mark Lievens ME Engineers 2021.03.04 Response (Approved as Noted/Resubmit) from: Kuebler Perry (Populous) Remarks: Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-06 |  | 26 51 13-1.5 CCD Updates and S19 and D3 Resubmits-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-06 |  | 26 51 13-1.5 CCD Updates and S19 and D3 Resubmits-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-02-05 02:00 |  | 26 51 13-1.5 CCD Updates and S19 and D3 Resubmits-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-10 |  | 26 51 13-1.5 CCD_S19 _D3 Resubmits-MAM_ME_POP.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-10 |  | 26 51 13-1.5 CCD_S19 _D3 Resubmits-MAM_ME_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-10 02:00 |  | 26 51 13-1.5 CCD_S19 _D3 Resubmits-MAM_ME_POP.pdf
26 51 13-001-05-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-001-05 LIGHTING FIXTURES - CCD Updates and S19 and D3 Resubmittal | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 51 13-001-05 - 26 51 13-001-05 LIGHTING FIXTURES - CCD Updates and S19 and D3 Resubmittal | -1 | 2021-03-24
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-10 02:00 |  | 26 51 13-1.5 CCD_S19 _D3 Resubmits-MAM_ME_POP.pdf
26 51 13-005-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-005-00: LIGHTING FIXTURES - Alternate Fixtures | Closed | Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-09 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Kuebler Perry (Populous) |  |  |  | 2019-12-23 | 2020-01-16 | 39 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-01-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03573 | Received | For Review | 2019-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-12-23 | Submittal Number: 26 51 13-5.0 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: LIGHTING FIXTURES - ALTERNATE FIXTURES Description: INCLUDED IN SUBMITTAL 26 51 13-1.0 Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 05051 | Forwarded | For Review | 2019-12-10 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2019-12-17 | Submittal Number: 26 51 13-5.0 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: LIGHTING FIXTURES - ALTERNATE FIXTURES Description: INCLUDED IN SUBMITTAL 26 51 13-1.0 Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 05171 | Forwarded | For Review | 2019-12-16 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2019-12-23 | Submittal Number: 26 51 13-5.0 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: LIGHTING FIXTURES - ALTERNATE FIXTURES Description: INCLUDED IN SUBMITTAL 26 51 13-1.0 Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 03777 | Review Response | Approved as Noted/Resubmit | 2020-01-02 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Please note that the finish on fixture types B24 and B29 shall be confirmed prior to being returned. Fixture type B24 is a step light used in the upper concourse vomitories. B29 is a step light used in the event level vomitories. Let me know if you have any questions. Thanks, Mark Lievens ME Engineers 2020.01.02 | Info Exchange
| 05315 | Forwarded | For Review | 2020-01-03 | Josh Dobken (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous) | 2019-12-23 | Submittal Number: 26 51 13-5.0 From: PATRICK KLEIN Final Due Date: 12/23/19 Subject: LIGHTING FIXTURES - ALTERNATE FIXTURES Description: INCLUDED IN SUBMITTAL 26 51 13-1.0 Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 05516 | Responded and Closed | Approved as Noted/Resubmit | 2020-01-16 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Please note that the finish on fixture types B24 and B29 shall be confirmed prior to being returned. Fixture type B24 is a step light used in the upper concourse vomitories. B29 is a step light used in the event level vomitories. Let me know if you have any questions. Thanks, Mark Lievens ME Engineers 2020.01.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-09 02:00 |  | 26 51 13-5.0 Alternate Fixtures-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 26 51 13-5.0 Alternate Fixtures-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 26 51 13-5.0 Alternate Fixtures-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2019-12-09 02:00 |  | 26 51 13-5.0 Alternate Fixtures-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-09 02:00 |  | 26 51 13-5.0 Alternate Fixtures-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-01-16 |  | 26 51 13-5.0 Alternate Fixtures-MAM-ME_POP.pdf
26 51 13-005-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-005-01 LIGHTING FIXTURES - Alternate Fixtures (L7, B20, B20A, and B24) | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-10 | Responded and Closed - Rejected |  | Mark Lievens (ME Engineers), Allison Wood (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-24 | 2020-08-14 | 66 |  | Record Copies; Transfers; Submittals |  | 44 |  | 2020-08-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06324 | Received | For Review | 2020-06-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-24 | Submittal Number: 26 51 13-5.1 From: PATRICK KLEIN Final Due Date: 06/24/20 Subject: LIGHTING FIXTURES - ALTERNATE FIXTURES (L7, B20, B20A, AND B24) Description: INCLUDED IN SUBMITTAL 26 51 13-1.0 Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 08529 | Forwarded | For Review | 2020-06-10 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Allison Wood (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-17 | · Submittal Number: 26 51 13-5.1 From: PATRICK KLEIN Final Due Date: 06/24/20 Subject: LIGHTING FIXTURES - ALTERNATE FIXTURES (L7, B20, B20A, AND B24) Description: INCLUDED IN SUBMITTAL 26 51 13-1.0 Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 07556 | Review Response | Approved as Noted/Resubmit | 2020-07-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2020.07.23 | Info Exchange
| 10055 | Responded and Closed | Rejected | 2020-08-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Submittal Rejected by Populous. Fixtures submitted will not be used on project. Rejection overrides ME dispositions. Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2020.07.23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-10 |  | 26 51 13-5.1 Alternate Fixtures-MAM.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-10 |  | TL35K-24V CH 014 FR-1FT.ies
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-10 |  | 26 51 13-5.1 Alternate Fixtures-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-10 |  | TL35K-24V CH 014 FR-1FT.ies
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-06-09 02:00 |  | 26 51 13-5.1 Alternate Fixtures-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-06-09 02:00 |  | TL35K-24V CH 014 FR-1FT.ies
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-14 02:00 |  | Submittal Review Form-Lighting - Alternate Fixtures_pop.pdf
26 51 13-007-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-007-00 LIGHTING FIXTURES - Alignment with Deferred Spaces | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-30 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-19 | 2020-08-13 | 15 |  | Record Copies; Transfers; Submittals | 26 51 13-007-00-01 - 26 51 13-007-00 LIGHTING FIXTURES - Alignment with Deferred Spaces | 15 |  | 2020-08-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07259 | Received | For Review | 2020-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-19 | Submittal Number: 26 51 13-7.0 From: PATRICK KLEIN Final Due Date: 08/18/20 Subject: LIGHTING FIXTURES - ALIGNMENT WITH DEFERRED SPACES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 09671 | Forwarded | For Review | 2020-07-30 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-06 | Submittal Number: 26 51 13-7.0 From: PATRICK KLEIN Final Due Date: 08/18/20 Subject: LIGHTING FIXTURES - ALIGNMENT WITH DEFERRED SPACES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 07555 | Review Response | Approved as Noted/Resubmit | 2020-08-08 | David Riffel (ME Engineers) | Populous SCA_CCA |  | See attached for ME review comments. | Info Exchange
| 07540 | Review Response | Revise and Resubmit | 2020-08-13 | Kuebler Perry (Populous) | Populous SCA_CCA |  | See attached review, refer to engineers comments. | Info Exchange
| 10040 | Responded and Closed | Revise and Resubmit | 2020-08-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached review, refer to engineers comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-29 |  | 26 51 13-7.0 Alignment with Deferred Spaces-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-29 |  | 26 51 13-7.0 Alignment with Deferred Spaces-MAM.pdf
| Review Response |  | David Riffel (ME Engineers) | 1 | 2020-07-28 02:00 |  | 26 51 13-7.0 Alignment with Deferred Spaces-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-08-13 |  | 26 51 13-7.0 Alignment with Deferred Spaces-MAM-ME-POP_ REVIEW.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-29 |  | 26 51 13-7.0 Alignment with Deferred Spaces-MAM.pdf
26 51 13-007-00-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-007-00 LIGHTING FIXTURES - Alignment with Deferred Spaces | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 51 13-007-00 - 26 51 13-007-00 LIGHTING FIXTURES - Alignment with Deferred Spaces | -1 | 2020-08-27
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-29 |  | 26 51 13-7.0 Alignment with Deferred Spaces-MAM.pdf
26 51 13-008-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-008-00 Light Fixtures (Concrete Embedded) | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-31 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-08-14 | 2020-08-06 | 7 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07304 | Received | For Review | 2020-07-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-14 | Submittal Number: 26 51 13-8.0 From: PATRICK KLEIN Final Due Date: 08/14/20 Subject: LIGHT FIXTURES (CONCRETE EMBEDDED) Description: PLEASE NOTE THAT THESE SUBMITTALS WILL NEED TO BE EXPEDITED. THESE ARE CONCRETE EMBEDDED LIGHT FIXTURES AND REQUIRE APPROVAL AS SOON AS POSSIBLE IN ORDER TO RELEASE THE CAST-IN PLACE BOXES. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 09743 | Forwarded | For Review | 2020-08-03 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-10 | Submittal Number: 26 51 13-8.0 From: PATRICK KLEIN Final Due Date: 08/14/20 Subject: LIGHT FIXTURES (CONCRETE EMBEDDED) Description: PLEASE NOTE THAT THESE SUBMITTALS WILL NEED TO BE EXPEDITED. THESE ARE CONCRETE EMBEDDED LIGHT FIXTURES AND REQUIRE APPROVAL AS SOON AS POSSIBLE IN ORDER TO RELEASE THE CAST-IN PLACE BOXES. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 07448 | Review Response | Approved as Noted | 2020-08-05 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Populous - Please provide input on the finish of the LP11, LP11A, LP11B, and LP14 fixtures included within. Thank you, Mark Lievens ME Engineers 2020.08.05 | Info Exchange
| 09916 | Responded and Closed | Approved as Noted | 2020-08-06 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.08.05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-31 |  | 26 51 13-8.0 Deferred Space Concrete Embedded Fixtures-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-31 |  | 26 51 13-8.0 Deferred Space Concrete Embedded Fixtures-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-31 |  | 26 51 13-8.0 Deferred Space Concrete Embedded Fixtures-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-31 |  | 26 51 13-8.0 Deferred Space Concrete Embedded Fixtures-MAM.pdf
26 51 13-009-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-009-00 CPA Valley Deferred Mock Up Needs | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-21 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Kuebler Perry (Populous), David Riffel (ME Engineers) |  |  |  | 2020-09-04 | 2020-09-03 | 14 |  | Record Copies; Transfers; Submittals | 26 51 13-009-00-01 - 26 51 13-009-00 CPA Valley Deferred Mock Up Needs | 15 |  | 2020-09-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07644 | Received | For Review | 2020-08-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-09-04 | Submittal Number: 26 51 13-9.0 From: BINH DUONG Final Due Date: 09/03/20 Subject: CPA VALLEY DEFERRED MOCK UP NEEDS Description: PLEASE NOTE THE SUBMITTAL NEEDS TO BE EXPEDITED. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10185 | Forwarded | For Review | 2020-08-20 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-27 | Submittal Number: 26 51 13-9.0 From: BINH DUONG Final Due Date: 09/03/20 Subject: CPA VALLEY DEFERRED MOCK UP NEEDS Description: PLEASE NOTE THE SUBMITTAL NEEDS TO BE EXPEDITED. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10186 | Forwarded | For Review | 2020-08-20 | Shaina Burris (Populous) | Kuebler Perry (Populous); David Riffel (ME Engineers) | 2020-08-27 | Submittal Number: 26 51 13-9.0 From: BINH DUONG Final Due Date: 09/03/20 Subject: CPA VALLEY DEFERRED MOCK UP NEEDS Description: PLEASE NOTE THE SUBMITTAL NEEDS TO BE EXPEDITED. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 07937 | Review Response | Approved as Noted/Resubmit | 2020-08-27 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) |  | See the attached lighting fixture submittal review. Populous - please review the finishes as requested within the submittal review form. This submittal shall also be forwarded to Rockwell for review of the AC and LT fixture types included within. Please let us know if there are any questions. Thank you, Mark Lievens ME Engineers 2020.08.27 | Info Exchange
| 07938 | Review Response | Approved as Noted/Resubmit | 2020-08-31 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) |  | Please see the attached updated submittal review dated 2020.08.31. Apologies for the confusion but after further review of this submittal alongside the other light fixture submittals we have currently, we have adjusted and added review comments accordingly. Please let us know if you have any questions regarding this submittal or if a call is needed to discuss the light fixture finishes. Thank you, Mark Lievens ME Engineers 2020.08.31 | Info Exchange
| 07915 | Review Response | Approved as Noted/Resubmit | 2020-09-03 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | See attached submittal review. | Info Exchange
| 10532 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-03 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 26 51 13-9.0 Mockup Spaces Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-20 |  | 26 51 13-9.0 Mockup Spaces Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-20 |  | 26 51 13-9.0 Mockup Spaces Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-19 02:00 |  | 26 51 13-9.0 Mockup Spaces Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-19 02:00 |  | 26 51 13-9.0 Mockup Spaces Product Data-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-03 |  | 26 51 13-9.0 Mockup Spaces Product Data-MAM-ME - 2020.08.31_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-20 |  | 26 51 13-9.0 Mockup Spaces Product Data-MAM.pdf
26 51 13-009-00-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-009-00 CPA Valley Deferred Mock Up Needs | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 51 13-009-00 - 26 51 13-009-00 CPA Valley Deferred Mock Up Needs | -1 | 2020-09-17
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 26 51 13-9.0 Mockup Spaces Product Data-MAM.pdf
26 51 13-010-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-010-00 CPA Valley Custom Light Fixtures | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-21 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-04 | 2020-09-11 | 22 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-09-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07645 | Received | For Review | 2020-08-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-04 | Submittal Number: 26 51 13-10.0 From: BINH DUONG Final Due Date: 09/03/20 Subject: CPA VALLEY CUSTOM LIGHT FIXTURES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10187 | Forwarded | For Review | 2020-08-20 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-27 | Submittal Number: 26 51 13-10.0 From: BINH DUONG Final Due Date: 09/03/20 Subject: CPA VALLEY CUSTOM LIGHT FIXTURES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 08063 | Review Response | Approved as Noted/Resubmit | 2020-08-28 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.08.28 | Info Exchange
| 10726 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-11 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.08.28 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 26 51 13-10.0 Custom Fixture Package-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-20 |  | 26 51 13-10.0 Custom Fixture Package-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-19 02:00 |  | 26 51 13-10.0 Custom Fixture Package-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-09-11 02:00 |  | 26 51 13-10.0 Custom Fixture Package-MAM-ME_POP.pdf
26 51 13-010-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-010-01 LIGHTING FIXTURES - LT22 and LT23 Shop Drawings-MAM | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-19 | 2020-10-15 | 11 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-10-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08566 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 26 51 13-10.1 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: LIGHTING FIXTURES - LT22 AND LT23 SHOP DRAWINGS-MAM Description: PLEASE NOTE THAT THESE SUBMITTALS WILL NEED TO BE EXPEDITED. FIXTURES LT22 AND LT23 ARE IN THIS PACKAGE. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11327 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-12 | Submittal Number: 26 51 13-10.1 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: LIGHTING FIXTURES - LT22 AND LT23 SHOP DRAWINGS-MAM Description: PLEASE NOTE THAT THESE SUBMITTALS WILL NEED TO BE EXPEDITED. FIXTURES LT22 AND LT23 ARE IN THIS PACKAGE. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 08801 | Review Response | Approved as Noted/Resubmit | 2020-10-08 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.08 | Info Exchange
| 11634 | Responded and Closed | Approved as Noted/Resubmit | 2020-10-15 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.08 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 26 51 13-10.1 LT22 and LT23 Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 26 51 13-10.1 LT22 and LT23 Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-05 |  | 26 51 13-10.1 LT22 and LT23 Shop Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-15 |  | 26 51 13-10.1 LT22 and LT23 Shop Drawings-MAM-RG_ME_POP.pdf
26 51 13-010-02 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-010-02 LIGHTING FIXTURES - LT23 Shop Drawings-MAM | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-27 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-10 | 2020-10-28 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-10-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09020 | Received | For Review | 2020-10-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-10 | Submittal Number: 26 51 13-10.2 From: PATRICK KLEIN Final Due Date: 11/09/20 Subject: LIGHTING FIXTURES - LT23 SHOP DRAWINGS-MAM Description: PLEASE NOTE THAT THESE SUBMITTALS WILL NEED TO BE EXPEDITED. LT23 ADDITIONAL INFORMATION (COD DRIVER INFO). IF POSSIBLE, PLEASE HAVE THIS TURN AROUND BY 10/27 TO HAVE THIS FIXTURE AVAILABLE IN MOCK UPS. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11901 | Forwarded | For Review | 2020-10-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-03 | Submittal Number: 26 51 13-10.2 From: PATRICK KLEIN Final Due Date: 11/09/20 Subject: LIGHTING FIXTURES - LT23 SHOP DRAWINGS-MAM Description: PLEASE NOTE THAT THESE SUBMITTALS WILL NEED TO BE EXPEDITED. LT23 ADDITIONAL INFORMATION (COD DRIVER INFO). IF POSSIBLE, PLEASE HAVE THIS TURN AROUND BY 10/27 TO HAVE THIS FIXTURE AVAILABLE IN MOCK UPS. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 09074 | Review Response | Approved as Noted | 2020-10-27 | David Riffel (ME Engineers) | Populous SCA_CCA |  | See attached for ME Review Comments. | Info Exchange
| 11980 | Responded and Closed | Approved as Noted | 2020-10-28 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 26 51 13-10.2 LT 23 Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 26 51 13-10.2 LT 23 Shop Drawings-MAM.pdf
| Review Response |  | David Riffel (ME Engineers) | 1 | 2020-10-27 |  | 26 51 13-10.2 LT 23 Shop Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-28 |  | 26 51 13-10.2 LT 23 Shop Drawings-RG REVIEW-ME_POP.pdf
26 51 13-011-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-011-00 Standard Decorative Fixtures | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-25 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-09 07:00 | 2020-09-11 | 18 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-09-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07722 | Received | For Review | 2020-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-09-09 07:00 | Submittal Number: 26 51 13-11.0 From: BINH DUONG Final Due Date: 09/08/20 Subject: STANDARD DECORATIVE FIXTURES Description: PLEASE NOTE THE SUBMITTAL NEEDS TO BE EXPEDITED. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10276 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-31 | Submittal Number: 26 51 13-11.0 From: BINH DUONG Final Due Date: 09/08/20 Subject: STANDARD DECORATIVE FIXTURES Description: PLEASE NOTE THE SUBMITTAL NEEDS TO BE EXPEDITED. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 08064 | Review Response | Approved as Noted/Resubmit | 2020-09-02 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) |  | See the attached submittal review. Please note that these fixtures will require Rockwell's review and final approval of submitted fixtures and finishes. Any approval indicated within our review of the electrical/dimming information is pending Rockwell's approval of the fixture itself. Thank you, Mark Lievens ME Engineers 2020.09.02 | Info Exchange
| 10727 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: See the attached submittal review. Please note that these fixtures will require Rockwell's review and final approval of submitted fixtures and finishes. Any approval indicated within our review of the electrical/dimming information is pending Rockwell's approval of the fixture itself. Thank you, Mark Lievens ME Engineers 2020.09.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 26 51 13-11.0 Standard Decorative Fixture Package-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 26 51 13-11.0 Standard Decorative Fixture Package-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-23 02:00 |  | 26 51 13-11.0 Standard Decorative Fixture Package-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-11 02:00 |  | 26 51 13-11.0 Standard Decorative Fixture Package-MAM-ME_POP.pdf
26 51 13-011-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-011-01 Standard Decorative Fixtures | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-27 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-10 | 2020-11-11 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09019 | Received | For Review | 2020-10-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-10 | Submittal Number: 26 51 13-11.1 From: PATRICK KLEIN Final Due Date: 11/09/20 Subject: STANDARD DECORATIVE FIXTURES Description: SUBMITTAL HELD OPEN FOR LT-04 RESUBMISSION Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11900 | Forwarded | For Review | 2020-10-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-03 | Submittal Number: 26 51 13-11.1 From: PATRICK KLEIN Final Due Date: 11/09/20 Subject: STANDARD DECORATIVE FIXTURES Description: SUBMITTAL HELD OPEN FOR LT-04 RESUBMISSION Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 09380 | Review Response | Approved as Noted/Resubmit | 2020-11-11 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Rockwell shall provide final review and approval of these light fixtures. Thank you, Mark Lievens ME Engineers 2020.11.10 | Info Exchange
| 12380 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | NOT REVIEWED BY POPULOUS. ROCKWELL TO CONFIRM COMMENTS BY ENGINEER. Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Rockwell shall provide final review and approval of these light fixtures. Thank you, Mark Lievens ME Engineers 2020.11.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 26 51 13-11.1 Standard Decorative Fixture Package-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 26 51 13-11.1 Standard Decorative Fixture Package-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-26 02:00 |  | 26 51 13-11.1 Standard Decorative Fixture Package-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-11 02:00 |  | 26 51 13-11.1 Standard Decorative Fixture Package-MAM-ME_pop.pdf
26 51 13-011-02 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-011-02 Standard Decorative Fixtures | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-12 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-26 | 2021-03-08 | 25 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11369 | Received | For Review | 2021-02-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-02-26 | Submittal Number: 26 51 13-11.2 From: PATRICK KLEIN Final Due Date: 02/03/21 Subject: STANDARD DECORATIVE FIXTURES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 14726 | Forwarded | For Review | 2021-02-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-18 | Submittal Number: 26 51 13-11.2 From: PATRICK KLEIN Final Due Date: 02/03/21 Subject: STANDARD DECORATIVE FIXTURES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11850 | Review Response | Approved as Noted | 2021-03-03 | Heidi Evans (ME Engineers) | Shaina Burris (Populous) |  |  | Info Exchange
| 15358 | Responded and Closed | Approved as Noted | 2021-03-08 | Bryan Klote (Populous) | Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-11 |  | 26 51 13-11.2 Standard Decorative Fixture Package - RG REVIEW.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-11 |  | 26 51 13-11.2 Standard Decorative Fixture Package - RG REVIEW.pdf
| Review Response |  | Heidi Evans (ME Engineers) | 1 | 2021-02-11 |  | 26 51 13-11.2 Standard Decorative Fixture Package - RG REVIEW.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-03-08 |  | 26 51 13-11.2 Standard Decorative- RG_ME_POP.pdf
26 51 13-012-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-012-00 Illume Deferred Space Fixture Package | Closed | Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-27 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2020-09-17 | 2020-09-24 | 29 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2020-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07779 | Received | For Review | 2020-08-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-09-17 | Submittal Number: 26 51 13-12.0 From: BINH DUONG Final Due Date: 09/16/20 Subject: ILLUME DEFERRED SPACE FIXTURE PACKAGE Description: PLEASE NOTE THAT THESE SUBMITTALS WILL NEED TO BE EXPEDITED. THIS IS A FULL SUBMITTAL EXCLUDING THE CUSTOM AND STANDARD DECORATIVE LIGHTS. THERE ARE INCLUSION OF SOME FIXTURES THAT WAS SENT IN FOR THE MOCK UP SUBMITTAL. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10359 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-03 | Submittal Number: 26 51 13-12.0 From: BINH DUONG Final Due Date: 09/16/20 Subject: ILLUME DEFERRED SPACE FIXTURE PACKAGE Description: PLEASE NOTE THAT THESE SUBMITTALS WILL NEED TO BE EXPEDITED. THIS IS A FULL SUBMITTAL EXCLUDING THE CUSTOM AND STANDARD DECORATIVE LIGHTS. THERE ARE INCLUSION OF SOME FIXTURES THAT WAS SENT IN FOR THE MOCK UP SUBMITTAL. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 08157 | Review Response | Approved as Noted/Resubmit | 2020-09-15 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) |  | Please see the attached submittal review. Populous - please provide selections on the finishes as noted within the submittal review form. Please also review the lighting drawings for each premium club/space to confirm finishes (XX-BL, XX-WH, XX-SL) are accurate. If any changes need to be made or clarifications on finishes for a light fixture depending on which club it is, please includes these drawing markups with the review similar to what was done for the suites. ME/Illume can be available for any discussions needed to help confirm light fixture finishes. Thank you, Mark Lievens ME Engineers 2020.09.15 | Info Exchange
| 10829 | Forwarded | For Review | 2020-09-16 | Josh Dobken (Populous) | Bryan Klote (Populous); Kuebler Perry (Populous); Chad Francis (Populous) | 2020-09-17 | Submittal Number: 26 51 13-12.0 From: BINH DUONG Final Due Date: 09/16/20 Subject: ILLUME DEFERRED SPACE FIXTURE PACKAGE Description: PLEASE NOTE THAT THESE SUBMITTALS WILL NEED TO BE EXPEDITED. THIS IS A FULL SUBMITTAL EXCLUDING THE CUSTOM AND STANDARD DECORATIVE LIGHTS. THERE ARE INCLUSION OF SOME FIXTURES THAT WAS SENT IN FOR THE MOCK UP SUBMITTAL. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 08334 | Review Response | Approved as Noted/Resubmit | 2020-09-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to comments on sheets for R/R criteria. | Info Exchange
| 11041 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to comments on sheets for R/R criteria. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-26 |  | 26 51 13-12.0 Illume Deferred Space Fixture Package-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-26 |  | 26 51 13-12.0 Illume Deferred Space Fixture Package-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-25 02:00 |  | 26 51 13-12.0 Illume Deferred Space Fixture Package-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-08-25 02:00 |  | 26 51 13-12.0 Illume Deferred Space Fixture Package-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-09-24 |  | 26 51 13-12.0 Illume Deferred Space Fixture Package-MAM - ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-08-26 |  | 26 51 13-12.0 Illume Deferred Space Fixture Package-MAM.pdf
26 51 13-012-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-012-01 Illume Deferred Space Fixture Package | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-02 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-20 | 2020-12-03 | 32 |  | Record Copies; Transfers; Submittals |  | 32 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09159 | Received | For Review | 2020-11-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-20 | Submittal Number: 26 51 13-12.1 From: PATRICK KLEIN Final Due Date: 11/20/20 Subject: ILLUME DEFERRED SPACE FIXTURE PACKAGE Description: PLEASE NOTE THAT THESE SUBMITTALS WILL NEED TO BE EXPEDITED. THIS IS A FULL SUBMITTAL EXCLUDING THE CUSTOM AND STANDARD DECORATIVE LIGHTS. THERE ARE INCLUSION OF SOME FIXTURES THAT WAS SENT IN FOR THE MOCK UP SUBMITTAL. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12081 | Forwarded | For Review | 2020-11-02 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-09 | Submittal Number: 26 51 13-12.1 From: PATRICK KLEIN Final Due Date: 11/20/20 Subject: ILLUME DEFERRED SPACE FIXTURE PACKAGE Description: PLEASE NOTE THAT THESE SUBMITTALS WILL NEED TO BE EXPEDITED. THIS IS A FULL SUBMITTAL EXCLUDING THE CUSTOM AND STANDARD DECORATIVE LIGHTS. THERE ARE INCLUSION OF SOME FIXTURES THAT WAS SENT IN FOR THE MOCK UP SUBMITTAL. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 09948 | Review Response | Approved as Noted/Resubmit | 2020-11-30 | David Riffel (ME Engineers) | Shaina Burris (Populous) |  | See attached for ME review comments. | Info Exchange
| 09876 | Review Response | Approved as Noted | 2020-12-03 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review and engineer's comments. | Info Exchange
| 12959 | Responded and Closed | Approved as Noted | 2020-12-03 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review and engineer's comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-02 |  | 26 51 13-12.1 Illume Deferred Space Fixture Package-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-02 |  | 26 51 13-12.1 Illume Deferred Space Fixture Package-MAM.pdf
| Review Response |  | David Riffel (ME Engineers) | 1 | 2020-11-01 01:00 |  | 26 51 13-12.1 Illume Deferred Space Fixture Package-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-03 |  | 26 51 13-12.1 Illume Deferred Space Fixture Package-MAM_ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-02 |  | 26 51 13-12.1 Illume Deferred Space Fixture Package-MAM.pdf
26 51 13-012-02 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-012-02 Illume Deferred Space Fixture Package | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-21 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-04 | 2021-02-03 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-02-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10873 | Received | For Review | 2021-01-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-02-04 | Submittal Number: 26 51 13-12.2 From: PATRICK KLEIN Final Due Date: 02/03/21 Subject: ILLUME DEFERRED SPACE FIXTURE PACKAGE Description: SEE ATTACHED AND RESUBMIT LP8A AND LP8-T2. SUBMIT SHOP DRAWINGS FOR THE FOLLOWING: DP1 (INCLUDE OPERABLE SAMPLE TO BE SENT TO SUITE 100 201 QUEEN ANNE AVE N. SEATTLE, WA 98109 ATTN. PATRICK KLEIN) LP5 LP5A LP6 (INCLUDING POWER SUPPLY) LP6C (INCLUDING POWER SUPPLY) LP6E LP7 LP12 LP16 Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 14115 | Forwarded | For Review | 2021-01-21 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-28 | Submittal Number: 26 51 13-12.2 From: PATRICK KLEIN Final Due Date: 02/03/21 Subject: ILLUME DEFERRED SPACE FIXTURE PACKAGE Description: SEE ATTACHED AND RESUBMIT LP8A AND LP8-T2. SUBMIT SHOP DRAWINGS FOR THE FOLLOWING: DP1 (INCLUDE OPERABLE SAMPLE TO BE SENT TO SUITE 100 201 QUEEN ANNE AVE N. SEATTLE, WA 98109 ATTN. PATRICK KLEIN) LP5 LP5A LP6 (INCLUDING POWER SUPPLY) LP6C (INCLUDING POWER SUPPLY) LP6E LP7 LP12 LP16 Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11883 | Review Response | Approved as Noted | 2021-02-01 | David Riffel (ME Engineers) | Shaina Burris (Populous) |  | See attached for ME Review comments. | Info Exchange
| 11165 | Review Response | Approved as Noted | 2021-02-03 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14472 | Responded and Closed | Approved as Noted | 2021-02-03 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-21 |  | 26 51 13-12.2 Illume Deferred Space Fixture Package-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-21 |  | 26 51 13-12.2 Illume Deferred Space Fixture Package-MAM.pdf
| Review Response |  | David Riffel (ME Engineers) | 1 | 2021-01-20 02:00 |  | 26 51 13-12.2 Illume Deferred Space Fixture Package-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-02-03 |  | 26 51 13-12.2 Illume Deferred Space Fixture Package-MAM_ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-21 |  | 26 51 13-12.2 Illume Deferred Space Fixture Package-MAM.pdf
26 51 13-012-03 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-012-03 LP16 Shop Drawings | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-17 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-03-31 | 2021-04-14 | 29 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2021-04-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12084 | Received | For Review | 2021-03-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-03-31 | Submittal Number: 26 51 13-12.3 From: PATRICK KLEIN Final Due Date: 03/31/21 Subject: LP16 SHOP DRAWINGS Description: LP16 SHOP DRAWINGS Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 15641 | Forwarded | For Review | 2021-03-17 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-24 | Submittal Number: 26 51 13-12.3 From: PATRICK KLEIN Final Due Date: 03/31/21 Subject: LP16 SHOP DRAWINGS Description: LP16 SHOP DRAWINGS Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12581 | Review Response | Approved as Noted/Resubmit | 2021-03-31 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Populous please confirm that matte white finish shall be provided for this fixture type LP16. It is used in the suite corridor and elevator lobbies in quads A and B of the suite level. Thank you, Mark Lievens ME Engineers 2021.03.31 | Info Exchange
| 12575 | Review Response | Approved as Noted/Resubmit | 2021-04-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16294 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-14 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-17 |  | 26 51 13-12.3 LP16 Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-17 |  | 26 51 13-12.3 LP16 Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-03-16 02:00 |  | 26 51 13-12.3 LP16 Shop Drawings-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-14 |  | 26 51 13-12.3 LP16 Shop Drawings-MAM - ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-03-17 |  | 26 51 13-12.3 LP16 Shop Drawings-MAM.pdf
26 51 13-012-04 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-012-04 LP16 Shop Drawings | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-14 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-28 | 2021-07-02 | 19 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13514 | Received | For Review | 2021-06-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction) | 2021-06-28 | Submittal Number: 26 51 13-12.4 From: PATRICK KLEIN Final Due Date: 06/27/21 Subject: LP16 SHOP DRAWINGS Description: LP16 SHOP DRAWINGS Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 17478 | Forwarded | For Review | 2021-06-14 | Patrick Klein (Mortenson Construction) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-21 | Submittal Number: 26 51 13-12.4 From: PATRICK KLEIN Final Due Date: 06/27/21 Subject: LP16 SHOP DRAWINGS Description: LP16 SHOP DRAWINGS Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 13769 | Review Response | Approved as Noted | 2021-06-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.06.23 | Info Exchange
| 17820 | Responded and Closed | Approved as Noted | 2021-07-02 | Patrick Klein (Mortenson Construction) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-14 |  | 26 51 13-12.4 LP16 Shop Drawings-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2021-06-14 |  | 26 51 13-12.4 LP16 Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-06-14 |  | 26 51 13-12.4 LP16 Shop Drawings-MAM.pdf
| Responded and Closed |  | Patrick Klein (Mortenson Construction) | 1 | 2021-07-02 |  | 26 51 13-12.4 LP16 Shop Drawings-MAM-ME_POP.pdf
26 51 13-013-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-013-00 LIGHTING FIXTURES - L25, D1, D2, D6, S1, S1A, S18, and S19 Shops | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-06 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-20 | 2020-10-20 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08594 | Received | For Review | 2020-10-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-10-20 | Submittal Number: 26 51 13-13.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: LIGHTING FIXTURES - L25, D1, D2, D6, S1, S1A, S18, AND S19 SHOPS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11357 | Forwarded | For Review | 2020-10-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-13 | Submittal Number: 26 51 13-13.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: LIGHTING FIXTURES - L25, D1, D2, D6, S1, S1A, S18, AND S19 SHOPS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 08885 | Review Response | Approved as Noted/Resubmit | 2020-10-19 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.19 | Info Exchange
| 08873 | Review Response | Approved as Noted | 2020-10-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 11732 | Responded and Closed | Approved as Noted | 2020-10-20 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 26 51 13-13.0 L25 D1 D2 D6 S1 S18 and S19 Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 26 51 13-13.0 L25 D1 D2 D6 S1 S18 and S19 Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-04 02:00 |  | 26 51 13-13.0 L25 D1 D2 D6 S1 S18 and S19 Shops-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-10-20 |  | 26 51 13-13.0 L25 D1 D2 D6 S1 S18 and S19 Shops-MAM-ME-POP RESPONSE.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-10-05 |  | 26 51 13-13.0 L25 D1 D2 D6 S1 S18 and S19 Shops-MAM.pdf
26 51 13-014-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-014-00 LIGHTING FIXTURES - Custom Package Shop Drawings | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-27 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-10 | 2020-11-11 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09018 | Received | For Review | 2020-10-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-10 | Submittal Number: 26 51 13-14.0 From: PATRICK KLEIN Final Due Date: 11/09/20 Subject: LIGHTING FIXTURES - CUSTOM PACKAGE SHOP DRAWINGS Description: SUBMITTAL HELD OPEN FOR SHOP DRAWINGS Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11899 | Forwarded | For Review | 2020-10-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-03 | Submittal Number: 26 51 13-14.0 From: PATRICK KLEIN Final Due Date: 11/09/20 Subject: LIGHTING FIXTURES - CUSTOM PACKAGE SHOP DRAWINGS Description: SUBMITTAL HELD OPEN FOR SHOP DRAWINGS Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 09382 | Review Response | Approved as Noted/Resubmit | 2020-11-10 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review of light fixtures' LED and electrical properities. Full light fixture shop drawing review and approval shall be provided by Rockwell. Thank you, Mark Lievens ME Engineers 2020.11.10 | Info Exchange
| 12381 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-11 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | NOT REVIEWED BY POPULOUS. ROCKWELL TO CONFIRM COMMENTS BY ENGINEER. Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review of light fixtures' LED and electrical properities. Full light fixture shop drawing review and approval shall be provided by Rockwell. Thank you, Mark Lievens ME Engineers 2020.11.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 26 51 13-14.0 Custom Package Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 26 51 13-14.0 Custom Package Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-26 02:00 |  | 26 51 13-14.0 Custom Package Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-11-11 02:00 |  | 26 51 13-14.0 Custom Package Shop Drawings-MAM-ME_pop.pdf
26 51 13-014-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-014-01 LIGHTING FIXTURES - Custom Decorative Package Shop Drawings | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-12 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-26 | 2021-03-08 | 25 |  | Record Copies; Transfers; Submittals | 26 51 13-014-01-01 - 26 51 13-014-01 LIGHTING FIXTURES - Custom Decorative Package Shop Drawings | 23 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11370 | Received | For Review | 2021-02-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-02-26 | Submittal Number: 26 51 13-14.1 From: PATRICK KLEIN Final Due Date: 02/03/21 Subject: LIGHTING FIXTURES - CUSTOM DECORATIVE PACKAGE SHOP DRAWINGS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 14727 | Forwarded | For Review | 2021-02-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-18 | Submittal Number: 26 51 13-14.1 From: PATRICK KLEIN Final Due Date: 02/03/21 Subject: LIGHTING FIXTURES - CUSTOM DECORATIVE PACKAGE SHOP DRAWINGS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11849 | Review Response | Approved as Noted/Resubmit | 2021-03-05 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.03.05 | Info Exchange
| 15357 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-08 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.03.05 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-11 |  | 26 51 13-14.1 Custom Package Shop Drawings - RG REVIEW.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-11 |  | 26 51 13-14.1 Custom Package Shop Drawings - RG REVIEW.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-02-11 |  | 26 51 13-14.1 Custom Package Shop Drawings - RG REVIEW.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-03-08 |  | 26 51 13-14.1 Custom Package Shop Drawings - RG_ME_POP.pdf
26 51 13-014-01-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-014-01 LIGHTING FIXTURES - Custom Decorative Package Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 51 13-014-01 - 26 51 13-014-01 LIGHTING FIXTURES - Custom Decorative Package Shop Drawings | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-08 |  | 26 51 13-14.1 Custom Package Shop Drawings - RG_ME_POP.pdf
26 51 13-015-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-015-00 LIGHTING FIXTURES - LP5 and LP6 Series Mock Up Shops | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-27 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-10 | 2020-11-11 | 16 |  | Record Copies; Transfers; Submittals | 26 51 13-015-00-01 - 26 51 13-015-00 LIGHTING FIXTURES - LP5 and LP6 Series Mock Up Shops | 15 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09017 | Received | For Review | 2020-10-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-10 | Submittal Number: 26 51 13-15.0 From: PATRICK KLEIN Final Due Date: 11/09/20 Subject: LIGHTING FIXTURES - LP5 AND LP6 SERIES MOCK UP SHOPS Description: PLEASE REVIEW LUMINI MOCK UPS FOR LP6, LP6B, LP6F FIXTURES. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11898 | Forwarded | For Review | 2020-10-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-03 | Submittal Number: 26 51 13-15.0 From: PATRICK KLEIN Final Due Date: 11/09/20 Subject: LIGHTING FIXTURES - LP5 AND LP6 SERIES MOCK UP SHOPS Description: PLEASE REVIEW LUMINI MOCK UPS FOR LP6, LP6B, LP6F FIXTURES. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 09378 | Review Response | Approved as Noted/Resubmit | 2020-11-10 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.10 | Info Exchange
| 12377 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-11 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 26 51 13-15.0 LP5 and LP6 Series Mock Up Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-27 |  | 26 51 13-15.0 LP5 and LP6 Series Mock Up Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-27 |  | 26 51 13-15.0 LP5 and LP6 Series Mock Up Shops-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-11-11 |  | 26 51 13-15.0 LP5 and LP6 Series Mock Up Shops-MAM-ME_POP.pdf
26 51 13-015-00-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-015-00 LIGHTING FIXTURES - LP5 and LP6 Series Mock Up Shops | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 51 13-015-00 - 26 51 13-015-00 LIGHTING FIXTURES - LP5 and LP6 Series Mock Up Shops | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-11 |  | 26 51 13-15.0 LP5 and LP6 Series Mock Up Shops-MAM-ME_POP.pdf
26 51 13-017-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-017-00 LIGHTING FIXTURES - Locker Room and Upper Con Food and Beverage Shop Drawings | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-04 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-11-18 | 2020-12-01 | 28 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-12-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09229 | Received | For Review | 2020-11-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-18 | Submittal Number: 26 51 13-17.0 From: PATRICK KLEIN Final Due Date: 11/18/20 Subject: LIGHTING FIXTURES - LOCKER ROOM AND UPPER CON FOOD AND BEVERAGE SHOP DRAWINGS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12186 | Forwarded | For Review | 2020-11-04 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-11 | Submittal Number: 26 51 13-17.0 From: PATRICK KLEIN Final Due Date: 11/18/20 Subject: LIGHTING FIXTURES - LOCKER ROOM AND UPPER CON FOOD AND BEVERAGE SHOP DRAWINGS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 09787 | Review Response | Approved as Noted/Resubmit | 2020-11-24 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.24 | Info Exchange
| 12868 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-01 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.24 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-04 |  | 26 51 13-17.0 Locker Room and UC Food and Beverage Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-04 |  | 26 51 13-17.0 Locker Room and UC Food and Beverage Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-03 02:00 |  | 26 51 13-17.0 Locker Room and UC Food and Beverage Shops-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-12-01 02:00 |  | 26 51 13-17.0 Locker Room and UC Food and Beverage Shops-MAM_ME REVIEW_pop.pdf
26 51 13-017-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-017-01 LIGHTING FIXTURES - Locker Room and Upper Con Food and Beverage Shop Drawings | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-01-27 08:00 | 2021-01-20 | 9 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10615 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-01-27 08:00 | Submittal Number: 26 51 13-17.1 From: PATRICK KLEIN Final Due Date: 01/25/21 Subject: LIGHTING FIXTURES - LOCKER ROOM AND UPPER CON FOOD AND BEVERAGE SHOP DRAWINGS Description: RESUBMIT L26 AND L33 SHOPS ACCORDINGLY Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 13822 | Forwarded | For Review | 2021-01-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-18 | Submittal Number: 26 51 13-17.1 From: PATRICK KLEIN Final Due Date: 01/25/21 Subject: LIGHTING FIXTURES - LOCKER ROOM AND UPPER CON FOOD AND BEVERAGE SHOP DRAWINGS Description: RESUBMIT L26 AND L33 SHOPS ACCORDINGLY Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10828 | Review Response | Approved as Noted | 2021-01-15 | David Riffel (ME Engineers) | Populous SCA_CCA |  | See attached for our review comments. | Info Exchange
| 14076 | Responded and Closed | Approved as Noted | 2021-01-20 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: David Riffel (ME Engineers) Remarks: See attached for our review comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 26 51 13-17.1 NHL Locker Room L26 Resubmittal-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-11 |  | 26 51 13-17.1 NHL Locker Room L26 Resubmittal-MAM.pdf
| Review Response |  | David Riffel (ME Engineers) | 1 | 2021-01-11 |  | 26 51 13-17.1 NHL Locker Room L26 Resubmittal-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-20 |  | 26 51 13-17.1 NHL Locker Room L26 Resubmittal-MAM_ME REVIEW_POP.pdf
26 51 13-018-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-018-00 LIGHTING FIXTURES - CCD 073 WNBA Locker Room Shops | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-06 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Kelsea Conkright (Populous), Chad Francis (Populous) |  |  |  | 2020-11-20 | 2020-12-03 | 28 |  | Record Copies; Transfers; Submittals |  | 27 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09275 | Received | For Review | 2020-11-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-20 | Submittal Number: 26 51 13-18.0 From: PATRICK KLEIN Final Due Date: 11/20/20 Subject: LIGHTING FIXTURES - CCD 073 WNBA LOCKER ROOM SHOPS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12227 | Forwarded | For Review | 2020-11-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-13 | Submittal Number: 26 51 13-18.0 From: PATRICK KLEIN Final Due Date: 11/20/20 Subject: LIGHTING FIXTURES - CCD 073 WNBA LOCKER ROOM SHOPS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 09850 | Review Response | Approved as Noted/Resubmit | 2020-11-24 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.24 | Info Exchange
| 12869 | Forwarded | For Review | 2020-12-01 | Josh Dobken (Populous) | Kelsea Conkright (Populous); Chad Francis (Populous) | 2020-11-20 | Submittal Number: 26 51 13-18.0 From: PATRICK KLEIN Final Due Date: 11/20/20 Subject: LIGHTING FIXTURES - CCD 073 WNBA LOCKER ROOM SHOPS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 09858 | Review Response | Approved as Noted/Resubmit | 2020-12-02 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 12939 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-03 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.24 Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-06 |  | 26 51 13-18.0 CCD 073 WNBA Locker Room Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-06 |  | 26 51 13-18.0 CCD 073 WNBA Locker Room Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-06 |  | 26 51 13-18.0 CCD 073 WNBA Locker Room Shops-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-11-05 02:00 |  | 26 51 13-18.0 CCD 073 WNBA Locker Room Shops-MAM.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2020-12-03 |  | 26 51 13-18.0 CCD 073 WNBA Locker Room Shops-MAM-ME_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-03 |  | 26 51 13-18.0 CCD 073 WNBA Locker Room Shops-MAM-ME_POP.pdf
26 51 13-018-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-018-01 LIGHTING FIXTURES - CCD 073 WNBA Locker Room Shops | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-08 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-22 | 2021-03-25 | 108 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2021-03-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10009 | Received | For Review | 2020-12-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-12-22 | Submittal Number: 26 51 13-18.1 From: PATRICK KLEIN Final Due Date: 12/22/20 Subject: LIGHTING FIXTURES - CCD 073 WNBA LOCKER ROOM SHOPS Description: RESUBMIT FIXTURE L26B. SHOP DRAWINGS ARE TO BE PROVIDED FOR THE BELOW FIXTURES: D1E D1F L26B L26C L29 L30 L30A Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 13099 | Forwarded | For Review | 2020-12-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-15 | Submittal Number: 26 51 13-18.1 From: PATRICK KLEIN Final Due Date: 12/22/20 Subject: LIGHTING FIXTURES - CCD 073 WNBA LOCKER ROOM SHOPS Description: RESUBMIT FIXTURE L26B. SHOP DRAWINGS ARE TO BE PROVIDED FOR THE BELOW FIXTURES: D1E D1F L26B L26C L29 L30 L30A Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10522 | Review Response | Approved as Noted/Resubmit | 2021-01-05 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.01.05 | Info Exchange
| 13734 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-08 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR COMMENTS REVISE/RESUBMIT ITEMS AS NOTED | Info Exchange
| 15828 | Reopened | Additional Information | 2021-03-25 11:10 | Chad Francis (Populous) |  |  | revised response
| 15829 | Responded and Closed | Approved as Noted | 2021-03-25 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED FOR COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-08 |  | 26 51 13-18.1 WNBA Locker Room Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-08 |  | 26 51 13-18.1 WNBA Locker Room Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-12-08 |  | 26 51 13-18.1 WNBA Locker Room Shop Drawings-MAM.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-01-08 |  | 26 51 13-18.1 WNBA Locker Room Shop Drawings-MAM-ME_POP.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-25 |  | 26 51 13-18.1 WNBA Locker Room Shop Drawings-MAM-ME-POP.pdf
26 51 13-018-02 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-018-02 WNBA- L26B Resubmittal | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-11 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-03-25 | 2021-03-25 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-03-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11950 | Received | For Review | 2021-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-03-25 | Submittal Number: 26 51 13-18.2 From: PATRICK KLEIN Final Due Date: 03/25/21 Subject: WNBA- L26B RESUBMITTAL Description: L26B SUBMITTAL AND SHOP DRAWINGS FOR WNBA LOCKER ROOM. PLEASE ADVISE ON WOOD FINISH. THESE FIXTURES HAVE A 12 WEEK LEAD TIME. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 15473 | Forwarded | For Review | 2021-03-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-18 | Submittal Number: 26 51 13-18.2 From: PATRICK KLEIN Final Due Date: 03/25/21 Status: OPEN Subject: WNBA- L26B RESUBMITTAL Description: L26B SUBMITTAL AND SHOP DRAWINGS FOR WNBA LOCKER ROOM. PLEASE ADVISE ON WOOD FINISH. THESE FIXTURES HAVE A 12 WEEK LEAD TIME. Spec Section: 26 51 13 - LIGHTING FIXTURES | Info Exchange
| 12233 | Review Response | Approved as Noted | 2021-03-24 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) |  | Please see the attached submittal review. Populous - Please select the wood finish shown on page 5 of this PDF. Thank you, Mark Lievens ME Engineers 2021.03.24 | Info Exchange
| 15823 | Responded and Closed | Approved as Noted | 2021-03-25 | Chad Francis (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-11 |  | 26 51 13-18.2 WNBA L26B Resubmittal-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-11 |  | 26 51 13-18.2 WNBA L26B Resubmittal-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-03-11 |  | 26 51 13-18.2 WNBA L26B Resubmittal-MAM.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-03-25 |  | 26 51 13-18.2 WNBA L26B Resubmittal-MAM-ME_POP.pdf
26 51 13-019-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-019-00 LIGHTING FIXTURES - Oyster Bar Chandelier | Closed | Lighting, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Kuebler Perry (Populous) |  |  |  | 2020-12-03 08:00 | 2020-12-10 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-12-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09472 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 26 51 13-19.0 From: PATRICK KLEIN Final Due Date: 12/01/20 Subject: LIGHTING FIXTURES - OYSTER BAR CHANDELIER Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12490 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-24 | Submittal Number: 26 51 13-19.0 From: PATRICK KLEIN Final Due Date: 12/01/20 Subject: LIGHTING FIXTURES - OYSTER BAR CHANDELIER Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10840 | Review Response | Approved as Noted | 2020-11-24 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mortenson shall send fixture to Rockwell for final approval. Thank you, Mark Lievens ME Engineers 2020.11.24 | Info Exchange
| 12781 | Forwarded | For Review | 2020-11-24 | Josh Dobken (Populous) | Kuebler Perry (Populous) | 2020-12-01 | Submittal Number: 26 51 13-19.0 From: PATRICK KLEIN Final Due Date: 12/01/20 Subject: LIGHTING FIXTURES - OYSTER BAR CHANDELIER Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10086 | Review Response | Approved as Noted | 2020-12-10 | Kuebler Perry (Populous) | Josh Dobken (Populous) |  |  | Info Exchange
| 13185 | Responded and Closed | Approved as Noted | 2020-12-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 26 51 13-19.0 Oyster Bar Chandelier-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 26 51 13-19.0 Oyster Bar Chandelier-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-15 02:00 |  | 26 51 13-19.0 Oyster Bar Chandelier-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-11-15 02:00 |  | 26 51 13-19.0 Oyster Bar Chandelier-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2020-12-10 |  | 26 51 13-19.0 Oyster Bar Chandelier-MAM-ME-POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2020-11-16 |  | 26 51 13-19.0 Oyster Bar Chandelier-MAM.pdf
26 51 13-022-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-022-00 LIGHTING FIXTURES - CCD 075 Shop Drawings (L34, L27, L32, B20, L7, S1, S1A, and S14B) | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-08 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-22 | 2021-01-05 | 29 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-01-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10010 | Received | For Review | 2020-12-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-12-22 | Submittal Number: 26 51 13-22.0 From: PATRICK KLEIN Final Due Date: 12/22/20 Subject: LIGHTING FIXTURES - CCD 075 SHOP DRAWINGS (L34, L27, L32, B20, L7, S1, S1A, AND S14B) Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 13101 | Forwarded | For Review | 2020-12-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-15 | Submittal Number: 26 51 13-22.0 From: PATRICK KLEIN Final Due Date: 12/22/20 Subject: LIGHTING FIXTURES - CCD 075 SHOP DRAWINGS (L34, L27, L32, B20, L7, S1, S1A, AND S14B) Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10450 | Review Response | Approved as Noted | 2020-12-22 | David Riffel (ME Engineers) | Shaina Burris (Populous) |  |  | Info Exchange
| 13645 | Responded and Closed | Approved as Noted | 2021-01-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to comments in submittal Response (Approved as Noted) from: David Riffel (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-08 |  | 26 51 13-22.0 CCD 075 Shop Drawings (L34 L27 L32 B20 L7 S1 S1A and S14B)-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-08 |  | 26 51 13-22.0 CCD 075 Shop Drawings (L34 L27 L32 B20 L7 S1 S1A and S14B)-MAM.pdf
| Review Response |  | David Riffel (ME Engineers) | 1 | 2020-12-07 02:00 |  | 26 51 13-22.0 CCD 075 Shop Drawings (L34 L27 L32 B20 L7 S1 S1A and S14B)-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-05 02:00 |  | 26 51 13-22.0 CCD 075 Shop Drawings (L34 L27 L32 B20 L7 S1 S1A and S14B)-MAM_ME Review_POP.pdf
26 51 13-023-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-023-00 LIGHTING FIXTURES - LP5, LP5A and LP10 Shop Drawings | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-15 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-01 08:00 | 2021-01-26 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-01-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10728 | Received | For Review | 2021-01-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-02-01 08:00 | Submittal Number: 26 51 13-23.0 From: PATRICK KLEIN Final Due Date: 01/29/21 Subject: LIGHTING FIXTURES - LP5, LP5A AND LP10 SHOP DRAWINGS Description: SHOP DRAWINGS PROVIDED FOR THE FOLLOWING LIGHT FIXTURES: LP5, LP10, LP10A, LP5A-WH, LP5A & LP5-WH Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 13957 | Forwarded | For Review | 2021-01-15 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-01-22 | Submittal Number: 26 51 13-23.0 From: PATRICK KLEIN Final Due Date: 01/29/21 Subject: LIGHTING FIXTURES - LP5, LP5A AND LP10 SHOP DRAWINGS Description: SHOP DRAWINGS PROVIDED FOR THE FOLLOWING LIGHT FIXTURES: LP5, LP10, LP10A, LP5A-WH, LP5A & LP5-WH Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11882 | Review Response | Approved as Noted | 2021-01-22 | David Riffel (ME Engineers) | Shaina Burris (Populous) |  | See attached for ME Review comments. | Info Exchange
| 10969 | Review Response | Approved as Noted | 2021-01-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14247 | Responded and Closed | Approved as Noted | 2021-01-26 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | 26 51 13-23.0 LP5 LP5A and LP10 Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | 26 51 13-23.0 LP5 LP5A and LP10 Shop Drawings-MAM.pdf
| Review Response |  | David Riffel (ME Engineers) | 1 | 2021-01-13 02:00 |  | 26 51 13-23.0 LP5 LP5A and LP10 Shop Drawings-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-01-26 |  | 26 51 13-23.0 LP5 LP5A and LP10 Shop Drawings-MAM-ME _POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-01-14 |  | 26 51 13-23.0 LP5 LP5A and LP10 Shop Drawings-MAM.pdf
26 51 13-024-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-024-00 LIGHTING FIXTURES - DP1, DP3, and S19 Samples | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-14 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Kuebler Perry (Populous) |  |  |  | 2021-01-06 | 2021-01-05 | 23 |  | Record Copies; Transfers; Submittals | 26 51 13-024-00-01 - 26 51 13-024-00 LIGHTING FIXTURES - DP1, DP3, and S19 Samples | 8 |  | 2021-01-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10123 | Received | For Review | 2020-12-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2021-01-06 | Submittal Number: 26 51 13-24.0 From: PATRICK KLEIN Final Due Date: 12/29/20 Subject: LIGHTING FIXTURES - DP1, DP3, AND S19 SAMPLES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 13232 | Forwarded | For Review | 2020-12-14 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-21 | Submittal Number: 26 51 13-24.0 From: PATRICK KLEIN Final Due Date: 12/29/20 Subject: LIGHTING FIXTURES - DP1, DP3, AND S19 SAMPLES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10467 | Review Response | Approved as Noted/Resubmit | 2020-12-21 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.12.21 | Info Exchange
| 13557 | Forwarded | For Review | 2021-01-04 | Josh Dobken (Populous) | Kuebler Perry (Populous) |  | Submittal Number: 26 51 13-24.0 From: PATRICK KLEIN Final Due Date: 12/29/20 Subject: LIGHTING FIXTURES - DP1, DP3, AND S19 SAMPLES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Email
| 13666 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.12.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-12 |  | 26 51 13-24.0 DP1 DP3 and S19 Samples-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-12 |  | 26 51 13-24.0 DP1 DP3 and S19 Samples-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-12-11 02:00 |  | 26 51 13-24.0 DP1 DP3 and S19 Samples-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-12-11 02:00 |  | 26 51 13-24.0 DP1 DP3 and S19 Samples-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-05 02:00 |  | 26 51 13-24.0 DP1 DP3 and S19 Samples-MAM_ME REVIEW_pop.pdf
26 51 13-024-00-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-024-00 LIGHTING FIXTURES - DP1, DP3, and S19 Samples | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 51 13-024-00 - 26 51 13-024-00 LIGHTING FIXTURES - DP1, DP3, and S19 Samples | -1 | 2021-01-19
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-05 02:00 |  | 26 51 13-24.0 DP1 DP3 and S19 Samples-MAM_ME REVIEW_pop.pdf
26 51 13-027-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-027-00 LIGHTING FIXTURES - LT-28 Bulb Submittal | Closed | Architectural, Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-23 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Kuebler Perry (Populous), David Riffel (ME Engineers) |  |  |  | 2021-03-09 | 2021-03-23 | 29 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2021-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11620 | Received | For Review | 2021-02-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-03-09 | Submittal Number: 26 51 13-27.0 From: PATRICK KLEIN Final Due Date: 02/22/21 Subject: LIGHTING FIXTURES - LT-28 BULB SUBMITTAL Description: PLEASE REVIEW THE REVISION FOR LT-28 LIGHT BULB Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 15060 | Forwarded | For Review | 2021-02-24 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); David Riffel (ME Engineers) | 2021-03-03 | Submittal Number: 26 51 13-27.0 From: PATRICK KLEIN Final Due Date: 02/22/21 Subject: LIGHTING FIXTURES - LT-28 BULB SUBMITTAL Description: PLEASE REVIEW THE REVISION FOR LT-28 LIGHT BULB Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12190 | Review Response | Approved as Noted/Resubmit | 2021-03-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review ready to be returned to Mortenson. Thank you, Mark Lievens ME Engineers 2021.03.23 | Info Exchange
| 15776 | Responded and Closed | Approved as Noted | 2021-03-23 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review ready to be returned to Mortenson. Thank you, Mark Lievens ME Engineers 2021.03.23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-23 02:00 |  | 26 51 13-27.0 LT-28 Bulb Submittal-RG REVIEW.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-23 02:00 |  | 26 51 13-27.0 LT-28 Bulb Submittal-RG REVIEW.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-02-23 02:00 |  | 26 51 13-27.0 LT-28 Bulb Submittal-RG REVIEW.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-29 02:00 |  | 26 51 13-27.0 LT-28 Bulb Submittal-RG-ME REVIEW_POPV2.pdf
26 51 13-028-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-028-00 LIGHTING FIXTURES - Luminii Shop Drawings | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-02-22 | 2021-03-24 | 45 |  | Record Copies; Transfers; Submittals |  | 44 |  | 2021-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11249 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-02-22 | Submittal Number: 26 51 13-28.0 From: PATRICK KLEIN Final Due Date: 02/19/21 Subject: LIGHTING FIXTURES - LUMINII SHOP DRAWINGS Description: THE LUMINNI SHOP DRAWINGS ARE BEING PROVIDED FOR THE FOLLOWING AREAS: CHAIRMAN'S CLUB CONCOURSE A CONCOURSE B CONCOURSE C CONCOURSE D SE METRO CLUB MT. BAKER CLUB SE SPACE NEEDLE CLUB & SW SPACE NEEDLE CLUB SE SUITES TUNNEL CLUBS A, A1, B1, E, B, D, C AND TUNNEL CLUB CORRIDOR Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 14564 | Forwarded | For Review | 2021-02-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-15 | Submittal Number: 26 51 13-28.0 From: PATRICK KLEIN Final Due Date: 02/19/21 Subject: LIGHTING FIXTURES - LUMINII SHOP DRAWINGS Description: THE LUMINNI SHOP DRAWINGS ARE BEING PROVIDED FOR THE FOLLOWING AREAS: CHAIRMAN'S CLUB CONCOURSE A CONCOURSE B CONCOURSE C CONCOURSE D SE METRO CLUB MT. BAKER CLUB SE SPACE NEEDLE CLUB & SW SPACE NEEDLE CLUB SE SUITES TUNNEL CLUBS A, A1, B1, E, B, D, C AND TUNNEL CLUB CORRIDOR Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 15765 | Forwarded | For Review | 2021-03-23 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-22 | Submittal Number: 26 51 13-28.0 From: PATRICK KLEIN Final Due Date: 02/19/21 Subject: LIGHTING FIXTURES - LUMINII SHOP DRAWINGS Description: THE LUMINNI SHOP DRAWINGS ARE BEING PROVIDED FOR THE FOLLOWING AREAS: CHAIRMAN'S CLUB CONCOURSE A CONCOURSE B CONCOURSE C CONCOURSE D SE METRO CLUB MT. BAKER CLUB SE SPACE NEEDLE CLUB & SW SPACE NEEDLE CLUB SE SUITES TUNNEL CLUBS A, A1, B1, E, B, D, C AND TUNNEL CLUB CORRIDOR Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12208 | Review Response | Approved as Noted/Resubmit | 2021-03-23 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review ready to be sent to Mortenson. This submittal has been marked as very HOT to return. Thank you, Mark Lievens ME Engineers 2021.03.23 | Info Exchange
| 15797 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-24 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.03.23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-07 |  | 26 51 13-28.0 Luminii Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-07 |  | 26 51 13-28.0 Luminii Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-06 02:00 |  | 26 51 13-28.0 Luminii Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-02-06 |  | 26 51 13-28.0 Luminii Shop Drawings-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-03-24 |  | 26 51 13-28.0 Luminii Shop Drawings-MAM-ME_POP.pdf
26 51 13-028-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-028-01 LIGHTING FIXTURES - LP6E Shop Drawings | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-25 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-04-09 07:00 | 2021-04-14 | 21 |  | Record Copies; Transfers; Submittals | 26 51 13-028-01-01 - 26 51 13-028-01 LIGHTING FIXTURES - LP6E Shop Drawings | 21 |  | 2021-04-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12239 | Received | For Review | 2021-03-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-04-09 07:00 | Submittal Number: 26 51 13-28.1 From: PATRICK KLEIN Final Due Date: 04/08/21 Subject: LIGHTING FIXTURES - LP6E SHOP DRAWINGS Description: SHOP DRAWINGS PROVIDED FOR THE FOLLOWING LIGHT FIXTURE: LP6E PLEASE REVIEW. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 15830 | Forwarded | For Review | 2021-03-25 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-04-01 | Submittal Number: 26 51 13-28.1 From: PATRICK KLEIN Final Due Date: 04/08/21 Subject: LIGHTING FIXTURES - LP6E SHOP DRAWINGS Description: SHOP DRAWINGS PROVIDED FOR THE FOLLOWING LIGHT FIXTURE: LP6E PLEASE REVIEW. Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12580 | Review Response | Approved as Noted/Resubmit | 2021-04-08 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.04.08 | Info Exchange
| 12574 | Review Response | Approved as Noted/Resubmit | 2021-04-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16292 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-14 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-25 |  | 26 51 13-28.1 Luminii Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-25 |  | 26 51 13-28.1 Luminii Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-03-24 02:00 |  | 26 51 13-28.1 Luminii Shop Drawings-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-14 |  | 26 51 13-28.1 Luminii Shop Drawings-MAM - ME POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-03-25 |  | 26 51 13-28.1 Luminii Shop Drawings-MAM.pdf
26 51 13-028-01-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-028-01 LIGHTING FIXTURES - LP6E Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 51 13-028-01 - 26 51 13-028-01 LIGHTING FIXTURES - LP6E Shop Drawings | -1 | 2021-04-28
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-25 |  | 26 51 13-28.1 Luminii Shop Drawings-MAM.pdf
26 51 13-029-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-029-00 LIGHTING FIXTURES - S20/S20A Shop Drawings | Closed | Lighting, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Todd Spangler (Populous) |  |  |  | 2021-02-22 | 2021-03-04 | 25 |  | Record Copies; Transfers; Submittals | 26 51 13-029-00-01 - 26 51 13-029-00 LIGHTING FIXTURES - S20/S20A Shop Drawings | 15 |  | 2021-03-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11258 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-02-22 | Submittal Number: 26 51 13-29.0 From: PATRICK KLEIN Final Due Date: 02/22/21 Subject: LIGHTING FIXTURES - S20/S20A SHOP DRAWINGS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 14582 | Forwarded | For Review | 2021-02-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-15 | Submittal Number: 26 51 13-29.0 From: PATRICK KLEIN Final Due Date: 02/22/21 Subject: LIGHTING FIXTURES - S20/S20A SHOP DRAWINGS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11764 | Review Response | Revise and Resubmit | 2021-02-22 | David Riffel (ME Engineers) | Shaina Burris (Populous) |  | See attached for ME Review comments. | Info Exchange
| 15078 | Forwarded | For Review | 2021-02-24 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous) | 2021-02-22 | Submittal Number: 26 51 13-29.0 From: PATRICK KLEIN Final Due Date: 02/22/21 Subject: LIGHTING FIXTURES - S20/S20A SHOP DRAWINGS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Email
| 15267 | Responded and Closed | Revise and Resubmit | 2021-03-04 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-08 |  | 26 51 13-29.0 S20 S20A Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-08 |  | 26 51 13-29.0 S20 S20A Shop Drawings-MAM.pdf
| Review Response |  | David Riffel (ME Engineers) | 1 | 2021-02-08 |  | 26 51 13-29.0 S20 S20A Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-07 02:00 |  | 26 51 13-29.0 S20 S20A Shop Drawings-MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-03-04 |  | 26 51 13-29.0 S20 S20A Shop Drawings-MAM_ME _POP.pdf
26 51 13-029-00-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-029-00 LIGHTING FIXTURES - S20/S20A Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 51 13-029-00 - 26 51 13-029-00 LIGHTING FIXTURES - S20/S20A Shop Drawings | -1 | 2021-03-18
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-04 |  | 26 51 13-29.0 S20 S20A Shop Drawings-MAM_ME _POP.pdf
26 51 13-030-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-030-00 LIGHTING FIXTURES - CCD 082 and CCD 086 Fixtures | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-15 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-03-01 | 2021-03-10 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-03-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11413 | Received | For Review | 2021-02-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-03-01 | Submittal Number: 26 51 13-30.0 From: PATRICK KLEIN Final Due Date: 03/01/21 Subject: LIGHTING FIXTURES - CCD 082 AND CCD 086 FIXTURES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 14780 | Forwarded | For Review | 2021-02-15 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-02-22 | Submittal Number: 26 51 13-30.0 From: PATRICK KLEIN Final Due Date: 03/01/21 Subject: LIGHTING FIXTURES - CCD 082 AND CCD 086 FIXTURES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11926 | Review Response | Approved as Noted/Resubmit | 2021-03-03 | Heidi Evans (ME Engineers) | Shaina Burris (Populous) |  |  | Info Exchange
| 11921 | Review Response | Approved as Noted/Resubmit | 2021-03-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 15446 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-10 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 26 51 13-30.0 CCD 082 and CCD 086 Fixtures-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-15 |  | 26 51 13-30.0 CCD 082 and CCD 086 Fixtures-MAM.pdf
| Review Response |  | Heidi Evans (ME Engineers) | 1 | 2021-02-14 02:00 |  | 26 51 13-30.0 CCD 082 and CCD 086 Fixtures-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-10 |  | 26 51 13-30.0 POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-02-15 |  | 26 51 13-30.0 CCD 082 and CCD 086 Fixtures-MAM.pdf
26 51 13-030-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-030-01 LIGHTING FIXTURES - L12C Resubmittal | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-11 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-03-25 | 2021-03-24 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-03-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11952 | Received | For Review | 2021-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-03-25 | Submittal Number: 26 51 13-30.1 From: PATRICK KLEIN Final Due Date: 03/24/21 Subject: LIGHTING FIXTURES - L12C RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 15475 | Forwarded | For Review | 2021-03-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-18 | Submittal Number: 26 51 13-30.1 From: PATRICK KLEIN Final Due Date: 03/24/21 Subject: LIGHTING FIXTURES - L12C RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12229 | Review Response | Approved | 2021-03-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review ready to return to Mortenson. Thank you, Mark Lievens ME Engineers 2021.03.23 | Info Exchange
| 15819 | Responded and Closed | Approved | 2021-03-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review ready to return to Mortenson. Thank you, Mark Lievens ME Engineers 2021.03.23 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-10 |  | 26 51 13-30.1 L12C Resubmittal-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-10 |  | 26 51 13-30.1 L12C Resubmittal-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-03-09 02:00 |  | 26 51 13-30.1 L12C Resubmittal-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-24 02:00 |  | 26 51 13-30.1 L12C Resubmittal-MAM-ME_POP.pdf
26 51 13-033-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-033-00 LIGHTING FIXTURES - S20/S20A/L33/L36 Shops | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-04-19 | 2021-04-27 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12405 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 26 51 13-33.0 From: PATRICK KLEIN Final Due Date: 04/19/21 Subject: LIGHTING FIXTURES - S20/S20A/L33/L36 SHOPS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 16078 | Forwarded | For Review | 2021-04-05 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-04-12 | Submittal Number: 26 51 13-33.0 From: PATRICK KLEIN Final Due Date: 04/19/21 Subject: LIGHTING FIXTURES - S20/S20A/L33/L36 SHOPS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12827 | Review Response | Revise and Resubmit | 2021-04-21 | David Riffel (ME Engineers) | Populous SCA_CCA |  | See attached for ME review comments. | Info Exchange
| 12795 | Review Response | Approved as Noted | 2021-04-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 16538 | Responded and Closed | Approved as Noted | 2021-04-27 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 26 51 13-33.0 S20 S20A L33 and L36 shops.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 26 51 13-33.0 S20 S20A L33 and L36 shops.pdf
| Review Response |  | David Riffel (ME Engineers) | 1 | 2021-04-05 |  | 26 51 13-33.0 S20 S20A L33 and L36 shops.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-27 |  | 26 51 13-33.0 S20 S20A L33 and L36 shops - ME_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 26 51 13-33.0 S20 S20A L33 and L36 shops.pdf
26 51 13-033-01 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-033-01 LIGHTING FIXTURES - L36 Resubmittal | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-10 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-05-24 | 2021-05-26 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-05-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13012 | Received | For Review | 2021-05-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-24 | Submittal Number: 26 51 13-33.1 From: PATRICK KLEIN Final Due Date: 05/24/21 Subject: LIGHTING FIXTURES - L36 RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 16835 | Forwarded | For Review | 2021-05-10 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-17 | Submittal Number: 26 51 13-33.1 From: PATRICK KLEIN Final Due Date: 05/24/21 Subject: LIGHTING FIXTURES - L36 RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 13267 | Review Response | Approved as Noted/Resubmit | 2021-05-25 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Populous - Can you please confirm the white finish for this fixture? It's the cove light used within Toilets/Grooming (01.37.10) area in the NHL locker room. Thank you, Mark Lievens ME Engineers 2021.05.25 | Info Exchange
| 17169 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.05.25 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 26 51 13-33.1 L36 Resubmittal-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-10 |  | 26 51 13-33.1 L36 Resubmittal-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-05-10 |  | 26 51 13-33.1 L36 Resubmittal-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-26 |  | 26 51 13-33.1 L36 Resubmittal-MAM - ME Review_pop.pdf
26 51 13-033-02 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-033-02 LIGHTING FIXTURES - L36 Resubmittal | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-28 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-14 07:00 | 2021-06-02 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-06-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13324 | Received | For Review | 2021-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction) | 2021-06-14 07:00 | Submittal Number: 26 51 13-33.2 From: PATRICK KLEIN Final Due Date: 06/10/21 Subject: LIGHTING FIXTURES - L36 RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 17237 | Forwarded | For Review | 2021-06-01 | Patrick Klein (Mortenson Construction) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-08 | Submittal Number: 26 51 13-33.2 From: PATRICK KLEIN Final Due Date: 06/10/21 Subject: LIGHTING FIXTURES - L36 RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 13357 | Review Response | Approved as Noted | 2021-06-02 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Populous - Please confirm a white finish for this fixture. It is the cove light used within the NHL locker room grooming area. Thank you, Mark Lievens ME Engineers 2021.06.02 | Info Exchange
| 13360 | Review Response | Approved as Noted | 2021-06-02 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17287 | Responded and Closed | Approved as Noted | 2021-06-02 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Populous - Please confirm a white finish for this fixture. It is the cove light used within the NHL locker room grooming area. Thank you, Mark Lievens ME Engineers 2021.06.02 Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-27 |  | 26 51 13-33.2 L36 Shops-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2021-05-27 |  | 26 51 13-33.2 L36 Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-05-27 |  | 26 51 13-33.2 L36 Shops-MAM.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-02 |  | 26 51 13-33.2 L36 Shops-MAM - ME Review_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-27 |  | 26 51 13-33.2 L36 Shops-MAM.pdf
26 51 13-035-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-035-00 CCD 088- Amazon Artist Lounge | Closed | Lighting, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Kuebler Perry (Populous) |  |  |  | 2021-04-22 | 2021-04-26 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12472 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction) | 2021-04-22 | Submittal Number: 26 51 13-35.0 From: PATRICK KLEIN Final Due Date: 04/14/21 Subject: CCD 088- AMAZON ARTIST LOUNGE Description: ADDED FIXTURE TYPES L7A AND L39 FOR THE AMAZON ARTIST LOUNGE Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 16162 | Forwarded | For Review | 2021-04-08 | Patrick Klein (Mortenson Construction) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-04-15 | Submittal Number: 26 51 13-35.0 From: PATRICK KLEIN Final Due Date: 04/14/21 Subject: CCD 088- AMAZON ARTIST LOUNGE Description: ADDED FIXTURE TYPES L7A AND L39 FOR THE AMAZON ARTIST LOUNGE Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 16259 | Forwarded | For Review | 2021-04-12 | Patrick Klein (Mortenson Construction) | Kuebler Perry (Populous) | 2021-04-19 | Submittal Number: 26 51 13-35.0 From: PATRICK KLEIN Final Due Date: 04/14/21 Subject: CCD 088- AMAZON ARTIST LOUNGE Description: ADDED FIXTURE TYPES L7A AND L39 FOR THE AMAZON ARTIST LOUNGE Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12790 | Review Response | Approved as Noted | 2021-04-22 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Populous shall confirm the finish of light fixture type L39 included within the submittal which is used within the sound booth of the amazon artist lounge. The fixture is a trimless flanged fixture however there is a small line of fixture that can be seen between the lens and drywall to hold the lens in place that can be seen. Currently the contractor has selected black but I believe it should be the color of the walls within the sound booth. If this is black, then it should just be a confirmed response required. Let me know if you have any quesitons and I can provide additional details. Thank you, Mark Lievens ME Engineers 2021.04.22 | Info Exchange
| 12787 | Review Response | Approved as Noted | 2021-04-26 | Kuebler Perry (Populous) | Patrick Klein (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| 16527 | Responded and Closed | Approved as Noted | 2021-04-26 | Patrick Klein (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 26 51 13-35.0 CCD 088 Amazon Artist Lounge-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2021-04-08 |  | 26 51 13-35.0 CCD 088 Amazon Artist Lounge-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2021-04-07 02:00 |  | 26 51 13-35.0 CCD 088 Amazon Artist Lounge-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-07 02:00 |  | 26 51 13-35.0 CCD 088 Amazon Artist Lounge-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-26 |  | 26 51 13-35.0 CCD 088 Amazon Artist Lounge-MAM-ME-POP.pdf
| Responded and Closed |  | Patrick Klein (Mortenson Construction) | 1 | 2021-04-08 |  | 26 51 13-35.0 CCD 088 Amazon Artist Lounge-MAM.pdf
26 51 13-037-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-037-00 LIGHTING FIXTURES - L8A Fixtures in Event Corridor | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-13 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-04-27 | 2021-04-26 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-04-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12560 | Received | For Review | 2021-04-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction) | 2021-04-27 | Submittal Number: 26 51 13-37.0 From: PATRICK KLEIN Final Due Date: 04/27/21 Subject: LIGHTING FIXTURES - L8A FIXTURES IN EVENT CORRIDOR Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 16269 | Forwarded | For Review | 2021-04-13 | Patrick Klein (Mortenson Construction) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-04-20 | Submittal Number: 26 51 13-37.0 From: PATRICK KLEIN Final Due Date: 04/27/21 Subject: LIGHTING FIXTURES - L8A FIXTURES IN EVENT CORRIDOR Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12791 | Review Response | Approved as Noted | 2021-04-22 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.04.22 | Info Exchange
| 12788 | Review Response | Approved as Noted | 2021-04-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16528 | Responded and Closed | Approved as Noted | 2021-04-26 | Patrick Klein (Mortenson Construction) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-13 |  | 26 51 13-37.0 L8A Fixtures in Event Corridor-MAM.pdf
| Forwarded |  | Patrick Klein (Mortenson Construction) | 1 | 2021-04-13 |  | 26 51 13-37.0 L8A Fixtures in Event Corridor-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-12 02:00 |  | 26 51 13-37.0 L8A Fixtures in Event Corridor-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-26 |  | 26 51 13-37.0 L8A Fixtures in Event Corridor-MAM-ME-POP.pdf
| Responded and Closed |  | Patrick Klein (Mortenson Construction) | 1 | 2021-04-26 |  | 26 51 13-37.0 L8A Fixtures in Event Corridor-MAM-ME-POP.pdf
26 51 13-038-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-038-00 LIGHTING FIXTURES - CCD 101 Coors Light Bar Shop Drawings | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-17 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-01 | 2021-07-02 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13560 | Received | For Review | 2021-06-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-07-01 | Submittal Number: 26 51 13-38.0 From: PATRICK KLEIN Final Due Date: 07/01/21 Subject: LIGHTING FIXTURES - CCD 101 COORS LIGHT BAR SHOP DRAWINGS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 17557 | Forwarded | For Review | 2021-06-17 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-24 | Submittal Number: 26 51 13-38.0 From: PATRICK KLEIN Final Due Date: 07/01/21 Subject: LIGHTING FIXTURES - CCD 101 COORS LIGHT BAR SHOP DRAWINGS Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 13763 | Review Response | Approved as Noted | 2021-07-01 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.01 | Info Exchange
| 17815 | Responded and Closed | Approved as Noted | 2021-07-02 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.01 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-17 |  | 26 51 13-38.0 CCD 101 Coors Light Bar Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-17 |  | 26 51 13-38.0 CCD 101 Coors Light Bar Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-06-17 |  | 26 51 13-38.0 CCD 101 Coors Light Bar Shops-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-07-02 |  | 26 51 13-38.0 CCD 101 Coors Light Bar Shops-MAM-ME_POP.pdf
26 51 13-039-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-039-00 LIGHTING FIXTURES - CCD 108 Living Wall Track Lighting, L48 | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-01 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-15 | 2021-07-02 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13750 | Received | For Review | 2021-07-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-07-15 | Submittal Number: 26 51 13-39.0 From: PATRICK KLEIN Final Due Date: 07/02/21 Subject: LIGHTING FIXTURES - CCD 108 LIVING WALL TRACK LIGHTING, L48 Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 17799 | Forwarded | For Review | 2021-07-01 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-08 | Submittal Number: 26 51 13-39.0 From: PATRICK KLEIN Final Due Date: 07/02/21 Subject: LIGHTING FIXTURES - CCD 108 LIVING WALL TRACK LIGHTING, L48 Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 13776 | Review Response | Approved as Noted | 2021-07-02 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.07.02 | Info Exchange
| 17830 | Responded and Closed | Approved as Noted | 2021-07-02 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.07.02 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-01 |  | 26 51 13-39.0 CCD 108 Living Wall Track Lighting L48-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-01 |  | 26 51 13-39.0 CCD 108 Living Wall Track Lighting L48-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-01 |  | 26 51 13-39.0 CCD 108 Living Wall Track Lighting L48-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-07-02 |  | 19155-S00041 CCD108 Living Wall Track Lighting L48 - ME_POP.pdf
26 51 13-041-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-041-00 LIGHTING FIXTURES - L25 Resubmittal | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-03 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-17 | 2021-08-24 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14198 | Received | For Review | 2021-08-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-08-17 | Submittal Number: 26 51 13-41.0 From: PATRICK KLEIN Final Due Date: 08/17/21 Subject: LIGHTING FIXTURES - L25 RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 18353 | Forwarded | For Review | 2021-08-03 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-10 | Submittal Number: 26 51 13-41.0 From: PATRICK KLEIN Final Due Date: 08/17/21 Subject: LIGHTING FIXTURES - L25 RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 14451 | Review Response | Approved as Noted | 2021-08-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.08.23 | Info Exchange
| 14439 | Review Response | Approved as Noted | 2021-08-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18637 | Responded and Closed | Approved as Noted | 2021-08-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-03 |  | 26 51 13-41.0 L25 Resubmittal-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-03 |  | 26 51 13-41.0 L25 Resubmittal-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-02 02:00 |  | 26 51 13-41.0 L25 Resubmittal-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-24 02:00 |  | 26 51 13-41.0 L25 Resubmittal-MAM-ME-POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-02 02:00 |  | 26 51 13-41.0 L25 Resubmittal-MAM.pdf
26 51 13-042-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-042-00 LIGHTING FIXTURES - D19 Resubmittal | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-03 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-17 | 2021-08-24 | 22 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14204 | Received | For Review | 2021-08-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-08-17 | Submittal Number: 26 51 13-42.0 From: PATRICK KLEIN Final Due Date: 08/17/21 Subject: LIGHTING FIXTURES - D19 RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 18340 | Forwarded | For Review | 2021-08-03 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-10 | Submittal Number: 26 51 13-42.0 From: PATRICK KLEIN Final Due Date: 08/17/21 Subject: LIGHTING FIXTURES - D19 RESUBMITTAL Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 14452 | Review Response | Approved | 2021-08-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.08.23 | Info Exchange
| 14440 | Review Response | Approved as Noted | 2021-08-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18638 | Responded and Closed | Approved as Noted | 2021-08-24 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-03 |  | 26 51 13-42.0 D19 Resubmittal-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-03 |  | 26 51 13-42.0 D19 Resubmittal-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-02 02:00 |  | 26 51 13-42.0 D19 Resubmittal-MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-24 02:00 |  | 26 51 13-42.0 D19 Resubmittal-MAM-ME-POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-02 02:00 |  | 26 51 13-42.0 D19 Resubmittal-MAM.pdf
26 51 13-043-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-043-00 LIGHTING FIXTURES -L41 Shop Drawings and Product Data | Closed | Lighting, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-11 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-25 | 2021-09-08 | 29 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2021-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14320 | Received | For Review | 2021-08-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-08-25 | Submittal Number: 26 51 13-43.0 From: PATRICK KLEIN Final Due Date: 08/25/21 Subject: LIGHTING FIXTURES -L41 SHOP DRAWINGS AND PRODUCT DATA Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 18490 | Forwarded | For Review | 2021-08-11 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-18 | Submittal Number: 26 51 13-43.0 From: PATRICK KLEIN Final Due Date: 08/25/21 Subject: LIGHTING FIXTURES -L41 SHOP DRAWINGS AND PRODUCT DATA Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 14603 | Review Response | Approved as Noted | 2021-09-08 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.09.08 | Info Exchange
| 18826 | Responded and Closed | Approved as Noted | 2021-09-08 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.09.08 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-11 |  | 26 51 13-43.0 L41 Shop Drawings and Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-11 |  | 26 51 13-43.0 L41 Shop Drawings and Product Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-11 |  | 26 51 13-43.0 L41 Shop Drawings and Product Data-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-09-08 |  | 26 51 13-43.0 L41 Shop Drawings and Product Data-MAM-ME_POP.pdf
26 51 13-044-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-044-00 19155-S0044 O&M Lighting | Open - Overdue | Lighting, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-31 | Forwarded - For Review |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers) |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers) |  | 2021-09-20 07:00 |  | 38 |  | Record Copies; Transfers; Submittals |  | 8
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14549 | Received | For Review | 2021-08-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-20 07:00 | Submittal Number: 26 51 13-44.0 From: BINH DUONG Final Due Date: 09/15/21 Subject: 19155-S0044 O&M LIGHTING Description: SUBMITTAL OVERVIEW: OPERATION & MAINTENANCE MANUALS PER OUR VENDOR - BLU54 Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 19033 | Forwarded | For Review | 2021-09-30 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers) |  | Submittal Number: 26 51 13-44.0 From: BINH DUONG Final Due Date: 09/15/21 Subject: 19155-S0044 O&M LIGHTING Description: SUBMITTAL OVERVIEW: OPERATION & MAINTENANCE MANUALS PER OUR VENDOR - BLU54 Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-30 02:00 |  | 26 51 13-44.0 O&M Lighting.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-30 |  | 26 51 13-44.0 O&M Lighting.pdf
26 51 13-045-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-045-00 1st Ave. N. Garage Lighting Package | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-07 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-09-21 | 2021-09-08 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14579 | Received | For Review | 2021-09-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Allie Zimmerman | 2021-09-21 | Submittal Number: 26 51 13-45.0 From: ALLIE ZIMMERMAN Final Due Date: 09/10/21 Subject: 1ST AVE. N. GARAGE LIGHTING PACKAGE Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 18794 | Forwarded | For Review | 2021-09-07 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-09-14 | Submittal Number: 26 51 13-45.0 From: ALLIE ZIMMERMAN Final Due Date: 09/10/21 Subject: 1ST AVE. N. GARAGE LIGHTING PACKAGE Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 14602 | Review Response | Approved as Noted | 2021-09-08 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.09.08 | Info Exchange
| 14601 | Review Response | Approved as Noted | 2021-09-08 | Mark Lievens (ME Engineers) | Tom Usher (Populous) |  | Pending response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.09.08 | Info Exchange
| 18824 | Responded and Closed | Approved as Noted | 2021-09-08 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Allie Zimmerman |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-07 |  | Submittal 26 51 13-45 Revision 0 1st Ave. N. Garage Lighting Package_MAM Reviewed.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-07 |  | Submittal 26 51 13-45 Revision 0 1st Ave. N. Garage Lighting Package_MAM Reviewed.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-09-07 |  | Submittal 26 51 13-45 Revision 0 1st Ave. N. Garage Lighting Package_MAM Reviewed.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-09-08 |  | Submittal 26 51 13-45 Revision 0 1st Ave. N. Garage Lighting Package_MAM_ME_POP.pdf
26 51 13-046-00 | 26 51 13 - LIGHTING FIXTURES | 26 51 13-046-00 LIGHTING FIXTURES - Kraken Bar L24A Fixtures | Open - Overdue | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-27 | Forwarded - For Review |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) | 2021-10-04 | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  | 2021-10-11 |  | 11 |  | Record Copies; Transfers; Submittals |  | 11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14709 | Received | For Review | 2021-09-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-10-11 | Submittal Number: 26 51 13-46.0 From: PATRICK KLEIN Final Due Date: 10/10/21 Subject: LIGHTING FIXTURES - KRAKEN BAR L24A FIXTURES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| 18968 | Forwarded | For Review | 2021-09-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-10-04 | Submittal Number: 26 51 13-46.0 From: PATRICK KLEIN Final Due Date: 10/10/21 Subject: LIGHTING FIXTURES - KRAKEN BAR L24A FIXTURES Description: Spec Section: 26 51 13 - LIGHTING FIXTURES Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-26 |  | 26 51 13-46.0 Kraken Bar L24A Fixtures-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-26 |  | 26 51 13-46.0 Kraken Bar L24A Fixtures-MAM.pdf
26 55 22-003-00 | 26 55 22 - HEAT TRACE EQUIPMENT | 26 55 22-003-00 Heat Trace Equipment for Fire Protection | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-07 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-22 07:00 | 2020-04-22 | 16 |  | Record Copies; Transfers; Submittals | 26 55 22-003-01 - 26 55 22-003-00 Heat Trace Equipment for Fire Protection | 16 |  | 2020-04-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05233 | Received | For Review | 2020-04-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Simran George (M.A. Mortenson Company) | 2020-04-22 07:00 | Submittal Number: 26 55 22-3.0 From: SIMRAN GEORGE Final Due Date: 04/20/20 Subject: HEAT TRACE EQUIPMENT FOR FIRE PROTECTION Description: SUBMIT PRODUCT DATA FOR ALL HEAT TRACE EQUIPMENT THAT SERVES FIRE PROTECTION PIPING Spec Section: 26 55 22 - HEAT TRACE EQUIPMENT Status: OPEN | Info Exchange
| 07122 | Forwarded | For Review | 2020-04-07 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-14 | Submittal Number: 26 55 22-3.0 From: SIMRAN GEORGE Final Due Date: 04/20/20 Subject: HEAT TRACE EQUIPMENT FOR FIRE PROTECTION Description: SUBMIT PRODUCT DATA FOR ALL HEAT TRACE EQUIPMENT THAT SERVES FIRE PROTECTION PIPING Spec Section: 26 55 22 - HEAT TRACE EQUIPMENT Status: OPEN | Info Exchange
| 05495 | Review Response | Approved as Noted/Resubmit | 2020-04-22 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens 2020.04.21 | Info Exchange
| 07449 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-22 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens 2020.04.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-06 |  | 26 55 22-3.0 Heat Trace Equipment for Fire Protection - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-06 |  | 26 55 22-3.0 Heat Trace Equipment for Fire Protection - MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-05 02:00 |  | 26 55 22-3.0 Heat Trace Equipment for Fire Protection - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-22 02:00 |  | 26 55 22-3.0 Heat Trace Equipment for Fire Protection - MAM-ME_POP.pdf
26 55 22-003-01 | 26 55 22 - HEAT TRACE EQUIPMENT | 26 55 22-003-00 Heat Trace Equipment for Fire Protection | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 26 55 22-003-00 - 26 55 22-003-00 Heat Trace Equipment for Fire Protection | -1 | 2020-05-06
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-22 02:00 |  | 26 55 22-3.0 Heat Trace Equipment for Fire Protection - MAM-ME_POP.pdf
26 56 13-001-00 | 26 56 13 - POLES AND STANDARDS | 26 56 13-001-00 POLES AND STANDARDS - Shop Drawings and Wiring Diagrams | Closed | Electrical, Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-19 | Responded and Closed - Rejected |  | Mark Lievens (ME Engineers), Allison Wood (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Greg Briggs (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Bryan Klote (Populous), Chris Minter (Populous) |  |  |  | 2020-06-03 07:00 | 2020-07-15 | 58 |  | Record Copies; Transfers; Submittals |  | 37 |  | 2020-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05913 | Received | For Review | 2020-05-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-03 07:00 | Submittal Number: 26 56 13-1.0 From: PATRICK KLEIN Final Due Date: 06/02/20 Subject: POLES AND STANDARDS - SHOP DRAWINGS AND WIRING DIAGRAMS Description: SHOP DRAWINGS SHALL INCLUDE BUT NOT BE LIMITED TO : - 1. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITHA SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. 2. MANUFACTURERS DIMENSIONED SCALE DRAWINGS SHOWING IN COMPLETE DETAIL, THE FABRICATION OF ALL ELECTRICAL POLE STANDARDS, ARMS, AND HARDWARE INCLUDING OVERALL AND DETAIL DIMENSIONS, FINISHES, METAL THICKNESS, TYPE, FABRICATION METHODS, SUPPORT METHOD, BALLASTS, HINGES, GASKETS, WIND LOADING, WIRE/CABLE CONNECTIONS, AND ALL OTHER INFORMATION TO SHOW COMPLIANCE WITH THE CONTRACT DOCUMENTS WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL POLES AND STANDARDS SHOWING CONNECTIONS TO ELECTRICAL POWER PANEL FEEDERS, SWITCHES, AND CONTROLLERS. DIFFERENTIATE BETWEEN PORTIONS OF ELECTRICAL WIRING WHICH ARE MANUFACTURER-INSTALLED AND PORTIONS WHICH ARE FIELD- INSTALLED. Spec Section: 26 56 13 - POLES AND STANDARDS Status: OPEN | Info Exchange
| 08022 | Forwarded | For Review | 2020-05-18 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Allison Wood (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-25 | Submittal Number: 26 56 13-1.0 From: PATRICK KLEIN Final Due Date: 06/02/20 Subject: POLES AND STANDARDS - SHOP DRAWINGS AND WIRING DIAGRAMS Description: SHOP DRAWINGS SHALL INCLUDE BUT NOT BE LIMITED TO : - 1. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITHA SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. 2. MANUFACTURERS DIMENSIONED SCALE DRAWINGS SHOWING IN COMPLETE DETAIL, THE FABRICATION OF ALL ELECTRICAL POLE STANDARDS, ARMS, AND HARDWARE INCLUDING OVERALL AND DETAIL DIMENSIONS, FINISHES, METAL THICKNESS, TYPE, FABRICATION METHODS, SUPPORT METHOD, BALLASTS, HINGES, GASKETS, WIND LOADING, WIRE/CABLE CONNECTIONS, AND ALL OTHER INFORMATION TO SHOW COMPLIANCE WITH THE CONTRACT DOCUMENTS WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL POLES AND STANDARDS SHOWING CONNECTIONS TO ELECTRICAL POWER PANEL FEEDERS, SWITCHES, AND CONTROLLERS. DIFFERENTIATE BETWEEN PORTIONS OF ELECTRICAL WIRING WHICH ARE MANUFACTURER-INSTALLED AND PORTIONS WHICH ARE FIELD- INSTALLED. Spec Section: 26 56 13 - POLES AND STANDARDS Status: OPEN | Info Exchange
| 06299 | Review Response | Approved as Noted/Resubmit | 2020-06-08 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.08 | Info Exchange
| 08496 | Forwarded | For Review | 2020-06-09 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) | 2020-06-03 | Submittal Number: 26 56 13-1.0 From: PATRICK KLEIN Final Due Date: 06/02/20 Subject: POLES AND STANDARDS - SHOP DRAWINGS AND WIRING DIAGRAMS Description: SHOP DRAWINGS SHALL INCLUDE BUT NOT BE LIMITED TO : - 1. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITHA SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. 2. MANUFACTURERS DIMENSIONED SCALE DRAWINGS SHOWING IN COMPLETE DETAIL, THE FABRICATION OF ALL ELECTRICAL POLE STANDARDS, ARMS, AND HARDWARE INCLUDING OVERALL AND DETAIL DIMENSIONS, FINISHES, METAL THICKNESS, TYPE, FABRICATION METHODS, SUPPORT METHOD, BALLASTS, HINGES, GASKETS, WIND LOADING, WIRE/CABLE CONNECTIONS, AND ALL OTHER INFORMATION TO SHOW COMPLIANCE WITH THE CONTRACT DOCUMENTS WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL POLES AND STANDARDS SHOWING CONNECTIONS TO ELECTRICAL POWER PANEL FEEDERS, SWITCHES, AND CONTROLLERS. DIFFERENTIATE BETWEEN PORTIONS OF ELECTRICAL WIRING WHICH ARE MANUFACTURER-INSTALLED AND PORTIONS WHICH ARE FIELD- INSTALLED. Spec Section: 26 56 13 - POLES AND STANDARDS Status: OPEN | Info Exchange
| 08632 | Forwarded | For Review | 2020-06-15 | Josh Dobken (Populous) | Bryan Klote (Populous); Chris Minter (Populous) | 2020-06-03 | Submittal Number: 26 56 13-1.0 From: PATRICK KLEIN Final Due Date: 06/02/20 Subject: POLES AND STANDARDS - SHOP DRAWINGS AND WIRING DIAGRAMS Description: SHOP DRAWINGS SHALL INCLUDE BUT NOT BE LIMITED TO : - 1. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITHA SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. 2. MANUFACTURERS DIMENSIONED SCALE DRAWINGS SHOWING IN COMPLETE DETAIL, THE FABRICATION OF ALL ELECTRICAL POLE STANDARDS, ARMS, AND HARDWARE INCLUDING OVERALL AND DETAIL DIMENSIONS, FINISHES, METAL THICKNESS, TYPE, FABRICATION METHODS, SUPPORT METHOD, BALLASTS, HINGES, GASKETS, WIND LOADING, WIRE/CABLE CONNECTIONS, AND ALL OTHER INFORMATION TO SHOW COMPLIANCE WITH THE CONTRACT DOCUMENTS WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL POLES AND STANDARDS SHOWING CONNECTIONS TO ELECTRICAL POWER PANEL FEEDERS, SWITCHES, AND CONTROLLERS. DIFFERENTIATE BETWEEN PORTIONS OF ELECTRICAL WIRING WHICH ARE MANUFACTURER-INSTALLED AND PORTIONS WHICH ARE FIELD- INSTALLED. Spec Section: 26 56 13 - POLES AND STANDARDS Status: OPEN | Info Exchange
| 06982 | Review Response | Rejected | 2020-06-23 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  | See comments by TT on page 5-7. Resubmit with loads imposed, signed and sealed calculations, and alternate anchorage details as required. SDK ¦ TT ¦ 6/23/2020 | Info Exchange
| 09349 | Responded and Closed | Rejected | 2020-07-15 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Samar Kenkre (Thornton Tomasetti) Remarks: See comments by TT on page 5-7. Resubmit with loads imposed, signed and sealed calculations, and alternate anchorage details as required. SDK ¦ TT ¦ 6/23/2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-18 |  | 26 56 13-1.0 Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-18 |  | 26 56 13-1.0 Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-17 02:00 |  | 26 56 13-1.0 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-17 02:00 |  | 26 56 13-1.0 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-17 02:00 |  | 26 56 13-1.0 Shop Drawings-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-05-17 02:00 |  | 26 56 13-1.0 Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-07-15 02:00 |  | 26 56 13-1.0 Shop Drawings-MAM-ME_TT REVIEW_POP.pdf
26 56 13-001-01 | 26 56 13 - POLES AND STANDARDS | 26 56 13-001-01 POLES AND STANDARDS - Shop Drawings and Wiring Diagrams | Closed | Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-07 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Bryan Klote (Populous), Todd Spangler (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2020-08-21 | 2020-09-28 | 53 |  | Record Copies; Transfers; Submittals |  | 48 |  | 2020-09-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07454 | Received | For Review | 2020-08-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-08-21 | Submittal Number: 26 56 13-1.1 From: PATRICK KLEIN Final Due Date: 08/20/20 Subject: POLES AND STANDARDS - SHOP DRAWINGS AND WIRING DIAGRAMS Description: SHOP DRAWINGS SHALL INCLUDE BUT NOT BE LIMITED TO : - 1. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITHA SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. 2. MANUFACTURERS DIMENSIONED SCALE DRAWINGS SHOWING IN COMPLETE DETAIL, THE FABRICATION OF ALL ELECTRICAL POLE STANDARDS, ARMS, AND HARDWARE INCLUDING OVERALL AND DETAIL DIMENSIONS, FINISHES, METAL THICKNESS, TYPE, FABRICATION METHODS, SUPPORT METHOD, BALLASTS, HINGES, GASKETS, WIND LOADING, WIRE/CABLE CONNECTIONS, AND ALL OTHER INFORMATION TO SHOW COMPLIANCE WITH THE CONTRACT DOCUMENTS WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL POLES AND STANDARDS SHOWING CONNECTIONS TO ELECTRICAL POWER PANEL FEEDERS, SWITCHES, AND CONTROLLERS. DIFFERENTIATE BETWEEN PORTIONS OF ELECTRICAL WIRING WHICH ARE MANUFACTURER-INSTALLED AND PORTIONS WHICH ARE FIELD- INSTALLED. Spec Section: 26 56 13 - POLES AND STANDARDS Status: OPEN | Info Exchange
| 09922 | Forwarded | For Review | 2020-08-07 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-08-14 | Submittal Number: 26 56 13-1.1 From: PATRICK KLEIN Final Due Date: 08/20/20 Subject: POLES AND STANDARDS - SHOP DRAWINGS AND WIRING DIAGRAMS Description: SHOP DRAWINGS SHALL INCLUDE BUT NOT BE LIMITED TO : - 1. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITHA SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. 2. MANUFACTURERS DIMENSIONED SCALE DRAWINGS SHOWING IN COMPLETE DETAIL, THE FABRICATION OF ALL ELECTRICAL POLE STANDARDS, ARMS, AND HARDWARE INCLUDING OVERALL AND DETAIL DIMENSIONS, FINISHES, METAL THICKNESS, TYPE, FABRICATION METHODS, SUPPORT METHOD, BALLASTS, HINGES, GASKETS, WIND LOADING, WIRE/CABLE CONNECTIONS, AND ALL OTHER INFORMATION TO SHOW COMPLIANCE WITH THE CONTRACT DOCUMENTS WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL POLES AND STANDARDS SHOWING CONNECTIONS TO ELECTRICAL POWER PANEL FEEDERS, SWITCHES, AND CONTROLLERS. DIFFERENTIATE BETWEEN PORTIONS OF ELECTRICAL WIRING WHICH ARE MANUFACTURER-INSTALLED AND PORTIONS WHICH ARE FIELD- INSTALLED. Spec Section: 26 56 13 - POLES AND STANDARDS Status: OPEN | Info Exchange
| 10215 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Kni... | 2020-08-21 | Submittal Number: 26 56 13-1.1 From: PATRICK KLEIN Final Due Date: 08/20/20 Subject: POLES AND STANDARDS - SHOP DRAWINGS AND WIRING DIAGRAMS Description: SHOP DRAWINGS SHALL INCLUDE BUT NOT BE LIMITED TO : - 1. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITHA SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. 2. MANUFACTURERS DIMENSIONED SCALE DRAWINGS SHOWING IN COMPLETE DETAIL, THE FABRICATION OF ALL ELECTRICAL POLE STANDARDS, ARMS, AND HARDWARE INCLUDING OVERALL AND DETAIL DIMENSIONS, FINISHES, METAL THICKNESS, TYPE, FABRICATION METHODS, SUPPORT METHOD, BALLASTS, HINGES, GASKETS, WIND LOADING, WIRE/CABLE CONNECTIONS, AND ALL OTHER INFORMATION TO SHOW COMPLIANCE WITH THE CONTRACT DOCUMENTS WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL POLES AND STANDARDS SHOWING CONNECTIONS TO ELECTRICAL POWER PANEL FEEDERS, SWITCHES, AND CONTROLLERS. DIFFERENTIATE BETWEEN PORTIONS OF ELECTRICAL WIRING WHICH ARE MANUFACTURER-INSTALLED AND PORTIONS WHICH ARE FIELD- INSTALLED. Spec Section: 26 56 13 - POLES AND STANDARDS Status: OPEN | Info Exchange
| 08104 | Review Response | Approved as Noted | 2020-09-15 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 10773 | Forwarded | For Review | 2020-09-15 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Mark Lievens (ME Engineers); Rhys Van Bemmel (Swift and Company Landscape Arch); Nick Theimer (ME Engineers); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-08-21 | Submittal Number: 26 56 13-1.1 From: PATRICK KLEIN Final Due Date: 08/20/20 Subject: POLES AND STANDARDS - SHOP DRAWINGS AND WIRING DIAGRAMS Description: SHOP DRAWINGS SHALL INCLUDE BUT NOT BE LIMITED TO : - 1. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITHA SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. 2. MANUFACTURERS DIMENSIONED SCALE DRAWINGS SHOWING IN COMPLETE DETAIL, THE FABRICATION OF ALL ELECTRICAL POLE STANDARDS, ARMS, AND HARDWARE INCLUDING OVERALL AND DETAIL DIMENSIONS, FINISHES, METAL THICKNESS, TYPE, FABRICATION METHODS, SUPPORT METHOD, BALLASTS, HINGES, GASKETS, WIND LOADING, WIRE/CABLE CONNECTIONS, AND ALL OTHER INFORMATION TO SHOW COMPLIANCE WITH THE CONTRACT DOCUMENTS WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR ELECTRICAL POLES AND STANDARDS SHOWING CONNECTIONS TO ELECTRICAL POWER PANEL FEEDERS, SWITCHES, AND CONTROLLERS. DIFFERENTIATE BETWEEN PORTIONS OF ELECTRICAL WIRING WHICH ARE MANUFACTURER-INSTALLED AND PORTIONS WHICH ARE FIELD- INSTALLED. Spec Section: 26 56 13 - POLES AND STANDARDS Status: OPEN | Info Exchange
| 08276 | Review Response | Approved as Noted | 2020-09-23 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for our response to the 35ft pole submittal. | Info Exchange
| 11107 | Responded and Closed | Approved as Noted | 2020-09-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See attached for our response to the 35ft pole submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-06 |  | 26 56 13-1.1 Shops Diagrams and Calculations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-06 |  | 26 56 13-1.1 Shops Diagrams and Calculations-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-06 |  | 26 56 13-1.1 Shops Diagrams and Calculations-MAM.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-08-05 02:00 |  | 26 56 13-1.1 Shops Diagrams and Calculations-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-08-05 02:00 |  | 26 56 13-1.1 Shops Diagrams and Calculations-MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2020-09-23 02:00 |  | 26 56 13-1.1 Shops Diagrams and Calculations-MAM_TT_POP_SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-09-28 02:00 |  | 26 56 13-1.1 Shops Diagrams and Calculations-MAM_TT_POP_SWIFT_POP2.pdf
26 56 71-001-00 | 26 56 71 - LED ARENA LIGHTING FIXTURES | 26 56 71-001-00 LED ARENA LIGHTING FIXTURES - Product Data, Shop Drawings, Calculations, Wiring Diagrams, and Illumination Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-06 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Allison Wood (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-21 07:00 | 2020-05-12 | 37 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05219 | Received | For Review | 2020-04-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-21 07:00 | Submittal Number: 26 56 71-1.0 From: PATRICK KLEIN Final Due Date: 04/20/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA AND INSTALLATION INSTRUCTIONS ON EACH TYPE OF LIGHTING FIXTURE AND COMPONENT. PRODUCT DATA SHALL INCLUDE BUT NOT LIMITED TO NOISE LEVEL, STARTING CURRENT, RUNNING CURRENT, POWER FACTOR AND DRIVER CHARACTERISTICS. SHOP DRAWINGS : AFTER THE SUCCESSFUL MANUFACTURER IS AWARDED THE PROJECT THE MANUFACTURER MAY BE GIVEN THE AIMING STRATEGY PREPARED BY THE ENGINEER FOR THE MANUFACTURER TO PREPARE HIS SHOP DRAWINGS. THE DESIGN WILL INCLUDE AIMING DIAGRAMS, ILLUMINATION LEVELS FOR BOTH HORIZONTAL AND VERTICAL ANGLES. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITH SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. SHOP DRAWING SUBMITTAL : - 1. SUBMIT PLAN SCANS SHOWING PROPOSED MOUNTING USING MANUFACTURERS APPLICATION SOFTWARE WITH THE CATWALK MOUNTING HEIGHTS, WITH THE SPACING OF ALL ARENA FIXTURES ONA 3-0 SPACING. 2. SUBMIT COMPUTER GENERATED PHOTOMETRIC INFORMATION AS INDICATED ON THE DRAWINGS AND SPECIFIED HEREIN. 3. ARRAY TEST POINTS: SHALL BE PROVIDED ONA 10 FEETX 10 FEET GRID, COVERING THE ENTIRE PLAYING SURFACE AND SEATING BOWL AS REQUIRED. 4. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE, 10 FEET ABOVE PLAYING SURFACE AND 30 FEET ABOVE PLAYING SURFACE FOR ARENA LIGHTING. IN ADDITION, COMPUTER PHOTOMETRICS SHALL BE PROVIDED THROUGHOUT THE SEATING BOWL FOR THE MAINTENANCE AND EMERGENCY EGRESS LIGHTING. 5. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE FOR EACH OF THE FOLLOWING: A. HORIZONTAL B. MAIN AND REVERSE CAMERA C. SLASH CAMERAS D. VERTICAL ORTHOGONAL (CARDINAL DIRECTIONS) 6. LUMINAIRE DIRT DEPRECIATION SHALL BE UTILIZED IN THE CALCULATIONS. 7. THE CONTRACTOR SHALL BE RESPONSIBLE FOR INSTALLING AND CONTROLLING ALL ARENA AND EMERGENCY LIGHTING FIXTURES, AND AIMING OF EACH FIXTURE TO MAINTAIN THE COMPUTER GENERATED PHOTOMETRIC DESIGN. 8. THE MANUFACTURERS SHALL SUBMITA COMPLETE SET OF AIMING DIAGRAMS SHOWING THE TARGET AIMING POINT COORDINATES AND AN ALPHA NUMERIC AIMING ASSIGNMENTS ON THE PLAYING SURFACE FOR EACH LUMINAIRE, AS PART OF THE SHOP DRAWING SUBMITTAL. 9. SUBMIT DOCUMENTATION DEPICTING LUMINAIRE LOCATIONS ON THE CATWALK RACKS AND INDICATE COORDINATE, VECTOR AND TARGET ASSIGNMENTS FOR EACH LUMINAIRE. 10. THE ENGINEER MAY VISIT THE MANUFACTURER PRIOR TO SHOP DRAWING APPROVAL TO REVIEW AND ANALYZE THE COMPUTER MODEL FOR THE PLAYING SURFACE AND SEATING BOWL. ILLUMINATION DATA : PROVIDE ISOLUX PLOT DIAGRAM OF FOOTCANDLES ON HORIZONTAL AND VERTICAL SURFACE WHICH SHOWS COMPOSITE VALUES OF ILLUMINANCE PROJECTED FROM THE ARRANGEMENT OF LIGHT SOURCES FOR INDICATED FIXTURE LOCATIONS AND HEIGHTS. SCOREBOARD VERTICAL FOOTCANDLE CALCULATION SHALL BE REQUIRED INDICATINGA MAXIMUM OF 50 FOOTCANDLES ON THE FACE OF THE SCOREBOARD. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR THE LIGHTING FIXTURES SHOWING CONNECTIONS TO ELECTRICAL POWER PANELS, SWITCHES, CONTROLLERS, AND FEEDERS. DIFFERENTIATE BETWEEN PORTIONS OF WIRING WHICH ARE INSTALLED BY THE MANUFACTURER AND PORTIONS WHICH ARE FIELD INSTALLED. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 07103 | Forwarded | For Review | 2020-04-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Allison Wood (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-13 | Submittal Number: 26 56 71-1.0 From: PATRICK KLEIN Final Due Date: 04/20/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA AND INSTALLATION INSTRUCTIONS ON EACH TYPE OF LIGHTING FIXTURE AND COMPONENT. PRODUCT DATA SHALL INCLUDE BUT NOT LIMITED TO NOISE LEVEL, STARTING CURRENT, RUNNING CURRENT, POWER FACTOR AND DRIVER CHARACTERISTICS. SHOP DRAWINGS : AFTER THE SUCCESSFUL MANUFACTURER IS AWARDED THE PROJECT THE MANUFACTURER MAY BE GIVEN THE AIMING STRATEGY PREPARED BY THE ENGINEER FOR THE MANUFACTURER TO PREPARE HIS SHOP DRAWINGS. THE DESIGN WILL INCLUDE AIMING DIAGRAMS, ILLUMINATION LEVELS FOR BOTH HORIZONTAL AND VERTICAL ANGLES. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITH SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. SHOP DRAWING SUBMITTAL : - 1. SUBMIT PLAN SCANS SHOWING PROPOSED MOUNTING USING MANUFACTURERS APPLICATION SOFTWARE WITH THE CATWALK MOUNTING HEIGHTS, WITH THE SPACING OF ALL ARENA FIXTURES ONA 3-0 SPACING. 2. SUBMIT COMPUTER GENERATED PHOTOMETRIC INFORMATION AS INDICATED ON THE DRAWINGS AND SPECIFIED HEREIN. 3. ARRAY TEST POINTS: SHALL BE PROVIDED ONA 10 FEETX 10 FEET GRID, COVERING THE ENTIRE PLAYING SURFACE AND SEATING BOWL AS REQUIRED. 4. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE, 10 FEET ABOVE PLAYING SURFACE AND 30 FEET ABOVE PLAYING SURFACE FOR ARENA LIGHTING. IN ADDITION, COMPUTER PHOTOMETRICS SHALL BE PROVIDED THROUGHOUT THE SEATING BOWL FOR THE MAINTENANCE AND EMERGENCY EGRESS LIGHTING. 5. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE FOR EACH OF THE FOLLOWING: A. HORIZONTAL B. MAIN AND REVERSE CAMERA C. SLASH CAMERAS D. VERTICAL ORTHOGONAL (CARDINAL DIRECTIONS) 6. LUMINAIRE DIRT DEPRECIATION SHALL BE UTILIZED IN THE CALCULATIONS. 7. THE CONTRACTOR SHALL BE RESPONSIBLE FOR INSTALLING AND CONTROLLING ALL ARENA AND EMERGENCY LIGHTING FIXTURES, AND AIMING OF EACH FIXTURE TO MAINTAIN THE COMPUTER GENERATED PHOTOMETRIC DESIGN. 8. THE MANUFACTURERS SHALL SUBMITA COMPLETE SET OF AIMING DIAGRAMS SHOWING THE TARGET AIMING POINT COORDINATES AND AN ALPHA NUMERIC AIMING ASSIGNMENTS ON THE PLAYING SURFACE FOR EACH LUMINAIRE, AS PART OF THE SHOP DRAWING SUBMITTAL. 9. SUBMIT DOCUMENTATION DEPICTING LUMINAIRE LOCATIONS ON THE CATWALK RACKS AND INDICATE COORDINATE, VECTOR AND TARGET ASSIGNMENTS FOR EACH LUMINAIRE. 10. THE ENGINEER MAY VISIT THE MANUFACTURER PRIOR TO SHOP DRAWING APPROVAL TO REVIEW AND ANALYZE THE COMPUTER MODEL FOR THE PLAYING SURFACE AND SEATING BOWL. ILLUMINATION DATA : PROVIDE ISOLUX PLOT DIAGRAM OF FOOTCANDLES ON HORIZONTAL AND VERTICAL SURFACE WHICH SHOWS COMPOSITE VALUES OF ILLUMINANCE PROJECTED FROM THE ARRANGEMENT OF LIGHT SOURCES FOR INDICATED FIXTURE LOCATIONS AND HEIGHTS. SCOREBOARD VERTICAL FOOTCANDLE CALCULATION SHALL BE REQUIRED INDICATINGA MAXIMUM OF 50 FOOTCANDLES ON THE FACE OF THE SCOREBOARD. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR THE LIGHTING FIXTURES SHOWING CONNECTIONS TO ELECTRICAL POWER PANELS, SWITCHES, CONTROLLERS, AND FEEDERS. DIFFERENTIATE BETWEEN PORTIONS OF WIRING WHICH ARE INSTALLED BY THE MANUFACTURER AND PORTIONS WHICH ARE FIELD INSTALLED. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange