| 07429 | Forwarded | For Review | 2020-04-21 | Josh Dobken (Populous) | Mark Lievens (ME Engineers) | 2020-04-21 | Submittal Number: 26 56 71-1.0 From: PATRICK KLEIN Final Due Date: 04/20/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA AND INSTALLATION INSTRUCTIONS ON EACH TYPE OF LIGHTING FIXTURE AND COMPONENT. PRODUCT DATA SHALL INCLUDE BUT NOT LIMITED TO NOISE LEVEL, STARTING CURRENT, RUNNING CURRENT, POWER FACTOR AND DRIVER CHARACTERISTICS. SHOP DRAWINGS : AFTER THE SUCCESSFUL MANUFACTURER IS AWARDED THE PROJECT THE MANUFACTURER MAY BE GIVEN THE AIMING STRATEGY PREPARED BY THE ENGINEER FOR THE MANUFACTURER TO PREPARE HIS SHOP DRAWINGS. THE DESIGN WILL INCLUDE AIMING DIAGRAMS, ILLUMINATION LEVELS FOR BOTH HORIZONTAL AND VERTICAL ANGLES. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITH SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. SHOP DRAWING SUBMITTAL : - 1. SUBMIT PLAN SCANS SHOWING PROPOSED MOUNTING USING MANUFACTURERS APPLICATION SOFTWARE WITH THE CATWALK MOUNTING HEIGHTS, WITH THE SPACING OF ALL ARENA FIXTURES ONA 3-0 SPACING. 2. SUBMIT COMPUTER GENERATED PHOTOMETRIC INFORMATION AS INDICATED ON THE DRAWINGS AND SPECIFIED HEREIN. 3. ARRAY TEST POINTS: SHALL BE PROVIDED ONA 10 FEETX 10 FEET GRID, COVERING THE ENTIRE PLAYING SURFACE AND SEATING BOWL AS REQUIRED. 4. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE, 10 FEET ABOVE PLAYING SURFACE AND 30 FEET ABOVE PLAYING SURFACE FOR ARENA LIGHTING. IN ADDITION, COMPUTER PHOTOMETRICS SHALL BE PROVIDED THROUGHOUT THE SEATING BOWL FOR THE MAINTENANCE AND EMERGENCY EGRESS LIGHTING. 5. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE FOR EACH OF THE FOLLOWING: A. HORIZONTAL B. MAIN AND REVERSE CAMERA C. SLASH CAMERAS D. VERTICAL ORTHOGONAL (CARDINAL DIRECTIONS) 6. LUMINAIRE DIRT DEPRECIATION SHALL BE UTILIZED IN THE CALCULATIONS. 7. THE CONTRACTOR SHALL BE RESPONSIBLE FOR INSTALLING AND CONTROLLING ALL ARENA AND EMERGENCY LIGHTING FIXTURES, AND AIMING OF EACH FIXTURE TO MAINTAIN THE COMPUTER GENERATED PHOTOMETRIC DESIGN. 8. THE MANUFACTURERS SHALL SUBMITA COMPLETE SET OF AIMING DIAGRAMS SHOWING THE TARGET AIMING POINT COORDINATES AND AN ALPHA NUMERIC AIMING ASSIGNMENTS ON THE PLAYING SURFACE FOR EACH LUMINAIRE, AS PART OF THE SHOP DRAWING SUBMITTAL. 9. SUBMIT DOCUMENTATION DEPICTING LUMINAIRE LOCATIONS ON THE CATWALK RACKS AND INDICATE COORDINATE, VECTOR AND TARGET ASSIGNMENTS FOR EACH LUMINAIRE. 10. THE ENGINEER MAY VISIT THE MANUFACTURER PRIOR TO SHOP DRAWING APPROVAL TO REVIEW AND ANALYZE THE COMPUTER MODEL FOR THE PLAYING SURFACE AND SEATING BOWL. ILLUMINATION DATA : PROVIDE ISOLUX PLOT DIAGRAM OF FOOTCANDLES ON HORIZONTAL AND VERTICAL SURFACE WHICH SHOWS COMPOSITE VALUES OF ILLUMINANCE PROJECTED FROM THE ARRANGEMENT OF LIGHT SOURCES FOR INDICATED FIXTURE LOCATIONS AND HEIGHTS. SCOREBOARD VERTICAL FOOTCANDLE CALCULATION SHALL BE REQUIRED INDICATINGA MAXIMUM OF 50 FOOTCANDLES ON THE FACE OF THE SCOREBOARD. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR THE LIGHTING FIXTURES SHOWING CONNECTIONS TO ELECTRICAL POWER PANELS, SWITCHES, CONTROLLERS, AND FEEDERS. DIFFERENTIATE BETWEEN PORTIONS OF WIRING WHICH ARE INSTALLED BY THE MANUFACTURER AND PORTIONS WHICH ARE FIELD INSTALLED. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 05872 | Review Response | Approved as Noted/Resubmit | 2020-04-29 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.04.29 | Info Exchange
| 07919 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-12 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-06 |  | 26 56 71-1.0 PD Shops Wiring Diagrams and Illumination Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-06 |  | 26 56 71-1.0 PD Shops Wiring Diagrams and Illumination Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-04-05 02:00 |  | 26 56 71-1.0 PD Shops Wiring Diagrams and Illumination Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-04-05 02:00 |  | 26 56 71-1.0 PD Shops Wiring Diagrams and Illumination Data-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-04-06 |  | 26 56 71-1.0 PD Shops Wiring Diagrams and Illumination Data-MAM.pdf
26 56 71-001-01 | 26 56 71 - LED ARENA LIGHTING FIXTURES | 26 56 71-001-01 LED ARENA LIGHTING FIXTURES - Product Data, Shop Drawings, Calculations, Wiring Diagrams, and Illumination Data | Closed | Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-27 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Allison Wood (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Todd Spangler (Populous), Kuebler Perry (Populous) |  |  |  | 2020-06-10 | 2020-06-15 | 20 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06068 | Received | For Review | 2020-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-06-10 | Submittal Number: 26 56 71-1.1 From: PATRICK KLEIN Final Due Date: 06/10/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA AND INSTALLATION INSTRUCTIONS ON EACH TYPE OF LIGHTING FIXTURE AND COMPONENT. PRODUCT DATA SHALL INCLUDE BUT NOT LIMITED TO NOISE LEVEL, STARTING CURRENT, RUNNING CURRENT, POWER FACTOR AND DRIVER CHARACTERISTICS. SHOP DRAWINGS : AFTER THE SUCCESSFUL MANUFACTURER IS AWARDED THE PROJECT THE MANUFACTURER MAY BE GIVEN THE AIMING STRATEGY PREPARED BY THE ENGINEER FOR THE MANUFACTURER TO PREPARE HIS SHOP DRAWINGS. THE DESIGN WILL INCLUDE AIMING DIAGRAMS, ILLUMINATION LEVELS FOR BOTH HORIZONTAL AND VERTICAL ANGLES. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITH SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. SHOP DRAWING SUBMITTAL : - 1. SUBMIT PLAN SCANS SHOWING PROPOSED MOUNTING USING MANUFACTURERS APPLICATION SOFTWARE WITH THE CATWALK MOUNTING HEIGHTS, WITH THE SPACING OF ALL ARENA FIXTURES ONA 3-0 SPACING. 2. SUBMIT COMPUTER GENERATED PHOTOMETRIC INFORMATION AS INDICATED ON THE DRAWINGS AND SPECIFIED HEREIN. 3. ARRAY TEST POINTS: SHALL BE PROVIDED ONA 10 FEETX 10 FEET GRID, COVERING THE ENTIRE PLAYING SURFACE AND SEATING BOWL AS REQUIRED. 4. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE, 10 FEET ABOVE PLAYING SURFACE AND 30 FEET ABOVE PLAYING SURFACE FOR ARENA LIGHTING. IN ADDITION, COMPUTER PHOTOMETRICS SHALL BE PROVIDED THROUGHOUT THE SEATING BOWL FOR THE MAINTENANCE AND EMERGENCY EGRESS LIGHTING. 5. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE FOR EACH OF THE FOLLOWING: A. HORIZONTAL B. MAIN AND REVERSE CAMERA C. SLASH CAMERAS D. VERTICAL ORTHOGONAL (CARDINAL DIRECTIONS) 6. LUMINAIRE DIRT DEPRECIATION SHALL BE UTILIZED IN THE CALCULATIONS. 7. THE CONTRACTOR SHALL BE RESPONSIBLE FOR INSTALLING AND CONTROLLING ALL ARENA AND EMERGENCY LIGHTING FIXTURES, AND AIMING OF EACH FIXTURE TO MAINTAIN THE COMPUTER GENERATED PHOTOMETRIC DESIGN. 8. THE MANUFACTURERS SHALL SUBMITA COMPLETE SET OF AIMING DIAGRAMS SHOWING THE TARGET AIMING POINT COORDINATES AND AN ALPHA NUMERIC AIMING ASSIGNMENTS ON THE PLAYING SURFACE FOR EACH LUMINAIRE, AS PART OF THE SHOP DRAWING SUBMITTAL. 9. SUBMIT DOCUMENTATION DEPICTING LUMINAIRE LOCATIONS ON THE CATWALK RACKS AND INDICATE COORDINATE, VECTOR AND TARGET ASSIGNMENTS FOR EACH LUMINAIRE. 10. THE ENGINEER MAY VISIT THE MANUFACTURER PRIOR TO SHOP DRAWING APPROVAL TO REVIEW AND ANALYZE THE COMPUTER MODEL FOR THE PLAYING SURFACE AND SEATING BOWL. ILLUMINATION DATA : PROVIDE ISOLUX PLOT DIAGRAM OF FOOTCANDLES ON HORIZONTAL AND VERTICAL SURFACE WHICH SHOWS COMPOSITE VALUES OF ILLUMINANCE PROJECTED FROM THE ARRANGEMENT OF LIGHT SOURCES FOR INDICATED FIXTURE LOCATIONS AND HEIGHTS. SCOREBOARD VERTICAL FOOTCANDLE CALCULATION SHALL BE REQUIRED INDICATINGA MAXIMUM OF 50 FOOTCANDLES ON THE FACE OF THE SCOREBOARD. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR THE LIGHTING FIXTURES SHOWING CONNECTIONS TO ELECTRICAL POWER PANELS, SWITCHES, CONTROLLERS, AND FEEDERS. DIFFERENTIATE BETWEEN PORTIONS OF WIRING WHICH ARE INSTALLED BY THE MANUFACTURER AND PORTIONS WHICH ARE FIELD INSTALLED. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 08219 | Forwarded | For Review | 2020-05-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Allison Wood (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-03 | Submittal Number: 26 56 71-1.1 From: PATRICK KLEIN Final Due Date: 06/10/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA AND INSTALLATION INSTRUCTIONS ON EACH TYPE OF LIGHTING FIXTURE AND COMPONENT. PRODUCT DATA SHALL INCLUDE BUT NOT LIMITED TO NOISE LEVEL, STARTING CURRENT, RUNNING CURRENT, POWER FACTOR AND DRIVER CHARACTERISTICS. SHOP DRAWINGS : AFTER THE SUCCESSFUL MANUFACTURER IS AWARDED THE PROJECT THE MANUFACTURER MAY BE GIVEN THE AIMING STRATEGY PREPARED BY THE ENGINEER FOR THE MANUFACTURER TO PREPARE HIS SHOP DRAWINGS. THE DESIGN WILL INCLUDE AIMING DIAGRAMS, ILLUMINATION LEVELS FOR BOTH HORIZONTAL AND VERTICAL ANGLES. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITH SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. SHOP DRAWING SUBMITTAL : - 1. SUBMIT PLAN SCANS SHOWING PROPOSED MOUNTING USING MANUFACTURERS APPLICATION SOFTWARE WITH THE CATWALK MOUNTING HEIGHTS, WITH THE SPACING OF ALL ARENA FIXTURES ONA 3-0 SPACING. 2. SUBMIT COMPUTER GENERATED PHOTOMETRIC INFORMATION AS INDICATED ON THE DRAWINGS AND SPECIFIED HEREIN. 3. ARRAY TEST POINTS: SHALL BE PROVIDED ONA 10 FEETX 10 FEET GRID, COVERING THE ENTIRE PLAYING SURFACE AND SEATING BOWL AS REQUIRED. 4. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE, 10 FEET ABOVE PLAYING SURFACE AND 30 FEET ABOVE PLAYING SURFACE FOR ARENA LIGHTING. IN ADDITION, COMPUTER PHOTOMETRICS SHALL BE PROVIDED THROUGHOUT THE SEATING BOWL FOR THE MAINTENANCE AND EMERGENCY EGRESS LIGHTING. 5. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE FOR EACH OF THE FOLLOWING: A. HORIZONTAL B. MAIN AND REVERSE CAMERA C. SLASH CAMERAS D. VERTICAL ORTHOGONAL (CARDINAL DIRECTIONS) 6. LUMINAIRE DIRT DEPRECIATION SHALL BE UTILIZED IN THE CALCULATIONS. 7. THE CONTRACTOR SHALL BE RESPONSIBLE FOR INSTALLING AND CONTROLLING ALL ARENA AND EMERGENCY LIGHTING FIXTURES, AND AIMING OF EACH FIXTURE TO MAINTAIN THE COMPUTER GENERATED PHOTOMETRIC DESIGN. 8. THE MANUFACTURERS SHALL SUBMITA COMPLETE SET OF AIMING DIAGRAMS SHOWING THE TARGET AIMING POINT COORDINATES AND AN ALPHA NUMERIC AIMING ASSIGNMENTS ON THE PLAYING SURFACE FOR EACH LUMINAIRE, AS PART OF THE SHOP DRAWING SUBMITTAL. 9. SUBMIT DOCUMENTATION DEPICTING LUMINAIRE LOCATIONS ON THE CATWALK RACKS AND INDICATE COORDINATE, VECTOR AND TARGET ASSIGNMENTS FOR EACH LUMINAIRE. 10. THE ENGINEER MAY VISIT THE MANUFACTURER PRIOR TO SHOP DRAWING APPROVAL TO REVIEW AND ANALYZE THE COMPUTER MODEL FOR THE PLAYING SURFACE AND SEATING BOWL. ILLUMINATION DATA : PROVIDE ISOLUX PLOT DIAGRAM OF FOOTCANDLES ON HORIZONTAL AND VERTICAL SURFACE WHICH SHOWS COMPOSITE VALUES OF ILLUMINANCE PROJECTED FROM THE ARRANGEMENT OF LIGHT SOURCES FOR INDICATED FIXTURE LOCATIONS AND HEIGHTS. SCOREBOARD VERTICAL FOOTCANDLE CALCULATION SHALL BE REQUIRED INDICATINGA MAXIMUM OF 50 FOOTCANDLES ON THE FACE OF THE SCOREBOARD. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR THE LIGHTING FIXTURES SHOWING CONNECTIONS TO ELECTRICAL POWER PANELS, SWITCHES, CONTROLLERS, AND FEEDERS. DIFFERENTIATE BETWEEN PORTIONS OF WIRING WHICH ARE INSTALLED BY THE MANUFACTURER AND PORTIONS WHICH ARE FIELD INSTALLED. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 06405 | Review Response | Approved as Noted | 2020-06-08 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.08 | Info Exchange
| 08497 | Forwarded | For Review | 2020-06-09 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Kuebler Perry (Populous) | 2020-06-10 | Submittal Number: 26 56 71-1.1 From: PATRICK KLEIN Final Due Date: 06/10/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA AND INSTALLATION INSTRUCTIONS ON EACH TYPE OF LIGHTING FIXTURE AND COMPONENT. PRODUCT DATA SHALL INCLUDE BUT NOT LIMITED TO NOISE LEVEL, STARTING CURRENT, RUNNING CURRENT, POWER FACTOR AND DRIVER CHARACTERISTICS. SHOP DRAWINGS : AFTER THE SUCCESSFUL MANUFACTURER IS AWARDED THE PROJECT THE MANUFACTURER MAY BE GIVEN THE AIMING STRATEGY PREPARED BY THE ENGINEER FOR THE MANUFACTURER TO PREPARE HIS SHOP DRAWINGS. THE DESIGN WILL INCLUDE AIMING DIAGRAMS, ILLUMINATION LEVELS FOR BOTH HORIZONTAL AND VERTICAL ANGLES. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITH SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. SHOP DRAWING SUBMITTAL : - 1. SUBMIT PLAN SCANS SHOWING PROPOSED MOUNTING USING MANUFACTURERS APPLICATION SOFTWARE WITH THE CATWALK MOUNTING HEIGHTS, WITH THE SPACING OF ALL ARENA FIXTURES ONA 3-0 SPACING. 2. SUBMIT COMPUTER GENERATED PHOTOMETRIC INFORMATION AS INDICATED ON THE DRAWINGS AND SPECIFIED HEREIN. 3. ARRAY TEST POINTS: SHALL BE PROVIDED ONA 10 FEETX 10 FEET GRID, COVERING THE ENTIRE PLAYING SURFACE AND SEATING BOWL AS REQUIRED. 4. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE, 10 FEET ABOVE PLAYING SURFACE AND 30 FEET ABOVE PLAYING SURFACE FOR ARENA LIGHTING. IN ADDITION, COMPUTER PHOTOMETRICS SHALL BE PROVIDED THROUGHOUT THE SEATING BOWL FOR THE MAINTENANCE AND EMERGENCY EGRESS LIGHTING. 5. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE FOR EACH OF THE FOLLOWING: A. HORIZONTAL B. MAIN AND REVERSE CAMERA C. SLASH CAMERAS D. VERTICAL ORTHOGONAL (CARDINAL DIRECTIONS) 6. LUMINAIRE DIRT DEPRECIATION SHALL BE UTILIZED IN THE CALCULATIONS. 7. THE CONTRACTOR SHALL BE RESPONSIBLE FOR INSTALLING AND CONTROLLING ALL ARENA AND EMERGENCY LIGHTING FIXTURES, AND AIMING OF EACH FIXTURE TO MAINTAIN THE COMPUTER GENERATED PHOTOMETRIC DESIGN. 8. THE MANUFACTURERS SHALL SUBMITA COMPLETE SET OF AIMING DIAGRAMS SHOWING THE TARGET AIMING POINT COORDINATES AND AN ALPHA NUMERIC AIMING ASSIGNMENTS ON THE PLAYING SURFACE FOR EACH LUMINAIRE, AS PART OF THE SHOP DRAWING SUBMITTAL. 9. SUBMIT DOCUMENTATION DEPICTING LUMINAIRE LOCATIONS ON THE CATWALK RACKS AND INDICATE COORDINATE, VECTOR AND TARGET ASSIGNMENTS FOR EACH LUMINAIRE. 10. THE ENGINEER MAY VISIT THE MANUFACTURER PRIOR TO SHOP DRAWING APPROVAL TO REVIEW AND ANALYZE THE COMPUTER MODEL FOR THE PLAYING SURFACE AND SEATING BOWL. ILLUMINATION DATA : PROVIDE ISOLUX PLOT DIAGRAM OF FOOTCANDLES ON HORIZONTAL AND VERTICAL SURFACE WHICH SHOWS COMPOSITE VALUES OF ILLUMINANCE PROJECTED FROM THE ARRANGEMENT OF LIGHT SOURCES FOR INDICATED FIXTURE LOCATIONS AND HEIGHTS. SCOREBOARD VERTICAL FOOTCANDLE CALCULATION SHALL BE REQUIRED INDICATINGA MAXIMUM OF 50 FOOTCANDLES ON THE FACE OF THE SCOREBOARD. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR THE LIGHTING FIXTURES SHOWING CONNECTIONS TO ELECTRICAL POWER PANELS, SWITCHES, CONTROLLERS, AND FEEDERS. DIFFERENTIATE BETWEEN PORTIONS OF WIRING WHICH ARE INSTALLED BY THE MANUFACTURER AND PORTIONS WHICH ARE FIELD INSTALLED. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 08616 | Responded and Closed | Approved as Noted | 2020-06-15 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.06.08 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-27 |  | 26 56 71-1.1 PD Shops Wiring Diagrams and Illumination Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-27 |  | 26 56 71-1.1 PD Shops Wiring Diagrams and Illumination Data-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-05-27 |  | 26 56 71-1.1 PD Shops Wiring Diagrams and Illumination Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-26 02:00 |  | 26 56 71-1.1 PD Shops Wiring Diagrams and Illumination Data-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-15 |  | 26 56 71-1.1 PD Shops Wiring Diagrams and Illumination Data-MAM-ME_POP.pdf
26 56 71-001-02 | 26 56 71 - LED ARENA LIGHTING FIXTURES | 26 56 71-001-02 LED ARENA LIGHTING FIXTURES - Product Data, Shop Drawings, Calculations, Wiring Diagrams, and Illumination Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-17 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Allison Wood (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-31 | 2020-08-06 | 21 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06997 | Received | For Review | 2020-07-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-31 | Submittal Number: 26 56 71-1.2 From: PATRICK KLEIN Final Due Date: 07/30/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA AND INSTALLATION INSTRUCTIONS ON EACH TYPE OF LIGHTING FIXTURE AND COMPONENT. PRODUCT DATA SHALL INCLUDE BUT NOT LIMITED TO NOISE LEVEL, STARTING CURRENT, RUNNING CURRENT, POWER FACTOR AND DRIVER CHARACTERISTICS. SHOP DRAWINGS : AFTER THE SUCCESSFUL MANUFACTURER IS AWARDED THE PROJECT THE MANUFACTURER MAY BE GIVEN THE AIMING STRATEGY PREPARED BY THE ENGINEER FOR THE MANUFACTURER TO PREPARE HIS SHOP DRAWINGS. THE DESIGN WILL INCLUDE AIMING DIAGRAMS, ILLUMINATION LEVELS FOR BOTH HORIZONTAL AND VERTICAL ANGLES. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITH SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. SHOP DRAWING SUBMITTAL : - 1. SUBMIT PLAN SCANS SHOWING PROPOSED MOUNTING USING MANUFACTURERS APPLICATION SOFTWARE WITH THE CATWALK MOUNTING HEIGHTS, WITH THE SPACING OF ALL ARENA FIXTURES ONA 3-0 SPACING. 2. SUBMIT COMPUTER GENERATED PHOTOMETRIC INFORMATION AS INDICATED ON THE DRAWINGS AND SPECIFIED HEREIN. 3. ARRAY TEST POINTS: SHALL BE PROVIDED ONA 10 FEETX 10 FEET GRID, COVERING THE ENTIRE PLAYING SURFACE AND SEATING BOWL AS REQUIRED. 4. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE, 10 FEET ABOVE PLAYING SURFACE AND 30 FEET ABOVE PLAYING SURFACE FOR ARENA LIGHTING. IN ADDITION, COMPUTER PHOTOMETRICS SHALL BE PROVIDED THROUGHOUT THE SEATING BOWL FOR THE MAINTENANCE AND EMERGENCY EGRESS LIGHTING. 5. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE FOR EACH OF THE FOLLOWING: A. HORIZONTAL B. MAIN AND REVERSE CAMERA C. SLASH CAMERAS D. VERTICAL ORTHOGONAL (CARDINAL DIRECTIONS) 6. LUMINAIRE DIRT DEPRECIATION SHALL BE UTILIZED IN THE CALCULATIONS. 7. THE CONTRACTOR SHALL BE RESPONSIBLE FOR INSTALLING AND CONTROLLING ALL ARENA AND EMERGENCY LIGHTING FIXTURES, AND AIMING OF EACH FIXTURE TO MAINTAIN THE COMPUTER GENERATED PHOTOMETRIC DESIGN. 8. THE MANUFACTURERS SHALL SUBMITA COMPLETE SET OF AIMING DIAGRAMS SHOWING THE TARGET AIMING POINT COORDINATES AND AN ALPHA NUMERIC AIMING ASSIGNMENTS ON THE PLAYING SURFACE FOR EACH LUMINAIRE, AS PART OF THE SHOP DRAWING SUBMITTAL. 9. SUBMIT DOCUMENTATION DEPICTING LUMINAIRE LOCATIONS ON THE CATWALK RACKS AND INDICATE COORDINATE, VECTOR AND TARGET ASSIGNMENTS FOR EACH LUMINAIRE. 10. THE ENGINEER MAY VISIT THE MANUFACTURER PRIOR TO SHOP DRAWING APPROVAL TO REVIEW AND ANALYZE THE COMPUTER MODEL FOR THE PLAYING SURFACE AND SEATING BOWL. ILLUMINATION DATA : PROVIDE ISOLUX PLOT DIAGRAM OF FOOTCANDLES ON HORIZONTAL AND VERTICAL SURFACE WHICH SHOWS COMPOSITE VALUES OF ILLUMINANCE PROJECTED FROM THE ARRANGEMENT OF LIGHT SOURCES FOR INDICATED FIXTURE LOCATIONS AND HEIGHTS. SCOREBOARD VERTICAL FOOTCANDLE CALCULATION SHALL BE REQUIRED INDICATINGA MAXIMUM OF 50 FOOTCANDLES ON THE FACE OF THE SCOREBOARD. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR THE LIGHTING FIXTURES SHOWING CONNECTIONS TO ELECTRICAL POWER PANELS, SWITCHES, CONTROLLERS, AND FEEDERS. DIFFERENTIATE BETWEEN PORTIONS OF WIRING WHICH ARE INSTALLED BY THE MANUFACTURER AND PORTIONS WHICH ARE FIELD INSTALLED. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 09373 | Forwarded | For Review | 2020-07-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Allison Wood (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-23 | Submittal Number: 26 56 71-1.2 From: PATRICK KLEIN Final Due Date: 07/30/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: PRODUCT DATA : SUBMIT MANUFACTURERS PRODUCT DATA AND INSTALLATION INSTRUCTIONS ON EACH TYPE OF LIGHTING FIXTURE AND COMPONENT. PRODUCT DATA SHALL INCLUDE BUT NOT LIMITED TO NOISE LEVEL, STARTING CURRENT, RUNNING CURRENT, POWER FACTOR AND DRIVER CHARACTERISTICS. SHOP DRAWINGS : AFTER THE SUCCESSFUL MANUFACTURER IS AWARDED THE PROJECT THE MANUFACTURER MAY BE GIVEN THE AIMING STRATEGY PREPARED BY THE ENGINEER FOR THE MANUFACTURER TO PREPARE HIS SHOP DRAWINGS. THE DESIGN WILL INCLUDE AIMING DIAGRAMS, ILLUMINATION LEVELS FOR BOTH HORIZONTAL AND VERTICAL ANGLES. SUBMIT FIXTURE SHOP DRAWINGS IN BOOKLET FORM WITH SEPARATE SHEET FOR EACH FIXTURE, ASSEMBLED IN LUMINAIRE TYPE ALPHABETICAL OR NUMERICAL ORDER, WITH PROPOSED FIXTURE AND ACCESSORIES CLEARLY INDICATED ON EACH SHEET. SHOP DRAWING SUBMITTAL : - 1. SUBMIT PLAN SCANS SHOWING PROPOSED MOUNTING USING MANUFACTURERS APPLICATION SOFTWARE WITH THE CATWALK MOUNTING HEIGHTS, WITH THE SPACING OF ALL ARENA FIXTURES ONA 3-0 SPACING. 2. SUBMIT COMPUTER GENERATED PHOTOMETRIC INFORMATION AS INDICATED ON THE DRAWINGS AND SPECIFIED HEREIN. 3. ARRAY TEST POINTS: SHALL BE PROVIDED ONA 10 FEETX 10 FEET GRID, COVERING THE ENTIRE PLAYING SURFACE AND SEATING BOWL AS REQUIRED. 4. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE, 10 FEET ABOVE PLAYING SURFACE AND 30 FEET ABOVE PLAYING SURFACE FOR ARENA LIGHTING. IN ADDITION, COMPUTER PHOTOMETRICS SHALL BE PROVIDED THROUGHOUT THE SEATING BOWL FOR THE MAINTENANCE AND EMERGENCY EGRESS LIGHTING. 5. COMPUTER PHOTOMETRICS SHALL BE PROVIDED AT 3 FEET ABOVE PLAYING SURFACE FOR EACH OF THE FOLLOWING: A. HORIZONTAL B. MAIN AND REVERSE CAMERA C. SLASH CAMERAS D. VERTICAL ORTHOGONAL (CARDINAL DIRECTIONS) 6. LUMINAIRE DIRT DEPRECIATION SHALL BE UTILIZED IN THE CALCULATIONS. 7. THE CONTRACTOR SHALL BE RESPONSIBLE FOR INSTALLING AND CONTROLLING ALL ARENA AND EMERGENCY LIGHTING FIXTURES, AND AIMING OF EACH FIXTURE TO MAINTAIN THE COMPUTER GENERATED PHOTOMETRIC DESIGN. 8. THE MANUFACTURERS SHALL SUBMITA COMPLETE SET OF AIMING DIAGRAMS SHOWING THE TARGET AIMING POINT COORDINATES AND AN ALPHA NUMERIC AIMING ASSIGNMENTS ON THE PLAYING SURFACE FOR EACH LUMINAIRE, AS PART OF THE SHOP DRAWING SUBMITTAL. 9. SUBMIT DOCUMENTATION DEPICTING LUMINAIRE LOCATIONS ON THE CATWALK RACKS AND INDICATE COORDINATE, VECTOR AND TARGET ASSIGNMENTS FOR EACH LUMINAIRE. 10. THE ENGINEER MAY VISIT THE MANUFACTURER PRIOR TO SHOP DRAWING APPROVAL TO REVIEW AND ANALYZE THE COMPUTER MODEL FOR THE PLAYING SURFACE AND SEATING BOWL. ILLUMINATION DATA : PROVIDE ISOLUX PLOT DIAGRAM OF FOOTCANDLES ON HORIZONTAL AND VERTICAL SURFACE WHICH SHOWS COMPOSITE VALUES OF ILLUMINANCE PROJECTED FROM THE ARRANGEMENT OF LIGHT SOURCES FOR INDICATED FIXTURE LOCATIONS AND HEIGHTS. SCOREBOARD VERTICAL FOOTCANDLE CALCULATION SHALL BE REQUIRED INDICATINGA MAXIMUM OF 50 FOOTCANDLES ON THE FACE OF THE SCOREBOARD. WIRING DIAGRAMS : SUBMIT WIRING DIAGRAMS FOR THE LIGHTING FIXTURES SHOWING CONNECTIONS TO ELECTRICAL POWER PANELS, SWITCHES, CONTROLLERS, AND FEEDERS. DIFFERENTIATE BETWEEN PORTIONS OF WIRING WHICH ARE INSTALLED BY THE MANUFACTURER AND PORTIONS WHICH ARE FIELD INSTALLED. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 07433 | Review Response | Approved as Noted/Resubmit | 2020-07-31 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.31 | Info Exchange
| 09901 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-06 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.07.31 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-16 |  | 26 56 71-1.2 PD and Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-16 |  | 26 56 71-1.2 PD and Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-15 02:00 |  | 26 56 71-1.2 PD and Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-06 02:00 |  | 26 56 71-1.2 PD and Drawings-MAM-ME_POP.pdf
26 56 71-001-03 | 26 56 71 - LED ARENA LIGHTING FIXTURES | 26 56 71-001-03 LED ARENA LIGHTING FIXTURES - Product Data, Shop Drawings, Calculations, Wiring Diagrams, and Illumination Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-10-19 | 2020-10-19 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-10-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08568 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 26 56 71-1.3 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: SUBMIT PHOTOMETRIC CALCULATIONS FOR AISLE LIGHTS. REVIEW SKIP GLARE AT 600 PRESS LEVEL AND BATON SHADOW TO MINIMIZE EFFECTS. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 11329 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-10-12 | Submittal Number: 26 56 71-1.3 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: SUBMIT PHOTOMETRIC CALCULATIONS FOR AISLE LIGHTS. REVIEW SKIP GLARE AT 600 PRESS LEVEL AND BATON SHADOW TO MINIMIZE EFFECTS. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 08861 | Review Response | Revise and Resubmit | 2020-10-19 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.19 | Info Exchange
| 11713 | Responded and Closed | Revise and Resubmit | 2020-10-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Revise and Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.19 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 26 56 71-1.3 Aisle Light Photometrics-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 26 56 71-1.3 Aisle Light Photometrics-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-05 |  | 26 56 71-1.3 Aisle Light Photometrics-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-10-19 |  | 26 56 71-1.3 Aisle Light Photometrics-MAM-ME_POP.pdf
26 56 71-001-04 | 26 56 71 - LED ARENA LIGHTING FIXTURES | 26 56 71-001-04 LED ARENA LIGHTING FIXTURES - Product Data, Shop Drawings, Calculations, Wiring Diagrams, and Illumination Data | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-12-03 08:00 | 2020-12-08 | 22 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-12-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09471 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-12-03 08:00 | Submittal Number: 26 56 71-1.4 From: PATRICK KLEIN Final Due Date: 12/01/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: SUBMIT PHOTOMETRIC CALCULATIONS FOR AISLE LIGHTS. REVIEW SKIP GLARE AT 600 PRESS LEVEL AND BATON SHADOW TO MINIMIZE EFFECTS. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 12489 | Forwarded | For Review | 2020-11-17 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2020-11-24 | Submittal Number: 26 56 71-1.4 From: PATRICK KLEIN Final Due Date: 12/01/20 Subject: LED ARENA LIGHTING FIXTURES - PRODUCT DATA, SHOP DRAWINGS, CALCULATIONS, WIRING DIAGRAMS, AND ILLUMINATION DATA Description: SUBMIT PHOTOMETRIC CALCULATIONS FOR AISLE LIGHTS. REVIEW SKIP GLARE AT 600 PRESS LEVEL AND BATON SHADOW TO MINIMIZE EFFECTS. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 10006 | Review Response | Approved as Noted | 2020-12-04 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.12.04 | Info Exchange
| 13094 | Responded and Closed | Approved as Noted | 2020-12-08 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-16 |  | 26 56 71-1.4 Aisle Light Photometrics-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-11-16 |  | 26 56 71-1.4 Aisle Light Photometrics-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-16 |  | 26 56 71-1.4 Aisle Light Photometrics-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-08 |  | 26 56 71-1.4 Aisle Light Photometrics-MAM-ME_POP.pdf
26 56 71-001-05 | 26 56 71 - LED ARENA LIGHTING FIXTURES | 26 56 71-001-05 SL3 Photometric Reports | Closed | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-26 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-05-10 | 2021-05-17 | 22 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-05-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12759 | Received | For Review | 2021-04-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-05-10 | Submittal Number: 26 56 71-1.5 From: PATRICK KLEIN Final Due Date: 05/09/21 Subject: SL3 PHOTOMETRIC REPORTS Description: ATTACHED ARE 2 PHOTOMETRIC REPORTS WITH THE REVISED LAYOUT ON THE SL3'S. I NEED DIRECTION ON IF WE SHOULD BE GETTING 80 CRI FIXTURES OR 90 CRI FIXTURES. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 16492 | Forwarded | For Review | 2021-04-26 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-03 | Submittal Number: 26 56 71-1.5 From: PATRICK KLEIN Final Due Date: 05/09/21 Subject: SL3 PHOTOMETRIC REPORTS Description: ATTACHED ARE 2 PHOTOMETRIC REPORTS WITH THE REVISED LAYOUT ON THE SL3'S. I NEED DIRECTION ON IF WE SHOULD BE GETTING 80 CRI FIXTURES OR 90 CRI FIXTURES. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 13120 | Review Response | Approved as Noted | 2021-05-13 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.05.13 | Info Exchange
| 16975 | Responded and Closed | Approved as Noted | 2021-05-17 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.05.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-26 |  | 26 56 71-1.5 Updated SL3 Photoometric Reports-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-26 |  | 26 56 71-1.5 Updated SL3 Photoometric Reports-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-25 02:00 |  | 26 56 71-1.5 Updated SL3 Photoometric Reports-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-05-17 02:00 |  | 26 56 71-1.5 Updated SL3 Photometric Reports-MAM-ME_POP.pdf
26 56 71-007-00 | 26 56 71 - LED ARENA LIGHTING FIXTURES | 26 56 71-007-00 LED ARENA LIGHTING FIXTURES - Maintenance Data | Open - Overdue | Lighting | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-27 | Forwarded - For Review |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) | 2021-10-04 | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  | 2021-10-11 |  | 11 |  | Record Copies; Transfers; Submittals |  | 11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14710 | Received | For Review | 2021-09-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2021-10-11 | Submittal Number: 26 56 71-7.0 From: PATRICK KLEIN Final Due Date: 10/10/21 Subject: LED ARENA LIGHTING FIXTURES - MAINTENANCE DATA Description: MAINTENANCE DATA : SUBMIT MAINTENANCE DATA AND PARTS LIST FOR EACH LIGHTING FIXTURE AND ACCESSORY; INCLUDING TROUBLE-SHOOTING MAINTENANCE GUIDE. INCLUDE THAT DATA, PRODUCT DATA, AND SHOP DRAWINGS INA MAINTENANCE MANUAL. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| 18969 | Forwarded | For Review | 2021-09-27 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-10-04 | Submittal Number: 26 56 71-7.0 From: PATRICK KLEIN Final Due Date: 10/10/21 Subject: LED ARENA LIGHTING FIXTURES - MAINTENANCE DATA Description: MAINTENANCE DATA : SUBMIT MAINTENANCE DATA AND PARTS LIST FOR EACH LIGHTING FIXTURE AND ACCESSORY; INCLUDING TROUBLE-SHOOTING MAINTENANCE GUIDE. INCLUDE THAT DATA, PRODUCT DATA, AND SHOP DRAWINGS INA MAINTENANCE MANUAL. Spec Section: 26 56 71 - LED ARENA LIGHTING FIXTURES Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-26 |  | 26 56 71-7.0 Musco Maintenance Data-MAM.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-26 |  | 26 56 71-7.0 Stamp-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-26 |  | 26 56 71-7.0 Musco Maintenance Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-26 |  | 26 56 71-7.0 Stamp-MAM.pdf
27 05 00-001-00 | 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS | 27 05 00-001-00 COMMON WORK RESULTS FOR COMMUNICATIONS - Product Data, Shop Drawings, and Compliance Matrix | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-26 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-04-16 | 2020-05-14 | 50 |  | Record Copies; Transfers; Submittals |  | 48 |  | 2020-05-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05048 | Received | For Review | 2020-03-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-16 | Submittal Number: 27 05 00-1.0 From: ELLA PILGRIM Final Due Date: 04/15/20 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 06870 | Forwarded | For Review | 2020-03-25 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-01 | Submittal Number: 27 05 00-1.0 From: ELLA PILGRIM Final Due Date: 04/15/20 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 06885 | Forwarded | For Review | 2020-03-26 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-02 | Submittal Number: 27 05 00-1.0 From: ELLA PILGRIM Final Due Date: 04/15/20 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 07171 | Forwarded | For Review | 2020-04-09 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers) | 2020-04-09 | Submittal Number: 27 05 00-1.0 From: ELLA PILGRIM Final Due Date: 04/15/20 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 05903 | Review Response | Approved as Noted | 2020-05-11 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 07972 | Responded and Closed | Approved as Noted | 2020-05-14 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-25 |  | 27 05 00-1.0 - Common Work Results for Communications.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-25 |  | 27 05 00-1.0 - Common Work Results for Communications.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-25 |  | 27 05 00-1.0 - Common Work Results for Communications.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-24 02:00 |  | 27 05 00-1.0 - Common Work Results for Communications.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-03-24 02:00 |  | 27 05 00-1.0 - Common Work Results for Communications.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-14 |  | 27 05 00-1.0 - Common Work Results for Communications_ME_POP.pdf
27 05 00-001-01 | 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS | 27 05 00-001-01 COMMON WORK RESULTS FOR COMMUNICATIONS - Product Data, Shop Drawings, and Compliance Matrix | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-03 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist |  |  |  | 2020-06-17 | 2020-06-18 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06162 | Received | For Review | 2020-06-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-17 | Submittal Number: 27 05 00-1.1 From: ELLA PILGRIM Final Due Date: 06/16/20 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 08335 | Forwarded | For Review | 2020-06-03 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-06-10 | Submittal Number: 27 05 00-1.1 From: ELLA PILGRIM Final Due Date: 06/16/20 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 06482 | Review Response | Approved | 2020-06-18 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 08734 | Responded and Closed | Approved | 2020-06-18 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Abby Harrison (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-02 |  | 27 05 00-1.1 - Common Work Results for Communications.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-02 |  | 27 05 00-1.1 - Common Work Results for Communications.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-06-01 02:00 |  | 27 05 00-1.1 - Common Work Results for Communications.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-18 02:00 |  | 27 05 00-1.1 - Common Work Results for Communications_ME_POP.pdf
27 05 00-001-02 | 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS | 27 05 00-001-02 COMMON WORK RESULTS FOR COMMUNICATIONS - Product Data, Shop Drawings, and Compliance Matrix | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-23 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2020-12-09 | 2020-12-22 | 30 |  | Record Copies; Transfers; Submittals |  | 30 |  | 2020-12-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09659 | Received | For Review | 2020-11-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-09 | Submittal Number: 27 05 00-1.2 From: ELLA PILGRIM Final Due Date: 12/08/20 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 12710 | Forwarded | For Review | 2020-11-23 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2020-11-30 | Submittal Number: 27 05 00-1.2 From: ELLA PILGRIM Final Due Date: 12/08/20 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 10335 | Review Response | Revise and Resubmit | 2020-12-22 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 13501 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-22 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-21 |  | 27 05 00-1.2 - Common Work Results for Communications.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-21 |  | 27 05 00-1.2 - Common Work Results for Communications.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-11-20 02:00 |  | 27 05 00-1.2 - Common Work Results for Communications.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-22 02:00 |  | 27 05 00-1.2 - Common Work Results for Communications - ME Response_POP.pdf
27 05 00-001-03 | 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS | 27 05 00-001-03 COMMON WORK RESULTS FOR COMMUNICATIONS - Product Data, Shop Drawings, and Compliance Matrix | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-20 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-02-03 | 2021-02-10 | 22 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-02-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10844 | Received | For Review | 2021-01-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-03 | Submittal Number: 27 05 00-1.3 From: ELLA PILGRIM Final Due Date: 02/05/21 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 14087 | Forwarded | For Review | 2021-01-20 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-01-27 | Submittal Number: 27 05 00-1.3 From: ELLA PILGRIM Final Due Date: 02/05/21 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 11316 | Review Response | Approved as Noted | 2021-02-08 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 14669 | Responded and Closed | Approved as Noted | 2021-02-10 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-20 |  | 27 05 00-1.3 - Common Work Results for Communications.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-20 |  | 27 05 00-1.3 - Common Work Results for Communications.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-01-19 02:00 |  | 27 05 00-1.3 - Common Work Results for Communications.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-10 02:00 |  | 27 05 00-1.3 - Common Work Results for Communications - ME Response_pop.pdf
27 05 00-001-04 | 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS | 27 05 00-001-04 COMMON WORK RESULTS FOR COMMUNICATIONS - Product Data, Shop Drawings, and Compliance Matrix | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-03-02 | 2021-03-08 | 21 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11435 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ella Pilgrim (Mortenson Construction) | 2021-03-02 | Submittal Number: 27 05 00-1.4 From: ELLA PILGRIM Final Due Date: 03/02/21 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 14804 | Forwarded | For Review | 2021-02-15 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-02-22 | Submittal Number: 27 05 00-1.4 From: ELLA PILGRIM Final Due Date: 03/02/21 Subject: COMMON WORK RESULTS FOR COMMUNICATIONS - PRODUCT DATA, SHOP DRAWINGS, AND COMPLIANCE MATRIX Description: PRODUCT DATA : - 1. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 2. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST (I.E. TABLE OF CONTENTS) AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. COMPONENT LIST SHALL INCLUDE: A. COMPONENT NAME B. MANUFACTURER C. SPECIFIC PRODUCT NUMBER (TO CLEARLY INDICATE SPECIAL OPTIONS, COLORS, ETC.) 3. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 4. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. PREFABRICATION SHOP DRAWINGS : (REFER TO APPENDIX-3 FOR ADDITIONAL REQUIREMENTS) 1. GENERAL: ALL SHOP DRAWINGS SHALL BE PROVIDED ON CONTRACTOR SPECIFIC TITLE BLOCK. CONTRACTOR MAY USE TECHNOLOGY DRAWING FILES ASA STARTING POINT FOR SHOP DRAWINGS BUT ADDITIONAL INFORMATION SHALL BE ADDED AND/OR UPDATED AS NOTED BELOW. 2. SYMBOL LEGEND, ABBREVIATIONS, AND DESCRIPTION: DRAWINGS SHALL INCLUDE THE FOLLOWING: A. GENERAL PROJECT INFORMATION, CONTRACTOR COMPANY NAME, ETC. B. DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS C. TYPICAL DEVICE MOUNTING HEIGHTS D. GENERAL NOTES AND/OR SCOPE DESCRIPTION, EXCLUSIONS, ETC. 3. ONE-LINE WIRING DIAGRAMS: PROVIDE BACKBONE RACEWAY ONE-LINE, BACKBONE AND HORIZONTAL CABLING, COPPER PAIR AND FIBER STRAND COUNTS, CABLE QUANTITIES, SPLICE ENCLOSURES, ETC. 4. SITE PLAN: PROVIDE COMPLETE SITE AND EXTERIOR PLANS INDICATING ALL SITE AND BUILDING FAADE MOUNTED COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. ADDITIONALLY, MANHOLES, PULL-BOXES, AND ALL MAJOR RACEWAY ROUTING SHALL BE INDICATED FOR CONDUITS 2-INCHES AND LARGER. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE AND/OR PULL-BOX PLACEMENT AS COORDINATED AND/OR CONFIRMED WITH SERVICE PROVIDER, CIVIL ENGINEER AND OTHER TRADES. 5. FLOOR PLANS: A. FLOOR PLANS SHALL INDICATE ALL COMMUNICATION DEVICE OUTLETS, EQUIPMENT, AND COMPONENTS PROPOSED TO BE INSTALLED. B. FLOOR PLANS SHALL INDICATE CABLE ROUTING ORIGIN AND LABELING SCHEME FOR EACH CABLE AND TERMINATION POSITION. C. REFER TO DIVISION 26 WIRING DEVICES SPECIFICATION FOR ADDITIONAL REQUIREMENTS FOR FLOOR BOXES. D. RACEWAY ROUTING SHALL BE INDICATED FOR ALL IN-SLAB CONDUITS, CABLE TRAYS AND OVERHEAD CONDUITS 2-INCHES AND LARGER, BASED ON FINAL COORDINATION WITH ALL OTHER TRADES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 6. ENLARGED PLANS: A. PROVIDE = 1-0 ENLARGED PLANS OF ALL COMMUNICATION ROOMS (AS APPLICABLE) INDICATING THE POSITION OF EQUIPMENT CABINETS AND/OR RACKS, WIRING TERMINALS, PATCH PANELS, GROUNDING EQUIPMENT, CABLE TRAY, FIBER AND COPPER TERMINATIONS, AND OTHER LOW VOLTAGE SYSTEMS EQUIPMENT LAYOUT WITHIN THE ROOMS. B. SHOP DRAWINGS SHALL CLEARLY INDICATE FINAL CONDUIT/RISER (CORE DRILL AND/OR BLOCK-OUT) LOCATIONS AND SIZES AS COORDINATED AND/OR CONFIRMED WITH STRUCTURAL ENGINEER AND ANY FIELD CONDITIONS THAT IMPACT PROPOSED LOCATION. C. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WHERE EQUIPMENT CLEARANCES MAY BE LIMITED, FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 7. DETAILS: DOCUMENT METHOD OF ATTACHMENT OF RACKS TO THE FLOOR AND LADDER TRAY SYSTEMS, METHOD OF ATTACHMENT OF WALL MOUNTED DISTRIBUTION FRAMES, GROUNDING DETAILS INDICATING GROUNDING METHOD FOR CABINETS, RACKS, CABLE TRAY, CABLE MANAGEMENT, AND POWER DETAILS FOR RACK MOUNTED POWER DISTRIBUTION. 8. ELEVATIONS: A. RACK ELEVATIONS (PRODUCED IN VISIO, ACAD, OR SIMILAR) INDICATING EXACT PLACEMENT OF PATCH PANELS, FIBER TERMINALS AND ENCLOSURES, VERTICAL AND HORIZONTAL CABLE MANAGERS, RACK MOUNTED POWER STRIPS OR DISTRIBUTION UNITS, EMPTY RACK-UNITS, ETC. B. WALL ELEVATIONS SHALL DETAIL ANY AND ALL KNOWN COMPONENTS TO BE MOUNTED ON THE WALLS, WHETHER THOSE ITEMS ARE PROVIDED BY CONTRACTOR PRODUCING SHOP DRAWINGS OR NOT. COMPONENTS SHALL INCLUDE, BUT NOT BE LIMITED TO, ELECTRICAL AND/OR FIRE ALARM PANELS, SECURITY PANELS, DISTRIBUTED ANTENNA SYSTEM (DAS), CATV, COMMUNICATION INFRASTRUCTURE DISTRIBUTION FRAMES WITH BLOCK SIZE, CABLE ROUTING, CABLE MANAGEMENT, PAIR COUNTS, METHOD OF ATTACHMENT, ETC. 9. DRAWING SCALE: SHOP DRAWINGS SHALL BE DRAWN TO SCALE AND COMPLETELY DIMENSIONED AS TO CLEARLY SHOW CONSTRUCTION DETAIL. 10. LABELING: PROVIDE DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, CABLES, OUTLETS, WIRING BLOCKS AND/OR PATCH PANELS, DEVICE FACEPLATES, ETC. 11. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO THE SPECIFICATION RESPONSE SECTION WITHIN THIS SPECIFICATION AND APPENDIX 2 FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 11853 | Review Response | Approved | 2021-03-05 | Michael Mazzocchi (ME Engineers) | Shaina Burris (Populous) |  |  | Info Exchange
| 15367 | Responded and Closed | Approved | 2021-03-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| 16591 | Sent | For Information Only | 2021-04-27 | Josh Dobken (Populous) | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Responded and Closed (Approved) to: Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Response (Approved) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 27 05 00-1.4 Common Work Results for Communications.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-15 |  | 27 05 00-1.4 Common Work Results for Communications.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-02-14 02:00 |  | 27 05 00-1.4 Common Work Results for Communications.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-08 02:00 |  | 27 05 00-1.4 - Common Work Results for Communications - ME Response_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-02-14 02:00 |  | 27 05 00-1.4 Common Work Results for Communications.pdf
27 05 00-006-00 | 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS | 27 05 00-006-00 Labeling | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-20 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-04 | 2020-05-06 | 17 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05414 | Received | For Review | 2020-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-04 | Submittal Number: 27 05 00-6.0 From: ELLA PILGRIM Final Due Date: 05/01/20 Subject: LABELING Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 07351 | Forwarded | For Review | 2020-04-17 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-24 | Submittal Number: 27 05 00-6.0 From: ELLA PILGRIM Final Due Date: 05/01/20 Subject: LABELING Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 05748 | Review Response | Approved as Noted | 2020-05-05 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  | Red markups on submittal are ME comments. | Info Exchange
| 07802 | Responded and Closed | Approved as Noted | 2020-05-06 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Abby Harrison (ME Engineers) Remarks: Red markups on submittal are ME comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-17 |  | 27 05 00-6.0 - Labeling.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-17 |  | 27 05 00-6.0 - Labeling.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-04-16 02:00 |  | 27 05 00-6.0 - Labeling.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-06 02:00 |  | 27 05 00-6.0 - Labeling_ME_POP.pdf
27 05 00-006-01 | 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS | 27 05 00-006-01 Labeling | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-03-02 | 2021-03-01 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11456 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-02 | Submittal Number: 27 05 00-6.1 From: ELLA PILGRIM Final Due Date: 03/02/21 Subject: LABELING Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 14837 | Forwarded | For Review | 2021-02-16 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-02-23 | Submittal Number: 27 05 00-6.1 From: ELLA PILGRIM Final Due Date: 03/02/21 Subject: LABELING Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 11727 | Review Response | Revise and Resubmit | 2021-02-25 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 15199 | Responded and Closed | Revise and Resubmit | 2021-03-01 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 27 05 00-6.1 - Labeling.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-15 |  | 27 05 00-6.1 - Labeling.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-02-15 |  | 27 05 00-6.1 - Labeling.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-01 |  | 27 05 00-6.1 - Labeling - ME_POP.pdf
27 05 00-006-02 | 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS | 27 05 00-006-02 Labeling | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Bryan Klote (Populous) |  |  |  | 2021-04-22 | 2021-04-27 | 20 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12489 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-22 | Submittal Number: 27 05 00-6.2 From: ELLA PILGRIM Final Due Date: 04/23/21 Subject: LABELING Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 16179 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-04-15 | Submittal Number: 27 05 00-6.2 From: ELLA PILGRIM Final Due Date: 04/23/21 Subject: LABELING Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 12662 | Review Response | Approved | 2021-04-18 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 16383 | Forwarded | For Review | 2021-04-20 | Populous SCA_CCA | Bryan Klote (Populous) |  | Submittal Number: 27 05 00-6.2 From: ELLA PILGRIM Final Due Date: 04/23/21 Subject: LABELING Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 16597 | Responded and Closed | Approved | 2021-04-27 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 27 05 00-6.2 - Labeling.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 27 05 00-6.2 - Labeling.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-04-08 |  | 27 05 00-6.2 - Labeling.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 27 05 00-6.2 - Labeling.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-27 02:00 |  | 27 05 00-6.2 - Labeling - MEE Response_POP.pdf
27 05 00-007-00 | 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS | 27 05 00-007-00 Patch Panels | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-03-02 | 2021-03-01 | 14 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-03-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11434 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-02 | Submittal Number: 27 05 00-7.0 From: ELLA PILGRIM Final Due Date: 03/02/21 Subject: PATCH PANELS Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 14803 | Forwarded | For Review | 2021-02-15 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-02-22 | Submittal Number: 27 05 00-7.0 From: ELLA PILGRIM Final Due Date: 03/02/21 Subject: PATCH PANELS Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 11726 | Review Response | Approved as Noted | 2021-02-25 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 15197 | Responded and Closed | Approved | 2021-03-01 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 27 05 00-7.0 - Patch Panels.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-15 |  | 27 05 00-7.0 - Patch Panels.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-02-15 |  | 27 05 00-7.0 - Patch Panels.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-01 |  | 27 05 00-7.0 - Patch Panels - ME_POP.pdf
27 05 00-008-00 | 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS | 27 05 00-008-00 Cable | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-08 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Brian Elwell (Idibri) |  |  |  | 2021-03-22 | 2021-03-30 | 23 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-03-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11829 | Received | For Review | 2021-03-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-22 | Submittal Number: 27 05 00-8.0 From: ELLA PILGRIM Final Due Date: 03/23/21 Subject: CABLE Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 15336 | Forwarded | For Review | 2021-03-08 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-03-15 | Submittal Number: 27 05 00-8.0 From: ELLA PILGRIM Final Due Date: 03/23/21 Subject: CABLE Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 15393 | Forwarded | For Review | 2021-03-09 | Populous SCA_CCA | Brian Elwell (Idibri) | 2021-03-16 | Submittal Number: 27 05 00-8.0 From: ELLA PILGRIM Final Due Date: 03/23/21 Subject: CABLE Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 12295 | Review Response | No Action Taken or Required | 2021-03-10 | Brian Elwell (Idibri) | Populous SCA_CCA |  | This is for ME to review. | Info Exchange
| 12304 | Review Response | Revise and Resubmit | 2021-03-29 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 15934 | Responded and Closed | Revise and Resubmit | 2021-03-30 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  | Response (Revise and Resubmit) from: Michael Mazzocchi (ME Engineers) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-07 |  | 27 05 00-8.0 - Cable.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-07 |  | 27 05 00-8.0 - Cable.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-06 02:00 |  | 27 05 00-8.0 - Cable.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-03-06 02:00 |  | 27 05 00-8.0 - Cable.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-03-07 |  | 27 05 00-8.0 - Cable.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-30 |  | 27 05 00-8.0 - Cable - ME_POP.pdf
27 05 00-008-01 | 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS | 27 05 00-008-01 Cable | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-08 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Bryan Klote (Populous) |  |  |  | 2021-04-22 | 2021-04-27 | 20 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12490 | Received | For Review | 2021-04-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-22 | Submittal Number: 27 05 00-8.1 From: ALYSSA SANDOVAL Final Due Date: 04/23/21 Subject: CABLE Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 16180 | Forwarded | For Review | 2021-04-08 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-04-15 | Submittal Number: 27 05 00-8.1 From: ALYSSA SANDOVAL Final Due Date: 04/23/21 Subject: CABLE Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 12661 | Review Response | Approved | 2021-04-18 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 16382 | Forwarded | For Review | 2021-04-20 | Populous SCA_CCA | Bryan Klote (Populous) |  | Submittal Number: 27 05 00-8.1 From: ALYSSA SANDOVAL Final Due Date: 04/23/21 Subject: CABLE Description: Spec Section: 27 05 00 - COMMON WORK RESULTS FOR COMMUNICATIONS Status: OPEN | Info Exchange
| 16596 | Responded and Closed | Approved | 2021-04-27 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 27 05 00-8.1 - Cable.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 27 05 00-8.1 - Cable.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-04-08 |  | 27 05 00-8.1 - Cable.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 27 05 00-8.1 - Cable.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-27 02:00 |  | 27 05 00-8.1 - Cable - MEE Response_POP.pdf
27 05 33-003-00 | 27 05 33 - TELECOMMUNICATIONS RACEWAYS AND BOXES | 27 05 33-003-00 Telecommunications Raceway Product Data | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-04 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2020-12-18 | 2020-12-22 | 19 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-12-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09911 | Received | For Review | 2020-12-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-18 | Submittal Number: 27 05 33-3.0 From: TRINA BOMONTI Final Due Date: 12/17/20 Subject: TELECOMMUNICATIONS RACEWAY PRODUCT DATA Description: 27-05-33 – TELECOMMUNICATIONS RACEWAYS & BOXES TABLE OF CONTENTS: ELECTRIC METALLIC TUBING (EMT) EMT CONDUIT FITTINGS INSULATING BUSHINGS SCHEDULE 40/SCHEDULE 80 CONDUIT Spec Section: 27 05 33 - TELECOMMUNICATIONS RACEWAYS AND BOXES Status: OPEN | Info Exchange
| 12991 | Forwarded | For Review | 2020-12-04 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2020-12-11 | Submittal Number: 27 05 33-3.0 From: TRINA BOMONTI Final Due Date: 12/17/20 Subject: TELECOMMUNICATIONS RACEWAY PRODUCT DATA Description: 27-05-33 – TELECOMMUNICATIONS RACEWAYS & BOXES TABLE OF CONTENTS: ELECTRIC METALLIC TUBING (EMT) EMT CONDUIT FITTINGS INSULATING BUSHINGS SCHEDULE 40/SCHEDULE 80 CONDUIT Spec Section: 27 05 33 - TELECOMMUNICATIONS RACEWAYS AND BOXES Status: OPEN | Info Exchange
| 10321 | Review Response | Approved as Noted | 2020-12-21 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 13484 | Responded and Closed | Approved as Noted | 2020-12-22 | Populous SCA_CCA | Mike Steele (CAA ICON / Strategy Advisory); Elliott Veazey (CAA ICON / Strategy Advisory); Danny Keim (M.A. Mortenson Company); Mike Tihista (CAA ICON / Strategy Advisory); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector... |  | Response (Approved as Noted) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-03 |  | 270533-003-0 DAS Raceways.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-03 |  | 270533-003-0 DAS Raceways.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-12-02 02:00 |  | 270533-003-0 DAS Raceways.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-22 02:00 |  | 270533-003-0 DAS Raceways- ME _pop.pdf
27 05 36-001-00 | 27 05 36 - CABLE TRAYS | 27 05 36-001-00 CABLE TRAYS - Product Data | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-18 | Review Response - Approved as Noted |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-12-04 08:00 | 2019-12-16 | 29 |  | Record Copies; Transfers; Submittals |  | 149 |  | 2019-12-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03233 | Received | For Review | 2019-11-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-12-04 08:00 | Submittal Number: 27 05 36-1.0 From: PATRICK KLEIN Final Due Date: 12/02/19 Subject: CABLE TRAYS - PRODUCT DATA Description: PRODUCT DATA : - 1. COMPLIANCE MATRIX: PROVIDE FULL SPECIFICATION COMPLIANCE MATRIX AS DESCRIBED IN THE SPECIFICATION RESPONSE SECTION OF THIS SPECIFICATION SECTION. 2. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 3. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL IDENTIFY EACH COMPONENT NAME, MANUFACTURER, AND SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. 4. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 5. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. SHOP DRAWINGS AND AS-BUILT DRAWINGS SHALL INCLUDE : - 1. FLOOR PLANS: PROVIDE SCALED BUILDING FLOOR PLAN DRAWINGS (WITH CURRENT REFLECTED CEILING PLAN LAYER SHOWN) BASED ON ARCHITECTURAL BACKGROUND INDICATING INSTALLATION OF CABLE TRAY SYSTEMS AND ACCESSORIES INCLUDING CLAMPS, BRACKETS, HANGER RODS, SPLICE PLATE CONNECTORS, EXPANSION JOINT ASSEMBLIES AND FITTINGS. PLANS SHALL SHOW ACCURATELY SCALED COMPONENTS, MOUNTING HEIGHTS/ELEVATIONS, AND SPATIAL RELATIONSHIPS (CLEARANCES) TO ADJACENT STRUCTURE AND EQUIPMENT, INCLUDING BUT NOT LIMITED TO, HVAC DUCTWORK, PIPING, AND LIGHT FIXTURES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 2. DETAILS: SUBMIT CABLE TRAY SUPPORT DETAIL DRAWINGS INDICATING INSTALLATION OF CABLE TRAY SYSTEMS AND ACCESSORIES INCLUDING CLAMPS, BRACKETS, HANGER RODS, SPLICE PLATE CONNECTORS, EXPANSION JOINT ASSEMBLIES AND FITTINGS, AND ALL GROUNDING COMPONENTS. 3. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. Spec Section: 27 05 36 - CABLE TRAYS Status: OPEN | Info Exchange
| 04671 | Forwarded | For Review | 2019-11-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-25 | Submittal Number: 27 05 36-1.0 From: PATRICK KLEIN Final Due Date: 12/02/19 Subject: CABLE TRAYS - PRODUCT DATA Description: PRODUCT DATA : - 1. COMPLIANCE MATRIX: PROVIDE FULL SPECIFICATION COMPLIANCE MATRIX AS DESCRIBED IN THE SPECIFICATION RESPONSE SECTION OF THIS SPECIFICATION SECTION. 2. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 3. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL IDENTIFY EACH COMPONENT NAME, MANUFACTURER, AND SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. 4. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 5. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. SHOP DRAWINGS AND AS-BUILT DRAWINGS SHALL INCLUDE : - 1. FLOOR PLANS: PROVIDE SCALED BUILDING FLOOR PLAN DRAWINGS (WITH CURRENT REFLECTED CEILING PLAN LAYER SHOWN) BASED ON ARCHITECTURAL BACKGROUND INDICATING INSTALLATION OF CABLE TRAY SYSTEMS AND ACCESSORIES INCLUDING CLAMPS, BRACKETS, HANGER RODS, SPLICE PLATE CONNECTORS, EXPANSION JOINT ASSEMBLIES AND FITTINGS. PLANS SHALL SHOW ACCURATELY SCALED COMPONENTS, MOUNTING HEIGHTS/ELEVATIONS, AND SPATIAL RELATIONSHIPS (CLEARANCES) TO ADJACENT STRUCTURE AND EQUIPMENT, INCLUDING BUT NOT LIMITED TO, HVAC DUCTWORK, PIPING, AND LIGHT FIXTURES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 2. DETAILS: SUBMIT CABLE TRAY SUPPORT DETAIL DRAWINGS INDICATING INSTALLATION OF CABLE TRAY SYSTEMS AND ACCESSORIES INCLUDING CLAMPS, BRACKETS, HANGER RODS, SPLICE PLATE CONNECTORS, EXPANSION JOINT ASSEMBLIES AND FITTINGS, AND ALL GROUNDING COMPONENTS. 3. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. Spec Section: 27 05 36 - CABLE TRAYS Status: OPEN | Info Exchange
| 04684 | Forwarded | For Review | 2019-11-18 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers) | 2019-11-25 | Submittal Number: 27 05 36-1.0 From: PATRICK KLEIN Final Due Date: 12/02/19 Subject: CABLE TRAYS - PRODUCT DATA Description: PRODUCT DATA : - 1. COMPLIANCE MATRIX: PROVIDE FULL SPECIFICATION COMPLIANCE MATRIX AS DESCRIBED IN THE SPECIFICATION RESPONSE SECTION OF THIS SPECIFICATION SECTION. 2. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 3. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL IDENTIFY EACH COMPONENT NAME, MANUFACTURER, AND SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. 4. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 5. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. SHOP DRAWINGS AND AS-BUILT DRAWINGS SHALL INCLUDE : - 1. FLOOR PLANS: PROVIDE SCALED BUILDING FLOOR PLAN DRAWINGS (WITH CURRENT REFLECTED CEILING PLAN LAYER SHOWN) BASED ON ARCHITECTURAL BACKGROUND INDICATING INSTALLATION OF CABLE TRAY SYSTEMS AND ACCESSORIES INCLUDING CLAMPS, BRACKETS, HANGER RODS, SPLICE PLATE CONNECTORS, EXPANSION JOINT ASSEMBLIES AND FITTINGS. PLANS SHALL SHOW ACCURATELY SCALED COMPONENTS, MOUNTING HEIGHTS/ELEVATIONS, AND SPATIAL RELATIONSHIPS (CLEARANCES) TO ADJACENT STRUCTURE AND EQUIPMENT, INCLUDING BUT NOT LIMITED TO, HVAC DUCTWORK, PIPING, AND LIGHT FIXTURES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 2. DETAILS: SUBMIT CABLE TRAY SUPPORT DETAIL DRAWINGS INDICATING INSTALLATION OF CABLE TRAY SYSTEMS AND ACCESSORIES INCLUDING CLAMPS, BRACKETS, HANGER RODS, SPLICE PLATE CONNECTORS, EXPANSION JOINT ASSEMBLIES AND FITTINGS, AND ALL GROUNDING COMPONENTS. 3. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. Spec Section: 27 05 36 - CABLE TRAYS Status: OPEN | Info Exchange
| 03648 | Review Response | Approved as Noted/Resubmit | 2019-12-15 | Abby Harrison (ME Engineers) | Shaina Burris (Populous) |  | See attached for submittal. Thanks, | Info Exchange
| 05161 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-16 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Abby Harrison (ME Engineers) Remarks: See attached for submittal. Thanks, | Info Exchange
| 05358 | Review Response | Approved as Noted | 2020-04-14 | Josh Dobken (Populous) | Josh Dobken (Populous) |  | Item does not require any resubmission, and is being revised to only approved as noted. See attached email between ME, Populous, and MAM. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-18 |  | 27 05 36-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-18 |  | 27 05 36-1.0 Product Data-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-18 |  | 27 05 36-1.0 Product Data-MAM.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2019-11-17 02:00 |  | 27 05 36-1.0 Product Data-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-16 02:00 |  | 27 05 36-1.0 Product Data-MAM-ME_POP.pdf
27 05 36-001-01 | 27 05 36 - CABLE TRAYS | 27 05 36-001-01 CABLE TRAYS - Product Data | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-07 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-21 | 2020-05-19 | 13 |  | Record Copies; Transfers; Submittals | 27 05 36-001-02 - 27 05 36-001-01 CABLE TRAYS - Product Data | 13 |  | 2020-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05756 | Received | For Review | 2020-05-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-21 | Submittal Number: 27 05 36-1.1 From: ELLA PILGRIM Final Due Date: 05/20/20 Subject: CABLE TRAYS - PRODUCT DATA Description: PRODUCT DATA : - 1. COMPLIANCE MATRIX: PROVIDE FULL SPECIFICATION COMPLIANCE MATRIX AS DESCRIBED IN THE SPECIFICATION RESPONSE SECTION OF THIS SPECIFICATION SECTION. 2. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 3. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL IDENTIFY EACH COMPONENT NAME, MANUFACTURER, AND SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. 4. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 5. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. SHOP DRAWINGS AND AS-BUILT DRAWINGS SHALL INCLUDE : - 1. FLOOR PLANS: PROVIDE SCALED BUILDING FLOOR PLAN DRAWINGS (WITH CURRENT REFLECTED CEILING PLAN LAYER SHOWN) BASED ON ARCHITECTURAL BACKGROUND INDICATING INSTALLATION OF CABLE TRAY SYSTEMS AND ACCESSORIES INCLUDING CLAMPS, BRACKETS, HANGER RODS, SPLICE PLATE CONNECTORS, EXPANSION JOINT ASSEMBLIES AND FITTINGS. PLANS SHALL SHOW ACCURATELY SCALED COMPONENTS, MOUNTING HEIGHTS/ELEVATIONS, AND SPATIAL RELATIONSHIPS (CLEARANCES) TO ADJACENT STRUCTURE AND EQUIPMENT, INCLUDING BUT NOT LIMITED TO, HVAC DUCTWORK, PIPING, AND LIGHT FIXTURES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 2. DETAILS: SUBMIT CABLE TRAY SUPPORT DETAIL DRAWINGS INDICATING INSTALLATION OF CABLE TRAY SYSTEMS AND ACCESSORIES INCLUDING CLAMPS, BRACKETS, HANGER RODS, SPLICE PLATE CONNECTORS, EXPANSION JOINT ASSEMBLIES AND FITTINGS, AND ALL GROUNDING COMPONENTS. 3. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. Spec Section: 27 05 36 - CABLE TRAYS Status: OPEN | Info Exchange
| 07818 | Forwarded | For Review | 2020-05-07 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-14 | Submittal Number: 27 05 36-1.1 From: ELLA PILGRIM Final Due Date: 05/20/20 Subject: CABLE TRAYS - PRODUCT DATA Description: PRODUCT DATA : - 1. COMPLIANCE MATRIX: PROVIDE FULL SPECIFICATION COMPLIANCE MATRIX AS DESCRIBED IN THE SPECIFICATION RESPONSE SECTION OF THIS SPECIFICATION SECTION. 2. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 3. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL IDENTIFY EACH COMPONENT NAME, MANUFACTURER, AND SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. COMPONENT LIST AND MANUFACTURER CUT-SHEETS SHALL BE COMPILED TO MATCH THE ORDER OF EACH APPENDIX. 4. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDIX. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. 5. PRODUCT SUBSTITUTIONS: THESE SPECIFICATIONS ARE INTENDED TO BE PERFORMANCE BASED, THUS ALL PRODUCTS LISTED IN EACH RESPECTIVE APPENDIX 1: EQUIPMENT SCHEDULES ARE BENCHMARK PRODUCTS. THE CONTRACTOR SHALL INCLUDE PRODUCTS FROM ONE OF THE PRE-APPROVED MANUFACTURERS AS NOTED IN THE APPENDIX. THE CONTRACTOR MAY SUBMIT (ASA PROPOSED ALTERNATE SOLUTION) SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. SHOP DRAWINGS AND AS-BUILT DRAWINGS SHALL INCLUDE : - 1. FLOOR PLANS: PROVIDE SCALED BUILDING FLOOR PLAN DRAWINGS (WITH CURRENT REFLECTED CEILING PLAN LAYER SHOWN) BASED ON ARCHITECTURAL BACKGROUND INDICATING INSTALLATION OF CABLE TRAY SYSTEMS AND ACCESSORIES INCLUDING CLAMPS, BRACKETS, HANGER RODS, SPLICE PLATE CONNECTORS, EXPANSION JOINT ASSEMBLIES AND FITTINGS. PLANS SHALL SHOW ACCURATELY SCALED COMPONENTS, MOUNTING HEIGHTS/ELEVATIONS, AND SPATIAL RELATIONSHIPS (CLEARANCES) TO ADJACENT STRUCTURE AND EQUIPMENT, INCLUDING BUT NOT LIMITED TO, HVAC DUCTWORK, PIPING, AND LIGHT FIXTURES. SHOP DRAWINGS SHALL CLEARLY INDICATE AREAS WITH CABLE TRAY CLEARANCE LIMITATIONS AND/OR OTHER CABLE ACCESS LIMITATIONS FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. 2. DETAILS: SUBMIT CABLE TRAY SUPPORT DETAIL DRAWINGS INDICATING INSTALLATION OF CABLE TRAY SYSTEMS AND ACCESSORIES INCLUDING CLAMPS, BRACKETS, HANGER RODS, SPLICE PLATE CONNECTORS, EXPANSION JOINT ASSEMBLIES AND FITTINGS, AND ALL GROUNDING COMPONENTS. 3. DOCUMENTATION: PROVIDE SUBMITTALS AND DOCUMENTATION AS REQUIRED BY THE PROJECT MANUAL (IN ADDITION TO ELECTRONIC COPIES) FOR REVIEW OR AS INDICATED IN DIVISION 1 GENERAL CONDITIONS. Spec Section: 27 05 36 - CABLE TRAYS Status: OPEN | Info Exchange
| 05940 | Review Response | Revise and Resubmit | 2020-05-19 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 08069 | Responded and Closed | Approved as Noted/Resubmit | 2020-05-19 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | REFER TO ME DISPOSITION SHEET FOR ITEMS TO BE RESUBMITTED Response (Revise and Resubmit) from: Abby Harrison (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-06 |  | 27 05 36-1.1 - Cable Trays.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-06 |  | 27 05 36-1.1 - Cable Trays.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-05-05 02:00 |  | 27 05 36-1.1 - Cable Trays.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-19 02:00 |  | 27 05 36-1.1 - Cable Trays_ME_pop.pdf
27 05 36-001-02 | 27 05 36 - CABLE TRAYS | 27 05 36-001-01 CABLE TRAYS - Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 27 05 36-001-01 - 27 05 36-001-01 CABLE TRAYS - Product Data | -1 | 2020-06-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-19 02:00 |  | 27 05 36-1.1 - Cable Trays_ME_pop.pdf
27 05 43-001-00 | 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 27 05 43-001-00 Communications Vault Product Data | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-05 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-07-19 | 2019-07-23 | 19 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2019-07-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01690 | Received | For Review | 2019-07-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-07-19 | Submittal Number: 27 05 43-1.0 From: PATRICK KLEIN Final Due Date: 07/17/19 Subject: COMMUNICATIONS VAULT PRODUCT DATA Description: Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 02769 | Forwarded | For Review | 2019-07-03 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers) | 2019-07-10 | Submittal Number: 27 05 43-1.0 From: PATRICK KLEIN Final Due Date: 07/17/19 Subject: COMMUNICATIONS VAULT PRODUCT DATA Description: Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 01852 | Review Response | Approved as Noted | 2019-07-23 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  | See attached for submittal response. | Info Exchange
| 02981 | Responded and Closed | Approved | 2019-07-23 | Populous SCA_CCA | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Abby Harrison (ME Engineers) Remarks: See attached for submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-03 |  | 27 05 43-1.0 Communications Vault Product Data-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-07-03 |  | 27 05 43-1.0 Communications Vault Product Data-MAM.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2019-07-02 02:00 |  | 27 05 43-1.0 Communications Vault Product Data-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-07-23 02:00 |  | 27 05 43-1.0 Communications Vault Product Data-MAM_ME_POP.pdf
27 05 43-002-00 | 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 27 05 43-002-00 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Shop Drawings | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-02-20 | 2020-02-26 | 21 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2020-02-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04230 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-20 | Submittal Number: 27 05 43-2.0 From: ELLA PILGRIM Final Due Date: 02/19/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. SITE PLAN: PROVIDE COMPLETE SITE PLAN SHOWING ALL EXISTING AND PROPOSED UTILITIES. MANHOLES, HAND HOLES, AND MAJOR RACEWAY 2-INCHES AND LARGER SHALL BE INDICATED. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE/HAND HOLE PLACEMENT AS COORDINATED WITH SERVICE PROVIDER, CIVIL ENGINEER, AND OTHER APPLICABLE TRADES. 2. DETAILS: A. DUCT BANK SECTIONS: PROVIDE DUCT BANK SECTION DRAWING FOR EACH UNIQUE LENGTH OF TRENCH. B. MANHOLES, PULLBOXES, AND HAND HOLES: PROVIDE DETAILS INDICATING: 1) CONDUIT SIZE AND ENTRY LOCATIONS 2) COVER DESIGN 3) RACKING TYPE AND LOCATIONS 4) GROUNDING DETAILS 3. ONE-LINE DRAWINGS: PROVIDE ONE-LINE DRAWINGS INDICATING CONNECTION TO EXISTING SITE INFRASTRUCTURE. Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 05859 | Forwarded | For Review | 2020-02-06 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers) | 2020-02-13 | Submittal Number: 27 05 43-2.0 From: ELLA PILGRIM Final Due Date: 02/19/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. SITE PLAN: PROVIDE COMPLETE SITE PLAN SHOWING ALL EXISTING AND PROPOSED UTILITIES. MANHOLES, HAND HOLES, AND MAJOR RACEWAY 2-INCHES AND LARGER SHALL BE INDICATED. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE/HAND HOLE PLACEMENT AS COORDINATED WITH SERVICE PROVIDER, CIVIL ENGINEER, AND OTHER APPLICABLE TRADES. 2. DETAILS: A. DUCT BANK SECTIONS: PROVIDE DUCT BANK SECTION DRAWING FOR EACH UNIQUE LENGTH OF TRENCH. B. MANHOLES, PULLBOXES, AND HAND HOLES: PROVIDE DETAILS INDICATING: 1) CONDUIT SIZE AND ENTRY LOCATIONS 2) COVER DESIGN 3) RACKING TYPE AND LOCATIONS 4) GROUNDING DETAILS 3. ONE-LINE DRAWINGS: PROVIDE ONE-LINE DRAWINGS INDICATING CONNECTION TO EXISTING SITE INFRASTRUCTURE. Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 04525 | Review Response | Revise and Resubmit | 2020-02-25 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  | CAN'T RUN INCOMING CONDUIT THROUGH AIR SHAFT. COULD RUN UNDERNEATH SHAFT FOOTINGS DIRECTLY INTO DEMARC ROOM TDR-3A - 03.05.05 (SUBJECT TO STRUCTURAL APPROVAL ON RUNNING UNDERNEATH FOOTINGS). OTHER OPTIONS WOULD INCLUDE RUNNING AROUND AIR SHAFT AND STAIRWELLS. | Info Exchange
| 06230 | Responded and Closed | Revise and Resubmit | 2020-02-26 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Abby Harrison (ME Engineers) Remarks: CAN'T RUN INCOMING CONDUIT THROUGH AIR SHAFT. COULD RUN UNDERNEATH SHAFT FOOTINGS DIRECTLY INTO DEMARC ROOM TDR-3A - 03.05.05 (SUBJECT TO STRUCTURAL APPROVAL ON RUNNING UNDERNEATH FOOTINGS). OTHER OPTIONS WOULD INCLUDE RUNNING AROUND AIR SHAFT AND STAIRWELLS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 27 05 43-2.0 - Underground Ducts, Raceways and Manholes.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-06 |  | 27 05 43-2.0 - Underground Ducts, Raceways and Manholes.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-02-05 02:00 |  | 27 05 43-2.0 - Underground Ducts, Raceways and Manholes.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-26 02:00 |  | 27 05 43-2.0 - Underground Ducts, Raceways and Manholes_ME_POP.pdf
27 05 43-002-01 | 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 27 05 43-002-01 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Shop Drawings | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-11 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist |  |  |  | 2020-03-25 | 2020-04-03 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-04-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04769 | Received | For Review | 2020-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-25 | Submittal Number: 27 05 43-2.1 From: ELLA PILGRIM Final Due Date: 03/25/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. SITE PLAN: PROVIDE COMPLETE SITE PLAN SHOWING ALL EXISTING AND PROPOSED UTILITIES. MANHOLES, HAND HOLES, AND MAJOR RACEWAY 2-INCHES AND LARGER SHALL BE INDICATED. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE/HAND HOLE PLACEMENT AS COORDINATED WITH SERVICE PROVIDER, CIVIL ENGINEER, AND OTHER APPLICABLE TRADES. 2. DETAILS: A. DUCT BANK SECTIONS: PROVIDE DUCT BANK SECTION DRAWING FOR EACH UNIQUE LENGTH OF TRENCH. B. MANHOLES, PULLBOXES, AND HAND HOLES: PROVIDE DETAILS INDICATING: 1) CONDUIT SIZE AND ENTRY LOCATIONS 2) COVER DESIGN 3) RACKING TYPE AND LOCATIONS 4) GROUNDING DETAILS 3. ONE-LINE DRAWINGS: PROVIDE ONE-LINE DRAWINGS INDICATING CONNECTION TO EXISTING SITE INFRASTRUCTURE. Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 06543 | Forwarded | For Review | 2020-03-11 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-03-18 | Submittal Number: 27 05 43-2.1 From: ELLA PILGRIM Final Due Date: 03/25/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. SITE PLAN: PROVIDE COMPLETE SITE PLAN SHOWING ALL EXISTING AND PROPOSED UTILITIES. MANHOLES, HAND HOLES, AND MAJOR RACEWAY 2-INCHES AND LARGER SHALL BE INDICATED. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE/HAND HOLE PLACEMENT AS COORDINATED WITH SERVICE PROVIDER, CIVIL ENGINEER, AND OTHER APPLICABLE TRADES. 2. DETAILS: A. DUCT BANK SECTIONS: PROVIDE DUCT BANK SECTION DRAWING FOR EACH UNIQUE LENGTH OF TRENCH. B. MANHOLES, PULLBOXES, AND HAND HOLES: PROVIDE DETAILS INDICATING: 1) CONDUIT SIZE AND ENTRY LOCATIONS 2) COVER DESIGN 3) RACKING TYPE AND LOCATIONS 4) GROUNDING DETAILS 3. ONE-LINE DRAWINGS: PROVIDE ONE-LINE DRAWINGS INDICATING CONNECTION TO EXISTING SITE INFRASTRUCTURE. Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 05214 | Review Response | Approved as Noted | 2020-04-03 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 07086 | Responded and Closed | Approved as Noted | 2020-04-03 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Abby Harrison (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 27 05 43-2.1 - Underground Ducts, Raceways and Manholes.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-11 |  | 27 05 43-2.1 - Underground Ducts, Raceways and Manholes.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-03-10 02:00 |  | 27 05 43-2.1 - Underground Ducts, Raceways and Manholes.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-03 02:00 |  | 27 05 43-2.1 - Underground Ducts, Raceways and Manholes_ME_POP.pdf
27 05 43-002-02 | 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 27 05 43-002-02 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Shop Drawings | Closed | Technology, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-28 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-05-12 | 2021-05-17 | 20 |  | Record Copies; Transfers; Submittals | 27 05 43-002-02-01 - 27 05 43-002-02 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Shop Drawings | 20 |  | 2021-05-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12824 | Received | For Review | 2021-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-12 | Submittal Number: 27 05 43-2.2 From: ELLA PILGRIM Final Due Date: 05/12/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. SITE PLAN: PROVIDE COMPLETE SITE PLAN SHOWING ALL EXISTING AND PROPOSED UTILITIES. MANHOLES, HAND HOLES, AND MAJOR RACEWAY 2-INCHES AND LARGER SHALL BE INDICATED. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE/HAND HOLE PLACEMENT AS COORDINATED WITH SERVICE PROVIDER, CIVIL ENGINEER, AND OTHER APPLICABLE TRADES. 2. DETAILS: A. DUCT BANK SECTIONS: PROVIDE DUCT BANK SECTION DRAWING FOR EACH UNIQUE LENGTH OF TRENCH. B. MANHOLES, PULLBOXES, AND HAND HOLES: PROVIDE DETAILS INDICATING: 1) CONDUIT SIZE AND ENTRY LOCATIONS 2) COVER DESIGN 3) RACKING TYPE AND LOCATIONS 4) GROUNDING DETAILS 3. ONE-LINE DRAWINGS: PROVIDE ONE-LINE DRAWINGS INDICATING CONNECTION TO EXISTING SITE INFRASTRUCTURE. Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 16601 | Forwarded | For Review | 2021-04-28 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-05-05 | Submittal Number: 27 05 43-2.2 From: ELLA PILGRIM Final Due Date: 05/12/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. SITE PLAN: PROVIDE COMPLETE SITE PLAN SHOWING ALL EXISTING AND PROPOSED UTILITIES. MANHOLES, HAND HOLES, AND MAJOR RACEWAY 2-INCHES AND LARGER SHALL BE INDICATED. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE/HAND HOLE PLACEMENT AS COORDINATED WITH SERVICE PROVIDER, CIVIL ENGINEER, AND OTHER APPLICABLE TRADES. 2. DETAILS: A. DUCT BANK SECTIONS: PROVIDE DUCT BANK SECTION DRAWING FOR EACH UNIQUE LENGTH OF TRENCH. B. MANHOLES, PULLBOXES, AND HAND HOLES: PROVIDE DETAILS INDICATING: 1) CONDUIT SIZE AND ENTRY LOCATIONS 2) COVER DESIGN 3) RACKING TYPE AND LOCATIONS 4) GROUNDING DETAILS 3. ONE-LINE DRAWINGS: PROVIDE ONE-LINE DRAWINGS INDICATING CONNECTION TO EXISTING SITE INFRASTRUCTURE. Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 13126 | Review Response | Approved as Noted/Resubmit | 2021-05-10 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  | SEE SWIFT COMMENTS. | Info Exchange
| 16902 | Forwarded | For Review | 2021-05-12 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-05-12 | Submittal Number: 27 05 43-2.2 From: ELLA PILGRIM Final Due Date: 05/12/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - SHOP DRAWINGS Description: SHOP DRAWINGS : - 1. SITE PLAN: PROVIDE COMPLETE SITE PLAN SHOWING ALL EXISTING AND PROPOSED UTILITIES. MANHOLES, HAND HOLES, AND MAJOR RACEWAY 2-INCHES AND LARGER SHALL BE INDICATED. SHOP DRAWINGS SHALL REPRESENT FINAL CONDUIT ROUTING AND MANHOLE/HAND HOLE PLACEMENT AS COORDINATED WITH SERVICE PROVIDER, CIVIL ENGINEER, AND OTHER APPLICABLE TRADES. 2. DETAILS: A. DUCT BANK SECTIONS: PROVIDE DUCT BANK SECTION DRAWING FOR EACH UNIQUE LENGTH OF TRENCH. B. MANHOLES, PULLBOXES, AND HAND HOLES: PROVIDE DETAILS INDICATING: 1) CONDUIT SIZE AND ENTRY LOCATIONS 2) COVER DESIGN 3) RACKING TYPE AND LOCATIONS 4) GROUNDING DETAILS 3. ONE-LINE DRAWINGS: PROVIDE ONE-LINE DRAWINGS INDICATING CONNECTION TO EXISTING SITE INFRASTRUCTURE. Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Email
| 13127 | Review Response | Revise and Resubmit | 2021-05-17 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | See attached | Info Exchange
| 16985 | Responded and Closed | Revise and Resubmit | 2021-05-17 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Michael Mazzocchi (ME Engineers) Remarks: SEE SWIFT COMMENTS. Response (Revise and Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-27 |  | 27 05 43-2.2 - Underground Ducts Raceways and Manholes.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-27 |  | 27 05 43-2.2 - Underground Ducts Raceways and Manholes.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-04-26 02:00 |  | 27 05 43-2.2 - Underground Ducts Raceways and Manholes.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-26 02:00 |  | 27 05 43-2.2 - Underground Ducts Raceways and Manholes.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-17 02:00 |  | 27 05 43-2.2 - Underground Ducts Raceways and Manholes - MEE Response - SWIFT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-17 02:00 |  | 27 05 43-2.2 - Underground Ducts Raceways and Manholes - MEE Response - SWIFT_pop.pdf
27 05 43-002-02-01 | 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 27 05 43-002-02 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 27 05 43-002-02 - 27 05 43-002-02 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Shop Drawings | -1 | 2021-05-31
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 02:00 |  | 27 05 43-2.2 - Underground Ducts Raceways and Manholes - MEE Response - SWIFT_pop.pdf
27 05 43-004-00 | 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 27 05 43-004-00 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Product Data | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-02 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2019-10-16 | 2019-10-11 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-10-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02640 | Received | For Review | 2019-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (Mortenson Construction) | 2019-10-16 | Submittal Number: 27 05 43-4.0 From: PATRICK KLEIN Final Due Date: 10/16/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: PRODUCT DATA : THIS SECTION DOES NOT HAVEA BENCHMARK PRODUCT APPENDIX, THUS CONTRACTOR SHALL SUBMIT PRODUCT DATA FOR ALL APPLICABLE PRODUCTS AS REQUIRED PER TECHNOLOGY DRAWINGS INCLUDING, BUT NOT LIMITED TO: 1. MANHOLES, PULL BOXES, AND HAND HOLES. 2. DUCT BANK MATERIALS, INCLUDING SPACERS AND MISCELLANEOUS COMPONENTS. 3. WARNING TAPE AND TRACER WIRE. 4. CONDUITS. 5. INNER-DUCTS Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 03949 | Forwarded | For Review | 2019-10-02 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers) | 2019-10-09 | Submittal Number: 27 05 43-4.0 From: PATRICK KLEIN Final Due Date: 10/16/19 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA Description: PRODUCT DATA : THIS SECTION DOES NOT HAVEA BENCHMARK PRODUCT APPENDIX, THUS CONTRACTOR SHALL SUBMIT PRODUCT DATA FOR ALL APPLICABLE PRODUCTS AS REQUIRED PER TECHNOLOGY DRAWINGS INCLUDING, BUT NOT LIMITED TO: 1. MANHOLES, PULL BOXES, AND HAND HOLES. 2. DUCT BANK MATERIALS, INCLUDING SPACERS AND MISCELLANEOUS COMPONENTS. 3. WARNING TAPE AND TRACER WIRE. 4. CONDUITS. 5. INNER-DUCTS Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 02738 | Review Response | Revise and Resubmit | 2019-10-11 | Abby Harrison (ME Engineers) | Josh Dobken (Populous) |  | See attached PDF for ME response. | Info Exchange
| 04074 | Responded and Closed | Revise and Resubmit | 2019-10-11 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-02 02:00 |  | 27 05 43-4.0 Product Data-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-10-02 02:00 |  | 27 05 43-4.0 Product Data-MAM.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2019-10-02 |  | 27 05 43-4.0 Product Data-MAM.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2019-10-11 |  | 27 05 43-4.0 Product Data-MAM_ME_POP.pdf
27 05 43-004-01 | 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES | 27 05 43-004-01 UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - Product Data and Shop Drawings | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-06 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-05-20 | 2020-05-21 | 16 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-05-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05750 | Received | For Review | 2020-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-20 | Submittal Number: 27 05 43-4.1 From: ELLA PILGRIM Final Due Date: 05/20/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA AND SHOP DRAWINGS Description: PRODUCT DATA : THIS SECTION DOES NOT HAVEA BENCHMARK PRODUCT APPENDIX, THUS CONTRACTOR SHALL SUBMIT PRODUCT DATA FOR ALL APPLICABLE PRODUCTS AS REQUIRED PER TECHNOLOGY DRAWINGS INCLUDING, BUT NOT LIMITED TO: 1. MANHOLES, PULL BOXES, AND HAND HOLES. 2. DUCT BANK MATERIALS, INCLUDING SPACERS AND MISCELLANEOUS COMPONENTS. 3. WARNING TAPE AND TRACER WIRE. 4. CONDUITS. 5. INNER-DUCTS Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 07806 | Forwarded | For Review | 2020-05-06 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers) | 2020-05-13 | Submittal Number: 27 05 43-4.1 From: ELLA PILGRIM Final Due Date: 05/20/20 Subject: UNDERGROUND DUCTS, RACEWAYS AND MANHOLES - PRODUCT DATA AND SHOP DRAWINGS Description: PRODUCT DATA : THIS SECTION DOES NOT HAVEA BENCHMARK PRODUCT APPENDIX, THUS CONTRACTOR SHALL SUBMIT PRODUCT DATA FOR ALL APPLICABLE PRODUCTS AS REQUIRED PER TECHNOLOGY DRAWINGS INCLUDING, BUT NOT LIMITED TO: 1. MANHOLES, PULL BOXES, AND HAND HOLES. 2. DUCT BANK MATERIALS, INCLUDING SPACERS AND MISCELLANEOUS COMPONENTS. 3. WARNING TAPE AND TRACER WIRE. 4. CONDUITS. 5. INNER-DUCTS Spec Section: 27 05 43 - UNDERGROUND DUCTS, RACEWAYS AND MANHOLES Status: OPEN | Info Exchange
| 05980 | Review Response | Approved | 2020-05-19 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 08118 | Responded and Closed | Approved | 2020-05-21 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Abby Harrison (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-06 |  | 27 05 43-4.1 - Underground Ducts Raceways and Manholes.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-06 |  | 27 05 43-4.1 - Underground Ducts Raceways and Manholes.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-05-05 02:00 |  | 27 05 43-4.1 - Underground Ducts Raceways and Manholes.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-21 02:00 |  | 27 05 43-4.1 - Underground Ducts Raceways and Manholes_ME-pop.pdf
27 13 23-001-00 | 27 13 23 - COMMUNICATIONS OPTICAL FIBER BACKBONE CABLING | 27 13 23-001-00 Armored Fiber Clamp | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-23 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-05-07 | 2021-05-04 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12727 | Received | For Review | 2021-04-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-07 | Submittal Number: 27 13 23-1.0 From: ELLA PILGRIM Final Due Date: 05/07/21 Subject: ARMORED FIBER CLAMP Description: Spec Section: 27 13 23 - COMMUNICATIONS OPTICAL FIBER BACKBONE CABLING Status: OPEN | Info Exchange
| 16453 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-04-29 | Submittal Number: 27 13 23-1.0 From: ELLA PILGRIM Final Due Date: 05/07/21 Subject: ARMORED FIBER CLAMP Description: Spec Section: 27 13 23 - COMMUNICATIONS OPTICAL FIBER BACKBONE CABLING Status: OPEN | Info Exchange
| 12929 | Review Response | Approved | 2021-05-03 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 16712 | Responded and Closed | Approved | 2021-05-04 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-22 |  | 27 13 23-1.0 - Armored Fiber Clamp.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-22 |  | 27 13 23-1.0 - Armored Fiber Clamp.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-04-21 02:00 |  | 27 13 23-1.0 - Armored Fiber Clamp.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-04 02:00 |  | 27 13 23-1.0 - Armored Fiber Clamp - MEE Response_POP.pdf
27 15 00-001-00 | 27 15 00 - COMMUNICATIONS HORIZONTAL CABLING | 27 15 00-001-00 Horizontal Cabling | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-23 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2020-12-09 | 2020-12-29 | 37 |  | Record Copies; Transfers; Submittals |  | 30 |  | 2020-12-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09660 | Received | For Review | 2020-11-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-09 | Submittal Number: 27 15 00-1.0 From: ELLA PILGRIM Final Due Date: 12/09/20 Subject: HORIZONTAL CABLING Description: PLEASE REVIEW. Spec Section: 27 15 00 - COMMUNICATIONS HORIZONTAL CABLING Status: OPEN | Info Exchange
| 12711 | Forwarded | For Review | 2020-11-23 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2020-11-30 | Submittal Number: 27 15 00-1.0 From: ELLA PILGRIM Final Due Date: 12/09/20 Subject: HORIZONTAL CABLING Description: PLEASE REVIEW. Spec Section: 27 15 00 - COMMUNICATIONS HORIZONTAL CABLING Status: OPEN | Info Exchange
| 10360 | Review Response | Approved as Noted | 2020-12-22 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 13536 | Responded and Closed | Approved as Noted | 2020-12-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-21 |  | 27 15 00-1.0 - Horizontal Cabling.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-21 |  | 27 15 00-1.0 - Horizontal Cabling.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-11-21 |  | 27 15 00-1.0 - Horizontal Cabling.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-29 |  | 27 15 00-1.0 - Horizontal Cabling_ME_POP.pdf
27 15 00-002-00 | 27 15 00 - COMMUNICATIONS HORIZONTAL CABLING | 27 15 00-002-00 19155-S0043 O&M Communication Horizontal Cabling | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-30 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Nick Theimer (ME Engineers), Brian Elwell (Idibri), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-09-13 | 2021-09-21 | 23 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14528 | Received | For Review | 2021-08-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-13 | Submittal Number: 27 15 00-2.0 From: BINH DUONG Final Due Date: 09/08/21 Subject: 19155-S0043 O&M COMMUNICATION HORIZONTAL CABLING Description: SUBMITTAL OVERVIEW: OPERATION & MAINTENANCE MANUALS PER SUB-CONTRACTOR - EZ INTERFACE Spec Section: 27 15 00 - COMMUNICATIONS HORIZONTAL CABLING Status: OPEN | Info Exchange
| 18729 | Forwarded | For Review | 2021-08-31 | Populous SCA_CCA | Bryan Klote (Populous); Nick Theimer (ME Engineers); Brian Elwell (Idibri); Michael Mazzocchi (ME Engineers) | 2021-09-06 | Submittal Number: 27 15 00-2.0 From: BINH DUONG Final Due Date: 09/08/21 Subject: 19155-S0043 O&M COMMUNICATION HORIZONTAL CABLING Description: SUBMITTAL OVERVIEW: OPERATION & MAINTENANCE MANUALS PER SUB-CONTRACTOR - EZ INTERFACE Spec Section: 27 15 00 - COMMUNICATIONS HORIZONTAL CABLING Status: OPEN | Info Exchange
| 14542 | Review Response | No Action Taken or Required | 2021-08-31 | Brian Elwell (Idibri) | Populous SCA_CCA |  | This is for ME to review. | Info Exchange
| 14684 | Review Response | Approved | 2021-09-21 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 14685 | Review Response | Approved as Noted | 2021-09-21 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18938 | Responded and Closed | Approved as Noted | 2021-09-21 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Michael Mazzocchi (ME Engineers) Remarks: Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-30 02:00 |  | 271500-02-0 O&M Communication Horizontal Cabling.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-30 02:00 |  | 271500-02-0 O&M Communication Horizontal Cabling.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-08-30 02:00 |  | 271500-02-0 O&M Communication Horizontal Cabling.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-08-30 |  | 271500-02-0 O&M Communication Horizontal Cabling.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-09-21 |  | 271500-02-0 O&M Communication Horizontal Cabling - ME_POPpdf.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-30 |  | 271500-02-0 O&M Communication Horizontal Cabling.pdf
27 15 00-003-00 | 27 15 00 - COMMUNICATIONS HORIZONTAL CABLING | 27 15 00-003-00 Valley - Final Test Reports | Open | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-10-01 | Forwarded - For Review |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) | 2021-10-08 | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  | 2021-10-15 |  | 7 |  | Record Copies; Transfers; Submittals |  | 7
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14768 | Received | For Review | 2021-10-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ella Pilgrim (Mortenson Construction) | 2021-10-15 | Submittal Number: 27 15 00-3.0 From: ELLA PILGRIM Final Due Date: 10/08/21 Subject: VALLEY - FINAL TEST REPORTS Description: Spec Section: 27 15 00 - COMMUNICATIONS HORIZONTAL CABLING Status: OPEN | Info Exchange
| 19040 | Forwarded | For Review | 2021-10-01 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-10-08 | Submittal Number: 27 15 00-3.0 From: ELLA PILGRIM Final Due Date: 10/08/21 Subject: VALLEY - FINAL TEST REPORTS Description: Spec Section: 27 15 00 - COMMUNICATIONS HORIZONTAL CABLING Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-30 |  | 27 15 00-3.0 - Valley - Final Test Reports.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-30 |  | 27 15 00-3.0 - Valley - Final Test Reports.pdf
27 15 00-006-00 |  | 27 15 00-006-00 Cochran - Final Test Reports | Open | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-10-05 | Forwarded - For Review |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) | 2021-10-11 | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  | 2021-10-19 |  | 3 |  | Record Copies; Transfers; Submittals |  | 4
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14775 | Received | For Review | 2021-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ella Pilgrim (Mortenson Construction) | 2021-10-19 | Submittal Number: 27 15 00-6.0 From: ELLA PILGRIM Final Due Date: 11/03/21 Subject: COCHRAN - FINAL TEST REPORTS Description: Spec Section: 27 15 00 - COMMUNICATIONS HORIZONTAL CABLING Status: OPEN | Info Exchange
| 19046 | Forwarded | For Review | 2021-10-04 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-10-11 | Submittal Number: 27 15 00-6.0 From: ELLA PILGRIM Final Due Date: 11/03/21 Subject: COCHRAN - FINAL TEST REPORTS Description: Spec Section: 27 15 00 - COMMUNICATIONS HORIZONTAL CABLING Status: OPEN | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-10-04 |  | 27 15 00-6.0 Cochran - Final Test Reports.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-10-04 |  | 27 15 00-6.0 Cochran - Final Test Reports.pdf
27 21 00-001-00 | 27 21 00 - ENTERPRISE NETWORK SWITCHING AND ROUTING SYSTEM | 27 21 00-001-00 NETWORK SWITCHING AND ROUTING SYSTEM - Shop Drawings, Product Data, Coordination Data, Compliance Matrix, and Bill of Materials | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-14 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2020-10-02 | 2020-10-21 | 38 |  | Record Copies; Transfers; Submittals | 27 21 00-001-01 - 27 21 00-001-00 NETWORK SWITCHING AND ROUTING SYSTEM - Shop Drawings, Product Data, Coordination Data, Compliance Matrix, and Bill of Materials | 35 |  | 2020-10-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08116 | Received | For Review | 2020-09-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-02 | Submittal Number: 27 21 00-1.0 From: ELLA PILGRIM Final Due Date: 09/28/20 Subject: NETWORK SWITCHING AND ROUTING SYSTEM - SHOP DRAWINGS, PRODUCT DATA, COORDINATION DATA, COMPLIANCE MATRIX, AND BILL OF MATERIALS Description: WITHIN 15 DAYS AFTER AWARD OF CONTRACT OR AS DICTATED BY THE CONSTRUCTION SCHEDULE- (WHICHEVER PERIOD OF TIME IS SHORTER), THE CONTRACTOR SHALL SUBMIT PRE-DEPLOYMENT SUBMITTALS CONSISTING OF PRODUCT DATA, COMPLIANCE MATRIX AND SHOP DRAWINGS FOR OWNER AND ENGINEER REVIEW. PARTIAL SUBMITTALS WILL NOT BE ACCEPTED WITHOUT PRIOR WRITTEN APPROVAL FROM THE ARCHITECT. COORDINATE ALL SUBMITTAL DATES WITH CONSTRUCTION MANAGER. PRODUCT DATA : THE DATA NETWORK SYSTEM PRODUCT DATA SUBMITTAL SHALL BE SUBMITTED PRIOR TO STARTING ANY WORK FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. INFORMATION SHALL INCLUDE DETAILED MANUFACTURER'S SPECIFICATIONS FOR EACH COMPONENT TO BE INSTALLED. SUBMITTAL SHALL INCLUDEA LIST EVERY COMPONENT WITH MANUFACTURERS PART NUMBERS REFERENCED. MANUFACTURER DATA SHEETS WITH FEATURES, OPTIONS, RATINGS, AND PERFORMANCE. PRODUCT NUMBERS AND OPTIONS TO BE USED SHALL BE HIGHLIGHTED WITH COLOR MARKER. 1. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL IDENTIFY EACH COMPONENT NAME, MANUFACTURER, AND SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. EACH COMPONENT ON SHOP DRAWINGS, ELEVATIONS AND ONE-LINES SHALL SHARE THE SAME NAMING CONVENTION. 2. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR OR CLEARLY UNDERLINED ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. CUT SHEETS SHALL BE SUBMITTED IN THE SAME ORDER OF THE COMPONENT LIST. 3. PRODUCT SUBSTITUTIONS: THIS SPECIFICATION IS INTENDED TO BE PERFORMANCE BASED, THUS REQUIREMENTS AND PRODUCTS NOTED ARE BENCHMARKS. THE CONTRACTOR MAY SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. 4. SCHEDULE: A DETAILED SCHEDULE SHALL BE SUBMITTED WITH THE PREFABRICATION SUBMITTALS. THE SCHEDULE SHALL INCLUDE THE EXPECTED TIMELINES, FOR ORDERING, SHIPPING, BURN-IN, CONFIGURATION, INSTALLATION, ACCEPTANCE, AND TRAINING. SCHEDULE SHALL BE PRESENTED IN GANTT CHART FORMAT. DEPENDENCIES ON WORK BEING COMPLETED BY OTHERS SHALL BE CLEARLY DEFINED ON THE SCHEDULE. THE SCHEDULE SHALL BE COORDINATED WITH THE CONSTRUCTION MANAGER TO INCLUDE ALL CRITICAL PATH CONSTRUCTION DEADLINES IMPACTING THE DEPLOYMENT OF THE DATA NETWORK. THIS SHALL TAKE INTO ACCOUNT FINAL TESTING AND TURN OVER TO TAKE PLACE BEFORE THE OPENING OF THE BUILDING. 5. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 6. PRODUCT CERTIFICATES: SIGNED BY MANUFACTURERS OF SYSTEMS CERTIFYING THAT PRODUCTS FURNISHED COMPLY WITH REQUIREMENTS. 7. INSTALLER CERTIFICATES: PROVIDE MANUFACTURER CERTIFICATION SIGNED BY MANUFACTURER CERTIFYING THAT INSTALLERS HAVE BEEN TRAINED TO INSTALL ALL COMPONENTS OF THE SYSTEM AND COMPLY WITH MANUFACTURERS REQUIREMENTS. COORDINATION DATA : A DETAILED EQUIPMENT AND COMPONENT SCHEDULE WITH SUPPORTING MANUFACTURER CUT-SHEETS SHALL BE DEVELOPED FOR ALL EQUIPMENT, COMPONENTS AND OPTIONS FOR ARCHITECTURAL, ENGINEERING, AND CONSTRUCTION COORDINATION. THESE DOCUMENTS SHALL INCLUDE ELECTRICAL REQUIREMENTS (VOLTS, PHASE, AMPS, POWER CONSUMPTION, RECEPTACLE CONFIGURATION, ETC.), UPS REQUIREMENTS, HEAT DISSIPATION, TEMPERATURE OPERATING RANGE, TARGET OPERATING TEMPERATURE, PHYSICAL EQUIPMENT SIZES (LXWXH), EQUIPMENT DEPLOYMENT WEIGHT, EQUIPMENT CONFIGURATIONS FOR OWNER REVIEW, ETC. SHOP DRAWINGS : THE DATA NETWORK SHOP DRAWINGS SHALL BE SUBMITTED PRIOR TO ORDERING OF ANY EQUIPMENT AND STARTING OF ANY WORK. SHOP DRAWINGS SHALL BE SUBMITTED FOR REVIEW BY OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, SHOP DRAWINGS SHALL BE USED FOR COORDINATION WITH CONSTRUCTION MANAGER AND TRADES IMPACTED BY THIS INSTALLER. INFORMATION SHALL INCLUDE ALL DRAWINGS NECESSARY TO PRESENT INSTALLATION INTENT INCLUDING DIAGRAMS, PLANS, ENLARGED PLANS, ELEVATIONS, SECTIONS, DETAILS, AND INTERFACE TO OTHER WORK OR SYSTEMS. 1. LEGEND SHEET: PROVIDE DRAWINGS INCLUDING DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS. 2. NETWORK TOPOLOGY DIAGRAM: PROVIDED DRAWING OF ALL MAJOR COMPONENTS LOCATED IN MAIN COMMUNICATIONS ROOM, AND EACH INTERMEDIATE COMMUNICATIONS ROOM. DRAWINGS SHALL INCLUDE RELEVANT INFORMATION SUCH AS ROOM NUMBERS, EQUIPMENT NUMBER AND REFERENCES, UPLINKS, EQUIPMENT LINKS, BANDWIDTH, PANEL NUMBERS, AND UPLINK BANDWIDTHS. 3. ONE-LINE DIAGRAMS: PROVIDE DRAWINGS THAT INDICATE ALL EQUIPMENT BEING INTERCONNECTED, BACKBONE UPLINKS BETWEEN ACCESS LAYER SWITCHES, CORE SWITCHES, AND EXISTING CORE SWITCHES, ALL EQUIPMENT AND LOCATIONS. DRAWINGS SHALL INCLUDE RELEVANT INFORMATION SUCH AS ROOM NUMBERS, EQUIPMENT NUMBER AND REFERENCES, PANEL NUMBERS, AND UPLINK BANDWIDTHS. 4. FLOOR PLANS: PROVIDE SCALED PLAN DRAWINGS BASED ON ARCHITECTURAL BACKGROUND INDICATING EQUIPMENT AND LOCATIONS. DRAWINGS SHALL INCLUDE ALL RELEVANT INFORMATION SUCH AS ROOM NUMBERS, EQUIPMENT NUMBERS AND REFERENCES, PATCH PANEL NUMBERS, ETC. 5. ENLARGED PLANS: PROVIDE ENLARGED SCALED PLAN DRAWINGS FOR EQUIPMENT LAYOUTS IN COMMUNICATIONS ROOMS. EQUIPMENT SHALL BE CLEARLY LABELED INCLUDING NUMBERS AND REFERENCES. 6. ELEVATIONS: PROVIDE SCALED DRAWINGS FOR ELEVATIONS OF ALL EQUIPMENT LAYOUTS IN COMMUNICATIONS ROOMS, ON WALLS, IN RACKS, AND IN CABINETS. EQUIPMENT SHALL BE CLEARLY LABELED INCLUDING MODEL NUMBERS AND LABELING REFERENCES. 7. DETAILS: PROVIDE DETAIL DRAWINGS AS REQUIRED TO SHOW ANY INSTALLATION OR COMPONENT CONFIGURATIONS THAT REQUIRE GREATER DETAIL. 8. LABELING: PROVIDED DOCUMENTATION OF ALL EQUIPMENT AND COMPONENT LABELING, ETC. 9. SCHEDULE: A DETAILED SCHEDULE SHALL BE SUBMITTED WITH THE SHOP DRAWINGS. THE SCHEDULE SHALL INCLUDE THE EXPECTED TIMELINES, FOR ORDERING, SHIPPING, BURN-IN, CONFIGURATION, INSTALLATION, ACCEPTANCE, AND TRAINING. THE SCHEDULE SHALL BE COORDINATED WITH THE CONSTRUCTION MANAGER. REFER TO SECTION ABOVE FOR ADDITIONAL REQUIREMENTS RELATED TO SCHEDULING. COMPLIANCE MATRIX : PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. ANY DEVIATIONS SHALL BE FULLY EXPLAINED INCLUDING PROPOSED CHANGE. REFER TO SECTION 1.13 BID INFORMATION SECTION LATER IN THIS SPECIFICATION FOR ADDITIONAL REQUIREMENTS. BILL OF MATERIALS : - 1. PROVIDEA DETAILED BILL OF MATERIALS INCLUDING ALL EQUIPMENT, CABLES, COMPONENTS, FIRMWARE/SOFTWARE, AND OTHER OPTIONS. 2. INFORMATION SHALL BE LISTED IN SPECIFIC CATEGORIES ACCORDING TO EQUIPMENT TYPE AND INCLUDE A BASIC DESCRIPTION, QUANTITIES, RETAIL PRICE, EXTENDED PRICE, TOTAL PRICE, LABOR HOURS, LABOR COSTS, ETC. 3. LIST ALL EQUIPMENT ALTERNATES SEPARATELY AT END OF REPORT. THIS SHOULD INCLUDE ANY ADDS AND DEDUCT ALTERNATES. 4. CONTRACTOR SHALL REFER TO WARRANTY AND MAINTENANCE SECTIONS OF THE SPECIFICATION BELOW. CONTRACTOR SHALL LIST ALL EQUIPMENT MAINTENANCE AND SUPPORT ITEMS SEPARATELY AT END OF BILL OF MATERIALS BROKEN OUT IN THE SAME CATEGORIES AS THE REST OF THE EQUIPMENT. 5. PROVIDE UNIT COST FOR EACH PIECE OF EQUIPMENT, ACCESSORIES, AND LABOR SO THAT THE OWNER MAY SELECT THAT EQUIPMENT DURING THE PROJECT TO MEET EXPANDING OR DECLINING REQUIREMENTS. 6. REFER TO SECTION 1.13 BID INFORMATION SECTION LATER IN THIS SPECIFICATION FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 21 00 - ENTERPRISE NETWORK SWITCHING AND ROUTING SYSTEM Status: OPEN | Info Exchange
| 10784 | Forwarded | For Review | 2020-09-15 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-09-22 | Submittal Number: 27 21 00-1.0 From: ELLA PILGRIM Final Due Date: 09/28/20 Subject: NETWORK SWITCHING AND ROUTING SYSTEM - SHOP DRAWINGS, PRODUCT DATA, COORDINATION DATA, COMPLIANCE MATRIX, AND BILL OF MATERIALS Description: WITHIN 15 DAYS AFTER AWARD OF CONTRACT OR AS DICTATED BY THE CONSTRUCTION SCHEDULE- (WHICHEVER PERIOD OF TIME IS SHORTER), THE CONTRACTOR SHALL SUBMIT PRE-DEPLOYMENT SUBMITTALS CONSISTING OF PRODUCT DATA, COMPLIANCE MATRIX AND SHOP DRAWINGS FOR OWNER AND ENGINEER REVIEW. PARTIAL SUBMITTALS WILL NOT BE ACCEPTED WITHOUT PRIOR WRITTEN APPROVAL FROM THE ARCHITECT. COORDINATE ALL SUBMITTAL DATES WITH CONSTRUCTION MANAGER. PRODUCT DATA : THE DATA NETWORK SYSTEM PRODUCT DATA SUBMITTAL SHALL BE SUBMITTED PRIOR TO STARTING ANY WORK FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. INFORMATION SHALL INCLUDE DETAILED MANUFACTURER'S SPECIFICATIONS FOR EACH COMPONENT TO BE INSTALLED. SUBMITTAL SHALL INCLUDEA LIST EVERY COMPONENT WITH MANUFACTURERS PART NUMBERS REFERENCED. MANUFACTURER DATA SHEETS WITH FEATURES, OPTIONS, RATINGS, AND PERFORMANCE. PRODUCT NUMBERS AND OPTIONS TO BE USED SHALL BE HIGHLIGHTED WITH COLOR MARKER. 1. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL IDENTIFY EACH COMPONENT NAME, MANUFACTURER, AND SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. EACH COMPONENT ON SHOP DRAWINGS, ELEVATIONS AND ONE-LINES SHALL SHARE THE SAME NAMING CONVENTION. 2. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR OR CLEARLY UNDERLINED ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. CUT SHEETS SHALL BE SUBMITTED IN THE SAME ORDER OF THE COMPONENT LIST. 3. PRODUCT SUBSTITUTIONS: THIS SPECIFICATION IS INTENDED TO BE PERFORMANCE BASED, THUS REQUIREMENTS AND PRODUCTS NOTED ARE BENCHMARKS. THE CONTRACTOR MAY SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. 4. SCHEDULE: A DETAILED SCHEDULE SHALL BE SUBMITTED WITH THE PREFABRICATION SUBMITTALS. THE SCHEDULE SHALL INCLUDE THE EXPECTED TIMELINES, FOR ORDERING, SHIPPING, BURN-IN, CONFIGURATION, INSTALLATION, ACCEPTANCE, AND TRAINING. SCHEDULE SHALL BE PRESENTED IN GANTT CHART FORMAT. DEPENDENCIES ON WORK BEING COMPLETED BY OTHERS SHALL BE CLEARLY DEFINED ON THE SCHEDULE. THE SCHEDULE SHALL BE COORDINATED WITH THE CONSTRUCTION MANAGER TO INCLUDE ALL CRITICAL PATH CONSTRUCTION DEADLINES IMPACTING THE DEPLOYMENT OF THE DATA NETWORK. THIS SHALL TAKE INTO ACCOUNT FINAL TESTING AND TURN OVER TO TAKE PLACE BEFORE THE OPENING OF THE BUILDING. 5. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 6. PRODUCT CERTIFICATES: SIGNED BY MANUFACTURERS OF SYSTEMS CERTIFYING THAT PRODUCTS FURNISHED COMPLY WITH REQUIREMENTS. 7. INSTALLER CERTIFICATES: PROVIDE MANUFACTURER CERTIFICATION SIGNED BY MANUFACTURER CERTIFYING THAT INSTALLERS HAVE BEEN TRAINED TO INSTALL ALL COMPONENTS OF THE SYSTEM AND COMPLY WITH MANUFACTURERS REQUIREMENTS. COORDINATION DATA : A DETAILED EQUIPMENT AND COMPONENT SCHEDULE WITH SUPPORTING MANUFACTURER CUT-SHEETS SHALL BE DEVELOPED FOR ALL EQUIPMENT, COMPONENTS AND OPTIONS FOR ARCHITECTURAL, ENGINEERING, AND CONSTRUCTION COORDINATION. THESE DOCUMENTS SHALL INCLUDE ELECTRICAL REQUIREMENTS (VOLTS, PHASE, AMPS, POWER CONSUMPTION, RECEPTACLE CONFIGURATION, ETC.), UPS REQUIREMENTS, HEAT DISSIPATION, TEMPERATURE OPERATING RANGE, TARGET OPERATING TEMPERATURE, PHYSICAL EQUIPMENT SIZES (LXWXH), EQUIPMENT DEPLOYMENT WEIGHT, EQUIPMENT CONFIGURATIONS FOR OWNER REVIEW, ETC. SHOP DRAWINGS : THE DATA NETWORK SHOP DRAWINGS SHALL BE SUBMITTED PRIOR TO ORDERING OF ANY EQUIPMENT AND STARTING OF ANY WORK. SHOP DRAWINGS SHALL BE SUBMITTED FOR REVIEW BY OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, SHOP DRAWINGS SHALL BE USED FOR COORDINATION WITH CONSTRUCTION MANAGER AND TRADES IMPACTED BY THIS INSTALLER. INFORMATION SHALL INCLUDE ALL DRAWINGS NECESSARY TO PRESENT INSTALLATION INTENT INCLUDING DIAGRAMS, PLANS, ENLARGED PLANS, ELEVATIONS, SECTIONS, DETAILS, AND INTERFACE TO OTHER WORK OR SYSTEMS. 1. LEGEND SHEET: PROVIDE DRAWINGS INCLUDING DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS. 2. NETWORK TOPOLOGY DIAGRAM: PROVIDED DRAWING OF ALL MAJOR COMPONENTS LOCATED IN MAIN COMMUNICATIONS ROOM, AND EACH INTERMEDIATE COMMUNICATIONS ROOM. DRAWINGS SHALL INCLUDE RELEVANT INFORMATION SUCH AS ROOM NUMBERS, EQUIPMENT NUMBER AND REFERENCES, UPLINKS, EQUIPMENT LINKS, BANDWIDTH, PANEL NUMBERS, AND UPLINK BANDWIDTHS. 3. ONE-LINE DIAGRAMS: PROVIDE DRAWINGS THAT INDICATE ALL EQUIPMENT BEING INTERCONNECTED, BACKBONE UPLINKS BETWEEN ACCESS LAYER SWITCHES, CORE SWITCHES, AND EXISTING CORE SWITCHES, ALL EQUIPMENT AND LOCATIONS. DRAWINGS SHALL INCLUDE RELEVANT INFORMATION SUCH AS ROOM NUMBERS, EQUIPMENT NUMBER AND REFERENCES, PANEL NUMBERS, AND UPLINK BANDWIDTHS. 4. FLOOR PLANS: PROVIDE SCALED PLAN DRAWINGS BASED ON ARCHITECTURAL BACKGROUND INDICATING EQUIPMENT AND LOCATIONS. DRAWINGS SHALL INCLUDE ALL RELEVANT INFORMATION SUCH AS ROOM NUMBERS, EQUIPMENT NUMBERS AND REFERENCES, PATCH PANEL NUMBERS, ETC. 5. ENLARGED PLANS: PROVIDE ENLARGED SCALED PLAN DRAWINGS FOR EQUIPMENT LAYOUTS IN COMMUNICATIONS ROOMS. EQUIPMENT SHALL BE CLEARLY LABELED INCLUDING NUMBERS AND REFERENCES. 6. ELEVATIONS: PROVIDE SCALED DRAWINGS FOR ELEVATIONS OF ALL EQUIPMENT LAYOUTS IN COMMUNICATIONS ROOMS, ON WALLS, IN RACKS, AND IN CABINETS. EQUIPMENT SHALL BE CLEARLY LABELED INCLUDING MODEL NUMBERS AND LABELING REFERENCES. 7. DETAILS: PROVIDE DETAIL DRAWINGS AS REQUIRED TO SHOW ANY INSTALLATION OR COMPONENT CONFIGURATIONS THAT REQUIRE GREATER DETAIL. 8. LABELING: PROVIDED DOCUMENTATION OF ALL EQUIPMENT AND COMPONENT LABELING, ETC. 9. SCHEDULE: A DETAILED SCHEDULE SHALL BE SUBMITTED WITH THE SHOP DRAWINGS. THE SCHEDULE SHALL INCLUDE THE EXPECTED TIMELINES, FOR ORDERING, SHIPPING, BURN-IN, CONFIGURATION, INSTALLATION, ACCEPTANCE, AND TRAINING. THE SCHEDULE SHALL BE COORDINATED WITH THE CONSTRUCTION MANAGER. REFER TO SECTION ABOVE FOR ADDITIONAL REQUIREMENTS RELATED TO SCHEDULING. COMPLIANCE MATRIX : PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. ANY DEVIATIONS SHALL BE FULLY EXPLAINED INCLUDING PROPOSED CHANGE. REFER TO SECTION 1.13 BID INFORMATION SECTION LATER IN THIS SPECIFICATION FOR ADDITIONAL REQUIREMENTS. BILL OF MATERIALS : - 1. PROVIDEA DETAILED BILL OF MATERIALS INCLUDING ALL EQUIPMENT, CABLES, COMPONENTS, FIRMWARE/SOFTWARE, AND OTHER OPTIONS. 2. INFORMATION SHALL BE LISTED IN SPECIFIC CATEGORIES ACCORDING TO EQUIPMENT TYPE AND INCLUDE A BASIC DESCRIPTION, QUANTITIES, RETAIL PRICE, EXTENDED PRICE, TOTAL PRICE, LABOR HOURS, LABOR COSTS, ETC. 3. LIST ALL EQUIPMENT ALTERNATES SEPARATELY AT END OF REPORT. THIS SHOULD INCLUDE ANY ADDS AND DEDUCT ALTERNATES. 4. CONTRACTOR SHALL REFER TO WARRANTY AND MAINTENANCE SECTIONS OF THE SPECIFICATION BELOW. CONTRACTOR SHALL LIST ALL EQUIPMENT MAINTENANCE AND SUPPORT ITEMS SEPARATELY AT END OF BILL OF MATERIALS BROKEN OUT IN THE SAME CATEGORIES AS THE REST OF THE EQUIPMENT. 5. PROVIDE UNIT COST FOR EACH PIECE OF EQUIPMENT, ACCESSORIES, AND LABOR SO THAT THE OWNER MAY SELECT THAT EQUIPMENT DURING THE PROJECT TO MEET EXPANDING OR DECLINING REQUIREMENTS. 6. REFER TO SECTION 1.13 BID INFORMATION SECTION LATER IN THIS SPECIFICATION FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 21 00 - ENTERPRISE NETWORK SWITCHING AND ROUTING SYSTEM Status: OPEN | Info Exchange
| 11554 | Forwarded | For Review | 2020-10-13 | Populous SCA_CCA | Michael Mazzocchi (ME Engineers) | 2020-10-02 | Submittal Number: 27 21 00-1.0 From: ELLA PILGRIM Final Due Date: 09/28/20 Subject: NETWORK SWITCHING AND ROUTING SYSTEM - SHOP DRAWINGS, PRODUCT DATA, COORDINATION DATA, COMPLIANCE MATRIX, AND BILL OF MATERIALS Description: WITHIN 15 DAYS AFTER AWARD OF CONTRACT OR AS DICTATED BY THE CONSTRUCTION SCHEDULE- (WHICHEVER PERIOD OF TIME IS SHORTER), THE CONTRACTOR SHALL SUBMIT PRE-DEPLOYMENT SUBMITTALS CONSISTING OF PRODUCT DATA, COMPLIANCE MATRIX AND SHOP DRAWINGS FOR OWNER AND ENGINEER REVIEW. PARTIAL SUBMITTALS WILL NOT BE ACCEPTED WITHOUT PRIOR WRITTEN APPROVAL FROM THE ARCHITECT. COORDINATE ALL SUBMITTAL DATES WITH CONSTRUCTION MANAGER. PRODUCT DATA : THE DATA NETWORK SYSTEM PRODUCT DATA SUBMITTAL SHALL BE SUBMITTED PRIOR TO STARTING ANY WORK FOR REVIEW AND APPROVAL BY OWNER, ARCHITECT, AND ENGINEER. INFORMATION SHALL INCLUDE DETAILED MANUFACTURER'S SPECIFICATIONS FOR EACH COMPONENT TO BE INSTALLED. SUBMITTAL SHALL INCLUDEA LIST EVERY COMPONENT WITH MANUFACTURERS PART NUMBERS REFERENCED. MANUFACTURER DATA SHEETS WITH FEATURES, OPTIONS, RATINGS, AND PERFORMANCE. PRODUCT NUMBERS AND OPTIONS TO BE USED SHALL BE HIGHLIGHTED WITH COLOR MARKER. 1. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL IDENTIFY EACH COMPONENT NAME, MANUFACTURER, AND SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. EACH COMPONENT ON SHOP DRAWINGS, ELEVATIONS AND ONE-LINES SHALL SHARE THE SAME NAMING CONVENTION. 2. CUT-SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION. ALL COMPONENTS AND PARTS BEING USED SHALL BE HIGHLIGHTED IN COLOR OR CLEARLY UNDERLINED ON CUT-SHEETS TO DISTINGUISH SPECIFIC PRODUCT/PART NUMBERS, OPTIONS, COLORS, ACCESSORIES, ETC. CUT SHEETS SHALL BE SUBMITTED IN THE SAME ORDER OF THE COMPONENT LIST. 3. PRODUCT SUBSTITUTIONS: THIS SPECIFICATION IS INTENDED TO BE PERFORMANCE BASED, THUS REQUIREMENTS AND PRODUCTS NOTED ARE BENCHMARKS. THE CONTRACTOR MAY SUBSTITUTE MANUFACTURERS AND MODELS THAT MAY BE MORE COST EFFECTIVE OR READILY AVAILABLE. ALL SUBSTITUTIONS SHALL MEET OR EXCEED THE MINIMUM FUNCTIONAL, PHYSICAL, AND TECHNICAL SPECIFICATIONS. ACCEPTANCE OF SUCH SUBSTITUTIONS IS AT THE DISCRETION OF THE OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, THE REQUIREMENTS OF DIVISION 1 SPECIFICATIONS SHALL APPLY AND MAY SUPERSEDE REQUIREMENTS NOTED HEREIN. 4. SCHEDULE: A DETAILED SCHEDULE SHALL BE SUBMITTED WITH THE PREFABRICATION SUBMITTALS. THE SCHEDULE SHALL INCLUDE THE EXPECTED TIMELINES, FOR ORDERING, SHIPPING, BURN-IN, CONFIGURATION, INSTALLATION, ACCEPTANCE, AND TRAINING. SCHEDULE SHALL BE PRESENTED IN GANTT CHART FORMAT. DEPENDENCIES ON WORK BEING COMPLETED BY OTHERS SHALL BE CLEARLY DEFINED ON THE SCHEDULE. THE SCHEDULE SHALL BE COORDINATED WITH THE CONSTRUCTION MANAGER TO INCLUDE ALL CRITICAL PATH CONSTRUCTION DEADLINES IMPACTING THE DEPLOYMENT OF THE DATA NETWORK. THIS SHALL TAKE INTO ACCOUNT FINAL TESTING AND TURN OVER TO TAKE PLACE BEFORE THE OPENING OF THE BUILDING. 5. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. 6. PRODUCT CERTIFICATES: SIGNED BY MANUFACTURERS OF SYSTEMS CERTIFYING THAT PRODUCTS FURNISHED COMPLY WITH REQUIREMENTS. 7. INSTALLER CERTIFICATES: PROVIDE MANUFACTURER CERTIFICATION SIGNED BY MANUFACTURER CERTIFYING THAT INSTALLERS HAVE BEEN TRAINED TO INSTALL ALL COMPONENTS OF THE SYSTEM AND COMPLY WITH MANUFACTURERS REQUIREMENTS. COORDINATION DATA : A DETAILED EQUIPMENT AND COMPONENT SCHEDULE WITH SUPPORTING MANUFACTURER CUT-SHEETS SHALL BE DEVELOPED FOR ALL EQUIPMENT, COMPONENTS AND OPTIONS FOR ARCHITECTURAL, ENGINEERING, AND CONSTRUCTION COORDINATION. THESE DOCUMENTS SHALL INCLUDE ELECTRICAL REQUIREMENTS (VOLTS, PHASE, AMPS, POWER CONSUMPTION, RECEPTACLE CONFIGURATION, ETC.), UPS REQUIREMENTS, HEAT DISSIPATION, TEMPERATURE OPERATING RANGE, TARGET OPERATING TEMPERATURE, PHYSICAL EQUIPMENT SIZES (LXWXH), EQUIPMENT DEPLOYMENT WEIGHT, EQUIPMENT CONFIGURATIONS FOR OWNER REVIEW, ETC. SHOP DRAWINGS : THE DATA NETWORK SHOP DRAWINGS SHALL BE SUBMITTED PRIOR TO ORDERING OF ANY EQUIPMENT AND STARTING OF ANY WORK. SHOP DRAWINGS SHALL BE SUBMITTED FOR REVIEW BY OWNER, ARCHITECT, AND ENGINEER. ADDITIONALLY, SHOP DRAWINGS SHALL BE USED FOR COORDINATION WITH CONSTRUCTION MANAGER AND TRADES IMPACTED BY THIS INSTALLER. INFORMATION SHALL INCLUDE ALL DRAWINGS NECESSARY TO PRESENT INSTALLATION INTENT INCLUDING DIAGRAMS, PLANS, ENLARGED PLANS, ELEVATIONS, SECTIONS, DETAILS, AND INTERFACE TO OTHER WORK OR SYSTEMS. 1. LEGEND SHEET: PROVIDE DRAWINGS INCLUDING DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS. 2. NETWORK TOPOLOGY DIAGRAM: PROVIDED DRAWING OF ALL MAJOR COMPONENTS LOCATED IN MAIN COMMUNICATIONS ROOM, AND EACH INTERMEDIATE COMMUNICATIONS ROOM. DRAWINGS SHALL INCLUDE RELEVANT INFORMATION SUCH AS ROOM NUMBERS, EQUIPMENT NUMBER AND REFERENCES, UPLINKS, EQUIPMENT LINKS, BANDWIDTH, PANEL NUMBERS, AND UPLINK BANDWIDTHS. 3. ONE-LINE DIAGRAMS: PROVIDE DRAWINGS THAT INDICATE ALL EQUIPMENT BEING INTERCONNECTED, BACKBONE UPLINKS BETWEEN ACCESS LAYER SWITCHES, CORE SWITCHES, AND EXISTING CORE SWITCHES, ALL EQUIPMENT AND LOCATIONS. DRAWINGS SHALL INCLUDE RELEVANT INFORMATION SUCH AS ROOM NUMBERS, EQUIPMENT NUMBER AND REFERENCES, PANEL NUMBERS, AND UPLINK BANDWIDTHS. 4. FLOOR PLANS: PROVIDE SCALED PLAN DRAWINGS BASED ON ARCHITECTURAL BACKGROUND INDICATING EQUIPMENT AND LOCATIONS. DRAWINGS SHALL INCLUDE ALL RELEVANT INFORMATION SUCH AS ROOM NUMBERS, EQUIPMENT NUMBERS AND REFERENCES, PATCH PANEL NUMBERS, ETC. 5. ENLARGED PLANS: PROVIDE ENLARGED SCALED PLAN DRAWINGS FOR EQUIPMENT LAYOUTS IN COMMUNICATIONS ROOMS. EQUIPMENT SHALL BE CLEARLY LABELED INCLUDING NUMBERS AND REFERENCES. 6. ELEVATIONS: PROVIDE SCALED DRAWINGS FOR ELEVATIONS OF ALL EQUIPMENT LAYOUTS IN COMMUNICATIONS ROOMS, ON WALLS, IN RACKS, AND IN CABINETS. EQUIPMENT SHALL BE CLEARLY LABELED INCLUDING MODEL NUMBERS AND LABELING REFERENCES. 7. DETAILS: PROVIDE DETAIL DRAWINGS AS REQUIRED TO SHOW ANY INSTALLATION OR COMPONENT CONFIGURATIONS THAT REQUIRE GREATER DETAIL. 8. LABELING: PROVIDED DOCUMENTATION OF ALL EQUIPMENT AND COMPONENT LABELING, ETC. 9. SCHEDULE: A DETAILED SCHEDULE SHALL BE SUBMITTED WITH THE SHOP DRAWINGS. THE SCHEDULE SHALL INCLUDE THE EXPECTED TIMELINES, FOR ORDERING, SHIPPING, BURN-IN, CONFIGURATION, INSTALLATION, ACCEPTANCE, AND TRAINING. THE SCHEDULE SHALL BE COORDINATED WITH THE CONSTRUCTION MANAGER. REFER TO SECTION ABOVE FOR ADDITIONAL REQUIREMENTS RELATED TO SCHEDULING. COMPLIANCE MATRIX : PROVIDEA SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. ANY DEVIATIONS SHALL BE FULLY EXPLAINED INCLUDING PROPOSED CHANGE. REFER TO SECTION 1.13 BID INFORMATION SECTION LATER IN THIS SPECIFICATION FOR ADDITIONAL REQUIREMENTS. BILL OF MATERIALS : - 1. PROVIDEA DETAILED BILL OF MATERIALS INCLUDING ALL EQUIPMENT, CABLES, COMPONENTS, FIRMWARE/SOFTWARE, AND OTHER OPTIONS. 2. INFORMATION SHALL BE LISTED IN SPECIFIC CATEGORIES ACCORDING TO EQUIPMENT TYPE AND INCLUDE A BASIC DESCRIPTION, QUANTITIES, RETAIL PRICE, EXTENDED PRICE, TOTAL PRICE, LABOR HOURS, LABOR COSTS, ETC. 3. LIST ALL EQUIPMENT ALTERNATES SEPARATELY AT END OF REPORT. THIS SHOULD INCLUDE ANY ADDS AND DEDUCT ALTERNATES. 4. CONTRACTOR SHALL REFER TO WARRANTY AND MAINTENANCE SECTIONS OF THE SPECIFICATION BELOW. CONTRACTOR SHALL LIST ALL EQUIPMENT MAINTENANCE AND SUPPORT ITEMS SEPARATELY AT END OF BILL OF MATERIALS BROKEN OUT IN THE SAME CATEGORIES AS THE REST OF THE EQUIPMENT. 5. PROVIDE UNIT COST FOR EACH PIECE OF EQUIPMENT, ACCESSORIES, AND LABOR SO THAT THE OWNER MAY SELECT THAT EQUIPMENT DURING THE PROJECT TO MEET EXPANDING OR DECLINING REQUIREMENTS. 6. REFER TO SECTION 1.13 BID INFORMATION SECTION LATER IN THIS SPECIFICATION FOR ADDITIONAL REQUIREMENTS. Spec Section: 27 21 00 - ENTERPRISE NETWORK SWITCHING AND ROUTING SYSTEM Status: OPEN | Info Exchange
| 08909 | Review Response | Revise and Resubmit | 2020-10-19 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 11764 | Responded and Closed | Revise and Resubmit | 2020-10-21 | Populous SCA_CCA | Mike Steele (CAA ICON / Strategy Advisory); Elliott Veazey (CAA ICON / Strategy Advisory); Mike Tihista (CAA ICON / Strategy Advisory); Cody Koch (CAA ICON / Strategy Advisory) |  | Response (Revise and Resubmit) from: Michael Mazzocchi (ME Engineers) Remarks: See attached submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-14 |  | Climate Pledge Coordination Data 9_8_2020 Rev1.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-14 |  | Climate Pledge Product Data Rev1.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-14 |  | Climate Pledge Shop Drawings 9_9_2020 Rev1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-14 |  | Climate Pledge Coordination Data 9_8_2020 Rev1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-14 |  | Climate Pledge Product Data Rev1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-14 |  | Climate Pledge Shop Drawings 9_9_2020 Rev1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-13 02:00 |  | Climate Pledge Coordination Data 9_8_2020 Rev1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-13 02:00 |  | Climate Pledge Product Data Rev1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-13 02:00 |  | Climate Pledge Shop Drawings 9_9_2020 Rev1.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-09-13 02:00 |  | Climate Pledge Coordination Data 9_8_2020 Rev1.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-09-13 02:00 |  | Climate Pledge Product Data Rev1.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-09-13 02:00 |  | Climate Pledge Shop Drawings 9_9_2020 Rev1.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-21 02:00 |  | 27 21 00-001-00 NETWORK SWITCHING - ME Response_POP.pdf
27 21 00-001-01 | 27 21 00 - ENTERPRISE NETWORK SWITCHING AND ROUTING SYSTEM | 27 21 00-001-00 NETWORK SWITCHING AND ROUTING SYSTEM - Shop Drawings, Product Data, Coordination Data, Compliance Matrix, and Bill of Materials | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 27 21 00-001-00 - 27 21 00-001-00 NETWORK SWITCHING AND ROUTING SYSTEM - Shop Drawings, Product Data, Coordination Data, Compliance Matrix, and Bill of Materials | -1 | 2020-11-04
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-21 02:00 |  | 27 21 00-001-00 NETWORK SWITCHING - ME Response_POP.pdf
27 41 30-005-00 | 27 41 30 - VIDEO PRODUCTION | 27 41 30-005-00 Technical Furniture Shop Drawings | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-22 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri) |  |  |  | 2021-07-06 | 2021-06-30 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-06-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13612 | Received | For Review | 2021-06-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Cody Stieritz | 2021-07-06 | Submittal Number: 27 41 30-5.0 From: CODY STIERITZ Final Due Date: 06/30/21 Subject: TECHNICAL FURNITURE SHOP DRAWINGS Description: Spec Section: 27 41 30 - VIDEO PRODUCTION SYSTEMS Status: OPEN | Info Exchange
| 17625 | Forwarded | For Review | 2021-06-22 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-06-29 | Submittal Number: 27 41 30-5.0 From: CODY STIERITZ Final Due Date: 06/30/21 Subject: TECHNICAL FURNITURE SHOP DRAWINGS Description: Spec Section: 27 41 30 - VIDEO PRODUCTION SYSTEMS Status: OPEN | Info Exchange
| 13732 | Review Response | Approved as Noted | 2021-06-24 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  |  | Info Exchange
| 13733 | Review Response | Approved as Noted | 2021-06-30 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 17777 | Responded and Closed | Approved as Noted | 2021-06-30 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-22 |  | CPA Video Production - Furniture Shop Dwgs 6.14.21.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-22 |  | CPA Video Production - Furniture Shop Dwgs 6.14.21.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-06-22 |  | CPA Video Production - Furniture Shop Dwgs 6.14.21.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-06-30 |  | CPA Video Production - Furniture Shop Dwgs 6.14.21_i!iReview_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-06-22 |  | CPA Video Production - Furniture Shop Dwgs 6.14.21.pdf
27 41 30-007-00 | 27 41 30 - VIDEO PRODUCTION | 27 41 30-007-00 Design Drawings | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-30 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous), Ben Cating (Idibri), Brian Elwell (Idibri) |  |  |  | 2021-08-13 | 2021-08-16 | 18 |  | Record Copies; Transfers; Submittals | 27 41 30-007-00-01 - 27 41 30-007-00 Design Drawings | 15 |  | 2021-08-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14174 | Received | For Review | 2021-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Populous SCA_CCA; Cody Koch (CAA ICON / Strategy Advisory); Cody Stieritz | 2021-08-13 | Submittal Number: 27 41 30-7.0 From: CODY STIERITZ Final Due Date: 06/30/21 Subject: DESIGN DRAWINGS Description: Spec Section: 27 41 30 - VIDEO PRODUCTION SYSTEMS Status: OPEN | Info Exchange
| 18324 | Forwarded | For Review | 2021-08-02 | Shaina Burris (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-09 | Submittal Number: 27 41 30-7.0 From: CODY STIERITZ Final Due Date: 06/30/21 Subject: DESIGN DRAWINGS Description: Spec Section: 27 41 30 - VIDEO PRODUCTION SYSTEMS Status: OPEN | Info Exchange
| 18357 | Forwarded | For Review | 2021-08-03 | Kelsea Conkright (Populous) | Ben Cating (Idibri); Brian Elwell (Idibri) |  | Submittal Number: 27 41 30-7.0 From: CODY STIERITZ Final Due Date: 06/30/21 Subject: DESIGN DRAWINGS Description: Spec Section: 27 41 30 - VIDEO PRODUCTION SYSTEMS Status: OPEN | Info Exchange
| 14388 | Review Response | Approved as Noted/Resubmit | 2021-08-16 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Submittal is approved as noted, but we do want to see a revised set of documents incorporating the changes. | Info Exchange
| 18564 | Responded and Closed | Approved as Noted/Resubmit | 2021-08-16 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Resubmit with comments incorporated for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-02 |  | CPA Video Production - Diversified System Shop Drawings 7.20.21.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-08-02 |  | CPA Video Production - Diversified System Shop Drawings 7.20.21.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-08-02 |  | CPA Video Production - Diversified System Shop Drawings 7.20.21.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-16 |  | CPA Video Production - Diversified System Shop Drawings 7.20.21_idibri_POP.pdf
27 41 30-007-00-01 | 27 41 30 - VIDEO PRODUCTION | 27 41 30-007-00 Design Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 27 41 30-007-00 - 27 41 30-007-00 Design Drawings | -1 | 2021-08-30
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-16 |  | CPA Video Production - Diversified System Shop Drawings 7.20.21_idibri_POP.pdf
27 41 32-001-00 | 27 41 32 - BROADCAST CABLING | 27 41 32-001-00 BROADCAST CABLING - General | Closed | Audio-Visual, Technology, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-01 | Responded and Closed - Approved |  | Brian Elwell (Idibri), Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-06-15 | 2020-06-18 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-06-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06117 | Received | For Review | 2020-06-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-06-15 | Submittal Number: 27 41 32-1.0 From: ELLA PILGRIM Final Due Date: 06/12/20 Subject: BROADCAST CABLING - GENERAL Description: A BID SUBMITTALS: 1 CONTRACTOR'S QUALIFICATIONS: HAVE PREVIOUSLY INSTALLED AT LEAST 3 JOBS OF SIMILAR MAGNITUDE IN SPORTS VENUES, COMPLETED WITHIN THE LAST FIVE YEARS. PROVIDE NAME AND PHONE NUMBER OF REFERENCE FOR EACH REPRESENTATIVE PROJECT. IDENTIFY AT LEAST ONE SUCH COMPLETED JOB AVAILABLE FOR INSPECTION BY CONSULTANT OR OWNERS REPRESENTATIVE. 2 BIDDER WILL CONFIRM IN WRITING THAT THE FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 3 BIDDING CONTRACTOR WILL IDENTIFY ALL SUB-CONTRACTORS ON THE BID RESPONSE TEAM ANDA DETAILED SCOPE OF WORK FOR EACH SUB-CONTRACTOR. 4 BIDDER WILL CONFIRM IN WRITING THAT ANY SUB-CONTRACTOR FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE SUB-CONTRACTING FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 5 PROVIDE RESUMES OF PROJECT MANAGER, LEAD ENGINEER AND LEAD INSTALLERS WORKING ON THIS PROJECT. THIS WILL INCLUDE KEY TEAM MEMBERS OF ANY SUB CONTRACTOR. RESUMES MUST BE SUBMITTED WITH THIS BID RESPONSE 6 PROVIDEA SCHEDULE OF VALUES WITH UNIT PRICES FOR ALL SYSTEMS. SCHEDULE OF VALUES WILL BE USED FOR ANY ADD OR DEDUCT CHANGE ORDERS. BID RESPONSES WITHOUT SCHEDULE OF VALUES WILL BE RETURNED WITHOUT REVIEW. BIDDING CONTRACTOR WILL SUBMIT SPREADSHEET FORMATTED BY SPECIFICATION SECTION INDICATING MANUFACTURERS, MODEL NUMBERS, DESCRIPTIONS, TOTAL QUANTITIES, UNIT COSTS, AND EXTENDED COSTS. ATTACH SCHEDULE OF VALUES AT END OF BID FORM. B PROJECT SUBMITTALS: 1 PRODUCT DATA: SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT IN ACCORDANCE WITH PART 1 OF THE PROJECT MANUALS. 2 SHOP DRAWINGS: INDICATE COMPLETE DETAILS AND DIMENSIONS OF WORK TO BE PERFORMED AND INDICATE TYPES AND LOCATIONS OF EQUIPMENT, FABRICATED EQUIPMENT, AND OTHER DETAILS TO COMPLETELY DESCRIBE WORK TO BE PERFORMED. THERE SHALL BE NO WORK AUTHORIZED ON SITE WITHOUT THE PRIOR SUBMITTAL OFA COMPLETE SET OF SHOP DRAWINGS. ANY EXCEPTIONS TO THIS MUST BE IN WRITING AND APPROVED BY THE ARCHITECT. DETAILS TO INCLUDE THE FOLLOWING: A. WIRING SCHEMATIC. COMPLETE, DETAILED WIRING SCHEMATIC FOR ALL SYSTEMS, BASED ON THE CONTRACT DOCUMENTS BUT INCLUDING CABLE TYPES, IDENTIFICATION BY NUMBER AND COLOR CODES, AND DETAILED WIRING OF CONNECTIONS, BOTH AT EQUIPMENT AND BETWEEN EQUIPMENT RACKS AND WIRING IN CONDUIT. B. CONDUIT RISER DIAGRAMS FOR ALL SYSTEMS. C. RACK LAYOUT AND LOCATION DIAGRAMS WITH OVERALL DIMENSIONS. D. SCHEDULE OF TERMINATIONS FOR ALL SYSTEMS. E. TERMINAL STRIP LAYOUTS FOR ALL PROPOSED TERMINAL STRIPS TO BE USED IN JUNCTION BOXES OR IN THE EQUIPMENT RACKS. F. PANEL FABRICATION DETAILS INCLUDINGA PANEL ENGRAVING SCHEDULE. G. CABLE PULL LIST. SUBMIT ALL WIRING PULL LENGTHS FROM SOURCE TO DESTINATION. INCLUDE WIRE NUMBERS. H. SCHEMATIC DRAWINGS OF ANY CUSTOM CIRCUITRY OR EQUIPMENT MODIFICATIONS, INCLUDING CONNECTOR PINOUTS AND COMPONENT LISTS. I. PROVIDE COLOR INFORMATION FOR ALL RACKS AND ENCLOSURES SHOWN ON DRAWINGS. 3 CABLE AND CONNECTOR SUBMITTAL. SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24 IN LENGTH. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. C CONTRACT CLOSEOUT SUBMITTALS 1 KEEPA COMPLETE SET OF APPROVED SHOP DRAWINGS ON THE JOB AT ALL TIMES. NOTE ANY CHANGES MADE DURING INSTALLATION ONA SINGLE SET OF DRAWINGS. THIS SET OF MARKED UP DRAWINGS WILL NOT LEAVE THE JOBSITE UNTIL AFTER THE FINAL SYSTEM COMMISSIONING. SUBMIT TWO (2) CORRECTED SETS OF REPRODUCIBLE DRAWINGS SHOWING WORK AS INSTALLED. ALL AS-BUILT DRAWINGS TO BE PROVIDED BOTH IN ELECTRONIC FORM (ACAD 2012 OR LATER) AND IN HARD COPY (42X30). 2 SYSTEM REFERENCE MANUAL: PRIOR TO OWNER TRAINING, FURNISH 1 COPY, IN 3 RING BINDERS, SIZED TO HOLD THE MATERIAL PLUS 50% EXCESS, WITH CLEAR VINYL POCKETS ON COVER AND SPINE FOR PROJECT TITLE. PROVIDE TABULAR DIVIDERS WITH PERMANENT LEGENDS FOR THE FOLLOWING SECTIONS: A. A LEGEND OF ACRONYMS AND ABBREVIATIONS MUST ACCOMPANY ALL DOCUMENTATION. B. A LIST OF ALL TEST RESULTS PERFORMED ON THE SYSTEMS AS OUTLINED IN SECTION 3.5 PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE. C. A LIST OF ALL EQUIPMENT, INDICATING MANUFACTURER, MODEL, SERIAL NUMBER, AND EQUIPMENT LOCATION (I.E. RACK/ROOM NUMBER). UPDATE FOLLOWING ACCEPTANCE TESTING, IF CHANGED. D. REPRODUCED SCHEMATIC WIRING DIAGRAMS OF THE AUDIO/VIDEO SYSTEMS, BASED ON THE AS-BUILT DOCUMENTATION, ATA REDUCED SCALE EASY TO HANDLE BUT FULLY LEGIBLE. E. REPLACEMENT PARTS LISTS OF MAJOR ITEMS OF EQUIPMENT. F. PRODUCE COMPACT SYSTEM SCHEMATICS SHOWING ALL COMPONENTS, CABLES, AND WIRE NUMBERS THAT WILL BE MOUNTED ON THE WALL OF THE TRUCK DOCK AND ENGINEERING RACK ROOM. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 08276 | Forwarded | For Review | 2020-06-01 | Populous SCA_CCA | Brian Elwell (Idibri) | 2020-06-08 | Submittal Number: 27 41 32-1.0 From: ELLA PILGRIM Final Due Date: 06/12/20 Subject: BROADCAST CABLING - GENERAL Description: A BID SUBMITTALS: 1 CONTRACTOR'S QUALIFICATIONS: HAVE PREVIOUSLY INSTALLED AT LEAST 3 JOBS OF SIMILAR MAGNITUDE IN SPORTS VENUES, COMPLETED WITHIN THE LAST FIVE YEARS. PROVIDE NAME AND PHONE NUMBER OF REFERENCE FOR EACH REPRESENTATIVE PROJECT. IDENTIFY AT LEAST ONE SUCH COMPLETED JOB AVAILABLE FOR INSPECTION BY CONSULTANT OR OWNERS REPRESENTATIVE. 2 BIDDER WILL CONFIRM IN WRITING THAT THE FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 3 BIDDING CONTRACTOR WILL IDENTIFY ALL SUB-CONTRACTORS ON THE BID RESPONSE TEAM ANDA DETAILED SCOPE OF WORK FOR EACH SUB-CONTRACTOR. 4 BIDDER WILL CONFIRM IN WRITING THAT ANY SUB-CONTRACTOR FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE SUB-CONTRACTING FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 5 PROVIDE RESUMES OF PROJECT MANAGER, LEAD ENGINEER AND LEAD INSTALLERS WORKING ON THIS PROJECT. THIS WILL INCLUDE KEY TEAM MEMBERS OF ANY SUB CONTRACTOR. RESUMES MUST BE SUBMITTED WITH THIS BID RESPONSE 6 PROVIDEA SCHEDULE OF VALUES WITH UNIT PRICES FOR ALL SYSTEMS. SCHEDULE OF VALUES WILL BE USED FOR ANY ADD OR DEDUCT CHANGE ORDERS. BID RESPONSES WITHOUT SCHEDULE OF VALUES WILL BE RETURNED WITHOUT REVIEW. BIDDING CONTRACTOR WILL SUBMIT SPREADSHEET FORMATTED BY SPECIFICATION SECTION INDICATING MANUFACTURERS, MODEL NUMBERS, DESCRIPTIONS, TOTAL QUANTITIES, UNIT COSTS, AND EXTENDED COSTS. ATTACH SCHEDULE OF VALUES AT END OF BID FORM. B PROJECT SUBMITTALS: 1 PRODUCT DATA: SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT IN ACCORDANCE WITH PART 1 OF THE PROJECT MANUALS. 2 SHOP DRAWINGS: INDICATE COMPLETE DETAILS AND DIMENSIONS OF WORK TO BE PERFORMED AND INDICATE TYPES AND LOCATIONS OF EQUIPMENT, FABRICATED EQUIPMENT, AND OTHER DETAILS TO COMPLETELY DESCRIBE WORK TO BE PERFORMED. THERE SHALL BE NO WORK AUTHORIZED ON SITE WITHOUT THE PRIOR SUBMITTAL OFA COMPLETE SET OF SHOP DRAWINGS. ANY EXCEPTIONS TO THIS MUST BE IN WRITING AND APPROVED BY THE ARCHITECT. DETAILS TO INCLUDE THE FOLLOWING: A. WIRING SCHEMATIC. COMPLETE, DETAILED WIRING SCHEMATIC FOR ALL SYSTEMS, BASED ON THE CONTRACT DOCUMENTS BUT INCLUDING CABLE TYPES, IDENTIFICATION BY NUMBER AND COLOR CODES, AND DETAILED WIRING OF CONNECTIONS, BOTH AT EQUIPMENT AND BETWEEN EQUIPMENT RACKS AND WIRING IN CONDUIT. B. CONDUIT RISER DIAGRAMS FOR ALL SYSTEMS. C. RACK LAYOUT AND LOCATION DIAGRAMS WITH OVERALL DIMENSIONS. D. SCHEDULE OF TERMINATIONS FOR ALL SYSTEMS. E. TERMINAL STRIP LAYOUTS FOR ALL PROPOSED TERMINAL STRIPS TO BE USED IN JUNCTION BOXES OR IN THE EQUIPMENT RACKS. F. PANEL FABRICATION DETAILS INCLUDINGA PANEL ENGRAVING SCHEDULE. G. CABLE PULL LIST. SUBMIT ALL WIRING PULL LENGTHS FROM SOURCE TO DESTINATION. INCLUDE WIRE NUMBERS. H. SCHEMATIC DRAWINGS OF ANY CUSTOM CIRCUITRY OR EQUIPMENT MODIFICATIONS, INCLUDING CONNECTOR PINOUTS AND COMPONENT LISTS. I. PROVIDE COLOR INFORMATION FOR ALL RACKS AND ENCLOSURES SHOWN ON DRAWINGS. 3 CABLE AND CONNECTOR SUBMITTAL. SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24 IN LENGTH. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. C CONTRACT CLOSEOUT SUBMITTALS 1 KEEPA COMPLETE SET OF APPROVED SHOP DRAWINGS ON THE JOB AT ALL TIMES. NOTE ANY CHANGES MADE DURING INSTALLATION ONA SINGLE SET OF DRAWINGS. THIS SET OF MARKED UP DRAWINGS WILL NOT LEAVE THE JOBSITE UNTIL AFTER THE FINAL SYSTEM COMMISSIONING. SUBMIT TWO (2) CORRECTED SETS OF REPRODUCIBLE DRAWINGS SHOWING WORK AS INSTALLED. ALL AS-BUILT DRAWINGS TO BE PROVIDED BOTH IN ELECTRONIC FORM (ACAD 2012 OR LATER) AND IN HARD COPY (42X30). 2 SYSTEM REFERENCE MANUAL: PRIOR TO OWNER TRAINING, FURNISH 1 COPY, IN 3 RING BINDERS, SIZED TO HOLD THE MATERIAL PLUS 50% EXCESS, WITH CLEAR VINYL POCKETS ON COVER AND SPINE FOR PROJECT TITLE. PROVIDE TABULAR DIVIDERS WITH PERMANENT LEGENDS FOR THE FOLLOWING SECTIONS: A. A LEGEND OF ACRONYMS AND ABBREVIATIONS MUST ACCOMPANY ALL DOCUMENTATION. B. A LIST OF ALL TEST RESULTS PERFORMED ON THE SYSTEMS AS OUTLINED IN SECTION 3.5 PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE. C. A LIST OF ALL EQUIPMENT, INDICATING MANUFACTURER, MODEL, SERIAL NUMBER, AND EQUIPMENT LOCATION (I.E. RACK/ROOM NUMBER). UPDATE FOLLOWING ACCEPTANCE TESTING, IF CHANGED. D. REPRODUCED SCHEMATIC WIRING DIAGRAMS OF THE AUDIO/VIDEO SYSTEMS, BASED ON THE AS-BUILT DOCUMENTATION, ATA REDUCED SCALE EASY TO HANDLE BUT FULLY LEGIBLE. E. REPLACEMENT PARTS LISTS OF MAJOR ITEMS OF EQUIPMENT. F. PRODUCE COMPACT SYSTEM SCHEMATICS SHOWING ALL COMPONENTS, CABLES, AND WIRE NUMBERS THAT WILL BE MOUNTED ON THE WALL OF THE TRUCK DOCK AND ENGINEERING RACK ROOM. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 06395 | Review Response | Approved | 2020-06-05 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Approved as submitted. No comments. | Info Exchange
| 08498 | Forwarded | For Review | 2020-06-09 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-15 | Submittal Number: 27 41 32-1.0 From: ELLA PILGRIM Final Due Date: 06/12/20 Subject: BROADCAST CABLING - GENERAL Description: A BID SUBMITTALS: 1 CONTRACTOR'S QUALIFICATIONS: HAVE PREVIOUSLY INSTALLED AT LEAST 3 JOBS OF SIMILAR MAGNITUDE IN SPORTS VENUES, COMPLETED WITHIN THE LAST FIVE YEARS. PROVIDE NAME AND PHONE NUMBER OF REFERENCE FOR EACH REPRESENTATIVE PROJECT. IDENTIFY AT LEAST ONE SUCH COMPLETED JOB AVAILABLE FOR INSPECTION BY CONSULTANT OR OWNERS REPRESENTATIVE. 2 BIDDER WILL CONFIRM IN WRITING THAT THE FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 3 BIDDING CONTRACTOR WILL IDENTIFY ALL SUB-CONTRACTORS ON THE BID RESPONSE TEAM ANDA DETAILED SCOPE OF WORK FOR EACH SUB-CONTRACTOR. 4 BIDDER WILL CONFIRM IN WRITING THAT ANY SUB-CONTRACTOR FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE SUB-CONTRACTING FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 5 PROVIDE RESUMES OF PROJECT MANAGER, LEAD ENGINEER AND LEAD INSTALLERS WORKING ON THIS PROJECT. THIS WILL INCLUDE KEY TEAM MEMBERS OF ANY SUB CONTRACTOR. RESUMES MUST BE SUBMITTED WITH THIS BID RESPONSE 6 PROVIDEA SCHEDULE OF VALUES WITH UNIT PRICES FOR ALL SYSTEMS. SCHEDULE OF VALUES WILL BE USED FOR ANY ADD OR DEDUCT CHANGE ORDERS. BID RESPONSES WITHOUT SCHEDULE OF VALUES WILL BE RETURNED WITHOUT REVIEW. BIDDING CONTRACTOR WILL SUBMIT SPREADSHEET FORMATTED BY SPECIFICATION SECTION INDICATING MANUFACTURERS, MODEL NUMBERS, DESCRIPTIONS, TOTAL QUANTITIES, UNIT COSTS, AND EXTENDED COSTS. ATTACH SCHEDULE OF VALUES AT END OF BID FORM. B PROJECT SUBMITTALS: 1 PRODUCT DATA: SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT IN ACCORDANCE WITH PART 1 OF THE PROJECT MANUALS. 2 SHOP DRAWINGS: INDICATE COMPLETE DETAILS AND DIMENSIONS OF WORK TO BE PERFORMED AND INDICATE TYPES AND LOCATIONS OF EQUIPMENT, FABRICATED EQUIPMENT, AND OTHER DETAILS TO COMPLETELY DESCRIBE WORK TO BE PERFORMED. THERE SHALL BE NO WORK AUTHORIZED ON SITE WITHOUT THE PRIOR SUBMITTAL OFA COMPLETE SET OF SHOP DRAWINGS. ANY EXCEPTIONS TO THIS MUST BE IN WRITING AND APPROVED BY THE ARCHITECT. DETAILS TO INCLUDE THE FOLLOWING: A. WIRING SCHEMATIC. COMPLETE, DETAILED WIRING SCHEMATIC FOR ALL SYSTEMS, BASED ON THE CONTRACT DOCUMENTS BUT INCLUDING CABLE TYPES, IDENTIFICATION BY NUMBER AND COLOR CODES, AND DETAILED WIRING OF CONNECTIONS, BOTH AT EQUIPMENT AND BETWEEN EQUIPMENT RACKS AND WIRING IN CONDUIT. B. CONDUIT RISER DIAGRAMS FOR ALL SYSTEMS. C. RACK LAYOUT AND LOCATION DIAGRAMS WITH OVERALL DIMENSIONS. D. SCHEDULE OF TERMINATIONS FOR ALL SYSTEMS. E. TERMINAL STRIP LAYOUTS FOR ALL PROPOSED TERMINAL STRIPS TO BE USED IN JUNCTION BOXES OR IN THE EQUIPMENT RACKS. F. PANEL FABRICATION DETAILS INCLUDINGA PANEL ENGRAVING SCHEDULE. G. CABLE PULL LIST. SUBMIT ALL WIRING PULL LENGTHS FROM SOURCE TO DESTINATION. INCLUDE WIRE NUMBERS. H. SCHEMATIC DRAWINGS OF ANY CUSTOM CIRCUITRY OR EQUIPMENT MODIFICATIONS, INCLUDING CONNECTOR PINOUTS AND COMPONENT LISTS. I. PROVIDE COLOR INFORMATION FOR ALL RACKS AND ENCLOSURES SHOWN ON DRAWINGS. 3 CABLE AND CONNECTOR SUBMITTAL. SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24 IN LENGTH. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. C CONTRACT CLOSEOUT SUBMITTALS 1 KEEPA COMPLETE SET OF APPROVED SHOP DRAWINGS ON THE JOB AT ALL TIMES. NOTE ANY CHANGES MADE DURING INSTALLATION ONA SINGLE SET OF DRAWINGS. THIS SET OF MARKED UP DRAWINGS WILL NOT LEAVE THE JOBSITE UNTIL AFTER THE FINAL SYSTEM COMMISSIONING. SUBMIT TWO (2) CORRECTED SETS OF REPRODUCIBLE DRAWINGS SHOWING WORK AS INSTALLED. ALL AS-BUILT DRAWINGS TO BE PROVIDED BOTH IN ELECTRONIC FORM (ACAD 2012 OR LATER) AND IN HARD COPY (42X30). 2 SYSTEM REFERENCE MANUAL: PRIOR TO OWNER TRAINING, FURNISH 1 COPY, IN 3 RING BINDERS, SIZED TO HOLD THE MATERIAL PLUS 50% EXCESS, WITH CLEAR VINYL POCKETS ON COVER AND SPINE FOR PROJECT TITLE. PROVIDE TABULAR DIVIDERS WITH PERMANENT LEGENDS FOR THE FOLLOWING SECTIONS: A. A LEGEND OF ACRONYMS AND ABBREVIATIONS MUST ACCOMPANY ALL DOCUMENTATION. B. A LIST OF ALL TEST RESULTS PERFORMED ON THE SYSTEMS AS OUTLINED IN SECTION 3.5 PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE. C. A LIST OF ALL EQUIPMENT, INDICATING MANUFACTURER, MODEL, SERIAL NUMBER, AND EQUIPMENT LOCATION (I.E. RACK/ROOM NUMBER). UPDATE FOLLOWING ACCEPTANCE TESTING, IF CHANGED. D. REPRODUCED SCHEMATIC WIRING DIAGRAMS OF THE AUDIO/VIDEO SYSTEMS, BASED ON THE AS-BUILT DOCUMENTATION, ATA REDUCED SCALE EASY TO HANDLE BUT FULLY LEGIBLE. E. REPLACEMENT PARTS LISTS OF MAJOR ITEMS OF EQUIPMENT. F. PRODUCE COMPACT SYSTEM SCHEMATICS SHOWING ALL COMPONENTS, CABLES, AND WIRE NUMBERS THAT WILL BE MOUNTED ON THE WALL OF THE TRUCK DOCK AND ENGINEERING RACK ROOM. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 06481 | Review Response | No Action Taken or Required | 2020-06-18 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  | ME ENGINEERS REVIEWED ONLY AND HAS NO COMMENTS. | Info Exchange
| 08732 | Responded and Closed | Approved | 2020-06-18 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Abby Harrison (ME Engineers) Remarks: ME ENGINEERS REVIEWED ONLY AND HAS NO COMMENTS. Response (Approved) from: Brian Elwell (Idibri) Remarks: Approved as submitted. No comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-29 |  | 27 41 32-1.0 - Broadcast Cabling - General.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-29 |  | 27 41 32-1.0 - Broadcast Cabling - General.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-05-28 02:00 |  | 27 41 32-1.0 - Broadcast Cabling - General.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-28 02:00 |  | 27 41 32-1.0 - Broadcast Cabling - General.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-05-28 02:00 |  | 27 41 32-1.0 - Broadcast Cabling - General.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-06-18 02:00 |  | 27 41 32-1.0 - Broadcast Cabling_ME_IDIBRI_POP.pdf
27 41 32-001-01 | 27 41 32 - BROADCAST CABLING | 27 41 32-001-01 BROADCAST CABLING - General | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-13 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri) |  |  |  | 2020-10-27 | 2020-10-29 | 17 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-10-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08750 | Received | For Review | 2020-10-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-27 | Submittal Number: 27 41 32-1.1 From: ELLA PILGRIM Final Due Date: 10/28/20 Subject: BROADCAST CABLING - GENERAL Description: A BID SUBMITTALS: 1 CONTRACTOR'S QUALIFICATIONS: HAVE PREVIOUSLY INSTALLED AT LEAST 3 JOBS OF SIMILAR MAGNITUDE IN SPORTS VENUES, COMPLETED WITHIN THE LAST FIVE YEARS. PROVIDE NAME AND PHONE NUMBER OF REFERENCE FOR EACH REPRESENTATIVE PROJECT. IDENTIFY AT LEAST ONE SUCH COMPLETED JOB AVAILABLE FOR INSPECTION BY CONSULTANT OR OWNERS REPRESENTATIVE. 2 BIDDER WILL CONFIRM IN WRITING THAT THE FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 3 BIDDING CONTRACTOR WILL IDENTIFY ALL SUB-CONTRACTORS ON THE BID RESPONSE TEAM ANDA DETAILED SCOPE OF WORK FOR EACH SUB-CONTRACTOR. 4 BIDDER WILL CONFIRM IN WRITING THAT ANY SUB-CONTRACTOR FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE SUB-CONTRACTING FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 5 PROVIDE RESUMES OF PROJECT MANAGER, LEAD ENGINEER AND LEAD INSTALLERS WORKING ON THIS PROJECT. THIS WILL INCLUDE KEY TEAM MEMBERS OF ANY SUB CONTRACTOR. RESUMES MUST BE SUBMITTED WITH THIS BID RESPONSE 6 PROVIDEA SCHEDULE OF VALUES WITH UNIT PRICES FOR ALL SYSTEMS. SCHEDULE OF VALUES WILL BE USED FOR ANY ADD OR DEDUCT CHANGE ORDERS. BID RESPONSES WITHOUT SCHEDULE OF VALUES WILL BE RETURNED WITHOUT REVIEW. BIDDING CONTRACTOR WILL SUBMIT SPREADSHEET FORMATTED BY SPECIFICATION SECTION INDICATING MANUFACTURERS, MODEL NUMBERS, DESCRIPTIONS, TOTAL QUANTITIES, UNIT COSTS, AND EXTENDED COSTS. ATTACH SCHEDULE OF VALUES AT END OF BID FORM. B PROJECT SUBMITTALS: 1 PRODUCT DATA: SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT IN ACCORDANCE WITH PART 1 OF THE PROJECT MANUALS. 2 SHOP DRAWINGS: INDICATE COMPLETE DETAILS AND DIMENSIONS OF WORK TO BE PERFORMED AND INDICATE TYPES AND LOCATIONS OF EQUIPMENT, FABRICATED EQUIPMENT, AND OTHER DETAILS TO COMPLETELY DESCRIBE WORK TO BE PERFORMED. THERE SHALL BE NO WORK AUTHORIZED ON SITE WITHOUT THE PRIOR SUBMITTAL OFA COMPLETE SET OF SHOP DRAWINGS. ANY EXCEPTIONS TO THIS MUST BE IN WRITING AND APPROVED BY THE ARCHITECT. DETAILS TO INCLUDE THE FOLLOWING: A. WIRING SCHEMATIC. COMPLETE, DETAILED WIRING SCHEMATIC FOR ALL SYSTEMS, BASED ON THE CONTRACT DOCUMENTS BUT INCLUDING CABLE TYPES, IDENTIFICATION BY NUMBER AND COLOR CODES, AND DETAILED WIRING OF CONNECTIONS, BOTH AT EQUIPMENT AND BETWEEN EQUIPMENT RACKS AND WIRING IN CONDUIT. B. CONDUIT RISER DIAGRAMS FOR ALL SYSTEMS. C. RACK LAYOUT AND LOCATION DIAGRAMS WITH OVERALL DIMENSIONS. D. SCHEDULE OF TERMINATIONS FOR ALL SYSTEMS. E. TERMINAL STRIP LAYOUTS FOR ALL PROPOSED TERMINAL STRIPS TO BE USED IN JUNCTION BOXES OR IN THE EQUIPMENT RACKS. F. PANEL FABRICATION DETAILS INCLUDINGA PANEL ENGRAVING SCHEDULE. G. CABLE PULL LIST. SUBMIT ALL WIRING PULL LENGTHS FROM SOURCE TO DESTINATION. INCLUDE WIRE NUMBERS. H. SCHEMATIC DRAWINGS OF ANY CUSTOM CIRCUITRY OR EQUIPMENT MODIFICATIONS, INCLUDING CONNECTOR PINOUTS AND COMPONENT LISTS. I. PROVIDE COLOR INFORMATION FOR ALL RACKS AND ENCLOSURES SHOWN ON DRAWINGS. 3 CABLE AND CONNECTOR SUBMITTAL. SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24 IN LENGTH. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. C CONTRACT CLOSEOUT SUBMITTALS 1 KEEPA COMPLETE SET OF APPROVED SHOP DRAWINGS ON THE JOB AT ALL TIMES. NOTE ANY CHANGES MADE DURING INSTALLATION ONA SINGLE SET OF DRAWINGS. THIS SET OF MARKED UP DRAWINGS WILL NOT LEAVE THE JOBSITE UNTIL AFTER THE FINAL SYSTEM COMMISSIONING. SUBMIT TWO (2) CORRECTED SETS OF REPRODUCIBLE DRAWINGS SHOWING WORK AS INSTALLED. ALL AS-BUILT DRAWINGS TO BE PROVIDED BOTH IN ELECTRONIC FORM (ACAD 2012 OR LATER) AND IN HARD COPY (42X30). 2 SYSTEM REFERENCE MANUAL: PRIOR TO OWNER TRAINING, FURNISH 1 COPY, IN 3 RING BINDERS, SIZED TO HOLD THE MATERIAL PLUS 50% EXCESS, WITH CLEAR VINYL POCKETS ON COVER AND SPINE FOR PROJECT TITLE. PROVIDE TABULAR DIVIDERS WITH PERMANENT LEGENDS FOR THE FOLLOWING SECTIONS: A. A LEGEND OF ACRONYMS AND ABBREVIATIONS MUST ACCOMPANY ALL DOCUMENTATION. B. A LIST OF ALL TEST RESULTS PERFORMED ON THE SYSTEMS AS OUTLINED IN SECTION 3.5 PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE. C. A LIST OF ALL EQUIPMENT, INDICATING MANUFACTURER, MODEL, SERIAL NUMBER, AND EQUIPMENT LOCATION (I.E. RACK/ROOM NUMBER). UPDATE FOLLOWING ACCEPTANCE TESTING, IF CHANGED. D. REPRODUCED SCHEMATIC WIRING DIAGRAMS OF THE AUDIO/VIDEO SYSTEMS, BASED ON THE AS-BUILT DOCUMENTATION, ATA REDUCED SCALE EASY TO HANDLE BUT FULLY LEGIBLE. E. REPLACEMENT PARTS LISTS OF MAJOR ITEMS OF EQUIPMENT. F. PRODUCE COMPACT SYSTEM SCHEMATICS SHOWING ALL COMPONENTS, CABLES, AND WIRE NUMBERS THAT WILL BE MOUNTED ON THE WALL OF THE TRUCK DOCK AND ENGINEERING RACK ROOM. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 11558 | Forwarded | For Review | 2020-10-13 | Populous SCA_CCA | Brian Elwell (Idibri) | 2020-10-20 | Submittal Number: 27 41 32-1.1 From: ELLA PILGRIM Final Due Date: 10/28/20 Subject: BROADCAST CABLING - GENERAL Description: A BID SUBMITTALS: 1 CONTRACTOR'S QUALIFICATIONS: HAVE PREVIOUSLY INSTALLED AT LEAST 3 JOBS OF SIMILAR MAGNITUDE IN SPORTS VENUES, COMPLETED WITHIN THE LAST FIVE YEARS. PROVIDE NAME AND PHONE NUMBER OF REFERENCE FOR EACH REPRESENTATIVE PROJECT. IDENTIFY AT LEAST ONE SUCH COMPLETED JOB AVAILABLE FOR INSPECTION BY CONSULTANT OR OWNERS REPRESENTATIVE. 2 BIDDER WILL CONFIRM IN WRITING THAT THE FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 3 BIDDING CONTRACTOR WILL IDENTIFY ALL SUB-CONTRACTORS ON THE BID RESPONSE TEAM ANDA DETAILED SCOPE OF WORK FOR EACH SUB-CONTRACTOR. 4 BIDDER WILL CONFIRM IN WRITING THAT ANY SUB-CONTRACTOR FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE SUB-CONTRACTING FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 5 PROVIDE RESUMES OF PROJECT MANAGER, LEAD ENGINEER AND LEAD INSTALLERS WORKING ON THIS PROJECT. THIS WILL INCLUDE KEY TEAM MEMBERS OF ANY SUB CONTRACTOR. RESUMES MUST BE SUBMITTED WITH THIS BID RESPONSE 6 PROVIDEA SCHEDULE OF VALUES WITH UNIT PRICES FOR ALL SYSTEMS. SCHEDULE OF VALUES WILL BE USED FOR ANY ADD OR DEDUCT CHANGE ORDERS. BID RESPONSES WITHOUT SCHEDULE OF VALUES WILL BE RETURNED WITHOUT REVIEW. BIDDING CONTRACTOR WILL SUBMIT SPREADSHEET FORMATTED BY SPECIFICATION SECTION INDICATING MANUFACTURERS, MODEL NUMBERS, DESCRIPTIONS, TOTAL QUANTITIES, UNIT COSTS, AND EXTENDED COSTS. ATTACH SCHEDULE OF VALUES AT END OF BID FORM. B PROJECT SUBMITTALS: 1 PRODUCT DATA: SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT IN ACCORDANCE WITH PART 1 OF THE PROJECT MANUALS. 2 SHOP DRAWINGS: INDICATE COMPLETE DETAILS AND DIMENSIONS OF WORK TO BE PERFORMED AND INDICATE TYPES AND LOCATIONS OF EQUIPMENT, FABRICATED EQUIPMENT, AND OTHER DETAILS TO COMPLETELY DESCRIBE WORK TO BE PERFORMED. THERE SHALL BE NO WORK AUTHORIZED ON SITE WITHOUT THE PRIOR SUBMITTAL OFA COMPLETE SET OF SHOP DRAWINGS. ANY EXCEPTIONS TO THIS MUST BE IN WRITING AND APPROVED BY THE ARCHITECT. DETAILS TO INCLUDE THE FOLLOWING: A. WIRING SCHEMATIC. COMPLETE, DETAILED WIRING SCHEMATIC FOR ALL SYSTEMS, BASED ON THE CONTRACT DOCUMENTS BUT INCLUDING CABLE TYPES, IDENTIFICATION BY NUMBER AND COLOR CODES, AND DETAILED WIRING OF CONNECTIONS, BOTH AT EQUIPMENT AND BETWEEN EQUIPMENT RACKS AND WIRING IN CONDUIT. B. CONDUIT RISER DIAGRAMS FOR ALL SYSTEMS. C. RACK LAYOUT AND LOCATION DIAGRAMS WITH OVERALL DIMENSIONS. D. SCHEDULE OF TERMINATIONS FOR ALL SYSTEMS. E. TERMINAL STRIP LAYOUTS FOR ALL PROPOSED TERMINAL STRIPS TO BE USED IN JUNCTION BOXES OR IN THE EQUIPMENT RACKS. F. PANEL FABRICATION DETAILS INCLUDINGA PANEL ENGRAVING SCHEDULE. G. CABLE PULL LIST. SUBMIT ALL WIRING PULL LENGTHS FROM SOURCE TO DESTINATION. INCLUDE WIRE NUMBERS. H. SCHEMATIC DRAWINGS OF ANY CUSTOM CIRCUITRY OR EQUIPMENT MODIFICATIONS, INCLUDING CONNECTOR PINOUTS AND COMPONENT LISTS. I. PROVIDE COLOR INFORMATION FOR ALL RACKS AND ENCLOSURES SHOWN ON DRAWINGS. 3 CABLE AND CONNECTOR SUBMITTAL. SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24 IN LENGTH. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. C CONTRACT CLOSEOUT SUBMITTALS 1 KEEPA COMPLETE SET OF APPROVED SHOP DRAWINGS ON THE JOB AT ALL TIMES. NOTE ANY CHANGES MADE DURING INSTALLATION ONA SINGLE SET OF DRAWINGS. THIS SET OF MARKED UP DRAWINGS WILL NOT LEAVE THE JOBSITE UNTIL AFTER THE FINAL SYSTEM COMMISSIONING. SUBMIT TWO (2) CORRECTED SETS OF REPRODUCIBLE DRAWINGS SHOWING WORK AS INSTALLED. ALL AS-BUILT DRAWINGS TO BE PROVIDED BOTH IN ELECTRONIC FORM (ACAD 2012 OR LATER) AND IN HARD COPY (42X30). 2 SYSTEM REFERENCE MANUAL: PRIOR TO OWNER TRAINING, FURNISH 1 COPY, IN 3 RING BINDERS, SIZED TO HOLD THE MATERIAL PLUS 50% EXCESS, WITH CLEAR VINYL POCKETS ON COVER AND SPINE FOR PROJECT TITLE. PROVIDE TABULAR DIVIDERS WITH PERMANENT LEGENDS FOR THE FOLLOWING SECTIONS: A. A LEGEND OF ACRONYMS AND ABBREVIATIONS MUST ACCOMPANY ALL DOCUMENTATION. B. A LIST OF ALL TEST RESULTS PERFORMED ON THE SYSTEMS AS OUTLINED IN SECTION 3.5 PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE. C. A LIST OF ALL EQUIPMENT, INDICATING MANUFACTURER, MODEL, SERIAL NUMBER, AND EQUIPMENT LOCATION (I.E. RACK/ROOM NUMBER). UPDATE FOLLOWING ACCEPTANCE TESTING, IF CHANGED. D. REPRODUCED SCHEMATIC WIRING DIAGRAMS OF THE AUDIO/VIDEO SYSTEMS, BASED ON THE AS-BUILT DOCUMENTATION, ATA REDUCED SCALE EASY TO HANDLE BUT FULLY LEGIBLE. E. REPLACEMENT PARTS LISTS OF MAJOR ITEMS OF EQUIPMENT. F. PRODUCE COMPACT SYSTEM SCHEMATICS SHOWING ALL COMPONENTS, CABLES, AND WIRE NUMBERS THAT WILL BE MOUNTED ON THE WALL OF THE TRUCK DOCK AND ENGINEERING RACK ROOM. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 09084 | Review Response | Approved as Noted | 2020-10-28 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 12025 | Responded and Closed | Approved as Noted | 2020-10-29 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-12 |  | 27 41 32-1.1 Broadcast Cabling General.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-12 |  | 27 41 32-1.1 Broadcast Cabling General.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-10-12 |  | 27 41 32-1.1 Broadcast Cabling General.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-29 02:00 |  | 27 41 32-1.1 Broadcast Cabling General i!i reviewed_POP.pdf
27 41 32-001-02 | 27 41 32 - BROADCAST CABLING | 27 41 32-001-02 BROADCAST CABLING - General | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-23 | Responded and Closed - Approved |  | Brian Elwell (Idibri) |  |  |  | 2020-12-09 | 2020-12-03 | 11 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09661 | Received | For Review | 2020-11-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-09 | Submittal Number: 27 41 32-1.2 From: ELLA PILGRIM Final Due Date: 12/08/20 Subject: BROADCAST CABLING - GENERAL Description: A BID SUBMITTALS: 1 CONTRACTOR'S QUALIFICATIONS: HAVE PREVIOUSLY INSTALLED AT LEAST 3 JOBS OF SIMILAR MAGNITUDE IN SPORTS VENUES, COMPLETED WITHIN THE LAST FIVE YEARS. PROVIDE NAME AND PHONE NUMBER OF REFERENCE FOR EACH REPRESENTATIVE PROJECT. IDENTIFY AT LEAST ONE SUCH COMPLETED JOB AVAILABLE FOR INSPECTION BY CONSULTANT OR OWNERS REPRESENTATIVE. 2 BIDDER WILL CONFIRM IN WRITING THAT THE FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 3 BIDDING CONTRACTOR WILL IDENTIFY ALL SUB-CONTRACTORS ON THE BID RESPONSE TEAM ANDA DETAILED SCOPE OF WORK FOR EACH SUB-CONTRACTOR. 4 BIDDER WILL CONFIRM IN WRITING THAT ANY SUB-CONTRACTOR FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE SUB-CONTRACTING FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 5 PROVIDE RESUMES OF PROJECT MANAGER, LEAD ENGINEER AND LEAD INSTALLERS WORKING ON THIS PROJECT. THIS WILL INCLUDE KEY TEAM MEMBERS OF ANY SUB CONTRACTOR. RESUMES MUST BE SUBMITTED WITH THIS BID RESPONSE 6 PROVIDEA SCHEDULE OF VALUES WITH UNIT PRICES FOR ALL SYSTEMS. SCHEDULE OF VALUES WILL BE USED FOR ANY ADD OR DEDUCT CHANGE ORDERS. BID RESPONSES WITHOUT SCHEDULE OF VALUES WILL BE RETURNED WITHOUT REVIEW. BIDDING CONTRACTOR WILL SUBMIT SPREADSHEET FORMATTED BY SPECIFICATION SECTION INDICATING MANUFACTURERS, MODEL NUMBERS, DESCRIPTIONS, TOTAL QUANTITIES, UNIT COSTS, AND EXTENDED COSTS. ATTACH SCHEDULE OF VALUES AT END OF BID FORM. B PROJECT SUBMITTALS: 1 PRODUCT DATA: SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT IN ACCORDANCE WITH PART 1 OF THE PROJECT MANUALS. 2 SHOP DRAWINGS: INDICATE COMPLETE DETAILS AND DIMENSIONS OF WORK TO BE PERFORMED AND INDICATE TYPES AND LOCATIONS OF EQUIPMENT, FABRICATED EQUIPMENT, AND OTHER DETAILS TO COMPLETELY DESCRIBE WORK TO BE PERFORMED. THERE SHALL BE NO WORK AUTHORIZED ON SITE WITHOUT THE PRIOR SUBMITTAL OFA COMPLETE SET OF SHOP DRAWINGS. ANY EXCEPTIONS TO THIS MUST BE IN WRITING AND APPROVED BY THE ARCHITECT. DETAILS TO INCLUDE THE FOLLOWING: A. WIRING SCHEMATIC. COMPLETE, DETAILED WIRING SCHEMATIC FOR ALL SYSTEMS, BASED ON THE CONTRACT DOCUMENTS BUT INCLUDING CABLE TYPES, IDENTIFICATION BY NUMBER AND COLOR CODES, AND DETAILED WIRING OF CONNECTIONS, BOTH AT EQUIPMENT AND BETWEEN EQUIPMENT RACKS AND WIRING IN CONDUIT. B. CONDUIT RISER DIAGRAMS FOR ALL SYSTEMS. C. RACK LAYOUT AND LOCATION DIAGRAMS WITH OVERALL DIMENSIONS. D. SCHEDULE OF TERMINATIONS FOR ALL SYSTEMS. E. TERMINAL STRIP LAYOUTS FOR ALL PROPOSED TERMINAL STRIPS TO BE USED IN JUNCTION BOXES OR IN THE EQUIPMENT RACKS. F. PANEL FABRICATION DETAILS INCLUDINGA PANEL ENGRAVING SCHEDULE. G. CABLE PULL LIST. SUBMIT ALL WIRING PULL LENGTHS FROM SOURCE TO DESTINATION. INCLUDE WIRE NUMBERS. H. SCHEMATIC DRAWINGS OF ANY CUSTOM CIRCUITRY OR EQUIPMENT MODIFICATIONS, INCLUDING CONNECTOR PINOUTS AND COMPONENT LISTS. I. PROVIDE COLOR INFORMATION FOR ALL RACKS AND ENCLOSURES SHOWN ON DRAWINGS. 3 CABLE AND CONNECTOR SUBMITTAL. SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24 IN LENGTH. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. C CONTRACT CLOSEOUT SUBMITTALS 1 KEEPA COMPLETE SET OF APPROVED SHOP DRAWINGS ON THE JOB AT ALL TIMES. NOTE ANY CHANGES MADE DURING INSTALLATION ONA SINGLE SET OF DRAWINGS. THIS SET OF MARKED UP DRAWINGS WILL NOT LEAVE THE JOBSITE UNTIL AFTER THE FINAL SYSTEM COMMISSIONING. SUBMIT TWO (2) CORRECTED SETS OF REPRODUCIBLE DRAWINGS SHOWING WORK AS INSTALLED. ALL AS-BUILT DRAWINGS TO BE PROVIDED BOTH IN ELECTRONIC FORM (ACAD 2012 OR LATER) AND IN HARD COPY (42X30). 2 SYSTEM REFERENCE MANUAL: PRIOR TO OWNER TRAINING, FURNISH 1 COPY, IN 3 RING BINDERS, SIZED TO HOLD THE MATERIAL PLUS 50% EXCESS, WITH CLEAR VINYL POCKETS ON COVER AND SPINE FOR PROJECT TITLE. PROVIDE TABULAR DIVIDERS WITH PERMANENT LEGENDS FOR THE FOLLOWING SECTIONS: A. A LEGEND OF ACRONYMS AND ABBREVIATIONS MUST ACCOMPANY ALL DOCUMENTATION. B. A LIST OF ALL TEST RESULTS PERFORMED ON THE SYSTEMS AS OUTLINED IN SECTION 3.5 PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE. C. A LIST OF ALL EQUIPMENT, INDICATING MANUFACTURER, MODEL, SERIAL NUMBER, AND EQUIPMENT LOCATION (I.E. RACK/ROOM NUMBER). UPDATE FOLLOWING ACCEPTANCE TESTING, IF CHANGED. D. REPRODUCED SCHEMATIC WIRING DIAGRAMS OF THE AUDIO/VIDEO SYSTEMS, BASED ON THE AS-BUILT DOCUMENTATION, ATA REDUCED SCALE EASY TO HANDLE BUT FULLY LEGIBLE. E. REPLACEMENT PARTS LISTS OF MAJOR ITEMS OF EQUIPMENT. F. PRODUCE COMPACT SYSTEM SCHEMATICS SHOWING ALL COMPONENTS, CABLES, AND WIRE NUMBERS THAT WILL BE MOUNTED ON THE WALL OF THE TRUCK DOCK AND ENGINEERING RACK ROOM. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 12712 | Forwarded | For Review | 2020-11-23 | Populous SCA_CCA | Brian Elwell (Idibri) | 2020-11-30 | Submittal Number: 27 41 32-1.2 From: ELLA PILGRIM Final Due Date: 12/08/20 Subject: BROADCAST CABLING - GENERAL Description: A BID SUBMITTALS: 1 CONTRACTOR'S QUALIFICATIONS: HAVE PREVIOUSLY INSTALLED AT LEAST 3 JOBS OF SIMILAR MAGNITUDE IN SPORTS VENUES, COMPLETED WITHIN THE LAST FIVE YEARS. PROVIDE NAME AND PHONE NUMBER OF REFERENCE FOR EACH REPRESENTATIVE PROJECT. IDENTIFY AT LEAST ONE SUCH COMPLETED JOB AVAILABLE FOR INSPECTION BY CONSULTANT OR OWNERS REPRESENTATIVE. 2 BIDDER WILL CONFIRM IN WRITING THAT THE FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 3 BIDDING CONTRACTOR WILL IDENTIFY ALL SUB-CONTRACTORS ON THE BID RESPONSE TEAM ANDA DETAILED SCOPE OF WORK FOR EACH SUB-CONTRACTOR. 4 BIDDER WILL CONFIRM IN WRITING THAT ANY SUB-CONTRACTOR FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE SUB-CONTRACTING FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 5 PROVIDE RESUMES OF PROJECT MANAGER, LEAD ENGINEER AND LEAD INSTALLERS WORKING ON THIS PROJECT. THIS WILL INCLUDE KEY TEAM MEMBERS OF ANY SUB CONTRACTOR. RESUMES MUST BE SUBMITTED WITH THIS BID RESPONSE 6 PROVIDEA SCHEDULE OF VALUES WITH UNIT PRICES FOR ALL SYSTEMS. SCHEDULE OF VALUES WILL BE USED FOR ANY ADD OR DEDUCT CHANGE ORDERS. BID RESPONSES WITHOUT SCHEDULE OF VALUES WILL BE RETURNED WITHOUT REVIEW. BIDDING CONTRACTOR WILL SUBMIT SPREADSHEET FORMATTED BY SPECIFICATION SECTION INDICATING MANUFACTURERS, MODEL NUMBERS, DESCRIPTIONS, TOTAL QUANTITIES, UNIT COSTS, AND EXTENDED COSTS. ATTACH SCHEDULE OF VALUES AT END OF BID FORM. B PROJECT SUBMITTALS: 1 PRODUCT DATA: SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT IN ACCORDANCE WITH PART 1 OF THE PROJECT MANUALS. 2 SHOP DRAWINGS: INDICATE COMPLETE DETAILS AND DIMENSIONS OF WORK TO BE PERFORMED AND INDICATE TYPES AND LOCATIONS OF EQUIPMENT, FABRICATED EQUIPMENT, AND OTHER DETAILS TO COMPLETELY DESCRIBE WORK TO BE PERFORMED. THERE SHALL BE NO WORK AUTHORIZED ON SITE WITHOUT THE PRIOR SUBMITTAL OFA COMPLETE SET OF SHOP DRAWINGS. ANY EXCEPTIONS TO THIS MUST BE IN WRITING AND APPROVED BY THE ARCHITECT. DETAILS TO INCLUDE THE FOLLOWING: A. WIRING SCHEMATIC. COMPLETE, DETAILED WIRING SCHEMATIC FOR ALL SYSTEMS, BASED ON THE CONTRACT DOCUMENTS BUT INCLUDING CABLE TYPES, IDENTIFICATION BY NUMBER AND COLOR CODES, AND DETAILED WIRING OF CONNECTIONS, BOTH AT EQUIPMENT AND BETWEEN EQUIPMENT RACKS AND WIRING IN CONDUIT. B. CONDUIT RISER DIAGRAMS FOR ALL SYSTEMS. C. RACK LAYOUT AND LOCATION DIAGRAMS WITH OVERALL DIMENSIONS. D. SCHEDULE OF TERMINATIONS FOR ALL SYSTEMS. E. TERMINAL STRIP LAYOUTS FOR ALL PROPOSED TERMINAL STRIPS TO BE USED IN JUNCTION BOXES OR IN THE EQUIPMENT RACKS. F. PANEL FABRICATION DETAILS INCLUDINGA PANEL ENGRAVING SCHEDULE. G. CABLE PULL LIST. SUBMIT ALL WIRING PULL LENGTHS FROM SOURCE TO DESTINATION. INCLUDE WIRE NUMBERS. H. SCHEMATIC DRAWINGS OF ANY CUSTOM CIRCUITRY OR EQUIPMENT MODIFICATIONS, INCLUDING CONNECTOR PINOUTS AND COMPONENT LISTS. I. PROVIDE COLOR INFORMATION FOR ALL RACKS AND ENCLOSURES SHOWN ON DRAWINGS. 3 CABLE AND CONNECTOR SUBMITTAL. SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24 IN LENGTH. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. C CONTRACT CLOSEOUT SUBMITTALS 1 KEEPA COMPLETE SET OF APPROVED SHOP DRAWINGS ON THE JOB AT ALL TIMES. NOTE ANY CHANGES MADE DURING INSTALLATION ONA SINGLE SET OF DRAWINGS. THIS SET OF MARKED UP DRAWINGS WILL NOT LEAVE THE JOBSITE UNTIL AFTER THE FINAL SYSTEM COMMISSIONING. SUBMIT TWO (2) CORRECTED SETS OF REPRODUCIBLE DRAWINGS SHOWING WORK AS INSTALLED. ALL AS-BUILT DRAWINGS TO BE PROVIDED BOTH IN ELECTRONIC FORM (ACAD 2012 OR LATER) AND IN HARD COPY (42X30). 2 SYSTEM REFERENCE MANUAL: PRIOR TO OWNER TRAINING, FURNISH 1 COPY, IN 3 RING BINDERS, SIZED TO HOLD THE MATERIAL PLUS 50% EXCESS, WITH CLEAR VINYL POCKETS ON COVER AND SPINE FOR PROJECT TITLE. PROVIDE TABULAR DIVIDERS WITH PERMANENT LEGENDS FOR THE FOLLOWING SECTIONS: A. A LEGEND OF ACRONYMS AND ABBREVIATIONS MUST ACCOMPANY ALL DOCUMENTATION. B. A LIST OF ALL TEST RESULTS PERFORMED ON THE SYSTEMS AS OUTLINED IN SECTION 3.5 PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE. C. A LIST OF ALL EQUIPMENT, INDICATING MANUFACTURER, MODEL, SERIAL NUMBER, AND EQUIPMENT LOCATION (I.E. RACK/ROOM NUMBER). UPDATE FOLLOWING ACCEPTANCE TESTING, IF CHANGED. D. REPRODUCED SCHEMATIC WIRING DIAGRAMS OF THE AUDIO/VIDEO SYSTEMS, BASED ON THE AS-BUILT DOCUMENTATION, ATA REDUCED SCALE EASY TO HANDLE BUT FULLY LEGIBLE. E. REPLACEMENT PARTS LISTS OF MAJOR ITEMS OF EQUIPMENT. F. PRODUCE COMPACT SYSTEM SCHEMATICS SHOWING ALL COMPONENTS, CABLES, AND WIRE NUMBERS THAT WILL BE MOUNTED ON THE WALL OF THE TRUCK DOCK AND ENGINEERING RACK ROOM. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 09872 | Review Response | Approved | 2020-11-23 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 12955 | Responded and Closed | Approved | 2020-12-03 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-21 |  | 27 41 32-1.2 Broadcast Cabling General.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-21 |  | 27 41 32-1.2 Broadcast Cabling General.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-11-21 |  | 27 41 32-1.2 Broadcast Cabling General.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-03 |  | 27 41 32-1.2 Broadcast Cabling General_Idibri_POP.pdf
27 41 32-001-03 | 27 41 32 - BROADCAST CABLING | 27 41 32-001-03 BROADCAST CABLING - General | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-09 | Responded and Closed - Approved |  | Brian Elwell (Idibri) |  |  |  | 2020-12-23 | 2020-12-29 | 21 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-12-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10061 | Received | For Review | 2020-12-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Ella Pilgrim (M.A. Mortenson Company) | 2020-12-23 | Submittal Number: 27 41 32-1.3 From: ELLA PILGRIM Final Due Date: 12/24/20 Subject: BROADCAST CABLING - GENERAL Description: A BID SUBMITTALS: 1 CONTRACTOR'S QUALIFICATIONS: HAVE PREVIOUSLY INSTALLED AT LEAST 3 JOBS OF SIMILAR MAGNITUDE IN SPORTS VENUES, COMPLETED WITHIN THE LAST FIVE YEARS. PROVIDE NAME AND PHONE NUMBER OF REFERENCE FOR EACH REPRESENTATIVE PROJECT. IDENTIFY AT LEAST ONE SUCH COMPLETED JOB AVAILABLE FOR INSPECTION BY CONSULTANT OR OWNERS REPRESENTATIVE. 2 BIDDER WILL CONFIRM IN WRITING THAT THE FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 3 BIDDING CONTRACTOR WILL IDENTIFY ALL SUB-CONTRACTORS ON THE BID RESPONSE TEAM ANDA DETAILED SCOPE OF WORK FOR EACH SUB-CONTRACTOR. 4 BIDDER WILL CONFIRM IN WRITING THAT ANY SUB-CONTRACTOR FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE SUB-CONTRACTING FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 5 PROVIDE RESUMES OF PROJECT MANAGER, LEAD ENGINEER AND LEAD INSTALLERS WORKING ON THIS PROJECT. THIS WILL INCLUDE KEY TEAM MEMBERS OF ANY SUB CONTRACTOR. RESUMES MUST BE SUBMITTED WITH THIS BID RESPONSE 6 PROVIDEA SCHEDULE OF VALUES WITH UNIT PRICES FOR ALL SYSTEMS. SCHEDULE OF VALUES WILL BE USED FOR ANY ADD OR DEDUCT CHANGE ORDERS. BID RESPONSES WITHOUT SCHEDULE OF VALUES WILL BE RETURNED WITHOUT REVIEW. BIDDING CONTRACTOR WILL SUBMIT SPREADSHEET FORMATTED BY SPECIFICATION SECTION INDICATING MANUFACTURERS, MODEL NUMBERS, DESCRIPTIONS, TOTAL QUANTITIES, UNIT COSTS, AND EXTENDED COSTS. ATTACH SCHEDULE OF VALUES AT END OF BID FORM. B PROJECT SUBMITTALS: 1 PRODUCT DATA: SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT IN ACCORDANCE WITH PART 1 OF THE PROJECT MANUALS. 2 SHOP DRAWINGS: INDICATE COMPLETE DETAILS AND DIMENSIONS OF WORK TO BE PERFORMED AND INDICATE TYPES AND LOCATIONS OF EQUIPMENT, FABRICATED EQUIPMENT, AND OTHER DETAILS TO COMPLETELY DESCRIBE WORK TO BE PERFORMED. THERE SHALL BE NO WORK AUTHORIZED ON SITE WITHOUT THE PRIOR SUBMITTAL OFA COMPLETE SET OF SHOP DRAWINGS. ANY EXCEPTIONS TO THIS MUST BE IN WRITING AND APPROVED BY THE ARCHITECT. DETAILS TO INCLUDE THE FOLLOWING: A. WIRING SCHEMATIC. COMPLETE, DETAILED WIRING SCHEMATIC FOR ALL SYSTEMS, BASED ON THE CONTRACT DOCUMENTS BUT INCLUDING CABLE TYPES, IDENTIFICATION BY NUMBER AND COLOR CODES, AND DETAILED WIRING OF CONNECTIONS, BOTH AT EQUIPMENT AND BETWEEN EQUIPMENT RACKS AND WIRING IN CONDUIT. B. CONDUIT RISER DIAGRAMS FOR ALL SYSTEMS. C. RACK LAYOUT AND LOCATION DIAGRAMS WITH OVERALL DIMENSIONS. D. SCHEDULE OF TERMINATIONS FOR ALL SYSTEMS. E. TERMINAL STRIP LAYOUTS FOR ALL PROPOSED TERMINAL STRIPS TO BE USED IN JUNCTION BOXES OR IN THE EQUIPMENT RACKS. F. PANEL FABRICATION DETAILS INCLUDINGA PANEL ENGRAVING SCHEDULE. G. CABLE PULL LIST. SUBMIT ALL WIRING PULL LENGTHS FROM SOURCE TO DESTINATION. INCLUDE WIRE NUMBERS. H. SCHEMATIC DRAWINGS OF ANY CUSTOM CIRCUITRY OR EQUIPMENT MODIFICATIONS, INCLUDING CONNECTOR PINOUTS AND COMPONENT LISTS. I. PROVIDE COLOR INFORMATION FOR ALL RACKS AND ENCLOSURES SHOWN ON DRAWINGS. 3 CABLE AND CONNECTOR SUBMITTAL. SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24 IN LENGTH. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. C CONTRACT CLOSEOUT SUBMITTALS 1 KEEPA COMPLETE SET OF APPROVED SHOP DRAWINGS ON THE JOB AT ALL TIMES. NOTE ANY CHANGES MADE DURING INSTALLATION ONA SINGLE SET OF DRAWINGS. THIS SET OF MARKED UP DRAWINGS WILL NOT LEAVE THE JOBSITE UNTIL AFTER THE FINAL SYSTEM COMMISSIONING. SUBMIT TWO (2) CORRECTED SETS OF REPRODUCIBLE DRAWINGS SHOWING WORK AS INSTALLED. ALL AS-BUILT DRAWINGS TO BE PROVIDED BOTH IN ELECTRONIC FORM (ACAD 2012 OR LATER) AND IN HARD COPY (42X30). 2 SYSTEM REFERENCE MANUAL: PRIOR TO OWNER TRAINING, FURNISH 1 COPY, IN 3 RING BINDERS, SIZED TO HOLD THE MATERIAL PLUS 50% EXCESS, WITH CLEAR VINYL POCKETS ON COVER AND SPINE FOR PROJECT TITLE. PROVIDE TABULAR DIVIDERS WITH PERMANENT LEGENDS FOR THE FOLLOWING SECTIONS: A. A LEGEND OF ACRONYMS AND ABBREVIATIONS MUST ACCOMPANY ALL DOCUMENTATION. B. A LIST OF ALL TEST RESULTS PERFORMED ON THE SYSTEMS AS OUTLINED IN SECTION 3.5 PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE. C. A LIST OF ALL EQUIPMENT, INDICATING MANUFACTURER, MODEL, SERIAL NUMBER, AND EQUIPMENT LOCATION (I.E. RACK/ROOM NUMBER). UPDATE FOLLOWING ACCEPTANCE TESTING, IF CHANGED. D. REPRODUCED SCHEMATIC WIRING DIAGRAMS OF THE AUDIO/VIDEO SYSTEMS, BASED ON THE AS-BUILT DOCUMENTATION, ATA REDUCED SCALE EASY TO HANDLE BUT FULLY LEGIBLE. E. REPLACEMENT PARTS LISTS OF MAJOR ITEMS OF EQUIPMENT. F. PRODUCE COMPACT SYSTEM SCHEMATICS SHOWING ALL COMPONENTS, CABLES, AND WIRE NUMBERS THAT WILL BE MOUNTED ON THE WALL OF THE TRUCK DOCK AND ENGINEERING RACK ROOM. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 13161 | Forwarded | For Review | 2020-12-09 | Ella Pilgrim (M.A. Mortenson Company) | Brian Elwell (Idibri) | 2020-12-16 | Submittal Number: 27 41 32-1.3 From: ELLA PILGRIM Final Due Date: 12/24/20 Subject: BROADCAST CABLING - GENERAL Description: A BID SUBMITTALS: 1 CONTRACTOR'S QUALIFICATIONS: HAVE PREVIOUSLY INSTALLED AT LEAST 3 JOBS OF SIMILAR MAGNITUDE IN SPORTS VENUES, COMPLETED WITHIN THE LAST FIVE YEARS. PROVIDE NAME AND PHONE NUMBER OF REFERENCE FOR EACH REPRESENTATIVE PROJECT. IDENTIFY AT LEAST ONE SUCH COMPLETED JOB AVAILABLE FOR INSPECTION BY CONSULTANT OR OWNERS REPRESENTATIVE. 2 BIDDER WILL CONFIRM IN WRITING THAT THE FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 3 BIDDING CONTRACTOR WILL IDENTIFY ALL SUB-CONTRACTORS ON THE BID RESPONSE TEAM ANDA DETAILED SCOPE OF WORK FOR EACH SUB-CONTRACTOR. 4 BIDDER WILL CONFIRM IN WRITING THAT ANY SUB-CONTRACTOR FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE SUB-CONTRACTING FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 5 PROVIDE RESUMES OF PROJECT MANAGER, LEAD ENGINEER AND LEAD INSTALLERS WORKING ON THIS PROJECT. THIS WILL INCLUDE KEY TEAM MEMBERS OF ANY SUB CONTRACTOR. RESUMES MUST BE SUBMITTED WITH THIS BID RESPONSE 6 PROVIDEA SCHEDULE OF VALUES WITH UNIT PRICES FOR ALL SYSTEMS. SCHEDULE OF VALUES WILL BE USED FOR ANY ADD OR DEDUCT CHANGE ORDERS. BID RESPONSES WITHOUT SCHEDULE OF VALUES WILL BE RETURNED WITHOUT REVIEW. BIDDING CONTRACTOR WILL SUBMIT SPREADSHEET FORMATTED BY SPECIFICATION SECTION INDICATING MANUFACTURERS, MODEL NUMBERS, DESCRIPTIONS, TOTAL QUANTITIES, UNIT COSTS, AND EXTENDED COSTS. ATTACH SCHEDULE OF VALUES AT END OF BID FORM. B PROJECT SUBMITTALS: 1 PRODUCT DATA: SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT IN ACCORDANCE WITH PART 1 OF THE PROJECT MANUALS. 2 SHOP DRAWINGS: INDICATE COMPLETE DETAILS AND DIMENSIONS OF WORK TO BE PERFORMED AND INDICATE TYPES AND LOCATIONS OF EQUIPMENT, FABRICATED EQUIPMENT, AND OTHER DETAILS TO COMPLETELY DESCRIBE WORK TO BE PERFORMED. THERE SHALL BE NO WORK AUTHORIZED ON SITE WITHOUT THE PRIOR SUBMITTAL OFA COMPLETE SET OF SHOP DRAWINGS. ANY EXCEPTIONS TO THIS MUST BE IN WRITING AND APPROVED BY THE ARCHITECT. DETAILS TO INCLUDE THE FOLLOWING: A. WIRING SCHEMATIC. COMPLETE, DETAILED WIRING SCHEMATIC FOR ALL SYSTEMS, BASED ON THE CONTRACT DOCUMENTS BUT INCLUDING CABLE TYPES, IDENTIFICATION BY NUMBER AND COLOR CODES, AND DETAILED WIRING OF CONNECTIONS, BOTH AT EQUIPMENT AND BETWEEN EQUIPMENT RACKS AND WIRING IN CONDUIT. B. CONDUIT RISER DIAGRAMS FOR ALL SYSTEMS. C. RACK LAYOUT AND LOCATION DIAGRAMS WITH OVERALL DIMENSIONS. D. SCHEDULE OF TERMINATIONS FOR ALL SYSTEMS. E. TERMINAL STRIP LAYOUTS FOR ALL PROPOSED TERMINAL STRIPS TO BE USED IN JUNCTION BOXES OR IN THE EQUIPMENT RACKS. F. PANEL FABRICATION DETAILS INCLUDINGA PANEL ENGRAVING SCHEDULE. G. CABLE PULL LIST. SUBMIT ALL WIRING PULL LENGTHS FROM SOURCE TO DESTINATION. INCLUDE WIRE NUMBERS. H. SCHEMATIC DRAWINGS OF ANY CUSTOM CIRCUITRY OR EQUIPMENT MODIFICATIONS, INCLUDING CONNECTOR PINOUTS AND COMPONENT LISTS. I. PROVIDE COLOR INFORMATION FOR ALL RACKS AND ENCLOSURES SHOWN ON DRAWINGS. 3 CABLE AND CONNECTOR SUBMITTAL. SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24 IN LENGTH. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. C CONTRACT CLOSEOUT SUBMITTALS 1 KEEPA COMPLETE SET OF APPROVED SHOP DRAWINGS ON THE JOB AT ALL TIMES. NOTE ANY CHANGES MADE DURING INSTALLATION ONA SINGLE SET OF DRAWINGS. THIS SET OF MARKED UP DRAWINGS WILL NOT LEAVE THE JOBSITE UNTIL AFTER THE FINAL SYSTEM COMMISSIONING. SUBMIT TWO (2) CORRECTED SETS OF REPRODUCIBLE DRAWINGS SHOWING WORK AS INSTALLED. ALL AS-BUILT DRAWINGS TO BE PROVIDED BOTH IN ELECTRONIC FORM (ACAD 2012 OR LATER) AND IN HARD COPY (42X30). 2 SYSTEM REFERENCE MANUAL: PRIOR TO OWNER TRAINING, FURNISH 1 COPY, IN 3 RING BINDERS, SIZED TO HOLD THE MATERIAL PLUS 50% EXCESS, WITH CLEAR VINYL POCKETS ON COVER AND SPINE FOR PROJECT TITLE. PROVIDE TABULAR DIVIDERS WITH PERMANENT LEGENDS FOR THE FOLLOWING SECTIONS: A. A LEGEND OF ACRONYMS AND ABBREVIATIONS MUST ACCOMPANY ALL DOCUMENTATION. B. A LIST OF ALL TEST RESULTS PERFORMED ON THE SYSTEMS AS OUTLINED IN SECTION 3.5 PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE. C. A LIST OF ALL EQUIPMENT, INDICATING MANUFACTURER, MODEL, SERIAL NUMBER, AND EQUIPMENT LOCATION (I.E. RACK/ROOM NUMBER). UPDATE FOLLOWING ACCEPTANCE TESTING, IF CHANGED. D. REPRODUCED SCHEMATIC WIRING DIAGRAMS OF THE AUDIO/VIDEO SYSTEMS, BASED ON THE AS-BUILT DOCUMENTATION, ATA REDUCED SCALE EASY TO HANDLE BUT FULLY LEGIBLE. E. REPLACEMENT PARTS LISTS OF MAJOR ITEMS OF EQUIPMENT. F. PRODUCE COMPACT SYSTEM SCHEMATICS SHOWING ALL COMPONENTS, CABLES, AND WIRE NUMBERS THAT WILL BE MOUNTED ON THE WALL OF THE TRUCK DOCK AND ENGINEERING RACK ROOM. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 10359 | Review Response | Approved | 2020-12-17 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 13535 | Responded and Closed | Approved | 2020-12-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-09 |  | 27 41 32-1.3 Broadcast Cabling General.pdf
| Forwarded |  | Ella Pilgrim (Mortenson Construction) | 1 | 2020-12-09 |  | 27 41 32-1.3 Broadcast Cabling General.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-12-09 |  | 27 41 32-1.3 Broadcast Cabling General.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-17 |  | 27 41 32-1.3 Broadcast Cabling General_Idibri_POP.pdf
27 41 32-001-04 | 27 41 32 - BROADCAST CABLING | 27 41 32-001-04 BROADCAST CABLING - General | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-19 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri) |  |  |  | 2021-02-02 | 2021-02-04 | 17 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-02-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10771 | Received | For Review | 2021-01-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-02 | Submittal Number: 27 41 32-1.4 From: ELLA PILGRIM Final Due Date: 02/03/21 Subject: BROADCAST CABLING - GENERAL Description: A BID SUBMITTALS: 1 CONTRACTOR'S QUALIFICATIONS: HAVE PREVIOUSLY INSTALLED AT LEAST 3 JOBS OF SIMILAR MAGNITUDE IN SPORTS VENUES, COMPLETED WITHIN THE LAST FIVE YEARS. PROVIDE NAME AND PHONE NUMBER OF REFERENCE FOR EACH REPRESENTATIVE PROJECT. IDENTIFY AT LEAST ONE SUCH COMPLETED JOB AVAILABLE FOR INSPECTION BY CONSULTANT OR OWNERS REPRESENTATIVE. 2 BIDDER WILL CONFIRM IN WRITING THAT THE FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 3 BIDDING CONTRACTOR WILL IDENTIFY ALL SUB-CONTRACTORS ON THE BID RESPONSE TEAM ANDA DETAILED SCOPE OF WORK FOR EACH SUB-CONTRACTOR. 4 BIDDER WILL CONFIRM IN WRITING THAT ANY SUB-CONTRACTOR FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE SUB-CONTRACTING FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 5 PROVIDE RESUMES OF PROJECT MANAGER, LEAD ENGINEER AND LEAD INSTALLERS WORKING ON THIS PROJECT. THIS WILL INCLUDE KEY TEAM MEMBERS OF ANY SUB CONTRACTOR. RESUMES MUST BE SUBMITTED WITH THIS BID RESPONSE 6 PROVIDEA SCHEDULE OF VALUES WITH UNIT PRICES FOR ALL SYSTEMS. SCHEDULE OF VALUES WILL BE USED FOR ANY ADD OR DEDUCT CHANGE ORDERS. BID RESPONSES WITHOUT SCHEDULE OF VALUES WILL BE RETURNED WITHOUT REVIEW. BIDDING CONTRACTOR WILL SUBMIT SPREADSHEET FORMATTED BY SPECIFICATION SECTION INDICATING MANUFACTURERS, MODEL NUMBERS, DESCRIPTIONS, TOTAL QUANTITIES, UNIT COSTS, AND EXTENDED COSTS. ATTACH SCHEDULE OF VALUES AT END OF BID FORM. B PROJECT SUBMITTALS: 1 PRODUCT DATA: SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT IN ACCORDANCE WITH PART 1 OF THE PROJECT MANUALS. 2 SHOP DRAWINGS: INDICATE COMPLETE DETAILS AND DIMENSIONS OF WORK TO BE PERFORMED AND INDICATE TYPES AND LOCATIONS OF EQUIPMENT, FABRICATED EQUIPMENT, AND OTHER DETAILS TO COMPLETELY DESCRIBE WORK TO BE PERFORMED. THERE SHALL BE NO WORK AUTHORIZED ON SITE WITHOUT THE PRIOR SUBMITTAL OFA COMPLETE SET OF SHOP DRAWINGS. ANY EXCEPTIONS TO THIS MUST BE IN WRITING AND APPROVED BY THE ARCHITECT. DETAILS TO INCLUDE THE FOLLOWING: A. WIRING SCHEMATIC. COMPLETE, DETAILED WIRING SCHEMATIC FOR ALL SYSTEMS, BASED ON THE CONTRACT DOCUMENTS BUT INCLUDING CABLE TYPES, IDENTIFICATION BY NUMBER AND COLOR CODES, AND DETAILED WIRING OF CONNECTIONS, BOTH AT EQUIPMENT AND BETWEEN EQUIPMENT RACKS AND WIRING IN CONDUIT. B. CONDUIT RISER DIAGRAMS FOR ALL SYSTEMS. C. RACK LAYOUT AND LOCATION DIAGRAMS WITH OVERALL DIMENSIONS. D. SCHEDULE OF TERMINATIONS FOR ALL SYSTEMS. E. TERMINAL STRIP LAYOUTS FOR ALL PROPOSED TERMINAL STRIPS TO BE USED IN JUNCTION BOXES OR IN THE EQUIPMENT RACKS. F. PANEL FABRICATION DETAILS INCLUDINGA PANEL ENGRAVING SCHEDULE. G. CABLE PULL LIST. SUBMIT ALL WIRING PULL LENGTHS FROM SOURCE TO DESTINATION. INCLUDE WIRE NUMBERS. H. SCHEMATIC DRAWINGS OF ANY CUSTOM CIRCUITRY OR EQUIPMENT MODIFICATIONS, INCLUDING CONNECTOR PINOUTS AND COMPONENT LISTS. I. PROVIDE COLOR INFORMATION FOR ALL RACKS AND ENCLOSURES SHOWN ON DRAWINGS. 3 CABLE AND CONNECTOR SUBMITTAL. SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24 IN LENGTH. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. C CONTRACT CLOSEOUT SUBMITTALS 1 KEEPA COMPLETE SET OF APPROVED SHOP DRAWINGS ON THE JOB AT ALL TIMES. NOTE ANY CHANGES MADE DURING INSTALLATION ONA SINGLE SET OF DRAWINGS. THIS SET OF MARKED UP DRAWINGS WILL NOT LEAVE THE JOBSITE UNTIL AFTER THE FINAL SYSTEM COMMISSIONING. SUBMIT TWO (2) CORRECTED SETS OF REPRODUCIBLE DRAWINGS SHOWING WORK AS INSTALLED. ALL AS-BUILT DRAWINGS TO BE PROVIDED BOTH IN ELECTRONIC FORM (ACAD 2012 OR LATER) AND IN HARD COPY (42X30). 2 SYSTEM REFERENCE MANUAL: PRIOR TO OWNER TRAINING, FURNISH 1 COPY, IN 3 RING BINDERS, SIZED TO HOLD THE MATERIAL PLUS 50% EXCESS, WITH CLEAR VINYL POCKETS ON COVER AND SPINE FOR PROJECT TITLE. PROVIDE TABULAR DIVIDERS WITH PERMANENT LEGENDS FOR THE FOLLOWING SECTIONS: A. A LEGEND OF ACRONYMS AND ABBREVIATIONS MUST ACCOMPANY ALL DOCUMENTATION. B. A LIST OF ALL TEST RESULTS PERFORMED ON THE SYSTEMS AS OUTLINED IN SECTION 3.5 PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE. C. A LIST OF ALL EQUIPMENT, INDICATING MANUFACTURER, MODEL, SERIAL NUMBER, AND EQUIPMENT LOCATION (I.E. RACK/ROOM NUMBER). UPDATE FOLLOWING ACCEPTANCE TESTING, IF CHANGED. D. REPRODUCED SCHEMATIC WIRING DIAGRAMS OF THE AUDIO/VIDEO SYSTEMS, BASED ON THE AS-BUILT DOCUMENTATION, ATA REDUCED SCALE EASY TO HANDLE BUT FULLY LEGIBLE. E. REPLACEMENT PARTS LISTS OF MAJOR ITEMS OF EQUIPMENT. F. PRODUCE COMPACT SYSTEM SCHEMATICS SHOWING ALL COMPONENTS, CABLES, AND WIRE NUMBERS THAT WILL BE MOUNTED ON THE WALL OF THE TRUCK DOCK AND ENGINEERING RACK ROOM. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 14008 | Forwarded | For Review | 2021-01-19 | Populous SCA_CCA | Brian Elwell (Idibri) | 2021-01-26 | Submittal Number: 27 41 32-1.4 From: ELLA PILGRIM Final Due Date: 02/03/21 Subject: BROADCAST CABLING - GENERAL Description: A BID SUBMITTALS: 1 CONTRACTOR'S QUALIFICATIONS: HAVE PREVIOUSLY INSTALLED AT LEAST 3 JOBS OF SIMILAR MAGNITUDE IN SPORTS VENUES, COMPLETED WITHIN THE LAST FIVE YEARS. PROVIDE NAME AND PHONE NUMBER OF REFERENCE FOR EACH REPRESENTATIVE PROJECT. IDENTIFY AT LEAST ONE SUCH COMPLETED JOB AVAILABLE FOR INSPECTION BY CONSULTANT OR OWNERS REPRESENTATIVE. 2 BIDDER WILL CONFIRM IN WRITING THAT THE FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 3 BIDDING CONTRACTOR WILL IDENTIFY ALL SUB-CONTRACTORS ON THE BID RESPONSE TEAM ANDA DETAILED SCOPE OF WORK FOR EACH SUB-CONTRACTOR. 4 BIDDER WILL CONFIRM IN WRITING THAT ANY SUB-CONTRACTOR FIRM HAS FIVE YEARS OF EXPERIENCE WITH EQUIPMENT AND SYSTEMS OF THE TYPES SPECIFIED, THAT THE SUB-CONTRACTING FIRM MAINTAINSA FULLY STAFFED AND EQUIPPED SERVICE FACILITY. 5 PROVIDE RESUMES OF PROJECT MANAGER, LEAD ENGINEER AND LEAD INSTALLERS WORKING ON THIS PROJECT. THIS WILL INCLUDE KEY TEAM MEMBERS OF ANY SUB CONTRACTOR. RESUMES MUST BE SUBMITTED WITH THIS BID RESPONSE 6 PROVIDEA SCHEDULE OF VALUES WITH UNIT PRICES FOR ALL SYSTEMS. SCHEDULE OF VALUES WILL BE USED FOR ANY ADD OR DEDUCT CHANGE ORDERS. BID RESPONSES WITHOUT SCHEDULE OF VALUES WILL BE RETURNED WITHOUT REVIEW. BIDDING CONTRACTOR WILL SUBMIT SPREADSHEET FORMATTED BY SPECIFICATION SECTION INDICATING MANUFACTURERS, MODEL NUMBERS, DESCRIPTIONS, TOTAL QUANTITIES, UNIT COSTS, AND EXTENDED COSTS. ATTACH SCHEDULE OF VALUES AT END OF BID FORM. B PROJECT SUBMITTALS: 1 PRODUCT DATA: SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT IN ACCORDANCE WITH PART 1 OF THE PROJECT MANUALS. 2 SHOP DRAWINGS: INDICATE COMPLETE DETAILS AND DIMENSIONS OF WORK TO BE PERFORMED AND INDICATE TYPES AND LOCATIONS OF EQUIPMENT, FABRICATED EQUIPMENT, AND OTHER DETAILS TO COMPLETELY DESCRIBE WORK TO BE PERFORMED. THERE SHALL BE NO WORK AUTHORIZED ON SITE WITHOUT THE PRIOR SUBMITTAL OFA COMPLETE SET OF SHOP DRAWINGS. ANY EXCEPTIONS TO THIS MUST BE IN WRITING AND APPROVED BY THE ARCHITECT. DETAILS TO INCLUDE THE FOLLOWING: A. WIRING SCHEMATIC. COMPLETE, DETAILED WIRING SCHEMATIC FOR ALL SYSTEMS, BASED ON THE CONTRACT DOCUMENTS BUT INCLUDING CABLE TYPES, IDENTIFICATION BY NUMBER AND COLOR CODES, AND DETAILED WIRING OF CONNECTIONS, BOTH AT EQUIPMENT AND BETWEEN EQUIPMENT RACKS AND WIRING IN CONDUIT. B. CONDUIT RISER DIAGRAMS FOR ALL SYSTEMS. C. RACK LAYOUT AND LOCATION DIAGRAMS WITH OVERALL DIMENSIONS. D. SCHEDULE OF TERMINATIONS FOR ALL SYSTEMS. E. TERMINAL STRIP LAYOUTS FOR ALL PROPOSED TERMINAL STRIPS TO BE USED IN JUNCTION BOXES OR IN THE EQUIPMENT RACKS. F. PANEL FABRICATION DETAILS INCLUDINGA PANEL ENGRAVING SCHEDULE. G. CABLE PULL LIST. SUBMIT ALL WIRING PULL LENGTHS FROM SOURCE TO DESTINATION. INCLUDE WIRE NUMBERS. H. SCHEMATIC DRAWINGS OF ANY CUSTOM CIRCUITRY OR EQUIPMENT MODIFICATIONS, INCLUDING CONNECTOR PINOUTS AND COMPONENT LISTS. I. PROVIDE COLOR INFORMATION FOR ALL RACKS AND ENCLOSURES SHOWN ON DRAWINGS. 3 CABLE AND CONNECTOR SUBMITTAL. SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24 IN LENGTH. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. C CONTRACT CLOSEOUT SUBMITTALS 1 KEEPA COMPLETE SET OF APPROVED SHOP DRAWINGS ON THE JOB AT ALL TIMES. NOTE ANY CHANGES MADE DURING INSTALLATION ONA SINGLE SET OF DRAWINGS. THIS SET OF MARKED UP DRAWINGS WILL NOT LEAVE THE JOBSITE UNTIL AFTER THE FINAL SYSTEM COMMISSIONING. SUBMIT TWO (2) CORRECTED SETS OF REPRODUCIBLE DRAWINGS SHOWING WORK AS INSTALLED. ALL AS-BUILT DRAWINGS TO BE PROVIDED BOTH IN ELECTRONIC FORM (ACAD 2012 OR LATER) AND IN HARD COPY (42X30). 2 SYSTEM REFERENCE MANUAL: PRIOR TO OWNER TRAINING, FURNISH 1 COPY, IN 3 RING BINDERS, SIZED TO HOLD THE MATERIAL PLUS 50% EXCESS, WITH CLEAR VINYL POCKETS ON COVER AND SPINE FOR PROJECT TITLE. PROVIDE TABULAR DIVIDERS WITH PERMANENT LEGENDS FOR THE FOLLOWING SECTIONS: A. A LEGEND OF ACRONYMS AND ABBREVIATIONS MUST ACCOMPANY ALL DOCUMENTATION. B. A LIST OF ALL TEST RESULTS PERFORMED ON THE SYSTEMS AS OUTLINED IN SECTION 3.5 PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE. C. A LIST OF ALL EQUIPMENT, INDICATING MANUFACTURER, MODEL, SERIAL NUMBER, AND EQUIPMENT LOCATION (I.E. RACK/ROOM NUMBER). UPDATE FOLLOWING ACCEPTANCE TESTING, IF CHANGED. D. REPRODUCED SCHEMATIC WIRING DIAGRAMS OF THE AUDIO/VIDEO SYSTEMS, BASED ON THE AS-BUILT DOCUMENTATION, ATA REDUCED SCALE EASY TO HANDLE BUT FULLY LEGIBLE. E. REPLACEMENT PARTS LISTS OF MAJOR ITEMS OF EQUIPMENT. F. PRODUCE COMPACT SYSTEM SCHEMATICS SHOWING ALL COMPONENTS, CABLES, AND WIRE NUMBERS THAT WILL BE MOUNTED ON THE WALL OF THE TRUCK DOCK AND ENGINEERING RACK ROOM. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 11213 | Review Response | Approved as Noted | 2021-01-28 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 14514 | Responded and Closed | Approved as Noted | 2021-02-04 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-19 |  | 27 41 32-1.4 Broadcast Cabling.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-19 |  | 27 41 32-1.4 Broadcast Cabling.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-01-19 |  | 27 41 32-1.4 Broadcast Cabling.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-04 |  | 27 41 32-1.4 Broadcast Cabling i!i_POP.pdf
27 41 32-003-00 | 27 41 32 - BROADCAST CABLING | 27 41 32-003-00 BROADCAST CABLING - Tests And Inspections | Open | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-28 | Pending Review Response - Approved as Noted/Resubmit |  | Brian Elwell (Idibri) |  |  |  | 2021-10-12 |  | 10 |  | Record Copies; Transfers; Submittals |  | 10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14737 | Received | For Review | 2021-09-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ella Pilgrim (Mortenson Construction) | 2021-10-12 | Submittal Number: 27 41 32-3.0 From: ELLA PILGRIM Final Due Date: 10/11/21 Subject: BROADCAST CABLING - TESTS AND INSPECTIONS Description: A PROVIDEA PRE-COMMISSIONING SYSTEMS REPORT TO THE CONSULTANT TWO WEEKS PRIOR TO THE SCHEDULED SYSTEMS COMMISSIONING PROVING ALL SYSTEMS TO BE IN FULL COMPLIANCE. REPORT SHALL INCLUDE TEST RESULTS, DATE OF EACH TEST, PERTINENT CONDITIONS SUCH AS CONTROL SETTINGS, ETC., AND TEST EQUIPMENT EMPLOYED. IN ADDITION, SUBMIT WRITTEN NOTIFICATION THAT THE INSTALLATION HAS BEEN COMPLETED IN ACCORDANCE WITH THE REQUIREMENTS OF THE CONTRACT DOCUMENTS, AND IS READY FOR ACCEPTANCE TESTING. B DURING ALL CONSULTANT WALKTHROUGHS, THE PROJECT MANAGER WILL BE PRESENT. C IF DURING ACCEPTANCE TESTING IT BECOMES EVIDENT THAT FURTHER ADJUSTMENT OR WORK MAY BE REQUIRED TO BRING THE SYSTEM INTO COMPLIANCE, THE CONTRACTOR WILL CONTINUE TO WORK UNTIL THE SYSTEM IS ACCEPTABLE AT NO ADDITIONAL CHARGE TO THE CONTRACT PRICE. IF APPROVAL IS DELAYED BECAUSE OF DEFECTIVE EQUIPMENT, POOR INSTALLATION, OR FAILURE OF EQUIPMENT TO MEET THE REQUIREMENTS OF THESE SPECIFICATIONS, THE CONTRACTOR WILL PAY FOR ADDITIONAL TIME AND EXPENSES OF THE CONSULTANT AT THE CONSULTANT'S STANDARD RATE IN EFFECT AT THAT TIME, DURING ANY EXTENSION OF THE ACCEPTANCE TESTING PERIOD. THE CONTRACTOR WILL PROVIDE RENTAL OR LOANER EQUIPMENT TO MAKE THE SYSTEM OPERATIONAL IN CRITICAL CASES OF EQUIPMENT FAILURE PRIOR TO CONTRACT COMPLETION. D PROVIDE FOUR PORTABLE UHF BUSINESS BAND RADIOS FOR USE DURING ACCEPTANCE TESTING. RADIOS SHOULD HAVEA TRANSMISSION RANGE SUFFICIENT TO COVER ENTIRE PROJECT. E VERIFY THE FOLLOWING BEFORE BEGINNING ACTUAL TESTS AND ADJUSTMENTS ON THE SYSTEM: 1 ELECTRONIC DEVICES ARE PROPERLY GROUNDED. 2 INSULATION AND SHRINK TUBING ARE PRESENT WHERE REQUIRED. 3 DUST, DEBRIS, SOLDER, SPLATTER, ETC. IS REMOVED. 4 CABLE IS DRESSED, ROUTED, AND LABELED; CONNECTIONS ARE CONSISTENT WITH REGARD TO POLARITY. F CABLING TESTS. 1 SUBMIT PRINTED TEST REPORTS PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE TO THE CONSULTANT AS PART OF THE PRE-COMMISSIONING SYSTEMS REPORT. 2 AFTER INSTALLATION, AND BEFORE TERMINATION, ALL WIRING AND CABLING SHALL BE CHECKED AND TESTED WITHA MEGOHMETER TO ENSURE THERE ARE NO GROUNDS, OPENS, OR SHORTS ON ANY CONDUCTOR OR SHIELDS. 3 VERIFY ALL AUDIO LINES ARE WIRED TO MAINTAIN PROPER CONTINUITY AND POLARITY. 4 PERFORM TDR MEASUREMENTS ON ALL TRIAX AND COAX VIDEO CABLES. 5 TEST ALL CAT6 CABLES TO VERIFY THEY MEET FULL CAT6 SPECIFICATIONS. TESTS WILL USEA CERTIFIED TESTER THAT WILL CONFIRM BANDWIDTH, CABLE DISTANCE, AND ERROR AND BIT RATE DETECTION. 6 OPTICAL FIBER CABLE TESTING A. TEST LINK ATTENUATION OF ALL INSTALLED FIBER OPTIC STRANDS AFTER SPLICING AND TERMINATION IN ACCORDANCE WITH ANSI/TIA/EIA-568-B.1, SECTION 11.3. B. TEST ALL INSTALLED FIBER OPTIC STRANDS AFTER SPLICING AND TERMINATION WITH AN OTDR (OPTICAL TIME-DOMAIN REFLECTOMETER) PER TIA/EIA-455-61: C. FIBERS THAT ARE BROKEN OR DAMAGED SHALL BE REPLACED AT NO COST TO THE OWNER AND REPLACED FIBER OPTIC CABLES SHALL BE RE-TESTED. D. PROVIDE TEST RESULTS IN BOTH PDF AND IN THE NATIVE FILE FORMAT OF THE OTDR. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 18999 | Forwarded | For Review | 2021-09-27 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-10-04 | Submittal Number: 27 41 32-3.0 From: ELLA PILGRIM Final Due Date: 10/11/21 Subject: BROADCAST CABLING - TESTS AND INSPECTIONS Description: A PROVIDEA PRE-COMMISSIONING SYSTEMS REPORT TO THE CONSULTANT TWO WEEKS PRIOR TO THE SCHEDULED SYSTEMS COMMISSIONING PROVING ALL SYSTEMS TO BE IN FULL COMPLIANCE. REPORT SHALL INCLUDE TEST RESULTS, DATE OF EACH TEST, PERTINENT CONDITIONS SUCH AS CONTROL SETTINGS, ETC., AND TEST EQUIPMENT EMPLOYED. IN ADDITION, SUBMIT WRITTEN NOTIFICATION THAT THE INSTALLATION HAS BEEN COMPLETED IN ACCORDANCE WITH THE REQUIREMENTS OF THE CONTRACT DOCUMENTS, AND IS READY FOR ACCEPTANCE TESTING. B DURING ALL CONSULTANT WALKTHROUGHS, THE PROJECT MANAGER WILL BE PRESENT. C IF DURING ACCEPTANCE TESTING IT BECOMES EVIDENT THAT FURTHER ADJUSTMENT OR WORK MAY BE REQUIRED TO BRING THE SYSTEM INTO COMPLIANCE, THE CONTRACTOR WILL CONTINUE TO WORK UNTIL THE SYSTEM IS ACCEPTABLE AT NO ADDITIONAL CHARGE TO THE CONTRACT PRICE. IF APPROVAL IS DELAYED BECAUSE OF DEFECTIVE EQUIPMENT, POOR INSTALLATION, OR FAILURE OF EQUIPMENT TO MEET THE REQUIREMENTS OF THESE SPECIFICATIONS, THE CONTRACTOR WILL PAY FOR ADDITIONAL TIME AND EXPENSES OF THE CONSULTANT AT THE CONSULTANT'S STANDARD RATE IN EFFECT AT THAT TIME, DURING ANY EXTENSION OF THE ACCEPTANCE TESTING PERIOD. THE CONTRACTOR WILL PROVIDE RENTAL OR LOANER EQUIPMENT TO MAKE THE SYSTEM OPERATIONAL IN CRITICAL CASES OF EQUIPMENT FAILURE PRIOR TO CONTRACT COMPLETION. D PROVIDE FOUR PORTABLE UHF BUSINESS BAND RADIOS FOR USE DURING ACCEPTANCE TESTING. RADIOS SHOULD HAVEA TRANSMISSION RANGE SUFFICIENT TO COVER ENTIRE PROJECT. E VERIFY THE FOLLOWING BEFORE BEGINNING ACTUAL TESTS AND ADJUSTMENTS ON THE SYSTEM: 1 ELECTRONIC DEVICES ARE PROPERLY GROUNDED. 2 INSULATION AND SHRINK TUBING ARE PRESENT WHERE REQUIRED. 3 DUST, DEBRIS, SOLDER, SPLATTER, ETC. IS REMOVED. 4 CABLE IS DRESSED, ROUTED, AND LABELED; CONNECTIONS ARE CONSISTENT WITH REGARD TO POLARITY. F CABLING TESTS. 1 SUBMIT PRINTED TEST REPORTS PROVING THE SYSTEMS TO BE IN FULL COMPLIANCE TO THE CONSULTANT AS PART OF THE PRE-COMMISSIONING SYSTEMS REPORT. 2 AFTER INSTALLATION, AND BEFORE TERMINATION, ALL WIRING AND CABLING SHALL BE CHECKED AND TESTED WITHA MEGOHMETER TO ENSURE THERE ARE NO GROUNDS, OPENS, OR SHORTS ON ANY CONDUCTOR OR SHIELDS. 3 VERIFY ALL AUDIO LINES ARE WIRED TO MAINTAIN PROPER CONTINUITY AND POLARITY. 4 PERFORM TDR MEASUREMENTS ON ALL TRIAX AND COAX VIDEO CABLES. 5 TEST ALL CAT6 CABLES TO VERIFY THEY MEET FULL CAT6 SPECIFICATIONS. TESTS WILL USEA CERTIFIED TESTER THAT WILL CONFIRM BANDWIDTH, CABLE DISTANCE, AND ERROR AND BIT RATE DETECTION. 6 OPTICAL FIBER CABLE TESTING A. TEST LINK ATTENUATION OF ALL INSTALLED FIBER OPTIC STRANDS AFTER SPLICING AND TERMINATION IN ACCORDANCE WITH ANSI/TIA/EIA-568-B.1, SECTION 11.3. B. TEST ALL INSTALLED FIBER OPTIC STRANDS AFTER SPLICING AND TERMINATION WITH AN OTDR (OPTICAL TIME-DOMAIN REFLECTOMETER) PER TIA/EIA-455-61: C. FIBERS THAT ARE BROKEN OR DAMAGED SHALL BE REPLACED AT NO COST TO THE OWNER AND REPLACED FIBER OPTIC CABLES SHALL BE RE-TESTED. D. PROVIDE TEST RESULTS IN BOTH PDF AND IN THE NATIVE FILE FORMAT OF THE OTDR. Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
|  | Pending Review Response | Approved as Noted/Resubmit | 2021-10-06 18:06 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-27 |  | 27 41 32-3.0 Broadcast Cabling Tests and Inspections.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-27 |  | 27 41 32-3.0 Broadcast Cabling Tests and Inspections.pdf
27 41 32-004-00 | 27 41 32 - BROADCAST CABLING | 27 41 32-004-00 Broadcast Innerduct | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-16 | Responded and Closed - Approved |  | Brian Elwell (Idibri) |  |  |  | 2021-03-02 | 2021-03-02 | 15 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-03-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11436 | Received | For Review | 2021-02-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-02 | Submittal Number: 27 41 32-4.0 From: ELLA PILGRIM Final Due Date: 03/02/21 Subject: BROADCAST INNERDUCT Description: Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 14805 | Forwarded | For Review | 2021-02-15 | Populous SCA_CCA | Brian Elwell (Idibri) | 2021-02-22 | Submittal Number: 27 41 32-4.0 From: ELLA PILGRIM Final Due Date: 03/02/21 Subject: BROADCAST INNERDUCT Description: Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 11745 | Review Response | Approved | 2021-02-24 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Innercuct not required for armored fiber used for broadcast cabling | Info Exchange
| 15217 | Responded and Closed | Approved | 2021-03-02 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Brian Elwell (Idibri) Remarks: Innercuct not required for armored fiber used for broadcast cabling | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-15 |  | 27 41 32-4.0 - Broadcast Innerduct.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-15 |  | 27 41 32-4.0 - Broadcast Innerduct.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-02-15 |  | 27 41 32-4.0 - Broadcast Innerduct.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-02 |  | 27 41 32-4.0 - Broadcast Innerduct i!i_pop.pdf
27 41 32-005-00 | 27 41 32 - BROADCAST CABLING | 27 41 32-005-00 Audio Cable | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-22 | Responded and Closed - Approved |  | Brian Elwell (Idibri) |  |  |  | 2021-05-06 | 2021-05-05 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-05-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12721 | Received | For Review | 2021-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-06 | Submittal Number: 27 41 32-5.0 From: ELLA PILGRIM Final Due Date: 05/07/21 Subject: AUDIO CABLE Description: Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 16446 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Brian Elwell (Idibri) | 2021-04-29 | Submittal Number: 27 41 32-5.0 From: ELLA PILGRIM Final Due Date: 05/07/21 Subject: AUDIO CABLE Description: Spec Section: 27 41 32 - BROADCAST CABLING Status: OPEN | Info Exchange
| 12958 | Review Response | Approved | 2021-05-04 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 16768 | Responded and Closed | Approved | 2021-05-05 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-22 |  | 27 41 32-5.0 - Audio Cable.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-22 |  | 27 41 32-5.0 - Audio Cable.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-04-22 |  | 27 41 32-5.0 - Audio Cable.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-05 |  | 27 41 32-5.0 - Audio Cable i!i Rvwd_POP.pdf
27 41 33-005-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-005-00 Daktronics ProRail | Closed | Audio-Visual, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-17 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Michael Mazzocchi (ME Engineers) |  |  |  | 2020-12-03 | 2020-12-07 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-12-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09511 | Received | For Review | 2020-11-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory) | 2020-12-03 | Submittal Number: 27 41 33-5.0 From: SCOTT LOUWAGIE Final Due Date: 11/30/20 Subject: DAKTRONICS PRORAIL Description: DAKTRONICS PRORAIL SHOP AND RISER DRAWINGS. Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 12535 | Forwarded | For Review | 2020-11-17 | Elliott Veazey (CAA ICON / Strategy Advisory) | Brian Elwell (Idibri) | 2020-11-24 | Submittal Number: 27 41 33-5.0 From: SCOTT LOUWAGIE Final Due Date: 11/30/20 Subject: DAKTRONICS PRORAIL Description: DAKTRONICS PRORAIL SHOP AND RISER DRAWINGS. Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 09848 | Review Response | Approved as Noted | 2020-11-23 | Ben Cating (Idibri) | Elliott Veazey (CAA ICON / Strategy Advisory) |  |  | Info Exchange
| 09849 | Review Response | Approved as Noted | 2020-11-23 | Brian Elwell (Idibri) | Elliott Veazey (CAA ICON / Strategy Advisory) |  | Ben Cating from Idibri uploaded the submittal w/ stamp and comments. | Info Exchange
| 12828 | Forwarded | For Review | 2020-11-30 | Elliott Veazey (CAA ICON / Strategy Advisory) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Michael Mazzocchi (ME Engineers) | 2020-12-03 | Submittal Number: 27 41 33-5.0 From: SCOTT LOUWAGIE Final Due Date: 11/30/20 Subject: DAKTRONICS PRORAIL Description: DAKTRONICS PRORAIL SHOP AND RISER DRAWINGS. Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 09975 | Review Response | Approved as Noted | 2020-12-07 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens | Info Exchange
| 13055 | Responded and Closed | Approved as Noted | 2020-12-07 | Elliott Veazey (CAA ICON / Strategy Advisory) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-17 |  | Seattle ProRail Drawing Submittal 11.10.2020.pdf
| Forwarded |  | Elliott Veazey (CAA ICON / Strategy Advisory) | 1 | 2020-11-17 |  | Seattle ProRail Drawing Submittal 11.10.2020.pdf
| Review Response |  | Ben Cating (Idibri) | 1 | 2020-11-23 |  | Seattle ProRail Drawing Submittal 11.10.2020_i!iComments.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-11-17 |  | Seattle ProRail Drawing Submittal 11.10.2020.pdf
| Forwarded |  | Elliott Veazey (CAA ICON / Strategy Advisory) | 1 | 2020-11-16 02:00 |  | Seattle ProRail Drawing Submittal 11.10.2020.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-11-16 |  | Seattle ProRail Drawing Submittal 11.10.2020.pdf
| Responded and Closed |  | Elliott Veazey (CAA ICON / Strategy Advisory) | 1 | 2020-11-17 |  | Seattle ProRail Drawing Submittal 11.10.2020.pdf
27 41 33-006-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-006-00 Daktronics Hoist Submittal | Closed | Audio-Visual, Technology, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Brian Elwell (Idibri), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-21 | 2020-12-22 | 16 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-12-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09967 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-21 | Submittal Number: 27 41 33-6.0 From: ELLIOTT VEAZEY Final Due Date: 12/21/20 Subject: DAKTRONICS HOIST SUBMITTAL Description: ATTACHED ARE THE HOIST SUBMITTALS FOR THE TWO DUAL DISPLAYS. Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 13043 | Forwarded | For Review | 2020-12-07 | Populous SCA_CCA | Nick Theimer (ME Engineers); Brian Elwell (Idibri); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2020-12-14 | Submittal Number: 27 41 33-6.0 From: ELLIOTT VEAZEY Final Due Date: 12/21/20 Subject: DAKTRONICS HOIST SUBMITTAL Description: ATTACHED ARE THE HOIST SUBMITTALS FOR THE TWO DUAL DISPLAYS. Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 13105 | Forwarded | For Review | 2020-12-08 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2020-12-15 | Submittal Number: 27 41 33-6.0 From: ELLIOTT VEAZEY Final Due Date: 12/21/20 Subject: DAKTRONICS HOIST SUBMITTAL Description: ATTACHED ARE THE HOIST SUBMITTALS FOR THE TWO DUAL DISPLAYS. Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 10165 | Review Response | Approved as Noted | 2020-12-08 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Confirm length of travel will allow centerhungs to be dropped to ground level, and confirm proposed rigpoints will work with final centerhung shop drawings. | Info Exchange
| 10319 | Review Response | Approved as Noted | 2020-12-15 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.12.15 | Info Exchange
| 10320 | Review Response | Not Required For Review | 2020-12-18 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | Received for record. TT has not reviewed this submittal in detail. Submit final hoist calculations and loads imposed to SER for review and approval. Additionally, provide load-celled as-built weight of scoreboard prior to installation for SER review. TT-FK ¦ 2020-12-18 | Info Exchange
| 13487 | Responded and Closed | Approved as Noted | 2020-12-22 | Populous SCA_CCA | Mike Steele (CAA ICON / Strategy Advisory); Elliott Veazey (CAA ICON / Strategy Advisory); Mike Tihista (CAA ICON / Strategy Advisory); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Byron Noll... |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: Confirm length of travel will allow centerhungs to be dropped to ground level, and confirm proposed rigpoints will work with final centerhung shop drawings. Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.12.15 Response (Not Required For Review) from: Franz Kogler (Thornton Tomasetti) Remarks: Received for record. TT has not reviewed this submittal in detail. Submit final hoist calculations and loads imposed to SER for review and approval. Additionally, provide load-celled as-built weight of scoreboard prior to installation for SER review. TT-FK ¦ 2020-12-18 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 15064743 Seattle Center - Climate Pledge Arena REVA 12-4-20.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-07 |  | 15064743 Seattle Center - Climate Pledge Arena REVA 12-4-20.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-06 02:00 |  | 15064743 Seattle Center - Climate Pledge Arena REVA 12-4-20.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-12-07 |  | 15064743 Seattle Center - Climate Pledge Arena REVA 12-4-20.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-12-15 02:00 |  | 15064743 Seattle Center - Climate Pledge Arena REVA 12-4-20 - ME Review.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-12-06 02:00 |  | 15064743 Seattle Center - Climate Pledge Arena REVA 12-4-20.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-22 02:00 |  | 15064743 Seattle Center - Climate Pledge Arena REVA 12-4-20 - COMBINED_POP.pdf
27 41 33-006-01 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-006-01 Daktronics Hoist Submittal | Closed | Audio-Visual, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-09 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Brian Elwell (Idibri), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-02-23 | 2021-02-23 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-02-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11295 | Received | For Review | 2021-02-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Scott Louwagie; Cody Stieritz | 2021-02-23 | Submittal Number: 27 41 33-6.1 From: ELLIOTT VEAZEY Final Due Date: 01/27/21 Subject: DAKTRONICS HOIST SUBMITTAL Description: ATTACHED ARE THE HOIST SUBMITTALS FOR THE TWO DUAL DISPLAYS. Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 14643 | Forwarded | For Review | 2021-02-09 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Brian Elwell (Idibri); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-02-16 | Submittal Number: 27 41 33-6.1 From: ELLIOTT VEAZEY Final Due Date: 01/27/21 Subject: DAKTRONICS HOIST SUBMITTAL Description: ATTACHED ARE THE HOIST SUBMITTALS FOR THE TWO DUAL DISPLAYS. Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 11575 | Review Response | Approved as Noted | 2021-02-15 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 14897 | Forwarded | For Review | 2021-02-17 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-02-23 | Submittal Number: 27 41 33-6.1 From: ELLIOTT VEAZEY Final Due Date: 01/27/21 Subject: DAKTRONICS HOIST SUBMITTAL Description: ATTACHED ARE THE HOIST SUBMITTALS FOR THE TWO DUAL DISPLAYS. Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 11576 | Review Response | Approved as Noted | 2021-02-19 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See attached comments. | Info Exchange
| 15031 | Responded and Closed | Approved as Noted | 2021-02-23 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attached comments. Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-09 |  | 27 41 33-006-01 Daktronics Hoist Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-09 |  | 27 41 33-006-01 Daktronics Hoist Submittal.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-02-09 |  | 27 41 33-006-01 Daktronics Hoist Submittal.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-08 02:00 |  | 27 41 33-006-01 Daktronics Hoist Submittal.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-02-08 |  | 27 41 33-006-01 Daktronics Hoist Submittal.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-23 |  | 27 41 33-006-01 Daktronics Hoist Submittal_TT_Idibri_POP.pdf
27 41 33-007-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-007-00 Daktronics - Centerhung/Structure | Closed | Audio-Visual, Technology, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-16 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Brian Elwell (Idibri), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Mark Lievens (ME Engineers), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2021-04-30 | 2021-05-04 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12607 | Received | For Review | 2021-04-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Scott Louwagie | 2021-04-30 | Submittal Number: 27 41 33-7.0 From: ELLIOTT VEAZEY Final Due Date: 01/18/21 Subject: DAKTRONICS - CENTERHUNG/STRUCTURE Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 16327 | Forwarded | For Review | 2021-04-15 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Brian Elwell (Idibri); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-04-22 | Submittal Number: 27 41 33-7.0 From: ELLIOTT VEAZEY Final Due Date: 01/18/21 Subject: DAKTRONICS - CENTERHUNG/STRUCTURE Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 16329 | Forwarded | For Review | 2021-04-15 | Shaina Burris (Populous) | Mark Lievens (ME Engineers) | 2021-04-22 | Submittal Number: 27 41 33-7.0 From: ELLIOTT VEAZEY Final Due Date: 01/18/21 Subject: DAKTRONICS - CENTERHUNG/STRUCTURE Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 12909 | Review Response | Approved | 2021-04-23 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  |  | Info Exchange
| 12910 | Review Response | No Action Taken or Required | 2021-04-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | No electrical connection information included within submittal. TT shall review for structural requirements and design caclculations. Electrical load and connection information shall be submitted within a future submittal. Mark Lievens ME Engineers 2021.04.23 | Info Exchange
| 16504 | Forwarded | For Review | 2021-04-26 | Todd Spangler (Populous) | Matt Ross (Thornton Tomasetti) |  | Submittal Number: 27 41 33-7.0 From: ELLIOTT VEAZEY Final Due Date: 01/18/21 Subject: DAKTRONICS - CENTERHUNG/STRUCTURE Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 16667 | Forwarded | For Review | 2021-05-01 | Shaina Burris (Populous) | Franz Kogler (Thornton Tomasetti) | 2021-04-30 | Submittal Number: 27 41 33-7.0 From: ELLIOTT VEAZEY Final Due Date: 01/18/21 Subject: DAKTRONICS - CENTERHUNG/STRUCTURE Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 12911 | Review Response | Approved as Noted | 2021-05-03 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Exceptions noted, see attached. No resubmit required unless requirements not met. | Info Exchange
| 16698 | Responded and Closed | Approved as Noted | 2021-05-04 | Todd Spangler (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | No electrical connection information included within submittal. Mark Lievens ME Engineers 2021.04.23 Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: Exceptions noted, see attached. No resubmit required unless requirements not met. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-15 |  | C28953-5600 Installation Drawings SS 2021-02-24.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-15 |  | c28953-5600 Shops SS 2021-02-24 SS 2021-02-24.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-15 |  | Seattle Pledge Arena CH calcs SS 2021-02-24.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-15 |  | C28953-5600 Installation Drawings SS 2021-02-24.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-15 |  | c28953-5600 Shops SS 2021-02-24 SS 2021-02-24.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-15 |  | Seattle Pledge Arena CH calcs SS 2021-02-24.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-15 |  | C28953-5600 Installation Drawings SS 2021-02-24.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-15 |  | c28953-5600 Shops SS 2021-02-24 SS 2021-02-24.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-15 |  | Seattle Pledge Arena CH calcs SS 2021-02-24.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-04-15 |  | C28953-5600 Installation Drawings SS 2021-02-24.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-04-15 |  | c28953-5600 Shops SS 2021-02-24 SS 2021-02-24.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-04-15 |  | Seattle Pledge Arena CH calcs SS 2021-02-24.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-15 |  | C28953-5600 Installation Drawings SS 2021-02-24.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-15 |  | c28953-5600 Shops SS 2021-02-24 SS 2021-02-24.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-15 |  | Seattle Pledge Arena CH calcs SS 2021-02-24.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2021-04-15 |  | C28953-5600 Installation Drawings SS 2021-02-24.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2021-04-15 |  | c28953-5600 Shops SS 2021-02-24 SS 2021-02-24.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2021-04-15 |  | Seattle Pledge Arena CH calcs SS 2021-02-24.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-15 |  | C28953-5600 Installation Drawings SS 2021-02-24.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-15 |  | c28953-5600 Shops SS 2021-02-24 SS 2021-02-24.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-15 |  | Seattle Pledge Arena CH calcs SS 2021-02-24.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-04-15 |  | C28953-5600 Installation Drawings SS 2021-02-24.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-04-15 |  | c28953-5600 Shops SS 2021-02-24 SS 2021-02-24.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-04-15 |  | Seattle Pledge Arena CH calcs SS 2021-02-24.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-05-04 |  | 27 41 33-007-00 - Seattle Pledge Arena CH calcs SS 2021-02-24_TT_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-05-04 |  | 27 41 33-007-00 - C28953-5600 Installation Drawings SS 2021-02-24_TT_i!i_POP.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-05-04 |  | 27 41 33-007-00 - c28953-5600 Shops SS 2021-02-24 SS 2021-02-24_TT_i!I_POP.pdf
27 41 33-008-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-008-00 Daktronics - Interior LED Displays | Closed | Audio-Visual, Structural, Architectural, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-04 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian Elwell (Idibri), David Riffel (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-18 | 2021-03-22 | 19 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11788 | Received | For Review | 2021-03-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Populous SCA_CCA; Scott Louwagie; Cody Stieritz | 2021-03-18 | Submittal Number: 27 41 33-8.0 From: ELLIOTT VEAZEY Final Due Date: 03/18/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 15276 | Forwarded | For Review | 2021-03-04 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian Elwell (Idibri); David Riffel (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti);... | 2021-03-11 | Submittal Number: 27 41 33-8.0 From: ELLIOTT VEAZEY Final Due Date: 03/18/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 12080 | Review Response | Approved as Noted | 2021-03-10 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Confirm weight of Atrium Roof LED System. | Info Exchange
| 12081 | Review Response | No Action Taken or Required | 2021-03-11 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | No electrical connection information regarding interior Daktronics displays included within submittal. Submit electrical connection information of interior displays for review. Mark Lievens ME Engineers 2021.03.11 | Info Exchange
| 12082 | Review Response | Approved as Noted | 2021-03-12 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 15713 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-22 | Todd Spangler (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACHED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-04 |  | 27 41 33-8.0 Interior Shops minus tunnels and South Atrium.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-04 |  | 27 41 33-8.0 Interior Shops minus tunnels and South Atrium.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-04 |  | 27 41 33-8.0 Interior Shops minus tunnels and South Atrium.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-03-04 |  | 27 41 33-8.0 Interior Shops minus tunnels and South Atrium.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-03-04 |  | 27 41 33-8.0 Interior Shops minus tunnels and South Atrium.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-03-22 |  | 27 41 33-8.0 Interior Shops minus tunnels and South Atrium_i!i_TT_POP.pdf
27 41 33-008-01 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-008-01 Daktronics - Interior LED Displays | Closed | Audio-Visual, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian Elwell (Idibri), David Riffel (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-05 | 2021-04-28 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12693 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Populous SCA_CCA; Scott Louwagie; Cody Stieritz | 2021-05-05 | Submittal Number: 27 41 33-8.1 From: ELLIOTT VEAZEY Final Due Date: 04/20/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 16413 | Forwarded | For Review | 2021-04-20 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian Elwell (Idibri); David Riffel (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti);... | 2021-04-27 | Submittal Number: 27 41 33-8.1 From: ELLIOTT VEAZEY Final Due Date: 04/20/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 12841 | Review Response | No Action Taken or Required | 2021-04-22 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 12842 | Review Response | Approved | 2021-04-26 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  |  | Info Exchange
| 16620 | Responded and Closed | Approved as Noted | 2021-04-28 | Todd Spangler (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | MAM TO COORDINATE WITH DIMENSIONS OF INTD-1B | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-20 |  | 27 41 33-008-01 Daktronics - Interior LED Displays.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-20 |  | 27 41 33-008-01 Daktronics - Interior LED Displays.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-20 |  | 27 41 33-008-01 Daktronics - Interior LED Displays.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-04-20 |  | 27 41 33-008-01 Daktronics - Interior LED Displays.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-04-28 |  | 27 41 33-008-01 Daktronics - Interior LED Displays_i!i_POP.pdf
27 41 33-009-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-009-00 Daktronics - Exterior LED Displays | Closed | Audio-Visual, Structural, Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-02 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian Elwell (Idibri), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Kelly Holton (Populous), Mary Lim (Populous) |  |  |  | 2021-03-16 | 2021-03-17 | 16 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-03-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11743 | Received | For Review | 2021-03-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Scott Louwagie | 2021-03-16 | Submittal Number: 27 41 33-9.0 From: ELLIOTT VEAZEY Final Due Date: 02/05/21 Subject: DAKTRONICS - EXTERIOR LED DISPLAYS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 15215 | Forwarded | For Review | 2021-03-02 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-03-09 | Submittal Number: 27 41 33-9.0 From: ELLIOTT VEAZEY Final Due Date: 02/05/21 Subject: DAKTRONICS - EXTERIOR LED DISPLAYS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 15222 | Forwarded | For Review | 2021-03-02 | Shaina Burris (Populous) | Mark Lievens (ME Engineers) | 2021-03-09 | Submittal Number: 27 41 33-9.0 From: ELLIOTT VEAZEY Final Due Date: 02/05/21 Subject: DAKTRONICS - EXTERIOR LED DISPLAYS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 15230 | Forwarded | For Review | 2021-03-02 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian Elwell (Idibri); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thorn... | 2021-03-09 | Submittal Number: 27 41 33-9.0 From: ELLIOTT VEAZEY Final Due Date: 02/05/21 Subject: DAKTRONICS - EXTERIOR LED DISPLAYS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 12061 | Review Response | Approved as Noted | 2021-03-05 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 12062 | Review Response | Approved | 2021-03-08 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 15444 | Forwarded | For Review | 2021-03-10 | Todd Spangler (Populous) | Kelly Holton (Populous); Mary Lim (Populous) |  | Submittal Number: 27 41 33-9.0 From: ELLIOTT VEAZEY Final Due Date: 02/05/21 Subject: DAKTRONICS - EXTERIOR LED DISPLAYS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 12063 | Review Response | Approved as Noted/Resubmit | 2021-03-11 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.03.11 | Info Exchange
| 12078 | Review Response | Approved as Noted/Resubmit | 2021-03-17 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15635 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-17 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.03.11 Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-02 |  | 27 41 33-9.0 Exterior Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-02 |  | 27 41 33-9.0 Exterior Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-02 |  | 27 41 33-9.0 Exterior Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-02 |  | 27 41 33-9.0 Exterior Submittal.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-03-02 |  | 27 41 33-9.0 Exterior Submittal.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-02 |  | 27 41 33-9.0 Exterior Submittal.pdf
| Forwarded |  | Todd Spangler (Populous) | 1 | 2021-03-02 |  | 27 41 33-9.0 Exterior Submittal.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-03-02 |  | 27 41 33-9.0 Exterior Submittal.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-17 |  | 27 41 33-9.0 Exterior Submittal - i!i_TT_MEE_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-17 |  | 27 41 33-9.0 Exterior Submittal - i!i_TT_MEE_POP.pdf
27 41 33-009-01 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-009-01 Daktronics - Exterior LED Displays | Closed | Audio-Visual, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian Elwell (Idibri), David Riffel (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-05 | 2021-05-04 | 14 |  | Record Copies; Transfers; Submittals | 27 41 33-009-01-01 - 27 41 33-009-01 Daktronics - Exterior LED Displays | 10 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12694 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Scott Louwagie; Cody Stieritz | 2021-05-05 | Submittal Number: 27 41 33-9.1 From: ELLIOTT VEAZEY Final Due Date: 04/08/21 Subject: DAKTRONICS - EXTERIOR LED DISPLAYS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 16414 | Forwarded | For Review | 2021-04-20 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian Elwell (Idibri); David Riffel (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti);... | 2021-04-27 | Submittal Number: 27 41 33-9.1 From: ELLIOTT VEAZEY Final Due Date: 04/08/21 Subject: DAKTRONICS - EXTERIOR LED DISPLAYS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 12914 | Review Response | No Action Taken or Required | 2021-04-22 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 12915 | Review Response | Approved | 2021-04-26 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  |  | Info Exchange
| 12916 | Review Response | Approved as Noted/Resubmit | 2021-04-29 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Brian Elwell (Idibri); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.04.29 | Info Exchange
| 16700 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-04 | Todd Spangler (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.04.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-20 |  | 27 41 33-009-01 Daktronics - Exterior LED Displays.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-20 |  | 27 41 33-009-01 Daktronics - Exterior LED Displays.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-04-20 |  | 27 41 33-009-01 Daktronics - Exterior LED Displays.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-20 |  | 27 41 33-009-01 Daktronics - Exterior LED Displays.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-05-04 |  | 27 41 33-009-01 Daktronics - Exterior LED Displays_ME_i!i_POP.pdf
27 41 33-009-01-01 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-009-01 Daktronics - Exterior LED Displays | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 27 41 33-009-01 - 27 41 33-009-01 Daktronics - Exterior LED Displays | -1 | 2021-05-18
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-04 |  | 27 41 33-009-01 Daktronics - Exterior LED Displays_ME_i!i_POP.pdf
27 41 33-010-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-010-00 Daktronics - Interior LED Displays (Event Level Tunnel Boards) | Closed | Electrical, Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-26 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Brian Elwell (Idibri), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-10 07:00 | 2021-06-07 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13280 | Received | For Review | 2021-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Scott Louwagie | 2021-06-10 07:00 | Submittal Number: 27 41 33-10.0 From: ELLIOTT VEAZEY Final Due Date: 03/05/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS (EVENT LEVEL TUNNEL BOARDS) Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 17184 | Forwarded | For Review | 2021-05-26 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Brian Elwell (Idibri); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-06-02 | Submittal Number: 27 41 33-10.0 From: ELLIOTT VEAZEY Final Due Date: 03/05/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS (EVENT LEVEL TUNNEL BOARDS) Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 13439 | Review Response | Approved as Noted | 2021-06-03 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.06.03 | Info Exchange
| 13440 | Review Response | Approved | 2021-06-07 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  |  | Info Exchange
| 17379 | Responded and Closed | Approved as Noted | 2021-06-07 | Josh Dobken (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Koch (CAA ICON / Strategy Advisory) |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.06.03 Response (Approved) from: Brian Elwell (Idibri) Remarks: | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-26 |  | 27 41 33-010-00 Daktronics - Interior LED Displays.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-05-25 02:00 |  | 27 41 33-010-00 Daktronics - Interior LED Displays.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-05-25 02:00 |  | 27 41 33-010-00 Daktronics - Interior LED Displays.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-07 02:00 |  | 27 41 33-010-00 Daktronics - Interior LED Displays - ME_i!i_POP.pdf
27 41 33-011-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-011-00 Daktronics - Controls Equipment/Scoring | Closed | Audio-Visual, Electrical, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian Elwell (Idibri), David Riffel (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-05-05 | 2021-05-04 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12695 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Scott Louwagie | 2021-05-05 | Submittal Number: 27 41 33-11.0 From: ELLIOTT VEAZEY Final Due Date: 01/29/21 Subject: DAKTRONICS - CONTROLS EQUIPMENT/SCORING Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 16415 | Forwarded | For Review | 2021-04-20 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian Elwell (Idibri); David Riffel (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti);... | 2021-04-27 | Submittal Number: 27 41 33-11.0 From: ELLIOTT VEAZEY Final Due Date: 01/29/21 Subject: DAKTRONICS - CONTROLS EQUIPMENT/SCORING Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 12917 | Review Response | No Action Taken or Required | 2021-04-22 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 12918 | Review Response | Revise and Resubmit | 2021-04-28 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  |  | Info Exchange
| 12919 | Review Response | No Action Taken or Required | 2021-04-29 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | No electrical connection information included within submittal therefor no review from ME is required. Mark Lievens ME Engineers 2021.04.29 | Info Exchange
| 16701 | Responded and Closed | Revise and Resubmit | 2021-05-04 | Todd Spangler (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: Response (Revise and Resubmit) from: Brian Elwell (Idibri) Remarks: Response (No Action Taken or Required) from: Mark Lievens (ME Engineers) Remarks: No electrical connection information included within submittal therefor no review from ME is required. Mark Lievens ME Engineers 2021.04.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-20 |  | Control Submittals Rev 1 4.19.21.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-20 |  | Control Submittals Rev 1 4.19.21.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-20 |  | Control Submittals Rev 1 4.19.21.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-04-20 |  | Control Submittals Rev 1 4.19.21.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-20 |  | Control Submittals Rev 1 4.19.21.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-05-04 |  | 27 41 33-011-00 - Control Submittals Rev 1 4.19.21_i!i_POP.pdf
27 41 33-011-01 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-011-01 Daktronics Controls Equipment/Scoring | Closed | Audio-Visual, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-02 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian Elwell (Idibri), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-06-16 | 2021-06-09 | 8 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-06-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13356 | Received | For Review | 2021-06-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Populous SCA_CCA; Scott Louwagie | 2021-06-16 | Submittal Number: 27 41 33-11.1 From: ELLIOTT VEAZEY Final Due Date: 06/14/21 Subject: DAKTRONICS CONTROLS EQUIPMENT/SCORING Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 17283 | Forwarded | For Review | 2021-06-02 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian Elwell (Idibri); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton... |  | Submittal Number: 27 41 33-11.1 From: ELLIOTT VEAZEY Final Due Date: 06/14/21 Subject: DAKTRONICS CONTROLS EQUIPMENT/SCORING Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 13468 | Review Response | No Action Taken or Required | 2021-06-02 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Received for record. | Info Exchange
| 13469 | Review Response | Approved as Noted | 2021-06-07 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  |  | Info Exchange
| 17415 | Responded and Closed | Approved as Noted | 2021-06-09 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 17528 | Sent | For Information Only | 2021-06-15 | Josh Dobken (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); Brooke Burcham (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: Received for record. Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| 18142 | Sent | For Information Only | 2021-07-20 | Josh Dobken (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); Christian Albers (Mortenson Construction) |  | Sent to: Elliott Veazey (CAA ICON / Strategy Advisory); Brooke Burcham (Mortenson Construction); Christian Albers (Mortenson Construction) Remarks: Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: Received for record. Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-02 |  | 27 41 33-011-01 Daktronics Controls Equipment.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-06-02 |  | 27 41 33-011-01 Daktronics Controls Equipment.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-06-02 |  | 27 41 33-011-01 Daktronics Controls Equipment.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-06-07 |  | 27 41 33-011-01 Daktronics Controls Equipment_i!iResponse.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-06-09 |  | 27 41 33-011-01 Daktronics Controls Equipment_i!iResponse-POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-06-01 02:00 |  | 27 41 33-011-01 Daktronics Controls Equipment.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-06-01 02:00 |  | 27 41 33-011-01 Daktronics Controls Equipment.pdf
27 41 33-012-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-012-00 Daktronics Vom and Dasher Submittal | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Ben Cating (Idibri), Brian Elwell (Idibri) |  |  |  | 2021-01-22 08:00 | 2021-01-22 | 16 |  | Record Copies; Transfers; Submittals | 27 41 33-012-00-01 - 27 41 33-012-00 Daktronics Vom and Dasher Submittal | 16 |  | 2021-01-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10512 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Populous SCA_CCA; Scott Louwagie | 2021-01-22 08:00 | Submittal Number: 27 41 33-12.0 From: SCOTT LOUWAGIE Final Due Date: 01/20/21 Subject: DAKTRONICS VOM AND DASHER SUBMITTAL Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 13718 | Forwarded | For Review | 2021-01-07 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-01-14 | Submittal Number: 27 41 33-12.0 From: SCOTT LOUWAGIE Final Due Date: 01/20/21 Subject: DAKTRONICS VOM AND DASHER SUBMITTAL Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 13900 | Forwarded | For Review | 2021-01-13 | Populous SCA_CCA | Ben Cating (Idibri); Brian Elwell (Idibri) |  | Submittal Number: 27 41 33-12.0 From: SCOTT LOUWAGIE Final Due Date: 01/20/21 Subject: DAKTRONICS VOM AND DASHER SUBMITTAL Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 10832 | Review Response | Approved as Noted/Resubmit | 2021-01-20 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Please provided additional information requested. | Info Exchange
| 10912 | Review Response | Approved as Noted/Resubmit | 2021-01-22 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.01.22 | Info Exchange
| 14167 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: Please provided additional information requested. Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.01.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-07 |  | 27 41 33-012-00 Daktronics Vom.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-07 |  | 27 41 33-012-00 Daktronics Vom.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-07 |  | 27 41 33-012-00 Daktronics Vom.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-01-20 |  | 27 41 33-012-00 Daktronics Vom_i!iResponse.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-01-07 |  | 27 41 33-012-00 Daktronics Vom.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-22 |  | 27 41 33-012-00 Daktronics Vom_i!iResponse_ME_POP.pdf
27 41 33-012-00-01 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-012-00 Daktronics Vom and Dasher Submittal | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 27 41 33-012-00 - 27 41 33-012-00 Daktronics Vom and Dasher Submittal | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-22 |  | 27 41 33-012-00 Daktronics Vom_i!iResponse_ME_POP.pdf
27 41 33-013-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-013-00 Daktronics - Dual Display LED Boards | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Brian Elwell (Idibri), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Jackie Lybarger (ME Engineers), Mitchell.Carlson@me-engineers.com |  |  |  | 2021-02-22 | 2021-02-16 | 9 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-02-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11250 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Scott Louwagie; Cody Stieritz | 2021-02-22 | Submittal Number: 27 41 33-13.0 From: CODY STIERITZ Final Due Date: 02/18/21 Subject: DAKTRONICS - DUAL DISPLAY LED BOARDS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 14566 | Forwarded | For Review | 2021-02-08 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Brian Elwell (Idibri); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-02-15 | Submittal Number: 27 41 33-13.0 From: CODY STIERITZ Final Due Date: 02/18/21 Subject: DAKTRONICS - DUAL DISPLAY LED BOARDS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 11498 | Review Response | Approved as Noted | 2021-02-15 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 14895 | Forwarded | For Review | 2021-02-16 | Kelsea Conkright (Populous) | Jackie Lybarger (ME Engineers); Michael Mazzocchi (ME Engineers); Mitchell.Carlson@me-engineers.com |  | Submittal Number: 27 41 33-13.0 From: CODY STIERITZ Final Due Date: 02/18/21 Subject: DAKTRONICS - DUAL DISPLAY LED BOARDS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 14896 | Responded and Closed | Approved as Noted | 2021-02-16 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-08 |  | 27 41 33-013-00 Centerhung Riser and Shop Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-08 |  | 27 41 33-013-00 Centerhung Riser and Shop Submittal.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-02-08 |  | 27 41 33-013-00 Centerhung Riser and Shop Submittal.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-02-08 |  | 27 41 33-013-00 Centerhung Riser and Shop Submittal.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-16 |  | 27 41 33-013-00 Centerhung Riser and Shop Submittal_i!i_POP.pdf
27 41 33-014-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-014-00 Daktronics - Interior LED Displays Electrical | Closed | Electrical, Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-16 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Brian Elwell (Idibri), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers) |  |  |  | 2021-04-30 | 2021-05-04 | 19 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-05-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12610 | Received | For Review | 2021-04-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Scott Louwagie | 2021-04-30 | Submittal Number: 27 41 33-14.0 From: CODY STIERITZ Final Due Date: 04/02/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS ELECTRICAL Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 16375 | Forwarded | For Review | 2021-04-19 | Josh Dobken (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Brian Elwell (Idibri) | 2021-04-26 | Submittal Number: 27 41 33-14.0 From: CODY STIERITZ Final Due Date: 04/02/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS ELECTRICAL Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 16595 | Forwarded | For Review | 2021-04-27 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers) | 2021-04-30 | Submittal Number: 27 41 33-14.0 From: CODY STIERITZ Final Due Date: 04/02/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS ELECTRICAL Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 12912 | Review Response | Approved | 2021-04-28 | Brian Elwell (Idibri) | Josh Dobken (Populous) |  | ME Engineers should look at the electrical power distribution portion of this submittal. | Info Exchange
| 12913 | Review Response | Approved as Noted | 2021-04-29 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Brian Elwell (Idibri); Josh Dobken (Populous) |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.04.29 | Info Exchange
| 16699 | Responded and Closed | Approved as Noted | 2021-05-04 | Todd Spangler (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.04.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-04-15 02:00 |  | 27 41 33-014-00 Electrical Risers minus Ceiling and INTD-6.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-04-15 02:00 |  | 27 41 33-014-00 Electrical Risers minus Ceiling and INTD-6.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-04-20 02:00 |  | Transmittal_Submittal - 27 41 33-014-00 (Forwarded).pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-04-15 |  | 27 41 33-014-00 Electrical Risers minus Ceiling and INTD-6.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-15 |  | 27 41 33-014-00 Electrical Risers minus Ceiling and INTD-6.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-20 |  | Transmittal_Submittal - 27 41 33-014-00 (Forwarded).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-05-04 |  | 27 41 33-014-00 Electrical Risers minus Ceiling and INTD-6_ME_i!i_POP.pdf
27 41 33-015-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-015-00 Daktronics - Interior LED Displays - Suite Level Fascia Boards | Closed | Audio-Visual, Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-30 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Brian Elwell (Idibri), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-08-13 | 2021-08-18 | 20 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-08-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14175 | Received | For Review | 2021-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Populous SCA_CCA; Scott Louwagie; Cody Stieritz | 2021-08-13 | Submittal Number: 27 41 33-15.0 From: CODY STIERITZ Final Due Date: 03/19/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS - SUITE LEVEL FASCIA BOARDS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 18325 | Forwarded | For Review | 2021-08-02 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Brian Elwell (Idibri); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-08-09 | Submittal Number: 27 41 33-15.0 From: CODY STIERITZ Final Due Date: 03/19/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS - SUITE LEVEL FASCIA BOARDS Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 14292 | Review Response | Approved | 2021-08-10 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Approved - no exceptions | Info Exchange
| 14392 | Review Response | Approved as Noted | 2021-08-17 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see attached submittal review. Thanks, Mark Lievens ME Engineers 2021.08.17 | Info Exchange
| 18591 | Responded and Closed | Approved as Noted | 2021-08-18 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-02 |  | 27 41 33-015-00 Daktronics - Interior LED Displays.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-08-02 |  | 27 41 33-015-00 Daktronics - Interior LED Displays.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-02 |  | 27 41 33-015-00 Daktronics - Interior LED Displays.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-08-18 |  | 27 41 33-015-00 Daktronics - Interior LED Displays_i!i_ME_POP.pdf
27 41 33-016-00 | 27 41 33 - DISPLAY SYSTEMS | 27 41 33-016-00 Daktronics - Interior LED Displays - South Atrium Board | Closed | Audio-Visual, Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-30 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Brian Elwell (Idibri), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-13 | 2021-08-18 | 20 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-08-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14176 | Received | For Review | 2021-07-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Populous SCA_CCA; Scott Louwagie; Cody Stieritz | 2021-08-13 | Submittal Number: 27 41 33-16.0 From: CODY STIERITZ Final Due Date: 03/19/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS - SOUTH ATRIUM BOARD Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 18326 | Forwarded | For Review | 2021-08-02 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Brian Elwell (Idibri); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-09 | Submittal Number: 27 41 33-16.0 From: CODY STIERITZ Final Due Date: 03/19/21 Subject: DAKTRONICS - INTERIOR LED DISPLAYS - SOUTH ATRIUM BOARD Description: Spec Section: 27 41 33 - DISPLAY SYSTEMS Status: OPEN | Info Exchange
| 14290 | Review Response | Approved | 2021-08-10 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Approved - No Exceptions | Info Exchange
| 14394 | Review Response | Approved | 2021-08-17 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.08.17 | Info Exchange
| 18592 | Responded and Closed | Approved as Noted | 2021-08-18 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-02 |  | 27 41 33-016-00 Daktronics - Interior LED Displays.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-08-02 |  | 27 41 33-016-00 Daktronics - Interior LED Displays.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-02 |  | 27 41 33-016-00 Daktronics - Interior LED Displays.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-08-18 |  | 27 41 33-016-00 Daktronics - Interior LED Displays - ME_idibri_POP.pdf
27 41 34.1-002-00 | 27 41 34 - AV SYSTEMS | 27 41 34.1-002-00 AV SYSTEMS - Product Data, Shop Drawings, and Calculations | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-28 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri) |  |  |  | 2020-11-11 | 2020-11-06 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-11-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09064 | Received | For Review | 2020-10-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-11-11 | Submittal Number: 27 41 34.1-2.0 From: ELLA PILGRIM Final Due Date: 11/10/20 Subject: AV SYSTEMS - PRODUCT DATA, SHOP DRAWINGS, AND CALCULATIONS Description: SUBMIT WITHIN 30 DAYS OF CONTRACT AWARD. SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT THAT WILL BE PROVIDED AS PART OF THIS CONTRACT. SUBMIT ELECTRONICALLY AS A SINGLE PDF. ALL EQUIPMENT CUT SHEETS WILL BE ARRANGED PER SPECIFICATION SECTION NUMBER. PROVIDE A TABLE OF CONTENTS AND A BOOKMARK AT THE START OF EVERY PRODUCT SHEET. SUBMIT HEAT LOAD CALCULATIONS SHOWING HOW NUMBERS WERE DERIVED. Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 11952 | Forwarded | For Review | 2020-10-28 | Populous SCA_CCA | Brian Elwell (Idibri) | 2020-11-04 | Submittal Number: 27 41 34.1-2.0 From: ELLA PILGRIM Final Due Date: 11/10/20 Subject: AV SYSTEMS - PRODUCT DATA, SHOP DRAWINGS, AND CALCULATIONS Description: SUBMIT WITHIN 30 DAYS OF CONTRACT AWARD. SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT THAT WILL BE PROVIDED AS PART OF THIS CONTRACT. SUBMIT ELECTRONICALLY AS A SINGLE PDF. ALL EQUIPMENT CUT SHEETS WILL BE ARRANGED PER SPECIFICATION SECTION NUMBER. PROVIDE A TABLE OF CONTENTS AND A BOOKMARK AT THE START OF EVERY PRODUCT SHEET. SUBMIT HEAT LOAD CALCULATIONS SHOWING HOW NUMBERS WERE DERIVED. Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 09279 | Review Response | Approved as Noted | 2020-11-05 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 12239 | Responded and Closed | Approved as Noted | 2020-11-06 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-27 |  | 27-41-34-1 - CPA Suite Mockup Sound-AV Submittal.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-27 |  | 27-41-34-1 - CPA Suite Mockup Sound-AV Submittal.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-10-27 |  | 27-41-34-1 - CPA Suite Mockup Sound-AV Submittal.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-16 |  | 27 05 36-1.0 Product Data-MAM-ME_POP.pdf
27 41 34.1-010-00 | 27 41 34 - AV SYSTEMS | 27 41 34.1-010-00 AV SYSTEMS - Calculations | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-18 | Responded and Closed - Approved |  | Brian Elwell (Idibri) |  |  |  | 2021-06-02 07:00 | 2021-05-27 | 10 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13148 | Received | For Review | 2021-05-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Elliott Veazey (CAA ICON / Strategy Advisory); Cody Stieritz | 2021-06-02 07:00 | Submittal Number: 27 41 34.1-10.0 From: ELLA PILGRIM Final Due Date: 06/26/20 Subject: AV SYSTEMS - CALCULATIONS Description: WIRELESS FREQUENCY ANALYSIS. IT IS THE RESPONSIBILITY OF THE CONTRACTOR TO COORDINATE ALL WIRELESS FREQUENCIES. THE CONTRACTOR SHALL PERFORM A SPECTRAL SWEEP FROM 140 MHZ THROUGH 3 GHZ IN THE FACILITY AND THEN PRESENT A WRITTEN REPORT OF PROPOSED NEW FREQUENCIES. THE CONTRACTOR MUST ARRANGE AND PERFORM THIS SWEEP AT A TIME OF DAY THAT REFLECTS THE TIME OF FACILITY USE. THE CONTRACTOR SHOULD ALSO INCLUDE IN THE REPORT ADDITIONAL FREQUENCIES FOR FUTURE EXPANSION. THE CONTRACTOR WILL INCORPORATE ANY EXISTING AND OTHER NEW FREQUENCIES IN THE DETERMINATION OF THE NEW FREQUENCIES TO BE USED, INCLUDING BUT NOT LIMITED TO WIRELESS INTERCOM, WIRELESS CAMERAS AND WIRELESS RADIOS. Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 17007 | Forwarded | For Review | 2021-05-18 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-05-25 | Submittal Number: 27 41 34.1-10.0 From: ELLA PILGRIM Final Due Date: 06/26/20 Subject: AV SYSTEMS - CALCULATIONS Description: WIRELESS FREQUENCY ANALYSIS. IT IS THE RESPONSIBILITY OF THE CONTRACTOR TO COORDINATE ALL WIRELESS FREQUENCIES. THE CONTRACTOR SHALL PERFORM A SPECTRAL SWEEP FROM 140 MHZ THROUGH 3 GHZ IN THE FACILITY AND THEN PRESENT A WRITTEN REPORT OF PROPOSED NEW FREQUENCIES. THE CONTRACTOR MUST ARRANGE AND PERFORM THIS SWEEP AT A TIME OF DAY THAT REFLECTS THE TIME OF FACILITY USE. THE CONTRACTOR SHOULD ALSO INCLUDE IN THE REPORT ADDITIONAL FREQUENCIES FOR FUTURE EXPANSION. THE CONTRACTOR WILL INCORPORATE ANY EXISTING AND OTHER NEW FREQUENCIES IN THE DETERMINATION OF THE NEW FREQUENCIES TO BE USED, INCLUDING BUT NOT LIMITED TO WIRELESS INTERCOM, WIRELESS CAMERAS AND WIRELESS RADIOS. Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 13299 | Review Response | Approved | 2021-05-25 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  |  | Info Exchange
| 17200 | Responded and Closed | Approved | 2021-05-27 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | CPA - Wireless Mic Frequency Report.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-17 |  | CPA - Wireless Mic Frequency Report.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-05-16 02:00 |  | CPA - Wireless Mic Frequency Report.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-05-27 02:00 |  | 27 41 34.1-10.0 CPA - Wireless Mic Frequency Report i!i rvwd_POP.pdf
27 41 34.1-012-00 | 27 41 34 - AV SYSTEMS | 27 41 34.1-012-00 AV Systems - Product Data | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-14 | Responded and Closed - Approved as Noted/Resubmit |  | Brian Elwell (Idibri) |  |  |  | 2021-01-06 | 2020-12-30 | 17 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-12-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10125 | Received | For Review | 2020-12-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-06 | Submittal Number: 27 41 34.1-12.0 From: ELLA PILGRIM Final Due Date: 12/28/20 Subject: AV SYSTEMS - PRODUCT DATA Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 13235 | Forwarded | For Review | 2020-12-14 | Populous SCA_CCA | Brian Elwell (Idibri) | 2020-12-21 | Submittal Number: 27 41 34.1-12.0 From: ELLA PILGRIM Final Due Date: 12/28/20 Subject: AV SYSTEMS - PRODUCT DATA Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 10361 | Review Response | Approved as Noted/Resubmit | 2020-12-23 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Please make corrections and add missing items. | Info Exchange
| 13537 | Responded and Closed | Approved as Noted/Resubmit | 2020-12-30 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: Please make corrections and add missing items. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-11 |  | 0004304 - Climate Pledge Arena - AV Submittals. REV1 ar.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-11 |  | 0004304 - Climate Pledge Arena - AV Submittals. REV1 ar.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-12-11 |  | 0004304 - Climate Pledge Arena - AV Submittals. REV1 ar.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-30 |  | 0004304 - Climate Pledge Arena - AV Submittals. REV1_Idibri_POP.pdf
27 41 34.1-012-01 | 27 41 34 - AV SYSTEMS | 27 41 34.1-012-01 AV Systems - Product Data | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-01 | Responded and Closed - Approved as Noted/Resubmit |  | Brian Elwell (Idibri) |  |  |  | 2021-02-15 | 2021-02-15 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11088 | Received | For Review | 2021-02-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Koch (CAA ICON / Strategy Advisory); Cody Stieritz | 2021-02-15 | Submittal Number: 27 41 34.1-12.1 From: ELLA PILGRIM Final Due Date: 02/09/21 Subject: AV SYSTEMS - PRODUCT DATA Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 14386 | Forwarded | For Review | 2021-02-01 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-02-08 | Submittal Number: 27 41 34.1-12.1 From: ELLA PILGRIM Final Due Date: 02/09/21 Subject: AV SYSTEMS - PRODUCT DATA Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 11439 | Review Response | Approved as Noted/Resubmit | 2021-02-09 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 14808 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| 14931 | Sent | For Information Only | 2021-02-18 | Josh Dobken (Populous) | Domingo Sampayo (Mortenson Construction); Ella Pilgrim (Mortenson Construction) |  | MAM - please manually close this item in Procore. Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-01 |  | 0004304 – Climate Pledge Arena - AV Submittals REV2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-01 |  | 0004304 – Climate Pledge Arena - AV Submittals REV2.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-02-01 |  | 0004304 – Climate Pledge Arena - AV Submittals REV2.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-15 |  | 27 41 34.1-012-01 AV Systems-!i!_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-01-31 02:00 |  | 0004304 – Climate Pledge Arena - AV Submittals REV2.pdf
27 41 34.1-012-02 | 27 41 34 - AV SYSTEMS | 27 41 34.1-012-02 AV Systems - Product Data | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-08 | Responded and Closed - Approved as Noted/Resubmit |  | Brian Elwell (Idibri) |  |  |  | 2021-03-22 | 2021-03-22 | 15 |  | Record Copies; Transfers; Submittals | 27 41 34.1-012-02-01 - 27 41 34.1-012-02 AV Systems - Product Data | 15 |  | 2021-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11830 | Received | For Review | 2021-03-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Koch (CAA ICON / Strategy Advisory) | 2021-03-22 | Submittal Number: 27 41 34.1-12.2 From: ELLA PILGRIM Final Due Date: 03/17/21 Subject: AV SYSTEMS - PRODUCT DATA Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 15337 | Forwarded | For Review | 2021-03-08 | Cody Koch (CAA ICON / Strategy Advisory) | Brian Elwell (Idibri) | 2021-03-15 | Submittal Number: 27 41 34.1-12.2 From: ELLA PILGRIM Final Due Date: 03/17/21 Subject: AV SYSTEMS - PRODUCT DATA Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 12129 | Review Response | Approved as Noted/Resubmit | 2021-03-17 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 12132 | Review Response | Approved as Noted/Resubmit | 2021-03-22 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15708 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-05 |  | 0004304 - Climate Pledge Arena - AV Submittals REV2.pdf
| Forwarded |  | Cody Koch (CAA ICON / Strategy Advisory) | 1 | 2021-03-05 |  | 0004304 - Climate Pledge Arena - AV Submittals REV2.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-03-05 |  | 0004304 - Climate Pledge Arena - AV Submittals REV2.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-22 |  | 0004304 - Climate Pledge Arena - AV Submittals REV2 i!i reviewed_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-22 |  | 0004304 - Climate Pledge Arena - AV Submittals REV2 i!i reviewed_POP.pdf
27 41 34.1-012-02-01 | 27 41 34 - AV SYSTEMS | 27 41 34.1-012-02 AV Systems - Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 27 41 34.1-012-02 - 27 41 34.1-012-02 AV Systems - Product Data | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-22 |  | 0004304 - Climate Pledge Arena - AV Submittals REV2 i!i reviewed_POP.pdf
27 41 34.1-013-00 | 27 41 34 - AV SYSTEMS | 27 41 34.1-013-00 Main Con D1 Hard lid Shop Drawings | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved as Noted/Resubmit |  | Brian Elwell (Idibri) |  |  |  | 2021-01-21 | 2021-01-13 | 7 |  | Record Copies; Transfers; Submittals | 27 41 34.1-013-00-01 - 27 41 34.1-013-00 Main Con D1 Hard lid Shop Drawings | 7 |  | 2021-01-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10517 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Ella Pilgrim (Mortenson Construction); Cody Koch (CAA ICON / Strategy Advisory) | 2021-01-21 | Submittal Number: 27 41 34.1-13.0 From: ELLA PILGRIM Final Due Date: 01/13/21 Subject: MAIN CON D1 HARD LID SHOP DRAWINGS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 13720 | Forwarded | For Review | 2021-01-07 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-01-14 | Submittal Number: 27 41 34.1-13.0 From: ELLA PILGRIM Final Due Date: 01/13/21 Subject: MAIN CON D1 HARD LID SHOP DRAWINGS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 13721 | Forwarded | For Review | 2021-01-07 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-01-14 | Submittal Number: 27 41 34.1-13.0 From: ELLA PILGRIM Final Due Date: 01/13/21 Subject: MAIN CON D1 HARD LID SHOP DRAWINGS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 10673 | Review Response | Approved as Noted/Resubmit | 2021-01-11 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Approved, but please make corrections and resubmit. | Info Exchange
| 10679 | Review Response | Approved as Noted/Resubmit | 2021-01-13 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 13899 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-13 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: Approved, but please make corrections and resubmit. Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-07 |  | CPA - MAIN CONCOURSE QUAD D - SOUND-AV PLANS (1).pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-01-07 |  | CPA - MAIN CONCOURSE QUAD D - SOUND-AV PLANS (1).pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-13 |  | CPA - MAIN CONCOURSE QUAD D - SOUND-AV PLANS - i!i Rvwd_POP.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-01-13 |  | CPA - MAIN CONCOURSE QUAD D - SOUND-AV PLANS - i!i Rvwd_POP.pdf
27 41 34.1-013-00-01 | 27 41 34 - AV SYSTEMS | 27 41 34.1-013-00 Main Con D1 Hard lid Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 27 41 34.1-013-00 - 27 41 34.1-013-00 Main Con D1 Hard lid Shop Drawings | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-13 |  | CPA - MAIN CONCOURSE QUAD D - SOUND-AV PLANS - i!i Rvwd_POP.pdf
27 41 34.1-014-00 | 27 41 34 - AV SYSTEMS | 27 41 34.1-014-00 Speaker Shop Drawings | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-14 | Responded and Closed - Approved as Noted/Resubmit |  | Brian Elwell (Idibri) |  |  |  | 2021-01-29 08:00 | 2021-01-31 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-01-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10714 | Received | For Review | 2021-01-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Koch (CAA ICON / Strategy Advisory) | 2021-01-29 08:00 | Submittal Number: 27 41 34.1-14.0 From: ELLA PILGRIM Final Due Date: 01/28/21 Subject: SPEAKER SHOP DRAWINGS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 13936 | Forwarded | For Review | 2021-01-14 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-01-21 | Submittal Number: 27 41 34.1-14.0 From: ELLA PILGRIM Final Due Date: 01/28/21 Subject: SPEAKER SHOP DRAWINGS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 11065 | Review Response | Approved as Noted/Resubmit | 2021-01-27 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 11070 | Review Response | Approved as Noted/Resubmit | 2021-01-31 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 14368 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-31 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-14 |  | 2021-01-12 0004304 CPA SOUND-AV SUBMITTAL SET 27 41 34.1 .pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-14 |  | 2021-01-12 0004304 CPA SOUND-AV SUBMITTAL SET 27 41 34.1 .pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-01-14 |  | 2021-01-12 0004304 CPA SOUND-AV SUBMITTAL SET 27 41 34.1 .pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-31 |  | 2021-01-12 0004304 CPA SOUND-AV SUBMITTAL SET 27 41 34.1 - i!i_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-14 |  | 2021-01-12 0004304 CPA SOUND-AV SUBMITTAL SET 27 41 34.1 .pdf
27 41 34.1-014-01 | 27 41 34 - AV SYSTEMS | 27 41 34.1-014-01 Speaker Shop Drawings | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-08 | Responded and Closed - Approved as Noted/Resubmit |  | Brian Elwell (Idibri) |  |  |  | 2021-03-22 07:00 | 2021-03-28 | 21 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-03-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12076 | Received | For Review | 2021-03-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Koch (CAA ICON / Strategy Advisory) | 2021-03-22 07:00 | Submittal Number: 27 41 34.1-14.1 From: ELLA PILGRIM Final Due Date: 03/09/21 Subject: SPEAKER SHOP DRAWINGS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 15630 | Forwarded | For Review | 2021-03-17 | Cody Koch (CAA ICON / Strategy Advisory) | Brian Elwell (Idibri) | 2021-03-12 | Submittal Number: 27 41 34.1-14.1 From: ELLA PILGRIM Final Due Date: 03/09/21 Subject: SPEAKER SHOP DRAWINGS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 12274 | Review Response | Approved as Noted/Resubmit | 2021-03-24 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 12275 | Review Response | Approved as Noted/Resubmit | 2021-03-28 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 15888 | Responded and Closed | Approved as Noted/Resubmit | 2021-03-28 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Koch (CAA ICON / Strategy Advisory) |  | Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| 16119 | Sent | For Information Only | 2021-04-06 | Cody Koch (CAA ICON / Strategy Advisory) | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Koch (CAA ICON / Strategy Advisory) |  | Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Koch (CAA ICON / Strategy Advisory) Remarks: Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-16 02:00 |  | 27 41 34.1-014-01 Speaker Shop Drawings.pdf
| Forwarded |  | Cody Koch (CAA ICON / Strategy Advisory) | 1 | 2021-03-17 |  | 27 41 34.1-014-01 Speaker Shop Drawings.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-03-17 |  | 27 41 34.1-014-01 Speaker Shop Drawings.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-03-28 |  | 27 41 34.1-014-01 Speaker Shop Drawings-~i!i Review_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-16 |  | 27 41 34.1-014-01 Speaker Shop Drawings.pdf
| Sent |  | Cody Koch (CAA ICON / Strategy Advisory) | 1 | 2021-03-16 02:00 |  | 27 41 34.1-014-01 Speaker Shop Drawings.pdf
27 41 34.1-014-02 | 27 41 34 - AV SYSTEMS | 27 41 34.1-014-02 Speaker Shop Drawings | Closed | Audio-Visual, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-10 | Responded and Closed - Approved as Noted/Resubmit |  | Brian Elwell (Idibri), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-05-24 | 2021-05-21 | 12 |  | Record Copies; Transfers; Submittals | 27 41 34.1-014-02-01 - 27 41 34.1-014-02 Speaker Shop Drawings | 12 |  | 2021-05-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12994 | Received | For Review | 2021-05-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Koch (CAA ICON / Strategy Advisory) | 2021-05-24 | Submittal Number: 27 41 34.1-14.2 From: CODY STIERITZ Final Due Date: 05/06/21 Subject: SPEAKER SHOP DRAWINGS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 16817 | Forwarded | For Review | 2021-05-10 | Cody Koch (CAA ICON / Strategy Advisory) | Brian Elwell (Idibri) | 2021-05-17 | Submittal Number: 27 41 34.1-14.2 From: CODY STIERITZ Final Due Date: 05/06/21 Subject: SPEAKER SHOP DRAWINGS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 16841 | Forwarded | For Review | 2021-05-10 | Populous SCA_CCA | Matt Ross (Thornton Tomasetti) |  | Submittal Number: 27 41 34.1-14.2 From: CODY STIERITZ Final Due Date: 05/06/21 Subject: SPEAKER SHOP DRAWINGS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 13222 | Review Response | Approved as Noted | 2021-05-17 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 13223 | Review Response | Approved as Noted/Resubmit | 2021-05-21 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Resubmit for record with Washington Stamp as noted. | Info Exchange
| 17112 | Responded and Closed | Approved as Noted/Resubmit | 2021-05-21 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: Response (Approved as Noted/Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Resubmit for record with Washington Stamp as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-10 |  | 2021-04-29 Structural Calculations - CPA Bowl Rigging.pdf
| Forwarded |  | Cody Koch (CAA ICON / Strategy Advisory) | 1 | 2021-05-10 |  | 2021-04-29 Structural Calculations - CPA Bowl Rigging.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-10 |  | 2021-04-29 Structural Calculations - CPA Bowl Rigging.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-05-10 |  | 2021-04-29 Structural Calculations - CPA Bowl Rigging.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-10 |  | 2021-04-29 Structural Calculations - CPA Bowl Rigging.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-21 |  | 2021-04-29 Structural Calculations - CPA Bowl Rigging - i!i_TT_POP.pdf
27 41 34.1-014-02-01 | 27 41 34 - AV SYSTEMS | 27 41 34.1-014-02 Speaker Shop Drawings | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 27 41 34.1-014-02 - 27 41 34.1-014-02 Speaker Shop Drawings | -1 | 2021-06-04
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-21 |  | 2021-04-29 Structural Calculations - CPA Bowl Rigging - i!i_TT_POP.pdf
27 41 34.1-015-00 | 27 41 34 - AV SYSTEMS | 27 41 34.1-015-00 Diversified Structural Shop Drawings | Closed | Audio-Visual, Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-04 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-18 | 2021-03-23 | 20 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11790 | Received | For Review | 2021-03-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Koch (CAA ICON / Strategy Advisory) | 2021-03-18 | Submittal Number: 27 41 34.1-15.0 From: CODY STIERITZ Final Due Date: 03/15/21 Subject: DIVERSIFIED STRUCTURAL SHOP DRAWINGS Description: INCLUDE ALL STRUCTURAL / LOADING INFORMATION FOR TT REVIEW. Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 15285 | Forwarded | For Review | 2021-03-04 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-11 | Submittal Number: 27 41 34.1-15.0 From: CODY STIERITZ Final Due Date: 03/15/21 Subject: DIVERSIFIED STRUCTURAL SHOP DRAWINGS Description: INCLUDE ALL STRUCTURAL / LOADING INFORMATION FOR TT REVIEW. Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 11975 | Review Response | Approved as Noted | 2021-03-11 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | TT only reviewed loads imposed at locations identified on page 11 of this submittal. Any speaker attachments to rigging grid and/or press truss framing are still outstanding and shall be submitted for review and approval in a separate package. TT-FK ¦ 2021-03-11 | Info Exchange
| 15514 | Responded and Closed | Approved as Noted | 2021-03-23 | Josh Dobken (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); Cody Koch (CAA ICON / Strategy Advisory); Cody Stieritz |  | Disposition has been updated from "Approved as Noted / Resubmit" to "Approved as Noted". Please provide outstanding materials in a separate submittal as indicated previously. Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: TT only reviewed loads imposed at locations identified on page 11 of this submittal. Any speaker attachments to rigging grid and/or press truss framing are still outstanding and shall be submitted for review and approval in a separate package. TT-FK ¦ 2021-03-11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-04 |  | CPA - Main Bowl Speaker Arrays Atachement Submittal.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-03 02:00 |  | CPA - Main Bowl Speaker Arrays Atachement Submittal.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-03-03 02:00 |  | CPA - Main Bowl Speaker Arrays Atachement Submittal.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-23 02:00 |  | 274134.1-015-00 CPA - Main Bowl Speaker Arrays Atachement Submittal_TTFK_POP_V2.pdf
27 41 34.1-016-00 | 27 41 34 - AV SYSTEMS | 27 41 34.1-016-00 Diversified Structural Shop Drawings - East, West and South Catwalk | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-04 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-06-18 | 2021-06-14 | 11 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-06-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13393 | Received | For Review | 2021-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Koch (CAA ICON / Strategy Advisory) | 2021-06-18 | Submittal Number: 27 41 34.1-16.0 From: CODY STIERITZ Final Due Date: 03/29/21 Subject: DIVERSIFIED STRUCTURAL SHOP DRAWINGS - EAST, WEST AND SOUTH CATWALK Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 17321 | Forwarded | For Review | 2021-06-04 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-06-11 | Submittal Number: 27 41 34.1-16.0 From: CODY STIERITZ Final Due Date: 03/29/21 Subject: DIVERSIFIED STRUCTURAL SHOP DRAWINGS - EAST, WEST AND SOUTH CATWALK Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 17361 | Forwarded | For Review | 2021-06-07 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Cr... | 2021-06-14 | Submittal Number: 27 41 34.1-16.0 From: CODY STIERITZ Final Due Date: 03/29/21 Subject: DIVERSIFIED STRUCTURAL SHOP DRAWINGS - EAST, WEST AND SOUTH CATWALK Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 13444 | Review Response | Not Required For Review | 2021-06-07 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  | There is nothing for Idibri to check. You may want to run this by TT to see if they want to review it. | Info Exchange
| 13517 | Review Response | Approved as Noted | 2021-06-11 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attachment for submittal review. | Info Exchange
| 17488 | Responded and Closed | Approved as Noted | 2021-06-14 | Chris Minter (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-04 |  | CPA - Sound-AV Equipment Racks Catwalk Weight Loads (1).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-04 |  | CPA - Sound-AV Equipment Racks Catwalk Weight Loads (1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-03 02:00 |  | CPA - Sound-AV Equipment Racks Catwalk Weight Loads (1).pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-06-03 02:00 |  | CPA - Sound-AV Equipment Racks Catwalk Weight Loads (1).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-06-03 |  | CPA - Sound-AV Equipment Racks Catwalk Weight Loads (1).pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-06-11 |  | CPA - Sound-AV Equipment Racks Catwalk Weight Loads_TTReview.pdf
| Responded and Closed |  | Chris Minter (Populous) | 1 | 2021-06-14 |  | CPA - Sound-AV Equipment Racks Catwalk Weight Loads_TTReview-POP.pdf
27 41 34.1-017-00 | 27 41 34 - AV SYSTEMS | 27 41 34.1-017-00 Diagrams/Rack Elevations | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-04 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri) |  |  |  | 2021-05-18 | 2021-05-27 | 24 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2021-05-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12930 | Received | For Review | 2021-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Koch (CAA ICON / Strategy Advisory) | 2021-05-18 | Submittal Number: 27 41 34.1-17.0 From: ELLA PILGRIM Final Due Date: 04/06/21 Subject: DIAGRAMS/RACK ELEVATIONS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 16718 | Forwarded | For Review | 2021-05-04 | Shaina Burris (Populous) | Brian Elwell (Idibri) |  | Submittal Number: 27 41 34.1-17.0 From: ELLA PILGRIM Final Due Date: 04/06/21 Subject: DIAGRAMS/RACK ELEVATIONS Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 13268 | Review Response | Approved as Noted | 2021-05-25 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 17201 | Responded and Closed | Approved as Noted | 2021-05-27 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-04 |  | CPA - SOUND-AV MASTER DIAGRAMS-RACKS-PLATES 042921.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-04 |  | CPA - SOUND-AV MASTER DIAGRAMS-RACKS-PLATES 042921.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-05-04 |  | CPA - SOUND-AV MASTER DIAGRAMS-RACKS-PLATES 042921.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-05-27 02:00 |  | 274134 1-017-00- SOUND-AV MASTER DIAGRAMS-Idibri_pop.pdf
27 41 34.1-018-00 | 27 41 34 - AV SYSTEMS | 27 41 34.1-018-00 AV Console Product Data | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-04 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri) |  |  |  | 2021-06-18 | 2021-06-11 | 8 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-06-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13394 | Received | For Review | 2021-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Koch (CAA ICON / Strategy Advisory); Cody Stieritz | 2021-06-18 | Submittal Number: 27 41 34.1-18.0 From: CODY STIERITZ Final Due Date: 06/21/21 Subject: AV CONSOLE PRODUCT DATA Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 17322 | Forwarded | For Review | 2021-06-04 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-06-11 | Submittal Number: 27 41 34.1-18.0 From: CODY STIERITZ Final Due Date: 06/21/21 Subject: AV CONSOLE PRODUCT DATA Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 13441 | Review Response | Approved as Noted | 2021-06-07 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  |  | Info Exchange
| 17380 | Responded and Closed | Approved as Noted | 2021-06-07 | Josh Dobken (Populous) | Elliott Veazey (CAA ICON / Strategy Advisory); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Koch (CAA ICON / Strategy Advisory); Cody Stieritz |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| 17457 | Reopened | Additional Information | 2021-06-11 09:50 | Josh Dobken (Populous) |  |  | Revisions to comments
| 17458 | Responded and Closed | Approved as Noted | 2021-06-11 | Josh Dobken (Populous) | Cody Koch (CAA ICON / Strategy Advisory) |  | Reopened (Additional Information) by: Josh Dobken Remarks: Revisions to comments See clouded changes. | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-04 |  | CPA Audio Control Room -TBC - DS-10359-20_Drawing.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-04 |  | CPA Audio Control Room -TBC - DS-10359-20_Drawing.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-06-03 02:00 |  | CPA Audio Control Room -TBC - DS-10359-20_Drawing.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-07 02:00 |  | CPA Audio Control Room -TBC - DS-10359-20_Drawing-i!I rvwd_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-06-11 02:00 |  | CPA Audio Control Room -TBC - DS-10359-20_Drawing-i!I rvwd_POPv2.pdf
27 41 34.1-019-00 | 27 41 34 - AV SYSTEMS | 27 41 34.1-019-00 Touch Panel Layout & Design | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-02 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri) |  |  |  | 2021-07-19 07:00 | 2021-07-21 | 20 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13782 | Received | For Review | 2021-07-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Koch (CAA ICON / Strategy Advisory); Anthony Rosenfeld (Diversified Systems); Cody Stieritz | 2021-07-19 07:00 | Submittal Number: 27 41 34.1-19.0 From: CODY STIERITZ Final Due Date: 07/21/21 Subject: TOUCH PANEL LAYOUT & DESIGN Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 17837 | Forwarded | For Review | 2021-07-06 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-07-13 | Submittal Number: 27 41 34.1-19.0 From: CODY STIERITZ Final Due Date: 07/21/21 Subject: TOUCH PANEL LAYOUT & DESIGN Description: Spec Section: 27 41 34.1 - AV SYSTEMS ATTACHMENT A Status: OPEN | Info Exchange
| 14037 | Review Response | Approved as Noted | 2021-07-21 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 18161 | Responded and Closed | Approved as Noted | 2021-07-21 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-02 |  | CPA - AV Touch Screen Look & Feel Submittal.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-02 |  | CPA - AV Touch Screen Look & Feel Submittal.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-07-02 |  | CPA - AV Touch Screen Look & Feel Submittal.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-07-21 |  | CPA - AV Touch Screen Look & Feel Submittal-Idibri_pop.pdf
27 41 34-005-00 | 27 41 34 - AV SYSTEMS | 27 41 34-005-00 AV SYSTEMS - Samples | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-12 | Responded and Closed - Approved |  | Brian Elwell (Idibri) |  |  |  | 2020-03-26 | 2020-03-18 | 7 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04781 | Received | For Review | 2020-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-03-26 | Submittal Number: 27 41 34-5.0 From: ELLA PILGRIM Final Due Date: 03/25/20 Subject: AV SYSTEMS - SAMPLES Description: SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24? IN LENGTH. SUBMIT 2 CABLE/CONNECTOR ASSEMBLIES FOR EACH TYPE OF CABLE USED ON THE PROJECT. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. SPEAKER AND SPEAKER MOUNT COLORS. SUBMIT ACCORDING TO CONDITIONS OF THE CONSTRUCTION CONTRACT AND PROJECT MANUAL. MILLWORK COLORS AND SAMPLES. SUBMIT ACCORDING TO CONDITIONS OF THE CONSTRUCTION CONTRACT AND PROJECT MANUAL Spec Section: 27 41 34 - AV SYSTEMS Status: OPEN | Info Exchange
| 06556 | Forwarded | For Review | 2020-03-12 | Populous SCA_CCA | Brian Elwell (Idibri) | 2020-03-19 | Submittal Number: 27 41 34-5.0 From: ELLA PILGRIM Final Due Date: 03/25/20 Subject: AV SYSTEMS - SAMPLES Description: SUBMIT SAMPLE CABLES WITH CONNECTIONS AND WIRE LABELS. CABLE SAMPLES SHOULD BE NO GREATER THAN 24? IN LENGTH. SUBMIT 2 CABLE/CONNECTOR ASSEMBLIES FOR EACH TYPE OF CABLE USED ON THE PROJECT. CABLE JACKET ID LETTERING MUST BE INCLUDED ON SAMPLE CABLE. SPEAKER AND SPEAKER MOUNT COLORS. SUBMIT ACCORDING TO CONDITIONS OF THE CONSTRUCTION CONTRACT AND PROJECT MANUAL. MILLWORK COLORS AND SAMPLES. SUBMIT ACCORDING TO CONDITIONS OF THE CONSTRUCTION CONTRACT AND PROJECT MANUAL Spec Section: 27 41 34 - AV SYSTEMS Status: OPEN | Info Exchange
| 04938 | Review Response | Approved | 2020-03-15 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 06734 | Responded and Closed | Approved | 2020-03-18 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached Response (Approved) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 27 41 34-5.0 AV Systems - Samples.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-11 |  | 27 41 34-5.0 AV Systems - Samples.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-03-10 02:00 |  | 27 41 34-5.0 AV Systems - Samples.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-03-18 02:00 |  | 27 41 34-5.0 AV Systems - Samples i!i Resp_POP.pdf
27 41 36-001-00 | 27 41 36 - BOWL AUDIO | 27 41 36-001-00 BOWL AUDIO - Product Data and Shop Drawings | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-04 | Responded and Closed - Approved as Noted/Resubmit |  | Brian Elwell (Idibri) |  |  |  | 2021-01-18 | 2021-01-13 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-01-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10379 | Received | For Review | 2021-01-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-18 | Submittal Number: 27 41 36-1.0 From: ELLA PILGRIM Final Due Date: 12/30/20 Subject: BOWL AUDIO - PRODUCT DATA AND SHOP DRAWINGS Description: SUBMIT WITHIN 30 DAYS OF CONTRACT AWARD. SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT THAT WILL BE PROVIDED AS PART OF THIS CONTRACT. SUBMIT ELECTRONICALLY AS A SINGLE PDF. ALL EQUIPMENT CUT SHEETS WILL BE ARRANGED PER SPECIFICATION SECTION NUMBER. PROVIDE A TABLE OF CONTENTS AND A BOOKMARK AT THE START OF EVERY PRODUCT SHEET. Spec Section: 27 41 36 - BOWL AUDIO SYSTEMS Status: OPEN | Info Exchange
| 13562 | Forwarded | For Review | 2021-01-04 | Populous SCA_CCA | Brian Elwell (Idibri) | 2021-01-11 | Submittal Number: 27 41 36-1.0 From: ELLA PILGRIM Final Due Date: 12/30/20 Subject: BOWL AUDIO - PRODUCT DATA AND SHOP DRAWINGS Description: SUBMIT WITHIN 30 DAYS OF CONTRACT AWARD. SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT THAT WILL BE PROVIDED AS PART OF THIS CONTRACT. SUBMIT ELECTRONICALLY AS A SINGLE PDF. ALL EQUIPMENT CUT SHEETS WILL BE ARRANGED PER SPECIFICATION SECTION NUMBER. PROVIDE A TABLE OF CONTENTS AND A BOOKMARK AT THE START OF EVERY PRODUCT SHEET. Spec Section: 27 41 36 - BOWL AUDIO SYSTEMS Status: OPEN | Info Exchange
| 10680 | Review Response | Approved as Noted/Resubmit | 2021-01-11 | Brian Elwell (Idibri) | Populous SCA_CCA |  | Approved, but please make corrections, supply missing equipment, and resubmit. | Info Exchange
| 10692 | Review Response | Approved as Noted/Resubmit | 2021-01-13 | Kelsea Conkright (Populous) | Populous SCA_CCA |  | Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: Approved, but please make corrections, supply missing equipment, and resubmit. | Info Exchange
| 13913 | Responded and Closed | Approved as Noted/Resubmit | 2021-01-13 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: Approved, but please make corrections, supply missing equipment, and resubmit. Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| 13992 | Sent | For Information Only | 2021-01-15 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction) |  | Responded and Closed (Approved as Noted/Resubmit) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: Response (Approved as Noted/Resubmit) from: Brian Elwell (Idibri) Remarks: Approved, but please make corrections, supply missing equipment, and resubmit. Response (Approved as Noted/Resubmit) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-23 |  | 0004304 - Climate Pledge Arena - Audio Submittals. REV1.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-23 |  | 0004304 - Climate Pledge Arena - Audio Submittals. REV1.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2020-12-23 |  | 0004304 - Climate Pledge Arena - Audio Submittals. REV1.pdf
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-01-13 |  | 0004304 - Climate Pledge Arena - Audio Submittals. REV1 i!i Rvwd_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-23 |  | 0004304 - Climate Pledge Arena - Audio Submittals. REV1.pdf
| Sent |  | Populous SCA_CCA | 1 | 2020-12-22 02:00 |  | 0004304 - Climate Pledge Arena - Audio Submittals. REV1.pdf
27 41 36-001-01 | 27 41 36 - BOWL AUDIO | 27 41 36-001-01 BOWL AUDIO - Product Data and Shop Drawings | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-01 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri) |  |  |  | 2021-02-15 | 2021-02-15 | 15 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-02-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11089 | Received | For Review | 2021-02-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Koch (CAA ICON / Strategy Advisory) | 2021-02-15 | Submittal Number: 27 41 36-1.1 From: ELLA PILGRIM Final Due Date: 02/12/21 Subject: BOWL AUDIO - PRODUCT DATA AND SHOP DRAWINGS Description: SUBMIT WITHIN 30 DAYS OF CONTRACT AWARD. SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT THAT WILL BE PROVIDED AS PART OF THIS CONTRACT. SUBMIT ELECTRONICALLY AS A SINGLE PDF. ALL EQUIPMENT CUT SHEETS WILL BE ARRANGED PER SPECIFICATION SECTION NUMBER. PROVIDE A TABLE OF CONTENTS AND A BOOKMARK AT THE START OF EVERY PRODUCT SHEET. Spec Section: 27 41 36 - BOWL AUDIO SYSTEMS Status: OPEN | Info Exchange
| 14387 | Forwarded | For Review | 2021-02-01 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-02-08 | Submittal Number: 27 41 36-1.1 From: ELLA PILGRIM Final Due Date: 02/12/21 Subject: BOWL AUDIO - PRODUCT DATA AND SHOP DRAWINGS Description: SUBMIT WITHIN 30 DAYS OF CONTRACT AWARD. SUBMIT MANUFACTURER'S PRODUCT DATA SHEETS FOR EACH ITEM OF EQUIPMENT THAT WILL BE PROVIDED AS PART OF THIS CONTRACT. SUBMIT ELECTRONICALLY AS A SINGLE PDF. ALL EQUIPMENT CUT SHEETS WILL BE ARRANGED PER SPECIFICATION SECTION NUMBER. PROVIDE A TABLE OF CONTENTS AND A BOOKMARK AT THE START OF EVERY PRODUCT SHEET. Spec Section: 27 41 36 - BOWL AUDIO SYSTEMS Status: OPEN | Info Exchange
| 11437 | Review Response | Approved as Noted | 2021-02-09 | Brian Elwell (Idibri) | Shaina Burris (Populous) |  |  | Info Exchange
| 14807 | Responded and Closed | Approved as Noted | 2021-02-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| 14930 | Sent | For Information Only | 2021-02-18 | Josh Dobken (Populous) | Domingo Sampayo (Mortenson Construction); Ella Pilgrim (Mortenson Construction) |  | MAM - please manually close this item in your system. Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-01 |  | 27 41 36-001-01 BOWL AUDIO.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-01 |  | 27 41 36-001-01 BOWL AUDIO.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-02-01 |  | 27 41 36-001-01 BOWL AUDIO.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-09 |  | 27 41 36-001-01 BOWL AUDIO i!i_POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-01-31 02:00 |  | 27 41 36-001-01 BOWL AUDIO.pdf
27 41 39-001-01 | 27 41 39 | 27 41 39-001-01 IPTV Submittal Package | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-05 | Responded and Closed - Approved |  | Brian Elwell (Idibri) |  |  |  | 2021-05-19 | 2021-05-12 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12942 | Received | For Review | 2021-05-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Koch (CAA ICON / Strategy Advisory); Cody Stieritz | 2021-05-19 | Submittal Number: 27 41 39-1.1 From: CODY STIERITZ Final Due Date: 05/19/21 Subject: IPTV SUBMITTAL PACKAGE Description: Spec Section: 27 41 39 - IPTV SYSTEMS Status: OPEN | Info Exchange
| 16731 | Forwarded | For Review | 2021-05-04 | Shaina Burris (Populous) | Brian Elwell (Idibri) | 2021-05-11 | Submittal Number: 27 41 39-1.1 From: CODY STIERITZ Final Due Date: 05/19/21 Subject: IPTV SUBMITTAL PACKAGE Description: Spec Section: 27 41 39 - IPTV SYSTEMS Status: OPEN | Info Exchange
| 13082 | Review Response | Approved | 2021-05-10 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 16920 | Responded and Closed | Approved | 2021-05-12 | Kelsea Conkright (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-04 |  | 27 41 39 CLIMATE PLEDGE ARENA SUBMITTALS IPTV SYSTEM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-04 |  | 27 41 39 CLIMATE PLEDGE ARENA SUBMITTALS IPTV SYSTEM.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-05-04 |  | 27 41 39 CLIMATE PLEDGE ARENA SUBMITTALS IPTV SYSTEM.pdf
| Responded and Closed |  | Kelsea Conkright (Populous) | 1 | 2021-05-12 |  | 27 41 39 CLIMATE PLEDGE ARENA SUBMITTALS IPTV SYSTEM i!i rvwd_pop.pdf
27 41 39-002-00 | 27 41 39 | 27 41 39-002-00 TV Displays and Mounts | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-27 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri) |  |  |  | 2021-05-11 | 2021-05-14 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-05-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12808 | Received | For Review | 2021-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Stieritz | 2021-05-11 | Submittal Number: 27 41 39-2.0 From: CODY STIERITZ Final Due Date: 05/11/21 Subject: TV DISPLAYS AND MOUNTS Description: Spec Section: 27 41 39 - IPTV SYSTEMS Status: OPEN | Info Exchange
| 16555 | Forwarded | For Review | 2021-04-27 | Shaina Burris (Populous) | Brian Elwell (Idibri) |  | Submittal Number: 27 41 39-2.0 From: CODY STIERITZ Final Due Date: 05/11/21 Subject: TV DISPLAYS AND MOUNTS Description: Spec Section: 27 41 39 - IPTV SYSTEMS Status: OPEN | Info Exchange
| 16616 | Forwarded | For Review | 2021-04-28 | Kelsea Conkright (Populous) | Brian Elwell (Idibri) |  | Submittal Number: 27 41 39-2.0 From: CODY STIERITZ Final Due Date: 05/11/21 Subject: TV DISPLAYS AND MOUNTS Description: Spec Section: 27 41 39 - IPTV SYSTEMS Status: OPEN | Info Exchange
| 13110 | Review Response | Approved as Noted | 2021-05-05 | Brian Elwell (Idibri) | Kelsea Conkright (Populous) |  |  | Info Exchange
| 13111 | Review Response | Approved as Noted | 2021-05-14 | Kelsea Conkright (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 16955 | Responded and Closed | Approved as Noted | 2021-05-14 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: Response (Approved as Noted) from: Kelsea Conkright (Populous) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-27 |  | 27 41 39-2 CPA TV Displays & Mounts Plans.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-27 |  | CPA_TV MATRIX_MEETING NOTES - 4-26-2021.xlsx
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-27 |  | 27 41 39-2 CPA TV Displays & Mounts Plans.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-27 |  | CPA_TV MATRIX_MEETING NOTES - 4-26-2021.xlsx
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-04-27 |  | 27 41 39-2 CPA TV Displays & Mounts Plans.pdf
| Forwarded |  | Kelsea Conkright (Populous) | 1 | 2021-04-27 |  | CPA_TV MATRIX_MEETING NOTES - 4-26-2021.xlsx
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-04-27 |  | 27 41 39-2 CPA TV Displays & Mounts Plans.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-04-27 |  | CPA_TV MATRIX_MEETING NOTES - 4-26-2021.xlsx
| Review Response |  | Kelsea Conkright (Populous) | 1 | 2021-05-14 |  | 27 41 39-2 CPA TV Displays & Mounts Plans-Idibri_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-27 |  | 27 41 39-2 CPA TV Displays & Mounts Plans.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-27 |  | CPA_TV MATRIX_MEETING NOTES - 4-26-2021.xlsx
27 41 39-003-00 | 27 41 39 | 27 41 39-003-00 IPTV Single Lines | Closed | Audio-Visual | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-04 | Responded and Closed - Approved as Noted |  | Brian Elwell (Idibri) |  |  |  | 2021-06-18 | 2021-06-15 | 12 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-06-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13395 | Received | For Review | 2021-06-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-18 | Submittal Number: 27 41 39-3.0 From: CODY STIERITZ Final Due Date: 06/22/21 Subject: IPTV SINGLE LINES Description: Spec Section: 27 41 39 - IPTV SYSTEMS Status: OPEN | Info Exchange
| 17323 | Forwarded | For Review | 2021-06-04 | Populous SCA_CCA | Brian Elwell (Idibri) | 2021-06-11 | Submittal Number: 27 41 39-3.0 From: CODY STIERITZ Final Due Date: 06/22/21 Subject: IPTV SINGLE LINES Description: Spec Section: 27 41 39 - IPTV SYSTEMS Status: OPEN | Info Exchange
| 13540 | Review Response | Approved as Noted | 2021-06-15 | Brian Elwell (Idibri) | Populous SCA_CCA |  |  | Info Exchange
| 17519 | Responded and Closed | Approved as Noted | 2021-06-15 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brian Elwell (Idibri) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-03 |  | Climate Pledge Arena_IPTV Drawing Set as of 2021-06-03 (No Ingest).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-06-03 |  | Climate Pledge Arena_IPTV Drawing Set as of 2021-06-03 (No Ingest).pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-06-03 |  | Climate Pledge Arena_IPTV Drawing Set as of 2021-06-03 (No Ingest).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-15 |  | Climate Pledge Arena_IPTV Drawing Set as of 2021-06-03 (No Ingest) i!i rvwd_POP.pdf
27 53 20-009-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-009-00 CPA DAS Hangers-Supports | Closed | Technology, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-12-21 | 2020-12-22 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09950 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-21 | Submittal Number: 27 53 20-9.0 From: JILL OLSON Final Due Date: 12/21/20 Subject: CPA DAS HANGERS-SUPPORTS Description: 26-05-29 CPA HANGERS AND SUPPORTS Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 13028 | Forwarded | For Review | 2020-12-07 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2020-12-14 | Submittal Number: 27 53 20-9.0 From: JILL OLSON Final Due Date: 12/21/20 Subject: CPA DAS HANGERS-SUPPORTS Description: 26-05-29 CPA HANGERS AND SUPPORTS Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 13106 | Forwarded | For Review | 2020-12-08 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael... | 2020-12-15 | Submittal Number: 27 53 20-9.0 From: JILL OLSON Final Due Date: 12/21/20 Subject: CPA DAS HANGERS-SUPPORTS Description: 26-05-29 CPA HANGERS AND SUPPORTS Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 10260 | Review Response | No Action Taken or Required | 2020-12-18 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | TT has not reviewed this submittal. Provide support attachment layout and loads imposed to EOR for review in accordance with Structural General Note SU-5. TT-FK ¦ 2020-12-18 | Info Exchange
| 10324 | Review Response | Approved as Noted | 2020-12-21 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 13491 | Responded and Closed | Approved as Noted | 2020-12-22 | Populous SCA_CCA | Mike Steele (CAA ICON / Strategy Advisory); Elliott Veazey (CAA ICON / Strategy Advisory); Mike Tihista (CAA ICON / Strategy Advisory); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Koch... |  | Response (No Action Taken or Required) from: Franz Kogler (Thornton Tomasetti) Remarks: TT has not reviewed this submittal. Provide support attachment layout and loads imposed to EOR for review in accordance with Structural General Note SU-5. TT-FK ¦ 2020-12-18 Response (Approved as Noted) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 275320-009-0 CPA DAS Hangers-Supports.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-07 |  | 275320-009-0 CPA DAS Hangers-Supports.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-06 02:00 |  | 275320-009-0 CPA DAS Hangers-Supports.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-12-06 02:00 |  | 275320-009-0 CPA DAS Hangers-Supports.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-12-06 02:00 |  | 275320-009-0 CPA DAS Hangers-Supports.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-22 02:00 |  | 27 53 20-009-00 CPA DAS Hanger-Supports - ME Response_TT_POP.pdf
27 53 20-010-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-010-00 Telecommunications Raceway Product Data | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-07 | Responded and Closed - Not Required For Review |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2020-12-21 | 2020-12-22 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-12-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09966 | Received | For Review | 2020-12-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-21 | Submittal Number: 27 53 20-10.0 From: TRINA BOMONTI Final Due Date: 12/17/20 Subject: TELECOMMUNICATIONS RACEWAY PRODUCT DATA Description: 27-05-33 – TELECOMMUNICATIONS RACEWAYS & BOXES TABLE OF CONTENTS: ELECTRIC METALLIC TUBING (EMT) EMT CONDUIT FITTINGS INSULATING BUSHINGS SCHEDULE 40/SCHEDULE 80 CONDUIT Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 13042 | Forwarded | For Review | 2020-12-07 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2020-12-14 | Submittal Number: 27 53 20-10.0 From: TRINA BOMONTI Final Due Date: 12/17/20 Subject: TELECOMMUNICATIONS RACEWAY PRODUCT DATA Description: 27-05-33 – TELECOMMUNICATIONS RACEWAYS & BOXES TABLE OF CONTENTS: ELECTRIC METALLIC TUBING (EMT) EMT CONDUIT FITTINGS INSULATING BUSHINGS SCHEDULE 40/SCHEDULE 80 CONDUIT Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 10326 | Review Response | Not Required For Review | 2020-12-21 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  | This is a duplicate submittal of 27 05 33-003. | Info Exchange
| 13490 | Responded and Closed | Not Required For Review | 2020-12-22 | Populous SCA_CCA | Mike Steele (CAA ICON / Strategy Advisory); Elliott Veazey (CAA ICON / Strategy Advisory); Mike Tihista (CAA ICON / Strategy Advisory); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Koch... |  | Response (Not Required For Review) from: Michael Mazzocchi (ME Engineers) Remarks: This is a duplicate submittal of 27 05 33-003. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-07 |  | 270533-003-0 DAS Raceways.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-07 |  | 270533-003-0 DAS Raceways.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-12-06 02:00 |  | 270533-003-0 DAS Raceways.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-06 02:00 |  | 270533-003-0 DAS Raceways.pdf
27 53 20-024-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-024-00 DAS/ Wi-Fi Under Seat Mock-Up | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-04 | Responded and Closed - No Action Taken or Required |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-02-18 | 2021-03-29 | 54 |  | Record Copies; Transfers; Submittals |  | 48 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11215 | Received | For Review | 2021-02-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Michael Mazzocchi (ME Engineers) | 2021-02-18 | Submittal Number: 27 53 20-24.0 From: COLIN SAIZ Final Due Date: 03/08/21 Subject: DAS/ WI-FI UNDER SEAT MOCK-UP Description: 1. ENCLOSURES NOT SECURED TO PRECAST 2. TREAD TO BOTTOM OF RAIL DIMENSION: 7" 3. SPACING BETWEEN SEAT RAIL BRACKETS CAN INCREASE BY 12" Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 14512 | Forwarded | For Review | 2021-02-04 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-02-11 | Submittal Number: 27 53 20-24.0 From: COLIN SAIZ Final Due Date: 03/08/21 Subject: DAS/ WI-FI UNDER SEAT MOCK-UP Description: 1. ENCLOSURES NOT SECURED TO PRECAST 2. TREAD TO BOTTOM OF RAIL DIMENSION: 7" 3. SPACING BETWEEN SEAT RAIL BRACKETS CAN INCREASE BY 12" Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 12296 | Review Response | No Action Taken or Required | 2021-03-23 | Michael Mazzocchi (ME Engineers) | Shaina Burris (Populous) |  |  | Info Exchange
| 15926 | Responded and Closed | No Action Taken or Required | 2021-03-29 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Colin.Saiz@mortenson.com |  | Response (No Action Taken or Required) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-04 |  | 275320-024-0 DAS. Wi-Fi Under Seat Mock-Up.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-04 |  | 275320-024-0 DAS. Wi-Fi Under Seat Mock-Up.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-02-03 02:00 |  | 275320-024-0 DAS. Wi-Fi Under Seat Mock-Up.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-03 02:00 |  | 275320-024-0 DAS. Wi-Fi Under Seat Mock-Up.pdf
27 53 20-035-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-035-00 MAP 1800 Plastic Access Pnl | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-18 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-04-01 | 2021-03-19 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12102 | Received | For Review | 2021-03-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-01 | Submittal Number: 27 53 20-35.0 From: JILL OLSON Final Due Date: 04/02/21 Subject: 27-53-20 MAP 1800 PLASTIC ACCESS PNL Description: PLEASE NOTE: SIZE NEEDED -ROUGH OPENING 18X18/ FLANGE 20 1/4 X 20 1/4 Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 15661 | Forwarded | For Review | 2021-03-18 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti) | 2021-03-25 | Submittal Number: 27 53 20-35.0 From: JILL OLSON Final Due Date: 04/02/21 Subject: 27-53-20 MAP 1800 PLASTIC ACCESS PNL Description: PLEASE NOTE: SIZE NEEDED -ROUGH OPENING 18X18/ FLANGE 20 1/4 X 20 1/4 Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 12117 | Review Response | Revise and Resubmit | 2021-03-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Provide the same access panels for DAS that the rest of the building is using- sizes can vary. Provide a trimless, paintable option that matches the product in permium areas. Provide a flanges option that matches the product in the rest of the arena. | Info Exchange
| 15683 | Responded and Closed | Revise and Resubmit | 2021-03-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | 1. Provide the same access panels for DAS that the rest of the building is using- sizes can vary. GC to confirm on submittal review. 2. Provide a trimless, paintable option that matches the product in premium areas. 3. Provide a flanged option that matches the product in the rest of the arena. | Info Exchange
| 15686 | Reopened | Additional Information | 2021-03-19 14:48 | Kuebler Perry (Populous)
| 12119 | Review Response | Approved as Noted | 2021-03-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 15687 | Responded and Closed | Approved as Noted | 2021-03-19 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-18 |  | 275320-035-0 MAP 1800 Plastic Access Pnl.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-18 |  | 275320-035-0 MAP 1800 Plastic Access Pnl.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-18 |  | 275320-035-0 MAP 1800 Plastic Access Pnl.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-03-19 |  | 275320-035-0 MAP _POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-18 |  | 275320-035-0 MAP 1800 Plastic Access Pnl.pdf
27 53 20-036-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-036-00 oDAS 24x36x30 HandHole | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-25 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-03-11 | 2021-03-16 | 20 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-03-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11643 | Received | For Review | 2021-02-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Stieritz | 2021-03-11 | Submittal Number: 27 53 20-36.0 From: JILL OLSON Final Due Date: 03/12/21 Subject: 27-53-20 ODAS 24X36X30 HANDHOLE Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 15089 | Forwarded | For Review | 2021-02-25 | Cody Stieritz | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-03-04 | Submittal Number: 27 53 20-36.0 From: JILL OLSON Final Due Date: 03/12/21 Subject: 27-53-20 ODAS 24X36X30 HANDHOLE Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 12059 | Review Response | Approved | 2021-03-10 | Michael Mazzocchi (ME Engineers) | Cody Stieritz |  |  | Info Exchange
| 15615 | Responded and Closed | Approved | 2021-03-16 | Cody Stieritz | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz |  | Response (Approved) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-25 |  | 275320-036-0 oDAS 24x36x30 HandHole.pdf
| Forwarded |  | Cody Stieritz | 1 | 2021-02-25 |  | 275320-036-0 oDAS 24x36x30 HandHole.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-02-24 02:00 |  | 275320-036-0 oDAS 24x36x30 HandHole.pdf
| Responded and Closed |  | Cody Stieritz | 1 | 2021-03-16 02:00 |  | 275320-036-0 DAS 24x36x30 HandHole - ME Response_POP.pdf
27 53 20-044-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-044-00 DAS ED.8.100 / Event Levels A-F Point Load | Closed | Technology, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-01 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-03-15 | 2021-03-08 | 8 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11695 | Received | For Review | 2021-03-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-15 | Submittal Number: 27 53 20-44.0 From: JILL OLSON Final Due Date: 03/15/21 Subject: DAS ED.8.100 / EVENT LEVELS A-F POINT LOAD Description: MARKUP REFLECTING MAX WEIGHT FOR SECTIONS OUTLINED AND CALCULATED WEIGHT AT EACH POINT Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 15152 | Forwarded | For Review | 2021-03-01 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Mazzocchi (ME Engineers) | 2021-03-08 | Submittal Number: 27 53 20-44.0 From: JILL OLSON Final Due Date: 03/15/21 Subject: DAS ED.8.100 / EVENT LEVELS A-F POINT LOAD Description: MARKUP REFLECTING MAX WEIGHT FOR SECTIONS OUTLINED AND CALCULATED WEIGHT AT EACH POINT Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 11855 | Review Response | Approved | 2021-03-02 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. | Info Exchange
| 15371 | Responded and Closed | Approved | 2021-03-08 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz; Colin.Saiz@mortenson.com |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-26 02:00 |  | 275320-044-0 DAS - ED.8.100.A-F - EVENT LEVEL POINT LOADS.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-26 02:00 |  | 27 53 20-044-00 DAS EVENT LEVEL POINT LOADS_MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-26 02:00 |  | 27 53 20-044-00 DAS EVENT LEVEL POINT LOADS_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-08 02:00 |  | 27 53 20-044-00 DAS EVENT LEVEL POINT LOADS_MAM_TT_POP.pdf
27 53 20-045-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-045-00 DAS MAIN CONCOURSE A-F POINT LOAD | Closed | Technology, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-26 | Responded and Closed - Approved |  | Bryan Klote (Populous), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-03-12 | 2021-03-08 | 11 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11698 | Received | For Review | 2021-02-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Stieritz | 2021-03-12 | Submittal Number: 27 53 20-45.0 From: JILL OLSON Final Due Date: 03/15/21 Subject: DAS ED.8.300 / MAIN CONCOURSE A-F POINT LOAD Description: MARKUP REFLECTING MAX WEIGHT FOR SECTIONS OUTLINED AND CALCULATED WEIGHT AT EACH POINT Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 15155 | Forwarded | For Review | 2021-03-01 | Josh Dobken (Populous) | Bryan Klote (Populous); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Mazzocchi (ME En... | 2021-03-08 | Submittal Number: 27 53 20-45.0 From: JILL OLSON Final Due Date: 03/15/21 Subject: DAS ED.8.300 / MAIN CONCOURSE A-F POINT LOAD Description: MARKUP REFLECTING MAX WEIGHT FOR SECTIONS OUTLINED AND CALCULATED WEIGHT AT EACH POINT Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 11854 | Review Response | Approved | 2021-03-02 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | TT has no exceptions. | Info Exchange
| 15368 | Responded and Closed | Approved | 2021-03-08 | Josh Dobken (Populous) | Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz; Colin.Saiz@mortenson.com |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-26 02:00 |  | 275320-045-0 DAS ED.8.300 _MAIN CONCOURSE A-F POINT LOAD.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-26 02:00 |  | 27 53 20-045-00 MAIN CONCOURSE A-F POINT LOAD_MAM.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-02-26 02:00 |  | 27 53 20-045-00 MAIN CONCOURSE A-F POINT LOAD_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-03-08 02:00 |  | 27 53 20-045-00 MAIN CONCOURSE A-F POINT LOAD_MAM_TT_POP.pdf
27 53 20-050-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-050-00 DAS ED.8.200. A-F - Mech Mezz POINT LOADS | Closed | Structural, Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-04 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-03-18 | 2021-03-05 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-03-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11795 | Received | For Review | 2021-03-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-18 | Submittal Number: 27 53 20-50.0 From: JILL OLSON Final Due Date: 03/19/21 Subject: DAS ED.8.200. A-F - MECH MEZZ POINT LOADS Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 15283 | Forwarded | For Review | 2021-03-04 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (M... | 2021-03-11 | Submittal Number: 27 53 20-50.0 From: JILL OLSON Final Due Date: 03/19/21 Subject: DAS ED.8.200. A-F - MECH MEZZ POINT LOADS Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 11824 | Review Response | Approved | 2021-03-05 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | TT has no exceptions. Any and all connections to precast stadia units to be coordinated with and reviewed by precast engineers. | Info Exchange
| 15329 | Responded and Closed | Approved | 2021-03-05 | Populous SCA_CCA | Elliott Veazey (CAA ICON / Strategy Advisory); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Koch (CAA ICON / Strategy Advisory); Cody Stieritz; Colin.Saiz@mortenson.com |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions. Any and all connections to precast stadia units to be coordinated with and reviewed by precast engineers. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-04 |  | 275320-050-0 ED.8.200.A-F- Mech Mezz Point Loads.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-04 |  | 275320-050-0 ED.8.200.A-F- Mech Mezz Point Loads.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-03 02:00 |  | 275320-050-0 ED.8.200.A-F- Mech Mezz Point Loads.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-05 02:00 |  | 275320-050-0 ED.8.200.A-F- Mech Mezz Point Loads_TT+POP.pdf
27 53 20-051-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-051-00 ED.8.500 A-D Upper Concourse POINT LOADS | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-12 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2021-03-26 | 2021-03-22 | 11 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11968 | Received | For Review | 2021-03-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-26 | Submittal Number: 27 53 20-51.0 From: JILL OLSON Final Due Date: 03/29/21 Subject: ED.8.500 A-D UPPER CONCOURSE POINT LOADS Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 15503 | Forwarded | For Review | 2021-03-12 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-19 | Submittal Number: 27 53 20-51.0 From: JILL OLSON Final Due Date: 03/29/21 Subject: ED.8.500 A-D UPPER CONCOURSE POINT LOADS Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 12148 | Review Response | Approved | 2021-03-17 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | All loads imposed and attachment to precast to be verified by Precast Engineer. | Info Exchange
| 15714 | Responded and Closed | Approved as Noted | 2021-03-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | All loads imposed and attachment to precast to be verified by Precast Engineer. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-12 |  | 275320-51-0 ED.8.500 A-D UPPER CONCOURSE POINT LOADS.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-12 |  | 275320-51-0 ED.8.500 A-D UPPER CONCOURSE POINT LOADS.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-03-12 |  | 275320-51-0 ED.8.500 A-D UPPER CONCOURSE POINT LOADS.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-12 |  | 275320-51-0 ED.8.500 A-D UPPER CONCOURSE POINT LOADS.pdf
27 53 20-052-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-052-00 DAS -Underseat Enclosures | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-03-29 | 2021-04-12 | 29 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2021-04-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12003 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Michael Mazzocchi (ME Engineers) | 2021-03-29 | Submittal Number: 27 53 20-52.0 From: JILL OLSON Final Due Date: 04/06/21 Subject: 27-53-20 DAS -UNDERSEAT ENCLOSURES Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 15548 | Forwarded | For Review | 2021-03-15 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth Knihtila (Thornton Tomasetti); Sean Mc... | 2021-03-22 | Submittal Number: 27 53 20-52.0 From: JILL OLSON Final Due Date: 04/06/21 Subject: 27-53-20 DAS -UNDERSEAT ENCLOSURES Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 15570 | Forwarded | For Review | 2021-03-15 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Michael Mazzocchi (ME Engineers) | 2021-03-22 | Submittal Number: 27 53 20-52.0 From: JILL OLSON Final Due Date: 04/06/21 Subject: 27-53-20 DAS -UNDERSEAT ENCLOSURES Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 16168 | Forwarded | For Review | 2021-04-08 | Josh Dobken (Populous) | Michael Mazzocchi (ME Engineers) | 2021-03-29 | Submittal Number: 27 53 20-52.0 From: JILL OLSON Final Due Date: 04/06/21 Subject: 27-53-20 DAS -UNDERSEAT ENCLOSURES Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 12548 | Review Response | Approved | 2021-04-09 | Michael Mazzocchi (ME Engineers) | Josh Dobken (Populous) |  |  | Info Exchange
| 16255 | Responded and Closed | Approved | 2021-04-12 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz; Colin.Saiz@mortenson.com |  | Response (Approved) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-15 |  | 27 53 20-52.0 DAS- Underseat Enclosures.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-15 |  | 27 53 20-52.0 DAS- Underseat Enclosures.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-14 03:00 |  | 27 53 20-52.0 DAS- Underseat Enclosures.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-14 03:00 |  | 27 53 20-52.0 DAS- Underseat Enclosures.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-03-14 03:00 |  | 27 53 20-52.0 DAS- Underseat Enclosures.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-12 02:00 |  | 27 53 20-52.0 DAS- Underseat Enclosures - MEE_POP.pdf
27 53 20-053-01 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-053-01 DAS South Parcel Garage-Conduit Install | Closed | Structural, Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-05 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-04-19 | 2021-05-05 | 31 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-05-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12374 | Received | For Review | 2021-04-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-19 | Submittal Number: 27 53 20-53.1 From: JILL OLSON Final Due Date: 04/16/21 Subject: 27-53-20 DAS SOUTH PARCEL GARAGE-CONDUIT INSTALL Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 16030 | Forwarded | For Review | 2021-04-01 | Populous SCA_CCA | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (ME Engineers); Sean McNeill (Thornton T... | 2021-04-08 | Submittal Number: 27 53 20-53.1 From: JILL OLSON Final Due Date: 04/16/21 Subject: 27-53-20 DAS SOUTH PARCEL GARAGE-CONDUIT INSTALL Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 12659 | Review Response | Approved as Noted | 2021-04-15 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 16703 | Forwarded | For Review | 2021-05-04 | Populous SCA_CCA | Michael Mazzocchi (ME Engineers) | 2021-04-19 | Submittal Number: 27 53 20-53.1 From: JILL OLSON Final Due Date: 04/16/21 Subject: 27-53-20 DAS SOUTH PARCEL GARAGE-CONDUIT INSTALL Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 16762 | Responded and Closed | Approved as Noted | 2021-05-05 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz; Colin.Saiz@mortenson.com |  | Response (Approved as Noted) from: Michael Mazzocchi (ME Engineers) Remarks: APPROVED AS NOTED - MISSING LEVELS 1 & 2. AS LONG AS CONDUIT INSTALLED ON MISSING LEVELS IS CONSISTENT WITH UPPER LEVELS, NO NEED FOR RESUBMISSION. CONTRACTOR TO CONFRIM NO DIFFERENCES WITH THESE LEVELS. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 275320-053-0 DAS South Parcel Garage-Conduit Install.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 275320-053-0 DAS South Parcel Garage-Conduit Install.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-04-01 |  | 275320-053-0 DAS South Parcel Garage-Conduit Install.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-31 02:00 |  | 275320-053-0 DAS South Parcel Garage-Conduit Install.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-05 02:00 |  | 275320-053-0 DAS South Parcel Garage-Conduit Install - MEE Response_pop.pdf
27 53 20-066-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-066-00 Prime Snorkel Waterproofing_Snyder 4.2.21 | Closed | Structural, Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-06 | Responded and Closed - Not Required For Review |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-04-20 | 2021-04-07 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-04-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12420 | Received | For Review | 2021-04-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Stieritz | 2021-04-20 | Submittal Number: 27 53 20-66.0 From: JILL OLSON Final Due Date: 04/21/21 Subject: 27-53-20 PRIME SNORKEL WATERPROOFING_SNYDER 4.2.21 Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 16094 | Forwarded | For Review | 2021-04-06 | Cody Stieritz | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (ME Engineers); Sean McNeill (Thornton T... | 2021-04-13 | Submittal Number: 27 53 20-66.0 From: JILL OLSON Final Due Date: 04/21/21 Subject: 27-53-20 PRIME SNORKEL WATERPROOFING_SNYDER 4.2.21 Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 16134 | Responded and Closed | Not Required For Review | 2021-04-07 | Cody Stieritz | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Colin.Saiz@mortenson.com |  | Not reviewed. | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 275320-066-0 Prime Snorkel Waterproofing_Snyder.pdf
| Forwarded |  | Cody Stieritz | 1 | 2021-04-05 |  | 275320-066-0 Prime Snorkel Waterproofing_Snyder.pdf
| Responded and Closed |  | Cody Stieritz | 1 | 2021-04-04 02:00 |  | 275320-066-0 Prime Snorkel Waterproofing_Snyder.pdf
27 53 20-067-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-067-00 DAS South Parcel Garage-POINT LOADS | Closed | Structural, Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-06 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-04-20 | 2021-04-20 | 15 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12421 | Received | For Review | 2021-04-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Stieritz | 2021-04-20 | Submittal Number: 27 53 20-67.0 From: JILL OLSON Final Due Date: 04/21/21 Subject: 27-53-20 DAS SOUTH PARCEL GARAGE-POINT LOADS Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 16095 | Forwarded | For Review | 2021-04-06 | Cody Stieritz | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (ME Engineers); Sean McNeill (Thornton T... | 2021-04-13 | Submittal Number: 27 53 20-67.0 From: JILL OLSON Final Due Date: 04/21/21 Subject: 27-53-20 DAS SOUTH PARCEL GARAGE-POINT LOADS Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 12689 | Review Response | Approved as Noted | 2021-04-07 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See comments in attached submittal. TT-FK ¦ 2021-04-07 | Info Exchange
| 12789 | Review Response | Not Required For Review | 2021-04-15 | Michael Mazzocchi (ME Engineers) | Cody Stieritz |  |  | Info Exchange
| 16409 | Responded and Closed | Approved as Noted | 2021-04-20 | Bryan Klote (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz; Colin.Saiz@mortenson.com |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments in attached submittal. TT-FK ¦ 2021-04-07 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-05 |  | 275320-067-0 DAS South Parcel Garage- POINT LOADS.pdf
| Forwarded |  | Cody Stieritz | 1 | 2021-04-05 |  | 275320-067-0 DAS South Parcel Garage- POINT LOADS.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-04-05 |  | 275320-067-0 DAS South Parcel Garage- POINT LOADS.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-04-04 02:00 |  | 275320-067-0 DAS South Parcel Garage- POINT LOADS.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-04-20 |  | 275320-067-0 DAS South Parcel Garage- POINT LOADS_TT_POP.pdf
27 53 20-073-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-073-00 A-F Suite Level POINT LOADS 4.12.21 | Closed | Technology, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-13 | Responded and Closed - Approved |  | Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-04-27 | 2021-04-27 | 15 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12556 | Received | For Review | 2021-04-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Stieritz | 2021-04-27 | Submittal Number: 27 53 20-73.0 From: JILL OLSON Final Due Date: 04/27/21 Subject: 27-53-20 A-F SUITE LEVEL POINT LOADS 4.12.21 Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 16264 | Forwarded | For Review | 2021-04-13 | Cody Stieritz | Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Heidi Evans (ME Engineers); Sean McNeill (Thornton T... | 2021-04-20 | Submittal Number: 27 53 20-73.0 From: JILL OLSON Final Due Date: 04/27/21 Subject: 27-53-20 A-F SUITE LEVEL POINT LOADS 4.12.21 Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 12819 | Review Response | Approved | 2021-04-13 | Matt Ross (Thornton Tomasetti) | Cody Stieritz |  | EOR has no exceptions. Any and all attachments to precast to be coordinated with precast engineer, typ. | Info Exchange
| 16593 | Responded and Closed | Approved | 2021-04-27 | Cody Stieritz | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz; Colin.Saiz@mortenson.com |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: EOR has no exceptions. Any and all attachments to precast to be coordinated with precast engineer, typ. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-12 |  | 275320-073-0 A-F Suite Level Point Loads.pdf
| Forwarded |  | Cody Stieritz | 1 | 2021-04-12 |  | 275320-073-0 A-F Suite Level Point Loads.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-04-11 02:00 |  | 275320-073-0 A-F Suite Level Point Loads.pdf
| Responded and Closed |  | Cody Stieritz | 1 | 2021-04-27 02:00 |  | 275320-073-0 A-F Suite Level Point Loads_TT_POP.pdf
27 53 20-097-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-097-00 DAS Headend Room - Hermanson Exhaust Submittal | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-16 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-08-30 | 2021-08-18 | 3 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-08-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14386 | Received | For Review | 2021-08-16 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-08-30 | Submittal Number: 27 53 20-97.0 From: COLIN SAIZ Final Due Date: 08/20/21 Subject: DAS HEADEND ROOM - HERMANSON EXHAUST SUBMITTAL Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 18562 | Forwarded | For Review | 2021-08-16 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-08-23 | Submittal Number: 27 53 20-97.0 From: COLIN SAIZ Final Due Date: 08/20/21 Subject: DAS HEADEND ROOM - HERMANSON EXHAUST SUBMITTAL Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 14407 | Review Response | Approved | 2021-08-16 | Nick Theimer (ME Engineers) | Populous SCA_CCA |  | See attached for review. Nick Theimer ME Engineers 2021.08.16 | Info Exchange
| 18593 | Responded and Closed | Approved | 2021-08-18 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.08.16 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-16 |  | 275320-097-0 DAS Headend Room - Hermanson Exhaust Submittal.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-16 |  | 275320-097-0 DAS Headend Room - Hermanson Exhaust Submittal.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-08-16 |  | 275320-097-0 DAS Headend Room - Hermanson Exhaust Submittal.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-18 |  | 275320-097-0 DAS Headend Room - Hermanson Exhaust Submittal_ME_POP.pdf
27 53 20-098-00 | 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENT | 27 53 20-098-00 DAS - Nystrom Access Door Product Data | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-19 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-09-02 | 2021-08-24 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14418 | Received | For Review | 2021-08-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-02 | Submittal Number: 27 53 20-98.0 From: COLIN SAIZ Final Due Date: 09/03/21 Subject: DAS - NYSTROM ACCESS DOOR PRODUCT DATA Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 18612 | Forwarded | For Review | 2021-08-19 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-08-26 | Submittal Number: 27 53 20-98.0 From: COLIN SAIZ Final Due Date: 09/03/21 Subject: DAS - NYSTROM ACCESS DOOR PRODUCT DATA Description: Spec Section: 27 53 20 - DISTRIBUTED ANTENNA SYSTEMS (DAS) GENERAL REQUIREMENTS Status: OPEN | Info Exchange
| 14448 | Review Response | Approved | 2021-08-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18649 | Responded and Closed | Approved | 2021-08-24 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-19 |  | 275320-098-0 DAS - Nystrom Access Door Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-19 |  | 275320-098-0 DAS - Nystrom Access Door Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-24 02:00 |  | 275320-098-0 DAS - Nystrom Access Door Product Data_POP.pdf
28 00 00-001-00 | 28 00 00 - SECURITY SYSTEMS - GENERAL | 28 00 00-001-00 SECURITY SYSTEMS GENERAL - Product Data, Compliance Matrix, and Shop Drawings | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-21 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist |  |  |  | 2020-09-10 | 2020-09-22 | 33 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2020-09-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07673 | Received | For Review | 2020-08-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-09-10 | Submittal Number: 28 00 00-1.0 From: ELLA PILGRIM Final Due Date: 09/11/20 Subject: SECURITY SYSTEMS GENERAL - PRODUCT DATA, COMPLIANCE MATRIX, AND SHOP DRAWINGS Description: PRODUCT DATA : - 1. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. D. AS SPECIFIED: CLEARLY IDENTIFY IF THE COMPONENT IS AS SPECIFIED OR IS A SUBSTITUTE TO THE COMPONENT SPECIFIED. E. COMPONENT LIST ORDER: THE COMPONENT LIST ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 2. CUT SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDICES WITHIN EACH DIVISION 28 SPECIFICATION SUB- SECTION. CUT SHEETS SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. HIGHLIGHT APPLICABLE PART NUMBERS. D. CUT SHEET ORDER: THE CUT SHEET ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 3. PRODUCT SUBSTITUTIONS: REFER TO SUBSTITUTION SECTION (SEE ABOVE). 4. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDE A SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO APPENDIX 2 AT THE END OF THIS SECTION FOR ADDITIONAL REQUIREMENTS. A. GENERAL NOTICE: PROVIDE A GENERAL NOTICE FOR ACCEPTANCE OF ALL SECTIONS WITH THIS SPECIFICATION. B. EXCEPTIONS: 1) PROVIDE ALL EXCEPTION TO THE SPECIFICATION LIST: A) SPECIFICATIONS SECTION REFERENCE B) STATEMENT OF EXCEPTION C) EXPLANATION OF EXCEPTION 2) IF THE CONTRACT HAS NO EXCEPTION TO THE SPECIFICATIONS THEN PROVIDE A NO EXCEPTIONS TAKEN STATEMENT. SHOP DRAWINGS AND AS-BUILT DRAWINGS : SUBMIT DRAWINGS ON PROPOSED LAYOUT(S) OF SECURITY SYSTEMS COMPONENTS. THE FOLLOWING DRAWINGS SHALL BE SUBMITTED FOR REVIEW BY ARCHITECT, ENGINEER, AND OWNER; PRIOR TO COMMENCING INSTALLATION OF ANY SECURITY SYSTEMS COMPONENTS: 1. LEGEND: PROVIDE DRAWINGS INCLUDING DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS. 2. ONE-LINE DIAGRAMS: PROVIDE DRAWINGS THAT INDICATE ALL EQUIPMENT COMPONENTS, LOCATIONS, INTEGRATION, ETC. AS REQUIRED TO COMPLETE A FULLY FUNCTIONING SECURITY SYSTEM AS DESCRIBED THROUGHOUT THE SECURITY SPECIFICATIONS AND DRAWINGS. 3. PLANS: PROVIDE SCALED SITE AND BUILDING PLAN DRAWINGS (WITH CURRENT REFLECTED CEILING PLAN LAYER SHOWN) BASED ON ARCHITECTURAL BACKGROUND INDICATING FIELD DEVICES, EQUIPMENT LOCATIONS, RACKS LOCATIONS, PANEL LOCATIONS AND CABLE PATHWAYS. 4. ENLARGED PLANS AND ELEVATIONS: PROVIDE ENLARGED SCALED PLAN DRAWINGS AND ELEVATIONS FOR EQUIPMENT LAYOUTS IN ALL SECURITY MONITORING LOCATIONS AND EACH COMMUNICATIONS ROOM (AND/OR OTHER APPLICABLE ROOMS WITH SECURITY COMPONENTS). DRAWINGS SHALL INCLUDE WALLS, DOOR(S), AND ALL ITEMS LISTED IN SECTION ABOVE. 5. DETAILS: PROVIDE DETAIL DRAWINGS AS REQUIRED TO SHOW COMPONENTS REQUIRING GREATER DETAIL, INCLUDING BUT NOT LIMITED TO, CAMERA MOUNTING DETAILS, SECURITY CONTROL PANEL MOUNTING AND COMPONENTS, IP ENCODERS AND COMPONENT INTERFACES, ETC. 6. LABELING: PROVIDED DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, JUNCTION BOXES, CABLE, OUTLETS, CROSS-CONNECTS, PATCH CABLES, DEVICE FACEPLATES, ETC. ADDITIONALLY, ALL ELECTRONIC EQUIPMENT SHALL BE LABELED INCLUDING EQUIPMENT RACKS/CABINETS, SECURITY CONTROL PANELS, RECORDING DEVICES, VIDEO SERVERS, VIDEO MONITORS, COMPUTER WORKSTATIONS, VIDEO CAMERAS, IP ENCODERS (AS NECESSARY), MICROPHONES, POWER SUPPLIES, UPS SYSTEMS, MEDIA/TRANSMISSION CONVERTERS AND TRANSCEIVERS, ENCLOSURES, ETC. CONTRACTOR SHALL COORDINATE LABELING OF ALL COMPONENTS WITH THE OWNER, ARCHITECT, AND ENGINEER PRIOR TO COMMENCING WORK. 7. DOCUMENTATION: PROVIDE A MINIMUM OF ONE (1) HARDCOPY SET OF PRINTS FOR REVIEW IF THE DIVISION 1 REQUIREMENTS DO NOT REQUIRE HARD COPIES. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. 8. AS-BUILT DRAWING DOCUMENTATION: ALL DOCUMENTATION SHALL BE SHALL BE PROVIDED AS AUTOCAD (CURRENT VERSION) FILES OR AS SPECIFIED IN THE DIVISION 1 REQUIREMENTS. ADDITIONALLY, PROVIDE AN ELECTRONIC PDF COPY OF AS-BUILT DRAWINGS TO THE ENGINEER UPON PROJECT CLOSE-OUT. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 10218 | Forwarded | For Review | 2020-08-24 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-08-31 | Submittal Number: 28 00 00-1.0 From: ELLA PILGRIM Final Due Date: 09/11/20 Subject: SECURITY SYSTEMS GENERAL - PRODUCT DATA, COMPLIANCE MATRIX, AND SHOP DRAWINGS Description: PRODUCT DATA : - 1. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. D. AS SPECIFIED: CLEARLY IDENTIFY IF THE COMPONENT IS AS SPECIFIED OR IS A SUBSTITUTE TO THE COMPONENT SPECIFIED. E. COMPONENT LIST ORDER: THE COMPONENT LIST ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 2. CUT SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDICES WITHIN EACH DIVISION 28 SPECIFICATION SUB- SECTION. CUT SHEETS SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. HIGHLIGHT APPLICABLE PART NUMBERS. D. CUT SHEET ORDER: THE CUT SHEET ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 3. PRODUCT SUBSTITUTIONS: REFER TO SUBSTITUTION SECTION (SEE ABOVE). 4. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDE A SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO APPENDIX 2 AT THE END OF THIS SECTION FOR ADDITIONAL REQUIREMENTS. A. GENERAL NOTICE: PROVIDE A GENERAL NOTICE FOR ACCEPTANCE OF ALL SECTIONS WITH THIS SPECIFICATION. B. EXCEPTIONS: 1) PROVIDE ALL EXCEPTION TO THE SPECIFICATION LIST: A) SPECIFICATIONS SECTION REFERENCE B) STATEMENT OF EXCEPTION C) EXPLANATION OF EXCEPTION 2) IF THE CONTRACT HAS NO EXCEPTION TO THE SPECIFICATIONS THEN PROVIDE A NO EXCEPTIONS TAKEN STATEMENT. SHOP DRAWINGS AND AS-BUILT DRAWINGS : SUBMIT DRAWINGS ON PROPOSED LAYOUT(S) OF SECURITY SYSTEMS COMPONENTS. THE FOLLOWING DRAWINGS SHALL BE SUBMITTED FOR REVIEW BY ARCHITECT, ENGINEER, AND OWNER; PRIOR TO COMMENCING INSTALLATION OF ANY SECURITY SYSTEMS COMPONENTS: 1. LEGEND: PROVIDE DRAWINGS INCLUDING DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS. 2. ONE-LINE DIAGRAMS: PROVIDE DRAWINGS THAT INDICATE ALL EQUIPMENT COMPONENTS, LOCATIONS, INTEGRATION, ETC. AS REQUIRED TO COMPLETE A FULLY FUNCTIONING SECURITY SYSTEM AS DESCRIBED THROUGHOUT THE SECURITY SPECIFICATIONS AND DRAWINGS. 3. PLANS: PROVIDE SCALED SITE AND BUILDING PLAN DRAWINGS (WITH CURRENT REFLECTED CEILING PLAN LAYER SHOWN) BASED ON ARCHITECTURAL BACKGROUND INDICATING FIELD DEVICES, EQUIPMENT LOCATIONS, RACKS LOCATIONS, PANEL LOCATIONS AND CABLE PATHWAYS. 4. ENLARGED PLANS AND ELEVATIONS: PROVIDE ENLARGED SCALED PLAN DRAWINGS AND ELEVATIONS FOR EQUIPMENT LAYOUTS IN ALL SECURITY MONITORING LOCATIONS AND EACH COMMUNICATIONS ROOM (AND/OR OTHER APPLICABLE ROOMS WITH SECURITY COMPONENTS). DRAWINGS SHALL INCLUDE WALLS, DOOR(S), AND ALL ITEMS LISTED IN SECTION ABOVE. 5. DETAILS: PROVIDE DETAIL DRAWINGS AS REQUIRED TO SHOW COMPONENTS REQUIRING GREATER DETAIL, INCLUDING BUT NOT LIMITED TO, CAMERA MOUNTING DETAILS, SECURITY CONTROL PANEL MOUNTING AND COMPONENTS, IP ENCODERS AND COMPONENT INTERFACES, ETC. 6. LABELING: PROVIDED DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, JUNCTION BOXES, CABLE, OUTLETS, CROSS-CONNECTS, PATCH CABLES, DEVICE FACEPLATES, ETC. ADDITIONALLY, ALL ELECTRONIC EQUIPMENT SHALL BE LABELED INCLUDING EQUIPMENT RACKS/CABINETS, SECURITY CONTROL PANELS, RECORDING DEVICES, VIDEO SERVERS, VIDEO MONITORS, COMPUTER WORKSTATIONS, VIDEO CAMERAS, IP ENCODERS (AS NECESSARY), MICROPHONES, POWER SUPPLIES, UPS SYSTEMS, MEDIA/TRANSMISSION CONVERTERS AND TRANSCEIVERS, ENCLOSURES, ETC. CONTRACTOR SHALL COORDINATE LABELING OF ALL COMPONENTS WITH THE OWNER, ARCHITECT, AND ENGINEER PRIOR TO COMMENCING WORK. 7. DOCUMENTATION: PROVIDE A MINIMUM OF ONE (1) HARDCOPY SET OF PRINTS FOR REVIEW IF THE DIVISION 1 REQUIREMENTS DO NOT REQUIRE HARD COPIES. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. 8. AS-BUILT DRAWING DOCUMENTATION: ALL DOCUMENTATION SHALL BE SHALL BE PROVIDED AS AUTOCAD (CURRENT VERSION) FILES OR AS SPECIFIED IN THE DIVISION 1 REQUIREMENTS. ADDITIONALLY, PROVIDE AN ELECTRONIC PDF COPY OF AS-BUILT DRAWINGS TO THE ENGINEER UPON PROJECT CLOSE-OUT. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 08260 | Review Response | Approved as Noted/Resubmit | 2020-09-18 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  | See attached document for submittal 28 00 00 ME response. | Info Exchange
| 10963 | Responded and Closed | Approved as Noted/Resubmit | 2020-09-22 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Resubmit/submit items specified in review. BK/Populous 09.22.2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-20 |  | 28 00 00-1.0 Security Systems General.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-08-20 |  | 28 00 00-1.0 Security Systems General.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-08-20 |  | 28 00 00-1.0 Security Systems General.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-20 |  | 28 00 00-1.0 Security Systems General.pdf
28 00 00-001-01 | 28 00 00 - SECURITY SYSTEMS - GENERAL | 28 00 00-001-01 SECURITY SYSTEMS GENERAL - Product Data, Compliance Matrix, and Shop Drawings | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-06 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2020-10-26 | 2020-11-03 | 29 |  | Record Copies; Transfers; Submittals |  | 29 |  | 2020-11-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08593 | Received | For Review | 2020-10-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-26 | Submittal Number: 28 00 00-1.1 From: ELLA PILGRIM Final Due Date: 10/20/20 Subject: SECURITY SYSTEMS GENERAL - PRODUCT DATA, COMPLIANCE MATRIX, AND SHOP DRAWINGS Description: PRODUCT DATA : - 1. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. D. AS SPECIFIED: CLEARLY IDENTIFY IF THE COMPONENT IS AS SPECIFIED OR IS A SUBSTITUTE TO THE COMPONENT SPECIFIED. E. COMPONENT LIST ORDER: THE COMPONENT LIST ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 2. CUT SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDICES WITHIN EACH DIVISION 28 SPECIFICATION SUB- SECTION. CUT SHEETS SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. HIGHLIGHT APPLICABLE PART NUMBERS. D. CUT SHEET ORDER: THE CUT SHEET ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 3. PRODUCT SUBSTITUTIONS: REFER TO SUBSTITUTION SECTION (SEE ABOVE). 4. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDE A SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO APPENDIX 2 AT THE END OF THIS SECTION FOR ADDITIONAL REQUIREMENTS. A. GENERAL NOTICE: PROVIDE A GENERAL NOTICE FOR ACCEPTANCE OF ALL SECTIONS WITH THIS SPECIFICATION. B. EXCEPTIONS: 1) PROVIDE ALL EXCEPTION TO THE SPECIFICATION LIST: A) SPECIFICATIONS SECTION REFERENCE B) STATEMENT OF EXCEPTION C) EXPLANATION OF EXCEPTION 2) IF THE CONTRACT HAS NO EXCEPTION TO THE SPECIFICATIONS THEN PROVIDE A NO EXCEPTIONS TAKEN STATEMENT. SHOP DRAWINGS AND AS-BUILT DRAWINGS : SUBMIT DRAWINGS ON PROPOSED LAYOUT(S) OF SECURITY SYSTEMS COMPONENTS. THE FOLLOWING DRAWINGS SHALL BE SUBMITTED FOR REVIEW BY ARCHITECT, ENGINEER, AND OWNER; PRIOR TO COMMENCING INSTALLATION OF ANY SECURITY SYSTEMS COMPONENTS: 1. LEGEND: PROVIDE DRAWINGS INCLUDING DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS. 2. ONE-LINE DIAGRAMS: PROVIDE DRAWINGS THAT INDICATE ALL EQUIPMENT COMPONENTS, LOCATIONS, INTEGRATION, ETC. AS REQUIRED TO COMPLETE A FULLY FUNCTIONING SECURITY SYSTEM AS DESCRIBED THROUGHOUT THE SECURITY SPECIFICATIONS AND DRAWINGS. 3. PLANS: PROVIDE SCALED SITE AND BUILDING PLAN DRAWINGS (WITH CURRENT REFLECTED CEILING PLAN LAYER SHOWN) BASED ON ARCHITECTURAL BACKGROUND INDICATING FIELD DEVICES, EQUIPMENT LOCATIONS, RACKS LOCATIONS, PANEL LOCATIONS AND CABLE PATHWAYS. 4. ENLARGED PLANS AND ELEVATIONS: PROVIDE ENLARGED SCALED PLAN DRAWINGS AND ELEVATIONS FOR EQUIPMENT LAYOUTS IN ALL SECURITY MONITORING LOCATIONS AND EACH COMMUNICATIONS ROOM (AND/OR OTHER APPLICABLE ROOMS WITH SECURITY COMPONENTS). DRAWINGS SHALL INCLUDE WALLS, DOOR(S), AND ALL ITEMS LISTED IN SECTION ABOVE. 5. DETAILS: PROVIDE DETAIL DRAWINGS AS REQUIRED TO SHOW COMPONENTS REQUIRING GREATER DETAIL, INCLUDING BUT NOT LIMITED TO, CAMERA MOUNTING DETAILS, SECURITY CONTROL PANEL MOUNTING AND COMPONENTS, IP ENCODERS AND COMPONENT INTERFACES, ETC. 6. LABELING: PROVIDED DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, JUNCTION BOXES, CABLE, OUTLETS, CROSS-CONNECTS, PATCH CABLES, DEVICE FACEPLATES, ETC. ADDITIONALLY, ALL ELECTRONIC EQUIPMENT SHALL BE LABELED INCLUDING EQUIPMENT RACKS/CABINETS, SECURITY CONTROL PANELS, RECORDING DEVICES, VIDEO SERVERS, VIDEO MONITORS, COMPUTER WORKSTATIONS, VIDEO CAMERAS, IP ENCODERS (AS NECESSARY), MICROPHONES, POWER SUPPLIES, UPS SYSTEMS, MEDIA/TRANSMISSION CONVERTERS AND TRANSCEIVERS, ENCLOSURES, ETC. CONTRACTOR SHALL COORDINATE LABELING OF ALL COMPONENTS WITH THE OWNER, ARCHITECT, AND ENGINEER PRIOR TO COMMENCING WORK. 7. DOCUMENTATION: PROVIDE A MINIMUM OF ONE (1) HARDCOPY SET OF PRINTS FOR REVIEW IF THE DIVISION 1 REQUIREMENTS DO NOT REQUIRE HARD COPIES. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. 8. AS-BUILT DRAWING DOCUMENTATION: ALL DOCUMENTATION SHALL BE SHALL BE PROVIDED AS AUTOCAD (CURRENT VERSION) FILES OR AS SPECIFIED IN THE DIVISION 1 REQUIREMENTS. ADDITIONALLY, PROVIDE AN ELECTRONIC PDF COPY OF AS-BUILT DRAWINGS TO THE ENGINEER UPON PROJECT CLOSE-OUT. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 11356 | Forwarded | For Review | 2020-10-06 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2020-10-13 | Submittal Number: 28 00 00-1.1 From: ELLA PILGRIM Final Due Date: 10/20/20 Subject: SECURITY SYSTEMS GENERAL - PRODUCT DATA, COMPLIANCE MATRIX, AND SHOP DRAWINGS Description: PRODUCT DATA : - 1. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. D. AS SPECIFIED: CLEARLY IDENTIFY IF THE COMPONENT IS AS SPECIFIED OR IS A SUBSTITUTE TO THE COMPONENT SPECIFIED. E. COMPONENT LIST ORDER: THE COMPONENT LIST ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 2. CUT SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDICES WITHIN EACH DIVISION 28 SPECIFICATION SUB- SECTION. CUT SHEETS SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. HIGHLIGHT APPLICABLE PART NUMBERS. D. CUT SHEET ORDER: THE CUT SHEET ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 3. PRODUCT SUBSTITUTIONS: REFER TO SUBSTITUTION SECTION (SEE ABOVE). 4. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDE A SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO APPENDIX 2 AT THE END OF THIS SECTION FOR ADDITIONAL REQUIREMENTS. A. GENERAL NOTICE: PROVIDE A GENERAL NOTICE FOR ACCEPTANCE OF ALL SECTIONS WITH THIS SPECIFICATION. B. EXCEPTIONS: 1) PROVIDE ALL EXCEPTION TO THE SPECIFICATION LIST: A) SPECIFICATIONS SECTION REFERENCE B) STATEMENT OF EXCEPTION C) EXPLANATION OF EXCEPTION 2) IF THE CONTRACT HAS NO EXCEPTION TO THE SPECIFICATIONS THEN PROVIDE A NO EXCEPTIONS TAKEN STATEMENT. SHOP DRAWINGS AND AS-BUILT DRAWINGS : SUBMIT DRAWINGS ON PROPOSED LAYOUT(S) OF SECURITY SYSTEMS COMPONENTS. THE FOLLOWING DRAWINGS SHALL BE SUBMITTED FOR REVIEW BY ARCHITECT, ENGINEER, AND OWNER; PRIOR TO COMMENCING INSTALLATION OF ANY SECURITY SYSTEMS COMPONENTS: 1. LEGEND: PROVIDE DRAWINGS INCLUDING DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS. 2. ONE-LINE DIAGRAMS: PROVIDE DRAWINGS THAT INDICATE ALL EQUIPMENT COMPONENTS, LOCATIONS, INTEGRATION, ETC. AS REQUIRED TO COMPLETE A FULLY FUNCTIONING SECURITY SYSTEM AS DESCRIBED THROUGHOUT THE SECURITY SPECIFICATIONS AND DRAWINGS. 3. PLANS: PROVIDE SCALED SITE AND BUILDING PLAN DRAWINGS (WITH CURRENT REFLECTED CEILING PLAN LAYER SHOWN) BASED ON ARCHITECTURAL BACKGROUND INDICATING FIELD DEVICES, EQUIPMENT LOCATIONS, RACKS LOCATIONS, PANEL LOCATIONS AND CABLE PATHWAYS. 4. ENLARGED PLANS AND ELEVATIONS: PROVIDE ENLARGED SCALED PLAN DRAWINGS AND ELEVATIONS FOR EQUIPMENT LAYOUTS IN ALL SECURITY MONITORING LOCATIONS AND EACH COMMUNICATIONS ROOM (AND/OR OTHER APPLICABLE ROOMS WITH SECURITY COMPONENTS). DRAWINGS SHALL INCLUDE WALLS, DOOR(S), AND ALL ITEMS LISTED IN SECTION ABOVE. 5. DETAILS: PROVIDE DETAIL DRAWINGS AS REQUIRED TO SHOW COMPONENTS REQUIRING GREATER DETAIL, INCLUDING BUT NOT LIMITED TO, CAMERA MOUNTING DETAILS, SECURITY CONTROL PANEL MOUNTING AND COMPONENTS, IP ENCODERS AND COMPONENT INTERFACES, ETC. 6. LABELING: PROVIDED DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, JUNCTION BOXES, CABLE, OUTLETS, CROSS-CONNECTS, PATCH CABLES, DEVICE FACEPLATES, ETC. ADDITIONALLY, ALL ELECTRONIC EQUIPMENT SHALL BE LABELED INCLUDING EQUIPMENT RACKS/CABINETS, SECURITY CONTROL PANELS, RECORDING DEVICES, VIDEO SERVERS, VIDEO MONITORS, COMPUTER WORKSTATIONS, VIDEO CAMERAS, IP ENCODERS (AS NECESSARY), MICROPHONES, POWER SUPPLIES, UPS SYSTEMS, MEDIA/TRANSMISSION CONVERTERS AND TRANSCEIVERS, ENCLOSURES, ETC. CONTRACTOR SHALL COORDINATE LABELING OF ALL COMPONENTS WITH THE OWNER, ARCHITECT, AND ENGINEER PRIOR TO COMMENCING WORK. 7. DOCUMENTATION: PROVIDE A MINIMUM OF ONE (1) HARDCOPY SET OF PRINTS FOR REVIEW IF THE DIVISION 1 REQUIREMENTS DO NOT REQUIRE HARD COPIES. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. 8. AS-BUILT DRAWING DOCUMENTATION: ALL DOCUMENTATION SHALL BE SHALL BE PROVIDED AS AUTOCAD (CURRENT VERSION) FILES OR AS SPECIFIED IN THE DIVISION 1 REQUIREMENTS. ADDITIONALLY, PROVIDE AN ELECTRONIC PDF COPY OF AS-BUILT DRAWINGS TO THE ENGINEER UPON PROJECT CLOSE-OUT. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 09212 | Review Response | Revise and Resubmit | 2020-11-03 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 12167 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-03 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Michael Mazzocchi (ME Engineers) Remarks: Refer to MEE comments within disposition sheet for items to be resubmitted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 28 00 00-1.1 Security Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-10-05 |  | 28 00 00-1.1 Security Shop Drawings.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-10-04 02:00 |  | 28 00 00-1.1 Security Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-11-03 02:00 |  | 28 00 00-001-01 SECURITY SYSTEMS GENERAL - ME Response_pop.pdf
28 00 00-001-02 | 28 00 00 - SECURITY SYSTEMS - GENERAL | 28 00 00-001-02 SECURITY SYSTEMS GENERAL - Product Data, Compliance Matrix, and Shop Drawings | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-11-23 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2020-12-15 08:00 | 2020-12-15 | 23 |  | Record Copies; Transfers; Submittals |  | 22 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09662 | Received | For Review | 2020-11-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-15 08:00 | Submittal Number: 28 00 00-1.2 From: ELLA PILGRIM Final Due Date: 12/08/20 Subject: SECURITY SYSTEMS GENERAL - PRODUCT DATA, COMPLIANCE MATRIX, AND SHOP DRAWINGS Description: PRODUCT DATA : - 1. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. D. AS SPECIFIED: CLEARLY IDENTIFY IF THE COMPONENT IS AS SPECIFIED OR IS A SUBSTITUTE TO THE COMPONENT SPECIFIED. E. COMPONENT LIST ORDER: THE COMPONENT LIST ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 2. CUT SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDICES WITHIN EACH DIVISION 28 SPECIFICATION SUB- SECTION. CUT SHEETS SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. HIGHLIGHT APPLICABLE PART NUMBERS. D. CUT SHEET ORDER: THE CUT SHEET ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 3. PRODUCT SUBSTITUTIONS: REFER TO SUBSTITUTION SECTION (SEE ABOVE). 4. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDE A SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO APPENDIX 2 AT THE END OF THIS SECTION FOR ADDITIONAL REQUIREMENTS. A. GENERAL NOTICE: PROVIDE A GENERAL NOTICE FOR ACCEPTANCE OF ALL SECTIONS WITH THIS SPECIFICATION. B. EXCEPTIONS: 1) PROVIDE ALL EXCEPTION TO THE SPECIFICATION LIST: A) SPECIFICATIONS SECTION REFERENCE B) STATEMENT OF EXCEPTION C) EXPLANATION OF EXCEPTION 2) IF THE CONTRACT HAS NO EXCEPTION TO THE SPECIFICATIONS THEN PROVIDE A NO EXCEPTIONS TAKEN STATEMENT. SHOP DRAWINGS AND AS-BUILT DRAWINGS : SUBMIT DRAWINGS ON PROPOSED LAYOUT(S) OF SECURITY SYSTEMS COMPONENTS. THE FOLLOWING DRAWINGS SHALL BE SUBMITTED FOR REVIEW BY ARCHITECT, ENGINEER, AND OWNER; PRIOR TO COMMENCING INSTALLATION OF ANY SECURITY SYSTEMS COMPONENTS: 1. LEGEND: PROVIDE DRAWINGS INCLUDING DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS. 2. ONE-LINE DIAGRAMS: PROVIDE DRAWINGS THAT INDICATE ALL EQUIPMENT COMPONENTS, LOCATIONS, INTEGRATION, ETC. AS REQUIRED TO COMPLETE A FULLY FUNCTIONING SECURITY SYSTEM AS DESCRIBED THROUGHOUT THE SECURITY SPECIFICATIONS AND DRAWINGS. 3. PLANS: PROVIDE SCALED SITE AND BUILDING PLAN DRAWINGS (WITH CURRENT REFLECTED CEILING PLAN LAYER SHOWN) BASED ON ARCHITECTURAL BACKGROUND INDICATING FIELD DEVICES, EQUIPMENT LOCATIONS, RACKS LOCATIONS, PANEL LOCATIONS AND CABLE PATHWAYS. 4. ENLARGED PLANS AND ELEVATIONS: PROVIDE ENLARGED SCALED PLAN DRAWINGS AND ELEVATIONS FOR EQUIPMENT LAYOUTS IN ALL SECURITY MONITORING LOCATIONS AND EACH COMMUNICATIONS ROOM (AND/OR OTHER APPLICABLE ROOMS WITH SECURITY COMPONENTS). DRAWINGS SHALL INCLUDE WALLS, DOOR(S), AND ALL ITEMS LISTED IN SECTION ABOVE. 5. DETAILS: PROVIDE DETAIL DRAWINGS AS REQUIRED TO SHOW COMPONENTS REQUIRING GREATER DETAIL, INCLUDING BUT NOT LIMITED TO, CAMERA MOUNTING DETAILS, SECURITY CONTROL PANEL MOUNTING AND COMPONENTS, IP ENCODERS AND COMPONENT INTERFACES, ETC. 6. LABELING: PROVIDED DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, JUNCTION BOXES, CABLE, OUTLETS, CROSS-CONNECTS, PATCH CABLES, DEVICE FACEPLATES, ETC. ADDITIONALLY, ALL ELECTRONIC EQUIPMENT SHALL BE LABELED INCLUDING EQUIPMENT RACKS/CABINETS, SECURITY CONTROL PANELS, RECORDING DEVICES, VIDEO SERVERS, VIDEO MONITORS, COMPUTER WORKSTATIONS, VIDEO CAMERAS, IP ENCODERS (AS NECESSARY), MICROPHONES, POWER SUPPLIES, UPS SYSTEMS, MEDIA/TRANSMISSION CONVERTERS AND TRANSCEIVERS, ENCLOSURES, ETC. CONTRACTOR SHALL COORDINATE LABELING OF ALL COMPONENTS WITH THE OWNER, ARCHITECT, AND ENGINEER PRIOR TO COMMENCING WORK. 7. DOCUMENTATION: PROVIDE A MINIMUM OF ONE (1) HARDCOPY SET OF PRINTS FOR REVIEW IF THE DIVISION 1 REQUIREMENTS DO NOT REQUIRE HARD COPIES. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. 8. AS-BUILT DRAWING DOCUMENTATION: ALL DOCUMENTATION SHALL BE SHALL BE PROVIDED AS AUTOCAD (CURRENT VERSION) FILES OR AS SPECIFIED IN THE DIVISION 1 REQUIREMENTS. ADDITIONALLY, PROVIDE AN ELECTRONIC PDF COPY OF AS-BUILT DRAWINGS TO THE ENGINEER UPON PROJECT CLOSE-OUT. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 12713 | Forwarded | For Review | 2020-11-23 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2020-11-30 | Submittal Number: 28 00 00-1.2 From: ELLA PILGRIM Final Due Date: 12/08/20 Subject: SECURITY SYSTEMS GENERAL - PRODUCT DATA, COMPLIANCE MATRIX, AND SHOP DRAWINGS Description: PRODUCT DATA : - 1. COMPONENT LIST: PROVIDE COMPLETE SUBMITTAL COMPONENT LIST AT THE BEGINNING OF THE SUBMITTAL PACKAGE. COMPONENT LIST SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. D. AS SPECIFIED: CLEARLY IDENTIFY IF THE COMPONENT IS AS SPECIFIED OR IS A SUBSTITUTE TO THE COMPONENT SPECIFIED. E. COMPONENT LIST ORDER: THE COMPONENT LIST ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 2. CUT SHEETS: SUBMIT MANUFACTURERS CUT-SHEETS ON ALL COMPONENTS LISTED WITHIN THIS SPECIFICATION AND CORRESPONDING APPENDICES WITHIN EACH DIVISION 28 SPECIFICATION SUB- SECTION. CUT SHEETS SHALL INCLUDE: A. COMPONENT DESCRIPTION: CLEARLY IDENTIFY EACH COMPONENT DESCRIPTION B. MANUFACTURER: CLEARLY IDENTIFY THE COMPONENTS MANUFACTURER C. MODEL NUMBER: CLEARLY IDENTIFY SPECIFIC PRODUCT/PART NUMBER. ALL PART NUMBERS SHALL CLEARLY INDICATE SPECIAL OPTIONS, COLOR, ACCESSORIES, ETC. HIGHLIGHT APPLICABLE PART NUMBERS. D. CUT SHEET ORDER: THE CUT SHEET ORDER SHALL BE COMPILED TO MATCH THE ORDER OF APPENDIX 1 WITHIN EACH DIVISION 28 SPECIFICATION SUB-SECTION. APPENDIX 1 CAN BE PROVIDED TO CONTRACT UPON REQUEST. 3. PRODUCT SUBSTITUTIONS: REFER TO SUBSTITUTION SECTION (SEE ABOVE). 4. WARRANTY INFORMATION: PROVIDE ALL WARRANTY INFORMATION AS DESCRIBED IN THIS SPECIFICATION SECTION FOR REVIEW AND APPROVAL. COMPLIANCE MATRIX : - 1. COMPLIANCE MATRIX: PROVIDE A SPECIFICATION COMPLIANCE MATRIX INDICATING COMPLIANCE OR DEVIATION FOR EACH ITEM IN THE SPECIFICATION. REFER TO APPENDIX 2 AT THE END OF THIS SECTION FOR ADDITIONAL REQUIREMENTS. A. GENERAL NOTICE: PROVIDE A GENERAL NOTICE FOR ACCEPTANCE OF ALL SECTIONS WITH THIS SPECIFICATION. B. EXCEPTIONS: 1) PROVIDE ALL EXCEPTION TO THE SPECIFICATION LIST: A) SPECIFICATIONS SECTION REFERENCE B) STATEMENT OF EXCEPTION C) EXPLANATION OF EXCEPTION 2) IF THE CONTRACT HAS NO EXCEPTION TO THE SPECIFICATIONS THEN PROVIDE A NO EXCEPTIONS TAKEN STATEMENT. SHOP DRAWINGS AND AS-BUILT DRAWINGS : SUBMIT DRAWINGS ON PROPOSED LAYOUT(S) OF SECURITY SYSTEMS COMPONENTS. THE FOLLOWING DRAWINGS SHALL BE SUBMITTED FOR REVIEW BY ARCHITECT, ENGINEER, AND OWNER; PRIOR TO COMMENCING INSTALLATION OF ANY SECURITY SYSTEMS COMPONENTS: 1. LEGEND: PROVIDE DRAWINGS INCLUDING DESCRIPTIONS OF ALL ABBREVIATIONS AND SYMBOLS. 2. ONE-LINE DIAGRAMS: PROVIDE DRAWINGS THAT INDICATE ALL EQUIPMENT COMPONENTS, LOCATIONS, INTEGRATION, ETC. AS REQUIRED TO COMPLETE A FULLY FUNCTIONING SECURITY SYSTEM AS DESCRIBED THROUGHOUT THE SECURITY SPECIFICATIONS AND DRAWINGS. 3. PLANS: PROVIDE SCALED SITE AND BUILDING PLAN DRAWINGS (WITH CURRENT REFLECTED CEILING PLAN LAYER SHOWN) BASED ON ARCHITECTURAL BACKGROUND INDICATING FIELD DEVICES, EQUIPMENT LOCATIONS, RACKS LOCATIONS, PANEL LOCATIONS AND CABLE PATHWAYS. 4. ENLARGED PLANS AND ELEVATIONS: PROVIDE ENLARGED SCALED PLAN DRAWINGS AND ELEVATIONS FOR EQUIPMENT LAYOUTS IN ALL SECURITY MONITORING LOCATIONS AND EACH COMMUNICATIONS ROOM (AND/OR OTHER APPLICABLE ROOMS WITH SECURITY COMPONENTS). DRAWINGS SHALL INCLUDE WALLS, DOOR(S), AND ALL ITEMS LISTED IN SECTION ABOVE. 5. DETAILS: PROVIDE DETAIL DRAWINGS AS REQUIRED TO SHOW COMPONENTS REQUIRING GREATER DETAIL, INCLUDING BUT NOT LIMITED TO, CAMERA MOUNTING DETAILS, SECURITY CONTROL PANEL MOUNTING AND COMPONENTS, IP ENCODERS AND COMPONENT INTERFACES, ETC. 6. LABELING: PROVIDED DOCUMENTATION OF ALL LABELING SCHEMES FOR CONDUIT, BACK-BOXES, JUNCTION BOXES, CABLE, OUTLETS, CROSS-CONNECTS, PATCH CABLES, DEVICE FACEPLATES, ETC. ADDITIONALLY, ALL ELECTRONIC EQUIPMENT SHALL BE LABELED INCLUDING EQUIPMENT RACKS/CABINETS, SECURITY CONTROL PANELS, RECORDING DEVICES, VIDEO SERVERS, VIDEO MONITORS, COMPUTER WORKSTATIONS, VIDEO CAMERAS, IP ENCODERS (AS NECESSARY), MICROPHONES, POWER SUPPLIES, UPS SYSTEMS, MEDIA/TRANSMISSION CONVERTERS AND TRANSCEIVERS, ENCLOSURES, ETC. CONTRACTOR SHALL COORDINATE LABELING OF ALL COMPONENTS WITH THE OWNER, ARCHITECT, AND ENGINEER PRIOR TO COMMENCING WORK. 7. DOCUMENTATION: PROVIDE A MINIMUM OF ONE (1) HARDCOPY SET OF PRINTS FOR REVIEW IF THE DIVISION 1 REQUIREMENTS DO NOT REQUIRE HARD COPIES. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. 8. AS-BUILT DRAWING DOCUMENTATION: ALL DOCUMENTATION SHALL BE SHALL BE PROVIDED AS AUTOCAD (CURRENT VERSION) FILES OR AS SPECIFIED IN THE DIVISION 1 REQUIREMENTS. ADDITIONALLY, PROVIDE AN ELECTRONIC PDF COPY OF AS-BUILT DRAWINGS TO THE ENGINEER UPON PROJECT CLOSE-OUT. COORDINATE WITH GENERAL CONTRACTOR OR CONSTRUCTION MANAGER TO ENSURE SUBMISSION IS PER PROJECT REQUIREMENTS. Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 10153 | Review Response | Approved as Noted | 2020-12-14 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 13286 | Responded and Closed | Approved as Noted | 2020-12-15 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Michael Mazzocchi (ME Engineers) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-21 |  | 28 00 00-1.2 Security Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-11-21 |  | 28 00 00-1.2 Security Shop Drawings.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-11-21 |  | 28 00 00-1.2 Security Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-15 |  | 28 00 00-1.2 SECURITY SYSTEMS SHOP DRAWINGS_ME_POP.pdf
28 00 00-009-00 | 28 00 00 - SECURITY SYSTEMS - GENERAL | 28 00 00-009-00 Security Shop Drawings - Deferred Spaces | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-01 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2020-12-15 | 2020-12-15 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09783 | Received | For Review | 2020-12-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-12-15 | Submittal Number: 28 00 00-9.0 From: ELLA PILGRIM Final Due Date: 01/11/21 Subject: SECURITY SHOP DRAWINGS - DEFERRED SPACES Description: Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 12863 | Forwarded | For Review | 2020-12-01 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2020-12-08 | Submittal Number: 28 00 00-9.0 From: ELLA PILGRIM Final Due Date: 01/11/21 Subject: SECURITY SHOP DRAWINGS - DEFERRED SPACES Description: Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 10150 | Review Response | Revise and Resubmit | 2020-12-14 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 13282 | Responded and Closed | Revise and Resubmit | 2020-12-15 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Revise and Resubmit) from: Michael Mazzocchi (ME Engineers) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-01 |  | 28 00 00-9.0 Deferred Space Security Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-12-01 |  | 28 00 00-9.0 Deferred Space Security Shop Drawings.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-12-01 |  | 28 00 00-9.0 Deferred Space Security Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-12-15 |  | 28 00 00-9.0 Deferred Space Security Shop Drawings_ME_POP.pdf
28 00 00-009-01 | 28 00 00 - SECURITY SYSTEMS - GENERAL | 28 00 00-009-01 Security Shop Drawings - Deferred Spaces | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-01-27 08:00 | 2021-02-01 | 21 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-02-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10616 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-27 08:00 | Submittal Number: 28 00 00-9.1 From: ELLA PILGRIM Final Due Date: 01/22/21 Subject: SECURITY SHOP DRAWINGS - DEFERRED SPACES Description: Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 13824 | Forwarded | For Review | 2021-01-11 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-01-18 | Submittal Number: 28 00 00-9.1 From: ELLA PILGRIM Final Due Date: 01/22/21 Subject: SECURITY SHOP DRAWINGS - DEFERRED SPACES Description: Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 11109 | Review Response | Approved as Noted | 2021-01-28 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 14416 | Responded and Closed | Approved as Noted | 2021-02-01 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (Mortenson Construction); Gretchen Toshach (Mortenson C... |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 28 00 00-9.1 Deferred Space Security Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-11 |  | 28 00 00-9.1 Deferred Space Security Shop Drawings.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-01-11 |  | 28 00 00-9.1 Deferred Space Security Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-01 |  | 28 00 00-9.1 Deferred Space Security Shop Drawings - ME_POP.pdf
28 00 00-010-00 | 28 00 00 - SECURITY SYSTEMS - GENERAL | 28 00 00-010-00 Security Rack Elevations | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-19 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-04-05 07:00 | 2021-04-27 | 40 |  | Record Copies; Transfers; Submittals |  | 35 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12114 | Received | For Review | 2021-03-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-05 07:00 | Submittal Number: 28 00 00-10.0 From: ELLA PILGRIM Final Due Date: 04/05/21 Subject: SECURITY RACK ELEVATIONS Description: Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 15680 | Forwarded | For Review | 2021-03-19 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-03-26 | Submittal Number: 28 00 00-10.0 From: ELLA PILGRIM Final Due Date: 04/05/21 Subject: SECURITY RACK ELEVATIONS Description: Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 12818 | Review Response | Approved as Noted | 2021-04-22 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 16592 | Responded and Closed | Approved as Noted | 2021-04-27 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-19 |  | 28 00 00-10.0 - Security Rack Elevations.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-19 |  | 28 00 00-10.0 - Security Rack Elevations.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-03-18 02:00 |  | 28 00 00-10.0 - Security Rack Elevations.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-27 02:00 |  | 28 00 00-10.0 - Security Rack Elevations - MEE Response_POP.pdf
28 00 00-011-00 | 28 00 00 | 28 00 00-011-00 19155-S0046 O&M Security | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-01 | Responded and Closed - Approved as Noted |  | Michael Mazzocchi (ME Engineers) |  |  |  | 2021-09-21 | 2021-10-01 | 31 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-10-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14553 | Received | For Review | 2021-09-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-21 | Submittal Number: 28 00 00-11.0 From: BINH DUONG Final Due Date: 09/09/21 Subject: 19155-S0046 O&M SECURITY Description: SUBMITTAL OVERVIEW: OPERATION & MAINTENANCE MANUALS PER COCHRAN'S PROVISION. Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 19022 | Forwarded | For Review | 2021-09-29 | Populous SCA_CCA | Michael Mazzocchi (ME Engineers) |  | Submittal Number: 28 00 00-11.0 From: BINH DUONG Final Due Date: 09/09/21 Subject: 19155-S0046 O&M SECURITY Description: SUBMITTAL OVERVIEW: OPERATION & MAINTENANCE MANUALS PER COCHRAN'S PROVISION. Spec Section: 28 00 00 - SECURITY SYSTEMS - GENERAL Status: OPEN | Info Exchange
| 14769 | Review Response | Approved as Noted | 2021-10-01 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 19041 | Responded and Closed | Approved as Noted | 2021-10-01 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Michael Mazzocchi (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-01 02:00 |  | 28 00 00-011-0 O&M Security.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-09-01 |  | 28 00 00-011-0 O&M Security.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-09-01 |  | 28 00 00-011-0 O&M Security.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-10-01 |  | 28 00 00-011-0 O&M Security - MEE_POP.pdf
28 31 00-001-00 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-001-00 ADDRESSABLE FIRE ALARM SYSTEM - Product Data and Qualifications | Closed | Architectural, Fire Protection, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-01 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Mark Lievens (ME Engineers), Jackie Lybarger (ME Engineers) |  |  |  | 2020-04-16 07:00 | 2020-04-21 | 21 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2020-04-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05155 | Received | For Review | 2020-04-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-04-16 07:00 | Submittal Number: 28 31 00-1.0 From: PATRICK KLEIN Final Due Date: 04/10/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - PRODUCT DATA AND QUALIFICATIONS Description: PROCEDURE - PREPARE AND MAKE SUBMITTALS LISTED IN ACCORDANCE WITH DIVISION 1, SUBMITTALS AS REQUIRED BY LOCAL DEPARTMENT OF FIRE. PRODUCT DATA - SUBMIT MANUFACTURERS SPECIFICATIONS, RECOMMENDATIONS, AND INSTALLATION INSTRUCTION FOR USE INTENDED. THE DATA SHALL INCLUDE BUT IS NOT LIMITED TO THE FOLLOWING: 1. CONTROL PANELS 2. CABINETS 3. MANUAL STATIONS 4. BATTERIES 5. BATTERY CHARGER 6. SMOKE SENSORS 7. INSTALLERS TRAINING HISTORY 8. VISUAL ALARMS 9. AUDIO/VISUAL ALARMS 10. ADDRESSABLE INTERFACE DEVICES 11. CENTRAL PROCESSING UNIT 12. WIRING CONDUCTORS 13. WIRE CONNECTORS 14. THERMAL SENSORS 15. ELECTROMAGNETIC DOOR HOLD-OPEN DEVICES 16. REMOTE ALPHA NUMERIC LCD ANNUNCIATORS WITH CONTROL CAPABILITIES. 17. TWO-WAY VOICE COMMUNICATION SYSTEM 18. MANUFACTURERS RECOMMENDED CALIBRATED TEST METHOD FOR SMOKE SENSORS AND SMOKE DETECTORS. 19. INCLUDE UNDERWRITERS LABORATORIES OR FACTORY MUTUAL LISTING CARDS FOR EQUIPMENT PROVIDED. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 06989 | Forwarded | For Review | 2020-03-31 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-04-07 | Submittal Number: 28 31 00-1.0 From: PATRICK KLEIN Final Due Date: 04/10/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - PRODUCT DATA AND QUALIFICATIONS Description: PROCEDURE - PREPARE AND MAKE SUBMITTALS LISTED IN ACCORDANCE WITH DIVISION 1, SUBMITTALS AS REQUIRED BY LOCAL DEPARTMENT OF FIRE. PRODUCT DATA - SUBMIT MANUFACTURERS SPECIFICATIONS, RECOMMENDATIONS, AND INSTALLATION INSTRUCTION FOR USE INTENDED. THE DATA SHALL INCLUDE BUT IS NOT LIMITED TO THE FOLLOWING: 1. CONTROL PANELS 2. CABINETS 3. MANUAL STATIONS 4. BATTERIES 5. BATTERY CHARGER 6. SMOKE SENSORS 7. INSTALLERS TRAINING HISTORY 8. VISUAL ALARMS 9. AUDIO/VISUAL ALARMS 10. ADDRESSABLE INTERFACE DEVICES 11. CENTRAL PROCESSING UNIT 12. WIRING CONDUCTORS 13. WIRE CONNECTORS 14. THERMAL SENSORS 15. ELECTROMAGNETIC DOOR HOLD-OPEN DEVICES 16. REMOTE ALPHA NUMERIC LCD ANNUNCIATORS WITH CONTROL CAPABILITIES. 17. TWO-WAY VOICE COMMUNICATION SYSTEM 18. MANUFACTURERS RECOMMENDED CALIBRATED TEST METHOD FOR SMOKE SENSORS AND SMOKE DETECTORS. 19. INCLUDE UNDERWRITERS LABORATORIES OR FACTORY MUTUAL LISTING CARDS FOR EQUIPMENT PROVIDED. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 07179 | Forwarded | For Review | 2020-04-09 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-04-16 | Submittal Number: 28 31 00-1.0 From: PATRICK KLEIN Final Due Date: 04/10/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - PRODUCT DATA AND QUALIFICATIONS Description: PROCEDURE - PREPARE AND MAKE SUBMITTALS LISTED IN ACCORDANCE WITH DIVISION 1, SUBMITTALS AS REQUIRED BY LOCAL DEPARTMENT OF FIRE. PRODUCT DATA - SUBMIT MANUFACTURERS SPECIFICATIONS, RECOMMENDATIONS, AND INSTALLATION INSTRUCTION FOR USE INTENDED. THE DATA SHALL INCLUDE BUT IS NOT LIMITED TO THE FOLLOWING: 1. CONTROL PANELS 2. CABINETS 3. MANUAL STATIONS 4. BATTERIES 5. BATTERY CHARGER 6. SMOKE SENSORS 7. INSTALLERS TRAINING HISTORY 8. VISUAL ALARMS 9. AUDIO/VISUAL ALARMS 10. ADDRESSABLE INTERFACE DEVICES 11. CENTRAL PROCESSING UNIT 12. WIRING CONDUCTORS 13. WIRE CONNECTORS 14. THERMAL SENSORS 15. ELECTROMAGNETIC DOOR HOLD-OPEN DEVICES 16. REMOTE ALPHA NUMERIC LCD ANNUNCIATORS WITH CONTROL CAPABILITIES. 17. TWO-WAY VOICE COMMUNICATION SYSTEM 18. MANUFACTURERS RECOMMENDED CALIBRATED TEST METHOD FOR SMOKE SENSORS AND SMOKE DETECTORS. 19. INCLUDE UNDERWRITERS LABORATORIES OR FACTORY MUTUAL LISTING CARDS FOR EQUIPMENT PROVIDED. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 05473 | Review Response | Approved as Noted/Resubmit | 2020-04-15 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous) |  | See the attached submittal review. Populous - Please note that I've requested you input on if white or red fire alarm notification devices should be provided. Let me know if you have any questions. Thank you, Mark Lievens ME Engineers 2020.04.15 | Info Exchange
| 07431 | Responded and Closed | Approved as Noted/Resubmit | 2020-04-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: See the attached submittal review. Let me know if you have any questions. Thank you, Mark Lievens ME Engineers 2020.04.15 Populous to confirm color of devices in shop drawing review. See attached submittal. Resubmit items as indicated by ME. jhd/POP | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-31 |  | 28 31 00-1.0 Product Data and Qualifications-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-31 |  | 28 31 00-1.0 Product Data and Qualifications-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-03-30 02:00 |  | 28 31 00-1.0 Product Data and Qualifications-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-03-30 02:00 |  | 28 31 00-1.0 Product Data and Qualifications-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-21 02:00 |  | 28 31 00-1.0 Product Data and Qualifications-MAM-ME_POP.pdf
28 31 00-001-01 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-001-01 ADDRESSABLE FIRE ALARM SYSTEM - OSID Beam Detection Product Data | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-22 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-01-14 | 2021-01-12 | 22 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-01-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10310 | Received | For Review | 2020-12-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Stieritz | 2021-01-14 | Submittal Number: 28 31 00-1.1 From: CODY STIERITZ Final Due Date: 10/30/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - OSID BEAM DETECTION PRODUCT DATA Description: PROVIDE OSID BEAM DETECTION PRODUCT DATA FOR REVIEW AND APPROVAL Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 13469 | Forwarded | For Review | 2020-12-22 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-12-29 | Submittal Number: 28 31 00-1.1 From: CODY STIERITZ Final Due Date: 10/30/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - OSID BEAM DETECTION PRODUCT DATA Description: PROVIDE OSID BEAM DETECTION PRODUCT DATA FOR REVIEW AND APPROVAL Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 13618 | Forwarded | For Review | 2021-01-04 | Josh Dobken (Populous) | Michael Mazzocchi (ME Engineers) | 2021-01-11 | Submittal Number: 28 31 00-1.1 From: CODY STIERITZ Final Due Date: 10/30/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - OSID BEAM DETECTION PRODUCT DATA Description: PROVIDE OSID BEAM DETECTION PRODUCT DATA FOR REVIEW AND APPROVAL Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 10624 | Review Response | Approved | 2021-01-11 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.01.11 | Info Exchange
| 13837 | Responded and Closed | Approved as Noted | 2021-01-12 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.01.11 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-22 |  | 28 31 00-1.1 Fire Alarm - OSID Beam Detection PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-22 |  | 28 31 00-1.1 Fire Alarm - OSID Beam Detection PD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-12-21 02:00 |  | 28 31 00-1.1 Fire Alarm - OSID Beam Detection PD-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-12-22 |  | 28 31 00-1.1 Fire Alarm - OSID Beam Detection PD-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-01-12 |  | 28 31 00-1.1 Fire Alarm - OSID Beam Detection PD-ME_POP.pdf
28 31 00-002-00 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-002-00 ADDRESSABLE FIRE ALARM SYSTEM - Shop Drawings, Wiring Diagrams, and Calculations | Closed | Technology, Electrical, Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-09 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Mark Lievens (ME Engineers), Jackie Lybarger (ME Engineers) |  |  |  | 2020-07-23 | 2020-08-18 | 41 |  | Record Copies; Transfers; Submittals |  | 40 |  | 2020-08-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06888 | Received | For Review | 2020-07-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-23 | Submittal Number: 28 31 00-2.0 From: PATRICK KLEIN Final Due Date: 07/23/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - SHOP DRAWINGS, WIRING DIAGRAMS, AND CALCULATIONS Description: DRAWINGS 1. DETAILED DRAWINGS FOR THE FIRE ALARM SYSTEM SHALL CONSIST OF ILLUSTRATIONS, SCHEDULES, PERFORMANCE CHARTS, BATTERY CALCULATIONS, POINT LISTS, INSTRUCTIONS, DIAGRAMS, AND COMPLETE DETAILED DRAWINGS OF THE FIRE ALARM SYSTEM. 2. A DESCRIPTIVE INDEX OF DRAWINGS IN THE SUBMITTAL WITH DRAWINGS LISTED IN SEQUENCE BY DRAWING NUMBER. 3. A LEGEND SHEET IDENTIFYING DEVICE SYMBOLS, NOMENCLATURE, AND CONVENTIONS USED IN THE PACKAGE. 4. FLOOR PLANS DRAWN TO A SCALE NOT LESS THAN 1/8 INCH EQUALS 1 FOOT WHICH CLEARLY SHOW LOCATIONS OF DEVICES, EQUIPMENT, RISERS, PANELS, ELECTRICAL POWER CONNECTIONS, APPROXIMATE LOCATION OF CONDUIT RUNS, AND OTHER DETAILS REQUIRED TO CLEARLY DESCRIBE THE PROPOSED SYSTEM. 5. A SCALE PLAN VIEW OF THE FIRE COMMAND CENTER AND SECURITY OFFICE WITH DIMENSIONED LAYOUT OF ALL EQUIPMENT THEREIN. 6. LOCATION OF CONTROL PANELS, DETECTORS, SUPERVISORY SWITCHES, MANUAL PULL STATIONS, VISUAL/AUDIBLE ALARMS AND ELECTRICAL DEVICES. CLEARLY AND COMPLETELY INDICATE THE FUNCTION OF THE CONTROL PANEL AND DEVICES. INDICATE CONDUIT ROUTING AND SIZES, AND THE NUMBER OF CONDUCTORS CONTAINED IN EACH. INDICATE POINTS OF CONNECTION AND TERMINALS USED FOR ELECTRICAL FIELD CONNECTIONS IN THE SYSTEM, WITH A WIRING COLOR CODE. INDICATE TERMINATION POINTS OF DEVICES AND INDICATE THE INTERCONNECTION OF MODULES REQUIRED FOR PROPER OPERATION OF THE SYSTEM. INDICATE INTERCONNECTION BETWEEN MODULES AND DEVICES. CONTROL DIAGRAMS SHALL BE SUPPLEMENTED WITH A NARRATIVE DESCRIPTION OF THE SYSTEM. POINT-TO-POINT WIRING DIAGRAMS SHALL INDICATE CONTROL PANEL WIRING AND MAKE AND MODEL OF DEVICES AND EQUIPMENT. SIGNAL CIRCUIT DIAGRAMS SHALL SHOW CURRENT DRAW AND LOAD BY DEVICE AND BY CIRCUIT. DESIGN DATA 1. BATTERY STANDBY POWER REQUIREMENTS CALCULATIONS. 2. SUBMIT DESIGN CALCULATIONS FOR THE SYSTEM SUBSTANTIATING BATTERY STANDBY POWER REQUIREMENTS, CALCULATIONS SHOWING BATTERY CAPACITY AND SUPERVISORY AND ALARM POWER REQUIREMENTS. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 09230 | Forwarded | For Review | 2020-07-09 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-07-16 | Submittal Number: 28 31 00-2.0 From: PATRICK KLEIN Final Due Date: 07/23/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - SHOP DRAWINGS, WIRING DIAGRAMS, AND CALCULATIONS Description: DRAWINGS 1. DETAILED DRAWINGS FOR THE FIRE ALARM SYSTEM SHALL CONSIST OF ILLUSTRATIONS, SCHEDULES, PERFORMANCE CHARTS, BATTERY CALCULATIONS, POINT LISTS, INSTRUCTIONS, DIAGRAMS, AND COMPLETE DETAILED DRAWINGS OF THE FIRE ALARM SYSTEM. 2. A DESCRIPTIVE INDEX OF DRAWINGS IN THE SUBMITTAL WITH DRAWINGS LISTED IN SEQUENCE BY DRAWING NUMBER. 3. A LEGEND SHEET IDENTIFYING DEVICE SYMBOLS, NOMENCLATURE, AND CONVENTIONS USED IN THE PACKAGE. 4. FLOOR PLANS DRAWN TO A SCALE NOT LESS THAN 1/8 INCH EQUALS 1 FOOT WHICH CLEARLY SHOW LOCATIONS OF DEVICES, EQUIPMENT, RISERS, PANELS, ELECTRICAL POWER CONNECTIONS, APPROXIMATE LOCATION OF CONDUIT RUNS, AND OTHER DETAILS REQUIRED TO CLEARLY DESCRIBE THE PROPOSED SYSTEM. 5. A SCALE PLAN VIEW OF THE FIRE COMMAND CENTER AND SECURITY OFFICE WITH DIMENSIONED LAYOUT OF ALL EQUIPMENT THEREIN. 6. LOCATION OF CONTROL PANELS, DETECTORS, SUPERVISORY SWITCHES, MANUAL PULL STATIONS, VISUAL/AUDIBLE ALARMS AND ELECTRICAL DEVICES. CLEARLY AND COMPLETELY INDICATE THE FUNCTION OF THE CONTROL PANEL AND DEVICES. INDICATE CONDUIT ROUTING AND SIZES, AND THE NUMBER OF CONDUCTORS CONTAINED IN EACH. INDICATE POINTS OF CONNECTION AND TERMINALS USED FOR ELECTRICAL FIELD CONNECTIONS IN THE SYSTEM, WITH A WIRING COLOR CODE. INDICATE TERMINATION POINTS OF DEVICES AND INDICATE THE INTERCONNECTION OF MODULES REQUIRED FOR PROPER OPERATION OF THE SYSTEM. INDICATE INTERCONNECTION BETWEEN MODULES AND DEVICES. CONTROL DIAGRAMS SHALL BE SUPPLEMENTED WITH A NARRATIVE DESCRIPTION OF THE SYSTEM. POINT-TO-POINT WIRING DIAGRAMS SHALL INDICATE CONTROL PANEL WIRING AND MAKE AND MODEL OF DEVICES AND EQUIPMENT. SIGNAL CIRCUIT DIAGRAMS SHALL SHOW CURRENT DRAW AND LOAD BY DEVICE AND BY CIRCUIT. DESIGN DATA 1. BATTERY STANDBY POWER REQUIREMENTS CALCULATIONS. 2. SUBMIT DESIGN CALCULATIONS FOR THE SYSTEM SUBSTANTIATING BATTERY STANDBY POWER REQUIREMENTS, CALCULATIONS SHOWING BATTERY CAPACITY AND SUPERVISORY AND ALARM POWER REQUIREMENTS. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 09318 | Forwarded | For Review | 2020-07-14 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-21 | Submittal Number: 28 31 00-2.0 From: PATRICK KLEIN Final Due Date: 07/23/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - SHOP DRAWINGS, WIRING DIAGRAMS, AND CALCULATIONS Description: DRAWINGS 1. DETAILED DRAWINGS FOR THE FIRE ALARM SYSTEM SHALL CONSIST OF ILLUSTRATIONS, SCHEDULES, PERFORMANCE CHARTS, BATTERY CALCULATIONS, POINT LISTS, INSTRUCTIONS, DIAGRAMS, AND COMPLETE DETAILED DRAWINGS OF THE FIRE ALARM SYSTEM. 2. A DESCRIPTIVE INDEX OF DRAWINGS IN THE SUBMITTAL WITH DRAWINGS LISTED IN SEQUENCE BY DRAWING NUMBER. 3. A LEGEND SHEET IDENTIFYING DEVICE SYMBOLS, NOMENCLATURE, AND CONVENTIONS USED IN THE PACKAGE. 4. FLOOR PLANS DRAWN TO A SCALE NOT LESS THAN 1/8 INCH EQUALS 1 FOOT WHICH CLEARLY SHOW LOCATIONS OF DEVICES, EQUIPMENT, RISERS, PANELS, ELECTRICAL POWER CONNECTIONS, APPROXIMATE LOCATION OF CONDUIT RUNS, AND OTHER DETAILS REQUIRED TO CLEARLY DESCRIBE THE PROPOSED SYSTEM. 5. A SCALE PLAN VIEW OF THE FIRE COMMAND CENTER AND SECURITY OFFICE WITH DIMENSIONED LAYOUT OF ALL EQUIPMENT THEREIN. 6. LOCATION OF CONTROL PANELS, DETECTORS, SUPERVISORY SWITCHES, MANUAL PULL STATIONS, VISUAL/AUDIBLE ALARMS AND ELECTRICAL DEVICES. CLEARLY AND COMPLETELY INDICATE THE FUNCTION OF THE CONTROL PANEL AND DEVICES. INDICATE CONDUIT ROUTING AND SIZES, AND THE NUMBER OF CONDUCTORS CONTAINED IN EACH. INDICATE POINTS OF CONNECTION AND TERMINALS USED FOR ELECTRICAL FIELD CONNECTIONS IN THE SYSTEM, WITH A WIRING COLOR CODE. INDICATE TERMINATION POINTS OF DEVICES AND INDICATE THE INTERCONNECTION OF MODULES REQUIRED FOR PROPER OPERATION OF THE SYSTEM. INDICATE INTERCONNECTION BETWEEN MODULES AND DEVICES. CONTROL DIAGRAMS SHALL BE SUPPLEMENTED WITH A NARRATIVE DESCRIPTION OF THE SYSTEM. POINT-TO-POINT WIRING DIAGRAMS SHALL INDICATE CONTROL PANEL WIRING AND MAKE AND MODEL OF DEVICES AND EQUIPMENT. SIGNAL CIRCUIT DIAGRAMS SHALL SHOW CURRENT DRAW AND LOAD BY DEVICE AND BY CIRCUIT. DESIGN DATA 1. BATTERY STANDBY POWER REQUIREMENTS CALCULATIONS. 2. SUBMIT DESIGN CALCULATIONS FOR THE SYSTEM SUBSTANTIATING BATTERY STANDBY POWER REQUIREMENTS, CALCULATIONS SHOWING BATTERY CAPACITY AND SUPERVISORY AND ALARM POWER REQUIREMENTS. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 07601 | Review Response | Approved as Noted/Resubmit | 2020-08-17 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) |  | Please see the attached submittal review. I've incorporated the comments regarding device locations from our discussion last Tuesday. Thank you, Mark Lievens ME Engineers 2020.08.17 | Info Exchange
| 10120 | Responded and Closed | Approved as Noted/Resubmit | 2020-08-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. I've incorporated the comments regarding device locations from our discussion last Tuesday. Thank you, Mark Lievens ME Engineers 2020.08.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-09 |  | 28 31 00-2.0 Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-09 |  | 28 31 00-2.0 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-07-08 02:00 |  | 28 31 00-2.0 Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-07-08 02:00 |  | 28 31 00-2.0 Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-18 02:00 |  | 28 31 00-2.0 Shop Drawings-MAM-ME_pop.pdf
28 31 00-002-01 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-002-01 ADDRESSABLE FIRE ALARM SYSTEM - Bowl Beam Detection Coverage | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-28 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Mark Lievens (ME Engineers), Jackie Lybarger (ME Engineers) |  |  |  | 2020-09-14 07:00 | 2020-09-14 | 18 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07807 | Received | For Review | 2020-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-09-14 07:00 | Submittal Number: 28 31 00-2.1 From: PATRICK KLEIN Final Due Date: 09/11/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - BOWL BEAM DETECTION COVERAGE Description: DRAWINGS 1. DETAILED DRAWINGS FOR THE FIRE ALARM SYSTEM SHALL CONSIST OF ILLUSTRATIONS, SCHEDULES, PERFORMANCE CHARTS, BATTERY CALCULATIONS, POINT LISTS, INSTRUCTIONS, DIAGRAMS, AND COMPLETE DETAILED DRAWINGS OF THE FIRE ALARM SYSTEM. 2. A DESCRIPTIVE INDEX OF DRAWINGS IN THE SUBMITTAL WITH DRAWINGS LISTED IN SEQUENCE BY DRAWING NUMBER. 3. A LEGEND SHEET IDENTIFYING DEVICE SYMBOLS, NOMENCLATURE, AND CONVENTIONS USED IN THE PACKAGE. 4. FLOOR PLANS DRAWN TO A SCALE NOT LESS THAN 1/8 INCH EQUALS 1 FOOT WHICH CLEARLY SHOW LOCATIONS OF DEVICES, EQUIPMENT, RISERS, PANELS, ELECTRICAL POWER CONNECTIONS, APPROXIMATE LOCATION OF CONDUIT RUNS, AND OTHER DETAILS REQUIRED TO CLEARLY DESCRIBE THE PROPOSED SYSTEM. 5. A SCALE PLAN VIEW OF THE FIRE COMMAND CENTER AND SECURITY OFFICE WITH DIMENSIONED LAYOUT OF ALL EQUIPMENT THEREIN. 6. LOCATION OF CONTROL PANELS, DETECTORS, SUPERVISORY SWITCHES, MANUAL PULL STATIONS, VISUAL/AUDIBLE ALARMS AND ELECTRICAL DEVICES. CLEARLY AND COMPLETELY INDICATE THE FUNCTION OF THE CONTROL PANEL AND DEVICES. INDICATE CONDUIT ROUTING AND SIZES, AND THE NUMBER OF CONDUCTORS CONTAINED IN EACH. INDICATE POINTS OF CONNECTION AND TERMINALS USED FOR ELECTRICAL FIELD CONNECTIONS IN THE SYSTEM, WITH A WIRING COLOR CODE. INDICATE TERMINATION POINTS OF DEVICES AND INDICATE THE INTERCONNECTION OF MODULES REQUIRED FOR PROPER OPERATION OF THE SYSTEM. INDICATE INTERCONNECTION BETWEEN MODULES AND DEVICES. CONTROL DIAGRAMS SHALL BE SUPPLEMENTED WITH A NARRATIVE DESCRIPTION OF THE SYSTEM. POINT-TO-POINT WIRING DIAGRAMS SHALL INDICATE CONTROL PANEL WIRING AND MAKE AND MODEL OF DEVICES AND EQUIPMENT. SIGNAL CIRCUIT DIAGRAMS SHALL SHOW CURRENT DRAW AND LOAD BY DEVICE AND BY CIRCUIT. DESIGN DATA 1. BATTERY STANDBY POWER REQUIREMENTS CALCULATIONS. 2. SUBMIT DESIGN CALCULATIONS FOR THE SYSTEM SUBSTANTIATING BATTERY STANDBY POWER REQUIREMENTS, CALCULATIONS SHOWING BATTERY CAPACITY AND SUPERVISORY AND ALARM POWER REQUIREMENTS. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 10385 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-09-03 | Submittal Number: 28 31 00-2.1 From: PATRICK KLEIN Final Due Date: 09/11/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - BOWL BEAM DETECTION COVERAGE Description: DRAWINGS 1. DETAILED DRAWINGS FOR THE FIRE ALARM SYSTEM SHALL CONSIST OF ILLUSTRATIONS, SCHEDULES, PERFORMANCE CHARTS, BATTERY CALCULATIONS, POINT LISTS, INSTRUCTIONS, DIAGRAMS, AND COMPLETE DETAILED DRAWINGS OF THE FIRE ALARM SYSTEM. 2. A DESCRIPTIVE INDEX OF DRAWINGS IN THE SUBMITTAL WITH DRAWINGS LISTED IN SEQUENCE BY DRAWING NUMBER. 3. A LEGEND SHEET IDENTIFYING DEVICE SYMBOLS, NOMENCLATURE, AND CONVENTIONS USED IN THE PACKAGE. 4. FLOOR PLANS DRAWN TO A SCALE NOT LESS THAN 1/8 INCH EQUALS 1 FOOT WHICH CLEARLY SHOW LOCATIONS OF DEVICES, EQUIPMENT, RISERS, PANELS, ELECTRICAL POWER CONNECTIONS, APPROXIMATE LOCATION OF CONDUIT RUNS, AND OTHER DETAILS REQUIRED TO CLEARLY DESCRIBE THE PROPOSED SYSTEM. 5. A SCALE PLAN VIEW OF THE FIRE COMMAND CENTER AND SECURITY OFFICE WITH DIMENSIONED LAYOUT OF ALL EQUIPMENT THEREIN. 6. LOCATION OF CONTROL PANELS, DETECTORS, SUPERVISORY SWITCHES, MANUAL PULL STATIONS, VISUAL/AUDIBLE ALARMS AND ELECTRICAL DEVICES. CLEARLY AND COMPLETELY INDICATE THE FUNCTION OF THE CONTROL PANEL AND DEVICES. INDICATE CONDUIT ROUTING AND SIZES, AND THE NUMBER OF CONDUCTORS CONTAINED IN EACH. INDICATE POINTS OF CONNECTION AND TERMINALS USED FOR ELECTRICAL FIELD CONNECTIONS IN THE SYSTEM, WITH A WIRING COLOR CODE. INDICATE TERMINATION POINTS OF DEVICES AND INDICATE THE INTERCONNECTION OF MODULES REQUIRED FOR PROPER OPERATION OF THE SYSTEM. INDICATE INTERCONNECTION BETWEEN MODULES AND DEVICES. CONTROL DIAGRAMS SHALL BE SUPPLEMENTED WITH A NARRATIVE DESCRIPTION OF THE SYSTEM. POINT-TO-POINT WIRING DIAGRAMS SHALL INDICATE CONTROL PANEL WIRING AND MAKE AND MODEL OF DEVICES AND EQUIPMENT. SIGNAL CIRCUIT DIAGRAMS SHALL SHOW CURRENT DRAW AND LOAD BY DEVICE AND BY CIRCUIT. DESIGN DATA 1. BATTERY STANDBY POWER REQUIREMENTS CALCULATIONS. 2. SUBMIT DESIGN CALCULATIONS FOR THE SYSTEM SUBSTANTIATING BATTERY STANDBY POWER REQUIREMENTS, CALCULATIONS SHOWING BATTERY CAPACITY AND SUPERVISORY AND ALARM POWER REQUIREMENTS. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 10572 | Forwarded | For Review | 2020-09-08 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-09-14 | Submittal Number: 28 31 00-2.1 From: PATRICK KLEIN Final Due Date: 09/11/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - BOWL BEAM DETECTION COVERAGE Description: DRAWINGS 1. DETAILED DRAWINGS FOR THE FIRE ALARM SYSTEM SHALL CONSIST OF ILLUSTRATIONS, SCHEDULES, PERFORMANCE CHARTS, BATTERY CALCULATIONS, POINT LISTS, INSTRUCTIONS, DIAGRAMS, AND COMPLETE DETAILED DRAWINGS OF THE FIRE ALARM SYSTEM. 2. A DESCRIPTIVE INDEX OF DRAWINGS IN THE SUBMITTAL WITH DRAWINGS LISTED IN SEQUENCE BY DRAWING NUMBER. 3. A LEGEND SHEET IDENTIFYING DEVICE SYMBOLS, NOMENCLATURE, AND CONVENTIONS USED IN THE PACKAGE. 4. FLOOR PLANS DRAWN TO A SCALE NOT LESS THAN 1/8 INCH EQUALS 1 FOOT WHICH CLEARLY SHOW LOCATIONS OF DEVICES, EQUIPMENT, RISERS, PANELS, ELECTRICAL POWER CONNECTIONS, APPROXIMATE LOCATION OF CONDUIT RUNS, AND OTHER DETAILS REQUIRED TO CLEARLY DESCRIBE THE PROPOSED SYSTEM. 5. A SCALE PLAN VIEW OF THE FIRE COMMAND CENTER AND SECURITY OFFICE WITH DIMENSIONED LAYOUT OF ALL EQUIPMENT THEREIN. 6. LOCATION OF CONTROL PANELS, DETECTORS, SUPERVISORY SWITCHES, MANUAL PULL STATIONS, VISUAL/AUDIBLE ALARMS AND ELECTRICAL DEVICES. CLEARLY AND COMPLETELY INDICATE THE FUNCTION OF THE CONTROL PANEL AND DEVICES. INDICATE CONDUIT ROUTING AND SIZES, AND THE NUMBER OF CONDUCTORS CONTAINED IN EACH. INDICATE POINTS OF CONNECTION AND TERMINALS USED FOR ELECTRICAL FIELD CONNECTIONS IN THE SYSTEM, WITH A WIRING COLOR CODE. INDICATE TERMINATION POINTS OF DEVICES AND INDICATE THE INTERCONNECTION OF MODULES REQUIRED FOR PROPER OPERATION OF THE SYSTEM. INDICATE INTERCONNECTION BETWEEN MODULES AND DEVICES. CONTROL DIAGRAMS SHALL BE SUPPLEMENTED WITH A NARRATIVE DESCRIPTION OF THE SYSTEM. POINT-TO-POINT WIRING DIAGRAMS SHALL INDICATE CONTROL PANEL WIRING AND MAKE AND MODEL OF DEVICES AND EQUIPMENT. SIGNAL CIRCUIT DIAGRAMS SHALL SHOW CURRENT DRAW AND LOAD BY DEVICE AND BY CIRCUIT. DESIGN DATA 1. BATTERY STANDBY POWER REQUIREMENTS CALCULATIONS. 2. SUBMIT DESIGN CALCULATIONS FOR THE SYSTEM SUBSTANTIATING BATTERY STANDBY POWER REQUIREMENTS, CALCULATIONS SHOWING BATTERY CAPACITY AND SUPERVISORY AND ALARM POWER REQUIREMENTS. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 08101 | Review Response | Revise and Resubmit | 2020-09-10 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.09.10 | Info Exchange
| 10767 | Responded and Closed | Revise and Resubmit | 2020-09-14 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Revise and Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.09.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 28 31 00-2.1 Bowl Beam Detection Coverage-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-27 |  | 28 31 00-2.1 Bowl Beam Detection Coverage-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-08-26 02:00 |  | 28 31 00-2.1 Bowl Beam Detection Coverage-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-08-26 |  | 28 31 00-2.1 Bowl Beam Detection Coverage-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-14 |  | 28 31 00-2.1 Bowl Beam Detection Coverage-MAM-ME_POP.pdf
28 31 00-002-02 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-002-02 ADDRESSABLE FIRE ALARM SYSTEM - Bowl Beam Detection Coverage | Closed | Fire Alarm | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-02 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Bryan Klote (Populous), Tom Usher (Populous), Ben Muscente (Howe Engineers, Inc.), Stephen Napolitano (Howe Engineers, Inc.) |  |  |  | 2021-03-16 | 2021-04-12 | 42 |  | Record Copies; Transfers; Submittals | 28 31 00-002-02-01 - 28 31 00-002-02 ADDRESSABLE FIRE ALARM SYSTEM - Bowl Beam Detection Coverage | 42 |  | 2021-04-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11740 | Received | For Review | 2021-03-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Stieritz | 2021-03-16 | Submittal Number: 28 31 00-2.2 From: CODY STIERITZ Final Due Date: 03/17/21 Subject: ADDRESSABLE FIRE ALARM SYSTEM - BOWL BEAM DETECTION COVERAGE Description: DRAWINGS 1. DETAILED DRAWINGS FOR THE FIRE ALARM SYSTEM SHALL CONSIST OF ILLUSTRATIONS, SCHEDULES, PERFORMANCE CHARTS, BATTERY CALCULATIONS, POINT LISTS, INSTRUCTIONS, DIAGRAMS, AND COMPLETE DETAILED DRAWINGS OF THE FIRE ALARM SYSTEM. 2. A DESCRIPTIVE INDEX OF DRAWINGS IN THE SUBMITTAL WITH DRAWINGS LISTED IN SEQUENCE BY DRAWING NUMBER. 3. A LEGEND SHEET IDENTIFYING DEVICE SYMBOLS, NOMENCLATURE, AND CONVENTIONS USED IN THE PACKAGE. 4. FLOOR PLANS DRAWN TO A SCALE NOT LESS THAN 1/8 INCH EQUALS 1 FOOT WHICH CLEARLY SHOW LOCATIONS OF DEVICES, EQUIPMENT, RISERS, PANELS, ELECTRICAL POWER CONNECTIONS, APPROXIMATE LOCATION OF CONDUIT RUNS, AND OTHER DETAILS REQUIRED TO CLEARLY DESCRIBE THE PROPOSED SYSTEM. 5. A SCALE PLAN VIEW OF THE FIRE COMMAND CENTER AND SECURITY OFFICE WITH DIMENSIONED LAYOUT OF ALL EQUIPMENT THEREIN. 6. LOCATION OF CONTROL PANELS, DETECTORS, SUPERVISORY SWITCHES, MANUAL PULL STATIONS, VISUAL/AUDIBLE ALARMS AND ELECTRICAL DEVICES. CLEARLY AND COMPLETELY INDICATE THE FUNCTION OF THE CONTROL PANEL AND DEVICES. INDICATE CONDUIT ROUTING AND SIZES, AND THE NUMBER OF CONDUCTORS CONTAINED IN EACH. INDICATE POINTS OF CONNECTION AND TERMINALS USED FOR ELECTRICAL FIELD CONNECTIONS IN THE SYSTEM, WITH A WIRING COLOR CODE. INDICATE TERMINATION POINTS OF DEVICES AND INDICATE THE INTERCONNECTION OF MODULES REQUIRED FOR PROPER OPERATION OF THE SYSTEM. INDICATE INTERCONNECTION BETWEEN MODULES AND DEVICES. CONTROL DIAGRAMS SHALL BE SUPPLEMENTED WITH A NARRATIVE DESCRIPTION OF THE SYSTEM. POINT-TO-POINT WIRING DIAGRAMS SHALL INDICATE CONTROL PANEL WIRING AND MAKE AND MODEL OF DEVICES AND EQUIPMENT. SIGNAL CIRCUIT DIAGRAMS SHALL SHOW CURRENT DRAW AND LOAD BY DEVICE AND BY CIRCUIT. DESIGN DATA 1. BATTERY STANDBY POWER REQUIREMENTS CALCULATIONS. 2. SUBMIT DESIGN CALCULATIONS FOR THE SYSTEM SUBSTANTIATING BATTERY STANDBY POWER REQUIREMENTS, CALCULATIONS SHOWING BATTERY CAPACITY AND SUPERVISORY AND ALARM POWER REQUIREMENTS. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 15212 | Forwarded | For Review | 2021-03-02 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-03-09 | Submittal Number: 28 31 00-2.2 From: CODY STIERITZ Final Due Date: 03/17/21 Subject: ADDRESSABLE FIRE ALARM SYSTEM - BOWL BEAM DETECTION COVERAGE Description: DRAWINGS 1. DETAILED DRAWINGS FOR THE FIRE ALARM SYSTEM SHALL CONSIST OF ILLUSTRATIONS, SCHEDULES, PERFORMANCE CHARTS, BATTERY CALCULATIONS, POINT LISTS, INSTRUCTIONS, DIAGRAMS, AND COMPLETE DETAILED DRAWINGS OF THE FIRE ALARM SYSTEM. 2. A DESCRIPTIVE INDEX OF DRAWINGS IN THE SUBMITTAL WITH DRAWINGS LISTED IN SEQUENCE BY DRAWING NUMBER. 3. A LEGEND SHEET IDENTIFYING DEVICE SYMBOLS, NOMENCLATURE, AND CONVENTIONS USED IN THE PACKAGE. 4. FLOOR PLANS DRAWN TO A SCALE NOT LESS THAN 1/8 INCH EQUALS 1 FOOT WHICH CLEARLY SHOW LOCATIONS OF DEVICES, EQUIPMENT, RISERS, PANELS, ELECTRICAL POWER CONNECTIONS, APPROXIMATE LOCATION OF CONDUIT RUNS, AND OTHER DETAILS REQUIRED TO CLEARLY DESCRIBE THE PROPOSED SYSTEM. 5. A SCALE PLAN VIEW OF THE FIRE COMMAND CENTER AND SECURITY OFFICE WITH DIMENSIONED LAYOUT OF ALL EQUIPMENT THEREIN. 6. LOCATION OF CONTROL PANELS, DETECTORS, SUPERVISORY SWITCHES, MANUAL PULL STATIONS, VISUAL/AUDIBLE ALARMS AND ELECTRICAL DEVICES. CLEARLY AND COMPLETELY INDICATE THE FUNCTION OF THE CONTROL PANEL AND DEVICES. INDICATE CONDUIT ROUTING AND SIZES, AND THE NUMBER OF CONDUCTORS CONTAINED IN EACH. INDICATE POINTS OF CONNECTION AND TERMINALS USED FOR ELECTRICAL FIELD CONNECTIONS IN THE SYSTEM, WITH A WIRING COLOR CODE. INDICATE TERMINATION POINTS OF DEVICES AND INDICATE THE INTERCONNECTION OF MODULES REQUIRED FOR PROPER OPERATION OF THE SYSTEM. INDICATE INTERCONNECTION BETWEEN MODULES AND DEVICES. CONTROL DIAGRAMS SHALL BE SUPPLEMENTED WITH A NARRATIVE DESCRIPTION OF THE SYSTEM. POINT-TO-POINT WIRING DIAGRAMS SHALL INDICATE CONTROL PANEL WIRING AND MAKE AND MODEL OF DEVICES AND EQUIPMENT. SIGNAL CIRCUIT DIAGRAMS SHALL SHOW CURRENT DRAW AND LOAD BY DEVICE AND BY CIRCUIT. DESIGN DATA 1. BATTERY STANDBY POWER REQUIREMENTS CALCULATIONS. 2. SUBMIT DESIGN CALCULATIONS FOR THE SYSTEM SUBSTANTIATING BATTERY STANDBY POWER REQUIREMENTS, CALCULATIONS SHOWING BATTERY CAPACITY AND SUPERVISORY AND ALARM POWER REQUIREMENTS. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 15223 | Forwarded | For Review | 2021-03-02 | Josh Dobken (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Ben Muscente (Howe Engineers, Inc.); Stephen Napolitano (Howe Engineers, Inc.) | 2021-03-09 | Submittal Number: 28 31 00-2.2 From: CODY STIERITZ Final Due Date: 03/17/21 Subject: ADDRESSABLE FIRE ALARM SYSTEM - BOWL BEAM DETECTION COVERAGE Description: DRAWINGS 1. DETAILED DRAWINGS FOR THE FIRE ALARM SYSTEM SHALL CONSIST OF ILLUSTRATIONS, SCHEDULES, PERFORMANCE CHARTS, BATTERY CALCULATIONS, POINT LISTS, INSTRUCTIONS, DIAGRAMS, AND COMPLETE DETAILED DRAWINGS OF THE FIRE ALARM SYSTEM. 2. A DESCRIPTIVE INDEX OF DRAWINGS IN THE SUBMITTAL WITH DRAWINGS LISTED IN SEQUENCE BY DRAWING NUMBER. 3. A LEGEND SHEET IDENTIFYING DEVICE SYMBOLS, NOMENCLATURE, AND CONVENTIONS USED IN THE PACKAGE. 4. FLOOR PLANS DRAWN TO A SCALE NOT LESS THAN 1/8 INCH EQUALS 1 FOOT WHICH CLEARLY SHOW LOCATIONS OF DEVICES, EQUIPMENT, RISERS, PANELS, ELECTRICAL POWER CONNECTIONS, APPROXIMATE LOCATION OF CONDUIT RUNS, AND OTHER DETAILS REQUIRED TO CLEARLY DESCRIBE THE PROPOSED SYSTEM. 5. A SCALE PLAN VIEW OF THE FIRE COMMAND CENTER AND SECURITY OFFICE WITH DIMENSIONED LAYOUT OF ALL EQUIPMENT THEREIN. 6. LOCATION OF CONTROL PANELS, DETECTORS, SUPERVISORY SWITCHES, MANUAL PULL STATIONS, VISUAL/AUDIBLE ALARMS AND ELECTRICAL DEVICES. CLEARLY AND COMPLETELY INDICATE THE FUNCTION OF THE CONTROL PANEL AND DEVICES. INDICATE CONDUIT ROUTING AND SIZES, AND THE NUMBER OF CONDUCTORS CONTAINED IN EACH. INDICATE POINTS OF CONNECTION AND TERMINALS USED FOR ELECTRICAL FIELD CONNECTIONS IN THE SYSTEM, WITH A WIRING COLOR CODE. INDICATE TERMINATION POINTS OF DEVICES AND INDICATE THE INTERCONNECTION OF MODULES REQUIRED FOR PROPER OPERATION OF THE SYSTEM. INDICATE INTERCONNECTION BETWEEN MODULES AND DEVICES. CONTROL DIAGRAMS SHALL BE SUPPLEMENTED WITH A NARRATIVE DESCRIPTION OF THE SYSTEM. POINT-TO-POINT WIRING DIAGRAMS SHALL INDICATE CONTROL PANEL WIRING AND MAKE AND MODEL OF DEVICES AND EQUIPMENT. SIGNAL CIRCUIT DIAGRAMS SHALL SHOW CURRENT DRAW AND LOAD BY DEVICE AND BY CIRCUIT. DESIGN DATA 1. BATTERY STANDBY POWER REQUIREMENTS CALCULATIONS. 2. SUBMIT DESIGN CALCULATIONS FOR THE SYSTEM SUBSTANTIATING BATTERY STANDBY POWER REQUIREMENTS, CALCULATIONS SHOWING BATTERY CAPACITY AND SUPERVISORY AND ALARM POWER REQUIREMENTS. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 12654 | Review Response | Approved as Noted/Resubmit | 2021-04-09 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | See the attached submittal review which includes Howes and ME's comments. Populous - please take a look at the comments highlighted in yellow on the FA2 sheets for items device locations/colors that shall be confirmed. Let me know if there are any questions. Thank you, Mark Lievens ME Engineers 2021.04.09 | Info Exchange
| 12543 | Review Response | Approved as Noted/Resubmit | 2021-04-12 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 16242 | Responded and Closed | Approved as Noted/Resubmit | 2021-04-12 | Kuebler Perry (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-02 |  | 283100-002-2 Addressable Fire Alarm Shop Drawings_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-02 |  | 283100-002-2 Addressable Fire Alarm Shop Drawings_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-01 02:00 |  | 283100-002-2 Addressable Fire Alarm Shop Drawings_MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-03-01 02:00 |  | 283100-002-2 Addressable Fire Alarm Shop Drawings_MAM.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-04-12 |  | 283100-002-2_ME-NT_HOWE_CS-MAM_ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-03-02 |  | 283100-002-2 Addressable Fire Alarm Shop Drawings_MAM.pdf
28 31 00-002-02-01 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-002-02 ADDRESSABLE FIRE ALARM SYSTEM - Bowl Beam Detection Coverage | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 28 31 00-002-02 - 28 31 00-002-02 ADDRESSABLE FIRE ALARM SYSTEM - Bowl Beam Detection Coverage | -1 | 2021-04-26
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-02 |  | 283100-002-2 Addressable Fire Alarm Shop Drawings_MAM.pdf
28 31 00-011-00 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-011-00 ADDRESSABLE FIRE ALARM SYSTEM - NHL and WNBA Locker Room Shop Drawings | Closed | Fire Protection, Electrical, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-21 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Mark Lievens (ME Engineers) |  |  |  | 2020-10-05 | 2020-10-13 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-10-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08227 | Received | For Review | 2020-09-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-10-05 | Submittal Number: 28 31 00-11.0 From: PATRICK KLEIN Final Due Date: 10/05/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - NHL AND WNBA LOCKER ROOM SHOP DRAWINGS Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 10924 | Forwarded | For Review | 2020-09-21 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-09-28 | Submittal Number: 28 31 00-11.0 From: PATRICK KLEIN Final Due Date: 10/05/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - NHL AND WNBA LOCKER ROOM SHOP DRAWINGS Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 11527 | Forwarded | For Review | 2020-10-12 | Populous SCA_CCA | Mark Lievens (ME Engineers) | 2020-10-05 | Submittal Number: 28 31 00-11.0 From: PATRICK KLEIN Final Due Date: 10/05/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - NHL AND WNBA LOCKER ROOM SHOP DRAWINGS Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 08759 | Review Response | Approved as Noted | 2020-10-13 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Populous - Please confirm the fire alarm speaker/strobe relocations that are noted in blue within the submittal prior to return to Mortenson. Thank you, Mark Lievens ME Engineers 2020.10.13 | Info Exchange
| 11575 | Responded and Closed | Approved as Noted | 2020-10-13 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.10.13 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-21 |  | 28 31 00-11.0 NHL and WNBA Locker Room Shop Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-21 |  | 28 31 00-11.0 NHL and WNBA Locker Room Shop Drawings-MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-09-21 |  | 28 31 00-11.0 NHL and WNBA Locker Room Shop Drawings-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-09-21 |  | 28 31 00-11.0 NHL and WNBA Locker Room Shop Drawings-MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-10-13 |  | 28 31 00-11.0 NHL and WNBA Locker Room Shop Drawings-MAM-ME_POP.pdf
28 31 00-012-00 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-012-00 ADDRESSABLE FIRE ALARM SYSTEM - Deferred Spaces Product Data | Closed | Architectural, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-05 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Mark Lievens (ME Engineers), Bryan Klote (Populous), Kuebler Perry (Populous) |  |  |  | 2020-10-19 | 2020-11-11 | 38 |  | Record Copies; Transfers; Submittals | 28 31 00-012-00-01 - 28 31 00-012-00 ADDRESSABLE FIRE ALARM SYSTEM - Deferred Spaces Product Data | 19 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08569 | Received | For Review | 2020-10-05 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-10-19 | Submittal Number: 28 31 00-12.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - DEFERRED SPACES PRODUCT DATA Description: 283100: ADDRESSABLE FIRE ALARM SYSTEM PLEASE REVIEW. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 11330 | Forwarded | For Review | 2020-10-05 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2020-10-12 | Submittal Number: 28 31 00-12.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - DEFERRED SPACES PRODUCT DATA Description: 283100: ADDRESSABLE FIRE ALARM SYSTEM PLEASE REVIEW. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 11364 | Forwarded | For Review | 2020-10-06 | Shaina Burris (Populous) | Mark Lievens (ME Engineers) | 2020-10-13 | Submittal Number: 28 31 00-12.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - DEFERRED SPACES PRODUCT DATA Description: 283100: ADDRESSABLE FIRE ALARM SYSTEM PLEASE REVIEW. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 08620 | Review Response | Approved as Noted/Resubmit | 2020-10-06 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Populous - please provide direction on fire alarm device colors for deferred spaces within submittal or clarify if this will be provided within the shop drawing review process. Thank you, Mark Lievens ME Engineers | Info Exchange
| 11392 | Forwarded | For Review | 2020-10-06 | Josh Dobken (Populous) | Bryan Klote (Populous); Kuebler Perry (Populous) | 2020-10-13 | Submittal Number: 28 31 00-12.0 From: PATRICK KLEIN Final Due Date: 10/19/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - DEFERRED SPACES PRODUCT DATA Description: 283100: ADDRESSABLE FIRE ALARM SYSTEM PLEASE REVIEW. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 09375 | Review Response | Not Required For Review | 2020-10-23 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  | This will be reviewed by electrical | Info Exchange
| 12374 | Responded and Closed | Approved as Noted/Resubmit | 2020-11-11 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-05 |  | 28 31 00-12.0 Deferred Spaces PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 28 31 00-12.0 Deferred Spaces PD-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-05 |  | 28 31 00-12.0 Deferred Spaces PD-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-04 02:00 |  | 28 31 00-12.0 Deferred Spaces PD-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-10-04 02:00 |  | 28 31 00-12.0 Deferred Spaces PD-MAM.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-10-05 |  | 28 31 00-12.0 Deferred Spaces PD-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-11-11 |  | 28 31 00-12.0 Deferred Spaces PD-MAM-ME_POP.pdf
28 31 00-012-00-01 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-012-00 ADDRESSABLE FIRE ALARM SYSTEM - Deferred Spaces Product Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 28 31 00-012-00 - 28 31 00-012-00 ADDRESSABLE FIRE ALARM SYSTEM - Deferred Spaces Product Data | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-11-11 |  | 28 31 00-12.0 Deferred Spaces PD-MAM-ME_POP.pdf
28 31 00-013-00 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-013-00 ADDRESSABLE FIRE ALARM SYSTEM - Premium Spaces Shop Drawings | Closed | Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-10-30 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Mark Lievens (ME Engineers) |  |  |  | 2020-11-13 | 2020-11-11 | 13 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2020-11-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 09117 | Received | For Review | 2020-10-30 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-11-13 | Submittal Number: 28 31 00-13.0 From: PATRICK KLEIN Final Due Date: 11/12/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - PREMIUM SPACES SHOP DRAWINGS Description: 283100: ADDRESSABLE FIRE ALARM SYSTEM PLEASE REVIEW. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 12031 | Forwarded | For Review | 2020-10-30 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2020-11-06 | Submittal Number: 28 31 00-13.0 From: PATRICK KLEIN Final Due Date: 11/12/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - PREMIUM SPACES SHOP DRAWINGS Description: 283100: ADDRESSABLE FIRE ALARM SYSTEM PLEASE REVIEW. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 12040 | Forwarded | For Review | 2020-10-30 | Shaina Burris (Populous) | Mark Lievens (ME Engineers) | 2020-11-06 | Submittal Number: 28 31 00-13.0 From: PATRICK KLEIN Final Due Date: 11/12/20 Subject: ADDRESSABLE FIRE ALARM SYSTEM - PREMIUM SPACES SHOP DRAWINGS Description: 283100: ADDRESSABLE FIRE ALARM SYSTEM PLEASE REVIEW. Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 09194 | Review Response | No Action Taken or Required | 2020-11-03 | Michael Mazzocchi (ME Engineers) | Shaina Burris (Populous) |  | To be reviewed by electrical | Info Exchange
| 09377 | Review Response | Approved as Noted | 2020-11-10 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.10 | Info Exchange
| 12376 | Responded and Closed | Approved as Noted | 2020-11-11 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Morten... |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2020.11.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-10-29 |  | 28 31 00-13.0 Premium Spaces Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-29 |  | 28 31 00-13.0 Premium Spaces Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-10-29 |  | 28 31 00-13.0 Premium Spaces Shops-MAM.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2020-10-28 02:00 |  | 28 31 00-13.0 Premium Spaces Shops-MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2020-10-29 |  | 28 31 00-13.0 Premium Spaces Shops-MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-11-11 |  | 28 31 00-13.0 Premium Spaces Shops-MAM-ME_POP.pdf
28 31 00-014-00 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-014-00 Smoke Control Panel | Closed | Fire Alarm, Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-26 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers), Ben Muscente (Howe Engineers, Inc.), Stephen Napolitano (Howe Engineers, Inc.) |  |  |  | 2021-04-12 07:00 | 2021-04-05 | 11 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12250 | Received | For Review | 2021-03-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-12 07:00 | Submittal Number: 28 31 00-14.0 From: LAUREN DUNHAM Final Due Date: 04/12/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 15850 | Forwarded | For Review | 2021-03-26 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-04-02 | Submittal Number: 28 31 00-14.0 From: LAUREN DUNHAM Final Due Date: 04/12/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 15876 | Forwarded | For Review | 2021-03-26 | Populous SCA_CCA | Ben Muscente (Howe Engineers, Inc.); Stephen Napolitano (Howe Engineers, Inc.) |  | Submittal Number: 28 31 00-14.0 From: LAUREN DUNHAM Final Due Date: 04/12/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 12394 | Review Response | Revise and Resubmit | 2021-03-30 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | See attached for reviews from Howe Engineers and ME Engineers. Nick Theimer ME Engineers 2021.03.30 | Info Exchange
| 16061 | Responded and Closed | Revise and Resubmit | 2021-04-05 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction); Cody Stieritz |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for reviews from Howe Engineers and ME Engineers. Nick Theimer ME Engineers 2021.03.30 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-25 |  | 283100-014-0 Smoke Control Panel Layout.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-25 |  | 283100-014-0 Smoke Control Panel Layout.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-25 |  | 283100-014-0 Smoke Control Panel Layout.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-03-24 02:00 |  | 283100-014-0 Smoke Control Panel Layout.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-05 02:00 |  | 283100-014-0 Smoke Control Panel Layout_HOWE_ME_POP.pdf
28 31 00-014-01 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-014-01 Smoke Control Panel | Closed | Fire Alarm | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-09 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Ben Muscente (Howe Engineers, Inc.), Jackie Lybarger (ME Engineers), Stephen Napolitano (Howe Engineers, Inc.), Heidi Evans (ME Engineers) |  |  |  | 2021-04-23 | 2021-04-20 | 12 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12508 | Received | For Review | 2021-04-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-23 | Submittal Number: 28 31 00-14.1 From: LAUREN DUNHAM Final Due Date: 04/22/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 16200 | Forwarded | For Review | 2021-04-09 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Ben Muscente (Howe Engineers, Inc.); Jackie Lybarger (ME Engineers); Stephen Napolitano (Howe Engineers, Inc.); Heidi Evans (ME Engineers) | 2021-04-16 | Submittal Number: 28 31 00-14.1 From: LAUREN DUNHAM Final Due Date: 04/22/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 12688 | Review Response | Revise and Resubmit | 2021-04-15 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for reviews by ME Engineers and Howe Engineers. Nick Theimer ME Engineers 2021.04.15 | Info Exchange
| 16408 | Responded and Closed | Revise and Resubmit | 2021-04-20 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for reviews by ME Engineers and Howe Engineers. Nick Theimer ME Engineers 2021.04.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-08 |  | 283100-014-1 Smoke Control Panel Layout.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-08 |  | 283100-014-1 Smoke Control Panel Layout.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-04-08 |  | 283100-014-1 Smoke Control Panel Layout.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-20 |  | 283100-014-1 Smoke Control Panel Layout_ME-HOWE_POP.pdf
28 31 00-014-02 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-014-02 Smoke Control Panel | Closed | Fire Alarm | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-22 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Ben Muscente (Howe Engineers, Inc.), Jackie Lybarger (ME Engineers), Stephen Napolitano (Howe Engineers, Inc.), Heidi Evans (ME Engineers) |  |  |  | 2021-05-06 | 2021-04-27 | 6 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-04-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12719 | Received | For Review | 2021-04-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-06 | Submittal Number: 28 31 00-14.2 From: LAUREN DUNHAM Final Due Date: 05/06/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 16442 | Forwarded | For Review | 2021-04-22 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Ben Muscente (Howe Engineers, Inc.); Jackie Lybarger (ME Engineers); Stephen Napolitano (Howe Engineers, Inc.); Heidi Evans (ME Engineers) | 2021-04-29 | Submittal Number: 28 31 00-14.2 From: LAUREN DUNHAM Final Due Date: 05/06/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 12820 | Review Response | Revise and Resubmit | 2021-04-22 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.04.22 | Info Exchange
| 16594 | Responded and Closed | Revise and Resubmit | 2021-04-27 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz; Colin.Saiz@mortenson.com |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.04.22 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-21 |  | 283100-014-2 Smoke Control Panel Layout Rev 2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-21 |  | 283100-014-2 Smoke Control Panel Layout Rev 2.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-04-20 02:00 |  | 283100-014-2 Smoke Control Panel Layout Rev 2.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-27 02:00 |  | 283100-014-2 Smoke Control Panel Layout Rev 2_ME_HOWE_POP.pdf
28 31 00-014-03 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-014-03 Smoke Control Panel | Closed | Fire Alarm | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-27 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-05-11 | 2021-04-30 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-04-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12809 | Received | For Review | 2021-04-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Cody Stieritz | 2021-05-11 | Submittal Number: 28 31 00-14.3 From: LAUREN DUNHAM Final Due Date: 05/03/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 16556 | Forwarded | For Review | 2021-04-27 | Cody Stieritz | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-05-04 | Submittal Number: 28 31 00-14.3 From: LAUREN DUNHAM Final Due Date: 05/03/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 12881 | Review Response | Revise and Resubmit | 2021-04-30 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Cody Stieritz |  | See attached for review from ME Engineers and Howe Engineers. Nick Theimer ME Engineers 2021.04.30 | Info Exchange
| 16663 | Responded and Closed | Revise and Resubmit | 2021-04-30 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review from ME Engineers and Howe Engineers. Nick Theimer ME Engineers 2021.04.30 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-27 |  | 283100-014-3 Smoke Control Panel Layout Rev 3.pdf
| Forwarded |  | Cody Stieritz | 1 | 2021-04-27 |  | 283100-014-3 Smoke Control Panel Layout Rev 3.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-04-30 02:00 |  | 283100-014-3 Smoke Control Panel Layout Rev 3_ME_HOWE.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-04-30 02:00 |  | 283100-014-3 Smoke Control Panel Layout Rev 3_ME_HOWE_POP.pdf
28 31 00-014-04 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-014-04 Smoke Control Panel | Closed | Fire Alarm | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-07 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Ben Muscente (Howe Engineers, Inc.), Jackie Lybarger (ME Engineers), Stephen Napolitano (Howe Engineers, Inc.), Heidi Evans (ME Engineers) |  |  |  | 2021-05-21 | 2021-05-10 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12975 | Received | For Review | 2021-05-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-21 | Submittal Number: 28 31 00-14.4 From: LAUREN DUNHAM Final Due Date: 05/14/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 16794 | Forwarded | For Review | 2021-05-07 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Ben Muscente (Howe Engineers, Inc.); Jackie Lybarger (ME Engineers); Stephen Napolitano (Howe Engineers, Inc.); Heidi Evans (ME Engineers) | 2021-05-14 | Submittal Number: 28 31 00-14.4 From: LAUREN DUNHAM Final Due Date: 05/14/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 13024 | Review Response | Revise and Resubmit | 2021-05-10 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review from ME Engineers and Howe Engineers. Nick Theimer ME Engineers 2021.05.10 | Info Exchange
| 16854 | Responded and Closed | Revise and Resubmit | 2021-05-10 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz |  | Response (Revise and Resubmit) from: Nick Theimer (ME Engineers) Remarks: See attached for review from ME Engineers and Howe Engineers. Nick Theimer ME Engineers 2021.05.10 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-06 |  | 283100-014-4 Smoke Control Panel Layout Rev 4.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-06 |  | 283100-014-4 Smoke Control Panel Layout Rev 4.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-05 02:00 |  | 283100-014-4 Smoke Control Panel Layout Rev 4.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-10 02:00 |  | 283100-014-4 Smoke Control Panel Layout Rev 4_ME_POP.pdf
28 31 00-014-05 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-014-05 Smoke Control Panel | Closed | Fire Alarm | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-17 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-06-01 07:00 | 2021-05-19 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13125 | Received | For Review | 2021-05-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Cody Stieritz | 2021-06-01 07:00 | Submittal Number: 28 31 00-14.5 From: LAUREN DUNHAM Final Due Date: 05/11/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 16984 | Forwarded | For Review | 2021-05-17 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-24 | Submittal Number: 28 31 00-14.5 From: LAUREN DUNHAM Final Due Date: 05/11/21 Subject: SMOKE CONTROL PANEL Description: Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 13182 | Review Response | Approved as Noted | 2021-05-19 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous) |  | See attached for review from ME Engineers and Howe Engineers. Nick Theimer ME Engineers 2021.05.19 | Info Exchange
| 17070 | Responded and Closed | Approved as Noted | 2021-05-19 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Cody Stieritz; Colin.Saiz@mortenson.com |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review from ME Engineers and Howe Engineers. Nick Theimer ME Engineers 2021.05.19 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-17 |  | 283100-014-5 Smoke Control Panel Layout Rev 5.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-17 |  | 283100-014-5 Smoke Control Panel Layout Rev 5.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-05-16 02:00 |  | 283100-014-5 Smoke Control Panel Layout Rev 5.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-19 02:00 |  | 283100-014-5 Smoke Control Panel Layout Rev 5_ME_HOWE_POP.pdf
28 31 00-015-00 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-015-00 19155-S0042 O&M Fire Alarm System | Closed | Fire Alarm, Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-31 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-09-14 | 2021-09-21 | 22 |  | Record Copies; Transfers; Submittals | 28 31 00-015-00-01 - 28 31 00-015-00 19155-S0042 O&M Fire Alarm System | 23 |  | 2021-09-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14529 | Received | For Review | 2021-08-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-14 | Submittal Number: 28 31 00-15.0 From: BINH DUONG Final Due Date: 09/13/21 Subject: 19155-S0042 O&M FIRE ALARM SYSTEM Description: SUBMITTAL OVERVIEW: OPERATION & MAINTENANCE MANUALS PER SUB-CONTRACTOR - ADT Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 18730 | Forwarded | For Review | 2021-08-30 | Populous SCA_CCA | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Michael Mazzocchi (ME Engineers) | 2021-09-06 | Submittal Number: 28 31 00-15.0 From: BINH DUONG Final Due Date: 09/13/21 Subject: 19155-S0042 O&M FIRE ALARM SYSTEM Description: SUBMITTAL OVERVIEW: OPERATION & MAINTENANCE MANUALS PER SUB-CONTRACTOR - ADT Spec Section: 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM Status: OPEN | Info Exchange
| 14677 | Review Response | Approved as Noted/Resubmit | 2021-09-21 | Mark Lievens (ME Engineers) | Populous SCA_CCA |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.09.21 | Info Exchange
| 18929 | Responded and Closed | Approved as Noted/Resubmit | 2021-09-21 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.09.21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-30 02:00 |  | 28 31 00-15.0 19155-S0042 O&M Fire Alarm System.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-30 02:00 |  | 28 31 00-15.0 19155-S0042 O&M Fire Alarm System.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-30 |  | 28 31 00-15.0 19155-S0042 O&M Fire Alarm System.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-21 |  | 28 31 00-15.0 19155-S0042 O&M Fire Alarm System - ME_POP.pdf
28 31 00-015-00-01 | 28 31 00 - ADDRESSABLE FIRE ALARM SYSTEM | 28 31 00-015-00 19155-S0042 O&M Fire Alarm System | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 28 31 00-015-00 - 28 31 00-015-00 19155-S0042 O&M Fire Alarm System | -1 | 2021-10-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-21 |  | 28 31 00-15.0 19155-S0042 O&M Fire Alarm System - ME_POP.pdf
28 50 00-001-00 | 28 50 00 - AREA OF RESCUE ASSISTANCE SYSTEM | 28 50 00-001-00 AREA OF RESCUE ASSISTANCE SYSTEM - Product Data, Manufacturer's Instructions, and Shop Drawings | Closed | Technology, Electrical, Fire Protection | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-09 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Mark Lievens (ME Engineers), Jackie Lybarger (ME Engineers) |  |  |  | 2020-07-23 | 2020-08-14 | 37 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-08-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06887 | Received | For Review | 2020-07-09 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Patrick Klein (M.A. Mortenson Company) | 2020-07-23 | Submittal Number: 28 50 00-1.0 From: PATRICK KLEIN Final Due Date: 07/23/20 Subject: AREA OF RESCUE ASSISTANCE SYSTEM - PRODUCT DATA, MANUFACTURER'S INSTRUCTIONS, AND SHOP DRAWINGS Description: GENERAL : DATA SHEETS ON ALL EQUIPMENT BEING PROVIDED AS WELL AS RECOMMENDED CABLE TYPES. INTERNAL CONTROL CABINET DRAWINGS SHOWING INTERNAL BLOCK DIAGRAM CONNECTIONS SHALL BE PROVIDED. WIRING DIAGRAMS SHOWING TYPICAL FIELD WIRING CONNECTIONS AS WELL AS SINGLE LINE FLOOR PLAN INDICATING EQUIPMENT LOCATIONS AS WELL AS CABLE ROUTINGS AND QUANTITIES. PRODUCT DATA : SUBMIT PRODUCT DATA, INCLUDING MANUFACTURER'S PRODUCT SHEET, FOR SPECIFIED PRODUCTS, INCLUDING MAIN CONTROL PANEL, CALL STATIONS AND CABLING. SHOP DRAWINGS : SUBMIT SHOP DRAWINGS SHOWING LAYOUT, PROFILES, AND PRODUCT COMPONENTS, INCLUDING ANCHORAGE AND ACCESSORIES. INCLUDE CABLING DIAGRAMS, WIRING DIAGRAMS, STATION INSTALLATION DETAILS, AND EQUIPMENT CABINET DETAILS. MANUFACTURER'S INSTRUCTIONS: MANUFACTURER'S INSTALLATION INSTRUCTIONS. Spec Section: 28 50 00 - AREA OF RESCUE ASSISTANCE SYSTEM Status: OPEN | Info Exchange
| 09229 | Forwarded | For Review | 2020-07-09 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-07-16 | Submittal Number: 28 50 00-1.0 From: PATRICK KLEIN Final Due Date: 07/23/20 Subject: AREA OF RESCUE ASSISTANCE SYSTEM - PRODUCT DATA, MANUFACTURER'S INSTRUCTIONS, AND SHOP DRAWINGS Description: GENERAL : DATA SHEETS ON ALL EQUIPMENT BEING PROVIDED AS WELL AS RECOMMENDED CABLE TYPES. INTERNAL CONTROL CABINET DRAWINGS SHOWING INTERNAL BLOCK DIAGRAM CONNECTIONS SHALL BE PROVIDED. WIRING DIAGRAMS SHOWING TYPICAL FIELD WIRING CONNECTIONS AS WELL AS SINGLE LINE FLOOR PLAN INDICATING EQUIPMENT LOCATIONS AS WELL AS CABLE ROUTINGS AND QUANTITIES. PRODUCT DATA : SUBMIT PRODUCT DATA, INCLUDING MANUFACTURER'S PRODUCT SHEET, FOR SPECIFIED PRODUCTS, INCLUDING MAIN CONTROL PANEL, CALL STATIONS AND CABLING. SHOP DRAWINGS : SUBMIT SHOP DRAWINGS SHOWING LAYOUT, PROFILES, AND PRODUCT COMPONENTS, INCLUDING ANCHORAGE AND ACCESSORIES. INCLUDE CABLING DIAGRAMS, WIRING DIAGRAMS, STATION INSTALLATION DETAILS, AND EQUIPMENT CABINET DETAILS. MANUFACTURER'S INSTRUCTIONS: MANUFACTURER'S INSTALLATION INSTRUCTIONS. Spec Section: 28 50 00 - AREA OF RESCUE ASSISTANCE SYSTEM Status: OPEN | Info Exchange
| 09317 | Forwarded | For Review | 2020-07-14 | Josh Dobken (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2020-07-21 | Submittal Number: 28 50 00-1.0 From: PATRICK KLEIN Final Due Date: 07/23/20 Subject: AREA OF RESCUE ASSISTANCE SYSTEM - PRODUCT DATA, MANUFACTURER'S INSTRUCTIONS, AND SHOP DRAWINGS Description: GENERAL : DATA SHEETS ON ALL EQUIPMENT BEING PROVIDED AS WELL AS RECOMMENDED CABLE TYPES. INTERNAL CONTROL CABINET DRAWINGS SHOWING INTERNAL BLOCK DIAGRAM CONNECTIONS SHALL BE PROVIDED. WIRING DIAGRAMS SHOWING TYPICAL FIELD WIRING CONNECTIONS AS WELL AS SINGLE LINE FLOOR PLAN INDICATING EQUIPMENT LOCATIONS AS WELL AS CABLE ROUTINGS AND QUANTITIES. PRODUCT DATA : SUBMIT PRODUCT DATA, INCLUDING MANUFACTURER'S PRODUCT SHEET, FOR SPECIFIED PRODUCTS, INCLUDING MAIN CONTROL PANEL, CALL STATIONS AND CABLING. SHOP DRAWINGS : SUBMIT SHOP DRAWINGS SHOWING LAYOUT, PROFILES, AND PRODUCT COMPONENTS, INCLUDING ANCHORAGE AND ACCESSORIES. INCLUDE CABLING DIAGRAMS, WIRING DIAGRAMS, STATION INSTALLATION DETAILS, AND EQUIPMENT CABINET DETAILS. MANUFACTURER'S INSTRUCTIONS: MANUFACTURER'S INSTALLATION INSTRUCTIONS. Spec Section: 28 50 00 - AREA OF RESCUE ASSISTANCE SYSTEM Status: OPEN | Info Exchange
| 07557 | Review Response | Approved | 2020-07-29 | Abby Harrison (ME Engineers) | Shaina Burris (Populous) |  | Contractor to confirm category cabling does not exceed distance limitations. Contractor to confirm area plan cable quantities and one-line cable quantities match. Populous to confirm Area of Rescue Assistance signage and signage locations. Abby Harrison ME Engineers 2020.07.29 | Info Exchange
| 10056 | Responded and Closed | Approved | 2020-08-14 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Abby Harrison (ME Engineers) Remarks: Contractor to confirm category cabling does not exceed distance limitations. Contractor to confirm area plan cable quantities and one-line cable quantities match. Populous to confirm Area of Rescue Assistance signage and signage locations. Abby Harrison ME Engineers 2020.07.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-09 |  | 28 50 00-1.0 PD and Shops-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-09 |  | 28 50 00-1.0 PD and Shops-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-07-08 02:00 |  | 28 50 00-1.0 PD and Shops-MAM.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-07-08 02:00 |  | 28 50 00-1.0 PD and Shops-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-08-14 02:00 |  | 28 50 00-1.0 PD and Shops-MAM_ME_pop.pdf
28 53 20-001-00 | 28 53 20 - EMERGENCY RESPONDER RADIO SYSTEM (ERRS) | 28 53 20-001-00 EMERGENCY RESPONDER RADIO SYSTEM (ERRS) - Product Data and Virtual Wireless Model | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-06 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist |  |  |  | 2020-05-20 | 2020-05-27 | 22 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2020-05-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05739 | Received | For Review | 2020-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-20 | Submittal Number: 28 53 20-1.0 From: ELLA PILGRIM Final Due Date: 05/19/20 Subject: EMERGENCY RESPONDER RADIO SYSTEM (ERRS) - PRODUCT DATA AND VIRTUAL WIRELESS MODEL Description: PRODUCT DATA : THE DAS PRODUCT DATA SUBMITTAL SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY. INFORMATION SHALL INCLUDE DETAILED PARTS LIST FOR ALL COMPONENTS AND MANUFACTURER'S PRODUCT DATA FOR EACH COMPONENT TO BE INSTALLED. VIRTUAL WIRELESS MODEL : AFTER PROJECT AWARD, PROVIDE PLAN DRAWINGS BASED ON ARCHITECTURAL BACKGROUND OR MODEL INDICATING DEVICE AND ANTENNA PLACEMENT BASED ON WIRELESS MODELING COMPUTER SOFTWARE. CONSTRUCTION MATERIALS SHALL BE INPUTTED INTO THE SOFTWARE PROGRAM FOR STRUCTURE, WALLS, FLOORS, AND CEILINGS AS WELL AS RADIO FREQUENCIES, ZONES, AND CAPACITY TO HELP PREDICT COVERAGE AND PLACEMENT OF ANTENNAS AND ASSOCIATED COVERAGE PATTERNS. INFORMATION SUBMITTED SHALL INCLUDE COVERAGE DRAWING (HEAT MAP) AS WELL AS PLACEMENT OF ANTENNAS, EQUIPMENT, CABLE AND CONDUIT ROUTING, REFLECTED CEILING PLAN LAYER, ETC. MODELS SHALL BE DEVELOPED USING IBWAVE OR EQUIVALENT INDUSTRY RECOGNIZED SOFTWARE. DRAWINGS SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY Spec Section: 28 53 20 - EMERGENCY RESPONDER SYSTEM Status: OPEN | Info Exchange
| 07786 | Forwarded | For Review | 2020-05-06 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-05-13 | Submittal Number: 28 53 20-1.0 From: ELLA PILGRIM Final Due Date: 05/19/20 Subject: EMERGENCY RESPONDER RADIO SYSTEM (ERRS) - PRODUCT DATA AND VIRTUAL WIRELESS MODEL Description: PRODUCT DATA : THE DAS PRODUCT DATA SUBMITTAL SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY. INFORMATION SHALL INCLUDE DETAILED PARTS LIST FOR ALL COMPONENTS AND MANUFACTURER'S PRODUCT DATA FOR EACH COMPONENT TO BE INSTALLED. VIRTUAL WIRELESS MODEL : AFTER PROJECT AWARD, PROVIDE PLAN DRAWINGS BASED ON ARCHITECTURAL BACKGROUND OR MODEL INDICATING DEVICE AND ANTENNA PLACEMENT BASED ON WIRELESS MODELING COMPUTER SOFTWARE. CONSTRUCTION MATERIALS SHALL BE INPUTTED INTO THE SOFTWARE PROGRAM FOR STRUCTURE, WALLS, FLOORS, AND CEILINGS AS WELL AS RADIO FREQUENCIES, ZONES, AND CAPACITY TO HELP PREDICT COVERAGE AND PLACEMENT OF ANTENNAS AND ASSOCIATED COVERAGE PATTERNS. INFORMATION SUBMITTED SHALL INCLUDE COVERAGE DRAWING (HEAT MAP) AS WELL AS PLACEMENT OF ANTENNAS, EQUIPMENT, CABLE AND CONDUIT ROUTING, REFLECTED CEILING PLAN LAYER, ETC. MODELS SHALL BE DEVELOPED USING IBWAVE OR EQUIVALENT INDUSTRY RECOGNIZED SOFTWARE. DRAWINGS SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY Spec Section: 28 53 20 - EMERGENCY RESPONDER SYSTEM Status: OPEN | Info Exchange
| 06159 | Review Response | No Action Taken or Required | 2020-05-18 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  | Submittal Reviewed only. | Info Exchange
| 08207 | Responded and Closed | Revise and Resubmit | 2020-05-27 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | 28 53 20-1.0 - Emergency Responder Radio System - Product Data and Virtual Wireless Model.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-05 |  | 28 53 20-1.0 - Emergency Responder Radio System - Product Data and Virtual Wireless Model.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-05-04 02:00 |  | 28 53 20-1.0 - Emergency Responder Radio System - Product Data and Virtual Wireless Model.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-27 |  | 28 53 20-1.0 - Emergency Responder Radio System - Product Data_ME_POP.pdf
28 53 20-001-01 | 28 53 20 - EMERGENCY RESPONDER RADIO SYSTEM (ERRS) | 28 53 20-001-01 EMERGENCY RESPONDER RADIO SYSTEM (ERRS) - Product Data and Virtual Wireless Model | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-29 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist |  |  |  | 2020-07-14 07:00 | 2020-07-20 | 22 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06657 | Received | For Review | 2020-06-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-07-14 07:00 | Submittal Number: 28 53 20-1.1 From: ELLA PILGRIM Final Due Date: 07/15/20 Subject: EMERGENCY RESPONDER RADIO SYSTEM (ERRS) - PRODUCT DATA AND VIRTUAL WIRELESS MODEL Description: PRODUCT DATA : THE DAS PRODUCT DATA SUBMITTAL SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY. INFORMATION SHALL INCLUDE DETAILED PARTS LIST FOR ALL COMPONENTS AND MANUFACTURER'S PRODUCT DATA FOR EACH COMPONENT TO BE INSTALLED. VIRTUAL WIRELESS MODEL : AFTER PROJECT AWARD, PROVIDE PLAN DRAWINGS BASED ON ARCHITECTURAL BACKGROUND OR MODEL INDICATING DEVICE AND ANTENNA PLACEMENT BASED ON WIRELESS MODELING COMPUTER SOFTWARE. CONSTRUCTION MATERIALS SHALL BE INPUTTED INTO THE SOFTWARE PROGRAM FOR STRUCTURE, WALLS, FLOORS, AND CEILINGS AS WELL AS RADIO FREQUENCIES, ZONES, AND CAPACITY TO HELP PREDICT COVERAGE AND PLACEMENT OF ANTENNAS AND ASSOCIATED COVERAGE PATTERNS. INFORMATION SUBMITTED SHALL INCLUDE COVERAGE DRAWING (HEAT MAP) AS WELL AS PLACEMENT OF ANTENNAS, EQUIPMENT, CABLE AND CONDUIT ROUTING, REFLECTED CEILING PLAN LAYER, ETC. MODELS SHALL BE DEVELOPED USING IBWAVE OR EQUIVALENT INDUSTRY RECOGNIZED SOFTWARE. DRAWINGS SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY Spec Section: 28 53 20 - EMERGENCY RESPONDER SYSTEM Status: OPEN | Info Exchange
| 08969 | Forwarded | For Review | 2020-06-29 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-07-06 | Submittal Number: 28 53 20-1.1 From: ELLA PILGRIM Final Due Date: 07/15/20 Subject: EMERGENCY RESPONDER RADIO SYSTEM (ERRS) - PRODUCT DATA AND VIRTUAL WIRELESS MODEL Description: PRODUCT DATA : THE DAS PRODUCT DATA SUBMITTAL SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY. INFORMATION SHALL INCLUDE DETAILED PARTS LIST FOR ALL COMPONENTS AND MANUFACTURER'S PRODUCT DATA FOR EACH COMPONENT TO BE INSTALLED. VIRTUAL WIRELESS MODEL : AFTER PROJECT AWARD, PROVIDE PLAN DRAWINGS BASED ON ARCHITECTURAL BACKGROUND OR MODEL INDICATING DEVICE AND ANTENNA PLACEMENT BASED ON WIRELESS MODELING COMPUTER SOFTWARE. CONSTRUCTION MATERIALS SHALL BE INPUTTED INTO THE SOFTWARE PROGRAM FOR STRUCTURE, WALLS, FLOORS, AND CEILINGS AS WELL AS RADIO FREQUENCIES, ZONES, AND CAPACITY TO HELP PREDICT COVERAGE AND PLACEMENT OF ANTENNAS AND ASSOCIATED COVERAGE PATTERNS. INFORMATION SUBMITTED SHALL INCLUDE COVERAGE DRAWING (HEAT MAP) AS WELL AS PLACEMENT OF ANTENNAS, EQUIPMENT, CABLE AND CONDUIT ROUTING, REFLECTED CEILING PLAN LAYER, ETC. MODELS SHALL BE DEVELOPED USING IBWAVE OR EQUIVALENT INDUSTRY RECOGNIZED SOFTWARE. DRAWINGS SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY Spec Section: 28 53 20 - EMERGENCY RESPONDER SYSTEM Status: OPEN | Info Exchange
| 07037 | Review Response | Approved as Noted | 2020-07-15 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  | THE FINAL LOCATION OF PUBLIC SAFETY HEADEND RACK LOCATED WITHIN DAS ROOM TO BE FIELD COORDINATED. DAS ROOM LAYOUT NOT YET FINALIZED WITH CELLULAR DAS PROVIDER. ANY EXPOSED ERRCS EQUIPMENT TO BE PAINTED TO MATCH SURROUNDINGS IN PREMIUM AREAS. CONFIRM FINAL PAINT COLORS WITH POPULOUS. CONFIRM JUNCTION BOXES ON WHICH ANTENNAS MOUNT ARE LARGE ENOUGH TO HOUSE EQUIPMENT AND BEND RADIUS OF ANTENNA CABLE. ABBY HARRISON ME ENGINEERS 2020.07.15 | Info Exchange
| 09423 | Responded and Closed | Approved as Noted | 2020-07-20 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company) |  | Remarks: THE FINAL LOCATION OF PUBLIC SAFETY HEADEND RACK LOCATED WITHIN DAS ROOM TO BE FIELD COORDINATED. DAS ROOM LAYOUT NOT YET FINALIZED WITH CELLULAR DAS PROVIDER. ANY EXPOSED ERRCS EQUIPMENT TO BE PAINTED TO MATCH SURROUNDINGS IN PREMIUM AREAS. CONFIRM FINAL PAINT COLORS WITH POPULOUS. CONFIRM JUNCTION BOXES ON WHICH ANTENNAS MOUNT ARE LARGE ENOUGH TO HOUSE EQUIPMENT AND BEND RADIUS OF ANTENNA CABLE. ABBY HARRISON ME ENGINEERS 2020.07.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-29 |  | 28 53 20-1.1 - Emergency Responder Radio System.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-06-29 |  | 28 53 20-1.1 - Emergency Responder Radio System.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-06-29 |  | 28 53 20-1.1 - Emergency Responder Radio System.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-07-20 |  | 28 53 20-1.1 - Emergency Responder Radio System_ME_POP.pdf
28 53 20-001-02 | 28 53 20 - EMERGENCY RESPONDER RADIO SYSTEM (ERRS) | 28 53 20-001-02 EMERGENCY RESPONDER RADIO SYSTEM (ERRS) - Product Data and Virtual Wireless Model | Closed | Technology, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-21 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Abby Harrison (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist |  |  |  | 2020-08-04 | 2020-08-06 | 17 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2020-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07057 | Received | For Review | 2020-07-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-08-04 | Submittal Number: 28 53 20-1.2 From: ELLA PILGRIM Final Due Date: 08/03/20 Subject: EMERGENCY RESPONDER RADIO SYSTEM (ERRS) - PRODUCT DATA AND VIRTUAL WIRELESS MODEL Description: PRODUCT DATA : THE DAS PRODUCT DATA SUBMITTAL SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY. INFORMATION SHALL INCLUDE DETAILED PARTS LIST FOR ALL COMPONENTS AND MANUFACTURER'S PRODUCT DATA FOR EACH COMPONENT TO BE INSTALLED. VIRTUAL WIRELESS MODEL : AFTER PROJECT AWARD, PROVIDE PLAN DRAWINGS BASED ON ARCHITECTURAL BACKGROUND OR MODEL INDICATING DEVICE AND ANTENNA PLACEMENT BASED ON WIRELESS MODELING COMPUTER SOFTWARE. CONSTRUCTION MATERIALS SHALL BE INPUTTED INTO THE SOFTWARE PROGRAM FOR STRUCTURE, WALLS, FLOORS, AND CEILINGS AS WELL AS RADIO FREQUENCIES, ZONES, AND CAPACITY TO HELP PREDICT COVERAGE AND PLACEMENT OF ANTENNAS AND ASSOCIATED COVERAGE PATTERNS. INFORMATION SUBMITTED SHALL INCLUDE COVERAGE DRAWING (HEAT MAP) AS WELL AS PLACEMENT OF ANTENNAS, EQUIPMENT, CABLE AND CONDUIT ROUTING, REFLECTED CEILING PLAN LAYER, ETC. MODELS SHALL BE DEVELOPED USING IBWAVE OR EQUIVALENT INDUSTRY RECOGNIZED SOFTWARE. DRAWINGS SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY Spec Section: 28 53 20 - EMERGENCY RESPONDER SYSTEM Status: OPEN | Info Exchange
| 09446 | Forwarded | For Review | 2020-07-21 | Populous SCA_CCA | Nick Theimer (ME Engineers); Abby Harrison (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist | 2020-07-28 | Submittal Number: 28 53 20-1.2 From: ELLA PILGRIM Final Due Date: 08/03/20 Subject: EMERGENCY RESPONDER RADIO SYSTEM (ERRS) - PRODUCT DATA AND VIRTUAL WIRELESS MODEL Description: PRODUCT DATA : THE DAS PRODUCT DATA SUBMITTAL SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY. INFORMATION SHALL INCLUDE DETAILED PARTS LIST FOR ALL COMPONENTS AND MANUFACTURER'S PRODUCT DATA FOR EACH COMPONENT TO BE INSTALLED. VIRTUAL WIRELESS MODEL : AFTER PROJECT AWARD, PROVIDE PLAN DRAWINGS BASED ON ARCHITECTURAL BACKGROUND OR MODEL INDICATING DEVICE AND ANTENNA PLACEMENT BASED ON WIRELESS MODELING COMPUTER SOFTWARE. CONSTRUCTION MATERIALS SHALL BE INPUTTED INTO THE SOFTWARE PROGRAM FOR STRUCTURE, WALLS, FLOORS, AND CEILINGS AS WELL AS RADIO FREQUENCIES, ZONES, AND CAPACITY TO HELP PREDICT COVERAGE AND PLACEMENT OF ANTENNAS AND ASSOCIATED COVERAGE PATTERNS. INFORMATION SUBMITTED SHALL INCLUDE COVERAGE DRAWING (HEAT MAP) AS WELL AS PLACEMENT OF ANTENNAS, EQUIPMENT, CABLE AND CONDUIT ROUTING, REFLECTED CEILING PLAN LAYER, ETC. MODELS SHALL BE DEVELOPED USING IBWAVE OR EQUIVALENT INDUSTRY RECOGNIZED SOFTWARE. DRAWINGS SHALL BE SUBMITTED FOR REVIEW AND APPROVAL BY AHJ PRIOR TO STARTING ANY WORK. COPIES SHALL BE PROVIDED TO ME ENGINEERS FOR REFERENCE ONLY Spec Section: 28 53 20 - EMERGENCY RESPONDER SYSTEM Status: OPEN | Info Exchange
| 07435 | Review Response | Approved as Noted | 2020-08-04 | Abby Harrison (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 09904 | Responded and Closed | Approved as Noted | 2020-08-06 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Abby Harrison (ME Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-20 |  | 28 53 20-1.2 - Emergency Responder Radio System.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-07-20 |  | 28 53 20-1.2 - Emergency Responder Radio System.pdf
| Review Response |  | Abby Harrison (ME Engineers) | 1 | 2020-07-19 02:00 |  | 28 53 20-1.2 - Emergency Responder Radio System.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-08-06 02:00 |  | 28 53 20-1.2 - Emergency Responder Radio System_ME_pop.pdf
28 53 20-006-00 | 28 53 20 - EMERGENCY RESPONDER RADIO SYSTEM (ERRS) | 28 53 20-006-00 Public Safety Das - Indoor Wide Band Omni Antenna | Closed | Technology | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-26 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-09-09 | 2021-09-08 | 14 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-09-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14475 | Received | For Review | 2021-08-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-09-09 | Submittal Number: 28 53 20-6.0 From: COLIN SAIZ Final Due Date: 09/10/21 Subject: PUBLIC SAFETY DAS - INDOOR WIDE BAND OMNI ANTENNA Description: Spec Section: 28 53 20 - EMERGENCY RESPONDER SYSTEM Status: OPEN | Info Exchange
| 18668 | Forwarded | For Review | 2021-08-25 | Populous SCA_CCA | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-09-01 | Submittal Number: 28 53 20-6.0 From: COLIN SAIZ Final Due Date: 09/10/21 Subject: PUBLIC SAFETY DAS - INDOOR WIDE BAND OMNI ANTENNA Description: Spec Section: 28 53 20 - EMERGENCY RESPONDER SYSTEM Status: OPEN | Info Exchange
| 14599 | Review Response | Approved as Noted | 2021-08-27 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  | This PS antenna swap is approved for the (7) locations. Approval is only based on aesthetics. Contractor to confirm that the same performance criteria will be met with the new antenna. | Info Exchange
| 18821 | Forwarded | For Review | 2021-09-08 | Populous SCA_CCA | Michael Mazzocchi (ME Engineers) |  | Submittal Number: 28 53 20-6.0 From: COLIN SAIZ Final Due Date: 09/10/21 Subject: PUBLIC SAFETY DAS - INDOOR WIDE BAND OMNI ANTENNA Description: Spec Section: 28 53 20 - EMERGENCY RESPONDER SYSTEM Status: OPEN | Info Exchange
| 14635 | Review Response | Approved as Noted | 2021-09-08 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 18822 | Responded and Closed | Approved as Noted | 2021-09-08 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Colin.Saiz@mortenson.com |  | Response (Approved as Noted) from: Michael Mazzocchi (ME Engineers) Remarks: This PS antenna swap is approved for the (7) locations. Approval is only based on aesthetics. Contractor to confirm that the same performance criteria will be met with the new antenna. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-25 |  | 28 53 20-06-0 - Public Safety DAS - Indoor Wide Band Omni Antenna.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-25 |  | 28 53 20-06-0 - Public Safety DAS - Indoor Wide Band Omni Antenna.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-08-25 |  | 28 53 20-06-0 - Public Safety DAS - Indoor Wide Band Omni Antenna.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-25 |  | 28 53 20-06-0 - Public Safety DAS - Indoor Wide Band Omni Antenna.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-08-25 |  | 28 53 20-06-0 - Public Safety DAS - Indoor Wide Band Omni Antenna.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-08 |  | 28 53 20-06-0 - Public Safety DAS - Indoor Wide Band Omni Antenna_ME_POP.pdf
31 20 00-003-0 | 31 20 00 - EARTHWORK | 31 20 00-003-0 Detectable Warning Tape | Closed | Civil | Domingo Sampayo (Mortenson Construction) | 2019-04-09 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant |  |  |  | 2019-04-23 | 2019-04-10 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-04-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01145 | Received | For Review | 2019-04-09 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-23 |  | Email
| 02027 | Forwarded | For Review | 2019-04-09 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-16 |  | Info Exchange
| 01155 | Review Response | Approved | 2019-04-09 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  |  | Info Exchange
| 02035 | Responded and Closed | Approved | 2019-04-10 | SCA_CCA@populous.com | Domingo Sampayo (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-09 |  | 31 20 00-003-0 Detectable Warning Tape.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-09 |  | 31 20 00-003-0 Detectable Warning Tape.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-04-09 |  | 31 20 00-003-0 Detectable Warning Tape.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-10 |  | 31 20 00-003-0 Detectable Warning Tape DCI_POP.pdf
31 20 00-005-0 | 31 20 00 - EARTHWORK | 31 20 00-005-0 Gravel Borrow | Closed | Civil | Domingo Sampayo (Mortenson Construction) | 2019-04-09 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant |  |  |  | 2019-04-23 | 2019-04-10 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-04-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01150 | Received | For Review | 2019-04-09 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-23 |  | Email
| 02030 | Forwarded | For Review | 2019-04-09 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-16 |  | Info Exchange
| 01156 | Review Response | Approved | 2019-04-09 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  |  | Info Exchange
| 02039 | Responded and Closed | Approved | 2019-04-10 | SCA_CCA@populous.com | Domingo Sampayo (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-09 |  | 31 20 00-005-0 Gravel Borrow.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-09 |  | 31 20 00-005-0 Gravel Borrow.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-04-09 |  | 31 20 00-005-0 Gravel Borrow.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-10 |  | 31 20 00-005-0 Gravel Borrow DCI POP.pdf
31 20 00-009-0 | 31 20 00 - EARTHWORK | 31 20 00-009-0 Gravel for Trench Backfill | Closed | Civil | Domingo Sampayo (Mortenson Construction) | 2019-04-09 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant |  |  |  | 2019-04-23 | 2019-04-10 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-04-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01148 | Received | For Review | 2019-04-09 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-23 |  | Email
| 02028 | Forwarded | For Review | 2019-04-09 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-16 |  | Info Exchange
| 01153 | Review Response | Approved | 2019-04-09 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  |  | Info Exchange
| 02040 | Responded and Closed | Approved | 2019-04-10 | SCA_CCA@populous.com | Domingo Sampayo (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-09 |  | 31 20 00-009-0 Gravel for Trench Backfill.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-09 |  | 31 20 00-009-0 Gravel for Trench Backfill.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-04-09 |  | 31 20 00-009-0 Gravel for Trench Backfill.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-10 |  | 31 20 00-009-0 Gravel for Trench Backfill DCI POP.pdf
31 20 00-012-00 | 31 20 00 - EARTHWORK | 31 20 00-012-00 (Temporary Dewatering) | Closed | Civil | Joe Korchemniy (Mortenson Construction) | 2019-04-18 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant |  |  |  | 2019-05-02 | 2019-04-30 | 13 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-04-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01193 | Received | For Review | 2019-04-18 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-02 |  | Email
| 02109 | Forwarded | For Review | 2019-04-17 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-24 |  | Info Exchange
| 01248 | Review Response | Approved | 2019-04-30 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  | See attached | Email
| 02204 | Responded and Closed | Approved | 2019-04-30 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-17 |  | 31 20 00-012-00 Groundwater Control Plan.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-17 |  | 31 20 00-012-00 Groundwater Control Plan.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-04-30 |  | 31 20 00-012-00 Groundwater Control _DCI 043019.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-30 |  | 31 20 00-012-00 Groundwater Control _DCI 043019_POP.pdf
31 20 00-013-00 | 31 20 00 - EARTHWORK | 31 20 00-013-00 Structural Fill and Subbase | Closed | Structural | Domingo Sampayo (Mortenson Construction) | 2019-05-08 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, David Winter (Hart Crowser), Brice Exley (Hart Crowser), Joseph Harmon (Hart Crowser), Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers), Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2019-05-22 | 2019-05-15 | 8 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-05-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01280 | Received | For Review | 2019-05-08 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-22 |  | Email
| 02246 | Forwarded | For Review | 2019-05-07 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-14 |  | Info Exchange
| 01285 | Review Response | No Action Taken or Required | 2019-05-08 | Matt Ross (Thornton Tomasetti) | SCA_CCA@populous.com |  | This submittal should be sent to Hart Crowser for review and approval. | Info Exchange
| 02253 | Forwarded | For Review | 2019-05-08 | SCA_CCA@populous.com | David Winter (Hart Crowser); Brice Exley (Hart Crowser); Joseph Harmon (Hart Crowser) | 2019-05-15 |  | Info Exchange
| 01291 | Review Response | Approved | 2019-05-08 | Joseph Harmon (Hart Crowser) | SCA_CCA@populous.com |  |  | Info Exchange
| 02264 | Forwarded | For Review | 2019-05-08 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-05-15 | Hart Crowser approved this one - wanted to make sure you didn't need to put your eyes on it as well. | Info Exchange
| 01334 | Review Response | Approved | 2019-05-15 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  |  | Info Exchange
| 02319 | Forwarded | For Review | 2019-05-15 | SCA_CCA@populous.com | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous) |  |  | Info Exchange
| 02321 | Responded and Closed | Approved | 2019-05-15 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved) from: Joseph Harmon (Hart Crowser) Remarks: Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-05-07 |  | 31 20 00-013-00 Structural Fill and Subbase.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-07 |  | 31 20 00-013-00 Structural Fill and Subbase.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-05-07 |  | 31 20 00-013-00 Structural Fill and Subbase.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-07 |  | 31 20 00-013-00 Structural Fill and Subbase.pdf
| Review Response |  | Joseph Harmon (Hart Crowser) | 1 | 2019-05-07 |  | 31 20 00-013-00 Structural Fill and Subbase.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-08 |  | 31 20 00-013-00 Structural Fill and Subbase_HC.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-05-08 |  | 31 20 00-013-00 Structural Fill and Subbase_HC.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-07 |  | 31 20 00-013-00 Structural Fill and Subbase.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-15 02:00 |  | 31 20 00-013-00 Structural Fill and Subbase_HC - DCI_POP.pdf
31 20 00-014-00 | 31 20 00 - EARTHWORK | 31 20 00-014-00 Pea Gravel | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-19 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-08-02 | 2019-07-22 | 4 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2019-07-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01815 | Received | For Review | 2019-07-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-02 | Submittal Number: 31 20 00-14.0 From: DOMINGO SAMPAYO Final Due Date: 07/22/19 Subject: PEA GRAVEL Description: PEA GRAVEL TO BE USED FOR UTILITIES BACKFILLING OPERATIONS. Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 02940 | Forwarded | For Review | 2019-07-18 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-07-25 | Submittal Number: 31 20 00-14.0 From: DOMINGO SAMPAYO Final Due Date: 07/22/19 Subject: PEA GRAVEL Description: PEA GRAVEL TO BE USED FOR UTILITIES BACKFILLING OPERATIONS. Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 01846 | Review Response | Approved | 2019-07-22 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  |  | Info Exchange
| 02972 | Responded and Closed | Approved | 2019-07-22 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Josh Broussard (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Jarrett Grant (DCI Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-18 |  | 31 20 00-14 Pea Gravel.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-18 |  | 31 20 00-14 Pea Gravel.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2019-07-22 02:00 |  | 31 20 00-14 Pea Gravel_DCI.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-22 02:00 |  | 31 20 00-14 Pea Gravel_DCI_POP.pdf
31 20 00-016-00 | 31 20 00 - EARTHWORK | 31 20 00-016-00 Structural Backfill-Recycled Concrete | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-18 | Responded and Closed - Rejected |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-01-10 | 2020-01-03 | 17 | General | Record Copies; Transfers; Submittals |  | 16 |  | 2020-01-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03674 | Received | For Review | 2019-12-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2020-01-10 | Submittal Number: 31 20 00-16.0 From: JUAN BOLANOS Final Due Date: 12/23/19 Subject: STRUCTURAL BACKFILL-RECYCLED CONCRETE Description: Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 05194 | Forwarded | For Review | 2019-12-18 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-12-25 | Submittal Number: 31 20 00-16.0 From: JUAN BOLANOS Final Due Date: 12/23/19 Subject: STRUCTURAL BACKFILL-RECYCLED CONCRETE Description: Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 03776 | Review Response | Rejected | 2020-01-02 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached for our review of the submittal. | Info Exchange
| 05314 | Responded and Closed | Rejected | 2020-01-03 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Josh Broussard (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Jarrett Grant (DCI Engineers) Remarks: See attached for our review of the submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-18 |  | 31 20 00-16 Structural Backfill-Recycled Concrete.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-18 |  | 31 20 00-16 Structural Backfill-Recycled Concrete.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2019-12-17 02:00 |  | 31 20 00-16 Structural Backfill-Recycled Concrete.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-01-03 02:00 |  | 31 20 00-16 Structural Backfill-Recycled Concrete_DCI_POP.pdf
31 20 00-016-01 | 31 20 00 - EARTHWORK | 31 20 00-016-01 Common Fill - Recycled Concrete | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-07 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-01-21 | 2020-01-08 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-01-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03816 | Received | For Review | 2020-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Josh Broussard (Mortenson Construction) | 2020-01-21 | Submittal Number: 31 20 00-16.1 From: JUAN BOLANOS Final Due Date: 01/20/20 Subject: COMMON FILL - RECYCLED CONCRETE Description: THIS SUBMITTED RECYCLED CONCRETE FILL WILL BE USED AS COMMON FILL BETWEEN STRUCTURAL FILL/NATIVE BEARING SOIL AND THE 6” SUBBASE/DRAINAGE LAYER TO REESTABLISH THE SUBGRADE ELEVATION WHERE FOOTING EXCAVATION OCCURS. STRUCTURAL FILL AND SUBBASE WILL BE PER SUBMITTAL #31 20 00-13. Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 05357 | Forwarded | For Review | 2020-01-07 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-01-14 | Submittal Number: 31 20 00-16.1 From: JUAN BOLANOS Final Due Date: 01/20/20 Subject: COMMON FILL - RECYCLED CONCRETE Description: THIS SUBMITTED RECYCLED CONCRETE FILL WILL BE USED AS COMMON FILL BETWEEN STRUCTURAL FILL/NATIVE BEARING SOIL AND THE 6” SUBBASE/DRAINAGE LAYER TO REESTABLISH THE SUBGRADE ELEVATION WHERE FOOTING EXCAVATION OCCURS. STRUCTURAL FILL AND SUBBASE WILL BE PER SUBMITTAL #31 20 00-13. Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 03849 | Review Response | Approved as Noted | 2020-01-08 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | Attached is our review of this materials submittal. | Info Exchange
| 05396 | Responded and Closed | Approved as Noted | 2020-01-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Josh Broussard (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: Attached is our review of this materials submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-06 |  | 31 20 00-16.1 Common Fill-Recycled Concrete.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-06 |  | 31 20 00-16.1 Common Fill-Recycled Concrete.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-01-08 02:00 |  | 31 20 00-16.1 Common Fill-Recycled Concrete_DCI.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-01-08 02:00 |  | 31 20 00-16.1 Common Fill-Recycled Concrete_DCI_POP.pdf
31 20 00-018-00 | 31 20 00 - EARTHWORK | 31 20 00-018-00 Bedding & Backfill for UG Plumbing | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-11 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-03-25 | 2020-03-18 | 8 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-03-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04761 | Received | For Review | 2020-03-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-03-25 | Submittal Number: 31 20 00-18.0 From: GRETCHEN TOSHACH Final Due Date: 04/01/20 Subject: BEDDING & BACKFILL FOR UG PLUMBING Description: BEDDING AND BACKFILL PROUCT DATA FOR UNDERGROUND PLUMBING PIPING Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 06531 | Forwarded | For Review | 2020-03-11 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-03-18 | Submittal Number: 31 20 00-18.0 From: GRETCHEN TOSHACH Final Due Date: 04/01/20 Subject: BEDDING & BACKFILL FOR UG PLUMBING Description: BEDDING AND BACKFILL PROUCT DATA FOR UNDERGROUND PLUMBING PIPING Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 04939 | Review Response | Approved as Noted | 2020-03-12 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 06735 | Responded and Closed | Approved as Noted | 2020-03-18 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-11 |  | 31 20 00-18.0 UG Plumbing Bedding Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-11 |  | 31 20 00-18.0 UG Plumbing Bedding Product Data - MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-03-10 02:00 |  | 31 20 00-18.0 UG Plumbing Bedding Product Data - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-03-18 02:00 |  | 31 20 00-18.0 UG Plumbing Bedding Product Data - MAM_DCI_POP.pdf
31 20 00-018-01 | 31 20 00 - EARTHWORK | 31 20 00-018-01 Bedding & Backfill for UG Plumbing | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-28 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-05-12 | 2020-04-28 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05577 | Received | For Review | 2020-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-05-12 | Submittal Number: 31 20 00-18.1 From: GRETCHEN TOSHACH Final Due Date: 05/15/20 Subject: BEDDING & BACKFILL FOR UG PLUMBING Description: BEDDING AND BACKFILL PROUCT DATA FOR UNDERGROUND PLUMBING PIPING Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 07564 | Forwarded | For Review | 2020-04-27 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-05-04 | Submittal Number: 31 20 00-18.1 From: GRETCHEN TOSHACH Final Due Date: 05/15/20 Subject: BEDDING & BACKFILL FOR UG PLUMBING Description: BEDDING AND BACKFILL PROUCT DATA FOR UNDERGROUND PLUMBING PIPING Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 05601 | Review Response | Approved | 2020-04-27 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached review of the material submittal. - J. Grant, DCI Engineers | Info Exchange
| 07592 | Responded and Closed | Approved | 2020-04-28 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Jarrett Grant (DCI Engineers) Remarks: See attached review of the material submittal. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-27 |  | 31 20 00-18.1 Earthwrk Bedding_Backfill - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-27 |  | 31 20 00-18.1 Earthwrk Bedding_Backfill - MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-04-26 02:00 |  | 31 20 00-18.1 Earthwrk Bedding_Backfill - MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-28 02:00 |  | 31 20 00-18.1 Earthwrk Bedding_Backfill - DCI_POP.pdf
31 20 00-020-00 | 31 20 00 - EARTHWORK | 31 20 00-020-00 Capillary Break Material ( Type 22 & Type 28) | Closed | Civil, Geotechnical/Foundations | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-14 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers), David Winter (Hart Crowser), Brice Exley (Hart Crowser) |  |  |  | 2020-05-29 07:00 | 2020-06-05 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2020-06-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05861 | Received | For Review | 2020-05-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-05-29 07:00 | Submittal Number: 31 20 00-20.0 From: DOMINGO SAMPAYO Final Due Date: 05/18/20 Subject: CAPILLARY BREAK MATERIAL ( TYPE 22 & TYPE 28) Description: TYPE 22 TO BE USED UNDER THE SLAB, WHILE TYPE 28 TO BE USED AROUND THE DRAINAGE PIPING. SIEVE ANALYSIS ARE ATTACHED AND SAMPLES HAVE BEEN DELIVERED TO MORTENSON TO BE PICKED UP BY HART CROWSER. RFI #2386.1 APPROVED THIS MATERIAL. Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 07952 | Forwarded | For Review | 2020-05-14 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-05-21 | Submittal Number: 31 20 00-20.0 From: DOMINGO SAMPAYO Final Due Date: 05/18/20 Subject: CAPILLARY BREAK MATERIAL ( TYPE 22 & TYPE 28) Description: TYPE 22 TO BE USED UNDER THE SLAB, WHILE TYPE 28 TO BE USED AROUND THE DRAINAGE PIPING. SIEVE ANALYSIS ARE ATTACHED AND SAMPLES HAVE BEEN DELIVERED TO MORTENSON TO BE PICKED UP BY HART CROWSER. RFI #2386.1 APPROVED THIS MATERIAL. Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 07973 | Forwarded | For Review | 2020-05-14 | Josh Dobken (Populous) | David Winter (Hart Crowser); Brice Exley (Hart Crowser) | 2020-05-21 | Submittal Number: 31 20 00-20.0 From: DOMINGO SAMPAYO Final Due Date: 05/18/20 Subject: CAPILLARY BREAK MATERIAL ( TYPE 22 & TYPE 28) Description: TYPE 22 TO BE USED UNDER THE SLAB, WHILE TYPE 28 TO BE USED AROUND THE DRAINAGE PIPING. SIEVE ANALYSIS ARE ATTACHED AND SAMPLES HAVE BEEN DELIVERED TO MORTENSON TO BE PICKED UP BY HART CROWSER. RFI #2386.1 APPROVED THIS MATERIAL. Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 06240 | Review Response | Approved as Noted | 2020-06-03 | Brice Exley (Hart Crowser) | Josh Dobken (Populous) |  | Submit material to Mayes for testing as previous discussed via email. | Info Exchange
| 06241 | Review Response | Approved as Noted | 2020-06-05 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  |  | Info Exchange
| 08424 | Responded and Closed | Approved as Noted | 2020-06-05 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Brice Exley (Hart Crowser) Remarks: Submit material to Mayes for testing as previous discussed via email. Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-13 |  | 31 20 00-20 Capillary Break Material ( Type 22 & Type 28).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-05-13 |  | 31 20 00-20 Capillary Break Material ( Type 22 & Type 28).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-05-12 02:00 |  | 31 20 00-20 Capillary Break Material ( Type 22 & Type 28).pdf
| Review Response |  | Brice Exley (Hart Crowser) | 1 | 2020-05-12 02:00 |  | 31 20 00-20 Capillary Break Material ( Type 22 & Type 28).pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-05-12 02:00 |  | 31 20 00-20 Capillary Break Material ( Type 22 & Type 28).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-06-05 02:00 |  | 31 20 00-20 Capillary Break Material ( Type 22 & Type 28)_DCI_POP.pdf
31 20 00-021-00 | 31 20 00 - EARTHWORK | 31 20 00-021-00 Type 2 Agregate (per C202 UTILITY PLAN SOUTH PARCEL) | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-28 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-09-14 07:00 | 2020-09-01 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07808 | Received | For Review | 2020-08-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-09-14 07:00 | Submittal Number: 31 20 00-21.0 From: DOMINGO SAMPAYO Final Due Date: 09/11/20 Subject: TYPE 2 AGREGATE (PER C202 UTILITY PLAN SOUTH PARCEL) Description: TYPE 2 AGGREGATE TO BE USED ON THE SOUTH PARCEL AS SHOWN ON THE DRAWING (C202 UTILITY PLAN SOUTH PARCEL). Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 10386 | Forwarded | For Review | 2020-08-27 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-09-03 | Submittal Number: 31 20 00-21.0 From: DOMINGO SAMPAYO Final Due Date: 09/11/20 Subject: TYPE 2 AGREGATE (PER C202 UTILITY PLAN SOUTH PARCEL) Description: TYPE 2 AGGREGATE TO BE USED ON THE SOUTH PARCEL AS SHOWN ON THE DRAWING (C202 UTILITY PLAN SOUTH PARCEL). Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 07888 | Review Response | Approved as Noted | 2020-08-28 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 10490 | Responded and Closed | Approved as Noted | 2020-09-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-27 |  | 31 20 00-21 Type 2 Agregate (C202).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-27 |  | 31 20 00-21 Type 2 Agregate (C202).pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-08-27 |  | 31 20 00-21 Type 2 Agregate (C202).pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-01 |  | 31 20 00-21 Type 2 Agregate (C202)_DCI_POP.pdf
31 20 00-022-00 | 31 20 00 - EARTHWORK | 31 20 00-022-00 Rainwater Cistern Backfill | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-28 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-05-12 | 2021-04-28 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12833 | Received | For Review | 2021-04-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-12 | Submittal Number: 31 20 00-22.0 From: JUAN BOLANOS Final Due Date: 05/12/21 Subject: RAINWATER CISTERN BACKFILL Description: BACKFILL MATERIAL AROUND THE RAINWATER CISTERN. Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 16608 | Forwarded | For Review | 2021-04-28 | Populous SCA_CCA | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-05-05 | Submittal Number: 31 20 00-22.0 From: JUAN BOLANOS Final Due Date: 05/12/21 Subject: RAINWATER CISTERN BACKFILL Description: BACKFILL MATERIAL AROUND THE RAINWATER CISTERN. Spec Section: 31 20 00 - EARTHWORK Status: OPEN | Info Exchange
| 12838 | Review Response | Approved | 2021-04-28 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached materials submittal review. - J. Grant, DCI Engineers | Info Exchange
| 16614 | Responded and Closed | Approved | 2021-04-28 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Jarrett Grant (DCI Engineers) Remarks: See attached materials submittal review. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-28 |  | 2021-04-28 312000-0022-00 Rainwater Cistern Backfill PD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-28 |  | 2021-04-28 312000-0022-00 Rainwater Cistern Backfill PD_MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-04-27 02:00 |  | 2021-04-28 312000-0022-00 Rainwater Cistern Backfill PD_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-28 02:00 |  | 31 20 00-022-00 Rainwater Cistern Backfill PD_MAM_DCI_POP.pdf
31 63 29-001-00 | 31 63 29 - CAISSONS | 31 63 29-001-00 Type 17 Gravel Backfilling | Closed | Structural | Domingo Sampayo (Mortenson Construction) | 2019-03-07 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti) |  |  |  | 2019-03-22 | 2019-03-26 | 20 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2019-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01025 | Received | For Review | 2019-03-07 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-03-22 |  | Email
| 01861 | Forwarded | For Review | 2019-03-08 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti (Boston)); Ali Helwa (Thornton Tomasetti... | 2019-03-15 |  | Info Exchange
| 01965 | Responded and Closed | Not Required For Review | 2019-03-26 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-03-08 |  | 31 63 29-001-0 Type 17 Gravel Backfilling.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-08 |  | 31 63 29-001-0 Type 17 Gravel Backfilling.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-03-26 |  | 31 63 29-001-0 Type 17 Gravel Backfilling_POP.pdf
31 63 29-002-00 | 31 63 29 - CAISSONS | 31 63 29-002-00 Caisson Concrete Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-20 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-06 | 2019-12-05 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-12-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03275 | Received | For Review | 2019-11-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-12-06 | Submittal Number: 31 63 29-2.0 From: JOE KORCHEMNIY Final Due Date: 11/29/19 Subject: CAISSON CONCRETE MIX DESIGN Description: MIX DESIGN FOR BP1-BP3 DRILLED SHAFTS (5000 PSI) AND APPROVED ADMIXTURE USED FOR TRS SHAFTS AND SOLDIER PILE STRUCTURAL TOES. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 04722 | Forwarded | For Review | 2019-11-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-27 | Submittal Number: 31 63 29-2.0 From: JOE KORCHEMNIY Final Due Date: 11/29/19 Subject: CAISSON CONCRETE MIX DESIGN Description: MIX DESIGN FOR BP1-BP3 DRILLED SHAFTS (5000 PSI) AND APPROVED ADMIXTURE USED FOR TRS SHAFTS AND SOLDIER PILE STRUCTURAL TOES. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03520 | Review Response | Approved as Noted/Resubmit | 2019-12-04 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | While the documents received are acceptable, additional documentation is missing and must be submitted for full approval. Per correspondence with MAM, resubmittal to include continuous approval status reports, Concrete Mix Design Submittal Forms and acknowledgments regarding retarders and shrinkage reports. SDK ¦ TT ¦ 12/4/2019 | Info Exchange
| 04986 | Responded and Closed | Approved as Noted/Resubmit | 2019-12-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Samar Kenkre (Thornton Tomasetti) Remarks: While the documents received are acceptable, additional documentation is missing and must be submitted for full approval. Per correspondence with MAM, resubmittal to include continuous approval status reports, Concrete Mix Design Submittal Forms and acknowledgments regarding retarders and shrinkage reports. SDK ¦ TT ¦ 12/4/2019 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-19 |  | Submittal #31 63 29-2.0 Caisson Concrete Mix Design.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-19 |  | Submittal #31 63 29-2.0 Caisson Concrete Mix Design.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-12-05 02:00 |  | Submittal #31 63 29-2.0 Caisson Concrete Mix Design_TT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-05 02:00 |  | Submittal #31 63 29-2.0 Caisson Concrete Mix Design_TT_POP.pdf
31 63 29-002-01 | 31 63 29 - CAISSONS | 31 63 29-002-01 Caisson Concrete Mix Design | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-03 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-20 07:00 | 2020-04-17 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-04-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05207 | Received | For Review | 2020-04-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-20 07:00 | Submittal Number: 31 63 29-2.1 From: ELLA PILGRIM Final Due Date: 04/17/20 Subject: CAISSON CONCRETE MIX DESIGN Description: MIX DESIGN FOR ALL DRILLED SHAFTS (5000 PSI) Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 07079 | Forwarded | For Review | 2020-04-03 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-10 | Submittal Number: 31 63 29-2.1 From: ELLA PILGRIM Final Due Date: 04/17/20 Subject: CAISSON CONCRETE MIX DESIGN Description: MIX DESIGN FOR ALL DRILLED SHAFTS (5000 PSI) Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05404 | Review Response | Approved | 2020-04-16 | Samar Kenkre (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 07334 | Responded and Closed | Approved | 2020-04-17 | Populous SCA_CCA | Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-03 |  | 31 63 29-2.1 Caisson Concrete Mix Design.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-03 |  | 31 63 29-2.1 Caisson Concrete Mix Design.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2020-04-03 |  | 31 63 29-2.1 Caisson Concrete Mix Design.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-17 |  | 31 63 29-2.1 Caisson Concrete Mix Design-MAM_TT_POP.pdf
31 63 29-003-00 | 31 63 29 - CAISSONS | 31 63 29-003-00 Caisson Construction Methods | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-09 | 2019-12-03 | 13 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-12-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03294 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-12-09 | Submittal Number: 31 63 29-3.0 From: JOE KORCHEMNIY Final Due Date: 12/04/19 Subject: CAISSON CONSTRUCTION METHODS Description: CAISSON CONSTRUCTION PROCEDURES ATTACHED. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 04743 | Forwarded | For Review | 2019-11-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-27 | Submittal Number: 31 63 29-3.0 From: JOE KORCHEMNIY Final Due Date: 12/04/19 Subject: CAISSON CONSTRUCTION METHODS Description: CAISSON CONSTRUCTION PROCEDURES ATTACHED. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03441 | Review Response | No Action Taken or Required | 2019-12-03 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Received for record only. | Info Exchange
| 04913 | Responded and Closed | No Action Taken or Required | 2019-12-03 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Received for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-20 |  | Submittal #31 63 29-3.0 Caisson Construction Methods.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-20 |  | Submittal #31 63 29-3.0 Caisson Construction Methods.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-20 |  | Submittal #31 63 29-3.0 Caisson Construction Methods.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-12-03 |  | Submittal #31 63 29-3.0 Caisson Construction Methods_POP.pdf
31 63 29-004-00 | 31 63 29 - CAISSONS | 31 63 29-004-00 Permanent Caisson Shop Drawings (BP1 and BP2) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-01 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-11-15 | 2019-11-08 | 8 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-11-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03005 | Received | For Review | 2019-11-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-11-15 | Submittal Number: 31 63 29-4.0 From: JOE KORCHEMNIY Final Due Date: 11/18/19 Subject: PERMANENT CAISSON SHOP DRAWINGS (BP1 AND BP2) Description: BP1 AND BP2 CAISSON SHOP DRAWINGS Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 04395 | Forwarded | For Review | 2019-11-01 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-08 | Submittal Number: 31 63 29-4.0 From: JOE KORCHEMNIY Final Due Date: 11/18/19 Subject: PERMANENT CAISSON SHOP DRAWINGS (BP1 AND BP2) Description: BP1 AND BP2 CAISSON SHOP DRAWINGS Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03128 | Review Response | Approved as Noted | 2019-11-07 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04539 | Responded and Closed | Approved as Noted | 2019-11-08 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-31 |  | Submittal #31 63 29-4.0 Caisson Shop Drawing (BP1 and BP2).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-31 |  | Submittal #31 63 29-4.0 Caisson Shop Drawing (BP1 and BP2).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-10-31 |  | Submittal #31 63 29-4.0 Caisson Shop Drawing (BP1 and BP2).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-11-08 |  | Submittal #31 63 29-4.0 Caisson Shop Drawing (BP1 and BP2)_TT_POP.pdf
31 63 29-005-00 | 31 63 29 - CAISSONS | 31 63 29-005-00 Caisson Layout | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-12-05 | 2019-12-06 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2019-12-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03253 | Received | For Review | 2019-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-12-05 | Submittal Number: 31 63 29-5.0 From: JOE KORCHEMNIY Final Due Date: 11/29/19 Subject: CAISSON LAYOUT Description: SEE CAISSON LAYOUT DRAWINGS ATTACHED SHOWING LOCATION FROM GRID, TOP OF CAISSON CONCRETE ELEVATION, DIAMETER OF SHAFT, AND DEPTH. NAMING CONVENTION FOR CAISSONS ESTABLISHED TO FACILITATE INSTALLATION COORDINATION. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 04695 | Forwarded | For Review | 2019-11-19 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-26 | Submittal Number: 31 63 29-5.0 From: JOE KORCHEMNIY Final Due Date: 11/29/19 Subject: CAISSON LAYOUT Description: SEE CAISSON LAYOUT DRAWINGS ATTACHED SHOWING LOCATION FROM GRID, TOP OF CAISSON CONCRETE ELEVATION, DIAMETER OF SHAFT, AND DEPTH. NAMING CONVENTION FOR CAISSONS ESTABLISHED TO FACILITATE INSTALLATION COORDINATION. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03529 | Review Response | Approved as Noted | 2019-12-06 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 04998 | Forwarded | For Review | 2019-12-06 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2019-12-05 | Submittal Number: 31 63 29-5.0 From: JOE KORCHEMNIY Final Due Date: 11/29/19 Subject: CAISSON LAYOUT Description: SEE CAISSON LAYOUT DRAWINGS ATTACHED SHOWING LOCATION FROM GRID, TOP OF CAISSON CONCRETE ELEVATION, DIAMETER OF SHAFT, AND DEPTH. NAMING CONVENTION FOR CAISSONS ESTABLISHED TO FACILITATE INSTALLATION COORDINATION. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 04999 | Responded and Closed | Approved as Noted | 2019-12-06 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-18 |  | Submittal #31 63 29-5.0 Caisson Layout.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-18 |  | Submittal #31 63 29-5.0 Caisson Layout.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-17 02:00 |  | Submittal #31 63 29-5.0 Caisson Layout.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-11-17 02:00 |  | Submittal #31 63 29-5.0 Caisson Layout.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-12-06 |  | Submittal #31 63 29-5.0 Caisson Layout_TT_POP.pdf
31 63 29-006-00 | 31 63 29 - CAISSONS | 31 63 29-006-00 Mill Certificates | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-05-06 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-05-20 | 2020-05-11 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-05-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05740 | Received | For Review | 2020-05-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-20 | Submittal Number: 31 63 29-6.0 From: ELLA PILGRIM Final Due Date: 05/19/20 Subject: MILL CERTIFICATES Description: PER SPECIFICATION SECTION 032000, SUBMIT FOR RECORD CERTIFIED REPORTS FOR PHYSICAL AND CHEMICAL PROPERTIES OF FOLLOWING MATERIALS: A. REINFORCEMENT BARS. B. PERMANENT STEEL LINERS. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 07788 | Forwarded | For Review | 2020-05-06 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-05-13 | Submittal Number: 31 63 29-6.0 From: ELLA PILGRIM Final Due Date: 05/19/20 Subject: MILL CERTIFICATES Description: PER SPECIFICATION SECTION 032000, SUBMIT FOR RECORD CERTIFIED REPORTS FOR PHYSICAL AND CHEMICAL PROPERTIES OF FOLLOWING MATERIALS: A. REINFORCEMENT BARS. B. PERMANENT STEEL LINERS. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05808 | Review Response | No Action Taken or Required | 2020-05-11 | Sean McNeill (Thornton Tomasetti) | Populous SCA_CCA |  | Received for record. | Info Exchange
| 07872 | Responded and Closed | No Action Taken or Required | 2020-05-11 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Sean McNeill (Thornton Tomasetti) Remarks: Received for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-05-05 |  | 31 63 29-6.0 - Mill Certificates.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-05-05 |  | 31 63 29-6.0 - Mill Certificates.pdf
| Review Response |  | Sean McNeill (Thornton Tomasetti) | 1 | 2020-05-04 02:00 |  | 31 63 29-6.0 - Mill Certificates.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-05-11 02:00 |  | 31 63 29-6.0 - Mill Certificates_TT_POP.pdf
31 63 29-007-00 | 31 63 29 - CAISSONS | 31 63 29-007-00 Drilled Test Shaft Submittal Package | Closed | Structural | Joe Korchemniy (M.A. Mortenson Company) | 2019-03-29 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), David Winter (Hart Crowser), Brice Exley (Hart Crowser), Joseph Harmon (Hart Crowser) |  |  |  | 2019-04-12 | 2019-04-23 | 26 |  | Record Copies; Transfers; Submittals |  | 26 |  | 2019-04-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01107 | Received | For Review | 2019-03-29 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-12 |  | Email
| 01980 | Forwarded | For Review | 2019-03-29 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-04-05 | This submittal is the SCA Drilled Test Shaft plan for the temporary roof support foundations. Test shaft is scheduled to be drilled Saturday 3/30/19. | Info Exchange
| 02013 | Forwarded | For Review | 2019-04-05 | SCA_CCA@populous.com | David Winter (Hart Crowser); Brice Exley (Hart Crowser); Joseph Harmon (Hart Crowser) | 2019-04-12 | This submittal is the SCA Drilled Test Shaft plan for the temporary roof support foundations. Test shaft is scheduled to be drilled Saturday 3/30/19. | Info Exchange
| 01212 | Review Response | No Action Taken or Required | 2019-04-23 | Brice Exley (Hart Crowser) | SCA_CCA@populous.com |  | We take no exception, and the work has been completed. | Info Exchange
| 02147 | Responded and Closed | No Action Taken or Required | 2019-04-23 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Response (No Action Taken or Required) from: Brice Exley (Hart Crowser) Remarks: We take no exception, and the work has been completed. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-28 |  | 31 63 29-007-0 Drilled Test Shaft Submittal Package.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-28 |  | 31 63 29-007-0 Drilled Test Shaft Submittal Package.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-28 |  | 31 63 29-007-0 Drilled Test Shaft Submittal Package.pdf
| Review Response |  | Brice Exley (Hart Crowser) | 1 | 2019-03-28 |  | 31 63 29-007-0 Drilled Test Shaft Submittal Package.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-23 |  | 31 63 29-007-0 Drilled Test Shaft Submittal Package_POP.pdf
31 63 29-008-00 | 31 63 29 - CAISSONS | 31 63 29-008-00 TRS - Below Grade Exterior Pile | Closed | Structural | Ella Pilgrim | 2019-04-12 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-04-26 | 2019-04-30 | 19 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2019-04-30
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01168 | Received | For Review | 2019-04-12 | Ella Pilgrim | Shaina Burris (Populous) | 2019-04-26 |  | Email
| 02059 | Forwarded | For Review | 2019-04-12 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-04-19 |  | Info Exchange
| 01242 | Review Response | Revise and Resubmit | 2019-04-29 | Mark Membreno (Thornton Tomasetti) | Shaina Burris (Populous) |  | See markups on PDF. Lengths and quantities not reviewed. Contractor to coordinate with 4/22/2019 drawings. | Info Exchange
| 02192 | Responded and Closed | Revise and Resubmit | 2019-04-30 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Ella Pilgrim |  | Response (Revise and Resubmit) from: Mark Membreno (Thornton Tomasetti) Remarks: See markups on PDF. Lengths and quantities not reviewed. Contractor to coordinate with 4/22/2019 drawings. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Ella Pilgrim (Mortenson Construction) | 1 | 2019-04-12 |  | 31 63 29-008-0 TRS - Below Grade Exterior Pile.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-04-12 |  | 31 63 29-008-0 TRS - Below Grade Exterior Pile.pdf
| Review Response |  | Mark Membreno (Thornton Tomasetti) | 1 | 2019-04-12 |  | 31 63 29-008-0 TRS - Below Grade Exterior Pile.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-04-30 |  | 31 63 29-008-0 TRS - Below Grade Exterior Pile_TT REVIEW_POP.pdf
31 63 29-008-01 | 31 63 29 - CAISSONS | 31 63 29-008-01 TRS - Below Grade Exterior Pile | Closed | Structural | Ella Pilgrim (Mortenson Construction) | 2019-05-07 | Responded and Closed - Not Required For Review |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary (Thornton Tomasetti), Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-05-21 | 2019-05-08 | 2 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-05-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01269 | Received | For Review | 2019-05-07 | Ella Pilgrim | SCA_CCA@populous.com | 2019-05-21 |  | Email
| 02233 | Forwarded | For Review | 2019-05-06 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-13 |  | Info Exchange
| 02260 | Responded and Closed | Not Required For Review | 2019-05-08 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Ella Pilgrim |  | Submittals regarding TRS are to be sent directly to TT. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Ella Pilgrim (Mortenson Construction) | 1 | 2019-05-06 |  | 31 63 29-008-01 TRS - Below Grade Exterior Pile.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-06 |  | 31 63 29-008-01 TRS - Below Grade Exterior Pile.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-06 |  | 31 63 29-008-01 TRS - Below Grade Exterior Pile.pdf
31 63 29-009-00 | 31 63 29 - CAISSONS | 31 63 29-009-00 Exterior Pipe Window SD | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-18 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-05-02 | 2019-05-02 | 15 |  | Record Copies; Transfers; Submittals | 31 63 29-009-01 - 31 63 29-009-01 Exterior Pipe Window SD | 15 |  | 2019-05-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01194 | Received | For Review | 2019-04-18 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-02 |  | Email
| 02115 | Forwarded | For Review | 2019-04-18 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-04-25 |  | Info Exchange
| 01253 | Review Response | Revise and Resubmit | 2019-05-02 | Mark Membreno (Thornton Tomasetti) | SCA_CCA@populous.com |  | Plate material to be A572 Gr 50. Revise embed. lengths per drawings dated 4/22/2019. South chevron/buttress area embed lengths to be revised in future Rev 5. Date TBD | Info Exchange
| 02213 | Responded and Closed | Revise and Resubmit | 2019-05-02 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Response (Revise and Resubmit) from: Mark Membreno (Thornton Tomasetti) Remarks: Plate material to be A572 Gr 50. Revise embed. lengths per drawings dated 4/22/2019. South chevron/buttress area embed lengths to be revised in future Rev 5. Date TBD | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-17 |  | 31 63 29-009-00 Exterior Pipe Window SD.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-17 |  | 31 63 29-009-00 Exterior Pipe Window SD.pdf
| Review Response |  | Mark Membreno (Thornton Tomasetti) | 1 | 2019-04-17 |  | 31 63 29-009-00 Exterior Pipe Window SD.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-02 |  | Submittal _31 63 29-9.0_TT Review 20190502_POP.pdf
31 63 29-009-01 | 31 63 29 - CAISSONS | 31 63 29-009-01 Exterior Pipe Window SD | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-06-05 | Closed - No Action Taken | [7 empty] | 1 |  | Record Copies; Submittals | 31 63 29-009-00 - 31 63 29-009-00 Exterior Pipe Window SD | -1 | 2019-05-16 | 2019-06-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01455 | Received | No Action Required | 2019-06-05 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) |  | Received for record | Email
| 02461 | Closed | No Action Taken | 2019-06-05 | Josh Dobken (Populous)
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-06-05 |  | 31 63 29-9-1 TRS - Exterior Pipe Window Shop Drawin_TT Review.pdf
31 63 29-024-00 | 31 63 29 - CAISSONS | 31 63 29-024-00 Installer Qualifications | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-07 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-11-21 | 2019-11-20 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03108 | Received | For Review | 2019-11-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-11-21 | Submittal Number: 31 63 29-24.0 From: JOE KORCHEMNIY Final Due Date: 11/20/19 Subject: INSTALLER QUALIFICATIONS Description: DRILLED SHAFT INSTALLER QUALIFICATIONS. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 04511 | Forwarded | For Review | 2019-11-07 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-14 | Submittal Number: 31 63 29-24.0 From: JOE KORCHEMNIY Final Due Date: 11/20/19 Subject: INSTALLER QUALIFICATIONS Description: DRILLED SHAFT INSTALLER QUALIFICATIONS. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03284 | Review Response | No Action Taken or Required | 2019-11-19 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Installer Qualifications have been retained for record only. | Info Exchange
| 04734 | Responded and Closed | No Action Taken or Required | 2019-11-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: Installer Qualifications have been retained for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-06 |  | Submittal #31 63 29-24.0 Installer Qualifications.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-06 |  | Submittal #31 63 29-24.0 Installer Qualifications.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-05 02:00 |  | Submittal #31 63 29-24.0 Installer Qualifications.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-11-05 02:00 |  | Submittal #31 63 29-24.0 Installer Qualifications.pdf
31 63 29-025-00 | 31 63 29 - CAISSONS | 31 63 29-025-00 TRS - Drilled Shaft Rebar Cage | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-03 | 2019-11-20 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-11-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03254 | Received | For Review | 2019-11-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-12-03 | Submittal Number: 31 63 29-25.0 From: ELLA PILGRIM Final Due Date: 12/03/19 Subject: TRS - DRILLED SHAFT REBAR CAGE Description: Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 04696 | Forwarded | For Review | 2019-11-19 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-26 | Submittal Number: 31 63 29-25.0 From: ELLA PILGRIM Final Due Date: 12/03/19 Subject: TRS - DRILLED SHAFT REBAR CAGE Description: Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03285 | Review Response | Approved as Noted | 2019-11-20 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 04735 | Responded and Closed | Approved as Noted | 2019-11-20 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim; AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-18 |  | 31 63 29-25.0 - TRS - Drilled Shaft Rebar Cage.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-11-18 |  | 31 63 29-25.0 - TRS - Drilled Shaft Rebar Cage.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-17 02:00 |  | 31 63 29-25.0 - TRS - Drilled Shaft Rebar Cage.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-11-20 02:00 |  | 31 63 29-25.0 - TRS - Drilled Shaft Rebar Cage_TT Review_POP.pdf
31 63 29-026-00 | 31 63 29 - CAISSONS | 31 63 29-026-00 Caisson Product Data | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-11-21 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-09 | 2019-12-06 | 16 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2019-12-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03302 | Received | For Review | 2019-11-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-12-09 | Submittal Number: 31 63 29-26.0 From: JOE KORCHEMNIY Final Due Date: 12/04/19 Subject: CAISSON PRODUCT DATA Description: CAISSON PRODUCT DATA FOR CENTRALIZERS, TERMINATORS, AND COUPLERS. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 04756 | Forwarded | For Review | 2019-11-21 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-11-27 | Submittal Number: 31 63 29-26.0 From: JOE KORCHEMNIY Final Due Date: 12/04/19 Subject: CAISSON PRODUCT DATA Description: CAISSON PRODUCT DATA FOR CENTRALIZERS, TERMINATORS, AND COUPLERS. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03530 | Review Response | Approved | 2019-12-05 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | TT has no exceptions to the product data. | Info Exchange
| 05000 | Responded and Closed | Approved | 2019-12-06 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Matt Ross (Thornton Tomasetti) Remarks: TT has no exceptions to the product data. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-11-20 |  | Submittal #31 63 29-26.0 Caisson Product Data.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-11-20 |  | Submittal #31 63 29-26.0 Caisson Product Data.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-11-19 02:00 |  | Submittal #31 63 29-26.0 Caisson Product Data.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-06 02:00 |  | Submittal #31 63 29-26.0 Caisson Product Data_TT Review_POP.pdf
31 63 29-027-00 | 31 63 29 - CAISSONS | 31 63 29-027-00: Permanent Caisson Shop Drawing (BP3) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2019-12-20 | 2019-12-19 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-12-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03531 | Received | For Review | 2019-12-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-12-20 | Submittal Number: 31 63 29-27.0 From: JOE KORCHEMNIY Final Due Date: 12/19/19 Subject: PERMANENT CAISSON SHOP DRAWING (BP3) Description: PERMANENT CAISSON SHOP DRAWING FOR BP3 DRILLED SHAFTS Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05001 | Forwarded | For Review | 2019-12-06 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth K... | 2019-12-13 | Submittal Number: 31 63 29-27.0 From: JOE KORCHEMNIY Final Due Date: 12/19/19 Subject: PERMANENT CAISSON SHOP DRAWING (BP3) Description: PERMANENT CAISSON SHOP DRAWING FOR BP3 DRILLED SHAFTS Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03712 | Review Response | Approved as Noted | 2019-12-19 | Samar Kenkre (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 05242 | Responded and Closed | Approved as Noted | 2019-12-19 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Samar Kenkre (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-05 02:00 |  | Submittal #31 63 29-27.0 BP3 Caisson Shop Drawing.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-05 02:00 |  | Submittal #31 63 29-27.0 BP3 Caisson Shop Drawing.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-12-05 02:00 |  | Submittal #31 63 29-27.0 BP3 Caisson Shop Drawing.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-12-19 02:00 |  | Submittal _31 63 29-27.0 BP3 Caisson Shop Drawing_TT_POP.pdf
31 63 29-027-01 | 31 63 29 - CAISSONS | 31 63 29-027-01 Permanent Caisson Shop Drawing (BP3) REV 1 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-29 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-12 | 2020-02-07 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2020-02-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04105 | Received | For Review | 2020-01-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2020-02-12 | Submittal Number: 31 63 29-27.1 From: JOE KORCHEMNIY Final Due Date: 02/07/20 Subject: PERMANENT CAISSON SHOP DRAWING (BP3) REV 1 Description: REVISED PERMANENT CAISSON SHOP DRAWING FOR 80' CAGE BP3 DRILLED SHAFTS. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05704 | Forwarded | For Review | 2020-01-28 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-04 | Submittal Number: 31 63 29-27.1 From: JOE KORCHEMNIY Final Due Date: 02/07/20 Subject: PERMANENT CAISSON SHOP DRAWING (BP3) REV 1 Description: REVISED PERMANENT CAISSON SHOP DRAWING FOR 80' CAGE BP3 DRILLED SHAFTS. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 04266 | Review Response | Approved as Noted | 2020-02-06 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See comments on attached submittal. | Info Exchange
| 05904 | Responded and Closed | Approved as Noted | 2020-02-07 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); Ella Pilgrim; AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments on attached submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-01-28 |  | Submittal #31 63 29-27.1 BP3 Caisson Shop Drawing REV 1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-01-28 |  | Submittal #31 63 29-27.1 BP3 Caisson Shop Drawing REV 1.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-01-27 02:00 |  | Submittal #31 63 29-27.1 BP3 Caisson Shop Drawing REV 1.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-07 02:00 |  | Submittal #31 63 29-27.1 BP3 Caisson Shop Drawing REV 1_TTReview_POP.pdf
31 63 29-027-02 | 31 63 29 - CAISSONS | 31 63 29-027-02 Permanent Caisson S2 Shop Drawing (BP3) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-26 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-09 | 2020-04-02 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2020-04-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05070 | Received | For Review | 2020-03-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-09 | Submittal Number: 31 63 29-27.2 From: ELLA PILGRIM Final Due Date: 04/09/20 Subject: PERMANENT CAISSON S2 SHOP DRAWING (BP3) Description: REVISED PERMANENT CAISSON SHOP DRAWING FOR DRILLED SHAFT S2 REBAR CAGE Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 06895 | Forwarded | For Review | 2020-03-26 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-02 | Submittal Number: 31 63 29-27.2 From: ELLA PILGRIM Final Due Date: 04/09/20 Subject: PERMANENT CAISSON S2 SHOP DRAWING (BP3) Description: REVISED PERMANENT CAISSON SHOP DRAWING FOR DRILLED SHAFT S2 REBAR CAGE Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05184 | Review Response | Approved as Noted | 2020-04-02 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  |  | Info Exchange
| 07038 | Responded and Closed | Approved as Noted | 2020-04-02 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See attached response | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-26 |  | 31 63 29-27.2 Permanent Caisson S2 Shop Drawings (BP3).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-26 |  | 31 63 29-27.2 Permanent Caisson S2 Shop Drawings (BP3).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-04-02 02:00 |  | 31 63 29-27.2 Permanent Caisson S2 Shop Drawings (BP3)_TTFK.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-02 02:00 |  | 31 63 29-27.2 Permanent Caisson S2 Shop Drawings (BP3)_TTFK_POP.pdf
31 63 29-028-00 | 31 63 29 - CAISSONS | 31 63 29-028-00 Y-Column Drilled Shaft Layout (DS16-DS19) | Closed | Structural, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-11 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-03 | 2019-12-17 | 7 | General | Record Copies; Transfers; Submittals |  | 7 |  | 2019-12-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03595 | Received | For Review | 2019-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2020-01-03 | Submittal Number: 31 63 29-28.0 From: JOE KORCHEMNIY Final Due Date: 12/20/19 Subject: Y-COLUMN DRILLED SHAFT LAYOUT (DS16-DS19) Description: LAYOUT DRAWING FOR Y-COLUMN DRILLED SHAFTS DS16-DS19 LOCATED IN QUAD D FOR DESIGN TEAM APPROVAL OF SHAFT DEPTH AND LOCATION OFF GRID. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05077 | Forwarded | For Review | 2019-12-11 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-18 | Submittal Number: 31 63 29-28.0 From: JOE KORCHEMNIY Final Due Date: 12/20/19 Subject: Y-COLUMN DRILLED SHAFT LAYOUT (DS16-DS19) Description: LAYOUT DRAWING FOR Y-COLUMN DRILLED SHAFTS DS16-DS19 LOCATED IN QUAD D FOR DESIGN TEAM APPROVAL OF SHAFT DEPTH AND LOCATION OFF GRID. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03644 | Review Response | Approved as Noted | 2019-12-13 | Matt Ross (Thornton Tomasetti) | Shaina Burris (Populous) |  | Arch to review Y-Column dimensional locations from Grid. Foundations to be centered under columns. | Info Exchange
| 05163 | Forwarded | For Review | 2019-12-16 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Seth K... | 2019-12-23 | Submittal Number: 31 63 29-28.0 From: JOE KORCHEMNIY Final Due Date: 12/20/19 Subject: Y-COLUMN DRILLED SHAFT LAYOUT (DS16-DS19) Description: LAYOUT DRAWING FOR Y-COLUMN DRILLED SHAFTS DS16-DS19 LOCATED IN QUAD D FOR DESIGN TEAM APPROVAL OF SHAFT DEPTH AND LOCATION OFF GRID. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03665 | Review Response | Approved as Noted | 2019-12-17 | Franz Kogler (Thornton Tomasetti) | Josh Dobken (Populous) |  | This return supersedes the previous return. Please note that MAM still needs to complete survey at the existing chevron to determine any discrepancy between the existing position in the field and the assumed position of the chevron extension column. Subsequently, TT can actually review the chevron drilled shaft layout. | Info Exchange
| 05187 | Responded and Closed | Approved as Noted | 2019-12-17 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-10 |  | Submittal #31 63 29-28.0 Y-col Drilled Shaft Layout (DS16-DS19).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-10 |  | Submittal #31 63 29-28.0 Y-col Drilled Shaft Layout (DS16-DS19).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-10 |  | Submittal #31 63 29-28.0 Y-col Drilled Shaft Layout (DS16-DS19).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-12-16 02:00 |  | Submittal #31 63 29-28.0 Y-col DS Layout (DS16-DS20) REV1.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-12-16 02:00 |  | Submittal #31 63 29-28.0 Y-col DS Layout (DS16-DS20) REV1.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-12-17 |  | Submittal #31 63 29-28.0 Y-col DS Layout (DS16-DS20) REV1_TT_POP.pdf
31 63 29-028-01 | 31 63 29 - CAISSONS | 31 63 29-028-01 Y-Column Drilled Shaft Layout (DS1-DS15) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-26 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-16 | 2020-01-14 | 20 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2020-01-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03742 | Received | For Review | 2019-12-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2020-01-16 | Submittal Number: 31 63 29-28.1 From: JOE KORCHEMNIY Final Due Date: 01/06/20 Subject: Y-COLUMN DRILLED SHAFT LAYOUT (DS1-DS15) Description: LAYOUT DRAWING FOR Y-COLUMN DRILLED SHAFTS DS1-DS15. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05276 | Forwarded | For Review | 2019-12-26 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-01-02 | Submittal Number: 31 63 29-28.1 From: JOE KORCHEMNIY Final Due Date: 01/06/20 Subject: Y-COLUMN DRILLED SHAFT LAYOUT (DS1-DS15) Description: LAYOUT DRAWING FOR Y-COLUMN DRILLED SHAFTS DS1-DS15. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03912 | Review Response | Approved as Noted/Resubmit | 2020-01-13 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | Approved as noted. Resubmit marked caissons as noted in attachment. | Info Exchange
| 05471 | Responded and Closed | Approved as Noted/Resubmit | 2020-01-14 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-26 |  | Submittal #31 63 29-28.1 Y-col Drilled Shaft Layout (DS1-DS15).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-26 |  | Submittal #31 63 29-28.1 Y-col Drilled Shaft Layout (DS1-DS15).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2019-12-26 |  | Submittal #31 63 29-28.1 Y-col Drilled Shaft Layout (DS1-DS15).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2020-01-14 |  | Submittal #31 63 29-28.1 Y-col Drilled Shaft Layout (DS1-DS15)_TT_POP.pdf
31 63 29-028-02 | 31 63 29 - CAISSONS | 31 63 29-028-02 Y-Column Drilled Shaft Layout (East, West and North Chevrons) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-07 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-02-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04242 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-20 | Submittal Number: 31 63 29-28.2 From: ELLA PILGRIM Final Due Date: 02/18/20 Subject: Y-COLUMN DRILLED SHAFT LAYOUT (EAST, WEST AND NORTH CHEVRONS) Description: LAYOUT DRAWING FOR Y-COLUMN DRILLED SHAFTS DS1-DS15. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05872 | Forwarded | For Review | 2020-02-06 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 31 63 29-28.2 From: ELLA PILGRIM Final Due Date: 02/18/20 Subject: Y-COLUMN DRILLED SHAFT LAYOUT (EAST, WEST AND NORTH CHEVRONS) Description: LAYOUT DRAWING FOR Y-COLUMN DRILLED SHAFTS DS1-DS15. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 04267 | Review Response | Approved as Noted | 2020-02-07 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See comments on attached submittal. | Info Exchange
| 05906 | Responded and Closed | Approved as Noted | 2020-02-07 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim; AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments on attached submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | 31 63 29-28.2 Y-Column Drilled Shaft Layout (East, West and North Chevrons).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-06 |  | 31 63 29-28.2 Y-Column Drilled Shaft Layout (East, West and North Chevrons).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-02-05 02:00 |  | 31 63 29-28.2 Y-Column Drilled Shaft Layout (East, West and North Chevrons).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-07 02:00 |  | 31 63 29-28.2 Y-Column Drilled Shaft Layout (East, West and North Chevrons)_TTReview_POP.pdf
31 63 29-028-03 | 31 63 29 - CAISSONS | 31 63 29-028-03 Y-Column Drilled Shaft Layout (E5, E6, E8) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-20 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-03 | 2020-04-02 | 14 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2020-04-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04966 | Received | For Review | 2020-03-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-03 | Submittal Number: 31 63 29-28.3 From: ELLA PILGRIM Final Due Date: 04/03/20 Subject: Y-COLUMN DRILLED SHAFT LAYOUT (E5, E6, E8) Description: LAYOUT DRAWING FOR Y-COLUMN DRILLED SHAFTS AT Y COLUMNS 5, 6 AND 8. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 06771 | Forwarded | For Review | 2020-03-20 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-03-27 | Submittal Number: 31 63 29-28.3 From: ELLA PILGRIM Final Due Date: 04/03/20 Subject: Y-COLUMN DRILLED SHAFT LAYOUT (E5, E6, E8) Description: LAYOUT DRAWING FOR Y-COLUMN DRILLED SHAFTS AT Y COLUMNS 5, 6 AND 8. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05177 | Review Response | Approved as Noted | 2020-03-30 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See comments on attached submittal return. | Info Exchange
| 07021 | Responded and Closed | Approved | 2020-04-01 | Populous SCA_CCA | Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | SEE ATTACJED. | Info Exchange
| 07040 | Reopened | Additional Information | 2020-04-02 09:14 | Josh Dobken (Populous) |  |  | Reopened due to error sending in Newforma
| 07041 | Responded and Closed | Approved as Noted | 2020-04-02 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Franz Kogler (Thornton Tomasetti) Remarks: See comments on attached submittal return. Reopened (Additional Information) by: Josh Dobken Remarks: Reopened due to error sending in Newforma | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-03-20 |  | 31 63 29-28.3 Y-Column Drilled Shaft Layout (E5 E6 E8).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-03-20 |  | 31 63 29-28.3 Y-Column Drilled Shaft Layout (E5 E6 E8).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-03-20 |  | 31 63 29-28.3 Y-Column Drilled Shaft Layout (E5 E6 E8).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-01 |  | 31 63 29-28.3 Y-Column Drilled Shaft Layout (E5 E6 E8)_TT_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-01 02:00 |  | 31 63 29-28.3 Y-Column Drilled Shaft Layout (E5 E6 E8)_TT_POP.pdf
31 63 29-029-00 | 31 63 29 - CAISSONS | 31 63 29-029-00 Drilled Shaft Testing Plan | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-12-11 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-01-03 | 2019-12-13 | 3 | General | Record Copies; Transfers; Submittals |  | 3 |  | 2019-12-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03596 | Received | For Review | 2019-12-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-01-03 | Submittal Number: 31 63 29-29.0 From: ELLA PILGRIM Final Due Date: 12/24/19 Subject: DRILLED SHAFT TESTING PLAN Description: Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05078 | Forwarded | For Review | 2019-12-11 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2019-12-18 | Submittal Number: 31 63 29-29.0 From: ELLA PILGRIM Final Due Date: 12/24/19 Subject: DRILLED SHAFT TESTING PLAN Description: Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 03632 | Review Response | No Action Taken or Required | 2019-12-13 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Retained for record only. | Info Exchange
| 05134 | Responded and Closed | No Action Taken or Required | 2019-12-13 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Ella Pilgrim; AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: Retained for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-10 |  | 31 63 29-29.0 - Drilled Shaft Testing Plan.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-12-10 |  | 31 63 29-29.0 - Drilled Shaft Testing Plan.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-12-09 02:00 |  | 31 63 29-29.0 - Drilled Shaft Testing Plan.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-12-13 02:00 |  | 31 63 29-29.0 - Drilled Shaft Testing Plan_POP.pdf
31 63 29-029-01 | 31 63 29 - CAISSONS | 31 63 29-029-01 Drilled Shaft Testing Plan | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-10 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-02-24 | 2020-02-26 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-02-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04287 | Received | For Review | 2020-02-10 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-24 | Submittal Number: 31 63 29-29.1 From: ELLA PILGRIM Final Due Date: 02/24/20 Subject: DRILLED SHAFT TESTING PLAN Description: SUBMITTAL CONTAINS A LAYOUT OF THE SHAFTS REQUIRED TO BE TESTED MOVING FORWARD. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05932 | Forwarded | For Review | 2020-02-10 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-17 | Submittal Number: 31 63 29-29.1 From: ELLA PILGRIM Final Due Date: 02/24/20 Subject: DRILLED SHAFT TESTING PLAN Description: SUBMITTAL CONTAINS A LAYOUT OF THE SHAFTS REQUIRED TO BE TESTED MOVING FORWARD. Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 04524 | Review Response | No Action Taken or Required | 2020-02-26 | Matt Ross (Thornton Tomasetti) | Populous SCA_CCA |  | Retained for Record. | Info Exchange
| 06229 | Responded and Closed | No Action Taken or Required | 2020-02-26 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Matt Ross (Thornton Tomasetti) Remarks: Retained for Record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-10 |  | 31 63 29-29.1 Drilled Shaft Testing Plan.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-10 |  | 31 63 29-29.1 Drilled Shaft Testing Plan.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2020-02-09 02:00 |  | 31 63 29-29.1 Drilled Shaft Testing Plan.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-09 02:00 |  | 31 63 29-29.1 Drilled Shaft Testing Plan.pdf
31 63 29-031-00 | 31 63 29 - CAISSONS | 31 63 29-031-00 BP4 Shop Drawings | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-03 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti) |  |  |  | 2020-04-20 07:00 | 2020-04-17 | 15 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2020-04-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05208 | Received | For Review | 2020-04-03 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-04-20 07:00 | Submittal Number: 31 63 29-31.0 From: ELLA PILGRIM Final Due Date: 04/17/20 Subject: BP4 SHOP DRAWINGS Description: SUBMITTAL INCLUDES SHOP DRAWINGS FOR THE ADDED BP4 REBAR CAGES Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 07080 | Forwarded | For Review | 2020-04-03 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-04-10 | Submittal Number: 31 63 29-31.0 From: ELLA PILGRIM Final Due Date: 04/17/20 Subject: BP4 SHOP DRAWINGS Description: SUBMITTAL INCLUDES SHOP DRAWINGS FOR THE ADDED BP4 REBAR CAGES Spec Section: 31 63 29 - CAISSONS Status: OPEN | Info Exchange
| 05403 | Review Response | Approved as Noted | 2020-04-16 | Franz Kogler (Thornton Tomasetti) | Populous SCA_CCA |  | See comments on attached submittal. | Info Exchange
| 07333 | Responded and Closed | Approved as Noted | 2020-04-17 | Populous SCA_CCA | Ella Pilgrim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for review and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-03 |  | 31 63 29-31.0 - BP4 Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-03 |  | 31 63 29-31.0 - BP4 Shop Drawings.pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2020-04-03 |  | 31 63 29-31.0 - BP4 Shop Drawings.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-17 |  | 31 63 29-31.0 - BP4 Shop Drawings-MAM_TT_POP.pdf
31 66 16-001-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-001-00: Soldier Pile and Lagging Qualifications | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-03-25 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti) |  |  |  | 2019-04-08 | 2019-04-08 | 15 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2019-04-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01093 | Received | For Review | 2019-03-25 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) | 2019-04-08 |  | Info Exchange
| 01958 | Forwarded | For Review | 2019-03-25 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-04-01 |  | Info Exchange
| 01127 | Review Response | Approved | 2019-04-04 | Benjamin Harmon (Thornton Tomasetti) | Josh Dobken (Populous) |  | Approved. See attached. | Info Exchange
| 02014 | Responded and Closed | Approved as Noted | 2019-04-08 | Shaina Burris (Populous) | Joe Korchemniy (Mortenson Construction) |  | Response (Approved) from: Benjamin Harmon (Thornton Tomasetti) Remarks: Approved. See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-25 |  | Submittal #33 66 16-1.0 Tieback Installer Qualifications.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-03-25 |  | Submittal #33 66 16-1.0 Tieback Installer Qualifications.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-03-25 |  | Submittal #33 66 16-1.0 Tieback Installer Qualifications.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2019-04-04 |  | Submittal #31 66 16-1.0 Tieback Installer Qualifications - TT Review_POP.pdf
31 66 16-002-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-002-00 Shoring construction method plan | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-03-26 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti) |  |  |  | 2019-04-09 | 2019-04-05 | 11 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01098 | Received | For Review | 2019-03-26 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-09 |  | Email
| 01963 | Forwarded | For Review | 2019-03-26 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-04-02 | Sequence of installation for soldier pile, lagging and bracing are included in this package and all related equipment. See attachment. Tieback installation plan to be separate submittal. | Info Exchange
| 01129 | Review Response | Approved | 2019-04-04 | Benjamin Harmon (Thornton Tomasetti) | SCA_CCA@populous.com |  | Approved. See attached. | Info Exchange
| 02001 | Responded and Closed | Approved | 2019-04-05 | SCA_CCA@populous.com | Joe Korchemniy (Mortenson Construction) |  | Response (Approved) from: Benjamin Harmon (Thornton Tomasetti) Remarks: Approved. See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-26 |  | 31 66 16-002-0 Shoring construction method plan.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-26 |  | 31 66 16-002-0 Shoring construction method plan.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-03-26 |  | 31 66 16-002-0 Shoring construction method plan.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-05 |  | 31 66 16-002-0 Shoring construction method plan - TT review_POP.pdf
31 66 16-003-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-003-00 Mill Certificates | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-03-26 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti) |  |  |  | 2019-04-09 | 2019-04-05 | 11 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2019-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01099 | Received | For Review | 2019-03-26 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-09 |  | Email
| 01960 | Forwarded | For Review | 2019-03-26 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-04-02 | Mill Certs as received. | Info Exchange
| 01130 | Review Response | Approved | 2019-04-04 | Benjamin Harmon (Thornton Tomasetti) | SCA_CCA@populous.com |  | Approved. See attached. | Info Exchange
| 02003 | Responded and Closed | Approved as Noted | 2019-04-05 | SCA_CCA@populous.com | Joe Korchemniy (Mortenson Construction) |  | Response (Approved) from: Benjamin Harmon (Thornton Tomasetti) and Tom Usher (Populous) Remarks: Approved as Noted. See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-26 |  | 31 66 16-003-0 Mill Certificates.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-03-26 |  | 31 66 16-003-0 Mill Certificates.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-03-26 |  | 31 66 16-003-0 Mill Certificates.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-05 |  | 31 66 16-003-0 Mill Certificates - TT Review_POP.pdf
31 66 16-004-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-004-0 Tieback Installation | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-08 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, David Winter (Hart Crowser), Brice Exley (Hart Crowser), Joseph Harmon (Hart Crowser) |  |  |  | 2019-04-22 | 2019-05-02 | 25 |  | Record Copies; Transfers; Submittals |  | 28 |  | 2019-05-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01139 | Received | For Review | 2019-04-08 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-22 |  | Email
| 02012 | Forwarded | For Review | 2019-04-05 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-04-12 |  | Info Exchange
| 02201 | Forwarded | For Review | 2019-04-30 | SCA_CCA@populous.com | David Winter (Hart Crowser); Brice Exley (Hart Crowser); Joseph Harmon (Hart Crowser) | 2019-04-22 | Please confirm that installation will produce capacity recommended in Geotech Report. | Email
| 01251 | Review Response | Approved | 2019-05-02 | Benjamin Harmon (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02211 | Responded and Closed | Approved | 2019-05-02 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-05 |  | Submittal #31 66 16-4.0 Tieback Installation.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-05 |  | Submittal #31 66 16-4.0 Tieback Installation.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-05 |  | Submittal #31 66 16-4.0 Tieback Installation.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-04-05 |  | Submittal #31 66 16-4.0 Tieback Installation.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-02 |  | Submittal #31 66 16-4.0 Tieback Installation_combined_POP.pdf
31 66 16-005-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-005-00 Shoring Pile Shop Drawing (NORTH) | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-02 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti) |  |  |  | 2019-04-16 | 2019-04-05 | 4 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01118 | Received | For Review | 2019-04-02 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-16 |  | Email
| 01989 | Forwarded | For Review | 2019-04-02 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-04-09 |  | Info Exchange
| 01131 | Review Response | Approved as Noted | 2019-04-03 | Ali Helwa (Thornton Tomasetti) | SCA_CCA@populous.com |  | North wall shop-drawing submittal-review attached. | Info Exchange
| 02004 | Responded and Closed | Approved | 2019-04-05 | SCA_CCA@populous.com | Joe Korchemniy (Mortenson Construction) |  | Response (Approved as Noted) from: Ali Helwa (Thornton Tomasetti) Remarks: North wall shop-drawing submittal-review attached. Response (Approved as Noted) from: Tom Usher (Populous) Remarks: Submittal number on submittal form is incorrect. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-02 |  | Submittal #31 66 16-5.0 Shoring Pile Shop Drawing (NORTH).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-02 |  | Submittal #31 66 16-5.0 Shoring Pile Shop Drawing (NORTH).pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-04-02 |  | Submittal #31 66 16-5.0 Shoring Pile Shop Drawing (NORTH).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-05 |  | 31 66 16-5.0 Shoring Pile Shop Drawing (NORTH) - TT review_POP.pdf
31 66 16-006-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-006-00: Shoring Pile Shop Drawing (EAST) | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-03-29 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti) |  |  |  | 2019-04-12 | 2019-04-03 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2019-04-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01112 | Received | For Review | 2019-03-29 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) | 2019-04-12 | Shoring Pile shop drawing EAST elevation only. Approved based on revisions to be made by the design team as discussed in 3.27.19 M/DBM shop drawing review meeting. | Info Exchange
| 01981 | Forwarded | For Review | 2019-03-29 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-04-05 | Shoring Pile shop drawing EAST elevation only. Approved based on revisions to be made by the design team as discussed in 3.27.19 M/DBM shop drawing review meeting. | Info Exchange
| 01123 | Review Response | Approved as Noted | 2019-04-03 | Benjamin Harmon (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached for reviewed submittal. | Info Exchange
| 01995 | Responded and Closed | Approved as Noted | 2019-04-03 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Benjamin Harmon (Thornton Tomasetti) Remarks: See attached for reviewed submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-29 |  | Submittal #33 66 16-6.0 Shoring Pile Shop Drawing (EAST).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-03-29 |  | Submittal #33 66 16-6.0 Shoring Pile Shop Drawing (EAST).pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-03-29 |  | Submittal #33 66 16-6.0 Shoring Pile Shop Drawing (EAST).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-03-29 |  | Submittal #33 66 16-6.0 Shoring Pile Shop Drawing (EAST).pdf
31 66 16-006-01 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-006-1 Shoring Pile SD (EAST) | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-09 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary |  |  |  | 2019-04-23 | 2019-04-12 | 4 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-04-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01144 | Received | For Review | 2019-04-09 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-23 |  | Email
| 02023 | Forwarded | For Review | 2019-04-09 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... |  |  | Info Exchange
| 01170 | Review Response | Approved as Noted | 2019-04-11 | Ali Helwa (Thornton Tomasetti) | SCA_CCA@populous.com |  | Joe, we noticed the flange plates are not drawn for pockets B through H, however the flange plates are correctly counted for in quantities table. For the sake of completeness please draw the flange plates on hole titled as B through H. | Info Exchange
| 02063 | Responded and Closed | Approved as Noted | 2019-04-12 | SCA_CCA@populous.com | Joe Korchemniy (Mortenson Construction) |  | Response (Approved as Noted) from: Ali Helwa (Thornton Tomasetti) Remarks: Joe, we noticed the flange plates are not drawn for pockets B through H, however the flange plates are correctly counted for in quantities table. For the sake of completeness please draw the flange plates on hole titled as B through H. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-09 |  | 31 66 16-006-1 Shoring Pile SD (EAST).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-09 |  | 31 66 16-006-1 Shoring Pile SD (EAST).pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-04-09 |  | 31 66 16-006-1 Shoring Pile SD (EAST).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-12 |  | 31 66 16-006-1 Shoring Pile SD (EAST)_AFH_TT POP.pdf
31 66 16-006-02 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-006-02 Shoring Pile SD (EAST) Rev 2 | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-17 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-05-01 | 2019-05-07 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2019-05-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01191 | Received | For Review | 2019-04-17 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-01 |  | Email
| 02105 | Forwarded | For Review | 2019-04-17 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-04-24 |  | Info Exchange
| 01275 | Review Response | Approved as Noted | 2019-05-07 | Ali Helwa (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02241 | Responded and Closed | Approved as Noted | 2019-05-07 | SCA_CCA@populous.com | Joe Korchemniy (Mortenson Construction) |  |  | Info Exchange
| 02242 | Reopened | Additional Information | 2019-05-07 14:42 | Shaina Burris (Populous)
| 02243 | Responded and Closed | Approved as Noted | 2019-05-07 | SCA_CCA@populous.com | Joe Korchemniy (Mortenson Construction) |  | Joe- See additional pdf. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-17 |  | 31 66 16-006-2 Shoring Pile SD (EAST) Rev 2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-17 |  | 31 66 16-006-2 Shoring Pile SD (EAST) Rev 2.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-04-17 |  | 31 66 16-006-2 Shoring Pile SD (EAST) Rev 2.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-07 |  | 31 66 16-006-2 Shoring Pile SD (EAST) Rev 2_TT_AFH POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-07 |  | 31 66 16-006-2 Shoring Pile SD (EAST) Rev 2_TT_AFH POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-07 |  | East wall utility & TB clashes AFH 05072019.pdf
31 66 16-006-03 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-006-03 Shoring Pile Shop Drawing (EAST) Rev 3 | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-05-08 | Responded and Closed - Approved as Noted | [5 empty] | 2019-05-22 | 2019-05-08 | 1 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2019-05-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01287 | Received | For Review | 2019-05-08 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) | 2019-05-22 | REV 3 to have updated tieback declination angles in Pile Schedule (As discussed w/ TT on 05.07.19) | Info Exchange
| 02256 | Responded and Closed | Approved as Noted | 2019-05-08 | Ali Helwa (Thornton Tomasetti) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Please find attached shop drawing review in the format you requested. I incorporated the information from the east wall utility & TB clashes into the shop drawing submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Responded and Closed |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-05-08 |  | 31 66 16-006-03 Shoring Pile SD (EAST) Rev 3_TT_AFH_POP.pdf
| Responded and Closed |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-05-08 |  | East wall utility & TB clashes AFH 05072019.pdf
31 66 16-006-04 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-006-04 Shoring Pile SD (EAST) REV 4 | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-05-10 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary |  |  |  | 2019-05-24 | 2019-05-10 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01305 | Received | For Review | 2019-05-10 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-24 |  | Email
| 02282 | Forwarded | For Review | 2019-05-10 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-17 |  | Info Exchange
| 01307 | Review Response | Approved | 2019-05-10 | Ali Helwa (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02284 | Responded and Closed | Approved | 2019-05-10 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-05-10 |  | 31 66 16-006-04 Shoring Pile SD (EAST) REV 4.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-10 |  | 31 66 16-006-04 Shoring Pile SD (EAST) REV 4.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-05-10 |  | 31 66 16-006-04 Shoring Pile SD (EAST) REV 4.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-10 |  | 31 66 16-006-04 Shoring Pile SD (EAST) REV 4_TT Review_POP.pdf
31 66 16-007-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-007-00 Shoring Pile Shop Drawing (WEST) | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-03-29 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti) |  |  |  | 2019-04-12 | 2019-04-02 | 5 |  | Record Copies; Transfers; Submittals | 31 66 16-007-01 - 31 66 16-007-01 Shoring Pile Shop Drawing (WEST) | 5 |  | 2019-04-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01113 | Received | For Review | 2019-03-29 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) | 2019-04-12 | Shoring pile shop drawing for the WEST elevation only. Approved based on revisions to be made by the design team as discussed in 3.27.19 M/DBM shop drawing review meeting. Mortenson recognizes that the south half of the west wall design is still in progress due to the west temp ramp and SW snorkel. | Info Exchange
| 01982 | Forwarded | For Review | 2019-03-29 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-04-05 | Shoring pile shop drawing for the WEST elevation only. Approved based on revisions to be made by the design team as discussed in 3.27.19 M/DBM shop drawing review meeting. Mortenson recognizes that the south half of the west wall design is still in progress due to the west temp ramp and SW snorkel. | Info Exchange
| 01117 | Review Response | Approved as Noted/Resubmit | 2019-04-02 | Josh Dobken (Populous) | Josh Dobken (Populous) |  | See shoring pile schedule from TT - numbers have been revised to correctly match submittal number. | Info Exchange
| 01988 | Responded and Closed | Approved as Noted/Resubmit | 2019-04-02 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction); Greg Radom (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Josh Dobken (Populous) Remarks: See shoring pile schedule from TT - numbers have been revised to correctly match submittal number. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-29 |  | Submittal #31 66 16-7.0 Shoring Pile Shop Drawing (WEST).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-03-29 |  | Submittal #31 66 16-7.0 Shoring Pile Shop Drawing (WEST).pdf
| Review Response |  | Josh Dobken (Populous) | 1 | 2019-04-02 |  | Submittal #31 66 16-7.0 Shoring Pile Shop Drawing (WEST) TT_POP CORRECTED NUMBER.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-03-29 |  | Submittal #31 66 16-7.0 Shoring Pile Shop Drawing (WEST).pdf
31 66 16-007-01 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-007-01 Shoring Pile Shop Drawing (WEST) | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-03 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti) |  |  |  | 2019-04-17 | 2019-04-03 | 1 |  | Record Copies; Transfers; Submittals | 31 66 16-007-00 - 31 66 16-007-00 Shoring Pile Shop Drawing (WEST) | 1 | 2019-04-16 | 2019-04-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01122 | Received | For Review | 2019-04-03 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) | 2019-04-17 | REV 0 Approval applies to piles WS43 - WS88 and W93 - W110. Rev 1 is intended to include approval for the rest of North Half of West Elevation (W71A - W92). REV 0 is attached for reference. Per discussion with Matt Farber (TT) and Tom Usher (Populous) on 4/2/19, Rev 1 is intended to include the remaining piles for the North Half of the West Elevation (W71A - W92). | Info Exchange
| 01993 | Forwarded | For Review | 2019-04-03 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-04-10 | REV 0 Approval applies to piles WS43 - WS88 and W93 - W110. Rev 1 is intended to include approval for the rest of North Half of West Elevation (W71A - W92). REV 0 is attached for reference. Per discussion with Matt Farber (TT) and Tom Usher (Populous) on 4/2/19, Rev 1 is intended to include the remaining piles for the North Half of the West Elevation (W71A - W92). | Info Exchange
| 01124 | Review Response | Approved as Noted | 2019-04-03 | Benjamin Harmon (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached for the reviewed submittal. | Info Exchange
| 01996 | Responded and Closed | Approved as Noted | 2019-04-03 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Benjamin Harmon (Thornton Tomasetti) Remarks: See attached for the reviewed submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-03 |  | Submittal #31 66 16-7.0 Shoring Pile Shop Drawing (WEST) TT_POP CORRECTED NUMBER.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-04-03 |  | Submittal #31 66 16-7.0 Shoring Pile Shop Drawing (WEST) TT_POP CORRECTED NUMBER.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-04-03 |  | Submittal #31 66 16-7.0 Shoring Pile Shop Drawing (WEST) TT_POP CORRECTED NUMBER.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-04-03 |  | Submittal #31 66 16-7.0 Shoring Pile Shop Drawing (WEST) TT_POP CORRECTED NUMBER.pdf
31 66 16-007-02 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-007-02 Shoring Pile SD (WEST) | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-09 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary |  |  |  | 2019-04-23 | 2019-04-10 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-04-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01143 | Received | For Review | 2019-04-09 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-23 |  | Email
| 02024 | Forwarded | For Review | 2019-04-09 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-04-16 |  | Info Exchange
| 01160 | Review Response | Approved as Noted | 2019-04-10 | Ali Helwa (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02042 | Responded and Closed | Approved as Noted | 2019-04-10 | SCA_CCA@populous.com | Joe Korchemniy (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-09 |  | 31 66 16-007-2 Shoring Pile SD (WEST).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-09 |  | 31 66 16-007-2 Shoring Pile SD (WEST).pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-04-09 |  | 31 66 16-007-2 Shoring Pile SD (WEST).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-10 |  | 31 66 16-007-2 Shoring Pile SD (WEST)_AFH_TT POP.pdf
31 66 16-007-03 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-007-03 Shoring Pile SD (WEST) Rev 3 | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-17 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-05-01 | 2019-05-03 | 17 |  | Record Copies; Transfers; Submittals | 31 66 16-007-04 - 31 66 16-007-04 Shoring Pile SD (WEST) Rev 4 | 17 |  | 2019-05-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01192 | Received | For Review | 2019-04-17 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-01 |  | Email
| 02106 | Forwarded | For Review | 2019-04-17 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-04-24 |  | Info Exchange
| 01259 | Review Response | Approved as Noted | 2019-05-03 | Ali Helwa (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02221 | Responded and Closed | Approved as Noted/Resubmit | 2019-05-03 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | See attached partial approval, resubmit for remaining portions | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-17 |  | 31 66 16-007-03 Shoring Pile SD (WEST) Rev 3.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-17 |  | 31 66 16-007-03 Shoring Pile SD (WEST) Rev 3.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-04-17 |  | 31 66 16-007-03 Shoring Pile SD (WEST) Rev 3.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-03 |  | 31 66 16-007-03 Shoring Pile SD (WEST) Rev 3_TT Review_POP.pdf
31 66 16-007-04 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-007-04 Shoring Pile SD (WEST) Rev 4 | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-05-14 | Responded and Closed - Approved as Noted/Resubmit | [5 empty] | 2019-05-28 | 2019-05-14 | 1 |  | Record Copies; Transfers; Submittals | 31 66 16-007-03 - 31 66 16-007-03 Shoring Pile SD (WEST) Rev 3, 31 66 16-007-05 - 31 66 16-007-05 Shoring Pile SD (WEST) Rev 5 | -1 | 2019-05-17 | 2019-05-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01322 | Received | For Review | 2019-05-14 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) | 2019-05-28 | Piles W25 - W35 have added tiebacks in Rev 4. | Info Exchange
| 01323 | Review Response | Approved as Noted/Resubmit | 2019-05-14 | Ali Helwa (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 02307 | Responded and Closed | Approved as Noted/Resubmit | 2019-05-14 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Ali Helwa (Thornton Tomasetti) Remarks: Revision-4 of the west side shop drawing attached. The only edits in this revision are for piles W26 through W35, added two rows of tiebacks in the fine grained zone. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-05-14 02:00 |  | 31 66 16-007-04 Shoring Pile SD (WEST) Rev 4_TT Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-05-14 02:00 |  | 31 66 16-007-04 Shoring Pile SD (WEST) Rev 4_TT Review_POP.pdf
31 66 16-007-05 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-007-05 Shoring Pile SD (WEST) Rev 5 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-06-28 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-07-15 | 2019-07-09 | 12 |  | Record Copies; Transfers; Submittals | 31 66 16-007-04 - 31 66 16-007-04 Shoring Pile SD (WEST) Rev 4 | 12 | 2019-05-28 | 2019-07-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01651 | Received | For Review | 2019-06-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-07-15 | Submittal Number: 31 66 16-7.5 From: JOE KORCHEMNIY Final Due Date: 05/24/19 Subject: SHORING PILE SHOP DRAWING (WEST TEMP RAMP) REV 5 Description: REV 5 TO INCORPORATE WEST TEMP RAMP SHOP DRAWINGS. REDESIGN IS IN PROGRESS BY TT AS OF 5/15. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 02719 | Forwarded | For Review | 2019-06-28 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-08 | Submittal Number: 31 66 16-7.5 From: JOE KORCHEMNIY Final Due Date: 05/24/19 Subject: SHORING PILE SHOP DRAWING (WEST TEMP RAMP) REV 5 Description: REV 5 TO INCORPORATE WEST TEMP RAMP SHOP DRAWINGS. REDESIGN IS IN PROGRESS BY TT AS OF 5/15. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 01710 | Review Response | Approved as Noted | 2019-07-09 | Ali Helwa (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 02810 | Responded and Closed | Approved as Noted | 2019-07-09 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); Greg Radom (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Ali Helwa (Thornton Tomasetti) Remarks: See attached | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | Submittal #31 66 16-7.5 Shoring Pile Shop Drawing (WEST TEMP RAMP) Rev 5.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | Submittal #31 66 16-7.5 Shoring Pile Shop Drawing (WEST TEMP RAMP) Rev 5(1).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | West Temp Ramp Soldier Pile Shop Drawings.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-27 |  | West Temp Ramp Soldier Pile Shop Drawings(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | Submittal #31 66 16-7.5 Shoring Pile Shop Drawing (WEST TEMP RAMP) Rev 5.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | Submittal #31 66 16-7.5 Shoring Pile Shop Drawing (WEST TEMP RAMP) Rev 5(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | West Temp Ramp Soldier Pile Shop Drawings.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-27 |  | West Temp Ramp Soldier Pile Shop Drawings(1).pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-06-27 |  | Submittal #31 66 16-7.5 Shoring Pile Shop Drawing (WEST TEMP RAMP) Rev 5.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-06-27 |  | Submittal #31 66 16-7.5 Shoring Pile Shop Drawing (WEST TEMP RAMP) Rev 5(1).pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-06-27 |  | West Temp Ramp Soldier Pile Shop Drawings.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-06-27 |  | West Temp Ramp Soldier Pile Shop Drawings(1).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-09 |  | Submittal #31 66 16-7.5 Shoring Pile Shop Drawing (WEST TEMP RAMP) Rev 5_TT_POP.pdf
31 66 16-008-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-008-00 Shoring Pile Shop Drawing (SOUTH) | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-03-29 | Closed - Void |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti) |  |  |  | 2019-04-12 |  | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2019-04-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01114 | Received | For Review | 2019-03-29 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) | 2019-04-12 | Shoring Pile Shop Drawing for SOUTH elevation only. Approved based on revisions to be made by the design team as discussed in 3.27.19 M/DBM shop drawing review meeting. Mortenson recognizes that the south wall design is still in progress and additional coordination efforts will continue. | Info Exchange
| 01983 | Forwarded | For Review | 2019-03-29 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Meeok... | 2019-04-05 | Shoring Pile Shop Drawing for SOUTH elevation only. Approved based on revisions to be made by the design team as discussed in 3.27.19 M/DBM shop drawing review meeting. Mortenson recognizes that the south wall design is still in progress and additional coordination efforts will continue. | Info Exchange
| 02089 | Closed | Void | 2019-04-16 | Josh Dobken (Populous) |  |  | Team, The current plan is to submit Shoring shop drawings for the remainder of the elevations (South half of East and West elevation, all of South elevation) in the next few days based on CCD-001. As a heads up, I have taken the South Elevation shop drawing submittal out of the design teams court and placed it into M/DBM’s court. Thank you, Joe Korchemniy, Field Engineer Seattle Operating Group 10230 NE Points Drive, Suite 300 Kirkland, WA 98033
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-03-29 |  | Submittal #31 66 16-8.0 Shoring Pile Shop Drawing (SOUTH).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-03-29 |  | Submittal #31 66 16-8.0 Shoring Pile Shop Drawing (SOUTH).pdf
31 66 16-008-01 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-008-01 Shoring Pile SD (SOUTH) | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-18 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-05-02 | 2019-05-10 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2019-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01199 | Received | For Review | 2019-04-18 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-02 |  | Email
| 02119 | Forwarded | For Review | 2019-04-18 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-04-25 |  | Info Exchange
| 01308 | Review Response | Approved as Noted | 2019-05-10 | Ali Helwa (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02285 | Responded and Closed | Approved as Noted | 2019-05-10 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-18 |  | 31 66 16-008-01 Shoring Pile SD (SOUTH).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-18 |  | 31 66 16-008-01 Shoring Pile SD (SOUTH).pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-04-18 |  | 31 66 16-008-01 Shoring Pile SD (SOUTH).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-10 |  | 31 66 16-008-01 Shoring Pile SD (SOUTH)_TT Review_POP.pdf
31 66 16-009-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-009-00 Permanent Shoring Pile Survey Layout | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-18 | Responded and Closed - Rejected |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-05-02 | 2019-04-25 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-04-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01195 | Received | For Review | 2019-04-18 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-02 |  | Email
| 02110 | Forwarded | For Review | 2019-04-18 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-04-25 |  | Info Exchange
| 01217 | Review Response | Rejected | 2019-04-25 | Todd Spangler (Populous) | Josh Dobken (Populous); Shaina Burris (Populous) |  | See attachment for response and comments. | Mail
| 02167 | Responded and Closed | Rejected | 2019-04-25 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Response (Rejected) from: Todd Spangler (Populous) Remarks: See attachment for response and comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-18 |  | 31 66 16-009-00 Permanent Shoring Pile Survey Layout.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-18 |  | 31 66 16-009-00 Permanent Shoring Pile Survey Layout.pdf
| Review Response |  | Todd Spangler (Populous) | 1 | 2019-04-25 |  | 31 66 16-009-00 Permanent Shoring Pile Survey Layout_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-18 |  | 31 66 16-009-00 Permanent Shoring Pile Survey Layout.pdf
31 66 16-009-01 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-009-01 Permanent Shoring Pile Survey Layout | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-05-01 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-05-15 | 2019-05-10 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-05-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01250 | Received | For Review | 2019-05-01 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-15 |  | Email
| 02208 | Forwarded | For Review | 2019-05-01 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-08 |  | Info Exchange
| 01304 | Review Response | Approved as Noted | 2019-05-09 | Benjamin Harmon (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02281 | Responded and Closed | Approved as Noted/Resubmit | 2019-05-10 | SCA_CCA@populous.com | Joe Korchemniy (Mortenson Construction) |  | See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-05-01 |  | 31 66 16-009-01 Permanent Shoring Pile Survey Layout.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-01 |  | 31 66 16-009-01 Permanent Shoring Pile Survey Layout.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-05-01 |  | 31 66 16-009-01 Permanent Shoring Pile Survey Layout.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-01 |  | 31 66 16-009-01 Permanent Shoring Pile Survey Layout.pdf
31 66 16-009-02 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-009-02: Permanent Shoring Pile Survey Layout REV 2 | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-06-06 | Sent and Closed - For Construction |  | Greg Briggs (Thornton Tomasetti), Todd Spangler (Populous), Matthew Farber (Thornton Tomasetti), Josh Dobken (Populous), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-06-20 |  | 21 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-06-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01465 | Received | For Review | 2019-06-06 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-20 | Rev 2 Soldier Pile Layout incorporating west temp ramp. REV 2 includes West Temp ramp resubmittal per CCD-007 | Info Exchange
| 02472 | Forwarded | For Review | 2019-06-07 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Todd Spangler (Populous); Matthew Farber (Thornton Tomasetti); Josh Dobken (Populous); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tom... | 2019-06-14 | Rev 2 Soldier Pile Layout incorporating west temp ramp. REV 2 includes West Temp ramp resubmittal per CCD-007 | Info Exchange
| 01540 | Review Response | Approved as Noted | 2019-06-14 | Benjamin Harmon (Thornton Tomasetti) | Josh Dobken (Populous) |  | See attached for our review and response. | Info Exchange
| 01548 | Review Response | Revise and Resubmit | 2019-06-18 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Please see attached for our comments. | Info Exchange
| 02576 | Responded and Closed | Revise and Resubmit | 2019-06-18 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Response (Revise and Resubmit) from: Matt Ross (Thornton Tomasetti) Remarks: Please see attached for our comments. Please revise and resubmit once west ramp has been issued. | Info Exchange
| 02692 | Reopened | Additional Information | 2019-06-26 17:17 | Todd Spangler (Populous)
| 02693 | Sent and Closed | For Construction | 2019-06-26 | Josh Dobken (Populous) | Joe Korchemniy (Mortenson Construction); Greg Radom (Mortenson Construction) |  | here is the re-reviewed submittal for the west temp ramp. TAS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-06-07 |  | Submittal #31 66 16-9.2 Permanent Shoring Pile Survey Layout REV 2 (West Ramp).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-07 |  | Submittal #31 66 16-9.2 Permanent Shoring Pile Survey Layout REV 2 (West Ramp).pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-06-07 |  | Submittal #31 66 16-9.2 Permanent Shoring Pile Survey Layout REV 2 (West Ramp).pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2019-06-18 |  | #31 66 16-9.2 Permanent Shoring Pile Survey Layout (West Ramp)_TT_POP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-07 |  | Submittal #31 66 16-9.2 Permanent Shoring Pile Survey Layout REV 2 (West Ramp).pdf
| Sent and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | #31 66 16-9.2 Permanent Shoring Pile Survey Layout (West Ramp)_TT_POP.pdf
31 66 16-010-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-010-00 Tieback Anchor SD (Phase 1)-Above El 114)) | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-04-24 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-05-08 | 2019-05-03 | 10 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2019-05-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01215 | Received | For Review | 2019-04-24 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-08 |  | Email
| 02155 | Forwarded | For Review | 2019-04-25 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... |  |  | Info Exchange
| 01257 | Review Response | Approved as Noted/Resubmit | 2019-05-03 | Ali Helwa (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02219 | Responded and Closed | Approved as Noted/Resubmit | 2019-05-03 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | See attached partial approval, resubmit for remainder of tiebacks. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-04-24 |  | 31 66 16-010-00 Tieback Anchor SD (Phase 1).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-24 |  | 31 66 16-010-00 Tieback Anchor SD (Phase 1).pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-05-03 |  | 31 66 16-010-00 Tieback Anchor SD (Phase 1)-(Above El 114)_TT MARKUP.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-05-03 |  | 31 66 16-010-00 Tieback Anchor SD (Phase 1)-(Above El 114)_TT MARKUP_POP.pdf
31 66 16-010-01 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-010-01 Tieback Anchor SD (Phase 1) NORTH Half of East and West REV 1 | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-05-06 | Responded and Closed - Revise and Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary (Thornton Tomasetti), Mark Membreno (Thornton Tomasetti) |  |  |  | 2019-05-20 | 2019-05-06 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-05-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01266 | Received | For Review | 2019-05-06 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-20 |  | Email
| 02229 | Forwarded | For Review | 2019-05-06 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-13 |  | Info Exchange
| 02234 | Responded and Closed | Revise and Resubmit | 2019-05-06 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Sending back revise/resubmit due to contractor updated submittal information. | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-05-06 |  | 31 66 16-010-01.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-06 |  | 31 66 16-010-01.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-05-06 |  | 31 66 16-010-01_POP.pdf
31 66 16-010-02 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-010-02 Tieback Anchor SD (Phase 1) REV 2 | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-05-07 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary |  |  |  | 2019-05-21 | 2019-05-07 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-05-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01271 | Received | For Review | 2019-05-07 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-21 |  | Email
| 02235 | Forwarded | For Review | 2019-05-07 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-14 |  | Info Exchange
| 01282 | Review Response | Approved as Noted | 2019-05-07 | Ali Helwa (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02248 | Responded and Closed | Approved as Noted | 2019-05-07 | SCA_CCA@populous.com | Joe Korchemniy (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-05-07 |  | 31 66 16-010-02 Tieback Anchor SD (Phase 1) REV 2.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-07 |  | 31 66 16-010-02 Tieback Anchor SD (Phase 1) REV 2.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-05-07 |  | 31 66 16-010-02 Tieback Anchor SD (Phase 1) REV 2.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-07 |  | 31 66 16-010-02 Tieback Anchor SD (Phase 1) REV _TT Review POP.pdf
31 66 16-010-03 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-010-03 Tieback Anchor Shop Drawings (Phase 1) REV 3 | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-05-10 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Shawn Leary, Todd Spangler (Populous), Tom Usher (Populous) |  |  |  | 2019-05-24 | 2019-05-22 | 13 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2019-05-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01306 | Received | For Review | 2019-05-10 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-24 |  | Email
| 02283 | Forwarded | For Review | 2019-05-10 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali Helwa (Thornton Tomasetti); Shawn... | 2019-05-17 |  | Info Exchange
| 01333 | Review Response | Approved as Noted | 2019-05-15 | Ali Helwa (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02318 | Forwarded | For Review | 2019-05-15 | SCA_CCA@populous.com | Todd Spangler (Populous); Tom Usher (Populous) |  |  | Info Exchange
| 02357 | Responded and Closed | Approved as Noted | 2019-05-22 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Response (Approved as Noted) from: Ali Helwa (Thornton Tomasetti) Remarks: See attached submittal, approved as noted. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-05-10 |  | 31 66 16-010-03 Tieback Anchor Shop Drawings (Phase 1) REV 3.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-10 |  | 31 66 16-010-03 Tieback Anchor Shop Drawings (Phase 1) REV 3.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-05-10 |  | 31 66 16-010-03 Tieback Anchor Shop Drawings (Phase 1) REV 3.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-15 |  | 31 66 16-010-03 Tieback Anchor Shop Drawings (Phase 1) REV 4_TT.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-22 02:00 |  | 31 66 16-010-03 Tieback Anchor Shop Drawings (Phase 1) REV 3_TT_POP.pdf
31 66 16-011-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-011-00: Tangent Shaft Rebar Cage SD | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-05-23 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-06-07 | 2019-06-05 | 14 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-06-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01383 | Received | For Review | 2019-05-23 | Joe Korchemniy (Mortenson Construction) | SCA_CCA@populous.com | 2019-06-07 |  | Email
| 02379 | Forwarded | For Review | 2019-05-24 | SCA_CCA@populous.com | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fra... | 2019-05-31 |  | Info Exchange
| 01394 | Review Response | Approved as Noted | 2019-05-30 | Benjamin Harmon (Thornton Tomasetti) | SCA_CCA@populous.com |  |  | Info Exchange
| 02441 | Responded and Closed | Approved as Noted | 2019-06-05 | SCA_CCA@populous.com | Joe Korchemniy (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-05-24 |  | 31 66 16-011-00 Tangent Shaft Rebar Cage SD.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-24 |  | 31 66 16-011-00 Tangent Shaft Rebar Cage SD.pdf
| Review Response |  | Benjamin Harmon (Thornton Tomasetti) | 1 | 2019-05-24 |  | 31 66 16-011-00 Tangent Shaft Rebar Cage SD.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-06-05 |  | Submittal #31 66 16-11.0 Tangent Shaft Rebar Cage Shop Drawing.pdf
31 66 16-011-01 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-011-01: Tangent Shaft Rebar Cage Shop Drawings REV 1 | Closed | Structural | Joe Korchemniy (Mortenson Construction) | 2019-06-10 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-06-24 | 2019-06-19 | 10 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-06-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01482 | Received | For Review | 2019-06-10 | Joe Korchemniy (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-24 | REV 1 amended to reflect Tin Lok Lau comments in REV 0 and RFI 1129. | Info Exchange
| 02490 | Forwarded | For Review | 2019-06-10 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-06-17 | REV 1 amended to reflect Tin Lok Lau comments in REV 0 and RFI 1129. | Info Exchange
| 01512 | Review Response | Approved as Noted | 2019-06-12 | Ali Helwa (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 02531 | Forwarded | For Review | 2019-06-13 | Josh Dobken (Populous) | Todd Spangler (Populous) | 2019-06-20 | REV 1 amended to reflect Tin Lok Lau comments in REV 0 and RFI 1129. | Email
| 02591 | Responded and Closed | Approved as Noted | 2019-06-19 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction) |  | Response (Approved as Noted) from: Ali Helwa (Thornton Tomasetti) Remarks: Approved as noted, see attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Joe Korchemniy (Mortenson Construction) | 1 | 2019-06-10 |  | Submittal #31 66 16-11.1 Tangent Shaft Rebar Cage Shop Drawing.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-10 |  | Submittal #31 66 16-11.1 Tangent Shaft Rebar Cage Shop Drawing.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-06-10 |  | Submittal #31 66 16-11.1 Tangent Shaft Rebar Cage Shop Drawing.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-10 |  | Submittal #31 66 16-11.1 Tangent Shaft Rebar Cage Shop Drawing.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-19 |  | Submittal #31 66 16-11.1 Tangent Shaft Rebar Cage Shop Drawing - TT Review_POP.pdf
31 66 16-012-00 | 31 66 16 - SOLDIER PILE AND LAGGING | Tieback Anchor Shop Drawings (Phase 2 - Below El 114) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-06-26 | Responded and Closed - Approved as Noted/Resubmit |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-07-17 | 2019-07-15 | 20 |  | Record Copies; Transfers; Submittals | 31 66 16-012-01 - 31 66 16-012-01 Tieback Anchor Shop Drawings (Phase 2 - Below El 114) | 19 |  | 2019-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01642 | Received | For Review | 2019-06-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-07-17 | Submittal Number: 31 66 16-12.0 From: JOE KORCHEMNIY Final Due Date: 07/10/19 Subject: TIEBACK ANCHOR SHOP DRAWINGS (PHASE 2 - BELOW EL 114) Description: SEE ATTACHMENT FOR TIEBACK ANCHOR SHOP DRAWINGS PHASE 2 - BELOW EL ~ 114. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 02707 | Forwarded | For Review | 2019-06-27 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-05 | Submittal Number: 31 66 16-12.0 From: JOE KORCHEMNIY Final Due Date: 07/10/19 Subject: TIEBACK ANCHOR SHOP DRAWINGS (PHASE 2 - BELOW EL 114) Description: SEE ATTACHMENT FOR TIEBACK ANCHOR SHOP DRAWINGS PHASE 2 - BELOW EL ~ 114. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 01777 | Review Response | Approved as Noted/Resubmit | 2019-07-15 | Ali Helwa (Thornton Tomasetti) | Josh Dobken (Populous) |  | Submittal included 8 tieback levels from ground surface to elev. +62.0. Review was limited to tiebacks above elevation +90.0 for the North, East, and West walls. Please resubmit for review of the rest of the tiebacks. Please divide the shop drawing submittal and submit in order of priority. | Info Exchange
| 02900 | Responded and Closed | Approved as Noted/Resubmit | 2019-07-15 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); Greg Radom (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted/Resubmit) from: Ali Helwa (Thornton Tomasetti) Remarks: Submittal included 8 tieback levels from ground surface to elev. +62.0. Review was limited to tiebacks above elevation +90.0 for the North, East, and West walls. Please resubmit for review of the rest of the tiebacks. Please divide the shop drawing submittal and submit in order of priority. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-26 |  | Submittal #31 66 16-12.0 Phase 2 Tieback Shop Drawings (Below El ~ 114).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-06-26 |  | Submittal #31 66 16-12.0 Phase 2 Tieback Shop Drawings (Below El ~ 114)(1).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | Submittal #31 66 16-12.0 Phase 2 Tieback Shop Drawings (Below El ~ 114).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-26 |  | Submittal #31 66 16-12.0 Phase 2 Tieback Shop Drawings (Below El ~ 114)(1).pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-06-26 |  | Submittal #31 66 16-12.0 Phase 2 Tieback Shop Drawings (Below El ~ 114).pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-06-26 |  | Submittal #31 66 16-12.0 Phase 2 Tieback Shop Drawings (Below El ~ 114)(1).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-07-15 |  | Submittal _31 66 16-12.0 Phase 2 Tieback Shop Drawings (Below El ~ 114)_TT Review_POP.pdf
31 66 16-012-01 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-012-01 Tieback Anchor Shop Drawings (Phase 2 - Below El 114) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-19 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-02 | 2019-08-13 | 26 |  | Record Copies; Transfers; Submittals | 31 66 16-012-00 - Tieback Anchor Shop Drawings (Phase 2 - Below El 114) | 23 | 2019-07-29 | 2019-08-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01821 | Received | For Review | 2019-07-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-08-02 | Submittal Number: 31 66 16-12.1 From: JOE KORCHEMNIY Final Due Date: 08/09/19 Subject: TIEBACK ANCHOR SHOP DRAWINGS (PHASE 2 - BELOW EL 114) REV 1 Description: REV 0 INCLUDED APPROVAL OF TIEBACKS ABOVE EL +90' NORTH, EAST AND WEST SIDE. REV 1 TO INCLUDE APPROVAL FOR TIEBACKS BELOW EL +90. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 02946 | Forwarded | For Review | 2019-07-18 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-25 | Submittal Number: 31 66 16-12.1 From: JOE KORCHEMNIY Final Due Date: 08/09/19 Subject: TIEBACK ANCHOR SHOP DRAWINGS (PHASE 2 - BELOW EL 114) REV 1 Description: REV 0 INCLUDED APPROVAL OF TIEBACKS ABOVE EL +90' NORTH, EAST AND WEST SIDE. REV 1 TO INCLUDE APPROVAL FOR TIEBACKS BELOW EL +90. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 02027 | Review Response | Approved as Noted | 2019-08-09 | Ali Helwa (Thornton Tomasetti) | Josh Dobken (Populous) |  |  | Info Exchange
| 03217 | Responded and Closed | Approved as Noted | 2019-08-13 | Todd Spangler (Populous) | Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-18 02:00 |  | Submittal #31 66 16-12.1 Phase 2 Tieback Shop Drawings REV 1.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-07-18 02:00 |  | Submittal #31 66 16-12.1 Phase 2 Tieback Shop Drawings REV 1.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-07-18 |  | Submittal #31 66 16-12.1 Phase 2 Tieback Shop Drawings REV 1.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-13 |  | Submittal _31 66 16-12.0 Phase 2 Tieback Shop Drawings REV 2_TT Review_POP.pdf
31 66 16-012-02 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-012-02 Tieback Anchor Shop Drawings (Phase 2 - Below El 114) REV 2 | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-04 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-09-18 | 2019-09-05 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-09-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02293 | Received | For Review | 2019-09-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-09-18 | Submittal Number: 31 66 16-12.2 From: JOE KORCHEMNIY Final Due Date: 09/13/19 Subject: TIEBACK ANCHOR SHOP DRAWINGS (PHASE 2 - BELOW EL 114) REV 2 Description: COMMENTS INCLUDE DISCREPANCIES BETWEEN CONTRACT DRAWINGS UP TO CCD-025 AND REV 1 "APPROVED AS NOTED" SHOP DRAWINGS. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 03516 | Forwarded | For Review | 2019-09-04 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-11 | Submittal Number: 31 66 16-12.2 From: JOE KORCHEMNIY Final Due Date: 09/13/19 Subject: TIEBACK ANCHOR SHOP DRAWINGS (PHASE 2 - BELOW EL 114) REV 2 Description: COMMENTS INCLUDE DISCREPANCIES BETWEEN CONTRACT DRAWINGS UP TO CCD-025 AND REV 1 "APPROVED AS NOTED" SHOP DRAWINGS. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 02316 | Review Response | Approved as Noted | 2019-09-04 | Ali Helwa (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 03547 | Responded and Closed | Approved as Noted | 2019-09-05 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Ali Helwa (Thornton Tomasetti) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-04 |  | 31 66 16-12.2 Phase 2 Tieback Shop Drawings REV 2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-04 |  | 31 66 16-12.2 Phase 2 Tieback Shop Drawings REV 2.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-09-03 02:00 |  | 31 66 16-12.2 Phase 2 Tieback Shop Drawings REV 2.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-05 02:00 |  | 31 66 16-12.2 Phase 2 Tieback Shop Drawings REV 2_TT_POP.pdf
31 66 16-012-03 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-012-03 Tieback Anchor Shop Drawings (Added South Tiebacks) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-20 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-04 | 2019-09-24 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2019-09-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02460 | Received | For Review | 2019-09-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-10-04 | Submittal Number: 31 66 16-12.3 From: JOE KORCHEMNIY Final Due Date: 09/29/19 Subject: TIEBACK ANCHOR SHOP DRAWINGS (ADDED SOUTH TIEBACKS) Description: RFI 1248.1 RESULTED IN ADDED TIEBACKS BELOW EL 114' ON THE SOUTH ELEVATION. PLEASE REVIEW/APPROVE ATTACHED SHOP DRAWING FOR THE ADDED TIEBACKS AND PHASE 1 TIEBACKS THAT WERE MOVED BELOW EL 114'. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 03731 | Forwarded | For Review | 2019-09-20 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-09-27 | Submittal Number: 31 66 16-12.3 From: JOE KORCHEMNIY Final Due Date: 09/29/19 Subject: TIEBACK ANCHOR SHOP DRAWINGS (ADDED SOUTH TIEBACKS) Description: RFI 1248.1 RESULTED IN ADDED TIEBACKS BELOW EL 114' ON THE SOUTH ELEVATION. PLEASE REVIEW/APPROVE ATTACHED SHOP DRAWING FOR THE ADDED TIEBACKS AND PHASE 1 TIEBACKS THAT WERE MOVED BELOW EL 114'. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 02496 | Review Response | Approved as Noted | 2019-09-24 | Seth Knihtila (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached submittal for details | Info Exchange
| 03772 | Responded and Closed | Approved as Noted | 2019-09-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Seth Knihtila (Thornton Tomasetti) Remarks: See attached submittal for details | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-19 |  | Submittal #31 66 16-12.3 Added South Tiebacks.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-19 |  | Submittal #31 66 16-12.3 Added South Tiebacks.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-18 02:00 |  | Submittal #31 66 16-12.3 Added South Tiebacks.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-24 02:00 |  | Submittal #31 66 16-12.3 Added South Tiebacks_TT_POP.pdf
31 66 16-013-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-013-00 North Portal Soldier Pile Shop Drawing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-18 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Todd Spangler (Populous) |  |  |  | 2019-08-01 | 2019-08-07 | 21 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2019-08-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01808 | Received | For Review | 2019-07-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-08-01 | Submittal Number: 31 66 16-13.0 From: JOE KORCHEMNIY Final Due Date: 07/26/19 Subject: NORTH PORTAL SOLDIER PILE SHOP DRAWING Description: NORTH PORTAL SHOP DRAWINGS ATTACHED. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 02935 | Forwarded | For Review | 2019-07-18 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-07-25 | Submittal Number: 31 66 16-13.0 From: JOE KORCHEMNIY Final Due Date: 07/26/19 Subject: NORTH PORTAL SOLDIER PILE SHOP DRAWING Description: NORTH PORTAL SHOP DRAWINGS ATTACHED. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 01987 | Review Response | Approved as Noted | 2019-08-02 | Ali Helwa (Thornton Tomasetti) | Shaina Burris (Populous) |  | McMillen Jacobs to review piles NPSP-N1 through NPSP N6 and detail. NP12 second tieback elevation corrected from elevation +85'-6" to elevation +83'-0"; edit accounting for this elevation change for NP-12 row 2 will be accounted for in the following CCD. | Info Exchange
| 03138 | Forwarded | For Review | 2019-08-07 | Populous SCA_CCA | Todd Spangler (Populous) | 2019-08-01 | Submittal Number: 31 66 16-13.0 From: JOE KORCHEMNIY Final Due Date: 07/26/19 Subject: NORTH PORTAL SOLDIER PILE SHOP DRAWING Description: NORTH PORTAL SHOP DRAWINGS ATTACHED. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 03139 | Responded and Closed | Approved as Noted | 2019-08-07 | Todd Spangler (Populous) | Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-17 |  | Submittal #31 66 16-13.0 North Portal Soldier Pile Shop Drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-07-18 |  | Submittal #31 66 16-13.0 North Portal Soldier Pile Shop Drawings.pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-07-18 |  | Submittal #31 66 16-13.0 North Portal Soldier Pile Shop Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-07-17 |  | Submittal #31 66 16-13.0 North Portal Soldier Pile Shop Drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-07 |  | Submittal #31 66 16-13.0 North Portal Soldier Pile Shop Drawings_MK_AH_1 - POP.pdf
31 66 16-013-01 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-013-01 North Portal Soldier Pile Shop Drawing | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-07 | Responded and Closed - Approved as Noted |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2019-08-21 | 2019-08-09 | 3 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01999 | Received | For Review | 2019-08-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-08-21 | Submittal Number: 31 66 16-13.1 From: JOE KORCHEMNIY Final Due Date: 08/09/19 Subject: NORTH PORTAL SOLDIER PILE SHOP DRAWING Description: NORTH PORTAL SHOP DRAWINGS ATTACHED PER CCD-023. TEMP PILES TO BE SENT FOR REVIEW DIRECTLY TO MJA. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 03152 | Forwarded | For Review | 2019-08-08 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-08-15 | Submittal Number: 31 66 16-13.1 From: JOE KORCHEMNIY Final Due Date: 08/09/19 Subject: NORTH PORTAL SOLDIER PILE SHOP DRAWING Description: NORTH PORTAL SHOP DRAWINGS ATTACHED PER CCD-023. TEMP PILES TO BE SENT FOR REVIEW DIRECTLY TO MJA. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 02019 | Review Response | Approved as Noted | 2019-08-08 | Ali Helwa (Thornton Tomasetti) | Shaina Burris (Populous) |  | Submittal review missing MJA review. | Info Exchange
| 03177 | Responded and Closed | Approved as Noted | 2019-08-09 | Todd Spangler (Populous) | Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Submittal review missing MJA review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-07 |  | Submittal #31 66 16-13.1 North Portal Soldier Pile Shop Drawings REV 1 (CCD-023).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-07 |  | Submittal #31 66 16-13.1 North Portal Soldier Pile Shop Drawings REV 1 (CCD-023).pdf
| Review Response |  | Ali Helwa (Thornton Tomasetti) | 1 | 2019-08-07 |  | Submittal #31 66 16-13.1 North Portal Soldier Pile Shop Drawings REV 1 (CCD-023).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-08-09 |  | Submittal #31 66 16-13.1 North Portal Soldier Pile Shop Drawings REV 1_TT_POP.pdf
31 66 16-014-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-014-00 South Parcel- Shoring Submittals | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-17 | Review Response - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Ali Helwa (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-01 | 2019-09-18 | 2 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2019-09-18
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02441 | Received | For Review | 2019-09-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-10-01 | Submittal Number: 31 66 16-14.0 From: TYRONE THORNTON Final Due Date: 09/25/19 Subject: SOUTH PARCEL- SHORING SUBMITTALS Description: FOR YOUR RECORD OF ALL APPROVED SUBMITTALS AND CONSTRUCTION WORK PLASNS PERTAINING TO THE SOUTH PARCEL SHORING, REFERENCING SPEC SECTION 31 66 16. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 03702 | Forwarded | For Review | 2019-09-17 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Ali... | 2019-09-24 | Submittal Number: 31 66 16-14.0 From: TYRONE THORNTON Final Due Date: 09/25/19 Subject: SOUTH PARCEL- SHORING SUBMITTALS Description: FOR YOUR RECORD OF ALL APPROVED SUBMITTALS AND CONSTRUCTION WORK PLASNS PERTAINING TO THE SOUTH PARCEL SHORING, REFERENCING SPEC SECTION 31 66 16. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 03720 | Responded and Closed | Rejected | 2019-09-18 | Populous SCA_CCA | Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Please revise - combine the attached packages into one document. Provide the submittal stamp sheet at the front with Mortenson's stamp included. | Info Exchange
| 02485 | Review Response | No Action Taken or Required | 2019-09-20 | Seth Knihtila (Thornton Tomasetti) | Populous SCA_CCA |  | Mcmillen Jacobs Associates to review south parcel shoring package. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-00010-WeldingProcedure-Response (2).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0011-ADDMIX-Response.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0015-CWPTiebackInstall,Testing, & Lagging-Response.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0020-CWPEquipmentDesp-Response.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0021A-CWPSoliderPileInstall-Response.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0022-CWPShaftExcavation-Response.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0027A-CWPSecantPile-Response.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0001B-SoliderPileShops-Response (3).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0002B-TIEBACK&INSTALL-Response (1).pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0003-TieBackAnchorGroutResponse.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0004A-MILLCERT-Response.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0005-WelderCertDP#1-Response.pdf
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-17 |  | Subm-0009-CDFMix-Response (1).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0005-WelderCertDP#1-Response.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0009-CDFMix-Response (1).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-00010-WeldingProcedure-Response (2).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0011-ADDMIX-Response.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0015-CWPTiebackInstall,Testing, & Lagging-Response.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0020-CWPEquipmentDesp-Response.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0021A-CWPSoliderPileInstall-Response.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0022-CWPShaftExcavation-Response.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0027A-CWPSecantPile-Response.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0001B-SoliderPileShops-Response (3).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0002B-TIEBACK&INSTALL-Response (1).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0003-TieBackAnchorGroutResponse.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-09-17 |  | Subm-0004A-MILLCERT-Response.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-00010-WeldingProcedure-Response (2).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0011-ADDMIX-Response.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0015-CWPTiebackInstall,Testing, & Lagging-Response.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0020-CWPEquipmentDesp-Response.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0021A-CWPSoliderPileInstall-Response.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0022-CWPShaftExcavation-Response.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0027A-CWPSecantPile-Response.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0001B-SoliderPileShops-Response (3).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0002B-TIEBACK&INSTALL-Response (1).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0003-TieBackAnchorGroutResponse.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0004A-MILLCERT-Response.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0005-WelderCertDP#1-Response.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-09-16 02:00 |  | Subm-0009-CDFMix-Response (1).pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0005-WelderCertDP#1-Response.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0009-CDFMix-Response (1).pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-00010-WeldingProcedure-Response (2).pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0011-ADDMIX-Response.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0015-CWPTiebackInstall,Testing, & Lagging-Response.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0020-CWPEquipmentDesp-Response.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0021A-CWPSoliderPileInstall-Response.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0022-CWPShaftExcavation-Response.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0027A-CWPSecantPile-Response.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0001B-SoliderPileShops-Response (3).pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0002B-TIEBACK&INSTALL-Response (1).pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0003-TieBackAnchorGroutResponse.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-16 02:00 |  | Subm-0004A-MILLCERT-Response.pdf
31 66 16-014-01 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-014-01 South Parcel- Shoring Submittals | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-07 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Benjamin Harmon (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-21 | 2019-10-21 | 15 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2019-10-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02687 | Received | For Review | 2019-10-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (Mortenson Construction) | 2019-10-21 | Submittal Number: 31 66 16-14.1 From: TYRONE THORNTON Final Due Date: 10/21/19 Subject: SOUTH PARCEL- SHORING SUBMITTALS Description: FOR YOUR RECORD OF ALL APPROVED SUBMITTALS AND CONSTRUCTION WORK PLASNS PERTAINING TO THE SOUTH PARCEL SHORING, REFERENCING SPEC SECTION 31 66 16. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 04010 | Forwarded | For Review | 2019-10-07 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Benjamin Harmon (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Mee... | 2019-10-14 | Submittal Number: 31 66 16-14.1 From: TYRONE THORNTON Final Due Date: 10/21/19 Subject: SOUTH PARCEL- SHORING SUBMITTALS Description: FOR YOUR RECORD OF ALL APPROVED SUBMITTALS AND CONSTRUCTION WORK PLASNS PERTAINING TO THE SOUTH PARCEL SHORING, REFERENCING SPEC SECTION 31 66 16. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 02863 | Review Response | No Action Taken or Required | 2019-10-18 | Samar Kenkre (Thornton Tomasetti) | Shaina Burris (Populous) |  | We have received this submittal for record. Thanks, Samar | Info Exchange
| 04222 | Responded and Closed | No Action Taken or Required | 2019-10-21 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Samar Kenkre (Thornton Tomasetti) Remarks: We have received this submittal for record. Thanks, Samar | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-07 |  | 31 66 16-014-01 South Parcel- Shoring Submittals.pdf
| Review Response |  | Samar Kenkre (Thornton Tomasetti) | 1 | 2019-10-06 02:00 |  | 31 66 16-014-01 South Parcel- Shoring Submittals.pdf
31 66 16-015-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-015-00 KEXP Tierod Void Grout (TT ERS Action Item 0017) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-26 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Andy Tatkowski (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti) |  |  |  | 2019-10-10 | 2019-10-04 | 9 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2019-10-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02536 | Received | For Review | 2019-09-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2019-10-10 | Submittal Number: 31 66 16-15.0 From: JOE KORCHEMNIY Final Due Date: 10/10/19 Subject: KEXP TIEROD VOID GROUT (TT ERS ACTION ITEM 0017) Description: SEE ATTACHED PRODUCT DATA FOR THE GROUT USED TO FILL THE VOID AT KEXP TIEROD #8. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 03822 | Forwarded | For Review | 2019-09-26 | Josh Dobken (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Andy Tatkowski (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Fran... | 2019-10-03 | Submittal Number: 31 66 16-15.0 From: JOE KORCHEMNIY Final Due Date: 10/10/19 Subject: KEXP TIEROD VOID GROUT (TT ERS ACTION ITEM 0017) Description: SEE ATTACHED PRODUCT DATA FOR THE GROUT USED TO FILL THE VOID AT KEXP TIEROD #8. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 02633 | Review Response | Approved as Noted | 2019-10-02 | Seth Knihtila (Thornton Tomasetti) | Josh Dobken (Populous) |  | TT Approves this submittal for this instance only (tierod #8 on KEXP Building). If additional voids are encountered, non shrink grout to be used and additional material submittals may be required. | Info Exchange
| 03977 | Responded and Closed | No Action Taken or Required | 2019-10-04 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for comments. If additional voids are encountered, non shrink grout to be used and additional material submittals are required. | Info Exchange
| 03978 | Sent | For Information Only | 2019-10-04 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for comments. If additional voids are encountered, non shrink grout to be used and additional material submittals are required. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-26 02:00 |  | Submittal #31 66 16-15.0 KEXP Tieback Void Grout (TT Action Item 0017).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-26 02:00 |  | Submittal #31 66 16-15.0 KEXP Tieback Void Grout (TT Action Item 0017).pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2019-09-26 |  | Submittal #31 66 16-15.0 KEXP Tieback Void Grout (TT Action Item 0017).pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2019-10-04 |  | Submittal #31 66 16-15.0 KEXP Tieback Void Grout_TT_POP.pdf
| Sent |  | Todd Spangler (Populous) | 1 | 2019-09-26 |  | Submittal #31 66 16-15.0 KEXP Tieback Void Grout (TT Action Item 0017).pdf
31 66 16-016-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-016-00 ERS Welding Procedures (WPS) | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - No Action Taken or Required |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-07 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-02-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04243 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Joe Korchemniy (Mortenson Construction) | 2020-02-20 | Submittal Number: 31 66 16-16.0 From: JOE KORCHEMNIY Final Due Date: 02/17/20 Subject: ERS WELDING PROCEDURES (WPS) Description: SEE ATTACHED ERS WPS(S) FOR RECORD. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 05873 | Forwarded | For Review | 2020-02-06 | Shaina Burris (Populous) | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 31 66 16-16.0 From: JOE KORCHEMNIY Final Due Date: 02/17/20 Subject: ERS WELDING PROCEDURES (WPS) Description: SEE ATTACHED ERS WPS(S) FOR RECORD. Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 04269 | Review Response | No Action Taken or Required | 2020-02-07 | Seth Knihtila (Thornton Tomasetti) | Shaina Burris (Populous) |  | We have received this submittal for record. | Info Exchange
| 05908 | Responded and Closed | No Action Taken or Required | 2020-02-07 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Joe Korchemniy (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (No Action Taken or Required) from: Seth Knihtila (Thornton Tomasetti) Remarks: We have received this submittal for record. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | Submittal #31 66 16-16.0 ERS Welding Procedures (WPS).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-06 |  | Submittal #31 66 16-16.0 ERS Welding Procedures (WPS).pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2020-02-05 02:00 |  | Submittal #31 66 16-16.0 ERS Welding Procedures (WPS).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-02-05 02:00 |  | Submittal #31 66 16-16.0 ERS Welding Procedures (WPS).pdf
31 66 16-017-00 | 31 66 16 - SOLDIER PILE AND LAGGING | 31 66 16-017-00 North Portal - Secant Pile Backfill | Closed | Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-06 | Responded and Closed - Approved |  | Greg Briggs (Thornton Tomasetti), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Samar Kenkre (Thornton Tomasetti), Michael Oakland (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Seth Knihtila (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti) |  |  |  | 2020-02-20 | 2020-02-07 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2020-02-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04244 | Received | For Review | 2020-02-06 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-02-20 | Submittal Number: 31 66 16-17.0 From: TYRONE THORNTON Final Due Date: 02/12/20 Subject: NORTH PORTAL - SECANT PILE BACKFILL Description: NON-SHRINK GROUT REQUIRED PER 12/SS1-85 FOR BACKFILL AT THE SECANT PILE BREAK-OUT IN THE NORTH PORTAL Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 05874 | Forwarded | For Review | 2020-02-06 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 31 66 16-17.0 From: TYRONE THORNTON Final Due Date: 02/12/20 Subject: NORTH PORTAL - SECANT PILE BACKFILL Description: NON-SHRINK GROUT REQUIRED PER 12/SS1-85 FOR BACKFILL AT THE SECANT PILE BREAK-OUT IN THE NORTH PORTAL Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 05875 | Forwarded | For Review | 2020-02-06 | Populous SCA_CCA | Greg Briggs (Thornton Tomasetti); Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Samar Kenkre (Thornton Tomasetti); Michael Oakland (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kog... | 2020-02-13 | Submittal Number: 31 66 16-17.0 From: TYRONE THORNTON Final Due Date: 02/12/20 Subject: NORTH PORTAL - SECANT PILE BACKFILL Description: NON-SHRINK GROUT REQUIRED PER 12/SS1-85 FOR BACKFILL AT THE SECANT PILE BREAK-OUT IN THE NORTH PORTAL Spec Section: 31 66 16 - SOLDIER PILE AND LAGGING Status: OPEN | Info Exchange
| 04268 | Review Response | Approved | 2020-02-07 | Seth Knihtila (Thornton Tomasetti) | Populous SCA_CCA |  | Grout to be placed per manufacturers specifications | Info Exchange
| 05907 | Responded and Closed | Approved | 2020-02-07 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Seth Knihtila (Thornton Tomasetti) Remarks: Grout to be placed per manufacturers specifications | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-06 |  | Backfill Non-Shrink Grout Submittal.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-06 |  | Backfill Non-Shrink Grout Submittal.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-02-06 |  | Backfill Non-Shrink Grout Submittal.pdf
| Review Response |  | Seth Knihtila (Thornton Tomasetti) | 1 | 2020-02-05 02:00 |  | Backfill Non-Shrink Grout Submittal.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-02-07 02:00 |  | 31 66 16-17.0 Backfill Non-Shrink Grout Submittal_TT_POP.pdf
32 12 16-001-00 | 32 12 16 - HOT MIX ASPHALT PAVING | 32 12 16-001-00 Tack Coat | Closed | Civil | Domingo Sampayo (Mortenson Construction) | 2019-05-13 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-05-27 | 2019-05-13 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-05-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01312 | Received | For Review | 2019-05-13 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-27 |  | Email
| 02289 | Forwarded | For Review | 2019-05-13 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-05-20 |  | Info Exchange
| 01318 | Review Response | Approved | 2019-05-13 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  |  | Info Exchange
| 02303 | Responded and Closed | Approved | 2019-05-13 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-05-13 |  | 32 12 16-001-0 Tack Coat.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-13 |  | 32 12 16-001-0 Tack Coat.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-05-13 |  | 32 12 16-001-0 Tack Coat.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-13 |  | 32 12 16-001-0 Tack Coat_DCI_POP.pdf
32 12 16-002-00 | 32 12 16 - HOT MIX ASPHALT PAVING | 32 12 16-002-00 Hot Mix Asphalt Design | Closed | Civil | Domingo Sampayo (Mortenson Construction) | 2019-05-08 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-05-22 | 2019-05-08 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-05-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01278 | Received | For Review | 2019-05-08 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-22 |  | Email
| 02244 | Forwarded | For Review | 2019-05-07 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-05-14 |  | Info Exchange
| 01286 | Review Response | Approved | 2019-05-08 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  | See the attached. Acceptable | Info Exchange
| 02254 | Responded and Closed | Approved | 2019-05-08 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: See the attached. Acceptable | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-05-07 |  | 32 12 16-002-00 Hot Mix Asphalt Design.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-07 |  | 32 12 16-002-00 Hot Mix Asphalt Design.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-05-08 |  | 32 12 16-002-00 Hot Mix Asphalt Design_DCI.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-08 |  | 32 12 16-002-00 Hot Mix Asphalt Design_DCI_POP.pdf
32 12 16-005-00 | 32 12 16 - HOT MIX ASPHALT PAVING | 32 12 16-005-00 HMA Mix-1st Ave | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-13 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-04-27 | 2020-04-21 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2020-04-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05295 | Received | For Review | 2020-04-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-04-27 | Submittal Number: 32 12 16-5.0 From: JUAN BOLANOS Final Due Date: 04/20/20 Subject: HMA MIX-1ST AVE Description: THE PLAN IS TO USE THIS HMA MIX ON THE REPAIR AREAS THAT WILL BE AFFECTED BY THE NEW SIDE SEWER/STORM CONNECTION. Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 07203 | Forwarded | For Review | 2020-04-13 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-04-20 | Submittal Number: 32 12 16-5.0 From: JUAN BOLANOS Final Due Date: 04/20/20 Subject: HMA MIX-1ST AVE Description: THE PLAN IS TO USE THIS HMA MIX ON THE REPAIR AREAS THAT WILL BE AFFECTED BY THE NEW SIDE SEWER/STORM CONNECTION. Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 05451 | Review Response | Approved as Noted | 2020-04-15 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 07398 | Forwarded | For Review | 2020-04-20 | Josh Dobken (Populous) | Jarrett Grant (DCI Engineers) | 2020-04-27 | Submittal Number: 32 12 16-5.0 From: JUAN BOLANOS Final Due Date: 04/20/20 Subject: HMA MIX-1ST AVE Description: THE PLAN IS TO USE THIS HMA MIX ON THE REPAIR AREAS THAT WILL BE AFFECTED BY THE NEW SIDE SEWER/STORM CONNECTION. Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 05470 | Review Response | Approved as Noted | 2020-04-21 | Jarrett Grant (DCI Engineers) | Josh Dobken (Populous) |  | See attached. | Info Exchange
| 07423 | Responded and Closed | Approved as Noted | 2020-04-21 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-11 |  | 32 12 16-5 HMA Mix -1st Ave N.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-11 |  | 32 12 16-5 HMA Mix -1st Ave N.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-04-10 02:00 |  | 32 12 16-5 HMA Mix -1st Ave N.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-04-20 02:00 |  | 32 12 16-5 HMA Mix -1st Ave N_MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-04-21 02:00 |  | 32 12 16-5 HMA Mix -1st Ave N_DCI.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-21 02:00 |  | 32 12 16-5 HMA Mix -1st Ave N_DCI_POP.pdf
32 12 16-006-00 | 32 12 16 - HOT MIX ASPHALT PAVING | 32 12 16-006-00 Hot Mix Asphalt Paving at South Parcel and 1st Ave Garage Entry | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-14 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-01-06 | 2020-12-15 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2020-12-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10126 | Received | For Review | 2020-12-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-01-06 | Submittal Number: 32 12 16-6.0 From: CHRISTIAN GENEROSA Final Due Date: 12/28/20 Subject: HOT MIX ASPHALT PAVING AT SOUTH PARCEL AND 1ST AVE GARAGE ENTRY Description: HOT MIX ASPHALT MIX DESIGN: WSDOT SECTION 5.04 HMA CLASS 1/2- INCH ASPHALT DESIGN CONFORMING TO COS SECTION 9-03.8. HOT MIX ASPHALT TO BE UTILIZED AT THE SOUTH PARCEL PARKING AREAS AND 1ST AVE GARAGE ENTRY. THIS SUBMITTAL INCLUDES HMA MIX DESIGN AND MATERIAL CERTIFICATES. Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 13236 | Forwarded | For Review | 2020-12-14 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-12-21 | Submittal Number: 32 12 16-6.0 From: CHRISTIAN GENEROSA Final Due Date: 12/28/20 Subject: HOT MIX ASPHALT PAVING AT SOUTH PARCEL AND 1ST AVE GARAGE ENTRY Description: HOT MIX ASPHALT MIX DESIGN: WSDOT SECTION 5.04 HMA CLASS 1/2- INCH ASPHALT DESIGN CONFORMING TO COS SECTION 9-03.8. HOT MIX ASPHALT TO BE UTILIZED AT THE SOUTH PARCEL PARKING AREAS AND 1ST AVE GARAGE ENTRY. THIS SUBMITTAL INCLUDES HMA MIX DESIGN AND MATERIAL CERTIFICATES. Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 10163 | Review Response | Approved as Noted | 2020-12-14 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 13296 | Responded and Closed | Approved as Noted | 2020-12-15 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-12 |  | 2020-12-12 321216-6 HMA Mix Design_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-12 |  | 2020-12-12 321216-6 HMA Mix Design_MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-12-12 |  | 2020-12-12 321216-6 HMA Mix Design_MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-12-15 |  | 2020-12-12 321216-6 HMA Mix Design_MAM_DCI_POP.pdf
32 12 16-007-00 | 32 12 16 - HOT MIX ASPHALT PAVING | 32 12 16-007-00 Precast Wheel Stops Product Data | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-23 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-01-15 | 2021-01-04 | 13 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-01-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10340 | Received | For Review | 2020-12-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-01-15 | Submittal Number: 32 12 16-7.0 From: CHRISTIAN GENEROSA Final Due Date: 01/05/21 Subject: PRECAST WHEEL STOPS PRODUCT DATA Description: WHEEL STOPS: PRECAST, AIR-ENTRAINED CONCRETE, 2500-PSI MINIMUM COMPRESSIVE STRENGTH, 6 INCHES HIGH BY 10 INCHES WIDE BY 69.5 INCHES LONG. PROVIDE CHAMFERED CORNERS AND DRAINAGE SLOTS ON UNDERSIDE AND HOLES FOR ANCHORING INTO SUBGRADE. 1. DOWELS: GALVANIZED STEEL, 3/4-INCH DIAMETER, 18-INCH MINIMUM LENGTH THIS SCOPE IS FOR THE 1ST AVE GARAGE Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 13507 | Forwarded | For Review | 2020-12-23 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-12-30 | Submittal Number: 32 12 16-7.0 From: CHRISTIAN GENEROSA Final Due Date: 01/05/21 Subject: PRECAST WHEEL STOPS PRODUCT DATA Description: WHEEL STOPS: PRECAST, AIR-ENTRAINED CONCRETE, 2500-PSI MINIMUM COMPRESSIVE STRENGTH, 6 INCHES HIGH BY 10 INCHES WIDE BY 69.5 INCHES LONG. PROVIDE CHAMFERED CORNERS AND DRAINAGE SLOTS ON UNDERSIDE AND HOLES FOR ANCHORING INTO SUBGRADE. 1. DOWELS: GALVANIZED STEEL, 3/4-INCH DIAMETER, 18-INCH MINIMUM LENGTH THIS SCOPE IS FOR THE 1ST AVE GARAGE Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 10426 | Review Response | Approved as Noted | 2020-12-31 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached. - J. Grant | Info Exchange
| 13602 | Responded and Closed | Approved as Noted | 2021-01-04 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-22 |  | 2020-12-22 Precast Wheel Stop Product Data_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-22 |  | 2020-12-22 Precast Wheel Stop Product Data_MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-12-22 |  | 2020-12-22 Precast Wheel Stop Product Data_MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-01-04 |  | 2020-12-22 Precast Wheel Stop Product Data_DCI_POP.pdf
32 12 16-008-00 | 32 12 16 - HOT MIX ASPHALT PAVING | 32 12 16-008-00 Pavement Marking Paint Product Data | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-12-23 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-01-15 | 2021-01-04 | 13 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-01-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10341 | Received | For Review | 2020-12-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-01-15 | Submittal Number: 32 12 16-8.0 From: CHRISTIAN GENEROSA Final Due Date: 01/06/21 Subject: PAVEMENT MARKING PAINT PRODUCT DATA Description: PAVEMENT-MARKING PAINT: ALKYD-RESIN TYPE, LEAD AND CHROMATE FREE, READY MIXED, COMPLYING WITH FS TT-P-115, TYPE I OR AASHTO M 248, TYPE N, COS SECTIONS 8-22 AND 9-29.2. 1. COLOR: WHITE, OR AS INDICATED THIS SCOPE IS FOR THE NEW ARENA GARAGE, EXISTING 1ST AVE GARAGE, AND SOUTH PARCEL Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 13508 | Forwarded | For Review | 2020-12-23 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-12-30 | Submittal Number: 32 12 16-8.0 From: CHRISTIAN GENEROSA Final Due Date: 01/06/21 Subject: PAVEMENT MARKING PAINT PRODUCT DATA Description: PAVEMENT-MARKING PAINT: ALKYD-RESIN TYPE, LEAD AND CHROMATE FREE, READY MIXED, COMPLYING WITH FS TT-P-115, TYPE I OR AASHTO M 248, TYPE N, COS SECTIONS 8-22 AND 9-29.2. 1. COLOR: WHITE, OR AS INDICATED THIS SCOPE IS FOR THE NEW ARENA GARAGE, EXISTING 1ST AVE GARAGE, AND SOUTH PARCEL Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 10427 | Review Response | Approved as Noted | 2020-12-31 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 13605 | Responded and Closed | Approved as Noted | 2021-01-04 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-12-22 |  | 2020-12-22 Low VOC Acrylic Paint Striping_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-12-22 |  | 2020-12-22 Low VOC Acrylic Paint Striping_MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-12-22 |  | 2020-12-22 Low VOC Acrylic Paint Striping_MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-01-04 |  | 2020-12-22 Low VOC Acrylic Paint Striping_DCI_POP.pdf
32 12 16-009-00 | 32 12 16 - HOT MIX ASPHALT PAVING | 32 12 16-009-00 Herbicide Treatment Product Data | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-11 | Responded and Closed - Rejected |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-01-26 08:00 | 2021-01-20 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10599 | Received | For Review | 2021-01-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-01-26 08:00 | Submittal Number: 32 12 16-9.0 From: CHRISTIAN GENEROSA Final Due Date: 01/25/21 Subject: HERBICIDE TREATMENT PRODUCT DATA Description: SUBGRADE HERBICIDE TREATMENT AT THE SOUTH PARCEL PARKING AREAS AND 1ST AVE GARAGE ENTRY Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 13804 | Forwarded | For Review | 2021-01-11 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-01-18 | Submittal Number: 32 12 16-9.0 From: CHRISTIAN GENEROSA Final Due Date: 01/25/21 Subject: HERBICIDE TREATMENT PRODUCT DATA Description: SUBGRADE HERBICIDE TREATMENT AT THE SOUTH PARCEL PARKING AREAS AND 1ST AVE GARAGE ENTRY Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 10834 | Review Response | Rejected | 2021-01-20 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | As noted in 2017 COS Standard Specifications section 5-02.3(2)C, the use of soil residual herbicides is prohibited. Please ignore section 2.1A of the Civil Specification 32 12 16 Hot Mix Asphalt Paving. See attached. - J. Grant, DCI Engineers | Info Exchange
| 14083 | Responded and Closed | Rejected | 2021-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Rejected) from: Jarrett Grant (DCI Engineers) Remarks: As noted in 2017 COS Standard Specifications section 5-02.3(2)C, the use of soil residual herbicides is prohibited. Please ignore section 2.1A of the Civil Specification 32 12 16 Hot Mix Asphalt Paving. See attached. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 2021-01-09 Herbicide_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-11 |  | 2021-01-09 Herbicide_MAM Review.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-01-10 02:00 |  | 2021-01-09 Herbicide_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-20 02:00 |  | 32 12 16-009-00 2021-01-09 Herbicide_MAM Review_DCI_POP.pdf
32 12 16-010-00 | 32 12 16 - HOT MIX ASPHALT PAVING | 32 12 16-010-00 Tack Coat - South Parcel and 1st Ave Garage Entry | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-01-27 08:00 | 2021-01-20 | 9 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10631 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-01-27 08:00 | Submittal Number: 32 12 16-10.0 From: CHRISTIAN GENEROSA Final Due Date: 01/26/21 Subject: TACK COAT - SOUTH PARCEL AND 1ST AVE GARAGE ENTRY Description: Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 13839 | Forwarded | For Review | 2021-01-12 | Populous SCA_CCA | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-01-19 | Submittal Number: 32 12 16-10.0 From: CHRISTIAN GENEROSA Final Due Date: 01/26/21 Subject: TACK COAT - SOUTH PARCEL AND 1ST AVE GARAGE ENTRY Description: Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 10807 | Review Response | Approved | 2021-01-14 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 14056 | Responded and Closed | Approved | 2021-01-20 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 2021-01-11 US Oil_CSS1 Tack SPECS_MAM Review.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-01-11 |  | 2021-01-11 US Oil_CSS1 Tack SPECS_MAM Review.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-01-10 02:00 |  | 2021-01-11 US Oil_CSS1 Tack SPECS_MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-01-20 02:00 |  | 321216-010-00 2021-01-11 US Oil_CSS1 Tack SPECS_MAM Review_DCI_pop.pdf
32 12 16-011-00 | 32 12 16 - HOT MIX ASPHALT PAVING | 32 12 16-011-00 Crushed Surfacing Base Course Product Data - South Parcel and 1st Ave Garage Entry | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-01-27 08:00 | 2021-01-20 | 9 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-01-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10630 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-01-27 08:00 | Submittal Number: 32 12 16-11.0 From: CHRISTIAN GENEROSA Final Due Date: 01/26/21 Subject: CRUSHED SURFACING BASE COURSE PRODUCT DATA - SOUTH PARCEL AND 1ST AVE GARAGE ENTRY Description: PRODUCT DATA/SUMMARY REPORT FOR CRUSHED SURFACING BASE COURSE AT THE SOUTH PARCEL PARKING AREAS AND 1ST AVE GARAGE ENTRY. Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 13838 | Forwarded | For Review | 2021-01-12 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-01-19 | Submittal Number: 32 12 16-11.0 From: CHRISTIAN GENEROSA Final Due Date: 01/26/21 Subject: CRUSHED SURFACING BASE COURSE PRODUCT DATA - SOUTH PARCEL AND 1ST AVE GARAGE ENTRY Description: PRODUCT DATA/SUMMARY REPORT FOR CRUSHED SURFACING BASE COURSE AT THE SOUTH PARCEL PARKING AREAS AND 1ST AVE GARAGE ENTRY. Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 10806 | Review Response | Approved | 2021-01-14 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 14055 | Responded and Closed | Approved | 2021-01-20 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 2021-01-11 2379 CSBC 9-03.9(3) Crushed Surfacing BC_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-11 |  | 2021-01-11 2379 CSBC 9-03.9(3) Crushed Surfacing BC_MAM Review.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-01-10 02:00 |  | 2021-01-11 2379 CSBC 9-03.9(3) Crushed Surfacing BC_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-01-20 02:00 |  | 2021-01-11 2379 CSBC 9-03.9(3) Crushed Surfacing BC_MAM Review_DCI_pop.pdf
32 12 16-012-00 | 32 12 16 - HOT MIX ASPHALT PAVING | 32 12 16-012-00 Parking Stencils for New Arena Garage and 1st Ave Garage | Closed | Civil, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-02 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers), Omar Masood (DCI Engineers) |  |  |  | 2021-07-19 07:00 | 2021-07-13 | 12 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13762 | Received | For Review | 2021-07-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-19 07:00 | Submittal Number: 32 12 16-12.0 From: MICHAEL HENNESSY Final Due Date: 07/15/21 Subject: PARKING STENCILS FOR NEW ARENA GARAGE AND 1ST AVE GARAGE Description: PARKING STENCILS FOR NEW ARENA GARAGE AND 1ST AVE GARAGE Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING Status: OPEN | Info Exchange
| 17814 | Forwarded | For Review | 2021-07-01 | Populous SCA_CCA | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers); Omar Masood | 2021-07-08 | Submittal Number: 32 12 16-12.0 From: MICHAEL HENNESSY Final Due Date: 07/15/21 Subject: PARKING STENCILS FOR NEW ARENA GARAGE AND 1ST AVE GARAGEStatus: OPEN Description: PARKING STENCILS FOR NEW ARENA GARAGE AND 1ST AVE GARAGE Spec Section: 32 12 16 - HOT MIX ASPHALT PAVING | Info Exchange
| 13915 | Review Response | No Action Taken or Required | 2021-07-09 | Omar Masood (DCI Engineers) | Populous SCA_CCA |  | No Review Required from DCI. -O. Masood, DCI Engineers | Info Exchange
| 18018 | Responded and Closed | Approved | 2021-07-13 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-01 |  | 2021-07-01 321216-0012-00 Parking Stencils for New Arena Garage and 1st Ave Garage.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-01 |  | 2021-07-01 321216-0012-00 Parking Stencils for New Arena Garage and 1st Ave Garage.pdf
| Review Response |  | Omar Masood (DCI Engineers) | 1 | 2021-06-30 02:00 |  | 2021-07-01 321216-0012-00 Parking Stencils for New Arena Garage and 1st Ave Garage.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-13 02:00 |  | 32 12 16-012-00 Parking Stencils for New Arena Garage and 1st Ave Garage_pop.pdf
32 12 43-001-00 | 32 12 43 - FLEXIBLE POROUS PAVEMENT | 32 12 43-001-00 FLEXIBLE POROUS PAVEMENT - Product Data | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-08 | Responded and Closed - Approved as Noted/Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-22 | 2021-02-24 | 17 |  | Record Copies; Transfers; Submittals | 32 12 43-001-01 - 32 12 43-001-01 FLEXIBLE POROUS PAVEMENT - Product Data | 17 |  | 2021-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11271 | Received | For Review | 2021-02-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-02-22 | Submittal Number: 32 12 43-1.0 From: CHRISTIAN GENEROSA Final Due Date: 02/22/21 Subject: FLEXIBLE POROUS PAVEMENT - PRODUCT DATA Description: PRODUCT DATA : MANUFACTURER'S DATA SHEETS ON EACH PRODUCT TO BE USED, INCLUDING: 1. PREPARATION INSTRUCTIONS AND RECOMMENDATIONS. 2. STORAGE AND HANDLING REQUIREMENTS AND RECOMMENDATIONS. 3. INSTALLATION METHODS. Spec Section: 32 12 43 - FLEXIBLE POROUS PAVING Status: OPEN | Info Exchange
| 14603 | Forwarded | For Review | 2021-02-08 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-15 | Submittal Number: 32 12 43-1.0 From: CHRISTIAN GENEROSA Final Due Date: 02/22/21 Subject: FLEXIBLE POROUS PAVEMENT - PRODUCT DATAStatus: OPEN Description: PRODUCT DATA : MANUFACTURER'S DATA SHEETS ON EACH PRODUCT TO BE USED, INCLUDING: 1. PREPARATION INSTRUCTIONS AND RECOMMENDATIONS. 2. STORAGE AND HANDLING REQUIREMENTS AND RECOMMENDATIONS. 3. INSTALLATION METHODS. Spec Section: 32 12 43 - FLEXIBLE POROUS PAVING | Info Exchange
| 11639 | Review Response | Approved as Noted/Resubmit | 2021-02-24 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | Approved for all but edging. Attached edging product required. | Info Exchange
| 15086 | Responded and Closed | Approved as Noted/Resubmit | 2021-02-24 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted/Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Approved for all but edging. Attached edging product required. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-08 |  | 2020-02-08 321243-0001-00 Flexible Porous Pavement PD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-02-08 |  | 2020-02-08 321243-0001-00 Flexible Porous Pavement PD_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-02-07 02:00 |  | 2020-02-08 321243-0001-00 Flexible Porous Pavement PD_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-02-24 02:00 |  | 321243-001-00 Flexible Porous Pavement PD_MAM - SWIFT_POP.pdf
32 12 43-001-01 | 32 12 43 - FLEXIBLE POROUS PAVEMENT | 32 12 43-001-01 FLEXIBLE POROUS PAVEMENT - Product Data | Closed | Civil, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-01 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Damon Smith (DCI Engineers), Gareth Loveridge (Swift and Company Landscape Arch), Jarrett Grant (DCI Engineers) |  |  |  | 2021-03-15 | 2021-03-03 | 3 |  | Record Copies; Transfers; Submittals | 32 12 43-001-00 - 32 12 43-001-00 FLEXIBLE POROUS PAVEMENT - Product Data | 2 | 2021-03-10 | 2021-03-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11725 | Received | For Review | 2021-03-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-15 | Submittal Number: 32 12 43-1.1 From: CHRISTIAN GENEROSA Final Due Date: 03/15/21 Subject: FLEXIBLE POROUS PAVEMENT - PRODUCT DATA Description: PRODUCT DATA : MANUFACTURER'S DATA SHEETS ON EACH PRODUCT TO BE USED, INCLUDING: 1. PREPARATION INSTRUCTIONS AND RECOMMENDATIONS. 2. STORAGE AND HANDLING REQUIREMENTS AND RECOMMENDATIONS. 3. INSTALLATION METHODS. Spec Section: 32 12 43 - FLEXIBLE POROUS PAVING Status: OPEN | Info Exchange
| 15193 | Forwarded | For Review | 2021-03-01 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Damon Smith (DCI Engineers); Gareth Loveridge (Swift and Company Landscape Arch); Jarrett Grant (DCI Engineers) | 2021-03-08 | Submittal Number: 32 12 43-1.1 From: CHRISTIAN GENEROSA Final Due Date: 03/15/21 Subject: FLEXIBLE POROUS PAVEMENT - PRODUCT DATA Description: PRODUCT DATA : MANUFACTURER'S DATA SHEETS ON EACH PRODUCT TO BE USED, INCLUDING: 1. PREPARATION INSTRUCTIONS AND RECOMMENDATIONS. 2. STORAGE AND HANDLING REQUIREMENTS AND RECOMMENDATIONS. 3. INSTALLATION METHODS. Spec Section: 32 12 43 - FLEXIBLE POROUS PAVING Status: OPEN | Info Exchange
| 11772 | Review Response | Approved | 2021-03-02 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | Updated submittal for corrected edging product. | Info Exchange
| 15253 | Responded and Closed | Approved | 2021-03-03 | Populous SCA_CCA | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Updated submittal for corrected edging product. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-01 02:00 |  | 2020-02-08 321243-0001-01 Flexible Porous Pavement PD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-01 02:00 |  | 32 12 43-001-01 Flexible Porous Pavement PD_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-01 02:00 |  | 32 12 43-001-01 Flexible Porous Pavement PD_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-03 02:00 |  | 32 12 43-001-01 Flexible Porous Pavement PD_MAM - SWIFT_POP.pdf
32 12 43-003-00 | 32 12 43 - FLEXIBLE POROUS PAVEMENT | 32 12 43-003-00 FLEXIBLE POROUS PAVEMENT - LEED Data | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-02 | Responded and Closed - Revise and Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-16 | 2021-03-09 | 8 |  | Record Copies; Transfers; Submittals | 32 12 43-003-00-01 - 32 12 43-003-00 FLEXIBLE POROUS PAVEMENT - LEED Data | 3 |  | 2021-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11741 | Received | For Review | 2021-03-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-16 | Submittal Number: 32 12 43-3.0 From: CHRISTIAN GENEROSA Final Due Date: 03/15/21 Subject: FLEXIBLE POROUS PAVEMENT - LEED DATA Description: LEED SUBMITTALS : PROVIDE LEED V4.0 DOCUMENTATION OF HOW THE REQUIREMENTS OF CREDIT WILL BE MET: 1. LIST OF PROPOSED MATERIALS WITH RECYCLED CONTENT. INDICATE POST-CONSUMER RECYCLED CONTENT AND PRE-CONSUMER RECYCLED CONTENT FOR EACH PRODUCT HAVING RECYCLED CONTENT. 2. PRODUCT DATA AND CERTIFICATION LETTER INDICATING PERCENTAGES BY WEIGHT OF POST-CONSUMER AND PRE-CONSUMER RECYCLED CONTENT FOR PRODUCTS HAVING RECYCLED CONTENT. 3. INDOOR ENVIRONMENTAL QUALITY, PROVIDE GREEN THIRD-PARTY CERTIFICATION OR EVALUATION US GREEN BUILDING COUNCIL (USGBC). Spec Section: 32 12 43 - FLEXIBLE POROUS PAVING Status: OPEN | Info Exchange
| 15213 | Forwarded | For Review | 2021-03-02 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-09 | Submittal Number: 32 12 43-3.0 From: CHRISTIAN GENEROSA Final Due Date: 03/15/21 Subject: FLEXIBLE POROUS PAVEMENT - LEED DATA Description: LEED SUBMITTALS : PROVIDE LEED V4.0 DOCUMENTATION OF HOW THE REQUIREMENTS OF CREDIT WILL BE MET: 1. LIST OF PROPOSED MATERIALS WITH RECYCLED CONTENT. INDICATE POST-CONSUMER RECYCLED CONTENT AND PRE-CONSUMER RECYCLED CONTENT FOR EACH PRODUCT HAVING RECYCLED CONTENT. 2. PRODUCT DATA AND CERTIFICATION LETTER INDICATING PERCENTAGES BY WEIGHT OF POST-CONSUMER AND PRE-CONSUMER RECYCLED CONTENT FOR PRODUCTS HAVING RECYCLED CONTENT. 3. INDOOR ENVIRONMENTAL QUALITY, PROVIDE GREEN THIRD-PARTY CERTIFICATION OR EVALUATION US GREEN BUILDING COUNCIL (USGBC). Spec Section: 32 12 43 - FLEXIBLE POROUS PAVING Status: OPEN | Info Exchange
| 11863 | Review Response | Revise and Resubmit | 2021-03-04 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 15382 | Responded and Closed | Revise and Resubmit | 2021-03-09 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Revise and Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-01 |  | 2021-03-01 321243-0003-00 Flexible Porous Pavement LEED_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-01 |  | 2021-03-01 321243-0003-00 Flexible Porous Pavement LEED_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-01 |  | 2021-03-01 321243-0003-00 Flexible Porous Pavement LEED_MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-03-09 |  | 2021-03-01 321243-0003-00 Flexible Porous Pavement LEED-SWIFT_POP.pdf
32 12 43-003-00-01 | 32 12 43 - FLEXIBLE POROUS PAVEMENT | 32 12 43-003-00 FLEXIBLE POROUS PAVEMENT - LEED Data | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 32 12 43-003-00 - 32 12 43-003-00 FLEXIBLE POROUS PAVEMENT - LEED Data | -1 | 2021-04-05
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-09 |  | 2021-03-01 321243-0003-00 Flexible Porous Pavement LEED-SWIFT_POP.pdf
32 13 13-009-00 | 32 13 13 - CONCRETE PAVING | 32 13 13-009-00 Site Paving Mix Designs | Closed | Civil, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-12 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers), Matthew Farber (Thornton Tomasetti), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-05-26 | 2021-06-03 | 23 |  | Record Copies; Transfers; Submittals |  | 23 |  | 2021-06-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13064 | Received | For Review | 2021-05-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-05-26 | Submittal Number: 32 13 13-9.0 From: CHRISTIAN ALBERS Final Due Date: 05/25/21 Subject: SITE PAVING MIX DESIGNS Description: SEE ATTACHED SITE PAVING MIX DESIGNS FOR FLATWORK, THIS INCLUDES MIX DESIGN PROPOSAL FOR SITE SIGNAGE THICKENED FOOTING LOCATIONS. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 16900 | Forwarded | For Review | 2021-05-12 | Christian Albers (Mortenson Construction) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-05-19 | Submittal Number: 32 13 13-9.0 From: CHRISTIAN ALBERS Final Due Date: 05/25/21 Subject: SITE PAVING MIX DESIGNS Description: SEE ATTACHED SITE PAVING MIX DESIGNS FOR FLATWORK, THIS INCLUDES MIX DESIGN PROPOSAL FOR SITE SIGNAGE THICKENED FOOTING LOCATIONS. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 16933 | Forwarded | For Review | 2021-05-13 | Christian Albers (Mortenson Construction) | Matthew Farber (Thornton Tomasetti); Matt Ross (Thornton Tomasetti) | 2021-05-20 | Submittal Number: 32 13 13-9.0 From: CHRISTIAN ALBERS Final Due Date: 05/25/21 Subject: SITE PAVING MIX DESIGNS Description: SEE ATTACHED SITE PAVING MIX DESIGNS FOR FLATWORK, THIS INCLUDES MIX DESIGN PROPOSAL FOR SITE SIGNAGE THICKENED FOOTING LOCATIONS. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 13218 | Review Response | Approved as Noted | 2021-05-20 | Jarrett Grant (DCI Engineers) | Tom Usher (Populous); Damon Smith (DCI Engineers); Josh Dobken (Populous) |  | See attached submittal review. - J. Grant, DCI Engineers | Info Exchange
| 17108 | Responded and Closed | Approved as Noted | 2021-05-20 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached submittal review. - J. Grant, DCI Engineers | Info Exchange
| 13382 | Review Response | Approved as Noted | 2021-06-03 | Matt Ross (Thornton Tomasetti) | Christian Albers (Mortenson Construction) |  | See attached for TT comments. | Info Exchange
| 17310 | Reopened | Additional Information | 2021-06-03 13:54 | Josh Dobken (Populous) |  |  | Returned in error without response from TT.
| 17311 | Responded and Closed | Approved as Noted | 2021-06-03 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached submittal review. - J. Grant, DCI Engineers Response (Approved as Noted) from: Matt Ross (Thornton Tomasetti) Remarks: See attached for TT comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | 32 13 13 - 09 - Site Paving Mix Designs.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-11 |  | 32 13 13 - 09 - Site Paving Mix Designs.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-10 02:00 |  | 32 13 13 - 09 - Site Paving Mix Designs.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-05-10 02:00 |  | 32 13 13 - 09 - Site Paving Mix Designs.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-20 02:00 |  | 32 13 13 - 09 - Site Paving Mix Designs_DCI_POP.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-05-10 02:00 |  | 32 13 13 - 09 - Site Paving Mix Designs.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-03 02:00 |  | 32 13 13 - 09 - Site Paving Mix Designs_TT_DCI_POPv2.pdf
32 13 13-010-00 | 32 13 13 - CONCRETE PAVING | 32 13 13-010-00 Joint Sealant Product Data | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-27 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-06-11 07:00 | 2021-06-07 | 12 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13296 | Received | For Review | 2021-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-06-11 07:00 | Submittal Number: 32 13 13-10.0 From: CHRISTIAN ALBERS Final Due Date: 06/08/21 Subject: JOINT SEALANT PRODUCT DATA Description: SEE ATTACHED PRODUCT DATA AND COLOR SELECTION FOR JOINT SEALANT TO BE USED ON SITEWORK. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 17196 | Forwarded | For Review | 2021-05-27 | Christian Albers (Mortenson Construction) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-06-03 | Submittal Number: 32 13 13-10.0 From: CHRISTIAN ALBERS Final Due Date: 06/08/21 Subject: JOINT SEALANT PRODUCT DATA Description: SEE ATTACHED PRODUCT DATA AND COLOR SELECTION FOR JOINT SEALANT TO BE USED ON SITEWORK. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 13442 | Review Response | Approved as Noted | 2021-06-02 | Jarrett Grant (DCI Engineers) | Christian Albers (Mortenson Construction) |  | See attached review. -J. Grant, DCI Engineers | Info Exchange
| 17381 | Responded and Closed | Approved as Noted | 2021-06-07 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached review. -J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-26 |  | 32 13 13 - 10 - Joint Sealant Product Data.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-26 |  | 32 13 13 - 10 - Joint Sealant Product Data.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-05-25 02:00 |  | 32 13 13 - 10 - Joint Sealant Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-07 02:00 |  | 32 13 13 - 10 - Joint Sealant Product Data_DCI_POP.pdf
32 13 13-011-00 | 32 13 13 - CONCRETE PAVING | 32 13 13-011-00 Fiber Expansion Board Product Data | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-27 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-06-11 07:00 | 2021-06-07 | 12 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13297 | Received | For Review | 2021-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-06-11 07:00 | Submittal Number: 32 13 13-11.0 From: CHRISTIAN ALBERS Final Due Date: 06/09/21 Subject: FIBER EXPANSION BOARD PRODUCT DATA Description: SEE ATTACHED PRODUCT DATA FOR SITEWORK EXPANSION BOARD MATERIAL. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 17197 | Forwarded | For Review | 2021-05-27 | Christian Albers (Mortenson Construction) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-06-03 | Submittal Number: 32 13 13-11.0 From: CHRISTIAN ALBERS Final Due Date: 06/09/21 Subject: FIBER EXPANSION BOARD PRODUCT DATA Description: SEE ATTACHED PRODUCT DATA FOR SITEWORK EXPANSION BOARD MATERIAL. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 13443 | Review Response | Approved as Noted | 2021-06-02 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached review. - J. Grant, DCI Engineers | Info Exchange
| 17382 | Responded and Closed | Approved as Noted | 2021-06-07 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached review. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-26 |  | 32 13 13 - 11 - Fiber Expansion Board Product Data.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-26 |  | 32 13 13 - 11 - Fiber Expansion Board Product Data.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-05-25 02:00 |  | 32 13 13 - 11 - Fiber Expansion Board Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-07 02:00 |  | 32 13 13 - 11 - Fiber Expansion Board Product Data_DCI_POP.pdf
32 13 13-012-00 | 32 13 13 - CONCRETE PAVING | 32 13 13-012-00 Area 6 North Courtyard Flatwork Layout Drawings | Closed | Civil, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-27 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Tom Usher (Populous), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-06-11 07:00 | 2021-06-08 | 13 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-06-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13298 | Received | For Review | 2021-05-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-06-11 07:00 | Submittal Number: 32 13 13-12.0 From: CHRISTIAN ALBERS Final Due Date: 06/09/21 Subject: AREA 6 NORTH COURTYARD FLATWORK LAYOUT DRAWINGS Description: SEE ATTACHED AREA 6 NORTH COURTYARD FLATWORK LAYOUT AND SEQUENCE DRAWINGS FOR REVIEW. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 17198 | Forwarded | For Review | 2021-05-27 | Christian Albers (Mortenson Construction) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-06-03 | Submittal Number: 32 13 13-12.0 From: CHRISTIAN ALBERS Final Due Date: 06/09/21 Subject: AREA 6 NORTH COURTYARD FLATWORK LAYOUT DRAWINGS Description: SEE ATTACHED AREA 6 NORTH COURTYARD FLATWORK LAYOUT AND SEQUENCE DRAWINGS FOR REVIEW. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 17202 | Forwarded | For Review | 2021-05-27 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Tom Usher (Populous); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-03 | Submittal Number: 32 13 13-12.0 From: CHRISTIAN ALBERS Final Due Date: 06/09/21 Subject: AREA 6 NORTH COURTYARD FLATWORK LAYOUT DRAWINGS Description: SEE ATTACHED AREA 6 NORTH COURTYARD FLATWORK LAYOUT AND SEQUENCE DRAWINGS FOR REVIEW. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 17226 | Forwarded | For Review | 2021-06-01 | Christian Albers (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-08 | Submittal Number: 32 13 13-12.0 From: CHRISTIAN ALBERS Final Due Date: 06/09/21 Subject: AREA 6 NORTH COURTYARD FLATWORK LAYOUT DRAWINGS Description: SEE ATTACHED AREA 6 NORTH COURTYARD FLATWORK LAYOUT AND SEQUENCE DRAWINGS FOR REVIEW. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 13381 | Review Response | Approved as Noted | 2021-06-01 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Christian Albers (Mortenson Construction) |  | See comments in attached pdf. Per converstaion with Christain Albers, zip-strips to be used at "wet-set" EJs. | Info Exchange
| 13450 | Review Response | Approved as Noted | 2021-06-07 | Jarrett Grant (DCI Engineers) | Christian Albers (Mortenson Construction) |  | See attached submittal review. - J. Grant, DCI Engineers | Info Exchange
| 17387 | Responded and Closed | Approved as Noted | 2021-06-07 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See comments in attached pdf. Per converstaion with Christain Albers, zip-strips to be used at "wet-set" EJs. Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached submittal review. - J. Grant, DCI Engineers | Info Exchange
| 17394 | Reopened | Additional Information | 2021-06-08 08:43 | Josh Dobken (Populous) |  |  | Reopened for additional comments.
| 17395 | Responded and Closed | Approved as Noted | 2021-06-08 | Populous SCA_CCA | Christian Albers (Mortenson Construction) |  | Responded and Closed (Approved as Noted) to: Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) Remarks: Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See comments in attached pdf. Per converstaion with Christain Albers, zip-strips to be used at "wet-set" EJs. Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached submittal review. - J. Grant, DCI Engineers Reopened (Additional Information) by: Josh Dobken Remarks: Reopened for additional comments. | Email
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-26 |  | 32 13 13 - 12 - Area 6 North Courtyard Flatwork Layout Drawings.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-26 |  | 32 13 13 - 12 - Area 6 North Courtyard Flatwork Layout Drawings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-25 02:00 |  | 32 13 13 - 12 - Area 6 North Courtyard Flatwork Layout Drawings.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-26 |  | 32 13 13 - 12 - Area 6 North Courtyard Flatwork Layout Drawings.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-26 |  | 32 13 13 - 12 - Area 6 North Courtyard Flatwork Layout Drawings.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-05-25 02:00 |  | 32 13 13 - 12 - Area 6 North Courtyard Flatwork Layout Drawings.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-07 02:00 |  | 32 13 13 - 12 - Area 6 North Courtyard Flatwork Layout Drawings - SWIFT_DCI_POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-08 02:00 |  | 32 13 13 - 12 - Area 6 North Courtyard Flatwork Layout Drawings - SWIFT_DCI_POPv2.pdf
32 13 13-013-00 | 32 13 13 - CONCRETE PAVING | 32 13 13-013-00 Area 7 Flatwork Layout Drawings | Closed | Landscape, Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-28 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-06-14 07:00 | 2021-06-14 | 18 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-06-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13325 | Received | For Review | 2021-05-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-06-14 07:00 | Submittal Number: 32 13 13-13.0 From: CHRISTIAN ALBERS Final Due Date: 06/11/21 Subject: AREA 7 FLATWORK LAYOUT DRAWINGS Description: SEE ATTACHED AREA 7 FLATWORK LAYOUT AND SEQUENCE DRAWINGS FOR REVIEW. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 17238 | Forwarded | For Review | 2021-06-01 | Christian Albers (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-08 | Submittal Number: 32 13 13-13.0 From: CHRISTIAN ALBERS Final Due Date: 06/11/21 Subject: AREA 7 FLATWORK LAYOUT DRAWINGS Description: SEE ATTACHED AREA 7 FLATWORK LAYOUT AND SEQUENCE DRAWINGS FOR REVIEW. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 17277 | Forwarded | For Review | 2021-06-01 | Josh Dobken (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-06-08 | Submittal Number: 32 13 13-13.0 From: CHRISTIAN ALBERS Final Due Date: 06/11/21 Subject: AREA 7 FLATWORK LAYOUT DRAWINGS Description: SEE ATTACHED AREA 7 FLATWORK LAYOUT AND SEQUENCE DRAWINGS FOR REVIEW. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 13518 | Review Response | Approved as Noted | 2021-06-09 | Jarrett Grant (DCI Engineers) | Josh Dobken (Populous) |  | See attached review. - J. Grant, DCI Engineers | Info Exchange
| 13524 | Review Response | Approved as Noted | 2021-06-14 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | Josh, See attached for Swift's comments. Please add consolidate with the Populous comments as we discussed on the doc control call today. thanks, Rhys | Info Exchange
| 17496 | Responded and Closed | Approved as Noted | 2021-06-14 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached review. - J. Grant, DCI Engineers Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See attached for Swift's comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-28 |  | 32 13 13 - 13 - Area 7 Flatwork Layout Drawings.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-28 |  | 32 13 13 - 13 - Area 7 Flatwork Layout Drawings.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-05-27 02:00 |  | 32 13 13 - 13 - Area 7 Flatwork Layout Drawings.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-05-27 |  | 32 13 13 - 13 - Area 7 Flatwork Layout Drawings.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-27 02:00 |  | 32 13 13 - 13 - Area 7 Flatwork Layout Drawings.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-14 02:00 |  | 32 13 13 - 13 - Area 7 Flatwork Layout Drawings_ALL COMBINED.pdf
32 13 13-014-00 | 32 13 13 - CONCRETE PAVING | 32 13 13-014-00 Sitework Flatwork Concrete Water Cure | Closed | Civil, Structural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-23 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Damon Smith (DCI Engineers), Gareth Loveridge (Swift and Company Landscape Arch), Jarrett Grant (DCI Engineers), Omar Masood (DCI Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-07 | 2021-06-28 | 6 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-06-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13620 | Received | For Review | 2021-06-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-07-07 | Submittal Number: 32 13 13-14.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: SITEWORK FLATWORK CONCRETE WATER CURE Description: PER COORDINATION WITH SWIFT PLEASE CONFIRM THIS WATER CURE TYPE IS AN ACCEPTABLE PRODUCT TO CURE THE SITEWORK SLABS. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 17635 | Forwarded | For Review | 2021-06-23 | Christian Albers (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Damon Smith (DCI Engineers); Gareth Loveridge (Swift and Company Landscape Arch); Jarrett Grant (DCI Engineers); Omar Masood | 2021-06-30 | Submittal Number: 32 13 13-14.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: SITEWORK FLATWORK CONCRETE WATER CURE Description: PER COORDINATION WITH SWIFT PLEASE CONFIRM THIS WATER CURE TYPE IS AN ACCEPTABLE PRODUCT TO CURE THE SITEWORK SLABS. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 17654 | Forwarded | For Review | 2021-06-24 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Ross Cussen | 2021-07-01 | Submittal Number: 32 13 13-14.0 From: CHRISTIAN ALBERS Final Due Date: 07/06/21 Subject: SITEWORK FLATWORK CONCRETE WATER CURE Description: PER COORDINATION WITH SWIFT PLEASE CONFIRM THIS WATER CURE TYPE IS AN ACCEPTABLE PRODUCT TO CURE THE SITEWORK SLABS. Spec Section: 32 13 13 - PEDESTRIAN CONCRETE PAVING Status: OPEN | Info Exchange
| 13694 | Review Response | Approved | 2021-06-25 | Omar Masood | Tom Usher (Populous); Josh Dobken (Populous) |  | See DCI response attached. DCI takes no exception to the submittal as shown on the specification provided. | Info Exchange
| 17731 | Responded and Closed | Approved | 2021-06-28 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved) from: Omar Masood Remarks: See DCI response attached. DCI takes no exception to the submittal as shown on the specification provided. | Info Exchange
| 18120 | Sent | For Information Only | 2021-07-19 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Responded and Closed (Approved) to: Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) Remarks: Response (Approved) from: Omar Masood Remarks: See DCI response attached. DCI takes no exception to the submittal as shown on the specification provided. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-22 |  | 32 13 13 - 14 - Sitework Flatwork Concrete Water Cure.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-22 |  | 32 13 13 - 14 - Sitework Flatwork Concrete Water Cure.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-06-21 02:00 |  | 32 13 13 - 14 - Sitework Flatwork Concrete Water Cure.pdf
| Review Response |  | Omar Masood (DCI Engineers) | 1 | 2021-06-21 02:00 |  | 32 13 13 - 14 - Sitework Flatwork Concrete Water Cure.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-06-28 02:00 |  | 32 13 13 - 14 - Sitework Flatwork Concrete Water Cure - DCI Response_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-06-21 02:00 |  | 32 13 13 - 14 - Sitework Flatwork Concrete Water Cure.pdf
32 13 73-005-00 | 32 13 73 - CONCRETE PAVING JOINT SEALANTS | 32 13 73-005-00 Concrete Joint Sealant for South Parcel Decline Paving Joints | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2021-05-25 | 2021-05-24 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-05-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13046 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-05-25 | Submittal Number: 32 13 73-5.0 From: CHRISTIAN GENEROSA Final Due Date: 05/25/21 Subject: CONCRETE JOINT SEALANT FOR SOUTH PARCEL DECLINE PAVING JOINTS Description: CONCRETE JOINT SEALANT FOR SOUTH PARCEL DECLINE PAVING JOINTS Spec Section: 32 13 73 - CONCRETE PAVING JOINT SEALANTS Status: OPEN | Info Exchange
| 16876 | Forwarded | For Review | 2021-05-11 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-05-18 | Submittal Number: 32 13 73-5.0 From: CHRISTIAN GENEROSA Final Due Date: 05/25/21 Subject: CONCRETE JOINT SEALANT FOR SOUTH PARCEL DECLINE PAVING JOINTS Description: CONCRETE JOINT SEALANT FOR SOUTH PARCEL DECLINE PAVING JOINTS Spec Section: 32 13 73 - CONCRETE PAVING JOINT SEALANTS Status: OPEN | Info Exchange
| 13245 | Review Response | Approved as Noted | 2021-05-20 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached submittal review. - J. Grant, DCI Engineers | Info Exchange
| 17136 | Responded and Closed | Approved as Noted | 2021-05-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached submittal review. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | 2021-05-11 079200-0010-00 Concrete Joint Sealant SP_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-05-11 |  | 2021-05-11 079200-0010-00 Concrete Joint Sealant SP_MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-05-10 02:00 |  | 2021-05-11 079200-0010-00 Concrete Joint Sealant SP_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-05-24 02:00 |  | 321373-005-00 Concrete Joint Sealant SP_MAM_DCI_pop.pdf
32 31 13-002-00 | 32 31 13 - CHAIN LINK FENCES AND GATES | 32 31 13-002-00 - Chain Link Fences and Gates SD, PD | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-22 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2021-03-08 | 2021-03-11 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-03-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11571 | Received | For Review | 2021-02-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-08 | Submittal Number: 32 31 13-2.0 From: JES PELKEY Final Due Date: 03/08/21 Subject: CHAIN LINK FENCES AND GATES - SHOP DRAWINGS, PRODUCT DATA COOLING TOWER, PIPING ENCLOSURE, SUITE LVL AREA F MECH ROOM, EVENT LVL AREA E CONDENSER RACKS Description: SHOP DRAWINGS : FOR EACH TYPE OF FENCE AND GATE ASSEMBLY. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. 2. INCLUDE ACCESSORIES, HARDWARE, GATE OPERATION, AND OPERATIONAL CLEARANCES. 2/21/2021: SHOP DRAWINGS AND PRODUCT DATA INCLUDED IN THIS SUBMITTAL. Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 14993 | Forwarded | For Review | 2021-02-22 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2021-03-01 | Submittal Number: 32 31 13-2.0 From: JES PELKEY Final Due Date: 03/08/21 Subject: CHAIN LINK FENCES AND GATES - SHOP DRAWINGS, PRODUCT DATA COOLING TOWER, PIPING ENCLOSURE, SUITE LVL AREA F MECH ROOM, EVENT LVL AREA E CONDENSER RACKS Description: SHOP DRAWINGS : FOR EACH TYPE OF FENCE AND GATE ASSEMBLY. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. 2. INCLUDE ACCESSORIES, HARDWARE, GATE OPERATION, AND OPERATIONAL CLEARANCES. 2/21/2021: SHOP DRAWINGS AND PRODUCT DATA INCLUDED IN THIS SUBMITTAL. Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 15497 | Responded and Closed | Approved as Noted | 2021-03-11 | Shaina Burris (Populous) | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-21 02:00 |  | 2021-02-21 323113-0002-00 Chain Link Fence and Gates SD PD_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-21 02:00 |  | 2021-02-21 323113-0002-00 Chain Link Fence and Gates SD PD_MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-03-11 |  | 323113-0002-00 Chain Link Fence and Gates SD PD_MAM_POP.pdf
32 31 13-003-00 | 32 31 13 - CHAIN LINK FENCES AND GATES | 32 31 13-003-00 CHAIN LINK FENCES AND GATES - Samples | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-14 | Responded and Closed - Approved |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2021-04-28 | 2021-04-23 | 10 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-04-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12587 | Received | For Review | 2021-04-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Generosa | 2021-04-28 | Submittal Number: 32 31 13-3.0 From: CHRISTIAN GENEROSA Final Due Date: 04/28/21 Subject: CHAIN LINK FENCES AND GATES - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF COMPONENT WITH FACTORY-APPLIED FINISH, PREPARED ON SAMPLES OF SIZE INDICATED BELOW: 1. POLYMER-COATED COMPONENTS: IN 6-INCH LENGTHS FOR COMPONENTS AND ON FULL-SIZED UNITS FOR ACCESSORIES. Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 16301 | Forwarded | For Review | 2021-04-14 | Christian Generosa | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-04-21 | Submittal Number: 32 31 13-3.0 From: CHRISTIAN GENEROSA Final Due Date: 04/28/21 Subject: CHAIN LINK FENCES AND GATES - SAMPLES Description: SAMPLES FOR VERIFICATION : FOR EACH TYPE OF COMPONENT WITH FACTORY-APPLIED FINISH, PREPARED ON SAMPLES OF SIZE INDICATED BELOW: 1. POLYMER-COATED COMPONENTS: IN 6-INCH LENGTHS FOR COMPONENTS AND ON FULL-SIZED UNITS FOR ACCESSORIES. Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 16475 | Responded and Closed | Approved | 2021-04-23 | Tom Usher (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-14 |  | 2021-04-14 323113-0003-00 Chain Link Fence Sample_MAM.pdf
| Forwarded |  | Christian Generosa | 1 | 2021-04-14 |  | 2021-04-14 323113-0003-00 Chain Link Fence Sample_MAM.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2021-04-23 |  | 2021-04-14 323113-0003-00 Chain Link Fence Sample_MAM_POP.pdf
32 31 13-004-00 | 32 31 13 - CHAIN LINK FENCES AND GATES | 32 31 13-004-00 CHAIN LINK FENCES AND GATES - Delegated-Design Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-21 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2021-05-05 | 2021-04-23 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-04-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12699 | Received | For Review | 2021-04-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-05-05 | Submittal Number: 32 31 13-4.0 From: CHRISTIAN GENEROSA Final Due Date: 05/05/21 Subject: CHAIN LINK FENCES AND GATES - DELEGATED-DESIGN SUBMITTAL Description: DELEGATED-DESIGN SUBMITTAL : FOR STRUCTURAL PERFORMANCE OF CHAIN-LINK FENCE AND GATE FRAMEWORKS, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 16420 | Forwarded | For Review | 2021-04-21 | Shaina Burris (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-04-28 | Submittal Number: 32 31 13-4.0 From: CHRISTIAN GENEROSA Final Due Date: 05/05/21 Subject: CHAIN LINK FENCES AND GATES - DELEGATED-DESIGN SUBMITTAL Description: DELEGATED-DESIGN SUBMITTAL : FOR STRUCTURAL PERFORMANCE OF CHAIN-LINK FENCE AND GATE FRAMEWORKS, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 16477 | Responded and Closed | Approved as Noted | 2021-04-23 | Tom Usher (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-20 |  | 2021-04-20 Chain Link Fences and Gates DD-Cooling Tower Piping Enclosure Mech Rm Condenser Racks_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-04-20 |  | 2021-04-20 Chain Link Fences and Gates DD-Cooling Tower Piping Enclosure Mech Rm Condenser Racks_MAM.pdf
| Responded and Closed |  | Tom Usher (Populous) | 1 | 2021-04-23 |  | 32 32 13-004 Chain Link -Cooling Tower Mech Rm Condenser Racks_MAM_POP.pdf
32 31 13-009-00 | 32 31 13 - CHAIN LINK FENCES AND GATES | 32 31 13-009-00 SCL Switchgear Vault Fence | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-08 | Responded and Closed - Not Required For Review |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2021-03-22 | 2021-03-26 | 19 |  | Record Copies; Transfers; Submittals |  | 19 |  | 2021-03-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11843 | Received | For Review | 2021-03-08 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-03-22 | Submittal Number: 32 31 13-9.0 From: CHRISTIAN ALBERS Final Due Date: 03/22/21 Subject: SCL SWITCHGEAR VAULT FENCE Description: SEE ATTACHED PRODUCT DATA AND SHOP DRAWINGS FOR THE SCL SWITCHGEAR VAULT FENCE IN THE 1ST AVE GARAGE SUBMITTED FOR RECORD. PREVIOUSLY SUBMITTED AND APPROVED BY CHRIS MINTER. Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 15354 | Forwarded | For Review | 2021-03-08 | Christian Albers (Mortenson Construction) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-03-15 | Submittal Number: 32 31 13-9.0 From: CHRISTIAN ALBERS Final Due Date: 03/22/21 Subject: SCL SWITCHGEAR VAULT FENCE Description: SEE ATTACHED PRODUCT DATA AND SHOP DRAWINGS FOR THE SCL SWITCHGEAR VAULT FENCE IN THE 1ST AVE GARAGE SUBMITTED FOR RECORD. PREVIOUSLY SUBMITTED AND APPROVED BY CHRIS MINTER. Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 15874 | Responded and Closed | Not Required For Review | 2021-03-26 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-08 |  | CPA - BIFOLD SWING GATE SUBMITTAL-POP.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-03-08 |  | CPA - BIFOLD SWING GATE SUBMITTAL-POP.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-07 02:00 |  | CPA - BIFOLD SWING GATE SUBMITTAL-POP.pdf
32 31 13-010-00 | 32 31 13 - CHAIN LINK FENCES AND GATES | 32 31 13-010-00 Chain Link Fence Shop Drawings and Product Data for Electrical Room 01.11.08 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2021-03-29 | 2021-03-22 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11990 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-29 | Submittal Number: 32 31 13-10.0 From: CHRISTIAN GENEROSA Final Due Date: 03/28/21 Subject: CHAIN LINK FENCE SHOP DRAWINGS AND PRODUCT DATA FOR ELECTRICAL ROOM 01.11.08 Description: SHOP DRAWINGS AND PRODUCT DATA FOR CHAIN LINK FENCING AND GATES AT ELECTRICAL ROOM 01.11.08 Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 15530 | Forwarded | For Review | 2021-03-15 | Populous SCA_CCA | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-03-22 | Submittal Number: 32 31 13-10.0 From: CHRISTIAN GENEROSA Final Due Date: 03/28/21 Subject: CHAIN LINK FENCE SHOP DRAWINGS AND PRODUCT DATA FOR ELECTRICAL ROOM 01.11.08 Description: SHOP DRAWINGS AND PRODUCT DATA FOR CHAIN LINK FENCING AND GATES AT ELECTRICAL ROOM 01.11.08 Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 15748 | Responded and Closed | Approved as Noted | 2021-03-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-14 |  | 2021-03-14 323113-0010-00 Chain Link Fence SD and PD RM 01.11.08_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-14 |  | 2021-03-14 323113-0010-00 Chain Link Fence SD and PD RM 01.11.08_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-22 |  | 2021-03-14 323113-0010-00 Chain Link Fence SD and PD RM 01.11.08_MAM_POP.pdf
32 31 13-011-00 | 32 31 13 - CHAIN LINK FENCES AND GATES | 32 31 13-011-00 Chain Link Fences and Gates Delegated Design Submittal for Electrical Room 01.11.08 | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-19 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2021-05-03 | 2021-04-23 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-04-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12635 | Received | For Review | 2021-04-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-03 | Submittal Number: 32 31 13-11.0 From: CHRISTIAN GENEROSA Final Due Date: 05/03/21 Subject: CHAIN LINK FENCES AND GATES DELEGATED DESIGN SUBMITTAL FOR ELECTRICAL ROOM 01.11.08 Description: DELEGATED DESIGN SUBMITTAL FOR ELECTRICAL ROOM 01.11.08. Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 16352 | Forwarded | For Review | 2021-04-19 | Populous SCA_CCA | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-04-26 | Submittal Number: 32 31 13-11.0 From: CHRISTIAN GENEROSA Final Due Date: 05/03/21 Subject: CHAIN LINK FENCES AND GATES DELEGATED DESIGN SUBMITTAL FOR ELECTRICAL ROOM 01.11.08 Description: DELEGATED DESIGN SUBMITTAL FOR ELECTRICAL ROOM 01.11.08. Spec Section: 32 31 13 - CHAIN LINK FENCES AND GATES Status: OPEN | Info Exchange
| 16476 | Responded and Closed | Approved as Noted | 2021-04-23 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-18 |  | 323113-0011-00 Chain Link Fences and Gates DD Elec Rm 01.11.08_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-18 |  | 323113-0011-00 Chain Link Fences and Gates DD Elec Rm 01.11.08_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-23 |  | 323113-0011-00 Chain Link Fences and Gates DD Elec Rm 01.11.08_MAM_POP.pdf
32 31 16-002-00 | 32 31 19 - DECORATIVE METAL FENCES AND GATES | 32 31 16-002-00 DECORATIVE METAL FENCES AND GATES - SD, PD - South Parcel | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-22 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2021-03-08 | 2021-03-11 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-03-11
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11573 | Received | For Review | 2021-02-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-08 | Submittal Number: 32 31 16-2.0 From: CHRISTIAN GENEROSA Final Due Date: 03/08/21 Subject: DECORATIVE METAL FENCES AND GATES - SHOP DRAWINGS, PRODUCT DATA - SOUTH PARCEL Description: SHOP DRAWINGS : FOR ALL FENCING AND GATE COMPONENTS. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. 1. INCLUDE DIAGRAMS FOR POWER, SIGNAL, AND CONTROL WIRING. 2/21/2021: SHOP DRAWINGS AND PRODUCT DATA FOR THIS SCOPE IS INCLUDED IN THIS SUBMITTAL. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 14994 | Forwarded | For Review | 2021-02-22 | Josh Dobken (Populous) | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous) | 2021-03-01 | Submittal Number: 32 31 16-2.0 From: CHRISTIAN GENEROSA Final Due Date: 03/08/21 Subject: DECORATIVE METAL FENCES AND GATES - SHOP DRAWINGS, PRODUCT DATA - SOUTH PARCEL Description: SHOP DRAWINGS : FOR ALL FENCING AND GATE COMPONENTS. INCLUDE PLANS, ELEVATIONS, SECTIONS, DETAILS, AND ATTACHMENTS TO OTHER WORK. 1. INCLUDE DIAGRAMS FOR POWER, SIGNAL, AND CONTROL WIRING. 2/21/2021: SHOP DRAWINGS AND PRODUCT DATA FOR THIS SCOPE IS INCLUDED IN THIS SUBMITTAL. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 15496 | Responded and Closed | Approved as Noted | 2021-03-11 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-21 02:00 |  | 2021-02-21 323116-0002-00 Decorative Metal Fences and Gates SD PD_MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-02-21 02:00 |  | 2021-02-21 323116-0002-00 Decorative Metal Fences and Gates SD PD_MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-03-11 |  | 323116-0002-00 Decorative Metal Fences and Gates SD PD_MAM_POP.pdf
32 31 16-003-00 | 32 31 16 | 32 31 16-003-00 DECORATIVE METAL FENCES AND GATES - Samples | Closed | Architectural, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-01 | Responded and Closed - Approved |  | Bryan Klote (Populous), Todd Spangler (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-04-15 | 2021-04-05 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-04-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12343 | Received | For Review | 2021-04-01 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-04-15 | Submittal Number: 32 31 16-3.0 From: JES PELKEY Final Due Date: 04/09/21 Subject: DECORATIVE METAL FENCES AND GATES - SAMPLES Description: SAMPLES : FOR EACH FENCE MATERIAL AND FOR EACH COLOR SPECIFIED. 1. PROVIDE SAMPLES 12 INCHES IN LENGTH FOR LINEAR MATERIALS. 2. PROVIDE SAMPLES 48 INCHES SQUARE FOR SHEET OR PLATE MATERIALS. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 15991 | Forwarded | For Review | 2021-04-01 | Populous SCA_CCA | Bryan Klote (Populous); Todd Spangler (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-04-08 | Submittal Number: 32 31 16-3.0 From: JES PELKEY Final Due Date: 04/09/21 Subject: DECORATIVE METAL FENCES AND GATES - SAMPLES Description: SAMPLES : FOR EACH FENCE MATERIAL AND FOR EACH COLOR SPECIFIED. 1. PROVIDE SAMPLES 12 INCHES IN LENGTH FOR LINEAR MATERIALS. 2. PROVIDE SAMPLES 48 INCHES SQUARE FOR SHEET OR PLATE MATERIALS. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 16062 | Forwarded | For Review | 2021-04-05 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-04-12 | Submittal Number: 32 31 16-3.0 From: JES PELKEY Final Due Date: 04/09/21 Subject: DECORATIVE METAL FENCES AND GATES - SAMPLES Description: SAMPLES : FOR EACH FENCE MATERIAL AND FOR EACH COLOR SPECIFIED. 1. PROVIDE SAMPLES 12 INCHES IN LENGTH FOR LINEAR MATERIALS. 2. PROVIDE SAMPLES 48 INCHES SQUARE FOR SHEET OR PLATE MATERIALS. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 12408 | Review Response | Not Required For Review | 2021-04-05 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | Not a Swift scope item. | Info Exchange
| 16082 | Responded and Closed | Approved | 2021-04-05 | Populous SCA_CCA | Jes Pelkey (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-01 |  | 2021-03-26 323116-0003-00 Decorative Metal Fence and Gate Samples_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-01 |  | 2021-03-26 323116-0003-00 Decorative Metal Fence and Gate Samples_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-31 02:00 |  | 2021-03-26 323116-0003-00 Decorative Metal Fence and Gate Samples_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-31 |  | 2021-03-26 323116-0003-00 Decorative Metal Fence and Gate Samples_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-05 |  | 2021-03-26 323116-0003-00 Decorative Metal Fence and Gate Samples_MAM - SWIFT_POP.pdf
32 31 16-005-00 | 32 31 16 | 32 31 16-005-00 DECORATIVE METAL FENCES AND GATES - Delegated-Design Submittal | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-19 | Review Response - Approved as Noted |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2021-05-03 | 2021-04-23 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-04-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12636 | Received | For Review | 2021-04-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-03 | Submittal Number: 32 31 16-5.0 From: CHRISTIAN GENEROSA Final Due Date: 05/03/21 Subject: DECORATIVE METAL FENCES AND GATES - DELEGATED-DESIGN SUBMITTAL Description: DELEGATED-DESIGN SUBMITTAL : FOR FENCING AND GATE ASSEMBLIES, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 16353 | Forwarded | For Review | 2021-04-19 | Populous SCA_CCA | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-04-26 | Submittal Number: 32 31 16-5.0 From: CHRISTIAN GENEROSA Final Due Date: 05/03/21 Subject: DECORATIVE METAL FENCES AND GATES - DELEGATED-DESIGN SUBMITTAL Description: DELEGATED-DESIGN SUBMITTAL : FOR FENCING AND GATE ASSEMBLIES, INCLUDING ANALYSIS DATA SIGNED AND SEALED BY THE QUALIFIED PROFESSIONAL ENGINEER RESPONSIBLE FOR THEIR PREPARATION. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 16474 | Responded and Closed | Approved as Noted | 2021-04-23 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | See attached for submittal comments | Info Exchange
| 12745 | Review Response | Approved as Noted | 2021-04-23 | Tom Usher (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa Remarks: See attached for submittal comments | Info Exchange
| 16739 | Sent | For Information Only | 2021-05-04 | Populous SCA_CCA | Domingo Sampayo (Mortenson Construction); Brooke Burcham (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Tom Usher (Populous) Remarks: Responded and Closed (Approved as Noted) to: AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa Remarks: See attached for submittal comments | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-18 |  | 323116-0005-00 Decorative Metal Fences and Gates DD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-18 |  | 323116-0005-00 Decorative Metal Fences and Gates DD_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-04-18 |  | 323116-0005-00 Decorative Metal Fences and Gates DD_MAM.pdf
| Review Response |  | Tom Usher (Populous) | 1 | 2021-04-23 |  | 323116-0005-00 Decorative Metal Fences and Gates DD_MAM_POP.pdf
| Sent |  | Populous SCA_CCA | 1 | 2021-04-17 02:00 |  | 323116-0005-00 Decorative Metal Fences and Gates DD_MAM.pdf
32 31 16-011-00 | 32 31 16 | 32 31 16-011-00 South Parcel Telescoping Gate - G3 Shop Drawings and Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2021-03-29 | 2021-03-29 | 15 |  | Record Copies; Transfers; Submittals |  | 15 |  | 2021-03-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11991 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-03-29 | Submittal Number: 32 31 16-11.0 From: CHRISTIAN GENEROSA Final Due Date: 03/29/21 Subject: SOUTH PARCEL TELESCOPING GATE - G3 SHOP DRAWINGS AND PRODUCT DATA Description: SHOP DRAWINGS AND PRODUCT DATA FOR THE TELESCOPING GATES MARKED AS G3 ON SHEET A2-1G. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 15531 | Forwarded | For Review | 2021-03-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-03-22 | Submittal Number: 32 31 16-11.0 From: CHRISTIAN GENEROSA Final Due Date: 03/29/21 Subject: SOUTH PARCEL TELESCOPING GATE - G3 SHOP DRAWINGS AND PRODUCT DATA Description: SHOP DRAWINGS AND PRODUCT DATA FOR THE TELESCOPING GATES MARKED AS G3 ON SHEET A2-1G. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 15891 | Responded and Closed | Approved as Noted | 2021-03-29 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-14 |  | 2021-03-14 323116-0011-00 G3 Gate SD and PD_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-03-14 |  | 2021-03-14 323116-0011-00 G3 Gate SD and PD_MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-03-29 |  | 2021-03-14 323116-0011-00 G3 Gate SD and PD_MAM_POP.pdf
32 31 16-012-00 | 32 31 16 | 32 31 16-012-00 Decorative Metal fence & Gates Color Selections | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-15 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2021-03-29 | 2021-03-22 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-03-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11992 | Received | For Review | 2021-03-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-03-29 | Submittal Number: 32 31 16-12.0 From: CHRISTIAN GENEROSA Final Due Date: 03/28/21 Subject: DECORATIVE METAL FENCE & GATES COLOR SELECTIONS Description: COLOR SELECTION FOR THE DECORATIVE METAL FENCE OMEGA PRODUCT. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 15532 | Forwarded | For Review | 2021-03-15 | Populous SCA_CCA | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-03-22 | Submittal Number: 32 31 16-12.0 From: CHRISTIAN GENEROSA Final Due Date: 03/28/21 Subject: DECORATIVE METAL FENCE & GATES COLOR SELECTIONS Description: COLOR SELECTION FOR THE DECORATIVE METAL FENCE OMEGA PRODUCT. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 15700 | Responded and Closed | Approved as Noted | 2021-03-22 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-14 |  | 2021-03-14 Decorative Metal Fence & Gates Color Selections_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-03-14 |  | 2021-03-14 Decorative Metal Fence & Gates Color Selections_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-03-22 |  | 2021-03-14 Decorative Metal Fence & Gates Color Selections_MAM_POP.pdf
32 31 16-013-00 | 32 31 16 | 32 31 16-013-00 South Parcel G5 Telescoping Gate- Shop Drawings, Product Data | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-04-26 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous), Mark Lievens (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-05-10 | 2021-05-03 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-05-03
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12760 | Received | For Review | 2021-04-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-10 | Submittal Number: 32 31 16-13.0 From: CHRISTIAN GENEROSA Final Due Date: 05/10/21 Subject: SOUTH PARCEL G5 TELESCOPING GATE- SHOP DRAWINGS, PRODUCT DATA Description: SOUTH PARCEL TELESCOPING GATE G5 DESIGNATION FOR DECLINE RAMP. THIS SUBMITTAL INCLUDES THE SHOP DRAWING AND PRODUCT DATA FOR THE ASSOCIATED COMPONENTS OF THE SYSTEM. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 16493 | Forwarded | For Review | 2021-04-26 | Populous SCA_CCA | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-05-03 | Submittal Number: 32 31 16-13.0 From: CHRISTIAN GENEROSA Final Due Date: 05/10/21 Subject: SOUTH PARCEL G5 TELESCOPING GATE- SHOP DRAWINGS, PRODUCT DATA Description: SOUTH PARCEL TELESCOPING GATE G5 DESIGNATION FOR DECLINE RAMP. THIS SUBMITTAL INCLUDES THE SHOP DRAWING AND PRODUCT DATA FOR THE ASSOCIATED COMPONENTS OF THE SYSTEM. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 16576 | Forwarded | For Review | 2021-04-27 | Populous SCA_CCA | Mark Lievens (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-04 | Submittal Number: 32 31 16-13.0 From: CHRISTIAN GENEROSA Final Due Date: 05/10/21 Subject: SOUTH PARCEL G5 TELESCOPING GATE- SHOP DRAWINGS, PRODUCT DATA Description: SOUTH PARCEL TELESCOPING GATE G5 DESIGNATION FOR DECLINE RAMP. THIS SUBMITTAL INCLUDES THE SHOP DRAWING AND PRODUCT DATA FOR THE ASSOCIATED COMPONENTS OF THE SYSTEM. Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 12904 | Review Response | Approved as Noted | 2021-05-03 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Tom Usher (Populous); Josh Dobken (Populous); Populous SCA_CCA |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.05.03 | Info Exchange
| 12899 | Review Response | Approved as Noted | 2021-05-03 | Mark Lievens (ME Engineers) | Tom Usher (Populous) |  |  | Info Exchange
| 16690 | Responded and Closed | Approved as Noted | 2021-05-03 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Tom Usher (Populous); Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-04-26 |  | 2021-04-25 323116-0013-00 South Parcel G5 Telescoping Gate SDPD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-26 |  | 2021-04-25 323116-0013-00 South Parcel G5 Telescoping Gate SDPD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-04-26 |  | 2021-04-25 323116-0013-00 South Parcel G5 Telescoping Gate SDPD_MAM.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-04-26 |  | 2021-04-25 323116-0013-00 South Parcel G5 Telescoping Gate SDPD_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-03 |  | 323116-0013-00 S Parcel G5 Telescop Gate_MAM_ME_POP.pdf
32 31 16-014-00 | 32 31 16 | 32 31 16-014-00 Decorative Metal Gate at Ticket Office Roof Shop Drawings | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-14 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous), Chad Francis (Populous) |  |  |  | 2021-07-28 | 2021-07-15 | 2 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13922 | Received | For Review | 2021-07-14 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-07-28 | Submittal Number: 32 31 16-14.0 From: CHRISTIAN GENEROSA Final Due Date: 07/27/21 Subject: DECORATIVE METAL GATE AT TICKET OFFICE ROOF SHOP DRAWINGS Description: Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 18025 | Forwarded | For Review | 2021-07-13 | Shaina Burris (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous); Chad Francis (Populous) | 2021-07-20 | Submittal Number: 32 31 16-14.0 From: CHRISTIAN GENEROSA Final Due Date: 07/27/21 Subject: DECORATIVE METAL GATE AT TICKET OFFICE ROOF SHOP DRAWINGS Description: Spec Section: 32 31 16 - DECORATIVE METAL FENCES AND GATES Status: OPEN | Info Exchange
| 18065 | Responded and Closed | Approved as Noted | 2021-07-15 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-13 |  | 2021-07-13 323116-0014-00 Decorative Metal Gate for Ticket Office Roof SD_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-13 |  | 2021-07-13 323116-0014-00 Decorative Metal Gate for Ticket Office Roof SD_MAM.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-07-15 |  | 32 31 16-0014-00 Decorative Metal Gate for Ticket Office Roof SD_MAM_POP.pdf
32 84 00-001-00 | 32 84 00 - PLANTING IRRIGATION | 32 84 00-001-00 PLANTING IRRIGATION - Product Data | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-07 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-01-22 08:00 | 2021-01-24 | 18 |  | Record Copies; Transfers; Submittals |  | 16 |  | 2021-01-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10513 | Received | For Review | 2021-01-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Generosa | 2021-01-22 08:00 | Submittal Number: 32 84 00-1.0 From: CHRISTIAN GENEROSA Final Due Date: 01/20/21 Subject: PLANTING IRRIGATION - PRODUCT DATA Description: PRODUCT DATA : INCLUDE MANUFACTURERS PRODUCT LITERATURE FOR ALL PRODUCTS TO BE INSTALLED IN THIS SYSTEM. INCLUDE MATERIAL SHOWING MANUFACTURERS NAME, CATALOG NUMBERS, CATALOG CUTS, TECHNICAL DATA, AND INSTALLATION, OPERATION, AND MAINTENANCE INSTRUCTIONS FOR EACH PRODUCT. Spec Section: 32 84 00 - PLANTING IRRIGATION Status: OPEN | Info Exchange
| 13716 | Forwarded | For Review | 2021-01-07 | Christian Generosa | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-01-14 | Submittal Number: 32 84 00-1.0 From: CHRISTIAN GENEROSA Final Due Date: 01/20/21 Subject: PLANTING IRRIGATION - PRODUCT DATA Description: PRODUCT DATA : INCLUDE MANUFACTURERS PRODUCT LITERATURE FOR ALL PRODUCTS TO BE INSTALLED IN THIS SYSTEM. INCLUDE MATERIAL SHOWING MANUFACTURERS NAME, CATALOG NUMBERS, CATALOG CUTS, TECHNICAL DATA, AND INSTALLATION, OPERATION, AND MAINTENANCE INSTRUCTIONS FOR EACH PRODUCT. Spec Section: 32 84 00 - PLANTING IRRIGATION Status: OPEN | Info Exchange
| 10922 | Review Response | Approved as Noted | 2021-01-22 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Christian Generosa |  |  | Info Exchange
| 14180 | Responded and Closed | Approved as Noted | 2021-01-24 | Christian Generosa | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-06 |  | Seattle Center Arena - Irrigation Submittal - 01-04-21_MAM Review.pdf
| Forwarded |  | Christian Generosa | 1 | 2021-01-06 |  | Seattle Center Arena - Irrigation Submittal - 01-04-21_MAM Review.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-01-05 02:00 |  | Seattle Center Arena - Irrigation Submittal - 01-04-21_MAM Review.pdf
| Responded and Closed |  | Christian Generosa | 1 | 2021-01-24 02:00 |  | 32 84 00-001-00 Seattle Center Arena - Irrigation Submittal - 01-04-21_MAM Review - SWIFT_pop.pdf
32 84 00-001-01 | 32 84 00 - PLANTING IRRIGATION | 32 84 00-001-01 Planting Irrigation - Product Data | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-27 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-08-10 | 2021-08-16 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2021-08-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14142 | Received | For Review | 2021-07-27 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2021-08-10 |  | Email
| 18277 | Forwarded | For Review | 2021-07-27 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-03 |  | Info Exchange
| 14387 | Review Response | Approved | 2021-08-16 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | Review for rain sensor and valve box only. All other items per previous submittal. | Info Exchange
| 18563 | Responded and Closed | Approved | 2021-08-16 | Shaina Burris (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa; michael.hennessy@mortenson.com |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Review for rain sensor and valve box only. All other items per previous submittal. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-27 |  | 2021-07-13 32 84 00-0001-01 PLANTING IRRIGATION - Product Data_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-27 |  | 2021-07-13 32 84 00-0001-01 PLANTING IRRIGATION - Product Data_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-07-27 |  | 2021-07-13 32 84 00-0001-01 PLANTING IRRIGATION - Product Data_MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-07-27 |  | 2021-07-13 32 84 00-0001-01 PLANTING IRRIGATION - Product Data_MAM.pdf
32 84 00-008-00 | 32 84 00 - PLANTING IRRIGATION | 32 84 00-008-00 Irrigation Exterior Conduit and J-Box for Control Wire Pathway Product Data | Closed | Landscape, Electrical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-11 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-05-25 | 2021-05-19 | 9 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-05-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13043 | Received | For Review | 2021-05-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-25 | Submittal Number: 32 84 00-8.0 From: CHRISTIAN GENEROSA Final Due Date: 05/25/21 Subject: IRRIGATION EXTERIOR CONDUIT AND J-BOX FOR CONTROL WIRE PATHWAY PRODUCT DATA Description: CONTROL WIRE CONDUIT AND J-BOX PRODUCT DATA FOR EXTERIOR ROUTED IRRIGATION. Spec Section: 32 84 00 - PLANTING IRRIGATION Status: OPEN | Info Exchange
| 16874 | Forwarded | For Review | 2021-05-11 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-05-18 | Submittal Number: 32 84 00-8.0 From: CHRISTIAN GENEROSA Final Due Date: 05/25/21 Subject: IRRIGATION EXTERIOR CONDUIT AND J-BOX FOR CONTROL WIRE PATHWAY PRODUCT DATA Description: CONTROL WIRE CONDUIT AND J-BOX PRODUCT DATA FOR EXTERIOR ROUTED IRRIGATION. Spec Section: 32 84 00 - PLANTING IRRIGATION Status: OPEN | Info Exchange
| 16986 | Forwarded | For Review | 2021-05-17 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-05-24 | Submittal Number: 32 84 00-8.0 From: CHRISTIAN GENEROSA Final Due Date: 05/25/21 Subject: IRRIGATION EXTERIOR CONDUIT AND J-BOX FOR CONTROL WIRE PATHWAY PRODUCT DATA Description: CONTROL WIRE CONDUIT AND J-BOX PRODUCT DATA FOR EXTERIOR ROUTED IRRIGATION. Spec Section: 32 84 00 - PLANTING IRRIGATION Status: OPEN | Info Exchange
| 13174 | Review Response | Approved as Noted | 2021-05-17 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | See attached for comments. | Info Exchange
| 17062 | Responded and Closed | Approved as Noted | 2021-05-19 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See attached for comments. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-11 |  | 2021-05-11 Planting Irrigation Exterior Conduit and JBox for Control Wire PD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-11 |  | 2021-05-11 Planting Irrigation Exterior Conduit and JBox for Control Wire PD_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-10 02:00 |  | 2021-05-11 Planting Irrigation Exterior Conduit and JBox for Control Wire PD_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-10 02:00 |  | 2021-05-11 Planting Irrigation Exterior Conduit and JBox for Control Wire PD_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-19 02:00 |  | 328400-008-00 Irrigation Ext Conduit and JBox for Control Wire PD_MAM - SWIFT_POP.pdf
32 84 00-009-00 | 32 84 00 - PLANTING IRRIGATION | 32 84 00-009-00 Planting Irrigation Point of Connection Water Pressure Test Area 6 & 7 | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-29 | Responded and Closed - No Action Taken or Required |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-08-12 | 2021-08-02 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-08-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14163 | Received | For Review | 2021-07-29 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-08-12 | Submittal Number: 32 84 00-9.0 From: MICHAEL HENNESSY Final Due Date: 08/12/21 Subject: PLANTING IRRIGATION POINT OF CONNECTION WATER PRESSURE TEST AREA 6 & 7 Description: PLANTING IRRIGATION POINT OF CONNECTION WATER PRESSURE TEST AREA 6 & 7 Spec Section: 32 84 00 - PLANTING IRRIGATION Status: OPEN | Info Exchange
| 18308 | Forwarded | For Review | 2021-07-29 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-05 | Submittal Number: 32 84 00-9.0 From: MICHAEL HENNESSY Final Due Date: 08/12/21 Subject: PLANTING IRRIGATION POINT OF CONNECTION WATER PRESSURE TEST AREA 6 & 7 Description: PLANTING IRRIGATION POINT OF CONNECTION WATER PRESSURE TEST AREA 6 & 7 Spec Section: 32 84 00 - PLANTING IRRIGATION Status: OPEN | Info Exchange
| 18309 | Forwarded | For Review | 2021-07-29 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-05 | Submittal Number: 32 84 00-9.0 From: MICHAEL HENNESSY Final Due Date: 08/12/21 Subject: PLANTING IRRIGATION POINT OF CONNECTION WATER PRESSURE TEST AREA 6 & 7 Description: PLANTING IRRIGATION POINT OF CONNECTION WATER PRESSURE TEST AREA 6 & 7 Spec Section: 32 84 00 - PLANTING IRRIGATION Status: OPEN | Info Exchange
| 14185 | Review Response | Approved | 2021-07-30 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 18338 | Responded and Closed | No Action Taken or Required | 2021-08-02 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction); Christian Generosa |  | RECEIVED FOR RECORD Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-29 |  | 2021-07-29 328400-0009-00 Planting Irrigation Point of Connection Water Pressure Test Areas 6 & 7_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-29 |  | 2021-07-29 328400-0009-00 Planting Irrigation Point of Connection Water Pressure Test Areas 6 & 7_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-29 |  | 2021-07-29 328400-0009-00 Planting Irrigation Point of Connection Water Pressure Test Areas 6 & 7_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-07-28 02:00 |  | 2021-07-29 328400-0009-00 Planting Irrigation Point of Connection Water Pressure Test Areas 6 & 7_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-28 02:00 |  | 2021-07-29 328400-0009-00 Planting Irrigation Point of Connection Water Pressure Test Areas 6 & 7_MAM.pdf
32 84 00-010-00 | 32 84 00 - PLANTING IRRIGATION | 32 84 00-010-00 Living wall irrigation shop drawings | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-25 | Responded and Closed - Not Required For Review |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-09-08 | 2021-09-01 | 8 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14473 | Received | For Review | 2021-08-25 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Shaina Burris (Populous) | 2021-09-08 | Submittal Number: 32 84 00-10.0 From: NICK NOWOJ Final Due Date: 08/30/21 Subject: LIVING WALL IRRIGATION SHOP DRAWINGS Description: LIVING WALL IRRIGATION SHOP DRAWINGS Spec Section: 32 84 00 - PLANTING IRRIGATION Status: OPEN | Info Exchange
| 18666 | Forwarded | For Review | 2021-08-25 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-09-01 | Submittal Number: 32 84 00-10.0 From: NICK NOWOJ Final Due Date: 08/30/21 Subject: LIVING WALL IRRIGATION SHOP DRAWINGS Description: LIVING WALL IRRIGATION SHOP DRAWINGS Spec Section: 32 84 00 - PLANTING IRRIGATION Status: OPEN | Info Exchange
| 18670 | Forwarded | For Review | 2021-08-25 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) |  | Submittal Number: 32 84 00-10.0 From: NICK NOWOJ Final Due Date: 08/30/21 Subject: LIVING WALL IRRIGATION SHOP DRAWINGS Description: LIVING WALL IRRIGATION SHOP DRAWINGS Spec Section: 32 84 00 - PLANTING IRRIGATION Status: OPEN | Info Exchange
| 14539 | Review Response | No Action Taken or Required | 2021-08-26 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | Reviewed. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 26 August 2021 | Info Exchange
| 18743 | Responded and Closed | Not Required For Review | 2021-09-01 | Todd Spangler (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | REVIEWED. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-25 |  | 32 84 00-10.0 Living wall irrigation shop drawings.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-25 |  | 32 84 00-10.0 Living wall irrigation shop drawings.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-08-25 |  | 32 84 00-10.0 Living wall irrigation shop drawings.pdf
| Responded and Closed |  | Todd Spangler (Populous) | 1 | 2021-09-01 |  | 32 84 00-10.0 Living wall irrigation shop drawings_MEE_POP.pdf
32 90 00-007-00 | 32 90 00 - PLANTING | 32 90 00-007-00 PLANTING - Samples | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-26 | Responded and Closed - Approved as Noted/Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-06-10 07:00 | 2021-06-13 | 19 |  | Record Copies; Transfers; Submittals | 32 90 00-007-00-01 - 32 90 00-007-00 PLANTING - Samples | 17 |  | 2021-06-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13275 | Received | For Review | 2021-05-26 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-06-10 07:00 | Submittal Number: 32 90 00-7.0 From: CHRISTIAN GENEROSA Final Due Date: 06/09/21 Subject: PLANTING - SAMPLES Description: SAMPLES : SUBMIT AT LEAST ONE MONTH PRIOR TO LANDSCAPE PRECONSTRUCTION MEETING. LABEL EACH SAMPLE GIVING NAME OF PRODUCT AND MANUFACTURER AND/OR SUPPLIERS NAME. 1. COMPOSTED: TWO (2) ONE-POUND BAGS. 2. BARK MULCH: TWO (2) ONE-POUND BAGS. 3. TOPSOIL: TWO (2) ONE-POUND BAGS. 4. PLANTING FILL: TWO (2) ONE-POUND BAGS. 5. CRUSHED GRAVEL MULCH: TWO (2) ONE-POUND BAGS. 6. DRAIN ROCK: TWO (2) ONE-POUND BAGS. EXCLUDING SAND, GUYING MATERIAL, ROOT BARRIERS, AND PERFORATED PIPE AND INSPECTION RISERS. WILL FOLLOW-UP/CONFIRM WITH ANOTHER SUBMITTAL. Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 17180 | Forwarded | For Review | 2021-05-26 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-02 | Submittal Number: 32 90 00-7.0 From: CHRISTIAN GENEROSA Final Due Date: 06/09/21 Subject: PLANTING - SAMPLES Description: SAMPLES : SUBMIT AT LEAST ONE MONTH PRIOR TO LANDSCAPE PRECONSTRUCTION MEETING. LABEL EACH SAMPLE GIVING NAME OF PRODUCT AND MANUFACTURER AND/OR SUPPLIERS NAME. 1. COMPOSTED: TWO (2) ONE-POUND BAGS. 2. BARK MULCH: TWO (2) ONE-POUND BAGS. 3. TOPSOIL: TWO (2) ONE-POUND BAGS. 4. PLANTING FILL: TWO (2) ONE-POUND BAGS. 5. CRUSHED GRAVEL MULCH: TWO (2) ONE-POUND BAGS. 6. DRAIN ROCK: TWO (2) ONE-POUND BAGS. EXCLUDING SAND, GUYING MATERIAL, ROOT BARRIERS, AND PERFORATED PIPE AND INSPECTION RISERS. WILL FOLLOW-UP/CONFIRM WITH ANOTHER SUBMITTAL. Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 13500 | Review Response | Approved as Noted/Resubmit | 2021-06-11 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | See notes in pdf. Resubmit for 5/8" clean crushed basalt in lieu of 1" round drainrock per on-site conversation, and landscape mulch. | Info Exchange
| 17461 | Responded and Closed | Approved as Noted/Resubmit | 2021-06-13 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted/Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See notes in pdf. Resubmit for 5/8" clean crushed basalt in lieu of 1" round drainrock per on-site conversation, and landscape mulch. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-26 |  | 2021-05-26 329000-0007-00 Planting Samples Part 1_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-26 |  | 2021-05-26 329000-0007-00 Planting Samples Part 1_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-25 02:00 |  | 2021-05-26 329000-0007-00 Planting Samples Part 1_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-06-13 02:00 |  | 32 90 00-07-00 Planting Samples Part 1_MAM - SWIFT_POP.pdf
32 90 00-007-00-01 | 32 90 00 - PLANTING | 32 90 00-007-00 PLANTING - Samples | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 32 90 00-007-00 - 32 90 00-007-00 PLANTING - Samples | -1 | 2021-06-28
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-13 02:00 |  | 32 90 00-07-00 Planting Samples Part 1_MAM - SWIFT_POP.pdf
32 90 00-010-00 | 32 90 00 - PLANTING | 32 90 00-010-00 Plant Material List (Part 1) | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-01-12 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-01-27 08:00 | 2021-04-12 | 91 |  | Record Copies; Transfers; Submittals |  | 91 |  | 2021-04-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 10629 | Received | For Review | 2021-01-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-01-27 08:00 | Submittal Number: 32 90 00-10.0 From: CHRISTIAN GENEROSA Final Due Date: 01/26/21 Subject: PLANT MATERIAL LIST (PART 1) Description: THIS IS PART ONE OF THE PLANT MATERIAL TO BE SUBMITTED. Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 13836 | Forwarded | For Review | 2021-01-12 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-01-19 | Submittal Number: 32 90 00-10.0 From: CHRISTIAN GENEROSA Final Due Date: 01/26/21 Subject: PLANT MATERIAL LIST (PART 1) Description: THIS IS PART ONE OF THE PLANT MATERIAL TO BE SUBMITTED. Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 12553 | Review Response | Approved as Noted | 2021-04-12 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | See attached for remaining clarifications to shrub species. | Info Exchange
| 16261 | Responded and Closed | Approved as Noted | 2021-04-12 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: See attached for remaining clarifications to shrub species. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-01-11 |  | 2020-01-11 Seattle Center Plant Submittal - 01-05-20_MAM Review.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-01-11 |  | 2020-01-11 Seattle Center Plant Submittal - 01-05-20_MAM Review.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-01-10 02:00 |  | 2020-01-11 Seattle Center Plant Submittal - 01-05-20_MAM Review.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-04-12 02:00 |  | 32 90 00-010-00 Seattle Center Plant Submittal - 2021-04-12 SWIFT plants_pop.pdf
32 90 00-011-00 | 32 90 00 - PLANTING | 32 90 00-011-00 Plant Material List (Part 2) Product Data/Certifications | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-07 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-05-21 | 2021-05-24 | 18 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2021-05-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12976 | Received | For Review | 2021-05-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-05-21 | Submittal Number: 32 90 00-11.0 From: CHRISTIAN GENEROSA Final Due Date: 05/20/21 Subject: PLANT MATERIAL LIST (PART 2) PRODUCT DATA/CERTIFICATIONS Description: THE PART TWO TO THIS SUBMITTAL INCLUDES: SEDUM MAT PLANT MATERIAL SOD PRODUCT DATA/CERTIFICATION LETTER COMPOST PRODUCT DATA, CERTIFICATION LETTER, TEST REPORT TOP SOIL PRODUCT DATA, CERTIFICATION LETTER, TEST REPORT MULCH PRODUCT DATA/CERTIFICATION LETTER ROW TREE ROOT BARRIER PRODUCT DATA GUYING/STAKING MATERIAL PRODUCT DATA Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 16795 | Forwarded | For Review | 2021-05-07 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-05-14 | Submittal Number: 32 90 00-11.0 From: CHRISTIAN GENEROSA Final Due Date: 05/20/21 Subject: PLANT MATERIAL LIST (PART 2) PRODUCT DATA/CERTIFICATIONS Description: THE PART TWO TO THIS SUBMITTAL INCLUDES: SEDUM MAT PLANT MATERIAL SOD PRODUCT DATA/CERTIFICATION LETTER COMPOST PRODUCT DATA, CERTIFICATION LETTER, TEST REPORT TOP SOIL PRODUCT DATA, CERTIFICATION LETTER, TEST REPORT MULCH PRODUCT DATA/CERTIFICATION LETTER ROW TREE ROOT BARRIER PRODUCT DATA GUYING/STAKING MATERIAL PRODUCT DATA Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 13249 | Review Response | Approved as Noted | 2021-05-20 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 17145 | Responded and Closed | Approved as Noted | 2021-05-24 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-06 |  | 2021-05-06 329000-0011-00 Plant Material List Pt2_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-05-06 |  | 2021-05-06 329000-0011-00 Plant Material List Pt2_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-05 02:00 |  | 2021-05-06 329000-0011-00 Plant Material List Pt2_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-05-24 02:00 |  | 329000-011-00 Plant Material List Pt2_MAM - SWIFT_POP.pdf
32 90 00-012-00 | 32 90 00 - PLANTING | 32 90 00-012-00 Plant Material List (Part 3) | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-07 | Responded and Closed - Approved as Noted/Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-06-21 | 2021-07-09 | 33 |  | Record Copies; Transfers; Submittals | 32 90 00-012-00-01 - 32 90 00-012-00 Plant Material List (Part 3) | 33 |  | 2021-07-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13433 | Received | For Review | 2021-06-07 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-06-21 | Submittal Number: 32 90 00-12.0 From: CHRISTIAN GENEROSA Final Due Date: 06/21/21 Subject: PLANT MATERIAL LIST (PART 3) Description: PART 3 OF THE PLANT MATERIAL LIST. Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 17373 | Forwarded | For Review | 2021-06-07 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-06-14 | Submittal Number: 32 90 00-12.0 From: CHRISTIAN GENEROSA Final Due Date: 06/21/21 Subject: PLANT MATERIAL LIST (PART 3) Description: PART 3 OF THE PLANT MATERIAL LIST. Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 13882 | Review Response | Approved as Noted/Resubmit | 2021-07-09 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Approved for all items noted. Resubmit for: 1. Confirm Leucothoe species, 'fontanesiana' preferred. 2. Provide photo confirmation of Vacc. ovatum or alternative substitution. See note on plant list. 3. Sedum mat for planter at garage entry drive is omitted (area 3). Provide confirmation on product mix.- | Info Exchange
| 17973 | Responded and Closed | Approved as Noted/Resubmit | 2021-07-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved as Noted/Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Approved for all items noted. Resubmit for: 1. Confirm Leucothoe species, 'fontanesiana' preferred. 2. Provide photo confirmation of Vacc. ovatum or alternative substitution. See note on plant list. 3. Sedum mat for planter at garage entry drive is omitted (area 3). Provide confirmation on product mix.- | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-07 |  | 2021-06-07 3290000-0012-00 Plant Material List Part 3 (Plant Material) Product Data_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-07 |  | 2021-06-07 3290000-0012-00 Plant Material List Part 3 (Plant Material) Product Data_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-06-06 02:00 |  | 2021-06-07 3290000-0012-00 Plant Material List Part 3 (Plant Material) Product Data_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-07-09 02:00 |  | 329000-012-00 Plant Material List Part 3 (Plant Material) Product Data_MAM - SWIFT_POP.pdf
32 90 00-012-00-01 | 32 90 00 - PLANTING | 32 90 00-012-00 Plant Material List (Part 3) | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | 32 90 00-012-00 - 32 90 00-012-00 Plant Material List (Part 3) | -1 | 2021-07-23
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-09 02:00 |  | 329000-012-00 Plant Material List Part 3 (Plant Material) Product Data_MAM - SWIFT_POP.pdf
32 90 00-013-00 | 32 90 00 - PLANTING | 32 90 00-013-00 Drain Rock Sample (5/8" Clean Crushed Basalt) | Closed | Civil, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-02 | Responded and Closed - Revise and Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Damon Smith (DCI Engineers), Omar Masood (DCI Engineers) |  |  |  | 2021-07-19 07:00 | 2021-07-08 | 7 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13783 | Received | For Review | 2021-07-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-19 07:00 | Submittal Number: 32 90 00-13.0 From: MICHAEL HENNESSY Final Due Date: 07/16/21 Subject: DRAIN ROCK SAMPLE (5/8" CLEAN CRUSHED BASALT) Description: DRAIN ROCK SAMPLE (5/8" CLEAN CRUSHED BASALT) Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 17838 | Forwarded | For Review | 2021-07-06 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-07-13 | Submittal Number: 32 90 00-13.0 From: MICHAEL HENNESSY Final Due Date: 07/16/21 Subject: DRAIN ROCK SAMPLE (5/8" CLEAN CRUSHED BASALT) Description: DRAIN ROCK SAMPLE (5/8" CLEAN CRUSHED BASALT) Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 17871 | Forwarded | For Review | 2021-07-06 | Populous SCA_CCA | Damon Smith (DCI Engineers); Omar Masood | 2021-07-13 | Submittal Number: 32 90 00-13.0 From: MICHAEL HENNESSY Final Due Date: 07/16/21 Subject: DRAIN ROCK SAMPLE (5/8" CLEAN CRUSHED BASALT) Description: DRAIN ROCK SAMPLE (5/8" CLEAN CRUSHED BASALT) Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 13852 | Review Response | Approved as Noted | 2021-07-07 | Omar Masood | Populous SCA_CCA |  | Review required by SWIFT for submittal approval. - O. Masood, DCI Engineers | Info Exchange
| 13853 | Review Response | Revise and Resubmit | 2021-07-07 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  | Rock must be 5/8" clean crushed basalt, dark in color. Sample illustrates too much color variation and does not appear to be all basalt. | Info Exchange
| 17949 | Responded and Closed | Revise and Resubmit | 2021-07-08 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Revise and Resubmit) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Rock must be 5/8" clean crushed basalt, dark in color. Sample illustrates too much color variation and does not appear to be all basalt. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-02 |  | 2021-07-02 329000-0013-00 Drain Rock Sample (Clean Crushed Basalt)_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-02 |  | 2021-07-02 329000-0013-00 Drain Rock Sample (Clean Crushed Basalt)_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-01 02:00 |  | 2021-07-02 329000-0013-00 Drain Rock Sample (Clean Crushed Basalt)_MAM.pdf
| Review Response |  | Omar Masood (DCI Engineers) | 1 | 2021-07-01 02:00 |  | 2021-07-02 329000-0013-00 Drain Rock Sample (Clean Crushed Basalt)_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-07-01 02:00 |  | 2021-07-02 329000-0013-00 Drain Rock Sample (Clean Crushed Basalt)_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-07-08 02:00 |  | 32 90 00-013-00 Drain Rock Sample (Clean Crushed Basalt)_MAM - SWIFT_POP.pdf
32 90 00-013-01 | 32 90 00 - PLANTING | 32 90 00-013-01 Drain Rock Sample (5/8" Clean Crushed Basalt) | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-07-15 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-07-29 | 2021-08-04 | 21 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2021-08-04
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13954 | Received | For Review | 2021-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2021-07-29 | Submittal Number: 32 90 00-13.1 From: MICHAEL HENNESSY Final Due Date: 07/29/21 Subject: DRAIN ROCK SAMPLE (5/8" CLEAN CRUSHED BASALT) Description: DRAIN ROCK SAMPLE (5/8" CLEAN CRUSHED BASALT) REV. 1 Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18057 | Forwarded | For Review | 2021-07-15 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-07-22 | Submittal Number: 32 90 00-13.1 From: MICHAEL HENNESSY Final Due Date: 07/29/21 Subject: DRAIN ROCK SAMPLE (5/8" CLEAN CRUSHED BASALT) Description: DRAIN ROCK SAMPLE (5/8" CLEAN CRUSHED BASALT) REV. 1 Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 14220 | Review Response | Approved | 2021-08-03 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 18374 | Responded and Closed | Approved | 2021-08-04 | Populous SCA_CCA | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-15 |  | 2021-07-15 329000-0013-01 Drain Rock Sample (Clean Crushed Basalt)_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-07-15 |  | 2021-07-15 329000-0013-01 Drain Rock Sample (Clean Crushed Basalt)_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-07-14 02:00 |  | 2021-07-15 329000-0013-01 Drain Rock Sample (Clean Crushed Basalt)_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-08-04 02:00 |  | 32 90 00-013-01 Drain Rock Sample (Clean Crushed Basalt)_MAM - SWIFT_POP.pdf
32 90 00-014-00 | 32 90 00 - PLANTING | 32 90 00-014-00 Planting Material List (Part 4) Additional Product Data | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-02 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-08-16 | 2021-08-19 | 18 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2021-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14177 | Received | For Review | 2021-08-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-08-16 | Submittal Number: 32 90 00-14.0 From: CHRISTIAN GENEROSA Final Due Date: 08/16/21 Subject: PLANTING MATERIAL LIST (PART 4) ADDITIONAL PRODUCT DATA Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18327 | Forwarded | For Review | 2021-08-02 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-08-09 | Submittal Number: 32 90 00-14.0 From: CHRISTIAN GENEROSA Final Due Date: 08/16/21 Subject: PLANTING MATERIAL LIST (PART 4) ADDITIONAL PRODUCT DATA Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 14409 | Review Response | Approved | 2021-08-18 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Populous SCA_CCA |  |  | Info Exchange
| 18599 | Responded and Closed | Approved | 2021-08-19 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-30 |  | 2021-07-30 329000-0014-00 Planting Material List pt 4 PD_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-30 |  | 2021-07-30 329000-0014-00 Planting Material List pt 4 PD_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-07-30 |  | 2021-07-30 329000-0014-00 Planting Material List pt 4 PD_MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-08-19 |  | 2021-07-30 329000-0014-00 Planting Material List pt 4 PD_MAM - SWIFT_POP.pdf
32 90 00-015-00 | 32 90 00 - PLANTING | 32 90 00-015-00 Top Soil Test Reports (Revised from Planting Material Part 2) | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-08-31 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Shawn Stankewich (Swift and Company Landscape Arch) |  |  |  | 2021-09-14 | 2021-09-13 | 14 |  | Record Copies; Transfers; Submittals |  | 10 |  | 2021-09-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14547 | Received | For Review | 2021-08-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-09-14 | Submittal Number: 32 90 00-15.0 From: CHRISTIAN GENEROSA Final Due Date: 09/14/21 Subject: TOP SOIL TEST REPORTS (REVISED FROM PLANTING MATERIAL PART 2) Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18757 | Forwarded | For Review | 2021-09-01 | Populous SCA_CCA | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-09-08 | Submittal Number: 32 90 00-15.0 From: CHRISTIAN GENEROSA Final Due Date: 09/14/21 Subject: TOP SOIL TEST REPORTS (REVISED FROM PLANTING MATERIAL PART 2) Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18844 | Forwarded | For Review | 2021-09-09 | Bryan Klote (Populous) | Shawn Stankewich (Swift and Company Landscape Arch) |  | Submittal Number: 32 90 00-15.0 From: CHRISTIAN GENEROSA Final Due Date: 09/14/21 Subject: TOP SOIL TEST REPORTS (REVISED FROM PLANTING MATERIAL PART 2) Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 14632 | Review Response | Approved | 2021-09-10 | Shawn Stankewich (Swift and Company Landscape Arch) | Bryan Klote (Populous) |  | Please see response attached. | Info Exchange
| 18871 | Responded and Closed | Approved | 2021-09-13 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Shawn Stankewich (Swift and Company Landscape Arch) Remarks: Please see response attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-08-30 02:00 |  | 32 90 00-0015-00 Top Soil Test Reports (From Planting Material pt2) Revised_MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-30 02:00 |  | 32 90 00-0015-00 Top Soil Test Reports (From Planting Material pt2) Revised_MAM.pdf
| Forwarded |  | Bryan Klote (Populous) | 1 | 2021-08-30 |  | 32 90 00-0015-00 Top Soil Test Reports (From Planting Material pt2) Revised_MAM.pdf
| Review Response |  | Shawn Stankewich (Swift and Company Landscape Arch) | 1 | 2021-08-30 |  | 32 90 00-0015-00 Top Soil Test Reports (From Planting Material pt2) Revised_MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-09-13 |  | 32 90 00-0015-00 Top Soil Test Reports Revised_MAM_SWIFT_POP.pdf
32 90 00-016-00 | 32 90 00 - PLANTING | 32 90 00-016-00 Manufacturers Mineral Co. Black Pebble 5/16" Crushed Gravel Mulch | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-02 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Shawn Stankewich (Swift and Company Landscape Arch) |  |  |  | 2021-09-16 | 2021-09-13 | 12 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-09-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14559 | Received | For Review | 2021-09-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-09-16 | Submittal Number: 32 90 00-16.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: MANUFACTURERS MINERAL CO. BLACK PEBBLE 5/16" CRUSHED GRAVEL MULCH Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18771 | Forwarded | For Review | 2021-09-03 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-09-10 | Submittal Number: 32 90 00-16.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: MANUFACTURERS MINERAL CO. BLACK PEBBLE 5/16" CRUSHED GRAVEL MULCH Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18843 | Forwarded | For Review | 2021-09-09 | Bryan Klote (Populous) | Shawn Stankewich (Swift and Company Landscape Arch) |  | Submittal Number: 32 90 00-16.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: MANUFACTURERS MINERAL CO. BLACK PEBBLE 5/16" CRUSHED GRAVEL MULCH Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 14631 | Review Response | Approved | 2021-09-10 | Shawn Stankewich (Swift and Company Landscape Arch) | Bryan Klote (Populous) |  | Please find response attached. | Info Exchange
| 18870 | Responded and Closed | Approved | 2021-09-13 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Shawn Stankewich (Swift and Company Landscape Arch) Remarks: Please find response attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-01 |  | 32 90 00-0016-00 Manufacturers Mineral Co. Black Pebble Gravel Mulch.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-01 |  | 32 90 00-0016-00 Manufacturers Mineral Co. Black Pebble Gravel Mulch.pdf
| Forwarded |  | Bryan Klote (Populous) | 1 | 2021-09-01 |  | 32 90 00-0016-00 Manufacturers Mineral Co. Black Pebble Gravel Mulch.pdf
| Review Response |  | Shawn Stankewich (Swift and Company Landscape Arch) | 1 | 2021-09-01 |  | 32 90 00-0016-00 Manufacturers Mineral Co. Black Pebble Gravel Mulch.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-09-13 |  | 32 90 00-0016-00 Black Pebble Gravel Mulch_SWIFT_POP.pdf
32 90 00-017-00 | 32 90 00 - PLANTING | 32 90 00-017-00 Plant Material List (Part 5) | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-02 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Shawn Stankewich (Swift and Company Landscape Arch) |  |  |  | 2021-09-16 | 2021-09-13 | 12 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-09-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14558 | Received | For Review | 2021-09-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-09-16 | Submittal Number: 32 90 00-17.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: PLANT MATERIAL LIST (PART 5) Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18770 | Forwarded | For Review | 2021-09-03 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-09-10 | Submittal Number: 32 90 00-17.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: PLANT MATERIAL LIST (PART 5) Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18842 | Forwarded | For Review | 2021-09-09 | Bryan Klote (Populous) | Shawn Stankewich (Swift and Company Landscape Arch) |  | Submittal Number: 32 90 00-17.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: PLANT MATERIAL LIST (PART 5) Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 14630 | Review Response | Approved | 2021-09-10 | Shawn Stankewich (Swift and Company Landscape Arch) | Bryan Klote (Populous) |  | Please find response attached. | Info Exchange
| 18869 | Responded and Closed | Approved | 2021-09-13 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Shawn Stankewich (Swift and Company Landscape Arch) Remarks: Please find response attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-01 |  | 32 90 00-0017-00 Plant Material List Part 5.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-01 |  | 32 90 00-0017-00 Plant Material List Part 5.pdf
| Forwarded |  | Bryan Klote (Populous) | 1 | 2021-09-01 |  | 32 90 00-0017-00 Plant Material List Part 5.pdf
| Review Response |  | Shawn Stankewich (Swift and Company Landscape Arch) | 1 | 2021-09-01 |  | 32 90 00-0017-00 Plant Material List Part 5.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-09-13 |  | 32 90 00-0017-00 Plant Material List Part 5_SWIFT_POP.pdf
32 90 00-018-00 | 32 90 00 - PLANTING | 32 90 00-018-00 Porous Paving Sample | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-02 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Shawn Stankewich (Swift and Company Landscape Arch) |  |  |  | 2021-09-16 | 2021-09-13 | 12 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-09-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14560 | Received | For Review | 2021-09-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-09-16 | Submittal Number: 32 90 00-18.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: POROUS PAVING SAMPLE Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18773 | Forwarded | For Review | 2021-09-03 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-09-10 | Submittal Number: 32 90 00-18.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: POROUS PAVING SAMPLE Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18841 | Forwarded | For Review | 2021-09-09 | Bryan Klote (Populous) | Shawn Stankewich (Swift and Company Landscape Arch) |  | Submittal Number: 32 90 00-18.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: POROUS PAVING SAMPLE Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 14629 | Review Response | Approved | 2021-09-10 | Shawn Stankewich (Swift and Company Landscape Arch) | Bryan Klote (Populous) |  | Please see response attached. | Info Exchange
| 18868 | Responded and Closed | Approved | 2021-09-13 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Shawn Stankewich (Swift and Company Landscape Arch) Remarks: Please see response attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-01 |  | 32 90 00-0018-00 Porous Paving Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-01 |  | 32 90 00-0018-00 Porous Paving Sample.pdf
| Forwarded |  | Bryan Klote (Populous) | 1 | 2021-09-01 |  | 32 90 00-0018-00 Porous Paving Sample.pdf
| Review Response |  | Shawn Stankewich (Swift and Company Landscape Arch) | 1 | 2021-09-01 |  | 32 90 00-0018-00 Porous Paving Sample.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-09-13 |  | 32 90 00-0018-00 Porous Paving Sample_SWIFT_POP.pdf
32 90 00-019-00 | 32 90 00 - PLANTING | 32 90 00-019-00 Landscape Mulch Sample | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-02 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch), Shawn Stankewich (Swift and Company Landscape Arch) |  |  |  | 2021-09-15 | 2021-09-13 | 12 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-09-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14561 | Received | For Review | 2021-09-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-09-15 | Submittal Number: 32 90 00-19.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: LANDSCAPE MULCH SAMPLE Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18774 | Forwarded | For Review | 2021-09-03 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-09-10 | Submittal Number: 32 90 00-19.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: LANDSCAPE MULCH SAMPLE Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18840 | Forwarded | For Review | 2021-09-09 | Bryan Klote (Populous) | Shawn Stankewich (Swift and Company Landscape Arch) |  | Submittal Number: 32 90 00-19.0 From: CHRISTIAN GENEROSA Final Due Date: 09/15/21 Subject: LANDSCAPE MULCH SAMPLE Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 14628 | Review Response | Approved | 2021-09-10 | Shawn Stankewich (Swift and Company Landscape Arch) | Bryan Klote (Populous) |  | Please find Swift's response attached. | Info Exchange
| 18867 | Responded and Closed | Approved | 2021-09-13 | Bryan Klote (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Shawn Stankewich (Swift and Company Landscape Arch) Remarks: Please find Swift's response attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-01 |  | 32 90 00-0019-00 Landscape Mulch Sample.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-01 |  | 32 90 00-0019-00 Landscape Mulch Sample.pdf
| Forwarded |  | Bryan Klote (Populous) | 1 | 2021-09-01 |  | 32 90 00-0019-00 Landscape Mulch Sample.pdf
| Review Response |  | Shawn Stankewich (Swift and Company Landscape Arch) | 1 | 2021-09-01 |  | 32 90 00-0019-00 Landscape Mulch Sample.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-09-13 |  | 32 90 00-0019-00 Landscape Mulch Sample_SWIFT_POP.pdf
32 90 00-020-00 | 32 90 00 - PLANTING | 32 90 00-020-00 Landscaping Sod Product Data | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-09-13 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Shawn Stankewich (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-09-27 | 2021-09-29 | 17 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2021-09-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14626 | Received | For Review | 2021-09-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-09-27 | Submittal Number: 32 90 00-20.0 From: CHRISTIAN GENEROSA Final Due Date: 09/24/21 Subject: LANDSCAPING SOD PRODUCT DATA Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 18865 | Forwarded | For Review | 2021-09-11 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Shawn Stankewich (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-09-20 | Submittal Number: 32 90 00-20.0 From: CHRISTIAN GENEROSA Final Due Date: 09/24/21 Subject: LANDSCAPING SOD PRODUCT DATA Description: Spec Section: 32 90 00 - PLANTING Status: OPEN | Info Exchange
| 14753 | Review Response | Approved | 2021-09-28 | Shawn Stankewich (Swift and Company Landscape Arch) | Populous SCA_CCA |  | Please find submittal response attached. Thanks! Shawn | Info Exchange
| 19020 | Responded and Closed | Approved | 2021-09-29 | Populous SCA_CCA | AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Shawn Stankewich (Swift and Company Landscape Arch) Remarks: Please find submittal response attached. Thanks! Shawn | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-09-10 |  | 32 90 00-0020-00 Sod Product Data_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-10 |  | 32 90 00-0020-00 Sod Product Data_MAM.pdf
| Review Response |  | Shawn Stankewich (Swift and Company Landscape Arch) | 1 | 2021-09-10 |  | 32 90 00-0020-00 Sod Product Data_MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2021-09-29 |  | 32 90 00-0020-00 Sod Product Data_MAM_SWIFT_POP.pdf
32 94 00-001-00 | 32 94 00 - SOIL CELLS | 32 94 00-001-00 SOIL CELLS - Product Data | Closed | Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-02-12 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-02-26 | 2021-02-24 | 13 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-02-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11383 | Received | For Review | 2021-02-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Christian Generosa | 2021-02-26 | Submittal Number: 32 94 00-1.0 From: CHRISTIAN GENEROSA Final Due Date: 02/26/21 Subject: SOIL CELLS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT SUBMIT CUT SHEETS GIVING NAME OF PRODUCT. Spec Section: 32 94 00 - SOIL CELLS Status: OPEN | Info Exchange
| 14736 | Forwarded | For Review | 2021-02-12 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-02-19 | Submittal Number: 32 94 00-1.0 From: CHRISTIAN GENEROSA Final Due Date: 02/26/21 Subject: SOIL CELLS - PRODUCT DATA Description: PRODUCT DATA : FOR EACH TYPE OF PRODUCT SUBMIT CUT SHEETS GIVING NAME OF PRODUCT. Spec Section: 32 94 00 - SOIL CELLS Status: OPEN | Info Exchange
| 11640 | Review Response | Approved | 2021-02-24 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  |  | Info Exchange
| 15087 | Responded and Closed | Approved | 2021-02-24 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-02-11 |  | 2021-02-11 329400-0001-00 Soil Cells PD_MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-02-11 |  | 2021-02-11 329400-0001-00 Soil Cells PD_MAM.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-02-10 02:00 |  | 2021-02-11 329400-0001-00 Soil Cells PD_MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-02-24 02:00 |  | 329400-001-00 Soil Cells PD_MAM - SWIFT_POP.pdf
33 41 00-001-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-001-00 Some Pipe and Fittings Product Data | Closed | Utilities | Domingo Sampayo (Mortenson Construction) | 2019-04-09 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant |  |  |  | 2019-04-23 | 2019-04-10 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-04-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01146 | Received | For Review | 2019-04-09 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-23 |  | Email
| 02025 | Forwarded | For Review | 2019-04-09 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-16 |  | Info Exchange
| 01159 | Review Response | Approved as Noted | 2019-04-09 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  |  | Info Exchange
| 02041 | Responded and Closed | Approved as Noted | 2019-04-10 | SCA_CCA@populous.com | Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Darren Simpson (DCI Engineers) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-09 |  | 33 41 00-001-0 Some Pipe and Fittings Product Data.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-09 |  | 33 41 00-001-0 Some Pipe and Fittings Product Data.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-04-09 |  | 33 41 00-001-0 Some Pipe and Fittings Product Data.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-10 |  | 33 41 00-001-0 Some Pipe and Fittings Product Data DCI POP.pdf
33 41 00-001-01 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-001-1 Product Data (Some Pipe and Fittings) | Closed | Utilities | Domingo Sampayo (Mortenson Construction) | 2019-04-12 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant |  |  |  | 2019-04-26 | 2019-04-25 | 14 |  | Record Copies; Transfers; Submittals |  | 14 |  | 2019-04-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01166 | Received | For Review | 2019-04-12 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-26 |  | Email
| 02054 | Forwarded | For Review | 2019-04-12 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-19 |  | Info Exchange
| 02153 | Forwarded | For Review | 2019-04-24 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant |  |  | Email
| 01219 | Review Response | Approved | 2019-04-25 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  | See the attached. | Info Exchange
| 02159 | Responded and Closed | Approved | 2019-04-25 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: See the attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-12 |  | 33 41 00-001-1 Product Data Some Pipe and Fittings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-12 |  | 33 41 00-001-1 Product Data Some Pipe and Fittings.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-12 |  | 33 41 00-001-1 Product Data Some Pipe and Fittings.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-04-25 |  | 33 41 00-001-1 Product Data Some Pipe and Fittings_DCI.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-25 |  | 33 41 00-001-1 Product Data Some Pipe and Fittings_DCI_POP.pdf
33 41 00-002-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-002-00 MH Storm Utility Drainage Piping | Closed | Utilities | Domingo Sampayo (Mortenson Construction) | 2019-04-09 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant |  |  |  | 2019-04-23 | 2019-04-10 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-04-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01147 | Received | For Review | 2019-04-09 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-23 |  | Email
| 02026 | Forwarded | For Review | 2019-04-09 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-16 |  | Info Exchange
| 01157 | Review Response | Approved as Noted | 2019-04-09 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  |  | Info Exchange
| 01158 | Review Response | Approved as Noted | 2019-04-10 | Tom Usher (Populous) | Tom Usher (Populous) |  | Response (Approved as Noted) from: Darren Simpson (DCI Engineers) | Info Exchange
| 02037 | Responded and Closed | Approved as Noted | 2019-04-10 | SCA_CCA@populous.com | Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Tom Usher (Populous) Remarks: Response (Approved as Noted) from: Darren Simpson (DCI Engineers) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-09 |  | 33 41 00-002-0 MH Storm Utility Drainage Piping.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-09 |  | 33 41 00-002-0 MH Storm Utility Drainage Piping.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-04-09 |  | 33 41 00-002-0 MH Storm Utility Drainage Piping.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-10 |  | 33 41 00-002-0 MH Storm Utility Drainage Piping DCI POP.pdf
33 41 00-002-01 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-002-01 Shop Drawings (MH) | Closed | Utilities | Domingo Sampayo (Mortenson Construction) | 2019-04-22 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant |  |  |  | 2019-05-06 | 2019-04-25 | 4 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2019-04-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01206 | Received | For Review | 2019-04-22 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-05-06 |  | Email
| 02140 | Forwarded | For Review | 2019-04-23 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-30 |  | Info Exchange
| 02152 | Forwarded | For Review | 2019-04-24 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant |  |  | Email
| 01218 | Review Response | Approved as Noted | 2019-04-25 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  | See the attached. | Info Exchange
| 02158 | Responded and Closed | Approved as Noted | 2019-04-25 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Darren Simpson (DCI Engineers) Remarks: See the attached. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-04-23 |  | 33 41 00-002-01 Shop Drawings (MH).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-23 |  | 33 41 00-002-01 Shop Drawings (MH).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-23 |  | 33 41 00-002-01 Shop Drawings (MH).pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-04-25 |  | 33 41 00-002-01 Shop Drawings (MH)_DCI.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-25 |  | 33 41 00-002-01 Shop Drawings (MH)_DCI_POP.pdf
33 41 00-004-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-004-00 South Parcel Detention Vault SDs & Calcs | Closed | Utilities | Josh Broussard (Mortenson Construction) | 2019-04-09 | Responded and Closed - Approved as Noted/Resubmit |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant, Brian MacRae (Thornton Tomasetti), Bryan Klote (Populous), Tom Usher (Populous), Chris Minter (Populous) |  |  |  | 2019-04-23 | 2019-04-15 | 7 |  | Record Copies; Transfers; Submittals | 33 41 00-004-01 - 33 41 00-004-01 South Parcel Detention Vault SDs & Calcs | 7 |  | 2019-04-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01149 | Received | For Review | 2019-04-09 | Josh Broussard (Mortenson Construction) | SCA_CCA@populous.com | 2019-04-23 |  | Email
| 02029 | Forwarded | For Review | 2019-04-09 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-16 |  | Info Exchange
| 01154 | Review Response | Approved | 2019-04-09 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  |  | Info Exchange
| 02036 | Forwarded | For Review | 2019-04-10 | SCA_CCA@populous.com | Brian MacRae (Thornton Tomasetti) |  |  | Info Exchange
| 01173 | Review Response | Approved as Noted/Resubmit | 2019-04-15 | Brian MacRae (Thornton Tomasetti) | SCA_CCA@populous.com |  | Populous - Contractor is looking for this submittal today, please forward on in a timely manner. | Info Exchange
| 02076 | Forwarded | For Review | 2019-04-15 | SCA_CCA@populous.com | Bryan Klote (Populous); Tom Usher (Populous); Chris Minter (Populous) |  |  | Info Exchange
| 02083 | Responded and Closed | Approved as Noted/Resubmit | 2019-04-15 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Josh Broussard (Mortenson Construction) |  | Please find attached PDF with comments from TT. Please review and resubmit based on TT provided notes. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Josh Broussard (Mortenson Construction) | 1 | 2019-04-09 |  | 33 41 00-004-0 South Parcel Detention Vault SDs & Calcs.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-09 |  | 33 41 00-004-0 South Parcel Detention Vault SDs & Calcs.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-04-09 |  | 33 41 00-004-0 South Parcel Detention Vault SDs & Calcs.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-09 |  | 33 41 00-004-0 South Parcel Detention Vault SDs & Calcs.pdf
| Review Response |  | Brian MacRae (Thornton Tomasetti) | 1 | 2019-04-09 |  | 33 41 00-004-0 South Parcel Detention Vault SDs & Calcs.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-04-09 |  | 33 41 00-004-0 South Parcel Detention Vault SDs & Calcs.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-04-15 |  | 33 41 00-004-0 South Parcel Detention Vault SDs & Calcs_DCI TT POP COMBINED.pdf
33 41 00-004-01 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-004-01 South Parcel Detention Vault SDs & Calcs | Closed | Utilities | Josh Broussard (Mortenson Construction) | 2019-04-17 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant, Brian MacRae (Thornton Tomasetti) |  |  |  | 2019-05-01 | 2019-04-22 | 6 |  | Record Copies; Transfers; Submittals | 33 41 00-004-00 - 33 41 00-004-00 South Parcel Detention Vault SDs & Calcs | 3 | 2019-04-29 | 2019-04-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01186 | Received | For Review | 2019-04-17 | Josh Broussard (Mortenson Construction) | Shaina Burris (Populous) | 2019-05-01 |  | Email
| 02097 | Forwarded | For Review | 2019-04-17 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-17 |  | Info Exchange
| 02098 | Forwarded | For Review | 2019-04-17 | Shaina Burris (Populous) | Brian MacRae (Thornton Tomasetti) |  |  | Info Exchange
| 01201 | Review Response | Approved | 2019-04-18 | Brian MacRae (Thornton Tomasetti) | Shaina Burris (Populous) |  |  | Info Exchange
| 02123 | Responded and Closed | Approved | 2019-04-18 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Josh Broussard (Mortenson Construction) |  | Response (Approved) from: Brian MacRae (Thornton Tomasetti) Remarks: | Info Exchange
| 02124 | Reopened | Additional Information | 2019-04-18 19:15 | Josh Dobken (Populous) |  |  | Reopened to attach file
| 02125 | Responded and Closed | Approved | 2019-04-18 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Josh Broussard (Mortenson Construction) |  | Response (Approved) from: Brian MacRae (Thornton Tomasetti) Remarks: | Info Exchange
| 02127 | Reopened | Additional Information | 2019-04-19 11:15 | Josh Dobken (Populous) |  |  | Reopened to forward to DCI for their approval
| 02128 | Forwarded | For Review | 2019-04-19 | Josh Dobken (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant | 2019-04-26 | Please find submittal reviewed by TT, requiring review by DCI before sending back to MAM. | Info Exchange
| 01202 | Review Response | Approved | 2019-04-19 | Darren Simpson (DCI Engineers) | Josh Dobken (Populous) |  |  | Info Exchange
| 02129 | Responded and Closed | Approved | 2019-04-22 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Damion Walker (Mortenson Construction); Josh Broussard (Mortenson Construction) |  | Response (Approved) from: Brian MacRae (Thornton Tomasetti) Response (Approved) from: Darren Simpson (DCI Engineers) See attached approval | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Josh Broussard (Mortenson Construction) | 1 | 2019-04-17 |  | 33 41 00-004-01 South Parcel Detention Vault Sds & Calcs R1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-04-17 |  | 33 41 00-004-01 South Parcel Detention Vault Sds & Calcs R1.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-04-17 |  | 33 41 00-004-01 South Parcel Detention Vault Sds & Calcs R1.pdf
| Review Response |  | Brian MacRae (Thornton Tomasetti) | 1 | 2019-04-17 |  | 33 41 00-004-01 South Parcel Detention Vault Sds & Calcs R1.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-04-17 |  | 33 41 00-004-01 South Parcel Detention Vault Sds & Calcs R1.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-04-18 |  | 33 41 00-004-1 South Parcel Detention Vault Sds & Calcs R1_TT_POP.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-04-17 |  | 33 41 00-004-01 South Parcel Detention Vault Sds & Calcs R1.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-04-17 |  | 33 41 00-004-01 South Parcel Detention Vault Sds & Calcs R1.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-04-22 |  | 33 41 00-004-1 South Parcel Detention Vault Sds & Calcs R1_TT_DCI_POP.pdf
33 41 00-005-0 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-005-0 South Parcel Submittal Package | Closed | Utilities | Domingo Sampayo (Mortenson Construction) | 2019-05-20 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-06-03 | 2019-05-22 | 3 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-05-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01355 | Received | For Review | 2019-05-20 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-06-03 |  | Email
| 02341 | Forwarded | For Review | 2019-05-20 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-05-27 |  | Info Exchange
| 01366 | Review Response | Approved | 2019-05-21 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  | Civil update to C200 to match catch basin naming convention pending. | Info Exchange
| 02353 | Responded and Closed | Approved | 2019-05-22 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: Civil update to C200 to match catch basin naming convention pending. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-05-20 |  | 33 41 00-005-0 South Parcel Submittal Package.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-20 |  | 33 41 00-005-0 South Parcel Submittal Package.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-05-19 02:00 |  | 33 41 00-005-0 South Parcel Submittal Package.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-22 02:00 |  | 33 41 00-005-0 South Parcel Submittal Package_DCI_POP.pdf
33 41 00-006-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-006-00 CMP (Tanks) - South Parcel | Closed | Utilities | Domingo Sampayo (Mortenson Construction) | 2019-05-22 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-06-05 | 2019-05-23 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-05-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01368 | Received | For Review | 2019-05-22 | Domingo Sampayo (Mortenson Construction) | SCA_CCA@populous.com | 2019-06-05 |  | Email
| 02355 | Forwarded | For Review | 2019-05-22 | SCA_CCA@populous.com | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-05-29 |  | Info Exchange
| 01370 | Review Response | Approved | 2019-05-22 | Darren Simpson (DCI Engineers) | SCA_CCA@populous.com |  |  | Info Exchange
| 02364 | Responded and Closed | Approved | 2019-05-23 | SCA_CCA@populous.com | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-05-22 |  | 33 41 00-006-00 CMP (Tanks) - South Parcel.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-05-22 |  | 33 41 00-006-00 CMP (Tanks) - South Parcel.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-05-21 02:00 |  | 33 41 00-006-00 CMP (Tanks) - South Parcel.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-05-23 02:00 |  | 33 41 00-006-00 CMP (Tanks) - South Parcel_DCI_POP.pdf
33 41 00-007-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-007-00: South Parcel Submittal Package #2 - Shop Drawings | Closed | Utilities | Domingo Sampayo (Mortenson Construction) | 2019-06-04 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-06-18 | 2019-06-05 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-06-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01436 | Received | For Review | 2019-06-04 | Domingo Sampayo (Mortenson Construction) | Josh Dobken (Populous) | 2019-06-18 | This submittal includes the shop drawings for the CMP tank, Control tees and Saddle Tee Connection. | Info Exchange
| 02439 | Forwarded | For Review | 2019-06-04 | Josh Dobken (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-06-11 | This submittal includes the shop drawings for the CMP tank, Control tees and Saddle Tee Connection. | Info Exchange
| 01440 | Review Response | Approved as Noted | 2019-06-05 | Darren Simpson (DCI Engineers) | Josh Dobken (Populous) |  | Please note marking on the two control structures. Dimensions corrected and elevations provided for reference. | Info Exchange
| 02445 | Responded and Closed | Approved as Noted | 2019-06-05 | Josh Dobken (Populous) | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved as Noted) from: Darren Simpson (DCI Engineers) Remarks: Please note marking on the two control structures. Dimensions corrected and elevations provided for reference. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-06-04 |  | 33 41 00-007-00 South Parcel Package #2-Shop Drawings.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-06-04 |  | 33 41 00-007-00 South Parcel Package #2-Shop Drawings.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-06-04 |  | 33 41 00-007-00 South Parcel Package #2-Shop Drawings.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-06-05 |  | 33 41 00-007-00 South Parcel Package #2-Shop Drawings_DCI_POP.pdf
33 41 00-008-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-008-00 South Parcel Submittal Package #2 (Additional) | Closed | Utilities | Domingo Sampayo (Mortenson Construction) | 2019-06-21 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-07-05 | 2019-06-26 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2019-06-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01596 | Received | For Review | 2019-06-21 | Domingo Sampayo (Mortenson Construction) | Populous SCA_CCA | 2019-07-05 |  | Email
| 02636 | Forwarded | For Review | 2019-06-21 | Populous SCA_CCA | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-06-28 |  | Info Exchange
| 01633 | Review Response | Approved | 2019-06-26 | Darren Simpson (DCI Engineers) | Populous SCA_CCA |  | Approved | Info Exchange
| 02697 | Responded and Closed | Approved | 2019-06-26 | Populous SCA_CCA | Tamara Hartner (Mortenson Construction); Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: Approved | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Domingo Sampayo (Mortenson Construction) | 1 | 2019-06-21 |  | 33 41 00-008-00 South Parcel Submittal Package #2 (Additional).pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-06-21 |  | 33 41 00-008-00 South Parcel Submittal Package #2 (Additional).pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-06-21 |  | 33 41 00-008-00 South Parcel Submittal Package #2 (Additional).pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-06-26 |  | 33 41 00-008-00 South Parcel Submittal Package #2 (Additional) - DCI_POP.pdf
33 41 00-009-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-009-00 CMP Tanks Saddle Tee's | Closed | Utilities | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-07-31 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-08-14 | 2019-08-01 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2019-08-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 01924 | Received | For Review | 2019-07-31 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2019-08-14 | Submittal Number: 33 41 00-9.0 From: TYRONE THORNTON Final Due Date: 08/16/19 Subject: CMP TANKS SADDLE TEE'S Description: JR HAYES UPDATED THE SUBMITTAL (33 41 00-6) TO REPRESENT 4 BOLTS FOR THE CONNECTION OF THE SADDLE TEE'S TO THE EXISTING CMP TANKS, INSTEAD OF 8 BOLTS. Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 03070 | Forwarded | For Review | 2019-07-31 | Populous SCA_CCA | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-08-07 | Submittal Number: 33 41 00-9.0 From: TYRONE THORNTON Final Due Date: 08/16/19 Subject: CMP TANKS SADDLE TEE'S Description: JR HAYES UPDATED THE SUBMITTAL (33 41 00-6) TO REPRESENT 4 BOLTS FOR THE CONNECTION OF THE SADDLE TEE'S TO THE EXISTING CMP TANKS, INSTEAD OF 8 BOLTS. Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 01948 | Review Response | Approved | 2019-07-31 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 01950 | Review Response | Approved | 2019-07-31 | Darren Simpson (DCI Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 03096 | Responded and Closed | Approved | 2019-08-01 | Populous SCA_CCA | Tyrone Thornton (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See attached for approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-07-31 |  | Submittal # 33 41 00-9_CMP Saddle Tee.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2019-07-31 |  | Submittal # 33 41 00-9_CMP Saddle Tee.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2019-07-31 |  | Submittal # 33 41 00-9_CMP Saddle Tee.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-07-31 |  | Submittal # 33 41 00-9_CMP Saddle Tee.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2019-07-31 |  | Submittal # 33 41 00-9_CMP Saddle Tee.pdf
33 41 00-010-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-010-00 Storm Utilities Package #2 (PVC Pipe, Area Drain, SSMH 10, SDMH-8, Frame & Covers, and CB Casting) | Closed | Utilities | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-15 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-08-29 | 2019-08-28 | 14 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-08-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02075 | Received | For Review | 2019-08-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-08-29 | Submittal Number: 33 41 00-10.0 From: JUAN BOLANOS Final Due Date: 08/28/19 Subject: STORM UTILITIES PACKAGE #2 (PVC PIPE, AREA DRAIN, SSMH 10, SDMH-8, FRAME & COVERS, AND CB CASTING) Description: PVC PIPE, AREA DRAIN, SSMH 10, SDMH-8, FRAME AND COVERS, AND CB CASTING Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 03248 | Forwarded | For Review | 2019-08-15 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-08-22 | Submittal Number: 33 41 00-10.0 From: JUAN BOLANOS Final Due Date: 08/28/19 Subject: STORM UTILITIES PACKAGE #2 (PVC PIPE, AREA DRAIN, SSMH 10, SDMH-8, FRAME & COVERS, AND CB CASTING) Description: PVC PIPE, AREA DRAIN, SSMH 10, SDMH-8, FRAME AND COVERS, AND CB CASTING Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 02228 | Review Response | Approved | 2019-08-27 | Darren Simpson (DCI Engineers) | Shaina Burris (Populous) |  | Approved | Info Exchange
| 03447 | Responded and Closed | Approved | 2019-08-28 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Josh Broussard (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: Approved | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-14 |  | 33 41 00-10 Storm Utilities Package #2.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-14 |  | 33 41 00-10 Storm Utilities Package #2.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-08-13 02:00 |  | 33 41 00-10 Storm Utilities Package #2.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-08-28 02:00 |  | 33 41 00-10 Storm Utilities Package #2_DCI_POP.pdf
33 41 00-011-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-011-00 Trench Drain C204 (Trench Drain Schedule 25 & 26) | Closed | Civil, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-19 | Responded and Closed - Rejected |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2019-10-03 | 2019-10-08 | 20 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2019-10-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02455 | Received | For Review | 2019-09-19 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-10-03 | Submittal Number: 33 41 00-11.0 From: DOMINGO SAMPAYO Final Due Date: 09/26/19 Subject: TRENCH DRAIN C204 (TRENCH DRAIN SCHEDULE 25 & 26) Description: NORTH COURT TRENCH DRAINS PER C204 (TRENCH DRAIN SCHEDULE 25 & 26) Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 03725 | Forwarded | For Review | 2019-09-19 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-09-26 | Submittal Number: 33 41 00-11.0 From: DOMINGO SAMPAYO Final Due Date: 09/26/19 Subject: TRENCH DRAIN C204 (TRENCH DRAIN SCHEDULE 25 & 26) Description: NORTH COURT TRENCH DRAINS PER C204 (TRENCH DRAIN SCHEDULE 25 & 26) Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 02488 | Review Response | Approved | 2019-09-23 | Darren Simpson (DCI Engineers) | Shaina Burris (Populous) |  | Forward to Landscape to review Grate selection | Info Exchange
| 03764 | Forwarded | For Review | 2019-09-23 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2019-09-30 | Submittal Number: 33 41 00-11.0 From: DOMINGO SAMPAYO Final Due Date: 09/26/19 Subject: TRENCH DRAIN C204 (TRENCH DRAIN SCHEDULE 25 & 26) Description: NORTH COURT TRENCH DRAINS PER C204 (TRENCH DRAIN SCHEDULE 25 & 26) Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 02699 | Review Response | Rejected | 2019-10-01 | Gareth Loveridge (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | The design is based upon the ACO K100S, which has a galvanized steel edge at the surface. The polydrain is not acceptable. The submitted product does not match, and is not equivalent. It does not meet the design aesthetics. It looks very different than the metal edge channel when installed. Also, there was not included the specified grate from the 129300 Site Furnishing specification. | Info Exchange
| 04031 | Responded and Closed | Rejected | 2019-10-08 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Rejected) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: The design is based upon the ACO K100S, which has a galvanized steel edge at the surface. The polydrain is not acceptable. The submitted product does not match, and is not equivalent. It does not meet the design aesthetics. It looks very different than the metal edge channel when installed. Also, there was not included the specified grate from the 129300 Site Furnishing specification. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-18 |  | Trench Drain C204 (Trench Drain Schedule 25 & 26).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-19 |  | 33 41 00-011-00 Trench Drain C204 (Trench Drain Schedule 25 & 26).pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-09-18 02:00 |  | 33 41 00-011-00 Trench Drain C204 (Trench Drain Schedule 25 & 26).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-09-17 02:00 |  | Trench Drain C204 (Trench Drain Schedule 25 & 26).pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2019-10-08 02:00 |  | 33 41 00-011-00 Trench Drain C204 (Trench Drain Schedule 25 & 26) - SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-08 02:00 |  | 33 41 00-011-00 Trench Drain C204 (Trench Drain Schedule 25 & 26) - SWIFT_POP.pdf
33 41 00-011-01 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-011-01 Trench Drain C204 (Trench Drain Schedule 25 & 26) | Closed | Civil, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-28 | Responded and Closed - Revise and Resubmit |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Gareth Loveridge (Swift and Company Landscape Arch), Jarrett Grant (DCI Engineers) |  |  |  | 2020-03-13 | 2020-03-19 | 21 |  | Record Copies; Transfers; Submittals |  | 21 |  | 2020-03-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04564 | Received | For Review | 2020-02-28 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-03-13 | Submittal Number: 33 41 00-11.1 From: DOMINGO SAMPAYO Final Due Date: 03/06/20 Subject: TRENCH DRAIN C204 (TRENCH DRAIN SCHEDULE 25 & 26) Description: NORTH COURT TRENCH DRAINS PER C204 (TRENCH DRAIN SCHEDULE 25 & 26) Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 06292 | Forwarded | For Review | 2020-02-28 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Gareth Loveridge (Swift and Company Landscape Arch); Jarrett Grant (DCI Engineers) | 2020-03-06 | Submittal Number: 33 41 00-11.1 From: DOMINGO SAMPAYO Final Due Date: 03/06/20 Subject: TRENCH DRAIN C204 (TRENCH DRAIN SCHEDULE 25 & 26) Description: NORTH COURT TRENCH DRAINS PER C204 (TRENCH DRAIN SCHEDULE 25 & 26) Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 06304 | Forwarded | For Review | 2020-03-02 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-03-09 | Submittal Number: 33 41 00-11.1 From: DOMINGO SAMPAYO Final Due Date: 03/06/20 Subject: TRENCH DRAIN C204 (TRENCH DRAIN SCHEDULE 25 & 26) Description: NORTH COURT TRENCH DRAINS PER C204 (TRENCH DRAIN SCHEDULE 25 & 26) Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 04802 | Review Response | Approved as Noted | 2020-03-11 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 06581 | Forwarded | For Review | 2020-03-12 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2020-03-13 | Submittal Number: 33 41 00-11.1 From: DOMINGO SAMPAYO Final Due Date: 03/06/20 Subject: TRENCH DRAIN C204 (TRENCH DRAIN SCHEDULE 25 & 26) Description: NORTH COURT TRENCH DRAINS PER C204 (TRENCH DRAIN SCHEDULE 25 & 26) Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Email
| 04963 | Review Response | Revise and Resubmit | 2020-03-19 | Gareth Loveridge (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | See attached for the SWIFT review comments. Grate is rejected – it doesn’t match the spec. Channel is compatible with specified and grate and meets design intent. | Email
| 06763 | Responded and Closed | Revise and Resubmit | 2020-03-19 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers Response (Revise and Resubmit) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: See attached for the SWIFT review comments. Grate is rejected – it doesn’t match the spec. Channel is compatible with specified and grate and meets design intent. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-28 |  | 33 41 00-11 R1Trench Drain C204 (Schedule 25 & 26).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-28 |  | 33 41 00-11 R1Trench Drain C204 (Schedule 25 & 26).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-27 02:00 |  | 33 41 00-11 R1Trench Drain C204 (Schedule 25 & 26).pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-02-27 02:00 |  | 33 41 00-11 R1Trench Drain C204 (Schedule 25 & 26).pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-02-27 02:00 |  | 33 41 00-11 R1Trench Drain C204 (Schedule 25 & 26).pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2020-03-19 02:00 |  | 33 41 00-11 R1Trench Drain C204 (Schedule 25 & 26) - SWIFT.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-03-19 |  | 33 41 00-11 R1Trench Drain C204 (Schedule 25 & 26) - SWIFT_DCI_POP.pdf
33 41 00-011-02 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-011-02 Trench Drain C204 (Trench Drain Schedule 25 & 26) | Closed | Civil, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-03-23 | Responded and Closed - Approved as Noted |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Gareth Loveridge (Swift and Company Landscape Arch), Jarrett Grant (DCI Engineers) |  |  |  | 2020-04-06 | 2020-04-16 | 25 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-04-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04977 | Received | For Review | 2020-03-23 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-04-06 | Submittal Number: 33 41 00-11.2 From: DOMINGO SAMPAYO Final Due Date: 04/15/20 Subject: TRENCH DRAIN C204 (TRENCH DRAIN SCHEDULE 25 & 26) Description: NORTH COURT TRENCH DRAINS PER C204 (TRENCH DRAIN SCHEDULE 25 & 26) Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 06789 | Forwarded | For Review | 2020-03-23 | Shaina Burris (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Gareth Loveridge (Swift and Company Landscape Arch); Jarrett Grant (DCI Engineers) | 2020-03-30 | Submittal Number: 33 41 00-11.2 From: DOMINGO SAMPAYO Final Due Date: 04/15/20 Subject: TRENCH DRAIN C204 (TRENCH DRAIN SCHEDULE 25 & 26) Description: NORTH COURT TRENCH DRAINS PER C204 (TRENCH DRAIN SCHEDULE 25 & 26) Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 05475 | Review Response | Approved as Noted | 2020-04-07 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 05397 | Review Response | Approved as Noted | 2020-04-15 | Gareth Loveridge (Swift and Company Landscape Arch) | Shaina Burris (Populous) |  | Attached is the response. Grate is acceptable, however the material needs to be cast aluminum as noted. It is a standard product, and re-submittal Is not required. | Email
| 07329 | Responded and Closed | Approved as Noted | 2020-04-16 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Pending response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers Response (Approved as Noted) from: Gareth Loveridge (Swift and Company Landscape Arch) Remarks: Attached is the response. Grate is acceptable, however the material needs to be cast aluminum as noted. It is a standard product, and re-submittal Is not required. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-03-23 |  | 33 41 00-11-2 Trench Drain C204 (Schedule 25 & 26).pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-03-22 02:00 |  | 33 41 00-11-2 Trench Drain C204 (Schedule 25 & 26).pdf
| Review Response |  | Gareth Loveridge (Swift and Company Landscape Arch) | 1 | 2020-04-16 02:00 |  | 33 41 00-11-2 Trench Drain C204 (Schedule 25 & 26)_DCI-SWIFT.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-16 02:00 |  | 33 41 00-11-2 Trench Drain C204 (Schedule 25 & 26)_DCI-SWIFT_POP.pdf
33 41 00-012-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-012-00 Coupling | Closed | Utilities | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-09-12 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-09-26 | 2019-09-17 | 6 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2019-09-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02389 | Received | For Review | 2019-09-12 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Domingo Sampayo (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-26 | Submittal Number: 33 41 00-12.0 From: JUAN BOLANOS Final Due Date: 09/25/19 Subject: COUPLING Description: THIS COUPLING WILL BE USED ON THE PVC TO CONCRETE PIPE CONNECTION (ROOF DRAINS TO EXISTING OR NEW DRAIN). Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 03636 | Forwarded | For Review | 2019-09-12 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-09-19 | Submittal Number: 33 41 00-12.0 From: JUAN BOLANOS Final Due Date: 09/25/19 Subject: COUPLING Description: THIS COUPLING WILL BE USED ON THE PVC TO CONCRETE PIPE CONNECTION (ROOF DRAINS TO EXISTING OR NEW DRAIN). Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 02442 | Review Response | Approved | 2019-09-13 | Darren Simpson (DCI Engineers) | Shaina Burris (Populous) |  | Approved | Info Exchange
| 03703 | Responded and Closed | Approved | 2019-09-17 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Darren Simpson (DCI Engineers) Remarks: Approved | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-09-11 |  | 33 41 00-12 Coupling.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-09-11 |  | 33 41 00-12 Coupling.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-09-10 02:00 |  | 33 41 00-12 Coupling.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-17 02:00 |  | 33 41 00-12 Coupling-DCI_POP.pdf
33 41 00-013-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-013-00 Revised SSMH #8 and 10" PVC added | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-10-02 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2019-10-16 | 2019-10-09 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2019-10-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02616 | Received | For Review | 2019-10-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (Mortenson Construction) | 2019-10-16 | Submittal Number: 33 41 00-13.0 From: JUAN BOLANOS Final Due Date: 10/02/19 Subject: REVISED SSMH#8 AND 10" PVC ADDED Description: Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 03918 | Forwarded | For Review | 2019-10-02 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-10-09 | Submittal Number: 33 41 00-13.0 From: JUAN BOLANOS Final Due Date: 10/02/19 Subject: REVISED SSMH#8 AND 10" PVC ADDED Description: Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 02705 | Review Response | Approved | 2019-10-09 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached materials submittal review. - J. Grant, DCI Engineers | Info Exchange
| 04039 | Responded and Closed | Approved | 2019-10-09 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Jarrett Grant (DCI Engineers) Remarks: See attached materials submittal review. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-10-01 |  | Revised SSMH-8 and 10 Inch PVC Added.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-10-02 |  | 33 41 00-013-00 Revised SSMH-8 and 10 Inch PVC Added.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2019-10-01 02:00 |  | 33 41 00-013-00 Revised SSMH-8 and 10 Inch PVC Added.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-10-09 02:00 |  | 33 41 00-013-00 Revised SSMH-8 and 10 Inch PVC Added_DCI_POP.pdf
33 41 00-015-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-015-00 Access Hatches and Restrictor Assemblies (East & West Detention Tanks) | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-02-11 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-02-25 | 2020-02-27 | 17 |  | Record Copies; Transfers; Submittals |  | 17 |  | 2020-02-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 04298 | Received | For Review | 2020-02-11 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-02-25 | Submittal Number: 33 41 00-15.0 From: DOMINGO SAMPAYO Final Due Date: 03/06/20 Subject: ACCESS HATCHES AND RESTRICTOR ASSEMBLIES (EAST & WEST DETENTION TANKS) Description: ACCESS HATCHES AND RESTRICTOR ASSEMBLIES AS SHOWN ON C300-WEST DETENTION VAULT DETAILS AND C301 EAST DETENTION VAULT DETAILS. Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 05951 | Forwarded | For Review | 2020-02-11 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-02-18 | Submittal Number: 33 41 00-15.0 From: DOMINGO SAMPAYO Final Due Date: 03/06/20 Subject: ACCESS HATCHES AND RESTRICTOR ASSEMBLIES (EAST & WEST DETENTION TANKS) Description: ACCESS HATCHES AND RESTRICTOR ASSEMBLIES AS SHOWN ON C300-WEST DETENTION VAULT DETAILS AND C301 EAST DETENTION VAULT DETAILS. Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 04625 | Review Response | Approved as Noted | 2020-02-27 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached materials submittal review. - J. Grant, DCI Engineers | Info Exchange
| 06269 | Responded and Closed | Approved as Noted | 2020-02-27 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached materials submittal review. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-02-11 |  | 33 41 00-15 Acc. Hatches & Restrictor (E & W Det. Tanks).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-02-11 |  | 33 41 00-15 Acc. Hatches & Restrictor (E & W Det. Tanks).pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-02-10 02:00 |  | 33 41 00-15 Acc. Hatches & Restrictor (E & W Det. Tanks).pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-02-27 |  | 33 41 00-15 Acc. Hatches & Restrictor (E & W Det. Tanks)_DCI_POP.pdf
33 41 00-016-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-016-00 Storm & Sewer Package #3 (1st Ave N) | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-13 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-04-27 | 2020-04-20 | 8 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2020-04-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05296 | Received | For Review | 2020-04-13 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-04-27 | Submittal Number: 33 41 00-16.0 From: JUAN BOLANOS Final Due Date: 04/20/20 Subject: STORM & SEWER PACKAGE #3 (1ST AVE N) Description: PREVIOUSLY MATERIAL HAVE BEEN APPROVED BUT NEW MANUFACTURE MATERIAL IS PLANNED TO BE USE. DETECTABLE TAPE 334100-1 REV 2 SECTION 312000 PART 2.1 E FITTING SPECIFICATIONS 334100-1 REV 2 SECTION 334100 PART 2.1 C GASKET Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 07204 | Forwarded | For Review | 2020-04-13 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-04-20 | Submittal Number: 33 41 00-16.0 From: JUAN BOLANOS Final Due Date: 04/20/20 Subject: STORM & SEWER PACKAGE #3 (1ST AVE N) Description: PREVIOUSLY MATERIAL HAVE BEEN APPROVED BUT NEW MANUFACTURE MATERIAL IS PLANNED TO BE USE. DETECTABLE TAPE 334100-1 REV 2 SECTION 312000 PART 2.1 E FITTING SPECIFICATIONS 334100-1 REV 2 SECTION 334100 PART 2.1 C GASKET Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 05448 | Review Response | Approved as Noted | 2020-04-15 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached. - J. Grant, DCI Engineers | Info Exchange
| 07393 | Responded and Closed | Approved as Noted | 2020-04-20 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-13 |  | 33 41 00-16 Storm & Sewer Package #3 (1st Ave N).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-04-13 |  | 33 41 00-16 Storm & Sewer Package #3 (1st Ave N).pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-04-12 02:00 |  | 33 41 00-16 Storm & Sewer Package #3 (1st Ave N).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-04-20 02:00 |  | 33 41 00-16 Storm & Sewer Package #3 (1st Ave N)_DCI_POP.pdf
33 41 00-017-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-017-00 Catch Basins TYPE 50 (CB-S1, CB-S2, CB-S12) - SCL Work & Bressi | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-07-15 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-07-29 | 2020-07-20 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2020-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06981 | Received | For Review | 2020-07-15 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-07-29 | Submittal Number: 33 41 00-17.0 From: DOMINGO SAMPAYO Final Due Date: 07/29/20 Subject: CATCH BASINS TYPE 50 (CB-S1, CB-S2, CB-S12) - SCL WORK & BRESSI Description: CATCH BASINS TYPE 50 (CB-S1, CB-S2, CB-S12) FO TTHE SCL & BRESSI WORK. Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 09347 | Forwarded | For Review | 2020-07-15 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-07-22 | Submittal Number: 33 41 00-17.0 From: DOMINGO SAMPAYO Final Due Date: 07/29/20 Subject: CATCH BASINS TYPE 50 (CB-S1, CB-S2, CB-S12) - SCL WORK & BRESSI Description: CATCH BASINS TYPE 50 (CB-S1, CB-S2, CB-S12) FO TTHE SCL & BRESSI WORK. Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 07036 | Review Response | Approved | 2020-07-20 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached review of the materials submittal. - J. Grant, DCI Engineers | Info Exchange
| 09422 | Responded and Closed | Approved | 2020-07-20 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved) from: Jarrett Grant (DCI Engineers) Remarks: See attached review of the materials submittal. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-07-14 |  | 33 41 00-17 Catch Basins TYPE 50.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-07-14 |  | 33 41 00-17 Catch Basins TYPE 50.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-07-14 |  | 33 41 00-17 Catch Basins TYPE 50.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-20 |  | 33 41 00-17 Catch Basins TYPE 50_DCI_POP.pdf
33 41 00-018-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-018-00 Storm & Sewer Submittal Package (1st Ave) - UPDATED | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-09-18 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-10-02 | 2020-10-05 | 18 |  | Record Copies; Transfers; Submittals |  | 18 |  | 2020-10-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 08198 | Received | For Review | 2020-09-18 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Domingo Sampayo (M.A. Mortenson Company) | 2020-10-02 | Submittal Number: 33 41 00-18.0 From: DOMINGO SAMPAYO Final Due Date: 10/07/20 Subject: STORM & SEWER SUBMITTAL PACKAGE (1ST AVE) - UPDATED Description: Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 10884 | Forwarded | For Review | 2020-09-18 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-09-25 | Submittal Number: 33 41 00-18.0 From: DOMINGO SAMPAYO Final Due Date: 10/07/20 Subject: STORM & SEWER SUBMITTAL PACKAGE (1ST AVE) - UPDATED Description: Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 08542 | Review Response | Approved as Noted | 2020-10-05 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached. All materials to be used within City of Seattle Right-of-way will need to be reviewed and approved by SDOT and SPU. - J. Grant, DCI Engineers | Info Exchange
| 11300 | Responded and Closed | Approved as Noted | 2020-10-05 | Josh Dobken (Populous) | Danny Keim (M.A. Mortenson Company); Domingo Sampayo (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached. All materials to be used within City of Seattle Right-of-way will need to be reviewed and approved by SDOT and SPU. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-09-18 |  | 33 41 00-18 Storm & Sewer Pack (1st Ave).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-09-18 |  | 33 41 00-18 Storm & Sewer Pack (1st Ave).pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-09-17 02:00 |  | 33 41 00-18 Storm & Sewer Pack (1st Ave).pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2020-10-05 02:00 |  | 33 41 00-18 Storm & Sewer Pack (1st Ave)_DCI_POP.pdf
33 41 00-019-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-019-00 N-Courtyard Submittal Package | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-03-02 | Responded and Closed - Revise and Resubmit |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-03-16 | 2021-03-09 | 8 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-03-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 11742 | Received | For Review | 2021-03-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-03-16 | Submittal Number: 33 41 00-19.0 From: DOMINGO SAMPAYO Final Due Date: 03/05/21 Subject: N-COURTYARD SUBMITTAL PACKAGE Description: Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 15214 | Forwarded | For Review | 2021-03-02 | Christian Albers (Mortenson Construction) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-03-09 | Submittal Number: 33 41 00-19.0 From: DOMINGO SAMPAYO Final Due Date: 03/05/21 Subject: N-COURTYARD SUBMITTAL PACKAGE Description: Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 11860 | Review Response | Revise and Resubmit | 2021-03-02 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached review. - J. Grant, DCI Engineers | Info Exchange
| 15234 | Forwarded | For Review | 2021-03-02 | Josh Dobken (Populous) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-03-09 | Submittal Number: 33 41 00-19.0 From: DOMINGO SAMPAYO Final Due Date: 03/05/21 Subject: N-COURTYARD SUBMITTAL PACKAGE Description: Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 11861 | Review Response | Not Required For Review | 2021-03-04 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  |  | Info Exchange
| 15380 | Responded and Closed | Revise and Resubmit | 2021-03-09 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | Response (Revise and Resubmit) from: Jarrett Grant (DCI Engineers) Remarks: See attached review. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-03-02 |  | 33 41 00-19.0 North Courtyard Submittal Package.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-03-02 |  | 33 41 00-19.0 North Courtyard Submittal Package.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-03-02 |  | 33 41 00-19.0 North Courtyard Submittal Package.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-03-01 02:00 |  | 33 41 00-19.0 North Courtyard Submittal Package.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-03-01 |  | 33 41 00-19.0 North Courtyard Submittal Package.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-03-09 |  | 33 41 00-19.0 North Courtyard Submittal Package_DCI_SWIFT_POP.pdf
33 41 00-019-01 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-019-01 N-Courtyard Submittal Package | Closed | Civil, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-04 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers), Rhys Van Bemmel (Swift and Company Landscape Arch), Gareth Loveridge (Swift and Company Landscape Arch) |  |  |  | 2021-05-18 | 2021-05-12 | 9 |  | Record Copies; Transfers; Submittals |  | 9 |  | 2021-05-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 12931 | Received | For Review | 2021-05-04 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Albers (Mortenson Construction) | 2021-05-18 | Submittal Number: 33 41 00-19.1 From: CHRISTIAN ALBERS Final Due Date: 03/05/21 Subject: N-COURTYARD SUBMITTAL PACKAGE Description: SEE ATTACHED REVISION CLARIFYING THE LOCATION OF CB 241 REFERENCED IN THE SUBMITTAL PACKAGE. Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 16719 | Forwarded | For Review | 2021-05-04 | Christian Albers (Mortenson Construction) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2021-05-11 | Submittal Number: 33 41 00-19.1 From: CHRISTIAN ALBERS Final Due Date: 03/05/21 Subject: N-COURTYARD SUBMITTAL PACKAGE Description: SEE ATTACHED REVISION CLARIFYING THE LOCATION OF CB 241 REFERENCED IN THE SUBMITTAL PACKAGE. Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 16747 | Forwarded | For Review | 2021-05-05 | Christian Albers (Mortenson Construction) | Rhys Van Bemmel (Swift and Company Landscape Arch); Gareth Loveridge (Swift and Company Landscape Arch) | 2021-05-12 | Submittal Number: 33 41 00-19.1 From: CHRISTIAN ALBERS Final Due Date: 03/05/21 Subject: N-COURTYARD SUBMITTAL PACKAGE Description: SEE ATTACHED REVISION CLARIFYING THE LOCATION OF CB 241 REFERENCED IN THE SUBMITTAL PACKAGE. Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 13025 | Review Response | Approved as Noted | 2021-05-07 | Jarrett Grant (DCI Engineers) | Christian Albers (Mortenson Construction) |  | See attached submittal review. - J. Grant, DCI Engineers | Info Exchange
| 13073 | Review Response | Approved | 2021-05-12 | Rhys Van Bemmel (Swift and Company Landscape Arch) | Josh Dobken (Populous) |  | Approved for perforated pipe and filter fabric only. All other items per civil review. | Info Exchange
| 16910 | Responded and Closed | Approved as Noted | 2021-05-12 | Christian Albers (Mortenson Construction) | Danny Keim (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Albers (Mortenson Construction) |  | Response (Approved as Noted) from: Jarrett Grant (DCI Engineers) Remarks: See attached submittal review. - J. Grant, DCI Engineers Response (Approved) from: Rhys Van Bemmel (Swift and Company Landscape Arch) Remarks: Approved for perforated pipe and filter fabric only. All other items per civil review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-04 |  | 33 41 00-019.1 - North Courtyard Submittal Package.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-04 |  | 33 41 00-019.1 - North Courtyard Submittal Package.pdf
| Forwarded |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-04 |  | 33 41 00-019.1 - North Courtyard Submittal Package.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-05-03 02:00 |  | 33 41 00-019.1 - North Courtyard Submittal Package.pdf
| Review Response |  | Rhys Van Bemmel (Swift and Company Landscape Arch) | 1 | 2021-05-03 02:00 |  | 33 41 00-019.1 - North Courtyard Submittal Package.pdf
| Responded and Closed |  | Christian Albers (Mortenson Construction) | 1 | 2021-05-12 02:00 |  | 33 41 00-019.1 - North Courtyard Submittal Package - Swift_DCI_POP.pdf
33 41 00-020-00 | 33 41 00 - STORM UTILITY DRAINAGE PIPING | 33 41 00-020-00 Grout for Precast Storm Vault | Closed | Civil, Landscape | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-05-21 | Responded and Closed - Approved |  | Rhys Van Bemmel (Swift and Company Landscape Arch), Damon Smith (DCI Engineers), Gareth Loveridge (Swift and Company Landscape Arch), Jarrett Grant (DCI Engineers) |  |  |  | 2021-06-07 07:00 | 2021-06-07 | 18 |  | Record Copies; Transfers; Submittals |  | 13 |  | 2021-06-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13224 | Received | For Review | 2021-05-21 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Christian Generosa | 2021-06-07 07:00 | Submittal Number: 33 41 00-20.0 From: JUAN BOLANOS Final Due Date: 06/04/21 Subject: GROUT FOR PRECAST STORM VAULT Description: GROUT PRODUCT THAT WILL BE USE ON THE PRECAST STORM VAULT. Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 17113 | Forwarded | For Review | 2021-05-21 | Christian Generosa | Rhys Van Bemmel (Swift and Company Landscape Arch); Damon Smith (DCI Engineers); Gareth Loveridge (Swift and Company Landscape Arch); Jarrett Grant (DCI Engineers) | 2021-05-28 | Submittal Number: 33 41 00-20.0 From: JUAN BOLANOS Final Due Date: 06/04/21 Subject: GROUT FOR PRECAST STORM VAULT Description: GROUT PRODUCT THAT WILL BE USE ON THE PRECAST STORM VAULT. Spec Section: 33 41 00 - STORM UTILITY DRAINAGE PIPING Status: OPEN | Info Exchange
| 13438 | Review Response | Approved | 2021-06-02 | Jarrett Grant (DCI Engineers) | Christian Generosa |  | See attached review. - J. Grant, DCI Engineers | Info Exchange
| 17378 | Responded and Closed | Approved | 2021-06-07 | Christian Generosa | Danny Keim (Mortenson Construction); Domingo Sampayo (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction); Christian Generosa |  | Response (Approved) from: Jarrett Grant (DCI Engineers) Remarks: See attached review. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-05-21 |  | 2021-05-21 334100-0020-00 Grout for Precast Storm Vault_MAM.pdf
| Forwarded |  | Christian Generosa | 1 | 2021-05-21 |  | 2021-05-21 334100-0020-00 Grout for Precast Storm Vault_MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2021-05-20 02:00 |  | 2021-05-21 334100-0020-00 Grout for Precast Storm Vault_MAM.pdf
| Responded and Closed |  | Christian Generosa | 1 | 2021-06-07 02:00 |  | 33 41 00-020-00 Grout for Precast Storm Vault_MAM_DCI_POP.pdf
33 46 00-001-00 | 33 46 00 - SUBDRAINAGE | 33 46 00-001-00 SUBDRAINAGE - Product Data | Closed | Utilities | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-01-02 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-01-16 | 2020-01-02 | 1 | General | Record Copies; Transfers; Submittals |  | 1 |  | 2020-01-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 03751 | Received | For Review | 2020-01-02 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (Mortenson Construction) | 2020-01-16 | Submittal Number: 33 46 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 01/15/20 Subject: SUBDRAINAGE - PRODUCT DATA Description: PRODUCT DATA : - 1. DRAINAGE PANELS, INCLUDING RATED CAPACITIES. 2. GEOTEXTILE FILTER FABRICS. Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Info Exchange
| 05285 | Forwarded | For Review | 2020-01-02 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-01-09 | Submittal Number: 33 46 00-1.0 From: GRETCHEN TOSHACH Final Due Date: 01/15/20 Subject: SUBDRAINAGE - PRODUCT DATA Description: PRODUCT DATA : - 1. DRAINAGE PANELS, INCLUDING RATED CAPACITIES. 2. GEOTEXTILE FILTER FABRICS. Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Info Exchange
| 05293 | Responded and Closed | Approved | 2020-01-02 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (Mortenson Construction) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-12-31 |  | 33 4600 Subdrainage Agg-Pipe-Sock Product Data - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-12-31 |  | 33 4600 Subdrainage Agg-Pipe-Sock Product Data - MAM.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2020-01-02 |  | 33 4600 Subdrainage Agg-Pipe-Sock Product Data - MAM POP.pdf
33 46 00-001-01 | 33 46 00 - SUBDRAINAGE | 33 46 00-001-01 SUBDRAINAGE - Product Data | Closed | Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-24 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers) |  |  |  | 2020-05-08 | 2020-04-28 | 5 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2020-04-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05539 | Received | For Review | 2020-04-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA | 2020-05-08 | Submittal Number: 33 46 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 05/15/20 Subject: SUBDRAINAGE - PRODUCT DATA Description: PRODUCT DATA : - 1. DRAINAGE PANELS, INCLUDING RATED CAPACITIES. 2. GEOTEXTILE FILTER FABRICS. Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Info Exchange
| 07512 | Forwarded | For Review | 2020-04-24 | Populous SCA_CCA | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-05-01 | Submittal Number: 33 46 00-1.1 From: GRETCHEN TOSHACH Final Due Date: 05/15/20 Subject: SUBDRAINAGE - PRODUCT DATA Description: PRODUCT DATA : - 1. DRAINAGE PANELS, INCLUDING RATED CAPACITIES. 2. GEOTEXTILE FILTER FABRICS. Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Info Exchange
| 05600 | Review Response | Approved | 2020-04-27 | Jarrett Grant (DCI Engineers) | Populous SCA_CCA |  | See attached review of the material submittal. - J. Grant, DCI Engineers | Info Exchange
| 07590 | Responded and Closed | Approved | 2020-04-28 | Populous SCA_CCA | Danny Keim (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Gretchen Toshach (M.A. Mortenson Company) |  | Response (Approved) from: Jarrett Grant (DCI Engineers) Remarks: See attached review of the material submittal. - J. Grant, DCI Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-24 |  | 33 46 00-1.1 Subdrainage Pipe - MAM.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2020-04-24 |  | 33 46 00-1.1 Subdrainage Pipe - MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-04-23 02:00 |  | 33 46 00-1.1 Subdrainage Pipe - MAM.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-28 02:00 |  | 33 46 00-1.1 Subdrainage Pipe - DCI_POP.pdf
33 46 00-002-00 | 33 46 00 - SUBDRAINAGE | 33 46 00-002-00 SUBDRAINAGE - Shop Drawings | Closed | Plumbing, Civil | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2019-08-22 | Responded and Closed - Approved as Noted |  | Damon Smith (DCI Engineers), Darren Simpson (DCI Engineers), Jarrett Grant (DCI Engineers), Tom Usher (Populous), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Brice Exley (Hart Crowser), Joseph Harmon (Hart Crowser), David Winter (Hart Crowser) |  |  |  | 2019-09-05 | 2019-09-10 | 20 |  | Record Copies; Transfers; Submittals |  | 20 |  | 2019-09-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 02170 | Received | For Review | 2019-08-22 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Patrick Klein (Mortenson Construction); . (Seattle Arena Company, LLC) | 2019-09-05 | Submittal Number: 33 46 00-2.0 From: PATRICK KLEIN Final Due Date: 09/04/19 Subject: SUBDRAINAGE - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DEWATERING SYSTEM, PREPARED BY OR UNDER THE SUPERVISION OFA QUALIFIED PROFESSIONAL ENGINEER. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND DETAILS. 2. SHOW ARRANGEMENT, LOCATIONS OF RISERS, HEADERS, PUMPS, AND DISCHARGE LINES; AND MEANS OF DISCHARGE, AND DISPOSAL OF WATER. Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Info Exchange
| 03369 | Forwarded | For Review | 2019-08-21 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Darren Simpson (DCI Engineers); Jarrett Grant (DCI Engineers) | 2019-08-28 | Submittal Number: 33 46 00-2.0 From: PATRICK KLEIN Final Due Date: 09/04/19 Subject: SUBDRAINAGE - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DEWATERING SYSTEM, PREPARED BY OR UNDER THE SUPERVISION OFA QUALIFIED PROFESSIONAL ENGINEER. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND DETAILS. 2. SHOW ARRANGEMENT, LOCATIONS OF RISERS, HEADERS, PUMPS, AND DISCHARGE LINES; AND MEANS OF DISCHARGE, AND DISPOSAL OF WATER. Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Info Exchange
| 02332 | Review Response | Approved as Noted | 2019-09-06 | Darren Simpson (DCI Engineers) | Shaina Burris (Populous) |  | This submittal should be reviewed by Mechanical and Geotechnical | Info Exchange
| 03569 | Forwarded | For Review | 2019-09-06 | Josh Dobken (Populous) | Tom Usher (Populous); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Brice Exley (Hart Crowser); Joseph Harmon (Hart Crowser) | 2019-09-05 | Submittal Number: 33 46 00-2.0 From: PATRICK KLEIN Final Due Date: 09/04/19 Subject: SUBDRAINAGE - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DEWATERING SYSTEM, PREPARED BY OR UNDER THE SUPERVISION OFA QUALIFIED PROFESSIONAL ENGINEER. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND DETAILS. 2. SHOW ARRANGEMENT, LOCATIONS OF RISERS, HEADERS, PUMPS, AND DISCHARGE LINES; AND MEANS OF DISCHARGE, AND DISPOSAL OF WATER. Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Email
| 02346 | Review Response | No Action Taken or Required | 2019-09-09 | Dave Ferguson (ME Engineers) | Josh Dobken (Populous) |  | Reviewed. See attached David J. Ferguson, P.E. ME Engineers, Inc. 9 September 2019 | Info Exchange
| 03583 | Forwarded | For Review | 2019-09-09 | Josh Dobken (Populous) | David Winter (Hart Crowser); Brice Exley (Hart Crowser); Joseph Harmon (Hart Crowser) | 2019-09-05 | Submittal Number: 33 46 00-2.0 From: PATRICK KLEIN Final Due Date: 09/04/19 Subject: SUBDRAINAGE - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DEWATERING SYSTEM, PREPARED BY OR UNDER THE SUPERVISION OFA QUALIFIED PROFESSIONAL ENGINEER. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND DETAILS. 2. SHOW ARRANGEMENT, LOCATIONS OF RISERS, HEADERS, PUMPS, AND DISCHARGE LINES; AND MEANS OF DISCHARGE, AND DISPOSAL OF WATER. Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Email
| 03609 | Responded and Closed | Approved as Noted | 2019-09-10 | Josh Dobken (Populous) | Danny Keim (Mortenson Construction); Patrick Klein (Mortenson Construction); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | See notes from Tom Usher in attached submittal. Hart Crowser comments address requirement for tunnel drainage only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2019-08-21 |  | 33 46 00-2.0 Shop Drawings-MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2019-08-21 |  | 33 46 00-2.0 Shop Drawings-MAM.pdf
| Review Response |  | Darren Simpson (DCI Engineers) | 1 | 2019-08-20 02:00 |  | 33 46 00-2.0 Shop Drawings-MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-08-20 02:00 |  | 33 46 00-2.0 Shop Drawings-MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2019-09-09 02:00 |  | 33 46 00-2.0 Shop Drawings_MEE Review_9 Sep 19.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2019-08-20 02:00 |  | 33 46 00-2.0 Shop Drawings-MAM.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2019-09-10 02:00 |  | 33 46 00-2.0 Shop Drawings_MEE Review_9 Sep 19 POP.pdf
33 46 00-002-01 | 33 46 00 - SUBDRAINAGE | 33 46 00-002-01 SUBDRAINAGE SD | Closed | Civil, Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-06-17 | Responded and Closed - Revise and Resubmit |  | Damon Smith (DCI Engineers), Jarrett Grant (DCI Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-07-01 | 2020-07-17 | 31 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2020-07-17
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 06466 | Received | For Review | 2020-06-17 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-07-01 | Submittal Number: 33 46 00-2.1 From: PATRICK KLEIN Final Due Date: 06/22/20 Subject: SUBDRAINAGE - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DEWATERING SYSTEM, PREPARED BY OR UNDER THE SUPERVISION OFA QUALIFIED PROFESSIONAL ENGINEER. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND DETAILS. 2. SHOW ARRANGEMENT, LOCATIONS OF RISERS, HEADERS, PUMPS, AND DISCHARGE LINES; AND MEANS OF DISCHARGE, AND DISPOSAL OF WATER. UPDATED SHOP DRAWINGS, PER ISSUED DOCUMENTS IN APRIL 2020 Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Info Exchange
| 08715 | Forwarded | For Review | 2020-06-17 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Jarrett Grant (DCI Engineers) | 2020-06-24 | Submittal Number: 33 46 00-2.1 From: PATRICK KLEIN Final Due Date: 06/22/20 Subject: SUBDRAINAGE - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DEWATERING SYSTEM, PREPARED BY OR UNDER THE SUPERVISION OFA QUALIFIED PROFESSIONAL ENGINEER. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND DETAILS. 2. SHOW ARRANGEMENT, LOCATIONS OF RISERS, HEADERS, PUMPS, AND DISCHARGE LINES; AND MEANS OF DISCHARGE, AND DISPOSAL OF WATER. UPDATED SHOP DRAWINGS, PER ISSUED DOCUMENTS IN APRIL 2020 Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Info Exchange
| 08837 | Forwarded | For Review | 2020-06-23 | Josh Dobken (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2020-06-30 | Submittal Number: 33 46 00-2.1 From: PATRICK KLEIN Final Due Date: 06/22/20 Subject: SUBDRAINAGE - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DEWATERING SYSTEM, PREPARED BY OR UNDER THE SUPERVISION OFA QUALIFIED PROFESSIONAL ENGINEER. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND DETAILS. 2. SHOW ARRANGEMENT, LOCATIONS OF RISERS, HEADERS, PUMPS, AND DISCHARGE LINES; AND MEANS OF DISCHARGE, AND DISPOSAL OF WATER. UPDATED SHOP DRAWINGS, PER ISSUED DOCUMENTS IN APRIL 2020 Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Info Exchange
| 07010 | Review Response | No Action Taken or Required | 2020-06-23 | Dave Ferguson (ME Engineers) | Josh Dobken (Populous) |  | Reviewed. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 23 June 2020 | Info Exchange
| 07075 | Review Response | Approved as Noted | 2020-07-10 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | See attached review. - J. Grant, DCI Engineers | Info Exchange
| 09388 | Responded and Closed | Revise and Resubmit | 2020-07-17 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  | Comments/layout corrections from RFI 2584 need to be incorporated before approval (attached for reference). Bryan Klote/Populous 07.17.2020 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-06-17 |  | 33 46 00-2.0 Sub Slab Drainage - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-06-17 |  | 33 46 00-2.0 Sub Slab Drainage - MAM.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2020-06-16 02:00 |  | 33 46 00-2.0 Sub Slab Drainage - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-06-16 |  | 33 46 00-2.0 Sub Slab Drainage - MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-06-16 02:00 |  | 33 46 00-2.0 Sub Slab Drainage - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-07-17 |  | 33 46 00-2.0 Sub Slab Drainage - MAM_DCI_POP.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-06-12 |  | SCA - Underslab Drainage Floor Cleanouts CCD057_MEE Comments_12 Jun 20_COMBINED.pdf
33 46 00-002-02 | 33 46 00 - SUBDRAINAGE | 33 46 00-002-02 SUBDRAINAGE - Shop Drawings | Closed | Civil, Plumbing | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-08-24 | Responded and Closed - Approved |  | Damon Smith (DCI Engineers), Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Jarrett Grant (DCI Engineers), Heidi Evans (ME Engineers) |  |  |  | 2020-09-08 07:00 | 2020-09-01 | 9 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2020-09-01
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 07704 | Received | For Review | 2020-08-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Gretchen Toshach (M.A. Mortenson Company) | 2020-09-08 07:00 | Submittal Number: 33 46 00-2.2 From: GRETCHEN TOSHACH Final Due Date: 09/07/20 Subject: SUBDRAINAGE - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DEWATERING SYSTEM, PREPARED BY OR UNDER THE SUPERVISION OFA QUALIFIED PROFESSIONAL ENGINEER. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND DETAILS. 2. SHOW ARRANGEMENT, LOCATIONS OF RISERS, HEADERS, PUMPS, AND DISCHARGE LINES; AND MEANS OF DISCHARGE, AND DISPOSAL OF WATER. UPDATED SHOP DRAWINGS, PER ISSUED DOCUMENTS IN APRIL 2020 Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Info Exchange
| 10253 | Forwarded | For Review | 2020-08-24 | Shaina Burris (Populous) | Damon Smith (DCI Engineers); Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Jarrett Grant (DCI Engineers); Heidi Evans (ME Engineers) | 2020-08-31 | Submittal Number: 33 46 00-2.2 From: GRETCHEN TOSHACH Final Due Date: 09/07/20 Subject: SUBDRAINAGE - SHOP DRAWINGS Description: SHOP DRAWINGS : FOR DEWATERING SYSTEM, PREPARED BY OR UNDER THE SUPERVISION OFA QUALIFIED PROFESSIONAL ENGINEER. 1. INCLUDE PLANS, ELEVATIONS, SECTIONS, AND DETAILS. 2. SHOW ARRANGEMENT, LOCATIONS OF RISERS, HEADERS, PUMPS, AND DISCHARGE LINES; AND MEANS OF DISCHARGE, AND DISPOSAL OF WATER. UPDATED SHOP DRAWINGS, PER ISSUED DOCUMENTS IN APRIL 2020 Spec Section: 33 46 00 - SUBDRAINAGE Status: OPEN | Info Exchange
| 07889 | Review Response | No Action Taken or Required | 2020-08-24 | Dave Ferguson (ME Engineers) | Populous SCA_CCA |  | Reviewed. No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 24 August 2020 | Info Exchange
| 07923 | Review Response | Approved as Noted | 2020-08-28 | Jarrett Grant (DCI Engineers) | Shaina Burris (Populous) |  | Deferring to architect. See attached. - J. Grant, DCI Engineers | Info Exchange
| 10491 | Responded and Closed | Approved | 2020-09-01 | Bryan Klote (Populous) | Danny Keim (M.A. Mortenson Company); Patrick Klein (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction); Simran George (M.A. Mortenson Company); Gretchen Toshach (M.A. Mortenson Company) |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-08-24 |  | 33 46 00-2.2 Sub Slab Drainage - MAM.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2020-08-24 |  | 33 46 00-2.2 Sub Slab Drainage - MAM.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2020-08-24 |  | 33 46 00-2.2 Sub Slab Drainage - MAM.pdf
| Review Response |  | Jarrett Grant (DCI Engineers) | 1 | 2020-08-23 02:00 |  | 33 46 00-2.2 Sub Slab Drainage - MAM.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2020-09-01 |  | 33 46 00-2.2 Sub Slab Drainage - MAM_DCI_POP.pdf
46.0 | 08 11 13 - HOLLOW METAL DOORS AND FRAMES | Non-Priority Doors & Frames - Event Level | Closed |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2020-04-20 | Responded and Closed - Rejected | [5 empty] | 2020-05-04 | 2020-04-24 | 5 |  | Record Copies; Transfers; Submittals |  | -1 |  | 2020-04-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 05537 | Received | For Review | 2020-04-20 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Populous SCA_CCA; Tyrone Thornton (M.A. Mortenson Company) | 2020-05-04 | Submittal Number: 46.0 From: TYRONE THORNTON Final Due Date: 05/13/20 Subject: NON-PRIORITY DOORS & FRAMES - EVENT LEVEL Description: THIS SUBMITTAL WILL INCLUDE ALL REMAINING NON-PRIORITY DOORS AND FRAMES ON EVENT LEVEL. Spec Section: Status: OPEN | Info Exchange
| 07507 | Responded and Closed | Rejected | 2020-04-24 | Populous SCA_CCA | Tyrone Thornton (M.A. Mortenson Company); AI Assistant Mortenson Procore Connector (Mortenson Construction) |  | This submittal does not follow numbering protocols. Resubmit with required corrections. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2020-04-18 02:00 |  | SCA - Event Level (Remaining) Doors Submittal_ MAM Review.pdf
| Responded and Closed |  | Populous SCA_CCA | 1 | 2020-04-18 02:00 |  | SCA - Event Level (Remaining) Doors Submittal_ MAM Review.pdf
RS 05 12 00-001-00 | 05 12 00 - STEEL | RS 05 12 00-001-00 Structural Steel Erection and Shop Drawings | Closed | Structural, Architectural | Mark.Nonato@bnbuilders.com | 2021-07-08 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-13 07:00 | 2021-07-12 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13841 | Received | For Review | 2021-07-08 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-07-13 07:00 | Kuebler/Shaina, Please see attached Submittal: RS 051200-001-0 Structural Steel Erection and Shop Drawings for review and approval. NOTE: This is a HOT submittal and need an expedited review. Please turn around by today or tomorrow at the latest. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17916 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Sean McNeill (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-15 | Kuebler/Shaina, Please see attached Submittal: RS 051200-001-0 Structural Steel Erection and Shop Drawings for review and approval. NOTE: This is a HOT submittal and need an expedited review. Please turn around by today or tomorrow at the latest. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13957 | Review Response | Approved as Noted/Resubmit | 2021-07-09 | Matt Ross (Thornton Tomasetti) | Kuebler Perry (Populous); Shaina Burris (Populous) |  | Resubmit Upper Concourse Door Jambs per comments and response to RFI RS-0003. All other parts of submittal are approved as noted. Arch to review. | Info Exchange
| 13885 | Review Response | Approved as Noted | 2021-07-12 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17975 | Responded and Closed | Approved as Noted | 2021-07-12 | Kuebler Perry (Populous) | Mark.Nonato@bnbuilders.com |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-08 |  | RS 051200-001-0 Structural Steel Erection and Shop Drawings - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-08 |  | RS 051200-001-0 Structural Steel Erection and Shop Drawings - For Approval.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-07-07 02:00 |  | RS 051200-001-0 Structural Steel Erection and Shop Drawings - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-12 |  | RS 051200-001-0 Structural Steel Erection and Shop Drawings - For Approval_TT_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-08 |  | RS 051200-001-0 Structural Steel Erection and Shop Drawings - For Approval.pdf
RS 05 12 00-001-01 | 05 12 00 - STEEL | RS 05 12 00-001-01 Revised Overhead Door Support | Closed | Structural | Mark Nonato | 2021-08-04 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-08-06 07:00 | 2021-08-05 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-08-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14214 | Received | For Review | 2021-08-04 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti); Shaina Burris (Populous) | 2021-08-06 07:00 | Kuebler/Matthew, Please see attached Submittal: RS 051200-001-1 Revised Overhead Door Support for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18367 | Forwarded | For Review | 2021-08-04 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-08-11 | Kuebler/Matthew, Please see attached Submittal: RS 051200-001-1 Revised Overhead Door Support for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14269 | Review Response | Approved as Noted | 2021-08-05 | Matt Ross (Thornton Tomasetti) | Kuebler Perry (Populous); Shaina Burris (Populous); Chad Francis (Populous) |  | Arch to review. | Info Exchange
| 14227 | Review Response | Approved as Noted | 2021-08-05 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18383 | Responded and Closed | Approved as Noted | 2021-08-05 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-04 |  | RS 051200-001-1 Revised Overhead Door Support - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-04 |  | RS 051200-001-1 Revised Overhead Door Support - For Approval.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-08-03 02:00 |  | RS 051200-001-1 Revised Overhead Door Support - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-05 |  | RS 051200-001-1 RevOverhead DSupportl_TT-POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-04 |  | RS 051200-001-1 Revised Overhead Door Support - For Approval.pdf
RS 05 12 00-002-00 | 05 12 00 - STEEL | RS 05 12 00-002-00 Jersey Coaster Support Steel | Closed | Structural | Mark Nonato | 2021-08-05 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-08-19 | 2021-08-05 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-08-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14222 | Received | For Review | 2021-08-05 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti); Shaina Burris (Populous) | 2021-08-19 | Kuebler/Matthew, Please see attached Submittal: 051200-002-0 Jersey Coaster Support Steel for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18378 | Forwarded | For Review | 2021-08-04 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-08-11 | Kuebler/Matthew, Please see attached Submittal: 051200-002-0 Jersey Coaster Support Steel for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14270 | Review Response | Approved | 2021-08-05 | Matt Ross (Thornton Tomasetti) | Kuebler Perry (Populous); Shaina Burris (Populous) |  | Arch to Review. | Info Exchange
| 14228 | Review Response | Approved as Noted | 2021-08-05 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18384 | Responded and Closed | Approved as Noted | 2021-08-05 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-04 |  | RS 051200-002-0 Jersey Coaster Support Steel - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-04 |  | RS 051200-002-0 Jersey Coaster Support Steel - For Approval.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-08-03 02:00 |  | RS 051200-002-0 Jersey Coaster Support Steel - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-05 |  | RS 051200-002-0 JC steel - For Approval_TT_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-04 |  | RS 051200-002-0 Jersey Coaster Support Steel - For Approval.pdf
RS 06 41 00-001-00 | 06 41 00 | RS 06 41 00-001-00 Casework Materials | Closed | Architectural | Mark.Nonato@bnbuilders.com | 2021-07-08 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-13 07:00 | 2021-07-12 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13834 | Received | For Review | 2021-07-08 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-07-13 07:00 | Kuebler/Shaina, Please see attached Submittal: RS 064100-001-0 Casework Materials for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17908 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-15 | Kuebler/Shaina, Please see attached Submittal: RS 064100-001-0 Casework Materials for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13895 | Review Response | Approved as Noted | 2021-07-12 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 17992 | Responded and Closed | Approved as Noted | 2021-07-12 | Kuebler Perry (Populous) | Mark.Nonato@bnbuilders.com |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-08 |  | RS 064100-001-0 Casework Materials - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-08 |  | RS 064100-001-0 Casework Materials - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-12 |  | RS 064100-001-0 Casework Materials - For Approval_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-08 |  | RS 064100-001-0 Casework Materials - For Approval.pdf
RS 06 41 00-002-00 | 06 41 00 | RS 06 41 00-002-00 Casework (Cashwrap, Backwrap, Customization Station) | Closed | Architectural | Mark Nonato | 2021-07-12 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-15 07:00 | 2021-07-16 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13892 | Received | For Review | 2021-07-12 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-07-15 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-002-0 Casework (Cashwrap, Backwrap, Customization Station) for review and approval. NOTE: Includes: · Cashwrap o If mobile POS dimensions change Astound can adjust that. · Backwrap o Outer shell right now as Astound’s original scope o If scope changes to add internal structures, Astound can adjust drawings · Customization station Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17987 | Forwarded | For Review | 2021-07-12 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-002-0 Casework (Cashwrap, Backwrap, Customization Station) for review and approval. NOTE: Includes: · Cashwrap o If mobile POS dimensions change Astound can adjust that. · Backwrap o Outer shell right now as Astound’s original scope o If scope changes to add internal structures, Astound can adjust drawings · Customization station Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13983 | Review Response | Revise and Resubmit | 2021-07-16 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18086 | Responded and Closed | Revise and Resubmit | 2021-07-16 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-12 |  | RS 064100-002-0 Casework (Cashwrap, Backwrap, Customization Station) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-12 |  | RS 064100-002-0 Casework (Cashwrap, Backwrap, Customization Station) - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-16 |  | RS 064100-002-0 Casework (Cashwrap, Backwrap, Customization Station) - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-12 |  | RS 064100-002-0 Casework (Cashwrap, Backwrap, Customization Station) - For Approval.pdf
RS 06 41 00-002-01 | 06 41 00 | RS 06 41 00-002-01 Casework (Cashwrap, Backwrap, Customization Station) | Closed | Architectural | Mark Nonato | 2021-07-21 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-04 | 2021-07-21 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-07-21
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14032 | Received | For Review | 2021-07-21 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-08-04 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-002-1 Casework (Cashwrap, Backwrap, Customization Station) for review and approval. NOTE: This is HOT. Please expedite review and return by Friday morning at the latest so that Astound can begin production on Friday to hit their scheduled install date. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18151 | Forwarded | For Review | 2021-07-21 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-28 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-002-1 Casework (Cashwrap, Backwrap, Customization Station) for review and approval. NOTE: This is HOT. Please expedite review and return by Friday morning at the latest so that Astound can begin production on Friday to hit their scheduled install date. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14043 | Review Response | Approved as Noted | 2021-07-21 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached submittal review. Submit shop drawings for heat-press counter. | Info Exchange
| 18168 | Responded and Closed | Approved as Noted | 2021-07-21 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. Submit shop drawings for heat-press counter. | Info Exchange
| 18237 | Sent | For Information Only | 2021-07-26 | Josh Dobken (Populous) | Mark Nonato |  | Responded and Closed (Approved as Noted) to: Mark Nonato Remarks: Refer to attached submittal review. Submit shop drawings for heat-press counter. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-21 |  | RS 064100-002-1 Casework (Cashwrap, Backwrap, Customization Station) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-21 |  | RS 064100-002-1 Casework (Cashwrap, Backwrap, Customization Station) - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-21 |  | RS 064100-002-1 Casework (Cashwrap, Backwrap, Customization Station) - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-16 |  | RS 064100-002-0 Casework - POP.pdf
| Sent |  | Josh Dobken (Populous) | 1 | 2021-07-20 02:00 |  | RS 064100-002-1 Casework (Cashwrap, Backwrap, Customization Station) - For Approval.pdf
RS 06 41 00-003-00 | 06 41 00 | RS 06 41 00-003-00 Casework (TV Bulkhead, Perimeter Doors, Mesh Grid, Mesh Panels) | Closed | Architectural | Mark Nonato | 2021-07-12 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-15 07:00 | 2021-07-16 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-16
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13893 | Received | For Review | 2021-07-12 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-07-15 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-003-0 Casework (TV Bulkhead, Perimeter Doors, Mesh Grid, Mesh Panels) for review and approval. NOTE: Includes: · Suite Level TV Bulkhead o Does this need an engineering stamp? · Perimeter doors o Astound believes these need an engineering stamp. Astound is working on getting the contact info for the person being used on site there. · Free Standing Steel Grid (t-shape) · Suite Level Mesh Panels Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17988 | Forwarded | For Review | 2021-07-12 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-003-0 Casework (TV Bulkhead, Perimeter Doors, Mesh Grid, Mesh Panels) for review and approval. NOTE: Includes: · Suite Level TV Bulkhead o Does this need an engineering stamp? · Perimeter doors o Astound believes these need an engineering stamp. Astound is working on getting the contact info for the person being used on site there. · Free Standing Steel Grid (t-shape) · Suite Level Mesh Panels Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13982 | Review Response | Approved as Noted/Resubmit | 2021-07-16 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18085 | Responded and Closed | Approved as Noted/Resubmit | 2021-07-16 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-12 |  | RS 064100-003-0 Casework (TV Bulkhead, Perimeter Doors, Mesh Grid, Mesh Panels) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-12 |  | RS 064100-003-0 Casework (TV Bulkhead, Perimeter Doors, Mesh Grid, Mesh Panels) - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-16 |  | RS 064100-003-0 Casework (TV Bulkhead, Perimeter Doors, Mesh Grid, Mesh Panels) - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-12 |  | RS 064100-003-0 Casework (TV Bulkhead, Perimeter Doors, Mesh Grid, Mesh Panels) - For Approval.pdf
RS 06 41 00-003-01 | 06 41 00 | RS 06 41 00-003-01 Casework (Pivot Doors) | Closed | Architectural | Mark Nonato | 2021-07-22 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-05 | 2021-07-23 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14045 | Received | For Review | 2021-07-22 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-08-05 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-003-1 Casework (Pivot Doors) for review and approval. NOTE: Attached is the resubmittal of the pivot doors only. Astound only detailed one for approval. Standard review time is acceptable. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18171 | Forwarded | For Review | 2021-07-22 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-29 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-003-1 Casework (Pivot Doors) for review and approval. NOTE: Attached is the resubmittal of the pivot doors only. Astound only detailed one for approval. Standard review time is acceptable. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14080 | Review Response | Revise and Resubmit | 2021-07-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18206 | Responded and Closed | Revise and Resubmit | 2021-07-23 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-22 |  | RS 064100-003-1 Casework (Pivot Doors) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-22 |  | RS 064100-003-1 Casework (Pivot Doors) - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-23 |  | RS 064100-003-1 Casework (Pivot Doors) - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-22 |  | RS 064100-003-1 Casework (Pivot Doors) - For Approval.pdf
RS 06 41 00-003-02 | 06 41 00 | RS 06 41 00-003-02 Casework (Updated Perimeter Doors and Freestanding Grid) | Closed | Architectural | Mark Nonato | 2021-07-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-28 | 2021-07-27 | 2 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14095 | Received | For Review | 2021-07-26 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-07-28 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-003-2 Casework (Updated Perimeter Doors and Freestanding Grid) for review and approval. PLEASE DISREGARD PREVIOUS SUBMISSION. NOTE: Attached are updated Perimeter Door drawings, including hardware which should resolve the comments for revision on the previous submittal. Please note, only (1) left door will have panic hardware, so no bolts, but the other left doors will have a bolt. As for the drawings, the middle and right doors show the bolts. Also attached is the door layout showing gaps between doors. Per conversation between Jen (Astound) and Kuebler(Populous) this morning about the Freestanding Grid. This submittal also included the requested angle hidden on the doors, and hidden on the freestanding grid as well. Thanks, From: Mark Nonato Sent: Friday, July 23, 2021 1:50 PM To: Kuebler Perry <Kuebler.Perry@populous.com>; shaina.burris@populous.com; josh.dobken@populous.com; bryan.klote@populous.com; Chad Francis <Chad.Francis@populous.com> Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; Byron Noll <byron.noll@caaicon.com> Subject: CPA Retail - Submittal: RS 064100-003-2 Casework (Updated Perimeter Doors) Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-003-2 Casework (Updated Perimeter Doors) for review and approval. NOTE: Attached are updated Perimeter Door drawings, including hardware. Please note, only (1) left door will have panic hardware. Also attached is the door layout showing gaps between doors. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18222 | Forwarded | For Review | 2021-07-23 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-30 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-003-2 Casework (Updated Perimeter Doors and Freestanding Grid) for review and approval. PLEASE DISREGARD PREVIOUS SUBMISSION. NOTE: Attached are updated Perimeter Door drawings, including hardware which should resolve the comments for revision on the previous submittal. Please note, only (1) left door will have panic hardware, so no bolts, but the other left doors will have a bolt. As for the drawings, the middle and right doors show the bolts. Also attached is the door layout showing gaps between doors. Per conversation between Jen (Astound) and Kuebler(Populous) this morning about the Freestanding Grid. This submittal also included the requested angle hidden on the doors, and hidden on the freestanding grid as well. Thanks, From: Mark Nonato Sent: Friday, July 23, 2021 1:50 PM To: Kuebler Perry <Kuebler.Perry@populous.com>; shaina.burris@populous.com; josh.dobken@populous.com; bryan.klote@populous.com; Chad Francis <Chad.Francis@populous.com> Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; Byron Noll <byron.noll@caaicon.com> Subject: CPA Retail - Submittal: RS 064100-003-2 Casework (Updated Perimeter Doors) Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-003-2 Casework (Updated Perimeter Doors) for review and approval. NOTE: Attached are updated Perimeter Door drawings, including hardware. Please note, only (1) left door will have panic hardware. Also attached is the door layout showing gaps between doors. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14122 | Review Response | Approved as Noted | 2021-07-27 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached submittal review. | Info Exchange
| 18255 | Responded and Closed | Approved as Noted | 2021-07-27 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-23 |  | RS 064100-003-2 Casework (Updated Perimeter Doors and Freestanding Grid).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-23 |  | RS 064100-003-2 Casework (Updated Perimeter Doors and Freestanding Grid).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-27 |  | RS 064100-003-2 Casework _POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-23 |  | RS 064100-003-2 Casework (Updated Perimeter Doors and Freestanding Grid).pdf
RS 06 41 00-004-00 | 06 41 00 | RS 06 41 00-004-00 Casework (Customization Back Counter) | Closed | Architectural | Mark Nonato | 2021-07-26 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-28 07:00 | 2021-07-27 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14105 | Received | For Review | 2021-07-26 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-07-28 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-004-0 Casework (Customization Back Counter) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18235 | Forwarded | For Review | 2021-07-26 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-02 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-004-0 Casework (Customization Back Counter) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14121 | Review Response | Approved as Noted | 2021-07-27 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached submittal review. | Info Exchange
| 18253 | Responded and Closed | Approved as Noted | 2021-07-27 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-26 |  | RS 064100-004-0 Casework (Customization Back Counter) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-26 |  | RS 064100-004-0 Casework (Customization Back Counter) - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-27 |  | RS 064100-004-0 Casework Back Counter - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-26 |  | RS 064100-004-0 Casework (Customization Back Counter) - For Approval.pdf
RS 06 41 00-005-00 | 06 41 00 | RS 06 41 00-005-00 Casework (Jersey Wall) | Closed | Architectural | Josh Dobken (Populous) | 2021-08-02 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-04 07:00 | 2021-08-25 | 24 |  | Record Copies; Transfers; Submittals |  | 24 |  | 2021-08-25
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14193 | Received | For Review | 2021-08-02 | Josh Dobken (Populous) | Shaina Burris (Populous) | 2021-08-04 07:00 | From: Mark Nonato <Mark.Nonato@bnbuilders.com> Sent: Monday, August 2, 2021 1:11 PM To: Kuebler Perry <Kuebler.Perry@populous.com>; Josh Dobken <Josh.Dobken@populous.com> Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; Byron Noll <byron.noll@caaicon.com> Subject: CPA Retail - Submittal: RS 064100-005-0 Casework (Jersey Wall) Kuebler, Please see attached Preliminary Submittal: RS 064100-004-0 Casework (Customization Back Counter) for review prior to official submittal. NOTE: Attached is a Preliminary submittal for the Jersey Wall. Astound is proposing a build slightly different than what was detailed in an effort to make it structurally sound and accommodate the aesthetic that they are going for. There mentioned that there were some inconclusive details in the Architectural documents, so they would like Populous to get eyes on this and see this is an acceptable direction. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18347 | Forwarded | For Review | 2021-08-02 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-09 | From: Mark Nonato <Mark.Nonato@bnbuilders.com> Sent: Monday, August 2, 2021 1:11 PM To: Kuebler Perry <Kuebler.Perry@populous.com>; Josh Dobken <Josh.Dobken@populous.com> Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; Byron Noll <byron.noll@caaicon.com> Subject: CPA Retail - Submittal: RS 064100-005-0 Casework (Jersey Wall) Kuebler, Please see attached Preliminary Submittal: RS 064100-004-0 Casework (Customization Back Counter) for review prior to official submittal. NOTE: Attached is a Preliminary submittal for the Jersey Wall. Astound is proposing a build slightly different than what was detailed in an effort to make it structurally sound and accommodate the aesthetic that they are going for. There mentioned that there were some inconclusive details in the Architectural documents, so they would like Populous to get eyes on this and see this is an acceptable direction. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 18576 | Forwarded | For Review | 2021-08-17 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-04 | From: Mark Nonato <Mark.Nonato@bnbuilders.com> Sent: Monday, August 2, 2021 1:11 PM To: Kuebler Perry <Kuebler.Perry@populous.com>; Josh Dobken <Josh.Dobken@populous.com> Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; Byron Noll <byron.noll@caaicon.com> Subject: CPA Retail - Submittal: RS 064100-005-0 Casework (Jersey Wall) Kuebler, Please see attached Preliminary Submittal: RS 064100-004-0 Casework (Customization Back Counter) for review prior to official submittal. NOTE: Attached is a Preliminary submittal for the Jersey Wall. Astound is proposing a build slightly different than what was detailed in an effort to make it structurally sound and accommodate the aesthetic that they are going for. There mentioned that there were some inconclusive details in the Architectural documents, so they would like Populous to get eyes on this and see this is an acceptable direction. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 18639 | Forwarded | For Review | 2021-08-24 | Shaina Burris (Populous) | Kuebler Perry (Populous) | 2021-08-04 | From: Mark Nonato <Mark.Nonato@bnbuilders.com> Sent: Monday, August 2, 2021 1:11 PM To: Kuebler Perry <Kuebler.Perry@populous.com>; Josh Dobken <Josh.Dobken@populous.com> Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; Byron Noll <byron.noll@caaicon.com> Subject: CPA Retail - Submittal: RS 064100-005-0 Casework (Jersey Wall) Kuebler, Please see attached Preliminary Submittal: RS 064100-004-0 Casework (Customization Back Counter) for review prior to official submittal. NOTE: Attached is a Preliminary submittal for the Jersey Wall. Astound is proposing a build slightly different than what was detailed in an effort to make it structurally sound and accommodate the aesthetic that they are going for. There mentioned that there were some inconclusive details in the Architectural documents, so they would like Populous to get eyes on this and see this is an acceptable direction. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14474 | Review Response | Approved as Noted | 2021-08-25 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 18667 | Responded and Closed | Approved as Noted | 2021-08-25 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Josh Dobken (Populous) | 1 | 2021-08-02 |  | RS 064100-005-0 Casework (Jersey Wall) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-02 |  | RS 064100-005-0 Casework (Jersey Wall) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-02 |  | RS 064100-005-0 Casework (Jersey Wall) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-02 |  | RS 064100-005-0 Casework (Jersey Wall) - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-25 |  | RS 064100-005-0 Casework (Jersey Wall) -Final_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-02 |  | RS 064100-005-0 Casework (Jersey Wall) - For Approval.pdf
RS 06 41 00-006-00 | 06 41 00 | RS 06 41 00-006-00 Casework (Storage Units and Hat Wall) | Closed | Architectural | Mark Nonato | 2021-08-04 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-06 07:00 | 2021-08-05 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-08-05
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14216 | Received | For Review | 2021-08-04 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-08-06 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-006-0 Casework (Storage Units and Hat Wall) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18369 | Forwarded | For Review | 2021-08-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-11 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-006-0 Casework (Storage Units and Hat Wall) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14231 | Review Response | Approved as Noted | 2021-08-05 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached submittal review. | Info Exchange
| 18387 | Responded and Closed | Approved as Noted | 2021-08-05 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-04 |  | RS 064100-006-0 Casework (Storage Units and Hat Wall) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-04 |  | RS 064100-006-0 Casework (Storage Units and Hat Wall) - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-05 |  | RS 064100-006-0 Storage+Hat wall_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-04 |  | RS 064100-006-0 Casework (Storage Units and Hat Wall) - For Approval.pdf
RS 06 41 00-007-00 | 06 41 00 | RS 06 41 00-007-00 Casework (TV Bulkhead) | Closed | Architectural | Mark Nonato | 2021-08-04 | Responded and Closed - Not Required For Review |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matt Ross (Thornton Tomasetti), Byron Noll (CAA ICON / Strategy Advisory), JSanderson@diversifiedus.com |  |  |  | 2021-08-06 07:00 | 2021-08-09 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-08-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14217 | Received | For Review | 2021-08-04 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); JSanderson@diversifiedus.com | 2021-08-06 07:00 | + Jeff with Diversified From: Mark Nonato Sent: Wednesday, August 4, 2021 12:28 PM To: Kuebler Perry <Kuebler.Perry@populous.com>; shaina.burris@populous.com; josh.dobken@populous.com; bryan.klote@populous.com; Chad Francis <Chad.Francis@populous.com> Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; Byron Noll <byron.noll@caaicon.com> Subject: CPA Retail - Submittal: RS 064100-007-0 Casework (TV Bulkhead) Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-007-0 Casework (TV Bulkhead) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18370 | Forwarded | For Review | 2021-08-04 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-11 | + Jeff with Diversified From: Mark Nonato Sent: Wednesday, August 4, 2021 12:28 PM To: Kuebler Perry <Kuebler.Perry@populous.com>; shaina.burris@populous.com; josh.dobken@populous.com; bryan.klote@populous.com; Chad Francis <Chad.Francis@populous.com> Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; Byron Noll <byron.noll@caaicon.com> Subject: CPA Retail - Submittal: RS 064100-007-0 Casework (TV Bulkhead) Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-007-0 Casework (TV Bulkhead) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 18399 | Forwarded | For Review | 2021-08-06 | Kuebler Perry (Populous) | Matt Ross (Thornton Tomasetti) |  | + Jeff with Diversified From: Mark Nonato Sent: Wednesday, August 4, 2021 12:28 PM To: Kuebler Perry <Kuebler.Perry@populous.com>; shaina.burris@populous.com; josh.dobken@populous.com; bryan.klote@populous.com; Chad Francis <Chad.Francis@populous.com> Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; Byron Noll <byron.noll@caaicon.com> Subject: CPA Retail - Submittal: RS 064100-007-0 Casework (TV Bulkhead) Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-007-0 Casework (TV Bulkhead) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 18408 | Forwarded | For Review | 2021-08-06 | Kuebler Perry (Populous) | Byron Noll (CAA ICON / Strategy Advisory); JSanderson@diversifiedus.com |  | I think this is for Diversified, nothing for us or TT to review- we didn't ask for a resubmit. This has different TV mounting plates to accommodate their equipment. + Jeff with Diversified From: Mark Nonato Sent: Wednesday, August 4, 2021 12:28 PM To: Kuebler Perry <Kuebler.Perry@populous.com>; shaina.burris@populous.com; josh.dobken@populous.com; bryan.klote@populous.com; Chad Francis <Chad.Francis@populous.com> Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; Byron Noll <byron.noll@caaicon.com> Subject: CPA Retail - Submittal: RS 064100-007-0 Casework (TV Bulkhead) Kuebler/Shaina/Josh, Please see attached Submittal: RS 064100-007-0 Casework (TV Bulkhead) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14251 | Review Response | Not Required For Review | 2021-08-09 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18413 | Responded and Closed | Not Required For Review | 2021-08-09 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-04 |  | RS 064100-007-0 Casework (TV Bulkhead) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-04 |  | RS 064100-007-0 Casework (TV Bulkhead) - For Approval.pdf
| Forwarded |  | Kuebler Perry (Populous) | 1 | 2021-08-04 |  | RS 064100-007-0 Casework (TV Bulkhead) - For Approval.pdf
| Forwarded |  | Kuebler Perry (Populous) | 1 | 2021-08-04 |  | RS 064100-007-0 Casework (TV Bulkhead) - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-09 |  | RS 064100-007-0 Casework (TV Bulkhead) - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-04 |  | RS 064100-007-0 Casework (TV Bulkhead) - For Approval.pdf
RS 06 41 00-008-00 | 06 41 00 | RS 06 41 00-008-00 TV Bulkhead (Engineering and Structural Calcs) | Closed | Structural | Mark Nonato | 2021-08-23 | Responded and Closed - Revise and Resubmit |  | Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-08-25 | 2021-08-26 | 4 |  | Record Copies; Transfers; Submittals | RS 06 41 00-008-00-01 - RS 06 41 00-008-00 TV Bulkhead (Engineering and Structural Calcs) | 4 |  | 2021-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14435 | Received | For Review | 2021-08-23 | Mark Nonato | Bryan Klote (Populous); Matthew Farber (Thornton Tomasetti); Kuebler Perry (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti); Shaina Burris (Populous) | 2021-08-25 | Kuebler/Matt, Please see attached Submittal: RS 064100-001-0 TV Bulkhead (Engineering and Structural Calcs) for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18633 | Forwarded | For Review | 2021-08-23 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-08-25 | Kuebler/Matt, Please see attached Submittal: RS 064100-008-0 TV Bulkhead (Engineering and Structural Calcs) for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14495 | Review Response | Revise and Resubmit | 2021-08-25 | Franz Kogler (Thornton Tomasetti) | Shaina Burris (Populous) |  | See attached submittal for comments. Provide signed+sealed calculations. TT-FK ¦ 2021-08-25 | Info Exchange
| 14483 | Review Response | Revise and Resubmit | 2021-08-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 18681 | Responded and Closed | Revise and Resubmit | 2021-08-26 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-23 |  | RS 064100-001-0 TV Bulkhead (Engineering and Structural Calcs).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-23 |  | RS 064100-001-0 TV Bulkhead (Engineering and Structural Calcs).pdf
| Review Response |  | Franz Kogler (Thornton Tomasetti) | 1 | 2021-08-22 02:00 |  | RS 064100-001-0 TV Bulkhead (Engineering and Structural Calcs).pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-26 |  | RS 064100-008-0 TV Bulkhead (Engineering and Structural Calcs) -_TT_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-23 |  | RS 064100-001-0 TV Bulkhead (Engineering and Structural Calcs).pdf
RS 06 41 00-008-00-01 | 06 41 00 | RS 06 41 00-008-00 TV Bulkhead (Engineering and Structural Calcs) | Expected - Overdue |  | Mark Nonato | [9 empty] | -1 |  | Submittals | RS 06 41 00-008-00 - RS 06 41 00-008-00 TV Bulkhead (Engineering and Structural Calcs) | -1 | 2021-09-09
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | Mark Nonato | 1 | 2021-08-23 |  | RS 064100-001-0 TV Bulkhead (Engineering and Structural Calcs).pdf
RS 06 41 00-008-01 |  | RS 06 41 00-008-01 TV Bulkhead | Closed | Structural, Architectural | Mark Nonato | 2021-08-31 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Kuebler Perry (Populous), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-09-02 07:00 | 2021-09-14 | 15 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-09-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14620 | Received | For Review | 2021-08-31 | Mark Nonato | Shaina Burris (Populous) | 2021-09-02 07:00 |  | Info Exchange
| 18873 | Forwarded | For Review | 2021-09-13 | Shaina Burris (Populous) | Matthew Farber (Thornton Tomasetti); Kuebler Perry (Populous); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-09-02 |  | Info Exchange
| 14656 | Review Response | Approved as Noted | 2021-09-13 | Matt Ross (Thornton Tomasetti) | Kuebler Perry (Populous); Shaina Burris (Populous) |  | See attached for TT review. | Info Exchange
| 14648 | Review Response | Approved as Noted | 2021-09-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  |  | Info Exchange
| 18888 | Responded and Closed | Approved as Noted | 2021-09-14 | Kuebler Perry (Populous) | Mark Nonato |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-30 |  | RS 064100-008-1 TV Bulkhead (Engineering and Structural Calcs) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-30 |  | RS 064100-008-1 TV Bulkhead (Engineering and Structural Calcs) - For Approval.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-08-29 02:00 |  | RS 064100-008-1 TV Bulkhead (Engineering and Structural Calcs) - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-09-14 |  | RS 064100-008-1 TV Bulkhead - For Approval_TT_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-30 |  | RS 064100-008-1 TV Bulkhead (Engineering and Structural Calcs) - For Approval.pdf
RS 06 41 00-009-00 | 06 41 00 | RS 064100-009-0 Casework (Coors Light Security Gate Millwork) | Closed | Architectural | Mark Nonato | 2021-08-30 | Responded and Closed - Approved as Noted/Resubmit |  | Kuebler Perry (Populous), Chad Francis (Populous) |  |  |  | 2021-09-01 07:00 | 2021-09-02 | 4 |  | Record Copies; Transfers; Submittals | RS 06 41 00-009-00-01 - RS 064100-009-0 Casework (Coors Light Security Gate Millwork) | 4 |  | 2021-09-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14531 | Received | For Review | 2021-08-30 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-09-01 07:00 | Kuebler, Please see attached Submittal: RS 064100-009-0 Casework (Coors Light Security Gate Millwork) for review and approval. NOTE: Attached is the submittal for the Coors Light Security Millwork. Astound will draw the mirror version once this version is approved. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18732 | Forwarded | For Review | 2021-08-30 | Josh Dobken (Populous) | Kuebler Perry (Populous); Chad Francis (Populous) | 2021-09-06 | Kuebler, Please see attached Submittal: RS 064100-009-0 Casework (Coors Light Security Gate Millwork) for review and approval. NOTE: Attached is the submittal for the Coors Light Security Millwork. Astound will draw the mirror version once this version is approved. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14550 | Review Response | Approved as Noted/Resubmit | 2021-09-02 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18763 | Responded and Closed | Approved as Noted/Resubmit | 2021-09-02 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-30 02:00 |  | RS 064100-009-0 Casework (Coors Light Security Gate Millwork) - For Approval.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-08-30 02:00 |  | RS 064100-009-0 Casework (Coors Light Security Gate Millwork) - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-31 02:00 |  | RS 064100-009-0 Casework (Coors Light Security Gate Millwork) - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-30 02:00 |  | RS 064100-009-0 Casework (Coors Light Security Gate Millwork) - For Approval.pdf
RS 06 41 00-009-00-01 | 06 41 00 | RS 064100-009-0 Casework (Coors Light Security Gate Millwork) | Expected - Overdue |  | Mark Nonato | [9 empty] | -1 |  | Submittals | RS 06 41 00-009-00 - RS 064100-009-0 Casework (Coors Light Security Gate Millwork) | -1 | 2021-09-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | Mark Nonato | 1 | 2021-08-30 02:00 |  | RS 064100-009-0 Casework (Coors Light Security Gate Millwork) - For Approval.pdf
RS 06 41 00-010-00 | 06 41 00 | RS 06 41 00-010-00 Casework (Perimeter Doors RAL 9004 Pantone 296 Alternate Finish) | Closed | Architectural | Mark Nonato | 2021-09-07 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-09-09 07:00 | 2021-09-07 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-09-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14573 | Received | For Review | 2021-09-07 | Mark Nonato | Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-09-09 07:00 | Kuebler, Please see attached Submittal: RS 064100-010-0 Casework (Perimeter Doors RAL 9004 Pantone 296 Alternate Finish) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18791 | Forwarded | For Review | 2021-09-07 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-09-14 | Kuebler, Please see attached Submittal: RS 064100-010-0 Casework (Perimeter Doors RAL 9004 Pantone 296 Alternate Finish) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14580 | Review Response | Approved | 2021-09-07 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 18798 | Responded and Closed | Approved | 2021-09-07 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-09-07 |  | RS 064100-010-0 Casework (Perimeter Doors RAL 9004 Pantone 296.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-07 |  | RS 064100-010-0 Casework (Perimeter Doors RAL 9004 Pantone 296.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-09-07 02:00 |  | RS 064100-010-0 Casework (Perimeter Doors RAL_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-09-06 02:00 |  | RS 064100-010-0 Casework (Perimeter Doors RAL 9004 Pantone 296.pdf
RS 08 10 00-001-01 | 08 10 00 | RS 08 10 00-001-01 HM Doors, Frames, and Hardware | Closed | Architectural | Mark.Nonato@bnbuilders.com | 2021-07-01 | Responded and Closed - Approved as Noted |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Rick Lewis (Studio 08 Consultants), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Linda Scott (Studio 08 Consultants), Chad Francis (Populous) |  |  |  | 2021-07-15 | 2021-07-02 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13758 | Received | For Review | 2021-07-01 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-07-15 | Kuebler/Shaina, Please see attached Submittal: RS 081000-001-1 HM Doors, Frames, and Hardware - For Approval for review and approval. NOTE: As discussed, this submittal is critical. Please return this submittal same day/next day. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17804 | Forwarded | For Review | 2021-07-01 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Rick Lewis (Studio 08 Consultants); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Linda Scott (Studio 08 Consultants); Chad Francis (Populous) | 2021-07-08 | Kuebler/Shaina, Please see attached Submittal: RS 081000-001-1 HM Doors, Frames, and Hardware - For Approval for review and approval. NOTE: As discussed, this submittal is critical. Please return this submittal same day/next day. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13773 | Review Response | Approved as Noted | 2021-07-02 | Linda Scott (Studio 08 Consultants) | Shaina Burris (Populous) |  | Please find attached the reviewed submittal referenced above. If you have questions or comments, please feel free to contact me. Thanks. | Info Exchange
| 17824 | Responded and Closed | Approved as Noted | 2021-07-02 | Chad Francis (Populous) | Mark.Nonato@bnbuilders.com |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-01 |  | RS 081000-001-1 HM Doors, Frames, and Hardware - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-01 |  | RS 081000-001-1 HM Doors, Frames, and Hardware - For Approval.pdf
| Review Response |  | Linda Scott (Studio 08 Consultants) | 1 | 2021-07-01 |  | RS 081000-001-1 HM Doors, Frames, and Hardware - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-02 |  | RS 081000-001-1 HM Doors, Frames, and Hardware - For Approval ST08 REVIEW_POP.pdf
RS 08 33 23-001-00 | 08 33 23 - OVERHEAD COILING DOORS | RS 08 33 23-001-00 Overhead Coiling Door | Closed | Architectural | Mark Nonato | 2021-06-28 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-13 07:00 | 2021-07-07 | 10 |  | Record Copies; Transfers; Submittals | RS 08 33 23-001-00-01 - RS 08 33 23-001-00 Overhead Coiling Door | 11 |  | 2021-07-07
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13670 | Received | For Review | 2021-06-28 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-07-13 07:00 | Kuebler/Shaina, Please see attached Submittal: RS 083323-001-0 Overhead Coiling Door for review and approval. NOTE: The current lead times are 4-8 weeks. Please review and turn around by Monday. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17699 | Forwarded | For Review | 2021-06-27 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Kuebler/Shaina, Please see attached Submittal: RS 083323-001-0 Overhead Coiling Door for review and approval. NOTE: The current lead times are 4-8 weeks. Please review and turn around by Monday. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 17900 | Responded and Closed | Revise and Resubmit | 2021-07-07 | Chad Francis (Populous) | Mark.Nonato@bnbuilders.com |  | Revised OHD will be issued on 7/9/21 per owners direction. Please see attached advanced copy of the product spec for a Cookson Coiling Grille that will be issued for reference. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-06-27 |  | RS 08 33 23-001-0 Overhead Coiling Door - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-27 |  | RS 08 33 23-001-0 Overhead Coiling Door - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-07 |  | RS 08 33 23-001-0 Overhead Coiling Door - For Approval_POP.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-07 |  | 08 33 26 - overhead coiling grilles.pdf
RS 08 33 23-001-00-01 | 08 33 23 - OVERHEAD COILING DOORS | RS 08 33 23-001-00 Overhead Coiling Door | Expected - Overdue |  | Mark Nonato | [9 empty] | -1 |  | Submittals | RS 08 33 23-001-00 - RS 08 33 23-001-00 Overhead Coiling Door | -1 | 2021-07-21
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | Mark Nonato | 1 | 2021-07-07 |  | RS 08 33 23-001-0 Overhead Coiling Door - For Approval_POP.pdf
| Expected |  | Mark Nonato | 1 | 2021-07-07 |  | 08 33 26 - overhead coiling grilles.pdf
RS 08 33 23-001-01 | 08 33 23 - OVERHEAD COILING DOORS | RS 08 33 23-001-01 Overhead Coiling Door | Closed | Architectural | Mark Nonato | 2021-07-22 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-05 | 2021-07-22 | 1 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-07-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14044 | Received | For Review | 2021-07-22 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-08-05 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 083323-001-1 Overhead Coiling for review and approval. NOTE: This is really HOT. Please expedite review and return same day. Current lead time is 4-9 weeks. We are pushing for 4 weeks with an install date of 9/27. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18169 | Forwarded | For Review | 2021-07-22 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-29 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 083323-001-1 Overhead Coiling for review and approval. NOTE: This is really HOT. Please expedite review and return same day. Current lead time is 4-9 weeks. We are pushing for 4 weeks with an install date of 9/27. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 18179 | Responded and Closed | Approved | 2021-07-22 | Chad Francis (Populous) | Mark Nonato |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-22 |  | RS 083323-001-1 Overhead Coiling Door - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-22 |  | RS 083323-001-1 Overhead Coiling Door - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-22 |  | RS 083323-001-1 Overhead Coiling Door - For Approval_POP.pdf
RS 08 35 00-001-00 | 08 35 00 | RS 08 35 00-001-0- Coors Light Sliding Security Folding Grille Door | Closed | Architectural, Structural | Mark Nonato | 2021-08-26 | Responded and Closed - Approved as Noted |  | Matthew Farber (Thornton Tomasetti), Kuebler Perry (Populous), Matt Ross (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti) |  |  |  | 2021-08-30 | 2021-08-27 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-08-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14506 | Received | For Review | 2021-08-26 | Mark Nonato | Bryan Klote (Populous); Matthew Farber (Thornton Tomasetti); Kuebler Perry (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti); Shaina Burris (Populous) | 2021-08-30 | Kuebler/Matt, Please see attached Submittal: RS 083500-001-0 Coors Light Sliding Security Folding Grille Door for review and approval. NOTE: Please expedite review of this submittal. After the cover sheet/transmittal there are two pages showing the beam detail discussed with Kuebler (POP). Please confirm that the proposed plan for the existing condition for track mounting is acceptable. Due to existing monokote fireproofing on beam, BNB plans utilize steel angles welded to the beam and use 3"x6" wood blocking bolted to the steel angle below the monokote. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18702 | Forwarded | For Review | 2021-08-26 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Kuebler Perry (Populous); Matt Ross (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti) | 2021-08-30 | Kuebler/Matt, Please see attached Submittal: RS 083500-001-0 Coors Light Sliding Security Folding Grille Door for review and approval. NOTE: Please expedite review of this submittal. After the cover sheet/transmittal there are two pages showing the beam detail discussed with Kuebler (POP). Please confirm that the proposed plan for the existing condition for track mounting is acceptable. Due to existing monokote fireproofing on beam, BNB plans utilize steel angles welded to the beam and use 3"x6" wood blocking bolted to the steel angle below the monokote. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14507 | Review Response | Approved as Noted | 2021-08-27 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 14508 | Review Response | Approved as Noted | 2021-08-27 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| 18705 | Responded and Closed | Approved as Noted | 2021-08-27 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-26 02:00 |  | RS 083500-001-0 Coors Light Sliding Security Folding Grille Door - For Approval.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-08-26 02:00 |  | RS 083500-001-0 Coors Light Sliding Security Folding Grille Door - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-27 |  | RS 083500-001-0 Coors Light Sliding Security Folding Grille Door_POP.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-27 |  | RS 083500-001-0 Coors Light Sliding Security Folding Grille Door_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-26 |  | RS 083500-001-0 Coors Light Sliding Security Folding Grille Door - For Approval.pdf
RS 08 43 00-001-00 | 08 43 00 | RS 08 43 00-001-00 Storefront Shop Drawings | Closed | Architectural | Mark.Nonato@bnbuilders.com | 2021-07-08 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-13 07:00 | 2021-07-14 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13835 | Received | For Review | 2021-07-08 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-07-13 07:00 | Kuebler/Shaina, Please see attached Submittal: RS 084300-001-0 Storefront Shop Drawings for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17910 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-15 | Kuebler/Shaina, Please see attached Submittal: RS 084300-001-0 Storefront Shop Drawings for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 17926 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-15 | Kuebler/Shaina, Please see attached Submittal: RS 084300-001-0 Storefront Shop Drawings for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13937 | Review Response | Revise and Resubmit | 2021-07-14 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 18043 | Responded and Closed | Revise and Resubmit | 2021-07-14 | Kuebler Perry (Populous) | Mark.Nonato@bnbuilders.com |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-08 |  | RS 084300-001-0 Storefront Shop Drawings - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-08 |  | RS 084300-001-0 Storefront Shop Drawings - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-08 |  | RS 084300-001-0 Storefront Shop Drawings - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-14 |  | RS 084300-001-0 Storefront Shop Drawings - For Approval_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-08 |  | RS 084300-001-0 Storefront Shop Drawings - For Approval.pdf
RS 08 43 00-001-01 | 08 43 00 | RS 08 43 00-001-01 Storefront Shop Drawings | Closed | Architectural | Mark Nonato | 2021-07-19 | Responded and Closed - Approved as Noted/Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-21 07:00 | 2021-07-19 | 1 |  | Record Copies; Transfers; Submittals | RS 08 43 00-001-01-01 - RS 08 43 00-001-01 Storefront Shop Drawings | 4 |  | 2021-07-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13989 | Received | For Review | 2021-07-19 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-07-21 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 084300-001-1 Storefront Shop Drawings for review and approval. NOTE: This is the Kawneer Trifab 400 system which has a 4” mullion. Kawneer is confident that the lead times should be the same as the previous submitted system. We will have a confirmed ship date next week. Mission Glass will also be shipping out some sealant samples on Monday. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18094 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-23 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 084300-001-1 Storefront Shop Drawings for review and approval. NOTE: This is the Kawneer Trifab 400 system which has a 4” mullion. Kawneer is confident that the lead times should be the same as the previous submitted system. We will have a confirmed ship date next week. Mission Glass will also be shipping out some sealant samples on Monday. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14009 | Review Response | Approved as Noted/Resubmit | 2021-07-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Several dimensions are incorrect. Confirm ceiling heights and steel configuration - resubmit with corrections, for record only. | Info Exchange
| 18122 | Responded and Closed | Approved as Noted/Resubmit | 2021-07-19 | Kuebler Perry (Populous) | Mark Nonato |  | Several dimensions are incorrect. Confirm ceiling heights and steel configuration - resubmit with corrections, for record only. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-16 |  | RS 084300-001-1 Storefront Shop Drawings - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | RS 084300-001-1 Storefront Shop Drawings - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-19 |  | RS 084300-001-1 Storefront Shop Drawings - For Approval - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-16 |  | RS 084300-001-1 Storefront Shop Drawings - For Approval.pdf
RS 08 43 00-001-01-01 | 08 43 00 | RS 08 43 00-001-01 Storefront Shop Drawings | Expected - Overdue |  | Mark Nonato | [9 empty] | -1 |  | Submittals | RS 08 43 00-001-01 - RS 08 43 00-001-01 Storefront Shop Drawings | -1 | 2021-08-02
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | Mark Nonato | 1 | 2021-07-16 |  | RS 084300-001-1 Storefront Shop Drawings - For Approval.pdf
RS 08 43 00-002-00 | 08 43 00 | RS 08 43 00-002-00 Storefront Product Data (Framing, Glazing, Joint Sealants) | Closed | Architectural | Mark Nonato | 2021-07-13 | Responded and Closed - Revise and Resubmit |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-27 | 2021-07-14 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-14
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13903 | Received | For Review | 2021-07-13 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-07-27 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 084300-002-0 Storefront Product Data (Framing, Glazing, Joint Sealants) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18005 | Forwarded | For Review | 2021-07-13 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-20 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 084300-002-0 Storefront Product Data (Framing, Glazing, Joint Sealants) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 18041 | Responded and Closed | Revise and Resubmit | 2021-07-14 | Chad Francis (Populous) | Mark.Nonato@bnbuilders.com |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-13 |  | RS 084300-002-0 Storefront Product Data (Framing, Glazing, Joint Sealants) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-13 |  | RS 084300-002-0 Storefront Product Data (Framing, Glazing, Joint Sealants) - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-14 |  | RS 084300-002-0 Storefront Product Data (Framing, Glazing, Joint Sealants) - For Approval_POP.pdf
RS 08 43 00-002-01 | 08 43 00 | RS 08 43 00-002-01 Storefront Product Data | Closed | Architectural | Mark Nonato | 2021-07-19 | Responded and Closed - Approved |  | Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Chris Minter (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-21 07:00 | 2021-07-19 | 1 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-07-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13990 | Received | For Review | 2021-07-19 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-07-21 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 084300-002-1 Storefront Product Data (Framing, Glazing, Joint Sealants) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18095 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Chris Minter (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-23 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 084300-002-1 Storefront Product Data (Framing, Glazing, Joint Sealants) for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14010 | Review Response | Approved | 2021-07-19 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18123 | Responded and Closed | Approved | 2021-07-19 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-16 |  | RS 084300-002-1 Storefront Product Data (Framing, Glazing, Joint Sealants) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | RS 084300-002-1 Storefront Product Data (Framing, Glazing, Joint Sealants) - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-19 |  | RS 084300-002-1 Storefront Product Data (Framing, Glazing, Joint Sealants) -POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-16 |  | RS 084300-002-1 Storefront Product Data (Framing, Glazing, Joint Sealants) - For Approval.pdf
RS 09 22 16-001-00 | 09 22 16 - NON-STRUCTURAL METAL FRAMING | RS 09 22 16-001-00 Framing and Drywall | Closed | Architectural | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-24 | Responded and Closed - Revise and Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous), Matt Ross (Thornton Tomasetti) |  |  |  | 2021-07-08 | 2021-07-02 | 9 |  | Record Copies; Transfers; Submittals | RS 09 22 16-001-00-01 - RS 09 22 16-001-00 Framing and Drywall | 9 |  | 2021-07-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13638 | Received | For Review | 2021-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-07-08 |  | Email
| 17675 | Forwarded | For Review | 2021-06-24 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-01 |  | Info Exchange
| 17760 | Forwarded | For Review | 2021-06-30 | Kuebler Perry (Populous) | Matt Ross (Thornton Tomasetti) | 2021-07-01 |  | Info Exchange
| 13775 | Review Response | Revise and Resubmit | 2021-07-02 | Matt Ross (Thornton Tomasetti) | Kuebler Perry (Populous) |  | ARCH TO REVIEW. | Info Exchange
| 17825 | Responded and Closed | Revise and Resubmit | 2021-07-02 | Chad Francis (Populous) | Ryan Beyers |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-24 |  | RS 092216-001-0 Framing and Drywall - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-24 |  | RS 092216-001-0 Framing and Drywall - For Approval.pdf
| Forwarded |  | Kuebler Perry (Populous) | 1 | 2021-06-23 23:00 |  | RS 092216-001-0 Framing and Drywall - For Approval.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-06-23 |  | RS 092216-001-0 Framing and Drywall - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-02 |  | RS 092216-001-0 Framing and Drywall - For Approval_TT_POP.pdf
RS 09 22 16-001-00-01 | 09 22 16 - NON-STRUCTURAL METAL FRAMING | RS 09 22 16-001-00 Framing and Drywall | Expected - Overdue |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | [9 empty] | -1 |  | Submittals | RS 09 22 16-001-00 - RS 09 22 16-001-00 Framing and Drywall | -1 | 2021-07-16
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-07-02 |  | RS 092216-001-0 Framing and Drywall - For Approval_TT_POP.pdf
RS 09 22 16-002-00 | 09 22 16 - NON-STRUCTURAL METAL FRAMING | RS 09 22 16-002-00 GWB Drywall | Closed | Architectural | Mark Nonato | 2021-07-14 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-28 | 2021-07-15 | 2 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13939 | Received | For Review | 2021-07-14 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-07-28 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 092216-002-0 GWB Drywall for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18046 | Forwarded | For Review | 2021-07-15 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-22 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 092216-002-0 GWB Drywall for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 18053 | Responded and Closed | Approved as Noted | 2021-07-15 | Chad Francis (Populous) | Mark.Nonato@bnbuilders.com |  | 1. SUBMITTAL NUMBER IS INCORRECT AND REVIEWED FOR SPEC 09 29 00, ALL ITEMS APPROVED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-15 |  | RS 092216-002-0 GWB Drywall - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-15 |  | RS 092216-002-0 GWB Drywall - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-15 |  | RS 092216-002-0 GWB Drywall - For Approval_POP.pdf
RS 09 22 16-003-00 | 09 22 16 - NON-STRUCTURAL METAL FRAMING | RS 09 22 16-003-00 Soffit Detail and Calculations for Pivot Door | Closed | Architectural | Mark Nonato | 2021-07-28 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-11 | 2021-07-29 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14150 | Received | For Review | 2021-07-28 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti); Shaina Burris (Populous); Chad Francis (Populous) | 2021-08-11 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 092216-003-0 Soffit Detail and Calculations for Pivot Door for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18292 | Forwarded | For Review | 2021-07-28 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-04 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 092216-003-0 Soffit Detail and Calculations for Pivot Door for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 18302 | Responded and Closed | Approved as Noted | 2021-07-29 | Chad Francis (Populous) | Mark Nonato |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-28 |  | RS 092216-003-0 Soffit Detail and Calculations for Pivot Door - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-28 |  | RS 092216-003-0 Soffit Detail and Calculations for Pivot Door - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-29 |  | RS 092216-003-0 Soffit Detail and Calculations for Pivot Door - For Approval_TT_POP.pdf
RS 09 51 00-001-00 | 09 51 00 - SUSPENDED CEILING SYSTEMS | RS 09 51 00-001-00 Suspended Ceiling Systems | Closed | Architectural | Mark Nonato | 2021-07-19 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-21 07:00 | 2021-07-20 | 2 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13984 | Received | For Review | 2021-07-19 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-07-21 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 095100-001-0 Suspended Ceiling Systems for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18089 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-23 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 095100-001-0 Suspended Ceiling Systems for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14018 | Review Response | Approved as Noted | 2021-07-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18138 | Responded and Closed | Approved as Noted | 2021-07-20 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-16 |  | RS 095100-001-0 Suspended Ceiling Systems - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | RS 095100-001-0 Suspended Ceiling Systems - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-20 |  | RS 095100-001-0 Suspended Ceiling Systems - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-16 |  | RS 095100-001-0 Suspended Ceiling Systems - For Approval.pdf
RS 09 60 00-001-00 |  | RS 09 60 00-001-00 Flooring | Closed | Architectural | Mark Nonato | 2021-07-06 | Responded and Closed - Approved |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-20 | 2021-07-08 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13793 | Received | For Review | 2021-07-06 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-07-20 | Kuebler/Shaina, Please see attached Submittal: RS 096000-001-0 Flooring for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17847 | Forwarded | For Review | 2021-07-06 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Kuebler/Shaina, Please see attached Submittal: RS 096000-001-0 Flooring for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13856 | Review Response | Approved | 2021-07-08 | Kuebler Perry (Populous) | Shaina Burris (Populous) |  | Refer to attached submittal response. | Info Exchange
| 17934 | Responded and Closed | Approved | 2021-07-08 | Kuebler Perry (Populous) | Mark.Nonato@bnbuilders.com |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-06 |  | RS 096000-001-0 Flooring - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-06 |  | RS 096000-001-0 Flooring - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-08 |  | RS 096000-001-0 Flooring - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-06 |  | RS 096000-001-0 Flooring - For Approval.pdf
RS 09 60 00-002-00 | 09 60 00 | RS 09 60 00-002-00 Flooring Material Samples | Closed | Architectural | Ryan Beyers | 2021-07-07 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-07-21 | 2021-07-08 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-08
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13825 | Received | For Review | 2021-07-07 | Ryan Beyers | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Mark.Nonato@bnbuilders.com | 2021-07-21 | Team, See attached Submittal: RS 096000-001-1 Flooring Material Samples for review and approval. We have overnighted physical samples to Kuebler’s attention. Regards, Ryan Beyers ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.530.3296 BNBuilders.com From: Mark Nonato <Mark.Nonato@bnbuilders.com> Sent: Tuesday, July 6, 2021 8:48 AM To: Kuebler Perry <Kuebler.Perry@populous.com>; shaina.burris@populous.com; josh.dobken@populous.com; bryan.klote@populous.com Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; byron.noll@caaico.com Subject: CPA Retail - Submittal: RS 096000-001-0 Flooring Kuebler/Shaina, Please see attached Submittal: RS 096000-001-0 Flooring for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17899 | Forwarded | For Review | 2021-07-07 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-07-14 | Team, See attached Submittal: RS 096000-001-1 Flooring Material Samples for review and approval. We have overnighted physical samples to Kuebler’s attention. Regards, Ryan Beyers ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.530.3296 BNBuilders.com From: Mark Nonato <Mark.Nonato@bnbuilders.com> Sent: Tuesday, July 6, 2021 8:48 AM To: Kuebler Perry <Kuebler.Perry@populous.com>; shaina.burris@populous.com; josh.dobken@populous.com; bryan.klote@populous.com Cc: Ryan Beyers <Ryan.Beyers@bnbuilders.com>; Bill Sweeney <Bill.Sweeney@bnbuilders.com>; Brad Lotz <Brad.Lotz@bnbuilders.com>; byron.noll@caaico.com Subject: CPA Retail - Submittal: RS 096000-001-0 Flooring Kuebler/Shaina, Please see attached Submittal: RS 096000-001-0 Flooring for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13855 | Review Response | Approved as Noted | 2021-07-08 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 17933 | Responded and Closed | Approved as Noted | 2021-07-08 | Kuebler Perry (Populous) | Ryan Beyers |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Ryan Beyers | 1 | 2021-07-07 |  | RS 096000-001-1 Flooring - Material Samples - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-07 |  | RS 096000-001-1 Flooring - Material Samples - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-08 |  | RS 096000-001-1 Flooring - Material Samples - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-07 |  | RS 096000-001-1 Flooring - Material Samples - For Approval.pdf
RS 09 90 00-001-00 | 09 90 00 | RS 09 90 00-001-00 Painting | Closed | Architectural | Mark Nonato | 2021-08-04 | Responded and Closed - Approved as Noted |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-06 07:00 | 2021-08-06 | 3 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14215 | Received | For Review | 2021-08-04 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-08-06 07:00 | Kuebler, Please see attached Submittal: RS 099000-001-0 Painting for review and approval. NOTE: Attached is the product data submittal, color schedule and shop drawings. One submittal for the Interior Painting and one for the High Performance Coatings (doors/frames/metal). On drawing A6-03-7 note 34 says to paint the video niche black. They need the Architect approval and a color number for this. Please note and markup on submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18368 | Forwarded | For Review | 2021-08-04 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-11 | Kuebler, Please see attached Submittal: RS 099000-001-0 Painting for review and approval. NOTE: Attached is the product data submittal, color schedule and shop drawings. One submittal for the Interior Painting and one for the High Performance Coatings (doors/frames/metal). On drawing A6-03-7 note 34 says to paint the video niche black. They need the Architect approval and a color number for this. Please note and markup on submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14242 | Review Response | Approved as Noted | 2021-08-06 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18398 | Responded and Closed | Approved as Noted | 2021-08-06 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-04 |  | RS 099000-001-0 Painting - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-04 |  | RS 099000-001-0 Painting - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-06 |  | RS 099000-001-0 Painting - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-04 |  | RS 099000-001-0 Painting - For Approval.pdf
RS 09 90 00-002-00 | 09 90 00 | RS 09 90 00-002-00 Paint Drawdown Samples | Closed | Architectural | Mark Nonato | 2021-08-23 | Responded and Closed - Approved as Noted/Resubmit |  | Bryan Klote (Populous), Kelsea Conkright (Populous), Todd Spangler (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-25 07:00 | 2021-08-26 | 4 |  | Record Copies; Transfers; Submittals | RS 09 90 00-002-00-01 - RS 09 90 00-002-00 Paint Drawdown Samples | 4 |  | 2021-08-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14432 | Received | For Review | 2021-08-23 | Mark Nonato | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-08-25 07:00 | All, My apologies, but please disregard the previous attachment. This revised /updated attachment includes P1 and P18. I am still awaiting the SW color 6085 match. It should have be sent already, but I also requested a photo and hope to get that soon and will forward as well directly to Kuebler. Thanks, From: Mark Nonato Sent: Monday, August 23, 2021 7:34 AM To: Kuebler Perry <Kuebler.Perry@populous.com>; shaina.burris@populous.com; josh.dobken@populous.com; bryan.klote@populous.com Subject: CPA Retail - Submittal: RS 099000-002-0 Paint Drawdown Samples Shaina/Josh/Kuebler, Please see attached Submittal: RS 099000-002-0 Paint Drawdown Samples for review and approval. NOTE: This was supposed to send on 8/12 but it got stuck in my Outbox. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18627 | Forwarded | For Review | 2021-08-23 | Shaina Burris (Populous) | Bryan Klote (Populous); Kelsea Conkright (Populous); Todd Spangler (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) | 2021-08-30 | All, My apologies, but please disregard the previous attachment. This revised /updated attachment includes P1 and P18. I am still awaiting the SW color 6085 match. It should have be sent already, but I also requested a photo and hope to get that soon and will forward as well directly to Kuebler. Thanks, From: Mark Nonato Sent: Monday, August 23, 2021 7:34 AM To: Kuebler Perry <Kuebler.Perry@populous.com>; shaina.burris@populous.com; josh.dobken@populous.com; bryan.klote@populous.com Subject: CPA Retail - Submittal: RS 099000-002-0 Paint Drawdown Samples Shaina/Josh/Kuebler, Please see attached Submittal: RS 099000-002-0 Paint Drawdown Samples for review and approval. NOTE: This was supposed to send on 8/12 but it got stuck in my Outbox. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14479 | Review Response | Approved as Noted/Resubmit | 2021-08-26 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18673 | Responded and Closed | Approved as Noted/Resubmit | 2021-08-26 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-23 |  | RS 099000-002-0 Paint Drawdown Samples - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-23 |  | RS 099000-002-0 Paint Drawdown Samples - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-26 |  | RS 099000-002-0 Paint Drawdown Samples - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-23 |  | RS 099000-002-0 Paint Drawdown Samples - For Approval.pdf
RS 09 90 00-002-00-01 | 09 90 00 | RS 09 90 00-002-00 Paint Drawdown Samples | Expected - Overdue |  | Mark Nonato | [9 empty] | -1 |  | Submittals | RS 09 90 00-002-00 - RS 09 90 00-002-00 Paint Drawdown Samples | -1 | 2021-09-09
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | Mark Nonato | 1 | 2021-08-23 |  | RS 099000-002-0 Paint Drawdown Samples - For Approval.pdf
RS 21 00 00-001-00 |  | RS 21 00 00-001-00 Fire Protection Material Data | Closed | Fire Protection | Mark.Nonato@bnbuilders.com | 2021-07-08 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-13 07:00 | 2021-07-12 | 5 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13832 | Received | For Review | 2021-07-08 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-07-13 07:00 | Kuebler/Shaina, Please see attached Submittal: RS 210000-001-0 Fire Protection Material Data for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17907 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-15 | Kuebler/Shaina, Please see attached Submittal: RS 210000-001-0 Fire Protection Material Data for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13891 | Review Response | Approved | 2021-07-09 | Dave Ferguson (ME Engineers) | Shaina Burris (Populous) |  | No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 9 July 21 | Info Exchange
| 17986 | Responded and Closed | Approved | 2021-07-12 | Josh Dobken (Populous) | Mark.Nonato@bnbuilders.com |  | Response (Approved) from: Dave Ferguson (ME Engineers) Remarks: No Exceptions Taken. See attached. David J. Ferguson, P.E. ME Engineers, Inc. 9 July 21 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-08 |  | RS 210000-001-0 Fire Protection Material Data - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-08 |  | RS 210000-001-0 Fire Protection Material Data - For Approval.pdf
| Review Response |  | Dave Ferguson (ME Engineers) | 1 | 2021-07-07 02:00 |  | RS 210000-001-0 Fire Protection Material Data - For Approval.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-07-12 02:00 |  | RS 210000-001-0 Fire Protection Material Data_ME Review_9 Jul 21_POP.pdf
RS 23 00 00-001-00 | 23 00 00 - MECHANICAL NARRATIVE | RS 23 00 00-001-00 HVAC Submittals | Closed | Mechanical | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 2021-06-24 | Responded and Closed - Approved as Noted |  | Nick Theimer (ME Engineers), Dave Ferguson (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-08 | 2021-06-29 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-06-29
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13636 | Received | For Review | 2021-06-24 | AI Assistant Mortenson Procore Connector (Mortenson Construction) | Shaina Burris (Populous) | 2021-07-08 |  | Email
| 17674 | Forwarded | For Review | 2021-06-24 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Dave Ferguson (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-01 |  | Info Exchange
| 13715 | Review Response | Approved as Noted | 2021-06-29 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.06.29 | Info Exchange
| 17754 | Responded and Closed | Approved as Noted | 2021-06-29 | Shaina Burris (Populous) | AI Assistant Mortenson Procore Connector (Mortenson Construction); Mark.Nonato@bnbuilders.com; bill.sweeney@bnbuilders.com |  | Response (Approved as Noted) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.06.29 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | AI Assistant Mortenson Procore Connector (Mortenson Construction) | 1 | 2021-06-24 |  | RS 230000-001-0 HVAC Submittals - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-06-24 |  | RS 230000-001-0 HVAC Submittals - For Approval.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-06-24 |  | RS 230000-001-0 HVAC Submittals - For Approval.pdf
| Responded and Closed |  | Shaina Burris (Populous) | 1 | 2021-06-29 |  | RS 230000-001-0 HVAC Submittals - For Approval_ME_POP.pdf
RS 23 00 00-002-00 | 23 00 00 - MECHANICAL NARRATIVE | RS 23 00 00-002-00 WSHP Hose Kits | Closed | Mechanical | Mark.Nonato@bnbuilders.com | 2021-07-08 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-13 07:00 | 2021-07-12 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-12
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13836 | Received | For Review | 2021-07-08 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-07-13 07:00 | Kuebler/Shaina, Please see attached Submittal: RS 230000-002-0 WSHP Hose Kits for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17911 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-15 | Kuebler/Shaina, Please see attached Submittal: RS 230000-002-0 WSHP Hose Kits for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13890 | Review Response | Approved | 2021-07-12 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.07.12 | Info Exchange
| 17985 | Responded and Closed | Approved | 2021-07-12 | Josh Dobken (Populous) | Mark.Nonato@bnbuilders.com |  | Response (Approved) from: Nick Theimer (ME Engineers) Remarks: See attached for review. Nick Theimer ME Engineers 2021.07.12 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-08 |  | RS 230000-002-0 WSHP Hose Kits - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-08 |  | RS 230000-002-0 WSHP Hose Kits - For Approval.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-07-07 02:00 |  | RS 230000-002-0 WSHP Hose Kits - For Approval.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-07-12 02:00 |  | RS 230000-002-0 WSHP Hose Kits - For Approval_ME_POP.pdf
RS 23 00 00-003-00 | 23 00 00 - MECHANICAL NARRATIVE | RS 23 00 00-003-00 Marked-Up Mechanical Drawings (M3-28) | Closed | Mechanical | Mark Nonato | 2021-07-16 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-20 07:00 | 2021-07-22 | 7 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13972 | Received | For Review | 2021-07-16 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-20 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 230000-003-0 Marked-Up Mechanical Drawings (M3-28) for review and approval. NOTE: The duct sizes are noted. ACCO is planning to order the sheet metal in the next day or two. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18074 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-23 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 230000-003-0 Marked-Up Mechanical Drawings (M3-28) for review and approval. NOTE: The duct sizes are noted. ACCO is planning to order the sheet metal in the next day or two. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14055 | Review Response | Approved | 2021-07-20 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.07.20 | Info Exchange
| 18182 | Responded and Closed | Approved | 2021-07-22 | Chad Francis (Populous) | Mark Nonato |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-16 |  | RS 230000-003-0 Marked-Up Mechanical Drawings (M3-28) - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | RS 230000-003-0 Marked-Up Mechanical Drawings (M3-28) - For Approval.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-07-16 |  | RS 230000-003-0 Marked-Up Mechanical Drawings (M3-28) - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-22 |  | RS 230000-003-0 Marked-Up Mechanical Drawings (M3-28)_ME_POP.pdf
RS 23 05 49-001-00 | 23 05 49 - SEISMIC RESTRAINTS | RS 23 05 49-001-00 HVAC ISAT Anchorage | Closed | Mechanical, Structural | Mark Nonato | 2021-07-15 | Responded and Closed - Approved as Noted/Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Matthew Farber (Thornton Tomasetti), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Raymond Chou (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-19 07:00 | 2021-07-26 | 12 |  | Record Copies; Transfers; Submittals | RS 23 05 49-001-00-01 - RS 23 05 49-001-00 HVAC ISAT Anchorage | 9 |  | 2021-07-26
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13958 | Received | For Review | 2021-07-15 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Matt Ross (Thornton Tomasetti); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-19 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 230549-001-0 HVAC ISAT Anchorage Submittal for review and approval. NOTE: No expedited review required. Standard review time is acceptable. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18060 | Forwarded | For Review | 2021-07-15 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-22 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 230549-001-0 HVAC ISAT Anchorage Submittal for review and approval. NOTE: No expedited review required. Standard review time is acceptable. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13961 | Review Response | Approved | 2021-07-15 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | See attached for review. Structural engineer to review. Nick Theimer ME Engineers 2021.07.15 | Info Exchange
| 18066 | Forwarded | For Review | 2021-07-15 | Josh Dobken (Populous) | Matthew Farber (Thornton Tomasetti); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tomasetti); Raymond Chou (Thornton Tomasetti); Michael Croly (Thornton Tomasetti); Ross Cussen | 2021-07-20 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 230549-001-0 HVAC ISAT Anchorage Submittal for review and approval. NOTE: No expedited review required. Standard review time is acceptable. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14106 | Review Response | Approved as Noted | 2021-07-23 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous) |  | Please provide HVAC layout, attachment point locations, and loads imposed related to this submittal for EOR review and approval. | Info Exchange
| 18236 | Responded and Closed | Approved as Noted/Resubmit | 2021-07-26 | Chad Francis (Populous) | Mark Nonato |  | Please provide HVAC layout, attachment point locations, and loads imposed related to this submittal for EOR review and approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-15 |  | RS 230549-001-0 HVAC ISAT Anchorage Submittal - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-15 |  | RS 230549-001-0 HVAC ISAT Anchorage Submittal - For Approval.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-07-14 02:00 |  | RS 230549-001-0 HVAC ISAT Anchorage Submittal - For Approval.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-07-14 02:00 |  | RS 230549-001-0 HVAC ISAT Anchorage Submittal - For Approval.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-07-14 |  | RS 230549-001-0 HVAC ISAT Anchorage Submittal - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-26 |  | RS 230549-001-0 HVAC ISAT Anchorage Submittal_ME_TT_POP.pdf
RS 23 05 49-001-00-01 | 23 05 49 - SEISMIC RESTRAINTS | RS 23 05 49-001-00 HVAC ISAT Anchorage | Expected - Overdue |  | Mark Nonato | [9 empty] | -1 |  | Submittals | RS 23 05 49-001-00 - RS 23 05 49-001-00 HVAC ISAT Anchorage | -1 | 2021-08-09
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | Mark Nonato | 1 | 2021-07-26 |  | RS 230549-001-0 HVAC ISAT Anchorage Submittal_ME_TT_POP.pdf
RS 23 09 00-001-00 | 23 09 00 - BUILDING AUTOMATION AND AUTOMATIC TEMP CONTROL SYS | RS 23 09 00-001-00 Siemens Controls | Closed | Mechanical | Mark Nonato | 2021-07-19 | Responded and Closed - Approved |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-21 07:00 | 2021-07-22 | 4 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14000 | Received | For Review | 2021-07-19 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-21 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 230900-001-0 Siemens Controls for review and approval. NOTE: No expedited review required. Standard review time is acceptable. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18110 | Forwarded | For Review | 2021-07-19 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-26 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 230900-001-0 Siemens Controls for review and approval. NOTE: No expedited review required. Standard review time is acceptable. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14054 | Review Response | Approved | 2021-07-20 | Nick Theimer (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) |  | See attached for review. Nick Theimer ME Engineers 2021.07.20 | Info Exchange
| 18181 | Responded and Closed | Approved | 2021-07-22 | Chad Francis (Populous) | Mark Nonato |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-19 |  | RS 230900-001-0 Siemens Controls - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-19 |  | RS 230900-001-0 Siemens Controls - For Approval.pdf
| Review Response |  | Nick Theimer (ME Engineers) | 1 | 2021-07-19 |  | RS 230900-001-0 Siemens Controls - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-22 |  | RS 230900-001-0 Siemens Controls_ME_POP.pdf
RS 26 05 19-001-00 | 26 05 19 - ELECTRICAL POWER CONDUCTORS AND CABLES | RS 26 05 19-001-00 Branch Feeder Wire & Conduit | Closed | Electrical | Mark Nonato | 2021-07-19 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-21 07:00 | 2021-07-19 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13986 | Received | For Review | 2021-07-19 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-21 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 260519-001-0 Branch Feeder Wire & Conduit for review and approval. NOTE: This is a HOT submittal. Prime will be installing pathway next week. Please try to return by Monday 7/19/21. These materials also have already been approved and is being used for the Main Arena. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18091 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-23 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 260519-001-0 Branch Feeder Wire & Conduit for review and approval. NOTE: This is a HOT submittal. Prime will be installing pathway next week. Please try to return by Monday 7/19/21. These materials also have already been approved and is being used for the Main Arena. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14005 | Review Response | Approved | 2021-07-17 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.17 | Info Exchange
| 18115 | Responded and Closed | Approved | 2021-07-19 | Josh Dobken (Populous) | Mark Nonato |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-16 |  | RS 260519-001-0 Branch Feeder Wire & Conduit - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | RS 260519-001-0 Branch Feeder Wire & Conduit - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-15 02:00 |  | RS 260519-001-0 Branch Feeder Wire & Conduit - For Approval.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-07-19 02:00 |  | RS 260519-001-0 Branch Feeder Wire & Conduit - For Approval - ME Review_POP.pdf
RS 26 05 29-001-00 | 26 05 29 - HANGERS AND SUPPORTS | RS 26 05 29-001-00 Hangers & Supports | Closed | Electrical, Structural | Mark Nonato | 2021-07-19 | Review Response - Approved as Noted |  | Mark Lievens (ME Engineers), Matthew Farber (Thornton Tomasetti), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Brian MacRae (Thornton Tomasetti), Matt Ross (Thornton Tomasetti), Meeok Kim (Thornton Tomasetti), Franz Kogler (Thornton Tomasetti), Heidi Evans (ME Engineers), Sean McNeill (Thornton Tomasetti), Michael Croly (Thornton Tomasetti), Ross Cussen |  |  |  | 2021-07-21 07:00 | 2021-07-22 | 4 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-07-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13987 | Received | For Review | 2021-07-19 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-21 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 260529-001-0 Hangers & Supports for review and approval. NOTE: This is a HOT submittal. Prime will be installing pathway next week. Please try to return by Monday 7/19/21. These materials also have already been approved and is being used for the Main Arena. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18092 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Matthew Farber (Thornton Tomasetti); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Brian MacRae (Thornton Tomasetti); Matt Ross (Thornton Tomasetti); Meeok Kim (Thornton Tomasetti); Franz Kogler (Thornton Tom... | 2021-07-23 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 260529-001-0 Hangers & Supports for review and approval. NOTE: This is a HOT submittal. Prime will be installing pathway next week. Please try to return by Monday 7/19/21. These materials also have already been approved and is being used for the Main Arena. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14053 | Review Response | Approved | 2021-07-17 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.17 | Info Exchange
| 18180 | Responded and Closed | Approved | 2021-07-22 | Chad Francis (Populous) | Mark Nonato |  | PLEASE SEE ATTACHED | Info Exchange
| 14093 | Review Response | Approved as Noted | 2021-07-23 | Matt Ross (Thornton Tomasetti) | Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) |  | Provide attachment points and loads imposed related to this submittal for EOR review and approval. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-16 |  | RS 260529-001-0 Hangers & Supports - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | RS 260529-001-0 Hangers & Supports - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-16 |  | RS 260529-001-0 Hangers & Supports - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-22 |  | RS 260529-001-0 Hangers & Supports - For Approval - ME Review_POP.pdf
| Review Response |  | Matt Ross (Thornton Tomasetti) | 1 | 2021-07-15 02:00 |  | RS 260529-001-0 Hangers & Supports - For Approval.pdf
RS 26 05 33-001-00 | 26 05 33 - RACEWAYS AND BOXES | RS 26 05 33-001-00 EMT Raceway | Closed | Electrical | Mark Nonato | 2021-07-19 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-21 07:00 | 2021-07-19 | 1 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-07-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13985 | Received | For Review | 2021-07-19 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-21 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 260533-001-0 EMT Raceway for review and approval. NOTE: This is a HOT submittal. Prime will be installing pathway next week. Please try to return by Monday 7/19/21. These materials also have already been approved and is being used for the Main Arena. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18090 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-23 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 260533-001-0 EMT Raceway for review and approval. NOTE: This is a HOT submittal. Prime will be installing pathway next week. Please try to return by Monday 7/19/21. These materials also have already been approved and is being used for the Main Arena. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14006 | Review Response | Approved | 2021-07-17 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.17 | Info Exchange
| 18116 | Responded and Closed | Approved | 2021-07-19 | Josh Dobken (Populous) | Mark Nonato |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.17 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-16 |  | RS 260533-001-0 EMT Raceway - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | RS 260533-001-0 EMT Raceway - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-15 02:00 |  | RS 260533-001-0 EMT Raceway - For Approval.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-07-19 02:00 |  | RS 260533-001-0 EMT Raceway - For Approval - ME Review_POP.pdf
RS 26 05 33-002-00 | 26 05 33 - RACEWAYS AND BOXES | RS 26 05 33-002-00 MC and FA Cable | Closed | Electrical | Mark Nonato | 2021-07-20 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-03 | 2021-07-22 | 3 |  | Record Copies; Transfers; Submittals |  | 1 |  | 2021-07-22
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14014 | Received | For Review | 2021-07-20 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-08-03 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 260533-002-0 MC and FA Cable for review and approval. NOTE: As discussed earlier with Populous. This is a HOT submittal. Prime will be installing pathway this week. Please try to return by tomorrow 7/20/21. These materials also have already been approved and is being used for the Main Arena. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18134 | Forwarded | For Review | 2021-07-20 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-27 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 260533-002-0 MC and FA Cable for review and approval. NOTE: As discussed earlier with Populous. This is a HOT submittal. Prime will be installing pathway this week. Please try to return by tomorrow 7/20/21. These materials also have already been approved and is being used for the Main Arena. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14056 | Review Response | Approved as Noted | 2021-07-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.20 | Info Exchange
| 18183 | Responded and Closed | Approved as Noted | 2021-07-22 | Chad Francis (Populous) | Mark Nonato |  | PLEASE SEE ATTACHED COMMENTS | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-20 |  | RS 260533-002-0 MC and FA Cable - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-20 |  | RS 260533-002-0 MC and FA Cable - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-20 |  | RS 260533-002-0 MC and FA Cable - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-22 |  | RS 260533-002-0 MC and FA Cable - For Approval - ME Review_POP.pdf
RS 26 05 33-003-00 | 26 05 33 - RACEWAYS AND BOXES | RS 26 05 33-003-00 Electrical Enclosures and Wireways | Closed | Electrical | Mark Nonato | 2021-08-16 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-30 | 2021-08-19 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14377 | Received | For Review | 2021-08-16 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Michael Mazzocchi (ME Engineers) | 2021-08-30 | Kuebler, Please see attached Submittal: RS 260533-003-0 Electrical Enclosures and Wireways for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18553 | Forwarded | For Review | 2021-08-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-23 | Kuebler, Please see attached Submittal: RS 260533-003-0 Electrical Enclosures and Wireways for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 18572 | Forwarded | For Review | 2021-08-17 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) |  | Kuebler, Please see attached Submittal: RS 260533-003-0 Electrical Enclosures and Wireways for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14419 | Review Response | Approved | 2021-08-19 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.08.19 | Info Exchange
| 18613 | Responded and Closed | Approved | 2021-08-19 | Bryan Klote (Populous) | Mark Nonato |  | Response (Approved) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.08.19 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-16 |  | RS 260533-003-0 Electrical Enclosures and Wireways - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-16 |  | RS 260533-003-0 Electrical Enclosures and Wireways - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-16 |  | RS 260533-003-0 Electrical Enclosures and Wireways - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-16 |  | RS 260533-003-0 Electrical Enclosures and Wireways - For Approval.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-08-19 |  | RS 260533-003-0 Electrical Enclosures and Wireways - For Approval - ME_POP.pdf
RS 26 27 26-001-00 | 26 27 26 - WIRING DEVICES | RS 26 27 26-001-00 Poke-thru Device | Closed | Electrical | Mark Nonato | 2021-07-16 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-20 07:00 | 2021-07-20 | 5 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13973 | Received | For Review | 2021-07-16 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-20 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 262726-001-0 Poke-thru Device for review and approval. NOTE: No expedited review required. Standard review time is acceptable. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18075 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-23 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 262726-001-0 Poke-thru Device for review and approval. NOTE: No expedited review required. Standard review time is acceptable. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14064 | Review Response | Approved as Noted | 2021-07-19 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Populous - Please confirm the finish of the floorbox covers within the team store. Thanks, Mark Lievens ME Engineers 2021.07.19 | Info Exchange
| 14016 | Review Response | Approved as Noted | 2021-07-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18136 | Responded and Closed | Approved as Noted | 2021-07-20 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-16 |  | RS 262726-001-0 Poke-thru Device - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | RS 262726-001-0 Poke-thru Device - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-15 02:00 |  | RS 262726-001-0 Poke-thru Device - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-20 |  | RS 262726-001-0 Poke-thru Device - For Approval - ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-16 |  | RS 262726-001-0 Poke-thru Device - For Approval.pdf
RS 26 27 26-002-00 | 26 27 26 - WIRING DEVICES | RS 26 27 26-002-00 Wiring Devices | Closed | Electrical | Mark Nonato | 2021-08-16 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-30 | 2021-08-19 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14375 | Received | For Review | 2021-08-16 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Michael Mazzocchi (ME Engineers) | 2021-08-30 | Kuebler, Please see attached Submittal: RS 262726-002-0 Wiring Devices for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18551 | Forwarded | For Review | 2021-08-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-23 | Kuebler, Please see attached Submittal: RS 262726-002-0 Wiring Devices for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14423 | Review Response | Approved as Noted | 2021-08-19 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Populous - Please select the receptacle colors to be used within the retail spaces. Thanks, Mark Lievens ME Engineers 2021.08.19 | Info Exchange
| 18617 | Responded and Closed | Approved as Noted | 2021-08-19 | Bryan Klote (Populous) | Mark Nonato |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.08.19 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-16 |  | RS 262726-002-0 Wiring Devices - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-16 |  | RS 262726-002-0 Wiring Devices - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-16 |  | RS 262726-002-0 Wiring Devices - For Approval.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-08-19 |  | RS 262726-002-0 Wiring Devices - For Approval - ME _POP.pdf
RS 26 50 00-001-00 | 26 50 00 | RS 26 50 00-001-00 Preliminary Lighting | Closed | Lighting | Mark.Nonato@bnbuilders.com | 2021-07-08 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-15 07:00 | 2021-07-13 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-07-13
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13850 | Received | For Review | 2021-07-08 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-15 07:00 | Kuebler/Shaina, Please see attached Submittal: RS 265000-001-0 Preliminary Lighting for review and approval. NOTE: Attached are the preliminary lighting submittals. Designer to specify finishes and options. We are still waiting on lead times for the alternate fixtures. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17927 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-15 | Kuebler/Shaina, Please see attached Submittal: RS 265000-001-0 Preliminary Lighting for review and approval. NOTE: Attached are the preliminary lighting submittals. Designer to specify finishes and options. We are still waiting on lead times for the alternate fixtures. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13925 | Review Response | Approved as Noted/Resubmit | 2021-07-13 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Please note that the fixtures requiring fixture finish selection are shown in bold. If you have any questions selecting finishes, please let me know. Thanks, Mark Lievens ME Engineers 2021.07.13 | Info Exchange
| 13910 | Review Response | Approved as Noted | 2021-07-13 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18013 | Responded and Closed | Approved as Noted | 2021-07-13 | Kuebler Perry (Populous) | Mark.Nonato@bnbuilders.com |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-08 |  | RS 265000-001-0 Preliminary Lighting - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-08 |  | RS 265000-001-0 Preliminary Lighting - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-07 02:00 |  | RS 265000-001-0 Preliminary Lighting - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-13 |  | RS 265000-001-0 Preliminary Lighting - ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-08 |  | RS 265000-001-0 Preliminary Lighting - For Approval.pdf
RS 26 50 00-002-00 | 26 50 00 | RS 26 50 00-002-00 Lighting Controls | Closed | Lighting | Mark Nonato | 2021-07-15 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-20 07:00 | 2021-07-20 | 6 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-07-20
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13950 | Received | For Review | 2021-07-15 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-20 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 265000-002-0 Lighting Controls for review and approval. NOTE: Please try to return by Friday 7/16/21. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18054 | Forwarded | For Review | 2021-07-15 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-22 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 265000-002-0 Lighting Controls for review and approval. NOTE: Please try to return by Friday 7/16/21. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14065 | Review Response | Approved as Noted | 2021-07-19 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.19 | Info Exchange
| 14017 | Review Response | Approved as Noted | 2021-07-20 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18137 | Responded and Closed | Approved as Noted | 2021-07-20 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-15 |  | RS 265000-002-0 Lighting Controls - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-15 |  | RS 265000-002-0 Lighting Controls - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-14 02:00 |  | RS 265000-002-0 Lighting Controls - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-07-20 |  | RS 265000-002-0 Lighting Controls - For Approval - ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-15 |  | RS 265000-002-0 Lighting Controls - For Approval.pdf
RS 26 50 00-003-00 | 26 50 00 | RS 26 50 00-003-00 L1 and L8A Light Fixture Alternates | Closed | Lighting | Mark Nonato | 2021-07-16 | Responded and Closed - Revise and Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-20 07:00 | 2021-07-19 | 4 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-07-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13975 | Received | For Review | 2021-07-16 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-20 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 265000-003-0 L1 and L8A Light Fixture Alternates for review and approval. NOTE: These are alternate fixtures with shorter lead times. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18077 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-23 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 265000-003-0 L1 and L8A Light Fixture Alternates for review and approval. NOTE: These are alternate fixtures with shorter lead times. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 18125 | Responded and Closed | Revise and Resubmit | 2021-07-19 | Josh Dobken (Populous) | Mark Nonato |  | AS A REVISION TO THIS SUBMITTAL, PLEASE RESUBMIT SUBSTITUTION REQUEST INFORMATION IN ACCORDANCE WITH SPEC SECTION 012500 1.4-A(2) | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-16 |  | RS 265000-003-0 L1 and L8A Light Fixture Alternates - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | RS 265000-003-0 L1 and L8A Light Fixture Alternates - For Approval.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-07-19 02:00 |  | RS 265000-003-0 L1 and L8A Light Fixture Alternates - For Approval_pop.pdf
RS 26 50 00-003-01 | 26 50 00 | RS 26 50 00-003-01 L1 and L8A Light Fixture Alternates | Closed | Lighting | Mark Nonato | 2021-07-20 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-22 07:00 | 2021-07-27 | 8 |  | Record Copies; Transfers; Submittals |  | 4 |  | 2021-07-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14021 | Received | For Review | 2021-07-20 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-22 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 265000-003-1 L1 and L8A Light Fixture Alternates for review and approval. NOTE: These are alternate fixtures with shorter lead times. This also is revised to include the Filled out Substitution Request Form. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18143 | Forwarded | For Review | 2021-07-20 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-27 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 265000-003-1 L1 and L8A Light Fixture Alternates for review and approval. NOTE: These are alternate fixtures with shorter lead times. This also is revised to include the Filled out Substitution Request Form. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14145 | Review Response | Approved as Noted | 2021-07-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Thanks, Mark Lievens ME Engineers 2021.07.23 | Info Exchange
| 18280 | Responded and Closed | Approved as Noted | 2021-07-27 | Bryan Klote (Populous) | Mark Nonato |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thanks, Mark Lievens ME Engineers | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-20 |  | RS 265000-003-1 L1 and L8A Light Fixture Alternates - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-20 |  | RS 265000-003-1 L1 and L8A Light Fixture Alternates - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-20 |  | RS 265000-003-1 L1 and L8A Light Fixture Alternates - For Approval.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-07-27 |  | RS 265000-003-1 L1 and L8A Light Fixture Alternates - ME_POP.pdf
RS 26 50 00-004-00 | 26 50 00 | RS 26 50 00-004-00 Lighting Control Shop Drawings | Closed | Lighting | Mark Nonato | 2021-07-26 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-30 07:00 | 2021-08-02 | 8 |  | Record Copies; Transfers; Submittals |  | 11 |  | 2021-08-02
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14096 | Received | For Review | 2021-07-26 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-30 07:00 | Kuebler/Shaina/Josh, Please click link HERE to download the Submittal: RS 265000-004-0 Lighting Control Shop Drawings for review and approval. NOTE: Standard review time is acceptable. Please return submittal by 7/30/21. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18223 | Forwarded | For Review | 2021-07-23 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-30 | Kuebler/Shaina/Josh, Please click link HERE to download the Submittal: RS 265000-004-0 Lighting Control Shop Drawings for review and approval. NOTE: Standard review time is acceptable. Please return submittal by 7/30/21. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14186 | Review Response | Approved as Noted | 2021-07-30 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.30 | Info Exchange
| 14183 | Review Response | Approved as Noted | 2021-08-02 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review | Info Exchange
| 18336 | Responded and Closed | Approved as Noted | 2021-08-02 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-23 |  | RS 265000-004-0 Lighting Control Shop Drawings - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-23 |  | RS 265000-004-0 Lighting Control Shop Drawings - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-22 02:00 |  | RS 265000-004-0 Lighting Control Shop Drawings - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-02 |  | RS 265000-004-0 Lighting Control Shop Drawings - ME-POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-07-23 |  | RS 265000-004-0 Lighting Control Shop Drawings - For Approval.pdf
RS 26 50 00-005-00 | 26 50 00 | RS 26 50 00-005-00 Fuse & Disconnect Switch | Closed | Electrical | Mark Nonato | 2021-08-04 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-06 07:00 | 2021-08-10 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-08-10
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14218 | Received | For Review | 2021-08-04 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-08-06 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 265000-005-0 Fuse & Disconnect Switch for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18371 | Forwarded | For Review | 2021-08-04 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-11 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 265000-005-0 Fuse & Disconnect Switch for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14300 | Review Response | Approved as Noted | 2021-08-10 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.08.10 | Info Exchange
| 14291 | Review Response | Approved as Noted | 2021-08-10 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18457 | Responded and Closed | Approved as Noted | 2021-08-10 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-04 |  | RS 265000-005-0 Fuse & Disconnect Switch - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-04 |  | RS 265000-005-0 Fuse & Disconnect Switch - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-03 02:00 |  | RS 265000-005-0 Fuse & Disconnect Switch - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-10 |  | RS 265000-005-0 Fuse & Disconnect Switch - ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-04 |  | RS 265000-005-0 Fuse & Disconnect Switch - For Approval.pdf
RS 26 50 00-006-00 | 26 50 00 | RS 26 50 00-006-00 Temp Fixtures Layout and Light Fixture Alternates (L13 and 14 Track, L14C, D, and E) | Closed | Electrical | Mark Nonato | 2021-09-03 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-09-08 07:00 | 2021-09-09 | 7 |  | Record Copies; Transfers; Submittals |  | 7 |  | 2021-09-09
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14569 | Received | For Review | 2021-09-03 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) | 2021-09-08 07:00 | Kuebler/Mark, Please see attached Submittal: RS 265000-006-0 Temp Fixtures Layout and Light Fixture Alternates (L13 and 14 Track, L14C, D, and E) - For Approval for review and approval. NOTE: Please expedite review of this submittal. As discussed, the markups address which fixtures will need alternates and which fixtures will require a temp fixture for final inspections. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18782 | Forwarded | For Review | 2021-09-03 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-09-10 | Kuebler/Mark, Please see attached Submittal: RS 265000-006-0 Temp Fixtures Layout and Light Fixture Alternates (L13 and 14 Track, L14C, D, and E) - For Approval for review and approval. NOTE: Please expedite review of this submittal. As discussed, the markups address which fixtures will need alternates and which fixtures will require a temp fixture for final inspections. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14611 | Review Response | Approved as Noted | 2021-09-09 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. FYI this does not differ to the submittal review already sent to BNB via email tonight. Thank you, Mark Lievens ME Engineers 2021.09.08 | Info Exchange
| 18839 | Responded and Closed | Approved as Noted | 2021-09-09 | Bryan Klote (Populous) | Mark Nonato |  | Response (Approved as Noted) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Thank you, Mark Lievens ME Engineers 2021.09.08 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-09-03 |  | RS 265000-006-0 Temp Fixtures Layout and Light Fixture Alternates.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-09-03 |  | RS 265000-006-0 Temp Fixtures Layout and Light Fixture Alternates.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-09-03 |  | RS 265000-006-0 Temp Fixtures Layout and Light Fixture Alternates.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-09-09 |  | RS 265000-006-0 Temp Fixtures Layout and Light Fixture Alternates - ME_POP.pdf
RS 26 51 13-001-00 | 26 51 13 - LIGHTING FIXTURES | RS 26 51 13-001-00 L43 Track Lighting | Closed | Lighting | Mark Nonato | 2021-08-16 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-30 | 2021-08-23 | 8 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-08-23
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14378 | Received | For Review | 2021-08-16 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Michael Mazzocchi (ME Engineers) | 2021-08-30 | Kuebler, Please see attached Submittal: 265113-001-0 L43 Track Lighting for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18554 | Forwarded | For Review | 2021-08-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-23 | Kuebler, Please see attached Submittal: 265113-001-0 L43 Track Lighting for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14456 | Review Response | Approved as Noted | 2021-08-20 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Populous shall confirm finish. Thanks, Mark Lievens ME Engineers 2021.08.20 | Info Exchange
| 14433 | Review Response | Approved as Noted | 2021-08-23 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal response. | Info Exchange
| 18629 | Responded and Closed | Approved as Noted | 2021-08-23 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal response. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-16 |  | RS 265113-001-0 L43 Track Lighting - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-16 |  | RS 265113-001-0 L43 Track Lighting - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-15 02:00 |  | RS 265113-001-0 L43 Track Lighting - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-23 02:00 |  | RS 265113-001-0 L43 Track Lighting - For Approval - ME _POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-15 02:00 |  | RS 265113-001-0 L43 Track Lighting - For Approval.pdf
RS 26 51 13-002-00 | 26 51 13 - LIGHTING FIXTURES | RS 26 51 13-002-00 Fixture Type L2 | Closed | Lighting | Mark Nonato | 2021-08-20 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-08-24 07:00 | 2021-08-24 | 5 |  | Record Copies; Transfers; Submittals |  | 6 |  | 2021-08-24
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14420 | Received | For Review | 2021-08-20 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Michael Mazzocchi (ME Engineers) | 2021-08-24 07:00 | Kuebler, Please see attached Submittal: RS 265113-002-0 Fixture Type L2 for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18614 | Forwarded | For Review | 2021-08-19 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-08-26 | Kuebler, Please see attached Submittal: RS 265113-002-0 Fixture Type L2 for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14455 | Review Response | Approved as Noted | 2021-08-23 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Populous shall confirm fixture finish. Fixture is used for emergency lighting and mounted above suite level as shown on EL2-4B. Mark Lievens ME Engineers 2021.08.23 | Info Exchange
| 14438 | Review Response | Approved as Noted | 2021-08-24 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18636 | Responded and Closed | Approved as Noted | 2021-08-24 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-19 |  | RS 265113-002-0 Fixture Type L2 - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-19 |  | RS 265113-002-0 Fixture Type L2 - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-08-18 02:00 |  | RS 265113-002-0 Fixture Type L2 - For Approval.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-24 02:00 |  | RS 265113-002-0 Fixture Type L2 - For Approval - ME - POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-18 02:00 |  | RS 265113-002-0 Fixture Type L2 - For Approval.pdf
RS 26 51 13-003-00 | 26 51 13 - LIGHTING FIXTURES | RS 26 51 13-003-00 Temp Lighting Fixture - PD (FOR RECORD) | Open | Lighting | Nick.Gass@bnbuilders.com | 2021-10-04 | Forwarded - For Review |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) | 2021-10-11 | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), David Riffel (ME Engineers), Heidi Evans (ME Engineers) |  | 2021-10-08 07:00 |  | 4 |  | Record Copies; Transfers; Submittals |  | 4
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14771 | Received | For Review | 2021-10-04 | Nick.Gass@bnbuilders.com | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous) | 2021-10-08 07:00 | Populous Team, Please find the attached submittal 265113-003-0 Temp Lighting Fixture - PD (FOR RECORD) for your review. BNB is requesting the reviewed submittal be returned within five (5) working days from the original date of this correspondence. Thanks, Nick Gass ¦ BNBuilders 2601 4th Avenue, Suite 350 ¦ Seattle, WA 98121 206.382.3443 office ¦ 425.218.5813 cell | Email
| 19042 | Forwarded | For Review | 2021-10-04 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); David Riffel (ME Engineers); Heidi Evans (ME Engineers) | 2021-10-11 | Populous Team, Please find the attached submittal 265113-003-0 Temp Lighting Fixture - PD (FOR RECORD) for your review. BNB is requesting the reviewed submittal be returned within five (5) working days from the original date of this correspondence. Thanks, Nick Gass ¦ BNBuilders 2601 4th Avenue, Suite 350 ¦ Seattle, WA 98121 206.382.3443 office ¦ 425.218.5813 cell | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Nick.Gass@bnbuilders.com | 1 | 2021-10-04 |  | RS 265113-003-0 Temp Lighting Fixture - PD (FOR RECORD).pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-10-04 |  | RS 265113-003-0 Temp Lighting Fixture - PD (FOR RECORD).pdf
RS 27 00 00-001-00 |  | RS 27 00 00-001-00 Low Voltage Systems | Closed | Technology | Mark Nonato | 2021-07-21 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-07-23 07:00 | 2021-07-27 | 7 |  | Record Copies; Transfers; Submittals |  | 8 |  | 2021-07-27
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14027 | Received | For Review | 2021-07-21 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-23 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 270000-001-0 Low Voltage Systems for review and approval. NOTE: No expedited review required. Standard review time is acceptable. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18146 | Forwarded | For Review | 2021-07-20 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-07-27 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 270000-001-0 Low Voltage Systems for review and approval. NOTE: No expedited review required. Standard review time is acceptable. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14144 | Review Response | Revise and Resubmit | 2021-07-27 | Michael Mazzocchi (ME Engineers) | Shaina Burris (Populous) |  |  | Info Exchange
| 18279 | Responded and Closed | Revise and Resubmit | 2021-07-27 | Bryan Klote (Populous) | Mark Nonato |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-20 |  | RS 270000-001-0 Low Voltage Systems - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-20 |  | RS 270000-001-0 Low Voltage Systems - For Approval.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-07-20 |  | RS 270000-001-0 Low Voltage Systems - For Approval.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-07-27 |  | RS 270000-001-0 Low Voltage Systems - ME_POP.pdf
RS 27 00 00-001-01 | 27 00 00 | RS 27 00 00-001-01 Low Voltage Systems | Closed | Audio-Visual, Technology, Electrical | Mark Nonato | 2021-08-03 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers), Brian Elwell (Idibri), Bryan Klote (Populous), Tom Usher (Populous), Kuebler Perry (Populous), Josh Dobken (Populous), Chad Francis (Populous) |  |  |  | 2021-08-05 07:00 | 2021-08-06 | 4 |  | Record Copies; Transfers; Submittals |  | 5 |  | 2021-08-06
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14191 | Received | For Review | 2021-08-03 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-08-05 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 270000-001-1 Low Voltage Systems for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18345 | Forwarded | For Review | 2021-08-02 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-08-09 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 270000-001-1 Low Voltage Systems for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 18375 | Forwarded | For Review | 2021-08-04 | Josh Dobken (Populous) | Brian Elwell (Idibri) | 2021-08-05 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 270000-001-1 Low Voltage Systems for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14238 | Review Response | No Action Taken or Required | 2021-08-05 | Brian Elwell (Idibri) | Josh Dobken (Populous) |  | This is to be reviewed by ME. It included telecom and security cabling. | Info Exchange
| 14239 | Review Response | Approved as Noted | 2021-08-05 | Michael Mazzocchi (ME Engineers) | Shaina Burris (Populous) |  |  | Info Exchange
| 18395 | Forwarded | For Review | 2021-08-06 | Shaina Burris (Populous) | Bryan Klote (Populous); Tom Usher (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Chad Francis (Populous) |  | Kuebler/Shaina/Josh, Please see attached Submittal: RS 270000-001-1 Low Voltage Systems for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14241 | Review Response | Approved as Noted | 2021-08-06 | Kuebler Perry (Populous) | Populous SCA_CCA |  | Refer to attached submittal review. | Info Exchange
| 18397 | Responded and Closed | Approved as Noted | 2021-08-06 | Kuebler Perry (Populous) | Mark Nonato |  | Refer to attached submittal review. | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-02 |  | RS 270000-001-1 Low Voltage Systems - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-02 |  | RS 270000-001-1 Low Voltage Systems - For Approval.pdf
| Forwarded |  | Josh Dobken (Populous) | 1 | 2021-08-01 02:00 |  | RS 270000-001-1 Low Voltage Systems - For Approval.pdf
| Review Response |  | Brian Elwell (Idibri) | 1 | 2021-08-01 |  | RS 270000-001-1 Low Voltage Systems - For Approval.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-08-02 |  | RS 270000-001-1 Low Voltage Systems - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-06 |  | RS 270000-001-1 Low Voltage Systems - ME Response.pdf
| Review Response |  | Kuebler Perry (Populous) | 1 | 2021-08-06 |  | RS 270000-001-1 Low Voltage Systems - ME_POP.pdf
| Responded and Closed |  | Kuebler Perry (Populous) | 1 | 2021-08-02 |  | RS 270000-001-1 Low Voltage Systems - For Approval.pdf
RS 28 23 00-001-00 | 28 23 00 - VIDEO SURVEILLANCE SYSTEM | RS 28 23 00-001-00 Security System | Closed | Security | Mark Nonato | 2021-08-16 | Responded and Closed - Revise and Resubmit |  | Nick Theimer (ME Engineers), Heidi Evans (ME Engineers), Joseph Gillcrist, Michael Mazzocchi (ME Engineers) |  |  |  | 2021-08-30 | 2021-08-19 | 4 |  | Record Copies; Transfers; Submittals |  | 3 |  | 2021-08-19
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14373 | Received | For Review | 2021-08-16 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Michael Mazzocchi (ME Engineers) | 2021-08-30 | Kuebler/Michael, Please see attached Submittal: RS 282300-001-0 Security System for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18548 | Forwarded | For Review | 2021-08-16 | Shaina Burris (Populous) | Nick Theimer (ME Engineers); Heidi Evans (ME Engineers); Joseph Gillcrist; Michael Mazzocchi (ME Engineers) | 2021-08-23 | Kuebler/Michael, Please see attached Submittal: RS 282300-001-0 Security System for review and approval. NOTE: Please expedite review of this submittal. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14410 | Review Response | Revise and Resubmit | 2021-08-18 | Michael Mazzocchi (ME Engineers) | Shaina Burris (Populous) |  |  | Info Exchange
| 18600 | Responded and Closed | Revise and Resubmit | 2021-08-19 | Bryan Klote (Populous) | Mark Nonato |  |  | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-16 |  | RS 282300-001-0 Security System - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-08-16 |  | RS 282300-001-0 Security System - For Approval.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-08-16 |  | RS 282300-001-0 Security System - For Approval.pdf
| Responded and Closed |  | Bryan Klote (Populous) | 1 | 2021-08-19 |  | RS 282300-001-0 Security System - ME_POP.pdf
RS 28 23 00-001-01 | 28 23 00 - VIDEO SURVEILLANCE SYSTEM | RS 28 23 00-001-01 Security System | Closed | Fire Alarm, Technology | Mark Nonato | 2021-08-30 | Responded and Closed - Approved |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Kuebler Perry (Populous), Michael Mazzocchi (ME Engineers) |  |  |  | 2021-09-01 | 2021-08-31 | 2 |  | Record Copies; Transfers; Submittals |  | 2 |  | 2021-08-31
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 14530 | Received | For Review | 2021-08-30 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Michael Mazzocchi (ME Engineers) | 2021-09-01 | Kuebler/Michael, Please see attached Submittal: RS 282300-001-1 Security System for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18731 | Forwarded | For Review | 2021-08-30 | Populous SCA_CCA | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Michael Mazzocchi (ME Engineers) | 2021-09-01 | Kuebler/Michael, Please see attached Submittal: RS 282300-001-1 Security System for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14533 | Review Response | Approved | 2021-08-31 | Michael Mazzocchi (ME Engineers) | Populous SCA_CCA |  |  | Info Exchange
| 18736 | Responded and Closed | Approved | 2021-08-31 | Chad Francis (Populous) | Mark Nonato |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-08-30 02:00 |  | RS 282300-001-1 Security System - For Approval.pdf
| Forwarded |  | Populous SCA_CCA | 1 | 2021-08-30 02:00 |  | RS 282300-001-1 Security System - For Approval.pdf
| Review Response |  | Michael Mazzocchi (ME Engineers) | 1 | 2021-08-30 |  | RS 282300-001-1 Security System - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-08-31 |  | RS 282300-001-01 Security System - ME Response_POP.pdf
RS 28 46 00-001-00 | 28 46 00 | RS 28 46 00-001-00 Fire Alarm Devices | Closed | Fire Alarm | Mark.Nonato@bnbuilders.com | 2021-07-08 | Responded and Closed - Approved as Noted/Resubmit |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-13 07:00 | 2021-07-15 | 8 |  | Record Copies; Transfers; Submittals | RS 28 46 00-001-00-01 - RS 28 46 00-001-00 Fire Alarm Devices | 8 |  | 2021-07-15
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13851 | Received | For Review | 2021-07-08 | Mark.Nonato@bnbuilders.com | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-13 07:00 | Kuebler/Shaina, Please see attached Submittal: RS 284600-001-0 Fire Alarm Devices for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 17929 | Forwarded | For Review | 2021-07-08 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-15 | Kuebler/Shaina, Please see attached Submittal: RS 284600-001-0 Fire Alarm Devices for review and approval. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 13955 | Review Response | Approved as Noted/Resubmit | 2021-07-15 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.15 | Info Exchange
| 18058 | Responded and Closed | Approved as Noted/Resubmit | 2021-07-15 | Josh Dobken (Populous) | Mark.Nonato@bnbuilders.com |  | Device colors to be chosen in shop drawing review. JD/ Populous 07/15/21 Response (Approved as Noted/Resubmit) from: Mark Lievens (ME Engineers) Remarks: Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.15 | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-08 |  | RS 284600-001-0 Fire Alarm Devices - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-08 |  | RS 284600-001-0 Fire Alarm Devices - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-07 02:00 |  | RS 284600-001-0 Fire Alarm Devices - For Approval.pdf
| Responded and Closed |  | Josh Dobken (Populous) | 1 | 2021-07-15 02:00 |  | RS 284600-001-0 Fire Alarm Devices - For Approval - ME Review_pop.pdf
RS 28 46 00-001-00-01 | 28 46 00 | RS 28 46 00-001-00 Fire Alarm Devices | Expected - Overdue |  | Mark Nonato | [9 empty] | -1 |  | Submittals | RS 28 46 00-001-00 - RS 28 46 00-001-00 Fire Alarm Devices | -1 | 2021-07-29
| Workflow | Action | From | Quantity | Date | Number | Description
| Expected |  | Mark Nonato | 1 | 2021-07-15 02:00 |  | RS 284600-001-0 Fire Alarm Devices - For Approval - ME Review_pop.pdf
RS 28 46 00-002-00 | 28 46 00 | RS 28 46 00-002-00 Fire Alarm Devices | Closed | Fire Alarm | Mark Nonato | 2021-07-19 | Responded and Closed - Approved as Noted |  | Mark Lievens (ME Engineers), Nick Theimer (ME Engineers), Jackie Lybarger (ME Engineers), Heidi Evans (ME Engineers) |  |  |  | 2021-07-21 07:00 | 2021-07-28 | 10 |  | Record Copies; Transfers; Submittals |  | 12 |  | 2021-07-28
| ID | Type | Action | Date | From | To | Due Date | Remarks | Via
| 13988 | Received | For Review | 2021-07-19 | Mark Nonato | Bryan Klote (Populous); Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous); Chad Francis (Populous); Michael Mazzocchi (ME Engineers) | 2021-07-21 07:00 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 284600-002-0 Fire Alarm Devices for review and approval. NOTE: Populous to confirm device colors in shop drawings. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Email
| 18093 | Forwarded | For Review | 2021-07-16 | Shaina Burris (Populous) | Mark Lievens (ME Engineers); Nick Theimer (ME Engineers); Jackie Lybarger (ME Engineers); Heidi Evans (ME Engineers) | 2021-07-23 | Kuebler/Shaina/Josh, Please see attached Submittal: RS 284600-002-0 Fire Alarm Devices for review and approval. NOTE: Populous to confirm device colors in shop drawings. Thanks, Mark Nonato ¦ BNBuilders 2601 4th Avenue, Suite 350 Seattle, WA 98121 T 206.382.3443 ¦ M 206.475.2669 BNBuilders.com | Info Exchange
| 14149 | Review Response | Approved as Noted | 2021-07-27 | Mark Lievens (ME Engineers) | Bryan Klote (Populous); Kuebler Perry (Populous); Josh Dobken (Populous); Shaina Burris (Populous) |  | Please see the attached submittal review. Mark Lievens ME Engineers 2021.07.27 | Info Exchange
| 18291 | Responded and Closed | Approved as Noted | 2021-07-28 | Chad Francis (Populous) | Mark Nonato |  | PLEASE SEE ATTACHED | Info Exchange
| Workflow | Action | From | Quantity | Date | Number | Description
| Received |  | Mark Nonato | 1 | 2021-07-16 |  | RS 284600-002-0 Fire Alarm Devices - For Approval.pdf
| Forwarded |  | Shaina Burris (Populous) | 1 | 2021-07-16 |  | RS 284600-002-0 Fire Alarm Devices - For Approval.pdf
| Review Response |  | Mark Lievens (ME Engineers) | 1 | 2021-07-16 |  | RS 284600-002-0 Fire Alarm Devices - For Approval.pdf
| Responded and Closed |  | Chad Francis (Populous) | 1 | 2021-07-28 |  | RS 284600-002-0 Fire Alarm Devices - For Approval - ME Review_POP.pdf